## Sheet1
Program-Year | CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
NC 2014 | SHS (2014) | Region VI | Bacolod City | 302700 | Alangilan NHS | BACOLOD CITY (Capital) | 0 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2790828.124 |  |  | COMPLETED | 1 | 2015-12-23 |  | 060614S00239 | 15GC0046 | 2015-07-13 | 2015-07-10 | 2015-07-27 | 2015-08-14 | 2015-08-20 | KENNETH CONSTRUCTION AND GENERAL MERCHANDISE
NC 2014 | SHS (2014) | Region VI | Bacolod City | 302702 | Barangay Singcang-Airport NHS | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8494965.051 |  |  | REVERTED | 0 |  |  | 060614S00200 | 15GC0064 | 2015-09-01 | 2015-09-02 | 2015-09-10 | 2015-09-22 | 2015-09-30
NC 2014 | SHS (2014) | Region VI | Bacolod City | 302703 | Bata NHS | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-04 |  | 060614S00201 | 15GC0070 | 2015-09-01 | 2015-09-02 | 2015-09-14 | 2015-09-24 | 2015-09-30 | JAIME B. CHING ENTERPRISES
NC 2014 | SHS (2014) | Region VI | Bacolod City | 302706 | Emiliano Lizares NHS | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-04 |  | 060614S00202 | 15GC0071 | 2015-09-01 | 2015-09-02 | 2015-09-14 | 2015-09-24 | 2015-09-30 | LEGACY CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Bacolod City | 311202 | Fr. Gratian Murray, AFSC IS | BACOLOD CITY (Capital) | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1 | 2016-02-03 |  | 060614S00203 | 15GC0073 | 2015-09-01 | 2015-09-02 | 2015-09-14 | 2015-09-24 | 2015-09-30 | SILVERGRACES CONSTRUCTION AND CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | Region VI | Bacolod City | 302712 | Handumanan NHS | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Bacolod City | 302713 | Jovito H. Sayson NHS | BACOLOD CITY (Capital) | 0 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2715828.124 |  |  | COMPLETED | 1 | 2015-11-15 | 2015-11-15 | 060614S00205 | 15GC0036 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-03 | 2015-08-12 | HUMMING BIRD CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region VI | Bacolod City | 302709 | Luis Hervias NHS | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-04 |  | 060614S00206 | 15GC0068 | 2015-09-01 | 2015-09-02 | 2015-09-14 | 2015-09-24 | 2015-09-30 | JAIME B. CHING ENTERPRISES
NC 2014 | SHS (2014) | Region VI | Bacolod City | 302711 | Luisa Medel NHS | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-04 |  | 060614S00197 | 15GC0072 | 2015-09-01 | 2015-09-02 | 2015-09-14 | 2015-09-24 | 2015-09-30 | LEGACY CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Bacolod City | 500189 | M. G. Medalla Integrated School | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8439965.051 |  |  | COMPLETED | 1 | 2016-03-04 |  | 060614S00208 | 15GC0065 | 2015-09-01 | 2015-09-02 | 2015-09-14 | 2015-09-24 | 2015-09-30 | HUMMING BIRD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Bacolod City | 302710 | Mandalagan NHS | BACOLOD CITY (Capital) | 0 | 1 | 2 | 2UNITS 1STY 1CL | 2014 K10 BATCH 1 | 2224658.24 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Bacolod City | 302710 | Mandalagan NHS | BACOLOD CITY (Capital) | 0 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2790828.124 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Bacolod City | 302714 | Mansilingan Agro-Ind. HS | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-04 |  | 060614S00221 | 15GC0069 | 2015-09-01 | 2015-09-02 | 2015-09-14 | 2015-09-24 | 2015-09-30 | JAIME B. CHING ENTERPRISES
NC 2014 | SHS (2014) | Region VI | Bacolod City | 302715 | Paglaum Village NHS | BACOLOD CITY (Capital) | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-03 |  | 060614S00210 | 15GC0074 | 2015-09-01 | 2015-09-02 | 2015-09-14 | 2015-09-24 | 2015-09-30 | HUMMING BIRD CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region VI | Bacolod City | 302704 | Romanito Maravilla NHS | BACOLOD CITY (Capital) | 0 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2715828.124 |  |  | COMPLETED | 1 | 2015-11-15 | 2015-11-15 | 060614S00199 | 15GC0035 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-06 | 2015-08-12 | HUMMING BIRD CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region VI | Bacolod City | 302716 | Sum-ag NHS | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Bacolod City | 302718 | Teofilo Gensoli, Sr. NHS | BACOLOD CITY (Capital) | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-01 | 2015-10-01 | 060614S00213 | 15GC0037 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-10 | 2015-08-12 | HUMMING BIRD CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region VI | Bago City | 302724 | Ramon Torres Louisiana NHS | BAGO CITY | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Cadiz City | 311405 | Banquerohan NHS (Dr. Vicente F Gustilo NHS-Banquerohan Ext) | CADIZ CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | REVERTED | 0 |  |  | 060614S00215 | 15GK0107 | 2015-09-09 | 2015-09-11
NC 2014 | SHS (2014) | Region VI | Cadiz City | 302726 | Cadiz Viejo NHS | CADIZ CITY | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2660828.124 |  |  | COMPLETED | 1 | 2015-12-28 | 2015-12-28 | 060614S00216 | 15KG0065 | 2015-07-03 | 2015-07-10 | 2015-07-24 | 2015-08-07 | 2015-08-18 | TSD BUILDERS CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region VI | Cadiz City | 302728 | Caduha-an NHS | CADIZ CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1 | 2016-02-24 |  | 060614S00217 | 15GK0094 | 2015-08-25 | 2015-08-25 | 2015-09-08 | 2015-09-15 | 2015-09-24 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | SHS (2014) | Region VI | Cadiz City | 302729 | Caduha-an NHS - Andres Bonifacio Ext. HS | CADIZ CITY | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2690828.124 |  |  | COMPLETED | 1 | 2015-12-28 | 2015-12-28 | 060614S00218 | 15KG0065 | 2015-07-03 | 2015-07-10 | 2015-07-24 | 2015-08-07 | 2015-08-18 | TSD BUILDERS CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Cadiz City | 311401 | Caduha-an NHS - Luna Ext. HS | CADIZ CITY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-12-18 | 2015-12-18 | 060614S00171 | 15GK0085 | 2015-08-10 | 2015-08-13 | 2015-08-27 | 2015-09-07 | 2015-09-15 | GKMM CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region VI | Cadiz City | 302730 | Dr. Vicente F. Gustilo Memorial NHS | CADIZ CITY | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10927342.5917 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Cadiz City | 117533 | Hiyang-Hiyang ES | CADIZ CITY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1122049.6543 |  |  | COMPLETED | 1 | 2015-12-18 | 2015-12-18 | 060614S00174 | 15GK0085 | 2015-08-10 | 2015-08-13 | 2015-08-27 | 2015-09-07 | 2015-09-15 | GKMM CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region VI | Cadiz City | 302736 | Jerusalem National High School (Villacin NHS - Jerusalem Ext. HS) | CADIZ CITY | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2710828.124 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Cadiz City | 302731 | Mabini National High School | CADIZ CITY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6369337.6381 |  |  | REVERTED | 0 |  |  | 060614S00220
NC 2014 | SHS (2014) | Region VI | CADIZ CITY | 311403 | Mabini NHS - Alimatoc Ext. HS | CADIZ CITY | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-28 | 2015-12-28 | 060614S00264 | 15GK0064 | 2015-07-03 | 2015-07-23 | 2015-07-24 | 2015-08-07 | 2015-08-18 | GKMM CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region VI | Cadiz City | 302727 | Sicaba NHS | CADIZ CITY | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2720828.124 |  |  | COMPLETED | 1 | 2015-12-28 | 2015-12-28 | 060614S00196 | 15KG0065 | 2015-07-03 | 2015-07-23 | 2015-07-24 | 2015-08-07 | 2015-08-18 | TSD BUILDERS CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region VI | Cadiz City | 302732 | SPED High School | CADIZ CITY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6369337.6381 |  |  | REVERTED | 0 |  |  | 060614S00184
NC 2014 | SHS (2014) | Region VI | Cadiz City | 302733 | Tiglawigan NHS | CADIZ CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1 | 2016-02-24 |  | 060614S00185 | 15GK0095 | 2015-08-25 | 2015-08-25 | 2015-09-08 | 2015-09-15 | 2015-09-24 | TSD BUILDERS CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region VI | Cadiz City | 302734 | Tiglawigan NHS - Magsaysay Extension High School | CADIZ CITY | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2690828.124 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Cadiz City | 302735 | Villacin NHS | CADIZ CITY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6369337.6381 |  |  | REVERTED | 0 |  |  | 060614S00183
NC 2014 | SHS (2014) | Region VI | Escalante City | 302595 | Buenavista NHS | CITY OF ESCALANTE | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-15 |  | 060614S00224 | 15GK0089 | 2015-08-18 | 2015-08-18 | 2015-09-01 | 2015-09-08 | 2015-09-17 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | K10 (2014) | Region VI | Escalante City | 325602 | Buenavista NHS - Langub Ext. | CITY OF ESCALANTE | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-05-01 | 2015-05-01 | 060614S00109 | 14GK040 | 2014-09-05 | 2014-10-17 | 2014-12-11 | 2014-12-17 | 2014-12-22 | By Administration
NC 2014 | SHS (2014) | Region VI | Escalante City | 302625 | Escalante NHS | CITY OF ESCALANTE | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-15 |  | 060614S00225 | 15GK0090 | 2015-08-18 | 2015-08-18 | 2015-09-01 | 2015-09-08 | 2015-09-17 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | SHS (2014) | Region VI | Escalante City | 302660 | Mabini NHS | CITY OF ESCALANTE | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 117830 | Balisong ES | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3165174.43 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-02 | 060614S00110 | 14GM0013 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-07-22 | 2014-07-31 | OPELL CONSTRUCTION AND DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 117831 | Ballo PS | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3065174.43 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-03 | 060614S00111 | 14GM0014 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-07-22 | 2014-07-31 | OPELL CONSTRUCTION AND DEVELOPMENT CORPORATION
NC 2014 | SHS (2014) | Region VI | Kabankalan City | 302785 | Bantayan NHS | CITY OF KABANKALAN | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8494965.051 |  |  | COMPLETED | 1 | 2016-03-25 |  | 060614S00238 | 15GM0052 | 2015-09-11 | 2015-09-14 | 2015-09-28 | 2015-10-06 | 2015-10-22 | H.L.J CONSTRUCTION & ENTERPRISES
NC 2014 | SHS (2014) | Region VI | Kabankalan City | 302786 | Binicuil NHS | CITY OF KABANKALAN | 6 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 11177342.5917 |  |  | COMPLETED | 1 |  |  | 060614S00237 | 0606-14-S-00237 | 2015-11-10 | 2015-11-13 | 2015-11-26 | 2015-12-10
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 117833 | Bugtong PS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2080417.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 060614S00112 | 14GM0015 | 2014-06-27 | 2014-06-27 | 2014-08-05 | 2014-08-15 | 2014-08-27 | GIMP VENTURES
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 302792 | Camansi NHS | CITY OF KABANKALAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 117836 | Carol-an ES | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3055174.43 |  |  | COMPLETED | 1 | 2014-11-19 | 2014-11-19 | 060614S00123 | 14GM0016 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 117839 | D.C.Gurrucharri MS | CITY OF KABANKALAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-10 | 060614S00114 | 14GM0017 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | ADP CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 117881 | Dacongcogon ES | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2985174.43 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 060614S00113 | 14GM0027 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 117882 | Dr. Pablo Torre PS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2060417.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 060614S00090 | 14GM0028 | 2014-06-27 | 2014-06-27 | 2014-08-05 | 2014-08-15 | 2014-08-27 | By Administration
NC 2014 | SHS (2014) | Region VI | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8374965.051 |  |  | COMPLETED | 1 | 2016-03-25 |  | 060614S00236 | 15GM0053 | 2015-09-11 | 2015-09-14 | 2015-09-28 | 2015-10-06 | 2015-10-22 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 117859 | Hilamonan ES | CITY OF KABANKALAN | 6 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 4020835.14 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-10 | 060614S00115 | 14GM0026 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | ETHAN PROPERTY DEVELOPER
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 117842 | Hinapunan ES | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2955174.43 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 060614S00106 | 14GM0018 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 117842 | Hinapunan Integrated School | CITY OF KABANKALAN | 6 | 1 | 5 | 1STY5CL | 2014 K10 BATCH 4B | 4673392.2448 |  |  | COMPLETED | 1 | 2016-01-04 |  | 060614S00180 | 15GM0044 | 2015-07-23 | 2015-07-27 | 2015-08-10 | 2015-08-18 | 2015-09-03 | TSD BUILDERS CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 302794 | Inapoy NHS | CITY OF KABANKALAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-02 | 060614S00133 | 14GM0033 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-30 | 2014-07-09 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 117886 | Lowag ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2014-10-26 | 2014-10-26 | 060614S00091 | 14GM0029 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | By Administration
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 117844 | Mansumbil PS | CITY OF KABANKALAN | 6 | 1 | 2 | 2UNITS 1STY 1CL | 2014 K10 BATCH 1 | 2274658.24 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 060614S00116 | 14GM0019 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 117846 | NOAC ES | CITY OF KABANKALAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 060614S00117 | 14GM0020 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-07-22 | 2014-07-31 | GALENO CONSTRUCTION, INC.
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 117847 | Oringao ES | CITY OF KABANKALAN | 6 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3880805.49 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-10 | 060614S00118 | 14GM0021 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | ETHAN PROPERTY DEVELOPER
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 117848 | Orong ES | CITY OF KABANKALAN | 6 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3820805.49 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 060614S00119 | 14GM0022 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-07-22 | 2014-07-31 | GALENO CONSTRUCTION, INC.
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 302798 | PINAGUINPINAN NHS | CITY OF KABANKALAN | 6 | 1 | 3 | 3UNITS 1STY 1CL | 2014 K10 BATCH 1 | 3356987.36 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 117850 | President Osmena Elementary School | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY 1CL & 1STY 2CL | 2014 K10 BATCH 1 | 3222746.69 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 060614S00120 | 14GM0023 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 117892 | Salong ES | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2915174.43 |  |  | COMPLETED | 1 | 2014-10-12 | 2014-10-12 | 060614S00092 | 14GM0030 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | ETHAN PROPERTY DEVELOPER
NC 2014 | SHS (2014) | Region VI | Kabankalan City | 302796 | Salong NHS | CITY OF KABANKALAN | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8374965.051 |  |  | COMPLETED | 1 | 2016-05-26 |  | 060614S00235 | 15GM0151 | 2015-11-10 | 2015-11-13 | 2015-11-26 | 2015-12-08 | 2015-12-23 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 117893 | San Jose ES | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2955174.43 |  |  | COMPLETED | 1 | 2014-10-12 | 2014-10-12 | 060614S00093 | 14GM0031 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-30 | 2014-07-09 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 117851 | SONEDCO ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 060614S00121 | 14GM0024 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 117869 | Tabugon ES | CITY OF KABANKALAN | 6 | 1 | 10 | 2STY10CL | 2014 K10 BATCH 4B | 13371310.093 |  |  | COMPLETED | 1 | 2016-04-24 |  | 060614S00170 | 15GM0054 | 2015-09-11 | 2015-09-14 | 2015-09-28 | 2015-10-06 | 2015-10-22 | H.L.J CONSTRUCTION & ENTERPRISES
NC 2014 | SHS (2014) | Region VI | Kabankalan City | 302797 | Tabugon NHS | CITY OF KABANKALAN | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8434965.051 |  |  | COMPLETED | 1 | 2016-05-26 |  | 060614S00234 | 15GM0152 | 2015-11-10 | 2015-11-13 | 2015-11-26 | 2015-12-08 | 2015-12-23 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | SHS (2014) | Region VI | Kabankalan City | 302800 | Tampalon NHS | CITY OF KABANKALAN | 6 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6539337.6381 |  |  | COMPLETED | 1 | 2016-03-25 |  | 060614S00233 | 15GM0055 | 2015-09-11 | 2015-09-14 | 2015-09-28 | 2015-10-06 | 2015-10-22 | AQUA DRAGON CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Kabankalan City | 117853 | Tan-awan ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2090417.57 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-20 | 060614S00098 | 14GM0025 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | SHS (2014) | Region VI | Kabankalan City | 312101 | TAN-AWAN NHS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-05 |  | 060614S00222 | 15GM0040 | 2015-07-23 | 2015-07-27 | 2015-08-10 | 2015-08-18 | 2015-09-03 | KENBE CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region VI | Kabankalan City | 302801 | Tapi National NHS | CITY OF KABANKALAN | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 | 2016-02-25 |  | 060614S00231 | 15GM0056 | 2015-09-11 | 2015-09-14 | 2015-09-28 | 2015-10-06 | 2015-10-22 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | SHS (2014) | Region VI | La Carlota City | 302751 | Dona H.S.Benedicto NHS | LA CARLOTA CITY | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Sagay City | 302762 | Bato National High School | SAGAY CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060614S00195 | 15GK0102 | 2015-09-01 | 2015-09-02
NC 2014 | SHS (2014) | Region VI | Sagay City | 302768 | Bulanon National High School | SAGAY CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Sagay City | 500036 | Colonia Divina Integrated School | SAGAY CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | REVERTED | 0 |  |  | 060614S00194 | 15GK0101 | 2015-09-01 | 2015-09-02
NC 2014 | K10 (2014) | Region VI | Sagay City | 500037 | Eusebio Lopez Memorial Integrated School | SAGAY CITY | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Sagay City | 500037 | Eusebio Lopez Memorial Integrated School | SAGAY CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Sagay City | 500038 | Himogaan Baybay Integrated School | SAGAY CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Sagay City | 117721 | Maria Lopez ES | Sagay City | 2 | 1 | 5 | 1STY1CL, 1STY4CL | 2014 K10 BATCH 2 | 4374000 |  |  | COMPLETED | 1 | 2015-03-07 | 2015-03-07 | 060614S00152 | 14GK0053 | 2014-09-19 | 2014-09-25 | 2014-10-07 | 2014-10-20 | 2014-10-29 | GKMM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VI | SAGAY CITY | 117697 | Matabas ES | SAGAY CITY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1092049.6543 |  |  | COMPLETED | 1 | 2015-12-18 | 2015-12-18 | 060614S00178 | 15GK0086 | 2015-08-10 | 2015-08-13 | 2015-08-27 | 2015-09-07 | 2015-09-15 | KENBE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | SAGAY CITY | 117738 | Pacol ES | SAGAY CITY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1062049.6543 |  |  | COMPLETED | 1 | 2015-12-18 | 2015-12-18 | 060614S00177 | 15GK0086 | 2015-08-10 | 2015-08-13 | 2015-08-27 | 2015-09-07 | 2015-09-15 | KENBE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Sagay City | 302767 | Sagay NHS | Sagay City | 2 | 1 | 9 | 2U-1STY3CL, 1STY2CL, 1STY1CL | 2014 K10 BATCH 2 | 7919000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | SAGAY CITY | 117705 | Suyac ES | SAGAY CITY | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4B | 4672048.49 |  |  | COMPLETED | 1 |  |  | 060614S00176
NC 2014 | K10 (2014) | Region VI | Sagay City | 117707 | Talusan ES | Sagay City | 2 | 1 | 4 | 2U-1STY2CL | 2014 K10 BATCH 2 | 3562000 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 060614S00153 | 14GK0052 | 2014-09-19 | 2014-09-25 | 2014-10-07 | 2014-10-20 | 2014-10-29 | GKMM CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region VI | Sagay City | 302771 | Vito NHS | SAGAY CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-02 |  | 060614S00192 | 15GK0104 | 2015-09-01 | 2015-09-02 | 2015-09-15 | 2015-09-22 | 2015-10-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | Region VI | San Carlos City | 302774 | Don Carlos Ledesma NHS | SAN CARLOS CITY | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | REVERTED | 0 |  |  | 060614S00191 | 15GK0092 | 2015-08-18 | 2015-08-19
NC 2014 | SHS (2014) | Region VI | San Carlos City | 302775 | Julio Ledesma NHS | SAN CARLOS CITY | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-04-08 |  | 060614S00190 | 15GK0117 | 2015-10-08 | 2015-10-08 | 2015-10-22 | 2015-10-30 | 2015-11-09 | KENNETH CONSTRUCTION AND GENERAL MERCHANDISE
NC 2014 | SHS (2014) | Region VI | San Carlos City | 302776 | Quezon NHS | SAN CARLOS CITY | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8344965.051 |  |  | REVERTED | 0 |  |  | 060614S00189 | 15GK0093 | 2015-08-18 | 2015-08-19 | 2015-09-01
NC 2014 | SHS (2014) | Region VI | San Carlos City | 302777 | Sipaway National High School | SAN CARLOS CITY | 1 | 1 | 4 | 1STY4CL | 2014 SHS BATCH 1 | 3619886.575 |  |  | COMPLETED | 1 | 2016-02-02 |  | 060614S00181 | 15GK0076 | 2015-07-16 | 2015-07-31 | 2015-08-04 | 2015-08-24 | 2015-08-26 | OPELL CONSTRUCTION AND DEVELOPMENT CORPORATION
NC 2014 | SHS (2014) | Region VI | Silay City | 302781 | Brgy. E. Lopez National High School | SILAY CITY | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-02 |  | 060614S00187 | 15GK0098 | 2015-09-01 | 2015-09-01 | 2015-09-08 | 2015-09-15 | 2015-09-24 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | Region VI | Silay City | 302778 | Brgy. Guimbala-on NHS | SILAY CITY | 3 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10437131.51 |  |  | COMPLETED | 1 | 2016-03-12 |  | 060614S00186 | 15GK0106 | 2015-09-09 | 2015-09-11 | 2015-09-24 | 2015-10-02 | 2015-10-12 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | Region VI | Silay City | 302779 | Don Felix T. Lacson NHS (Brgy. Capitan Ramon) | SILAY CITY | 3 | 1 | 4 | 1STY4CL | 2014 SHS BATCH 1 | 3491886.575 |  |  | COMPLETED | 1 | 2016-01-17 |  | 060614S00211 | 15GK0063 | 2015-07-03 | 2015-07-10 | 2015-07-24 | 2015-08-07 | 2015-08-18 | KENBE CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region VI | Silay City | 302780 | Doña Montserrat Lopez MHS | SILAY CITY | 3 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15221327.92 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region VI | Silay City | 500202 | Sibato Integrated School | SILAY CITY | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2370417.57 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-03-16 | 060614S00041 | 14GK0051 | 2014-09-05 | 2014-09-16 | 2014-10-01 | 2014-10-14 | 2014-10-22 | ADROIT CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Aklan | 114657 | Agbanawan PS | BANGA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1884740.174 |  |  | COMPLETED | 1 | 2016-01-30 |  | 060114S00053 | 15GA0099 | 2015-08-05 | 2015-08-06 | 2015-08-19 | 2015-08-27 | 2015-09-02 | CARME ROSE ENTERPRISE
NC 2014 | K10 (2014) | Region VI | Aklan | 114770 | Agbatuan PS | LIBACAO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1132049.6543 |  |  | REVERTED | 0 | 2015-10-30 |  | 060114S00074 | 15GA0112 | 2015-08-11 | 2015-08-12
NC 2014 | K10 (2014) | Region VI | Aklan | 310616 | Agtughangin Integrated School | MADALAG | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3140174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Aklan | 310604 | Aguinaldo T. Repiedad, Sr. IS | BANGA | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6399164.7656 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Aklan | 310604 | Aguinaldo T. Repiedad, Sr. IS | BANGA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8319965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Aklan | 302324 | Aklan NHS for Arts & Trades | KALIBO (Capital) | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Aklan | 302316 | Alaminos NHS | MADALAG | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Aklan | 114772 | Alfonso XII ES | LIBACAO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-10 | 060114S00009 | 14GA0043 | 2014-06-04 | 2014-06-05 | 2014-06-18 | 2014-07-17 | 2014-07-30 | INAMARGA ENTERPRISES
NC 2014 | K10 (2014) | Region VI | Aklan | 310617 | Alfonso XII NHS | LIBACAO | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3764886.575 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Aklan | 178008 | Alibagon PS | MAKATO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1894740.174 |  |  | COMPLETED | 1 | 2015-12-30 |  | 060114S00070 | 15GA0135 | 2015-08-05 | 2015-08-06 | 2015-08-19 | 2015-08-27 | 2015-09-02 | FIRST MAKEEN CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Aklan | 114878 | Alimbo Baybay PS | NABAS | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1037049.6543 |  |  | COMPLETED | 1 | 2015-12-30 |  | 060114S00065 | 15GA0116 | 2015-07-21 | 2015-07-22 | 2015-08-04 | 2015-08-27 | 2015-09-02 | FIRST MAKEEN CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Aklan | 302286 | Altavas National School | ALTAVAS | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Aklan | 310613 | Angas Integrated School | BATAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2015-11-29 |  | 060114S00090
NC 2014 | SHS (2014) | Region VI | Aklan | 302305 | Anselmo B. Legaspi NHS | MAKATO | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2720828.124 |  |  | COMPLETED | 1 | 2015-12-19 |  | 060114S00106 | 15GA0086 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-30 | 2015-08-22 | FIRST MAKEEN CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Aklan | 114731 | Aparicio ES | IBAJAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-12 | 060114S00010 | 14GA0058 | 2014-06-16 | 2014-06-17 | 2014-06-30 | 2014-07-16 | 2014-07-23 | DREAMWORX BUILDER & TRADING, INC.
NC 2014 | K10 (2014) | Region VI | Aklan | 302289 | Bacan National High School | BANGA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Aklan | 302289 | Bacan National High School | BANGA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Aklan | 114830 | Bagong Barrio ES | MAKATO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1142049.6543 |  |  | REVERTED | 0 | 2015-10-30 |  | 060114S00060 | 15GA0136 | 2015-08-05 | 2015-08-06
NC 2014 | K10 (2014) | Region VI | Aklan | 114701 | Bagong Bayan PS | BURUANGA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-22 | 060114S00024 | 14GA0059 | 2014-06-16 | 2014-06-17 | 2014-06-30 | 2014-07-18 | 2014-07-30 | LUMEL GLENN CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Aklan | 114805 | Balactasan Elementary School | MADALAG | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-11-22 | 2014-11-03 | 060114S00004 | 14GA0049 | 2014-06-13 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-24 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Aklan | 114647 | Bang Bang ES | Balete | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1001000 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-04-28 | 060114S00044 | 14GA0086 | 2014-10-28 | 2014-10-29 | 2014-11-11 | 2014-11-18 | 2014-11-24 | AUDRIC CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region VI | Aklan | 302291 | Batan Academy (A Nat'L Sch.) | BATAN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1 | 2016-01-29 |  | 060114S00108 | 15GA0063 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-08-27 | 2015-09-02 | ORANI BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VI | Aklan | 114717 | Batuan PS | IBAJAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-11-22 | 2014-11-04 | 060114S00013 | 14GA0041 | 2014-06-04 | 2014-06-05 | 2014-06-18 | 2014-07-18 | 2014-07-24 | DREAMWORX BUILDER & TRADING, INC.
NC 2014 | SHS (2014) | Region VI | Aklan | 302294 | Bay-ang-Magpag-ong NHS | BATAN | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-30 |  | 060114S00109 | 15GA0072 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-08-27 | 2015-09-02 | ORANI BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VI | Aklan | 114774 | Belen PS | LIBACAO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1267329.12 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-05 | 060114S00008 | 14GA0043 | 2014-06-04 | 2014-06-05 | 2014-06-18 | 2014-07-17 | 2014-07-30 | INAMARGA ENTERPRISES
NC 2014 | K10 (2014) | Region VI | Aklan | 302295 | Boracay NHS | MALAY | 2 | 1 | 6 | 2STY6CL (Completion) | 2014 K10 BATCH 3 | 5022327.906 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Aklan | 302295 | Boracay NHS | MALAY | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3190174.43 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Aklan | 302295 | Boracay NHS | MALAY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8494965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Aklan | 310611 | Boracay NHS - Manocmanoc Ext. | MALAY | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-20 |  | 060114S00110 | 15GA0126 | 2015-08-04 | 2015-08-05 | 2015-08-18 | 2015-08-27 | 2015-09-02 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VI | Aklan | 114879 | Buenafortuna PS | NABAS | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2015-03-15 | 2015-03-02 | 060114S00021 | 14GA0040 | 2014-06-04 | 2014-06-05 | 2014-06-18 | 2014-08-27 | 2014-08-29 | FIRST MAKEEN CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Aklan | 114777 | Bueosangay PS | Libacao | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1001000 |  |  | COMPLETED | 1 | 2015-12-30 |  | 060114S00045 | 15GA0038 | 2015-08-04 | 2015-08-05 | 2015-08-18 | 2015-08-27 | 2015-09-02 | CARME ROSE ENTERPRISE
NC 2014 | SHS (2014) | Region VI | Aklan | 302297 | Buruanga Vocational School | BURUANGA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8224965.051 |  |  | COMPLETED | 1 | 2016-02-29 |  | 060114S00126 | 15GA0049 | 2015-08-04 | 2015-08-05 | 2015-08-18 | 2015-08-27 | 2015-09-02 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | Region VI | Aklan | 302299 | Calizo NHS | BALETE | 1 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | 2014-12-19 |  | 060114S00111 | 15GA0069 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-22 | KENBE CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region VI | Aklan | 302300 | Camaligan NHS | BATAN | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6339337.6381 |  |  | COMPLETED | 1 | 2016-02-28 |  | 060114S00125 | 15GA0073 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-08-27 | 2015-09-02 | ORANI BUILDERS & SUPPLY
NC 2014 | SHS (2014) | Region VI | AKLAN | 302301 | Camanci NHS | BATAN | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-30 |  | 060114S00091 | 15GA0067 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-08-27 | 2015-09-02 | ORANI BUILDERS & SUPPLY
NC 2014 | SHS (2014) | Region VI | Aklan | 302302 | Candelaria NHS | NEW WASHINGTON | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-02 |  | 060114S00113 | 15GA0040 | 2015-06-30 | 2015-07-01 | 2015-07-14 | 2015-07-24 | 2015-08-05 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VI | Aklan | 114718 | Capilijan PS | IBAJAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-11-22 | 2014-11-07 | 060114S00011 | 14GA0041 | 2014-06-04 | 2014-06-05 | 2014-06-18 | 2014-07-18 | 2014-07-24 | DREAMWORX BUILDER & TRADING, INC.
NC 2014 | K10 (2014) | Region VI | Aklan | 114836 | Castillo ES | BALETE | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1052049.6543 |  |  | REVERTED | 0 | 2015-10-30 |  | 060114S00073
NC 2014 | SHS (2014) | Region VI | Aklan | 302304 | Catalino M. Prado NHS | LEZO | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2740828.124 |  |  | COMPLETED | 1 | 2016-01-14 |  | 060114S00101 | 15GA0083 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-30 | 2015-08-18 | INAMARGA ENTERPRISES
NC 2014 | K10 (2014) | Region VI | Aklan | 114847 | Caticlan ES | Malay | 2 | 1 | 5 | 1STY4CL, 1STY1CL | 2014 K10 BATCH 2 | 4410000 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region VI | Aklan | 500178 | Catmon Integrated School | ALTAVAS | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | AKLAN | 500178 | Catmon Integrated School | ALTAVAS | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Aklan | 302296 | Ciriaco L. Icamina, Sr. NHS | MALINAO | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2760828.124 |  |  | COMPLETED | 1 | 2015-12-14 |  | 060114S00115 | 15GA0080 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-08-26 | 2015-09-01 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE
NC 2014 | K10 (2014) | Region VI | Aklan | 114650 | Cortes Elementary School | BALETE | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-12-26 | 2014-12-20 | 060114S00038 | 14GA0051 | 2014-06-13 | 2014-06-13 | 2014-06-26 | 2014-07-17 | 2014-07-30 | FIRST MAKEEN CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Aklan | 500180 | Cortes Integrated School | BALETE | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2014 K10 BATCH 4B | 1954740.174 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | AKLAN | 302306 | Daja Sur NHS | BANGA | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-29 |  | 060114S00100 | 15GA0068 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-08-26 | 2015-09-01 | G.F. ROVERO MERCHANDISING
NC 2014 | K10 (2014) | Region VI | Aklan | 500181 | Dalagsaan Integrated School | LIBACAO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 2214740.174 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region VI | Aklan | 302298 | Dr. Ramon B. Legaspi, Sr. National High School | MAKATO | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3040174.43 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Aklan | 302298 | Dr. Ramon B. Legaspi, Sr. National High School | MAKATO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Aklan | 114929 | Dumatad PS | TANGALAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1037049.6543 |  |  | COMPLETED | 1 | 2016-01-30 |  | 060114S00051 | 15GA0118 | 2015-07-21 | 2015-07-22 | 2015-08-04 | 2015-08-27 | 2015-09-02 | FIRST MAKEEN CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Aklan | 302323 | Gaudencio L. Vega NHS (Nalook NHS) | KALIBO (Capital) | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6494337.6381 |  |  | COMPLETED | 1 | 2016-01-18 |  | 060114S00117 | 15GA0088 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-30 | 2015-08-21 | CARME ROSE ENTERPRISE
NC 2014 | K10 (2014) | Region VI | Aklan | 114881 | Gibon ES | NABAS | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-12-27 | 2014-12-20 | 060114S00022 | 14GA0054 | 2014-06-16 | 2014-06-17 | 2014-06-30 | 2014-07-18 | 2014-07-30 | FIRST MAKEEN CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Aklan | 302311 | Guadalupe NHS | LIBACAO | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6449337.6381 |  |  | COMPLETED | 1 | 2016-01-29 |  | 060114S00095 | 15GA0092 | 2015-07-14 | 2015-07-15 | 2015-07-28 | 2015-08-27 | 2015-09-01 | CARME ROSE ENTERPRISE
NC 2014 | K10 (2014) | Region VI | Aklan | 114654 | Guanko ES | BALETE | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region VI | Aklan | 500182 | Habana Integrated School | BURUANGA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1854740.174 |  |  | COMPLETED | 1 | 2016-01-29 |  | 060114S00069 | 15GA0117 | 2015-07-21 | 2015-07-22 | 2015-08-04 | 2015-08-27 | 2015-09-02 | LUMEL GLENN CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Aklan |  | Habana PS | NABAS | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Aklan | 302330 | Ibajay NHS | IBAJAY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8239965.051 |  |  | COMPLETED | 1 | 2016-01-29 |  | 060114S00118 | 15GA0054 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-08-03 | 2015-08-13 | G.F. ROVERO MERCHANDISING
NC 2014 | K10 (2014) | Region VI | Aklan | 500183 | Jawili Integrated School | TANGALAN | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2670828.124 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Aklan |  | Jose Borromeo Legaspi Memorial NHS | BALETE | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 | 2016-01-14 |  | 060114S00112 | 15GA0066 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-18 | G.F. ROVERO MERCHANDISING
NC 2014 | K10 (2014) | Region VI | Aklan | 302287 | Justicia Morales-Young NHS | ALTAVAS | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Aklan | 114849 | Kabulihan-Dumlog PS | MALAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-03-05 | 2015-03-03 | 060114S00016 | 14GA0042 | 2014-06-04 | 2014-06-05 | 2014-06-18 | 2014-08-27 | 2014-08-29 | FIRST MAKEEN CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Aklan | 310615 | Kalibo Intgrated Special Education Center | KALIBO (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1042049.6543 |  |  | REVERTED | 0
NC 2014 | SHS (2014) | Region VI | AKLAN | 310615 | Kalibo Intgrated Special Education Center | KALIBO (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | REVERTED | 0
NC 2014 | SHS (2014) | Region VI | AKLAN | 310610 | Kinalangay Viejo IS | MALINAO | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-18 |  | 060114S00086 | 15GA0082 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-08-05 | 2015-08-21 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE
NC 2014 | SHS (2014) | Region VI | Aklan | 310603 | LAMBERTO H. TIROL NATIONAL HIGH SCHOOL | MALAY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6569337.6381 |  |  | COMPLETED | 1 | 2016-02-04 |  | 060114S00119 | 15GA0093 | 2015-07-14 | 2015-07-15 | 2015-07-28 | 2015-08-05 | 2015-08-22 | FIRST MAKEEN CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Aklan | 500171 | Lezo Integrated School | LEZO | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2720828.124 |  |  | COMPLETED | 1 | 2015-12-18 |  | 060114S00120 | 15GA0084 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-08-05 | 2015-08-21 | CARME ROSE ENTERPRISE
NC 2014 | SHS (2014) | Region VI | Aklan | 302310 | Libacao National Forestry Vocational High School | LIBACAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 | 2015-12-31 |  | 060114S00121 | 15GA0048 | 2015-06-30 | 2015-07-01 | 2015-07-14 | 2015-07-30 | 2015-08-05 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | Region VI | AKLAN | 302312 | Lilo-an National High School | MALINAO | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-14 |  | 060114S00096 | 15GA0081 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-08-26 | 2015-09-01 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE
NC 2014 | SHS (2014) | Region VI | Aklan | 302313 | Linabuan NHS | KALIBO (Capital) | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8216965.051 |  |  | COMPLETED | 1 | 2016-01-31 |  | 060114S00122 | 15GA0045 | 2015-06-30 | 2015-07-01 | 2015-07-14 | 2015-07-30 | 2015-08-05 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | Region VI | Aklan | 302288 | Linayasan NHS | ALTAVAS | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-17 |  | 060114S00123 | 15GA0074 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-08-03 | 2015-08-21 | CARME ROSE ENTERPRISE
NC 2014 | K10 (2014) | Region VI | Aklan | 114787 | Loctuga ES | LIBACAO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 060114S00003 | 14GA0044 | 2014-06-04 | 2014-06-05 | 2014-06-18 | 2014-07-16 | 2014-07-24 | INAMARGA ENTERPRISES
NC 2014 | SHS (2014) | Region VI | AKLAN | 302314 | LOCTUGA NATIONAL HIGH SCHOOL | LIBACAO | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | REVERTED | 0 | 2015-11-29 |  | 060114S00097 | 15GA0102 | 2015-07-14 | 2015-07-15
NC 2014 | K10 (2014) | Region VI | Aklan | 310601 | LUPO NATIONAL HIGH SCHOOL | ALTAVAS | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Aklan | 310605 | Madalag NHS - Mamba Ext. | MADALAG | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1167329.12 |  |  | COMPLETED | 1 | 2014-12-27 | 2014-12-21 | 060114S00031 | 14GA0048 | 2014-06-13 | 2014-06-13 | 2014-06-26 | 2014-07-18 | 2014-07-30 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Aklan | 114885 | Magallanes PS | NABAS | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1839740.174 |  |  | COMPLETED | 1 | 2015-12-29 |  | 060114S00068 | 15GA0111 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-27 | 2015-09-01 | G.F. ROVERO MERCHANDISING
NC 2014 | K10 (2014) | Region VI | Aklan | 114691 | Magubahay Elementary School | BATAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1062049.6543 |  |  | COMPLETED | 1 | 2015-12-31 |  | 060114S00057 | 15GA0110 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-08-27 | 2015-09-02 | M O M ENTERPRISES
NC 2014 | SHS (2014) | Region VI | Aklan | 500172 | Makato Integrated School | MAKATO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 | 2016-02-28 |  | 060114S00124 | 15GA0044 | 2015-06-30 | 2015-07-01 | 2015-07-14 | 2015-07-30 | 2015-08-05 | G.F. ROVERO MERCHANDISING
NC 2014 | SHS (2014) | Region VI | Aklan |  | Malay National High School | MALAY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Aklan |  | Malay National High School | MALAY | 2 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8379203.2031 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Aklan | 302318 | Malay NHS - Santander-Panilongan Ext. | BURUANGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | AKLAN | 302318 | Malay NHS - Santander-Panilongan Ext. | BURUANGA | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Aklan | 114722 | Malindog PS | IBAJAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | REVERTED | 0 | 2015-10-30 |  | 060114S00076 | 15GA0101 | 2015-08-05 | 2015-08-06
NC 2014 | SHS (2014) | Region VI | Aklan | 302320 | Maloco NHS | IBAJAY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8239965.051 |  |  | COMPLETED | 1 | 2016-01-28 |  | 060114S00093 | 15GA0056 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-08-03 | 2015-08-06 | G.F. ROVERO MERCHANDISING
NC 2014 | K10 (2014) | Region VI | Aklan | 500184 | Mandong Integrated School | BATAN | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2700828.124 |  |  | COMPLETED | 1 | 2015-12-30 |  | 060114S00067 | 15GA0098 | 2015-08-05 | 2015-08-06 | 2015-08-19 | 2015-08-27 | 2015-09-02 | GGMU CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VI | Aklan | 310602 | Mangan National High School | BANGA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Aklan | 310602 | Mangan National High School | BANGA | 1 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2660828.124 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Aklan | 114851 | Manocmanoc ES | MALAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-04-28 | 060114S00017 | 14GA0056 | 2014-06-16 | 2014-06-17 | 2014-06-30 | 2014-07-18 | 2014-07-24 | FIRST MAKEEN CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Aklan | 114707 | Mayapay PS | BURUANGA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1052049.6543 |  |  | COMPLETED | 1 | 2015-10-30 |  | 060114S00071 | 15GA0117 | 2015-07-21 | 2015-07-22 | 2015-08-04 | 2015-08-27 | 2015-09-02 | LUMEL GLENN CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Aklan | 114791 | Maytaraw PS | LIBACAO | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2885417.57 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region VI | Aklan | 500185 | Medina Integrated School | MADALAG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1949740.174 |  |  | COMPLETED | 1 | 2015-12-30 |  | 060114S00062 | 15GA0141 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-08-27 | 2015-09-02 | KENBE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Aklan | 114852 | Naasog PS | MALAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | REVERTED | 0
NC 2014 | SHS (2014) | Region VI | Aklan | 302321 | Naile NHS | IBAJAY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 | 2015-12-28 |  | 060114S00077 | 15GA0057 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-08-03 | 2015-08-06 | G.F. ROVERO MERCHANDISING
NC 2014 | SHS (2014) | Region VI | Aklan | 302322 | Naisud NHS | IBAJAY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8224965.051 |  |  | COMPLETED | 1 | 2016-02-07 |  | 060114S00084 | 15GA0053 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-08-03 | 2015-08-06 | G.F. ROVERO MERCHANDISING
NC 2014 | SHS (2014) | Region VI | AKLAN | 500176 | NAPTI INTEGRATED SCHOOL | BATAN | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-30 |  | 060114S00099 | 15GA0078 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-08-27 | 2015-09-02 | ORANI BUILDERS & SUPPLY
NC 2014 | SHS (2014) | Region VI | Aklan | 500035 | Numancia Integrated School | NUMANCIA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8279965.051 |  |  | COMPLETED | 1 | 2016-01-01 |  | 060114S00087 | 15GA0042 | 2015-06-30 | 2015-07-01 | 2015-07-14 | 2015-07-30 | 2015-08-05 | G.F. ROVERO MERCHANDISING
NC 2014 | SHS (2014) | Region VI | Aklan | 302327 | Numancia National Sch. Of Fisheries | NUMANCIA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8279965.051 |  |  | COMPLETED | 1 | 2016-01-08 |  | 060114S00083 | 15GA0085 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-08-03 | 2015-08-12 | G.F. ROVERO MERCHANDISING
NC 2014 | SHS (2014) | Region VI | Aklan | 302328 | Ochando NHS | NEW WASHINGTON | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 | 2016-02-17 |  | 060114S00082 | 15GA0041 | 2015-06-30 | 2015-07-01 | 2015-07-14 | 2015-07-30 | 2015-08-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | Region VI | Aklan | 302329 | ONDOY NATIONAL HIGH SCHOOL | IBAJAY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8229965.051 |  |  | COMPLETED | 1 | 2016-01-06 |  | 060114S00080 | 15GA0055 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-30 | 2015-08-05 | G.F. ROVERO MERCHANDISING
NC 2014 | K10 (2014) | Region VI | Aklan | 500174 | Ortega IS | LIBACAO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Aklan | 114869 | Osman Elementary School | MALINAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1042049.6543 |  |  | REVERTED | 0 | 2015-10-30 |  | 060114S00050 | 15GA0143 | 2015-08-11 | 2015-08-12
NC 2014 | K10 (2014) | Region VI | Aklan | 302331 | Panayakan National High School | TANGALAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Aklan | 114824 | Panipiason PS | MADALAG | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1217329.12 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-20 | 060114S00014 | 14GA0048 | 2014-06-13 | 2014-06-13 | 2014-06-26 | 2014-07-18 | 2014-07-30 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Aklan | 500186 | Pinamuk-an Integrated School | NEW WASHINGTON | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1914740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Aklan | 114890 | Pinatuad PS | NABAS | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1057049.6543 |  |  | COMPLETED | 1 | 2015-12-30 |  | 060114S00052 | 15GA0116 | 2015-07-21 | 2015-07-22 | 2015-08-04 | 2015-08-27 | 2015-09-02 | FIRST MAKEEN CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Aklan | 114796 | Pinonoy PS | LIBACAO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1072049.6543 |  |  | COMPLETED | 1 | 2015-10-30 |  | 060114S00064 | 15GA0113 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-26 | 2015-09-01 | CARME ROSE ENTERPRISE
NC 2014 | K10 (2014) | Region VI | Aklan | 178007 | Prudencio T. Yerro ES | LEZO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-04 | 060114S00029 | 14GA0057 | 2014-06-16 | 2014-06-17 | 2014-06-30 | 2014-07-17 | 2014-07-30 | INAMARGA ENTERPRISES
NC 2014 | K10 (2014) | Region VI | Aklan | 178003 | Quirico T. Tabanera ES | MAKATO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-01-20 | 2015-01-16 | 060114S00025 | 14GA0055 | 2014-06-16 | 2014-06-17 | 2014-06-30 | 2014-07-17 | 2014-07-30 | FIRST MAKEEN CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Aklan | 302332 | Regional Science High School for Region VI | KALIBO (Capital) | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8379965.051 |  |  | COMPLETED | 1 | 2016-02-01 |  | 060114S00079 | 15GA0043 | 2015-06-30 | 2015-07-01 | 2015-07-14 | 2015-07-30 | 2015-08-05 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VI | Aklan | 114797 | Rivera PS | LIBACAO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-20 | 060114S00006 | 14GA0044 | 2014-06-04 | 2014-06-05 | 2014-06-18 | 2014-07-16 | 2014-07-24 | INAMARGA ENTERPRISES
NC 2014 | SHS (2014) | Region VI | Aklan | 302333 | Rizal J. Rodriguez Sr. NHS | BATAN | 1 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2690828.124 |  |  | COMPLETED | 1 | 2015-12-30 |  | 060114S00078 | 15GA0071 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-08-27 | 2015-09-02 | ORANI BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VI | Aklan | 114798 | Rosal ES | LIBACAO | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-02 | 060114S00005 | 14GA0047 | 2014-06-13 | 2014-06-13 | 2014-06-26 | 2014-07-17 | 2014-07-30 | INAMARGA ENTERPRISES
NC 2014 | K10 (2014) | Region VI | Aklan | 114855 | Sambiray PS | MALAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-04-28 | 060114S00019 | 14GA0056 | 2014-06-16 | 2014-06-17 | 2014-06-30 | 2014-07-18 | 2014-07-24 | FIRST MAKEEN CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Aklan | 114871 | San Dimas Elementary School | MALINAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1047049.6543 |  |  | COMPLETED | 1 | 2015-12-31 |  | 060114S00056 | 15GA0121 | 2015-07-21 | 2015-07-22 | 2015-08-04 | 2015-08-27 | 2015-09-02 | KENBE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Aklan | 114825 | San Jose PS | MADALAG | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-11-22 | 2014-11-02 | 060114S00015 | 14GA0049 | 2014-06-13 | 2014-06-13 | 2014-06-26 | 2014-07-21 | 2014-07-24 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Aklan | 310626 | San Roque Integrated School | MALINAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1042049.6543 |  |  | COMPLETED | 1 | 2015-12-20 |  | 060114S00059 | 15GA0120 | 2015-07-21 | 2015-07-22 | 2015-08-04 | 2015-08-10 | 2015-08-22 | KENBE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Aklan | 114709 | Santander ES | BURUANGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-12-21 | 2014-12-20 | 060114S00012 | 14GA0053 | 2014-06-16 | 2014-06-17 | 2014-06-30 | 2014-07-16 | 2014-07-23 | LUMEL GLENN CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Aklan | 500187 | Tabon Integrated School | BATAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1959740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Aklan |  | Tagororoc ES | NABAS | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1167329.12 |  |  | COMPLETED | 1 | 2015-03-10 | 2015-03-02 | 060114S00027 | 14GA0040 | 2014-06-04 | 2014-06-05 | 2014-06-18 | 2014-08-27 | 2014-08-29 | FIRST MAKEEN CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Aklan | 500173 | Tamalagon Integrated School | TANGALAN | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6379337.6381 |  |  | COMPLETED | 1 | 2016-01-19 |  | 060114S00085 | 15GA0046 | 2015-06-30 | 2015-07-01 | 2015-07-14 | 2015-07-30 | 2015-08-22 | FIRST MAKEEN CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Aklan | 302338 | Torralba NHS | BANGA | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1 | 2016-01-30 |  | 060114S00088 | 15GA0075 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-08-27 | 2015-09-02 | G.F. ROVERO MERCHANDISING
NC 2014 | K10 (2014) | Region VI | Aklan | 114727 | Tul-ang PS | IBAJAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1047049.6543 |  |  | COMPLETED | 1 | 2015-12-17 |  | 060114S00061 | 15GA0114 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-05 | 2015-08-19 | DREAMWORX BUILDER & TRADING, INC.
NC 2014 | SHS (2014) | Region VI | Aklan | 302339 | Unidos NHS | NABAS | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8289965.051 |  |  | COMPLETED | 1 | 2016-01-29 |  | 060114S00089 | 15GA0091 | 2015-08-05 | 2015-08-06 | 2015-08-19 | 2015-08-27 | 2015-09-02 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VI | Aklan | 114856 | Yapak Elementary School | MALAY | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3190174.43 |  |  | COMPLETED | 1 | 2015-05-31 | 2015-05-28 | 060114S00020 | 14GA0084 | 2014-11-25 | 2014-11-27 | 2014-12-09 | 2014-12-17 | 2014-12-23 | FIRST MAKEEN CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Antique | 115143 | Badiangan ES | PANDAN | 0 | 1 | 4 | 2 UNITS 1STY2CL | 2014 K10 BATCH 3 | 3429299.6121 |  |  | COMPLETED | 1 | 2015-06-30 | 2015-06-30 | 060214S00032 | 14GB0064 | 2014-11-13 | 2014-11-25 | 2014-11-26 | 2014-12-19 | 2015-01-12 | ANJUSH BUILDERS
NC 2014 | K10 (2014) | Region VI | Antique | 115028 | Bagacay ES | Culasi | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1095000 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 060214S00017 | 14GB0039-2 | 2014-08-21 | 2014-09-02 | 2014-09-03 | 2014-09-18 | 2014-10-06 | GATEWAY 21-25 CONSTRUCTION CORP. (FORMERLY E.D. DE
NC 2014 | K10 (2014) | Region VI | Antique | 115255 | Bagumbayan ES | San Remigio | 0 | 1 | 3 | 1STY2CL, 1STY1CL | 2014 K10 BATCH 2 | 2926050 |  |  | COMPLETED | 1 | 2015-02-03 | 2015-02-03 | 060214S00006 | 14GB0043-1 | 2014-08-21 | 2014-09-02 | 2014-09-03 | 2014-09-18 | 2014-09-29 | TIBIAO-ANTIQUE N.K. ENTERPRISE, INC.
NC 2014 | K10 (2014) | Region VI | Antique | 115032 | Batonan ES | Culasi | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1235000 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 060214S00013 | 14GB0037-1 | 2014-08-21 | 2014-09-02 | 2014-09-03 | 2014-09-18 | 2014-10-06 | TIBIAO-ANTIQUE N.K. ENTERPRISE, INC.
NC 2014 | K10 (2014) | Region VI | Antique | 115257 | Bawang ES | SAN REMIGIO | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1890524.8061 |  |  | COMPLETED | 1 | 2015-08-20 | 2015-08-20 | 060214S00028 | 14Gb0080 | 2014-11-19 | 2014-12-01 | 2014-12-02 | 2014-12-29 | 2015-02-12 | SETTLERS BUILDERS
NC 2014 | K10 (2014) | Region VI | Antique | 115178 | Bitas ES | Patnongon | 0 | 1 | 5 | 3U-1STY1CL, 1STY2CL | 2014 K10 BATCH 2 | 5039080 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 060214S00008 | 14GB0044-2 | 2014-08-21 | 2014-09-02 | 2014-09-03 | 2014-09-18 | 2014-10-06 | TIBIAO-ANTIQUE N.K. ENTERPRISE, INC.
NC 2014 | K10 (2014) | Region VI | Antique | 115035 | Buhi ES | Culasi | 0 | 1 | 3 | 1STY2CL, 1STY1CL | 2014 K10 BATCH 2 | 3111000 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 060214S00018 | 14GB0037-3 | 2014-08-21 | 2014-09-02 | 2014-09-03 | 2014-09-18 | 2014-10-06 | TIBIAO-ANTIQUE N.K. ENTERPRISE, INC.
NC 2014 | K10 (2014) | Region VI | Antique | 115066 | Calacja II ES | HAMTIC | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1004011.8851 |  |  | COMPLETED | 1 | 2015-02-03 | 2015-02-03 | 060214S00020 | 14GB0041 | 2014-08-21 | 2014-09-02 | 2014-09-03 | 2014-09-18 | 2014-10-07 | FVPS CONSTRUCTION CORP.
NC 2014 | K10 (2014) | Region VI | Antique | 115036 | Camancijan ES | Culasi | 0 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2140000 |  |  | COMPLETED | 1 | 2015-02-24 | 2015-02-24 | 060214S00015 | 14GB0038 | 2014-08-21 | 2014-09-02 | 2014-10-14 | 2014-10-23 | 2014-10-28 | ZTIM CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Antique | 115037 | Carit-an ES | Culasi | 0 | 1 | 5 | 1STY1CL, 1STY4CL | 2014 K10 BATCH 2 | 4736000 |  |  | COMPLETED | 1 | 2015-02-02 | 2015-01-03 | 060214S00012 | 14GB0039-1 | 2014-08-21 | 2014-09-02 | 2014-09-03 | 2014-09-18 | 2014-10-06 | GATEWAY 21-25 CONSTRUCTION CORP. (FORMERLY E.D. DE
NC 2014 | K10 (2014) | Region VI | Antique | 115128 | Codiong PS | LIBERTAD | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2016-02-24 |  | 060214S00003 | 15GB0081 | 2014-07-31 | 2014-08-12 | 2015-08-12 | 2015-09-01 | 2015-10-10 | KJC CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Antique | 115040 | Esperanza ES | Culasi | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1095000 |  |  | COMPLETED | 1 | 2015-02-24 | 2015-03-17 | 060214S00011 | 14GB0038 | 2014-08-21 | 2014-09-02 | 2014-10-14 | 2014-10-23 | 2014-10-28 | ZTIM CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Antique | 178508 | Evelio B. Javier Mem. Sch. | SAN JOSE (Capital) | 0 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4311999.6094 |  |  | COMPLETED | 1 | 2015-08-31 | 2015-08-31 | 060214S00024 | 14GB0101 | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-08 | 2015-02-13 | CONTE BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VI | Antique | 115086 | Fabrica ES | HAMTIC | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2669082.3437 |  |  | COMPLETED | 1 | 2015-02-03 | 2015-02-03 | 060214S00021 | 14GB0041-2 | 2014-08-21 | 2014-09-02 | 2014-09-03 | 2014-09-18 | 2014-10-07 | FVPS CONSTRUCTION CORP.
NC 2014 | K10 (2014) | Region VI | Antique | 115042 | Flores ES | Culasi | 0 | 1 | 4 | 2U-1STY1CL, 1STY2CL | 2014 K10 BATCH 2 | 4021000 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 060214S00010 | 14GB0042-2 | 2014-08-21 | 2014-09-02 | 2014-10-14 | 2014-10-23 | 2014-10-28 | ANJUSH BUILDERS
NC 2014 | K10 (2014) | Region VI | Antique | 115195 | Gella ES | Patnongon | 0 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2127380 |  |  | COMPLETED | 1 | 2015-05-30 | 2015-05-30 | 060214S00014 | 14GB0043-2 | 2014-08-21 | 2014-09-02 | 2014-09-03 | 2014-09-18 | 2014-10-06 | TIBIAO-ANTIQUE N.K. ENTERPRISE, INC.
NC 2014 | K10 (2014) | Region VI | Antique | 115261 | General Fullon ES | SAN REMIGIO | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2250417.57 |  |  | COMPLETED | 1 | 2014-12-01 | 2014-12-01 | 060214S00002 | 14GB0021-A | 2014-07-02 | 2014-07-14 | 2014-07-15 | 2014-07-28 | 2014-08-04 | ANJUSH BUILDERS
NC 2014 | K10 (2014) | Region VI | Antique | 115106 | Guisijan ES | LAUA-AN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 950026.0578 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 060214S00034 | 14GB0074 | 2014-11-13 | 2014-11-25 | 2014-11-26 | 2014-12-19 | 2015-01-12 | FVPS CONSTRUCTION CORP.
NC 2014 | K10 (2014) | Region VI | Antique | 115243 | Iguirindon ES | SAN REMIGIO | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2522471.208 |  |  | COMPLETED | 1 | 2016-02-10 |  | 060214S00041 | 14GB0078 | 2015-07-30 | 2015-08-11 | 2015-08-12 | 2015-09-22 | 2015-10-14 | KJC CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Antique | 114965 | Ipil-Jinalinan ES | Barbaza | 0 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2020000 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 060214S00016 | 14GB0037-2 | 2014-08-21 | 2014-09-02 | 2014-09-03 | 2014-09-18 | 2014-10-06 | TIBIAO-ANTIQUE N.K. ENTERPRISE, INC.
NC 2014 | K10 (2014) | Region VI | Antique | 115043 | Lipata-Lamputong ES | Culasi | 0 | 1 | 3 | 1STY2CL, 1STY1CL | 2014 K10 BATCH 2 | 2841000 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 060214S00009 | 14GB0038 | 2014-08-21 | 2014-09-02 | 2014-10-14 | 2014-10-23 | 2014-10-28 | ZTIM CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Antique | 302364 | Lirio M. Escaño, Sr. NHS | PATNONGON | 0 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8478953.2031 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Antique | 115155 | Luhod-Bayang ES | PANDAN | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-07 |  | 060214S00043 | 15GB0085 | 2015-08-18 | 2015-08-30 | 2015-09-02 | 2015-09-30 | 2015-10-07 | ANJUSH BUILDERS
NC 2014 | K10 (2014) | Region VI | Antique | 114966 | Lumboyan ES | BARBAZA | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1920674.8061 |  |  | COMPLETED | 1 | 2016-03-20 |  | 060214S00040 | 15GB0082 | 2015-07-30 | 2015-08-11 | 2015-09-16 | 2015-10-02 | 2015-10-30 | FVPS CONSTRUCTION CORP.
NC 2014 | K10 (2014) | Region VI | Antique | 115092 | M.V. Velasco MES | HAMTIC | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2532521.208 |  |  | COMPLETED | 1 | 2015-03-12 | 2015-03-12 | 060214S00035 | 14GB0066 | 2014-11-13 | 2014-11-25 | 2014-11-26 | 2015-12-17 | 2015-01-12 | HMM BUILDERS AND CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VI | Antique | 114993 | Maray ES | BUGASONG | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1759874.8061 |  |  | COMPLETED | 1 | 2016-01-30 | 2015-12-01 | 060214S00039 | 14GB0075-1 | 2015-07-30 | 2015-08-11 | 2015-08-12 | 2015-09-28 | 2015-11-02 | ANJUSH BUILDERS
NC 2014 | K10 (2014) | Region VI | Antique | 115116 | Maria ES | LAUA-AN | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1779974.8061 |  |  | COMPLETED | 1 | 2015-08-31 | 2015-08-31 | 060214S00033 | 14GB0076 | 2014-11-19 | 2014-12-01 | 2014-12-02 | 2014-12-22 | 2015-01-12 | FVPS CONSTRUCTION CORP.
NC 2014 | K10 (2014) | Region VI | Antique | 115264 | Mayor Antonio MS (Lumpatan ES) | SAN REMIGIO | 0 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2724975.8638 |  |  | COMPLETED | 1 | 2015-05-11 | 2015-05-11 | 060214S00027 | 14Gb0080 | 2014-11-19 | 2014-12-01 | 2014-12-02 | 2014-12-29 | 2015-01-12 | SETTLERS BUILDERS
NC 2014 | K10 (2014) | Region VI | Antique | 114995 | Pangalcagan ES | BUGASONG | 0 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 2 | 4754336.6298 |  |  | COMPLETED | 1 | 2015-05-30 | 2015-05-30 | 060214S00019 | 14GB0040 | 2014-08-21 | 2014-09-02 | 2014-09-03 | 2014-09-18 | 2014-10-07 | FVPS CONSTRUCTION CORP.
NC 2014 | K10 (2014) | Region VI | Antique | 115268 | Panpanan I ES | SAN REMIGIO | 0 | 1 | 6 | 2UNITS 1STY3CL | 2014 K10 BATCH 4A | 4824323.4291 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region VI | Antique | 115269 | Panpanan II PS | SAN REMIGIO | 0 | 1 | 6 | 3UNITS 1STY2CL | 2014 K10 BATCH 3 | 6033374.4182 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region VI | Antique | 115185 | Patlabawon ES | PATNONGON | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1759874.8061 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-04-11 | 060214S00030 | 14GB0076 | 2014-11-19 | 2014-12-01 | 2014-12-02 | 2014-12-22 | 2015-01-12 | FVPS CONSTRUCTION CORP.
NC 2014 | K10 (2014) | Region VI | Antique | 115205 | Samalague ES | Patnongon | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1053350 |  |  | COMPLETED | 1 | 2015-05-30 | 2015-05-30 | 060214S00007 | 14GB0040 | 2014-08-21 | 2014-09-02 | 2014-09-03 | 2014-09-18 | 2014-10-07 | FVPS CONSTRUCTION CORP.
NC 2014 | K10 (2014) | Region VI | Antique | 114970 | San Antonio ES | BARBAZA | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 950026.0578 |  |  | COMPLETED | 1 | 2015-12-12 | 2015-12-12 | 060214S00038 | 15GB0073 | 2014-11-13 | 2014-12-01 | 2015-08-12 | 2015-09-30 | 2015-10-14 | KJC CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Antique | 115052 | San Antonio ES | CULASI | 0 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3015174.43 |  |  | COMPLETED | 1 | 2014-12-01 | 2014-12-01 | 060214S00001 | 0602-14-S-00001-1 | 2014-07-02 | 2014-07-14 | 2014-07-15 | 2014-07-28 | 2014-08-04 | ANJUSH BUILDERS
NC 2014 | K10 (2014) | Region VI | Antique | 178507 | San Isidro PS | Tibiao | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1025000 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 060214S00005 | 14GB0037 | 2014-08-21 | 2014-09-02 | 2014-09-03 | 2014-09-18 | 2014-10-06 | TIBIAO-ANTIQUE N.K. ENTERPRISE, INC.
NC 2014 | K10 (2014) | Region VI | Antique | 115019 | Semirara Elementary School | CALUYA | 0 | 1 | 5 | 1STY5CL | 2014 K10 BATCH 3 | 4542699.7061 |  |  | COMPLETED | 1 | 2016-04-17 |  | 060214S00037 | 15GB0079 | 2015-07-30 | 2015-08-11 | 2015-09-16 | 2015-10-02 | 2015-10-30 | ANJUSH BUILDERS
NC 2014 | K10 (2014) | Region VI | Antique | 115137 | Taboc ES | LIBERTAD | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1815254.2861 |  |  | COMPLETED | 1 | 2015-07-31 | 2015-07-31 | 060214S00022 | 14GB0041-3 | 2014-08-21 | 2014-09-02 | 2014-09-03 | 2014-09-18 | 2014-10-07 | FVPS CONSTRUCTION CORP.
NC 2014 | K10 (2014) | Region VI | Antique | 115059 | Valderrama ES | Culasi | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1185000 |  |  | COMPLETED | 1 | 2015-05-30 | 2015-05-30 | 060214S00004 | 14GB0042-1 | 2014-08-21 | 2014-09-02 | 2014-10-14 | 2014-10-23 | 2014-10-28 | ANJUSH BUILDERS
NC 2014 | K10 (2014) | Region VI | Antique | 115172 | Vidal Gelito MS | PANDAN | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1719674.8061 |  |  | COMPLETED | 1 | 2015-06-11 | 2015-06-11 | 060214S00031 | 14GB0068 | 2014-11-13 | 2014-11-25 | 2014-11-26 | 2014-12-19 | 2015-02-12 | ANJUSH BUILDERS
NC 2014 | K10 (2014) | Region VI | Antique | 115026 | Villaresis Elementary School | CALUYA | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2653121.208 |  |  | COMPLETED | 1 |  |  | 060214S00036 | 0602-14-S-00036(CNTR) | 2015-07-30 | 2015-08-11 | 2015-09-16
NC 2014 | K10 (2014) | Region VI | Antique | 115275 | Walker-Proper PS (Walker PS) | SAN REMIGIO | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2813921.208 |  |  | COMPLETED | 1 |  |  | 060214S00025 | 14GB0079 | 2015-07-30 | 2015-08-11 | 2015-09-16
NC 2014 | K10 (2014) | Region VI | Antique | 115173 | Zaldivar ES | PANDAN | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2502371.208 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 060214S00023 | 14GB0068 | 2014-11-13 | 2014-11-25 | 2014-11-26 | 2014-12-19 | 2015-01-12 | ANJUSH BUILDERS
NC 2014 | K10 (2014) | Region VI | Capiz | 115548 | Alasaging ES | MA-AYON | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2015717.57 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 060314S00038 | 14GD0011-6 | 2014-07-14 | 2014-07-15 | 2014-07-31 | 2014-08-11 | 2014-08-13 | ROLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Capiz | 115691 | Banate ES | PONTEVEDRA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1050051.4745 |  |  | COMPLETED | 1 | 2014-10-27 | 2014-10-27 | 060314S00054 | 14GD0017-7 | 2014-07-09 | 2014-07-21 | 2014-07-22 | 2014-07-28 | 2014-07-31 | ROLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Capiz | 115668 | Braulio Morgan Patricio ES | PILAR | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 060314S00021 | 14GD0012-4 | 2014-07-14 | 2014-07-15 | 2014-07-31 | 2014-08-11 | 2014-08-13 | ROLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Capiz | 115621 | Buntod ES | PANAY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 060314S00033 | 14GD0012-5 | 2014-07-14 | 2014-07-15 | 2014-07-31 | 2014-08-11 | 2014-08-13 | ROLA CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 302388 | Cabugcabug NHS | PRESIDENT ROXAS | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1 | 2016-01-13 |  | 060314S00085 | 15GD0038 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-07 | 2015-08-14 | ROPRIM CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 302392 | Casanayan NHS | PILAR | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1 | 2016-01-13 |  | 060314S00086 | 15GD0039-1 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-07 | 2015-08-14 | ROPRIM CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 302395 | Comsr. Luis R. Asis NHS | PANAY | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 | 2016-01-13 |  | 060314S00087 | 15GD0036-1 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-07 | 2015-08-14 | ROLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Capiz | 115713 | Cubay-Ibaca ES | PRESIDENT ROXAS | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2888174.43 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 060314S00003 | 14GD0012-1 | 2014-07-14 | 2014-07-15 | 2014-07-31 | 2014-08-11 | 2014-08-13 | ROLA CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 310802 | Dao National High School | DAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-06 |  | 060314S00088 | 15G00173 | 2015-07-03 | 2015-07-03 | 2015-07-16 | 2015-07-30 | 2015-08-04 | PANAY EAST COAST CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | CAPIZ | 115434 | DAPLAS PS | DAO | 1 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2016000 |  |  | COMPLETED | 1 | 2015-11-16 | 2015-05-03 | 060314S00050 | 14GP0018 | 2014-10-09 | 2014-10-21 | 2014-10-22 | 2014-10-26 | 2014-11-22 | MBM CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Capiz | 115669 | Dayhagan ES | PILAR | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2890174.43 |  |  | COMPLETED | 1 | 2014-11-18 | 2014-11-18 | 060314S00007 | 14GD0012-3 | 2014-07-14 | 2014-07-15 | 2014-07-31 | 2014-08-11 | 2014-08-13 | ROLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | CAPIZ | 115671 | Dulangan ES | Pilar | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1023000 |  |  | COMPLETED | 1 | 2014-11-04 | 2014-11-04 | 060314S00043 | 14GD0017-3 | 2014-07-09 | 2014-07-21 | 2014-07-22 | 2014-07-28 | 2014-07-31 | ROLA CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 302400 | Dulangan NHS | PILAR | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6339337.6381 |  |  | COMPLETED | 1 | 2015-12-14 |  | 060314S00089 | 15GD0039-2 | 2015-06-30 | 2015-07-10 | 2015-07-22 | 2015-08-07 | 2015-08-14 | M.R. VARGAS CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Capiz | 115556 | Duluan ES | MA-AYON | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2005717.57 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 060314S00036 | 14GD0011-5 | 2014-07-14 | 2014-07-15 | 2014-07-31 | 2014-08-11 | 2014-08-13 | ROLA CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 302398 | Felix Balgos MNHS | PANAY | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 | 2016-01-13 |  | 060314S00090 | 15GD0036-2 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-07 | 2015-08-14 | ROLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Capiz | 115558 | Fernandez ES | MA-AYON | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2900474.43 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 060314S00035 | 14GD0011-4 | 2014-07-14 | 2014-07-15 | 2014-07-31 | 2014-08-11 | 2014-08-13 | ROLA CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 302404 | Florentina B. Degala NHS | MA-AYON | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 | 2016-01-13 |  | 060314S00100 | 15GD0041-1 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-07 | 2015-08-14 | KIRSKAT VENTURE
NC 2014 | K10 (2014) | Region VI | Capiz | 115697 | Gabuc ES | PONTEVEDRA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2079597.57 |  |  | COMPLETED | 1 | 2014-11-18 | 2014-11-18 | 060314S00005 | 14GD0011-2 | 2014-07-14 | 2014-07-15 | 2014-07-31 | 2014-08-11 | 2014-08-13 | ROLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Capiz | 115672 | Guise PS | PILAR | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2045417.57 |  |  | COMPLETED | 1 | 2014-11-28 | 2014-11-28 | 060314S00006 | 14GD0012-2 | 2014-07-14 | 2014-07-15 | 2014-07-31 | 2014-08-11 | 2014-08-13 | ROLA CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 302405 | Hipona NHS | PONTEVEDRA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 | 2016-01-13 |  | 060314S00092 | 15GD0043-2 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-07 | 2015-08-14 | ROPRIM CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Capiz | 115699 | Intongcan ES | PONTEVEDRA | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2898944.43 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 060314S00004 | 14GD0011-1 | 2014-07-14 | 2014-07-15 | 2014-07-31 | 2014-08-11 | 2014-08-13 | ROLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | CAPIZ | 115562 | Jebaca ES | Maayon | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1023000 |  |  | COMPLETED | 1 | 2014-11-04 | 2014-11-04 | 060314S00044 | 14GD0017-4 | 2014-07-09 | 2014-07-21 | 2014-07-22 | 2014-07-28 | 2014-07-31 | ROLA CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 302410 | Leodegario D. Deocampo Sr. NHS | PANITAN | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6569337.6381 |  |  | COMPLETED | 1 | 2016-01-13 |  | 060314S00083 | 15GD0044-1 | 2015-07-22 | 2015-07-10 | 2015-07-22 | 2015-08-07 | 2015-08-14 | ROPRIM CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Capiz | 115632 | Linao ES | PANAY | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2888174.43 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 060314S00037 | 14GD0012-6 | 2014-07-14 | 2014-07-15 | 2014-07-31 | 2014-08-11 | 2014-08-13 | ROLA CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 302413 | Maayon NHS | MA-AYON | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 | 2016-01-13 |  | 060314S00093 | 15GD0041-2 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-07 | 2015-08-14 | KIRSKAT VENTURE
NC 2014 | SHS (2014) | Region VI | Capiz | 302419 | Marciano M. Patricio (Pilar) | PILAR | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 | 2016-01-13 |  | 060314S00094 | 15GD0040 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-07 | 2015-08-14 | MBM CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Capiz | 115568 | Palaguian ES | MA-AYON | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2014-11-18 | 2014-11-18 | 060314S00034 | 14GD0011-3 | 2014-07-14 | 2014-07-15 | 2014-07-31 | 2014-08-11 | 2014-08-13 | ROLA CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 302418 | Panitan NHS | PANITAN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8489965.051 |  |  | COMPLETED | 1 | 2016-01-13 |  | 060314S00095 | 15GD0044-2 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-07 | 2015-08-14 | ROPRIM CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 310812 | Pawa National High School | PANAY | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1 | 2015-12-14 |  | 060314S00109 | 15GD0037-1 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-07 | 2015-08-14 | ROLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | CAPIZ | 115679 | PEDRO A. BERNAS ES | PILAR | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1023000 |  |  | COMPLETED | 1 | 2014-11-04 | 2014-11-04 | 060314S00042 | 14GD0017-2 | 2014-07-09 | 2014-07-21 | 2014-07-22 | 2014-07-28 | 2014-07-31 | ROLA CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | CAPIZ | 302422 | San Nicolas NHS (Pilar) | PILAR | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-27 | 2015-11-27 | 060314S00099 | 15GD0048M | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-07 | 2015-08-14 | M.R. VARGAS CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 302403 | Tuburan NHS | MA-AYON | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8579965.051 |  |  | COMPLETED | 1 | 2016-01-13 |  | 060314S00098 | 15GD0043-1 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-07 | 2015-08-14 | ROPRIM CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Capiz | 115725 | Agkaningay PS | SAPI-AN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2888124.43 |  |  | COMPLETED | 1 | 2015-11-16 | 2015-10-15 | 060314S00019 | 14GP0011 | 2014-08-03 | 2014-08-15 | 2014-08-16 | 2014-08-20 | 2014-11-22 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE
NC 2014 | K10 (2014) | Region VI | Capiz | 115597 | Agkawayan PS | MAMBUSAO | 2 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3906705.49 |  |  | COMPLETED | 1 | 2015-11-16 |  | 060314S00008 | 14GP0010 | 2014-08-03 | 2014-08-15 | 2014-08-16 | 2014-08-20 | 2014-11-22 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE
NC 2014 | K10 (2014) | Region VI | CAPIZ | 115470 | Aglanot ES | Dumarao | 2 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2036000 |  |  | COMPLETED | 1 | 2015-11-16 | 2015-07-22 | 060314S00048 | 14GP0017 | 2014-10-09 | 2014-10-21 | 2014-10-22 | 2014-10-26 | 2014-11-22 | ROLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | CAPIZ | 115411 | Agnaga ES | Cuartero | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1033000 |  |  | COMPLETED | 1 | 2015-11-16 | 2015-07-22 | 060314S00040 | 14GP0017 | 2014-11-01 | 2014-11-13 | 2014-11-14 | 2014-11-18 | 2014-11-22 | ROLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Capiz | 115803 | Agpalali ES | TAPAZ | 2 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3922005.49 |  |  | COMPLETED | 1 | 2015-11-16 |  | 060314S00014 | 14GP0015 | 2014-08-03 | 2014-08-15 | 2014-08-16 | 2014-08-20 | 2014-11-22 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE | SUSPENDED, Road heading to site is not passable, ONGOING KALAHI Concreting project
NC 2014 | K10 (2014) | Region VI | Capiz | 115472 | Agsirab ES | DUMARAO | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2888124.43 |  |  | COMPLETED | 1 | 2015-11-16 |  | 060314S00025 | 14GP0016 | 2014-08-03 | 2014-08-15 | 2014-08-16 | 2014-08-20 | 2014-11-22 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE
NC 2014 | K10 (2014) | Region VI | Capiz | 115519 | Agtupgop ES | JAMINDAN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2885174.43 |  |  | COMPLETED | 1 | 2015-11-16 |  | 060314S00010 | 14GP0008 | 2014-08-03 | 2014-08-15 | 2014-08-16 | 2014-08-20 | 2014-11-22 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE
NC 2014 | K10 (2014) | Region VI | Capiz | 115580 | Balat-an PS | MAMBUSAO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1129979.12 |  |  | COMPLETED | 1 | 2015-11-16 | 2015-05-11 | 060314S00032 | 14GP0016 | 2014-08-03 | 2014-08-15 | 2014-08-16 | 2014-08-20 | 2014-11-22 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE
NC 2014 | SHS (2014) | Region VI | CAPIZ | 310807 | Basiao NHS (formerly Ext. of Ivisan NHS) | IVISAN | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-07 |  | 060314S00097 | 15G00152 | 2015-06-18 | 2015-06-19 | 2015-07-02 | 2015-07-13 | 2015-07-21 | MBM CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Capiz | 115415 | Bito-on Ilaya ES | CUARTERO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1134979.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Capiz | 115478 | Calapawan ES (dumarao) | DUMARAO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1985717.57 |  |  | COMPLETED | 1 | 2015-11-16 | 2015-08-23 | 060314S00024 | 14GP0016 | 2014-08-03 | 2014-08-15 | 2014-08-16 | 2014-08-20 | 2014-11-22 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE
NC 2014 | SHS (2014) | Region VI | Capiz | 302390 | Candelaria NHS | TAPAZ | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-01 |  | 060314S00084 | 15G00163 | 2015-07-02 | 2015-07-03 | 2015-07-15 | 2015-07-27 | 2015-07-30 | MBM CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 302393 | Col. Patrocinio Artuz NHS | TAPAZ | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-17 |  | 060314S00069 | 15G00174 | 2015-07-08 | 2015-07-09 | 2015-07-23 | 2015-08-04 | 2015-08-13 | MBM CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 302396 | Cuartero NHS | CUARTERO | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 | 2016-04-21 |  | 060314S00058 | 15G00190 | 2015-07-15 | 2015-07-16 | 2015-07-30 | 2015-08-13 | 2015-08-19 | ROPRIM CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Capiz | 115812 | Daan Sur ES | TAPAZ | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3011074.43 |  |  | COMPLETED | 1 | 2015-11-16 |  | 060314S00013 | 14GP0007 | 2014-07-03 | 2014-08-15 | 2014-08-16 | 2014-08-20 | 2014-11-22 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE
NC 2014 | SHS (2014) | Region VI | Capiz | 302397 | David Moises MHS | MAMBUSAO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-01 |  | 060314S00059 | 15G00159 | 2015-07-02 | 2015-07-03 | 2015-07-15 | 2015-07-27 | 2015-07-30 | MBM CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Capiz | 115753 | Dayhagon PS | SIGMA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2091317.57 |  |  | COMPLETED | 1 | 2015-11-16 | 2015-07-25 | 060314S00018 | 14GP0011 | 2014-08-03 | 2014-08-15 | 2014-08-16 | 2014-08-20 | 2014-11-22 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE
NC 2014 | SHS (2014) | Region VI | Capiz | 310806 | Dumalag Central NHS | DUMALAG | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-06 |  | 060314S00060 | 15G00171 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-30 | 2015-08-04 | PANAY EAST COAST CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region VI | Capiz | 302402 | Estefania Montemayor NHS | DUMARAO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-01 |  | 060314S00061 | 15G00162 | 2015-07-02 | 2015-07-03 | 2015-07-15 | 2015-07-27 | 2015-07-30 | PANAY EAST COAST CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region VI | Capiz | 302406 | Ivisan NHS | IVISAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 | 2016-02-01 |  | 060314S00062 | 15G00161 | 2015-07-02 | 2015-07-03 | 2015-07-15 | 2015-07-27 | 2015-07-30 | MBM CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 302408 | Jagnaya NHS | JAMINDAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-01 |  | 060314S00063 | 15G00164 | 2015-07-03 | 2015-07-03 | 2015-07-15 | 2015-07-27 | 2015-07-30 | MBM CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 302409 | Jamindan NHS | JAMINDAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-01 |  | 060314S00064 | 15G00165 | 2015-07-02 | 2015-07-03 | 2015-07-15 | 2015-07-27 | 2015-07-30 | MBM CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 310810 | Lonoy National High School | SAPI-AN | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-18 |  | 060314S00065 | 15G00175 | 2015-07-08 | 2015-07-09 | 2015-07-23 | 2015-08-07 | 2015-08-14 | MBM CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 302411 | Lucero NHS | JAMINDAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-02 |  | 060314S00066 | 15G00166 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-28 | 2015-07-31 | MBM CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 302415 | Luis Escutin NHS | DAO | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1 | 2015-12-22 |  | 060314S00067 | 15G00176 | 2015-07-08 | 2015-07-09 | 2015-07-23 | 2015-08-10 | 2015-08-18 | PANAY EAST COAST CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Capiz | 115419 | Lunayan E/S | CUARTERO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2021017.57 |  |  | COMPLETED | 1 | 2015-11-16 | 2015-11-15 | 060314S00022 | 14GP0012 | 2014-08-03 | 2014-08-15 | 2014-08-16 | 2014-08-20 | 2014-11-22 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE
NC 2014 | K10 (2014) | Region VI | Capiz | 115757 | Maestro J. Reyes PS | SIGMA | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2931074.43 |  |  | COMPLETED | 1 | 2015-11-16 | 2015-06-16 | 060314S00017 | 14GP0008 | 2014-08-03 | 2014-08-15 | 2014-08-16 | 2014-08-20 | 2014-11-22 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE
NC 2014 | SHS (2014) | Region VI | Capiz | 310804 | Maindang NHS | CUARTERO | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6859337.6381 |  |  | COMPLETED | 1 | 2015-12-22 |  | 060314S00068 | 15G00177 | 2015-07-08 | 2015-07-09 | 2015-07-23 | 2015-08-10 | 2015-08-18 | MBM CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 302414 | MALONOY NATIONAL HIGH SCHOOL (DAO) | DAO | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-22 |  | 060314S00082 | 15G00178 | 2015-07-08 | 2015-07-09 | 2015-07-23 | 2015-08-10 | 2015-08-18 | PANAY EAST COAST CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Capiz | 115456 | Maludlud ES | DUMALAG | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2988124.43 |  |  | COMPLETED | 1 | 2015-11-16 |  | 060314S00029 | 14GP0012 | 2014-08-03 | 2014-08-15 | 2014-08-16 | 2014-08-20 | 2014-11-22 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE
NC 2014 | SHS (2014) | Region VI | CAPIZ | 310813 | Mambusao East NHS (ext. of David Moises) | MAMBUSAO | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-07 |  | 060314S00070 | 15G00154 | 2015-06-18 | 2015-06-19 | 2015-07-02 | 2015-07-13 | 2015-07-21 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE
NC 2014 | SHS (2014) | Region VI | Capiz | 310805 | MAMBUSAO NATIONAL HIGH SCHOOL | MAMBUSAO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-02 |  | 060314S00057 | 15G00167 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-28 | 2015-07-31 | PANAY EAST COAST CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region VI | Capiz | 302416 | Manuel F. Onato NHS | DUMARAO | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-22 |  | 060314S00072 | 15G00179 | 2015-07-08 | 2015-07-09 | 2015-07-23 | 2015-08-10 | 2015-08-18 | MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC.
NC 2014 | K10 (2014) | Region VI | Capiz | 115526 | Manuel Ganzon Advincula Elem. Sch. | JAMINDAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2084187.57 |  |  | REVERTED | 0 | 2015-11-16 |  | 060314S00020 | 14GP0010 | 2014-08-03 | 2014-08-15 | 2014-08-16 | 2014-08-20 | 2014-11-22 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE
NC 2014 | K10 (2014) | Region VI | Capiz | 115443 | Matagnop ES | DAO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-11-16 | 2015-06-16 | 060314S00031 | 14GP0013 | 2014-08-03 | 2014-08-15 | 2014-08-16 | 2014-08-20 | 2014-11-22 | ROPRIM CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Capiz | 115761 | Matangcong PS | SIGMA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2001017.57 |  |  | COMPLETED | 1 | 2015-11-16 | 2015-06-22 | 060314S00016 | 14GP0011 | 2014-08-03 | 2014-08-15 | 2014-08-16 | 2014-08-20 | 2014-11-22 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE
NC 2014 | K10 (2014) | Region VI | CAPIZ | 115511 | Panfilo Mendoza ES | Ivisan | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1023000 |  |  | COMPLETED | 1 | 2015-11-16 | 2015-05-03 | 060314S00041 | 14GP0018 | 2014-10-09 | 2014-10-21 | 2014-10-22 | 2014-10-26 | 2014-11-22 | MBM CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 310814 | Presentacion Diez Gregorio NHS | DUMARAO | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-22 |  | 060314S00073 | 15G00180 | 2015-07-08 | 2015-07-09 | 2015-07-23 | 2015-08-10 | 2015-08-18 | MONOLITHIC CONSTRUCTION & CONCRETE PRODUCTS, INC.
NC 2014 | SHS (2014) | Region VI | Capiz | 302421 | Putian NHS | CUARTERO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-02 |  | 060314S00074 | 15G00168 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-28 | 2015-07-31 | PANAY EAST COAST CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Capiz | 115446 | Quinayuya PS | DAO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-11-16 | 2015-08-23 | 060314S00030 | 14GP0013 | 2014-08-03 | 2014-08-15 | 2014-08-16 | 2014-08-20 | 2014-11-22 | ROPRIM CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Capiz | 115491 | R. Advincula Sr. MS | DUMARAO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-11-16 | 2015-08-23 | 060314S00023 | 14GP0009 | 2014-08-03 | 2014-08-15 | 2014-08-16 | 2014-08-20 | 2014-11-22 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE
NC 2014 | SHS (2014) | Region VI | Capiz | 302417 | Ramon A. Benjamin Sr. NHS | DUMARAO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-01 |  | 060314S00075 | 15G00158 | 2015-07-02 | 2015-07-03 | 2015-07-15 | 2015-07-27 | 2015-07-30 | MBM CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | CAPIZ | 310809 | REV. TOMAS CONEJAR NHS | TAPAZ | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-07 |  | 060314S00071 | 15G00153 | 2015-06-18 | 2015-06-19 | 2015-07-02 | 2015-07-13 | 2015-07-21 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE
NC 2014 | K10 (2014) | Region VI | Capiz | 115457 | San Agustin ES | DUMALAG | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2021017.57 |  |  | COMPLETED | 1 | 2015-11-16 | 2015-09-23 | 060314S00028 | 14GP0013 | 2014-08-03 | 2014-08-15 | 2014-08-16 | 2014-08-20 | 2014-11-22 | ROPRIM CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 302423 | San Nicolas NHS (Tapaz) | TAPAZ | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-02 |  | 060314S00078 | 15G00169 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-28 | 2015-07-31 | C.B. GARAY PHILWIDE BUILDERS
NC 2014 | K10 (2014) | Region VI | Capiz | 302424 | Sapian National High School | SAPI-AN | 2 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8228453.2031 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Capiz | 302424 | Sapian National High School | SAPI-AN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Capiz | 115767 | Sinandigan ES | SIGMA | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2885174.43 |  |  | COMPLETED | 1 | 2015-11-16 | 2015-12-10 | 060314S00015 | 14GP0007 | 2014-08-03 | 2014-08-15 | 2014-08-16 | 2014-08-20 | 2014-11-22 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE
NC 2014 | K10 (2014) | Region VI | Capiz | 115465 | Sta. Teresa ES | DUMALAG | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | CAPIZ | 115465 | Sta. Teresa ES | Dumalag | 2 |  | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2016000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | CAPIZ | 115467 | Sto. Rosario ES | Dumalag | 2 |  | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2036000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Capiz | 115467 | Sto. Rosario ES (dumalag) | DUMALAG | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2046317.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | CAPIZ | 115798 | SWITCH ES | TAPAZ EAST | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1033000 |  |  | COMPLETED | 1 | 2015-11-16 | 2015-02-18 | 060314S00045 | 14GP0018 | 2014-10-09 | 2014-10-21 | 2014-10-22 | 2014-10-26 | 2014-11-22 | MBM CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Capiz | 310803 | Tapaz NHS | TAPAZ | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2090417.57 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Capiz | 310803 | Tapaz NHS | TAPAZ | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | CAPIZ | 115496 | Taslan ES | Dumarao | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1023000 |  |  | COMPLETED | 1 | 2015-11-16 | 2015-11-02 | 060314S00047 | 14GP0017 | 2014-10-09 | 2014-10-21 | 2014-10-22 | 2014-10-26 | 2014-11-22 | ROLA CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Capiz | 302399 | Vicente Andaya Sr. NHS | SIGMA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-06 |  | 060314S00081 | 15G00172 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-30 | 2015-08-04 | PANAY EAST COAST CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | CAPIZ | 115508 | Victor A.Umiten Memorial School | Ivisan | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1003000 |  |  | COMPLETED | 1 | 2015-11-16 | 2015-08-23 | 060314S00046 | 14GP0018 | 2014-10-09 | 2014-10-21 | 2014-10-22 | 2014-10-26 | 2014-11-22 | MBM CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Guimaras | 302427 | Agsanayan NHS | BUENAVISTA | 0 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2670828.124 |  |  | COMPLETED | 1 | 2015-12-15 | 2015-12-15 | 060414S00021 | 15GE0038 | 2015-07-21 | 2015-07-22 | 2015-08-04 | 2015-08-10 | 2015-08-17 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY)
NC 2014 | SHS (2014) | Region VI | Guimaras | 302425 | Alegria NHS | SIBUNAG | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1 | 2015-12-24 | 2015-12-24 | 060414S00020 | 15GE0041 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-18 | 2015-08-26 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY)
NC 2014 | SHS (2014) | Region VI | GUIMARAS | 310901 | Ayangan National High School | SIBUNAG | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-23 | 2015-11-23 | 060414S00008 | 0604-14-S-00008 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-04 | 2015-09-14 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY)
NC 2014 | SHS (2014) | Region VI | Guimaras | 302426 | Buenavista NHS | BUENAVISTA | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1 | 2016-01-03 |  | 060414S00019 | 15GE0029 | 2015-07-06 | 2015-07-08 | 2015-07-21 | 2015-07-28 | 2015-08-06 | J.E. TICO CONSTRUCTION CO., INC. (FORMERLY: JET CO
NC 2014 | SHS (2014) | Region VI | Guimaras | 302428 | Cabalagnan NHS | NUEVA VALENCIA | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 | 2016-01-24 |  | 060414S00018 | 15GE0042 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-20 | 2015-08-27 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY)
NC 2014 | SHS (2014) | Region VI | Guimaras | 302435 | Calaya National High School | NUEVA VALENCIA | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 | 2016-01-07 |  | 060414S00017 | 15GE0031 | 2015-07-15 | 2015-07-16 | 2015-07-28 | 2015-08-03 | 2015-08-10 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY)
NC 2014 | SHS (2014) | Region VI | Guimaras | 302429 | Desiderio C. Gange NHS | SIBUNAG | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1 | 2016-01-14 |  | 060414S00016 | 15GE0035 | 2015-07-21 | 2015-07-22 | 2015-08-04 | 2015-08-10 | 2015-08-17 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY)
NC 2014 | SHS (2014) | Region VI | Guimaras | 302437 | Dr. Catalino Gallego Nava Memorial High School | SAN LORENZO | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1 | 2015-12-25 | 2015-12-25 | 060414S00009 | 15GE0036 | 2015-07-21 | 2015-07-22 | 2015-08-04 | 2015-08-10 | 2015-08-17 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY)
NC 2014 | SHS (2014) | Region VI | Guimaras | 302430 | East Valencia National High School | BUENAVISTA | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1 | 2015-12-04 | 2015-12-04 | 060414S00023 | 15GE0030 | 2015-07-06 | 2015-07-08 | 2015-07-21 | 2015-07-28 | 2015-08-06 | J.E. TICO CONSTRUCTION CO., INC. (FORMERLY: JET CO
NC 2014 | SHS (2014) | Region VI | GUIMARAS | 302431 | Getulio NHS | BUENAVISTA | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-23 | 2015-11-23 | 060414S00007 | 0604-14-S-00007 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-04 | 2015-09-14 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY)
NC 2014 | SHS (2014) | Region VI | Guimaras | 302432 | Jordan NHS | JORDAN (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-23 |  | 060414S00022 | 15GE0040 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-18 | 2015-08-26 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY)
NC 2014 | K10 (2014) | Region VI | Guimaras | 179503 | Mabini PS | BUENAVISTA | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2670828.124 |  |  | COMPLETED | 1 | 2016-01-20 |  | 060414S00006 | 0604-14-S-00006 | 2015-08-13 | 2015-08-14 | 2015-08-27 | 2015-09-09 | 2015-09-22 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY)
NC 2014 | SHS (2014) | Region VI | Guimaras | 302434 | Nueva Valencia National High School | NUEVA VALENCIA | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 | 2016-01-07 |  | 060414S00015 | 15GE0032 | 2015-07-15 | 2015-07-16 | 2015-07-28 | 2015-08-03 | 2015-08-10 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY)
NC 2014 | K10 (2014) | Region VI | Guimaras | 115830 | Paaralan ng Buhay ng Tacay | BUENAVISTA | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2016-01-20 |  | 060414S00002 | 0604-14-S-00002 | 2015-08-13 | 2015-08-14 | 2015-08-27 | 2015-09-09 | 2015-09-22 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY)
NC 2014 | K10 (2014) | Region VI | Guimaras | 115887 | Paaralan ng Buhay ng Tanglad | SIBUNAG | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1062049.6543 |  |  | COMPLETED | 1 | 2016-01-20 |  | 060414S00005 | 0604-14-S-00005 | 2015-08-13 | 2015-08-14 | 2015-08-27 | 2015-09-09 | 2015-09-22 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY)
NC 2014 | K10 (2014) | Region VI | Guimaras | 115914 | Panobolon PS | NUEVA VALENCIA | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1072049.6543 |  |  | COMPLETED | 1 | 2015-12-25 | 2015-12-25 | 060414S00004 | 0604-14-S-00004 | 2015-08-10 | 2015-08-12 | 2015-08-12 | 2015-08-19 | 2015-08-27 | By Administration
NC 2014 | SHS (2014) | Region VI | Guimaras | 302436 | Salvacion NHS | NUEVA VALENCIA | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 | 2016-01-07 |  | 060414S00014 | 15GE0033 | 2015-07-15 | 2015-07-16 | 2015-07-28 | 2015-08-03 | 2015-08-10 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY)
NC 2014 | SHS (2014) | Region VI | Guimaras | 302439 | San Lorenzo NHS - Suclaran Annex | SAN LORENZO | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 | 2016-01-14 |  | 060414S00013 | 15GE0037 | 2015-07-21 | 2015-07-22 | 2015-08-04 | 2015-08-10 | 2015-08-17 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY)
NC 2014 | K10 (2014) | Region VI | Guimaras | 179502 | San Nicolas PS | BUENAVISTA | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1 | 2014-09-23 | 2014-08-26 | 060414S00001 | 14GE0025 | 2014-06-04 | 2014-06-05 | 2014-06-10 | 2014-06-11 | 2014-06-20 | By Administration
NC 2014 | SHS (2014) | Region VI | Guimaras | 302433 | Simeon J. Jabasa NHS | NUEVA VALENCIA | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6429337.6381 |  |  | COMPLETED | 1 | 2015-12-25 | 2015-12-25 | 060414S00012 | 15GE0043 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-20 | 2015-08-27 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY)
NC 2014 | SHS (2014) | Region VI | Guimaras | 310902 | Supang National High School | BUENAVISTA | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8404965.051 |  |  | COMPLETED | 1 | 2016-01-03 |  | 060414S00011 | 15GE0028 | 2015-07-06 | 2015-07-08 | 2015-07-21 | 2015-07-28 | 2015-08-06 | J.E. TICO CONSTRUCTION CO., INC. (FORMERLY: JET CO
NC 2014 | SHS (2014) | Region VI | Guimaras | 302438 | Trinidad V. Canja-Sta. Teresa NHS | JORDAN (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1 | 2016-01-23 |  | 060414S00010 | 15GE0039 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-18 | 2015-08-26 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY)
NC 2014 | K10 (2014) | Region VI | Guimaras | 179501 | Unisan Multigrade School | NUEVA VALENCIA | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1072049.6543 |  |  | COMPLETED | 1 | 2015-12-25 | 2015-12-25 | 060414S00003 | 0604-14-S-00003 | 2015-08-10 | 2015-08-12 | 2015-08-12 | 2015-08-19 | 2015-08-27 | By Administration
NC 2014 | SHS (2014) | Region VI | Iloilo | 302509 | Iloilo NHS | ILOILO CITY (Capital) | 0 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 11377342.5917 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Iloilo | 302545 | Bacolod NHS | MIAGAO | 1 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3850805.49 |  |  | REVERTED | 0
NC 2014 | SHS (2014) | Region VI | Iloilo | 302495 | Don Felix Serra NHS | SAN JOAQUIN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8664965.051 |  |  | COMPLETED | 1 | 2016-01-01 |  | 060514S00162 | 15-GF-0041 | 2015-07-10 | 2015-07-09 | 2015-07-24 | 2015-08-06 | 2015-08-18 | J.E. TICO CONSTRUCTION CO., INC. (FORMERLY: JET CO
NC 2014 | SHS (2014) | Region VI | Iloilo | 302506 | Guimbal NHS | GUIMBAL | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 | 2016-01-21 |  | 060514S00161 | 15-GF-0035 | 2015-07-10 | 2015-07-09 | 2015-07-24 | 2015-08-06 | 2015-08-18 | IBC INTERNATIONAL BUILDERS CORPORATION
NC 2014 | SHS (2014) | Region VI | Iloilo | 302507 | Igbaras NHS | IGBARAS | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8764965.051 |  |  | COMPLETED | 1 | 2016-01-21 |  | 060514S00160 | 15-GF-0036 | 2015-07-10 | 2015-07-09 | 2015-07-24 | 2015-08-06 | 2015-08-18 | JHJ CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Iloilo | 302531 | Miagao NHS | MIAGAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8614965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Iloilo | 302542 | Oton National High School | OTON | 1 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 11177342.5917 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Iloilo | 302566 | SAN JOAQUIN SCHOOL OF FISHERIES | SAN JOAQUIN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8664965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Iloilo | 302578 | Tigbauan NHS | TIGBAUAN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 | 2016-01-21 |  | 060514S00150 | 15-GF-0039 | 2015-07-10 | 2015-07-09 | 2015-07-24 | 2015-08-06 | 2015-08-18 | KATHA BUILDERS
NC 2014 | SHS (2014) | Region VI | Iloilo | 302583 | Tubungan NHS | TUBUNGAN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8714965.051 |  |  | COMPLETED | 1 |  |  | 060514S00156 | 15-GF-0040 | 2015-07-10 | 2015-07-09 | 2015-07-24 | 2015-08-06 | 2015-08-18 | J.S. LAYSON & CO. , INC.
NC 2014 | SHS (2014) | Region VI | Iloilo | 311011 | Adriano Cabardo NHS | ALIMODIAN | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2810828.124 |  |  | Reverted | 0 |  |  | 060514S00166
NC 2014 | SHS (2014) | Region VI | Iloilo | 302446 | Alimodian NCHS | ALIMODIAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 | 2016-04-10 |  | 060514S00155 | 15GI0049 | 2015-10-06 | 2015-10-08 | 2015-10-20 | 2015-11-03 | 2015-11-13 | MBM CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Iloilo | 302516 | L.S. Salapantan NHS | SAN MIGUEL | 2 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8328653.2031 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Iloilo | 302516 | L.S. Salapantan NHS | SAN MIGUEL | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Iloilo | 302520 | Leganes National High School | LEGANES | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8305465.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Iloilo | 302522 | Leon NHS | LEON | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Iloilo | 115971 | Umingan Elementary School | ALIMODIAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1789187.4702 |  |  | REVERTED | 0 |  |  | 060514S00129
NC 2014 | K10 (2014) | Region VI | Iloilo | 116532 | Abilay Primary School | MAASIN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 998931.3377 |  |  | COMPLETED | 1 |  |  | 060514S00131 | 15GG0242 | 2015-12-15 | 2015-12-16 | 2015-12-29
NC 2014 | K10 (2014) | Region VI | Iloilo | 302452 | Badiangan NHS | BADIANGAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1698988.7202 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Iloilo | 302452 | Badiangan NHS | BADIANGAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8664965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Iloilo | 116445 | BANBAN ES | LAMBUNAO | 3 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2044000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Iloilo | 116389 | Barasalon ES | JANIUAY | 3 | 1 | 2 | 2UNITS 1STY 1CL | 2014 K10 BATCH 1 | 2434658.24 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 060514S00024 | 14GG0053 | 2014-06-30 | 2014-07-07 | 2014-07-15 | 2014-07-21 | 2014-07-28 | CHEDMARYL CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region VI | Iloilo | 302465 | Bingawan NHS | BINGAWAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Iloilo | 302477 | Calinog NCHS | CALINOG | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8664965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Iloilo | 116391 | Canauillan ES | JANIUAY | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1803207.2202 |  |  | REVERTED | 0
NC 2014 | SHS (2014) | Region VI | Iloilo | 311020 | Caninguan NHS | LAMBUNAO | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 | 2015-12-01 |  | 060514S00164 | 15GG0087 | 2015-06-03 | 2015-06-05 | 2015-06-18 | 2015-06-30 | 2015-09-08 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VI | Iloilo | 115999 | Catubig PS | BADIANGAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 950339.5877 |  |  | COMPLETED | 1 |  |  | 060514S00136 | 15GG0244 | 2015-12-15 | 2015-12-16 | 2015-12-29
NC 2014 | K10 (2014) | Region VI | Iloilo | 116138 | Corazon Galindo PS | CABATUAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1698988.7202 |  |  | COMPLETED | 1 |  |  | 060514S00134 | 15GG0245 | 2015-12-15 | 2015-12-16 | 2015-12-29
NC 2014 | K10 (2014) | Region VI | Iloilo | 180026 | Cornelio Gallego ES | LAMBUNAO | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-30 | 060514S00010 | 14GG0048 | 2014-06-30 | 2014-07-17 | 2014-07-15 | 2014-07-21 | 2014-07-28 | J E G CONSTRUCTION FIRM CORPORATION
NC 2014 | K10 (2014) | Region VI | Iloilo | 116108 | Don Salvador Hortelano Memorial School | BINGAWAN | 3 | 1 | 2 | 2UNITS 1STY 1CL | 2014 K10 BATCH 1 | 2414658.24 |  |  | COMPLETED | 1 | 2015-02-28 | 2015-02-28 | 060514S00018 | 14GG0052 | 2014-06-30 | 2014-07-07 | 2014-07-15 | 2014-07-21 | 2014-07-28 | J.E. TICO CONSTRUCTION CO., INC. (FORMERLY: JET CO
NC 2014 | K10 (2014) | Region VI | Iloilo | 116145 | J. Pueyo Elementary School | CABATUAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1698988.7202 |  |  | COMPLETED | 1 |  |  | 060514S00130 | 15GG0246 | 2015-12-15 | 2015-12-16 | 2015-12-29
NC 2014 | K10 (2014) | Region VI | Iloilo | 116601 | Janipa-an Elementary School | MINA | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 950339.5877 |  |  | COMPLETED | 1 |  |  | 060514S00121 | 15GG0247 | 2015-12-15 | 2015-12-16 | 2015-12-29
NC 2014 | SHS (2014) | Region VI | Iloilo | 311003 | Jayobo NHS | LAMBUNAO | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8864965.051 |  |  | COMPLETED | 1 | 2015-12-01 |  | 060514S00145 | 15GG0088 | 2015-06-03 | 2015-06-05 | 2015-06-18 | 2015-06-30 | 2015-09-08 | LEGACY CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Iloilo | 302517 | Lambunao NHS | LAMBUNAO | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8714965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Iloilo | 116431 | Lanot Grande ES | LAMBUNAO | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1803207.2202 |  |  | COMPLETED | 1 |  |  | 060514S00133 | 15GG0241 | 2015-12-15 | 2015-12-16 | 2015-12-29
NC 2014 | SHS (2014) | Region VI | Iloilo | 302524 | Maasin NCHS | MAASIN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2015-12-01 |  | 060514S00147 | 15GG0090 | 2015-06-03 | 2015-06-05 | 2015-06-18 | 2015-06-30 | 2015-09-09 | LEGACY CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Iloilo | 302526 | Malitbog NHS | CALINOG | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8614965.051 |  |  | COMPLETED | 1 | 2016-01-17 |  | 060514S00153 | 15GG0091 | 2015-06-03 | 2015-06-05 | 2015-06-18 | 2015-06-30 | 2015-09-01 | JHJ CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Iloilo | 116460 | Manaulan ES | LAMBUNAO | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Iloilo | 116460 | MANAULAN ES | LAMBUNAO | 3 |  | 5 | 3U-1STY1CL, 1STY2CL | 2014 K10 BATCH 2 | 4886000 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Iloilo | 302533 | Mina NHS | MINA | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8664965.051 |  |  | COMPLETED | 1 | 2015-12-13 |  | 060514S00149 | 15GG0092 | 2015-06-03 | 2015-06-05 | 2015-06-18 | 2015-06-30 | 2015-08-13 | ANJUSH BUILDERS
NC 2014 | K10 (2014) | Region VI | Iloilo | 116113 | NGINGI-AN PS | BINGAWAN | 3 | 1 | 4 | 1STY2CL, 2U-1STY1CL | 2014 K10 BATCH 2 | 3864000 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-04-30 | 060514S00138 | 14GG0100 | 2014-10-08 | 2014-10-10 | 2014-11-27 | 2014-12-18 | 2014-12-29 | J.E. TICO CONSTRUCTION CO., INC. (FORMERLY: JET CO
NC 2014 | SHS (2014) | Region VI | Iloilo | 302556 | Pototan National Comprehensive High School | POTOTAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 | 2015-12-07 |  | 060514S00141 | 15GG0093 | 2015-06-03 | 2015-06-05 | 2015-06-18 | 2015-06-30 | 2015-08-07 | ROPRIM CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Iloilo | 116155 | Tupol ES | CABATUAN | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2220417.57 |  |  | COMPLETED | 1 | 2015-02-28 | 2015-02-28 | 060514S00012 | 14GG0050 | 2014-06-30 | 2014-07-07 | 2014-07-15 | 2014-07-21 | 2014-07-28 | CHEDMARYL CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region VI | Iloilo | 302449 | Anilao NHS | ANILAO | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Iloilo | 302455 | Banate NHS | BANATE | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Iloilo | 302457 | Barotac Nuevo National Comprehensive High School | BAROTAC NUEVO | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 | 2016-01-19 |  | 060514S00165 | 15GG0096 | 2015-06-03 | 2015-06-05 | 2015-06-18 | 2015-06-30 | 2015-09-01 | ADP CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Iloilo | 116699 | Braulan PS | SAN ENRIQUE | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-11-30 | 060514S00009 | 14GG0051 | 2014-06-30 | 2014-07-07 | 2014-07-15 | 2014-07-21 | 2014-07-28 | PANAY EAST COAST CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region VI | Iloilo | 302490 | Dingle NHS | DINGLE | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Iloilo | 302497 | Duenas GCHS | DUEÑAS | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Iloilo | 302498 | Dumangas NHS | DUMANGAS | 4 | 1 | 10 | 2STY10CL | 2014 SHS BATCH 1 | 12821310.093 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Iloilo | 311006 | P.D. Monfort National Science HS | DUMANGAS | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 | 2015-12-15 | 2015-12-15 | 060514S00185 | 15GG0099 | 2015-06-03 | 2015-06-05 | 2015-06-18 | 2015-06-30 | 2015-08-12 | KIRSKAT VENTURE
NC 2014 | K10 (2014) | Region VI | Iloilo | 116328 | PULAO ES | DUMANGAS | 4 | 1 | 3 | 1STY1CL | 2014 K10 BATCH 2 | 1042000 |  |  | COMPLETED | 1 | 2015-01-30 | 2015-01-30 | 060514S00055 | 14GG067 | 2014-07-30 | 2014-08-11 | 2014-08-14 | 2014-08-20 | 2014-08-28 | PANAY EAST COAST CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region VI | Iloilo | 311008 | Rufino G. Palabrica, Sr. NHS | DINGLE | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1 | 2016-01-27 |  | 060514S00190 | 15GG0100 | 2015-06-03 | 2015-06-05 | 2015-06-18 | 2015-06-30 | 2015-09-04 | TOPMOST DEVELOPMENT & MKTG. CORP.
NC 2014 | K10 (2014) | Region VI | Iloilo | 116712 | Rumagayray PS | SAN ENRIQUE | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1719088.7202 |  |  | COMPLETED | 1 |  |  | 060514S00123 | 15GG0248 | 2015-12-15 | 2015-12-16 | 2015-12-29
NC 2014 | SHS (2014) | Region VI | Iloilo | 302564 | San Enrique NCHS | SAN ENRIQUE | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8305465.051 |  |  | COMPLETED | 1 | 2015-12-15 |  | 060514S00197 | 15GG0101 | 2015-06-03 | 2015-06-05 | 2015-06-18 | 2015-06-30 | 2015-08-12 | KIRSKAT VENTURE
NC 2014 | SHS (2014) | Region VI | Iloilo | 302443 | Ajuy NHS | AJUY | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-12-16 | 060514S00191 | 15GH0016c | 2015-06-19 | 2015-06-23 | 2015-06-24 | 2015-07-03 | 2015-07-20 | J.E. TICO CONSTRUCTION CO., INC. (FORMERLY: JET CO
NC 2014 | K10 (2014) | Region VI | Iloilo | 116481 | Alcantara PS | Lemery | 5 | 1 | 3 | 1STY2CL, 1STY1CL | 2014 K10 BATCH 2 | 2842000 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 060514S00100 | 14GH0036a | 2014-08-07 | 2014-08-20 | 2014-08-22 | 2014-08-29 | 2014-09-23 | STELLAR BUILDERS
NC 2014 | K10 (2014) | Region VI | Iloilo | 116772 | Ardemil ES | Sara | 5 | 1 | 11 | 1STY5CL, 1STY3CL, 1STY1CL, 1STY2CL | 2014 K10 BATCH 2 | 9818000 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 060514S00107 | 14GH0033b | 2014-08-07 | 2014-08-19 | 2014-08-21 | 2014-08-28 | 2014-09-23 | 5s CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Iloilo | 311009 | BALLESTEROS NHS | CARLES | 5 | 1 | 3 | 1STY2CL, 1STY1CL | 2014 K10 BATCH 2 | 3051250 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Iloilo | 116201 | BANCAL ES | Carles | 5 | 1 | 8 | 2U-1STY3CL, 2U-1STY1CL | 2014 K10 BATCH 2 | 7336000 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 060514S00092 | 14GH0042a | 2014-08-07 | 2014-08-19 | 2014-08-20 | 2014-08-25 | 2014-09-23 | Q. M. FLORETE CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Iloilo | 302458 | Barotac Viejo NHS | BAROTAC VIEJO | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8664965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Iloilo | 302460 | Batad NHS | BATAD | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Iloilo | 302461 | Bay-ang NHS | AJUY | 5 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6569337.6381 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-12-16 | 060514S00201 | 15GH0019 | 2015-06-19 | 2015-06-24 | 2015-06-26 | 2015-07-06 | 2015-07-20 | ADP CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Iloilo | 302462 | Bayas NHS | ESTANCIA | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Iloilo | 302462 | BAYAS NHS | ESTANCIA | 5 |  | 3 | 1STY2CL, 1STY1CL | 2014 K10 BATCH 2 | 3141000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Iloilo | 116484 | Benjamin Aguilar ES | Lemery | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1022000 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 060514S00029 | 14GH0036b | 2014-08-07 | 2014-08-19 | 2014-08-20 | 2014-08-24 | 2014-09-23 | 5s CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Iloilo | 116238 | BORRES POSADAS ES | CONCEPCION | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1032000 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-25 | 060514S00043 | 14GH0047d | 2014-08-07 | 2014-09-29 | 2014-10-10 | 2014-10-20 | 2014-10-27 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VI | Iloilo | 116063 | Bugnay Sur PS | BAROTAC VIEJO | 5 | 1 | 2 | 2UNITS 1STY 1CL | 2014 K10 BATCH 1 | 2399658.24 |  |  | COMPLETED | 1 | 2014-10-06 | 2014-10-06 | 060514S00015 | 14GH0017 | 2014-07-11 | 2014-07-24 | 2014-07-25 | 2014-07-31 | 2014-08-08 | J E G CONSTRUCTION FIRM CORPORATION
NC 2014 | K10 (2014) | Region VI | Iloilo | 116761 | Cabas-an ES | SAN RAFAEL | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1232329.12 |  |  | COMPLETED | 1 | 2014-10-06 | 2014-10-06 | 060514S00013 | 14GH0023 | 2014-07-11 | 2014-07-23 | 2014-07-25 | 2014-07-30 | 2014-08-08 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VI | Iloilo | 116014 | Camanbugan ES | BALASAN | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2014-10-06 | 2014-10-06 | 060514S00007 | 14GH0015 | 2014-07-12 | 2014-07-24 | 2014-07-25 | 2014-07-30 | 2014-08-08 | WOODLAND CONSTRUCTION & SUPPLY, INC.
NC 2014 | K10 (2014) | Region VI | Iloilo | 302493 | Carlos Lopez NHS | San Dionisio | 5 | 1 | 7 | 1STY5CL, 2U-1STY1CL | 2014 K10 BATCH 2 | 6289000 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Iloilo | 302493 | Carlos Lopez NHS | SAN DIONISIO | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Iloilo | 116213 | CAWAYAN ES | Carles | 5 | 1 | 4 | 1STY3CL, 1STY1CL | 2014 K10 BATCH 2 | 3683000 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 060514S00074 | 14GH0043b | 2014-08-07 | 2014-08-20 | 2014-08-22 | 2014-08-27 | 2014-09-23 | CHEDMARYL CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region VI | Iloilo | 302482 | Cawayan NHS | CARLES | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Iloilo | 116488 | Concepcion Juanillo MES | Lemery | 5 | 1 | 12 | 3U-1STY3CL, 1STY2CL, 1STY1CL | 2014 K10 BATCH 2 | 10835000 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 060514S00117 | 14GH0037b | 2014-08-07 | 2014-08-20 | 2014-08-22 | 2014-08-28 | 2014-09-23 | STELLAR BUILDERS
NC 2014 | K10 (2014) | Region VI | Iloilo | 116680 | Cubay ES | San Dionisio | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1022000 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Iloilo | 302486 | Culasi NHS | AJUY | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8614965.051 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-12-16 | 060514S00196 | 15GH0022 | 2015-06-19 | 2015-06-24 | 2015-06-26 | 2015-07-09 | 2015-07-20 | ADP CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Iloilo | 116244 | DANAO-DANAO PS | CONCEPCION | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1032000 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-25 | 060514S00042 | 14GH0047a | 2014-08-07 | 2014-09-29 | 2014-10-10 | 2014-10-20 | 2014-10-27 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VI | Iloilo | 116775 | Del Castillo Elementary School | Sara | 5 | 1 | 4 | 1STY3CL, 1STY1CL | 2014 K10 BATCH 2 | 3673000 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 060514S00094 | 14GH0032a | 2014-08-07 | 2014-08-19 | 2014-08-20 | 2014-08-27 | 2014-09-23 | WOODLAND CONSTRUCTION & SUPPLY, INC.
NC 2014 | K10 (2014) | Region VI | Iloilo | 116246 | Donato Valderrama PS | CONCEPCION | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 950339.5877 |  |  | COMPLETED | 1 | 2015-02-26 | 2015-02-26 | 060514S00137 | 14GH0092 | 2014-11-24 | 2014-11-28 | 2014-12-05 | 2014-12-15 | 2014-12-29 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VI | Iloilo | 116216 | GABI ES | CARLES | 5 | 1 | 6 | 2U-1STY1CL, 1STY4CL | 2014 K10 BATCH 2 | 5493000 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 060514S00108 | 14GH0041a | 2014-08-07 | 2014-08-19 | 2014-08-20 | 2014-09-08 | 2014-09-23 | WOODLAND CONSTRUCTION & SUPPLY, INC.
NC 2014 | K10 (2014) | Region VI | Iloilo | 116218 | GUINTICGAN ES | CARLES | 5 | 1 | 5 | 2U-1STY1CL, 1STY3CL | 2014 K10 BATCH 2 | 4695000 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 060514S00067 | 14GH0040a | 2014-08-07 | 2014-08-19 | 2014-08-20 | 2014-08-27 | 2014-09-23 | CHEDMARYL CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VI | Iloilo | 116779 | Ireneo Engle Sr. MES | SARA | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2200417.57 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 060514S00019 | 14GH20024 | 2014-09-15 | 2014-09-25 | 2014-09-26 | 2014-10-06 | 2014-10-13 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VI | Iloilo | 116781 | Labigan PS | SARA | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1272329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Iloilo | 302521 | Lemery National High School | LEMERY | 5 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-12-16 | 060514S00195 | 15GH0023 | 2015-06-19 | 2015-06-24 | 2015-06-26 | 2015-07-06 | 2015-07-20 | WOODLAND CONSTRUCTION & SUPPLY, INC.
NC 2014 | SHS (2014) | Region VI | Iloilo | 311007 | Loong NHS | CONCEPCION | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-12-16 | 060514S00194 | 15GH0024 | 2015-06-19 | 2015-06-24 | 2015-06-26 | 2015-07-06 | 2015-07-20 | ADP CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Iloilo | 116783 | Malapaya ES | Sara | 5 | 1 | 8 | 2U-1STY3CL, 2U-1STY1CL | 2014 K10 BATCH 2 | 7356000 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 060514S00099 | 14GH0032b | 2014-08-07 | 2014-08-20 | 2014-08-21 | 2014-08-29 | 2014-09-23 | WOODLAND CONSTRUCTION & SUPPLY, INC.
NC 2014 | K10 (2014) | Region VI | Iloilo | 115926 | Malayu-an ES | Ajuy | 5 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2034000 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 060514S00102 | 14GH0047c | 2014-08-07 | 2014-08-20 | 2014-08-21 | 2014-08-29 | 2014-09-23 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VI | Iloilo | 180032 | Nagsulang PS | LEMERY | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 960389.5877 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region VI | Iloilo | 180011 | Nasapahan PS | Lemery | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1022000 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 060514S00039 | 14GH0039c | 2014-08-07 | 2014-08-20 | 2014-08-21 | 2014-08-27 | 2014-09-23 | 5s CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region VI | Iloilo | 302541 | Nicomedes R. Tubar Sr. NHS | SAN DIONISIO | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8614965.051 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-12-16 | 060514S00189 | 15GH0025 | 2015-06-19 | 2015-06-24 | 2015-06-26 | 2015-07-06 | 2015-07-20 | J.E. TICO CONSTRUCTION CO., INC. (FORMERLY: JET CO
NC 2014 | K10 (2014) | Region VI | Iloilo | 116354 | PA-ON ES | ESTANCIA | 5 | 1 | 5 | 1STY4CL, 1STY1CL | 2014 K10 BATCH 2 | 4692000 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 060514S00084 | 14GH0046b | 2014-08-07 | 2014-08-19 | 2014-08-20 | 2014-08-25 | 2014-09-23 | CHEDMARYL CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VI | Iloilo | 115931 | Pedada ES | AJUY | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-10-06 | 2014-10-06 | 060514S00008 | 14GH0014 | 2014-07-11 | 2014-07-23 | 2014-07-25 | 2014-07-30 | 2014-08-08 | J.E. TICO CONSTRUCTION CO., INC. (FORMERLY: JET CO
NC 2014 | K10 (2014) | Region VI | Iloilo | 116223 | Piagao PS | CARLES | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1037473.0877 |  |  | COMPLETED | 1 | 2015-01-17 | 2015-01-17 | 060514S00124 | 14GH0071a | 2014-10-22 | 2014-10-31 | 2014-11-07 | 2014-11-17 | 2014-11-19 | 5s CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region VI | Iloilo | 302552 | Pili NHS | AJUY | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8614965.051 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-12-16 | 060514S00174 | 15GH0026 | 2015-06-19 | 2015-06-25 | 2015-06-26 | 2015-07-06 | 2015-07-20 | ADP CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region VI | Iloilo | 302484 | Roberto H. Tirol NHS | CONCEPCION | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8714965.051 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-12-16 | 060514S00168 | 15GH0027 | 2015-06-12 | 2015-06-24 | 2015-06-26 | 2015-07-06 | 2015-07-20 | J.E. TICO CONSTRUCTION CO., INC. (FORMERLY: JET CO
NC 2014 | K10 (2014) | Region VI | Iloilo | 116765 | San Andres ES | SAN RAFAEL | 5 | 1 | 5 | 1STY4CL, 1STY1CL | 2014 K10 BATCH 2 | 4471000 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 060514S00056 | 14GH0037a | 2014-08-07 | 2014-08-19 | 2014-08-20 | 2014-08-28 | 2014-09-23 | STELLAR BUILDERS
NC 2014 | K10 (2014) | Region VI | Iloilo | 302562 | San Antonio NHS | BAROTAC VIEJO | 5 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-10-06 | 2014-10-06 | 060514S00022 | 14GH0019 | 2014-07-11 | 2014-07-23 | 2014-07-25 | 2014-07-31 | 2014-08-08 | WOODLAND CONSTRUCTION & SUPPLY, INC.
NC 2014 | K10 (2014) | Region VI | Iloilo | 116497 | San Antonio PS | LEMERY | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 960389.5877 |  |  | COMPLETED | 1 | 2015-01-17 | 2015-01-17 | 060514S00125 | 14GH0071 | 2014-10-22 | 2014-10-31 | 2014-11-07 | 2014-11-13 | 2014-11-19 | 5s CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region VI | Iloilo | 302565 | San Fernando NHS | CARLES | 5 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2910828.124 |  |  | COMPLETED | 1 | 2015-10-17 | 2015-10-17 | 060514S00169 | 15GH0028 | 2015-06-15 | 2015-06-24 | 2015-06-26 | 2015-07-08 | 2015-07-20 | ALJ CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VI | Iloilo | 116355 | SAN ROQUE ES | ESTANCIA | 5 | 1 | 5 | 1STY4CL, 1STY1CL | 2014 K10 BATCH 2 | 4511000 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 060514S00086 | 14GH0052a | 2014-08-07 | 2014-08-19 | 2014-08-20 | 2014-08-24 | 2014-09-23 | WILLIAM UY CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Iloilo | 302570 | Sara NHS | SARA | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Iloilo | 180019 | Sincua PS | LEMERY | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 998931.3377 |  |  | COMPLETED | 1 | 2015-01-17 | 2015-01-17 | 060514S00128 | 14GH0071 | 2014-10-22 | 2014-10-31 | 2014-11-06 | 2014-11-12 | 2014-11-18 | 5s CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VI | Iloilo | 116695 | Talo Ato PS | San Dionisio | 5 | 1 | 4 | 4U-1STY1CL | 2014 K10 BATCH 2 | 4068000 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 060514S00089 | 14GH0053c | 2014-08-07 | 2014-08-19 | 2014-08-20 | 2014-08-27 | 2014-09-23 | CHEDMARYL CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VI | Iloilo | 116263 | TALOTO-AN ES | CONCEPCION | 5 | 1 | 4 | 1STY2CL, 2U-1STY1CL | 2014 K10 BATCH 2 | 3874000 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 060514S00065 | 14GH0047b | 2014-08-07 | 2014-08-19 | 2014-08-20 | 2014-09-10 | 2014-09-23 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VI | Iloilo | 116101 | Tanao ES | BATAD | 5 | 1 | 2 | 2UNITS 1STY 1CL | 2014 K10 BATCH 1 | 2414658.24 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Iloilo | 116101 | TANAO ES | Batad | 5 |  | 4 | 2U-1STY1CL, 1STY2CL | 2014 K10 BATCH 2 | 3864000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Iloilo | 116356 | Tanza ES | ESTANCIA | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2310417.57 |  |  | COMPLETED | 1 | 2014-10-06 | 2014-10-06 | 060514S00017 | 14GH0021 | 2014-07-11 | 2014-07-23 | 2014-07-25 | 2014-07-31 | 2014-08-08 | CHEDMARYL CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VI | Iloilo | 116229 | TINIGBAN ES | CARLES | 5 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2187400 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 060514S00109 | 14GH0042c | 2014-08-07 | 2014-08-20 | 2014-08-21 | 2014-08-28 | 2014-09-23 | Q. M. FLORETE CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | Iloilo | 116696 | Tuble ES | San Dionisio | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1022000 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 060514S00034 | 14GH0053a | 2014-08-07 | 2014-08-19 | 2014-08-20 | 2014-08-24 | 2014-09-23 | CHEDMARYL CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VI | Iloilo | 116088 | Ugasan ES | BAROTAC VIEJO | 5 | 1 | 2 | 2UNITS 1STY 1CL | 2014 K10 BATCH 1 | 2354658.24 |  |  | COMPLETED | 1 | 2014-10-06 | 2014-10-06 | 060514S00016 | 14GH0018 | 2014-07-11 | 2014-07-23 | 2014-07-25 | 2014-07-31 | 2014-08-08 | UNITEC BUILDER, INCORPORATED
NC 2014 | K10 (2014) | Region VI | Iloilo | 311001 | VALERIO PALMARES NHS | Batad | 5 | 1 | 9 | 1STY5CL, 1STY2CL, 2U-1STY1CL | 2014 K10 BATCH 2 | 8383000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | Iloilo | 116025 | Zaragosa ES | BALASAN | 5 | 1 | 3 | 1STY 1CL & 1STY 2CL | 2014 K10 BATCH 1 | 3392746.69 |  |  | COMPLETED | 1 | 2014-10-06 | 2014-10-06 | 060514S00011 | 14GH0016 | 2014-07-11 | 2014-07-23 | 2014-07-25 | 2014-07-31 | 2014-08-08 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2014 | SHS (2014) | Region VI | Iloilo City | 302737 | Fort San Pedro NHS | ILOILO CITY (Capital) | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15097518.84 |  |  | COMPLETED | 1 |  |  | 060514S00171 | 15GJ0106 | 2015-12-09 | 2015-12-11 | 2015-12-23 | 2015-12-29
NC 2014 | SHS (2014) | Region VI | Iloilo City | 302738 | Iloilo City NHS | ILOILO CITY (Capital) | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15037518.84 |  |  | COMPLETED | 1 | 2016-05-31 |  | 060514S00172 | 15GJ0054 | 2015-08-27 | 2015-08-28 | 2015-10-26 | 2015-11-23 | 2015-11-27 | H.L.J CONSTRUCTION & ENTERPRISES
NC 2014 | SHS (2014) | Region VI | Iloilo City | 302742 | Jalandoni MNHS | ILOILO CITY (Capital) | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14957518.84 |  |  | COMPLETED | 1 |  |  | 060514S00173
NC 2014 | SHS (2014) | Region VI | Iloilo City | 302744 | Jaro National High School | ILOILO CITY (Capital) | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14997518.84 |  |  | COMPLETED | 1 |  |  | 060514S00176 | 15GJ0094 | 2015-12-01 | 2015-12-02 | 2015-12-14 | 2015-12-29
NC 2014 | K10 (2014) | Region VI | Iloilo City | 302747 | La Paz NHS | ILOILO CITY (Capital) | 0 | 1 | 15 | 3STY15CL | 2014 K10 BATCH 3 | 23632771.7188 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Iloilo City | 302747 | La Paz NHS | ILOILO CITY (Capital) | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 15077518.84 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Iloilo City | 302749 | Mandurriao NHS | ILOILO CITY (Capital) | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15107518.84 |  |  | COMPLETED | 1 |  |  | 060514S00187 | 15GJ0105 | 2015-12-09 | 2015-12-11 | 2015-12-23 | 2015-12-29
NC 2014 | SHS (2014) | Region VI | Iloilo City | 302746 | R. G. Hechanova Memorial NHS | ILOILO CITY (Capital) | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6359337.6381 |  |  | COMPLETED | 1 | 2016-04-01 |  | 060514S00175 | 15GJ0055 | 2015-08-27 | 2015-08-28 | 2015-10-26 | 2015-11-23 | 2015-11-27 | V N GRANDE BUILDERS & SUPPLY
NC 2014 | SHS (2014) | Region VI | Iloilo City | 302750 | Ramon Avancena NHS | ILOILO CITY (Capital) | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14957518.84 |  |  | COMPLETED | 1 | 2016-05-31 |  | 060514S00167 | 15GJ0052 | 2015-08-25 | 2015-08-27 | 2015-10-26 | 2015-11-23 | 2015-11-27 | H.L.J CONSTRUCTION & ENTERPRISES
NC 2014 | SHS (2014) | Region VI | Iloilo City | 311501 | SPED - Integrated School for Exceptional Children | ILOILO CITY (Capital) | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | Reverted | 0 |  |  | 060514S00177
NC 2014 | SHS (2014) | Region VI | Iloilo City | 500191 | TCT-AR Foundation Integrated School | ILOILO CITY (Capital) | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 060514S00178
NC 2014 | SHS (2014) | Region VI | Passi City | 302806 | Efraim M. Santibanez National High School | CITY OF PASSI | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 | 2015-12-15 |  | 060514S00179 | 15GG0106 | 2015-06-03 | 2015-06-05 | 2015-06-18 | 2015-06-30 | 2015-08-06 | JB BALLERAS CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region VI | Passi City | 302804 | Mulapula NHS | CITY OF PASSI | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2015-12-01 |  | 060514S00200 | 15GG0102 | 2015-06-03 | 2015-06-05 | 2015-06-18 | 2015-06-30 | 2015-09-08 | LEGACY CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Passi City | 302805 | Passi NHS | CITY OF PASSI | 4 | 1 | 10 | 2STY10CL | 2014 SHS BATCH 1 | 13371310.093 |  |  | COMPLETED | 1 | 2015-12-01 |  | 060514S00199 | 15GG0105 | 2015-06-03 | 2015-06-05 | 2015-06-18 | 2015-06-30 | 2015-09-02 | P.B. OBIAL CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Passi City | 302807 | Salngan NHS | CITY OF PASSI | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2015-12-15 |  | 060514S00180 | 15GG0103 | 2015-06-03 | 2015-06-05 | 2015-06-18 | 2015-06-30 | 2015-08-11 | MBM CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | ROXAS CITY | 302755 | Bago NHS | ROXAS CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-20 | 2015-11-20 | 060314S00101 | 15GD0049M | 2015-07-09 | 2015-07-10 | 2015-08-13 | 2015-08-19 | 2015-08-25 | By Administration
NC 2014 | K10 (2014) | Region VI | ROXAS CITY | 117665 | BALIJUAGAN ES | ROXAS CITY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1003000 |  |  | COMPLETED | 1 | 2014-10-27 | 2014-10-27 | 060314S00051 | 14GD0017-5 | 2014-07-09 | 2014-07-21 | 2014-07-22 | 2014-07-28 | 2014-07-31 | ROLA CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Roxas City | 302756 | Balijuagan NHS | ROXAS CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-13 |  | 060314S00096 | 15GD0032-1 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-07 | 2015-08-14 | ROPRIM CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Roxas City | 302757 | Cong. Ramon A. Arnaldo HS | ROXAS CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-13 |  | 060314S00103 | 15GD0032-2 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-07 | 2015-08-14 | ROPRIM CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Roxas City | 302758 | Culasi NHS | ROXAS CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-13 |  | 060314S00104 | 15GD0033-1 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-07 | 2015-08-14 | ROPRIM CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Roxas City | 311704 | Don Ynocencio A. Del Rosario National High School formerly Tanque NHS-Dayao Extension | ROXAS CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-13 |  | 060314S00105 | 15GD0034-1 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-07 | 2015-08-14 | ROPRIM CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Roxas City | 302759 | Dumolog NHS | ROXAS CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-13 |  | 060314S00106 | 15GD0033-2 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-07 | 2015-08-14 | ROPRIM CONSTRUCTION
NC 2014 | K10 (2014) | Region VI | ROXAS CITY | 117680 | GERVACIO DIAZ ES | ROXAS CITY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1033000 |  |  | COMPLETED | 1 | 2014-10-31 | 2014-10-31 | 060314S00052 | 14GD0017-6 | 2014-07-09 | 2014-07-21 | 2014-07-22 | 2014-07-28 | 2014-07-31 | ROLA CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Roxas City | 302760 | Milibili NHS | ROXAS CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-14 |  | 060314S00107 | 15GD0035-1 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-07 | 2015-08-14 | ROPRIM CONSTRUCTION
NC 2014 | SHS (2014) | Region VI | Roxas City | 311702 | Roxas City School for Philippine Craftsmen | ROXAS CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VI | ROXAS CITY | 117664 | RUFINA ANDRADA SANTOS MS | ROXAS CITY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1033000 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region VI | Roxas City | 302761 | Tanque NHS | ROXAS CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-13 |  | 060314S00102 | 15GD0034-2 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-07 | 2015-08-14 | ROPRIM CONSTRUCTION
NC 2015 | K10 (2015) | Region VI | Bacolod City | 117468 | A.L. Jayme ES | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1 |  |  | 060615S00126 | 15GC0084 | 2015-09-27 | 2015-09-28 | 2015-10-12 | 2015-10-19 | 2015-10-26 | LEGACY CONSTRUCTION
NC 2015 | SHS (2015) | Region VI | Bacolod City | 302701 | Bacolod City National High School | BACOLOD CITY (Capital) | 0 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 63005781 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Bacolod City | 117478 | DoÃ±a E.J. Garcia ES | BACOLOD CITY (Capital) | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060615S00055 | 15GC0050 | 2015-08-02 | 2015-08-03 | 2015-08-17 | 2015-08-27 | 2015-09-18 | TSD BUILDERS CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VI | Bacolod City | 302705 | Domingo Lacson NHS | BACOLOD CITY (Capital) | 0 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31942890 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Bacolod City | 117488 | Don I. Nessia Sr. ES | BACOLOD CITY (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060615S00125 | 15GC0063 | 2015-08-19 | 2015-08-20 | 2015-09-01 | 2015-09-14 | 2015-09-21 | CGGFR CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VI | Bacolod City | 117482 | Educ.& Training Center Sch. II | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | REVERTED | 0
NC 2015 | K10 (2015) | Region VI | Bacolod City | 181005 | Handumanan ES II | BACOLOD CITY (Capital) | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 060615S00057 | 15GC0075 | 2015-09-01 | 2015-09-02 | 2015-09-14 | 2015-09-24 | 2015-09-30 | ST. RAYMUND CONSTRUCTION, INC.
NC 2015 | K10 (2015) | Region VI | Bacolod City | 117471 | Handumanan ES-1 | BACOLOD CITY (Capital) | 0 | 1 | 15 | 3STY15CL | 2015 K10 BATCH 6 | 21383013.45 |  |  | COMPLETED | 1 |  |  | 060615S00124 | 15GC089 | 2015-10-19 | 2015-10-20 | 2015-11-03 | 2015-11-06 | 2015-11-10 | JAIME B. CHING ENTERPRISES
NC 2015 | TECHVOC (2015) | Region VI | Bacolod City | 302712 | Handumanan NHS | BACOLOD CITY (Capital) | 0 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2529549.27 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VI | Bacolod City | 302716 | Sum-ag NHS | BACOLOD CITY (Capital) | 0 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2629549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Bacolod City | 181004 | Vista Alegre-Granada Relocation ES | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8184965.051 |  |  | COMPLETED | 1 |  |  | 060615S00121 | 15GC0083 | 2015-09-27 | 2015-09-28 | 2015-10-12 | 2015-10-19 | 2015-10-26 | LEGACY CONSTRUCTION | w/ defects and non conformance to standard plans. Inspected w/ local School Board and letter sent to DPWH
NC 2015 | K10 (2015) | Region VI | Bago City | 117525 | Najaba ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1993606.04 |  |  | COMPLETED | 1 |  |  | 060615S00127 | 060615S00127 | 2015-10-26 | 2015-10-27 | 2015-11-10 | 2015-11-23 | 2015-12-02 | HUMMING BIRD CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VI | Bago City | 302720 | Ramon Torres Dulao NHS | BAGO CITY | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 060615S00036 | 15GN0077 | 2015-08-06 | 2015-08-07 | 2015-08-20 | 2015-08-26 | 2015-09-04 | MICRO ASIA BUILDERS CORPORATION
NC 2015 | TECHVOC (2015) | Region VI | Bago City | 302724 | Ramon Torres Louisiana NHS | BAGO CITY | 4 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Bago City | 302721 | Ramon Torres Ma-ao Sugar Central NHS | BAGO CITY | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Bago City | 302721 | Ramon Torres Ma-ao Sugar Central NHS | BAGO CITY | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Bago City | 302722 | RAMON TORRES MALINGIN NATIONAL HIGH SCHOOL | BAGO CITY | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VI | Bago City | 302722 | RAMON TORRES MALINGIN NATIONAL HIGH SCHOOL | BAGO CITY | 4 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Bago City | 302719 | Ramon Torres NHS | BAGO CITY | 4 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 11207342.5917 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Bago City | 302719 | Ramon Torres NHS | BAGO CITY | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8494965 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VI | Bago City | 302719 | Ramon Torres NHS | BAGO CITY | 4 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Bago City | 302723 | Ramon Torres Sagasa NHS | BAGO CITY | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060615S00035 | 060615S00035 | 2015-11-25 | 2015-11-26 | 2015-12-08
NC 2015 | SHS (2015) | Region VI | Bago City | 302725 | Ramon Torres Taloc NHS | BAGO CITY | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 060615S00034 | 15GN0078 | 2015-08-06 | 2015-08-14 | 2015-08-20 | 2015-08-26 | 2015-09-04 | FOUR SG ENTERPRISES
NC 2015 | K10 (2015) | Region VI | Bago City | 117501 | T.M. Morada Sr. ES | BAGO CITY | 4 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 060615S00054 | 15GN0084 | 2015-08-09 | 2015-08-11 | 2015-08-24 | 2015-08-27 | 2015-09-08 | HUMMING BIRD CONSTRUCTION & SUPPLY
NC 2015 | TECHVOC (2015) | Region VI | Cadiz City | 302730 | Dr. Vicente F. Gustilo Memorial NHS | CADIZ CITY | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4829098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Cadiz City | 302736 | Jerusalem National High School (Villacin NHS - Jerusalem Ext. HS) | CADIZ CITY | 2 | 1 | 2 | ADDITIONAL 1STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Cadiz City | 302734 | Tiglawigan NHS - Magsaysay Extension High School | CADIZ CITY | 2 | 1 | 1 | ADDITIONAL 1STY1CL | 2015 ADDITIONAL FUND BATCH 9 | 1012049.6543 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VI | Escalante City | 302660 | Mabini NHS | CITY OF ESCALANTE | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Kabankalan City | 117841 | Bino ES | CITY OF KABANKALAN | 6 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060615S00053 | 15GM0064 | 2015-10-03 | 2015-09-29 | 2015-10-12 | 2015-10-21 | 2015-11-06 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VI | Kabankalan City | 302792 | Camansi NHS | CITY OF KABANKALAN | 6 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8304965 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Kabankalan City | 302787 | CAROL-AN NHS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2118606 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Kabankalan City | 302787 | CAROL-AN NHS | CITY OF KABANKALAN | 6 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3667969 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Kabankalan City | 302788 | DAAN BANUA NHS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 |  |  | 060615S00136 | 15GM0089 | 2015-10-12 | 2015-10-14 | 2015-10-26 | 2015-11-06 | 2015-11-20 | TSD BUILDERS CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region VI | Kabankalan City | 117883 | Ilan PS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2188606.04 |  |  | COMPLETED | 1 |  |  | 060615S00128 | 0606-15-S-00128 | 2015-10-20 | 2015-10-22
NC 2015 | K10 (2015) | Region VI | Kabankalan City | 302795 | Locotan NHS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 2088606 |  |  | COMPLETED | 1 |  |  | 060615S00140 | 15GM0090 | 2015-10-12 | 2015-10-14 | 2015-10-26 | 2015-11-06 | 2015-11-20 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2015 | K10 (2015) | Region VI | Kabankalan City | 117888 | Mamig ES | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060615S00052 | 15GM0046 | 2015-09-08 | 2015-09-11 | 2015-09-23 | 2015-10-05 | 2015-10-22 | ADROIT CONSTRUCTION
NC 2015 | SHS (2015) | Region VI | Kabankalan City | 302798 | PINAGUINPINAN NHS | CITY OF KABANKALAN | 6 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8334965 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Kabankalan City | 117849 | Pitgong ES | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060615S00043 | 15GM0045 | 2015-07-23 | 2015-07-27 | 2015-08-10 | 2015-08-18 | 2015-09-03 | ST. RAYMUND CONSTRUCTION, INC.
NC 2015 | TECHVOC (2015) | Region VI | La Carlota City | 302751 | Dona H.S.Benedicto NHS | LA CARLOTA CITY | 4 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2489549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | La Carlota City | 302751 | Dona H.S.Benedicto NHS | LA CARLOTA CITY | 4 | 1 | 30 | 3STY15CL | 2015 SHS BATCH 5 | 43126027 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VI | Sagay City | 302768 | Bulanon National High School | SAGAY CITY | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Sagay City | 117712 | Cesar Gamboa ES | SAGAY CITY | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060615S00049 | 15GK0108 | 2015-09-09 | 2015-09-09
NC 2015 | TECHVOC (2015) | Region VI | Sagay City | 500037 | Eusebio Lopez Memorial Integrated School | SAGAY CITY | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VI | Sagay City | 500038 | Himogaan Baybay Integrated School | SAGAY CITY | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2449549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Sagay City | 302767 | Sagay NHS | SAGAY CITY | 2 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15121327.92 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Sagay City | 500039 | Serafin V. Aguilar Integrated School | SAGAY CITY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 2058606 |  |  | COMPLETED | 1 |  |  | 060615S00138 | 15GK0127 | 2015-10-20 | 2015-10-21 | 2015-11-04 | 2015-11-11 | 2015-11-20 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VI | Sagay City |  | SNHS-Brgy. Lopez Jaena Ext. | SAGAY CITY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Sagay City |  | SNHS-Brgy. Rizal Ext. | SAGAY CITY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | San Carlos City | 302773 | Bagonbon NHS | SAN CARLOS CITY | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 7 | 8214965 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | San Carlos City | 302773 | Bagonbon NHS | SAN CARLOS CITY | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VI | Silay City | 302780 | Doña Montserrat Lopez MHS | SILAY CITY | 3 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4879098.54 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VI | Aklan | 302324 | Aklan NHS for Arts & Trades | KALIBO (Capital) | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2479549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Aklan | 302316 | Alaminos NHS | MADALAG | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2048606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Aklan | 310617 | Alfonso XII NHS | LIBACAO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2063606 |  |  | REVERTED | 0
NC 2015 | TECHVOC (2015) | Region VI | Aklan | 302286 | Altavas National School | ALTAVAS | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2479549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Aklan | 500180 | Cortes Integrated School | BALETE | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 5 | 1988606 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Aklan | 500181 | Dalagsaan Integrated School | LIBACAO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2288606 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | Region VI | Aklan | 302307 | Father Julian C. Rago Memorial NHS | BALETE | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8359965 |  |  | COMPLETED | 1 |  |  | 060115S00021 | 15GA0157 | 2015-12-08 | 2015-12-09 | 2015-12-22
NC 2015 | K10 (2015) | Region VI | Aklan | 114719 | Ibajay Central School | IBAJAY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1968606.04 |  |  | COMPLETED | 1 |  |  | 060115S00024 | 15GA0183 | 2015-11-24 | 2015-11-25 | 2015-12-08 | 2015-12-18 | 2015-12-28 | FIRST MAKEEN CONSTRUCTION
NC 2015 | K10 (2015) | Region VI | Aklan | 114688 | Ipil ES | BATAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2113606.04 |  |  | COMPLETED | 1 |  |  | 060115S00029 | 15GA0150 | 2015-09-03 | 2015-09-04 | 2015-09-17 | 2015-11-05 | 2015-11-10 | CARME ROSE ENTERPRISE
NC 2015 | K10 (2015) | Region VI | Aklan | 310630 | Ipil Integrated School | BATAN | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 060115S00013 | 15GA0122 | 2015-07-21 | 2015-07-22 | 2015-08-04 | 2015-08-27 | 2015-09-02 | ORANI BUILDERS & SUPPLY
NC 2015 | SHS (2015) | Region VI | Aklan | 500183 | Jawili Integrated School | TANGALAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1993606 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | Region VI | Aklan | 302309 | Jose F. Meñez Memorial National High School | BALETE | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 060115S00001 | 15GA0130 | 2015-09-03 | 2015-09-04 | 2015-09-17 | 2015-10-21 | 2015-10-26 | CARME ROSE ENTERPRISE
NC 2015 | SHS (2015) | Region VI | Aklan | 302287 | Justicia Morales-Young National High School | ALTAVAS | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1988606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Aklan | 114706 | Katipunan ES | BURUANGA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 060115S00014 | 15GA0103 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-27 | 2015-09-02 | KENBE CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VI | Aklan | 310601 | LUPO NATIONAL HIGH SCHOOL | ALTAVAS | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1988606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Aklan | 310629 | Ma. Cristina IS | MADALAG | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 7 | 2947592 |  |  | COMPLETED | 1 |  |  | 060115S00030 | 15GA0172 | 2015-10-28 | 2015-10-29
NC 2015 | SHS (2015) | Region VI | Aklan | 302315 | Madalag NHS | MADALAG | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8564965.051 |  |  | COMPLETED | 1 |  |  | 060115S00011 | 15GA0128 | 2015-08-04 | 2015-08-05 | 2015-08-18 | 2015-08-27 | 2015-09-02 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VI | Aklan | 302319 | Malinao Sch. For Phil. Craftsmen | MALINAO | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10697131.51 |  |  | COMPLETED | 1 |  |  | 060115S00010 | 15GA0201 | 2015-12-14 | 2015-12-15
NC 2015 | K10 (2015) | Region VI | Aklan | 114789 | Manika ES | LIBACAO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | REVERTED | 0 |  |  | 060115S00027 | 15GA0155 | 2015-09-02 | 2015-09-04
NC 2015 | SHS (2015) | Region VI | Aklan | 302303 | New Washington NCHS | NEW WASHINGTON | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6409337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Aklan | 302303 | New Washington NCHS | NEW WASHINGTON | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Aklan | 114683 | Nicolas R. Delgado Elementary School | BATAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2008606.04 |  |  | COMPLETED | 1 |  |  | 060115S00028 | 15GA0151 | 2015-11-26 | 2015-11-27 | 2015-12-10 | 2015-12-23 |  | FIRST MAKEEN CONSTRUCTION
NC 2015 | SHS (2015) | Region VI | Aklan | 500174 | Ortega IS | LIBACAO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6439337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Aklan | 302331 | Panayakan National High School | TANGALAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2363606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Aklan | 500186 | Pinamuk-an Integrated School | NEW WASHINGTON | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2118606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Aklan | 114826 | Singay PS | MADALAG | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | REVERTED | 0 |  |  | 060115S00025 | 15GA0160 | 2015-12-22 | 2015-12-23
NC 2015 | SHS (2015) | Region VI | Aklan | 302335 | Solido NHS | NABAS | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 3122592.44 |  |  | COMPLETED | 1 |  |  | 060115S00005 | 15GA0125 | 2015-08-04 | 2015-08-05 | 2015-08-18 | 2015-08-27 | 2015-09-02 | FIRST MAKEEN CONSTRUCTION
NC 2015 | K10 (2015) | Region VI | Aklan | 114725 | Sta. Cruz ES | IBAJAY | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 060115S00012 | 15GA0104 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-27 | 2015-09-01 | G.F. ROVERO MERCHANDISING
NC 2015 | SHS (2015) | Region VI | Aklan | 500187 | Tabon Integrated School | BATAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2138606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Aklan |  | Taroytoy PS | LIBACAO | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 3402592.44 |  |  | REVERTED | 0 |  |  | 060115S00026 | 15GA0154 | 2015-09-03 | 2015-09-04
NC 2015 | SHS (2015) | Region VI | Aklan |  | Toledo NHS | NABAS | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6389337.6381 |  |  | COMPLETED | 1 |  |  | 060115S00004 | 15GA0105 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-06 | 2015-08-22 | G.F. ROVERO MERCHANDISING
NC 2015 | SHS (2015) | Region VI | Aklan | 302340 | Union NHS | NABAS | 2 | 1 | 6 | 1STY6CL (Toilet Attached) | 2015 SHS BATCH 2 | 5492651.88 |  |  | COMPLETED | 1 |  |  | 060115S00003 | 15GA0144 | 2015-08-13 | 2015-08-14 | 2015-08-27 | 2015-08-28 | 2015-09-02 | FIRST MAKEEN CONSTRUCTION
NC 2015 | K10 (2015) | Region VI | Antique | 115339 | Amar PS | TIBIAO | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060215S00061 | 15GB0103 | 2015-10-22 | 2015-11-03 | 2015-11-27
NC 2015 | SHS (2015) | Region VI | Antique | 302341 | Antique NS | SAN JOSE (Capital) | 0 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 2 | 31185890.27 |  |  | COMPLETED | 1 |  |  | 060215S00055
NC 2015 | SHS (2015) | Region VI | Antique | 302342 | Antique VS | BUGASONG | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8249965.051 |  |  | COMPLETED | 1 |  |  | 060215S00036 | 15GB0169 | 2015-11-27 | 2015-12-09 | 2015-12-10
NC 2015 | K10 (2015) | Region VI | Antique | 115080 | Apdo ES | HAMTIC | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060215S00089 | 0602-15-S-00089 | 2015-11-07 | 2015-11-19 | 2015-11-20
NC 2015 | K10 (2015) | Region VI | Antique | 115081 | Asluman ES | HAMTIC | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060215S00090 | 0602-15-S-00090 | 2015-11-07 | 2015-11-19 | 2015-11-20
NC 2015 | K10 (2015) | Region VI | Antique | 115357 | Atabay ES | TOBIAS FORNIER (DAO) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060215S00080 | 0602-15-S-00080 | 2015-11-07 | 2015-11-19 | 2015-11-20
NC 2015 | SHS (2015) | Region VI | Antique | 302343 | Aureliana NHS | PATNONGON | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 060215S00046 | 15GB0168 | 2015-11-27 | 2015-12-09 | 2015-12-10
NC 2015 | K10 (2015) | Region VI | Antique | 115389 | Bakiang ES | VALDERRAMA | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2268606.04 |  |  | REVERTED | 0 |  |  | 060215S00076 | 0602-15-S-00076 | 2015-11-21
NC 2015 | SHS (2015) | Region VI | Antique | 302344 | Barangbang NHS | SAN REMIGIO | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 060215S00038 | 0602-15-S-00038 | 2015-12-05 | 2015-12-17 | 2015-12-18
NC 2015 | SHS (2015) | Region VI | ANTIQUE | 302345 | Barasanan NHS | TOBIAS FORNIER (DAO) | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 060215S00032 | 15GB0075 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-24 | 2015-09-21 | ANJUSH BUILDERS
NC 2015 | K10 (2015) | Region VI | Antique | 114958 | Barbaza CS | BARBAZA | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 060215S00057 | 15GB0173 | 2015-11-27 | 2015-12-09 | 2015-12-10
NC 2015 | SHS (2015) | Region VI | Antique | 302346 | Barbaza NHS | BARBAZA | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 060215S00028 | 15GB0132 | 2015-11-12 | 2015-11-24 | 2015-11-25
NC 2015 | SHS (2015) | Region VI | Antique | 302347 | Belison NS | BELISON | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8244965.051 |  |  | COMPLETED | 1 |  |  | 060215S00039 | 0602-15-S-00039 | 2015-12-05 | 2015-12-17 | 2015-12-18
NC 2015 | SHS (2015) | Region VI | Antique | 302348 | Bitadton NHS | CULASI | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6359337.6381 |  |  | COMPLETED | 1 |  |  | 060215S00048 | 15GB0153 | 2015-11-21 | 2015-12-03 | 2015-12-04
NC 2015 | K10 (2015) | Region VI | Antique | 115006 | Bonbon ES | CALUYA | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2238606.04 |  |  | COMPLETED | 1 |  |  | 060215S00096 | 0602-15-S-00096 | 2015-11-21
NC 2015 | K10 (2015) | Region VI | Antique | 115145 | Botbot ES | PANDAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060215S00093 | 0602-15-S-00093 | 2015-11-07 | 2015-11-19 | 2015-11-20
NC 2015 | K10 (2015) | Region VI | Antique | 115063 | Budbudan ES | HAMTIC | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060215S00087 | 0602-15-S-00087 | 2015-11-07 | 2015-11-19 | 2015-11-20
NC 2015 | K10 (2015) | Region VI | Antique | 115258 | Bugo CS | SAN REMIGIO | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060215S00064 | 0602-15-S-00064 | 2015-10-22 | 2015-11-03 | 2015-11-04
NC 2015 | K10 (2015) | Region VI | Antique | 115065 | Buhang - Annex ES | HAMTIC | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060215S00088 | 0602-15-S-00088 | 2015-11-07 | 2015-11-19 | 2015-11-20
NC 2015 | SHS (2015) | Region VI | Antique | 302349 | Buhang NHS | HAMTIC | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 |  |  | 060215S00050 | 0602-15-S-00050 | 2015-11-12 | 2015-11-24 | 2015-11-25
NC 2015 | K10 (2015) | Region VI | Antique | 115260 | Cabunga-an PS | SAN REMIGIO | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2063606.04 |  |  | REVERTED | 0 |  |  | 060215S00083 | 0602-15-S-00083 | 2015-12-06 | 2015-12-17 | 2015-12-18
NC 2015 | K10 (2015) | Region VI | Antique | 115312 | Calooy ES | SIBALOM | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 060215S00070 | 0602-15-S-00070 | 2015-11-14 | 2015-11-26
NC 2015 | SHS (2015) | Region VI | Antique | 302350 | Caluya NHS | CALUYA | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8644965.051 |  |  | COMPLETED | 1 |  |  | 060215S00049 | 15GB0162 | 2015-11-25
NC 2015 | K10 (2015) | Region VI | Antique | 115399 | Cansilayan PS | VALDERRAMA | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | REVERTED | 0 |  |  | 060215S00077 | 0602-15-S-00077 | 2015-12-29
NC 2015 | K10 (2015) | Region VI | Antique | 115224 | Canuto B. Pefianco Sr. ES (Madrangca ES) | SAN JOSE (Capital) | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 060215S00062 | 0602-15-S-00062
NC 2015 | K10 (2015) | Region VI | Antique | 115362 | Cato-ogan ES | TOBIAS FORNIER (DAO) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060215S00074 | 0602-15-S-00074 | 2015-11-07 | 2015-11-19 | 2015-11-20
NC 2015 | SHS (2015) | Region VI | Antique | 302351 | Col. Ruperto Abellon NHS | LAUA-AN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8229965.051 |  |  | COMPLETED | 1 |  |  | 060215S00040 | 15GB0179 | 2015-11-28
NC 2015 | SHS (2015) | Region VI | Antique | 302352 | Concepcion L. Cazeñas MS | TOBIAS FORNIER (DAO) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060215S00047 | 15GB0164 | 2015-11-25 | 2015-12-07
NC 2015 | SHS (2015) | Region VI | Antique | 302353 | Diclum NHS | TOBIAS FORNIER (DAO) | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6359337.6381 |  |  | COMPLETED | 1 |  |  | 060215S00011 | 15GB0171 | 2015-11-27 | 2015-12-09 | 2015-12-10
NC 2015 | SHS (2015) | Region VI | Antique | 310710 | Dr. Luis E. Baraquia NHS | SIBALOM | 0 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3484886.575 |  |  | COMPLETED | 1 |  |  | 060215S00045 | 0602-15-S-00045 | 2015-10-31 | 2015-11-12 | 2015-12-16
NC 2015 | SHS (2015) | Region VI | ANTIQUE | 310708 | Eastern Laua-an NHS (Maria NHS) | LAUA-AN | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 060215S00033 | 15GB0084 | 2015-08-18 | 2015-08-30 | 2015-09-02 | 2015-09-30 | 2015-10-22 | FVPS CONSTRUCTION CORP.
NC 2015 | SHS (2015) | Region VI | Antique | 302354 | Egaña NHS | SIBALOM | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 060215S00044 | 15GB0180 | 2015-11-28
NC 2015 | K10 (2015) | Region VI | Antique | 115151 | Fragante ES | PANDAN | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060215S00063 | 15GB0102 | 2015-10-31 | 2015-11-03 | 2015-11-04
NC 2015 | SHS (2015) | Region VI | ANTIQUE | 302355 | Gamad-Sto. Tomas NHS | TOBIAS FORNIER (DAO) | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 060215S00012 | 15GB0076 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-31 | 2015-09-21 | ANJUSH BUILDERS
NC 2015 | SHS (2015) | Region VI | Antique | 310704 | Gen. Leandro Fullon NHS | HAMTIC | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 |  |  | 060215S00043 | 15GB0178 | 2015-11-28
NC 2015 | SHS (2015) | Region VI | Antique | 302357 | Gideon M. Cabigunda MS | SAN REMIGIO | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 060215S00042 | 0602-15-S-00042 | 2015-12-10 | 2015-12-22 | 2015-12-23
NC 2015 | SHS (2015) | Region VI | Antique | 310707 | Gov. Evelio B. Javier MNHS | SAN REMIGIO | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8514965.051 |  |  | REVERTED | 0 |  |  | 060215S00041 | 15GB0177 | 2015-11-28
NC 2015 | SHS (2015) | Region VI | Antique | 302356 | Gov. Julian Fullon Pacificador NS | HAMTIC | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 060215S00035 | 15GB0176 | 2015-12-09 | 2015-12-21 | 2015-12-22
NC 2015 | SHS (2015) | Region VI | Antique | 302358 | Gov. Julio V. Macuja MCHS | HAMTIC | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 9214965.051 |  |  | REVERTED | 0 |  |  | 060215S00015 | 15GB0176 | 2015-11-28 | 2015-12-10 | 2015-12-11
NC 2015 | K10 (2015) | Region VI | Antique | 114988 | Guija-Sabang West ES | BUGASONG | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060215S00065 | 15GB0098 | 2015-10-31 | 2015-11-03 | 2015-11-04
NC 2015 | SHS (2015) | Region VI | Antique | 310701 | Guintas NHS | HAMTIC | 0 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3564886.575 |  |  | COMPLETED | 1 |  |  | 060215S00007 | 0602-15-S-00007 | 2015-10-31 | 2015-11-12 | 2015-11-13
NC 2015 | K10 (2015) | Region VI | Antique | 115368 | Igbangcal ES | TOBIAS FORNIER (DAO) | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060215S00059 | 0602-15-S-00059 | 2015-12-03 | 2015-12-15
NC 2015 | K10 (2015) | Region VI | Antique | 115369 | Igbanos PS | TOBIAS FORNIER (DAO) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | REVERTED | 0 |  |  | 060215S00084 | 0602-15-S-00084 | 2015-11-19
NC 2015 | SHS (2015) | Region VI | Antique | 302359 | Igburi NHS | PATNONGON | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | Terminated | 0 |  |  | 060215S00008 | 15GB0167 | 2015-11-27 | 2015-12-09 | 2015-12-10 |  |  |  | CONTRACT TERMNATED
NC 2015 | SHS (2015) | Region VI | ANTIQUE | 302360 | Igcado NHS | TOBIAS FORNIER (DAO) | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 060215S00003 | 0602-15-S-00003(CNTR) | 2015-09-28 | 2015-10-07 | 2015-10-08
NC 2015 | K10 (2015) | Region VI | Antique | 115317 | Igcocok ES | SIBALOM | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 060215S00071 | 0602-15-S-00071 | 2015-11-14 | 2015-11-26
NC 2015 | SHS (2015) | Region VI | ANTIQUE | 302361 | Igpalge NHS | ANINI-Y | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 060215S00005 | 0602-15-S-00005 | 2015-12-03 | 2015-12-15 | 2015-12-16
NC 2015 | K10 (2015) | Region VI | Antique | 115342 | Importante ES | TIBIAO | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 060215S00058 | 15GB0187 | 2015-11-27
NC 2015 | K10 (2015) | Region VI | Antique | 115262 | Insubuan ES | SAN REMIGIO | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | REVERTED | 0 |  |  | 060215S00078 | 0602-15-S-00078 | 2015-11-21
NC 2015 | K10 (2015) | Region VI | Antique | 115107 | Jaguiquican ES | LAUA-AN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Terminated | 0 |  |  | 060215S00091 | 0602-15-S-00091 | 2015-11-07 | 2015-11-19 | 2015-11-20 |  |  |  | CONTRACT TERMNATED
NC 2015 | K10 (2015) | Region VI | Antique | 115244 | La Union ES | SAN REMIGIO | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060215S00056 | 15GB0101 | 2015-11-14 | 2015-11-26
NC 2015 | K10 (2015) | Region VI | Antique | 115263 | Lapak PS | SAN REMIGIO | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 060215S00067 | 0602-15-S-00067 | 2015-11-19
NC 2015 | SHS (2015) | Region VI | ANTIQUE | 302362 | Laua-an NHS | LAUA-AN | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 060215S00004 | 0602-15-S-00004 | 2015-10-31 | 2015-11-12 | 2015-12-16
NC 2015 | SHS (2015) | Region VI | Antique | 302363 | Libertad NVS | LIBERTAD | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 060215S00009 | 15GB0163 | 2015-11-25 | 2015-12-07 | 2015-12-08
NC 2015 | SHS (2015) | Region VI | Antique | 302364 | Lirio M. Escaño, Sr. NHS | PATNONGON | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Antique | 115303 | Maasin ES | SIBALOM | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 060215S00069 | 0602-15-S-00069 | 2015-11-19
NC 2015 | SHS (2015) | Region VI | Antique | 302365 | Mag-aba NHS | PANDAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 060215S00052 | 0602-15-S-00052 | 2015-11-12 | 2015-11-24 | 2015-11-25
NC 2015 | K10 (2015) | Region VI | Antique | 115046 | Malalison ES | CULASI | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060215S00066 | 0602-15-S-00066 | 2015-11-14 | 2015-11-23 | 2015-11-27
NC 2015 | K10 (2015) | Region VI | Antique | 115117 | Maybunga PS | LAUA-AN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Terminated | 0 |  |  | 060215S00092 | 0602-15-S-00092 | 2015-11-07 | 2015-11-19 | 2015-11-20 |  |  |  | CONTRACT TERMNATED
NC 2015 | SHS (2015) | Region VI | Antique | 302366 | Moscoso-Rios NHS | HAMTIC | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8224965.051 |  |  | COMPLETED | 1 |  |  | 060215S00014 | 0602-15-S-00014(CNTR) | 2015-11-27 | 2015-12-09 | 2015-12-10
NC 2015 | K10 (2015) | Region VI | Antique | 114948 | Nasuli-C ES | ANINI-Y | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2008606.04 |  |  | COMPLETED | 1 |  |  | 060215S00085 | 0602-15-S-00085 | 2015-11-30
NC 2015 | SHS (2015) | Region VI | Antique | 302367 | Northern Antique VS | CULASI | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8324965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VI | Antique | 302367 | Northern Antique VS | CULASI | 0 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7238647.81 |  |  | Terminated | 0 | [10 empty] | CONTRACT TERMNATED
NC 2015 | SHS (2015) | Region VI | Antique | 302368 | Northern Bugasong NHS | BUGASONG | 0 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2650828.124 |  |  | COMPLETED | 1 |  |  | 060215S00027 | 15GB0135 | 2015-11-12 | 2015-11-24 | 2015-11-25
NC 2015 | SHS (2015) | Region VI | Antique | 310709 | Northern Bugasong NHS Annex - Pangalcagan Campus | BUGASONG | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6339337.6381 |  |  | COMPLETED | 1 |  |  | 060215S00025 | 15GB0172 | 2015-11-27 | 2015-12-09
NC 2015 | K10 (2015) | Region VI | Antique | 115284 | P. Javier PS | SEBASTE | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | Terminated | 0 |  |  | 060215S00072 | 0602-15-S-00072 | 2015-11-14 | 2015-11-26 | 2015-11-27 |  |  |  | CONTRACT TERMNATED
NC 2015 | SHS (2015) | Region VI | Antique | 302369 | Pandan NVHS | PANDAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060215S00054 | 15GB0185 | 2015-11-28 | 2015-12-10 | 2015-12-11
NC 2015 | SHS (2015) | Region VI | Antique | 302370 | Pangpang NHS | SIBALOM | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1 |  |  | 060215S00006 | 0602-15-S-00006 | 2015-11-17 | 2015-11-25 | 2015-12-18
NC 2015 | SHS (2015) | Region VI | Antique | 302371 | Pascual M. Osuyos MS | TOBIAS FORNIER (DAO) | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6349337.6381 |  |  | COMPLETED | 1 |  |  | 060215S00019 | 15GB0170 | 2015-11-27 | 2015-12-09
NC 2015 | SHS (2015) | Region VI | Antique | 302372 | Patria NS | PANDAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060215S00053 | 15GB0166 | 2015-11-27 | 2015-12-09 | 2015-12-10
NC 2015 | SHS (2015) | Region VI | Antique | 302373 | Pis-anan NHS | SIBALOM | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060215S00018 | 0602-15-S-00018 | 2015-11-12 | 2015-11-24
NC 2015 | K10 (2015) | Region VI | Antique | 115384 | Quezon PS | TOBIAS FORNIER (DAO) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060215S00075 | 0602-15-S-00075 | 2015-11-19
NC 2015 | K10 (2015) | Region VI | Antique | 115249 | Ramon Magsaysay ES | SAN REMIGIO | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2882592.44 |  |  | COMPLETED | 1 |  |  | 060215S00095 | 0602-15-S-00095 | 2015-11-21
NC 2015 | K10 (2015) | Region VI | Antique | 115270 | Rizal ES | SAN REMIGIO | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | REVERTED | 0 |  |  | 060215S00068 | 0602-15-S-00068 | 2015-11-19
NC 2015 | K10 (2015) | Region VI | Antique | 115406 | San Agustin ES | VALDERRAMA | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | REVERTED | 0 |  |  | 060215S00060 | 15GB0099 | 2015-10-22 | 2015-11-03 | 2015-11-27
NC 2015 | SHS (2015) | Region VI | Antique | 302375 | San Pedro NHS | SAN JOSE (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 060215S00016 | 0602-15-S-00016(CNTR) | 2015-11-28 | 2015-12-10
NC 2015 | SHS (2015) | Region VI | Antique | 302376 | San Roque-Ezpeleta NHS | ANINI-Y | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8714965.051 |  |  | COMPLETED | 1 |  |  | 060215S00017 | 15GB0184 | 2015-11-27 | 2015-12-09
NC 2015 | SHS (2015) | Region VI | Antique | 302377 | Sebaste HS | SEBASTE | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 060215S00013 | 0602-15-S-0001(CNTR) | 2015-11-12 | 2015-11-24 | 2015-11-25
NC 2015 | SHS (2015) | Region VI | Antique | 310705 | Semirara NHS | CALUYA | 0 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10937131.51 |  |  | COMPLETED | 1 |  |  | 060215S00031
NC 2015 | SHS (2015) | Region VI | Antique | 310703 | Sibalom NHS | SIBALOM | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 060215S00021 | 15GB0174 | 2015-11-27 | 2015-12-10 | 2015-12-11
NC 2015 | K10 (2015) | Region VI | Antique | 115021 | Sibato ES | CALUYA | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2238606.04 |  |  | COMPLETED | 1 |  |  | 060215S00086 | 0602-15-S-00086 | 2015-11-21
NC 2015 | K10 (2015) | Region VI | Antique | 115022 | Sibay ES | CALUYA | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2238606.04 |  |  | COMPLETED | 1 |  |  | 060215S00082 | 0602-15-S-00082 | 2015-11-21
NC 2015 | SHS (2015) | Region VI | Antique | 310706 | Sibay NHS | CALUYA | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6669337.6381 |  |  | COMPLETED | 1 |  |  | 060215S00020 | 15GB0154 | 2015-11-21 | 2015-12-03 | 2015-12-04
NC 2015 | SHS (2015) | Region VI | Antique | 302378 | Sido-San Juan NHS | SIBALOM | 0 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 |  |  | 060215S00022 | 15GB0134 | 2015-11-12 | 2015-11-24
NC 2015 | SHS (2015) | Region VI | Antique | 302379 | Southern Bugasong NHS | BUGASONG | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 060215S00023 | 15GB0186 | 2015-11-28 | 2015-12-10 | 2015-12-11
NC 2015 | SHS (2015) | Region VI | ANTIQUE | 302380 | Sta. Ana NHS | PANDAN | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 060215S00051 | 15GB0086 | 2015-08-18 | 2015-08-30 | 2015-09-02 | 2015-09-16 | 2015-09-21 | ANJUSH BUILDERS
NC 2015 | SHS (2015) | Region VI | Antique | 302381 | Sta. Justa NHS | TIBIAO | 0 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3564886.575 |  |  | Terminated | 0 |  |  | 060215S00024 | 0602-15-S-00024 | 2015-10-31 | 2015-11-12 | 2015-11-13 |  |  |  | CONTRACT TERMNATED
NC 2015 | SHS (2015) | Region VI | Antique | 310702 | Tario Lim MHS | TIBIAO | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 060215S00026 | 0602-15-S-00026 | 2015-11-12 | 2015-11-24
NC 2015 | K10 (2015) | Region VI | Antique | 115353 | Tigbaboy PS | TIBIAO | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Terminated | 0 |  |  | 060215S00073 | 0602-15-S-0007 | 2015-11-07 | 2015-11-19 | 2015-11-20 |  |  |  | CONTRACT TERMNATED
NC 2015 | SHS (2015) | Region VI | ANTIQUE | 302382 | Tinogboc NHS | CALUYA | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 060215S00002 | 15GB0078 | 2015-09-04 | 2015-09-15 | 2015-09-16 | 2015-11-03 | 2015-12-01 | ANJUSH BUILDERS
NC 2015 | K10 (2015) | Region VI | Antique | 115188 | Tobias Fornier ES | PATNONGON | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060215S00094 | 0602-15-S-00094 | 2015-12-05 | 2015-12-17 | 2015-12-18
NC 2015 | SHS (2015) | Region VI | Antique | 302383 | Union NHS | LIBERTAD | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6347337.6381 |  |  | COMPLETED | 1 |  |  | 060215S00037 | 15Gb0161 | 2015-11-25 | 2015-12-07 | 2015-12-08
NC 2015 | SHS (2015) | Region VI | Antique | 302384 | Valderrama NHS | VALDERRAMA | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8239965.051 |  |  | COMPLETED | 1 |  |  | 060215S00029 | 15GB0183 | 2015-11-27 | 2015-12-09 | 2015-12-10
NC 2015 | K10 (2015) | Region VI | Antique | 178504 | Valentine Saydoquis MS | SIBALOM | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | REVERTED | 0 |  |  | 060215S00081 | 0602-15-S-00081 | 2015-11-19
NC 2015 | K10 (2015) | Region VI | Antique | 178505 | Walker-Libodon PS | SAN REMIGIO | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2288606.04 |  |  | REVERTED | 0 |  |  | 060215S00079 | 0602-15-S-00079 | 2015-11-21
NC 2015 | K10 (2015) | Region VI | Capiz | 115644 | Ambilay ES | PANITAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060315S00037 | 15GD0067-3 | 2015-10-22 | 2015-10-08 | 2015-10-22 | 2015-10-30 | 2015-11-13 | M.R. VARGAS CONSTRUCTION
NC 2015 | K10 (2015) | Region VI | Capiz | 115550 | Balighot ES | MA-AYON | 1 | 1 | 8 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060315S00012 | 15GD0046 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-31 | 2015-08-14 | PANAY EAST COAST CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VI | Capiz | 302391 | Capiz National High School | ROXAS CITY (Capital) | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 27252469.42 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Capiz | 302391 | Capiz National High School | ROXAS CITY (Capital) | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Capiz | 302412 | East Villaflores NHS | MA-AYON | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 7019338 |  |  | COMPLETED | 1 |  |  | 060315S00021 | 15GD0067-1 | 2015-10-22 | 2015-10-08 | 2015-10-22 | 2015-10-30 | 2015-11-13 | M.R. VARGAS CONSTRUCTION
NC 2015 | K10 (2015) | Region VI | Capiz | 179008 | Epifania P. Bernas Elementary School | PILAR | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 060315S00034 | 15GD0065-1 | 2015-10-22 | 2015-10-08 | 2015-10-22 | 2015-10-30 | 2015-11-13 | ROCK 101 CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region VI | Capiz | 115635 | Navitas ES | PANAY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 060315S00038
NC 2015 | SHS (2015) | Region VI | Capiz | 302420 | Pontevedra NHS | PONTEVEDRA | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 2 | 31217890.27 |  |  | COMPLETED | 1 |  |  | 060315S00004 | 15GD0062 | 2015-10-07 | 2015-10-08 | 2015-10-22 | 2015-10-30 | 2015-11-13 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2015 | K10 (2015) | Region VI | Capiz | 115571 | Quevedo ES | MA-AYON | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060315S00015 | 15GD0047 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-31 | 2015-08-14 | ROPRIM CONSTRUCTION
NC 2015 | K10 (2015) | Region VI | Capiz | 115682 | San Silvestre ES | PILAR | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 060315S00013 | 15GD0048 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-31 | 2015-08-14 | ROCK 101 CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region VI | Capiz | 115723 | Sangkal ES | PRESIDENT ROXAS | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 060315S00035
NC 2015 | K10 (2015) | Region VI | Capiz | 115639 | Tanza Sur ES | PANAY | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060315S00014 | 15GD0049 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-31 | 2015-08-14 | ROLA CONSTRUCTION
NC 2015 | K10 (2015) | Region VI | Capiz | 115686 | Tomas Abelita Sr. ES | PILAR | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 060315S00036 | 15GD0065-2 | 2015-10-22 | 2015-10-08 | 2015-10-22 | 2015-10-30 | 2015-11-13 | ROCK 101 CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region VI | Capiz | 115577 | Tuburan ES | MA-AYON | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 060315S00039 | 15GD0066 | 2015-10-22 | 2015-10-08 | 2015-10-22 | 2015-10-30 | 2015-11-13 | EDLY CONSTRUCTION
NC 2015 | SHS (2015) | Region VI | Capiz | 310811 | YATING NATIONAL HIGH SCHOOL | PILAR | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 12988675 |  |  | COMPLETED | 1 |  |  | 060315S00025 | 15GD0071 | 2015-10-30 | 2015-10-23 | 2015-11-05 | 2015-11-16 | 2015-11-27 | M.R. VARGAS CONSTRUCTION
NC 2015 | K10 (2015) | Region VI | Capiz | 115468 | Agbatuan ES | DUMARAO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060315S00011 | 15G00181 | 2015-07-08 | 2015-07-09 | 2015-07-24 | 2015-08-05 | 2015-08-13 | MBM CONSTRUCTION
NC 2015 | K10 (2015) | Region VI | Capiz | 115599 | Angelo Llorente ES (bunga es) | MAMBUSAO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 060315S00033 | 15G00223 | 2015-08-10 | 2015-08-11 | 2015-08-26 | 2015-11-19 | 2015-11-27 | CLY - ABC BUILDERS
NC 2015 | K10 (2015) | Region VI | Capiz | 115805 | Arisgal PS | TAPAZ | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 060315S00009 | 15G00199 | 2015-07-23 | 2015-07-24 | 2015-08-06 | 2015-08-17 | 2015-08-27 | MBM CONSTRUCTION
NC 2015 | SHS (2015) | Region VI | Capiz | 302385 | Arturo Jugo NHS | DAO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 060315S00016 | 15G00210 | 2015-08-10 | 2015-08-11 | 2015-08-26 | 2015-10-20 | 2015-10-29 | CLY - ABC BUILDERS
NC 2015 | SHS (2015) | Region VI | Capiz | 310801 | Bagong Barrio NHS | TAPAZ | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 060315S00019 | 15G00212 | 2015-08-10 | 2015-08-11 | 2015-08-26 | 2015-10-20 | 2015-10-29 | CLY - ABC BUILDERS
NC 2015 | K10 (2015) | Region VI | Capiz | 302386 | Bungsuan NHS | DUMARAO | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Capiz | 302386 | Bungsuan NHS | DUMARAO | 2 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 5 | 12771310 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Capiz | 302389 | Camburanan NHS | TAPAZ | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 060315S00020 | 15G00211 | 2015-08-10 | 2015-08-11 | 2015-08-26 | 2015-10-20 | 2015-10-29 | CLY - ABC BUILDERS
NC 2015 | SHS (2015) | Region VI | Capiz | 311705 | Candelaria NHS- Roxas Ext. | TAPAZ | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 060315S00018 | 15G00214 | 2015-08-10 | 2015-08-11 | 2015-08-26 | 2015-10-20 | 2015-10-29 | PANAY EAST COAST CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VI | Capiz | 302401 | Concepcion Castro Garcia NHS (Dumalag NHS) Sta. Cruz | DUMALAG | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 5 | 10877343 |  |  | COMPLETED | 1 |  |  | 060315S00026 | 15G00215 | 2015-08-10 | 2015-08-11 | 2015-08-26 | 2015-10-20 | 2015-10-29 | MBM CONSTRUCTION
NC 2015 | K10 (2015) | Region VI | Capiz | 115480 | Cubi PS | DUMARAO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 060315S00028 | 15G00222 | 2015-08-10 | 2015-08-11 | 2015-08-26 | 2015-11-19 | 2015-11-27 | CLY - ABC BUILDERS
NC 2015 | K10 (2015) | Region VI | Capiz | 115811 | Daan Norte ES | TAPAZ | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2388606.04 |  |  | COMPLETED | 1 |  |  | 060315S00030 | 15G00227 | 2015-08-13 | 2015-08-25 | 2015-08-26
NC 2015 | K10 (2015) | Region VI | Capiz | 115439 | Lacaron ES | DAO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 060315S00041 | 15G00221 | 2015-08-10 | 2015-08-11 | 2015-08-26 | 2015-11-19 | 2015-11-27 | CLY - ABC BUILDERS
NC 2015 | K10 (2015) | Region VI | Capiz | 302407 | Macario Delfin Bermejo NHS | JAMINDAN | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Capiz | 302407 | Macario Delfin Bermejo NHS | JAMINDAN | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 5 | 10877343 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Capiz | 310815 | Mianay NHS | SIGMA | 2 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 7 | 11027343 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Capiz | 310815 | Mianay NHS | SIGMA | 2 | 1 | 12 | 2STY12CL | 2015 SHS BATCH 5 | 14579217 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Capiz | 115814 | Roxas ES | TAPAZ | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2188606.04 |  |  | COMPLETED | 1 |  |  | 060315S00040 | 15G00228 | 2015-08-10 | 2015-08-11 | 2015-08-26 | 2015-11-19 | 2015-11-27 | PANAY EAST COAST CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VI | Capiz | 310808 | SAN ANTONIO NATIONAL HIGH SCHOOL | CUARTERO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 060315S00017 | 15G00213 | 2015-08-10 | 2015-08-11 | 2015-08-26 | 2015-10-20 | 2015-10-29 | CLY - ABC BUILDERS
NC 2015 | K10 (2015) | Region VI | Capiz | 115751 | Simeon Bidiones Elementary School | SIGMA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060315S00031 | 15G00225 | 2015-08-10 | 2015-08-11 | 2015-08-26 | 2015-11-19 | 2015-11-27 | MJ BARCELONA CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region VI | Capiz | 115796 | Siya PS | TAPAZ | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2388606.04 |  |  | COMPLETED | 1 |  |  | 060315S00027 | 15G00226 | 2015-08-13 | 2015-08-25 | 2015-08-26
NC 2015 | K10 (2015) | Region VI | Capiz | 115817 | Sta. Ana ES | TAPAZ | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060315S00008 | 15G00182 | 2015-07-08 | 2015-07-09 | 2015-07-24 | 2015-08-10 | 2015-08-18 | MBM CONSTRUCTION
NC 2015 | K10 (2015) | Region VI | Capiz | 115818 | Tabon Elementary School | TAPAZ | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 4317968.78 |  |  | COMPLETED | 1 |  |  | 060315S00029 | 15G00229 | 2015-08-10 | 2015-08-11 | 2015-08-26 | 2015-11-19 | 2015-11-27 | KENBE CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region VI | Capiz | 115746 | WENCESLAO ONAS ELEM. SCHOOL | SAPI-AN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 060315S00032 | 15G00224 | 2015-08-10 | 2015-08-11 | 2015-08-26 | 2015-11-19 | 2015-11-27 | MJ BARCELONA CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region VI | Guimaras | 115899 | Paaralan ng Buhay ng Don Domingo Granada | NUEVA VALENCIA | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 060415S00017 | 0604-15-S-00017 | 2015-10-28 | 2015-10-29 | 2015-11-10 | 2015-11-23 | 2015-12-02 | ALJ CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region VI | Iloilo | 302509 | Iloilo NHS | ILOILO CITY (Capital) | 0 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 302445 | Alejandro Firmeza MNHS | MIAGAO | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 2863026 |  |  | COMPLETED | 1 |  |  | 060515S00135 | 15-GF-0081 | 2015-12-04 | 2015-12-03 | 2015-12-17
NC 2015 | K10 (2015) | Region VI | Iloilo | 116578 | Alimodias ES | MIAGAO | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060515S00086 | 15-GF-0048 | 2015-07-24 | 2015-07-23 | 2015-08-07 | 2015-08-19 | 2015-09-02 | PETRONAL BUILDERS
NC 2015 | SHS (2015) | Region VI | Iloilo | 311024 | Bagacay National High School | TIGBAUAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2014161 |  |  | COMPLETED | 1 |  |  | 060515S00119 | 15-GF-0080 | 2015-12-04 | 2015-12-03 | 2015-12-17
NC 2015 | K10 (2015) | Region VI | Iloilo | 116368 | Bagay ES | IGBARAS | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060515S00085 | 15-GF-0046 | 2015-07-24 | 2015-07-23 | 2015-08-07 | 2015-08-19 | 2015-09-02 | PETRONAL BUILDERS
NC 2015 | K10 (2015) | Region VI | Iloilo | 302459 | Barroc NHS | TIGBAUAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060515S00091 | 15-GF-0057 | 2015-08-11
NC 2015 | K10 (2015) | Region VI | Iloilo | 116722 | Bayunan ES | SAN JOAQUIN | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 060515S00088 | 15-GF-0050 | 2015-07-24 | 2015-07-23 | 2015-08-07 | 2015-08-19 | 2015-09-02 | PETRONAL BUILDERS
NC 2015 | SHS (2015) | Region VI | Iloilo | 302467 | Botong-Cabanbanan NHS | OTON | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8365252 |  |  | REVERTED | 0 |  |  | 060515S00136 | 15-GF-0084 | 2015-12-04 | 2015-12-03 | 2015-12-17
NC 2015 | SHS (2015) | Region VI | Iloilo | 302479 | Camangahan National High School | GUIMBAL | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8275417 |  |  | REVERTED | 0 |  |  | 060515S00131 | 15-GF-0082 | 2015-12-04 | 2015-12-03 | 2015-12-17
NC 2015 | SHS (2015) | Region VI | Iloilo | 302488 | Dapdap NHS | TIGBAUAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6470558 |  |  | COMPLETED | 1 |  |  | 060515S00134 | 15-GF-0074 | 2015-11-30 | 2015-11-27 | 2015-12-15
NC 2015 | K10 (2015) | Region VI | Iloilo | 116582 | Diday ES | MIAGAO | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060515S00087 | 15-GF-0049 | 2015-07-24 | 2015-07-23 | 2015-08-07 | 2015-08-19 | 2015-09-02 | S.T. SALCEDO CONSTRUCTION CORP.(FORMERLY: SHAK CONSTRUCTION & SUPPLY)
NC 2015 | SHS (2015) | Region VI | Iloilo | 302499 | Escalantera NHS | SAN JOAQUIN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6419338 |  |  | COMPLETED | 1 |  |  | 060515S00139 | 15-GF-0078 | 2015-11-30 | 2015-11-27 | 2015-12-15
NC 2015 | K10 (2015) | Region VI | Iloilo | 116728 | Igcadlum PS | SAN JOAQUIN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 060515S00172 | 15-GF-0065 | 2015-10-22 | 2015-10-22 | 2015-11-09 | 2015-11-20 | 2015-12-01 | KJC CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VI | Iloilo | 302515 | Kirayan NHS | MIAGAO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6369526 |  |  | COMPLETED | 1 |  |  | 060515S00133 | 15-GF-0076 | 2015-11-30 | 2015-11-27 | 2015-12-15
NC 2015 | SHS (2015) | Region VI | Iloilo | 311005 | Lanag Norte NHS | TUBUNGAN | 1 | 1 | 6 | 1STY6CL (Toilet Attached) | 2015 SHS BATCH 5 | 6473457 |  |  | REVERTED | 0 |  |  | 060515S00137 | 15-GF-0083 | 2015-12-04 | 2015-12-03 | 2015-12-17
NC 2015 | K10 (2015) | Region VI | Iloilo | 116832 | Lino Flores ES | TIGBAUAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060515S00090 | 15-GF-0052 | 2015-07-24 | 2015-07-23 | 2015-08-07 | 2015-08-19 | 2015-09-02 | PETRONAL BUILDERS
NC 2015 | K10 (2015) | Region VI | Iloilo | 116850 | Mayang PS | TUBUNGAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1948606.04 |  |  | COMPLETED | 1 |  |  | 060515S00176 | 15-GF-0064 | 2015-10-22 | 2015-10-22 | 2015-11-09 | 2015-11-20 | 2015-12-01 | BILLENA CONSTRUCTION
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302531 | Miagao NHS | MIAGAO | 1 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 5179098.54 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Iloilo | 116571 | Miranda ES | MIAGAO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1959306.04 |  |  | COMPLETED | 1 |  |  | 060515S00170 | 15-GF-0063 | 2015-10-23 | 2015-10-22 | 2015-11-09 | 2015-11-20 | 2015-12-01 | BILLENA CONSTRUCTION
NC 2015 | K10 (2015) | Region VI | Iloilo | 116737 | Montinola ES | SAN JOAQUIN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | REVERTED | 0 |  |  | 060515S00173 | 15-GF-0069 | 2015-10-22 | 2015-10-22 | 2015-12-28
NC 2015 | K10 (2015) | Region VI | Iloilo | 116382 | Mulangan ES | IGBARAS | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 060515S00083 | 15-GF-0047 | 2015-07-24 | 2015-07-20 | 2015-08-07 | 2015-08-19 | 2015-09-02 | JHJ CONSTRUCTION
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302542 | Oton National High School | OTON | 1 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 5079098.54 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Iloilo | 116365 | P.G. Garin MES | GUIMBAL | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | REVERTED | 0 |  |  | 060515S00169 | 15-GF-0067 | 2015-10-23 | 2015-10-22 | 2015-11-09 | 2015-11-20 | 2015-12-01 | BILLENA CONSTRUCTION
NC 2015 | K10 (2015) | Region VI | Iloilo | 116627 | Pakiad ES | OTON | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060515S00171 | 15-GF-0068 | 2015-10-22 | 2015-10-22 | 2015-11-09 | 2015-11-20 | 2015-12-01 | BILLENA CONSTRUCTION
NC 2015 | SHS (2015) | Region VI | Iloilo | 302548 | Parara NHS | TIGBAUAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6379572 |  |  | COMPLETED | 1 |  |  | 060515S00124 | 15-GF-0077 | 2015-11-30 | 2015-11-27 | 2015-12-15
NC 2015 | SHS (2015) | Region VI | Iloilo | 302549 | Particion NHS | GUIMBAL | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 060515S00194 | 15-GF-0079 | 2015-11-30 | 2015-11-27
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302566 | SAN JOAQUIN SCHOOL OF FISHERIES | SAN JOAQUIN | 1 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 5229098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 302571 | Sinogbuhan NHS | SAN JOAQUIN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6369338 |  |  | COMPLETED | 1 |  |  | 060515S00138 | 15-GF-0075 | 2015-11-30 | 2015-11-27 | 2015-12-15
NC 2015 | K10 (2015) | Region VI | Iloilo | 116838 | Sipitan Elementary School | Tigbauan | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 060515S00175 | 15-GF-0070 | 2015-10-22 | 2015-10-22 | 2015-11-09 | 2015-11-20 | 2015-12-01 | MJ BARCELONA CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region VI | Iloilo | 311013 | Supt. Arsenio M. Napud MHS | MIAGAO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6389579 |  |  | COMPLETED | 1 |  |  | 060515S00105 | 15-GF-0073 | 2015-11-30 | 2015-11-27 | 2015-12-15
NC 2015 | K10 (2015) | Region VI | Iloilo | 116746 | TAPIKAN ES | SAN JOAQUIN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060515S00174 | 15-GF-0066 | 2015-10-22 | 2015-10-22 | 2015-11-09 | 2015-11-20 | 2015-12-01 | KJC CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region VI | Iloilo | 116748 | Toog-Tiglawa ES | SAN JOAQUIN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060515S00089 | 15-GF-0051 | 2015-07-24 | 2015-07-23 | 2015-08-07 | 2015-08-19 | 2015-09-02 | PETRONAL BUILDERS
NC 2015 | K10 (2015) | Region VI | Iloilo | 116856 | Victoria ES | TUBUNGAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060515S00092 | 15-GF-0053 | 2015-07-24 | 2015-07-23 | 2015-08-07 | 2015-08-19 | 2015-09-02 | PETRONAL BUILDERS
NC 2015 | SHS (2015) | Region VI | Iloilo | 311017 | Bancal NHS | ALIMODIAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6439838 |  |  | COMPLETED | 1 |  |  | 060515S00132 | 0605-15-S-00132 | 2015-12-29
NC 2015 | K10 (2015) | Region VI | Iloilo | 311031 | BAYAG NATIONAL HIGH SCHOOL | LEON | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060515S00093 | 15GI0033 | 2015-08-05 | 2015-08-06 | 2015-08-18 | 2015-09-08 | 2015-09-18 | MBM CONSTRUCTION
NC 2015 | SHS (2015) | Region VI | Iloilo | 302466 | Bololacao NHS | NEW LUCENA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6569684 |  |  | COMPLETED | 1 |  |  | 060515S00129 | 0605-15-S-00129 | 2015-12-29
NC 2015 | SHS (2015) | Region VI | Iloilo | 302470 | Buga National High School | LEON | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6469938 |  |  | COMPLETED | 1 |  |  | 060515S00128 | 0605-15-S-00128 | 2015-12-29
NC 2015 | K10 (2015) | Region VI | Iloilo | 116469 | Bungso-an Elementary School | LEGANES | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 060515S00177 | 15GI0045 | 2015-10-05 | 2015-10-07 | 2015-10-19 | 2015-10-28 | 2015-11-06 | PANAY EAST COAST CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VI | Iloilo | 311028 | Dalid National High School | ALIMODIAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6569836 |  |  | COMPLETED | 1 |  |  | 060515S00117 | 0605-15-S-00117 | 2015-12-21
NC 2015 | K10 (2015) | Region VI | Iloilo | 116806 | Gen.Martin T. Delgado ES | SANTA BARBARA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 060515S00102 | 15GI0056 | 2015-10-15 | 2015-10-15 | 2015-10-28 | 2015-11-13 | 2015-11-20 | CLY - ABC BUILDERS
NC 2015 | SHS (2015) | Region VI | Iloilo | 302503 | Gines NHS | ALIMODIAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6639593 |  |  | COMPLETED | 1 |  |  | 060515S00127 | 0605-15-S-00127 | 2015-12-29
NC 2015 | SHS (2015) | Region VI | Iloilo | 302513 | Jelicuon-Cabugao NHS | NEW LUCENA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2058943 |  |  | COMPLETED | 1 |  |  | 060515S00126 | 0605-15-S-00126 | 2015-12-29
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302520 | Leganes National High School | LEGANES | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2520049.27 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302522 | Leon NHS | LEON | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2479549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Iloilo | 116510 | Manampunay Primary School | Leon I | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 060515S00164 | 15GI0046 | 2015-10-05 | 2015-10-07 | 2015-10-19 | 2015-10-28 | 2015-11-06 | CHAMPION BUILDERS AND SUPPLY
NC 2015 | K10 (2015) | Region VI | Iloilo | 180049 | Miac-ac Primary School | LEON | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 060515S00178
NC 2015 | SHS (2015) | Region VI | Iloilo | 302539 | New Lucena National Comprehensive High School | NEW LUCENA | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10997342.5917 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 302539 | New Lucena National Comprehensive High School | NEW LUCENA | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 302539 | New Lucena National Comprehensive High School | NEW LUCENA | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 302540 | New Lucena NHS | NEW LUCENA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6670230 |  |  | COMPLETED | 1 |  |  | 060515S00125 | 0605-15-S-00125 | 2015-12-29
NC 2015 | SHS (2015) | Region VI | Iloilo | 302550 | Pavia National High School | PAVIA | 2 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 2 | 35806257.14 |  |  | REVERTED | 0 |  |  | 060515S00059
NC 2015 | SHS (2015) | Region VI | Iloilo | 302551 | PAYAO NHS | SANTA BARBARA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6439658 |  |  | COMPLETED | 1 |  |  | 060515S00121 | 0605-15-S-00121 | 2015-12-29
NC 2015 | SHS (2015) | Region VI | Iloilo | 302573 | Sta. Barbara NCHS | SANTA BARBARA | 2 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 5 | 30362656 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302573 | Sta. Barbara NCHS | SANTA BARBARA | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 311021 | TACUYONG SUR NHS | LEON | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6489936 |  |  | COMPLETED | 1 |  |  | 060515S00114 | 0605-15-S-00114 | 2015-10-30
NC 2015 | K10 (2015) | Region VI | Iloilo | 180020 | Tina-an Norte ES | LEON | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 060515S00192 | 15GI0047 | 2015-10-05 | 2015-10-07 | 2015-10-19 | 2015-10-28 | 2015-11-06 | G. UY CONSTRUCTION
NC 2015 | SHS (2015) | Region VI | Iloilo | 302585 | Zarraga NHS | ZARRAGA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8345465.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 302585 | Zarraga NHS | ZARRAGA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 302441 | Abangay NHS | JANIUAY | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6819738 |  |  | COMPLETED | 1 |  |  | 060515S00122 | 15GG0223 | 2015-11-23 | 2015-11-26 | 2015-12-08 | 2015-12-22
NC 2015 | K10 (2015) | Region VI | Iloilo | 116387 | Aguingay ES | JANIUAY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 060515S00182 | 15GG0221 | 2015-11-16 | 2015-11-19 | 2015-12-01 | 2015-12-15
NC 2015 | K10 (2015) | Region VI | Iloilo | 116443 | AGUSTIN GALLEGO MEMORIAL ES | LAMBUNAO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060515S00187 | 15GG0220 | 2015-11-16 | 2015-11-19 | 2015-12-01 | 2015-12-23
NC 2015 | SHS (2015) | Region VI | Iloilo | 302444 | Alcarde Gustilo Mem. National High School | CALINOG | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 2993218 |  |  | COMPLETED | 1 |  |  | 060515S00104 | 15GG0224 | 2015-11-23 | 2015-11-26 | 2015-12-08 | 2015-12-21
NC 2015 | SHS (2015) | Region VI | Iloilo | 302447 | Ambrosio Maido MNHS | CABATUAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2099014 |  |  | COMPLETED | 1 |  |  | 060515S00120 | 15GG0225 | 2015-11-23 | 2015-11-26 | 2015-12-08 | 2015-12-22
NC 2015 | K10 (2015) | Region VI | Iloilo | 116597 | Armada-Pelaez MES | MINA | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060515S00190 | 15GG0219 | 2015-11-16 | 2015-11-19 | 2015-12-01 | 2015-12-22
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302465 | Bingawan NHS | BINGAWAN | 3 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4979098.54 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Iloilo | 116447 | Bontoc Elementary School | LAMBUNAO | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060515S00097 | 15GG0120 | 2015-07-09 | 2015-07-20 | 2015-07-21 | 2015-08-19 | 2015-10-12 | KENBE CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region VI | Iloilo | 116448 | Cabatangan PS | LAMBUNAO | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060515S00098 | 15GG0121 | 2015-07-09 | 2015-07-20 | 2015-07-21 | 2015-08-19 | 2015-11-18 | GGMU CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region VI | Iloilo | 302473 | Cabatuan NCHS | CABATUAN | 3 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 11177342.5917 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302473 | Cabatuan NCHS | CABATUAN | 3 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Iloilo | 116449 | Cabugao ES | LAMBUNAO | 3 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060515S00099 | 15GG0122 | 2015-07-09 | 2015-07-20 | 2015-07-21 | 2015-08-20 | 2015-09-22 | M.R. VARGAS CONSTRUCTION
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302477 | Calinog NCHS | CALINOG | 3 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2879549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Iloilo | 116538 | Camansi PS | MAASIN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 060515S00188 | 15GG0222 | 2015-11-16 | 2015-11-19 | 2015-12-01 | 2015-12-22
NC 2015 | K10 (2015) | Region VI | Iloilo | 116391 | Canauillan Elementary School | Janiuay I | 3 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 4127212.08 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Iloilo | 116653 | Igang ES | POTOTAN | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060515S00101 | 15GG0127 | 2015-07-09 | 2015-07-20 | 2015-07-21 | 2015-08-20 | 2015-11-27 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE
NC 2015 | SHS (2015) | Region VI | Iloilo | 302512 | Janiuay NCHS | JANIUAY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8664965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 302512 | Janiuay NCHS | JANIUAY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 302512 | Janiuay NCHS | JANIUAY | 3 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 2 | 18222268.79 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302512 | Janiuay NCHS | JANIUAY | 3 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 302514 | Jose Facultad MNHS | POTOTAN | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6829943 |  |  | COMPLETED | 1 |  |  | 060515S00106 | 15GG0226 | 2015-11-23 | 2015-11-26 | 2015-12-08 | 2015-12-22
NC 2015 | SHS (2015) | Region VI | Iloilo | 311025 | Jovita Alfaras Rivera NHS | BINGAWAN | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6540198 |  |  | COMPLETED | 1 |  |  | 060515S00113 | 15GG0231 | 2015-11-23 | 2015-11-26 | 2015-12-08 | 2015-12-22
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302517 | Lambunao NHS | LAMBUNAO | 3 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 5279098.54 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Iloilo | 116434 | Madarag ES | LAMBUNAO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060515S00186 | 15GG0217 | 2015-11-16 | 2015-11-19 | 2015-12-01 | 2015-12-22
NC 2015 | K10 (2015) | Region VI | Iloilo | 116190 | Marandig PS | CALINOG | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 060515S00095 | 15GG0118 | 2015-07-09 | 2015-07-20 | 2015-07-21 | 2015-08-18 | 2015-11-18 | GGMU CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region VI | Iloilo | 116129 | Moises Cuello PS | CABATUAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060515S00179 | 15GG0216 | 2015-11-16 | 2015-11-19 | 2015-12-01 | 2015-12-15
NC 2015 | K10 (2015) | Region VI | Iloilo | 116417 | Monte Magapa ES | JANIUAY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 060515S00185 | 15GG0215 | 2015-11-16 | 2015-11-19 | 2015-12-02 | 2015-12-15
NC 2015 | SHS (2015) | Region VI | Iloilo | 302546 | Palanguia National High School | POTOTAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8465621 |  |  | COMPLETED | 1 |  |  | 060515S00118 | 15GG0227 | 2015-11-23 | 2015-11-26 | 2015-12-08 | 2015-12-22
NC 2015 | K10 (2015) | Region VI | Iloilo | 116552 | Panalian ES | MAASIN | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060515S00084 | 15GG0126 | 2015-07-09 | 2015-07-20 | 2015-07-21 | 2015-08-19 | 2015-09-25 | J.C. ALBASON BUILDERS AND SUPPLY
NC 2015 | K10 (2015) | Region VI | Iloilo | 116462 | Petronio Leal MES | LAMBUNAO | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060515S00100 | 15GG0123 | 2015-07-09 | 2015-07-20 | 2015-07-21 | 2015-08-18 | 2015-10-21 | LEGACY CONSTRUCTION
NC 2015 | SHS (2015) | Region VI | Iloilo | 302559 | Quiling NHS | MAASIN | 3 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 4188369 |  |  | COMPLETED | 1 |  |  | 060515S00130 | 15GG0228 | 2015-11-23 | 2015-11-26 | 2015-12-08 | 2015-12-21
NC 2015 | SHS (2015) | Region VI | Iloilo | 302560 | Quipot National High School | JANIUAY | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6790085 |  |  | COMPLETED | 1 |  |  | 060515S00116 | 15GG0229 | 2015-11-23 | 2015-11-26 | 2015-12-08 | 2015-12-21
NC 2015 | K10 (2015) | Region VI | Iloilo | 116152 | Salacay ES | CABATUAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1968606.04 |  |  | COMPLETED | 1 |  |  | 060515S00166 | 15GG0214 | 2015-11-16 | 2015-11-19 | 2015-12-01 | 2015-12-10
NC 2015 | K10 (2015) | Region VI | Iloilo | 116466 | San Gregorio ES | LAMBUNAO | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060515S00071 | 15GG0124 | 2015-07-09 | 2015-07-20 | 2015-07-21 | 2015-08-26 | 2015-09-22 | SAN JOSE BUILDERS
NC 2015 | K10 (2015) | Region VI | Iloilo | 116672 | Sinuagan ES | POTOTAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060515S00191 | 15GG0213 | 2015-11-16 | 2015-11-19 | 2015-12-01 | 2015-12-22
NC 2015 | K10 (2015) | Region VI | Iloilo | 116197 | Supanga PS | CALINOG | 3 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3917968.78 |  |  | COMPLETED | 1 |  |  | 060515S00181 | 15GG0210 | 2015-11-09 | 2015-11-12 | 2015-11-24 | 2015-12-08
NC 2015 | K10 (2015) | Region VI | Iloilo | 116398 | Tambal ES | JANIUAY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 060515S00184 | 15GG0212 | 2015-11-09 | 2015-11-12 | 2015-11-24 | 2015-12-09
NC 2015 | SHS (2015) | Region VI | Iloilo | 302580 | Tina National High School | BADIANGAN | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6460088 |  |  | COMPLETED | 1 |  |  | 060515S00115 | 15GG0230 | 2015-11-23 | 2015-11-26 | 2015-12-08 | 2015-12-21
NC 2015 | K10 (2015) | Region VI | Iloilo | 116153 | Tiring CES | CABATUAN | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060515S00103 | 15GG0117 | 2015-07-09 | 2015-07-20 | 2015-07-21 | 2015-08-20 | 2015-11-19 | H.F. ENTERPRISES
NC 2015 | K10 (2015) | Region VI | Iloilo | 116560 | Trangka Elementary School | MAASIN | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 3102592.44 |  |  | COMPLETED | 1 |  |  | 060515S00189 | 15GG0209 | 2015-11-09 | 2015-11-12 | 2015-11-24 | 2015-12-15
NC 2015 | K10 (2015) | Region VI | Iloilo | 180005 | Ulayan ES | CALINOG | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 060515S00180 | 15GG0211 | 2015-11-09 | 2015-11-12 | 2015-11-24 | 2015-12-15
NC 2015 | K10 (2015) | Region VI | Iloilo | 116468 | Walang ES | LAMBUNAO | 3 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060515S00094 | 15GG0125 | 2015-07-09 | 2015-07-20 | 2015-07-21 | 2015-08-19 | 2015-11-23 | LEGACY CONSTRUCTION
NC 2015 | K10 (2015) | Region VI | Iloilo | 116401 | Yabon ES | JANIUAY | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 060515S00096 | 15GG0119 | 2015-07-09 | 2015-07-20 | 2015-07-21 | 2015-08-12 | 2015-09-22 | G. UY CONSTRUCTION
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302449 | Anilao NHS | ANILAO | 4 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 5079098.54 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Iloilo | 116290 | Aurora Araneta MES | DUEÑAS | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060515S00163 | 15GG0205 | 2015-11-09 | 2015-11-12 | 2015-11-24 | 2015-12-10
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302455 | Banate NHS | BANATE | 4 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Iloilo | 116293 | Banugan Elementary School | Dueñas | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 3002592.44 |  |  | COMPLETED | 1 |  |  | 060515S00151 | 15GG0208 | 2015-11-09 | 2015-11-12 | 2015-11-24 | 2015-12-17
NC 2015 | K10 (2015) | Region VI | Iloilo | 311503 | Barotac Nuevo NCHS-Tiwi Annex | BAROTAC NUEVO | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060515S00073 | 15GG0134 | 2015-07-09 | 2015-07-20 | 2015-07-21 | 2015-08-12 | 2015-10-09 | SBF CONSTRUCTION & DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VI | Iloilo | 302489 | De La Paz National High School | BANATE | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6469338 |  |  | COMPLETED | 1 |  |  | 060515S00112 | 15GG0232 | 2015-11-23 | 2015-11-26 | 2015-12-08 | 2015-12-22
NC 2015 | K10 (2015) | Region VI | Iloilo | 116301 | Dila-an PS | DUEÑAS | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060515S00150 | 15GG0206 | 2015-11-09 | 2015-11-12 | 2015-11-24 | 2015-12-17
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302490 | Dingle NHS | DINGLE | 4 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2509549.27 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302497 | Duenas GCHS | DUEÑAS | 4 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4819098.54 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302498 | Dumangas NHS | DUMANGAS | 4 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7178647.81 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 302527 | Malusgod NHS | DUEÑAS | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2922592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 302527 | Malusgod NHS | DUEÑAS | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 302543 | Pagdugue NHS | DUMANGAS | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6369861 |  |  | COMPLETED | 1 |  |  | 060515S00111 | 15GG0233 | 2015-11-23 | 2015-11-26 | 2015-12-08 | 2015-12-22
NC 2015 | K10 (2015) | Region VI | Iloilo | 116344 | Rosario ES | DUMANGAS | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060515S00148 | 15GG0207 | 2015-11-09 | 2015-11-12 | 2015-11-24 | 2015-12-17
NC 2015 | K10 (2015) | Region VI | Iloilo | 116331 | Tubigan ES | DUMANGAS | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060515S00140 | 15GG0204 | 2015-11-09 | 2015-11-12 | 2015-11-24 | 2015-12-17
NC 2015 | K10 (2015) | Region VI | Iloilo | 116200 | Asluman ES | CARLES | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2188606.04 |  |  | COMPLETED | 1 |  |  | 060515S00156 | 15GH0075 | 2015-09-11 | 2015-09-23 | 2015-09-24 | 2015-09-30 | 2015-11-03 | MJ BARCELONA CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region VI | Iloilo | 115920 | Badiangan Elementary School | AJUY | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 060515S00152 | 15GH0068 | 2015-09-12 | 2015-09-23 | 2015-09-25 | 2015-09-30 | 2015-11-03 | JHALL MARKETING & SERVICES
NC 2015 | K10 (2015) | Region VI | Iloilo | 116760 | Bagacay Primary School | San Rafael | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060515S00162 | 15GH0081 | 2015-09-17 | 2015-09-22 | 2015-09-24 | 2015-09-30 | 2015-11-03 | Q. M. FLORETE CONSTRUCTION
NC 2015 | SHS (2015) | Region VI | Iloilo | 302454 | Balasan NHS | BALASAN | 5 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10927342.5917 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302454 | Balasan NHS | BALASAN | 5 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302458 | Barotac Viejo NHS | BAROTAC VIEJO | 5 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 5229098.54 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302460 | Batad NHS | BATAD | 5 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Iloilo | 116013 | Batuan PS | BALASAN | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | REVERTED | 0 |  |  | 060515S00144 | 15GH0071 | 2015-09-11 | 2015-09-22 | 2015-09-24 | 2015-09-28 | 2015-11-03 | WOODLAND CONSTRUCTION & SUPPLY, INC.
NC 2015 | K10 (2015) | Region VI | Iloilo | 116204 | Batuanan ES | CARLES | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060515S00069 | 15GH0032 | 2015-07-23 | 2015-08-04 | 2015-08-05 | 2015-08-09 | 2015-08-24 | ANJUSH BUILDERS
NC 2015 | K10 (2015) | Region VI | Iloilo | 116205 | Binuluangan Elementary School | Carles | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 3252592.44 |  |  | COMPLETED | 1 |  |  | 060515S00149 | 15GH0056 | 2015-09-07 | 2015-09-17 | 2015-09-18 | 2015-09-24 | 2015-11-03 | PETRONAL BUILDERS
NC 2015 | K10 (2015) | Region VI | Iloilo | 116347 | Botongon ES | ESTANCIA | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060515S00076 | 15GH0035 | 2015-07-23 | 2015-08-04 | 2015-08-05 | 2015-08-09 | 2015-08-24 | 5s CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region VI | Iloilo | 116064 | California PS | BAROTAC VIEJO | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060515S00142 | 15GH0067 | 2015-09-14 | 2015-09-24 | 2015-09-25 | 2015-10-15 | 2015-11-03 | By Administration
NC 2015 | K10 (2015) | Region VI | Iloilo | 116348 | Cano-an ES | ESTANCIA | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 060515S00159 | 15GH0079 | 2015-09-17 | 2015-09-28 | 2015-09-29 | 2015-10-12 | 2015-11-03 | WOODLAND CONSTRUCTION & SUPPLY, INC.
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302493 | Carlos Lopez NHS | SAN DIONISIO | 5 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2729549.27 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302482 | Cawayan NHS | CARLES | 5 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2469549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Iloilo | 116680 | Cubay ES | SAN DIONISIO | 5 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 302494 | Don Casimero Andrada NHS | CARLES | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060515S00195 | 15GH0086 | 2015-09-17 | 2015-09-29 | 2015-09-29 | 2015-10-07 | 2015-10-27 | RRL BUILDERS CORPORATION
NC 2015 | SHS (2015) | Region VI | Iloilo | 302500 | Estancia National High School | ESTANCIA | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302500 | Estancia National High School | ESTANCIA | 5 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Iloilo | 116067 | Gen. Luna Elementary School | Barotac Viejo | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060515S00141 | 15GH0073 | 2015-09-11 | 2015-09-22 | 2015-09-24 | 2015-09-30 | 2015-11-03 | WOODLAND CONSTRUCTION & SUPPLY, INC.
NC 2015 | SHS (2015) | Region VI | Iloilo | 302502 | GEN. LUNA NHS | BAROTAC VIEJO | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6369338 |  |  | cOMPLETED | 1 |  |  | 060515S00110 | 15GH0059 | 2015-09-07 | 2015-09-17 | 2015-09-17 | 2015-09-24 | 2015-10-27 | KENBE CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VI | Iloilo | 302505 | GRANADA NHS | CARLES | 5 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 2 | 4187968.78 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 302505 | GRANADA NHS | CARLES | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 311009 | Granada NHS-Ballesteros Campus | CARLES | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 3362592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 311009 | Granada NHS-Ballesteros Campus | CARLES | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Iloilo | 116016 | Kinalkalan ES | BALASAN | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 060515S00072 | 15GH0031 | 2015-07-23 | 2015-08-04 | 2015-08-05 | 2015-08-09 | 2015-08-24 | UNITEC BUILDER, INCORPORATED
NC 2015 | K10 (2015) | Region VI | Iloilo | 116068 | La Fortuna Elementary School | Barotac Viejo | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 060515S00147 | 15GH0054 | 2015-09-07 | 2015-09-15 | 2015-09-16 | 2015-09-21 | 2015-11-03 | JHALL MARKETING & SERVICES
NC 2015 | K10 (2015) | Region VI | Iloilo | 116781 | Labigan Primary School | Sara | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Iloilo | 116017 | Lawis ES | BALASAN | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060515S00143 | 15GH0072 | 2015-09-11 | 2015-09-22 | 2015-09-24 | 2015-09-28 | 2015-11-03 | WOODLAND CONSTRUCTION & SUPPLY, INC.
NC 2015 | K10 (2015) | Region VI | Iloilo | 116352 | Lumbia ES | ESTANCIA | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060515S00077 | 15GH0036 | 2015-07-23 | 2015-08-04 | 2015-08-05 | 2015-08-09 | 2015-08-24 | 5s CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region VI | Iloilo | 302525 | Malapaya NHS | SARA | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060515S00079 | 15GH0038 | 2015-07-23 | 2015-08-04 | 2015-08-05 | 2015-08-09 | 2015-08-24 | 5s CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region VI | Iloilo | 116353 | Malbog ES | ESTANCIA | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 060515S00160 | 15GH0077 | 2015-09-11 | 2015-09-22 | 2015-09-24 | 2015-09-29 | 2015-11-03 | WOODLAND CONSTRUCTION & SUPPLY, INC.
NC 2015 | K10 (2015) | Region VI | Iloilo | 116254 | Maliog-liog ES | CONCEPCION | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060515S00070 | 15GH0033 | 2015-07-23 | 2015-08-04 | 2015-08-05 | 2015-08-09 | 2015-08-24 | 5s CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region VI | Iloilo | 116685 | Malunoy Primary School | San Dionisio | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060515S00161 | 15GH0080 | 2015-09-17 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-11-03 | PETRONAL BUILDERS
NC 2015 | K10 (2015) | Region VI | Iloilo | 115927 | Mangorocoro ES | AJUY | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 060515S00146 | 15GH0069 | 2015-09-12 | 2015-09-24 | 2015-09-25 | 2015-09-30 | 2015-11-03 | WOODLAND CONSTRUCTION & SUPPLY, INC.
NC 2015 | SHS (2015) | Region VI | Iloilo | 302532 | Milan NHS | LEMERY | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8304965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 302532 | Milan NHS | LEMERY | 5 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Iloilo | 116784 | Muyco Elementary School | SARA | 5 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060515S00078 | 15GH0037 | 2015-07-23 | 2015-08-04 | 2015-08-05 | 2015-08-10 | 2015-08-24 | JHALL MARKETING & SERVICES
NC 2015 | SHS (2015) | Region VI | Iloilo | 302555 | Polopiña NHS | CONCEPCION | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 5855185 |  |  | COMPLETED | 1 |  |  | 060515S00109 | 15GH0085 | 2015-09-16 | 2015-09-28 | 2015-09-29 | 2015-10-07 | 2015-10-27 | WOODLAND CONSTRUCTION & SUPPLY, INC.
NC 2015 | K10 (2015) | Region VI | Iloilo | 180012 | Pontoc Elementary School | LEMERY | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060515S00153 | 15GH0083 | 2015-09-17 | 2015-09-22 | 2015-09-23 | 2015-09-28 | 2015-11-03 | WOODLAND CONSTRUCTION & SUPPLY, INC.
NC 2015 | K10 (2015) | Region VI | Iloilo | 116076 | Rizal PS | BAROTAC VIEJO | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060515S00154 | 15GH0074 | 2015-09-11 | 2015-09-24 | 2015-09-25 | 2015-09-29 | 2015-11-03 | JHALL MARKETING & SERVICES
NC 2015 | K10 (2015) | Region VI | Iloilo | 116261 | Salvacion ES | CONCEPCION | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 060515S00075 | 15GH0034 | 2015-07-23 | 2015-08-04 | 2015-08-05 | 2015-08-09 | 2015-08-24 | 5s CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region VI | Iloilo | 116081 | San Juan Elementary School | Barotac Viejo | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 060515S00165 | 15GH0055 | 2015-09-07 | 2015-09-16 | 2015-09-17 | 2015-09-21 | 2015-11-03 | 5s CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VI | Iloilo | 302569 | San Rafael NHS (San Rafael) | SAN RAFAEL | 5 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10917342.5917 |  |  | COMPLETED | 1 |  |  | 060515S00042 | 15GH0047 | 2015-07-23 | 2015-08-04 | 2015-08-05 | 2015-08-09 | 2015-08-24 | UNITEC BUILDER, INCORPORATED
NC 2015 | SHS (2015) | Region VI | Iloilo | 311004 | Santiago NHS | BAROTAC VIEJO | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6369338 |  |  | COMPLETED | 1 |  |  | 060515S00107 | 15GH0060 | 2015-09-07 | 2015-09-17 | 2015-09-18 | 2015-09-24 | 2015-10-27 | MJ BARCELONA CONSTRUCTION AND SUPPLY
NC 2015 | TECHVOC (2015) | Region VI | Iloilo | 302570 | Sara NHS | SARA | 5 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4859098.54 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Iloilo | 115939 | Sto. Rosario ES | AJUY | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 060515S00145 | 15GH0070 | 2015-09-12 | 2015-09-24 | 2015-09-25 | 2015-09-29 | 2015-11-03 | WOODLAND CONSTRUCTION & SUPPLY, INC.
NC 2015 | K10 (2015) | Region VI | Iloilo | 116226 | Tabugon Elementary School | CARLES | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 3102592.44 |  |  | COMPLETED | 1 |  |  | 060515S00157 | 15GH0078 | 2015-09-17 | 2015-09-29 | 2015-09-30 | 2015-10-16 | 2015-11-03 | PETRONAL BUILDERS
NC 2015 | SHS (2015) | Region VI | Iloilo | 302577 | Talingting NHS | CARLES | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 3602592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 302577 | Talingting NHS | CARLES | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 311012 | Tambaliza NHS | CONCEPCION | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2428606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 311012 | Tambaliza NHS | CONCEPCION | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Iloilo | 311012 | Tambaliza NHS | CONCEPCION | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Iloilo | 116231 | Tunga Primary School | Carles | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2188606.04 |  |  | COMPLETED | 1 |  |  | 060515S00158 | 15GH0076 | 2015-09-11 | 2015-09-23 | 2015-09-24 | 2015-09-29 | 2015-11-03 | MJ BARCELONA CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region VI | Iloilo | 311001 | Valerio P. Palmares NHS | BATAD | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 2902592 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VI | Iloilo City | 117619 | Baluarte ES | ILOILO CITY (Capital) | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060515S00167
NC 2015 | K10 (2015) | Region VI | Iloilo City | 117582 | E. Yusay MS | ILOILO CITY (Capital) | 0 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 060515S00080 | 15GJ0060 | 2015-10-25 | 2015-10-30 | 2015-11-11 | 2015-12-03 | 2015-12-11 | Q. M. FLORETE CONSTRUCTION
NC 2015 | K10 (2015) | Region VI | Iloilo City | 302740 | Melchor L. Nava NHS | ILOILO CITY (Capital) | 0 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | REVERTED | 0 |  |  | 060515S00081
NC 2015 | K10 (2015) | Region VI | Iloilo City | 500191 | TCT-AR Foundation Integrated School | ILOILO CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8604965.051 |  |  | Reverted | 0 |  |  | 060515S00168
NC 2015 | K10 (2015) | Region VI | Passi City | 117918 | Anecito Panolino Elementary School | CITY OF PASSI | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060515S00074 | 15GG0132 | 2015-07-09 | 2015-07-20 | 2015-07-21 | 2015-08-13 | 2015-11-27 | VANNIE CONSTRUCTION AND SUPPLY (FORMERLY: VANNIE
NC 2015 | K10 (2015) | Region VI | Passi City | 186005 | BATUYANAN ELEMENTARY SCHOOL | CITY OF PASSI | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 060515S00082 | 15GG0133 | 2015-07-09 | 2015-07-20 | 2015-07-21 | 2015-08-19 | 2015-09-25 | PANAY EAST COAST CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VI | Passi City | 302803 | Gemumua-Agahon NHS | CITY OF PASSI | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Passi City | 302803 | Gemumua-Agahon NHS | CITY OF PASSI | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VI | Roxas City | 500193 | Marcos Fuentes IS | ROXAS CITY (Capital) | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 060315S00005 | 15GD0070 | 2015-10-22 | 2015-10-23 | 2015-11-05 | 2015-11-14 | 2015-11-27 | ROPRIM CONSTRUCTION
NC 2015 | K10 (2015) | Region VI | Roxas City | 311709 | Olotayan Integrated School | ROXAS CITY (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 2088606 |  |  | COMPLETED | 1 |  |  | 060315S00042
NC 2015 | TECHVOC (2015) | Region VI | Roxas City | 311702 | Roxas City School for Philippine Craftsmen | ROXAS CITY (Capital) | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2016 | SHS | Region VI | Bacolod City | 302700 | Alangilan Nhs | Bacolod City (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8471400 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Bacolod City | 302701 | Bacolod City Nhs | Bacolod City (Capital) | 0 | 1 | 40 | 4STY20CL | BATCH 9 CL | 67836000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Bacolod City | 302701 | Bacolod City Nhs | Bacolod City (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2448130 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Bacolod City | 302702 | Barangay Singcang-Airport Nhs | Bacolod City (Capital) | 0 | 1 | 20 | 4STY20CL | BATCH 3 CL | 33490440 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Bacolod City | 302703 | Bata National High School | Bacolod City (Capital) | 0 | 1 | 20 | 4STY20CL | BATCH 3 CL | 33575440 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Bacolod City | 302705 | Domingo Lacson Nhs | Bacolod City (Capital) | 0 | 1 | 30 | 3STY15CL | BATCH 9 CL | 47296129.59 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Bacolod City | 302705 | Domingo Lacson Nhs | Bacolod City (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2448130 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Bacolod City | 302706 | Emiliano Lizares Nhs | Bacolod City (Capital) | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34318179.297 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Bacolod City | 302706 | Emiliano Lizares Nhs | Bacolod City (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Bacolod City | 117484 | Estefania Es | Bacolod City (Capital) | 0 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22253143.62 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Bacolod City | 500190 | Fr. Gratian Murray, Afsc Is | Bacolod City (Capital) | 0 | 1 | 12 | 2STY6CL | BATCH 9 CL | 16942800 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Bacolod City | 302712 | Handumanan Nhs | Bacolod City (Capital) | 0 | 1 | 40 | 4STY20CL | BATCH 3 CL | 66980000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Bacolod City | 302713 | Jovito H. Sayson Nhs | Bacolod City (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16703510.712 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Bacolod City | 302713 | Jovito H. Sayson Nhs | Bacolod City (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2448130 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Bacolod City | 302709 | Luis Hervias Nhs | Bacolod City (Capital) | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31252890.27 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Bacolod City | 302709 | Luis Hervias Nhs | Bacolod City (Capital) | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Bacolod City | 302709 | Luis Hervias Nhs | Bacolod City (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Bacolod City | 302711 | Luisa Medel Nhs | Bacolod City (Capital) | 0 | 1 | 40 | 4STY20CL | BATCH 9 CL | 66980000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Bacolod City | 311201 | M. G. Medalla Integrated School | Bacolod City (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16703510.712 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Bacolod City | 302710 | Mandalagan National High School | Bacolod City (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16703510.712 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Bacolod City | 302714 | Mansilingan Agro-Ind. Hs | Bacolod City (Capital) | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34318179.297 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Bacolod City | 302714 | Mansilingan Agro-Ind. Hs | Bacolod City (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Bacolod City | 302704 | Romanito Maravilla Nhs | Bacolod City (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16703510.712 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Bacolod City | 302716 | Sum-Ag National High School | Bacolod City (Capital) | 0 | 1 | 40 | 4STY20CL | BATCH 9 CL | 66980000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Bacolod City | 302716 | Sum-Ag National High School | Bacolod City (Capital) | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5379660 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Bacolod City | 302718 | Teofilo M. Gensoli Sr. Nhs | Bacolod City (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8471400 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Bago City | 117524 | Mailum Es | Bago City | 4 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2802592.44 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Bago City | 117516 | R. M. Salas Es | Bago City | 4 | 1 | 4 | 1STY2CL | BATCH 5 CL | 3877212.08 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Bago City | 302720 | Ramon Torres Dulao Nhs | Bago City | 4 | 1 | 15 | 3STY15CL | BATCH 3 CL | 21383013.45 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Bago City | 302720 | Ramon Torres Dulao Nhs | Bago City | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2417461.96 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Bago City | 302720 | Ramon Torres Dulao Nhs | Bago City | 4 |  | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2417461.96 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Bago City | 302724 | Ramon Torres Louisiana Nhs | Bago City | 4 | 1 | 30 | 3STY15CL | BATCH 1 CL | 43187226.9 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Bago City | 302721 | Ramon Torres Maao Sugar Central Nhs | Bago City | 4 | 1 | 12 | 2STY6CL | BATCH 5 CL | 16429930.12 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Bago City | 302721 | Ramon Torres Maao Sugar Central Nhs | Bago City | 4 |  | 16 | 1STY4CL | BATCH 5 CL | 14671875.152 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Bago City | 302722 | Ramon Torres Malingin Nhs | Bago City | 4 | 1 | 16 | 2STY8CL | BATCH 5 CL | 21754685.18 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Bago City | 302719 | Ramon Torres Nhs | Bago City | 4 | 1 | 40 | 4STY20CL | BATCH 1 CL | 63890580.54 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Bago City | 302723 | Ramon Torres Sagasa Nhs | Bago City | 4 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8214965.06 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Bago City | 302723 | Ramon Torres Sagasa Nhs | Bago City | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2417461.96 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Bago City | 302725 | Ramon Torres Taloc Nhs | Bago City | 4 | 1 | 8 | 2STY8CL | BATCH 3 CL | 10877342.59 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Cadiz City | 117571 | Cadiz Viejo Es | Cadiz City | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20029495.669 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Cadiz City | 117573 | Caduha-An Es | Cadiz City | 2 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Cadiz City | 302728 | Caduha-An Nhs | Cadiz City | 2 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Cadiz City | 302729 | Caduha-An Nhs - Andres Bonifacio Ext. Hs | Cadiz City | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6430000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Cadiz City | 311401 | Caduha-An Nhs - Luna Ext. Hs | Cadiz City | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814741 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Cadiz City | 302730 | Dr. Vicente F. Gustilo Memorial Nhs - Daga Ext. Hs | Cadiz City | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 53085903.72 |  |  | Reverted | 0
NC 2016 | K10 | Region VI | Cadiz City | 302730 | Dr. Vicente F. Gustilo Memorial Nhs - Daga Ext. Hs | Cadiz City | 2 |  | 15 | 3STY15CL | BATCH 9 CL |  |  |  | Reverted | 0
NC 2016 | K10 | Region VI | Cadiz City | 311405 | Dr. Vicente F. Gustilo Memorial Nhs - Daga Ext. Hs To Banquerohan Nhs | Cadiz City | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6563273 |  |  | Reverted | 0
NC 2016 | SHS | Region VI | Cadiz City | 302736 | Jerusalem National High School | Cadiz City | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 9834608.3325 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Cadiz City | 302731 | Mabini National High School | Cadiz City | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11980076.8509 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Cadiz City | 302731 | Mabini National High School | Cadiz City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2427000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Cadiz City | 311403 | Mabini Nhs - Alimatoc Ext. Hs | Cadiz City | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12100076.8509 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Cadiz City | 302727 | Sicaba National High School | Cadiz City | 2 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16618460.712 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Cadiz City | 302732 | Sped High School | Cadiz City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2505684.72 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Cadiz City | 302732 | Sped Hs | Cadiz City | 2 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Cadiz City | 302733 | Tiglawigan Nhs | Cadiz City | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Cadiz City | 302734 | Tiglawigan Nhs - Magsaysay Extension High School | Cadiz City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2552371.2576 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Cadiz City | 117556 | Tres Andanas Es | Cadiz City | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1934741 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Cadiz City | 302735 | Villacin Nhs | Cadiz City | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Escalante City | 325602 | Buenavista Nhs - Langub Ext. | City Of Escalante | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Escalante City | 302625 | Escalante Nhs | City Of Escalante | 1 | 1 | 16 | 2STY8CL | BATCH 13 CL | 24300153.698 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Escalante City | 325603 | Escalante Nhs - Pinapugasan Ext. | City Of Escalante | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Escalante City | 302660 | Mabini Nhs | City Of Escalante | 1 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12950000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Escalante City | 302626 | Old Poblacion Nhs | City Of Escalante | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1900000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 117854 | Amian Es | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2108000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Kabankalan City | 302785 | Bantayan National High School | City Of Kabankalan | 6 | 1 | 10 | 2STY10CL | BATCH 3 CL | 13398000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Kabankalan City | 302785 | Bantayan National High School | City Of Kabankalan | 6 |  | 12 | 2STY12CL | BATCH 3 CL | 15324000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Kabankalan City | 302785 | Bantayan National High School | City Of Kabankalan | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2479549.27 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 302786 | Binicuil National High School | City Of Kabankalan | 6 | 1 | 24 | 3STY12CL | BATCH 1 CL | 38844537.58 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 302786 | Binicuil National High School | City Of Kabankalan | 6 |  | 6 | 3STY6CL | BATCH 1 CL | 11017131.51 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Kabankalan City | 302792 | Camansi Nhs | City Of Kabankalan | 6 | 1 | 8 | 2STY8CL | BATCH 5 CL | 11225000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Kabankalan City | 302792 | Camansi Nhs | City Of Kabankalan | 6 |  | 6 | 2STY6CL | BATCH 5 CL | 8476000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 117879 | Candiacap Es | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 117836 | Carol-An Es | City Of Kabankalan | 6 | 1 | 3 | 1STY3CL | BATCH 5 CL | 3056000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Kabankalan City | 302787 | Carol-An Nhs | City Of Kabankalan | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2617000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Kabankalan City | 302787 | Carol-An Nhs | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2153800 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Kabankalan City | 302787 | Carol-An Nhs | City Of Kabankalan | 6 |  | 4 | 1STY4CL | BATCH 9 CL | 4075500 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 117837 | Casipsipan Es | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1958000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 117837 | Casipsipan Es | City Of Kabankalan | 6 |  | 3 | 1STY3CL | BATCH 5 CL | 2831000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 117881 | Dacongcogon Elementary School | City Of Kabankalan | 6 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2931000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 302793 | Florentino Galang Sr. National High School | City Of Kabankalan | 6 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8416000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 302793 | Florentino Galang Sr. National High School | City Of Kabankalan | 6 |  | 18 | 3STY9CL | BATCH 5 CL | 30602000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Kabankalan City | 302793 | Florentino Galang Sr. National High School | City Of Kabankalan | 6 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 4899098.54 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 302793 | Florentino Galang Sr. National High School | City Of Kabankalan | 6 |  | 12 | 3STY12CL | BATCH 5 CL | 18462000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 312103 | Hinapunan Integrated School | City Of Kabankalan | 6 | 1 | 5 | 1STY5CL | BATCH 5 CL | 4869000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 302794 | Inapoy Nhs | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 117844 | Mansumbil Elementary School | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 117846 | Noac Elementary School | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2108000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Kabankalan City | 302798 | Pinaguinpinan Nhs | City Of Kabankalan | 6 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8396000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Kabankalan City | 302798 | Pinaguinpinan Nhs | City Of Kabankalan | 6 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 4899098.54 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 117850 | Pres. Osmena Es | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2158000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 117891 | Sagumayon Ps | City Of Kabankalan | 6 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1210000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Kabankalan City | 302797 | Tabugon National High School | City Of Kabankalan | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2689549.27 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 302797 | Tabugon National High School | City Of Kabankalan | 6 | 1 | 24 | 3STY12CL | BATCH 1 CL | 39564537.58 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 302799 | Tabugon Nhs - Tagoc Ext. | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 302790 | Tagukon Nhs | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 302800 | Tampalon National High School | City Of Kabankalan | 6 | 1 | 12 | 3STY12CL | BATCH 1 CL | 19782268.79 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 302800 | Tampalon National High School | City Of Kabankalan | 6 |  | 4 | 2STY4CL | BATCH 1 CL | 6902000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 117853 | Tan-Awan Es | City Of Kabankalan | 6 | 1 | 4 | 1STY4CL | BATCH 5 CL | 3855000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 312101 | Tan-Awan National High School | City Of Kabankalan | 6 | 1 | 10 | 2STY10CL | BATCH 1 CL | 14198000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Kabankalan City | 312101 | Tan-Awan National High School | City Of Kabankalan | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2559549.27 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 302801 | Tapi National High School | City Of Kabankalan | 6 | 1 | 12 | 3STY12CL | BATCH 1 CL | 19782000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Kabankalan City | 302801 | Tapi National High School | City Of Kabankalan | 6 |  | 8 | 2STY8CL | BATCH 1 CL | 12025000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Kabankalan City | 302801 | Tapi National High School | City Of Kabankalan | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2559549.27 |  |  | Completed | 1
NC 2016 | K10 | Region VI | La Carlota City | 302751 | Dona H.S.Benedicto Nhs | La Carlota City | 4 | 1 | 32 | 2STY8CL | BATCH 9 CL | 45627903.56 |  |  | Completed | 1
NC 2016 | K10 | Region VI | La Carlota City | 302751 | Dona H.S.Benedicto Nhs | La Carlota City | 4 |  | 12 | 2STY6CL | BATCH 9 CL | 16799979.18 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Sagay City | 302762 | Bato National High School | Sagay City | 2 | 1 | 32 | 4STY32CL | BATCH 9 CL | 48970442.044 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Sagay City | 302762 | Bato National High School | Sagay City | 2 |  | 6 | 2STY6CL | BATCH 9 CL | 8916630.47 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Sagay City | 302762 | Bato National High School | Sagay City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2429550 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Sagay City | 117725 | Baviera Es | Sagay City | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 2088607 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Sagay City | 302768 | Bulanon National High School | Sagay City | 2 | 1 | 18 | 3STY9CL | BATCH 5 CL | 28292601 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Sagay City | 302763 | Campo Bago Nhs | Sagay City | 2 |  | 2 | 1STY2CL | BATCH 3 CL | 2088607 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Sagay City | 302764 | Colonia Divina Integrated School | Sagay City | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20150000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Sagay City | 302764 | Colonia Divina Integrated School | Sagay City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2464550 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Sagay City | 302765 | Eusebio Lopez Memorial Integrated School | Sagay City | 2 | 1 | 32 | 4STY32CL | BATCH 9 CL | 44532220.04 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Sagay City | 302765 | Eusebio Lopez Memorial Integrated School | Sagay City | 2 |  | 8 | 2STY8CL | BATCH 9 CL | 10877342.5917 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Sagay City | 302765 | Eusebio Lopez Memorial Integrated School | Sagay City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2429550 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Sagay City | 302766 | Himogaan Baybay Integrated School | Sagay City | 2 | 1 | 15 | 3STY15CL | BATCH 5 CL | 23477167 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Sagay City | 302767 | Sagay Nhs | Sagay City | 2 | 1 | 24 | 4STY24CL | BATCH 13 CL | 37473468 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Sagay City |  | Shs, Sagay City | Sagay City | 2 | 1 | 64 | 4STY32CL | BATCH 9 CL | 97940884.088 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Sagay City |  | Shs, Sagay City | Sagay City | 2 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 7288650 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Sagay City |  | Snhs-Lopez Jaena Ext. | Sagay City | 2 | 1 | 24 | 4STY24CL | BATCH 1 CL | 37473468 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Sagay City |  | Snhs-Rizal Ext. | Sagay City | 2 | 1 | 18 | 3STY9CL | BATCH 1 CL | 30242655.84 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Sagay City | 117705 | Suyac Es | Sagay City | 2 | 1 | 2 | 2STY2CL | BATCH 9 CL | 4785541.84 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Sagay City | 302771 | Vito Nhs | Sagay City | 2 | 1 | 16 | 4STY16CL | BATCH 9 CL | 25032312 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Sagay City | 302771 | Vito Nhs | Sagay City | 2 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 7251000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | San Carlos City | 302774 | Don Carlos Ledesma Nhs | San Carlos City | 1 | 1 | 10 | 2STY10CL | BATCH 3 CL | 13150000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | San Carlos City | 302775 | Julio Ledesma Nhs | San Carlos City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | San Carlos City | 302775 | Julio Ledesma Nhs | San Carlos City | 1 | 1 | 12 | 3STY6CL | BATCH 13 CL | 22100000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | San Carlos City | 302776 | Quezon Nhs | San Carlos City | 1 | 1 | 12 | 2STY12CL | BATCH 3 CL | 15006508.15 |  |  | Completed | 1
NC 2016 | SHS | Region VI | San Carlos City | 302777 | Sipaway Nhs | San Carlos City | 1 | 1 | 4 | 1STY4CL | BATCH 3 CL | 3850000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | San Carlos City | 302777 | Sipaway Nhs | San Carlos City | 1 |  | 5 | 1STY5CL | BATCH 3 CL | 4650000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Silay City | 302780 | Doña Montserrat Lopez Memorial High School | Silay City | 3 | 1 | 48 | 4STY24CL | BATCH 9 CL | 77100000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Silay City | 302780 | Doña Montserrat Lopez Memorial High School | Silay City | 3 |  | 48 | 4STY16CL | BATCH 9 CL | 80107408.26 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Silay City | 117826 | Sibato Integrated School | Silay City | 3 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1188254.6197 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Aklan | 310620 | 4. Habana Integrated School | Buruanga | 2 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8950000 |  |  | Completed | 1 |  |  | P00070106VS - CW1 | 16GA0029 |  | 2016-03-09 |  | 2016-05-26 | 2016-05-31 | LUMEL GLENN CONST.
NC 2016 | K10 | Region VI | Aklan | 302337 | 8. Toledo National High School | Nabas | 2 | 1 | 12 | 3STY12CL | BATCH 3 CL | 18250000 |  |  | Completed | 1 |  |  | P00070532VS - CW1 | 16GA0030 |  | 2016-03-09 |  | 2016-05-26 | 2016-05-31 | AUDRIC CONST. & SUPPLY
NC 2016 | K10 | Region VI | Aklan | 310616 | Agtughangin Integrated School | Madalag | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2860000 |  |  | Completed | 1 |  |  | P00073579VS - CW1 | 16GA0046 |  | 2016-06-17 | 2016-06-17
NC 2016 | TECHVOC | Region VI | Aklan | 310616 | Agtughangin Integrated School | Madalag | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 |  |  | P00072356VS - CW1 | 16GA0038 |  | 2016-04-20 | 2016-04-20 | 2016-06-14 | 2016-06-15 | STEVEN CONST. & SUPPLY
NC 2016 | K10 | Region VI | Aklan | 302286 | Altavas National School | Altavas | 1 | 1 | 24 | 3STY12CL | BATCH 7 CL | 36494537.58 |  |  | Completed | 1 |  |  | P00072357VS - CW1 | 16GA0031 |  | 2016-03-09 | 2016-03-09 | 2016-05-26 | 2016-05-31 | AFG CONST. & CONST. SUPPLY
NC 2016 | K10 | Region VI | Aklan | 302286 | Altavas National School | Altavas | 1 |  | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 |  |  | P00072358VS - CW1 | 16GA0056 |  | 2016-07-15 | 2016-07-15 |  |  | G.F. ROVERO MERCHADISING
NC 2016 | K10 | Region VI | Aklan | 302334 | Rosario National High School | Malinao | 2 | 1 | 12 | 2STY6CL | BATCH 7 CL | 16549930.102 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Aklan | 302336 | Tangalan National High School | Tangalan | 2 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15221327.92 |  |  | Completed | 1 |  |  | P00074511VS - CW1
NC 2016 | K10 | Region VI | Antique | 115141 | Agripino Tambagahan Ms | Pandan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115027 | Alojipan Es | Culasi | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2016300 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302341 | Antique Ns | San Jose (Capital) | 0 | 1 | 24 | 4STY24CL | BATCH 9 CL | 35596257 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302341 | Antique Ns | San Jose (Capital) | 0 |  | 20 | 4STY20CL | BATCH 9 CL | 31102890 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Antique | 302341 | Antique Ns | San Jose (Capital) | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4860000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 302342 | Antique Vocational School | Bugasong | 0 | 1 | 30 | 3STY15CL | BATCH 9 CL | 42766026 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Antique | 302342 | Antique Vocational School | Bugasong | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4834000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115287 | Apong Elementary School | Sibalom | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1924650 |  |  | Terminated | 0 | [10 empty] | Terminated;abandoned
NC 2016 | K10 | Region VI | Antique | 114981 | Arangote Es | Bugasong | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1906320 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302343 | Aureliana Nhs | Patnongon | 0 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18222269 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 114957 | Bahoyan-Yapo Es | Barbaza | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1113254.6197 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302344 | Barangbang Nhs | San Remigio | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Antique | 302344 | Barangbang Nhs | San Remigio | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2489900 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 302345 | Barasanan National High School | Tobias Fornier (Dao) | 0 | 1 | 8 | 2STY4CL | BATCH 9 CL | 12864000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 302345 | Barasanan National High School | Tobias Fornier (Dao) | 0 |  | 2 | 1STY2CL | BATCH 9 CL | 1848000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302346 | Barbaza Nhs | Barbaza | 0 | 1 | 9 | 3STY9CL | BATCH 13 CL | 16618460.712 |  |  | Completed | 1 | [10 empty] | Abandoned;Contractor made an appeal to continue
NC 2016 | TECHVOC | Region VI | Antique | 302346 | Barbaza Nhs | Barbaza | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302347 | Belison Ns | Belison | 0 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21383013 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115178 | Bitas Es | Patnongon | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1942980 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115082 | Bongbongan Es | Hamtic | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1878825 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302350 | Caluya Nhs | Caluya | 0 | 1 | 18 | 3STY9CL | BATCH 9 CL | 32840921.6 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115397 | Cananghan Ps | Valderrama | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1997970 |  |  | Terminated | 0 | [10 empty] | Terminated; Abandoned
NC 2016 | K10 | Region VI | Antique | 115101 | Canituan Ps | Laua-An | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1924650 |  |  | Reverted | 0 | [10 empty] | For reversion; Site Problem
NC 2016 | TECHVOC | Region VI | Antique | 302351 | Col. Ruperto Abellon Nhs | Laua-An | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302352 | Concepcion L. Cazeñas Ms | Tobias Fornier (Dao) | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8377460 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302352 | Concepcion L. Cazeñas Ms | Tobias Fornier (Dao) | 0 |  | 4 | 2STY4CL | BATCH 9 CL | 6444320 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Antique | 302352 | Concepcion L. Cazeñas Ms | Tobias Fornier (Dao) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2441300 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115039 | Culasi North Es | Culasi | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 14941328 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115008 | Dawis Es | Caluya | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2934800 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 302353 | Diclum National High School | Tobias Fornier (Dao) | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Antique | 310710 | Dr. Luis E. Baraquia Nhs | Sibalom | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 310708 | Eastern Laua-An Nhs (Maria Nhs) | Laua-An | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Antique | 310708 | Eastern Laua-An Nhs (Maria Nhs) | Laua-An | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 302354 | Egaña National High School | Sibalom | 0 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3500000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302355 | Gamad-Sto. Tomas Nhs | Tobias Fornier (Dao) | 0 | 1 | 8 | 2STY4CL | BATCH 9 CL | 12926032 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115195 | Gella Es | Patnongon | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1924650 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115195 | Gella Es | Patnongon | 0 |  | 1 | 1STY1CL | BATCH 9 CL | 1074150 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 310704 | Gen. Leandro Fullon Ns | Hamtic | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15163198 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 310704 | Gen. Leandro Fullon Ns | Hamtic | 0 |  | 6 | 2STY6CL | BATCH 9 CL | 8418190 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 310704 | Gen. Leandro Fullon Ns | Hamtic | 0 |  | 4 | 1STY4CL | BATCH 9 CL | 3552500 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Antique | 310704 | Gen. Leandro Fullon Ns | Hamtic | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2453450 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115242 | General Luna Es | San Remigio | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1979640 |  |  | Terminated | 0 | [10 empty] | Terminated; Abandoned
NC 2016 | SHS | Region VI | Antique | 302357 | Gideon M. Cabigunda Ms | San Remigio | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302357 | Gideon M. Cabigunda Ms | San Remigio | 0 |  | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 310707 | Gov. Evelio B. Javier Mnhs | San Remigio | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1860495 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Antique | 310707 | Gov. Evelio B. Javier Mnhs | San Remigio | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2453450 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Antique | 302358 | Gov. Julio V. Macuja Mchs | Hamtic | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 302356 | Governor Julian Fullon Pacificador Ns | Hamtic | 0 | 1 | 10 | 2STY10CL | BATCH 9 CL | 12898000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 310701 | Guintas Nhs | Hamtic | 0 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3500000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115221 | Igbonglo Es | San Jose (Capital) | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1053690 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302359 | Igburi Nhs | Patnongon | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302360 | Igcado Nhs | Tobias Fornier (Dao) | 0 | 1 | 4 | 1STY2CL | BATCH 9 CL | 3757650 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115372 | Igcaputol Ps | Tobias Fornier (Dao) | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1860495 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115373 | Igdanlog Es | Tobias Fornier (Dao) | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1874243 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302361 | Igpalge Nhs | Anini-Y | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6506640 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115320 | Indag-An Es | Sibalom | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1906320 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115322 | Insarayan Es | Sibalom | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1869660 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115108 | Lactudan Ps | Laua-An | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1942980 |  |  | Terminated | 0 | [10 empty] | Terminated; Abandoned
NC 2016 | K10 | Region VI | Antique | 115109 | Latazon Ps | Laua-An | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2016300 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 302362 | Laua-An National High School | Laua-An | 0 | 1 | 8 | 2STY8CL | BATCH 1 CL | 10877342.5917 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302363 | Libertad Nvs | Libertad | 0 | 1 | 10 | 2STY10CL | BATCH 9 CL | 12898000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302363 | Libertad Nvs | Libertad | 0 |  | 8 | 2STY8CL | BATCH 9 CL | 10985000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302364 | Lirio M. Escaño, Sr. Nhs | Patnongon | 0 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8296000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Antique | 302364 | Lirio M. Escaño, Sr. Nhs | Patnongon | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115324 | Lotilla Es | Sibalom | 0 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3500000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115092 | M.V. Velasco Mes | Hamtic | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1869660 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302365 | Mag-Aba Nhs | Pandan | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302365 | Mag-Aba Nhs | Pandan | 0 |  | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302366 | Moscoso-Rios Nhs | Hamtic | 0 | 1 | 20 | 2STY10CL | BATCH 9 CL | 25692620 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302366 | Moscoso-Rios Nhs | Hamtic | 0 |  | 2 | 1STY2CL | BATCH 9 CL | 1814740 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Antique | 302366 | Moscoso-Rios Nhs | Hamtic | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115048 | Naba Ps | Culasi | 0 | 1 | 4 | 1STY2CL | BATCH 9 CL | 3666000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115328 | Nazareth Es | Sibalom | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 302367 | Northern Antique Vocational School | Culasi | 0 | 1 | 12 | 2STY6CL | BATCH 9 CL | 16429930 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 302367 | Northern Antique Vocational School | Culasi | 0 |  | 24 | 2STY12CL | BATCH 9 CL | 29158434 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 310709 | Northern Bugasong Nhs Annex | Bugasong | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6600120 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302369 | Pandan Nvhs | Pandan | 0 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12898000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302370 | Pangpang Nhs | Sibalom | 0 | 1 | 10 | 2STY10CL | BATCH 9 CL | 12898000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Antique | 302370 | Pangpang Nhs | Sibalom | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302371 | Pascual M. Osuyos Ms | Tobias Fornier (Dao) | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115185 | Patlabawon Es | Patnongon | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1897155 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 302372 | Patria National School | Pandan | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115133 | Paz Es | Libertad | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 302373 | Pis-Anan National High Sshool | Sibalom | 0 | 1 | 10 | 2STY10CL | BATCH 9 CL | 12898000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 302373 | Pis-Anan National High Sshool | Sibalom | 0 |  | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115229 | Salazar Es (Funda Dalipe Es) | San Jose (Capital) | 0 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10417232 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115229 | Salazar Es (Funda Dalipe Es) | San Jose (Capital) | 0 |  | 4 | 2STY4CL | BATCH 9 CL | 6473000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 302376 | San Roque-Ezpeleta Nhs | Anini-Y | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8418190 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 302376 | San Roque-Ezpeleta Nhs | Anini-Y | 0 |  | 4 | 1STY4CL | BATCH 9 CL | 3552500 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115231 | San Fernando Es | San Jose (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115055 | San Pascual Es | Culasi | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1924650 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302375 | San Pedro Nhs | San Jose (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302377 | Sebaste Hs | Sebaste | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10985000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Antique | 302377 | Sebaste Hs | Sebaste | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 310703 | Sibalom Nhs | Sibalom | 0 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21383013 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 310703 | Sibalom Nhs | Sibalom | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 14941328 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Antique | 310703 | Sibalom Nhs | Sibalom | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4860000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 310706 | Sibay Nhs | Caluya | 0 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3850000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302378 | Sido-San Juan Nhs | Sibalom | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 114980 | Sinaja-Salvacion Elementary School | Belison | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302379 | Southern Bugasong Nhs | Bugasong | 0 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3500000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302380 | Sta. Ana Nhs | Pandan | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7116271.4019 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Antique | 302380 | Sta. Ana Nhs | Pandan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2507000 |  |  | Terminated | 0 | [10 empty] | For request of funding to complete
NC 2016 | K10 | Region VI | Antique | 115169 | Tabay Es | Pandan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1897155 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 114955 | Tagaytay Es | Anini-Y | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1906320 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 310702 | Tario Lim National Memorial High School | Tibiao | 0 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21383013 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 310702 | Tario Lim National Memorial High School | Tibiao | 0 |  | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Antique | 310702 | Tario Lim National Memorial High School | Tibiao | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115171 | Tingib Es | Pandan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302382 | Tinogboc Nhs | Caluya | 0 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3850000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Antique | 302383 | Union Nhs | Libertad | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302383 | Union Nhs | Libertad | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Antique | 302384 | Valderrama Nhs | Valderrama | 0 | 1 | 18 | 3STY9CL | BATCH 9 CL | 29882656 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Antique | 302384 | Valderrama Nhs | Valderrama | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4834000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Antique | 115173 | Zaldivar Elementary School | Pandan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 115612 | Agbanban Elementary School | Panay | 1 | 1 | 2 | 1STY2CL | BATCH 1 CL | 4741198.48 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 115612 | Agbanban Elementary School | Panay | 1 |  | 3 | 1STY3CL | BATCH 1 CL |  |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302388 | Cabugcabug Nhs | President Roxas | 1 | 1 | 24 | 4STY24CL | BATCH 9 CL | 39440882.854 |  |  | COMPLETED | 1
NC 2016 | SHS | Region VI | Capiz | 302392 | Casanayan Nhs | Pilar | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22352343.62 |  |  | COMPLETED | 1
NC 2016 | SHS | Region VI | Capiz | 302395 | Comsr. Luis R. Asis Nhs | Panay | 1 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31650000 |  |  | COMPLETED | 1
NC 2016 | SHS | Region VI | Capiz | 302395 | Comsr. Luis R. Asis Nhs | Panay | 1 |  | 8 | 2STY8CL | BATCH 7 CL | 10877342.59 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 310802 | Dao National High School | Dao | 1 | 1 | 24 | 4STY24CL | BATCH 3 CL | 35627000 |  |  | COMPLETED | 1
NC 2016 | SHS | Region VI | Capiz | 302400 | Dulangan Nhs | Pilar | 1 | 1 | 10 | 2STY10CL | BATCH 1 CL | 13321310.093 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302400 | Dulangan Nhs | Pilar | 1 |  | 6 | 2STY6CL | BATCH 1 CL | 9200000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 302398 | Felix Balgos Nhs | Panay | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8829965.05 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302405 | Hipona Nhs | Pontevedra | 1 | 1 | 18 | 3STY18CL | BATCH 1 CL | 32550000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302405 | Hipona Nhs | Pontevedra | 1 |  | 9 | 3STY9CL | BATCH 1 CL | 16350000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Capiz | 302405 | Hipona Nhs | Pontevedra | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2650000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 115627 | Jamul-Awon Es | Panay | 1 | 1 | 3 | 1STY3CL | BATCH 1 CL | 2802592.44 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302410 | Leodegario D. Deocampo Sr. Nhs | Panitan | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10717131.51 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302413 | Maayon Nhs | Ma-Ayon | 1 | 1 | 16 | 4STY16CL | BATCH 9 CL | 27600000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302413 | Maayon Nhs | Ma-Ayon | 1 |  | 20 | 4STY20CL | BATCH 9 CL | 31470000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Capiz | 302413 | Maayon Nhs | Ma-Ayon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302419 | Marciano M. Patricio (Pilar) | Pilar | 1 | 1 | 24 | 4STY24CL | BATCH 9 CL | 39140882.854 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Capiz | 302419 | Marciano M. Patricio (Pilar) | Pilar | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 115718 | Pandan Es | President Roxas | 1 | 1 | 2 | 1STY2CL | BATCH 1 CL | 3037055.73 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 115718 | Pandan Es | President Roxas | 1 |  | 1 | 1STY1CL | BATCH 1 CL |  |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302418 | Panitan Nhs | Panitan | 1 | 1 | 32 | 4STY32CL | BATCH 1 CL | 44832220.04 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Capiz | 302418 | Panitan Nhs | Panitan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2750000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 310812 | Pawa National High School | Panay | 1 | 1 | 8 | 2STY4CL | BATCH 9 CL | 11504807.7485 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Capiz | 302420 | Pontevedra Nhs | Pontevedra | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2479549.27 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302420 | Pontevedra Nhs | Pontevedra | 1 | 1 | 15 | 3STY15CL | BATCH 13 CL | 23606314.795 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302422 | San Nicolas Nhs (Pilar) | Pilar | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14183441.1023 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 115662 | Tabuc Norte Ps | Panitan | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2096214.1914 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302403 | Tuburan Nhs | Ma-Ayon | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14183441.1023 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 115597 | Agkawayan Ps | Mambusao | 2 | 1 | 3 | 1STY3CL | BATCH 1 CL | 2802592.44 |  |  | Completed | 1 | [10 empty] | SUSPENDED, Road heading to site is not passable, ONGOING KALAHI Concreting project
NC 2016 | K10 | Region VI | Capiz | 115470 | Aglanot Es | Dumarao | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 115412 | Angub Elementary School | Cuartero | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302385 | Arturo Jugo Nhs | Dao | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5702403.8743 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 115475 | Badbaranan Es | Dumarao | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 310801 | Bagong Barrio Nhs | Tapaz | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5702403.8743 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 310807 | Basiao Nhs (Formerly Ext. Of Ivisan Nhs) | Ivisan | 2 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15122000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 115585 | Bergante Es | Mambusao | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302386 | Bungsuan Nhs | Dumarao | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6320000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302389 | Camburanan Nhs | Tapaz | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5702403.8743 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302390 | Candelaria Nhs | Tapaz | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5702403.8743 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 311705 | Candelaria Nhs- Roxas Extension | Tapaz | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5702403.8743 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302393 | Col. Patrocinio Artuz Nhs | Tapaz | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8215000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302401 | Concepcion Castro Garcia Nhs (Dumalag Nhs) Sta. Cruz | Dumalag | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5702403.8743 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302396 | Cuartero Nhs | Cuartero | 2 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22153000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302396 | Cuartero Nhs | Cuartero | 2 |  | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302397 | David Moises Mhs | Mambusao | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6320000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 310806 | Dumalag Central Nhs | Dumalag | 2 | 1 | 24 | 4STY24CL | BATCH 3 CL | 35597000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Capiz | 310806 | Dumalag Central Nhs | Dumalag | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302402 | Estefania Montemayor Nhs | Dumarao | 2 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31103000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Capiz | 302402 | Estefania Montemayor Nhs | Dumarao | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 115485 | Guinotos Ps | Dumarao | 2 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1013000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 115507 | Ivisan Es | Ivisan | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302406 | Ivisan Nhs | Ivisan | 2 | 1 | 12 | 4STY12CL | BATCH 3 CL | 22153000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302406 | Ivisan Nhs | Ivisan | 2 |  | 20 | 4STY20CL | BATCH 3 CL | 31103000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Capiz | 302406 | Ivisan Nhs | Ivisan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 115530 | Jaena Sur Ps | Jamindan | 2 | 1 | 3 | 1STY3CL | BATCH 1 CL | 2802592.44 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302408 | Jagnaya Nhs | Jamindan | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6320000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 179001 | Jambad Ps | Dumarao | 2 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1013000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302409 | Jamindan Nhs | Jamindan | 2 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15122000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302409 | Jamindan Nhs | Jamindan | 2 |  | 12 | 4STY12CL | BATCH 3 CL | 22153000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Capiz | 302409 | Jamindan Nhs | Jamindan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 310810 | Lonoy National High School | Sapi-An | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6320000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302411 | Lucero Nhs | Jamindan | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6320000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302415 | Luis Escutin Nhs | Dao | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5702403.8743 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 115419 | Lunayan E/S | Cuartero | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 115422 | Maindang Elementary School | Cuartero | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 310804 | Maindang National High School | Cuartero | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8215000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 302414 | Malonoy National High School | Dao | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6320000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Capiz | 302414 | Malonoy National High School | Dao | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 5000000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 310813 | Mambusao East Nhs (Ext. Of David Moises) | Mambusao | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8215000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Capiz | 310805 | Mambusao National High School | Mambusao | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 302416 | Manuel F. Onato Memorial Nhs | Dumarao | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8215000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Capiz | 302416 | Manuel F. Onato Memorial Nhs | Dumarao | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 115762 | Matinabus Es | Sigma | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Capiz | 310815 | Mianay Nhs | Sigma | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 115489 | Nagsulang Elementary School | Dumarao | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 310814 | Presentacion Diez Gregorio Nhs | Dumarao | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5702403.8743 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 302421 | Putian National High School | Cuartero | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1744744.436 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 115491 | R. Advincula Sr. Ms | Dumarao | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Capiz | 302417 | Ramon A. Benjamin Sr. Nhs | Dumarao | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 310809 | Rev. Tomas Conejar Nhs | Tapaz | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6320000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 310808 | San Antonio National High School | Cuartero | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5702403.8743 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302423 | San Nicolas Nhs (Tapaz) | Tapaz | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5702403.8743 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302424 | Sapian National High School | Sapi-An | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6320000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302424 | Sapian National High School | Sapi-An | 2 |  | 12 | 3STY12CL | BATCH 3 CL | 18223000 |  |  | Completed | 1 | [10 empty] | With approved additional funds
NC 2016 | K10 | Region VI | Capiz | 115495 | Tamulalod Es | Dumarao | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 310803 | Tapaz Nhs | Tapaz | 2 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26703000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 115546 | Ubog Es | Jamindan | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1815000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Capiz | 302399 | Vicente Andaya Sr. Nhs | Sigma | 2 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 | [10 empty] | With approved additional funds
NC 2016 | SHS | Region VI | Capiz | 302399 | Vicente Andaya Sr. Nhs | Sigma | 2 |  | 8 | 2STY8CL | BATCH 7 CL | 10877343 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Capiz | 302399 | Vicente Andaya Sr. Nhs | Sigma | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 1250000 |  |  | Reverted | 0
NC 2016 | TECHVOC | Region VI | Guimaras | 302427 | Agsanayan National High School | Buenavista | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Guimaras | 302425 | Alegria National High School | Sibunag | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8546000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Guimaras | 302425 | Alegria National High School | Sibunag | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Guimaras | 310901 | Ayangan National High School | Sibunag | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6532000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Guimaras | 302426 | Buenavista Nhs | Buenavista | 0 | 1 | 32 | 4STY32CL | BATCH 1 CL | 44532220.04 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Guimaras | 302428 | Cabalagnan National High School | Nueva Valencia | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8546000 |  |  | Reverted | 0
NC 2016 | SHS | Region VI | Guimaras | 302435 | Calaya National High School | Nueva Valencia | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Guimaras | 302429 | Desiderio C. Gange National High School | Sibunag | 0 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21383013.45 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Guimaras | 302437 | Dr. Catalino Gallego Nava Memorial High School | San Lorenzo | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8496000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Guimaras | 302437 | Dr. Catalino Gallego Nava Memorial High School | San Lorenzo | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Guimaras | 302430 | East Valencia National High School | Buenavista | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Guimaras | 302430 | East Valencia National High School | Buenavista | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Guimaras | 302431 | Getulio National High School | Buenavista | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Guimaras | 302432 | Jordan Nhs | Jordan Nhs | 0 | 1 | 18 | 3STY18CL | BATCH 1 CL | 28350000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Guimaras | 179503 | Mabini Primary School | Buenavista | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2668000 |  |  | Reverted | 0
NC 2016 | SHS | Region VI | Guimaras | 302434 | Nueva Valencia National High School | Nueva Valencia | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31353000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Guimaras | 115881 | Paaralan Ng Buhay Ng Ravina Sur | Sibunag | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Guimaras | 302436 | Salvacion National High School | Nueva Valencia | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Guimaras | 302439 | San Lorenzo Nhs-Suclaran Annex | San Lorenzo | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Guimaras | 179502 | San Nicolas Primary School | Buenavista | 0 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3650000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Guimaras | 115890 | Sebaste-Bubog Es | Sibunag | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1933000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Guimaras | 302433 | Semion J. Jabasa National High School | Nueva Valencia | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Guimaras | 310902 | Supang National High School | Buenavista | 0 | 1 | 10 | 2STY10CL | BATCH 9 CL | 13048000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Guimaras | 302438 | Trinidad V. Canja-Sta. Teresa National High School | Jordan | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31353000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Guimaras | 302438 | Trinidad V. Canja-Sta. Teresa National High School | Jordan | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4834000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Guimaras | 115846 | Umilig Primary School | Buenavista | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1933000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 116717 | Andres Bonifacio Es | San Joaquin | 1 | 1 | 6 | 1STY3CL | BATCH 9 CL | 5884821.8728 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 116717 | Andres Bonifacio Es | San Joaquin | 1 |  | 1 | 1STY1CL | BATCH 9 CL | 1138254.6197 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302545 | Bacolod Nhs | Miagao | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2326509.2394 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 311024 | Bagacay Nhs | Tigbauan | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302479 | Camangahan Nhs | Guimbal | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302488 | Dapdap Nhs | Tigbauan | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Iloilo | 302495 | Don Felix Serra Nhs | San Joaquin | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302495 | Don Felix Serra Nhs | San Joaquin | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8850000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302495 | Don Felix Serra Nhs | San Joaquin | 1 |  | 9 | 3STY9CL | BATCH 13 CL | 15418925.24 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302499 | Escalantera Nhs | San Joaquin | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11443844.661 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302506 | Guimbal Nhs | Guimbal | 1 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302507 | Igbaras Nhs | Igbaras | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15418925.24 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302531 | Miag-Ao Nhs | Miag-Ao | 1 | 1 | 24 | 2STY12CL | BATCH 13 CL | 29158434.36 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Iloilo | 302542 | Oton Nhs | Oton | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302542 | Oton Nhs | Oton | 1 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302542 | Oton Nhs | Oton | 1 |  | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302549 | Particion Nhs | Guimbal | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Iloilo | 302566 | San Joaquin School Of Fisheries | San Joaquin | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2564500 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302566 | San Joaquin School Of Fisheries | San Joaquin | 1 | 1 | 12 | 2STY12CL | BATCH 13 CL | 14579217.18 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 311013 | Supt. Arsenio M. Napud Mnhs | Miagao | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Iloilo | 311013 | Supt. Arsenio M. Napud Mnhs | Miagao | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302578 | Tigbauan Nhs | Tigbauan | 1 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Iloilo | 302578 | Tigbauan Nhs | Tigbauan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Iloilo | 302583 | Tubungan Nhs | Tubungan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302446 | Alimodian Nhs | Alimodian | 2 | 1 | 8 | 2STY4CL | BATCH 9 CL | 12638675.2761 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302446 | Alimodian Nhs | Alimodian | 2 |  | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Iloilo | 302446 | Alimodian Nhs | Alimodian | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 311017 | Bancal Nhs | Alimodian | 2 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13872542.8037 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 311017 | Bancal Nhs | Alimodian | 2 |  | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302466 | Bololacao Nhs | New Lucena | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11660000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302470 | Buga Nhs | Leon | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 311028 | Dalid Nhs | Alimodian | 2 | 1 | 12 | 2STY6CL | BATCH 9 CL | 18162923.1122 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 182504 | Desamparados Amita Elementary School | Alimodian | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302513 | Jelicuon-Cabugao Nhs | New Lucena | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319337.6381 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302520 | Leganes Nhs | Leganes | 2 | 1 | 16 | 2STY8CL | BATCH 9 CL | 23170000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302520 | Leganes Nhs | Leganes | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 7380000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Iloilo | 302520 | Leganes Nhs | Leganes | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302522 | Leon Nhs | Leon | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11660000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302522 | Leon Nhs | Leon | 2 |  | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302522 | Leon Nhs | Leon | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 7380000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302539 | New Lucena Nchs | New Lucena | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302540 | New Lucena Nhs | New Lucena | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11660000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302550 | Pavia Nhs | Pavia | 2 | 1 | 20 | 2STY8CL | BATCH 9 CL | 23320000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302550 | Pavia Nhs | Pavia | 2 |  | 4 | 2STY4CL |  | 6936271.4 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 311027 | Sinamay Nhs | Alimodian | 2 | 1 | 8 | 2STY4CL | BATCH 13 CL | 13872542.808 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302573 | Sta. Barbara Nhs | Sta. Barbara | 2 | 1 | 16 | 2STY8CL | BATCH 9 CL | 23320000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302573 | Sta. Barbara Nhs | Sta. Barbara | 2 |  | 12 | 2STY6CL | BATCH 9 CL | 18042923.1122 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Iloilo | 302573 | Sta. Barbara Nhs | Sta. Barbara | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 311021 | Tacuyong Sur Nhs | Leon | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7016271.4019 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302585 | Zarraga Nhs | Zarraga | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302585 | Zarraga Nhs | Zarraga | 2 |  | 12 | 2STY6CL | BATCH 9 CL | 18042923.1122 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302585 | Zarraga Nhs | Zarraga | 2 |  | 8 | 2STY8CL | BATCH 9 CL | 11660000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302441 | Abangay Nhs | Janiuay | 3 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2904910.9364 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Iloilo | 302447 | Ambrosio Maido Mnhs | Cabatuan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2429549.27 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302452 | Badiangan Nhs | Badiangan | 3 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8707539.88 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 311020 | Caninguan Nhs | Lambunao | 3 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8664965.05 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 311020 | Caninguan Nhs | Lambunao | 3 |  | 4 | 2STY4CL | BATCH 9 CL | 6569337.64 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Iloilo | 311020 | Caninguan Nhs | Lambunao | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 311003 | Jayobo Nhs | Lambunao | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6569337.64 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 311003 | Jayobo Nhs | Lambunao | 3 |  | 10 | 2STY10CL | BATCH 9 CL | 12971310.09 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Iloilo | 311003 | Jayobo Nhs | Lambunao | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 311025 | Jovito Alfaras Rivera Nhs | Bingawan | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6569337.64 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Iloilo | 311025 | Jovito Alfaras Rivera Nhs | Bingawan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Iloilo | 311025 | Jovito Alfaras Rivera Nhs | Bingawan | 3 |  | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302559 | Leon Mediana Nhs | Maasin | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6569337.64 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Iloilo | 302559 | Leon Mediana Nhs | Maasin | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302526 | Malitbog Nhs | Calinog | 3 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8664965.05 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Iloilo | 302526 | Malitbog Nhs | Calinog | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Iloilo | 302546 | Palanguia Nhs | Pototan | 3 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4834000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302546 | Palanguia Nhs | Pototan | 3 | 1 | 9 | 3STY9CL | BATCH 9 CL | 13816701.59 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302580 | Tina Nhs | Badiangan | 3 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8664965.05 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Iloilo | 302580 | Tina Nhs | Badiangan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302489 | De La Paz Nhs | Banate | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6569337.64 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302489 | De La Paz Nhs | Banate | 4 |  | 4 | 2STY4CL | BATCH 9 CL | 6569337.64 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302543 | Pagdugue Nhs | Dumangas | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6569337.64 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Iloilo | 302543 | Pagdugue Nhs | Dumangas | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 311006 | Pd Monfort National Science Hs | Dumangas | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6569337.64 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 311006 | Pd Monfort National Science Hs | Dumangas | 4 |  | 4 | 2STY4CL | BATCH 9 CL | 6569337.64 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302443 | Ajuy National High School | Ajuy | 5 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8814965.05 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302443 | Ajuy National High School | Ajuy | 5 |  | 8 | 2STY4CL | BATCH 13 CL | 13438675.28 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 116769 | Alfredo Sanson Mes | Sara | 5 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11077342.59 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 116769 | Alfredo Sanson Mes | Sara | 5 |  | 4 | 2STY4CL | BATCH 9 CL | 6719337.64 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 116771 | Apelo Es | Sara | 5 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6719337.64 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 116771 | Apelo Es | Sara | 5 |  | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 116772 | Ardemil Es | Sara | 5 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 116012 | Balasan Ces | Balasan | 5 | 1 | 18 | 3STY9CL | BATCH 13 CL | 30242655.84 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 116012 | Balasan Ces | Balasan | 5 |  | 6 | 2STY6CL | BATCH 13 CL | 8864965.05 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 116012 | Balasan Ces | Balasan | 5 |  | 6 | 2STY6CL | BATCH 13 CL | 8864965.05 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302454 | Balasan National High School | Balasan | 5 | 1 | 20 | 2STY10CL | BATCH 9 CL | 28066882.2047 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302454 | Balasan National High School | Balasan | 5 |  | 6 | 2STY6CL | BATCH 9 CL | 8864965.05 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302454 | Balasan National High School | Balasan | 5 |  | 16 | 2STY8CL | BATCH 9 CL | 23900153.7017 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 116201 | Bancal Es | Carles | 5 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 116201 | Bancal Es | Carles | 5 |  | 4 | 2STY4CL | BATCH 13 CL | 6719337.64 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 116202 | Barangcalan Es | Carles | 5 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3195402.03 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302458 | Barotac Viejo National High School | Barotac Viejo | 5 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8814965.05 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302458 | Barotac Viejo National High School | Barotac Viejo | 5 |  | 24 | 2STY8CL | BATCH 9 CL | 35850230.5526 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302460 | Batad National High School | Batad | 5 | 1 | 8 | 2STY8CL | BATCH 1 CL | 11027342.5917 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302460 | Batad National High School | Batad | 5 |  | 24 | 2STY8CL | BATCH 1 CL | 33232027.7751 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302462 | Bayas National High School | Estancia | 5 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7319337.64 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302493 | Carlos Lopez National High School | San Dionisio | 5 | 1 | 16 | 2STY8CL | BATCH 9 CL | 23900153.7017 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302493 | Carlos Lopez National High School | San Dionisio | 5 |  | 4 | 2STY4CL | BATCH 9 CL | 6319337.6381 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302482 | Cawayan National High School | Carles | 5 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6719337.64 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302482 | Cawayan National High School | Carles | 5 |  | 6 | 2STY6CL | BATCH 3 CL | 8814965.05 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302482 | Cawayan National High School | Carles | 5 |  | 6 | 2STY6CL | BATCH 3 CL | 8814965.05 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 116241 | Claudia Morata Villarias Ms | Concepcion | 5 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 116488 | Concepcion Juanillo Mes | Lemery | 5 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302486 | Culasi National High School | Ajuy | 5 | 1 | 8 | 2STY4CL | BATCH 3 CL | 13438675.28 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302486 | Culasi National High School | Ajuy | 5 |  | 6 | 2STY6CL | BATCH 3 CL | 8814965.05 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 116775 | Del Castillo Es | Sara | 5 | 1 | 4 | 1STY2CL | BATCH 9 CL | 3489488.872 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 116775 | Del Castillo Es | Sara | 5 |  | 3 | 1STY3CL | BATCH 9 CL | 2904910.9364 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302500 | Estancia National High School | Estancia | 5 | 1 | 12 | 2STY6CL | BATCH 9 CL | 17779930.1 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302500 | Estancia National High School | Estancia | 5 |  | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302500 | Estancia National High School | Estancia | 5 |  | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302500 | Estancia National High School | Estancia | 5 |  | 16 | 2STY8CL | BATCH 9 CL | 23900153.7017 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Iloilo | 302500 | Estancia National High School | Estancia | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2450333.3333 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Iloilo | 302502 | Gen. Luna Nhs | Barotac Viejo | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 116350 | Gogo Es | Estancia | 5 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2802592.44 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302505 | Granada Nhs | Carles | 5 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9736461.555 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 311009 | Granada Nhs-Ballesteros Campus | Carles | 5 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12170076.849 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 311009 | Granada Nhs-Ballesteros Campus | Carles | 5 |  | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302521 | Lemery National High School | Lemery | 5 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8814965.05 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302521 | Lemery National High School | Lemery | 5 |  | 4 | 2STY4CL | BATCH 13 CL | 6569337.64 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 311007 | Loong Nhs | Concepcion | 5 | 1 | 12 | 2STY6CL | BATCH 9 CL | 14816937.0918 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 116783 | Malapaya Es | Sara | 5 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2904910.9364 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 116783 | Malapaya Es | Sara | 5 |  | 6 | 2STY6CL | BATCH 9 CL | 8864965.05 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 116783 | Malapaya Es | Sara | 5 |  | 1 | 1STY1CL | BATCH 9 CL | 1113254.6197 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302541 | Nicomedes R. Tubar Sr. National High School | San Dionisio | 5 | 1 | 16 | 2STY8CL | BATCH 9 CL | 23900153.7017 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302541 | Nicomedes R. Tubar Sr. National High School | San Dionisio | 5 |  | 6 | 2STY6CL | BATCH 9 CL | 8814965.05 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302555 | Polopiña Nhs | Concepcion | 5 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302555 | Polopiña Nhs | Concepcion | 5 |  | 1 | 1STY1CL | BATCH 9 CL | 1224580.0817 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302484 | Roberto H. Tirol National High School | Concepcion | 5 | 1 | 16 | 2STY8CL | BATCH 1 CL | 21804685.1834 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302484 | Roberto H. Tirol National High School | Concepcion | 5 |  | 12 | 2STY6CL | BATCH 1 CL | 17769930.1 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302569 | San Rafael Nhs | San Rafael | 5 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6799337.64 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302569 | San Rafael Nhs | San Rafael | 5 |  | 8 | 2STY8CL | BATCH 9 CL | 11237342.59 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302569 | San Rafael Nhs | San Rafael | 5 |  | 9 | 3STY9CL | BATCH 9 CL | 13830000 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 311004 | Santiago Nhs | Barotac Viejo | 5 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6719337.64 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Iloilo | 311004 | Santiago Nhs | Barotac Viejo | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302570 | Sara National High School | Sara | 5 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8864965.05 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302570 | Sara National High School | Sara | 5 |  | 16 | 2STY8CL | BATCH 13 CL | 23975153.698 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302570 | Sara National High School | Sara | 5 |  | 8 | 2STY8CL | BATCH 13 CL | 11950076.849 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 116695 | Talo-Ato Ps | San Dionisio | 5 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2904910.9364 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 311012 | Tambaliza Nhs | Concepcion | 5 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12170076.849 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 311012 | Tambaliza Nhs | Concepcion | 5 |  | 6 | 2STY6CL | BATCH 9 CL | 9736461.555 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 311001 | Valerio Palmares National High School | Batad | 5 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6624337.64 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 311001 | Valerio Palmares National High School | Batad | 5 |  | 8 | 2STY8CL | BATCH 9 CL | 12040076.8509 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo City | 302738 | Iloilo City Nhs | Iloilo City (Capital) | 0 | 1 | 24 | 4STY12CL | BATCH 9 CL | 40334214.92 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo City | 302738 | Iloilo City Nhs | Iloilo City (Capital) | 0 |  | 40 | 4STY20CL | BATCH 9 CL | 57041951.34 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo City | 302742 | Jalandoni Mnhs | Iloilo City (Capital) | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 28520975.67 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo City | 302744 | Jaro Nhs | Iloilo City (Capital) | 0 | 1 | 12 | 4STY12CL | BATCH 9 CL | 20167107.46 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo City | 302744 | Jaro Nhs | Iloilo City (Capital) | 0 |  | 20 | 4STY20CL | BATCH 9 CL | 28520975.67 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo City | 302744 | Jaro Nhs | Iloilo City (Capital) | 0 |  | 12 | 4STY12CL | BATCH 9 CL | 20167107.46 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo City | 302747 | La Paz Nhs | Iloilo City (Capital) | 0 | 1 | 12 | 3STY12CL | BATCH 3 CL | 17127665.62 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo City | 302747 | La Paz Nhs | Iloilo City (Capital) | 0 |  | 6 | 3STY6CL | BATCH 3 CL | 10316033.27 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo City | 117606 | La Paz Nhs To La Paz Es I | Iloilo City (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo City | 302750 | Ramon Avancena Nhs | Iloilo City (Capital) | 0 | 1 | 16 | 4STY16CL | BATCH 1 CL | 27914453.1855 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302473 | Cabatuan Nchs | Cabatuan | 3 | 1 | 24 | 4STY24CL | BATCH 13 CL | 39140882.854 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302473 | Cabatuan Nchs | Cabatuan | 3 |  | 15 | 3STY15CL | BATCH 13 CL | 23506314.795 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302477 | Calinog Nchs | Calinog | 3 | 1 | 15 | 3STY15CL | BATCH 13 CL | 23506314.795 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302477 | Calinog Nchs | Calinog | 3 |  | 9 | 3STY9CL | BATCH 13 CL | 16618460.712 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302512 | Janiuay Nchs | Janiuay | 3 | 1 | 9 | 3STY9CL | BATCH 13 CL | 16618460.712 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302512 | Janiuay Nchs | Janiuay | 3 |  | 12 | 3STY12CL | BATCH 13 CL | 20029495.669 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302517 | Lambunao Nhs | Lambunao | 3 | 1 | 15 | 3STY15CL | BATCH 13 CL | 23506314.795 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302517 | Lambunao Nhs | Lambunao | 3 |  | 12 | 3STY12CL | BATCH 13 CL | 20029495.669 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302524 | Maasin Nhs | Maasin | 3 | 1 | 12 | 3STY12CL | BATCH 13 CL | 20029495.669 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302533 | Mina Nhs | Mina | 3 | 1 | 8 | 2STY4CL | BATCH 13 CL | 12638675.28 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302533 | Mina Nhs | Mina | 3 |  | 6 | 2STY6CL | BATCH 13 CL | 8404965.045 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302556 | Pototan Nhs | Pototan | 3 | 1 | 9 | 3STY9CL | BATCH 13 CL | 16618460.712 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302556 | Pototan Nhs | Pototan | 3 |  | 6 | 2STY6CL | BATCH 13 CL | 8404965.045 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302556 | Pototan Nhs | Pototan | 3 |  | 12 | 3STY12CL | BATCH 13 CL | 20029495.669 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302556 | Pototan Nhs | Pototan | 3 |  | 6 | 3STY6CL | BATCH 13 CL | 11443844.661 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302556 | Pototan Nhs | Pototan | 3 |  | 6 | 3STY6CL | BATCH 13 CL | 11443844.661 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302449 | Anilao Nhs | Anilao | 4 | 1 | 12 | 2STY12CL | BATCH 13 CL | 14579217.18 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302455 | Banate Nhs | Banate | 4 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302457 | Barotac Nuevo Cnhs | Barotac Nuevo | 4 | 1 | 20 | 4STY20CL | BATCH 13 CL | 34198179.297 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302457 | Barotac Nuevo Cnhs | Barotac Nuevo | 4 |  | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302490 | Dingle Nhs | Dingle | 4 | 1 | 12 | 3STY6CL | BATCH 13 CL | 22887689.322 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302497 | Dueñas Nhs | Dueñas | 4 | 1 | 28 | 4STY28CL | BATCH 13 CL | 44059740.754 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302497 | Dueñas Nhs | Dueñas | 4 |  | 32 | 4STY32CL | BATCH 13 CL | 48970442.044 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Iloilo | 302498 | Dumangas Nhs | Dumangas | 4 | 1 | 24 | 4STY24CL | BATCH 13 CL | 39140882.854 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302564 | San Enrique Nhs | San Enrique | 4 | 1 | 12 | 4STY12CL | BATCH 13 CL | 24352577.982 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Iloilo | 302564 | San Enrique Nhs | San Enrique | 4 |  | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Passi City | 302806 | Efraim M. Santibañez National High School | City Of Passi | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6569337.64 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Passi City | 302804 | Mulapula National High School | City Of Passi | 4 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13138675.28 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Passi City | 302805 | Passi National High School | City Of Passi | 4 |  | 45 | 3STY15CL | BATCH 9 CL | 68783507.97 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Passi City | 302805 | Passi National High School | City Of Passi | 4 | 1 | 15 | 3STY15CL | BATCH 9 CL | 22927835.99 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Passi City | 302805 | Passi National High School | City Of Passi | 4 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4350600 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Passi City | 302807 | Salngan National High School | City Of Passi | 4 | 1 | 12 | 2STY6CL | BATCH 9 CL | 17329930.1 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Roxas City | 117666 | Banica Elementary School | Roxas City (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.59 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Roxas City | 302757 | Cong. Ramon A. Arnaldo Hs | Roxas City (Capital) | 1 | 1 | 24 | 2STY6CL | BATCH 5 CL | 33456660 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VI | Roxas City | 302757 | Cong. Ramon A. Arnaldo Hs | Roxas City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.27 |  |  | Completed | 1
NC 2016 | SHS | Region VI | Roxas City | 311702 | Roxas City School For Philippine Craftsmen | Roxas City (Capital) | 1 | 1 | 24 | 2STY6CL | BATCH 1 CL | 33808660 |  |  | Completed | 1
NC 2016 | K10 | Region VI | Capiz | 115597 | Agkawayan Ps | Mambusao | 2 | 1 | 2 | 1STY2CL w/ toilet attached | BATCH 14 CL | 1949806.0072 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114711 | Tag-osip Elementary School | BURUANGA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2713745.93 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114836 | Castillo ES | MAKATO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2698745.93 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114899 | Don B. Refundo MES | NEW WASHINGTON | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2688745.93 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 114968 | Mayos ES | BARBAZA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2663745 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 114980 | Sinaja-Salvacion ES | BELISON | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 114990 | Igsoro ES | BUGASONG | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2863745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 114992 | Lacayon ES | BUGASONG | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2673745 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115003 | Alegria ES | CALUYA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3043745 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115028 | Bagacay ES | CULASI | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115032 | Batonan ES | CULASI | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 3793435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115032 | Batonan ES | CULASI | 0 |  | 3 | 1STY3CL | BATCH 4 | 3793435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115040 | Esperanza ES | CULASI | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115059 | Valderrama ES | CULASI | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115061 | Bongbongan I-II ES | HAMTIC | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2793745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115086 | Fabrica ES | HAMTIC | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115095 | Pili ES | HAMTIC | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2763745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115099 | Villavert MES | HAMTIC | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 3838435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115109 | Latazon PS | LAUA-AN | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115118 | Oloc ES | LAUA-AN | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115133 | Paz ES | LIBERTAD | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2713745 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115134 | Pucio ES | LIBERTAD | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2763745 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115138 | Tinigbas ES | LIBERTAD | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2663745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115208 | Tigbalogo ES | PATNONGON | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2763747 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115191 | Villa Salomon ES | PATNONGON | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2763746 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115231 | San Fernando ES | SAN JOSE (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115252 | Agricula ES | SAN REMIGIO | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2763745 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115253 | Alegria PS | SAN REMIGIO | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 4198435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115253 | Alegria PS | SAN REMIGIO | 0 |  | 3 | 1STY3CL | BATCH 4 | 4198435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115289 | Bongbongan I ES | SIBALOM | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2653744.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115289 | Bongbongan I ES | SIBALOM | 0 |  | 2 | 1STY2CL | BATCH 4 | 2653744.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115311 | Bululacao ES | SIBALOM | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2678745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115311 | Bululacao ES | SIBALOM | 0 |  | 2 | 1STY2CL | BATCH 4 | 2678745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115313 | Catmon ES | SIBALOM | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115317 | Igcocok ES | SIBALOM | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2673745 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115298 | Igsuming ES | SIBALOM | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2633745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115320 | Indag-an ES | SIBALOM | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2673745 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115322 | Insarayan ES | SIBALOM | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2643745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115331 | Pis-anan CS | SIBALOM | 0 | 1 | 4 | 1STY4CL | BATCH 4 | 4888351.15 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bacolod City | 117463 | A. Mabini ES | BACOLOD CITY (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3070000 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bacolod City | 117468 | A.L. Jayme ES | BACOLOD CITY (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3000000 |  |  | Completed | 1 | [10 empty] | WITH PUNCHLISTED DEFECTS - INCOMPLETE RECTIFICATION.
NC 2017 | K10 | Region VI | Bacolod City | 117478 | DoÃ±a E.J. Garcia ES | BACOLOD CITY (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 4036402.87 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bacolod City | 117475 | Don Crispino V. Ramos ES | BACOLOD CITY (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 4036402.87 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bago City | 117493 | A. M. Espinos ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2728267.98 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bago City | 117503 | B. Araneta ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2744779.38 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bago City | 117505 | Dr. A. Sian ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2778267.98 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bago City | 117506 | Gen. Juan A. Araneta ES | BAGO CITY | 4 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 4 | 5125243.98 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bago City | 117506 | Gen. Juan A. Araneta ES | BAGO CITY | 4 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2734419.38 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bago City | 117498 | J.L. Araneta Elementary School | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2734419.38 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bago City | 117507 | Jalsis ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2734419.38 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bago City | 117510 | M.L. Araneta ES | BAGO CITY | 4 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 4 | 5122999.34 |  |  | REVERTED | 0 | [10 empty] | Unfunded
NC 2017 | K10 | Region VI | Bago City | 117501 | T.M. Morada Sr. ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2728267.98 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Escalante City | 302595 | Buenavista NHS | CITY OF ESCALANTE | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3944413.41 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Escalante City | 302595 | Buenavista NHS | CITY OF ESCALANTE | 1 |  | 3 | 1STY3CL | BATCH 4 | 4068435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Escalante City | 117041 | Danao Port ES | CITY OF ESCALANTE | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 4068435.02 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Escalante City | 302615 | Dian-ay National High School | CITY OF ESCALANTE | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2988254.77 |  |  | REVERTED | 0
NC 2017 | K10 | Region VI | Escalante City | 117043 | Escalante CES | CITY OF ESCALANTE | 1 | 1 | 4 | 1STY4CL | BATCH 4 | 5188351.15 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Escalante City | 117046 | Jonobjonob ES | CITY OF ESCALANTE | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2913745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Escalante City | 302660 | Mabini National High School | CITY OF ESCALANTE | 1 | 1 | 5 | WORKSHOP BLDG (7x18) | BATCH 4 | 17929528.62 |  |  | REVERTED | 0
NC 2017 | SHS | Region VI | Escalante City | 302626 | Old Poblacion National High School | CITY OF ESCALANTE | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2913745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Escalante City | 302626 | Old Poblacion National High School | CITY OF ESCALANTE | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 4 | 5976509.54 |  |  | REVERTED | 0
NC 2017 | K10 | Region VI | Escalante City | 117050 | Tamlang ES | CITY OF ESCALANTE | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2913745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Escalante City | 302627 | Tamlang NHS | CITY OF ESCALANTE | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Escalante City | 117052 | Washington ES | CITY OF ESCALANTE | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 115956 | Cuyad Elementary School | ALIMODIAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2888254.17 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116359 | Camangahan ES Ext. | GUIMBAL | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116359 | Camangahan ES Ext. | GUIMBAL | 1 |  | 3 | 1STY3CL | BATCH 4 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Kabankalan City | 117856 | Camansi ES | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY3CL | BATCH 4 | 3978202.4 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Kabankalan City | 117887 | Magballo ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 2781943.14 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Kabankalan City | 117892 | Salong ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 2768032.36 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Kabankalan City | 117893 | San Jose ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 2772133.72 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Kabankalan City | 117869 | Tabugon ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 2814243.51 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Kabankalan City | 302797 | Tabugon NHS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 2780463.27 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Kabankalan City | 117870 | Tagoc ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 2781943.14 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Kabankalan City | 302790 | TAGUKON NATIONAL HIGH SCHOOL | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 2847936.07 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Kabankalan City | 117895 | Tapi ES | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY3CL | BATCH 4 | 4018606.34 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114625 | Altavas ES | ALTAVAS | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2904852.13 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Aklan | 302309 | Jose Feliciano Meñez Memorial National High School | BALETE | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2649437.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114659 | Badiangan ES | BANGA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2751745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114666 | Don Edecio S. Venturanza Memorial Elementary School | BANGA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2751745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114669 | Mangan ES | BANGA | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4166285.02 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Aklan | 302290 | Petronilo C. Ibadlit National High school | BANGA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2649437.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114684 | Cabugao ES | BATAN | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4020411.12 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114690 | Lupit ES | BATAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2751745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114696 | Palay Integrated School | BATAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114746 | Andagaw Elementary School | KALIBO (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114751 | Nalook Elementary School | KALIBO (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2704308.42 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114761 | Tigayon Elementary School | KALIBO (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2704693.42 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114765 | Ibao ES | LEZO | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3823435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114769 | Uldario P. Custodio ES | LEZO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2668745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114770 | Agbatuan PS | LIBACAO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2972887.42 |  |  | REVERTED | 0
NC 2017 | K10 | Region VI | Aklan | 114772 | Alfonso XII ES | LIBACAO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2713995.12 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114778 | Calacabian ES | LIBACAO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2663114.36 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114779 | Calamcan ES | LIBACAO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2650063.95 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114783 | Guadalupe ES | LIBACAO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2749074.78 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114789 | Manika ES | LIBACAO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2872846.28 |  |  | REVERTED | 0
NC 2017 | K10 | Region VI | Aklan | 114791 | Maytaraw PS | LIBACAO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3206433.09 |  |  | REVERTED | 0
NC 2017 | K10 | Region VI | Aklan | 114792 | Ogsip PS | LIBACAO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2653144.26 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114793 | Ortega IS | LIBACAO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2809011.14 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 310609 | Ortega IS | LIBACAO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2809011.14 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114798 | Rosal ES | LIBACAO | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 5169366.07 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114822 | Pang-itan Elementary School | MADALAG | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2763745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114822 | Pang-itan Elementary School | MADALAG | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2648745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Aklan | 302305 | Anselmo B. Legaspi NHS | MAKATO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2636309.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114834 | Calangcang ES | MAKATO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2708745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114835 | Calimbajan-Tina ES | MAKATO | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3829960.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114870 | Rosario ES | MALINAO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2643745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 310626 | San Roque Integrated School | MALINAO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2643745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114883 | LASERNA ELEMENTARY SCHOOL | NABAS | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3938605.54 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114887 | Nabas ES | NABAS | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3889621.45 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114895 | Unidos Elementary School | NABAS | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2732423.6 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114897 | Candelaria ES | NEW WASHINGTON | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3861396.65 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114898 | Cawayan ES | NEW WASHINGTON | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3851396.65 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114900 | Dumaguit ES | NEW WASHINGTON | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2736210.26 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114902 | Guinbaliwan ES | NEW WASHINGTON | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3889621.45 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114904 | Jugas ES | NEW WASHINGTON | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3889621.45 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114907 | New Washington ES | NEW WASHINGTON | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3889621.45 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114907 | New Washington ES | NEW WASHINGTON | 1 |  | 2 | 1STY2CL | BATCH 7 | 2664513.63 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114932 | Panayakan Elementary School | TANGALAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2753745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Antique | 310710 | Dr. Luis E. Baraquia NHS | SIBALOM | 0 | 1 | 4 | 1STY4CL | BATCH 7 | 4948351.15 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115315 | Egaña ES | SIBALOM | 0 | 1 | 3 | 1STY3CL | BATCH 7 | 3818435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115332 | Tabong-Tabong ES | SIBALOM | 0 | 1 | 3 | 1STY3CL | BATCH 7 | 3918435.02 |  |  | Terminated | 0 | [10 empty] | For request of funding to complete
NC 2017 | K10 | Region VI | Antique | 115332 | Tabong-Tabong ES | SIBALOM | 0 |  | 3 | 1STY3CL | BATCH 7 | 3918435.02 |  |  | Terminated | 0 | [10 empty] | For request of funding to complete
NC 2017 | K10 | Region VI | Antique | 115337 | Tulatula ES | SIBALOM | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2663745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115346 | Nonghinong ES | TIBIAO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2723746.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115346 | Nonghinong ES | TIBIAO | 0 |  | 2 | 1STY2CL | BATCH 7 | 2723746.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115354 | Tuno ES | TIBIAO | 0 | 1 | 3 | 1STY3CL | BATCH 7 | 3798435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115361 | Camansi ES | TOBIAS FORNIER (DAO) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2813745.92 |  |  | Terminated | 1 | [10 empty] | For request of funding to complete
NC 2017 | K10 | Region VI | Antique | 115380 | Nagsubuan ES | TOBIAS FORNIER (DAO) | 0 | 1 | 4 | 1STY4CL | BATCH 7 | 5038351.15 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bago City | 117513 | Atipuluan ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2728267.98 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bago City | 117515 | Caridad ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2728267.98 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bago City | 117509 | Lag-asan ES | BAGO CITY | 4 | 1 | 5 | 1STY5CL W/ TOILET | BATCH 7 | 6270334.67 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bago City | 117523 | Ma-ao ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2659107.95 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bago City | 117524 | Mailum ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2778267.98 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115417 | Carataya ES (cuartero) | CUARTERO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2686120.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115419 | Lunayan E/S | CUARTERO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2636695.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115420 | Mahabang Sapa PS | CUARTERO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2633745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115420 | Mahabang Sapa PS | CUARTERO | 2 |  | 2 | 1STY2CL | BATCH 7 | 2709370.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115429 | Agtambi PS | DAO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2651995.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115431 | Bita PS | DAO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115432 | Centro PS | DAO | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115434 | Daplas PS | DAO | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3871710.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115483 | Dumarao CS | DUMARAO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115482 | Eduardo Abalo, Sr. ES | DUMARAO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2671118.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115485 | Guinotos ES | DUMARAO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2690245.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115486 | Janguslob ES | DUMARAO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115499 | Agustin P. Navarra ES | IVISAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115500 | Almon PS | IVISAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115511 | Panfilo Mendoza ES | IVISAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2644597.19 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115513 | Tigis PS | IVISAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3922691.36 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115539 | North Lucero PS | JAMINDAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2633745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115542 | San Jose ES (jamindan) | JAMINDAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115544 | San Vicente ES (jamindan) | JAMINDAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2659771.55 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115599 | Angelo Llorente ES (bunga es) | MAMBUSAO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115588 | Cala-agus ES | MAMBUSAO | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115589 | Eusebio Villareal MS | MAMBUSAO | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115687 | Yating ES | PILAR | 1 | 1 | 4 | 2STY4CL | BATCH 7 | 8348972.94 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115726 | Agsilab Elementary School | SAPI-AN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2618745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115730 | Apogan PS | SAPI-AN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3798435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115732 | Benlit ES | SAPI-AN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2761526.09 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115734 | Bulon PS | SAPI-AN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2750658.63 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115750 | Balogo PS | SIGMA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2623745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115754 | Fructousa A. de Romero PS | SIGMA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2651995.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115756 | Loreto A. Balgos ES | SIGMA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2675448.46 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115751 | Simeon Bidiones Elementary School | SIGMA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2709370.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115790 | San Antonio ES (tapaz east) | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115793 | San Miguel Ilawod ES | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115794 | San Miguel Ilaya ES | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2651995.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115795 | San Roque ES (tapaz east) | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Guimaras | 115835 | Agsanayan ES | BUENAVISTA | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2820436.5 |  |  | Completed | 1 |  |  | 17GE0059 |  |  | 2017-09-07 | 2017-09-07 | 2017-12-04 | 2017-12-12 | ALJ Construction and Supply
NC 2017 | K10 | Region VI | Guimaras | 115838 | East Valencia ES | BUENAVISTA | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2820436.5 |  |  | Completed | 1 |  |  | 17GE0060 |  |  | 2017-09-05 | 2017-09-05 | 2017-12-04 | 2017-12-12 | ALJ Construction and Supply
NC 2017 | SHS | Region VI | Guimaras | 302431 | Getulio NHS | BUENAVISTA | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2820436.5 |  |  | Completed | 1 |  |  | 17GE0072 |  |  | 2017-09-14 | 2017-09-14 | 2017-12-04 | 2017-12-12 | ALJ Construction and Supply
NC 2017 | K10 | Region VI | Guimaras | 115826 | Old Poblacion ES | BUENAVISTA | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2820436.5 |  |  | Completed | 1 |  |  | 17GE0058 |  |  | 2017-09-05 | 2017-09-05 | 2017-12-04 | 2017-12-12 | ALJ Construction and Supply
NC 2017 | K10 | Region VI | Guimaras | 115841 | Piña Elementary School | BUENAVISTA | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2820436.5 |  |  | Completed | 1 |  |  | 17GE0061 |  |  | 2017-09-05 | 2017-09-05 | 2017-12-04 | 2017-12-12 | ST Salcedo Construction Corp.
NC 2017 | K10 | Region VI | Guimaras | 115842 | San Isidro ES | BUENAVISTA | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2820436.5 |  |  | Completed | 1 |  |  | 17GE0066 |  |  | 2017-09-12 | 2017-09-12 | 2017-12-04 | 2017-12-12 | ALJ Construction and Supply
NC 2017 | K10 | Region VI | Guimaras | 115844 | Supang CS | BUENAVISTA | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2820436.5 |  |  | Completed | 1 |  |  | 17GE0067 |  |  | 2017-09-12 | 2017-09-12 | 2017-12-04 | 2017-12-12 | ALJ Construction and Supply
NC 2017 | K10 | Region VI | Guimaras | 115892 | Calaya ES | NUEVA VALENCIA | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2820436.5 |  |  | Completed | 1 |  |  | 17GE0064 |  |  | 2017-09-12 | 2017-09-12 | 2017-12-04 | 2017-12-12 | RD Mandanas Construxction
NC 2017 | K10 | Region VI | Guimaras | 115894 | Dolores ES | NUEVA VALENCIA | 0 | 1 | 3 | 1STY3CL | BATCH 7 | 3890070.24 |  |  | Completed | 1 |  |  | 17GE0073 |  |  | 2017-09-14 | 2017-09-14 | 2017-12-04 | 2017-12-12 | ALJ Construction and Supply
NC 2017 | K10 | Region VI | Guimaras | 115908 | La Paz ES | NUEVA VALENCIA | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2820436.5 |  |  | Completed | 1 |  |  | 17GE0070 |  |  | 2017-09-14 | 2017-09-14 | 2017-12-04 | 2017-12-12 | ALJ Construction and Supply
NC 2017 | K10 | Region VI | Guimaras | 115896 | Magamay ES | NUEVA VALENCIA | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2820436.5 |  |  | Completed | 1 |  |  | 17GE0065 |  |  | 2017-09-12 | 2017-09-12 | 2017-12-04 | 2017-12-12 | ALJ Construction and Supply
NC 2017 | K10 | Region VI | Guimaras | 115915 | Salvacion CS | NUEVA VALENCIA | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2820436.5 |  |  | Completed | 1 |  |  | 17GE0071 |  |  | 2017-09-14 | 2017-09-14 | 2017-12-04 | 2017-12-12 | ALJ Construction and Supply
NC 2017 | K10 | Region VI | Guimaras | 115849 | Constancia ES | SAN LORENZO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2820436.5 |  |  | Completed | 1 |  |  | 17GE0068 |  |  | 2017-09-12 | 2017-09-12 | 2017-12-04 | 2017-12-12 | ALJ Construction and Supply
NC 2017 | K10 | Region VI | Iloilo | 115978 | Balunos ES | ANILAO | 4 | 1 | 3 | 1STY3CL | BATCH 7 | 3415097.1 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 115986 | Medina ES | ANILAO | 4 | 1 | 3 | 1STY3CL | BATCH 7 | 3458882.83 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 115994 | Bitaoyan ES | BADIANGAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2278230.85 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 115998 | Calansanan ES | BADIANGAN | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 3260355.07 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116000 | Iniligan ES | BADIANGAN | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 3271929.41 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116004 | Manaolan ES | BADIANGAN | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 3328044.51 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116005 | Mapili ES | BADIANGAN | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 3311042.63 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116008 | Tamocol ES | BADIANGAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2278230.85 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116009 | Tina ES | BADIANGAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2278230.85 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116012 | Balasan CES | BALASAN | 5 | 1 | 2 | 1STY2CL | BATCH 7 | 2870000 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Iloilo | 302455 | Banate NHS | BANATE | 4 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 5679161.32 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Iloilo | 302457 | Barotac Nuevo National Comprehensive High School | BAROTAC NUEVO | 4 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 5435485.35 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116045 | Guintas ES | BAROTAC NUEVO | 4 | 1 | 3 | 1STY3CL | BATCH 7 | 3260355.07 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Iloilo | 302473 | Cabatuan NCHS | CABATUAN | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2871036.86 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116146 | Marin ES | CABATUAN | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 3269614.54 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116128 | Martin Cubil ES | CABATUAN | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 3426262.45 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116177 | Banban Elementary School | CALINOG | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 3260355.07 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116195 | San Julian Elementary School | CALINOG | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2360895.72 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116271 | Calicuang ES | DINGLE | 4 | 1 | 3 | 1STY3CL | BATCH 7 | 3263466.54 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Iloilo | 302490 | Dingle NHS | DINGLE | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2738874.01 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116284 | Siniba-an ES | DINGLE | 4 | 1 | 3 | 1STY3CL | BATCH 7 | 3260355.07 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116319 | Bantud-Managuit ES | DUMANGAS | 4 | 1 | 3 | 1STY3CL | BATCH 7 | 3260355.07 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116340 | P.D. Monfort ES | DUMANGAS | 4 | 1 | 3 | 1STY3CL | BATCH 7 | 3426262.45 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116342 | Paloc Bigque ES | DUMANGAS | 4 | 1 | 3 | 1STY3CL | BATCH 7 | 3260355.07 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116330 | Sulangan ES | DUMANGAS | 4 | 1 | 3 | 1STY3CL | BATCH 7 | 3518790.39 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116390 | Calmay ES | JANIUAY | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2278230.85 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Iloilo | 302512 | Janiuay NCHS | JANIUAY | 3 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 9100845.05 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116396 | Kuyot Elementary School | JANIUAY | 3 | 1 | 1 | 1STY1CL | BATCH 7 | 1300103.44 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116413 | Madong CES | JANIUAY | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 3263466.54 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116416 | Martin Tirador MES | JANIUAY | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2278230.85 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116424 | Binaba-an ES | LAMBUNAO | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2278230.85 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 180024 | Caguisanan ES | LAMBUNAO | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2396468.35 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116451 | Caninguan CS | LAMBUNAO | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2281342.32 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116457 | Hipgos ES | LAMBUNAO | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2273005.95 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Iloilo | 302547 | Panuran NHS | LAMBUNAO | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2256623.43 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116465 | Pughanan ES | LAMBUNAO | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2256623.43 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116543 | Layog ES | MAASIN | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 3260355.07 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116556 | Quiling ES | MAASIN | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 3284447.45 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116670 | PALANGUIA ELEMENTARY SCHOOL | POTOTAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2278230.85 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116671 | Rizal ES | POTOTAN | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 3518790.39 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116703 | Garita ES | SAN ENRIQUE | 4 | 1 | 3 | 1STY3CL | BATCH 7 | 3494747.01 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116706 | Imbaquiran PS | SAN ENRIQUE | 4 | 1 | 2 | 1STY2CL | BATCH 7 | 2364487.43 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116711 | Paga ES | SAN ENRIQUE | 4 | 1 | 2 | 1STY2CL | BATCH 7 | 2281342.32 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Iloilo | 302564 | San Enrique NCHS | SAN ENRIQUE | 4 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 5848342.53 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Kabankalan City | 117831 | Ballo ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 7 | 2666000.64 |  |  | Reverted | 0
NC 2017 | K10 | Region VI | Kabankalan City | 117832 | Basak ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 7 | 2729854.38 |  |  | Reverted | 0
NC 2017 | K10 | Region VI | Kabankalan City | 117835 | Camingawan ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 7 | 2705769.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Kabankalan City | 117835 | Camingawan ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 7 | 2705769.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Kabankalan City | 312103 | Hinapunan Integrated School | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 7 | 2661302.64 |  |  | Reverted | 0
NC 2017 | K10 | Region VI | Kabankalan City | 117847 | Oringao ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 7 | 2651389.86 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Kabankalan City | 117853 | Tan-awan ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 7 | 2724815.36 |  |  | Completed | 1
NC 2017 | K10 | Region VI | La Carlota City | 117630 | Ayungon ES | LA CARLOTA CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2697850.06 |  |  | Completed | 1
NC 2017 | SHS | Region VI | La Carlota City | 302751 | Dona H.S.Benedicto NHS | LA CARLOTA CITY | 4 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 7 | 5241842.46 |  |  | Completed | 1
NC 2017 | K10 | Region VI | La Carlota City | 117648 | La Granja ES | LA CARLOTA CITY | 4 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 4089045.87 |  |  | Completed | 1
NC 2017 | SHS | Region VI | La Carlota City | 302752 | La Granja NHS | LA CARLOTA CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2753738.35 |  |  | Completed | 1
NC 2017 | K10 | Region VI | La Carlota City | 117643 | Salamanca ES | LA CARLOTA CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2750003.1 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Roxas City | 302759 | Dumolog NHS | ROXAS CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Roxas City | 302761 | Tanque NHS | ROXAS CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | San Carlos City | 117785 | Andres Bonifacio ES | SAN CARLOS CITY | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 5488351.15 |  |  | Reverted | 0
NC 2017 | SHS | Region VI | San Carlos City | 302773 | Bagonbon NHS | SAN CARLOS CITY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | San Carlos City | 117794 | Lina dela Viña Valmayor ES | SAN CARLOS CITY | 1 | 1 | 5 | 1STY5CL | BATCH 7 | 6872950.72 |  |  | Completed | 1
NC 2017 | K10 | Region VI | San Carlos City | 117765 | San Jose ES | SAN CARLOS CITY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Silay City | 117808 | La Purisima ES | SILAY CITY | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 3263745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Silay City | 117817 | Mambag-id ES | SILAY CITY | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4734532.15 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Silay City | 312005 | Napilas Integrated School | SILAY CITY | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4734532.15 |  |  | Reverted | 0
NC 2017 | K10 | Region VI | Silay City | 117809 | Napilas IS (Napilas ES) | SILAY CITY | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2663745.92 |  |  | Reverted | 0
NC 2017 | K10 | Region VI | Silay City | 117827 | Silay North ES | SILAY CITY | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4734532.15 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Silay City | 117828 | Sto. Rosario ES | SILAY CITY | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4734532.15 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114627 | Cabugao ES | ALTAVAS | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2658745.93 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114632 | Ginictan Elementary School | ALTAVAS | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2781383.95 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114633 | Guisi Elementary School | ALTAVAS | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2725669.51 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114639 | Odiong ES | ALTAVAS | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2761867.46 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114651 | Feliciano ES | BALETE | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2693745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114663 | Daja Norte ES | BANGA | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2693395.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114664 | Daja Sur ES | BANGA | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2693395.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114676 | Sigcay ES | BANGA | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2680245.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114678 | Torralba ES | BANGA | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2680245.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114680 | Angas Integrated School | BATAN | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2613745.93 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114687 | Camanci ES | BATAN | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2613745.93 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114736 | Monlaque ES | IBAJAY | 2 | 1 | 2 | 1STY2CL | BATCH 8 | 2683745.92 |  |  | REVERTED | 0
NC 2017 | K10 | Region VI | Aklan | 114748 | Caano Elementary School | KALIBO (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2648263.42 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114753 | Pook Elementary School | KALIBO (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2653495.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114771 | Agmailig ES | LIBACAO | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2731455.93 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114785 | Julita Elementary School | LIBACAO | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2675588.22 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114872 | San Ramon PS | MALINAO | 2 | 1 | 2 | 1STY2CL | BATCH 8 | 2628745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114906 | Mabilo ES | NEW WASHINGTON | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2654283.42 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114914 | Aliputos ES | NUMANCIA | 2 | 1 | 2 | 1STY2CL | BATCH 8 | 2644042.53 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114918 | Camanci Norte ES | NUMANCIA | 2 | 1 | 2 | 1STY2CL | BATCH 8 | 2628594.22 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Aklan | 302327 | Numancia National Sch. Of Fisheries | NUMANCIA | 2 | 1 | 2 | 1STY2CL | BATCH 8 | 2674339.14 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Aklan | 114934 | Tagas Elem. School | TANGALAN | 2 | 1 | 2 | 1STY2CL | BATCH 8 | 2683745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Aklan | 302336 | Tangalan National High School | TANGALAN | 2 | 1 | 3 | 1STY3CL | BATCH 8 | 4628437.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115554 | Canapian ES | MA-AYON | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115636 | Panay CS | PANAY | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2759093.01 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115670 | Carlos V. Lopez ES | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2763564.46 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115678 | San Esteban ES | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2723564.46 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115681 | San Ramon ES | PILAR | 1 | 1 | 3 | 1STY3CL | BATCH 8 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115707 | Aranguel ES | PRESIDENT ROXAS | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2638745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115709 | Bayuyan ES | PRESIDENT ROXAS | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2712393.85 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Escalante City | 302615 | Dian-ay National High School | CITY OF ESCALANTE | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3872818.75 |  |  | REVERTED | 0
NC 2017 | TVL | Region VI | Escalante City | 302615 | Dian-ay National High School | CITY OF ESCALANTE | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2988254.77 |  |  | REVERTED | 0
NC 2017 | K10 | Region VI | Escalante City | 117044 | Escalante ES I | CITY OF ESCALANTE | 1 | 1 | 5 | 1STY5CL | BATCH 8 | 6072650.72 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Escalante City | 117044 | Escalante ES I | CITY OF ESCALANTE | 1 |  | 2 | 1STY2CL | BATCH 8 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Escalante City | 302660 | Mabini National High School | CITY OF ESCALANTE | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3872818.75 |  |  | REVERTED | 0
NC 2017 | TVL | Region VI | Escalante City | 302626 | Old Poblacion National High School | CITY OF ESCALANTE | 1 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 7745637.5 |  |  | REVERTED | 0
NC 2017 | TVL | Region VI | Guimaras | 302427 | Agsanayan National High School | BUENAVISTA | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3387009.98 |  |  | Completed | 1 |  |  | 17GE0075 |  |  | 2017-09-12 | 2017-09-26 | 2017-12-20 | 2017-12-28 | ALJ Construction and Supply
NC 2017 | TVL | Region VI | Guimaras | 302430 | East Valencia National High School | BUENAVISTA | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3387009.98 |  |  | Completed | 1 |  |  | 17GE0076 |  |  | 2017-09-12 | 2017-09-26 | 2017-12-20 | 2017-12-28 | ALJ Construction and Supply
NC 2017 | TVL | Region VI | Guimaras | 302430 | East Valencia National High School | BUENAVISTA | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3387009.98 |  |  | Completed | 1 |  |  | 17GE0089 |  |  | 2017-09-12 | 2017-09-26 | 2017-12-20 | 2017-12-28 | ALJ Construction and Supply
NC 2017 | TVL | Region VI | Guimaras | 302434 | Nueva Valencia National High School | NUEVA VALENCIA | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3387009.98 |  |  | Completed | 1 |  |  | 17GE0077 |  |  | 2017-09-12 | 2017-09-27 | 2017-12-05 | 2017-12-14 | ALJ Construction and Supply
NC 2017 | TVL | Region VI | Guimaras | 302436 | Salvacion National High School | NUEVA VALENCIA | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3387009.98 |  |  | Completed | 1 |  |  | 17GE0078 |  |  | 2017-09-12 | 2017-09-27 | 2017-12-05 | 2017-12-14 | ALJ Construction and Supply
NC 2017 | TVL | Region VI | Guimaras | 302437 | Dr. Catalino Gallego Nava Memorial High School | SAN LORENZO | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3387009.98 |  |  | Completed | 1 |  |  | 17GE0079 |  |  | 2017-09-12 | 2017-09-27 | 2017-12-05 | 2017-12-14 | ALJ Construction and Supply
NC 2017 | K10 | Region VI | Iloilo | 115978 | Balunos ES | ANILAO | 4 | 1 | 3 | 1STY3CL | BATCH 8 | 3415097.1 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 115986 | Medina ES | ANILAO | 4 | 1 | 3 | 1STY3CL | BATCH 8 | 3458882.83 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 115994 | Bitaoyan ES | BADIANGAN | 3 | 1 | 2 | 1STY2CL | BATCH 8 | 2278230.85 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116000 | Iniligan ES | BADIANGAN | 3 | 1 | 3 | 1STY3CL | BATCH 8 | 3271929.41 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116008 | Tamocol ES | BADIANGAN | 3 | 1 | 2 | 1STY2CL | BATCH 8 | 2278230.85 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116045 | Guintas ES | BAROTAC NUEVO | 4 | 1 | 3 | 1STY3CL | BATCH 8 | 3260355.07 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116146 | Marin ES | CABATUAN | 3 | 1 | 3 | 1STY3CL | BATCH 8 | 3269614.54 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116128 | Martin Cubil ES | CABATUAN | 3 | 1 | 3 | 1STY3CL | BATCH 8 | 3426262.45 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116177 | Banban Elementary School | CALINOG | 3 | 1 | 3 | 1STY3CL | BATCH 8 | 3260355.07 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116271 | Calicuang ES | DINGLE | 4 | 1 | 3 | 1STY3CL | BATCH 8 | 3263466.54 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116284 | Siniba-an ES | DINGLE | 4 | 1 | 3 | 1STY3CL | BATCH 8 | 3260355.07 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116319 | Bantud-Managuit ES | DUMANGAS | 4 | 1 | 3 | 1STY3CL | BATCH 8 | 3260355.07 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116340 | P.D. Monfort ES | DUMANGAS | 4 | 1 | 3 | 1STY3CL | BATCH 8 | 3426262.45 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116342 | Paloc Bigque ES | DUMANGAS | 4 | 1 | 3 | 1STY3CL | BATCH 8 | 3260355.07 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116330 | Sulangan ES | DUMANGAS | 4 | 1 | 3 | 1STY3CL | BATCH 8 | 3518790.39 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116424 | Binaba-an ES | LAMBUNAO | 3 | 1 | 2 | 1STY2CL | BATCH 8 | 2278230.85 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116451 | Caninguan CS | LAMBUNAO | 3 | 1 | 2 | 1STY2CL | BATCH 8 | 2281342.32 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116566 | Guibongan-Igtuba ES | MIAGAO | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2638745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116585 | Igpajo ES | MIAGAO | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2773745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116570 | Miagao CES | MIAGAO | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2643745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116572 | Monteclaro ES | MIAGAO | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2683745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116591 | Oyungan ES | MIAGAO | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2668745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116574 | San Jose ES | MIAGAO | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2643745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116575 | Ticdalan ES | MIAGAO | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2688745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116670 | PALANGUIA ELEMENTARY SCHOOL | POTOTAN | 3 | 1 | 2 | 1STY2CL | BATCH 8 | 2278230.85 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116671 | Rizal ES | POTOTAN | 3 | 1 | 3 | 1STY3CL | BATCH 8 | 3518790.39 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116736 | Matambog Elementary School | SAN JOAQUIN | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2748745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116742 | Santa Rita ES | SAN JOAQUIN | 1 | 1 | 3 | 1STY3CL | BATCH 8 | 3873435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116746 | TAPIKAN ES | SAN JOAQUIN | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2638745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Iloilo | 302583 | Tubungan NHS | TUBUNGAN | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2643745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo City | 117593 | Balantang Elementary School | ILOILO CITY (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 8 | 2077545.03 |  |  | Completed | 1 |  |  | P00177839VS-CW1 | 17GJ0095 | 2017-08-08 | 2017-08-18 | 2017-08-30 | 2017-09-15 | 2017-12-06 | A.T. DUMLAO CONST.
NC 2017 | TVL | Region VI | Iloilo City | 302742 | Jalandoni Memorial National High School | ILOILO CITY (Capital) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3809568.21 |  |  | Completed | 1 |  |  | P00177841VS-CW1 | 17GJ0139
NC 2017 | K10 | Region VI | Iloilo City | 117597 | Jaro ES I | ILOILO CITY (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 8 | 2829636.42 |  |  | Completed | 1 |  |  | P00177840VS-CW1 | 17GJ0096 | 2017-08-08 | 2017-08-18 | 2017-08-30 | 2017-09-15 | 2018-01-09 | G.F. FALCIS CONST. & SUPPLY
NC 2017 | K10 | Region VI | Kabankalan City | 117830 | Balisong ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2648618.04 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Kabankalan City | 117874 | Bantayan ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2663657.04 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Kabankalan City | 117874 | Bantayan ES | CITY OF KABANKALAN | 6 |  | 2 | 1STY2CL | BATCH 8 | 2663657.04 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Kabankalan City | 117876 | Binicuil ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2613745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Kabankalan City | 302792 | Camansi NHS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2646145.6 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Kabankalan City | 117880 | Daan Banua ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Kabankalan City | 117884 | Jose G. Peralta MS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2613745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Kabankalan City | 302796 | Salong NHS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2646832.8 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Kabankalan City | 117871 | Tampalon ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2653550.94 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Kabankalan City | 302800 | Tampalon NHS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2653550.94 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302361 | Igpalge NHS | ANINI-Y | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2666190 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Antique | 302361 | Igpalge NHS | ANINI-Y | 0 |  | 2 | 1STY2CL | BATCH 10 | 2753745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 114945 | Lisub ES | ANINI-Y | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2673745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302376 | San Roque-Ezpeleta NHS | ANINI-Y | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2636190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302346 | Barbaza NHS | BARBAZA | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2586190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302347 | Belison NS | BELISON | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2586190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302342 | Antique Vocational School | BUGASONG | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2586190 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 114983 | Bagtason ES | BUGASONG | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 114986 | Camangahan ES | BUGASONG | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 114986 | Camangahan ES | BUGASONG | 0 |  | 2 | 1STY2CL | BATCH 10 | 2663745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302368 | Northern Bugasong NHS | BUGASONG | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2586190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 310709 | Northern Bugasong NHS Annex | BUGASONG | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2686190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302379 | Southern Bugasong NHS | BUGASONG | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2626190 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 114997 | Tagudtud ES | BUGASONG | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115007 | Caluya CS | CALUYA | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2913745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302350 | Caluya NHS | CALUYA | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2986190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 310705 | Semirara NHS | CALUYA | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2886190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 310706 | Sibay NHS | CALUYA | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2886190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302382 | Tinogboc NHS | CALUYA | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2886190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302367 | Northern Antique Vocational School | CULASI | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2586190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302349 | Buhang NHS | HAMTIC | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2586190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 310704 | Gen. Leandro Fullon NS | HAMTIC | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2691190 |  |  | REVERTED | 0
NC 2017 | TVL | Region VI | Antique | 302358 | Gov. Julio V. Macuja MCHS | HAMTIC | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2711190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302356 | Governor Julian Fullon Pacificador National School | HAMTIC | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2586190 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115087 | Guintas ES | HAMTIC | 0 | 1 | 3 | 1STY3CL | BATCH 10 | 3868435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115087 | Guintas ES | HAMTIC | 0 |  | 3 | 1STY3CL | BATCH 10 | 3818435.02 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 310701 | Guintas NHS | HAMTIC | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2636190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302366 | Moscoso-Rios NHS | HAMTIC | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2586190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302351 | Col. Ruperto Abellon NHS | LAUA-AN | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2611190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 310708 | Eastern Laua-an NHS (Maria NHS) | LAUA-AN | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2626190 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115110 | Laua-an CS | LAUA-AN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302362 | Laua-an NHS | LAUA-AN | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2586190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302363 | Libertad NVS | LIBERTAD | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2636190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302383 | Union NHS | LIBERTAD | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2666190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302365 | Mag-aba National High School | PANDAN | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2651190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302369 | Pandan NVHS | PANDAN | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2611190 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115162 | Patria ES | PANDAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302372 | Patria National School | PANDAN | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2611190 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Antique | 302372 | Patria NS | PANDAN | 0 |  | 2 | 1STY2CL | BATCH 10 | 2653745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302380 | Sta. Ana NHS | PANDAN | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2656190 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115176 | Aureliana ES | PATNONGON | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302343 | Aureliana NHS | PATNONGON | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2586190 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115193 | Carit-an CS | PATNONGON | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302359 | Igburi National High School | PATNONGON | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2611190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302364 | Lirio M. Escaño NHS | PATNONGON | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2586190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302341 | Antique NS | SAN JOSE (Capital) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2586190 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115215 | Bagumbayan ES | SAN JOSE (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2773745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302375 | San Pedro NHS | SAN JOSE (Capital) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2586190 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115233 | Tubudan Cansadan ES | SAN JOSE (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2643745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302344 | Barangbang NHS | SAN REMIGIO | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2836190 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115238 | Calag-itan CS | SAN REMIGIO | 0 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115238 | Calag-itan CS | SAN REMIGIO | 0 |  | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302357 | Gideon M. Cabigunda MS | SAN REMIGIO | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2616190 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Antique | 302357 | Gideon M. Cabigunda MS | SAN REMIGIO | 0 |  | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 310707 | Gov. Evelio B. Javier MNHS | SAN REMIGIO | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2746190 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115276 | Abiera ES | SEBASTE | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115279 | Aras-asan ES | SEBASTE | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302377 | Sebaste HS | SEBASTE | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2636190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 310710 | Dr. Luis E. Baraquia NHS | SIBALOM | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2626190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302354 | Egaña National High School | SIBALOM | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2586190 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115304 | Pangpang ES | SIBALOM | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302370 | Pangpang NHS | SIBALOM | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2611190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302373 | Pis-anan National High Sshool | SIBALOM | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2586190 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Antique | 302373 | Pis-anan NHS | SIBALOM | 0 |  | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302378 | Sido-San Juan NHS | SIBALOM | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2586190 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Antique | 302378 | Sido-San Juan NHS | SIBALOM | 0 |  | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115345 | Martinez ES | TIBIAO | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115350 | Sta. Justa ES | TIBIAO | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302381 | Sta. Justa National High School | TIBIAO | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2586190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 310702 | Tario Lim National Memorial High School | TIBIAO | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2586190 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115358 | Atioes ES | TOBIAS FORNIER (DAO) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2638745.92 |  |  | REVERTED | 0
NC 2017 | K10 | Region VI | Antique | 115358 | Atioes ES | TOBIAS FORNIER (DAO) | 0 |  | 2 | 1STY2CL | BATCH 10 | 2638745.92 |  |  | REVERTED | 0
NC 2017 | K10 | Region VI | Antique | 115359 | Barasanan ES | TOBIAS FORNIER (DAO) | 0 | 1 | 3 | 1STY3CL | BATCH 10 | 3893435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115359 | Barasanan ES | TOBIAS FORNIER (DAO) | 0 |  | 3 | 1STY3CL | BATCH 10 | 3893435.02 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302352 | Concepcion L. CazeÃ±as MS | TOBIAS FORNIER (DAO) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3958435.02 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Antique | 302352 | Concepcion L. Cazeñas MS | TOBIAS FORNIER (DAO) | 0 |  | 2 | 1STY2CL | BATCH 10 | 2693745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115365 | Diclum ES | TOBIAS FORNIER (DAO) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2663745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302353 | Diclum National High School | TOBIAS FORNIER (DAO) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2766190 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Antique | 115366 | Gamad Sto. Tomas ES | TOBIAS FORNIER (DAO) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2663745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302355 | Gamad-Sto. Tomas NHS | TOBIAS FORNIER (DAO) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2636190 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Antique | 302384 | Valderrama NHS | VALDERRAMA | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2676190 |  |  | REVERTED | 0
NC 2017 | K10 | Region VI | Capiz | 115409 | Agcabugao Elementary School | CUARTERO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115410 | Agdahon ES | CUARTERO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2651995.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115411 | Agnaga ES | CUARTERO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115412 | Angub Elementary School | CUARTERO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115413 | Balingasag PS | CUARTERO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115414 | Bito-on Elementary School | CUARTERO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2643745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115423 | Mainit Elementary School | CUARTERO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115424 | Malagab-I ES | CUARTERO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115425 | Nagba ES | CUARTERO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2636695.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115426 | Putian ES | CUARTERO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115427 | San Antonio ES (Cuartero) | CUARTERO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2643745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115428 | SINABSABAN ELEMENTARY SCHOOL | CUARTERO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115415 | Vicente F. Fabuna ES (Bito-on Ilaya) | CUARTERO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2660022.82 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115430 | Agtanguay ES | DAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2661745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115435 | Alfonso E. Espiritu MS | DAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115445 | Antonio Abad ES (Quinabcaban) | DAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115438 | Ilas Sur ES | DAO | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3883185.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115439 | Lacaron ES | DAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2694597.19 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115440 | Malonoy ES (dao) | DAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2768002.26 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115441 | Manhoy ES | DAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2661745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115442 | Mapulang Bato PS | DAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2629171.55 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115436 | Nicanor Escutin MS | DAO | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3854497.52 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115446 | Quinayuya ES | DAO | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4008753.86 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115448 | Agbay-ang ES | DUMALAG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2661745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115449 | Buntog ES | DUMALAG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2629171.55 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115450 | Concepcion ES | DUMALAG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2720058.42 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115451 | Consolacion ES | DUMALAG | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115452 | Dolores ES | DUMALAG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2660022.82 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115453 | Dr. Laureano R. Frial ES | DUMALAG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2629171.55 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115455 | Duran ES | DUMALAG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2692495.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115456 | Maludlud ES | DUMALAG | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3927691.36 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115458 | San Jose ES (dumalag) | DUMALAG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115459 | San Martin ES | DUMALAG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2671120.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115460 | San Miguel ES | DUMALAG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2660022.82 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115462 | Sta. Cruz ES | DUMALAG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2615245.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115463 | Sta. Monica ES | DUMALAG | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3783860.65 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115465 | Sta. Teresa ES | DUMALAG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2709370.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115466 | Sto. Niño ES | DUMALAG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2651995.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115468 | Agbatuan ES | DUMARAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2709368.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115470 | Aglanot ES | DUMARAO | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3773435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115472 | Agsirab ES | DUMARAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2690245.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115473 | Alipaciawan ES | DUMARAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2709370.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115474 | Astorga ES | DUMARAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2765258.42 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115475 | Badbaranan ES | DUMARAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2636695.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115477 | Cabangahan PS (dumarao) | DUMARAO | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3837285.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115478 | Calapawan ES (dumarao) | DUMARAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115479 | Codingle ES | DUMARAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115481 | Dacuton ES | DUMARAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2623745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115488 | Malonoy ES (dumarao) | DUMARAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Capiz | 302417 | Mayor Ramon A. Benjamin Sr. National High School | DUMARAO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2559062.5 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Capiz | 302417 | Mayor Ramon A. Benjamin Sr. National High School | DUMARAO | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2616245.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115489 | NAGSULANG ELEMENTARY SCHOOL | DUMARAO | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3883185.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115490 | Ongol Ilaya PS | DUMARAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2663745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115490 | Ongol Ilaya PS | DUMARAO | 2 |  | 2 | 1STY2CL | BATCH 10 | 2644597.19 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115492 | Salcedo ES | DUMARAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115493 | San Juan ES (dumarao) | DUMARAO | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3802860.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115494 | Sibariwan Elementary School | DUMARAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2623745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115495 | Tamulalod ES | DUMARAO | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3842285.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115496 | Taslan ES (dumarao) | DUMARAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2633745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115497 | Tina ES (DUMARAO) | DUMARAO | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115502 | BASIAO ELEMENTARY SCHOOL | IVISAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2818745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115503 | Cabugao ES (ivisan) | IVISAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115504 | Cudian ES | IVISAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2661745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115508 | Victor A. Umiten Memorial School | IVISAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2717397.82 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115508 | Victor A. Umiten Memorial School | IVISAN | 2 |  | 2 | 1STY2CL | BATCH 10 | 2717397.82 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115515 | Agbun -0d Elementary School | JAMINDAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2671120.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115516 | Agcagay ES | JAMINDAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2701972.19 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115517 | Aglibacao PS | JAMINDAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2644597.19 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115518 | Agloloway ES | JAMINDAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2665745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115521 | Camp Jamindan ES | JAMINDAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115522 | Caridad PS | JAMINDAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2633745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115514 | Francisco C. Vacaro ES | JAMINDAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2623745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115527 | Guintas ES | JAMINDAN | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3854497.52 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115528 | Igang PS | JAMINDAN | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115529 | Jaena Norte ES | JAMINDAN | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115530 | Jaena Sur PS | JAMINDAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115532 | Jamindan ES | JAMINDAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115533 | La Paz PS | JAMINDAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115534 | Linambasan ES | JAMINDAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115535 | Lucero ES | JAMINDAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115536 | Maantol Elementary School | JAMINDAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115537 | Masnang PS | JAMINDAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2706299.73 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115538 | Milan ES | JAMINDAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2651995.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115546 | Ubog ES | JAMINDAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2625745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115580 | Balat-an PS | MAMBUSAO | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3992715.19 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115582 | Batiano ES | MAMBUSAO | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4113943.36 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115584 | Baye ES | MAMBUSAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115587 | Bungsi ES | MAMBUSAO | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3891840.1 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115601 | Caidquid ES | MAMBUSAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2821561.83 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115598 | Diosdado Bayot ES (Bitayan ES) | MAMBUSAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2662022.82 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115583 | Gavino M. Navarra ES | MAMBUSAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115603 | Libo-o Primary School | MAMBUSAO | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4021164.46 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Capiz | 310805 | MAMBUSAO NATIONAL HIGH SCHOOL | MAMBUSAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2884552.17 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115592 | Minoro ES | MAMBUSAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115607 | Ramon A. Villareal MS | MAMBUSAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2615245.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115608 | Sinondojan Primary School | MAMBUSAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2668511 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115609 | Tongatong ES | MAMBUSAO | 2 | 1 | 4 | 1STY4CL | BATCH 10 | 5067107.44 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115596 | Tugas ES | MAMBUSAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115728 | Agtatacay Sur Elementary School | SAPI-AN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115735 | CAMANSI PRIMARY SCHOOL | SAPI-AN | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3840810.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115736 | Culasi Elementary School | SAPI-AN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115737 | Damayan ES | SAPI-AN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115742 | Majanlud ES | SAPI-AN | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3950338.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115743 | Maninang ES | SAPI-AN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2644345.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115741 | Telesforo Aperocho ES | SAPI-AN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2690245.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115746 | WENCESLAO ONAS ELEM. SCHOOL | SAPI-AN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2651995.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115747 | Acbo ES | SIGMA | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115748 | Amaga ES | SIGMA | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115749 | Atty. Santiago Abella Vito ES | SIGMA | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115757 | Maestro J. Reyes PS | SIGMA | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115758 | Mangoso ES | SIGMA | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115760 | Margarita Soriano ES | SIGMA | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3828200.1 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115762 | Matinabus ES | SIGMA | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2695893.55 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115765 | Pascual Gregore ES (Pinamalatican ES) | SIGMA | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3860988.83 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115766 | Sigma CES | SIGMA | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2673745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115767 | Sinandigan ES | SIGMA | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2667295.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115770 | Acuña ES | TAPAZ | 2 | 1 | 4 | 1STY4CL | BATCH 10 | 5290892.37 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115802 | Agcococ ES | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115771 | Aglinab ES | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3136495.1 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115804 | Apero ES | TAPAZ | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115806 | Artuz Elementary School | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115773 | Bagong Barrio ES | TAPAZ | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115807 | Camburanan ES | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2775113.11 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115808 | Candelaria ES | TAPAZ | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3871710.02 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Capiz | 302393 | Col. Patrocinio Artuz NHS | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2661745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115810 | Cristina ES | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115778 | Garcia ES | TAPAZ | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115780 | Katipunan ES | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2651995.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115781 | Lagdungan ES | TAPAZ | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115777 | Leopoldo Gialogo ES | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115783 | Libertad ES | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2668511 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115785 | Malitbog ES | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115809 | Mariano Gleyo ES | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 179007 | Martin Gimeno PS | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2651995.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 179007 | Martin Gimeno PS | TAPAZ | 2 |  | 2 | 1STY2CL | BATCH 10 | 2651995.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115813 | Mawang ES | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115789 | Roosevelt ES | TAPAZ | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115814 | Roxas ES | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115814 | Roxas ES | TAPAZ | 2 |  | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115792 | San Jose ES (tapaz east) | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2746561.83 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115815 | San Julian ES | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115816 | San Nicolas ES | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2665383.42 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115817 | Sta. Ana ES | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115797 | Sta. Petronila PS | TAPAZ | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3952965.19 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115798 | Switch ES | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115819 | Tapaz CES | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115820 | Taslan ES (tapaz west) | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115801 | Wright ES | TAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | La Carlota City | 302751 | Doña Hortencia Salas Benedicto NHS | LA CARLOTA CITY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3693957.95 |  |  | Completed | 1
NC 2017 | TVL | Region VI | La Carlota City | 302751 | Doña Hortencia Salas Benedicto NHS | LA CARLOTA CITY | 4 |  | 6 | WORKSHOP BLDG (7x18) | BATCH 10 | 17872071.3 |  |  | Completed | 1
NC 2017 | TVL | Region VI | La Carlota City | 302751 | Doña Hortencia Salas Benedicto NHS | LA CARLOTA CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5957357.9 |  |  | Completed | 1
NC 2017 | TVL | Region VI | La Carlota City | 302751 | Doña Hortencia Salas Benedicto NHS | LA CARLOTA CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5957357.9 |  |  | Completed | 1
NC 2017 | K10 | Region VI | La Carlota City | 117640 | La Carlota North ES | LA CARLOTA CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2697850.06 |  |  | Completed | 1
NC 2017 | K10 | Region VI | La Carlota City | 117636 | La Carlota South ES I | LA CARLOTA CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2723948.4 |  |  | Completed | 1
NC 2017 | TVL | Region VI | La Carlota City | 302752 | La Granja NHS | LA CARLOTA CITY | 4 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3101854.95 |  |  | Completed | 1
NC 2017 | TVL | Region VI | La Carlota City | 302752 | La Granja NHS | LA CARLOTA CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 6203710.7 |  |  | Completed | 1
NC 2017 | TVL | Region VI | La Carlota City | 302752 | La Granja NHS | LA CARLOTA CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 6203710.7 |  |  | Completed | 1
NC 2017 | TVL | Region VI | La Carlota City | 302752 | La Granja NHS | LA CARLOTA CITY | 4 |  | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 7142449.08 |  |  | Completed | 1
NC 2017 | K10 | Region VI | La Carlota City | 117649 | San Miguel ES I | LA CARLOTA CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2723948.4 |  |  | Completed | 1
NC 2017 | TVL | Region VI | La Carlota City | 302754 | San Miguel NHS | LA CARLOTA CITY | 4 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5755805.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | La Carlota City | 302754 | San Miguel NHS | LA CARLOTA CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5755805.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Roxas City | 117678 | Antonio Villasis MS | ROXAS CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2653745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Roxas City | 117678 | Antonio Villasis MS | ROXAS CITY (Capital) | 1 |  | 4 | 1STY4CL | BATCH 10 | 5048351.15 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Roxas City | 117666 | Banica Elementary School | ROXAS CITY (Capital) | 1 | 1 | 4 | 1STY4CL | BATCH 10 | 5058351.15 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Roxas City | 117666 | Banica Elementary School | ROXAS CITY (Capital) | 1 |  | 4 | 1STY4CL | BATCH 10 | 5058351.15 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Roxas City | 302757 | Cong. Ramon A. Arnaldo HS | ROXAS CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2693745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Roxas City | 117680 | Don Gervacio Diaz ES | ROXAS CITY (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3923435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Roxas City | 117658 | Inzo Arnaldo Village Integrated School | ROXAS CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2813745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Roxas City | 311707 | Inzo Arnaldo Village Integrated School | ROXAS CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2813745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Roxas City | 117684 | Katipunan Village ES | ROXAS CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2803745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Roxas City | 117684 | Katipunan Village ES | ROXAS CITY (Capital) | 1 |  | 2 | 1STY2CL | BATCH 10 | 2803745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Roxas City | 117685 | Lawa-an ES | ROXAS CITY (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 4008435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Roxas City | 117686 | Loctugan ES | ROXAS CITY (Capital) | 1 | 1 | 5 | 1STY5CL | BATCH 10 | 6512650.72 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Roxas City | 117688 | Sofronio A. Cordovero Integrated School | ROXAS CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2893745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Roxas City | 117688 | Sofronio A. Cordovero Integrated School | ROXAS CITY (Capital) | 1 |  | 2 | 1STY2CL | BATCH 10 | 2783745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Roxas City | 311708 | Sofronio A. Cordovero Integrated School | ROXAS CITY (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 4108435.02 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Sagay City | 302762 | Bato National High School | SAGAY CITY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3872818.75 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | Sagay City | 302762 | Bato National High School | SAGAY CITY | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | Sagay City | 302762 | Bato National High School | SAGAY CITY | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5976509.54 |  |  | Reverted | 0
NC 2017 | K10 | Region VI | Sagay City | 117695 | Buenaventura Rodriguez ES | SAGAY CITY | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2913745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Sagay City | 302768 | Bulanon National High School | SAGAY CITY | 2 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | Sagay City | 302768 | Bulanon National High School | SAGAY CITY | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | Sagay City | 302768 | Bulanon National High School | SAGAY CITY | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | Sagay City | 500036 | Colonia Divina Integrated School | SAGAY CITY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3872818.75 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | Sagay City | 500036 | Colonia Divina Integrated School | SAGAY CITY | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | Sagay City | 500036 | Colonia Divina Integrated School | SAGAY CITY | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | Sagay City | 500037 | Eusebio Lopez Memorial Integrated School | SAGAY CITY | 2 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5976509.54 |  |  | Reverted | 0
NC 2017 | K10 | Region VI | Sagay City | 117714 | Fabrica ES | SAGAY CITY | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Sagay City | 500038 | Himogaan Baybay Integrated School | SAGAY CITY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 4072818.75 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | Sagay City | 500038 | Himogaan Baybay Integrated School | SAGAY CITY | 2 |  | 3 | WORKSHOP BLDG (7x18) | BATCH 10 | 9564763.31 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | Sagay City | 500038 | Himogaan Baybay Integrated School | SAGAY CITY | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 6376509.54 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | Sagay City | 500038 | Himogaan Baybay Integrated School | SAGAY CITY | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5976509.54 |  |  | Reverted | 0
NC 2017 | K10 | Region VI | Sagay City | 117718 | Himogaan Baybay IS | SAGAY CITY | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Sagay City | 117722 | Ricardo Gamboa | SAGAY CITY | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2913745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Sagay City | 343922 | Sagay City Senior High SChool | SAGAY CITY | 2 | 1 | 4 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 14691275 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | Sagay City | 343922 | Sagay City Senior High SChool | SAGAY CITY | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | Sagay City | 343922 | Sagay City Senior High SChool | SAGAY CITY | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | Sagay City | 311802 | Sagay National High School - Rizal Extension | SAGAY CITY | 2 | 1 | 4 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 15293500 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | Sagay City | 311802 | Sagay National High School - Rizal Extension | SAGAY CITY | 2 |  | 6 | WORKSHOP BLDG (7x18) | BATCH 10 | 17929528.62 |  |  | Reverted | 0
NC 2017 | SHS | Region VI | Sagay City | 302767 | Sagay NHS | SAGAY CITY | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4068435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Sagay City | 117708 | Tu-ong ES | SAGAY CITY | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Sagay City | 117735 | Valeriana G. Analucas ES | SAGAY CITY | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2913745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Aklan | 302287 | Justicia Morales-Young National High School | ALTAVAS | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2554000 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Aklan | 302307 | Father Julian C. Rago Memorial NHS | BALETE | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 2672917.56 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Aklan | 302308 | Jose Borromeo Legaspi Memorial National High School | BALETE | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 2724237.37 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Aklan | 302309 | Jose Feliciano Meñez Memorial National High School | BALETE | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 2724237.37 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Aklan | 302294 | Bay-ang-Magpag-ong NHS | BATAN | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 2623449.26 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Aklan | 302318 | BURUANGA NATIONAL HIGH SCHOOL | BURUANGA | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 2764862.8 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Aklan | 500181 | Dalagsaan Integrated School | LIBACAO | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 3433530.2 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | Aklan | 302310 | Libacao National Forestry Vocational High School | LIBACAO | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2685250 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Aklan | 302310 | Libacao National Forestry Vocational High School | LIBACAO | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2685250 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Aklan | 310616 | Agtughangin Integrated School | MADALAG | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2884090 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Aklan | 302315 | Madalag NHS | MADALAG | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2599000 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Aklan | 310603 | LAMBERTO H. TIROL NATIONAL HIGH SCHOOL | MALAY | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 3089334 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | Aklan | 302317 | Malay National High School | MALAY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2707237.75 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Aklan | 302317 | Malay National High School | MALAY | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 2639238.75 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Aklan | 500175 | Kinalangay Viejo IS | MALINAO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2554000 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Aklan | 500175 | Kinalangay Viejo IS | MALINAO | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2554000 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Aklan | 302302 | Candelaria NHS | NEW WASHINGTON | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2630048.76 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Aklan | 302328 | Ochando National High School | NEW WASHINGTON | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2630048.76 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Aklan | 302328 | Ochando National High School | NEW WASHINGTON | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2677494.03 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | Aklan | 500035 | Numancia Integrated School | NUMANCIA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2670421 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Aklan | 302327 | Numancia National Sch. Of Fisheries | NUMANCIA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2609882 |  |  | Reverted | 0
NC 2017 | K10 | Region VI | Bacolod City | 117461 | A. Lizares ES | BACOLOD CITY (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 12 | 24655247.73 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bacolod City | 117461 | A. Lizares ES | BACOLOD CITY (Capital) | 0 |  | 2 | 1STY2CL | BATCH 12 | 2645505.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bacolod City | 117468 | A.L. Jayme ES | BACOLOD CITY (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 12 | 24678047.73 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bacolod City | 117468 | A.L. Jayme ES | BACOLOD CITY (Capital) | 0 |  | 9 | 3STY9CL | BATCH 12 | 24688047.73 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bacolod City | 117456 | Bata ES II | BACOLOD CITY (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 8980904.76 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bacolod City | 117489 | Don R. A. Medel Sr. ES | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 12 | 12773014.84 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bacolod City | 117489 | Don R. A. Medel Sr. ES | BACOLOD CITY (Capital) | 0 |  | 6 | 2STY6CL | BATCH 12 | 11656168.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bacolod City | 117483 | EDUCATION & TRAINING CENTER SCHOOL III | BACOLOD CITY (Capital) | 0 | 1 | 12 | 3STY12CL | BATCH 12 | 29546467.25 |  |  | Reverted | 0
NC 2017 | K10 | Region VI | Bacolod City | 117483 | EDUCATION & TRAINING CENTER SCHOOL III | BACOLOD CITY (Capital) | 0 |  | 6 | 3STY6CL | BATCH 12 | 13739515.1 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bacolod City | 117490 | F.R. Flores ES | BACOLOD CITY (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bacolod City | 117471 | Handumanan ES-1 | BACOLOD CITY (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 12 | 24468047.73 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bacolod City | 117485 | Mariano G. Medalla Integrated School | BACOLOD CITY (Capital) | 0 | 1 | 6 | 3STY6CL | BATCH 12 | 13739515.1 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bacolod City | 117467 | R. Alunan ES | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 12 | 11656168.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bacolod City | 117474 | Vista Alegre ES | BACOLOD CITY (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 8945901.76 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Bacolod City | 181004 | Vista Alegre-Granada Relocation ES | BACOLOD CITY (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 9072261.76 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Bago City | 302720 | Ramon Torres Dulao NHS | BAGO CITY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3570535.96 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Bago City | 302720 | Ramon Torres Dulao NHS | BAGO CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5714957.12 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Cadiz City | 302729 | Caduha-an NHS - Andres Bonifacio Ext. HS | CADIZ CITY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3972818.46 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | Cadiz City | 302730 | Dr. Vicente F. Gustilo Memorial NHS | CADIZ CITY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3422818.46 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | Cadiz City | 302731 | Mabini National High School | CADIZ CITY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3822818.46 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | Cadiz City | 302732 | SPED High School | CADIZ CITY | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 3822818.46 |  |  | Reverted | 0
NC 2017 | K10 | Region VI | Capiz | 115547 | Aglimocon ES | MA-AYON | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2713745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Capiz | 302412 | East Villaflores NHS | MA-AYON | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2693745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115576 | Tepacla ES | MA-AYON | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115652 | Cogon ES (Panitan) | PANITAN | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2731041.78 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115684 | Sta. Fe ES | PILAR | 1 | 1 | 3 | 1STY3CL | BATCH 12 | 3818435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115689 | Ameligan ES | PONTEVEDRA | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Capiz | 115704 | Rizal ES | PONTEVEDRA | 1 | 1 | 3 | 1STY3CL | BATCH 12 | 3843435.02 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Escalante City | 302625 | Escalante National High School | CITY OF ESCALANTE | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Iloilo | 302443 | Ajuy NHS | AJUY | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3904000 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 115919 | Alejo Posadas MES | AJUY | 5 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 12 | 5135500 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Iloilo | 302486 | Culasi NHS | AJUY | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3904000 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Iloilo | 302446 | Alimodian NCHS | ALIMODIAN | 2 | 1 | 4 | 1STY4CL | BATCH 12 | 5232814.7 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 115947 | Atabay ES | ALIMODIAN | 2 | 1 | 3 | 1STY3CL | BATCH 12 | 4171402.87 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 115952 | Cabacanan ES | ALIMODIAN | 2 | 1 | 3 | 1STY3CL | BATCH 12 | 4231402.87 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 115952 | Cabacanan ES | ALIMODIAN | 2 |  | 2 | 1STY2CL | BATCH 12 | 3028254.17 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116017 | Lawis ES | BALASAN | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 2844223 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116020 | Pedro Bedez ES | BALASAN | 5 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 12 | 5135500 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116025 | Zaragosa ES | BALASAN | 5 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4124580 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Iloilo | 302458 | Barotac Viejo National High School | BAROTAC VIEJO | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3904000 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Iloilo | 302458 | Barotac Viejo National High School | BAROTAC VIEJO | 5 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3946137 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Iloilo | 302502 | GEN. LUNA NHS | BAROTAC VIEJO | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3904000 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116069 | Lipata ES | BAROTAC VIEJO | 5 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4139180 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116070 | Nagpana PS | BAROTAC VIEJO | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 3145000 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116081 | San Juan ES | BAROTAC VIEJO | 5 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4100715 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Iloilo | 311004 | Santiago NHS | BAROTAC VIEJO | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3904000 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116092 | Batad CES | BATAD | 5 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4141206 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116095 | Jose P. Gonzalodo Sr. ES | BATAD | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 2869200 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116102 | Teodoro P. Gomeri ES | BATAD | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 2844223 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116212 | Carles CS | CARLES | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 2776100 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116242 | Concepcion CS | CONCEPCION | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 2877385 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116350 | Gogo ES | ESTANCIA | 5 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4435200 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116474 | Guinobatan ES | LEGANES | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 3018254.17 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116479 | Napnud ES | LEGANES | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2948254.17 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116479 | Napnud ES | LEGANES | 2 |  | 2 | 1STY2CL | BATCH 12 | 2838254.17 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116484 | Benjamin Aguilar ES | LEMERY | 5 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4233500 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116494 | Muyco ES | LEMERY | 5 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4089697 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116521 | Buga Central Elementary School | LEON | 2 | 1 | 4 | 1STY4CL | BATCH 12 | 5502814.7 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116521 | Buga Central Elementary School | LEON | 2 |  | 5 | 1STY5CL | BATCH 12 | 6434879.49 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116521 | Buga Central Elementary School | LEON | 2 |  | 2 | 1STY2CL | BATCH 12 | 3098254.17 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116608 | Bita-og Gaja ES | NEW LUCENA | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2818254.17 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116608 | Bita-og Gaja ES | NEW LUCENA | 2 |  | 3 | 1STY3CL | BATCH 12 | 4021402.87 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116609 | Bololacao ES | NEW LUCENA | 2 | 1 | 4 | 1STY4CL | BATCH 12 | 5312814.7 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116609 | Bololacao ES | NEW LUCENA | 2 |  | 2 | 1STY2CL | BATCH 12 | 3048254.17 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Iloilo | 302540 | New Lucena NHS | NEW LUCENA | 2 | 1 | 4 | 1STY4CL | BATCH 12 | 5232814.7 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116617 | Pasil-Jelicuon ES | NEW LUCENA | 2 | 1 | 3 | 1STY3CL | BATCH 12 | 4071402.87 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116617 | Pasil-Jelicuon ES | NEW LUCENA | 2 |  | 2 | 1STY2CL | BATCH 12 | 2958254.17 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116635 | Aganan Ungka ES | PAVIA | 2 | 1 | 4 | 1STY4CL | BATCH 12 | 5502814.7 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116694 | Siempreviva ES | SAN DIONISIO | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 3097000 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116758 | Sto. Niño ES | SAN MIGUEL | 2 | 1 | 3 | 1STY3CL | BATCH 12 | 4271402.87 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116765 | San Andres ES | SAN RAFAEL | 5 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4031649 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116768 | San Rafael Cs | SAN RAFAEL | 5 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4142400 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116791 | Agutayan-Lupa ES | SANTA BARBARA | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2828254.17 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116791 | Agutayan-Lupa ES | SANTA BARBARA | 2 |  | 2 | 1STY2CL | BATCH 12 | 3168254.17 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Iloilo | 302487 | Daga-Barasan NHS | SANTA BARBARA | 2 | 1 | 4 | 1STY4CL | BATCH 12 | 5582814.7 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116809 | Lanag ES | SANTA BARBARA | 2 | 1 | 3 | 1STY3CL | BATCH 12 | 3991402.87 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116812 | Payao ES | SANTA BARBARA | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2918254.17 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116813 | Sta. Barbara CES | SANTA BARBARA | 2 | 1 | 5 | 1STY5CL | BATCH 12 | 6434879.49 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116816 | Talongadian ES | SANTA BARBARA | 2 | 1 | 4 | 1STY4CL | BATCH 12 | 5592814.7 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo | 116769 | Alfredo Sanson MES | SARA | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 2967085 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo City | 117593 | Balantang Elementary School | ILOILO CITY (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 968454.97 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Iloilo City | 302750 | Ramon Avancena NHS | ILOILO CITY (Capital) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3809568.21 |  |  | Completed | 1 |  |  | P00181859VS-CW1 | 17GJ0140 | 2017-09-08 | 2017-09-15 | 2017-09-29 | 2017-10-13 |  | KRJ CONST.
NC 2017 | K10 | Region VI | Kabankalan City | 117834 | Bula ES | CITY OF KABANKALAN | 6 | 1 | 5 | 1STY5CL | BATCH 12 | 6422650.72 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Passi City | 117918 | Anecito Panolino Elementary School | CITY OF PASSI | 4 | 1 | 3 | 1STY3CL | BATCH 12 | 3275767.52 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Passi City | 117924 | Magdungao Proper ES | CITY OF PASSI | 4 | 1 | 2 | 1STY2CL | BATCH 12 | 2298303.665 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Passi City | 117924 | Magdungao Proper ES | CITY OF PASSI | 4 |  | 2 | 1STY2CL | BATCH 12 | 2298303.665 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Sagay City | 302771 | Vito National High School | SAGAY CITY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3872818.75 |  |  | Completed | 1
NC 2017 | TVL | Region VI | San Carlos City | 302775 | Julio Ledesma National High School | SAN CARLOS CITY | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3422318.75 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | San Carlos City | 302775 | Julio Ledesma National High School | SAN CARLOS CITY | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | San Carlos City | 302777 | Sipaway National High School | SAN CARLOS CITY | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | San Carlos City | 302777 | Sipaway National High School | SAN CARLOS CITY | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 3038254.17 |  |  | Reverted | 0
NC 2017 | TVL | Region VI | Silay City | 302780 | DoÃ±a Montserrat Lopez MHS | SILAY CITY | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3422818.75 |  |  | Reverted | 0
NC 2017 | K10 | Region VI | Bacolod City | 181005 | Handumanan ES II | BACOLOD CITY (Capital) | 0 | 1 | 6 | 3STY6CL | BATCH 13 | 13935375.1 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Bacolod City | 302669 | Felizardo C. Lipana NHS (Sta. Rita HS) | BACOLOD CITY (Capital) | 0 | 1 | 12 | 4STY12CL | BATCH 13 | 31824789.72 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Bacolod City | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 |  | 20 | 4STY20CL | BATCH 13 | 41513409.74 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Bacolod City | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 |  | 2 | 1STY2CL | BATCH 13 | 2789745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Bacolod City | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 |  | 16 | 4STY16CL | BATCH 13 | 37120737.96 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Bago City | 302720 | Ramon Torres Dulao NHS | BAGO CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 5714957.12 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Bago City | 302724 | Ramon Torres Louisiana NHS | BAGO CITY | 4 | 1 | 3 | WORKSHOP BLDG (7x18) | BATCH 13 | 8572434.48 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Bago City | 302724 | Ramon Torres Louisiana NHS | BAGO CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 5714957.12 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Bago City | 302724 | Ramon Torres Louisiana NHS | BAGO CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 5714957.12 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Bago City | 302721 | Ramon Torres Ma-ao Sugar Central NHS | BAGO CITY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3570535.96 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Bago City | 302721 | Ramon Torres Ma-ao Sugar Central NHS | BAGO CITY | 4 |  | 3 | WORKSHOP BLDG (7x18) | BATCH 13 | 8572434.48 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Bago City | 302721 | Ramon Torres Ma-ao Sugar Central NHS | BAGO CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 5714957.12 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Bago City | 302721 | Ramon Torres Ma-ao Sugar Central NHS | BAGO CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 5714957.12 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Bago City | 302722 | Ramon Torres Malingin National High School | BAGO CITY | 4 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 2976703.05 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Bago City | 302722 | Ramon Torres Malingin National High School | BAGO CITY | 4 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 2976702.95 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Bago City | 302722 | Ramon Torres Malingin National High School | BAGO CITY | 4 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 2976702.95 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Bago City | 302719 | Ramon Torres NHS | BAGO CITY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3647901.95 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Bago City | 302719 | Ramon Torres NHS | BAGO CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 5914533.12 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Bago City | 302719 | Ramon Torres NHS | BAGO CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 5914533.12 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Bago City | 302723 | Ramon Torres Sagasa National High School | BAGO CITY | 4 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 2976702.55 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Bago City | 302723 | Ramon Torres Sagasa National High School | BAGO CITY | 4 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 2976702.55 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Bago City | 302723 | Ramon Torres Sagasa National High School | BAGO CITY | 4 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 2976702.95 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Bago City | 302725 | Ramon Torres Taloc NHS | BAGO CITY | 4 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 2976702.55 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Bago City | 302725 | Ramon Torres Taloc NHS | BAGO CITY | 4 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 2976702.95 |  |  | Completed | 1
NC 2017 | TVL | Region VI | Bago City | 302725 | Ramon Torres Taloc NHS | BAGO CITY | 4 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 2976702.95 |  |  | Completed | 1
NC 2017 | K10 | Region VI | Iloilo City | 117580 | Arevalo ES | ILOILO CITY (Capital) | 0 | 1 | 15 | 3STY15CL | BATCH 14 | 34892863.87 |  |  | Completed | 1 |  |  | P00184452VS-CW1 | 17GJ0129 | 2017-09-08 | 2017-09-15 | 2017-09-29 | 2017-10-13 | 2018-01-05 | MORTE CONST.
NC 2017 | K10 | Region VI | Iloilo City | 117588 | Iloilo Central ES | ILOILO CITY (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 14 | 26274486.98 |  |  | Completed | 1 |  |  | P00184453VS-CW1 | 17GJ0131 | 2017-09-08 | 2017-09-15 | 2017-09-29 | 2017-10-13 | 2018-01-05 | A.D. PENDON CONST. & SUPPLY
NC 2017 | K10 | Region VI | Iloilo City | 117588 | Iloilo Central ES | ILOILO CITY (Capital) | 0 |  | 6 | 3STY6CL | BATCH 14 | 13945556.85 |  |  | Completed | 1 |  |  | P00184454VS-CW1 | 17GJ0128 | 2017-09-08 | 2017-09-15 | 2017-09-29 | 2017-10-13 | 2018-01-05 | ALJ CONST. & SUPPLY
NC 2017 | K10 | Region VI | Iloilo City | 117595 | Buntatala Tagbac Elem. School | ILOILO CITY (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 14 | 9400000 |  |  | Completed | 1 |  |  | P00184455VS-CW1 | 17GJ0105 | 2017-09-07 | 2017-09-15 | 2017-09-28 | 2017-10-12 | 2018-01-09 | A.D. PENDON CONST. & SUPPLY
NC 2017 | K10 | Region VI | Iloilo City | 117609 | Nabitasan ES | ILOILO CITY (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 14 | 9500000 |  |  | Completed | 1 |  |  | P00184456VS-CW1 | 17GJ0123 | 2017-09-08 | 2017-09-15 | 2017-09-29 | 2017-10-13 | 2017-12-22 | 5'S CONST. & SUPPLY
NC 2017 | K10 | Region VI | Iloilo City | 117615 | Hibao-an ES | ILOILO CITY (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 14 | 9400000 |  |  | Completed | 1 |  |  | P00184457VS-CW1 | 17GJ0107 | 2017-09-07 | 2017-09-15 | 2017-09-28 | 2017-10-12 | 2018-01-09 | A.D. PENDON CONST. & SUPPLY
NC 2017 | K10 | Region VI | Iloilo City | 117616 | Navais-Borres ES (L. Borres ES) | ILOILO CITY (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 14 | 9700000 |  |  | Completed | 1 |  |  | P00184458VS-CW1 | 17GJ0121 | 2017-09-08 | 2017-09-15 | 2017-09-29 | 2017-10-13 | 2017-12-22 | E.Z. GOLD CONST. & SUPPLY
NC 2017 | K10 | Region VI | Iloilo City | 117617 | Mandurriao ES | ILOILO CITY (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 14 | 12620000 |  |  | Completed | 1 |  |  | P00184459VS-CW1 | 17GJ0117 | 2017-09-08 | 2017-09-15 | 2017-09-29 | 2017-10-13 | 2017-12-22 | A.D. PENDON CONST. & SUPPLY
NC 2017 | K10 | Region VI | Iloilo City | 117619 | Baluarte ES | ILOILO CITY (Capital) | 0 | 1 | 12 | 3STY12CL | BATCH 14 | 31489831.3 |  |  | Completed | 1 |  |  | P00184460VS-CW1 | 17GJ0130 | 2017-09-08 | 2017-09-15 | 2017-09-29 | 2017-10-13 | 2018-01-05 | LEGACY CONST.
NC 2017 | K10 | Region VI | Iloilo City | 117620 | Esteban Juntado Sr. Elem. School | ILOILO CITY (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 14 | 9700000 |  |  | Completed | 1 |  |  | P00184461VS-CW1 | 17GJ0106 | 2017-09-07 | 2017-09-15 | 2017-09-28 | 2017-10-12 |  | E.Z. GOLD CONST. & SUPPLY
NC 2017 | K10 | Region VI | Iloilo City | 117621 | I. Arroyo ES | ILOILO CITY (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 14 | 9450000 |  |  | Completed | 1 |  |  | P00184462VS-CW1 | 17GJ0108 | 2017-09-07 | 2017-09-15 | 2017-09-28 | 2017-10-12
NC 2017 | K10 | Region VI | Iloilo City | 117626 | A. Montes ES I | ILOILO CITY (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 14 | 9800000 |  |  | Completed | 1 |  |  | P00184463VS-CW1 | 17GJ0122 | 2017-09-08 | 2017-09-15 | 2017-09-29 | 2017-10-13 | 2017-12-22 | ALJ CONST. & SUPPLY
NC 2017 | SHS | Region VI | Silay City | 302778 | Brgy. Guimbala-on NHS | SILAY CITY | 3 | 1 | 4 | 2STY4CL | BATCH 14 | 9950846.28 |  |  | Reverted | 0
NC 2017 | SHS | Region VI | Silay City | 302779 | Don Felix T. Lacson Memorial National High School | SILAY CITY | 3 | 1 | 4 | 2STY4CL | BATCH 14 | 9050846.28 |  |  | Reverted | 0
NC 2017 | SHS | Region VI | Silay City | 302780 | Doña Montserrat Lopez MHS | SILAY CITY | 3 | 1 | 8 | 4STY8CL | BATCH 14 | 20756429.32 |  |  | Reverted | 0
NC 2017 | SHS | Region VI | Silay City | 302780 | DoÃ±a Montserrat Lopez MHS | SILAY CITY | 3 |  | 4 | 2STY4CL | BATCH 14 | 9250846.28 |  |  | Reverted | 0
NC 2017 | SHS | Region VI | Silay City | 302781 | Brgy. E. Lopez National High School | SILAY CITY | 3 | 1 | 8 | 2STY8CL | BATCH 14 | 17079734.78 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Silay City | 302781 | Brgy. E. Lopez National High School | SILAY CITY | 3 |  | 4 | 2STY4CL | BATCH 14 | 9050846.28 |  |  | Completed | 1
NC 2017 | SHS | Region VI | Silay City | 302781 | Brgy. E. Lopez National High School | SILAY CITY | 3 |  | 4 | 2STY4CL | BATCH 14 | 9050846.26 |  |  | Reverted | 0
NC 2018 | K10 | Region VI | Aklan | 114641 | Talon ES | ALTAVAS | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9502130.8 |  |  | Completed | 1 |  |  | P00271866VS-CW1
NC 2018 | K10 | Region VI | Aklan | 114646 | Balete ES | BALETE | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9035901.76 |  |  | Completed | 1 |  |  | P00271867VS-CW1
NC 2018 | SHS | Region VI | Aklan | 114695 | NAPTI INTEGRATED SCHOOL | BATAN | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9253103.01 |  |  | Completed | 1 |  |  | P00271868VS-CW1 | 18GA0135 | 2018-06-29 | 2018-06-14 | 2018-06-29 | 2018-07-30 | 2018-07-30 | G.F. Rovero Merchandising
NC 2018 | SHS | Region VI | Aklan | 114695 | NAPTI INTEGRATED SCHOOL | BATAN | 1 |  | 4 | 2STY4CL | BATCH 1 | 9319084.26 |  |  | Completed | 1 |  |  | P00271869VS-CW1 | 18GA0133 | 2018-06-09 | 2018-06-14 | 2018-06-29 | 2018-07-30 | 2018-07-30 | Audric Const. & Supply
NC 2018 | K10 | Region VI | Aklan | 114750 | Kalibo Pilot Elementary School | KALIBO (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 17263102.76 |  |  | Completed | 1 |  |  | P00271870VS-CW1
NC 2018 | K10 | Region VI | Aklan | 114750 | Kalibo Pilot Elementary School | KALIBO (Capital) | 1 |  | 4 | 2STY4CL | BATCH 1 | 9106058.01 |  |  | Completed | 1 |  |  | P00271871VS-CW1
NC 2018 | K10 | Region VI | Aklan | 114846 | Balabag ES | MALAY | 2 | 1 | 2 | 1STY2CL | Batch 6 Realignment | 48539588.08 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Aklan | 114846 | Balabag ES | MALAY | 2 |  | 3 | 1STY3CL | Batch 6 Realignment | 0 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Aklan | 114846 | Balabag ES | MALAY | 2 |  | 6 | 1STY6CL | Batch 6 Realignment | 0 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Aklan | 114846 | Balabag ES | MALAY | 2 |  | 8 | 1STY8CL | Batch 6 Realignment | 0 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Aklan | 114851 | Manocmanoc ES | MALAY | 2 | 1 | 5 | 1STY5CL | Batch 6 Realignment | 53210127.15 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Aklan | 114851 | Manocmanoc ES | MALAY | 2 |  | 6 | 1STY6CL | Batch 6 Realignment | 0 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Aklan | 114851 | Manocmanoc ES | MALAY | 2 |  | 6 | 1STY6CL | Batch 6 Realignment | 0 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Aklan | 114851 | Manocmanoc ES | MALAY | 2 |  | 7 | 1STY7CL | Batch 6 Realignment | 0 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Aklan | 114921 | Laguinbanua ES | NUMANCIA | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9007262.76 |  |  | Completed | 1 |  |  | P00271876VS-CW1
NC 2018 | K10 | Region VI | Aklan | 114921 | Laguinbanua ES | NUMANCIA | 2 |  | 6 | 2STY6CL | BATCH 1 | 11717549.02 |  |  | Completed | 1 |  |  | P00271877VS-CW1
NC 2018 | K10 | Region VI | Aklan | 114923 | Numancia Integrated Sch | NUMANCIA | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11946372.02 |  |  | Completed | 1 |  |  | P00271878VS-CW1 | 18GA0167 | 2018-07-11 | 2018-07-18 | 2018-07-31
NC 2018 | SHS | Region VI | Aklan | 302286 | Altavas National School | ALTAVAS | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  | P00271880VS-CW1 | 18GA0159 | 2018-07-04 | 2018-07-11 | 2018-07-24 | 2018-07-31 |  | MBM Construction
NC 2018 | SHS | Region VI | Aklan | 302286 | Altavas National School | ALTAVAS | 1 |  | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  | P00271879VS-CW1 | 18GA0107 | 2018-07-04 | 2018-07-11 | 2018-07-24 | 2018-07-31 |  | MBM Construction
NC 2018 | TVL | Region VI | Aklan | 302286 | Altavas National School | ALTAVAS | 1 |  | 5 | Techvoc Standard Plan | BATCH 1 | 12820000 |  |  | Completed | 1 |  |  | P00271881VS-CW1 | 18GA0161 | 2018-07-04 | 2018-07-11 | 2018-07-24 | 2018-07-31 |  | MBM Construction
NC 2018 | SHS | Region VI | Aklan | 302287 | Justicia Morales-Young National High School | ALTAVAS | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  | P00271882VS-CW1 | 18GA0109 | 2018-07-04 | 2018-07-11 | 2018-07-24 | 2018-07-31 |  | Benzen Construction
NC 2018 | SHS | Region VI | Aklan | 302287 | Justicia Morales-Young National High School | ALTAVAS | 1 |  | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  | P00271883VS-CW1 | 18GA0110 | 2018-07-04 | 2018-07-11 | 2018-07-24 | 2018-07-31 |  | Edison Dev. & Const.
NC 2018 | SHS | Region VI | Aklan | 302287 | Justicia Morales-Young National High School | ALTAVAS | 1 |  | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  | P00271884VS-CW1 | 18GA0111 | 2018-07-04 | 2018-07-11 | 2018-07-24 | 2018-07-31 |  | Edison Dev. & Const.
NC 2018 | SHS | Region VI | Aklan | 302289 | Bacan National High School | BANGA | 1 | 1 | 12 | 3STY12CL | BATCH 1 | 31859267.25 |  |  | Completed | 1 |  |  | P00271885VS-CW1 | 18GA0143 | 2018-06-27 | 2018-07-04 | 2018-07-17 | 2018-07-30 | 2018-08-14 | Audric Const. & Supply
NC 2018 | SHS | Region VI | Aklan | 302291 | Batan Academy (A Nat'L Sch.) | BATAN | 1 | 1 | 12 | 4STY12CL | BATCH 1 | 33629789.72 |  |  | Completed | 1 |  |  | P00271886VS-CW1 | 18GA0170 | 2018-07-11 | 2018-07-18 | 2018-07-31
NC 2018 | SHS | Region VI | Aklan | 302294 | Bay-ang-Magpag-ong NHS | BATAN | 1 | 1 | 9 | 3STY9CL | BATCH 1 | 26558418.13 |  |  | Completed | 1 |  |  | P00271887VS-CW1 | 18GA0132 | 2018-06-09 | 2018-06-14 | 2018-06-29 | 2018-07-30 | 2018-08-17 | Audric Const. & Supply
NC 2018 | SHS | Region VI | Aklan | 302295 | Boracay NHS | MALAY | 2 | 1 | 4 | 1STY4CL | Batch 6 Realignment | 51380060.46 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Aklan | 302295 | Boracay NHS | MALAY | 2 |  | 8 | 1STY8CL | Batch 6 Realignment | 0 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Aklan | 302295 | Boracay NHS-Main | MALAY | 2 | 1 | 2 | mi | Batch 6 Realignment | 0 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Aklan | 302295 | Boracay NHS-Main | MALAY | 2 |  | 3 | 1STY3CL | Batch 6 Realignment | 0 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Aklan | 302298 | Dr. Ramon B. Legaspi, Sr. National High School | MAKATO | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 17005910.26 |  |  | Completed | 1 |  |  | P00271891VS-CW1 | 18GA0146 | 2018-06-27 | 2018-07-04 | 2018-07-17 | 2018-07-31 |  | Audric Const. & Supply
NC 2018 | SHS | Region VI | Aklan | 302299 | CALIZO NATIONAL HIGH SCHOOL | BALETE | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9017733.35 |  |  | Completed | 1 |  |  | P00271892VS-CW1 | 18GA0149 | 2018-06-27 | 2018-07-04 | 2018-07-17 | 2018-07-31
NC 2018 | SHS | Region VI | Aklan | 302301 | Camanci National High School | BATAN | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9038271.76 |  |  | Completed | 1 |  |  | P00271893VS-CW1 | 18GA0160 | 2018-07-04 | 2018-07-11 | 2018-07-24 | 2018-07-31 |  | Audric Const. & Supply
NC 2018 | SHS | Region VI | Aklan | 302301 | Camanci National High School | BATAN | 1 |  | 9 | 3STY9CL | BATCH 1 | 26749779.21 |  |  | Completed | 1 |  |  | P00271894VS-CW1 | 18GA0171 | 2018-07-11 | 2018-07-18 | 2018-07-31
NC 2018 | SHS | Region VI | Aklan | 302302 | Candelaria NHS | NEW WASHINGTON | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 17109300.41 |  |  | Completed | 1 |  |  | P00271895VS-CW1 | 18GA0158 | 2018-07-04 | 2018-07-11 | 2018-07-24 | 2018-07-31 |  | First Makeen Const.
NC 2018 | SHS | Region VI | Aklan | 302302 | Candelaria NHS | NEW WASHINGTON | 1 |  | 9 | 3STY9CL | BATCH 1 | 26764299.59 |  |  | Completed | 1 |  |  | P00271896VS-CW1 | 18GA0157 | 2018-07-04 | 2018-07-11 | 2018-07-24 | 2018-07-31 |  | First Makeen Const.
NC 2018 | SHS | Region VI | Aklan | 302304 | Catalino M. Prado NHS | LEZO | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  | P00271897VS-CW1 | 18GA0164 | 2018-07-11 | 2018-07-18 | 2018-07-31 |  |  | Inamarga Enterprises
NC 2018 | SHS | Region VI | Aklan | 302304 | Catalino M. Prado NHS | LEZO | 2 |  | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  | P00271898VS-CW1 | 18GA0165 | 2018-07-11 | 2018-07-18 | 2018-07-31 |  |  | Audric Const. & Supply
NC 2018 | SHS | Region VI | Aklan | 302306 | Daja Sur National High School | BANGA | 1 | 1 | 9 | 3STY9CL | BATCH 1 | 26528047.473 |  |  | Completed | 1 |  |  | P00271899VS-CW1 | 18GA0098 | 2018-06-08 | 2018-06-14 | 2018-06-28 | 2018-07-16 | 2018-08-07 | Audric Const. & Supply
NC 2018 | SHS | Region VI | Aklan | 302307 | Father Julian C. Rago Memorial NHS | BALETE | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9017733.35 |  |  | Completed | 1 |  |  | P00271900VS-CW1 | 18GA0091 | 2018-06-06 | 2018-06-13 | 2018-06-26 | 2018-06-29 | 2018-07-25 | Audric Const. & Supply
NC 2018 | SHS | Region VI | Aklan | 302307 | Father Julian C. Rago Memorial NHS | BALETE | 1 |  | 4 | 2STY4CL | BATCH 1 | 9085273.72 |  |  | Completed | 1 |  |  | P00271901VS-CW1 | 18GA0093 | 2018-06-06 | 2018-06-13 | 2018-06-26 | 2018-06-29 | 2018-07-25 | Audric Const. & Supply
NC 2018 | SHS | Region VI | Aklan | 302308 | Jose Borromeo Legaspi Memorial National High School | BALETE | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  | P00271902VS-CW1 | 18GA0162 | 2018-07-11 | 2018-07-18 | 2018-07-31 | 2018-08-14 |  | Audric Const. & Supply
NC 2018 | SHS | Region VI | Aklan | 302308 | Jose Borromeo Legaspi Memorial National High School | BALETE | 1 |  | 4 | 2STY4CL | BATCH 1 | 9059322 |  |  | Completed | 1 |  |  | P00271903VS-CW1 | 18GA0163 | 2018-07-11 | 2018-07-18 | 2018-07-31 |  |  | Audric Const. & Supply
NC 2018 | SHS | Region VI | Aklan | 302311 | Guadalupe NHS | LIBACAO | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 17427065.17 |  |  | Completed | 1 |  |  | P00271904VS-CW1 | 18GA0123 | 2018-06-09 | 2018-06-14 | 2018-07-29 | 2018-07-26 | 2018-08-17 | Audric Const. & Supply
NC 2018 | SHS | Region VI | Aklan | 302312 | Lilo-an National High School | MALINAO | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9096856.96 |  |  | Completed | 1 |  |  | P00271905VS-CW1 | 18GA0105 | 2018-06-08 | 2018-06-14 | 2018-07-28 | 2018-07-23 | 2018-08-14 | G.F. Rovero Merchandising
NC 2018 | SHS | Region VI | Aklan | 302312 | Lilo-an National High School | MALINAO | 2 |  | 4 | 2STY4CL | BATCH 1 | 9308322.19 |  |  | Completed | 1 |  |  | P00271906VS-CW1 | 18GA0106 | 2018-06-08 | 2018-06-14 | 2018-07-28 | 2018-07-23 | 2018-08-14 | G.F. Rovero Merchandising
NC 2018 | SHS | Region VI | Aklan | 302313 | Linabuan NHS | KALIBO (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 1 | 18635726.92 |  |  | Completed | 1 |  |  | P00271907VS-CW1 | 18GA0141 | 2018-06-27 | 2018-07-04 | 2018-07-17 | 2018-07-31 |  | First Makeen Const.
NC 2018 | SHS | Region VI | Aklan | 302313 | Linabuan NHS | KALIBO (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 1 | 18635726.92 |  |  | Completed | 1 |  |  | P00271908VS-CW1 | 18GA0142 | 2018-06-27 | 2018-07-04 | 2018-07-17 | 2018-07-31
NC 2018 | SHS | Region VI | Aklan | 302314 | LOCTUGA NATIONAL HIGH SCHOOL | LIBACAO | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 10956433.48 |  |  | Completed | 1 |  |  | P00271909VS-CW1 | 18GA0090 | 2018-06-06 | 2018-06-13 | 2018-06-26 | 2018-06-29 | 2018-08-03 | First Makeen Const.
NC 2018 | SHS | Region VI | Aklan | 302317 | Malay National High School | MALAY | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9031140.51 |  |  | Completed | 1 |  |  | P00271911VS-CW1 | 18GA0102 | 2018-06-06 | 2018-06-14 | 2018-07-28 | 2018-07-31 | 2018-08-17 | Audric Const. & Supply
NC 2018 | SHS | Region VI | Aklan | 302317 | Malay National High School | MALAY | 2 |  | 4 | 2STY4CL | BATCH 1 | 9031140.51 |  |  | Completed | 1 |  |  | P00271910VS-CW1 | 18GA0103 | 2018-06-08 | 2018-06-14 | 2018-07-28 | 2018-07-16 | 2018-08-07 | Audric Const. & Supply
NC 2018 | SHS | Region VI | Aklan | 302321 | Naile NHS | IBAJAY | 2 | 1 | 8 | 4STY8CL | BATCH 1 | 18680065.67 |  |  | Completed | 1 |  |  | P00271912VS-CW1 | 18GA0153 | 2018-07-04 | 2018-07-11 | 2018-07-24 | 2018-07-31 |  | G.F. Rovero Merchandising
NC 2018 | SHS | Region VI | Aklan | 302323 | Gaudencio L. Vega NHS (Nalook NHS) | KALIBO (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 1 | 18610820.67 |  |  | Completed | 1 |  |  | P00271914VS-CW1 | 18GA0138 | 2018-06-27 | 2018-07-04 | 2018-07-17 | 2018-07-31 |  | G.F. Rovero Merchandising
NC 2018 | SHS | Region VI | Aklan | 302323 | Gaudencio L. Vega NHS (Nalook NHS) | KALIBO (Capital) | 1 |  | 8 | 4STY8CL | BATCH 1 | 18742070.67 |  |  | Completed | 1 |  |  | P00271915VS-CW1 | 18GA0139 | 2018-06-27 | 2018-07-04 | 2018-07-17 | 2018-07-31 |  | G.F. Rovero Merchandising
NC 2018 | SHS | Region VI | Aklan | 302323 | Gaudencio L. Vega NHS (Nalook NHS) | KALIBO (Capital) | 1 |  | 8 | 4STY8CL | BATCH 1 | 18742070.67 |  |  | Completed | 1 |  |  | P00271913VS-CW1 | 18GA0140 | 2018-06-27 | 2018-07-04 | 2018-07-17 | 2018-07-31 |  | G.F. Rovero Merchandising
NC 2018 | SHS | Region VI | Aklan | 302327 | Numancia National Sch. Of Fisheries | NUMANCIA | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9011302.76 |  |  | Completed | 1 |  |  | P00271916VS-CW1 | 18GA0128 | 2018-07-04 | 2018-07-11 | 2018-07-24 | 2018-07-31
NC 2018 | SHS | Region VI | Aklan | 302327 | Numancia National Sch. Of Fisheries | NUMANCIA | 2 |  | 6 | 2STY6CL | BATCH 1 | 11781569.02 |  |  | Completed | 1 |  |  | P00271917VS-CW1 | 18GA0166 | 2018-07-11 | 2018-07-18 | 2018-07-31
NC 2018 | SHS | Region VI | Aklan | 302328 | Ochando National High School | NEW WASHINGTON | 1 | 1 | 9 | 3STY9CL | BATCH 1 | 26862842.77 |  |  | Completed | 1 |  |  | P00271918VS-CW1 | 18GA0156 | 2018-07-04 | 2018-07-11 | 2018-07-24 | 2018-07-31
NC 2018 | SHS | Region VI | Aklan | 302330 | Ibajay NHS | IBAJAY | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9802087.29 |  |  | Completed | 1 |  |  | P00271919VS-CW1 | 18GA0116 | 2018-07-04 | 2018-07-11 | 2018-07-24 | 2018-07-31 |  | G.F. Rovero Merchandising
NC 2018 | SHS | Region VI | Aklan | 302332 | Regional Science High School for Region VI | KALIBO (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 1 | 18539726.92 |  |  | Completed | 1 |  |  | P00271920VS-CW1 | 18GA0145 | 2018-06-27 | 2018-07-04 | 2018-07-17 | 2018-07-31 | 2018-08-17 | Audric Const & Supply
NC 2018 | SHS | Region VI | Aklan | 302333 | Rizal J. Rodriguez Sr. NHS | BATAN | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 11819149.24 |  |  | Completed | 1 |  |  | P00271921VS-CW1 | 18GA0117 | 2018-06-08 | 2018-06-14 | 2018-06-28 | 2018-07-16 | 2018-08-07 | First Makeen Const.
NC 2018 | SHS | Region VI | Aklan | 302335 | Solido National High School | NABAS | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12167057.53 |  |  | Completed | 1 |  |  | P00271922VS-CW1 | 18GA0089 | 2018-06-06 | 2018-06-13 | 2018-06-26 | 2018-06-29 | 2018-07-25 | G.F. Rovero Merchandising
NC 2018 | SHS | Region VI | Aklan | 302337 | Toledo NHS | NABAS | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12034865.8 |  |  | Completed | 1 |  |  | P00271923VS-CW1 | 18GA0094 | 2018-06-07 | 2018-06-14 | 2018-06-27 | 2018-06-29 | 2018-08-10 | G.F. Rovero Merchandising
NC 2018 | SHS | Region VI | Aklan | 302338 | Torralba NHS | BANGA | 1 | 1 | 9 | 3STY9CL | BATCH 1 | 26760547.73 |  |  | Completed | 1 |  |  | P00271924VS-CW1 | 18GA0119 | 2018-06-08 | 2018-06-14 | 2018-06-28 | 2018-07-31 |  | Audric Const. & Supply
NC 2018 | SHS | Region VI | Aklan | 302339 | Unidos NHS | NABAS | 2 | 1 | 9 | 3STY9CL | BATCH 1 | 27005490.26 |  |  | Completed | 1 |  |  | P00271925VS-CW1 | 18GA0154 | 2018-07-04 | 2018-07-11 | 2018-07-24 | 2018-07-31 |  | G.F. Rovero Merchandising
NC 2018 | SHS | Region VI | Aklan | 302339 | Unidos NHS | NABAS | 2 |  | 9 | 3STY9CL | BATCH 1 | 27005490.26 |  |  | Completed | 1 |  |  | P00271926VS-CW1 | 18GA0155 | 2018-07-04 | 2018-07-11 | 2018-07-24 | 2018-07-31 |  | G.F. Rovero Merchandising
NC 2018 | SHS | Region VI | Aklan | 302340 | Union National High School | NABAS | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9399591.44 |  |  | Completed | 1 |  |  | P00271928VS-CW1 | 18GA0114 | 2018-06-08 | 2018-06-14 | 2018-06-28 | 2018-07-30 | 2018-08-14 | G.F. Rovero Merchandising
NC 2018 | SHS | Region VI | Aklan | 302340 | Union National High School | NABAS | 2 |  | 4 | 2STY4CL | BATCH 1 | 9399590.76 |  |  | Completed | 1 |  |  | P00271927VS-CW1 | 18GA0126 | 2018-06-09 | 2018-06-14 | 2018-06-29 | 2018-07-26 | 2018-08-08 | G.F. Rovero Merchandising
NC 2018 | SHS | Region VI | Aklan | 310602 | Mangan National High School | BANGA | 1 | 1 | 8 | 4STY8CL | BATCH 1 | 18523470.67 |  |  | Completed | 1 |  |  | P00271929VS-CW1 | 18GA0147 | 2018-06-27 | 2018-07-04 | 2018-07-17 | 2018-07-31 |  | Audric Const. & Supply
NC 2018 | SHS | Region VI | Aklan | 310603 | LAMBERTO H. TIROL NATIONAL HIGH SCHOOL | MALAY | 2 | 1 | 1 | 1STY1CL | Batch 6 Realignment | 29513975.18 |  |  | REVERTED | 0
NC 2018 | SHS | Region VI | Aklan | 310603 | LAMBERTO H. TIROL NATIONAL HIGH SCHOOL | MALAY | 2 |  | 2 | 1STY2CL | Batch 6 Realignment | 0 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Aklan | 310603 | LAMBERTO H. TIROL NATIONAL HIGH SCHOOL | MALAY | 2 |  | 3 | 1STY3CL | Batch 6 Realignment | 0 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Aklan | 310603 | LAMBERTO H. TIROL NATIONAL HIGH SCHOOL | MALAY | 2 |  | 4 | 1STY4CL | Batch 6 Realignment | 0 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Aklan | 310616 | Agtughangin Integrated School | MADALAG | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9557524.81 |  |  | REVERTED | 0 | [10 empty] | cancelled; hauling cost matter
NC 2018 | SHS | Region VI | Aklan | 310617 | Alfonso XII NHS | LIBACAO | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9565297.32 |  |  | Completed | 1 |  |  | P00271932VS-CW1 | 18GA0095 | 2018-06-07 | 2018-06-14 | 2018-06-27 | 2018-06-29 | 2018-08-08 | Inamarga Enterprises
NC 2018 | SHS | Region VI | Aklan | 500035 | Numancia Integrated School | NUMANCIA | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 8991021.76 |  |  | Completed | 1 |  |  | P00271933VS-CW1 | 18GA0108 | 2018-06-08 | 2018-06-14 | 2018-07-28 | 2018-07-30 | 2018-08-14 | First Makeen Const.
NC 2018 | TVL | Region VI | Aklan | 500170 | Aguinaldo T. Repiedad, Sr. IS | BANGA | 1 | 1 | 1 | Techvoc Standard Plan | BATCH 1 | 2570200 |  |  | Completed | 1 |  |  | P00271934VS-CW1 | 18GA0097 | 2018-06-07 | 2018-06-14 | 2018-06-27 | 2018-06-29 | 2018-07-25 | Audric Const. & Supply
NC 2018 | SHS | Region VI | Aklan | 500171 | Lezo Integrated School | LEZO | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9017733.35 |  |  | Completed | 1 |  |  | P00271935VS-CW1 | 18GA0127 | 2018-06-09 | 2018-06-14 | 2018-06-29 | 2018-07-24 | 2018-08-14 | Inamarga Enterprises
NC 2018 | SHS | Region VI | Aklan | 500171 | Lezo Integrated School | LEZO | 2 |  | 4 | 2STY4CL | BATCH 1 | 9085273.72 |  |  | Completed | 1 |  |  | P00271936VS-CW1 | 18GA0115 | 2018-06-08 | 2018-06-14 | 2018-06-28 | 2018-07-30 |  | First Makeen Const.
NC 2018 | TVL | Region VI | Aklan | 500171 | Lezo Integrated School | LEZO | 2 |  | 1 | Techvoc Standard Plan | BATCH 1 | 2554000 |  |  | Completed | 1 |  |  | P00271937VS-CW1 | 18GA0096 | 2018-06-07 | 2018-06-14 | 2018-06-27 | 2018-06-29 | 2018-08-16 | Inamarga Enterprises
NC 2018 | SHS | Region VI | Aklan | 500173 | Tamalagon Integrated School | TANGALAN | 2 | 1 | 8 | 4STY8CL | BATCH 1 | 18749570.67 |  |  | Completed | 1 |  |  | P00271938VS-CW1 | 18GA0150 | 2018-06-27 | 2018-07-04 | 2018-07-17 | 2018-07-31 |  | First Makeen Const.
NC 2018 | SHS | Region VI | Aklan | 500174 | Ortega Integrated School | LIBACAO | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 16019210.26 |  |  | Completed | 1 |  |  | P00271939VS-CW1 | 18GA0152 | 2018-07-04 | 2018-07-11 | 2018-07-24 | 2018-07-31 |  | Inamarga Enterprises
NC 2018 | SHS | Region VI | Aklan | 500175 | Kinalangay Viejo IS | MALINAO | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11656168.02 |  |  | Completed | 1 |  |  | P00271940VS-CW1 | 18GA0168 | 2018-07-11 | 2018-07-18 | 2018-07-31
NC 2018 | SHS | Region VI | Aklan | 500175 | Kinalangay Viejo IS | MALINAO | 2 |  | 6 | 2STY6CL | BATCH 1 | 11656168.02 |  |  | Completed | 1 |  |  | P00271941VS-CW1 | 18GA0169 | 2018-07-11 | 2018-07-18 | 2018-07-31
NC 2018 | SHS | Region VI | Aklan | 500181 | Dalagsaan Integrated School | LIBACAO | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 19759942.74 |  |  | Terminated | 0 |  |  | P00271942VS-CW1 | 18GA0131 | 2018-08-03 | 2018-08-10 | 2018-08-23 |  |  |  | cannot be modified anymore; to terminate and revert funding then request for reprogramming
NC 2018 | SHS | Region VI | Aklan | 500182 | Habana Integrated School | BURUANGA | 2 | 1 | 9 | 3STY9CL | BATCH 1 | 26859419.56 |  |  | Completed | 1 |  |  | P00271943VS-CW1 | 18GA0124 | 2018-06-09 | 2018-06-14 | 2018-06-29 | 2018-07-19 | 2018-08-08 | G.F. Rovero Merchandising
NC 2018 | TVL | Region VI | Aklan | 500186 | Pinamuk-an Integrated School | NEW WASHINGTON | 1 | 1 | 1 | Techvoc Standard Plan | BATCH 1 | 2902660.66 |  |  | Completed | 1 |  |  | P00271944VS-CW1 | 18GA0099 | 2018-06-08 | 2018-06-14 | 2018-06-28 | 2018-07-23 | 2018-08-14 | Inamarga Enterprises
NC 2018 | K10 | Region VI | Antique | 115224 | Canuto B. Pefianco Sr. ES (Madrangca ES) | SAN JOSE (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 9045901.76 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Antique | 302342 | Antique VS | BUGASONG | 0 | 1 | 8 | 2STY8CL | BATCH 1 | 16974790.26 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Antique | 302351 | Col. Ruperto Abellon NHS | LAUA-AN | 0 | 1 | 9 | 3STY9CL | BATCH 1 | 25433084.36 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Antique | 302358 | Gov. Julio V. Macuja MCHS | HAMTIC | 0 | 1 | 6 | 2STY6CL | BATCH 1 | 12562303.88 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Antique | 302363 | Libertad NVS | LIBERTAD | 0 | 1 | 6 | 2STY6CL | BATCH 1 | 12362303.88 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Antique | 114939 | Anini-y CS | ANINI-Y | 0 | 1 | 6 | 2STY6CL | Batch 3 | 11945897.51 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Antique | 114967 | Magtulis ES | BARBAZA | 0 | 1 | 6 | 2STY6CL | Batch 3 | 12598855.86 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Antique | 115033 | Bitadton ES | CULASI | 0 | 1 | 8 | 2STY8CL | Batch 3 | 18078511.47 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Antique | 115179 | Col. Ruperto Abellon Sr. MS | PATNONGON | 0 | 1 | 6 | 2STY6CL | Batch 3 | 11845394.99 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Antique | 115212 | Assemblyman Segundo Moscoso MS | SAN JOSE (Capital) | 0 | 1 | 6 | 2STY6CL | Batch 3 | 11845394.99 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Antique | 115213 | Atabay ES | SAN JOSE (Capital) | 0 | 1 | 9 | 3STY9CL | Batch 3 | 24721656.01 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Antique | 115220 | Gov. Santos Capadocia MS | SAN JOSE (Capital) | 0 | 1 | 15 | 3STY15CL | Batch 3 | 33976823.81 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Antique | 115344 | Malabor ES | TIBIAO | 0 | 1 | 6 | 2STY6CL | Batch 3 | 11845394.99 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Antique | 115348 | San Francisco Norte ES | TIBIAO | 0 | 1 | 6 | 2STY6CL | Batch 3 | 11845394.99 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Antique | 115364 | Dao CS | TOBIAS FORNIER (DAO) | 0 | 1 | 6 | 2STY6CL | Batch 3 | 12548604.61 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Antique | 302341 | Antique NS | SAN JOSE (Capital) | 0 |  | 24 | 4STY24CL | Batch 3 | 47857698.23 |  |  | Completed | 1 | [10 empty] | Working on and off
NC 2018 | SHS | Region VI | Antique | 302341 | Antique NS | SAN JOSE (Capital) | 0 | 1 | 16 | 4STY16CL | Batch 3 | 37297224.08 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Bacolod City | 181002 | Fr. Gratian Murray, AFCS IS | BACOLOD CITY (Capital) | 0 | 1 | 4 | 2STY4 lab (2 science lab & 2 ICT lab) | BATCH 1 | 18931180 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Bacolod City | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 1 | 4506237.6667 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Bacolod City | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 1 | 4506237.6667 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Bacolod City | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 1 | 4506237.6667 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Bacolod City | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 |  | 8 | 4sty 8 regular workshop | BATCH 1 | 37852360 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Bacolod City | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 |  | 3 | 3sty 3 regular workshop | BATCH 1 | 14305885 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Bacolod City | 302700 | Alangilan NHS | BACOLOD CITY (Capital) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 1 | 4494571 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Bacolod City | 302700 | Alangilan NHS | BACOLOD CITY (Capital) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4082865.25 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Bacolod City | 302700 | Alangilan NHS | BACOLOD CITY (Capital) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4082865.25 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Bacolod City | 302700 | Alangilan NHS | BACOLOD CITY (Capital) | 0 |  | 4 | 2STY4 lab (2 science lab & 2 ICT lab) | BATCH 1 | 18931180 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Bacolod City | 302701 | Bacolod City NHS | BACOLOD CITY (Capital) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 1 | 4494571 |  |  | COMPLETED | 1 | [10 empty] | WITH DEFECTS (NOT YET RECTIFIED)
NC 2018 | TVL | Region VI | Bacolod City | 302701 | Bacolod City NHS | BACOLOD CITY (Capital) | 0 |  | 8 | 4sty- 8 regular workshop | BATCH 1 | 37712360 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Bacolod City | 302701 | Bacolod City NHS | BACOLOD CITY (Capital) | 0 |  | 2 | 2sty- 2 science lab | BATCH 1 | 9540590 |  |  | COMPLETED | 1 | [10 empty] | WITH DEFECTS (ON GOING RECTIFICATION)
NC 2018 | TVL | Region VI | Bacolod City | 302701 | Bacolod City NHS | BACOLOD CITY (Capital) | 0 |  | 2 | 2sty- 2 ICT lab | BATCH 1 | 9690590 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Bacolod City | 302702 | Barangay Singcang-Airport NHS | BACOLOD CITY (Capital) | 0 | 1 | 12 | 4STY 7 LAB (2 sci lab, 2 ICT, 3 regular workshop, 6 CL) | BATCH 1 | 48802065 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Bacolod City | 302703 | Bata NHS | BACOLOD CITY (Capital) | 0 | 1 | 8 | 4STY8 LAB (4 regular workshop, 2 sci lab, 2 ICT lab) | BATCH 1 | 37662360 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Bacolod City | 302704 | Romanito Maravilla NHS | BACOLOD CITY (Capital) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4232865.25 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Bacolod City | 302704 | Romanito Maravilla NHS | BACOLOD CITY (Capital) | 0 |  | 4 | 2STY4 lab (2 science lab & 2 ICT lab) | BATCH 1 | 20431180 |  |  | COMPLETED | 1 | [10 empty] | WITH DEFECTS (NOT YET RECTIFIED)
NC 2018 | TVL | Region VI | Bacolod City | 302705 | Domingo Lacson NHS | BACOLOD CITY (Capital) | 0 | 1 | 8 | 4STY8 LAB (4 regular workshop, 2 sci lab, 2 ICT lab) | BATCH 1 | 42012360 |  |  | COMPLETED | 1 | [10 empty] | WITH DEFECTS (NOT YET RECTIFIED)
NC 2018 | TVL | Region VI | Bacolod City | 302705 | Domingo Lacson NHS | BACOLOD CITY (Capital) | 0 |  | 2 | 2STY regular workshop w/ 2CL | BATCH 1 | 15490590 |  |  | COMPLETED | 1 | [10 empty] | WITH DEFECTS (NOT YET RECTIFIED)
NC 2018 | TVL | Region VI | Bacolod City | 302706 | Emiliano Lizares NHS | BACOLOD CITY (Capital) | 0 | 1 | 8 | 4STY8 LAB (4 regular workshop, 2 sci lab, 2 ICT lab) | BATCH 1 | 37562360 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Bacolod City | 302709 | Luis Hervias NHS | BACOLOD CITY (Capital) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 1 | 4494571 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Bacolod City | 302709 | Luis Hervias NHS | BACOLOD CITY (Capital) | 0 |  | 8 | 4STY8 LAB (4 regular workshop, 2 sci lab, 2 ICT lab) | BATCH 1 | 37712360 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Bacolod City | 302709 | Luis Hervias NHS | BACOLOD CITY (Capital) | 0 |  | 2 | 2sty- 2 regular workshop | BATCH 1 | 9575590 |  |  | COMPLETED | 1 | [10 empty] | ADDTINOAL FUND (BEFF 2021)
NC 2018 | TVL | Region VI | Bacolod City | 302710 | Mandalagan NHS | BACOLOD CITY (Capital) | 0 | 1 | 8 | 4STY8 LAB (4 regular workshop, 2 sci lab, 2 ICT lab) | BATCH 1 | 39212360 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Bacolod City | 302711 | Luisa Medel NHS | BACOLOD CITY (Capital) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4176198.5833 |  |  | COMPLETED | 1 | [10 empty] | WITH DEFECTS (NOT YET RECTIFIED)
NC 2018 | TVL | Region VI | Bacolod City | 302711 | Luisa Medel NHS | BACOLOD CITY (Capital) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4176198.5833 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Bacolod City | 302711 | Luisa Medel NHS | BACOLOD CITY (Capital) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4176198.5833 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Bacolod City | 302711 | Luisa Medel NHS | BACOLOD CITY (Capital) | 0 |  | 8 | 4STY4 LAB (2 sci lab, 2 ICT, w/ 4CL) | BATCH 1 | 19071180 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Bacolod City | 302712 | Handumanan NHS | BACOLOD CITY (Capital) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4267865.25 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Bacolod City | 302712 | Handumanan NHS | BACOLOD CITY (Capital) | 0 |  | 6 | 3STY6 LAB (2 sci lab, 2 ICT, 2 regular workshop) | BATCH 1 | 28531770 |  |  | COMPLETED | 1 | [10 empty] | WITH DEFECTS (ON GOING RECTIFICATION)
NC 2018 | TVL | Region VI | Bacolod City | 302713 | Jovito H. Sayson NHS | BACOLOD CITY (Capital) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4267865.25 |  |  | COMPLETED | 1 | [10 empty] | WITH DEFECTS (ON GOING RECTIFICATION)
NC 2018 | TVL | Region VI | Bacolod City | 302713 | Jovito H. Sayson NHS | BACOLOD CITY (Capital) | 0 |  | 6 | 2STY6 LAB (2 regular workshop, 2 sci lab, 2 ICT lab) | BATCH 1 | 28546770 |  |  | COMPLETED | 1 | [10 empty] | WITH DEFECTS (NOT YET RECTIFIED)
NC 2018 | TVL | Region VI | Bacolod City | 302714 | Mansilingan Agro-Ind. HS | BACOLOD CITY (Capital) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4187865.25 |  |  | COMPLETED | 1 | [10 empty] | WITH DEFECTS (NOT YET RECTIFIED)
NC 2018 | TVL | Region VI | Bacolod City | 302714 | Mansilingan Agro-Ind. HS | BACOLOD CITY (Capital) | 0 |  | 6 | 3STY6 LAB (2 sci lab, 2 ICT, 2 regular workshop) | BATCH 1 | 28636770 |  |  | Completed | 1 | [10 empty] | WITH DEFECTS (NOT YET RECTIFIED)
NC 2018 | TVL | Region VI | Bacolod City | 302715 | Paglaum Village NHS | BACOLOD CITY (Capital) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4382865.25 |  |  | Completed | 1 | [10 empty] | ADDTINOAL FUND (BEFF 2021)
NC 2018 | TVL | Region VI | Bacolod City | 302715 | Paglaum Village NHS | BACOLOD CITY (Capital) | 0 |  | 6 | 3STY6 LAB (2 sci lab, 2 ICT, 2 regular workshop) | BATCH 1 | 28903770 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Bacolod City | 302716 | Sum-ag NHS | BACOLOD CITY (Capital) | 0 | 1 | 6 | 3STY- 6 regular workshop | BATCH 1 | 28321770 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Bacolod City | 302716 | Sum-ag NHS | BACOLOD CITY (Capital) | 0 |  | 4 | 2STY4 lab (2 science lab & 2 ICT lab) | BATCH 1 | 18931180 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Bacolod City | 302718 | Teofilo M. Gensoli Sr. NHS | BACOLOD CITY (Capital) | 0 | 1 | 4 | 2STY4 lab (2 science lab & 2 ICT lab) | BATCH 1 | 18931180 |  |  | Completed | 1 | [10 empty] | WITH DEFECTS (NOT YET RECTIFIED)
NC 2018 | TVL | Region VI | Bacolod City | 311201 | M. G. Medalla Integrated School | BACOLOD CITY (Capital) | 0 | 1 | 4 | 4STY4 LAB (2 sci lab, 2 ICT lab) | BATCH 1 | 19141180 |  |  | Completed | 1 | [10 empty] | WITH DEFECTS (NOT YET RECTIFIED)
NC 2018 | TVL | Region VI | Bacolod City | 311202 | Fr. Gratian Murray, AFSC IS | BACOLOD CITY (Capital) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4082865.25 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Bacolod City | 311202 | Fr. Gratian Murray, AFSC IS | BACOLOD CITY (Capital) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4082865.25 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Bacolod City | 311202 | Fr. Gratian Murray, AFSC IS | BACOLOD CITY (Capital) | 0 |  | 4 | 2STY WORKSHOP BLDG | BATCH 1 | 18931180 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Bacolod City | 343604 | ANDRES BONIFACIO SENIOR HIGH SCHOOL | BACOLOD CITY (Capital) | 0 | 1 | 4 | 2STY4 lab (2 science lab & 2 ICT lab) | BATCH 1 | 18931180 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Bacolod City | 343604 | ANDRES BONIFACIO SENIOR HIGH SCHOOL | BACOLOD CITY (Capital) | 0 |  | 4 | 2sty- 2 regular workshop | BATCH 1 | 13340590 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Bago City | 117499 | Ma. Rosario Araneta ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2769354.78 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Bago City | 117510 | M.L. Araneta ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2735664.46 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Bago City | 302719 | Ramon Torres NHS | BAGO CITY | 4 | 1 | 8 | 2STY8CL | Batch 3 | 22521688.93 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Bago City | 361021 | Bago City Senior High School | BAGO CITY | 4 | 1 | 8 | 2STY8CL | Batch 3 | 22521688.93 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Bago City | 117523 | Ma-ao Elementary School | BAGO CITY | 4 | 1 | 6 | 2STY6CL | Batch 3 | 17661474.87 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Cadiz City | 302726 | Cadiz Viejo NHS | CADIZ CITY | 2 | 1 | 12 | 3STY12CL | BATCH 1 | 32894632.25 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Cadiz City | 302727 | Sicaba National High School | CADIZ CITY | 2 | 1 | 12 | 3STY12CL | BATCH 1 | 34489632.95 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Cadiz City | 302728 | Caduha-an NHS | Cadiz City | 2 | 1 | 20 | 4STY20CL | BATCH 1 | 55544539.82 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Cadiz City | 302728 | Caduha-an NHS | CADIZ CITY | 2 |  | 16 | 4STY16CL | BATCH 1 | 49970613.06 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Cadiz City | 302729 | Caduha-an NHS - Andres Bonifacio Ext. HS | CADIZ CITY | 2 | 1 | 16 | 4STY16CL | BATCH 1 | 41850250.73 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Cadiz City | 302730 | Dr. Vicente F. Gustilo Memorial NHS | CADIZ CITY | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 22742162.11 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Cadiz City | 302731 | Mabini National High School | CADIZ CITY | 2 | 1 | 16 | 4STY16CL | BATCH 1 | 49310613.07 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Cadiz City | 302732 | SPED High School | CADIZ CITY | 2 | 1 | 12 | 3STY12CL | BATCH 1 | 39958671.74 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Cadiz City | 302733 | Tiglawigan NHS | CADIZ CITY | 2 | 1 | 12 | 3STY12CL | BATCH 1 | 39499632.94 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Cadiz City | 302734 | Tiglawigan NHS - Magsaysay Extension High School | CADIZ CITY | 2 |  | 4 | 2STY4CL | BATCH 1 | 10153930.91 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Cadiz City | 302734 | Tiglawigan NHS - Magsaysay Extension High School | CADIZ CITY | 2 |  | 4 | 2STY4CL | BATCH 1 | 10142930.91 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Cadiz City | 302735 | Villacin National High School | CADIZ CITY | 2 | 1 | 12 | 3STY12CL | BATCH 1 | 38869671.74 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Cadiz City | 302736 | Jerusalem National High School | CADIZ CITY | 2 | 1 | 16 | 4STY16CL | BATCH 1 | 50025613.07 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Cadiz City | 311403 | Mabini NHS - Alimatoc Ext. HS | CADIZ CITY | 2 | 1 | 6 | 3STY6CL | BATCH 1 | 16020905.58 |  |  | completed | 1
NC 2018 | SHS | Region VI | Cadiz City | 311403 | Mabini NHS - Alimatoc Ext. HS | CADIZ CITY | 2 |  | 4 | 2STY4CL | BATCH 1 | 10582930.91 |  |  | completed | 1
NC 2018 | SHS | Region VI | Cadiz City | 311403 | Mabini NHS - Alimatoc Ext. HS | CADIZ CITY | 2 |  | 4 | 2STY4CL | BATCH 1 | 10582930.91 |  |  | completed | 1
NC 2018 | SHS | Region VI | Cadiz City | 311405 | Banquerohan NHS (Dr. Vicente F Gustilo NHS-Banquerohan Ext) | CADIZ CITY | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 24167162.11 |  |  | completed | 1
NC 2018 | SHS | Region VI | Cadiz City | 311405 | Banquerohan NHS (Dr. Vicente F Gustilo NHS-Banquerohan Ext) | CADIZ CITY | 2 |  | 8 | 2STY8CL | BATCH 1 | 24167162.11 |  |  | completed | 1
NC 2018 | TVL | Region VI | Capiz | 302418 | Panitan NHS | PANITAN | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4550118.06 |  |  | completed | 1
NC 2018 | TVL | Region VI | Capiz | 310812 | Pawa National High School | PANAY | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4470118.06 |  |  | completed | 1
NC 2018 | K10 | Region VI | Capiz | 115418 | Cuartero CES | CUARTERO | 2 | 1 | 15 | 3STY15CL | BATCH 1 | 38236939.69 |  |  | completed | 1
NC 2018 | K10 | Region VI | Capiz | 115454 | Dumalag CS | DUMALAG | 2 | 1 | 16 | 4STY16CL | BATCH 1 | 40620737.96 |  |  | completed | 1
NC 2018 | K10 | Region VI | Capiz | 115471 | Agmalate ES | DUMARAO | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 10025901.76 |  |  | completed | 1
NC 2018 | K10 | Region VI | Capiz | 115484 | Gibato Elementary School | DUMARAO | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 10025901.76 |  |  | completed | 1
NC 2018 | K10 | Region VI | Capiz | 115759 | Calixto Loyola Sr. ES (Mansacul ES) | SIGMA | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 10345901.76 |  |  | completed | 1
NC 2018 | K10 | Region VI | Capiz | 115763 | Jose Reyes Jarencio ES | SIGMA | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 10075901.76 |  |  | completed | 1
NC 2018 | SHS | Region VI | Capiz | 302389 | Camburanan NHS | TAPAZ | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 10025901.76 |  |  | completed | 1
NC 2018 | SHS | Region VI | Capiz | 302389 | Camburanan NHS | TAPAZ | 2 |  | 4 | 2STY4CL | BATCH 1 | 10125790.82 |  |  | completed | 1
NC 2018 | SHS | Region VI | Capiz | 302402 | Estefania Montemayor NHS | DUMARAO | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 19046665.26 |  |  | completed | 1
NC 2018 | TVL | Region VI | Capiz | 302406 | Ivisan NHS | IVISAN | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 1 | 2559062.5 |  |  | completed | 1
NC 2018 | SHS | Region VI | Capiz | 302407 | Macario Delfin Bermejo NHS | JAMINDAN | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 19889790.26 |  |  | completed | 1
NC 2018 | SHS | Region VI | Capiz | 302408 | Jagnaya NHS | JAMINDAN | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 18969790.26 |  |  | completed | 1
NC 2018 | SHS | Region VI | Capiz | 302416 | Manuel F. Onato NHS | DUMARAO | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 19158134.01 |  |  | completed | 1
NC 2018 | SHS | Region VI | Capiz | 302416 | Manuel F. Onato NHS | DUMARAO | 2 |  | 6 | 3STY6CL | BATCH 1 | 15384320.1 |  |  | completed | 1
NC 2018 | SHS | Region VI | Capiz | 302417 | Mayor Ramon A. Benjamin Sr. National High School | DUMARAO | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 19213540.26 |  |  | completed | 1
NC 2018 | SHS | Region VI | Capiz | 302421 | Putian National High School | CUARTERO | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 19248790.26 |  |  | completed | 1
NC 2018 | SHS | Region VI | Capiz | 310804 | Maindang National High School | CUARTERO | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 19248790.26 |  |  | completed | 1
NC 2018 | SHS | Region VI | Capiz | 310808 | SAN ANTONIO NATIONAL HIGH SCHOOL | CUARTERO | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 19873540.26 |  |  | completed | 1
NC 2018 | SHS | Region VI | Capiz | 310814 | Presentacion Diez Gregorio NHS | DUMARAO | 2 | 1 | 12 | 3STY12CL | BATCH 1 | 32728681.31 |  |  | completed | 1
NC 2018 | SHS | Region VI | Capiz | 310815 | Mianay NHS | SIGMA | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 10175901.76 |  |  | completed | 1
NC 2018 | K10 | Region VI | Capiz | 500429 | Aglalana Integrated School | DUMARAO | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 19116509.01 |  |  | completed | 1
NC 2018 | K10 | Region VI | Capiz | 115564 | Maayon ES | MA-AYON | 1 | 1 | 10 | 2STY10CL | Batch 3 | 26229600.7 |  |  | completed | 1
NC 2018 | K10 | Region VI | Capiz | 115575 | Tapulang ES | MA-AYON | 1 | 1 | 6 | 2STY6CL | Batch 3 | 17589731.38 |  |  | completed | 1
NC 2018 | K10 | Region VI | Capiz | 115616 | Bago Chiquito Elementary School | PANAY | 1 | 1 | 6 | 2STY6CL | Batch 3 | 18185320.64 |  |  | completed | 1
NC 2018 | K10 | Region VI | Capiz | 115647 | Cabangahan PS (panitan) | PANITAN | 1 | 1 | 6 | 2STY6CL | Batch 3 | 17629731.38 |  |  | completed | 1
NC 2018 | K10 | Region VI | Capiz | 115695 | Victoria C. Dais ES | PONTEVEDRA | 1 | 1 | 10 | 2STY10CL | Batch 3 | 27400576.74 |  |  | completed | 1
NC 2018 | K10 | Region VI | Capiz | 115698 | Hipona ES | PONTEVEDRA | 1 | 1 | 6 | 2STY6CL | Batch 6 Realignment | 17389731.38 |  |  | completed | 1
NC 2018 | K10 | Region VI | Capiz | 115704 | Rizal ES | PONTEVEDRA | 1 | 1 | 8 | 2STY8CL | Batch 3 | 21929666.04 |  |  | completed | 1
NC 2018 | TVL | Region VI | Capiz | 302391 | Capiz National High School | ROXAS CITY (Capital) | 1 | 1 | 4 | 2STY4CL lab (2sci lab & 2ICT lab) | Batch 3 | 22272059.36 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Capiz | 302392 | Casanayan National High School | PILAR | 1 | 1 | 4 | 2STY4CL lab (2sci lab & 2ICT lab) | Batch 3 | 22272059.36 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Capiz | 302404 | Florentina B. Degala NHS | MA-AYON | 1 | 1 | 10 | 2STY10CL | Batch 3 | 25999600.7 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Capiz | 115414 | Bito-on Elementary School | CUARTERO | 2 | 1 | 6 | 2STY6CL | Batch 5 | 12609335 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Capiz | 115454 | Dumalag CS | DUMALAG | 2 | 1 | 14 | 3STY9CL, 2STY4CL & Improvement/Completion of Multi Purpose Gym | Batch 5 | 45000000 |  |  | completed | 1
NC 2018 | TVL | Region VI | Escalante City | 302595 | Buenavista NHS | CITY OF ESCALANTE | 1 | 1 | 4 | 2STY WORKSHOP BLDG (2STY4CL 2017 SCI LAB) | BATCH 1 | 9955930.91 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Escalante City | 302615 | Dian-ay NHS | CITY OF ESCALANTE | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 12986784.82 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Escalante City | 302615 | Dian-ay NHS | CITY OF ESCALANTE | 1 |  | 6 | 2STY6CL | BATCH 1 | 12986784.82 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Escalante City | 302615 | Dian-ay NHS | CITY OF ESCALANTE | 1 |  | 4 | 2STY WORKSHOP BLDG (2STY4CL 2017 SCI LAB) | BATCH 1 | 9955930.91 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Escalante City | 302625 | Escalante NHS | CITY OF ESCALANTE | 1 | 1 | 4 | 2STY WORKSHOP BLDG (2STY4CL 2017 SCI LAB) | BATCH 1 | 9955930.91 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Escalante City | 302626 | Old Poblacion NHS | CITY OF ESCALANTE | 1 | 1 | 4 | 2STY WORKSHOP BLDG (2STY4CL 2017 SCI LAB) | BATCH 1 | 9955930.91 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Escalante City | 302627 | Tamlang NHS | CITY OF ESCALANTE | 1 | 1 | 4 | 2STY WORKSHOP BLDG (2STY4CL 2017 SCI LAB) | BATCH 1 | 9955930.91 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Escalante City | 302660 | Mabini NHS | CITY OF ESCALANTE | 1 | 1 | 4 | 2STY WORKSHOP BLDG (2STY4CL 2017 SCI LAB) | BATCH 1 | 9955930.91 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302425 | Alegria NHS | SIBUNAG | 0 | 1 | 2 | Const of 2STY2CL ICT lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302425 | Alegria NHS | SIBUNAG | 0 |  | 2 | Const of 2STY2CL Science lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302425 | Alegria NHS | SIBUNAG | 0 |  | 2 | Const of 2STY2CL Techvoc regular workshop G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302426 | Buenavista National High School | BUENAVISTA | 0 | 1 | 2 | Const of 2STY2CL Science lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302426 | Buenavista National High School | BUENAVISTA | 0 |  | 2 | Const of 2STY2CL Science lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302426 | Buenavista National High School | BUENAVISTA | 0 |  | 2 | Const of 2STY2CL Techvoc regular workshop G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302426 | Buenavista National High School | BUENAVISTA | 0 |  | 2 | Const of 2STY2CL Techvoc regular workshop G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302427 | Agsanayan National High School | BUENAVISTA | 0 | 1 | 2 | Const of 2STY2CL Science lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302427 | Agsanayan National High School | BUENAVISTA | 0 |  | 2 | Const of 2STY2CL ICT lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302429 | Desiderio C. Gange NHS | SIBUNAG | 0 | 1 | 2 | Const of 2STY2CL ICT lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302429 | Desiderio C. Gange NHS | SIBUNAG | 0 |  | 2 | Const of 2STY2CL Science lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302429 | Desiderio C. Gange NHS | SIBUNAG | 0 |  | 2 | Const of 2STY2CL Techvoc regular workshop G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302429 | Desiderio C. Gange NHS | SIBUNAG | 0 |  | 2 | Const of 2STY2CL Techvoc regular workshop G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302430 | East Valencia National High School | BUENAVISTA | 0 | 1 | 2 | Const of 2STY2CL ICT lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302430 | East Valencia National High School | BUENAVISTA | 0 |  | 2 | Const of 2STY2CL Science lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302431 | Getulio NHS | BUENAVISTA | 0 | 1 | 2 | Const of 2STY2CL ICT lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302431 | Getulio NHS | BUENAVISTA | 0 |  | 2 | Const of 2STY2CL Science lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302432 | Jordan NHS | JORDAN (Capital) | 0 | 1 | 2 | Const of 2STY2CL ICT lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302432 | Jordan NHS | JORDAN (Capital) | 0 |  | 2 | Const of 2STY2CL Science lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302432 | Jordan NHS | JORDAN (Capital) | 0 |  | 2 | Const of 2STY2CL Techvoc regular workshop G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302432 | Jordan NHS | JORDAN (Capital) | 0 |  | 2 | Const of 2STY2CL Techvoc regular workshop G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302433 | Simeon J. Jabasa National High School | NUEVA VALENCIA | 0 | 1 | 2 | Const of 2STY2CL ICT lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302433 | Simeon J. Jabasa National High School | NUEVA VALENCIA | 0 |  | 2 | Const of 2STY2CL Science lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302435 | Calaya National High School | NUEVA VALENCIA | 0 | 1 | 1 | Const of 2STY2CL ICT lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302437 | Dr. Catalino Gallego Nava Memorial High School | SAN LORENZO | 0 | 1 | 2 | Const of 2STY2CL ICT lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302437 | Dr. Catalino Gallego Nava Memorial High School | SAN LORENZO | 0 |  | 2 | Const of 2STY2CL Science lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302437 | Dr. Catalino Gallego Nava Memorial High School | SAN LORENZO | 0 |  | 2 | Const of 2STY2CL Techvoc regular workshop G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302438 | Trinidad V. Canja-Sta. Teresa NHS | JORDAN (Capital) | 0 | 1 | 2 | Const of 2STY2CL ICT lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302438 | Trinidad V. Canja-Sta. Teresa NHS | JORDAN (Capital) | 0 |  | 2 | Const of 2STY2CL Science lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302438 | Trinidad V. Canja-Sta. Teresa NHS | JORDAN (Capital) | 0 |  | 2 | Const of 2STY2CL Techvoc regular workshop G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302438 | Trinidad V. Canja-Sta. Teresa NHS | JORDAN (Capital) | 0 |  | 2 | Const of 2STY2CL Techvoc regular workshop G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302438 | Trinidad V. Canja-Sta. Teresa NHS | JORDAN (Capital) | 0 |  | 2 | Const of 2STY2CL Techvoc regular workshop G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302439 | Remedios E. Vilches-San Lorenzo National High School | SAN LORENZO | 0 | 1 | 2 | Const of 2STY2CL ICT lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 302439 | Remedios E. Vilches-San Lorenzo National High School | SAN LORENZO | 0 |  | 2 | Const of 2STY2CL Science lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 310901 | Ayangan National High School | SIBUNAG | 0 | 1 | 2 | Const of 2STY2CL ICT lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 310901 | Ayangan National High School | SIBUNAG | 0 |  | 2 | Const of 2STY2CL Science lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 310902 | Supang National High School | BUENAVISTA | 0 | 1 | 2 | Const of 2STY2CL ICT lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 310902 | Supang National High School | BUENAVISTA | 0 |  | 2 | Const of 2STY2CL Science lab G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Guimaras | 310902 | Supang National High School | BUENAVISTA | 0 |  | 2 | Const of 2STY2CL Techvoc regular workshop G.I. roof SB | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo | 116473 | Guihaman-Buntatala ES | LEGANES | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 13837810.18 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo | 116477 | Leganes CES | LEGANES | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 13248125.14 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo | 116806 | Gen.Martin T. Delgado ES | SANTA BARBARA | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 13588125.14 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Iloilo | 302516 | Leonora S. Salapantan NHS | SAN MIGUEL | 2 | 1 | 12 | 3STY12CL | BATCH 1 | 31778879.72 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Iloilo | 302516 | Leonora S. Salapantan NHS | SAN MIGUEL | 2 |  | 6 | 2STY6CL | BATCH 1 | 13548125.14 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Iloilo | 302520 | Leganes National High School | LEGANES | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 13537976.43 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Iloilo | 302550 | Pavia National High School | PAVIA | 2 | 1 | 15 | 3STY15CL | BATCH 1 | 36048912.24 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Iloilo | 302573 | Sta. Barbara NCHS | SANTA BARBARA | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 19513647.05 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302447 | Ambrosio Maido MNHS | CABATUAN | 3 | 1 | 1 | 1 regular workshop | BATCH 1 | 2538254.17 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302514 | Jose Facultad Memorial National High School | POTOTAN | 3 | 1 | 1 | 1 regular workshop | BATCH 1 | 2538254.17 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302517 | Lambunao National High School | LAMBUNAO | 3 | 1 | 1 | 1 regular workshop | BATCH 1 | 2538254.17 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 311025 | Jovita Alfaras Rivera National High School | BINGAWAN | 3 | 1 | 1 | 1 regular workshop | BATCH 1 | 2538254.17 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302493 | Carlos Lopez NHS | SAN DIONISIO | 5 | 1 | 1 | 1 unit regular workshop bldg. | BATCH 1 | 3361124.5 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302500 | Estancia National High School | ESTANCIA | 5 | 1 | 1 | 1 unit regular workshop bldg. | BATCH 1 | 3361124.5 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302500 | Estancia National High School | ESTANCIA | 5 |  | 1 | 1 unit regular workshop bldg. | BATCH 1 | 3361124.5 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 311001 | Valerio P. Palmares NHS | BATAD | 5 | 1 | 1 | 1 unit regular workshop bldg. | BATCH 1 | 3395864.03 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo | 116360 | Guimbal CES | GUIMBAL | 1 | 1 | 12 | 2STY12CL | Batch 3 | 25910233.89 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo | 116740 | San Joaquin Central Elementary School | SAN JOAQUIN | 1 | 1 | 8 | 2STY8CL | Batch 3 | 22030875.6 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302495 | Don Felix Serra NHS | SAN JOAQUIN | 1 | 1 | 16 | 4STY ICT & Scie Lab | Batch 3 | 42347993.26 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302506 | Guimbal NHS | GUIMBAL | 1 | 1 | 16 | 4STY ICT & Scie Lab | Batch 3 | 42407993.26 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302507 | Igbaras NHS | IGBARAS | 1 | 1 | 16 | 4STY ICT & Scie Lab | Batch 3 | 42552396.72 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302578 | Tigbauan NHS | TIGBAUAN | 1 | 1 | 16 | 4STY ICT & Scie Lab | Batch 3 | 43218056.45 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo | 115945 | Alimodian CES | ALIMODIAN | 2 | 1 | 6 | 2STY6CL | Batch 3 | 16745065.18 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo | 116861 | Sigangao ES | ZARRAGA | 2 | 1 | 6 | 2STY6CL | Batch 3 | 16420290.29 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302550 | Pavia National High School | PAVIA | 2 | 1 | 4 | ICT lab (2STY4 unit) | Batch 3 | 23005392.01 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo | 116156 | Aglibacao ES | CALINOG | 3 | 1 | 4 | 2STY4CL | Batch 3 | 9765082 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo | 116166 | Ipil ES | CALINOG | 3 | 1 | 4 | 2STY4CL | Batch 3 | 9765082 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo | 116193 | Maspasan Elementary School | CALINOG | 3 | 1 | 4 | 2STY4CL | Batch 3 | 9765082 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo | 116428 | Don Eugenio Ladrido MES | LAMBUNAO | 3 | 1 | 6 | 2STY6CL | Batch 3 | 12223716 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302441 | Abangay National High School | JANIUAY | 3 | 1 | 2 | 2sty- 2 ict lab | Batch 3 | 9765082 |  |  | REVERTED | 0 | [10 empty] | Terminated and Reverted
NC 2018 | TVL | Region VI | Iloilo | 302441 | Abangay National High School | JANIUAY | 3 | 1 | 2 | 2sty- 2 science lab | Batch 3 | 9765082 |  |  | completed | 1
NC 2018 | SHS | Region VI | Iloilo | 302442 | Acao NHS | CABATUAN | 3 | 1 | 4 | 2STY4CL | Batch 3 | 9765082 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Iloilo | 302444 | Alcarde Gustilo Mem. National High School | CALINOG | 3 | 1 | 6 | 2STY6CL | Batch 3 | 12223716 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302452 | Badiangan NHS | BADIANGAN | 3 | 1 | 4 | 4sty- 2 ict lab & 2 science lab | Batch 3 | 16260988.32 |  |  | completed | 1
NC 2018 | SHS | Region VI | Iloilo | 302453 | Badlan NHS | CALINOG | 3 | 1 | 4 | 2STY4CL | Batch 3 | 9765082 |  |  | completed | 1
NC 2018 | SHS | Region VI | Iloilo | 302471 | Burak NHS | MAASIN | 3 | 1 | 4 | 2STY4CL | Batch 3 | 9765082 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302473 | Cabatuan NCHS | CABATUAN | 3 | 1 | 4 | 4sty- 4 regular workshop | Batch 3 | 16399868.45 |  |  | completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302473 | Cabatuan NCHS | CABATUAN | 3 | 1 | 4 | 4sty- 2 ict lab & 2 science lab | Batch 3 | 16405221.14 |  |  | completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302477 | Calinog NCHS | CALINOG | 3 | 1 | 12 | 4STY- 2 ict lab & 2 science lab & 8 CL | Batch 3 | 33506916 |  |  | completed | 1
NC 2018 | SHS | Region VI | Iloilo | 302481 | CARVASANA NHS | CALINOG | 3 | 1 | 4 | 2STY4CL | Batch 3 | 9765082 |  |  | completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302512 | Janiuay NCHS | JANIUAY | 3 | 1 | 4 | 4sty- 2 ict lab & 2 science lab | Batch 3 | 16260989.33 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Iloilo | 302512 | Janiuay NCHS | JANIUAY | 3 |  | 4 | 2STY4CL | Batch 3 | 9765082 |  |  | completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302524 | Maasin National Comprehensive High School | MAASIN | 3 | 1 | 4 | 2STY- 2ICT lab & 2Scie lab | Batch 3 | 17115340 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302526 | Malitbog National High School | CALINOG | 3 | 1 | 2 | 2sty- 1 ict lab & 1 science lab | Batch 3 | 9780731.96 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302533 | Mina NHS | MINA | 3 | 1 | 2 | 2sty- 2 ict lab | Batch 3 | 9691082.81 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Iloilo | 302546 | PALANGUIA NATIONAL HIGH SCHOOL | POTOTAN | 3 | 1 | 6 | 2STY6CL | Batch 3 | 12223716 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302559 | Leon Mediana NHS | MAASIN | 3 | 1 | 2 | 2sty- 1 ict lab & 1 science lab | Batch 3 | 9780731.96 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Iloilo | 302560 | Quipot National High School | JANIUAY | 3 | 1 | 4 | 2STY4CL | Batch 3 | 9765082 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Iloilo | 311003 | Jayobo NHS | LAMBUNAO | 3 | 1 | 12 | 3STY12CL | Batch 3 | 33506916 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Iloilo | 311018 | Fernandez Perez MNHS | CALINOG | 3 | 1 | 4 | 2STY4CL | Batch 3 | 9765082 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 311020 | Caninguan NHS | LAMBUNAO | 3 | 1 | 4 | 4sty- 2 ict lab & 2 science lab | Batch 3 | 16260989.33 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 311025 | Jovita Alfaras Rivera National High School | BINGAWAN | 3 | 1 | 2 | 2sty- 1 ict lab & 1 science lab | Batch 3 | 9780731.96 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo | 116320 | Cali ES | DUMANGAS | 4 | 1 | 8 | 2STY8CL | Batch 3 | 17115341 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo | 116322 | Dacutan ES | DUMANGAS | 4 | 1 | 8 | 2STY8CL | Batch 3 | 17115341 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo | 116326 | Maquina ES | DUMANGAS | 4 | 1 | 8 | 2STY8CL | Batch 3 | 17115341 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo | 116335 | Bolilao Elementary School | DUMANGAS | 4 | 1 | 8 | 2STY8CL | Batch 3 | 17115341 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo | 116336 | Calao ES | DUMANGAS | 4 | 1 | 8 | 2STY8CL | Batch 3 | 17115341 |  |  | REVERTED | 0 | [10 empty] | Terminated and Reverted
NC 2018 | K10 | Region VI | Iloilo | 116344 | Rosario ES | DUMANGAS | 4 | 1 | 8 | 2STY8CL | Batch 3 | 17115341 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302455 | Banate NHS | BANATE | 4 | 1 | 4 | 4sty- 4 regular workshop | Batch 3 | 17559934 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302455 | Banate NHS | BANATE | 4 |  | 4 | 4STY- 2 ICT lab & 2 Scie lab | Batch 3 | 17559934 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302489 | De La Paz National High School | BANATE | 4 | 1 | 4 | 4STY- 2 ICT lab & 2 Scie lab | Batch 3 | 17559934 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302527 | Malusgod NHS | DUEÑAS | 4 | 1 | 2 | 2sty- 1 ict lab & 1 science lab | Batch 3 | 9780731.96 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302527 | Malusgod NHS | DUEÑAS | 4 | 1 | 2 | 2sty- 2 regular workshop | Batch 3 | 9576312.11 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo | 116488 | Concepcion Juanillo MES | LEMERY | 5 | 1 | 6 | 2STY6CL | Batch 3 | 14803687.17 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo | 116689 | Odiongan ES | SAN DIONISIO | 5 | 1 | 4 | 2STY4CL | Batch 3 | 11223023.7 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo | 116692 | Santikan ES | SAN DIONISIO | 5 | 1 | 8 | 2STY8CL | Batch 3 | 19435036.67 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo | 116780 | Juaneza ES | SARA | 5 | 1 | 6 | 2STY6CL | Batch 3 | 14571991.15 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo | 116780 | Juaneza ES | SARA | 5 |  | 4 | 2STY4CL | Batch 3 | 11141474.39 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo | 116785 | Purificacion S. Gustilo MES | SARA | 5 | 1 | 6 | 2STY6CL | Batch 3 | 14602412.03 |  |  | completed | 1
NC 2018 | K10 | Region VI | Iloilo | 116788 | Sara CES | SARA | 5 | 1 | 6 | 2STY6CL | Batch 3 | 14622559.82 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302454 | Balasan NHS | BALASAN | 5 | 1 | 4 | 1 unit 2sty combination of 2 Scie lab & 2 ICT lab | Batch 3 | 23028000 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302458 | Barotac Viejo National High School | BAROTAC VIEJO | 5 | 1 | 2 | 1 unit 2sty 2 ICT lab | Batch 3 | 10312610 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302458 | Barotac Viejo National High School | BAROTAC VIEJO | 5 |  | 2 | 1 unit 2sty 2 Science lab | Batch 3 | 10214000 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302460 | Batad National High School | BATAD | 5 | 1 | 4 | 1 unit 2sty 4 Regular workshop | Batch 3 | 24676000 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302460 | Batad National High School | BATAD | 5 |  | 4 | 1 unit 2sty combination of 2 Scie lab & 2 ICT lab | Batch 3 | 23688000 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302461 | Bay-ang NHS | AJUY | 5 | 1 | 2 | 1 unit 2sty 2 ICT lab | Batch 3 | 12463361.26 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302484 | Roberto H. Tirol High School | CONCEPCION | 5 | 1 | 4 | 1 unit 2sty combination of 2 Scie lab & 2 ICT lab | Batch 3 | 23788500 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302493 | Carlos Lopez NHS | SAN DIONISIO | 5 | 1 | 4 | 1 unit 2sty combination of 2 Scie lab & 2 ICT lab | Batch 3 | 22741140 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302493 | Carlos Lopez NHS | SAN DIONISIO | 5 | 1 | 2 | 1 unit 2sty 2 Regular Workshop | Batch 3 | 10390181.11 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Iloilo | 302494 | Don Casimero Andrada NHS | CARLES | 5 | 1 | 4 | 2STY4CL | Batch 3 | 11514360.96 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302494 | Don Casimero Andrada NHS | CARLES | 5 | 1 | 2 | 1 unit 2sty 2 Regular Workshop | Batch 3 | 10974964.89 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302500 | Estancia National High School | ESTANCIA | 5 | 1 | 2 | 1 unit 2sty 2 Science lab | Batch 3 | 10214000 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302500 | Estancia National High School | ESTANCIA | 5 | 1 | 2 | Const. of 1 unit 2sty 2 ICT lab | Batch 3 | 10279256.87 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302502 | GEN. LUNA NHS | BAROTAC VIEJO | 5 | 1 | 2 | 1 unit 2sty 2 ICT lab | Batch 3 | 12784564.16 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Iloilo | 302521 | Lemery National High School | LEMERY | 5 | 1 | 8 | 2STY8CL | Batch 3 | 24432117.68 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302532 | Milan NHS | LEMERY | 5 | 1 | 2 | 1 unit 2sty 2 Science lab | Batch 3 | 12365543.86 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302532 | Milan NHS | LEMERY | 5 |  | 2 | 1 unit 2sty 2 ICT lab | Batch 3 | 12761493.36 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Iloilo | 302541 | Nicomedes R. Tubar Sr. NHS | SAN DIONISIO | 5 | 1 | 8 | 2STY8CL | Batch 3 | 21028351.57 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Iloilo | 302570 | Sara NHS | SARA | 5 | 1 | 2 | 1 unit 2sty 2 ICT lab | Batch 3 | 12797653.6 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo City | 117595 | Buntatala Tagbac Elem. School | ILOILO CITY (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 9400000 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo City | 117597 | Jaro ES I | ILOILO CITY (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 1 | 27657774.69 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo City | 117598 | Jaro ES II | ILOILO CITY (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 9400000 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo City | 117601 | M.V. Hechanova MES | ILOILO CITY (Capital) | 0 | 1 | 10 | 2STY10CL | BATCH 1 | 22810000 |  |  | REVERTED | 0 | [10 empty] | REVERTED
NC 2018 | K10 | Region VI | Iloilo City | 117602 | Sambag ES | ILOILO CITY (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 9400000 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo City | 117610 | Ticud ES | ILOILO CITY (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 9400000 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo City | 117615 | Hibao-an ES | ILOILO CITY (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 9400000 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Iloilo City | 117621 | I. Arroyo ES | ILOILO CITY (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 9450000 |  |  | COMPLETED | 1
NC 2018 | K10 | Region VI | Iloilo City | 117624 | San Juan ES | ILOILO CITY (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 9795450.92 |  |  | COMPLETED | 1
NC 2018 | SHS | Region VI | Iloilo City | 302738 | Iloilo City NHS | ILOILO CITY (Capital) | 0 | 1 | 8 | 4STY8CL | BATCH 1 | 19250000 |  |  | COMPLETED | 1
NC 2018 | SHS | Region VI | Iloilo City | 302746 | R. G. Hechanova Memorial NHS | ILOILO CITY (Capital) | 0 | 1 | 8 | 4STY8CL | BATCH 1 | 19400000 |  |  | COMPLETED | 1
NC 2018 | SHS | Region VI | Iloilo City | 302738 | Iloilo City NHS | ILOILO CITY (Capital) | 0 | 1 | 8 | 4STY8CL | Batch 3 | 19701875 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302785 | Bantayan National High School | CITY OF KABANKALAN | 6 | 1 | 3 | 1unit- 3 sty regular workshop | BATCH 1 | 13954987.47 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302785 | Bantayan National High School | CITY OF KABANKALAN | 6 |  | 2 | 1unit-2 sty regular workshop | BATCH 1 | 9637002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302785 | Bantayan National High School | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9497002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302785 | Bantayan National High School | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9497002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302786 | Binicuil NHS | CITY OF KABANKALAN | 6 |  | 3 | 1unit- 3sty Regular Workshop | BATCH 1 | 13644987.47 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302786 | Binicuil NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty Regular Workshop | BATCH 1 | 9327002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302786 | Binicuil NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9727002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302786 | Binicuil NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9727002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302787 | CAROL-AN NHS | CITY OF KABANKALAN | 6 | 1 | 1 | 1unit- Unique Workshop | BATCH 1 | 2838745.92 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302787 | CAROL-AN NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9402002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302787 | CAROL-AN NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9602002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302792 | Camansi National High School | CITY OF KABANKALAN | 6 | 1 | 2 | 2STY Regular Workshop | BATCH 1 | 9727002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302792 | Camansi National High School | CITY OF KABANKALAN | 6 |  | 2 | 2STY Regular Workshop | BATCH 1 | 9727002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302792 | Camansi National High School | CITY OF KABANKALAN | 6 |  | 2 | 2STY Regular Workshop | BATCH 1 | 9457002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302792 | Camansi National High School | CITY OF KABANKALAN | 6 |  | 2 | 2STY Regular Workshop | BATCH 1 | 9457002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6 | 1 | 3 | 1unit- 3sty Regular Workshop | BATCH 1 | 13829987.47 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9512002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9512002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty Regular Workshop | BATCH 1 | 9437002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty Regular Workshop | BATCH 1 | 9437002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302796 | Salong NHS | CITY OF KABANKALAN | 6 | 1 | 3 | 1unit- 3sty Regular Workshop | BATCH 1 | 13674987.47 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302796 | Salong NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty Regular Workshop | BATCH 1 | 9357002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302796 | Salong NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9757002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302796 | Salong NHS | CITY OF KABANKALAN | 6 |  | 4 | 1unit- 2sty ICT lab | BATCH 1 | 9757002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302797 | Tabugon NHS | CITY OF KABANKALAN | 6 | 1 | 1 | 1unit- Unique Workshop | BATCH 1 | 2758745.92 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302797 | Tabugon NHS | CITY OF KABANKALAN | 6 |  | 3 | 1unit- 3sty Regular Workshop | BATCH 1 | 13689987.47 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302797 | Tabugon NHS | CITY OF KABANKALAN | 6 |  | 3 | 1unit- 3sty Regular Workshop | BATCH 1 | 13689987.47 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302797 | Tabugon NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9472002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302797 | Tabugon NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9472002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302800 | Tampalon NHS | CITY OF KABANKALAN | 6 | 1 | 3 | 1unit- 3sty Regular Workshop | BATCH 1 | 13684987.47 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302800 | Tampalon NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9467002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302800 | Tampalon NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9467002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302801 | Tapi National High School | CITY OF KABANKALAN | 6 | 1 | 3 | 1unit- 3sty Regular Workshop | BATCH 1 | 13684987.47 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302801 | Tapi National High School | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty Regular Workshop | BATCH 1 | 9367002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302801 | Tapi National High School | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9467002.9 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Kabankalan City | 302801 | Tapi National High School | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9467002.9 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Kabankalan City | 312101 | TAN-AWAN NATIONAL HIGH SCHOOL | CITY OF KABANKALAN | 6 | 1 | 1 | 1unit- Regular Workshop | BATCH 1 | 2843745.92 |  |  | Completed | 1 | [10 empty] | under NEG OCC Division
NC 2018 | TVL | Region VI | Kabankalan City | 312101 | TAN-AWAN NATIONAL HIGH SCHOOL | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9557002.9 |  |  | Completed | 1 | [10 empty] | under NEG OCC Division
NC 2018 | TVL | Region VI | Kabankalan City | 312101 | TAN-AWAN NATIONAL HIGH SCHOOL | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9557002.9 |  |  | Completed | 1 | [10 empty] | under NEG OCC Division
NC 2018 | K10 | Region VI | La Carlota City | 117647 | La Carlota South ES II | LA CARLOTA CITY | 4 | 1 | 4 | 2STY4CL | Batch 3 | 11386751.67 |  |  | Completed | 1 | [10 empty] | under NEG OCC Division
NC 2018 | SHS | Region VI | La Carlota City | 302754 | San Miguel NHS | LA CARLOTA CITY | 4 | 1 | 6 | 2STY6CL | Batch 3 | 17640895.68 |  |  | Completed | 1 | [10 empty] | under NEG OCC Division
NC 2018 | TVL | Region VI | Passi City | 302807 | Salngan National High School | CITY OF PASSI | 4 | 1 | 2 | 1sty- 1 science lab | BATCH 1 | 2637254.17 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Passi City | 302807 | Salngan National High School | CITY OF PASSI | 4 |  | 2 | 1sty- 1 science lab | BATCH 1 | 2637254.17 |  |  | COMPLETED | 1
NC 2018 | K10 | Region VI | Passi City | 117899 | Bitaogan ES | CITY OF PASSI | 4 | 1 | 6 | 2STY6CL | Batch 3 | 12223715 |  |  | COMPLETED | 1
NC 2018 | K10 | Region VI | Passi City | 117909 | Quinagaringan ES | CITY OF PASSI | 4 | 1 | 4 | 2STY4CL | Batch 3 | 9691082.81 |  |  | COMPLETED | 1
NC 2018 | K10 | Region VI | Passi City | 117912 | Aglalana ES | CITY OF PASSI | 4 | 1 | 8 | 2STY8CL | Batch 3 | 15453704 |  |  | COMPLETED | 1
NC 2018 | K10 | Region VI | Passi City | 117913 | Agtabo Elementary School | CITY OF PASSI | 4 | 1 | 4 | 2STY4CL | Batch 3 | 9691082.81 |  |  | COMPLETED | 1
NC 2018 | K10 | Region VI | Passi City | 117917 | BATU ELEMENTARY SCHOOL | CITY OF PASSI | 4 | 1 | 4 | 2STY4CL | Batch 3 | 9691082.81 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Roxas City | 302759 | Dumolog NHS | ROXAS CITY (Capital) | 1 | 1 | 2 | 1STY2CL lab (2 regular workshop) | BATCH 1 | 8135292.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Roxas City | 302760 | Milibili NHS | ROXAS CITY (Capital) | 1 | 1 | 2 | 1STY2CL (2 science lab) | BATCH 1 | 8185292.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Roxas City | 302760 | Milibili NHS | ROXAS CITY (Capital) | 1 |  | 2 | 1STY2CL (2 ICT lab) | BATCH 1 | 8135292.76 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Roxas City | 302761 | Tanque NHS | ROXAS CITY (Capital) | 1 | 1 | 2 | 1STY2CL lab (2 regular workshop) | BATCH 1 | 8238390.45 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Roxas City | 302761 | Tanque NHS | ROXAS CITY (Capital) | 1 |  | 2 | 1STY2CL (2 science lab) | BATCH 1 | 8143390.45 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Roxas City | 302761 | Tanque NHS | ROXAS CITY (Capital) | 1 |  | 2 | 1STY2CL (2 ICT lab) | BATCH 1 | 8143390.45 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Roxas City | 311702 | Roxas City School for Philippine Craftsmen | ROXAS CITY (Capital) | 1 | 1 | 1 | 1STY1CL (1 regular workshop) | BATCH 1 | 4546135.32 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Roxas City | 311702 | Roxas City School for Philippine Craftsmen | ROXAS CITY (Capital) | 1 |  | 2 | 1STY2CL (2 science lab) | BATCH 1 | 8146620.34 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Roxas City | 311702 | Roxas City School for Philippine Craftsmen | ROXAS CITY (Capital) | 1 |  | 2 | 1STY2CL (2 ICT lab) | BATCH 1 | 8146620.34 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Roxas City | 311704 | Don Ynocencio A. Del Rosario National High School formerly Tanque NHS-Dayao Extension | ROXAS CITY (Capital) | 1 | 1 | 2 | 1STY2CL (1 regular workshop) | BATCH 1 | 8327195.07 |  |  | Completed | 1
NC 2018 | TVL | Region VI | Roxas City | 302757 | Cong. Ramon A. Arnaldo HS | ROXAS CITY (Capital) | 1 | 1 | 4 | 2STY4CL lab (2 sci lab & 2 ict lab) | Batch 3 | 22534452.68 |  |  | Completed | 1
NC 2018 | SHS | Region VI | Sagay City | 302765 | Eusebio Lopez Memorial Integrated School | SAGAY CITY | 2 | 1 | 8 | 4STY WORKSHOP BLDG (4STY8CL Regular workshop) | BATCH 1 | 21792667.24 |  |  | COMPLETED | 1 | [10 empty] | not yet submitted the Certificate of Occupancy and Completion
NC 2018 | TVL | Region VI | Sagay City | 302767 | Sagay NHS | SAGAY CITY | 2 |  | 4 | 2STY WORKSHOP BLDG (2STY4CL science lab) | BATCH 1 | 12337629.29 |  |  | COMPLETED | 1
NC 2018 | TVL | Region VI | Sagay City | 302767 | Sagay NHS | SAGAY CITY | 2 |  | 4 | 2STY WORKSHOP BLDG (2STY4CL ICT lab) | BATCH 1 | 12447629.29 |  |  | COMPLETED | 1
NC 2018 | SHS | Region VI | Sagay City | 311802 | Sagay National High School - Rizal Extension | SAGAY CITY | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 10245841.94 |  |  | COMPLETED | 1
NC 2018 | SHS | Region VI | Sagay City | 343922 | Sagay City SHS | SAGAY CITY | 2 | 1 | 20 | 4STY20CL | BATCH 1 | 46289000.71 |  |  | COMPLETED | 1 | [10 empty] | COMPLETED AS PER DPWH POW BUT UNPAINTED
NC 2018 | SHS | Region VI | Sagay City | 343922 | Sagay City SHS | SAGAY CITY | 2 |  | 6 | 2STY6CL | BATCH 1 | 13321184.82 |  |  | COMPLETED | 1
NC 2018 | K10 | Region VI | Sagay City | 117693 | Bulanon Elementary School | SAGAY CITY | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12027869.01 |  |  | COMPLETED | 1 | [10 empty] | not yet submitted the Certificate of Occupancy and Completion
NC 2018 | K10 | Region VI | Sagay City | 117695 | Buenaventura Rodriguez Elementary School | SAGAY CITY | 2 | 1 | 8 | 2STY8CL | Batch 3 | 23233053.68 |  |  | COMPLETED | 1
NC 2018 | K10 | Region VI | Sagay City | 117707 | Talusan Elementary School | SAGAY CITY | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12027869.01 |  |  | COMPLETED | 1
NC 2018 | K10 | Region VI | Sagay City | 117709 | Vito Elementary School | SAGAY CITY | 2 | 1 | 6 | 2STY6CL | Batch 3 | 16341557.36 |  |  | COMPLETED | 1
NC 2018 | K10 | Region VI | Sagay City | 117716 | Gil Lopez Elementary School | SAGAY CITY | 2 | 1 | 8 | 2STY8CL | Batch 3 | 23033053.68 |  |  | COMPLETED | 1
NC 2018 | K10 | Region VI | Sagay City | 117721 | Maria Lopez Elementary School | SAGAY CITY | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12027869.01 |  |  | COMPLETED | 1
NC 2018 | SHS | Region VI | Sagay City | 302765 | Eusebio Lopez Memorial Integrated School | SAGAY CITY | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12312331.69 |  |  | COMPLETED | 1 | [10 empty] | not yet submitted the Certificate of Occupancy and Completion
NC 2018 | K10 | Region VI | San Carlos City | 117753 | Ramon Magsaysay ES | SAN CARLOS CITY | 1 | 1 | 8 | 2STY8CL | Batch 3 | 23133053.68 |  |  | Completed | 1
NC 2018 | K10 | Region VI | San Carlos City | 117785 | Andres Bonifacio ES | SAN CARLOS CITY | 1 | 1 | 4 | 2STY4CL | Batch 3 | 12277869.01 |  |  | Completed | 1
NC 2018 | K10 | Region VI | Silay City | 117801 | Don Eustaquio Hofilena MS | SILAY CITY | 3 | 1 | 6 | 2STY6CL | Batch 3 | 14820210.02 |  |  | COMPLETED | 1
NC 2018 | K10 | Region VI | Silay City | 117807 | Gov. Emilio Gaston Memorial ES | SILAY CITY | 3 | 1 | 6 | 2STY6CL | Batch 3 | 14720210.02 |  |  | COMPLETED | 1
NC 2018 | K10 | Region VI | Silay City | 117807 | Gov. Emilio Gaston ES | SILAY CITY | 3 |  | 8 | 2STY8CL | Batch 3 | 22418487.82 |  |  | COMPLETED | 1
NC 2019 | SHS | Region VI | Antique | 310707 | Gov. Evelio B. Javier MNHS | SAN REMIGIO | 0 | 1 | 4 | 2UNITS 1STY2CL W/ TOILET |  | 10627207.2136 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VI | Antique | 114943 | Igpalge ES | ANINI-Y | 0 | 1 | 9 | 3UNITS 1STY3CL |  | 11624773.44 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VI | Antique | 178517 | Ilaures Elementary School | BUGASONG | 0 | 1 | 3 | 1STY3CL W/ TOILET |  | 7293455.8492 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VI | Bago City | 117511 | Alianza Elementary School | BAGO CITY | 4 | 1 | 2 | 1STY2CL |  | 4950531.9261 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VI | Capiz | 115611 | Agbalo ES | PANAY | 1 | 1 | 4 | 2STY4CL |  | 13553595.2093 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VI | Capiz | 115642 | Agloway PS | PANITAN | 1 | 1 | 8 | 2STY8CL |  | 21773965.2051 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VI | Capiz | 115642 | Agloway PS | PANITAN | 1 |  | 6 | 2STY6CL |  | 17493355.7085 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VI | Capiz | 115640 | Antonio Belo Memorial ES | PANITAN | 1 | 1 | 4 | 2STY4CL |  | 13348083.7118 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VI | Capiz | 115761 | Matangcong PS | SIGMA | 2 | 1 | 4 | 2STY4CL |  | 13325737.676 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VI | Capiz | 115745 | Sapian Elementary School | SAPI-AN | 2 | 1 | 15 | 3STY15CL |  | 42004466.9341 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VI | Capiz | 115819 | Tapaz CES | TAPAZ | 2 | 1 | 4 | 2STY4CL |  | 11312057.9107 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VI | Capiz | 115819 | Tapaz CES | TAPAZ | 2 |  | 6 | 2STY6CL |  | 18075614.8964 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VI | Capiz | 115412 | Angub Elementary School | CUARTERO | 2 | 1 | 6 | 2STY6CL |  | 18075614.8964 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region VI | Escalante City | 311106 | Escalante NHS - Dr. Floro T. Bongco Mem. Ext. | CITY OF ESCALANTE | 1 | 1 | 8 | 2STY8CL |  | 21271534.0395 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VI | Iloilo | 116721 | Balbino Seron Elementary School | SAN JOAQUIN | 1 | 1 | 4 | 1STY4CL |  | 10002793.8932 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VI | Iloilo | 116721 | Balbino Seron Elementary School | SAN JOAQUIN | 1 |  | 4 | 1STY4CL |  | 10002793.8932 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | SHS | Region VI | Iloilo | 302508 | Igtalongon NHS | IGBARAS | 1 | 1 | 3 | 1STY3CL |  | 7408102.892 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | SHS | Region VI | Iloilo | 311011 | Adriano Cabardo NHS | ALIMODIAN | 2 | 1 | 2 | 1STY2CL |  | 4345082.9283 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VI | Iloilo | 116444 | Bagongbong ES | LAMBUNAO | 3 | 1 | 2 | 1STY2CL |  | 2992159.745 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VI | Iloilo | 116142 | Guibuangan Elementary School | CABATUAN | 3 | 1 | 3 | 1STY3CL |  | 4295943.075 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | SHS | Region VI | Iloilo | 302534 | Mostro NHS | ANILAO | 4 | 1 | 4 | 2STY4CL |  | 8882732.4525 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VI | Iloilo | 116092 | Batad CES | BATAD | 5 | 1 | 6 | 2STY6CL |  | 12300321.7892 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | TVL | Region VI | Iloilo City | 302744 | Jaro National High School | ILOILO CITY (Capital) | 0 | 1 | 3 | 3STY REG. WORKSHOP |  | 24920145 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VI | La Carlota City | 117635 | Ferlou ES | LA CARLOTA CITY | 4 | 1 | 2 | 1STY2CL |  | 4975662.145 |  | completed | 1 |  |  |  | 19GN0097 | 7/31/2019 | 2019-08-07 | 2019-08-19 |  | 2019-09-12 |  |  | 0
NC 2019 | K10 | Region VI | Passi City | 117898 | Bagacay Elementary School | CITY OF PASSI | 4 | 1 | 3 | 1STY3CL W/ TOILET |  | 6270144.27 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region VI | Roxas City | 500195 | Sofronio A. Cordovero Integrated School | ROXAS CITY (Capital) | 1 | 1 | 4 | 2STY4CL |  | 13192696.2118 |  | completed | 1 |  |  |  | 19GD0098 |  | 2019-07-31 | 2019-08-14 |  |  |  |  | 0
NC 2019 | K10 | Region VI | Sagay City | 117717 | Hautea Elementary School | SAGAY CITY | 2 | 1 | 3 | 1STY3CL |  | 5223570.1395 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VI | Silay City | 117801 | Don Eustaquio Hofilena Mem.Elem. School | SILAY CITY | 3 | 1 | 2 | 1STY2CL |  | 3244586.3377 |  | completed | 1 | [11 empty] | 0
NC 2020 | K10 | Region VI | Aklan | 114901 | Tomas SM Bautista Elementary School | NEW WASHINGTON | 1 | 1 | 2 | 1STY2CL |  | 5513750 |  |  | completed | 1
NC 2020 | K10 | Region VI | Aklan | 114912 | Tambak Elementary School | New Washington | 1 | 1 | 4 | 1STY4CL |  | 9523750 |  |  | completed | 1
NC 2020 | K10 | Region VI | Aklan | 114713 | Agbago ES | IBAJAY | 2 | 1 | 2 | 1STY2CL |  | 4711750 |  |  | Completed | 1
NC 2020 | K10 | Region VI | Aklan | 114842 | Mantiguib ES | MAKATO | 2 | 1 | 2 | 1STY2CL |  | 4711750 |  |  | completed | 1
NC 2020 | K10 | Region VI | Aklan | 114887 | Nabas ES | NABAS | 2 | 1 | 2 | 1STY2CL |  | 4711750 |  |  | Completed | 1
NC 2020 | K10 | Region VI | Aklan | 114917 | Bulwang Elementary School | Numancia | 2 | 1 | 8 | 2STY8CL |  | 25285462.24 |  |  | completed | 1
NC 2020 | SHS | Region VI | Aklan | 500183 | Jawili Integrated School | TANGALAN | 2 | 1 | 2 | 1STY2CL |  | 4711750 |  |  | Completed | 1
NC 2020 | K10 | Region VI | Antique | 115085 | Alberto Siasat ES (Casalngan ES) | HAMTIC | 0 | 1 | 2 | 1STY2CL |  | 5142631.97 |  | 5045853.42 | completed | 1 | 2020-12-20 |  | 20GB0124 | 20GB0124 |  | 2020-07-09 | 2020-07-21 |  | 2020-08-27 | Anjush Builders
NC 2020 | K10 | Region VI | Antique | 115102 | Capnayan PS | LAUA-AN | 0 | 1 | 3 | 1STY3CL |  | 7235007.27 |  | 7089063.2 | Completed | 1 |  | 2021-03-22 | 20GB0125 | 20GB0125 |  | 2020-07-09 | 2020-07-21 |  |  | One Piece Builders
NC 2020 | K10 | Region VI | Antique | 115117 | Maybunga PS | LAUA-AN | 0 | 1 | 2 | 1STY2CL |  | 5394516.39 |  | 5287650.07 | completed | 1 | 2020-12-25 |  | 20GB0126 | 20GB0126 |  | 2020-07-09 | 2020-07-21 |  | 2020-08-27 | Anjush Builders
NC 2020 | K10 | Region VI | Antique | 115260 | Cabunga-an-ES | SAN REMIGIO | 0 | 1 | 2 | 1STY2CL |  | 5394516.39 |  | 5358945.85 | Completed | 1 | 2020-12-20 | 2021-04-16 | 20GB0127 | 20GB0127 |  | 2020-07-09 | 2020-07-21 |  | 2020-08-28 | Aiden and Ayn Construction
NC 2020 | K10 | Region VI | Antique | 115287 | Apong Elementary School | SIBALOM | 0 | 1 | 4 | 2UNITS 1STY2CL |  | 10119020.21 |  |  | completed | 1 |  |  | 20GB0128 | 20GB0128 |  | 2020-07-09 | 2020-07-21
NC 2020 | K10 | Region VI | Antique | 115353 | Tigbaboy PS | TIBIAO | 0 | 1 | 2 | 1STY2CL |  | 5092255.08 |  | 4559516.11 | Completed | 1 |  | 2021-02-17 | 20GB0129 | 20GB0129 |  | 2020-07-09 | 2020-07-21 |  |  | Gateway 21-25 Construction Corp.
NC 2020 | K10 | Region VI | Antique | 115376 | Lawigan ES | TOBIAS FORNIER (DAO) | 0 | 1 | 4 | 2UNITS 1STY2CL |  | 10018266.45 |  | 9837994.06 | Completed | 1 | 2021-02-18 | 2021-07-21 | 20GB0130 | 20GB0130 |  | 2020-07-09 | 2020-07-21 |  | 2020-08-27 | Anjush Builders
NC 2020 | SHS | Region VI | Antique | 302345 | Barasanan National High School | TOBIAS FORNIER (DAO) | 0 | 1 | 20 | 4STY20CL |  | 46948270.7 |  |  | completed | 1 |  |  | 20GB0135 | 20GB0135 |  | 2020-07-15 | 2020-07-27 |  |  | Sentina Coinstruction and supply
NC 2020 | SHS | Region VI | Antique | 302347 | Belison NS | BELISON | 0 | 1 | 20 | 4STY20CL |  | 46948270.7 |  | 46481067.07 | completed | 1 | 2021-05-19 |  | 20GB0131 | 20GB0131 |  | 2020-07-09 | 2020-07-21 |  | 2020-08-27 | Anjush Builders
NC 2020 | SHS | Region VI | Antique | 302359 | Igburi National High School | PATNONGON | 0 | 1 | 9 | 3STY9CL |  | 24436050.34 |  |  | completed | 1 |  |  | 20GB0132 | 20GB0132 |  | 2020-07-09 | 2020-07-21 |  |  | One Piece Builders
NC 2020 | TVL | Region VI | Antique | 310704 | Gen. Leandro Fullon NS | HAMTIC | 0 | 1 | 2 | 2UNITS Unique Workshop (9x22.5m) |  | 10431120.87 |  | 9145534.43 | Completed | 1 |  |  | 20GB0133 | 20GB0133 |  | 2020-07-09 | 2020-07-21 |  |  | MJBL Construction and Services
NC 2020 | K10 | Region VI | Antique | 500515 | Kawit Integrated School | CULASI | 0 | 1 | 12 | 4UNITS 1STY3CL |  | 28441297.92 |  | 28020580.73 | completed | 1 | 2021-04-14 |  | 20GB0134 | 20GB0134 |  | 2020-07-09 | 2020-07-21 |  | 2020-08-27 | Anjush Builders
NC 2020 | K10 | Region VI | Bacolod City | 181004 | Vista Alegre-Granada Relocation ES | Bacolod City (Capital) | 0 | 1 | 6 | 2STY6CL |  | 17687859.38 |  |  | completed | 1 | [10 empty] | completed
NC 2020 | SHS | Region VI | Cadiz City | 302736 | Jerusalem National High School (yee-on Ext.) | Cadiz City | 2 | 1 | 4 | 1-unit 1-sty 4-cl with security grills, attached toilet |  | 10867540.7 |  |  | COMPLETED | 1
NC 2020 | K10 | Region VI | CAPIZ | 115578 | West Villaflores ES | MA-AYON | 1 | 1 | 4 | 2STY4CL |  | 16940041.21 |  |  | Completed | 1 | 2020-09-14 | [8 empty] | CLY-ABC BUILDERS
NC 2020 | K10 | Region VI | CAPIZ | 115415 | Vicente Fabuna ES | CUARTERO | 2 | 1 | 9 | 3STY9CL |  | 24838818.53 |  |  | Completed | 1 |  |  |  |  | 2021-07-31 | 2021-08-07 | 2021-08-20 |  |  | CLY-ABC BUILDERS
NC 2020 | K10 | Region VI | Capiz | 115420 | Mahabang Sapa PS | Cuartero | 2 | 1 | 6 | 2STY6CL |  | 17547856.3 |  |  | completed | 1 |  |  |  |  | 2021-07-31 | 2021-08-07 | 2021-08-20 |  |  | C.B. GARAY PHILWIDE BUILDERS
NC 2020 | K10 | Region VI | Escalante City | 501108 | Paitan IS | Escalante | 1 | 1 | 4 | 2STY4CL |  | 12431000 |  |  | COMPLETED | 1
NC 2020 | K10 | Region VI | Guimaras | 115873 | San Miguel Central School | Jordan | 0 | 1 | 4 | 2STY4CL |  | 10898879.76 |  |  | completed | 1 | [10 empty] | DWPH not yet submitt Building Permit and occupancy Permit
NC 2020 | SHS | Region VI | Iloilo | 302507 | Igbaras NHS | IGBARAS | 1 | 1 | 3 | Completion of 3STY9CL |  | 3007500 |  |  | Completed | 1
NC 2020 | SHS | Region VI | ILOILO | 302531 | MIAG-AO NATIONAL HIGH SCHOOL | MIAG-AO | 1 | 1 | 6 | 2STY6CL with Ground Improvements |  | 19047500 |  |  | Completed | 1
NC 2020 | K10 | Region VI | ILOILO | 115955 | Cunsad PS | ALIMODIAN | 2 | 1 | 2 | 1STY2CL |  | 5775321.68 |  |  | Completed | 1
NC 2020 | SHS | Region VI | ILOILO | 302492 | Don Benjamin Jalandoni Sr. MNHS | ZARRAGA | 2 | 1 | 5 | 1STY5CL |  | 13850432.06 |  |  | Completed | 1
NC 2020 | K10 | Region VI | ILOILO | 115990 | Agusipan Elementary School | Badiangan | 3 | 1 | 2 | 1STY2CL |  | 4912250 |  |  | Completed | 1
NC 2020 | K10 | Region VI | ILOILO | 116403 | Agcarope Elementary School | Janiuay II | 3 | 1 | 2 | 1STY2CL |  | 4912250 |  |  | Completed | 1
NC 2020 | K10 | Region VI | ILOILO | 116431 | Lanot Grande Elem. School | Lambunao East | 3 | 1 | 2 | 1STY2CL |  | 4912250 |  |  | Completed | 1
NC 2020 | K10 | Region VI | ILOILO | 116465 | Pughanan Integrated School | Lambunao West | 3 | 1 | 4 | 2STY4CL |  | 10426000 |  |  | Completed | 1
NC 2020 | K10 | Region VI | ILOILO | 116560 | Trangka Integrated School | Maasin | 3 | 1 | 2 | 1STY2CL |  | 5413500 |  |  | Completed | 1
NC 2020 | SHS | Region VI | Iloilo | 302491 | Dominador Abang MNHS | SAN ENRIQUE | 4 | 1 | 3 | 1STY3CL |  | 6351524.21 |  |  | Completed | 1
NC 2020 | K10 | Region VI | Iloilo | 116067 | Gen. Luna ES | BAROTAC VIEJO | 5 | 1 | 4 | 1STY4CL |  | 9824500 |  |  | Completed | 1
NC 2020 | K10 | Region VI | Iloilo | 116072 | Nueva Invencion ES | BAROTAC VIEJO | 5 | 1 | 4 | 1STY4CL |  | 9624000 |  |  | Completed | 1
NC 2020 | SHS | Region VI | ILOILO | 302523 | Luca NHS | AJUY | 5 | 1 | 9 | 3STY9CL |  | 31278000 |  |  | Completed | 1
NC 2020 | K10 | Region VI | Iloilo City | 117617 | Mandurriao ES | Iloilo City | 0 | 1 | 8 | 2STY8CL |  | 36114060 |  |  | Completed | 1
NC 2020 | K10 | Region VI | Iloilo City | 117625 | Taal ES | ILOILO CITY (Capital) | 0 | 1 | 4 | 2STY4CL |  | 16763805 |  |  | Completed | 1
NC 2020 | TVL | Region VI | Iloilo City | 302737 | Fort San Pedro National High School | Iloilo City | 0 | 1 | 3 | 3STY UNIQUE WORKSHOP |  | 24902100 |  |  | Completed | 1
NC 2020 | SHS | Region VI | Kabankalan City | 302794 | Inapoy NHS | Kabankalan City | 6 | 1 | 6 | 2STY6CL |  | 16190375 |  |  | COMPLETED | 1
NC 2020 | K10 | Region VI | La Carlota City | 117631 | Balabag ES | LA CARLOTA CITY | 4 | 1 | 2 | 1STY2CL |  | 5200849.65 |  |  | Completed | 1
NC 2020 | K10 | Region VI | La Carlota City | 117632 | Batuan ES | LA CARLOTA CITY | 4 | 1 | 2 | 1STY2CL |  | 5350650.12 |  |  | Completed | 1
NC 2020 | K10 | Region VI | Passi City | 101052 | Ayuyan Elementary School | CITY OF PASSI | 4 | 1 | 3 | 1STY3CL |  | 6351524.21 |  |  | COMPLETED | 1
NC 2020 | K10 | Region VI | ROXAS CITY | 117675 | Tanza ES | ROXAS CITY | 1 | 1 | 4 | 2STY4CL |  | 14084750.63 |  |  | COMPLETED | 1
NC 2020 | TVL | Region VI | San Carlos City | 302775 | Julio Ledesma NHS | San Carlos City | 1 | 1 | 4 | 2stryICT Lab |  | 12030000 |  |  | COMPLETED | 1
NC 2020 | SHS | Region VI | Silay City | 500198 | Silay SPED Center | SILAY CITY | 3 | 1 | 4 | 2STY4CL |  | 12531250 |  |  | COMPLETED | 1 | [9 empty] | Silvergraces Construction & Supply
NC 2021 | K10 | Region VI | Aklan | 114641 | Talon ES | ALTAVAS | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1979185.214 | 1974249.59 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Aklan | 114646 | Balete ES | BALETE | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 255915.4832 | 255277.29 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Aklan | 114695 | NAPTI INTEGRATED SCHOOL | BATAN | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 2665143.1222 | 2658496.88 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Aklan | 114695 | NAPTI INTEGRATED SCHOOL | BATAN | 1 |  | 4 | Construction/Completion (2STY4CL) |  | 2701740.6077 | 2695003.1 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Aklan | 114750 | Kalibo Pilot Elementary School | KALIBO (Capital) | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 176701.3016 | 176260.65 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302286 | Altavas National School | ALTAVAS | 1 |  | 4 | Construction/Completion (2STY4CL) |  | 1806733.3093 | 1802227.74 |  | COMPLETED | 1
NC 2021 | TVL | Region VI | Aklan | 302286 | Altavas National School | ALTAVAS | 1 |  | 5 | Construction/Completion (Techvoc Standard Plan) |  | 6263905.1912 | 6248284.48 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302294 | Bay-ang-Magpag-ong NHS | BATAN | 1 | 1 | 9 | Construction/Completion (3STY9CL) |  | 1456074.4985 | 1452443.39 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302299 | CALIZO NATIONAL HIGH SCHOOL | BALETE | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 229112.6031 | 228541.25 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302301 | Camanci National High School | BATAN | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 3994312.6996 | 3984351.82 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302302 | Candelaria NHS | NEW WASHINGTON | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 1217600.7508 | 1214564.34 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302307 | Father Julian C. Rago Memorial NHS | BALETE | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 495276.9446 | 494041.84 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302307 | Father Julian C. Rago Memorial NHS | BALETE | 1 |  | 4 | Construction/Completion (2STY4CL) |  | 397051.6337 | 396061.48 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302308 | Jose Borromeo Legaspi Memorial National High School | BALETE | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 360033.0981 | 359135.26 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302308 | Jose Borromeo Legaspi Memorial National High School | BALETE | 1 |  | 4 | Construction/Completion (2STY4CL) |  | 1165982.2564 | 1163074.57 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302311 | Guadalupe NHS | LIBACAO | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 1063877.0099 | 1061223.95 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302332 | Regional Science High School for Region VI | KALIBO (Capital) | 1 | 1 | 8 | Construction/Completion (4STY8CL) |  | 4573047.0574 | 4561642.95 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302333 | Rizal J. Rodriguez Sr. NHS | BATAN | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 3140368.7335 | 3132537.39 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 310602 | Mangan National High School | BANGA | 1 | 1 | 8 | Construction/Completion (4STY8CL) |  | 5548187.9602 | 5534352.08 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 310617 | Alfonso XII NHS | LIBACAO | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 538164.055 | 536822 |  | COMPLETED | 1
NC 2021 | TVL | Region VI | Aklan | 500170 | Aguinaldo T. Repiedad, Sr. IS | BANGA | 1 | 1 | 1 | Construction/Completion (Techvoc Standard Plan) |  | 678016.1533 | 676325.34 |  | COMPLETED | 1
NC 2021 | TVL | Region VI | Aklan | 500186 | Pinamuk-an Integrated School | NEW WASHINGTON | 1 | 1 | 1 | Construction/Completion (Techvoc Standard Plan) |  | 402940.6395 | 401935.8 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Aklan | 114921 | Laguinbanua ES | NUMANCIA | 2 |  | 6 | Construction/Completion (2STY6CL) |  | 1324243.2723 | 1320940.92 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Aklan | 114923 | Numancia Integrated Sch | NUMANCIA | 2 | 1 | 6 | Construction/Completion (2STY6CL) |  | 2792164.4035 | 2785201.4 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302304 | Catalino M. Prado NHS | LEZO | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 2703271.3651 | 2696530.04 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302304 | Catalino M. Prado NHS | LEZO | 2 |  | 4 | Construction/Completion (2STY4CL) |  | 2703271.3651 | 2696530.04 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302312 | Lilo-an National High School | MALINAO | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 986403.5292 | 983943.67 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302312 | Lilo-an National High School | MALINAO | 2 |  | 4 | Construction/Completion (2STY4CL) |  | 986403.5292 | 983943.67 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302317 | Malay National High School | MALAY | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1589589.9748 | 1585625.91 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302317 | Malay National High School | MALAY | 2 |  | 4 | Construction/Completion (2STY4CL) |  | 1589589.9748 | 1585625.91 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302327 | Numancia National Sch. Of Fisheries | NUMANCIA | 2 |  | 6 | Construction/Completion (2STY6CL) |  | 2878970.1768 | 2871790.7 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302335 | Solido National High School | NABAS | 2 | 1 | 6 | Construction/Completion (2STY6CL) |  | 432074.4324 | 430996.94 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302337 | Toledo NHS | NABAS | 2 | 1 | 6 | Construction/Completion (2STY6CL) |  | 604387.1098 | 602879.91 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302340 | Union National High School | NABAS | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1740386.5862 | 1736046.47 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 302340 | Union National High School | NABAS | 2 |  | 4 | Construction/Completion (2STY4CL) |  | 1740386.5862 | 1736046.47 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 500035 | Numancia Integrated School | NUMANCIA | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 2690820.275 | 2684110 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 500171 | Lezo Integrated School | LEZO | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 2598128.7741 | 2591649.65 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 500171 | Lezo Integrated School | LEZO | 2 |  | 4 | Construction/Completion (2STY4CL) |  | 2282701.0012 | 2277008.48 |  | COMPLETED | 1
NC 2021 | TVL | Region VI | Aklan | 500171 | Lezo Integrated School | LEZO | 2 |  | 1 | Construction/Completion (Techvoc Standard Plan) |  | 736014.7382 | 734179.29 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 500173 | Tamalagon Integrated School | TANGALAN | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 5381640.55 | 5368220 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 500175 | Kinalangay Viejo IS | MALINAO | 2 |  | 6 | Construction/Completion (2STY6CL) |  | 3002097.6779 | 2994611.15 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Aklan | 500182 | Habana Integrated School | BURUANGA | 2 | 1 | 9 | Construction/Completion (3STY9CL) |  | 766281.9776 | 764371.05 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Antique | 114947 | Milagrosa Elementary School | ANINI-Y | 0 | 1 | 2 | Construction/Completion (1STY2CL) |  | 5193008.8568 | 5180058.71 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Antique | 115107 | Jaguiquican ES | LAUA-AN | 0 | 1 | 2 | Construction/Completion (1STY2CL) |  | 1970057.7322 | 1965144.87 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Antique | 115108 | Lactudan PS | LAUA-AN | 0 | 1 | 2 | Construction/Completion (1STY2CL) |  | 5142631.9686 | 5129807.45 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Antique | 115116 | Maria ES | LAUA-AN | 0 | 1 | 5 | Construction/Completion (1STY5CL) |  | 4216483.5416 | 4205968.62 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Antique | 115124 | Tigunhao PS | LAUA-AN | 0 | 1 | 4 | Construction/Completion (2UNITS 1STY2CL) |  | 10018266.4481 | 9993283.24 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Antique | 115242 | General Luna ES | SAN REMIGIO | 0 | 1 | 2 | Construction/Completion (1STY2CL) |  | 5747154.5763 | 5732822.52 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Antique | 115284 | P. Javier PS | SEBASTE | 0 | 1 | 2 | Construction/Completion (1STY2CL) |  | 5193008.8568 | 5180058.71 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Antique | 115332 | Tabong-Tabong ES | SIBALOM | 0 | 1 | 2 | Construction/Completion (1STY2CL) |  | 5243385.7349 | 5230309.96 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Antique | 115361 | Camansi ES | TOBIAS FORNIER (DAO) | 0 | 1 | 2 | Construction/Completion (1STY2CL) |  | 5142631.9686 | 5129807.45 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Antique | 115369 | Igbanos PS | TOBIAS FORNIER (DAO) | 0 | 1 | 2 | Construction/Completion (1STY2CL) |  | 5293762.623 | 5280561.22 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Antique | 115377 | Lindero ES | TOBIAS FORNIER (DAO) | 0 | 1 | 2 | Construction/Completion (1STY2CL) |  | 5092255.0805 | 5079556.19 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Antique | 115397 | Cananghan PS | VALDERRAMA | 0 | 1 | 2 | Construction/Completion (1STY2CL) |  | 5394516.3893 | 5381063.73 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Antique | 115406 | San Agustin ES | VALDERRAMA | 0 | 1 | 3 | Construction/Completion (1STY3CL) |  | 6978085.1586 | 6960683.45 |  | COMPLETED | 1
NC 2021 | TVL | Region VI | Antique | 302367 | Northern Antique Vocational School | CULASI | 0 | 1 | 1 | Construction/Completion (UNIQUE WORKSHOP) |  | 2416147.305 | 2410122 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Antique | 302381 | Sta. Justa National High School | TIBIAO | 0 | 1 | 4 | Construction/Completion (1STY4CL) |  | 4542683.2572 | 4531354.87 |  | COMPLETED | 1
NC 2021 | TVL | Region VI | Bacolod City | 302711 | Luisa Medel NHS | BACOLOD CITY (Capital) | 0 | 1 | 8 | Construction/Completion (4STY4 LAB (2 sci lab, 2 ICT, w/ 4CL)) |  | 12785885 | 12754000 |  | COMPLETED | 1
NC 2021 | TVL | Region VI | Bacolod City | 311201 | M. G. Medalla Integrated School | BACOLOD CITY (Capital) | 0 | 1 | 4 | Construction/Completion (4STY4 LAB (2 sci lab, 2 ICT lab)) |  | 2265650 | 2260000 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Capiz | 115738 | Dapdapan ES | SAPI-AN | 2 | 1 | 5 | Construction/Completion (1STY5CL) |  | 9793438.4197 | 9769015.88 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Capiz | 302399 | Vicente Andaya Sr. NHS | SIGMA | 2 | 1 | 8 | Construction/Completion (2STY8CL) |  | 2023079.9271 | 2018034.84 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Capiz | 302424 | Sapian National High School | SAPI-AN | 2 | 1 | 12 | Construction/Completion (4STY12CL) |  | 3229993.1658 | 3221938.32 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Capiz | 310808 | SAN ANTONIO NATIONAL HIGH SCHOOL | CUARTERO | 2 | 1 | 8 | Construction/Completion (2STY8CL) |  | 2621411.3654 | 2614874.18 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Capiz | 501095 | Calixto Loyola Sr. Integrated School | SIGMA | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 897094.5636 | 894857.42 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Iloilo | 302531 | Miagao NHS | MIAGAO | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 5513645.0583 | 5499895.32 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Iloilo | 116142 | Guibuangan Elementary School | CABATUAN | 3 | 1 | 3 | Construction/Completion (1STY3CL) |  | 2112190.7386 | 2106923.43 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Iloilo | 116444 | Bagongbong ES | LAMBUNAO | 3 | 1 | 2 | Construction/Completion (1STY2CL) |  | 1584430.8191 | 1580479.62 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Iloilo | 302497 | Dueñas NHS | Dueñas | 4 | 1 | 28 | Construction/Completion (4STY28CL) |  | 1762702.8176 | 1758307.05 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Iloilo | 302534 | Mostro NHS | ANILAO | 4 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1477709.1602 | 1474024.1 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Iloilo | 116092 | Batad CES | BATAD | 5 | 1 | 6 | Construction/Completion (2STY6CL) |  | 3508750 | 3500000 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Iloilo City | 117615 | Hibao-an ES | ILOILO CITY (Capital) | 0 | 1 | 4 | Construction/Completion (2STY4CL) |  | 2205500 | 2200000 |  | COMPLETED | 1
NC 2021 | SHS | Region VI | Iloilo City | 302738 | Iloilo City NHS | ILOILO CITY (Capital) | 0 | 1 | 8 | Construction/Completion (4STY8CL) |  | 696737.5 | 695000 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Sagay City | 117717 | Hautea Elementary School | SAGAY CITY | 2 | 1 | 3 | Construction/Completion (1STY3CL) |  | 773328.5 | 771400 |  | COMPLETED | 1
NC 2021 | K10 | Region VI | Silay City | 117801 | Don Eustaquio Hofilena Mem.Elem. School | SILAY CITY | 3 | 1 | 2 | Construction/Completion (1STY2CL) |  | 555685.75 | 554300 |  | COMPLETED | 1
NC 2022 | K10 | Region VI | Aklan | 501181 | Vivo Integrated School | TANGALAN | 0 | 1 | 2 | 1STY2CL | 2 |  | 5253100 | 5585955.94 | completed | 1 | 2023-04-21 | 2023-05-18 | P00675154LZ-CW1 | 22FD0042 | 2022-11-25 | 2022-02-12 | 2022-12-15 | 2022-12-23 | 2022-12-28 | PHIMANA CONST. | 100% completed
NC 2022 | K10 | Region VI | Antique | 114942 | Iba ES | ANINI-Y | 0 | 1 | 3 | 1STY3CL | 2 |  | 6884887.9266 |  | completed | 1
NC 2022 | K10 | Region VI | Antique | 114973 | Belison CS | BELISON | 0 | 1 | 2 | 1STY2CL | 2 |  | 5016683.7433 |  | Completed | 1 | 2023-11-04 | 2023-11-04 | P00675161LZ-0 | 22FM0038 | 2022-11-26 | 2022-12-06 | 2022-12-02 | 2022-12-27 | 2023-06-01 | JOHNCB CONSTRUCTION & SUPPLIES | 100% completed based on Contract and with request for additional fund to full completion of project
NC 2022 | K10 | Region VI | Antique | 114991 | Jinalinan-Paliwan ES | BUGASONG | 0 | 1 | 3 | 1STY3CL | 2 |  | 6884887.9266 | 16573122.71 | Completed | 1 | 2023-07-11 | 2025-01-16 | P0067164LZ-CW1 | 22FL0081 | 2023-01-24 | 2023-01-31 | 2023-02-15 | 2023-02-03 | 2023-03-13 | RMH Construction and Supply
NC 2022 | K10 | Region VI | Antique | 115139 | Tinindugan Primary School | LIBERTAD | 0 | 1 | 2 | 1STY2CL | 2 |  | 5152707.3443 | 5124962.3 | Completed | 1 | 2023-05-28 |  | 22GB0074 | 22GB0074 | 2022-12-07 | 2022-12-15 | 2022-12-27 | 2023-01-17 | 2023-01-30 | ANJUSH BUILDERS
NC 2022 | K10 | Region VI | Guimaras | 115847 | Aguilar Elementary School | SAN LORENZO | 0 | 1 | 6 | 2STY6CL | 2 |  | 17508492.476 |  | Completed | 1 | 2023-06-05
NC 2022 | K10 | Region VI | Iloilo | 116091 | Banban PS | BATAD | 5 | 1 | 2 | 1STY2CL | 2 |  | 7819500 |  | Completed | 1
NC 2022 | SHS | Region VI | Aklan | 302297 | Buruanga Vocational School | BURUANGA | 0 | 1 | 2 | 1STY2CL | 2 |  | 5385680.625 |  | Completed | 1
NC 2022 | SHS | Region VI | Aklan | 500171 | Lezo IS | LEZO | 0 | 1 | 2 | 1STY2CL | 2 |  | 5103226.25 |  | Completed | 1
NC 2023 | K10 | Region VI | Aklan | 500170 | Aguinaldo T. Repiedad Sr. IS | BANGA |  | 1 |  | 3 | Batch 1 | 8473500 | 8400000 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Aklan | 114660 | Banga ES | BANGA |  | 1 |  | 4 | Batch 1 | 21789000 | 21600000 | 9951335.73 | Completed | 1 | 2024-02-07 |  | 23FD0054 | 23FD0054 |  | 2023-07-20 | 2023-08-01 |  | 2023-08-11 | HGG Builders and Supply | numerous items not yet rectified, allowable negative slippage exceeded, no time extension presented, please confirm with division office personnel representative for DPWH projects. DPWH to provide complete Data
NC 2023 | K10 | Region VI | Aklan | 500182 | Habana Integrated School | BURUANGA |  | 1 |  | 2 | Batch 1 | 5822505 | 5772000 |  | Completed | 1 | [10 empty] | Punclisted Items not yet complied. DPWH to provide complete Data
NC 2023 | K10 | Region VI | Aklan | 114713 | Agbago ES | IBAJAY |  | 1 |  | 6 | Batch 1 | 20982000 | 20800000 |  | Completed | 1 | [10 empty] | Punclisted Items not yet complied. DPWH to provide complete Data
NC 2023 | K10 | Region VI | Aklan | 114894 | Toledo Elementary School | NABAS |  | 1 |  | 3 | Batch 1 | 9280500 | 9200000 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Aklan | 114936 | Tangalan ES | TANGALAN |  | 1 |  | 4 | Batch 2 | 13061036.38 | 12619358.82 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Antique | 115218 | Delegate Angel Salazar Jr. MS | SAN JOSE (Capital) |  | 1 |  | 6 | Batch 1 | 16652101.98 | 16507659.95 | 16357659.81 | Ongoing | 1 | 2024-02-02 | 2024-12-02 | 23GB0132 | 23GB0132 | 2023-06-14 | 2023-06-21 | 2023-07-19 | 2023-08-08 | 2023-08-22 | KYRO BUILDERS, INC. | For final inspection and punchlisting.
NC 2023 | K10 | Region VI | Antique | 115367 | Igbalogo Elementary School | TOBIAS FORNIER (DAO) |  | 1 |  | 6 | Batch 1 | 14579838.68 | 14453371.68 | 14303371.67 | Ongoing | 1 | 2024-01-08 | 2024-11-25 | 23GB0131 | 23GB0131 | 2023-06-14 | 2023-06-21 | 2023-07-19 | 2023-08-08 | 2023-08-22 | KAIRO KONSTRAK, INC. | For final inspection and punchlisting.
NC 2023 | K10 | Region VI | Bacolod City | 302699 | ABKASA NHS | BACOLOD CITY (Capital) |  | 1 |  | 1 | Batch 1 | 2521875 | 2500000 | 2500000 | Completed | 1 | 2024-01-03 | 2024-01-29 | P00775013VS-CW1 | [6 empty] | SOLAPO CONSTRUCTION AND SUPPLY CO. | Completed and turned-over to school. DPWH to provide complete Data
NC 2023 | K10 | Region VI | Bacolod City | 117465 | Alberto D. Arceo Sr. ES | BACOLOD CITY (Capital) |  | 1 |  | 1 | Batch 1 | 2521875 | 2500000 | 2500000 | Completed | 1 | 2024-01-03 | 2024-01-29 | P0077508VS-CW1 | [6 empty] | SOLAPO CONSTRUCTION AND SUPPLY CO. | Completed and turned-over to school. DPWH to provide complete Data
NC 2023 | SHS | Region VI | Bacolod City | 302701 | Bacolod City NHS | BACOLOD CITY (Capital) |  | 1 |  | 1 | Batch 1 | 2521875 | 2500000 | 2500000 | Completed | 1 | 2024-01-03 | 2024-01-03 | P0077014VS-CW1 | [6 empty] | SOLAPO CONSTRUCTION AND SUPPLY CO. | Completed and turned-over to school. DPWH to provide complete Data
NC 2023 | K10 | Region VI | Bacolod City |  | Bacolod City NHS - Extension | BACOLOD CITY (Capital) |  | 1 |  | 1 | Batch 1 | 2521875 | 2500000 |  | not yet started | 0 | [10 empty] | reverted due to allocated school site not yet established (no school id)
NC 2023 | K10 | Region VI | Bacolod City | 117478 | Dona E.J. Garcia ES | BACOLOD CITY (Capital) |  | 1 |  | 1 | Batch 1 | 2521875 | 2500000 | 2402135 | Completed | 1 | 2024-01-03 | 2024-01-03 | P0077011VS-CW1 | [6 empty] | KJC CONSTRUCTION & SUPPLY | Completed and turned-over to school. DPWH to provide complete Data
NC 2023 | SHS | Region VI | Bacolod City | 302706 | Emiliano Lizares NHS | BACOLOD CITY (Capital) |  | 1 |  | 1 | Batch 1 | 2521875 | 2500000 | 2500000 | Completed | 1 | 2024-01-03 | 2024-01-29 | P00775016VS-CW1 | [6 empty] | SOLAPO CONSTRUCTION AND SUPPLY CO. | Completed and turned-over to school. DPWH to provide complete Data
NC 2023 | K10 | Region VI | Bacolod City | 117484 | Estefania ES | BACOLOD CITY (Capital) |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 5000000 | Completed | 1 | 2024-02-12 | 2024-02-12 | P00775012VS-CW1 | [6 empty] | SILVERRIA CONSTRUCTION AND CONSTRUCTION SUPPLY COMPANY | Completed and turned-over to school. DPWH to provide complete Data
NC 2023 | K10 | Region VI | Bacolod City | 117472 | Jose Gonzaga ES | BACOLOD CITY (Capital) |  | 1 |  | 12 | Batch 1 | 30262500 | 30000000 | 30000000 | Completed | 1 | 2024-07-01 | 2024-07-31 | P00775009VS-CW1 | [6 empty] | RISM BUILDERS AND CONSTRUCTION SERVICES INC. | Completed and turned-over to school. DPWH to provide complete Data
NC 2023 | SHS | Region VI | Bacolod City | 302704 | Romanito P. Maravilla, Sr. National High School | BACOLOD CITY (Capital) |  | 1 |  | 1 | Batch 1 | 2521875 | 2500000 | 2500000 | Completed | 1 | 2024-01-03 | 2024-02-29 | P00775015VS-CW1 | [6 empty] | SOLAPO CONSTRUCTION AND SUPPLY CO. | Completed and turned-over to school. DPWH to provide complete Data
NC 2023 | SHS | Region VI | Bacolod City | 302718 | Teofilo Gensoli,Sr. National High School | BACOLOD CITY (Capital) |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 5000000 | Completed | 1 | 2024-02-12 | 2024-01-15 | P00775017VS-CW1 | [6 empty] | RVDP Construction | Completed and turned-over to school. DPWH to provide complete Data
NC 2023 | K10 | Region VI | Bacolod City | 117474 | Vista Alegre ES | BACOLOD CITY (Capital) |  | 1 |  | 1 | Batch 1 | 2521875 | 2500000 | 2500000 | Completed | 1 | 2024-02-25 | 2024-02-25 | P00775010VS-CW1 | [6 empty] | SOLAPO CONSTRUCTION AND SUPPLY CO. | Completed and turned-over to school. DPWH to provide complete Data
NC 2023 | K10 | Region VI | Bago City | 117519 | Cristeta A. Dormido ES | BAGO CITY |  | 1 |  | 3 | Batch 1 | 6661039.51 | 6603260.98 | 6534399.05 | Completed | 1 | 2024-01-06 | [8 empty] | Bachoco Construction and Supply | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Bago City | 117528 | Don Salvador Benedicto Memorial School | BAGO CITY |  | 1 |  | 3 | Batch 1 | 6661039.51 | 6603260.98 | 6583541.79 | Completed | 1 | 2023-12-10 | [8 empty] | 911 Rovoca Development Co. | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Bago City | 117522 | Louisiana Elementary School | BAGO CITY |  | 1 |  | 5 | Batch 1 | 10732989.77 | 10639890.72 | 10533450.47 | Completed | 1 | 2024-06-23 |  | P00775933LZ-CW1 | 23FK0107 |  | 2023-08-08 | 2023-08-22 | 2023-08-30 | 2023-09-07 | GKMM Construction and Supplies, Inc. | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Cadiz City | 117533 | Hiyang-Hiyang ES | CADIZ CITY |  | 1 |  | 4 | Batch 1 | 8687799.44 | 8612440.58 | 67650141.66 | ongoing | 0.6 | 2024-07-29 |  | P00775594-CW1 | 23FL0069 | 2023-07-27 | 2023-08-03 | 2023-08-16 | 2023-08-30 | 2023-09-08 | Steven Const. and Supply / Kyla Const. Supply (JV) | On-going
NC 2023 | K10 | Region VI | Cadiz City | 117542 | Villacin ES | CADIZ CITY |  | 1 |  | 5 | Batch 1 | 10732989.77 | 10639890.72 | 21941660.47 | ongoing | 0.9 | 2024-07-29 |  | P00775944-CW1 | 23FL0069 | 2023-07-27 | 2023-08-03 | 2023-08-16 | 2023-08-30 | 2023-09-08 | Steven Const. and Supply / Kyla Const. Supply (JV) | On- going
NC 2023 | SHS | Region VI | Capiz | 302405 | Jose Diva Avelino Jr. NHS | PONTEVEDRA |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 7700000 | COMPLETED | 1 | 2024-05-02 |  | P00775024VS-CW1 |  | 2023-07-06 | 2023-06-14 | 2023-06-27 | 2023-07-08 | 2023-08-29 | SALMEGA BUILDERS | DPWH to provide complete Data
NC 2023 | SHS | Region VI | Capiz | 302409 | Jamindan National High School | JAMINDAN |  | 1 |  | 8 | Batch 1 | 22903616.81 | 22704948.51 | 22604305.03 | COMPLETED | 1 | 2024-05-19 | 2025-01-25 | P00775025VS | 23GP0089 | 2023-08-03 | 2023-08-22 | 2023-04-09 | 2023-09-28 | 2023-11-10 | 3 A'S & J CONSTRUCTION
NC 2023 | K10 | Region VI | Capiz | 115590 | Ilawod ES (mambusao east) | MAMBUSAO |  | 1 |  | 2 | Batch 1 | 4788571.5 | 4747034.94 | 4726144.25 | COMPLETED | 1 | 2023-12-30 | 2024-02-28 | P00775026VS | 23GP0090 | 2023-08-03 | 2023-08-22 | 2023-04-09 | 2023-09-28 | 2023-11-10 | KERGEL BUILDERS
NC 2023 | K10 | Region VI | Capiz | 115816 | San Nicolas ES | TAPAZ |  | 1 |  | 4 | Batch 1 | 8687799.44 | 8612440.58 | 8598770.96 | COMPLETED | 1 | 2024-02-29 | 2024-08-06 | P00775027VS | 23GP0091 | 2023-08-03 | 2023-08-22 | 2023-04-09 | 2023-09-28 | 2023-11-10 | 7 JL HARDWARE & CONSTRUCTION SUPPLIES
NC 2023 | K10 | Region VI | Guimaras | 115906 | Guiwanon Elementary School | NUEVA VALENCIA |  | 1 |  | 4 | Batch 1 | 11600625 | 11500000 | 11599565.8 | COMPLETED | 1 | 2023-12-02 | 2023-12-02 | P00775029VS-CW1 | 23ge0070 |  | 2023-07-04 | 2023-07-17 | 2023-07-26 | 2023-08-04 | J.E. TICO CONSTRUCTION CO., INC. | Completed
NC 2023 | K10 | Region VI | Guimaras | 115897 | Nueva Valencia Central School | NUEVA VALENCIA |  | 1 |  | 6 | Batch 1 | 18661875 | 18500000 | 18593457.63 | COMPLETED | 1 | 2023-12-23 | 2023-12-23 | P00775028VS-CW1 | 23ge00069 |  | 2024-06-29 | 2023-07-11 | 2023-07-18 | 2023-07-26 | J.E. TICO CONSTRUCTION CO., INC. | Completed
NC 2023 | K10 | Region VI | Guimaras | 305930 | Catalino G. Nava Farm School | SAN LORENZO |  | 1 |  | 2 | Batch 1 | 7178272.06 | 7116007 | 7176400.43 | COMPLETED | 1 | 2023-11-02 | 2023-10-31 | P00775031VS-CW1 | 23ge0071 |  | 2023-07-04 | 2023-07-17 | 2023-07-26 | 2023-08-04 | J.E. TICO CONSTRUCTION CO., INC. | Completed
NC 2023 | K10 | Region VI | Guimaras | 115859 | Tangaw Primary School | SAN LORENZO |  | 1 |  | 2 | Batch 1 | 5916665.76 | 5865344 | 5916404.28 | COMPLETED | 1 | 2023-10-24 | 2023-10-24 | P00775030VS-CW1 | 23ge0068 |  | 2024-06-29 | 2023-07-11 | 2023-07-18 | 2023-07-26 | J.E. TICO CONSTRUCTION CO., INC. | Completed
NC 2023 | K10 | Region VI | Iloilo | 501443 | Cabasi-Sta. Rosa Integrated School | GUIMBAL |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4994624.49 | Completed | 1 | 2023-12-28 | 2024-01-25 | P00775033VS-CW1 | 23GF0129 | 2023-07-28 | 2023-08-04 | 2023-08-17 | 2023-08-29 | 2023-09-08 | GATS AND SON CONSTRUCTION DEVELOPMENT CO. | Completed
NC 2023 | SHS | Region VI | Iloilo | 302536 | Nalundan NHS | GUIMBAL |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4932738.6 | Completed | 1 | 2024-01-15 | 2024-01-15 | P00775032VS-CW2 | 23GF0124 | 2023-07-13 | 2023-07-21 | 2023-08-02 | 2023-08-11 | 2023-08-24 | A MAQUILING CONSTRUCTION AND SUPPLY
NC 2023 | SHS | Region VI | Iloilo | 302542 | Oton National High School | OTON |  | 1 |  | 12 | Batch 1 | 29965927.5 | 29706000 | 29455648.72 | Completed | 1 | 2024-05-22 | 2024-05-22 | P00775034VS-CW1 | 23GF0132 | 2023-08-03 | 2023-08-10 | 2023-08-22 | 2023-08-30 | 2023-09-12 | RINEL COSNTRUCTION SERVICES
NC 2023 | K10 | Region VI | Iloilo | 115950 | Bancal ES | ALIMODIAN |  | 1 |  | 3 | Batch 1 | 9583125 | 9500000 | 9494127.04 | Completed | 1 |  |  | P00775035VS | 23GI0108 | 2023-06-24 | 2023-07-03 | 2023-07-17 | 2023-07-31 | 2023-08-11 |  | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Iloilo | 116513 | Pepe-Lonoc Elementary School | LEON |  | 1 |  | 3 | Batch 1 | 9583125 | 9500000 |  | Completed | 1 |  |  | P00775036VS | 23GI0109 | 2023-06-24 | 2023-07-03 | 2023-07-17 | 2023-07-31 | 2023-08-11 |  | DPWH to provide complete Data
NC 2023 | SHS | Region VI | Iloilo | 302540 | New Lucena National High School | NEW LUCENA |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | Completed | 1 |  |  | P00775037VS | 23GI0113 | 2023-07-27 | 2023-08-03 | 2023-08-15 | 2023-08-30 | 2023-07-14 |  | DPWH to provide complete Data
NC 2023 | SHS | Region VI | Iloilo | 302468 | Buayahon-Bantay NHS | SANTA BARBARA |  | 1 |  | 3 | Batch 1 | 9583125 | 9500000 |  | Completed | 1 |  |  | P00775038VS | 23GI0110 | 2023-06-24 | 2023-07-03 | 2023-07-17 | 2023-07-31 |  |  | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Iloilo | 116111 | Maganhop PS | BINGAWAN |  | 1 |  | 2 | Batch 1 | 5919345 | 5868000 | 5803747.93 | Completed | 1 |  | 2024-12-29 |  | 23GG0273 | 2023-06-15 | 2023-06-22 | 2023-07-05 | 2023-07-20 | 2023-07-26 | Po Suplico Construction Corporation | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Iloilo | 116112 | Malitbog Ilawod PS | BINGAWAN |  | 1 |  | 3 | Batch 1 | 7363875 | 7300000 | 5853462.9 | Completed | 1 |  | 2024-04-22 |  | 23GG0280 | 2023-06-15 | 2023-06-22 | 2023-07-05 | 2023-07-25 | 2023-08-04 | MJ Barcelona Construction and Supply | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Iloilo | 116117 | Tubod PS | BINGAWAN |  | 1 |  | 3 | Batch 1 | 7363875 | 7300000 | 5908723.41 | Completed | 1 |  | 2024-04-22 |  | 23GG0281 | 2023-06-15 | 2023-06-22 | 2023-07-05 | 2023-07-20 | 2023-07-26 | MJ Barcelona Construction and Supply | DPWH to provide complete Data
NC 2023 | SHS | Region VI | Iloilo | 302478 | Calmay NHS | JANIUAY |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 7837247.23 | Completed | 1 |  | 2024-01-25 |  | 23GG0284 | 2023-06-15 | 2023-06-22 | 2023-07-05 | 2023-07-25 | 2023-08-04 | MZ Builders and Construction Supply | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Iloilo | 116394 | Janiuay Pilot ES | JANIUAY |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9950000 | Completed | 1 |  | 2024-03-01 |  | 23GG0286 | 2023-06-15 | 2023-06-22 | 2023-07-05 | 2023-07-20 | 2023-07-26 | Kit'z Construction and Supply | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Iloilo | 116546 | Maasin CES | MAASIN |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 7916472.76 | Ongoing | 1 |  | 2024-07-10 |  | 23GG0285 | 2023-06-15 | 2023-06-22 | 2023-07-05 | 2023-08-01 | 2023-08-11 | MJBL Construction Services | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Iloilo | 116594 | Abat Elementary School | MINA |  | 1 |  | 2 | Batch 1 | 5919345 | 5868000 | 5364203.95 | Completed | 1 |  | 2024-07-22 |  | 23GG0274 | 2023-06-15 | 2023-06-22 | 2023-07-05 | 2023-07-25 | 2023-08-04 | Noe's Builders | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Iloilo | 116602 | Mina Central School | MINA |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9196876.97 | Completed | 1 |  | 2024-07-22 |  | 23GG0283 | 2023-06-15 | 2023-06-22 | 2023-07-05 | 2023-07-20 | 2023-07-26 | Noe's Builders | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Iloilo | 501478 | Taminla Integrated School | DUEÑAS |  | 1 |  | 3 | Batch 1 | 6661785 | 6604000 | 6400666.29 | Completed | 1 |  | 2024-04-11 |  | 23GG0282 | 2023-06-15 | 2023-06-22 | 2023-07-05 | 2023-07-20 | 2023-07-25 | Arrianne Mechandising and Construction Services, Inc. | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Iloilo | 116332 | Alyag PS | DUMANGAS |  | 1 |  | 2 | Batch 1 | 4791562.5 | 4750000 | 4471183.7 | Completed | 1 |  | 2023-11-28 |  | 23GG0277 | 2023-06-15 | 2023-06-22 | 2023-07-05 | 2023-07-20 | 2023-07-31 | El Prado Builders | DPWH to provide complete Data
NC 2023 | SHS | Region VI | Iloilo | 302483 | Cayos NHS | DUMANGAS |  | 1 |  | 2 | Batch 1 | 4791562.5 | 4750000 | 4021246.51 | Completed | 1 |  | 2024-03-18 |  | 23GG0279 | 2023-06-15 | 2023-06-22 | 2023-07-05 | 2023-07-21 | 2023-07-26 | A. Maquiling Construction and Supply | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Iloilo | 116323 | Dumangas CES | DUMANGAS |  | 1 |  | 2 | Batch 1 | 4791562.5 | 4750000 | 4345863.12 | Completed | 1 |  | 2023-12-29 |  | 23GG0275 | 2023-06-15 | 2023-06-22 | 2023-07-05 | 2023-07-21 | 2023-07-26 | Noe's Builders | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Iloilo | 116325 | Lacturan ES | DUMANGAS |  | 1 |  | 2 | Batch 1 | 4791562.5 | 4750000 | 4654713.16 | Completed | 1 |  | 2024-05-13 |  | 23GG0276 | 2023-06-15 | 2023-06-22 | 2023-07-05 | 2023-07-20 | 2023-07-26 | MZ Builders and Construction Supply | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Iloilo | 116343 | Paloc Sool ES | DUMANGAS |  | 1 |  | 2 | Batch 1 | 4791562.5 | 4750000 | 4642359.08 | Completed | 1 |  | 2023-11-17 |  | 23GG0278 | 2023-06-15 | 2023-06-22 | 2023-07-05 | 2023-07-20 | 2023-07-26 | DG Salas Construction Services | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Iloilo | 116066 | Del Pilar PS | BAROTAC VIEJO |  | 1 |  | 4 | Batch 1 | 8687799.44 | 8612440.58 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Iloilo | 501483 | Bulak Integrated School | BATAD |  | 1 |  | 2 | Batch 1 | 6365212.5 | 6310000 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Iloilo | 116100 | Pasayan PS | BATAD |  | 1 |  | 2 | Batch 1 | 6365212.5 | 6310000 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Iloilo | 116349 | Estancia Central Elementary School | ESTANCIA |  | 1 |  | 4 | Batch 1 | 15131250 | 15000000 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | SHS | Region VI | Iloilo | 302500 | Estancia National High School | ESTANCIA |  | 1 |  | 4 | Batch 1 | 15131250 | 15000000 |  | Ongoing | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | SHS | Region VI | Iloilo | 302493 | Carlos Lopez NHS | SAN DIONISIO |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Iloilo City | 117619 | Baluarte ES | ILOILO CITY (Capital) |  | 1 |  | 4 | Batch 1 | 11451808.4 | 11352474.25 | 11342107.61 | Ongoing | 1 | 2024-01-22 | 2025-05-21 | 140 |  | 2023-07-28 | 2023-08-04 | 2023-08-17 | 2023-10-12 | 2023-10-17 | NOE'S BUILDERS | Completed. DPWH to provide complete Data
NC 2023 | K10 | Region VI | Iloilo City | 117621 | I. Arroyo ES | ILOILO CITY (Capital) |  | 1 |  | 4 | Batch 1 | 15433875 | 15300000 | 15144785.17 | Ongoing | 0.45 | 2024-04-10 |  | 140 |  | 2023-08-23 | 2023-08-30 |  | 2023-10-19 | 2023-10-25 | TOP MOST DEV'T. CORP. | Rectification works. DPWH to provide complete Data
NC 2023 | K10 | Region VI | Iloilo City | 117588 | Iloilo Central ES | ILOILO CITY (Capital) |  | 1 |  | 6 | Batch 1 | 18157500 | 18000000 | 17814549.77 | Ongoing | 0.95 | 2024-04-04 |  | 175 |  | 2023-08-23 | 2023-08-30 |  | 2023-10-19 | 2023-10-25 | TOP MOST DEV'T. CORP. | Rectification works. DPWH to provide complete Data
NC 2023 | K10 | Region VI | Iloilo City | 117602 | Sambag ES | ILOILO CITY (Capital) |  | 1 |  | 4 | Batch 1 | 12105000 | 12000000 | 11518640.52 | Ongoing | 0.6 | 2024-01-31 |  | 140 |  | 2023-08-11 | 2023-08-18 | 2023-08-30 | 2023-10-12 | 2023-10-17 | JC ALBASON BUILDERS | Delay of works. DPWH to provide complete Data
NC 2023 | K10 | Region VI | Kabankalan City | 117840 | Esteban R. Abada Memorial School - West SPED | CITY OF KABANKALAN |  | 1 |  | 1 | Batch 1 | 2521875 | 2500000 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | SHS | Region VI | Roxas City | 302758 | Culasi NHS | ROXAS CITY (Capital) |  | 1 |  | 2 | Batch 1 | 29144730.92 | 28891926.56 | 24536275.6 | Completed | 1 | 2024-06-26 | 2024-06-17 | 23GD0078 | 23GD0078 | 2023-06-07 | 2023-06-14 | 2023-06-27 | 2023-08-21 |  | SALMEGA BUILDERS | with approved variation order
NC 2023 | K10 | Region VI | Sagay City | 311801 | Old Sagay National High School | SAGAY CITY |  | 1 |  | 10 | Batch 1 | 10732989.77 | 10639890.72 | 10320198.76 | Completed | 1 | 2023-11-20 | 2023-11-20 | 23GK0206 | 23GK0206 | 2023-05-30 | 2023-06-07 | 2023-06-21 | 2023-07-10 | 2023-07-21 | GALFONS BUILDERS AND SUPPLY, INC.
NC 2023 | K10 | Region VI | San Carlos City | 117776 | Iliranan IS | SAN CARLOS CITY |  | 1 |  | 5 | Batch 1 | 4788571.5 | 4747034.94 | 4718182.49 | Completed | 1 |  |  | 23GQ0065 |  | 2023-07-25 | 2023-08-01 | 2023-08-15 | 2023-09-08 |  | Kenneth Const. & Gen. Merchandise | DPWH to provide complete Data
NC 2023 | K10 | Region VI | San Carlos City | 117794 | Lina dela Viña Valmayor ES | SAN CARLOS CITY |  | 1 |  | 2 | Batch 1 | 4788571.5 | 4747034.94 | 4710071.52 | Completed | 1 |  |  | 23GQ0066 |  | 2023-07-25 | 2024-08-01 | 2023-08-15 | 2023-09-08 |  | Kenneth Const. & Gen. Merchandise | DPWH to provide complete Data
NC 2023 | K10 | Region VI | Sipalay City | 117365 | Barasbarasan Elementary School - Indangawan Annex | CITY OF SIPALAY |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4992477.72 | COMPLETED | 1 | 2023-12-06 | 2023-12-06 | P00775084VS-CW1 | 23GM0068 | 2023-06-15 | 2023-06-23 | 2023-07-05 | 2023-07-26 | 2023-08-17 | JVC TOUGH CORE CNST. AND BUILDERS CORP.
NC 2023 | K10 | Region VI | Sipalay City | 117376 | Macarandan ES | CITY OF SIPALAY |  | 1 |  | 2 | Batch 1 | 2521875 | 2500000 | 2500000 | COMPLETED | 1 | 2023-12-07 | 2023-12-17 | P00775085VS-CW1 | 23GM0069 | 2023-07-14 | 2023-07-24 | 2023-08-07 | 2023-08-25 | 2023-09-19 | JVC TOUGH CORE CNST. AND BUILDERS CORP.
NC 2023 | K10 | Region VI | Victorias City | 117431 | Estado ES | CITY OF VICTORIAS |  | 1 |  | 1 | Batch 1 | 16140000 | 16000000 | 15999999.62 | Completed | 1 | 2023-12-17 | 2024-01-19 | 23GK0208 | 23GK0208 | [5 empty] | KENBE CONSTRUCTION AND SUPPLY | Completed. DPWH to provide complete Data
NC 2024 |  | Region VI | Aklan | 302286 | Altavas National School | ALTAVAS |  | 1 | 9 | 3STY9CL | GAA 17B | 35100000 |  |  | Ongoing | 0.05
NC 2024 |  | Region VI | Aklan | 114643 | Aranas ES | BALETE |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Aklan | 500543 | Balete Integrated School | BALETE |  | 1 | 8 | 4STY8CL | GAA 17B | 31500000 |  |  | Ongoing | 0.15 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Aklan | 500170 | Aguinaldo T. Repiedad Sr. IS | BANGA |  | 1 | 6 | 3STY6CL | GAA 17B | 23500000 |  |  | Ongoing | 0.2 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Aklan | 114660 | Banga ES | BANGA |  | 1 | 6 | 2STY6CL | GAA 17B | 20000000 |  |  | Ongoing | 0.05 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Aklan | 501791 | Don Edecio S. Venturanza Integrated School | BANGA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.7 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Aklan | 114679 | Urquiola Memorial Elementary School | BANGA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Aklan | 302300 | Camaligan NHS | BATAN |  | 1 | 4 | 2STY4CL | GAA 17B | 15750000 |  |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Aklan | 114756 | Kalibo I ES | KALIBO (Capital) |  | 1 | 12 | 4STY12CL | GAA 17B | 46200000 |  |  | Ongoing | 0.2 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Aklan | 302310 | Libacao National Forestry Vocational High School | LIBACAO |  | 1 | 4 | 2STY4CL | GAA 17B | 15750000 |  |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Aklan | 302315 | Madalag NHS | MADALAG |  | 1 | 4 | 2STY4CL | GAA 17B | 15750000 |  |  | Ongoing | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Aklan | 302303 | New Washington NCHS | NEW WASHINGTON |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Aklan | 302303 | New Washington NCHS | NEW WASHINGTON |  | 1 | 8 | 4STY8CL | GAA 17B | 31500000 |  |  | Ongoing | 0.05 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Aklan | 302320 | Maloco NHS | IBAJAY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.85 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Aklan | 302320 | Maloco NHS | IBAJAY |  |  | 8 | 4STY8CL | GAA 17B | 31500000 |  |  | Ongoing | 0.05 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Aklan | 500171 | Lezo IS | LEZO |  | 1 | 8 | 2STY8CL | BATCH 1 | 26500000 |  |  | Ongoing | 0.05 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Aklan | 114834 | Calangcang ES | MAKATO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Aklan | 114878 | Alimbo Baybay PS | NABAS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.8 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Aklan | 114882 | Habana Elementary School | NABAS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Aklan | 500547 | Tagororoc INTEGRATED sCHOOL | NABAS |  | 1 | 5 | 1STY5CL | GAA 17B | 15000000 |  |  | Ongoing | 0.2 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Aklan | 114918 | Camanci Norte ES | NUMANCIA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Antique | 114944 | Igtumarom ES | ANINI-Y |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  | 9944870.85 | Completed | 1 | 2024-12-28 | 2025-05-30 | 24GB0120 | 24BG0120 | 2024-03-19 | 2024-03-27 | 2024-11-04 | 2024-04-24 | 2024-02-05 | ECII CONSTRUCTION AND SUPPLY | COMPLETED AND JOINT INSPECTED (MAY 30, 2025) DPWH to provide complete Data
NC 2024 |  | Region VI | Antique | 114958 | Barbaza Central School | BARBAZA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4964744.87 | Completed | 1 | 2024-08-30 | 2024-11-19 | 24GB0116 | 24GB0116 | 2024-03-19 | 2024-03-27 | 2024-11-04 | 2024-04-24 | 2024-02-05 | REVIM CONSTRUCTION | COMPLETED AND JOINT INSPECTED (MAY 30, 2025)DPWH to provide complete Data
NC 2024 |  | Region VI | Antique | 114962 | Esparar ES | BARBAZA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4943432.97 | Completed | 1 | 2024-03-10 | 2024-10-19 | 24GB0115 | 24GB0115 | 2024-03-19 | 2024-03-27 | 2024-11-04 | 2024-04-24 | 2024-02-05 | GATEWAY 21-25 CONSTRUCTION CORP. | COMPLETED AND JOINT INSPECTED (MAY 30, 2025)
NC 2024 |  | Region VI | Antique | 502276 | Flores Integrated School | CULASI |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  | 9941477.19 | Completed | 1 | 2024-09-29 | 2025-05-03 | 24GB0117 | 24GB0117 | 2024-03-19 | 2024-03-27 | 2024-11-04 | 2024-04-24 | 2024-02-05 | AIDEN & AYN CONSTRUCTION | COMPLETED AND JOINT INSPECTED (MAY 30, 2025)
NC 2024 |  | Region VI | Antique | 115054 | San Luis-Condes ES | CULASI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4967501.36 | Completed | 1 | 2024-08-30 | 2024-11-29 | 24GB0118 | 24GB0118 | 2024-03-19 | 2024-03-27 | 2024-11-04 | 2024-04-24 | 2024-02-05 | AIDEN & AYN CONSTRUCTION | COMPLETED AND JOINT INSPECTED (MAY 30, 2025)
NC 2024 |  | Region VI | Antique | 115105 | Guinbanga-an ES | LAUA-AN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4946127.61 | Completed | 1 | 2024-08-30 | 2024-10-16 | 24GB0111 | 24GB0111 | 2024-03-19 | 2024-03-27 | 2024-11-04 | 2024-04-24 | 2024-02-05 | MJSB BUILDERS AND SUPPLY | COMPLETED AND JOINT INSPECTED (MAY 30, 2025)
NC 2024 |  | Region VI | Antique | 115114 | Lugta ES | LAUA-AN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4950272.37 | Completed | 1 | 2024-08-30 | 2024-09-16 | 24GB0114 | 24GB0114 | 2024-03-19 | 2024-03-27 | 2024-11-04 | 2024-04-24 | 2024-02-05 | REVIM CONSTRUCTION | COMPLETED AND JOINT INSPECTED (MAY 30, 2025)
NC 2024 |  | Region VI | Antique | 115121 | San Ramon PS | LAUA-AN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4956005.93 | Completed | 1 | 2024-08-30 | 2025-02-14 | 24GB0121 | 24GB0121 | 2024-03-19 | 2024-03-27 | 2024-11-04 | 2024-04-24 | 2024-02-05 | KYMEARL CONSTRUCTION SEVICES | COMPLETED AND JOINT INSPECTED (MAY 30, 2025)
NC 2024 |  | Region VI | Antique | 115134 | Pucio ES | LIBERTAD |  | 1 | 2 | 1STY2CL | BATCH 2 | 5127667.45 |  | 5082000 | Ongoing | 0.92 | 2025-02-05 |  | 24GB0151 | 24GB0151 | 2024-11-27 | 2024-12-05 | 2024-12-17 | 2024-12-23 | 2025-06-01 | EC BUILDERS | COMPLETED AND JOINT INSPECTED (MAY 30, 2025)
NC 2024 |  | Region VI | Antique | 302369 | Pandan NVHS | PANDAN |  | 1 | 20 | TECVOC | BATCH 1 | 10000000 |  | 9944999.96 | Ongoing | 0.34 | 2025-02-08 |  | 24GB0156 | 24gB0156 | 2025-01-09 | 2025-01-17 | 2025-01-30 | 2025-04-03 | 2025-03-20 | SETTLERS | COMPLETED AND JOINT INSPECTED (MAY 30, 2025)
NC 2024 |  | Region VI | Antique | 502087 | Aningalan Integrated Farm School | SAN REMIGIO |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  | 9931085.93 | Completed | 1 | 2024-10-12 | 2025-01-13 | 24GB0119 | 24GB0119 | 2024-03-19 | 2024-03-27 | 2024-11-04 | 2024-04-24 | 2024-02-05 | KYMEARL CONSTRUCTION SEVICES | COMPLETED AND JOINT INSPECTED (MAY 30, 2025)
NC 2024 |  | Region VI | Antique | 115283 | Nauhon ES | SEBASTE |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969521.7 | Completed | 1 | 2024-08-30 | 2024-08-30 | 24GB0112 | 24GB0112 | 2024-03-19 | 2024-03-27 | 2024-11-04 | 2024-04-24 | 2024-02-05 | AIDEN & AYN CONSTRUCTION | With punchlist for compliance
NC 2024 |  | Region VI | Antique | 115345 | Martinez ES | TIBIAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4943972.59 | Completed | 1 | 2024-09-18 | 2024-10-28 | 24GB0113 | 24GB0113 | 2024-03-19 | 2024-03-27 | 2024-11-04 | 2024-04-24 | 2024-02-05 | GATEWAY 21-25 CONSTRUCTION CORP. | With punchlist for compliance
NC 2024 |  | Region VI | Bacolod City | 117452 | Banago Elementary School I | BACOLOD CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4925251.68 | Completed | 1 | 2024-10-28 | 2024-11-18 | 24GO0109 | 24GO0109 | [5 empty] | ROCK-WILLIAN CONSTRUCTION AND SUPPLY | COMPLETED AND JOINT INSPECTED (MAY 30, 2025). DPWH to provide complete Data
NC 2024 |  | Region VI | Bacolod City | 117455 | Bata Elementary School - I | BACOLOD CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4185926.78 | Completed | 1 | 2024-10-31 | 2024-11-25 | 24GO0105 | 24GO0105 | [5 empty] | SOLAPO CONSTRUCTION AND SUPPLY CO. | COMPLETED AND JOINT INSPECTED (MAY 30, 2025)DPWH to provide complete Data
NC 2024 |  | Region VI | Bacolod City | 117475 | Don Crispino V. Ramos Elementary School | BACOLOD CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4185853.7 | Completed | 1 | 2024-10-31 | 2024-11-25 | 24GO0108 | 24GO0108 | [5 empty] | SOLAPO CONSTRUCTION AND SUPPLY CO. | COMPLETED AND JOINT INSPECTED (MAY 30, 2025) DPWH to provide complete Data
NC 2024 |  | Region VI | Bacolod City | 117484 | Estefania Elementary School | BACOLOD CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4185926.78 | Completed | 1 | 2024-10-31 | 2024-11-25 | 24GO0105 | 24GO0105 | [5 empty] | SOLAPO CONSTRUCTION AND SUPPLY CO. | COMPLETED AND JOINT INSPECTED (MAY 30, 2025) DPWH to provide complete Data
NC 2024 |  | Region VI | Bacolod City | 117490 | F.R. Flores Elementary School | BACOLOD CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4185926.78 | Completed | 1 | 2024-10-31 | 2024-04-11 | 24GO0106 | 24GO0106 | [5 empty] | SOLAPO CONSTRUCTION AND SUPPLY CO. | COMPLETED AND JOINT INSPECTED (MAY 30, 2025) DPWH to provide complete Data
NC 2024 |  | Region VI | Bacolod City | 117473 | Paglaum Village Elementary School | BACOLOD CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4975000 | Completed | 1 | 2024-11-30 | 2024-11-30 | 24GO0102 | 24GO0102 | [5 empty] | KJC CONSTRUCTION & SUPPLY | COMPLETED AND JOINT INSPECTED (MAY 30, 2025) DPWH to provide complete Data
NC 2024 |  | Region VI | Bacolod City | 117473 | Paglaum Village Elementary School | BACOLOD CITY (Capital) |  |  | 16 | 4STY16CL | GAA 17B | 40000000 |  | 39800000 | Ongoing | 0.75 | 2025-04-30 |  | 24GO0103 | 24GO0103 | [5 empty] | GOLDSTAR MARKETING & CONSTRUCTION SERVICES, INC. / WILKINSON CONSTRUCTION | DPWH to provide complete Data
NC 2024 |  | Region VI | Bacolod City | 117491 | Sum-ag ES | BACOLOD CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4741711.67 | Completed | 1 | 2024-11-11 | 2024-11-11 | 24GO0107 | 24GO0107 | [5 empty] | KENBE CONSTRUCTION & SUPPLY | COMPLETED AND JOINT INSPECTED (MAY 30, 2025) DPWH to provide complete Data
NC 2024 |  | Region VI | Bago City | 117511 | Alianza Elementary School | BAGO CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4949269.88 | Completed | 1 | 2024-05-08 |  |  | 24GN0084 | [5 empty] | J. F. Uy Construction Services | DPWH to provide complete Data
NC 2024 |  | Region VI | Bago City | 117505 | Dr. A. Sian ES | BAGO CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4925053.59 | Completed | 1 | 2024-05-08 |  |  | 24GN0083 | [5 empty] | EMR Builders | DPWH to provide complete Data
NC 2024 |  | Region VI | Cadiz City | 117547 | Cotcot ES | CADIZ CITY |  | 1 | 4 | 2STY4CL | GAA 17B | 11000000 |  |  | Ongoing | 0.45 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Cadiz City | 117532 | Dr. V.F.Gustilo ES | CADIZ CITY |  | 1 | 4 | 2STY4CL | GAA 17B | 11000000 |  |  | Ongoing | 0.25 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Capiz | 501438 | Canapian Integrated School | MA-AYON |  | 1 | 4 | 2STY4CL | GAA 17B | 15750000 |  | 15500399.65 | Ongoing | 0.85 | 2024-08-02 |  | P00875280VS |  | 2024-04-09 | 2024-04-16 | 2024-04-30 | 2024-05-27 | 2024-06-13 | MEGAGOLD CONSTRUCTION AND DEVELOPMENT, OPC | DPWH to provide complete Data
NC 2024 |  | Region VI | Capiz | 501437 | Tapulang Integrated School | MA-AYON |  | 1 | 4 | 2UNITS 1STY2CL | GAA 17B | 10000000 |  | 9879940.75 | Completed | 1 | 2025-03-02 |  | P00875280VS |  | 2024-06-14 | 2024-06-21 | 2024-07-04 | 2024-09-08 | 2024-08-27 | CHASTUDON CONSTRUCTION SERVICES & SUPPLIES | DPWH to provide complete Data
NC 2024 |  | Region VI | Capiz | 501437 | Tapulang Integrated School | MA-AYON |  | 1 | 4 | 2STY4CL | GAA 17B | 15000000 |  | 14859476.05 | Completed | 1 | 2024-10-12 |  | P00875274VS |  | 2024-04-09 | 2024-04-16 | 2024-04-30 | 2024-05-26 | 2024-06-13 | ORANGEKONSTRUCT CIVIL ENGINEERING SERVICES | DPWH to provide complete Data
NC 2024 |  | Region VI | Capiz | 501089 | Bago Chiquito Integrated School | PANAY |  | 1 | 4 | 2UNITS 1STY2CL | GAA 17B | 10000000 |  | 8289863.62 | Ongoing | 0.85 | 2025-09-03 |  | P00875033VS |  | 2024-05-14 | 2024-05-21 | 2024-06-03 | 2024-08-27 | 2024-09-12 | NANA BUILDERS | DPWH to provide complete Data
NC 2024 |  | Region VI | Capiz | 501093 | Celestino D. Diaz Integrated School | PANITAN |  | 1 | 9 | 3STY9CL | GAA 17B | 25000000 |  | 24624528.62 | Ongoing | 0.35 | 2025-07-23 | [8 empty] | STEP N STONE CONSTRUCTION | DPWH to provide complete Data
NC 2024 |  | Region VI | Capiz | 501099 | Felixberto Dicon Dorado Sr. Integrated School | PANITAN |  | 1 | 4 | 2UNITS 1STY2CL | GAA 17B | 10000000 |  |  | Ongoing | 0.35 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Capiz | 501439 | Sinamongan Integrated School | PILAR |  | 1 | 4 | 2UNITS 1STY2CL | GAA 17B | 10000000 |  | 9900000 | Completed | 1 | 2025-03-15 |  | P00875034VS |  | 2024-05-14 | 2024-05-21 | 2024-06-03 | 2024-09-10 | 2024-09-30 | BROOKLYN & CONNOR BUILDERS | DPWH to provide complete Data
NC 2024 |  | Region VI | Capiz | 302391 | Capiz National High School | ROXAS CITY (Capital) |  | 1 | 9 | 3STY9CL | GAA 17B | 15750000 |  |  | Not Yet Started | 0 | [10 empty] | Awaiting for concurence approval from CO.DPWH to provide complete Data
NC 2024 |  | Region VI | Capiz | 115461 | Concepcion H. Castro ES | DUMALAG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4964606.82 | Completed | 1 | 2024-09-23 | 2025-07-02 | 24GP0069 (REBID) | 24GP0069 | 2024-06-05 | 2024-05-14 | 2024-05-29 | 2024-06-28 | 2024-07-16 | 3 A'S & J CONSTRUCTION
NC 2024 |  | Region VI | Capiz | 501098 | Dr. Laureano R. Frial Integrated School | DUMALAG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4964606.82 | Completed | 1 | 2024-10-21 | 2025-01-15 | 24GP0070 (REBID) | 24GP0070 | 2024-06-06 | 2024-06-13 | 2024-06-27 | 2024-07-29 | 2024-08-13 | 3 A'S & J CONSTRUCTION
NC 2024 |  | Region VI | Capiz | 115457 | San Agustin ES | DUMALAG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969481.38 | Ongoing | 0.95 | 2024-11-24 |  | 24GP0071 (TWO-FAILED BIDDING) | 24GP0071 | 2024-07-23 | 2024-07-30 | 2024-08-13 | 2024-08-29 | 2024-09-11 | 7 JL HARDWARE & CONSTRUCTION SUPPLIES | substantially completed
NC 2024 |  | Region VI | Capiz | 115459 | San Martin ES | DUMALAG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4964606.82 | Ongoing | 0.95 | 2024-10-10 |  | 24GP0076 (REBID) | 24GP0076 | 2024-06-05 | 2024-05-14 | 2024-05-29 | 2024-06-28 | 2024-07-16 | 3 A'S & J CONSTRUCTION | substantially completed
NC 2024 |  | Region VI | Capiz |  | San Rafael ES | DUMALAG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4964606.82 | Completed | 1 | 2024-11-24 | 2024-12-18 | 24GP0068 (TWO-FAILED BIDDING) | 24GP0068 | 2024-07-23 | 2024-07-30 | 2024-08-13 | 2024-08-29 | 2024-09-11 | 3 A'S & J CONSTRUCTION
NC 2024 |  | Region VI | Capiz | 115464 | Sta. Rita ES | DUMALAG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4964606.82 | Completed | 1 | 2024-11-24 | 2025-01-15 | 24GP0075 (TWO-FAILED BIDDING) | 24GP0075 | 2024-07-28 | 2024-07-30 | 2024-08-13 | 2024-08-29 | 2024-09-11 | 3 A'S & J CONSTRUCTION
NC 2024 |  | Region VI | Capiz | 115465 | Sta. Teresa ES | DUMALAG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4964606.82 | Completed | 1 | 2024-11-24 | 2024-03-28 | 25GP0073 (TWO-FAILED BIDDING) | 25GP0073 | 2024-07-28 | 2024-07-30 | 2024-08-13 | 2024-08-29 | 2024-09-11 | 3 A'S & J CONSTRUCTION
NC 2024 |  | Region VI | Capiz | 115467 | Sto. Rosario ES (dumalag) | DUMALAG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4964606.82 | Completed | 1 | 2024-10-21 | 2025-01-15 | 24GP0074 (REBID) | 24GP0074 | 2024-06-06 | 2024-06-13 | 2024-06-27 | 2024-07-29 | 2024-08-13 | 3 A'S & J CONSTRUCTION
NC 2024 |  | Region VI | Capiz | 500429 | Aglalana Integrated School | DUMARAO |  | 1 | 4 | 2STY4CL | GAA 17B | 15750000 |  | 15568579.11 | Completed | 1 | 2024-12-03 | 2025-01-02 | 24GP0076 | 24GP0076 | 2024-03-26 | 2024-04-02 | 2024-04-17 | 2024-05-20 | 2024-06-07 | ST. SALCEDO CONSTRUCTION CORP
NC 2024 |  | Region VI | Capiz | 501083 | Aglanot Integrated School | DUMARAO |  | 1 | 4 | 2STY4CL | GAA 17B | 15750000 |  | 15530926.94 | Completed | 1 | 2025-01-11 | 2025-10-02 | 24GP0080 (REBID) | 24GP0080 | 2024-06-05 | 2024-05-14 | 2024-05-29 | 2024-06-28 | 2024-07-16 | 7JL HARDWARE AND CONSTRUCTION SUPPLIES
NC 2024 |  | Region VI | Escalante City | 117044 | Escalante Elementary School | CITY OF ESCALANTE |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4944631.7 | Ongoing | 0.4 | 2025-01-29 |  | P00875370VS-CW1 | 24GQ0074 | 2024-07-24 | 2024-07-17 | 2024-08-14 | 2024-09-13 | 2024-09-24 | RJY Construction
NC 2024 |  | Region VI | Escalante City | 325604 | Magsaysay National High School | CITY OF ESCALANTE |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4945385.35 | Ongoing | 0.9 | 2025-01-29 |  | P00875371VS-CW1 | 24GQ0076 | 2024-07-24 | 2024-07-17 | 2024-08-15 | 2024-09-14 | 2024-09-25 | RJY Construction
NC 2024 |  | Region VI | Escalante City | 302626 | Old Poblacion National High School | CITY OF ESCALANTE |  | 1 | 2 | Construction of School Building | BATCH 1 | 4652142 |  | 4599903.81 | Ongoing | 1 | 2025-01-29 | 2025-01-29 | P00875659VS-CW1 | 24GQ0081 | 2024-07-24 | 2024-07-17 | 2024-08-16 | 2024-09-15 | 2024-09-26 | RJY Construction
NC 2024 |  | Region VI | Guimaras | 302430 | East Valencia National High School | BUENAVISTA |  | 1 | 4 | 2STY4CL | GAA 17B | 15750000 |  | 15514440.95 | Completed | 1 | 2024-11-26 | 2024-11-26 | P00875284VS | 24GE0064 |  | 2024-03-15 | 2024-03-27 | 2024-03-05 | 2024-05-15 | ALJ CONSTRUCTION & SUPPLY
NC 2024 |  | Region VI | Guimaras | 115864 | Jordan Central School | JORDAN (Capital) |  | 1 | 10 | 2STY10CL | GAA 17B | 40000000 |  | 39696137.55 | Ongoing | 0.71 | 2025-06-28 |  | P00875282VS | 24GE0068 |  | 2024-03-20 | 2024-03-04 | 2024-04-06 | 2024-06-28 | J.E.TICO CONSTRUCTION CO.,INC.
NC 2024 |  | Region VI | Guimaras | 302432 | Jordan NHS | JORDAN (Capital) |  | 1 | 4 | 2STY4CL | GAA 17B | 15750000 |  | 15569367.56 | Completed | 1 | 2024-11-18 | 2024-11-18 | P00875283VS | 24GE0063 |  | 2024-03-15 | 2024-03-27 | 2024-04-25 | 2024-07-05 | ST SALCEDO CONSTRUCTION CORP.
NC 2024 |  | Region VI | Guimaras | 302434 | Nueva Valencia National High School | NUEVA VALENCIA |  | 1 | 4 | 2STY4CL | GAA 17B | 15750000 |  | 15570923.76 | Completed | 1 | 2024-11-18 | 2024-11-18 | P00875285VS | 24GE0065 |  | 2024-03-15 | 2024-03-27 | 2024-04-25 | 2024-07-05 | ST SALCEDO CONSTRUCTION CORP.
NC 2024 |  | Region VI | Guimaras | 302437 | Dr. Catalino G. Nava Memorial High School | SAN LORENZO |  | 1 | 4 | 2STY4CL | GAA 17B | 15750000 |  | 15600784.32 | Completed | 1 | 2024-12-15 | 2024-11-10 | P00875286VS | 24GE0067 |  | 2024-03-20 | 2024-03-04 | 2024-05-20 | 2024-05-31 | ST SALCEDO CONSTRUCTION CORP.
NC 2024 |  | Region VI | Guimaras | 115888 | Sabang ES | SIBUNAG |  | 1 | 4 | 2STY4CL | GAA 17B | 15750000 |  | 15567880.02 | Completed | 1 | 2024-12-19 | 2024-12-19 | P00875287VS | 24GE0066 |  | 2024-03-20 | 2024-01-04 | 2024-05-24 | 2024-07-06 | IBC INTERNATIONAL BUILDERS CORPORATION
NC 2024 |  | Region VI | Himamaylan City | 117072 | Cong. Eliseo P. Limsiaco Sr. MES | CITY OF HIMAMAYLAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4964992.49 | Completed | 1 |  | 2025-02-28 | 24GL0119 | 24GL0119 |  |  | 2024-04-29 |  | 2024-05-23 | NOVANNE VENTURES CONSTRUCTION CORPORATION | 2 MONTHS DELAYED AS PER CONTRACT. DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 180037 | Atty. Blas & Maria Gerona ES | GUIMBAL |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4959916.54 | Completed | 1 | 2024-08-26 | 2024-08-26 | P00875339VS-CW1 | 24GF0125 | 2024-03-28 | 2024-04-04 | 2024-04-16 | 2024-04-24 | 2024-07-05 | DEACONS TEMPLE CONSTRUCTION & SUPPLY
NC 2024 |  | Region VI | Iloilo | 116360 | Guimbal Central Elementary School | GUIMBAL |  | 1 |  | Construction of School Building | GAA 17B | 48000000 |  | 47622728.77 | Ongoing | 0.6003 | 2025-07-19 |  | P00875290VS-CW1 | 24GF0145 | 2024-03-08 | 2024-12-08 | 2024-08-27 | 2024-04-09 | 2024-09-17 | ASDC 88 BUILDERS CORPORATION
NC 2024 |  | Region VI | Iloilo | 302506 | Guimbal NHS | GUIMBAL |  | 1 |  | Construction of School Building | GAA 17B | 48000000 |  | 47657800.23 | Ongoing | 0.4793 | 2025-12-08 |  | P00875289VS-CW1 | 24GF0147 | 2024-12-08 | 2024-08-19 | 2024-05-09 | 2024-09-13 | 2024-09-25 | ASDC 88 BUILDERS CORPORATION
NC 2024 |  | Region VI | Iloilo | 302536 | Nalundan NHS | GUIMBAL |  | 1 | 12 | 4STY12CL | GAA 17B | 40000000 |  | 39632616.67 | Completed | 1 | 2025-01-26 |  | P00875288VS-CW1 | 24GF0129 | 2024-04-18 | 2024-04-26 | 2024-08-05 | 2024-05-15 | 2024-05-30 | ASIA STRUCTURAL DEVELOPER CORPORATION
NC 2024 |  | Region VI | Iloilo | 501442 | Nanga Integrated School | GUIMBAL |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4959496.54 | Completed | 1 | 2024-08-26 | 2024-08-26 | P00875340VS-CW1 | 24GF0126 | 2024-03-28 | 2024-04-04 | 2024-04-16 | 2024-04-24 | 2024-07-05 | DEACONS TEMPLE CONSTRUCTION & SUPPLY
NC 2024 |  | Region VI | Iloilo | 116375 | Igbaras CES | IGBARAS |  | 1 |  | Construction of School Building | GAA 17B | 48000000 |  | 47757844.37 | Ongoing | 0.4526 | 2025-07-13 |  | P00875297VS-CW1 | 24GF0136 | 2024-04-06 | 2024-11-06 | 2024-06-24 | 2024-02-07 | 2024-07-15 | ASDC 88 BUILDERS CORPORATION
NC 2024 |  | Region VI | Iloilo |  | Iloilo Science & Technology University - Miagao Campus | MIAGAO |  | 1 |  | Construction of School Building | GAA 17B | 48370000 |  | 48037987.99 | Not Yet Started | 0 | 2025-06-22 |  | P00875298VS-CW1 | 24GF0146 | 2024-12-08 | 2024-08-19 | 2024-02-09 | 2024-10-09 | 2024-09-24 | ASDC 88 BUILDERS CORPORATION | Project is still suspended as of to date due to changes in approved plans/designs
NC 2024 |  | Region VI | Iloilo | 302531 | Miagao NHS | MIAGAO |  | 1 |  | Construction of School Building | GAA 17B | 68000000 |  | 67529608.72 | Ongoing | 0.5494 | 2025-03-30 |  | P00875291VS-CW1 | 24GF0141 | 2024-05-07 | 2024-12-07 | 2024-07-25 | 2024-07-30 | 2024-08-13 | ASDC 88 BUILDERS CORPORATION | Project is still suspended
NC 2024 |  | Region VI | Iloilo | 302476 | Batuan-Cadinglian NHS | OTON |  | 1 | 4 | 2STY4CL | BATCH 1 | 11600000 |  | 11531173.32 | Ongoing | 0.9939 | 2025-02-02 |  | P00875660VS-CW1 | 24GF0134 | 2024-05-17 | 2024-05-27 | 2024-10-06 | 2024-06-18 | 2024-02-07 | CONTE BUILDERS & CONSTRUCTION SUPPLY | due to obstruction of
NC 2024 |  | Region VI | Iloilo | 116626 | Oton CES | OTON |  | 1 |  | Construction of School Building | GAA 17B | 38000000 |  | 37698600.45 | Ongoing | 0.6062 | 2025-05-29 |  | P00875293VS-CW1 | 24GF0139 | 2024-06-28 | 2024-05-07 | 2024-07-17 | 2024-08-13 | 2024-08-27 | ASDC 88 BUILDERS CORPORATION | residential structure within
NC 2024 |  | Region VI | Iloilo | 302542 | Oton National High School | OTON |  | 1 |  | Construction of School Building | GAA 17B | 58000000 |  | 57581104.53 | Ongoing | 0.5598 | 2025-11-05 |  | P00875292VS-CW1 | 24GF0140 | 2024-05-07 | 2024-12-07 | 2024-07-31 | 2024-08-08 | 2024-08-20 | ASDC 88 BUILDERS CORPORATION | project boundary
NC 2024 |  | Region VI | Iloilo | 116629 | San Antonio-San Nicolas ES | OTON |  | 1 |  | Construction of School Building | GAA 17B | 48000000 |  | 47659200.25 | Ongoing | 0.5752 | 2025-05-14 |  | P00875295VS-CW1 | 24GF0148 | 2024-12-08 | 2024-08-19 | 2024-05-09 | 2024-09-13 | 2024-09-25 | CONTE BUILDERS & CONSTRUCTION SUPPLY
NC 2024 |  | Region VI | Iloilo | 302578 | Tigbauan NHS | TIGBAUAN |  | 1 |  | Construction of School Building | GAA 17B | 48000000 |  | 47581410.08 | Ongoing | 0.5315 | 2025-03-23 |  | P00875294VS-CW1 | 24GF0143 | 2024-05-07 | 2024-12-07 | 2024-07-25 | 2024-07-30 | 2024-08-13 | ASDC 88 BUILDERS CORPORATION
NC 2024 |  | Region VI | Iloilo | 116843 | Cadabdab ES | TUBUNGAN |  | 1 |  | Construction of School Building | GAA 17B | 48000000 |  | 47646646.58 | Ongoing | 0.6458 | 2025-09-06 |  | P00875296VS-CW1 | 24GF0142 | 2024-05-07 | 2024-12-07 | 2024-07-25 | 2024-07-30 | 2024-08-13 | ASDC 88 BUILDERS CORPORATION
NC 2024 |  | Region VI | Iloilo | 115948 | Bagsakan PS | ALIMODIAN |  | 1 | 4 | 2STY4CL | GAA 17B | 16500000 |  |  | Not Yet Started | 0 | [10 empty] | The project is currently suspended due to revision
NC 2024 |  | Region VI | Iloilo |  | Felimon Alfeche National High School | ALIMODIAN |  | 1 | 4 | 2STY4CL | GAA 17B | 15750000 |  |  | Not Yet Started | 0 | [10 empty] | of plans.
NC 2024 |  | Region VI | Iloilo | 115961 | Laylayan PS | ALIMODIAN |  | 1 | 4 | 1STY4CL | GAA 17B | 15500000 |  |  | Not Yet Started | 0
NC 2024 |  | Region VI | Iloilo | 302446 | Quinaspan NHS- Alimodian NCHS | ALIMODIAN |  | 1 | 8 | 2STY8CL | BATCH 1 | 28500000 |  |  | Not Yet Started | 0
NC 2024 |  | Region VI | Iloilo | 302520 | Leganes National High School | LEGANES |  | 1 | 4 | 2STY4CL | GAA 17B | 15750000 |  |  | Not Yet Started | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116509 | Leon Central Elementary School | LEON |  | 1 | 4 | 2STY4CL | GAA 17B | 15750000 |  |  | Not Yet Started | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 302550 | Pavia National High School | PAVIA |  | 1 | 6 | 3STY6CL | GAA 17B | 23500000 |  |  | Not Yet Started | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 302550 | Pavia National High School | PAVIA |  |  | 20 | 4STY20CL | GAA 17B | 76750000 |  |  | Not Yet Started | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 302475 | Cadagmayan NHS | SANTA BARBARA |  | 1 | 6 | 2STY6CL | BATCH 2 | 21000000 |  |  | Ongoing | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116812 | Payao ES | SANTA BARBARA |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  |  | Not Yet Started | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 302573 | Santa Barbara National Comprehensive High School | SANTA BARBARA |  | 1 | 4 | 2STY4CL (PHASE I) | GAA 17B | 16500000 |  |  | Not Yet Started | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 302573 | Santa Barbara National Comprehensive High School | SANTA BARBARA |  |  | 4 | 2STY4CL (PHASE II) | GAA 17B | 15750000 |  |  | Not Yet Started | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116813 | Sta. Barbara CES | SANTA BARBARA |  | 1 | 4 | 2STY4CL | GAA 17B | 15750000 |  |  | Not Yet Started | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116119 | Cabatuan CES | CABATUAN |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  | 8926685.01 | Ongoing | 0.899 | 2024-12-27 |  |  | 24GG0254 | 2024-05-14 | 2024-05-21 | 2024-04-06 | 2024-06-28 |  | EL DOLLIARES CONSTRUCTION, INC. | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116119 | Cabatuan CES | CABATUAN |  |  | 4 | 2STY4CL | GAA 17B | 15750000 |  | 15600867.8 | Ongoing | 0.5801 | 2024-03-12 |  |  | 24GG0256 | 2024-05-14 | 2024-05-21 | 2024-04-06 | 2024-06-27 |  | MDG CONSTRUCTION | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 302444 | Alcarde Gustilo Mem. National High School | CALINOG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4655763.85 | Completed | 1 | 2024-09-27 | 2024-10-25 |  | 24GG0216 | 2024-02-29 | 2024-07-03 | 2024-03-25 | 2024-05-15 |  | SKF BUILDERS AND SUPPLIES CORP. | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 302481 | CARVASANA NHS | CALINOG |  | 1 | 4 | 2STY4CL | GAA 17B | 15750000 |  | 15601038.2 | Completed | 1 | 2024-03-12 | 2024-09-24 |  | 24GG0257 | 2024-05-14 | 2024-05-21 | 2024-04-06 | 2024-06-27 |  | E.G. GARCIA CONSTRUCTION AND SUPPLY | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 302501 | Esteban S. Javellana MHS | CALINOG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4855000.01 | Completed | 1 | 2024-08-28 | 2025-01-23 |  | 24GG0206 | 2024-02-29 | 2024-07-03 | 2024-03-25 | 2024-04-19 |  | OTING CONSTRUCTION AND SUPPLY | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 302512 | Janiuay NCHS | JANIUAY |  | 1 | 4 | 2STY4CL | GAA 17B | 15750000 |  | 15644514.21 | Ongoing | 0.6133 | 2024-03-12 |  |  | 24GG0259 | 2024-05-14 | 2024-05-21 | 2024-04-06 | 2024-06-27 |  | OTING CONSTRUCTION AND SUPPLY | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116412 | Jibolo Elementary School | JANIUAY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4955540.43 | Completed | 1 | 2024-08-28 | 2024-09-24 |  | 24GG0214 | 2024-02-29 | 2024-07-03 | 2024-03-25 | 2024-04-19 |  | SKF BUILDERS AND SUPPLIES CORP. | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116395 | Juan C. Locsin MS | JANIUAY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4955540.53 | Completed | 1 | 2024-01-09 | 2024-09-24 |  | 24GG0215 | 2024-02-29 | 2024-07-03 | 2024-03-25 | 2024-04-22 |  | SKF BUILDERS AND SUPPLIES CORP. | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 501249 | Bagongbong Integrated School | LAMBUNAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4945000 | Completed | 1 | 2024-08-28 | 2024-03-10 |  | 24GG0205 | 2024-02-29 | 2024-07-03 | 2024-03-25 | 2024-04-19 |  | OTING CONSTRUCTION AND SUPPLY | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 137022 | Lorlina Solinap Navarra Elementary School | LAMBUNAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4924535.95 | Completed | 1 | 2024-01-09 | 2024-10-25 |  | 24GG0202 | 2024-02-29 | 2024-07-03 | 2024-03-25 | 2024-04-22 |  | PO SUPLICO CONSTRUCTION CORP. | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116464 | Panuran ES | LAMBUNAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4825727.39 | Completed | 1 | 2024-09-01 | 2024-02-28 |  | 24GG0207 | 2024-02-29 | 2024-07-03 | 2024-03-25 | 2024-04-22 |  | ARCEÑO CONSTRUCTION SUPPLIES | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116464 | Panuran ES | LAMBUNAO |  |  | 4 | 2STY4CL | GAA 17B | 15750000 |  | 15571249.13 | Ongoing | 0.7503 | 2024-10-12 |  |  | 24GG0255 | 2024-05-14 | 2024-05-21 | 2024-04-06 | 2024-06-27 |  | EZ GOLD CONSTRUCTION & SUPPLY | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 302572 | Siwalo NHS | MAASIN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4955540.58 | Completed | 1 | 2024-08-28 | 2024-09-24 |  | 24GG0217 | 2024-02-29 | 2024-07-03 | 2024-03-25 | 2024-04-19 |  | SKF BUILDERS AND SUPPLIES CORP. | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116600 | Dala-Singay Elementary School | MINA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4445319.25 | Completed | 1 | 2024-09-15 | 2024-12-14 |  | 24GG0203 | 2024-02-29 | 2024-07-03 | 2024-03-25 | 2024-09-05 |  | R. SEMILLA CONSTRUCTION AND MARKETING, INCORPORATED | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 137024 | Yugot Elementary School | MINA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4454281.3 | Completed | 1 | 2024-04-09 |  |  | 24GG0204 | 2024-02-29 | 2024-07-03 | 2024-03-25 | 2024-04-26 |  | QUATRO AMIGOS BUILDERS & SUPPLY | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 302449 | Anilao NHS | ANILAO |  | 1 | 4 | 2STY4CL | GAA 17B | 15750000 |  | 15621368.1 | Ongoing | 0.7541 | 2024-03-12 |  |  | 24GG0258 | 2024-05-14 | 2024-05-21 | 2024-04-06 | 2024-06-27 |  | PAG BUILDERS | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 180046 | Santiago Arandilla MS | ANILAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4944997.01 | Completed | 1 | 2024-06-09 | 2024-04-10 |  | 24GG0213 | 2024-02-29 | 2024-07-03 | 2024-03-25 | 2024-04-26 |  | PAG BUILDERS | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116049 | Lanas Elementary | BAROTAC NUEVO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4955000 | Completed | 1 | 2024-08-28 | 2024-08-28 |  | 24GG0211 | 2024-02-29 | 2024-07-03 | 2024-03-25 | 2024-04-19 |  | DG SALAS CONSTRUCTION SERVICES | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116058 | Tabucan Elementary School | BAROTAC NUEVO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4944942.56 | Completed | 1 | 2024-09-15 | 2024-09-24 |  | 24GG0219 | 2024-02-29 | 2024-07-03 | 2024-03-25 | 2024-04-26 |  | JMPTECH CONSTRUCTION & SUPPLY | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116062 | Tubungan PS | BAROTAC NUEVO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4955000 | Completed | 1 | 2024-09-01 | 2024-12-12 |  | 24GG0210 | 2024-02-29 | 2024-07-03 | 2024-03-25 | 2024-04-22 |  | DG SALAS CONSTRUCTION SERVICES | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116315 | Bacay ES | DUMANGAS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4949611.39 | Completed | 1 | 2024-09-15 | 2024-08-21 |  | 24GG0218 | 2024-02-29 | 2024-07-03 | 2024-03-25 | 2024-09-05 |  | EL PRADO BUILDERS | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116323 | Dumangas CES | DUMANGAS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4583094.77 | Completed | 1 | 2024-04-10 | 2024-04-10 |  | 24GG0209 | 2024-02-29 | 2024-07-03 | 2024-03-25 | 2024-09-05 |  | EL PRADO BUILDERS | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116339 | Nanding Lopez ES | DUMANGAS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4964000.01 | Completed | 1 | 2024-08-28 | 2024-10-15 |  | 24GG0208 | 2024-02-29 | 2024-07-03 | 2024-03-25 | 2024-04-19 |  | J.C. ALBASON BUILDERS AND SUPPLY | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 302491 | Dominador Abang MNHS | SAN ENRIQUE |  | 1 | 4 | 2STY4CL | GAA 17B | 15750000 |  | 15621249.98 | Ongoing | 0.8957 | 2024-10-15 |  |  | 24GG0220 | 2024-02-29 | 2024-07-03 | 2024-03-25 | 2024-04-26 |  | 1 BEATUS BUILDERS CORPORATION | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 501481 | Adcadarao Integrated School | AJUY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 302443 | Ajuy NHS | AJUY |  | 1 | 4 | 2STY4CL | GAA 17B | 15750000 |  |  | Not Yet Started | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116090 | Alapasco Primary School | BATAD |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 501493 | Binuluangan Integrated School | CARLES |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116481 | Alcantara PS | LEMERY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 180031 | Dalipe Prim. School | LEMERY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116492 | Jose Almiñana MES | LEMERY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116495 | Omio ES | LEMERY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116675 | Amayong PS | SAN DIONISIO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116677 | Batuan PS | SAN DIONISIO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 116779 | Ireneo Engle Sr. MES | SARA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo | 302509 | Iloilo NHS | ILOILO CITY (Capital) |  | 1 | 12 | 4STY12CL | GAA 17B | 46800000 |  |  | Not Yet Started | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo City | 117580 | Arevalo ES | ILOILO CITY (Capital) |  | 1 | 6 | 3STY6CL | GAA 17B | 23500000 |  | 22564148.02 | Ongoing | 0.4 | 2025-01-04 |  | 24GJ0081 |  | 2025-03-19 | 2025-03-26 | 2025-11-04 | 2025-05-23 | 2025-07-06 | Lucky H & K Construction | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo City | 302743 | Bo. Obrero NHS | ILOILO CITY (Capital) |  | 1 | 6 | 3STY6CL | GAA 17B | 20000000 |  |  | Not Yet Started | 0 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo City | 302737 | Fort San Pedro National High School | ILOILO CITY (Capital) |  | 1 | 8 | 4STY8CL | GAA 17B | 31500000 |  | 31295562.46 | Ongoing | 0.55 | 2025-01-02 |  | 24GJ0083 |  | 2025-03-19 | 2025-03-26 | 2025-11-04 | 2025-09-05 | 2025-05-17 | Champion Builders & Supply | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo City | 117615 | Hibao-an ES | ILOILO CITY (Capital) |  | 1 | 6 | 3STY6CL | GAA 17B | 20000000 |  | 19880000 | Completed | 1 | 2025-01-03 | 2025-07-05 | 24GJ0087 |  | 2025-03-20 | 2025-03-27 | 2025-11-04 | 2025-05-23 | 2025-07-06 | El Prado Builders | DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo City | 117615 | Hibao-an ES | ILOILO CITY (Capital) |  | 1 | 6 | 3STY6CL | GAA 17B | 23500000 |  | 22797937.46 | Ongoing | 0.95 | 2024-01-03 |  | 24GJ0084 |  | 2025-05-19 | 2025-05-26 | 2025-11-04 | 2025-05-23 | 2025-07-06 | Pesom Construction Services | WITH SUSPENSION ORDER. DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo City | 117588 | Iloilo Central ES | ILOILO CITY (Capital) |  | 1 | 6 | 3STY6CL | GAA 17B | 23500000 |  | 22681185.34 | Ongoing | 0.5 | 2025-01-01 |  | 24GJ0091 |  | 2025-05-19 | 2025-05-26 | 2025-11-04 | 2025-05-23 | 2025-07-06 | Noe's Builders | SHORT OF AWARD WAITING FOR SARO. DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo City | 302738 | Iloilo City NHS | ILOILO CITY (Capital) |  | 1 | 8 | 4STY8CL | GAA 17B | 31500000 |  | 30402215.17 | Ongoing | 0.6 | 2025-01-02 |  | 24GJ0089 |  | 2025-05-20 | 2025-05-27 | 2025-11-04 | 2025-09-05 | 2025-05-17 | Noe's Builders | WITH SUSPENSION ORDER. DPWH to provide complete Data
NC 2024 |  | Region VI | Iloilo City | 117617 | Mandurriao Elementary School | ILOILO CITY (Capital) |  | 1 | 6 | 3STY6CL | GAA 17B | 23500000 |  | 23082499.95 | Ongoing | 0.55 | 2025-01-01 |  | 24GJ0085 |  | 2025-03-19 | 2025-05-26 | 2025-11-04 | 2025-09-05 | 2025-05-17 | 5's Const. & Supply | Completed
NC 2024 |  | Region VI | Iloilo City | 137020 | Uswag San Isidro Elementary School | ILOILO CITY (Capital) |  | 1 | 6 | 3STY6CL | GAA 17B | 23500000 |  | 22984648.28 | Ongoing | 0.7 | 2025-01-03 |  | 24GJ0090 |  | 2025-03-19 | 2025-05-26 | 2025-11-04 | 2025-05-29 | 2025-07-06 | RBJR Const. | WITH SUSPENSION ORDER. DPWH to provide complete Data
NC 2024 |  | Region VI | Kabankalan City | 302789 | Kabankalan National High School | CITY OF KABANKALAN |  | 1 | 4 | 2STY4CL | GAA 17B | 20000000 |  |  | Not Yet Started | 0 | [10 empty] | WITH SUSPENSION ORDER. DPWH to provide complete Data
NC 2024 |  | Region VI | La Carlota City | 117634 | Caiñaman ES | LA CARLOTA CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 |  | 2024-08-20 |  | 24GH0093 | 2024-03-19 |  | 2024-08-04 | 2024-04-18 | 2024-07-05 | LJJR FIRE PROTECTION SERVICES | Completed. DPWH to provide complete Data
NC 2024 |  | Region VI | La Carlota City | 117638 | Cubay ES | LA CARLOTA CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 |  | 2024-02-09 |  | 24GH0085 | 2024-03-14 |  | 2024-02-04 | 2024-04-19 | 2024-07-05 | SBK CONSTRUCTION AND SERVICES INC. | Completed. DPWH to provide complete Data
NC 2024 |  | Region VI | La Carlota City | 117650 | San Miguel ES II | LA CARLOTA CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 |  | 2024-09-20 |  | 24GH0091 | 2024-03-19 |  | 2024-08-04 | 2024-04-19 | 2024-07-05 | EMR Builder | Completed. DPWH to provide complete Data
NC 2024 |  | Region VI | Passi City | 312203 | Agdahon Farm School | CITY OF PASSI |  | 1 | 6 | 2STY6CL | BATCH 1 | 16000000 |  |  | Ongoing | 0.46 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Passi City | 117908 | Passi I Central School | CITY OF PASSI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | Completed. DPWH to provide complete Data
NC 2024 |  | Region VI | Passi City | 117908 | Passi I Central School | CITY OF PASSI |  |  | 8 | 2STY8CL | GAA 17B | 31500000 |  |  | Ongoing | 0.73 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | Region VI | Roxas City | 117654 | Culasi ES | ROXAS CITY (Capital) |  | 1 | 4 | 2STY4CL | GAA 17B | 15750000 |  | 15499162.8 | Completed | 1 | 2025-11-02 | 2025-11-05 | P00875276VS-CW1 | 24GD0057 | 2024-05-31 | 2024-07-06 | 2024-06-20 | 2024-07-29 | 2024-08-22 | MEGAGOLD CONST.&DEVT., OPC | with approved time extension.
NC 2024 |  | Region VI | Roxas City | 302758 | Culasi NHS | ROXAS CITY (Capital) |  | 1 | 4 | 2STY4CL | GAA 17B | 15750000 |  | 15435664.91 | Completed | 1 | 2025-11-02 | 2025-11-05 | P00875277VS-CW1 | 24GD0058 | 2024-05-31 | 2024-07-06 | 2024-06-20 | 2024-07-29 | 2024-08-22 | SALMEGA BUILDERS | with approved time extension
NC 2024 |  | Region VI | Sagay City | 117695 | Buenaventura Rodriguez Elementary School | SAGAY CITY |  | 1 | 6 | 2STY6CL | GAA 17B | 18000000 |  | 17680890 | Ongoing | 0.75 | 2024-05-12 |  | 24GK0216 | 24GK0216 | 2024-05-29 | 2024-04-06 | 2024-06-18 | 2024-12-07 | 2024-07-18 | KENBE CONSTRUCTION & SUPPLY | Ongoing
NC 2024 |  | Region VI | San Carlos City | 302774 | Don Carlos Ledesma NHS | SAN CARLOS CITY |  | 1 | 12 | Construction of School Building | BATCH 1 | 30705000 |  | 30244039.3 | Ongoing | 0.15 | 2025-06-21 | [8 empty] | Kennith Construction | DPWH to provide complete Data
NC 2024 |  | Region VI | San Carlos City | 117760 | Guadalupe ES | SAN CARLOS CITY |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  | 9800750 | Ongoing | 0.4 | 2025-04-15 |  |  |  |  | 2024-08-28 | 2024-11-09 |  |  | IDMU Construction | DPWH to provide complete Data
NC 2024 |  | Region VI | Silay City | 185001 | Dominador 'Oking' Jison Memorial Elementary School | SILAY CITY |  | 1 | 8 | 4STY8CL | BATCH 1 | 36248000 |  | 35696291.09 | Ongoing | 0.3 |  |  | 24GK0210 |  |  | 2024-04-06 | 2024-06-18 | 2024-12-07 | 2024-07-18 | SILVERGRACES CONSTRUCTION & CONSTRUCTION SUPPLY | DPWH to provide complete Data
NC 2024 |  | Region VI | Silay City | 500199 | Don Albino & Doña Dolores Jison Integrated School | SILAY CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4875489.89 | Completed | 1 |  |  | 24GK0211 |  |  | 2024-04-06 | 2024-06-18 | 2024-12-07 | 2024-07-18 | KENBE CONSTRUCTION & SUPPLY | DPWH to provide complete Data
NC 2024 |  | Region VI | Sipalay City | 302640 | Gil Montilla NHS - Manlucahoc Ext. | CITY OF SIPALAY |  | 1 | 4 | 2STY4CL | BATCH 1 | 14100000 |  | 14064750 | Completed | 1 | 2024-05-08 | 2024-11-25 | P00875400VS-CW1 | 24GM0065 | 2024-03-06 | 2024-11-06 | 2024-06-24 | 2024-07-16 | 2024-07-29 | GC ANDS CONSTRUCTION AND SUPPLY
NC 2024 |  | Region VI | Sipalay City | 180522 | Omas ES | CITY OF SIPALAY |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  | 9975000 | Completed | 1 | 2024-04-02 | 2024-04-02 | P00875667VS-CW1 | 24GM0069 | 2024-10-07 | 2024-07-18 | 2024-07-30 | 2024-08-14 | 2024-08-29 | NOVANNE VENTURES CONST. CORP.

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.