## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of Sites Terminated | No. of CL Terminated | Status as of July 11, 2025
REPAIR 2020 | Region VI | Aklan | 500543 | Balete Integrated School | BALETE | 0 | 1 | 16 | Repair of Classrooms | 8100000 | 1 | 8100000 | COMPLETED | 1 | 2021-04-20 | 2021-05-27 | DepED-RO6-D1-2020BEFFREPAIR-C5-119-2019 | DepED-RO6-D1-2020BEFFREPAIR-C5-119-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | FIRST MAKEEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 114682 | Bay-ang Elementary School | BATAN | 0 | 1 | 2 | Repair of Classrooms | 1100000 | 1 | 1100000 | COMPLETED | 1 | 2021-02-09 | 2021-02-05 | DepED-RO6-D1-2020BEFFREPAIR-C8-122-2019 | DepED-RO6-D1-2020BEFFREPAIR-C8-122-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | SOLID MERCHNDISING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 302300 | Camaligan NHS | BATAN | 0 | 1 | 14 | Repair of Classroom | 5548400 | 1 | 5544942.25 | COMPLETED | 1 | 2021-04-25 | 2021-07-30 | DepED-RO6-D1-2020BEFFREPAIR-C4-118-2019 | DepED-RO6-D1-2020BEFFREPAIR-C4-118-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 114702 | Bel-is ES | BURUANGA | 0 | 1 | 3 | Repair of Classrooms | 1380283 | 1 | 1380282.63 | COMPLETED | 1 | 2021-03-26 | 2021-03-19 | DepED-RO6-D1-2020BEFFREPAIR-C6-120-2019 | DepED-RO6-D1-2020BEFFREPAIR-C6-120-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 114732 | Buenavista PS | IBAJAY | 0 | 1 | 2 | Repair of Classrooms | 1124398 | 1 | 1124397.6 | COMPLETED | 1 | 2021-03-26 | 2021-03-19 | DepED-RO6-D1-2020BEFFREPAIR-C6-120-2019 | DepED-RO6-D1-2020BEFFREPAIR-C6-120-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 114720 | Laguinbanwa ES | IBAJAY | 0 | 1 | 1 | Repair of Classroom | 867600 | 1 | 867057.75 | COMPLETED | 1 | 2021-04-25 | 2021-10-05 | DepED-RO6-D1-2020BEFFREPAIR-C4-118-2019 | DepED-RO6-D1-2020BEFFREPAIR-C4-118-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 500179 | Kalibo Integrated Special Education Center | KALIBO (Capital) | 0 | 1 | 10 | Repair of Classrooms | 4138369 | 1 | 4138369 | COMPLETED | 1 | 2021-02-09 | 2021-02-05 | DepED-RO6-D1-2020BEFFREPAIR-C8-122-2019 | DepED-RO6-D1-2020BEFFREPAIR-C8-122-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | SOLID MERCHNDISING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 114768 | Tayhawan Elementary School | LEZO | 0 | 1 | 2 | Repair of Classrooms | 1277929 | 1 | 1277928.98 | COMPLETED | 1 | 2021-03-26 | 2021-03-30 | DepED-RO6-D1-2020BEFFREPAIR-C6-120-2019 | DepED-RO6-D1-2020BEFFREPAIR-C6-120-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 114791 | Maytaraw PS | LIBACAO | 0 | 1 | 3 | Repair of Classrooms | 4307099 | 1 | 4307098.55 | COMPLETED | 1 | 2021-06-09 |  | DepED-RO6-D1-2020BEFFREPAIR-C1-115-2019 | DepED-RO6-D1-2020BEFFREPAIR-C1-115-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | BENZEN CONSTRUCTION | Last Mile School; The project is on-going but with slow accomplishment | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 114792 | Ogsip PS | LIBACAO | 0 | 1 | 1 | Repair of Classroom | 605000 | 1 | 605000 | COMPLETED | 1 | 2021-02-09 | 2021-02-05 | DepED-RO6-D1-2020BEFFREPAIR-C8-122-2019 | DepED-RO6-D1-2020BEFFREPAIR-C8-122-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | SOLID MERCHNDISING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 114800 | Taroytoy Primary School | LIBACAO | 0 | 1 | 4 | Repair of Classrooms | 2890128 | 1 | 2890127.37 | COMPLETED | 1 | 2021-11-25 | 2022-06-22 | DepED-RO6-D1-2020BEFFREPAIR-C2-116-2019 | DepED-RO6-D1-2020BEFFREPAIR-C2-116-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 114816 | Madalag ES | MADALAG | 0 | 1 | 4 | Repair of Classrooms | 2043391 | 1 | 2043390.79 | COMPLETED | 1 | 2021-03-26 | 2021-05-28 | DepED-RO6-D1-2020BEFFREPAIR-C6-120-2019 | DepED-RO6-D1-2020BEFFREPAIR-C6-120-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 302315 | Madalag NHS | MADALAG | 0 | 1 | 16 | Repair of Classrooms | 7561873 | 1 | 7561872.63 | COMPLETED | 1 | 2021-11-25 | 2022-06-22 | DepED-RO6-D1-2020BEFFREPAIR-C2-116-2019 | DepED-RO6-D1-2020BEFFREPAIR-C2-116-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 114864 | Lilo-an Elementary School | MALINAO | 0 | 1 | 5 | Repair of Classrooms | 2521003 | 1 | 2129225.57 | COMPLETED | 1 | 2021-04-08 | 2021-09-20 | DepED-RO6-D1-2020BEFFREPAIR-C7-121-2019 | DepED-RO6-D1-2020BEFFREPAIR-C7-121-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | CULASI GENERAL MERCHANDISING AND COSNTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 114936 | Tangalan ES | TANGALAN | 0 | 1 | 13 | Repair of Classrooms | 6365102 | 1 | 6365101.45 | COMPLETED | 1 | 2021-06-09 | 2022-01-10 | DepED-RO6-D1-2020BEFFREPAIR-C1-115-2019 | DepED-RO6-D1-2020BEFFREPAIR-C1-115-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 302336 | Tangalan National High School | TANGALAN | 0 | 1 | 8 | Repair of Classrooms | 3571719 | 1 | 3018495.53 | COMPLETED | 1 | 2021-04-08 | 2021-03-08 | DepED-RO6-D1-2020BEFFREPAIR-C7-121-2019 | DepED-RO6-D1-2020BEFFREPAIR-C7-121-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | CULASI GENERAL MERCHANDISING AND COSNTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 114658 | Bacan Elementary School | BANGA | 1 | 1 | 11 | Repair of Classrooms | 4912801 | 1 | 3479184.25 | COMPLETED | 1 | 2021-06-04 | 2021-06-10 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C1-086-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C1-086-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | LEGACY CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 302289 | Bacan National High School | BANGA | 1 | 1 | 11 | Repair of Classrooms | 4127044 | 1 | 2883553.52 | COMPLETED | 1 | 2021-06-04 | 2021-08-06 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C2-087-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C2-087-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | LEGACY CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 114660 | Banga ES | BANGA | 1 | 1 | 3 | Repair of Classrooms | 1456427 | 1 | 1063569.91 | COMPLETED | 1 | 2021-05-11 | 2021-07-30 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C11-096-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C11-096-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 302324 | Aklan NHS for Arts & Trades | KALIBO (Capital) | 1 | 1 | 4 | Repair of Classrooms | 1958234 | 1 | 1936838.36 | COMPLETED | 1 | 2021-05-11 | 2021-10-26 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C7-092-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C7-092-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 114755 | Estancia ES | KALIBO (Capital) | 1 | 1 | 6 | Repair of Classrooms | 2712717 | 1 | 2684061.64 | COMPLETED | 1 | 2021-05-11 | 2021-08-24 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C7-092-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C7-092-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 114756 | Kalibo I ES | KALIBO (Capital) | 1 | 1 | 3 | Repair of Classrooms | 1440784 | 1 | 755708.14 | COMPLETED | 1 | 2021-06-04 | 2021-09-09 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C6-091-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C6-091-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | LEGACY CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 114750 | Kalibo Pilot Elementary School | KALIBO (Capital) | 1 | 1 | 13 | Repair of Classrooms | 5935839 | 1 | 4501000 | COMPLETED | 1 | 2021-05-11 | 2021-08-06 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C3-088-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C3-088-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 302332 | Regional Science High School for Region VI | KALIBO (Capital) | 1 | 1 | 6 | Repair of Classrooms | 2208673 | 1 | 1935844.79 | COMPLETED | 1 | 2021-06-04 | 2021-06-10 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C6-091-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C6-091-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | LEGACY CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 114761 | Tigayon Elementary School | KALIBO (Capital) | 1 | 1 | 2 | Repair of Classrooms | 867016 | 1 | 1262252.98 | COMPLETED | 1 | 2021-06-05 | 2021-06-10 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C6-091-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C6-091-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | LEGACY CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 500172 | Makato Integrated School | MAKATO | 2 | 1 | 17 | Repair of Classrooms | 8142047 | 1 | 5283061.61 | COMPLETED | 1 | 2021-05-11 | 2021-05-10 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C5-090-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C5-090-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | GMO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 114866 | Malinao ES | MALINAO | 2 | 1 | 11 | Repair of Classrooms | 4509313 | 1 | 3479184.25 | COMPLETED | 1 | 2021-05-11 | 2021-04-30 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C9-094-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C9-094-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | LEGACY CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 302319 | Malinao Sch. For Phil. Craftsmen | MALINAO | 2 | 1 | 16 | Repair of Classrooms | 6322220 | 1 | 3479184.25 | COMPLETED | 1 | 2021-05-11 |  | DepED-RO6-D1-2020BEFFREPAIRBATCH2-C1-089-2020 | DepED-RO6-D1-2020BEFFREPAIRBATCH2-C1-089-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | LEGACY CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 114917 | Bulwang ES | NUMANCIA | 2 | 1 | 3 | Repair of Classrooms | 1735369 | 1 | 1267439.44 | COMPLETED | 1 | 2021-05-11 | 2021-07-29 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C11-096-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C11-096-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 114920 | Dongon ES | NUMANCIA | 2 | 1 | 11 | Repair of Classrooms | 4499768 | 1 | 3143162.58 | COMPLETED | 1 | 2021-05-11 | 2021-04-30 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C10-095-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C10-095-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | GMO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 114921 | Laguinbanua ES | NUMANCIA | 2 | 1 | 4 | Repair of Classrooms | 2403401 | 1 | 1755990.65 | COMPLETED | 1 | 2021-05-11 | 2021-07-29 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C11-096-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C11-096-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 500035 | Numancia Integrated Sch | NUMANCIA | 2 | 1 | 12 | Repair of Classrooms | 3571719 | 1 | 3065772.11 | COMPLETED | 1 | 2021-05-11 | 2021-06-11 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C8-093-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C8-093-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | GMO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 500035 | Numancia Integrated Sch | NUMANCIA | 2 |  | 11 | Repair of Classrooms | 4386775 | 1 | 897505.98 | COMPLETED | 1 | 2020-12-29 | 2020-11-23 | DepED-RO6-D1-2020QRF(REPAIR)-C21-038-2020 | DepED-RO6-D1-2020QRF(REPAIR)-C21-038-2020 | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-07-22 | 2020-08-24 | EARLY RISER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2020 | Region VI | Aklan | 500035 | Numancia Integrated Sch | NUMANCIA | 2 | 1 | 12 | Repair of Classrooms |  | 1 | 5850000 | COMPLETED | 1 | 2021-05-23 | 2021-12-10 | DepED-RO6-D1-2020BEFFREPAIR-C3-117-2019 | DepED-RO6-D1-2020BEFFREPAIR-C3-117-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-28 | FIRST MAKEEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region VI | Antique | 115001 | Yapu ES | BUGASONG | 0 | 1 | 7 | Repair of Classrooms | 2384806 | 1 | 2384805.52 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region VI | Antique | 115056 | San Vicente ES | CULASI | 0 | 1 | 5 | Repair of Classrooms | 1184099 | 1 | 1184098.51 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VI | Antique | 115058 | Tomao PS | CULASI | 0 | 1 | 2 | Repair of Classrooms | 707955 | 1 | 707954.51 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VI | Antique | 115120 | Paningayan Primary School | LAUA-AN | 0 | 1 | 2 | Repair of Classrooms | 541383 | 1 | 541382.91 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VI | Antique | 115127 | Bulanao ES | LIBERTAD | 0 | 1 | 4 | Repair of Classrooms | 1167416 | 1 | 1167415.76 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VI | Antique | 115162 | Patria ES | PANDAN | 0 | 1 | 12 | Repair of Classrooms | 3123406 | 1 | 3123405.87 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region VI | Antique | 302380 | Sta. Ana NHS | PANDAN | 0 | 1 | 3 | Repair of Classrooms | 893091 | 1 | 893090.82 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VI | Antique | 115182 | Magsaysay ES | PATNONGON | 0 | 1 | 3 | Repair of Classrooms | 922585 | 1 | 922584.33 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VI | Antique | 115190 | Villa Flores Elementary School | PATNONGON | 0 | 1 | 3 | Repair of Classrooms | 910960 | 1 | 910959.29 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VI | Antique | 115247 | Nagbangi I ES | SAN REMIGIO | 0 | 1 | 9 | Repair of Classrooms | 3312934 | 1 | 3312933.07 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VI | Antique | 115248 | Nagbangi II ES | SAN REMIGIO | 0 | 1 | 4 | Repair of Classrooms | 1171022 | 1 | 1171021.58 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VI | Antique | 115274 | Trinidad ES | SAN REMIGIO | 0 | 1 | 6 | Repair of Classrooms | 1758732 | 1 | 1758731.19 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VI | Antique | 115278 | Alegre ES | SEBASTE | 0 | 1 | 5 | Repair of Classrooms | 909620 | 1 | 909619.12 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VI | Antique | 115284 | P. Javier PS | SEBASTE | 0 | 1 | 1 | Repair of Classroom | 342209 | 1 | 342208.45 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VI | Antique | 115303 | MAASIN ELEMENTARY SCHOOL | SIBALOM | 0 | 1 | 4 | Repair of Classrooms | 652157 | 1 | 652156.8 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VI | Antique | 115340 | Bandoja PS | TIBIAO | 0 | 1 | 3 | Repair of Classrooms | 1168380 | 1 | 1168379.23 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VI | Antique | 115375 | Igtugas ES | TOBIAS FORNIER (DAO) | 0 | 1 | 4 | Repair of Classrooms | 1147844 | 1 | 1147843.2 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VI | Bacolod City | 117480 | BACOLOD CITY SPED CENTER | BACOLOD CITY (Capital) | 0 | 1 | 10 | Repair of Classrooms | 3101751 | 1 |  | COMPLETED | 1 | [10 empty] | RTA isuued, waiting for issuance of SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region VI | Bacolod City | 117454 | Mandalagan ES | BACOLOD CITY (Capital) | 0 | 1 | 17 | Repair of Classrooms | 5231763 | 1 |  | COMPLETED | 1 | [10 empty] | RTA isuued, waiting for issuance of SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0
REPAIR 2020 | Region VI | Bacolod City | 302718 | Teofilo M. Gensoli Sr. NHS | BACOLOD CITY (Capital) | 0 | 1 | 9 | Repair of Classrooms | 2161682 | 1 |  | COMPLETED | 1 | [10 empty] | RTA isuued, waiting for issuance of SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VI | Bago City | 117522 | Louisiana Elementary School | BAGO CITY | 4 | 1 | 6 | Repair of Classrooms | 2303740 | 1 | 1448262.47 | COMPLETED | 1 |  |  |  |  | 2020-02-10 | 2020-02-20 | 2020-03-04 | 2020-06-30 | 2020-11-06 | SUNSHINE SAPHIRE CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VI | Bago City | 117500 | Newton Jison ES | BAGO CITY | 4 | 1 | 9 | Repair of Classrooms | 3509767 | 1 | 2216066.59 | COMPLETED | 1 |  |  |  |  | 2020-02-10 | 2020-02-20 | 2020-03-04 | 2020-06-30 | 2020-11-06 | SUNSHINE SAPHIRE CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VI | Cadiz City | 302730 | Dr. Vicente F. Gustilo Memorial NHS | CADIZ CITY | 2 | 1 | 24 | Repair of Classrooms | 9493231 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0
REPAIR 2020 | Region VI | Cadiz City | 117564 | Luis Uy Chiat Elementary School | CADIZ CITY | 2 | 1 | 7 | Repair of Classrooms | 3333723 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115553 | Cabungahan Elementary School | MA-AYON | 1 | 1 | 8 | Repair of Classrooms | 2329273 | 1 | 2329272.6417 | COMPLETED | 1 | [9 empty] | PAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115566 | New Guia ES | MA-AYON | 1 | 1 | 9 | Repair of Classrooms | 2490000 | 1 | 2490000 | COMPLETED | 1 | [9 empty] | PAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115573 | Quinat-uyan ES | MA-AYON | 1 | 1 | 4 | Repair of Classrooms | 1054041 | 1 | 1054040.3583 | COMPLETED | 1 | [9 empty] | PAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115618 | Bato PS | PANAY | 1 | 1 | 1 | Repair of classroom | 330991 | 1 | 330990.7 | COMPLETED | 1 | [9 empty] | MBM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115625 | Daga ES | PANAY | 1 | 1 | 3 | Repair of Classrooms | 1042856 | 1 | 1042855.0883 | COMPLETED | 1 | [9 empty] | MBM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115643 | Agustin A. Almalbis MS | PANITAN | 1 | 1 | 4 | Repair of Classrooms | 1401985 | 1 | 1401984.7416 | COMPLETED | 1 | [9 empty] | MBM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115644 | Ambilay ES | PANITAN | 1 | 1 | 6 | Repair of Classrooms | 1869605 | 1 | 1869604.9884 | COMPLETED | 1 | [9 empty] | MBM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115681 | San Ramon ES | PILAR | 1 | 1 | 5 | Repair of Classrooms | 1539024 | 1 | 1539023.8911 | COMPLETED | 1 | [9 empty] | MBM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115683 | Sinamongan ES | PILAR | 1 | 1 | 6 | Repair of Classrooms | 1829503 | 1 | 1829502.0089 | COMPLETED | 1 | [9 empty] | MBM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115694 | Maximo Dais ES | PONTEVEDRA | 1 | 1 | 7 | Repair of Classrooms | 1620241 | 1 | 1620240.6971 | COMPLETED | 1 | [9 empty] | MBM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115776 | Joaquin Artuz ES | TAPAZ | 1 | 1 | 9 | Repair of Classrooms | 3740151 | 1 | 2880000 | COMPLETED | 1 | [9 empty] | RISM BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115409 | Agcabugao Elementary School | CUARTERO | 2 | 1 | 5 | Repair of Classrooms | 1960908 | 1 | 1441137.1718 | COMPLETED | 1 | [9 empty] | MARIZALOI CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115410 | Agdahon ES | CUARTERO | 2 | 1 | 10 | Repair of Classrooms | 4227569 | 1 | 3140790.49 | COMPLETED | 1 | [9 empty] | MARIZALOI CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115411 | Agnaga ES | CUARTERO | 2 | 1 | 3 | Repair of Classrooms | 820418 | 1 | 699736.1582 | COMPLETED | 1 | [9 empty] | MARIZALOI CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115415 | Vicente F. Fabuna ES (Bito-on Ilaya) | CUARTERO | 2 | 1 | 4 | Repair of Classrooms | 952108 | 1 | 820417.0046 | COMPLETED | 1 | [9 empty] | MBM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115429 | Agtambi PS | DAO | 2 | 1 | 2 | Repair of Classrooms | 559891 | 1 | 559890.5596 | COMPLETED | 1 | [9 empty] | PAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115430 | Agtanguay ES | DAO | 2 | 1 | 2 | Repair of Classrooms | 812715 | 1 | 812714.0019 | COMPLETED | 1 | [9 empty] | PAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115433 | Dao Central School | DAO | 2 | 1 | 12 | Repair of Classrooms | 3430391 | 1 | 3430390.57 | COMPLETED | 1 | [9 empty] | MBM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115451 | Consolacion ES | DUMALAG | 2 | 1 | 5 | Repair of Classrooms | 1652334 | 1 | 1504024.2016 | COMPLETED | 1 | [9 empty] | MBM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115452 | Dolores ES | DUMALAG | 2 | 1 | 5 | Repair of Classrooms | 1716193 | 1 | 1562151.7984 | COMPLETED | 1 | [9 empty] | MBM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115494 | SIBARIWAN ELEMENTARY SCHOOL | DUMARAO | 2 | 1 | 2 | Repair of Classrooms | 706078 | 1 | 706077.4034 | COMPLETED | 1 | [9 empty] | MBM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115499 | Agustin P. Navarra Elemenatary School | IVISAN | 2 | 1 | 7 | Repair of Classrooms | 2004443 | 1 | 2004442.1166 | COMPLETED | 1 | [9 empty] | MBM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115534 | Linambasan ES | JAMINDAN | 2 | 1 | 5 | Repair of Classrooms | 1539109 | 1 | 1539108.1154 | COMPLETED | 1 | [9 empty] | MBM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115591 | Malogo ES | MAMBUSAO | 2 | 1 | 3 | Repair of Classrooms | 1027966 | 1 | 1027965.9756 | COMPLETED | 1 | [9 empty] | MBM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115609 | Tongatong ES | MAMBUSAO | 2 | 1 | 5 | Repair of Classrooms | 1558188 | 1 | 1558187.0944 | COMPLETED | 1 | [9 empty] | MBM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115728 | Agtatacay Sur Elementary School | SAPI-AN | 2 | 1 | 5 | Repair of Classrooms | 1553419 | 1 | 1553418.7751 | COMPLETED | 1 | [9 empty] | MBM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115732 | Benlit ES | SAPI-AN | 2 | 1 | 6 | Repair of Classrooms | 1458094 | 1 | 1458093.1649 | COMPLETED | 1 | [9 empty] | MBM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115754 | Fructousa A. de Romero PS | SIGMA | 2 | 1 | 2 | Repair of Classrooms | 1395735 | 1 | 1395734.4385 | COMPLETED | 1 | [9 empty] | PAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115777 | Leopoldo Gialogo ES | TAPAZ | 2 | 1 | 6 | Repair of Classroom | 2098538 | 1 | 1738089.8534 | COMPLETED | 1 | [9 empty] | RISM BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115785 | Malitbog ES | TAPAZ | 2 | 1 | 4 | Repair of Classrooms | 1186124 | 1 | 355264.4993 | COMPLETED | 1 | [9 empty] | RISM BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115790 | San Antonio ES (tapaz east) | TAPAZ | 2 | 1 | 3 | Repair of Classrooms | 1358583 | 1 | 2098537.87 | COMPLETED | 1 | [9 empty] | FIRST R+J |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115794 | San Miguel Ilaya ES | TAPAZ | 2 | 1 | 6 | Repair of Classrooms | 2433015 | 1 | 1186123.46 | COMPLETED | 1 | [9 empty] | FIRST R+J |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 115816 | San Nicolas ES | TAPAZ | 2 | 1 | 5 | Repair of Classrooms | 2256671 | 1 | 1044735.5007 | COMPLETED | 1 | [9 empty] | RISM BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VI | Capiz | 179003 | Sinonod PS | TAPAZ | 2 | 1 | 1 | Repair of Classroom | 461989 | 1 | 1873910.1466 | COMPLETED | 1 | [9 empty] | RISM BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VI | Escalante City | 325605 | Escalante NHS - Libertad Ext. | CITY OF ESCALANTE | 1 | 1 | 5 | Repair of Classrooms | 1147308 | 1 | 1147307.33 | COMPLETED | 1 |  |  |  |  | January 2, 2020 | January 13, 2020 | January 23, 2020 | February 3, 2020 |  | JPEG Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VI | Escalante City | 117059 | Libertad Elementary School | CITY OF ESCALANTE | 1 | 1 | 12 | Repair of Classrooms | 2955791 | 1 | 2955791 | COMPLETED | 1 |  |  |  |  | January 2, 2020 | January 13, 2020 | January 23, 2020 | February 3, 2020 |  | JPEG Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region VI | Escalante City | 117060 | Mabini Central Elementary School | CITY OF ESCALANTE | 1 | 1 | 18 | Repair of Classrooms | 2527000 | 1 | 2526999.01 | COMPLETED | 1 |  |  |  |  | January 2, 2020 | January 13, 2020 | January 23, 2020 | February 3, 2020 |  | JPEG Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0
REPAIR 2020 | Region VI | Guimaras | 115905 | Cabalagnan Elementary School | NUEVA VALENCIA | 0 | 1 | 13 | Repair of Classrooms | 4617921 | 1 |  | COMPLETED | 1 |  |  |  |  | 25-Nov. 2019 | 19-Dec. 2019 | 19-Dec. 2019 | 26-Dec. 2019 | 6-Oct. 2020 | Quadtech Builders Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | Region VI | Guimaras | 179501 | Unisan Multigrade School | NUEVA VALENCIA | 0 | 1 | 5 | Repair of Classrooms | 1235832 | 1 |  | COMPLETED | 1 |  |  |  |  | 25-Nov. 2019 | 19-Dec. 2019 | 19-Dec. 2019 | 26-Dec. 2019 | 6-Oct. 2020 | Quadtech Builders Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VI | Guimaras | 115855 | Sapal Elementary School | SAN LORENZO | 0 | 1 | 10 | Repair of Classrooms | 2535000 | 1 |  | COMPLETED | 1 |  |  |  |  | 25-Nov. 2019 | 19-Dec. 2019 | 19-Dec. 2019 | 26-Dec. 2019 | 30-Sept. 2020 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region VI | Guimaras | 115879 | Liningwan Central School | SIBUNAG | 0 | 1 | 15 | Repair of Classrooms | 4793000 | 1 |  | COMPLETED | 1 |  |  |  |  | 25-Nov. 2019 | 19-Dec. 2019 | 19-Dec. 2019 | 26-Dec. 2019 | 30-Sept. 2020 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2020 | Region VI | Himamaylan City | 117071 | Catingib ES | CITY OF HIMAMAYLAN | 5 | 1 | 6 | Repair of Classrooms | 1291397 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VI | Himamaylan City | 117103 | Mambagaton ES | CITY OF HIMAMAYLAN | 5 | 1 | 13 | Repair of Classrooms | 4174262 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | Region VI | Himamaylan City | 117108 | Manuel Yulo ES | CITY OF HIMAMAYLAN | 5 | 1 | 7 | Repair of Classrooms | 2452596 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region VI | Iloilo | 116385 | Tano-ong PS | IGBARAS | 1 | 1 | 4 | Repair of Classrooms | 1048632 | 1 | 1048631.37 | COMPLETED | 1 | 2021-02-19 | 2021-05-21 | REPAIR2020-RVI-ILOILO-B1L1 | REPAIR2020-RVI-ILOILO-B1L1 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-13 | Anjush Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VI | Iloilo | 116631 | Sta. Clara ES | OTON | 1 | 1 | 7 | Repair of Classrooms | 1968930 | 1 | 1968929.53 | COMPLETED | 1 | 2021-02-16 | 2021-05-31 | REPAIR2020-RVI-ILOILO-B1L2 | REPAIR2020-RVI-ILOILO-B1L2 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-07 | SKY Builders Constrcution & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region VI | Iloilo | 116840 | Adgao-Tagpuan-Ingay ES | TUBUNGAN | 1 | 1 | 12 | Repair of Classrooms | 4831686 | 1 | 4831685.7 | COMPLETED | 1 | 2021-02-11 | 2021-02-05 | REPAIR2020-RVI-ILOILO-B1L3 | REPAIR2020-RVI-ILOILO-B1L3 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | October 5, 0200 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region VI | Iloilo | 116849 | Lanag Norte ES | TUBUNGAN | 1 | 1 | 10 | Repair of Classrooms | 3605887 | 1 | 3605886.45 | COMPLETED | 1 | 2021-02-24 | 2021-01-26 | REPAIR2020-RVI-ILOILO-B1L4 | REPAIR2020-RVI-ILOILO-B1L4 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-13 | Micro-Asia Builders Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region VI | Iloilo | 115953 | Cagay ES | ALIMODIAN | 2 | 1 | 5 | Repair of Classrooms | 2192144 | 1 | 2192143.8 | COMPLETED | 1 | 2021-02-11 | 2021-01-18 | REPAIR2020-RVI-ILOILO-B1L5 | REPAIR2020-RVI-ILOILO-B1L5 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-05 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VI | Iloilo | 116515 | Tacuyong Sur ELementary School | LEON | 2 | 1 | 14 | Repair of Classrooms | 5774000 | 1 | 5774000 | COMPLETED | 1 | 2021-02-11 | 2021-02-08 | REPAIR2020-RVI-ILOILO-B1L6 | REPAIR2020-RVI-ILOILO-B1L6 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-07 | RISM BUILDERS & CONST. SERVICES INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2020 | Region VI | Iloilo | 116611 | Cagban ES | NEW LUCENA | 2 | 1 | 8 | Repair of Classrooms | 2595137 | 1 | 2595136.29 | COMPLETED | 1 | 2021-02-04 | 2021-09-30 | REPAIR2020-RVI-ILOILO-B1L7 | REPAIR2020-RVI-ILOILO-B1L7 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-06 | SLW8 Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VI | Iloilo | 115998 | Calansanan ES | BADIANGAN | 3 | 1 | 6 | Repair of Classrooms | 2197355 | 1 | 2197354.33 | COMPLETED | 1 | 2021-02-24 | 2021-01-26 | REPAIR2020-RVI-ILOILO-B1L8 | REPAIR2020-RVI-ILOILO-B1L8 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-13 | Micro-Asia Builders Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VI | Iloilo | 116103 | Agba-o ES | BINGAWAN | 3 | 1 | 13 | Repair of Classrooms | 4161861 | 1 | 4161860.12 | COMPLETED | 1 | 2021-02-11 | 2021-02-10 | REPAIR2020-RVI-ILOILO-B1L9 | REPAIR2020-RVI-ILOILO-B1L9 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-07 | RISM BUILDERS & CONST. SERVICES INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | Region VI | Iloilo | 116663 | Danao ES | POTOTAN | 3 | 1 | 7 | Repair of Classrooms | 2915334 | 1 | 2915333.56 | COMPLETED | 1 | 2021-02-03 | 2021-05-25 | REPAIR2020-RVI-ILOILO-B1L10 | REPAIR2020-RVI-ILOILO-B1L10 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-06 | Q.M. Florete Cosntruction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region VI | Iloilo | 116276 | Libo-o ES | DINGLE | 4 | 1 | 10 | Repair of Classrooms | 3482400 | 1 | 3448463.39 | COMPLETED | 1 | 2021-02-11 | 2021-02-09 | REPAIR2020-RVI-ILOILO-B1L11 | REPAIR2020-RVI-ILOILO-B1L11 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-07 | GMO Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region VI | Iloilo | 116283 | SAN MATIAS ELEMENTARY SCHOOL | DINGLE | 4 | 1 | 10 | Repair of Classrooms | 4156798 | 1 | 4156797.5 | COMPLETED | 1 | 2021-02-13 | 2021-02-05 | REPAIR2020-RVI-ILOILO-B1L12 | REPAIR2020-RVI-ILOILO-B1L12 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-13 | Micro-Asia Builders Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region VI | Iloilo | 116762 | Calaigang ES | SAN RAFAEL | 5 | 1 | 11 | Repair of Classrooms | 4541350 | 1 | 4541349.37 | COMPLETED | 1 | 2021-02-19 | 2021-02-11 | REPAIR2020-RVI-ILOILO-B1L13 | REPAIR2020-RVI-ILOILO-B1L13 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-13 | Anjush Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2020 | Region VI | Iloilo City | 117580 | Arevalo ES | ILOILO CITY (Capital) | 0 | 1 | 9 | Repair of Classrooms | 1785842 | 1 | 1785842 | COMPLETED | 1 | 2020-02-09 | 2019-12-16 | 20-10-004 | 14-08-054 | 2018-11-14 | 2018-11-20 | 2018-12-07 | 2018-12-11 | 2019-09-05 | RISM BUILDERS & CONST. SERVICES INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VI | Iloilo City | 117584 | Sto. Domingo ES | ILOILO CITY (Capital) | 0 | 1 | 8 | Repair of Classrooms | 1562190 | 1 | 1562190 | COMPLETED | 1 | 2020-02-09 | 2019-12-16 | 20-10-005 | 14-08-054 | 2018-11-14 | 2018-11-20 | 2018-12-07 | 2018-12-11 | 2019-09-05 | RISM BUILDERS & CONST. SERVICES INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VI | Kabankalan City | 312102 | Bantayan NHS - Baras Diutay Ext. | CITY OF KABANKALAN | 6 | 1 | 5 | Repair of Classrooms | 2229775 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VI | Kabankalan City | 302795 | Locotan NHS | CITY OF KABANKALAN | 6 | 1 | 12 | Repair of Classrooms | 4316400 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region VI | Kabankalan City | 117863 | Magtongtong ES | CITY OF KABANKALAN | 6 | 1 | 8 | Repair of Classrooms | 2943394 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VI | Kabankalan City | 117844 | Mansumbil Elementary School | CITY OF KABANKALAN | 6 | 1 | 7 | Repair of Classrooms | 1382874 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region VI | Kabankalan City | 117865 | Pangyasan PS | CITY OF KABANKALAN | 6 | 1 | 2 | Repair of Classrooms | 592725 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VI | Kabankalan City | 117850 | Pres. Osmena ES | CITY OF KABANKALAN | 6 | 1 | 12 | Repair of Classrooms | 3207618 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region VI | La Carlota City | 117631 | Balabag ES | LA CARLOTA CITY | 4 | 1 | 15 | Repair of Classrooms | 3606012 | 1 |  | COMPLETED | 1 | [10 empty] | Already Submit the RTA/waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2020 | Region VI | La Carlota City | 117635 | Ferlou ES | LA CARLOTA CITY | 4 | 1 | 16 | Repair of Classrooms | 3822948 | 1 |  | COMPLETED | 1 | [10 empty] | Already Submit the RTA/waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2020 | Region VI | La Carlota City | 500192 | La Carlota City SPED Integrated School | LA CARLOTA CITY | 4 | 1 | 12 | Repair of Classrooms | 2089503 | 1 |  | COMPLETED | 1 | [10 empty] | Already Submit the RTA/waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region VI | Passi City | 186002 | AGLALANA ELEMENTARY SCHOOL - ANNEX | CITY OF PASSI | 4 | 1 | 7 | Repair of Classrooms | 1838647 | 1 | 1838646.33 | COMPLETED | 1 |  |  |  | RO6-D14-CY2020-REPAIR-CLASSROOMS-L2 |  |  |  |  | November 6, 2020 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region VI | Passi City | 186003 | Pagaypay Elementary School | CITY OF PASSI | 4 | 1 | 3 | Repair of Classrooms | 769662 | 1 | 769661.03 | COMPLETED | 1 |  |  |  | R06-D14-CY2020-REPAIR-CLASSROOMS-L1 |  |  |  |  | November 6, 2020 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VI | Passi City | 117928 | Talongonan Elementary School | CITY OF PASSI | 4 | 1 | 5 | Repair of Classrooms | 1289230 | 1 | 1289229.27 | COMPLETED | 1 |  |  |  | R06-D14-CY2020-REPAIR-CLASSROOMS-L1 |  |  |  |  | November 6, 2020 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VI | Sagay City | 117729 | Campo Santiago ES | Sagay City | 2 | 1 | 5 | Repair of Classrooms | 2352066 | 1 | 2352065.09 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-29 | 2019-12-12 |  |  | ROMBER CONSTRUCTION & GENERAL MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VI | Sagay City | 117717 | Hautea ES | Sagay City | 2 | 1 | 5 | Repair of Classrooms | 2225599 | 1 | 2225598.13 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-29 | 2019-12-12 |  |  | ROMBER CONSTRUCTION & GENERAL MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VI | Sagay City | 302770 | Sewahon National High School | SAGAY CITY | 2 | 1 | 6 | Repair of Classrooms | 2972911 | 1 | 2972910.93 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-29 | 2019-12-12 |  |  | ROMBER CONSTRUCTION & GENERAL MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VI | San Carlos City | 117796 | Malindog ES | SAN CARLOS CITY | 1 | 1 | 10 | Repair of Classrooms | 3494847 | 1 | 3491000 | COMPLETED | 1 | 2021-05-15 | 2021-05-15 | 7142036-2020BEFF | 7142036-2020BEFF | 2020-07-07 | 2020-08-06 | 2020-08-19 | 2020-10-30 | 2020-12-21 | RISM Builders & Construction Services, Inc. | 100% completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region VI | San Carlos City | 117764 | Punod ES | SAN CARLOS CITY | 1 | 1 | 9 | Repair of Classrooms | 3663014 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VI | San Carlos City | 117755 | Rizal ES | SAN CARLOS CITY | 1 | 1 | 2 | Repair of Classrooms | 716540 | 1 | 715000 | COMPLETED | 1 | 2021-05-15 | 2021-05-15 | 7142036-2020BEFF | 7142036-2020BEFF | 2020-07-07 | 2020-08-06 | 2020-08-19 | 2020-10-30 | 2020-12-21 | RISM Builders & Construction Services, Inc. | 100% completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VI | Silay City | 500199 | Don Albino & Doña Dolores Jison IS | SILAY CITY | 3 | 1 | 13 | Repair of Classrooms | 3869000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | Region VI | Sipalay City | 117360 | Maricalum ES | CITY OF SIPALAY | 6 | 1 | 6 | Repair of Classrooms | 2144197 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region VI | Aklan | 178009 | Taba-ao Primary School | BANGA | 1 | 1 | 1 | Repair of Classroom | 406986.56 | 1 | 275895.72 | COMPLETED | 1 | 2022-01-07 | 2019-12-02 | DepED-RO6-D1-2021BEFF-REPAIR-014-2021 | DepED-RO6-D1-2021BEFF-REPAIR-014-2021 | 2021-05-31 | 2021-06-10 | 2021-06-21 | 2021-07-22 | 2021-09-02 | LEGACY CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region VI | Aklan | 114689 | Lalab Elementary School | BATAN | 1 | 1 | 6 | Repair of Classrooms | 2858987.64 | 1 | 2166767.77 | COMPLETED | 1 | 2021-12-17 | 2021-12-03 | DepED-RO6-D1-2021BEFF-REPAIR-014-017-02-2021 | DepED-RO6-D1-2021BEFF-REPAIR-014-017-02-2021 | 2021-05-31 | 2021-06-10 | 2021-06-21 | 2021-07-12 | 2021-08-12 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region VI | Aklan | 114790 | Marapayao PS | LIBACAO | 1 | 1 | 1 | Repair of Classroom | 772571.99 | 1 | 593232.23 | COMPLETED | 1 | 2021-12-17 | 2021-10-08 | DepED-RO6-D1-2021BEFF-REPAIR-014-017-02-2021 | DepED-RO6-D1-2021BEFF-REPAIR-014-017-02-2021 | 2021-05-31 | 2021-06-10 | 2021-06-21 | 2021-07-12 | 2021-08-12 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region VI | Aklan | 114817 | Mamba ES | MADALAG | 1 | 1 | 3 | Repair of Classroom | 1674615.23 | 1 | 1269807.42 | COMPLETED | 1 | 2021-12-17 | 2021-12-03 | DepED-RO6-D1-2021BEFF-REPAIR-014-017-03-2021 | DepED-RO6-D1-2021BEFF-REPAIR-014-017-03-2021 | 2021-05-31 | 2021-06-10 | 2021-06-21 | 2021-07-12 | 2021-08-12 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region VI | Aklan | 114903 | Jalas ES | NEW WASHINGTON | 1 | 1 | 7 | Repair of Classrooms | 3323793.38 | 1 | 2334655.01 | COMPLETED | 1 | 2022-01-07 |  | DepED-RO6-D1-2021BEFF-REPAIR-014-2021 | DepED-RO6-D1-2021BEFF-REPAIR-014-2021 | 2021-05-31 | 2021-06-10 | 2021-06-21 | 2021-07-12 | 2021-09-02 | LEGACY CONSTRUCTION CORPORATION | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region VI | Aklan | 114844 | Tugas-Dumga ES | MAKATO | 2 | 1 | 4 | Repair of Classrooms | 2167538.09 | 1 | 1557587.79 | COMPLETED | 1 | 2022-01-22 |  | DepED-RO6-D1-2021BEFF-REPAIR-017-2021 | DepED-RO6-D1-2021BEFF-REPAIR-017-2021 | 2021-05-31 | 2021-06-10 | 2021-06-21 | 2021-07-12 | 2021-09-02 | LEGACY CONSTRUCTION CORPORATION | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region VI | Aklan | 114886 | Matabana ES | NABAS | 2 | 1 | 4 | Repair of Classrooms | 1988334.71 | 1 | 1513192.58 | COMPLETED | 1 | 2021-12-17 | 2021-12-03 | DepED-RO6-D1-2021BEFF-REPAIR-014-017-03-2021 | DepED-RO6-D1-2021BEFF-REPAIR-014-017-03-2021 | 2021-05-31 | 2021-06-10 | 2021-06-21 | 2021-07-12 | 2021-08-12 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region VI | Aklan | 114937 | Tondog Elementary School | TANGALAN | 2 | 1 | 6 | Repair of Classrooms | 1581722.29 | 1 | 993077.27 | COMPLETED | 1 | 2022-01-22 |  | DepED-RO6-D1-2021BEFF-REPAIR-017-2021 | DepED-RO6-D1-2021BEFF-REPAIR-017-2021 | 2021-05-31 | 2021-06-10 | 2021-06-21 | 2021-07-22 | 2021-09-02 | LEGACY CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region VI | Antique | 114940 | Bayo-Crispin V. Unica MS | ANINI-Y | 0 | 1 | 4 | Repair of Classrooms | 1653433.37 | 1 |  | COMPLETED | 1 | 2022-09-30 | [9 empty] | Roof and Roof Framing already Installed. Ceiling installed Painting and Electricakl Works partially completed. Remaining Works installed Painting, Blackboard, Hand Washing Facilities completion | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region VI | Antique | 114998 | Talisay Elementary School | BUGASONG | 0 | 1 | 13 | Repair of Classrooms | 6081093.6 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2021 | Region VI | Antique | 115122 | Santiago ES | LAUA-AN | 0 | 1 | 11 | Repair of Classrooms | 4395339.39 | 1 |  | COMPLETED | 1 | [10 empty] | All completed except for 1 buidling which previously occupied by the teachers. Remaining works to 1 builing included Ramp, Flood Marker, Roofing and Painting Wqorks | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2021 | Region VI | Antique | 115165 | San Joaquin ES | PANDAN | 0 | 1 | 5 | Repair of Classrooms | 2495960.52 | 1 |  | COMPLETED | 1 | [10 empty] | All completed except for 1 buidling. Remaining works to 1 builing included Ramp, Flood Marker, Roofing and Painting Wqorks | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region VI | Antique | 115234 | Aningalan ES | SAN REMIGIO | 0 | 1 | 17 | Repair of Classrooms | 3640593.42 | 1 |  | COMPLETED | 1 | [10 empty] | Nearing Completion. Remaining works includes Ceiling Works and Painting Works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0
REPAIR 2021 | Region VI | Antique | 115246 | Maragubdub ES | SAN REMIGIO | 0 | 1 | 9 | Repair of Classrooms | 4666788.52 | 1 |  | COMPLETED | 1 | 2022-09-30 | [9 empty] | Nearing Completion. Remaining works includes Ceiling Works and Painting Works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2021 | Region VI | Antique | 115326 | Mabini Elementary School | SIBALOM | 0 | 1 | 5 | Repair of Classrooms | 2643875.67 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region VI | Antique | 302352 | Concepcion L. Cazeñas MS | TOBIAS FORNIER (DAO) | 0 | 1 | 6 | Repair of Classrooms | 2977199.24 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region VI | Antique | 115378 | Manaling PS | TOBIAS FORNIER (DAO) | 0 | 1 | 1 | Repair of Classroom | 702351.68 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region VI | Antique | 115399 | Cansilayan PS | VALDERRAMA | 0 | 1 | 2 | Repair of Classrooms | 1990597.56 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VI | Bacolod City | 302699 | ABKASA National High School | Bacolod City | 0 | 1 | 8 | Repair of Classrooms | 3844978.53 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region VI | Bago City | 117514 | Bagroy ES | BAGO CITY | 4 | 1 | 5 | Repair of Classrooms | 2681518.72 | 1 |  | COMPLETED | 1 | 2022-09-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region VI | Cadiz City | 311405 | Banquerohan NHS | Cadiz City | 2 | 1 | 14 | Repair of Classrooms | 6452598.74 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2021 | Region VI | Cadiz City | 117538 | San Andres ES | Cadiz City | 2 | 1 | 3 | Repair of Classrooms | 1307681.97 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region VI | Cadiz City | 117540 | SPED Training Center | Cadiz City | 2 | 1 | 18 | Repair of Classrooms | 6854463.18 | 1 |  | reverted | 0.85 | 2023-01-31 | [9 empty] | Under suspension due to issue on building permit | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2021 | Region VI | Capiz |  | CANAPI-AN INTEGRATED SCHOOL | MAAYON | 1 | 1 | 6 | Repair of Classrooms | 2896550.15 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region VI | Capiz | 115638 | Tanza Norte ES | PANAY | 1 | 1 | 5 | Repair of Classrooms | 2061164.82 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region VI | Capiz | 115652 | Cogon ES (Panitan) | PANITAN | 1 | 1 | 4 | Repair of Classrooms | 951085.5 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region VI | Capiz | 115656 | Jesus Gonzalo Albana ES | PANITAN | 1 | 1 | 2 | Repair of Classroom | 644920.38 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VI | Capiz | 310811 | YATING NATIONAL HIGH SCHOOL | PILAR | 1 | 1 | 7 | Repair of Classrooms | 2165497.74 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region VI | Capiz | 115716 | Manoling ES | PRESIDENT ROXAS | 1 | 1 | 8 | Repair of Classroom | 2784400.98 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region VI | Capiz | 115493 | San Juan ES (dumarao) | DUMARAO | 2 | 1 | 6 | Repair of Classrooms | 2248964.16 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region VI | Capiz | 501092 | Bula Integrated School | MAMBUSAO | 2 | 1 | 12 | Repair of Classrooms | 4798702.92 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2021 | Region VI | Capiz | 115600 | Burias ES | MAMBUSAO | 2 | 1 | 9 | Repair of Classrooms | 3235894.97 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2021 | Region VI | Capiz | 115731 | Bangkal ES | SAPI-AN | 2 | 1 | 4 | Repair of Classrooms | 1285716.89 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region VI | Escalante City | 117042 | Don Esteban dela Rama Elementary School | CITY OF ESCALANTE | 1 | 1 | 11 | Repair of Classrooms | 4511858.06 | 1 |  | COMPLETED | 1 | 2022-09-30 | [9 empty] | Punclisted items are not yet addressed by the contractor | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2021 | Region VI | Guimaras | 115826 | Old Poblacion Elementary School | BUENAVISTA | 0 | 1 | 14 | Repair of Classrooms | 6571845.67 | 1 | 4475425.9695 | COMPLETED | 1 | 2021-12-23 |  | 04-2021-lot 1 | 04-2021-lot 1 | 2021-05-26 | 2021-06-08 | 2021-06-22 | 2021-07-09 | 2021-07-20 | GMO Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2021 | Region VI | Guimaras | 115873 | San Miguel Central School | JORDAN (Capital) | 0 | 1 | 8 | Repair of Classrooms | 3759977.03 | 1 | 2557000.0002 | COMPLETED | 1 | 2021-12-23 |  | 04-2021-lot 2 | 04-2021-lot 2 | 2021-05-26 | 2021-06-08 | 2021-06-22 | 2021-07-09 | 2021-07-20 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region VI | Guimaras | 115893 | Concordia Elementary School | NUEVA VALENCIA | 0 | 1 | 10 | Repair of Classrooms | 4818602.53 | 1 | 4777492.2348 | COMPLETED | 1 | 2021-12-23 | 2021-10-11 | 04-2021-lot 3 | 04-2021-lot 3 | 2021-05-26 | 2021-06-08 | 2021-06-22 | 2021-07-09 | 2021-07-20 | Early Riser Constructio |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region VI | Guimaras | 115901 | Paaralan ng Buhay ng La Orca | NUEVA VALENCIA | 0 | 1 | 6 | Repair of Classrooms | 2305588.33 | 1 | 2287314.6769 | COMPLETED | 1 | 2021-12-23 | 2021-10-11 | 04-2021-lot 3 | 04-2021-lot 3 | 2021-05-26 | 2021-06-08 | 2021-06-22 | 2021-07-09 | 2021-07-20 | Early Riser Constructio |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region VI | Himamaylan City | 117072 | Cong. Eliseo P. Limsiaco Sr. MES | CITY OF HIMAMAYLAN | 5 | 1 | 10 | Repair of Classrooms | 3443803.28 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region VI | Iloilo | 116724 | Dacdacanan ES | SAN JOAQUIN | 1 | 1 | 3 | Repair of Classrooms | 1555209.99 | 1 | 1058517.66 | COMPLETED | 1 | 2022-01-11 | 2022-01-05 | R-06--BEFF Repair -2021-B1-01 | R-06--BEFF Repair -2021-B1-01 | 2021-06-04 |  | 2021-06-25 | 2021-07-14 | 2021-08-18 | Wilkinson Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region VI | Iloilo | 116748 | Toog-Tiglawa ES | SAN JOAQUIN | 1 | 1 | 8 | Repair of Classrooms | 2533607.93 | 1 | 1720662.98 | COMPLETED | 1 | 2022-01-11 | 2022-01-05 | R-06--BEFF Repair -2021-B1-01 | R-06--BEFF Repair -2021-B1-01 | 2021-06-04 |  | 2021-06-25 | 2021-07-14 | 2021-08-18 | Wilkinson Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region VI | Iloilo | 115948 | Bagsakan PS | ALIMODIAN | 2 | 1 | 2 | Repair of Classrooms | 945620.53 | 1 | 658561.72 | COMPLETED | 1 | 2021-12-16 | 2021-09-17 | R-06--BEFF Repair -2021-B1-02 | R-06--BEFF Repair -2021-B1-02 | 2021-06-04 |  | 2021-06-25 | 2021-07-14 | 2021-08-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VI | Iloilo | 116502 | Apian Elementary School | LEON | 2 | 1 | 5 | Repair of Classrooms | 1961689.47 | 1 | 1366626.93 | COMPLETED | 1 | 2021-12-16 | 2021-09-12 | R-06--BEFF Repair -2021-B1-02 | R-06--BEFF Repair -2021-B1-02 | 2021-06-04 |  | 2021-06-25 | 2021-07-14 | 2021-08-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region VI | Iloilo | 116810 | Mambuyo ES | SANTA BARBARA | 2 | 1 | 5 | Repair of Classrooms | 2059368.98 | 1 | 1435111.64 | COMPLETED | 1 | 2021-12-16 | 2021-09-17 | R-06--BEFF Repair -2021-B1-02 | R-06--BEFF Repair -2021-B1-02 | 2021-06-04 |  | 2021-06-25 | 2021-07-14 | 2021-08-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region VI | Iloilo | 116646 | Barasan ES | POTOTAN | 3 | 1 | 11 | Repair of Classrooms | 3901045.83 | 1 | 2539424.22 | COMPLETED | 1 | 2022-01-11 | 2022-12-23 | R-06--BEFF Repair -2021-B1-03 | R-06--BEFF Repair -2021-B1-03 | 2021-06-04 |  | 2021-06-25 | 2021-07-14 | 2021-08-18 | Wilkinson Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2021 | Region VI | Iloilo | 116296 | Bugtongan ES | DUEÑAS | 4 | 1 | 8 | Repair of Classrooms | 2968679.52 | 1 | 2055495.78 | COMPLETED | 1 | 2021-12-16 | 2022-03-10 | R-06--BEFF Repair -2021-B1-04 | R-06--BEFF Repair -2021-B1-04 | 2021-06-04 |  | 2021-06-25 | 2021-07-14 | 2021-08-18 | Edison Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region VI | Iloilo | 116308 | Ponong Grande ES | DUEÑAS | 4 | 1 | 10 | Repair of Classrooms | 2483701.85 | 1 | 1691009.02 | COMPLETED | 1 | 2021-12-16 | 2022-03-10 | R-06--BEFF Repair -2021-B1-04 | R-06--BEFF Repair -2021-B1-04 | 2021-06-04 |  | 2021-06-25 | 2021-07-14 | 2021-08-18 | Edison Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region VI | Iloilo | 302460 | Batad National High School | BATAD | 5 | 1 | 35 | Repair of Classrooms | 6826100.75 | 1 | 4629459.85 | COMPLETED | 1 | 2021-12-16 | 2022-02-10 | R-06--BEFF Repair -2021-B1-05 | R-06--BEFF Repair -2021-B1-05 | 2021-06-04 |  | 2021-06-25 | 2021-07-14 | 2021-08-18 | Anjush Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 35 | 0 | 0
REPAIR 2021 | Region VI | Iloilo | 501491 | Batuanan IS | Carles | 5 | 1 | 5 | Repair of Classrooms | 1505955.39 | 1 | 1002969.95 | COMPLETED | 1 | 2021-12-16 | 2022-02-10 | R-06--BEFF Repair -2021-B1-05 | R-06--BEFF Repair -2021-B1-05 | 2021-06-04 |  | 2021-06-25 | 2021-07-14 | 2021-08-18 | Anjush Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region VI | Iloilo City | 117622 | Molo I ES | ILOILO CITY (Capital) | 0 | 1 | 13 | Repair of Classrooms | 2417742.86 | 1 |  | reverted | 0.88 | 2023-03-01 | [9 empty] | Terminated October 2022; Contractor (E.M. Sinai Construction Services blacklisted) | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2021 | Region VI | Iloilo City | 302746 | R. G. Hechanova Memorial NHS | ILOILO CITY (Capital) | 0 | 1 | 4 | Repair of Classrooms | 1181220.57 | 1 |  | reverted | 0.1 | 2023-06-01 | [9 empty] | Terminated October 2022; Contractor (E.M. Sinai Construction Services blacklisted) | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2021 | Region VI | Iloilo City | 500551 | SPED - Integrated School for Exceptional Children | ILOILO CITY (Capital) | 0 | 1 | 9 | Repair of Classrooms | 1283571.73 | 1 |  | reverted | 0.1 | 2023-06-01 | [9 empty] | Terminated October 2022; Contractor (E.M. Sinai Construction Services blacklisted) | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2021 | Region VI | Iloilo City | 117604 | Tacas ES | ILOILO CITY (Capital) | 0 | 1 | 7 | Repair of Classrooms | 1474559.97 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region VI | Kabankalan City | 117835 | Camingawan ES | CITY OF KABANKALAN | 6 | 1 | 15 | Repair of Classrooms | 5784190.44 | 1 | 5769246.44 | COMPLETED | 1 | [9 empty] | Rism Builers and Construction services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2021 | Region VI | Kabankalan City | 117880 | Daan Banua ES | CITY OF KABANKALAN | 6 | 1 | 22 | Repair of Classrooms | 4194461.43 | 1 | 4181072.72 | COMPLETED | 1 | [9 empty] | Rism Builers and Construction services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 0 | 0
REPAIR 2021 | Region VI | Kabankalan City | 117847 | Oringao ES | CITY OF KABANKALAN | 6 | 1 | 26 | Repair of Classrooms | 8719945.91 | 1 | 8705000 | COMPLETED | 1 | [9 empty] | Rism Builers and Construction services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 26 | 0 | 0
REPAIR 2021 | Region VI | Kabankalan City | 117853 | Tan-awan ES | CITY OF KABANKALAN | 6 | 1 | 18 | Repair of Classrooms | 6184935.25 | 1 | 6171000 | COMPLETED | 1 | [9 empty] | Rism Builers and Construction services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0
REPAIR 2021 | Region VI | La Carlota City | 117638 | Cubay ES | LA CARLOTA CITY | 4 | 1 | 11 | Repair of Classrooms | 5314284.33 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2021 | Region VI | Passi City | 117916 | Bacuranan Elementary School | CITY OF PASSI | 4 | 1 | 8 | Repair of Classrooms | 2985441.51 | 1 | 2447000 | COMPLETED | 1 | December 24, 2021 |  | RO6-D14-CY2021-REPAIR-CLASSROOMS-L1 | RO6-D14-CY2021-REPAIR-CLASSROOMS-L1 | June 08, 2021 | June 16, 2021 | August 16, 2021 | August 19, 2021 | August 24, 2021 | Rism Builders & Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region VI | Roxas City | 117669 | Don Manuel Arnaldo MS | ROXAS CITY (Capital) | 1 | 1 | 12 | Repair of Classrooms | 2999777.59 | 1 | 2069000 | COMPLETED | 1 | 2021-11-14 |  |  | CON-2021-019 | June 9, 2021 | June 16, 2021 | June 29, 2021 | June 30, 2021 | August 9, 2021 | RISM Builders & Const. Svs., Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2021 | Region VI | Sagay City | 117703 | Plaridel Elementary School | SAGAY CITY | 2 | 1 | 6 | Repair of Classrooms | 3004680.22 | 1 | 1832165.88 | COMPLETED | 1 | November 16, 2021 |  | 07-2021 | 07-2021 | June 7, 2021 | June 15, 2021 | June 30, 2021 | July 21, 2021 | August 16, 2021 | SANS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region VI | San Carlos City | 117742 | Ansulag ES | SAN CARLOS CITY | 1 | 1 | 6 | Repair of Classrooms | 2783150.74 | 1 | 2748000 | COMPLETED | 1 | 2021-06-25 | 2021-06-21 | 7773810-2021beff-ANSULAG ES | 7773810-2021beff-ANSULAG ES | 2021-06-17 | 2021-06-16 | 2021-07-07 | 2021-07-29 | 2021-08-20 | Rism Builders & Construction Services Inc. | 100% Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region VI | Silay City | 302778 | Brgy. Guimbala-on NHS | SILAY CITY | 3 | 1 | 6 | Repair of Classrooms | 2442021.84 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region VI | Sipalay City | 117359 | Hda. Maricalum ES | CITY OF SIPALAY | 6 | 1 | 5 | Repair of Classrooms | 2673447.53 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region VI | Aklan | 114702 | Bel-is ES | BURUANGA | 2 | 1 | 2 | Repair of Classrooms | 829930.76 | 1 | 822267.96 | COMPLETED | 1 | 2022-09-26 | 2022-09-13 | CY 2022 BEFF REAPIR - 001 | CY 2022 BEFF REAPIR - 001 | 2022-03-08 | 2022-03-15 | 2022-03-28 | 2022-04-07 | 2022-06-15 | EARLY RISER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region VI | Aklan | 114712 | Tigum ES | BURUANGA | 2 | 1 | 3 | Repair of Classrooms | 1291274.33 | 1 | 1275118.05 | COMPLETED | 1 | 2022-09-26 | 2022-10-21 | CY 2022 BEFF REAPIR - 001 | CY 2022 BEFF REAPIR - 001 | 2022-03-08 | 2022-03-15 | 2022-03-28 | 2022-04-07 | 2022-06-15 | EARLY RISER CONSTRUCTION | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region VI | Aklan | 114764 | Bugasongan ES | LEZO | 2 | 1 | 2 | Repair of Classrooms | 1059858.6 | 1 | 1053269.37 | COMPLETED | 1 | 2022-10-14 | 2022-09-26 | CY 2022 BEFF REAPIR - 002 | CY 2022 BEFF REAPIR - 002 | 2022-03-08 | 2022-03-15 | 2022-03-28 | 2022-04-07 | 2022-06-15 | SOLID MERCHNDISING | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region VI | Aklan | 114928 | Dapdap Elementary School | TANGALAN | 2 | 1 | 2 | Repair of Classrooms | 742820.94 | 1 | 735800.85 | COMPLETED | 1 | 2022-10-25 | 2022-11-11 | CY 2022 BEFF REAPIR - 002 | CY 2022 BEFF REAPIR - 002 | 2022-03-08 | 2022-03-15 | 2022-03-28 | 2022-04-07 | 2022-06-15 | SOLID MERCHNDISING | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region VI | Aklan | 500183 | Jawili Integrated School | TANGALAN | 2 | 1 | 1 | Repair of Classroom | 779456.07 | 1 | 771071.55 | COMPLETED | 1 | 2022-10-14 | 2022-11-18 | CY 2022 BEFF REAPIR - 002 | CY 2022 BEFF REAPIR - 002 | 2022-03-08 | 2022-03-15 | 2022-03-28 | 2022-04-07 | 2022-06-15 | SOLID MERCHNDISING | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2022 | Region VI | Antique | 114978 | Mojon ES | BELISON | 0 | 1 | 3 | Repair of Classrooms | 2121271 | 1 |  | COMPLETED | 1 | August 23, 2022 | [9 empty] | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region VI | Antique | 115131 | Lindero Elementary School | LIBERTAD | 0 | 1 | 7 | Repair of Classrooms | 3181906 | 1 |  | COMPLETED | 1 | September 3, 2022 | [9 empty] | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2022 | Region VI | Guimaras | 302439 | Remedios E. Vilches-San Lorenzo National High School | SAN LORENZO | 0 | 1 | 8 | Repair of Classrooms | 3637208.88 | 1 |  | COMPLETED | 1 | 2023-02-28 |  | 03-2022-lot 2 | No. 03-B-2022 | 2022-05-13 | 2022-05-25 | 2022-06-14 | 2022-07-01 | 2022-09-26 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2022 | Region VI | Iloilo | 116107 | Cairohan PS | BINGAWAN | 3 | 1 | 1 | Repair of Classroom | 531001.48 | 1 | 523711.43 | COMPLETED | 1 | ################ | 2022-08-19 | R-06-BEFF-2022-B1-L2 | R-06-BEFF-2022-B1-L2 | 2022-02-24 |  | 2022-03-15 | 2022-03-24 | 2022-07-18 | Wilkinson Construction | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2022 | Region VI | Iloilo | 116111 | Maganhop PS | BINGAWAN | 3 | 1 | 2 | Repair of Classrooms | 651145.99 | 1 | 642452.25 | COMPLETED | 1 | ################ | 2022-08-19 | R-06-BEFF-2022-B1-L2 | R-06-BEFF-2022-B1-L2 | 2022-02-24 |  | 2022-03-15 | 2022-03-24 | 2022-07-18 | Wilkinson Construction | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region VI | Iloilo | 116112 | Malitbog Ilawod PS | BINGAWAN | 3 | 1 | 3 | Repair of Classrooms | 1342396.18 | 1 | 1326345.85 | COMPLETED | 1 | ################ | Augsut 29, 2022 | R-06-BEFF-2022-B1-L2 | R-06-BEFF-2022-B1-L2 | 2022-02-24 |  | 2022-03-15 | 2022-03-24 | 2022-07-18 | Wilkinson Construction | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region VI | Iloilo | 116604 | Tipolo Elementary School | MINA | 3 | 1 | 11 | Repair of Classrooms | 1914166.05 | 1 | 1469603.52 | COMPLETED | 1 | ################ | 2022-12-16 | R-06-BEFF-2022-B1-L1 | R-06-BEFF-2022-B1-L1 | 2022-02-24 |  | 2022-03-15 | 2022-03-24 | 2022-07-18 | Em Sinai Constrction Services | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2022 | Region VI | Iloilo | 116092 | Batad CES | BATAD | 5 | 1 | 3 | Repair of Classrooms | 852867.33 | 1 | 851905.57 | COMPLETED | 1 | 2022-11-05 | 2022-08-05 | R-06-BEFF-2022-B1-L4 | R-06-BEFF-2022-B1-L4 | 2022-02-24 |  | 2022-03-15 | 2022-03-24 | 2022-07-08 | Early Riser Construction | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region VI | Iloilo | 116096 | Calangag PS | BATAD | 5 | 1 | 2 | Repair of Classrooms | 683361.1 | 1 | 659836.94 | COMPLETED | 1 | 2022-11-08 | 2022-08-23 | R-06-BEFF-2022-B1-L3 | R-06-BEFF-2022-B1-L3 | 2022-02-24 |  | 2022-03-15 | 2022-03-24 | 2022-07-11 | Anjush Builders | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region VI | Iloilo | 116101 | Tanao ES | BATAD | 5 | 1 | 2 | Repair of Classrooms | 747593.46 | 1 | 722281.84 | COMPLETED | 1 | 2022-11-08 | 2022-08-23 | R-06-BEFF-2022-B1-L3 | R-06-BEFF-2022-B1-L3 | 2022-02-24 |  | 2022-03-15 | 2022-03-24 | 2022-07-11 | Anjush Builders | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region VI | Iloilo | 116764 | Poscolon ES | SAN RAFAEL | 5 | 1 | 1 | Repair of Classroom | 488869.98 | 1 | 485512.27 | COMPLETED | 1 | 2022-11-05 | 2022-08-05 | R-06-BEFF-2022-B1-L4 | R-06-BEFF-2022-B1-L4 | 2022-02-24 |  | 2022-03-15 | 2022-03-24 | 2022-07-08 | Early Riser Construction | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region VI | Aklan | 114681 | Batan Elementary School | BATAN | 1st | 1 | 4 | Repair of Classrooms | 2517098.85 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VI | Aklan | 500179 | Kalibo Integrated Special Education Center | KALIBO (Capital) | 1st | 1 | 7 | Repair of Classrooms | 4617114.33 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | Region VI | Aklan | 178002 | Balusbos PS | BURUANGA | 2nd | 1 | 2 | Repair of Classrooms | 1594051.72 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VI | Aklan | 302320 | Maloco NHS | IBAJAY | 2nd | 1 | 3 | Repair of Classrooms | 1198143.75 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VI | Aklan | 302295 | Boracay NHS-Main | MALAY | 2nd | 1 | 4 | Repair of Classrooms | 5000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VI | Aklan | 114852 | Naasog Elementary School | MALAY | 2nd | 1 | 1 | Repair of Classrooms | 708172.08 | DEPED (Batch 1) | 681489.93 | COMPLETED | 1 | 2024-01-15 | 2023-12-22 |  |  | 2023-11-06 | 2023-11-13 | 2023-11-27 | 2023-11-29 | 2023-12-01 | Solid Merchandising |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region VI | Aklan | 114853 | Nabaoy Elementary School | MALAY | 2nd | 1 | 3 | Repair of Classrooms | 1827985.82 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VI | Aklan | 500035 | Numancia Integrated School | NUMANCIA | 2nd | 1 | 12 | Repair of Classrooms | 8133082.16 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2023 | Region VI | Antique | 114942 | Iba ES | ANINI-Y | Lone | 1 | 6 | Repair of Classrooms | 3233299.32 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VI | Antique | 114953 | San Ramon ES | ANINI-Y | Lone | 1 | 5 | Repair of Classrooms | 3399770.56 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | Already conducted final inspection. Contractor complying to punchlist | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VI | Antique | 114959 | Binangbang Elementary School | BARBAZA | Lone | 1 | 7 | Repair of Classrooms | 4550000 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | Delayed due to delay on the approval of variation orders | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | Region VI | Antique | 114976 | Concepcion ES | BELISON | Lone | 1 | 8 | Repair of Classrooms | 5240747.43 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | Delayed due to delay on the approval of variation orders | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region VI | Antique | 115000 | Tono-an ES | BUGASONG | Lone | 1 | 11 | Repair of Classrooms | 4904925.59 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | For final inspection | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2023 | Region VI | Antique | 115052 | San Antonio ES | CULASI | Lone | 1 | 10 | Repair of Classrooms | 6500000 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | Delayed due to delay on the approval of variation orders | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2023 | Region VI | Antique | 115074 | La Paz ES | HAMTIC | Lone | 1 | 8 | Repair of Classrooms | 5200000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region VI | Antique | 115135 | San Juan PS | LIBERTAD | Lone | 1 | 2 | Repair of Classrooms | 1212359.82 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VI | Antique | 115354 | Tuno Elementary School | TIBIAO | Lone | 1 | 11 | Repair of Classrooms | 7150000 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | Delayed due to delay on the approval of variation orders | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2023 | Region VI | Antique | 115367 | Igbalogo Elementary School | TOBIAS FORNIER (DAO) | Lone | 1 | 4 | Repair of Classrooms | 2600000 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | Delayed due to delay on the approval of variation orders | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VI | Antique | 115381 | Nasuli ES | TOBIAS FORNIER (DAO) | Lone | 1 | 5 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | Delayed due to delay on the approval of variation orders | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VI | Bacolod City | 302705 | Domingo Lacson NHS | BACOLOD CITY (Capital) | Lone | 1 | 63 | Repair of Classrooms | 16000000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 63 | 0 | 0
REPAIR 2023 | Region VI | Bago City | 117494 | Abuanan ES | BAGO CITY | 4th | 1 | 5 | Repair of Classrooms | 2988398.2 | DPWH (Batch 1) | 2840490.97 | COMPLETED | 1 |  |  |  | 23GN0088 | [5 empty] | 3rd Dragon Builders Innovation | for punchlisting | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VI | Bago City | 117499 | Ma. Rosario Araneta ES | BAGO CITY | 4th | 1 | 2 | Repair of Classrooms | 967373.67 | DEPED (Batch 1) |  | Reverted | 0 | [10 empty] | Reverted; Revised Program of Works due to increased in the amount of allocation. New allocation amount is 933,515.59 as reflected in the Sub-ARO | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2023 | Region VI | Bago City | 302725 | Ramon Torres Taloc NHS | BAGO CITY | 4th | 1 | 5 | Repair of Classrooms | 3685984.43 | DPWH (Batch 1) | 3556969.35 | COMPLETED | 1 |  |  |  | 23GN0089 | [5 empty] | SBK Construction Supplies &Services, Inc. | Punchlisted; For rectification works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VI | Cadiz City | 117531 | Cadiz East Elem. School II | CADIZ CITY | 2nd | 1 | 6 | Repair of Classrooms | 4033015.36 | DPWH (Batch 1) |  | Ongoing | 0.53 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2023 | Region VI | Cadiz City | 117546 | Cadiz East I ES | CADIZ CITY | 2nd | 1 | 6 | Repair of Classrooms | 2641333.48 | DPWH (Batch 1) |  | Ongoing | 0.53 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2023 | Region VI | Cadiz City | 117577 | M.V. Gamboa ES | CADIZ CITY | 2nd | 1 | 9 | Repair of Classrooms | 4138015.36 | DPWH (Batch 1) |  | Ongoing | 0.53 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0
REPAIR 2023 | Region VI | Guimaras | 115863 | Hoskyn Elementary School | JORDAN (Capital) | Lone | 1 | 13 | Repair of Classrooms | 8131708.84 | DPWH (Batch 1) |  | COMPLETED | 1 | 2024-02-05 | 2024-10-18 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2023 | Region VI | Guimaras | 115906 | Guiwanon Elementary School | NUEVA VALENCIA | Lone | 1 | 3 | Repair of Classrooms | 2292876.22 | DPWH (Batch 1) |  | COMPLETED | 1 | 2023-11-22 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VI | Guimaras | 115884 | Casilan Elementary School | SIBUNAG | Lone | 1 | 3 | Repair of Classrooms | 2404681.08 | DPWH (Batch 1) |  | COMPLETED | 1 | 2023-11-07 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VI | Himamaylan City | 117076 | Himamaylan CS | CITY OF HIMAMAYLAN | 5th | 1 | 32 | Repair of Classrooms | 20710702.02 | DPWH (Batch 1) |  | COMPLETED | 1 | 2024-03-12 | [8 empty] | RISM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0
REPAIR 2023 | Region VI | Himamaylan City | 302649 | Himamaylan NHS | CITY OF HIMAMAYLAN | 5th | 1 | 40 | Repair of Classrooms | 18127395.24 | DPWH (Batch 1) | 16617280.35 | COMPLETED | 1 | 2024-03-12 |  |  | 23GL0110 | [5 empty] | YRJ ENGINEERING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 0 | 0
REPAIR 2023 | Region VI | Iloilo | 116564 | Aguiauan Elementary School | MIAGAO | 1st | 1 | 4 | Repair of Classrooms | 2016272.62 | DPWH (Batch 1) |  | Ongoing | 0.95 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
REPAIR 2023 | Region VI | Iloilo | 116716 | Amboyu-an Elementary School | SAN JOAQUIN | 1st | 1 | 7 | Repair of Classrooms | 1982221.74 | DPWH (Batch 1) |  | Ongoing | 0.95 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0
REPAIR 2023 | Region VI | Iloilo | 116741 | San Luis ES | SAN JOAQUIN | 1st | 1 | 7 | Repair of Classrooms | 2488661.91 | DPWH (Batch 1) |  | Ongoing | 0.95 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0
REPAIR 2023 | Region VI | Iloilo | 116749 | Valverde ES | SAN JOAQUIN | 1st | 1 | 6 | Repair of Classrooms | 3305929.51 | DPWH (Batch 1) |  | Ongoing | 0.95 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2023 | Region VI | Iloilo | 180013 | Sambag PS | ZARRAGA | 2nd | 1 | 2 | Repair of Classrooms | 907827.62 | DEPED (Batch 2) | 692960.41 | COMPLETED | 1 | 2025-02-15 | 2024-09-28 | BEFF2023 B2-RVI-022-ILOILO-L1 | BEFF2023 B2-RVI-022-ILOILO-L1 | 2024-04-15 | 2024-04-15 | 2024-04-29 | 2024-08-12 | 2024-09-16 | ANJUSH BUILDERS | SDo does not received any ATPor memo/ sub-aro to facilitate this project. Previously it was realigned to zaraga CES by DPWH | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VI | Iloilo | 116863 | Zarraga CES | ZARRAGA | 2nd | 1 | 2 | Repair of Classrooms | 3540000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VI | Iloilo | 116104 | Alabidhan ES | BINGAWAN | 3rd | 1 | 11 | Repair of Classrooms | 5948743.45 | DPWH (Batch 1) |  | Ongoing | 0.95 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0
REPAIR 2023 | Region VI | Iloilo | 116114 | Quinangyana ES | BINGAWAN | 3rd | 1 | 10 | Repair of Classrooms | 5021523.53 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2023 | Region VI | Iloilo | 116115 | Quinar-upan Elementary School | BINGAWAN | 3rd | 1 | 11 | Repair of Classrooms | 4918391.96 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2023 | Region VI | Iloilo | 116173 | Agcalaga ES | CALINOG | 3rd | 1 | 2 | Repair of Classrooms | 2500000 | DPWH (Batch 2) |  | Ongoing | 0.95 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
REPAIR 2023 | Region VI | Iloilo | 116448 | Cabatangan PS | LAMBUNAO | 3rd | 1 | 4 | Repair of Classrooms | 5000000 | DPWH (Batch 2) |  | Ongoing | 0.95 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
REPAIR 2023 | Region VI | Iloilo | 116601 | Janipa-an Elementary School | MINA | 3rd | 1 | 5 | Repair of Classrooms | 2915360.46 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VI | Iloilo | 116097 | Caw-i Primary School | BATAD | 5th | 1 | 2 | Repair of Classrooms | 2700000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VI | Iloilo | 116761 | Cabas-an ES | SAN RAFAEL | 5th | 1 | 8 | Repair of Classrooms | 6000000 | DPWH (Batch 1) |  | Ongoing | 0.95 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0
REPAIR 2023 | Region VI | Iloilo City | 117581 | Calaparan ES | ILOILO CITY (Capital) | Lone | 1 | 15 | Repair of Classrooms | 3253237.06 | DPWH (Batch 1) | 3107980.01 | COMPLETED | 1 | 20/2/2024 |  | 170 | 23GJ0124 | 2023-08-09 | 15/9/2023 | 27/9/2023 | 13/11/2023 | 17/11/2023 | BEATUS BUILDERS | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2023 | Region VI | Iloilo City | 117629 | Jalandoni MS | ILOILO CITY (Capital) | Lone | 1 | 2 | Repair of Classrooms | 814156.9 | DEPED (Batch 1) | 667973.35 | COMPLETED | 1 | 2024-07-02 | 2024-05-04 | NONE | 2023-12-002 | 2023-10-20 | 2023-10-27 | 2023-12-12 | 2023-12-19 | 2023-12-29 | STEVEN CONSTRUCTION & SUPPLY | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VI | Iloilo City | 302747 | La Paz NHS - San Isidro Campus | ILOILO CITY (Capital) | Lone | 1 | 18 | Repair of Classrooms | 4354560 | DPWH (Batch 2) | 4194560.04 | COMPLETED | 1 | 2024-05-18 | 2024-06-09 | NONE | 23GJ0136 | [5 empty] | BENSON Const. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0
REPAIR 2023 | Region VI | Iloilo City | 117583 | Severo Abeto ES | ILOILO CITY (Capital) | Lone | 1 | 3 | Repair of Classrooms | 1167217.69 | DPWH (Batch 1) | 1075666.4 | COMPLETED | 1 | 21/1/2024 |  | 170 | 23GJ0125 | 2023-08-09 | 15/9/2023 | 27/9/2023 | 13/11/2023 | 17/11/2023 | NOE'S BUILDERS | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VI | Iloilo City | 117584 | Sto. Domingo ES | ILOILO CITY (Capital) | Lone | 1 | 2 | Repair of Classrooms | 806455.7 | DEPED (Batch 1) | 581887.65 | COMPLETED | 1 | 2024-07-02 | 2024-05-04 | NONE | 2023-12-002 | 2023-10-20 | 2023-10-27 | 2023-12-12 | 2023-12-19 | 2023-12-29 | STEVEN CONSTRUCTION & SUPPLY | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VI | Iloilo City | 117610 | Ticud ES | ILOILO CITY (Capital) | Lone | 1 | 4 | Repair of Classrooms | 725760 | DEPED (Batch 2) | 619354.91 | COMPLETED | 1 | 2024-09-05 | 2024-08-30 | NONE | 2024-02-001 | 2024-01-05 | 2024-01-12 | 2024-01-26 | 2024-03-28 | 2024-04-01 | NORTH STAR CONST. & TRADING | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VI | Kabankalan City | 117885 | Locotan ES | CITY OF KABANKALAN | 6th | 1 | 16 | Repair of Classrooms | 8750000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2023 | Region VI | Kabankalan City | 302790 | TAGUKON NATIONAL HIGH SCHOOL | CITY OF KABANKALAN | 6th | 1 | 9 | Repair of Classrooms | 7400000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2023 | Region VI | La Carlota City | 117646 | Haguimit ES | LA CARLOTA CITY | 4th | 1 | 6 | Repair of Classrooms | 2929318.76 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VI | La Carlota City | 117636 | La Carlota South ES I | LA CARLOTA CITY | 4th | 1 | 5 | Repair of Classrooms | 2147772.31 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VI | La Carlota City | 117645 | Miguel S. Mondia ES | LA CARLOTA CITY | 4th | 1 | 1 | Repair of Classrooms | 627522.77 | DEPED (Batch 1) | 575,831.40/29,723.19 | COMPLETED | 1 | 2024-04-30 | 2024-03-06 | PI2023-42 | 2024-01-004 | 2023-12-14 | 2024-01-06 | 2024-01-10 | 2024-01-19 | 2024-01-30 | Woodtrade Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region VI | La Carlota City | 117642 | Nagasi ES | LA CARLOTA CITY | 4th | 1 | 4 | Repair of Classrooms | 2428520.48 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VI | La Carlota City | 117649 | San Miguel ES I | LA CARLOTA CITY | 4th | 1 | 2 | Repair of Classrooms | 1210779.49 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VI | San Carlos City | 302774 | Don Carlos Ledesma NHS | SAN CARLOS CITY | 1st | 1 | 23 | Repair of Classrooms | 52600000 | DPWH (Batch 1) | 49509727.06 | Ongoing | 0.95 | 2024-10-01 |  | 23GQ0071 |  | 2023-09-05 | 2023-09-12 | SEPT. 28, 2023 | 2023-10-27 |  | Kenneth Construction & General Merchandise | On-going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0
REPAIR 2023 | Region VI | San Carlos City | 117749 | Marago-os ES | SAN CARLOS CITY | 1st | 1 | 3 | Repair of Classrooms | 8000000 | DPWH (Batch 1) | 7250984.52 | COMPLETED | 1 | 2024-04-06 |  | 23GQ0072 |  | 2023-09-05 | 2023-09-12 | 2023-09-28 | 2023-10-27 |  | Kenneth Construction & General Merchandise | Finished | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VI | Silay City | 185001 | Dominador 'Oking' Jison Memorial Elementary School | SILAY CITY | 3rd | 1 | 6 | Repair of Classrooms | 3811382.65 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | For punclisting | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VI | Silay City | 302779 | Don Felix T. Lacson Memorial National High School | SILAY CITY | 3rd | 1 | 6 | Repair of Classrooms | 2073578.52 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | For punclisting | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VI | Silay City | 117813 | Don Homero H. Tanpinco ES | SILAY CITY | 3rd | 1 | 8 | Repair of Classrooms | 3131408.66 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | For punclisting | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region VI | Silay City | 500201 | Violeta Integrated School | SILAY CITY | 3rd | 1 | 4 | Repair of Classrooms | 1120212.37 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | For punclisting | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2024 | Region VI | Aklan | 114908 | Ochando ES | NEW WASHINGTON | 1st | 1 | 6 | Repair of Classrooms | 3496545.95 | 1 |  | Under Procurement | 0 |  |  |  |  | 2024-06-07 | 2024-06-14 | 2024-06-26 |  |  | Nems Construction and Supply | Waiting for BAC Decision | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0
REPAIR 2024 | Region VI | Aklan | 114914 | Aliputos Elementary School | NUMANCIA | 2nd | 1 | 2 | Repair of Classrooms | 1181532.45 | 1 |  | Under Procurement | 0 |  |  |  |  | 2024-06-07 | 2024-06-14 | 2024-06-26 |  |  | Nems Construction and Supply | Waiting for BAC Decision | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
REPAIR 2024 | Region VI | Antique | 115285 | Sebaste CS | SEBASTE | Lone | 1 | 5 | Repair of Classrooms | 4423057.18 | 1 | 3997606.9 | COMPLETED | 1 | 2025-04-09 |  | R6-D2-GAA2024-30-SR | R6-D2-GAA2024-30-SR | 2024-09-10 | 2024-09-17 | 2024-10-01 | 2024-11-04 | 2024-11-18 | One Piece Builders | On-going, with proposed variation order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2024 | Region VI | Bacolod City | 117458 | Fernando F. Gonzaga Elementary School | BACOLOD CITY (Capital) | Lone | 1 | 6 | Repair of Classrooms | 3031152.68 | 1 | 2950000 | COMPLETED | 1 | 23/04/2025 |  | REPAIR 2024 -R06- BACOLOD CITY - 001 | R6BCD10112024-P159 | 2024-10-15 | 2024-10-22 | 2024-11-04 | 17/1/2025 | 17/1/2025 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | Ongoing implementation | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | Region VI | Cadiz City | 117538 | San Andres ES | CADIZ CITY | 2nd | 1 | 6 | Repair of Classrooms | 4292668.79 | 1 | 4149742.1 | COMPLETED | 1 |  |  |  |  | 2024-08-01 | 2024-08-12 | 2024-08-27 | 2024-08-28 |  | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | Region VI | Capiz | 115433 | Dao Central School | DAO | 2nd | 1 | 5 | Repair of Classrooms | 4054969.82 | 1 | 2694426.46 | COMPLETED | 1 | 2025-03-08 | 2024-12-12 | R6-DEPED-CAPIZ-CY2024-BEFF-BATCH1-LOT1 |  | 2024-06-28 | 2024-07-10 | 2024-07-22 | 2024-08-15 | 2024-10-03 | MARIZALOI Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2024 | Region VI | Escalante City | 302625 | Escalante National High School | CITY OF ESCALANTE | 1st | 1 | 4 | Repair of Classrooms | 2873738.94 | 1 | 2100000 | COMPLETED | 1 | 2024-02-02 |  | Project 03-2024 | Project 03, 2024 | 2024-07-23 | Augusut 1, 2024 | 2024-08-13 | 2024-09-11 | 2024-10-02 | Valkyrie Construction | Completed with approved VO in the amount of Php 200,160.90 and revised project completion is March 21, 2025 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2024 | Region VI | Guimaras | 115835 | Agsanayan Elementary School | BUENAVISTA | Lone | 1 | 3 | Repair of Classrooms | 2153338.98 | 1 | 1874685.87 | COMPLETED | 1 | 2025-01-31 | 2025-01-20 | Project 09-2024 | Project 09-2024 | 2024-05-29 | 2024-06-07 | 2024-06-20 | 2024-06-12 | 2024-09-27 | ALJ Construction & Supply | Completed with approved VO in the amount of 184, 878.02 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2024 | Region VI | Guimaras | 115892 | Calaya Elementary School | NUEVA VALENCIA | Lone | 1 | 3 | Repair of Classrooms | 2227973.84 | 1 | 1874685.87 | COMPLETED | 1 | 2025-01-31 | 2025-01-20 | Project 09-2024 | Project 09-2024 | 2024-05-29 | 2024-06-07 | 2024-06-20 | 2024-06-12 | 2024-09-27 | ALJ Construction & Supply | Completed with approved VO in the amount of 184, 878.02 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2024 | Region VI | Himamaylan City | 117092 | Cabanbanan ES | CITY OF HIMAMAYLAN | 5th | 1 | 5 | Repair of Classrooms | 4118434.58 | 1 | 2949000 | COMPLETED | 1 | 2025-03-09 | 2025-01-16 | IB-sdhc-062024-002 | IB-sdhc-062024-002 | 2024-06-26 | 2024-07-05 | 2024-07-17 | Sept. 3, 2024 | 2024-09-27 | RISM BUILDERS AND CONSTRUCTION SERVICES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2024 | Region VI | Iloilo | 116733 | Lawigan ES | SAN JOAQUIN | 1st | 1 | 5 | Repair of Classrooms | 2685430.12 | 1 | 2287984.48 | COMPLETED | 1 | 2025-04-04 |  | BEFF2024-RVI-022-ILOILO-REPAIR-L1 | BEFF2024-RVI-022-ILOILO-REPAIR-L1 | 2024-07-03 | 2024-07-10 | 2024-07-22 | 2024-10-11 | 2024-11-29 | PAG-UN BUILDERS & SUPPLY | For issuance of contract | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2024 | Region VI | Iloilo City | 302744 | Jaro National High School | ILOILO CITY (Capital) | Lone | 1 | 52 | Repair of Classrooms | 4219499.09 | 1 | 3165997.45 | COMPLETED | 1 | 2025-04-15 |  |  | 2024-08-002 | 23/07/2024 | 30/07/2024 | 13/08/2023 | 19/09/2024 | 2024-10-11 | MJBL CONST. SERVICES | On-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 52 | 0 | 0
REPAIR 2024 | Region VI | Kabankalan City | 117829 | Badiangay Elementary School | CITY OF KABANKALAN | 6th | 1 | 6 | Repair of Classrooms | 4273340.4 | 1 | 4207191 | not yet started | 0 |  |  | 2024-SB-03-PB003 |  | 2024-09-20 | 2024-09-26 | 2024-10-09 | 2024-10-15 |  | RISM BUILDERS AND CONSTRUCTION SERVICES INC. | For contract perfection | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
REPAIR 2024 | Region VI | La Carlota City | 117648 | La Granja ES | LA CARLOTA CITY | 4th | 1 | 6 | Repair of Classrooms | 4846699.89 | 1 | 3205383.35 | COMPLETED | 1 | 2025-12-30 | 2024-01-30 | 2024-15 |  | 2024-07-07 | 2024-07-14 | 2024-07-23 | 2024-08-16 | 2024-08-23 | EVERACTIVE CONSTRUCTION AND ENGINEERING SERVICES | 100% Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | Region VI | Passi City | 117898 | Bagacay Elementary School | CITY OF PASSI | 4th | 1 | 6 | Repair of Classrooms | 3641829.26 | 1 | 2522888.34 | COMPLETED | 1 | 2025-05-05 | 2025-02-21 | BEFF-REPAIR | RO6-D14-FY2024-BEFF-REPAIR-BAGACAY ES | 2024-07-20 | 2024-07-26 | 2024-08-06 | 2024-08-19 | 2024-11-29 | Early Riser Construction | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | Region VI | Passi City | 117917 | BATU ELEMENTARY SCHOOL | CITY OF PASSI | 4th | 1 | 7 | Repair of Classrooms | 5192559.24 | 1 | 3544345.94 | COMPLETED | 1 | 2025-05-05 | 2025-04-10 | BEFF-REPAIR | RO6-D14-FY2024-BEFF-REPAIR-BATU ES | 2024-07-20 | 2024-07-26 | 2024-08-06 | 2024-08-19 | 2024-11-29 | Early Riser Construction | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2024 | Region VI | Roxas City | 501336 | Cogon Integrated School | ROXAS CITY (Capital) | 1st | 1 | 3 | Repair of Classrooms | 5209139.51 | 1 | 3610777.43 | COMPLETED | 1 | 2025-05-18 | 2025-01-28 | 2024-059 | CON-2024-059 | sept. 16, 2024 | sept. 24, 2024 | 2024-10-08 | 2024-12-03 | 2024-12-09 | Reubin L. Yap, Contractor | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2024 | Region VI | Sagay City | 500036 | Colonia Divina Integrated School | SAGAY CITY | 2nd | 1 | 3 | Repair of Classrooms | 1968909.78 | 1 | 1580000 | COMPLETED | 1 | 2025-01-31 | 2025-01-20 | CPB-INFRA-01-2024 | CPB-INFRA-01-2024 | 2024-06-29 | 2024-07-05 | 2024-07-22 | 2024-08-02 | 2024-09-26 | KEANNE CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2024 | Region VI | Sagay City | 117733 | Lopez Jaena Elementary School | SAGAY CITY | 2nd | 1 | 3 | Repair of Classrooms | 1687636.95 | 1 | 1355000 | COMPLETED | 1 | 2025-01-31 | 2025-01-20 | CPB-INFRA-02-2024 | CPB-INFRA-02-2024 | 2024-06-29 | 2024-07-05 | 2024-07-22 | 2024-08-02 | 2024-09-26 | VALKYRIE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2024 | Region VI | San Carlos City | 117745 | Don Juan Ledesma ES | SAN CARLOS CITY | 1st | 1 | 2 | Repair of Classrooms | 919209.43 | 1 | 912811.81 | COMPLETED | 1 | 2024-12-30 | 2024-10-24 |  | PR# 2024-06-0044 |  |  | 2024-06-28 |  | 2024-09-28 | TMTC Construction & Supply | for approval of resolution to award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2024 | Region VI | Silay City | 117812 | Camantero Elementary School | SILAY CITY | 3rd | 1 | 6 | Repair of Classrooms | 4245236.51 | 1 | 4196891.26 | Not Yet Started | 0 |  |  |  |  | 2024-06-29 | 2024-07-08 | 2024-07-22 | 2024-08-21 |  | PAR Builders Electrical and Construction Supply Corp. | Perfection of Contract | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
REPAIR 2024 | Region VI | Sipalay City | 117372 | Canturay ES | CITY OF SIPALAY | 6th | 1 | 12 | Repair of Classrooms | 4380647.68 | 1 |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0
REPAIR 2024 | Region VI | Victorias City | 117444 | Salvacion ES | CITY OF VICTORIAS | 3rd | 1 | 5 | Repair of Classrooms | 4195227.21 | 1 | 2686903.84 | COMPLETED | 1 | 2025-03-15 |  | SDOVC-INFRA2024-002 | SDOVC-INFRA2024-002 | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%