## Sheet1
Program-Year | CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
NC 2014 | K10 (2014) | Region VII | Bais City | 323004 | Cambagahan National HS | BAIS CITY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-16 | 2015-04-17 | 070314S00118 | 14HK0020 | 2014-08-07 | 2014-08-22 | 2014-11-17 | 2014-12-09 | 2014-12-16 | L.C. CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bais City | 120089 | Cambaguio ES | BAIS CITY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-08-19 | 070314S00137 | 14HK0018 | 2014-08-07 | 2014-08-22 | 2014-12-11 | 2014-12-22 | 2014-12-29 | STARS & STRIPES CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bais City | 120075 | Cansanag ES | BAIS CITY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2015-02-16 | 2015-04-17 | 070314S00124 | 14HK0019 | 2014-08-07 | 2014-08-22 | 2014-11-14 | 2014-11-28 | 2014-12-16 | L.C. CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bais City | 120092 | Lonoy Elementary School | BAIS CITY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-16 | 2015-04-15 | 070314S00113 | 14HK0020 | 2014-08-07 | 2014-08-22 | 2014-12-11 | 2014-12-15 | 2014-12-17 | L.C. CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bais City | 303215 | Lonoy National High School | BAIS CITY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bais City | 120095 | Mabunao ES | BAIS CITY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-08-18 | 070314S00114 | 14HK0018 | 2014-08-07 | 2014-08-22 | 2014-12-11 | 2014-12-22 | 2014-12-29 | STARS & STRIPES CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bais City | 323007 | Mansangaban National HS | BAIS CITY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bais City | 120077 | Olympia ES | BAIS CITY | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4593399.6094 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-05-20 | 070314S00197 | 14HK0050 | 2014-12-14 | 2014-12-23 | 2014-12-29 | 2014-12-29 | 2014-12-29 | RICHFIELD BUILDERS
NC 2014 | K10 (2014) | Region VII | Bais City | 120103 | Sab-ahan ES | BAIS CITY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2015-02-16 | 2015-04-16 | 070314S00115 | 14HK0019 | 2014-08-07 | 2014-08-22 | 2014-11-14 | 2014-11-28 | 2014-12-16 | L.C. CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bais City | 237502 | Talungon Elementary School | BAIS CITY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1 | 2015-03-10 | 2015-03-10 | 070314S00116 | 14HK0019 | 2014-08-07 | 2014-08-22 | 2014-11-14 | 2014-11-28 | 2014-12-01 | L.C. CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bayawan City | 120167 | Uban-uban PS | Bayawan City | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1751222.0788 |  |  | COMPLETED | 1 | 2015-03-27 | 2015-03-27 | 070314S00189 | 14HL0032 | 2014-09-17 | 2014-09-28 | 2014-09-30 | 2014-10-09 | 2014-10-22 | CRIZEL CONSTRUCTION & CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region VII | Bayawan City | 232001 | Baican PS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2965174.43 |  |  | COMPLETED | 1 | 2015-06-03 | 2015-06-03 | 070314S00112 | 14HL0020 | 2014-11-26 | 2014-12-05 | 2014-12-09 | 2014-12-17 | 2014-12-29 | ASCENTIA CONSTRUCTION, INC.
NC 2014 | K10 (2014) | Region VII | Bayawan City | 303239 | Kalamtukan NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 990387.4407 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bayawan City | 120158 | Kangkawit PS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-05-04 | 2015-05-04 | 070314S00120 | 14HL0022 | 2014-11-26 | 2014-12-05 | 2014-12-09 | 2014-12-17 | 2014-12-29 | ASCENTIA CONSTRUCTION, INC.
NC 2014 | K10 (2014) | Region VII | Bayawan City | 321909 | Malabugas HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6313739.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bayawan City | 232003 | Napo ES | CITY OF BAYAWAN (TULONG) | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-03-27 | 2015-03-27 | 070314S00126 | 14HL0021 | 2014-09-17 | 2014-09-28 | 2014-09-30 | 2014-10-09 | 2014-10-22 | CRIZEL CONSTRUCTION & CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region VII | Bayawan City | 321904 | Villasol NHS | Bayawan City | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 976682.6705 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Dumaguete City | 303166 | Camanjac NHS | DUMAGUETE CITY (Capital) | 2 | 1 | 5 | 1STY 2CL & 1STY 3CL | 2014 K10 BATCH 1 | 4965592 |  |  | COMPLETED | 1 | 2015-11-03 |  | 070314S00129 | 15HK0077 | 2014-08-07 | 2014-08-22 | 2014-11-19 | 2014-09-11 | 2014-09-18 | C. LARA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Dumaguete City | 119945 | Cantil-e ES | DUMAGUETE CITY (Capital) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2015-01-17 | 2015-01-13 | 070314S00127 | 14HK0012 | 2014-08-07 | 2014-08-22 | 2014-09-02 | 2014-09-12 | 2014-09-22 | TRINITY CONSTRUCTION AND DEVELOPMENT
NC 2014 | K10 (2014) | Region VII | Dumaguete City | 119948 | Junob ES | DUMAGUETE CITY (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-01-17 | 2015-01-14 | 070314S00128 | 14HK0012 | 2014-08-07 | 2014-08-22 | 2014-09-02 | 2014-09-12 | 2014-09-22 | TRINITY CONSTRUCTION AND DEVELOPMENT
NC 2014 | K10 (2014) | Region VII | Dumaguete City | 312601 | PIAPI HIGH SCHOOL | DUMAGUETE CITY (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Dumaguete City | 312601 | PIAPI HIGH SCHOOL | DUMAGUETE CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8228453.2031 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Guihulngan City | 120233 | Antibalas ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | REVERTED | 0 |  |  | 070314S00131 | 070314S00131 | 2014-09-27 | 2014-10-09 | 2014-10-14 | 2014-11-04 | 2014-11-14
NC 2014 | K10 (2014) | Region VII | Guihulngan City | 120263 | Balogo ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-08-30 | 2015-08-30 | 070314S00217 | 070314S00217 | 2014-11-28 | 2014-12-19 | 2014-12-22 | 2015-01-22 | 2015-01-27 | GLUBROS DEVELOPMENT INC.
NC 2014 | K10 (2014) | Region VII | Guihulngan City | 120236 | Bonbon ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | REVERTED | 0 |  |  | 070314S00132 | 070314S00132 | 2014-09-27 | 2014-10-09 | 2014-10-14 | 2014-11-05 | 2014-11-14 |  | RECOMMENDATION FOR CONTRACT TERMINATION SUBMITTED TO DPWH REGIONAL OFFICE
NC 2014 | K10 (2014) | Region VII | Guihulngan City | 120240 | Cabal-asan PS | CITY OF GUIHULNGAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | REVERTED | 0 |  |  | 070314S00133 | 070314S00133 | 2014-10-30 | 2014-11-06 | 2014-11-12 | 2014-12-02 | 2014-12-18 |  | RECOMMENDATION FOR CONTRACT TERMINATION SUBMITTED TO DPWH REGIONAL OFFICE
NC 2014 | K10 (2014) | Region VII | Guihulngan City | 120248 | Lag-asan ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | REVERTED | 0 |  |  | 070314S00134 | 070314S00134 | 2014-10-30 | 2014-11-06 | 2014-11-12 | 2014-12-02 | 2014-12-18 |  | RECOMMENDATION FOR CONTRACT TERMINATION SUBMITTED TO DPWH REGIONAL OFFICE
NC 2014 | K10 (2014) | Region VII | Guihulngan City | 120250 | Lip-o ES | CITY OF GUIHULNGAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | REVERTED | 0 |  |  | 070314S00135 | 070314S00135 | 2014-10-30 | 2014-11-06 | 2014-11-12 | 2014-12-02 | 2014-12-18 |  | RECOMMENDATION FOR CONTRACT TERMINATION SUBMITTED TO DPWH REGIONAL OFFICE
NC 2014 | K10 (2014) | Region VII | Guihulngan City | 120254 | Matu-og ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4372299.6094 |  |  | COMPLETED | 1 | 2016-03-07 |  | 070314S00210 | 070314S00210 | 2015-07-24 | 2015-08-06 | 2015-08-11 | 2015-09-02 | 2015-09-23 | 8G CONSTRUCTION AND GENERAL SERVICES
NC 2014 | K10 (2014) | Region VII | Guihulngan City | 120281 | Plagatasanon ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4342149.6094 |  |  | COMPLETED | 1 | 2016-05-20 |  | 070314S00216 | 15HJ0167 | 2015-03-23 | 2015-05-19 | 2015-11-03 | 2015-11-20 | 2015-12-01 | SILLIMAN AVENUE CONST & SUPPLY (FORMERLY OVERDRIVE
NC 2014 | K10 (2014) | Region VII | Guihulngan City | 120257 | Sandayao ES | CITY OF GUIHULNGAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | REVERTED | 0 |  |  | 070314S00100 | 14HJ0006 | 2014-06-18 | 2014-07-16 | 2014-07-25 | 2014-08-12 | 2014-08-20 | LAB GENERAL ENGINEERING
NC 2014 | K10 (2014) | Region VII | TANJAY CITY | 234005 | Bulo ES | Tanjay City | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2547363.8262 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-12 | 070314S00188 | 14HK0039 | 2014-11-06 | 2014-11-18 | 2014-11-19 | 2014-12-22 | 2014-12-29 | RICHFIELD BUILDERS
NC 2014 | K10 (2014) | Region VII | TANJAY CITY | 120407 | Abante ES | PAMPLONA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | REVERTED | 0 |  |  | 070314S00020 | 14HK0037 | 2014-08-07 | 2014-08-22 | 2014-11-19 | 2014-12-02 |  | RICHFIELD BUILDERS
NC 2014 | K10 (2014) | Region VII | TANJAY CITY | 120414 | Fatima ES | PAMPLONA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2014-12-19 | 070314S00032 | 14HK0014 | 2014-08-07 | 2014-08-22 | 2014-09-02 | 2014-09-11 | 2014-09-30 | RICHFIELD BUILDERS
NC 2014 | K10 (2014) | Region VII | Tanjay City | 322301 | Graciano Banogon HS | CITY OF TANJAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-11 | 070314S00059 | 14HK0026 | 2014-08-07 | 2014-08-22 | 2014-09-04 | 2014-09-15 | 2014-09-29 | RICHFIELD BUILDERS
NC 2014 | K10 (2014) | Region VII | TANJAY CITY | 120415 | Hunop ES | PAMPLONA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-07 | 2014-12-18 | 070314S00033 | 14HK0013 | 2014-08-07 | 2014-08-22 | 2014-09-02 | 2014-09-12 | 2014-09-22 | R.E. SINGSON CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | TANJAY CITY | 312911 | Hunop HS | PAMPLONA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | TANJAY CITY | 120417 | Inawasan ES | PAMPLONA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1037049.6543 |  |  | COMPLETED | 1 | 2015-12-03 |  | 070314S00232 | 15HK0076 | 2015-08-11 | 2015-08-14 | 2015-08-18 | 2015-08-24 | 2015-08-27 | ZION CONSTRUCTION(FORMERLY MASTERPIECE CONST. & SU
NC 2014 | K10 (2014) | Region VII | TANJAY CITY | 303274 | Isidoro Salma MHS (Balayong ) | PAMPLONA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Tanjay City | 303284 | Lourdes L. del Prado MNHS | CITY OF TANJAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Tanjay City | 322305 | Luca HS | CITY OF TANJAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2080417.57 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-05 | 070314S00060 | 14HK0026 | 2014-08-07 | 2014-08-22 | 2014-09-04 | 2014-09-15 | 2014-09-29 | RICHFIELD BUILDERS
NC 2014 | K10 (2014) | Region VII | Tanjay City | 234003 | Lugta Elementary School | CITY OF TANJAY | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2975174.43 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-10 | 070314S00056 | 14HK0025 | 2014-08-07 | 2014-08-22 | 2014-09-04 | 2014-09-12 | 2014-09-29 | R.E. SINGSON CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | TANJAY CITY | 120424 | Samoyao Elem. School | PAMPLONA | 2 | 1 | 4 | 1STY 1CL & 1STY 3CL | 2014 K10 BATCH 1 | 3972503.55 |  |  | COMPLETED | 1 | 2015-01-27 | 2014-12-22 | 070314S00034 | 14HK0014 | 2014-08-07 | 2014-08-22 | 2014-09-02 | 2014-09-11 | 2014-09-30 | RICHFIELD BUILDERS
NC 2014 | K10 (2014) | Region VII | TANJAY CITY | 303273 | Sta. Agueda NHS | PAMPLONA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2240417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Tanjay City | 303282 | Tanjay NHS (Polo) | CITY OF TANJAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-09 | 070314S00057 | 14HK0025 | 2014-08-07 | 2014-08-22 | 2014-09-04 | 2014-09-12 | 2014-09-29 | R.E. SINGSON CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | BOGO CITY | 302930 | BANBAN NHS | BOGO | 4 | 1 | 3 | 1STY2CL, 1STY1CL | 2014 K10 BATCH 2 | 2935000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | BOGO CITY | 119117 | BINABAG ES | BOGO | 4 | 1 | 6 | 1STY3CL, 1STY1CL, 1STY2CL | 2014 K10 BATCH 2 | 5659000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00172 | 14HD0018 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | GOLDFIN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bogo City | 119107 | Bogo Central School 111 | CITY OF BOGO | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 950215.9023 |  |  | COMPLETED | 1 | 2015-07-05 | 2015-07-05 | 070214S00197 | 15HD0014 | 2015-02-04 | 2015-02-16 | 2015-02-17 | 2015-02-20 | 2015-03-02 | GONZALODO ENTERPRISES
NC 2014 | K10 (2014) | Region VII | Bogo City | 256501 | City of Bogo Science and Arts Academy | CITY OF BOGO | 4 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bogo City | 325001 | City of Bogo Science and Arts Academy | CITY OF BOGO | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | BOGO CITY | 119121 | DAKIT ES | BOGO | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1073000 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-25 | 070214S00187 | 14HD0017 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | ROVILLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | BOGO CITY | 119123 | LAPAZ ES | BOGO | 4 | 1 | 7 | 2U-1STY1CL, 1STY2CL, 1STY3CL | 2014 K10 BATCH 2 | 6702000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00183 | 14HD0018 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | GOLDFIN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bogo City | 302936 | Libertad NHS | CITY OF BOGO | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | BOGO CITY | 119124 | MALINGIN ES | BOGO | 4 | 1 | 4 | 1STY3CL, 1STY1CL | 2014 K10 BATCH 2 | 3797000 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-25 | 070214S00185 | 14HD0017 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | ROVILLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118630 | Abehilan ES | San Isidro | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-09-17 | 2015-09-17 | 070114S00364 | 15HC0032 | 2015-03-31 | 2015-04-12 | 2015-04-13 | 2015-04-17 | 2015-04-21 | AQSIL BUILDERS AND CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118532 | Agahay ES | Maribojoc | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-11-02 | 2015-09-30 | 070114S00357 | 14HA0046 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2015-01-21 | 2015-04-06 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | Region VII | Bohol | 118162 | Alegria ES | Catigbian | 1 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 3 | 2003537.6289 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00396 | 14HA0056 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 117967 | Angilan ES | Antequera | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2016-01-29 | 2015-09-30 | 070114S00402 | 14HA0052 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-05-27 | 2015-07-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118788 | Atty. Maximo C. Lasco Mem. ES | TUBIGON | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2060417.57 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-03-06 | 070114S00168 | 14HA0021 | 2014-09-29 | 2014-09-15 | 2014-09-29 | 2014-10-03 | 2014-11-18 | GAIL CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118164 | Baang ES | Catigbian | 1 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 3 | 4387009.8396 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00397 | 14HA0054 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 117983 | Baclayon Central ES | Baclayon | 1 | 1 | 10 | 2STY8CL & 2STY2CL | 2014 K10 BATCH 3 | 15569883.9844 |  |  | COMPLETED | 1 | 2016-04-15 |  | 070114S00442 | 15HA0063 | 2015-06-19 | 2015-06-10 | 2015-06-19 | 2015-06-25 | 2015-09-21 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118491 | Badbad Elementary School | Loon South | 1 | 1 | 4 | 2UNITS 1STY2CL | 2014 K10 BATCH 3 | 3576429.1398 |  |  | COMPLETED | 1 | 2016-01-01 | 2015-12-30 | 070114S00427 | 15HA0003 | 2015-01-26 | 2015-01-13 | 2015-01-26 | 2015-06-26 | 2015-09-03 | IJK CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118471 | Bagacay ES | Loon North | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3404228.7213 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00451 | 15HA0004 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118165 | Bagtic ES | Catigbian | 1 | 1 | 8 | 2UNITS 1STY2CL, 1STY3CL & 1STY1CL | 2014 K10 BATCH 3 | 7176993.2239 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00398 | 14HA0056 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 117930 | Bahi PS | ALBURQUERQUE | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1838464.5699 |  |  | COMPLETED | 1 | 2015-11-20 | 2015-09-30 | 070114S00382 | 14HA0044 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2015-01-28 | 2015-05-04 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | Region VII | Bohol | 118553 | Balicasag ES | PANGLAO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1112049.6543 |  |  | COMPLETED | 1 | 2016-04-18 |  | 070114S00481 | 15HA0079 | 2015-07-24 | 2015-07-13 | 2015-07-24 | 2015-08-05 | 2015-09-21 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 302907 | Bantolinao National High School | ANTEQUERA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118492 | Basac Elementary School | Loon South | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-12-15 | 070114S00372 | 15HA0002 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118534 | Bayacabac ES | MARIBOJOC | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118534 | Bayacabac ES | Maribojoc | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 302817 | Biking Tech-Voc HS | DAUIS | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1072118.8144 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118774 | Bilang-Bilangan ES | TUBIGON | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1112049.6543 |  |  | COMPLETED | 1 | 2016-04-18 |  | 070114S00484 | 15HA0086 | 2015-08-11 | 2015-07-30 | 2015-08-11 | 2015-08-19 | 2015-09-21 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region VII | Bohol | 117997 | Boctol ES | BALILIHAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2060417.57 |  |  | COMPLETED | 1 | 2015-02-24 | 2015-02-20 | 070114S00165 | 14HA0018 | 2014-09-03 | 2014-08-22 | 2014-09-03 | 2014-09-10 | 2014-11-06 | GAIL CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118089 | Bonbon Catmonan ES | Calape | 1 | 1 | 4 | 1STY1CL & 1STY3CL | 2014 K10 BATCH 3 | 3600564.0842 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00401 | 14HA0055 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118776 | Buenos Aires ES | TUBIGON | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-03-27 | 070114S00131 | 14HA0020 | 2014-09-29 | 2014-09-15 | 2014-09-29 | 2014-10-03 | 2014-11-18 | GAIL CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 117972 | Bungahan ES | Antequera | 1 | 1 | 5 | 2UNITS 1STY2CL & 1STY1CL | 2014 K10 BATCH 3 | 4578197.9542 |  |  | COMPLETED | 1 | 2016-01-29 | 2015-09-30 | 070114S00388 | 14HA0052 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-05-27 | 2015-07-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 186504 | Cabacungan ES | LOON | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2890828.124 |  |  | COMPLETED | 1 | 2016-03-31 |  | 070114S00483 | 15HA0081 | 2015-07-24 | 2015-07-13 | 2015-07-24 | 2015-08-05 | 2015-09-03 | GAIL CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118537 | Cabawan ES | Maribojoc | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-11-02 | 2015-09-30 | 070114S00355 | 14HA0046 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2015-01-21 | 2015-04-06 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | Region VII | Bohol | 118090 | Cabayugan ES | Calape | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-12 | 2015-09-30 | 070114S00394 | 15HA0001 | 2015-01-26 | 2015-01-13 | 2015-01-26 | 2015-01-30 | 2015-03-16 | BNYU ENTERPRISES & CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118495 | Cabug PS | Loon South | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118778 | Cabulijan ES | Tubigon | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00367 | 14HA0049 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118475 | Calayugan ES | Loon | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-10-30 | 2015-09-30 | 070114S00455 | 15HA0006 | 2015-04-28 | 2015-03-16 | 2015-04-28 | 2015-05-07 | 2015-07-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118167 | Cambailan ES | CATIGBIAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118167 | Cambailan ES | Catigbian | 1 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 3 | 4387009.8396 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 117984 | Cambanac PS | Baclayon | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-11-20 | 2015-09-30 | 070114S00454 | 14HA0044 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2015-01-28 | 2015-05-04 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | Region VII | Bohol | 118698 | Cambuac Norte PS | Sikatuna | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-08-28 | 2015-08-25 | 070114S00365 | 14HA0045 | 2015-03-02 | 2015-03-02 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118094 | Camias ES | Calape | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00393 | 14HA0055 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118496 | Campatud Elementary School | Loon South | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00432 | 15HA0004 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 500212 | Canangcaan Integrated School | CORELLA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol |  | Canangcaan IS | CORELLA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2015-03-28 | 2015-03-27 | 070114S00126 | 14HA0014 | 2014-08-29 | 2014-08-15 | 2014-08-29 | 2014-09-25 | 2014-12-18 | A.A. DE VERA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118202 | Cancatac ES | Corella | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-08-28 | 2015-08-25 | 070114S00350 | 14HA0045 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118095 | Canguha ES | CALAPE | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2016-04-18 |  | 070114S00480 | 15HA0082 | 2015-08-10 | 2015-07-27 | 2015-08-10 | 2015-08-14 | 2015-09-21 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region VII | Bohol | 118477 | Canhangdon PS | Loon | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-01 | 2015-09-30 | 070114S00453 | 15HA0005 | 2015-01-26 | 2015-01-13 | 2015-01-26 | 2015-01-30 | 2015-03-16 | BNYU ENTERPRISES & CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118478 | Caniga-an-Ubojan Elementary School | Loon | 1 | 1 | 6 | 2UNITS 1STY3CL | 2014 K10 BATCH 3 | 5197590.5394 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-09-30 | 070114S00456 | 15HA0059 | 2015-05-25 | 2015-05-12 | 2015-05-25 | 2015-05-29 | 2015-07-03 | GAIL CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118480 | Cantam Is ES | Loon North | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00449 | 15HA0004 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118481 | Cantaongon ES | LOON | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118481 | Cantaongon ES | Loon North | 1 | 1 | 4 | 1STY3CL & 1STY1CL | 2014 K10 BATCH 3 | 3600564.0842 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118169 | Catigbian Central ES | Catigbian | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-08-30 | 2015-08-25 | 070114S00400 | 14HA0053 | 2014-12-23 | 2014-12-11 | 2014-12-23 | 2015-01-07 | 2015-03-03 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 302833 | Catigbian NHS | Catigbian | 1 | 1 | 8 | 4UNITS 1STY2CL | 2014 K10 BATCH 3 | 7152858.2796 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118170 | Catigbian West Central ES | Catigbian | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-08-30 | 2015-08-28 | 070114S00360 | 14HA0053 | 2014-12-23 | 2014-12-11 | 2014-12-23 | 2015-01-07 | 2015-03-03 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118781 | Cawayanan ES | Tubigon | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-12-05 | 2015-09-30 | 070114S00407 | 14HA0049 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118556 | Danao ES | PANGLAO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-03-28 | 2015-03-27 | 070114S00130 | 14HA0014 | 2014-08-29 | 2014-08-15 | 2014-08-29 | 2014-09-25 | 2014-12-18 | A.A. DE VERA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118004 | Dorol ES | BALILIHAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-02-24 | 2015-01-20 | 070114S00166 | 14HA0018 | 2014-09-03 | 2014-08-22 | 2014-09-03 | 2014-09-10 | 2014-11-06 | GAIL CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118208 | Fatima ES | Cortes | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-08-28 | 2015-08-25 | 070114S00348 | 14HA0045 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118782 | Genonocan PS | Tubigon | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00404 | 14HA0049 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 117986 | Guiwanon ES | Baclayon | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-11-20 | 2015-09-30 | 070114S00446 | 14HA0044 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2015-01-28 | 2015-05-04 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | Region VII | Bohol | 118005 | Haguilanan Grande ES | BALILIHAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-03-05 | 070114S00167 | 14HA0019 | 2014-09-29 | 2014-09-15 | 2014-09-29 | 2014-10-03 | 2014-11-18 | GAIL CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 312320 | Haguilanan HS | CATIGBIAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1072118.8144 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118775 | Isaac Lopoz ES | TUBIGON | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2955174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118775 | Isaac Lopoz ES | Tubigon | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118541 | Jandig ES | Maribojoc | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-08-17 | 2015-08-15 | 070114S00373 | 14HA0047 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2014-12-21 | 2015-02-18 | ASCENTIA CONSTRUCTION, INC.
NC 2014 | K10 (2014) | Region VII | Bohol | 118785 | Jose Boja ES | Tubigon | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00405 | 14HA0048 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118097 | Labuun ES | Calape | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-12 | 2015-09-30 | 070114S00395 | 15HA0001 | 2015-01-26 | 2015-01-13 | 2015-01-26 | 2015-01-30 | 2015-03-16 | BNYU ENTERPRISES & CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118542 | Lagtangon ES | Maribojoc | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-11-02 | 2015-09-30 | 070114S00354 | 14HA0046 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2015-01-21 | 2015-04-06 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | Region VII | Bohol | 118484 | Lawis ES | Loon | 1 | 1 | 7 | 2UNITS 1STY3CL & 1STY1CL | 2014 K10 BATCH 3 | 6199359.3538 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00352 | 15HA0002 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118558 | Libaong ES | PANGLAO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1052049.6543 |  |  | COMPLETED | 1 | 2016-04-18 |  | 070114S00487 | 15HA0079 | 2015-07-24 | 2015-07-13 | 2015-07-24 | 2015-08-05 | 2015-09-21 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118499 | Lintuan ES | Loon South | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-10-17 | 2015-10-15 | 070114S00436 | 15HA0029 | 2015-03-16 | 2015-03-04 | 2015-03-16 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118500 | Loon South Central ES | Loon South | 1 | 1 | 7 | 2STY6CL & 1STY1CL | 2014 K10 BATCH 3 | 9230222.0176 |  |  | COMPLETED | 1 | 2015-10-12 | 2015-09-30 | 070114S00441 | 15HA0005 | 2015-01-26 | 2015-01-13 | 2015-01-26 | 2015-01-30 | 2015-03-16 | BNYU ENTERPRISES & CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 302871 | Loon South National H.S. | Loon South | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3404228.7213 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118209 | Loreto ES | Cortes | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-08-28 | 2015-08-25 | 070114S00349 | 14HA0045 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 312355 | Lourdes High School | CORTES | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1843489.5699 |  |  | COMPLETED | 1 | 2015-08-28 | 2015-08-25 | 070114S00386 | 14HA0045 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 302872 | Lourdes NHS | PANGLAO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1965466.749 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118177 | Mahayag Norte ES | CATIGBIAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1032049.6543 |  |  | COMPLETED | 1 | 2016-04-18 |  | 070114S00485 | 15HA0082 | 2015-08-10 | 2015-07-27 | 2015-08-10 | 2015-08-14 | 2015-09-21 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region VII | Bohol | 118179 | Maitum ES | CATIGBIAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118179 | Maitum ES | Catigbian | 1 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 3 | 4387009.8396 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118099 | Mandaug Gamay ES | Calape | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-10-12 | 2015-08-25 | 070114S00391 | 15HA0001 | 2015-01-26 | 2015-01-13 | 2015-01-26 | 2015-01-30 | 2015-03-16 | BNYU ENTERPRISES & CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118100 | Mantatao ES | CALAPE | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-04-07 | 2015-04-06 | 070114S00136 | 14HA0021 | 2014-09-29 | 2014-09-15 | 2014-09-29 | 2014-10-03 | 2014-11-18 | GAIL CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118544 | Maribojoc CES | Maribojoc | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-08-17 | 2015-08-15 | 070114S00362 | 14HA0047 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2014-12-21 | 2015-02-18 | ASCENTIA CONSTRUCTION, INC.
NC 2014 | K10 (2014) | Region VII | Bohol | 117989 | Miguel Oppus MES | Baclayon | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-11-20 | 2015-09-30 | 070114S00444 | 14HA0044 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2015-01-28 | 2015-05-04 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | Region VII | Bohol | 118486 | Mocpoc Elementary School | Loon | 1 | 1 | 6 | 3UNITS 1STY2CL | 2014 K10 BATCH 3 | 5364643.7097 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-09-30 | 070114S00458 | 15HA0058 | 2015-05-25 | 2015-05-12 | 2015-05-25 | 2015-05-29 | 2015-07-03 | YU CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118501 | Nagtubo Elementary School | Loon South | 1 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 3 | 4387009.8396 |  |  | COMPLETED | 1 | 2015-07-31 | 2015-09-30 | 070114S00434 | 15HA0060 | 2015-05-25 | 2015-05-25 | 2015-05-25 | 2015-05-29 | 2015-07-03 | GAIL CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118213 | New Lourdes ES | CORTES | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-12-17 | 2015-12-15 | 070114S00482 | 15HA0080 | 2015-07-24 | 2015-07-13 | 2015-07-24 | 2015-08-05 | 2015-09-18 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118487 | Nueva Vida ES | Loon North | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-10-29 | 070114S00452 | 15HA0027 | 2015-03-16 | 2015-03-04 | 2015-03-16 | 2015-05-27 | 2015-07-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118545 | Pagnitoan ES | Maribojoc | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-08-17 | 2015-08-15 | 070114S00359 | 14HA0047 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2014-12-24 | 2015-02-18 | ASCENTIA CONSTRUCTION, INC.
NC 2014 | K10 (2014) | Region VII | Bohol | 302881 | Pagnito-an NHS | MARIBOJOC | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 1001768.8144 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118790 | Pandan ES | TUBIGON | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2689245.2697 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00383 | 14HA0048 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118562 | Panglao Central Elementary School | Panglao | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-11-20 | 2015-11-19 | 070114S00439 | 14HA0044 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2015-01-28 | 2015-05-04 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | Region VII | Bohol | 118214 | Patrocinio ES | CORTES | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2935174.43 |  |  | COMPLETED | 1 | 2015-02-24 | 2015-02-20 | 070114S00127 | 14HA0015 | 2014-08-29 | 2014-08-15 | 2014-08-29 | 2014-09-25 | 2014-11-06 | GAIL CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118503 | Pig-ot ES | Loon South | 1 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 3 | 4387009.8396 |  |  | COMPLETED | 1 | 2015-10-01 | 2015-07-30 | 070114S00435 | 15HA0005 | 2015-01-26 | 2015-01-13 | 2015-01-26 | 2015-01-30 | 2015-03-16 | BNYU ENTERPRISES & CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118792 | Pinayagan Norte ES | Tubigon | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2016-01-16 |  | 070114S00370 | 15HA0061 | 2015-05-25 | 2015-05-12 | 2015-05-25 | 2015-05-29 | 2015-07-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118793 | Pinayagan Sur ES | Tubigon | 1 | 1 | 6 | 2UNITS 1STY3CL | 2014 K10 BATCH 3 | 5197590.5394 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00369 | 15HA0010 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118488 | Pondol ES | Loon | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00351 | 15HA0002 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118181 | Rizal PS | Catigbian | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00387 | 14HA0054 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118008 | Sagasa ES | Balilihan | 1 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 3 | 4387009.8396 |  |  | COMPLETED | 1 | 2015-08-30 | 2015-08-25 | 070114S00428 | 14HA0053 | 2014-12-23 | 2014-12-11 | 2014-12-23 | 2015-01-07 | 2015-03-03 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118547 | San Isidro PS | Maribojoc | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-08-17 | 2015-08-15 | 070114S00346 | 14HA0047 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2014-12-21 | 2015-02-18 | ASCENTIA CONSTRUCTION, INC.
NC 2014 | K10 (2014) | Region VII | Bohol | 118548 | San Roque ES | Maribojoc | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-11-02 | 2015-09-30 | 070114S00356 | 14HA0046 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2015-01-21 | 2015-04-06 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | Region VII | Bohol | 500211 | San Roque Integrated School | BALILIHAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 302900 | San Roque NHS | ALBURQUERQUE | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1102703.8954 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 302902 | Sandingan NHS | Loon | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3404228.7213 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118489 | Sondol Primary School | Loon | 1 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2789983.3843 |  |  | COMPLETED | 1 | 2015-10-27 | 2015-09-30 | 070114S00457 | 15HA0006 | 2015-01-26 | 2015-01-13 | 2015-01-26 | 2015-03-18 | 2015-07-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118550 | Sta. Cruz ES | Maribojoc | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3404228.7213 |  |  | COMPLETED | 1 | 2015-11-02 | 2015-09-30 | 070114S00353 | 14HA0046 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2015-01-21 | 2015-04-06 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | Region VII | Bohol | 117978 | Sto Rosario PS | Antequera | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2016-01-29 | 2015-09-30 | 070114S00433 | 14HA0052 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-05-27 | 2015-07-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118126 | Tambongan ES | Candijay | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-07-31 | 2015-07-31 | 070114S00448 | 15HB0002 | 2015-02-01 | 2015-02-04 | 2015-02-16 | 2015-02-25 | 2015-03-18 | FIRST BUILDERS AND DEVELOPERS
NC 2014 | K10 (2014) | Region VII | Bohol | 117985 | Tanday ES | BACLAYON | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-12-17 | 2015-12-15 | 070114S00486 | 15HA0080 | 2015-07-24 | 2015-07-13 | 2015-07-24 | 2015-08-05 | 2015-09-18 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118564 | Tawala ES | PANGLAO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1052049.6543 |  |  | COMPLETED | 1 | 2016-04-18 |  | 070114S00478 | 15HA0079 | 2015-07-24 | 2015-07-13 | 2015-07-24 | 2015-08-05 | 2015-09-21 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118506 | Ticugan Elementary School | Loon South | 1 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2789983.3843 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00358 | 15HA0002 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118796 | Tinangnan ES | Tubigon | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00368 | 14HA0049 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118105 | Tinibgan ES | Calape | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-12-15 | 2015-09-30 | 070114S00390 | 14HA0055 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118507 | Tiwi PS | Loon South | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-10-29 | 070114S00438 | 15HA0060 | 2015-05-25 | 2015-05-12 | 2015-05-25 | 2015-05-29 | 2015-07-03 | GAIL CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118552 | Toril PS | Maribojoc | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-11-02 | 2015-09-30 | 070114S00363 | 14HA0046 | 2014-12-17 | 2014-12-08 | 2014-12-17 | 2015-01-21 | 2015-04-06 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | Region VII | Bohol | 118787 | Tubigon East Central ES | Tubigon | 1 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 3 | 4387009.8396 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00366 | 15HA0010 | 2015-03-02 | 2015-02-18 | 2015-03-03 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118508 | Tubodacu Elementary School | Loon South | 1 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2789983.3843 |  |  | COMPLETED | 1 | 2016-01-01 | 2015-12-30 | 070114S00440 | 15HA0003 | 2015-01-26 | 2015-01-13 | 2015-01-26 | 2015-06-26 | 2015-09-03 | IJK CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118509 | Tubodio ES | Loon South | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2016-01-01 | 2015-12-30 | 070114S00445 | 15HA0003 | 2015-01-26 | 2015-01-13 | 2015-01-26 | 2015-06-26 | 2015-09-03 | IJK CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118799 | Ubujan ES | Tubigon | 1 | 1 | 4 | 2UNITS 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 3791752.1988 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-09-30 | 070114S00416 | 14HA0048 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-04-30 | 2015-05-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118107 | Ulbujan ES | CALAPE | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1052703.8954 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118107 | Uldujan ES | Calape | 1 | 1 | 6 | 1STY2CL, 1STY3CL & 1STY1CL | 2014 K10 BATCH 3 | 5388778.6541 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 117981 | Viga PS | Antequera | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2016-01-29 |  | 070114S00374 | 14HA0052 | 2015-03-02 | 2015-02-18 | 2015-03-02 | 2015-05-27 | 2015-07-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118744 | A.P. Gurrea Mem. ES | TALIBON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 070114S00176 | 14HC0027 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | DINAH JANE CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118801 | Achila ES | UBAY | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2669145.2697 |  |  | COMPLETED | 1 | 2015-09-19 | 2015-09-15 | 070114S00420 | 15HC0016 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118586 | Aguining ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2985174.43 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-20 | 070114S00186 | 14HC0042 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118365 | Anonang ES | INABANGA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-01-20 | 2015-01-15 | 070114S00173 | 14HC0018 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118184 | Bacani ES | CLARIN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-04-30 | 070114S00199 | 14HC0012 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118391 | Badiang PS | INABANGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-02-22 | 2015-02-22 | 070114S00200 | 14HC0040 | 2014-09-30 | 2014-10-12 | 2014-10-13 | 2014-10-17 | 2014-10-21 | SLP CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 186512 | Bagacay Annex ES | TALIBON | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2045417.57 |  |  | COMPLETED | 1 | 2015-02-24 | 2015-02-24 | 070114S00028 | 14HC0046 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | WILTAN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118733 | Bagacay ES | TALIBON | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2945174.43 |  |  | COMPLETED | 1 | 2015-02-24 | 2015-02-24 | 070114S00037 | 14HC0046 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | WILTAN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118366 | Baguhan E/S | Inabanga | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-11-27 | 2015-12-31 | 070114S00281 | 15HC0047 | 2015-06-10 | 2015-06-22 | 2015-06-23 | 2015-06-27 | 2015-07-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118392 | Bahan P/S | Inabanga | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-18 | 2015-10-18 | 070114S00286 | 15HC0049 | 2015-06-10 | 2015-06-22 | 2015-06-23 | 2015-06-27 | 2015-07-01 | 3N CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118322 | Banacon ES | JETAFE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2015-02-24 | 2015-02-24 | 070114S00213 | 14HC0017 | 2014-09-17 | 2014-09-29 | 2014-09-30 | 2014-10-04 | 2014-10-08 | EDANNA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118062 | Bantuan PS | BUENAVISTA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-02 | 070114S00139 | 14HC0009 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | P.B. OBIAL CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118588 | Baud ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2015-02-04 | 2015-02-04 | 070114S00187 | 14HC0020 | 2014-09-17 | 2014-09-29 | 2014-09-30 | 2014-10-04 | 2014-10-08 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118591 | Bayog ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1212329.12 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-20 | 070114S00189 | 14HC0042 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118642 | Bayongan ES | SAN MIGUEL | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1833439.5699 |  |  | COMPLETED | 1 | 2015-10-10 | 2015-05-31 | 070114S00417 | 15HC0015 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | BNYU ENTERPRISES & CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118028 | Bilangbilangan Daku ES | BIEN UNIDO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2690828.124 |  |  | COMPLETED | 1 | 2015-12-30 | 2015-12-15 | 070114S00474 | 15HC0056 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-07-30 | 2015-08-03 | DINAH JANE CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118029 | Bilangbilangan East PS | BIEN UNIDO | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2945174.43 |  |  | COMPLETED | 1 | 2015-08-03 | 2015-07-31 | 070114S00135 | S-00135 | 2015-03-16 | 2015-03-28 | 2015-03-29 | 2015-04-02 | 2015-04-06 | By Administration
NC 2014 | K10 (2014) | Region VII | Bohol | 118589 | Bogo ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 070114S00188 | 14HC0021 | 2014-11-19 | 2014-12-01 | 2014-12-02 | 2014-12-06 | 2014-12-10 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118185 | Bogtongbod E/S | Clarin | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118185 | Bogtongbod ES | CLARIN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2955174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118186 | Bonbon ES | CLARIN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118186 | Bonbon ES | Clarin | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 312324 | Bonbonon HS | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1177329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118806 | Bood ES | UBAY | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1848514.5699 |  |  | COMPLETED | 1 | 2015-09-19 | 2015-09-15 | 070114S00443 | 15HC0016 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118189 | Buangan ES | CLARIN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118189 | Buangan ES | Clarin | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118065 | Buenavista CES | BUENAVISTA | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2930174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118065 | Buenavista CES | Buenavista | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118807 | Buenavista ES | UBAY | 2 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3850805.49 |  |  | COMPLETED | 1 | 2015-03-26 | 2015-03-26 | 070114S00013 | 14HC0054 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | WILTAN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118368 | Bugang PS | Inabanga | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-11-05 | 2015-11-05 | 070114S00287 | 15HC0042 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-07-30 | 2015-08-03 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118718 | Burgos ES | TALIBON | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1868614.5699 |  |  | COMPLETED | 1 | 2015-10-19 | 2015-08-31 | 070114S00403 | 15HC0015 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | BNYU ENTERPRISES & CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118734 | Busalian ES | TALIBON | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 070114S00039 | 14HC0027 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | DINAH JANE CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118592 | Butan ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1182329.12 |  |  | COMPLETED | 1 | 2015-05-31 | 2015-05-31 | 070114S00190 | 14HC0021 | 2014-11-19 | 2014-12-01 | 2014-12-02 | 2014-12-06 | 2014-12-10 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118644 | Cabangahan PS | SAN MIGUEL | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-04-30 | 070114S00040 | 14HC0024 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | VIRLO CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol |  | Cabanugan IS | San Isidro | 2 | 1 | 7 | 1STY4CL & 1STY3CL | 2014 K10 BATCH 3 | 6003023.991 |  |  | COMPLETED | 1 | 2016-01-11 |  | 070114S00311 | 15HC0050 | 2015-06-11 | 2015-06-23 | 2015-06-24 | 2015-06-28 | 2015-07-02 | AQSIL BUILDERS AND CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol |  | Cabasakan ES | JETAFE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 070114S00212 | 14HC0016 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | EDANNA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118234 | Cabatuan ES | DANAO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-10-19 | 2015-10-19 | 070114S00277 | 15HC0003 | 2015-04-02 | 2015-04-14 | 2015-04-15 | 2015-04-19 | 2015-04-23 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region VII | Bohol | 118190 | Cabog E/S | Clarin | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2789983.3843 |  |  | COMPLETED | 1 | 2015-11-30 |  | 070114S00275 | 15HC0002 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region VII | Bohol | 118191 | Caboy E/S | Clarin | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118191 | Caboy ES | CLARIN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118068 | Cabul-an ES | BUENAVISTA | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2915174.43 |  |  | COMPLETED | 1 | 2015-03-26 | 2015-03-26 | 070114S00141 | 14HC0036 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | WILTAN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118219 | Cagawasan ES | DAGOHOY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118219 | Cagawasan ES | Dagohoy | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118394 | Cagawasan ES | INABANGA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-22 | 070114S00181 | 14HC0039 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118809 | Cagting ES | UBAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1032049.6543 |  |  | COMPLETED | 1 | 2015-10-24 | 2015-10-24 | 070114S00473 | 15HC0055 | 2015-07-01 | 2015-07-13 | 2015-07-14 | 2015-07-18 | 2015-07-22 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118634 | Caimbang ES | San Isidro | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-10-28 | 2015-08-31 | 070114S00263 | 15HC0005 | 2015-04-11 | 2015-04-23 | 2015-04-24 | 2015-04-28 | 2015-05-02 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118395 | Cainsican P/S | Inabanga | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118395 | Cainsican PS | INABANGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118810 | Calanggaman ES | UBAY | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2965174.43 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-31 | 070114S00012 | 14HC0056 | 2014-10-15 | 2014-10-27 | 2014-10-28 | 2014-11-01 | 2014-11-05 | AQSIL BUILDERS AND CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118811 | California ES | UBAY | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6358964.7656 |  |  | COMPLETED | 1 | 2015-11-29 | 2015-11-29 | 070114S00421 | 15HC0033 | 2015-04-13 | 2015-04-25 | 2015-04-26 | 2015-04-30 | 2015-05-04 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118735 | Calituban ES | TALIBON | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2965174.43 |  |  | COMPLETED | 1 | 2015-05-31 | 2015-05-31 | 070114S00061 | 14HC0045 | 2014-10-16 | 2014-10-28 | 2014-10-29 | 2014-11-02 | 2014-11-06 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Bohol | 118220 | Caluasan ES | DAGOHOY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-01-10 | 2015-01-10 | 070114S00207 | 14HC0013 | 2014-09-04 | 2014-09-16 | 2014-09-17 | 2014-09-21 | 2014-09-25 | AQSIL BUILDERS AND CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118645 | Caluasan ES | SAN MIGUEL | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118645 | Caluasan ES | San Miguel | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118070 | Cambus-oc ES | BUENAVISTA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2025417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118070 | Cambus-Oc ES | Buenavista | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118593 | Campamanog ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1182329.12 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-04-30 | 070114S00191 | 14HC0021 | 2014-11-19 | 2014-12-01 | 2014-12-02 | 2014-12-06 | 2014-12-10 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118326 | Campao ES | Getafe | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118326 | Campao ES | JETAFE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118636 | Candungao ES | SAN ISIDRO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1092703.8954 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-02-23 | 070114S00228 | 14HC0061 | 2014-09-22 | 2014-10-04 | 2014-10-05 | 2014-10-09 | 2014-10-13 | WILTAN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118328 | Cangmundo ES | Getafe | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-19 | 2015-10-19 | 070114S00247 | 15HC0015 | 2015-04-03 | 2015-04-15 | 2015-04-16 | 2015-04-20 | 2015-04-24 | BNYU ENTERPRISES & CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118594 | Canmangao ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1182329.12 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-04-30 | 070114S00192 | 14HC0021 | 2014-11-21 | 2014-12-03 | 2014-12-04 | 2014-12-08 | 2014-12-10 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118610 | Canmano ES | SAGBAYAN (BORJA) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1072118.8144 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-18 | 070114S00431 | 15HC0014 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | FFJJ CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118612 | Canmaya Diot ES | Sagbayan | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-30 | 070114S00243 | 15HC0013 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | FFJJ CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118638 | Cansague Sur ES | SAN ISIDRO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118638 | Cansague Sur ES | San Isidro | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118072 | Cantores PS | BUENAVISTA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-01-20 | 2015-01-15 | 070114S00143 | 14HC0010 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | P.B. OBIAL CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118192 | Cantoyoc P/S | Clarin | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-12-31 | 070114S00271 | 15HC0001 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region VII | Bohol | 118073 | Cantuba ES | BUENAVISTA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-03-26 | 2015-03-26 | 070114S00144 | 14HC0036 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | WILTAN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118648 | Capayas ES | SAN MIGUEL | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-04-30 | 070114S00038 | 14HC0024 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | VIRLO CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118236 | Carbon PS | DANAO | 2 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 3 | 2003537.6289 |  |  | COMPLETED | 1 | 2015-11-18 | 2015-11-18 | 070114S00413 | 15HC0003 | 2015-04-02 | 2015-04-14 | 2015-04-15 | 2015-04-19 | 2015-04-23 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region VII | Bohol | 118813 | Casate ES | UBAY | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2690828.124 |  |  | COMPLETED | 1 | 2015-12-23 | 2015-11-30 | 070114S00476 | 15HC0067 | 2015-08-05 | 2015-08-17 | 2015-08-18 | 2015-08-22 | 2015-08-26 | BNYU ENTERPRISES & CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 500210 | Cataban Integrated School | TALIBON | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-08-31 | 2015-08-31 | 070114S00060 | S-00060 | 2015-03-30 | 2015-04-11 | 2015-04-12 | 2015-04-16 | 2015-04-20 | By Administration
NC 2014 | K10 (2014) | Region VII | Bohol | 118074 | Catigbi-an ES | Buenavista | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-09-19 | 2015-09-19 | 070114S00376 | 15HC0007 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | LEDA CONSTRUCTION INCORPORATED
NC 2014 | K10 (2014) | Region VII | Bohol | 118639 | Causwagan PS | San Isidro | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-28 | 2015-08-31 | 070114S00252 | 15HC0005 | 2015-04-11 | 2015-04-23 | 2015-04-24 | 2015-04-28 | 2015-05-02 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118075 | Cawag ES | BUENAVISTA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-05-31 | 2015-05-31 | 070114S00145 | 14HC0010 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | P.B. OBIAL CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118193 | Clarin Central ES | CLARIN | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2689245.2697 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-12-31 | 070114S00408 | 15HC0001 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region VII | Bohol | 118330 | Corte-Baud ES | JETAFE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 070114S00210 | 14HC0016 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | EDANNA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118372 | Cuaming ES | INABANGA | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2965174.43 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-31 | 070114S00174 | 14HC0041 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | DINAH JANE CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 312337 | Dagnawan Integrated School | INABANGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-05-07 | 2015-05-07 | 070114S00025 | 14HC0057 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | 3S BUILDERS
NC 2014 | K10 (2014) | Region VII | Bohol | 118238 | Dagohoy ES | DANAO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118373 | Dait Sur ES | INABANGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-01-30 | 2015-01-15 | 070114S00175 | 14HC0041 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | DINAH JANE CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118239 | Danao CES | DANAO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-30 | 070114S00290 | 15HC0003 | 2015-04-02 | 2015-04-14 | 2015-04-15 | 2015-04-19 | 2015-04-23 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region VII | Bohol | 118748 | Diis ES | TRINIDAD | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2955174.43 |  |  | COMPLETED | 1 | 2015-03-02 | 2015-03-02 | 070114S00052 | 14HC0052 | 2014-10-13 | 2014-10-25 | 2014-10-26 | 2014-10-30 | 2014-11-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 302888 | Eugenio V. Amores NHS | Sagbayan | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2789983.3843 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118815 | Fatima ES | UBAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2015-01-20 | 2015-01-20 | 070114S00011 | 14HC0032 | 2014-09-17 | 2014-09-29 | 2014-09-30 | 2014-10-04 | 2014-10-08 | PHILKONSTRACK DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Bohol | 118650 | Garcia ES | SAN MIGUEL | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-01-18 | 2015-01-18 | 070114S00046 | 14HC0025 | 2014-09-05 | 2014-09-17 | 2014-09-18 | 2014-09-22 | 2014-09-26 | VIRLO CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118595 | Gaus ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2060417.57 |  |  | COMPLETED | 1 | 2015-05-31 | 2015-05-31 | 070114S00164 | 14HC0043 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118817 | Gov. Boyles ES | UBAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1182329.12 |  |  | COMPLETED | 1 | 2015-01-25 | 2015-01-20 | 070114S00010 | 14HC0055 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | PHILKONSTRACK DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Bohol | 118737 | Guindacpan ES | TALIBON | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2910174.43 |  |  | COMPLETED | 1 | 2015-08-31 | 2015-08-31 | 070114S00059 | S-00059 | 2015-04-14 | 2015-04-26 | 2015-04-27 | 2015-05-01 | 2015-05-05 | By Administration
NC 2014 | K10 (2014) | Region VII | Bohol | 118749 | Guinobatan ES | TRINIDAD | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1177329.12 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 070114S00051 | 14HC0028 | 2014-09-04 | 2014-09-16 | 2014-09-17 | 2014-09-21 | 2014-09-25 | BNYU ENTERPRISES & CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118818 | Guintaboan ES | UBAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-01-23 | 2015-01-23 | 070114S00009 | 14HC0029 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | DINAH JANE CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118651 | Hagbuyo PS | SAN MIGUEL | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1052703.8954 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-02-23 | 070114S00227 | 14HC0061 | 2014-10-21 | 2014-11-02 | 2014-11-03 | 2014-11-07 | 2014-11-11 | WILTAN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118819 | Hambabauran ES | UBAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-15 | 070114S00001 | 14HC0030 | 2014-09-04 | 2014-09-16 | 2014-09-17 | 2014-09-21 | 2014-09-25 | DINAH JANE CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 302828 | Handumon NHS | JETAFE | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2699295.2697 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118332 | Handumon ES | JETAFE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-15 | 070114S00209 | 14HC0016 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | EDANNA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 302857 | Hingotanan NHS | BIEN UNIDO | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2940174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118820 | Humayhumay ES | UBAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2060417.57 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 070114S00007 | 14HC0031 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | AQSIL BUILDERS AND CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118377 | Ilaya P/S | Inabanga | 2 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 3 | 2003537.6289 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-12-31 | 070114S00280 | 15HC0044 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-07-30 | 2015-08-03 | LCG CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118821 | Ilihan ES | UBAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1092218.8144 |  |  | COMPLETED | 1 | 2015-09-19 | 2015-09-19 | 070114S00422 | 15HC0016 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118400 | Ilihan PS | INABANGA | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2915174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118400 | Ilihan PS | Inabanga | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 500209 | Inabanga North Integrated School | INABANGA | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2945174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 312341 | Inabanga North Intrgrated School | Inabanga | 2 | 1 | 11 | 2UNITS 1STY3CL, 2UNITS 1STY2CL & 1STY1CL | 2014 K10 BATCH 3 | 9775788.4937 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118378 | Inabanga North IS | INABANGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118333 | Jagoliao ES | JETAFE | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1072118.8144 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-16 | 070114S00414 | 15HC0015 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | BNYU ENTERPRISES & CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118738 | Jao ES | TALIBON | 2 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3830805.49 |  |  | COMPLETED | 1 | 2015-07-30 | 2015-06-30 | 070114S00058 | S-00058 | 2015-02-09 | 2015-02-21 | 2015-02-22 | 2015-02-26 | 2015-03-02 | By Administration
NC 2014 | K10 (2014) | Region VII | Bohol | 118823 | Juagdan ES | Ubay | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-09-19 | 2015-09-15 | 070114S00256 | 15HC0016 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118225 | Kagawitan ES | DAGOHOY | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3514886.575 |  |  | COMPLETED | 1 | 2015-12-30 | 2015-12-15 | 070114S00477 | 15HC0057 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-07-30 | 2015-08-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118615 | Katipunan ES | SAGBAYAN (BORJA) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2015417.57 |  |  | COMPLETED | 1 | 2015-01-17 | 2015-01-17 | 070114S00043 | 14HC0022 | 2014-09-04 | 2014-09-16 | 2014-09-17 | 2014-09-21 | 2014-09-25 | SLP CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 302862 | Kauswagan NHS | TRINIDAD | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1157329.12 |  |  | COMPLETED | 1 | 2015-03-02 | 2015-03-02 | 070114S00018 | 14HC0052 | 2014-10-13 | 2014-10-25 | 2014-10-26 | 2014-10-30 | 2014-11-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118652 | La Esperanza ES | Dagohoy | 2 | 1 | 4 | 2UNITS 1STY2CL | 2014 K10 BATCH 3 | 3576429.1398 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118754 | La Union ES | TRINIDAD | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2935174.43 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-03-15 | 070114S00050 | 14HC0051 | 2014-10-02 | 2014-10-14 | 2014-10-15 | 2014-10-19 | 2014-10-23 | PHILKONSTRACK DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Bohol | 118381 | Liloan Sur ES | INABANGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-01-23 | 2015-01-23 | 070114S00182 | 14HC0019 | 2014-09-05 | 2014-09-17 | 2014-09-18 | 2014-09-22 | 2014-09-26 | YU CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118598 | Lipata ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-02-04 | 2015-02-04 | 070114S00085 | 14HC0020 | 2014-09-17 | 2014-09-29 | 2014-09-30 | 2014-10-04 | 2014-10-08 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118078 | Lubang ES | Buenavista | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-09-19 | 2015-09-19 | 070114S00430 | 15HC0006 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | LEDA CONSTRUCTION INCORPORATED
NC 2014 | K10 (2014) | Region VII | Bohol | 302831 | Lubang NHS | BUENAVISTA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1097703.8954 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 070114S00222 | 14HC0059 | 2014-10-30 | 2014-11-10 | 2014-11-11 | 2014-11-15 | 2014-11-19 | L.C. CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118404 | Lutao ES | Inabanga | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-18 | 2015-10-18 | 070114S00288 | 15HC0011 | 2015-04-01 | 2015-04-13 | 2015-04-14 | 2015-04-18 | 2015-04-22 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118405 | Luyo PS | INABANGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-01-23 | 2015-01-23 | 070114S00184 | 14HC0019 | 2014-09-05 | 2014-09-17 | 2014-09-18 | 2014-09-22 | 2014-09-26 | YU CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118827 | Luz ES | UBAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-31 | 070114S00014 | 14HC0030 | 2014-09-04 | 2014-09-16 | 2014-09-17 | 2014-09-21 | 2014-09-25 | DINAH JANE CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118406 | Mabuhay PS | Inabanga | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-10-18 | 2015-10-18 | 070114S00278 | 15HC0011 | 2015-04-01 | 2015-04-13 | 2015-04-14 | 2015-04-18 | 2015-04-22 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118079 | Magkaya ES | BUENAVISTA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118079 | Magkaya ES | Buenavista | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118242 | Magtangtang ES | DANAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-18 | 2015-08-31 | 070114S00264 | 15HC0004 | 2015-04-01 | 2015-04-13 | 2015-04-14 | 2015-04-18 | 2015-04-22 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118120 | Mahangin ES | Candijay | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-11-20 | 2015-12-31 | 070114S00255 | 15HC0073 | 2015-07-28 | 2015-08-09 | 2015-08-10 | 2015-08-14 | 2015-08-18 | AE BELLEZA BUILDERS
NC 2014 | K10 (2014) | Region VII | Bohol | 302873 | Mahayag NHS | SAN MIGUEL | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2035417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118227 | Mahayag PS | DAGOHOY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 070114S00194 | 14HC0014 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | PHILKONSTRACK DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Bohol | 118032 | Malingin ES | BIEN UNIDO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-04-09 | 2015-04-09 | 070114S00125 | 14HC0044 | 2014-12-15 | 2014-12-27 | 2014-12-28 | 2015-01-01 | 2015-01-05 | YS CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118228 | Malitbog ES | DAGOHOY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-01-10 | 2015-01-10 | 070114S00208 | 14HC0013 | 2014-09-04 | 2014-09-16 | 2014-09-17 | 2014-09-21 | 2014-09-25 | AQSIL BUILDERS AND CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118383 | Nabuad ES | Inabanga | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-10-28 | 2015-10-20 | 070114S00279 | 15HC0046 | 2015-06-10 | 2015-06-22 | 2015-06-23 | 2015-06-27 | 2015-07-01 | 3N CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118197 | Nahawan ES | CLARIN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1147329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118197 | Nahawan ES | Clarin | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3404228.7213 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118243 | Nahud ES | DANAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1858564.5699 |  |  | COMPLETED | 1 | 2015-11-17 | 2015-11-17 | 070114S00409 | 15HC0004 | 2015-04-01 | 2015-04-13 | 2015-04-14 | 2015-04-18 | 2015-04-22 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118337 | Nasingin ES | JETAFE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-15 | 070114S00202 | 14HC0016 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | EDANNA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118740 | Nocnocan ES | TALIBON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-03-23 | 2015-03-23 | 070114S00057 | 14HC0044 | 2014-10-29 | 2014-11-10 | 2014-11-11 | 2014-11-15 | 2014-11-19 | BNYU ENTERPRISES & CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118036 | Nueva Estrella ES | BIEN UNIDO | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2935174.43 |  |  | COMPLETED | 1 | 2015-04-09 | 2015-04-09 | 070114S00137 | 14HC0044 | 2014-12-15 | 2014-12-27 | 2014-12-28 | 2015-01-01 | 2015-01-05 | YS CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118080 | Nueva Granada ES | BUENAVISTA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | COMPLETED | 1 | 2015-06-30 | 2015-06-30 | 070114S00178 | 14HC0035 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | VIRLO CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118081 | Nueva Montana ES | Buenavista | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118081 | Nueva Montaña ES | BUENAVISTA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118082 | Overland ES | BUENAVISTA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118082 | Overland ES | Buenavista | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118083 | P. Tirol ES | Buenavista | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-09-19 | 2015-09-19 | 070114S00267 | 15HC0007 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | LEDA CONSTRUCTION INCORPORATED
NC 2014 | K10 (2014) | Region VII | Bohol | 118732 | P/Lt. Eugenio B. Artiaga ES | TALIBON | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2945174.43 |  |  | COMPLETED | 1 | 2015-03-23 | 2015-03-23 | 070114S00032 | 14HC0044 | 2014-10-29 | 2014-11-10 | 2014-11-11 | 2014-11-15 | 2014-11-19 | BNYU ENTERPRISES & CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118828 | Pag-asa ES | UBAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-31 | 070114S00006 | 14HC0056 | 2014-10-15 | 2014-10-27 | 2014-10-28 | 2014-11-01 | 2014-11-05 | AQSIL BUILDERS AND CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118338 | Pandanon ES | JETAFE | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2935174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 312322 | Pandanon HS | JETAFE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1147329.12 |  |  | COMPLETED | 1 | 2015-05-31 | 2015-05-31 | 070114S00015 | 14HC0038 | 2014-10-14 | 2014-10-26 | 2014-10-27 | 2014-10-31 | 2014-11-04 | BANTAY CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118084 | Panghagban ES | BUENAVISTA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2740828.124 |  |  | COMPLETED | 1 | 2015-12-30 | 2015-12-15 | 070114S00469 | 15HC0058 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-07-30 | 2015-08-03 | DINAH JANE CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118037 | Pinamgo ES | BIEN UNIDO | 2 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 2 | 4677514.4199 |  |  | COMPLETED | 1 | 2015-05-31 | 2015-05-31 | 070114S00219 | 14HC0044 | 2014-12-22 | 2015-01-03 | 2015-01-04 | 2015-01-08 | 2015-01-12 | YS CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118085 | Plateau PS | BUENAVISTA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 312331 | Ponciana E. Leoligao HS | TALIBON | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1920466.749 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 302895 | Pres. Carlos P. Garcia MHS | TALIBON | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118086 | Putingbato ES | BUENAVISTA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1097703.8954 |  |  | COMPLETED | 1 | 2015-04-17 | 2015-04-17 | 070114S00220 | 14HC0059 | 2014-10-29 | 2014-11-10 | 2014-11-11 | 2014-11-15 | 2014-11-19 | L.C. CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118087 | Rufo Hill ES | BUENAVISTA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 070114S00201 | 14HC0011 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | PHILKONSTRACK DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Bohol | 118741 | Sag ES | TALIBON | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2975174.43 |  |  | COMPLETED | 1 | 2015-08-31 | 2015-08-31 | 070114S00056 | S-00056 | 2015-02-09 | 2015-02-21 | 2015-02-22 | 2015-02-26 | 2015-03-02 | By Administration
NC 2014 | K10 (2014) | Region VII | Bohol | 118039 | Sagasa ES | BIEN UNIDO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-06-30 | 2015-06-30 | 070114S00138 | S-00138 | 2015-02-09 | 2015-02-21 | 2015-02-22 | 2015-02-26 | 2015-03-02 | By Administration
NC 2014 | K10 (2014) | Region VII | Bohol | 118618 | Sagbayan Central ES | Sagbayan | 2 | 1 | 21 | 4UNITS 1STY3CL, 3UNITS 1STY2CL & 3UNITS 1STY1CL | 2014 K10 BATCH 3 | 18765131.2318 |  |  | COMPLETED | 1 | 2015-10-27 | 2015-09-30 | 070114S00248 | 15HC0012 | 2015-03-11 | 2015-03-23 | 2015-03-24 | 2015-03-28 | 2015-04-01 | YS CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118620 | San Agustin ES | Sagbayan | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-19 | 070114S00241 | 15HC0014 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | FFJJ CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118723 | San Agustin ES | TALIBON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00033 | 14HC0045 | 2014-10-16 | 2014-10-28 | 2014-10-29 | 2014-11-02 | 2014-11-06 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Bohol | 118621 | San Antonio ES | Sagbayan | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-30 | 070114S00240 | 15HC0014 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | FFJJ CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118742 | San Francisco ES | TALIBON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 070114S00078 | 14HC0027 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | DINAH JANE CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118830 | San Francisco ES | UBAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 070114S00005 | 14HC0031 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | AQSIL BUILDERS AND CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118641 | San Isidro Central ES | San Isidro | 2 | 1 | 5 | 2UNITS 1STY2CL & 1STY1CL | 2014 K10 BATCH 3 | 4578197.9542 |  |  | COMPLETED | 1 | 2015-10-28 | 2015-10-28 | 070114S00246 | 15HC0005 | 2015-04-11 | 2015-04-23 | 2015-04-24 | 2015-04-28 | 2015-05-02 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118387 | San Isidro ES | INABANGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-01-20 | 2015-01-15 | 070114S00179 | 14HC0018 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118654 | San Isidro ES | SAN MIGUEL | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-04-30 | 070114S00036 | 14HC0024 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | VIRLO CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118762 | San Isidro ES | TRINIDAD | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 070114S00049 | 14HC0028 | 2014-09-04 | 2014-09-16 | 2014-09-17 | 2014-09-21 | 2014-09-25 | BNYU ENTERPRISES & CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118831 | San Isidro ES | UBAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-23 | 2015-01-23 | 070114S00004 | 14HC0029 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | DINAH JANE CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 312350 | San Isidro HS | TALIBON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 500114 | San Isidro IS | Sagbayan | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3404228.7213 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-19 | 070114S00239 | 15HC0014 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | FFJJ CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118388 | San Jose E/S | Inabanga | 2 | 1 | 7 | 1STY4CL & 1STY3CL | 2014 K10 BATCH 3 | 6003023.991 |  |  | COMPLETED | 1 | 2015-09-12 | 2015-08-31 | 070114S00282 | 15HC0008 | 2015-02-24 | 2015-03-08 | 2015-03-09 | 2015-03-13 | 2015-03-17 | YS CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118341 | San Jose ES | JETAFE | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1072118.8144 |  |  | COMPLETED | 1 | 2015-10-20 | 2015-09-18 | 070114S00415 | 15HC0015 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | BNYU ENTERPRISES & CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118604 | San Jose ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-02-04 | 2015-02-04 | 070114S00044 | 14HC0020 | 2014-09-17 | 2014-09-29 | 2014-09-30 | 2014-10-04 | 2014-10-08 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 302891 | San Jose NHS | INABANGA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2797047.671 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 302891 | San Jose NHS | Inabanga | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2789983.3843 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118247 | San Jose PS | DANAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1072118.8144 |  |  | COMPLETED | 1 | 2015-10-18 | 2015-08-31 | 070114S00410 | 15HC0004 | 2015-04-01 | 2015-04-13 | 2015-04-14 | 2015-04-18 | 2015-04-22 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118248 | San Miguel PS | DANAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1868614.5699 |  |  | COMPLETED | 1 | 2015-10-19 | 2015-08-31 | 070114S00411 | 15HC0003 | 2015-04-02 | 2015-04-14 | 2015-04-15 | 2015-04-19 | 2015-04-23 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region VII | Bohol | 302897 | San Miguel Technical Vocational School | SAN MIGUEL | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1117703.8954 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118726 | San Roque ES | TALIBON | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1072118.8144 |  |  | COMPLETED | 1 | 2015-10-10 | 2015-06-30 | 070114S00419 | 15HC0015 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | BNYU ENTERPRISES & CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118602 | San Vicente ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2935174.43 |  |  | COMPLETED | 1 | 2015-03-26 | 2015-03-26 | 070114S00045 | 14HC0043 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118763 | San Vicente ES | TRINIDAD | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-03-15 | 070114S00048 | 14HC0051 | 2014-10-02 | 2014-10-14 | 2014-10-15 | 2014-10-19 | 2014-10-23 | PHILKONSTRACK DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Bohol | 118833 | San Vicente ES | UBAY | 2 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3860805.49 |  |  | COMPLETED | 1 | 2015-06-30 | 2015-06-30 | 070114S00003 | 14HC0053 | 2014-10-13 | 2014-10-25 | 2014-10-26 | 2014-10-30 | 2014-11-03 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118625 | San Vicente Norte PS | Sagbayan | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-30 | 070114S00238 | 15HC0013 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | FFJJ CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118657 | San Vicente PS | SAN MIGUEL | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-04-30 | 070114S00035 | 14HC0024 | 2014-09-10 | 2014-09-22 | 2014-09-23 | 2014-09-27 | 2014-10-01 | VIRLO CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118626 | San Vicente Sur PS | Sagbayan | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-18 | 070114S00237 | 15HC0013 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | FFJJ CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118251 | Santo Niño PS | DANAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1858564.5699 |  |  | COMPLETED | 1 | 2015-10-18 | 2015-08-31 | 070114S00412 | 15HC0004 | 2015-04-01 | 2015-04-13 | 2015-04-14 | 2015-04-18 | 2015-04-22 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118834 | Sentinela ES | UBAY | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2945174.43 |  |  | COMPLETED | 1 | 2015-02-24 | 2015-02-24 | 070114S00002 | 14HC0055 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | PHILKONSTRACK DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Bohol | 118727 | Sikatuna ES | TALIBON | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1858564.5699 |  |  | COMPLETED | 1 | 2015-10-19 | 2015-08-31 | 070114S00418 | 15HC0015 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | BNYU ENTERPRISES & CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 500216 | Soom Integrated School | TRINIDAD | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1137703.8954 |  |  | COMPLETED | 1 | 2015-04-04 | 2015-04-04 | 070114S00235 | 14HC0060 | 2014-10-16 | 2014-10-28 | 2014-10-29 | 2014-11-02 | 2014-11-06 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 500216 | Soom IS | TRINIDAD | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 070114S00055 | 14HC0028 | 2014-09-04 | 2014-09-16 | 2014-09-17 | 2014-09-21 | 2014-09-25 | BNYU ENTERPRISES & CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118401 | South Inabannga Central Sch | Inabanga | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 302859 | Southern Inabanga HS | INABANGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118627 | Sta. Catalina ES | Sagbayan | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-30 | 070114S00245 | 15HC0013 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | FFJJ CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118658 | Sto. Niño PS | SAN MIGUEL | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 070114S00016 | 14HC0014 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | PHILKONSTRACK DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Bohol | 118407 | Sto. Rosario ES | Inabanga | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-09-12 | 2015-08-31 | 070114S00244 | 15HC0008 | 2015-02-24 | 2015-03-08 | 2015-03-09 | 2015-03-13 | 2015-03-17 | YS CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 302910 | Tagum Sur NHS | TRINIDAD | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1940466.749 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118743 | Talibon II Central ES | TALIBON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-03-31 | 070114S00054 | 14HC0032 | 2014-09-17 | 2014-09-29 | 2014-09-30 | 2014-10-04 | 2014-10-08 | PHILKONSTRACK DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Bohol | 118408 | Tambooc P/S | Inabanga | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-11-05 | 2015-11-05 | 070114S00284 | 15HC0041 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-07-30 | 2015-08-03 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 302844 | Taming NHS | DANAO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118838 | Tintinan ES | UBAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | COMPLETED | 1 | 2015-03-26 | 2015-03-26 | 070114S00008 | 14HC0054 | 2014-10-07 | 2014-10-19 | 2014-10-20 | 2014-10-24 | 2014-10-28 | WILTAN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118659 | Tomoc ES | San Miguel | 2 | 1 | 4 | 1STY3CL & 1STY1CL | 2014 K10 BATCH 3 | 3600564.0842 |  |  | COMPLETED | 1 | 2015-11-19 | 2015-11-19 | 070114S00260 | 15HC0052 | 2015-07-02 | 2015-07-14 | 2015-07-15 | 2015-07-19 | 2015-07-23 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region VII | Bohol | 118128 | Tubod ES | Candijay | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-11-20 | 2015-12-31 | 070114S00254 | 15HC0072 | 2015-07-28 | 2015-08-09 | 2015-08-10 | 2015-08-14 | 2015-08-18 | AE BELLEZA BUILDERS
NC 2014 | K10 (2014) | Region VII | Bohol |  | Tugas ES | JETAFE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1147329.12 |  |  | COMPLETED | 1 | 2015-01-20 | 2015-01-20 | 070114S00171 | 14HC0015 | 2014-09-02 | 2014-09-14 | 2014-09-15 | 2014-09-19 | 2014-09-23 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118606 | Tugas ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4A | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-10-31 | 070114S00460 | 15HC0037 | 2015-07-03 | 2015-07-15 | 2015-07-16 | 2015-07-20 | 2015-07-24 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118345 | Tulang ES | JETAFE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-02-04 | 2015-02-04 | 070114S00172 | 14HC0017 | 2014-09-17 | 2014-09-29 | 2014-09-30 | 2014-10-04 | 2014-10-08 | EDANNA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 302913 | Tulang NHS | JETAFE | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2015417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 186506 | Tunaan-Daku ES | TALIBON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-08-31 | 2015-08-31 | 070114S00023 | S-00023 | 2015-04-15 | 2015-04-27 | 2015-04-28 | 2015-05-02 | 2015-05-06 | By Administration
NC 2014 | K10 (2014) | Region VII | Bohol | 302915 | Ubay National Science HS | UBAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118629 | Ubojan ES | Sagbayan | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118629 | Ubojan ES | SAGBAYAN (BORJA) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118844 | Union ES | UBAY | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2690828.124 |  |  | COMPLETED | 1 | 2016-01-22 |  | 070114S00475 | 15HC0068 | 2015-08-05 | 2015-08-17 | 2015-08-18 | 2015-08-22 | 2015-08-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region VII | Bohol | 118410 | U-OG Ubuan ES | Inabanga | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118410 | U-og Ubujan ES | INABANGA | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2915174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 186503 | Villaflor P/S | Clarin | 2 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 3 | 2003537.6289 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-12-31 | 070114S00272 | 15HC0002 | 2015-03-03 | 2015-03-15 | 2015-03-16 | 2015-03-20 | 2015-03-24 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region VII | Bohol | 118510 | Abaca ES | MABINI | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2935174.43 |  |  | COMPLETED | 1 | 2015-03-17 | 2015-03-17 | 070114S00090 | 14HB0028 | 2014-09-08 | 2014-07-31 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118130 | Alegria ES | Carmen | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 070114S00336 | 14HB0064 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | FIRST BUILDERS AND DEVELOPERS
NC 2014 | K10 (2014) | Region VII | Bohol | 118847 | Anas ES | Valencia | 3 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 3 | 4387009.8396 |  |  | COMPLETED | 1 | 2015-07-10 | 2015-07-10 | 070114S00302 | 14HB0069 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118284 | Anibongan PS | DUERO | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1052703.8954 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-04-11 | 070114S00232 | 14HB0032 | 2014-09-08 | 2014-07-31 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118848 | Anonang ES | Valencia | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-07-01 | 2015-07-01 | 070114S00300 | 14HB0070 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118567 | Bagumbayan ES | PILAR | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1041968.8144 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 070114S00326 | 14HB0062 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118411 | Balili ES | Jagna | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-06-24 | 070114S00307 | 14HB0073 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 312356 | Bangwalog HS | DUERO | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1848514.5699 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-06-10 | 070114S00345 | 14HB0074 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | FIRST BUILDERS AND DEVELOPERS
NC 2014 | K10 (2014) | Region VII | Bohol | 302815 | Batuan NHS | BATUAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1082168.8144 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118660 | Bayawahan ES | Sevilla | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-05-11 | 2015-05-11 | 070114S00330 | 14HB0067 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | A.S. OBQUIA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118514 | Baybayon ES | MABINI | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2935174.43 |  |  | COMPLETED | 1 | 2015-03-17 | 2015-03-17 | 070114S00089 | 14HB0028 | 2014-09-08 | 2014-07-31 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118131 | Bicao ES | Carmen | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 070114S00337 | 14HB0064 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | FIRST BUILDERS AND DEVELOPERS
NC 2014 | K10 (2014) | Region VII | Bohol | 118132 | Bohog ES | CARMEN | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2915174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118132 | Bohog ES | Carmen | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 312329 | Bugsoc High School | SIERRA BULLONES | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-03-12 | 2015-03-12 | 070114S00073 | 14HB0029 | 2014-09-08 | 2014-07-31 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118350 | Bulawan ES | GUINDULMAN | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00119 | 14HB0027 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118413 | Bunga Ilaya PS | JAGNA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1232329.12 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00124 | 14HB0026 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118044 | Cabacnitan ES | Bilar | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 117937 | Cabatang ES | ALICIA | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1052018.8144 |  |  | COMPLETED | 1 | 2015-08-23 | 2015-08-23 | 070114S00261 | 14HB0060 | 2015-02-02 | 2015-02-04 | 2015-02-16 | 2015-02-25 | 2015-03-18 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118516 | Cabidian ES | MABINI | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2015-03-17 | 2015-03-17 | 070114S00088 | 14HB0028 | 2014-09-08 | 2014-07-31 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 500207 | Calatrava Integrated School | CARMEN | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118662 | Calingaan PS | Sevilla | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-05-11 | 2015-05-11 | 070114S00292 | 14HB0067 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | A.S. OBQUIA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118017 | Cambacay P/S | Batuan | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-05-14 | 2015-05-14 | 070114S00331 | 14HB0065 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118418 | Cambugason ES | JAGNA | 3 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3850805.49 |  |  | COMPLETED | 1 | 2015-04-14 | 2015-04-14 | 070114S00114 | 14HB0026 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118306 | Cambuyo ES | Garcia Hernandez | 3 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2789983.3843 |  |  | COMPLETED | 1 | 2015-08-09 | 2015-08-09 | 070114S00291 | 14HB0072 | 2014-12-02 | 2014-12-10 | 2014-12-23 | 2014-12-29 | 2015-01-12 | LTS BUILDERS AND CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 312352 | Cambuyo HS | GARCIA HERNANDEZ | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1930466.749 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 302865 | Candijay HS | CANDIJAY | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118852 | Canduao ES | Valencia | 3 | 1 | 5 | 1STY5CL | 2014 K10 BATCH 3 | 4194992.4492 |  |  | COMPLETED | 1 | 2015-07-08 | 2015-07-08 | 070114S00299 | 14HB0069 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118420 | Canjulao ES | JAGNA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00063 | 14HB0026 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118677 | Canlangit ES | Sierra Bullones | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 070114S00297 | 14HB0063 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118865 | Cansibao ES | VALENCIA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-24 | 070114S00079 | 14HB0030 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118354 | Cansiwang ES | GUINDULMAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00118 | 14HB0027 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118571 | Cansungay ES | PILAR | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1041968.8144 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 070114S00327 | 14HB0062 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118678 | Canta-ub ES | Sierra Bullones | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 070114S00296 | 14HB0063 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118018 | Cantigdas ES | BATUAN | 3 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 4000835.14 |  |  | COMPLETED | 1 | 2015-01-09 | 2015-01-09 | 070114S00095 | 14HB0021 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-28 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118154 | Carmen East Central ES | Carmen | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-05-20 | 2015-05-20 | 070114S00341 | 14HB0065 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118355 | Casbu ES | GUINDULMAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00109 | 14HB0027 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118274 | Catugasan ES | DIMIAO | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1864740.174 |  |  | COMPLETED | 1 | 2016-02-13 |  | 070114S00471 | 15HB0032 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 302834 | Catungawan NHS | Guindulman | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118446 | Conception ES | Loay | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-07-01 | 2015-07-01 | 070114S00305 | 14HB0070 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118048 | Dagohoy ES | Bilar | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-06-10 | 070114S00333 | 14HB0066 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | LTS BUILDERS AND CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118310 | Datag ES | Garcia Hernandez | 3 | 1 | 6 | 1STY3CL, 1STY2CL & 1STY1CL | 2014 K10 BATCH 3 | 5388778.6541 |  |  | COMPLETED | 1 | 2015-12-15 | 2015-12-15 | 070114S00304 | 15HB0029 | 2015-05-13 | 2015-05-15 | 2015-05-27 | 2015-06-04 | 2015-06-26 | LTS BUILDERS AND CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118518 | Del Mar ES | MABINI | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1868614.5699 |  |  | COMPLETED | 1 | 2015-05-20 | 2015-05-20 | 070114S00322 | 14HB0061 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118682 | Dusita ES | SIERRA BULLONES | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2955174.43 |  |  | COMPLETED | 1 | 2015-03-12 | 2015-03-12 | 070114S00082 | 14HB0029 | 2014-09-08 | 2014-07-31 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 302848 | Dusita NHS | Sierra Bullones | 3 | 1 | 4 | 2UNITS 1STY2CL | 2014 K10 BATCH 3 | 3576429.1398 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118137 | El Progreso ES | Carmen | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-05-20 | 2015-05-20 | 070114S00339 | 14HB0065 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118138 | El Salvador ES | Carmen | 3 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 3 | 2003537.6289 |  |  | COMPLETED | 1 | 2015-05-20 | 2015-05-20 | 070114S00340 | 14HB0065 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118312 | Garcia Hernandez Central ES | Garcia Hernandez | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118312 | Garcia-Hernandez Central ES | GARCIA HERNANDEZ | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118139 | Guadalupe ES | CARMEN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00101 | 14HB0023 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | AL CHRIS CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 302854 | Guinacot NHS | GUINDULMAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 302855 | Guinsularan High School | DUERO | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118359 | Guio-ang ES | GUINDULMAN | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2935174.43 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00116 | 14HB0027 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 302867 | Hinawanan NHS | LOAY | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 312358 | Jagna HS | JAGNA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118436 | Jambawan ES | LILA | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1052703.8954 |  |  | COMPLETED | 1 | 2015-08-05 | 2015-08-05 | 070114S00233 | 14HB0032 | 2014-09-08 | 2014-07-31 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118020 | Janlud ES | BATUAN | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-01-09 | 2015-01-09 | 070114S00096 | 14HB0021 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-28 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 117943 | Katipunan ES Annex | ALICIA | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2679195.2697 |  |  | COMPLETED | 1 | 2015-08-23 | 2015-08-23 | 070114S00262 | 14HB0060 | 2015-02-02 | 2015-02-04 | 2015-02-16 | 2015-02-25 | 2015-03-18 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118140 | Katipunan ES | CARMEN | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2016-02-13 |  | 070114S00472 | 15HB0032 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 312359 | Katipunan HS | ALICIA | 3 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 3980835.14 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 117944 | La Hacienda ES | ALICIA | 3 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3474578.7213 |  |  | COMPLETED | 1 | 2015-08-23 | 2015-08-23 | 070114S00265 | 14HB0060 | 2015-02-02 | 2015-02-04 | 2015-02-16 | 2015-02-26 | 2015-03-18 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 302863 | La Hacienda NHS | ALICIA | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1875466.749 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118141 | La Libertad ES | CARMEN | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2016-02-13 |  | 070114S00479 | 15HB0032 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118143 | La Salvacion ES | CARMEN | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00102 | 14HB0023 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | AL CHRIS CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118117 | La Union Elementary School | Candijay | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-07-10 | 2015-07-10 | 070114S00314 | 14HB0075 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118683 | La Union ES | SIERRA BULLONES | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1072118.8144 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 070114S00328 | 14HB0062 | 2014-12-02 | 2014-12-10 |  | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118144 | La Victoria ES | CARMEN | 3 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 3990835.14 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00103 | 14HB0022 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-28 | 2014-09-15 | AL CHRIS CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118855 | La Victoria ES | VALENCIA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-24 | 070114S00080 | 14HB0030 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 186513 | Lapu-lapu ES | Carmen | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-05-20 | 2015-05-20 | 070114S00343 | 14HB0065 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 302868 | Lila NHS | LILA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2025417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118670 | Lobgob ES | Sevilla | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-06-17 | 2015-06-17 | 070114S00293 | 14HB0068 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118466 | Loboc CES | Loboc | 3 | 1 | 9 | 3UNITS 1STY3CL | 2014 K10 BATCH 3 | 7796385.8091 |  |  | COMPLETED | 1 | 2016-01-21 |  | 070114S00332 | 15HB0030 | 2015-05-13 | 2015-05-15 | 2015-05-27 | 2015-06-04 | 2015-06-26 | WYNN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118295 | Lobogon ES | DUERO | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118295 | Lobogon ES | Duero | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118118 | Luan Elementary School | Candijay | 3 | 1 | 4 | 1STY3CL & 1STY1CL | 2014 K10 BATCH 3 | 3600564.0842 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 312336 | Lungsodaan High School | MABINI | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-03-17 | 2015-03-17 | 070114S00072 | 14HB0028 | 2014-09-08 | 2014-07-31 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118296 | Madua Norte PS | DUERO | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1052018.8144 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-06-10 | 070114S00321 | 14HB0074 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | FIRST BUILDERS AND DEVELOPERS
NC 2014 | K10 (2014) | Region VII | Bohol | 118671 | Magsaysay ES | SEVILLA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-02-27 | 070114S00083 | 14HB0025 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118685 | Magsaysay ES | Sierra Bullones | 3 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2789983.3843 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 070114S00312 | 14HB0062 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 117945 | Mahayag ES | ALICIA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-01-04 | 2015-01-04 | 070114S00053 | 14HB0019 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-28 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118521 | Mahayag ES | MABINI | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1072118.8144 |  |  | COMPLETED | 1 | 2015-05-11 | 2015-05-11 | 070114S00323 | 14HB0061 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 302878 | Mayuga NHS | GUINDULMAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1082703.8954 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118146 | Monte Hermoso ES | CARMEN | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-01-29 | 2015-01-29 | 070114S00104 | 14HB0024 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118148 | Monte Sunting ES | CARMEN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-01-29 | 2015-01-29 | 070114S00105 | 14HB0024 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118149 | Montevideo ES | CARMEN | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-01-29 | 2015-01-29 | 070114S00106 | 14HB0024 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118153 | Nueva Vida Sur ES | CARMEN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1838464.5699 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 070114S00319 | 14HB0064 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | FIRST BUILDERS AND DEVELOPERS
NC 2014 | K10 (2014) | Region VII | Bohol | 118279 | Oac ES | DIMIAO | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-02-27 | 070114S00094 | 14HB0025 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118431 | Odiong ES | Jagna | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-06-23 | 2015-06-23 | 070114S00308 | 14HB0073 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118524 | Paraiso ES | MABINI | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2669145.2697 |  |  | COMPLETED | 1 | 2015-05-20 | 2015-05-20 | 070114S00324 | 14HB0061 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118581 | Pilar Central ES | PILAR | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-03-12 | 2015-03-12 | 070114S00087 | 14HB0029 | 2014-09-08 | 2014-07-31 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 117963 | Porcenas PS | ANDA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-20 | 070114S00123 | 14HB0020 | 2014-09-08 | 2014-09-18 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118051 | Riverside PS | BILAR | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118051 | Riverside PS | Bilar | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118317 | Sacaon ES | Garcia Hernandez | 3 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2789983.3843 |  |  | COMPLETED | 1 | 2015-06-23 | 2015-06-23 | 070114S00317 | 14HB0071 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118689 | San Agustin ES | Sierra Bullones | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 070114S00298 | 14HB0063 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118125 | San Isidro ES | CANDIJAY | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2905174.43 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-20 | 070114S00099 | 14HB0020 | 2014-09-08 | 2014-09-18 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118300 | San Isidro ES | Duero | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-06-10 | 070114S00303 | 14HB0074 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | FIRST BUILDERS AND DEVELOPERS
NC 2014 | K10 (2014) | Region VII | Bohol | 118584 | San Isidro ES | PILAR | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2895174.43 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00093 | 14HB0023 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | AL CHRIS CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 302889 | San Isidro Tech-Voc HS | PILAR | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1875466.749 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118692 | San Juan ES | SIERRA BULLONES | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3065174.43 |  |  | COMPLETED | 1 | 2015-03-12 | 2015-03-12 | 070114S00081 | 14HB0029 | 2014-09-08 | 2014-07-31 | 2014-09-23 | 2014-10-07 | 2014-10-24 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118301 | San Pedro ES | DUERO | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-16 | 2015-02-16 | 070114S00121 | 14HB0031 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | AL CHRIS CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 186505 | San Rafael PS | MABINI | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1875466.749 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-02-27 | 070114S00216 | 14HB0033 | 2014-09-08 | 2014-07-31 | 2014-09-23 | 2014-10-07 | 2014-10-24 | WILTAN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 302903 | Sevilla NHS | Sevilla | 3 | 1 | 6 | 1STY4CL & 1STY2CL | 2014 K10 BATCH 3 | 5192443.2912 |  |  | COMPLETED | 1 | 2015-06-17 | 2015-06-17 | 070114S00294 | 14HB0068 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118693 | Sierra Bullones CES | Sierra Bullones | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 070114S00295 | 14HB0062 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 302905 | Sierra Bullones Technical Vocational High School | SIERRA BULLONES | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1875466.749 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118860 | Simang ES | Valencia | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-07-01 | 2015-07-01 | 070114S00301 | 14HB0070 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118054 | Subayon PS | BILAR | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2905174.43 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-02-27 | 070114S00098 | 14HB0025 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 302909 | Tabuan NHS | Garcia Hernandez | 3 | 1 | 3 | 2STY2CL & 1STY1CL | 2014 K10 BATCH 3 | 5293668.4288 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118155 | Tagaonan ES | CARMEN | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118155 | Tagaonan ES | Carmen | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Bohol | 118529 | Tambo ES | MABINI | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2669145.2697 |  |  | COMPLETED | 1 | 2015-05-20 | 2015-05-20 | 070114S00325 | 14HB0061 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 500208 | Tubod Monte IS | JAGNA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00091 | 14HB0026 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118158 | Vallehermoso ES | CARMEN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00115 | 14HB0023 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | AL CHRIS CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 312357 | Vallehermoso HS | CARMEN | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00070 | 14HB0023 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-27 | 2014-09-15 | AL CHRIS CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118159 | Villaflor ES | CARMEN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 070114S00117 | 14HB0022 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-28 | 2014-09-15 | AL CHRIS CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Bohol | 118161 | Villarcayo ES | CARMEN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1858564.5699 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 070114S00320 | 14HB0064 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | FIRST BUILDERS AND DEVELOPERS
NC 2014 | K10 (2014) | Region VII | Bohol | 117966 | Virgen ES | ANDA | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1858564.5699 |  |  | COMPLETED | 1 | 2015-07-10 | 2015-07-10 | 070114S00344 | 14HB0075 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Bohol | 118058 | Zamora ES | Bilar | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2598795.2697 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-06-10 | 070114S00335 | 14HB0066 | 2014-12-02 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-12 | LTS BUILDERS AND CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Carcar City | 119154 | Buenavista ES | Carcar City | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1 | 2015-05-31 | 2015-05-25 | 070214S00315 | 14-HE-0097 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | QUIRANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Carcar City | 119155 | Calidngan ES | Carcar City | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1 | 2015-05-31 | 2015-05-31 | 070214S00320 | 14-HE-0099 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | M.P. VILLEGAS CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Carcar City | 119172 | Canal ES | CITY OF CARCAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-10-17 | 2014-10-17 | 070214S00068 | 14-HE-0025 | 2014-05-27 | 2014-05-29 | 2014-06-10 | 2014-06-16 | 2014-06-20 | FIRST GRANDEUR BUILDERS
NC 2014 | K10 (2014) | Region VII | Carcar City | 302970 | Can-asujan NHS | CITY OF CARCAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Carcar City | 119158 | Carcar Central ES | Carcar City | 1 | 1 | 5 | 1STY5CL | 2014 K10 BATCH 3 | 4112918.6116 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 070214S00317 | 14-HE-0095 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | EL-JAKE BUILDERS
NC 2014 | K10 (2014) | Region VII | Carcar City | 303127 | Gelacio C. Babao, Sr. MNHS | CITY OF CARCAR | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10917293.5547 |  |  | COMPLETED | 1 | 2015-12-07 | 2015-12-07 | 070214S00309 | 14-HE-0122 | 2014-11-27 | 2014-12-15 | 2014-12-15 | 2014-12-18 | 2014-12-23 | QUIRANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Carcar City | 119173 | Guadalupe ES | Carcar City | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1 | 2015-05-01 | 2015-05-01 | 070214S00319 | 14-HE-0096 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | EL-JAKE BUILDERS
NC 2014 | K10 (2014) | Region VII | Carcar City | 119174 | Hunob Elementary School | CITY OF CARCAR | 1 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 3980835.14 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 070214S00067 | 14-HE-0026 | 2014-05-27 | 2014-05-29 | 2014-06-10 | 2014-06-16 | 2014-06-20 | FIRST GRANDEUR BUILDERS
NC 2014 | K10 (2014) | Region VII | Carcar City | 119175 | Kalangyawon ES | CITY OF CARCAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-14 | 070214S00066 | 14-HE-0027 | 2014-06-24 | 2014-06-26 | 2014-07-08 | 2014-07-11 | 2014-07-18 | QUIRANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Carcar City | 119176 | Kamanggahan Elementary School | CITY OF CARCAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Carcar City | 119176 | Kamanggahan ES | Carcar City | 1 | 1 | 4 | 2UNITS 1STY2CL | 2014 K10 BATCH 3 | 3500545.7907 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Carcar City | 119177 | Kayam Elementary School | CITY OF CARCAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Carcar City | 119177 | Kayam ES | Carcar City | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 950215.9023 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Carcar City | 324901 | LIBURON NATIONAL HIGH SCHOOL | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-05-22 | 2015-05-22 | 070214S00310 | 14-HE-0104 | 2014-11-18 | 2014-11-20 | 2014-12-02 | 2014-12-05 | 2014-12-09 | EL-JAKE BUILDERS
NC 2014 | K10 (2014) | Region VII | Carcar City | 119179 | Maximina V. Barangan ES (Mercado) | CITY OF CARCAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-01-13 | 2015-01-12 | 070214S00072 | 14-HE-0029 | 2014-06-24 | 2014-06-26 | 2014-07-08 | 2014-07-11 | 2014-07-18 | QM BUILDERS
NC 2014 | K10 (2014) | Region VII | Carcar City | 303016 | Maximino Noel Memorial National High School | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6318764.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Carcar City | 119180 | Napo ES | Carcar City | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1750272.8953 |  |  | COMPLETED | 1 | 2015-05-31 | 2015-05-25 | 070214S00302 | 14-HE-0100 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | M.P. VILLEGAS CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Carcar City | 356059 | Ocana National High School (Kalangyawon Extension) | CITY OF CARCAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Carcar City | 303066 | OCAÑA NHS | CITY OF CARCAR | 1 | 1 | 12 | 3STY12CL | 2014 K10 BATCH 3 | 18979709.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Carcar City | 119161 | Perrelos ES | Carcar City | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1 | 2015-05-01 | 2015-05-01 | 070214S00313 | 14-HE-0101 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | QUIRANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Carcar City | 119165 | Tagaytay ES | Carcar City | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1750272.8953 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Carcar City | 119165 | Tagaytay Primary School | CITY OF CARCAR | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Carcar City | 119184 | Upland ES | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6318764.7656 |  |  | COMPLETED | 1 | 2015-06-06 | 2015-06-05 | 070214S00306 | 14-HE-0110 | 2014-11-18 | 2014-11-20 | 2014-12-02 | 2014-12-05 | 2014-12-09 | QUIRANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Carcar City | 303126 | Valencia Vocational NHS | Carcar City | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3335125.5846 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Carcar City | 119170 | Valladolid ES | Carcar City | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1750272.8953 |  |  | COMPLETED | 1 | 2015-05-01 | 2015-05-01 | 070214S00324 | 14-HE-0096 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | EL-JAKE BUILDERS
NC 2014 | K10 (2014) | Region VII | Cebu | 312401 | Balud NHS | SAN FERNANDO | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4337124.6094 |  |  | COMPLETED | 1 | 2015-05-07 | 2015-05-07 | 070214S00284 | 14-HE-0117 | 2014-11-18 | 2014-11-20 | 2014-12-02 | 2014-12-05 | 2014-12-09 | QUIRANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119618 | Balungag ES | SAN FERNANDO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1252712.2061 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-14 | 070214S00166 | 14-HE-0051 | 2014-06-25 | 2014-06-26 | 2014-07-08 | 2014-07-11 | 2014-07-18 | VIRLO CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 312427 | Balungag NHS | SAN FERNANDO | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4563249.6094 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119481 | Calbasaan ES | MINGLANILLA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 2161149.1921 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119481 | Calbasaan ES | Minglanilla | 1 | 1 | 3 | 1STY2CL, 1STY1CL | 2014 K10 BATCH 2 | 2945000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 302969 | Camp 7 NHS | MINGLANILLA | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4392399.6094 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119710 | Candaguit ES | SIBONGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1102712.2061 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-14 | 070214S00165 | 14-HE-0051 | 2014-06-25 | 2014-06-26 | 2014-07-08 | 2014-07-11 | 2014-07-18 | VIRLO CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119713 | Lamacan ES | SIBONGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1182712.2061 |  |  | COMPLETED | 1 | 2014-10-15 | 2014-09-03 | 070214S00139 | 14-HE-0052 | 2014-06-25 | 2014-06-26 | 2014-07-08 | 2014-07-11 | 2014-07-18 | SB & T CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119485 | Lipata Central ES | MINGLANILLA | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-14 |  | 070214S00434 | 15-HE-0096 | 2015-07-15 | 2015-07-16 | 2015-08-04 | 2015-08-12 | 2015-08-18 | SB & T CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119716 | Magcagong PS | Sibonga | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 950215.9023 |  |  | COMPLETED | 1 | 2015-05-01 | 2015-05-01 | 070214S00301 | 14-HE-0102 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | QUIRANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119717 | Manatad ES | SIBONGA | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6600164.7656 |  |  | COMPLETED | 1 | 2015-06-06 | 2015-06-06 | 070214S00312 | 14-HE-0106 | 2014-11-18 | 2014-11-20 | 2014-12-02 | 2014-12-05 | 2014-12-09 | MAP ALVIOLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 312457 | Manatad NHS | SIBONGA | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6529814.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119486 | Manduang ES | MINGLANILLA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1010515.9023 |  |  | COMPLETED | 1 | 2015-03-02 | 2015-02-27 | 070214S00291 | 14-HE-0094 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-12-28 | 2014-12-03 | RAMIJO CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119718 | Mangyan ES | SIBONGA | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6709664.7656 |  |  | COMPLETED | 1 | 2015-06-06 | 2015-06-05 | 070214S00281 | 14-HE-0108 | 2014-11-18 | 2014-11-20 | 2014-12-02 | 2014-12-05 | 2014-12-09 | QM BUILDERS
NC 2014 | K10 (2014) | Region VII | Cebu | 119719 | Papan ES | Sibonga | 1 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 3 | 4294527.3578 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 070214S00288 | 14-HE-0102 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | QUIRANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 303102 | Simala NHS | SIBONGA | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6499664.7656 |  |  | COMPLETED | 1 | 2015-06-06 | 2015-06-05 | 070214S00283 | 14-HE-0109 | 2014-11-19 | 2014-12-20 | 2014-12-02 | 2014-12-05 | 2014-12-09 | QM BUILDERS
NC 2014 | K10 (2014) | Region VII | Cebu | 119488 | Tungkil ES | MINGLANILLA | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6358964.7656 |  |  | COMPLETED | 1 | 2015-05-22 | 2015-05-22 | 070214S00314 | 14-HE-0116 | 2014-11-18 | 2014-11-20 | 2014-12-02 | 2014-12-05 | 2014-12-09 | QM BUILDERS
NC 2014 | K10 (2014) | Region VII | Cebu | 312450 | Tungkil NHS | MINGLANILLA | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4442649.6094 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119480 | Vito ES | MINGLANILLA | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14456118.3984 |  |  | COMPLETED | 1 | 2016-01-06 |  | 070214S00322 | 14-HE-0128 | 2014-11-27 | 2014-12-01 | 2014-12-15 | 2014-12-18 | 2014-12-23 | GENETIAN BUILDERS
NC 2014 | K10 (2014) | Region VII | Cebu | 119489 | Agbalanga ES | Moalboal | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 950215.9023 |  |  | COMPLETED | 1 | 2015-04-25 | 2015-04-15 | 070214S00293 | 14-HG-0129 (Cluster 2) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | GELA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 118939 | Alambijud ES | Argao | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1 | 2015-04-25 | 2015-04-25 | 070214S00292 | 14-HG-0128 (Cluster 1) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SERCHER DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Cebu | 119291 | Amonsao Elem. School | DALAGUETE | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 2074740.174 |  |  | COMPLETED | 1 | 2015-09-05 | 2015-09-04 | 070214S00426 | 15HG0050 | 2015-06-05 | 2015-06-10 | 2015-06-22 | 2015-06-30 | 2015-07-01 | QUIRANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | CEBU | 119398 | Anao ES | GINATILAN | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 2 | 2903861.3982 |  |  | COMPLETED | 1 | 2015-01-10 | 2014-11-03 | 070214S00088 | 14-HG-0047 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-08-12 | 2014-08-13 | QUIRANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 302925 | Bala NHS | MOALBOAL | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4A | 1750272.8953 |  |  | COMPLETED | 1 | 2015-04-26 | 2015-04-26 | 070214S00408 | 14HG0153 | 2014-12-16 | 2014-12-17 | 2014-12-22 | 2015-01-19 | 2015-01-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | CEBU | 118942 | Balaas PS | ARGAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1861149.1921 |  |  | COMPLETED | 1 | 2014-12-22 | 2014-12-22 | 070214S00087 | 14-HG-0056 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | RIKDA CONSTRUCTION & DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Cebu | 119383 | Balaygtiki ES | DUMANJUG | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6459464.7656 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-06-24 | 070214S00358 | 14-HG-0137 (Cluster 9) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
NC 2014 | K10 (2014) | Region VII | Cebu | 118918 | Balisong-Casay ES | ARGAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1 | 2015-04-25 | 2015-04-25 | 070214S00295 | 14-HG-0128 (Cluster 1) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SERCHER DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Cebu | 118997 | Basangpangpang ES | BADIAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-05-25 | 070214S00296 | 14-HG-0130 (Cluster 3) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
NC 2014 | K10 (2014) | Region VII | Cebu | 119127 | Becerril ES | BOLJOON | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1082712.2061 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-30 | 070214S00084 | 14-HG-0052 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-08-12 | 2014-08-13 | QUIRANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119000 | Bugas ES | BADIAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 980365.9023 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-05-25 | 070214S00297 | 14-HG-0130 (Cluster 3) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
NC 2014 | K10 (2014) | Region VII | Cebu | 119494 | Bugho ES | Moalboal | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1 | 2015-04-25 | 2015-04-15 | 070214S00254 | 14-HG-0129 (Cluster 2) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | GELA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 118873 | Bulalacao PS | ALCOY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1 | 2015-04-25 | 2015-04-24 | 070214S00300 | 14-HG-0131 (Cluster 4) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Cebu | 118945 | Butong ES | ARGAO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2743213.9542 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-19 | 070214S00078 | 14-HG-0040 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | SERCHER DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Cebu | 187015 | Cabutongan ES | SANTANDER | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1112712.2061 |  |  | COMPLETED | 1 | 2014-10-22 | 2014-10-22 | 070214S00086 | 14-HG-0054 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-08-04 | 2014-08-05 | QUIRANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119373 | Calaboon ES | DUMANJUG | 2 | 1 | 8 | 2UNITS 2STY4CL | 2014 K10 BATCH 3 | 12798329.5312 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-03-26 | 070214S00355 | 14-HG-0136 | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | DINAH JANE CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Cebu | 119374 | Camboang ES | DUMANJUG | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6369337.6381 |  |  | COMPLETED | 1 | 2015-10-05 | 2015-10-05 | 070214S00433 | 15HG0049 | 2015-06-05 | 2015-06-10 | 2015-06-22 | 2015-06-30 | 2015-07-01 | GELA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119595 | Can-abujon ES | RONDA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2644754.4624 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-04-13 | 070214S00360 | 14-HG-0134 (Cluster 7) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | DINAH JANE CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Cebu | 118922 | Canbantug ES | ARGAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 2161149.1921 |  |  | COMPLETED | 1 | 2014-11-23 | 2014-11-15 | 070214S00075 | 14-HG-0044 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | QUIRANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119002 | Candiis ES | BADIAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1911072.8953 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-05-25 | 070214S00298 | 14-HG-0130 (Cluster 3) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
NC 2014 | K10 (2014) | Region VII | Cebu | 302982 | Cerde¤a NHS | MALABUYOC | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1951272.8953 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119376 | Cotcoton ES | DUMANJUG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1810572.8953 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-06-24 | 070214S00356 | 14-HG-0137 (Cluster 9) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
NC 2014 | K10 (2014) | Region VII | Cebu | 119298 | Dalaguete Central ES | DALAGUETE | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6399164.7656 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-06-24 | 070214S00323 | 14-HG-0132 (Cluster 5) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SERCHER DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Cebu | 302997 | Dalaguete NHS | DALAGUETE | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4352199.6094 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119607 | Dalahikan ES | SAMBOAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1951272.8953 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-04-13 | 070214S00361 | 14-HG-0134 (Cluster 7) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | DINAH JANE CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Cebu | 118928 | Dalas-ag PS | ARGAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1102712.2061 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-10-18 | 070214S00076 | 14-HG-0049 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | RAJLAURENTE CONSTRUCTION & DEVELOPMENT PHIL.
NC 2014 | K10 (2014) | Region VII | Cebu | 119299 | Dugyan ES | DALAGUETE | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-04-24 | 070214S00348 | 14-HG-0132 (Cluster 5) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SERCHER DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Cebu | 119131 | Granada ES | BOLJOON | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 950215.9023 |  |  | COMPLETED | 1 | 2015-04-25 | 2015-04-24 | 070214S00289 | 14-HG-0131 (Cluster 4) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Cebu | 118948 | Guiwanon ES | ARGAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1122712.2061 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-10-18 | 070214S00079 | 14-HG-0050 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | RAJLAURENTE CONSTRUCTION & DEVELOPMENT PHIL.
NC 2014 | K10 (2014) | Region VII | Cebu | 187006 | Kanghalo PS | DUMANJUG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 990415.9023 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-06-24 | 070214S00362 | 14-HG-0137 (Cluster 9) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
NC 2014 | K10 (2014) | Region VII | Cebu | 119301 | Karatagan ES | DALAGUETE | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2851238.7977 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-06-24 | 070214S00349 | 14-HG-0132 (Cluster 5) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SERCHER DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Cebu | 119302 | Langkas ES | DALAGUETE | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1090915.9023 |  |  | COMPLETED | 1 | 2015-03-26 | 2015-03-26 | 070214S00350 | 14-HG-0133 (Cluster 6) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Cebu | 118891 | Legaspi Elementary School | ALEGRIA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042712.2061 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-09-30 | 070214S00080 | 14-HG-0045 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | RUDPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119599 | Liboo ES | RONDA | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 2 | 2953861.3982 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-11-03 | 070214S00085 | 14-HG-0039 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | RUDPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119321 | Lumbang ES | DALAGUETE | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 950215.9023 |  |  | COMPLETED | 1 | 2015-03-26 | 2015-02-27 | 070214S00354 | 14-HG-0133 (Cluster 6) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | CEBU | 302944 | Lunop NHS | BOLJOON | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042712.2061 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 118955 | Malalag ES | ARGAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1252712.2061 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-10-18 | 070214S00090 | 14-HG-0051 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | RAJLAURENTE CONSTRUCTION & DEVELOPMENT PHIL.
NC 2014 | K10 (2014) | Region VII | Cebu | 119305 | Mantalongon ES | DALAGUETE | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2896004.4624 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-05-29 | 070214S00351 | 14-HG-0132 (Cluster 5) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SERCHER DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Cebu | 303000 | Mantalongon NHS | DALAGUETE | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6499664.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 118896 | Mayana ES | ALEGRIA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1192712.2061 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-10-15 | 070214S00074 | 14-HG-0046 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | RUDPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 118957 | Mompeller PS | ARGAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 2051149.1921 |  |  | COMPLETED | 1 | 2014-11-23 | 2014-11-03 | 070214S00081 | 14-HG-0042 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | QUIRANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119499 | Omay PS | Moalboal | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 950215.9023 |  |  | COMPLETED | 1 | 2015-04-25 | 2015-04-15 | 070214S00294 | 14-HG-0129 (Cluster 2) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | GELA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 312459 | Palanas Integrated School | GINATILAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | CEBU | 303084 | Salamanca NHS | GINATILAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042712.2061 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119449 | Salmeron ES | MALABUYOC | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2745254.4624 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-04-13 | 070214S00347 | 14-HG-0134 (Cluster 7) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | DINAH JANE CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Cebu | 119010 | Sanlagan ES | BADIAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-05-25 | 070214S00299 | 14-HG-0130 (Cluster 3) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
NC 2014 | K10 (2014) | Region VII | Cebu | 118960 | Sua ES | ARGAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1232712.2061 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-10-18 | 070214S00073 | 14-HG-0055 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | RIKDA CONSTRUCTION & DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Cebu | 118961 | Sumaguan ES | ARGAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 2011149.1921 |  |  | COMPLETED | 1 | 2014-11-23 | 2014-11-23 | 070214S00083 | 14-HG-0041 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-07-31 | 2014-08-01 | RUDPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 118933 | Tabayag ES | ARGAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 2261149.1921 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 070214S00077 | 14-HG-0043 | 2014-06-24 | 2014-06-25 | 2014-07-10 | 2014-08-12 | 2014-08-13 | QUIRANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119309 | Tabon ES | DALAGUETE | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2896004.4624 |  |  | COMPLETED | 1 | 2015-03-26 | 2015-03-26 | 070214S00352 | 14-HG-0133 (Cluster 6) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Cebu | 312454 | Tan-awan NHS | OSLOB | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119382 | Tapon ES | DUMANJUG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1810572.8953 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-06-24 | 070214S00369 | 14-HG-0137 (Cluster 9) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
NC 2014 | K10 (2014) | Region VII | Cebu | 119014 | Taytay ES | BADIAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-05-25 | 070214S00334 | 14-HG-0130 (Cluster 3) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
NC 2014 | K10 (2014) | Region VII | Cebu | 119310 | Tubod ES | DALAGUETE | 2 | 1 | 3 | 3UNITS 1STY1CL | 2014 K10 BATCH 3 | 7884013.3872 |  |  | COMPLETED | 1 | 2015-03-26 | 2015-02-27 | 070214S00353 | 14-HG-0133 (Cluster 6) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Cebu | 302923 | Tubod NHS | BADIAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 118963 | Tulang ES | Argao | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1750272.8953 |  |  | COMPLETED | 1 | 2015-04-25 | 2015-04-25 | 070214S00280 | 14-HG-0128 (Cluster 1) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SERCHER DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Cebu | 118938 | Usmad ES | Argao | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1 | 2015-04-25 | 2015-04-25 | 070214S00290 | 14-HG-0128 (Cluster 1) | 2014-10-27 | 2014-10-30 | 2014-11-11 | 2014-11-19 | 2014-11-20 | SERCHER DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Cebu | 312455 | Willy B. Wenceslao NHS | SANTANDER | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 118901 | Angilan Elementary School | ALOGUINSAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1010515.9023 |  |  | COMPLETED | 1 | 2015-03-22 | 2015-03-22 | 070214S00328 | 14HF0135 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-15 | By Administration
NC 2014 | K10 (2014) | Region VII | Cebu | 119552 | Anislag ES | PINAMUNGAHAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1112712.2061 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 070214S00178 | 14HF0042 | 2014-08-22 | 2014-09-02 | 2014-09-03 | 2014-09-10 | 2014-09-16 | DINAH JANE CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Cebu | 119826 | Antipolo ES | TUBURAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1092712.2061 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-26 | 070214S00171 | 14HF0044 | 2014-08-27 | 2014-09-08 | 2014-09-09 | 2014-09-16 | 2014-09-22 | FIRST GRANDEUR BUILDERS
NC 2014 | K10 (2014) | Region VII | Cebu | 119806 | Bagasawe ES | TUBURAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1082712.2061 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 070214S00174 | 14HF0043 | 2014-08-22 | 2014-09-02 | 2014-09-03 | 2014-09-10 | 2014-09-16 | MAP ALVIOLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119827 | Bakyawan ES | TUBURAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1971149.1921 |  |  | COMPLETED | 1 | 2015-02-10 | 2015-02-10 | 070214S00170 | 14HF0078 | 2014-10-15 | 2014-10-27 | 2014-10-28 | 2014-10-31 | 2014-11-06 | By Administration
NC 2014 | K10 (2014) | Region VII | Cebu | 303069 | Bartolome & Manuela Pañares MNHS | BARILI | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6399164.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119019 | Biasong ES | BALAMBAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1 | 2015-04-28 | 2015-04-28 | 070214S00333 | 14HF0121 | 2014-12-02 | 2014-12-03 | 2014-12-15 | 2014-12-18 | 2014-12-23 | LA PRUEBA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119074 | Bolocboloc ES | BARILI | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1 | 2015-02-12 | 2015-02-12 | 070214S00343 | 14HF0090 | 2014-11-14 | 2014-11-27 | 2014-11-28 | 2014-12-03 | 2014-12-08 | FIRST GRANDEUR BUILDERS
NC 2014 | K10 (2014) | Region VII | Cebu | 118904 | Bonbon ES | ALOGUINSAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-04-11 | 070214S00329 | 14HF0127 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-05 | DINAH JANE CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Cebu | 302950 | BUANOY NHS-EVENING OPPORTUNITY CLASS | BALAMBAN | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6399164.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119075 | Budbud ES | BARILI | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1 | 2015-03-14 | 2015-03-13 | 070214S00344 | 14HF0092 | 2014-11-14 | 2014-11-27 | 2014-11-28 | 2014-12-03 | 2014-12-08 | FIRST BUILDERS AND DEVELOPERS
NC 2014 | K10 (2014) | Region VII | Cebu | 187011 | Buhingtubig PS | PINAMUNGAHAN | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4392399.6094 |  |  | COMPLETED | 1 | 2015-04-22 | 2015-04-21 | 070214S00229 | 14HF0118 | 2014-11-27 | 2014-12-08 | 2014-12-09 | 2014-12-12 | 2014-12-17 | GOLDFIN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119555 | Busay ES | PINAMUNGAHAN | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2644754.4624 |  |  | COMPLETED | 1 | 2015-03-14 | 2015-03-13 | 070214S00218 | 14HF0091 | 2014-11-14 | 2014-11-27 | 2014-11-28 | 2014-12-03 | 2014-12-08 | BL PANGAN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119020 | C. Pepito ES | BALAMBAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1020565.9023 |  |  | COMPLETED | 1 | 2015-04-21 | 2015-04-21 | 070214S00346 | 14HF0132 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-15 | By Administration
NC 2014 | K10 (2014) | Region VII | Cebu | 303071 | Cagay NHS | BARILI | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1010515.9023 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119036 | Cambagucbok ES | BALAMBAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1951272.8953 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-02-27 | 070214S00339 | 14HF0123 | 2014-12-02 | 2014-12-12 | 2014-12-15 | 2014-12-18 | 2014-12-23 | BL PANGAN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119558 | Candiis ES | PINAMUNGAHAN | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2644754.4624 |  |  | COMPLETED | 1 | 2015-03-27 | 2015-03-26 | 070214S00222 | 14HF0123 | 2014-12-02 | 2014-12-12 | 2014-12-15 | 2014-12-18 | 2014-12-23 | BL PANGAN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119038 | Cantibas PS | BALAMBAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1100965.9023 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-02-26 | 070214S00340 | 14HF0123 | 2014-12-02 | 2014-12-12 | 2014-12-15 | 2014-12-18 | 2014-12-23 | BL PANGAN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119039 | Casili ES | BALAMBAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1951272.8953 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 070214S00341 | 14HF0114 | 2014-11-19 | 2014-12-01 | 2014-12-02 | 2014-12-05 | 2014-12-10 | LA PRUEBA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 302987 | Colonia NHS | TUBURAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1010515.9023 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119040 | Cornelio C. Melgar Elementary School | BALAMBAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4A | 1750272.8953 |  |  | COMPLETED | 1 | 2015-04-28 | 2015-04-28 | 070214S00414 | 14HF0147 | 2014-12-23 | 2014-12-16 | 2014-12-23 | 2015-01-07 | 2015-01-22 | By Administration
NC 2014 | K10 (2014) | Region VII | Cebu | 303045 | Federico & Solidad MNHS | BARILI | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2813213.9542 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119082 | Federico & Solidad Villaflor ES (Luhod ES) | BARILI | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-14 | 070214S00368 | 14HF0095 | 2014-11-14 | 2014-11-27 | 2014-11-28 | 2014-12-03 | 2014-12-08 | R.M. MONDARES CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119832 | Fortaliza PS | TUBURAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1092712.2061 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 070214S00169 | 14HF0046 | 2014-08-27 | 2014-09-08 | 2014-09-09 | 2014-09-16 | 2014-09-22 | QUIRANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119560 | Guimbawi-an ES | PINAMUNGAHAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1112712.2061 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 070214S00191 | 14HF0042 | 2014-08-22 | 2014-09-02 | 2014-09-03 | 2014-09-10 | 2014-09-16 | DINAH JANE CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Cebu | 119023 | Hingatmonan ES | BALAMBAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1901022.8953 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-04-11 | 070214S00335 | 14HF0126 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2014-12-26 | DINAH JANE CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Cebu | 312451 | Ireneo V. Diamante NHS | TUBURAN | 3 | 1 | 4 | 2UNITS 1STY2CL | 2014 K10 BATCH 3 | 3701545.7907 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119836 | Kabangkalan ES | TUBURAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1152712.2061 |  |  | COMPLETED | 1 | 2015-02-10 | 2015-02-10 | 070214S00168 | 14HF0074 | 2014-10-15 | 2014-10-27 | 2014-10-28 | 2014-10-31 | 2014-11-06 | By Administration
NC 2014 | K10 (2014) | Region VII | Cebu | 312453 | Kalangahan NHS | TUBURAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119839 | Kamansi ES | TUBURAN | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 3103213.9542 |  |  | COMPLETED | 1 | 2014-12-27 | 2014-12-27 | 070214S00167 | 14HF0045 | 2014-08-27 | 2014-09-08 | 2014-09-09 | 2014-09-16 | 2014-09-22 | MAP ALVIOLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119841 | Kansi ES | TUBURAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 2011149.1921 |  |  | COMPLETED | 1 | 2015-02-10 | 2015-02-09 | 070214S00096 | 14HF0075 | 2014-10-15 | 2014-10-27 | 2014-10-28 | 2014-10-31 | 2014-11-06 | By Administration
NC 2014 | K10 (2014) | Region VII | Cebu | 303029 | Lamac NHS | PINAMUNGAHAN | 3 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8328953.2031 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119080 | Lamak ES | BARILI | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2644754.4624 |  |  | COMPLETED | 1 | 2015-03-14 | 2015-03-14 | 070214S00345 | 14HF0105 | 2014-11-14 | 2014-11-27 | 2014-11-28 | 2014-12-03 | 2014-12-08 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Cebu | 119025 | Lamesa ES | BALAMBAN | 3 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8529953.2031 |  |  | COMPLETED | 1 | 2015-05-13 | 2015-05-13 | 070214S00325 | 14HF0121 | 2014-12-02 | 2014-12-03 | 2014-12-15 | 2014-12-18 | 2014-12-23 | LA PRUEBA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 118981 | Lunas Ii ES | ASTURIAS | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1 | 2015-02-12 | 2015-02-12 | 070214S00330 | 14HF0091 | 2014-11-14 | 2014-11-27 | 2014-11-28 | 2014-12-03 | 2014-12-08 | BL PANGAN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119814 | Lusong ES | TUBURAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1132712.2061 |  |  | COMPLETED | 1 | 2015-02-10 | 2015-02-09 | 070214S00164 | 14HF0077 | 2014-10-15 | 2014-10-27 | 2014-10-28 | 2014-10-31 | 2014-11-06 | By Administration
NC 2014 | K10 (2014) | Region VII | Cebu | 119562 | Lut-od ES | PINAMUNGAHAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1092712.2061 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119562 | Lut-od ES | Pinamungajan | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 303078 | Lut-od NHS | PINAMUNGAHAN | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4392399.6094 |  |  | COMPLETED | 1 | 2015-04-22 | 2015-04-21 | 070214S00200 | 14HF0118 | 2014-11-27 | 2014-12-08 | 2014-12-09 | 2014-12-12 | 2014-12-17 | GOLDFIN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119845 | Mag-atubang PS | TUBURAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1152712.2061 |  |  | COMPLETED | 1 | 2015-02-10 | 2015-02-10 | 070214S00149 | 14HF0076 | 2014-10-15 | 2014-10-27 | 2014-10-28 | 2014-10-31 | 2014-11-06 | By Administration
NC 2014 | K10 (2014) | Region VII | Cebu | 119084 | Maghanoy ES | BARILI | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1 | 2015-02-12 | 2015-02-12 | 070214S00253 | 14HF0090 | 2014-11-14 | 2014-11-27 | 2014-11-28 | 2014-12-03 | 2014-12-08 | FIRST GRANDEUR BUILDERS
NC 2014 | K10 (2014) | Region VII | Cebu | 119847 | Mangga ES | TUBURAN | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6419264.7656 |  |  | COMPLETED | 1 | 2015-04-13 | 2015-04-13 | 070214S00228 | 14HF0107 | 2014-11-14 | 2014-11-27 | 2014-11-28 | 2014-12-03 | 2014-12-08 | FIRST GRANDEUR BUILDERS
NC 2014 | K10 (2014) | Region VII | Cebu | 312418 | Manguiao NHS | ASTURIAS | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119098 | Mantalongon ES | BARILI | 3 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3395425.5846 |  |  | COMPLETED | 1 | 2015-04-13 | 2015-04-13 | 070214S00216 | 14HF0095 | 2014-11-14 | 2014-11-27 | 2014-11-28 | 2014-12-03 | 2014-12-08 | R.M. MONDARES CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119086 | Mantayupan ES | BARILI | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1 | 2015-04-21 | 2015-04-20 | 070214S00219 | 14HF0130 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-15 | By Administration
NC 2014 | K10 (2014) | Region VII | Cebu | 119817 | Matnog ES | TUBURAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1931149.1921 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 070214S00173 | 14HF0046 | 2014-08-27 | 2014-09-08 | 2014-09-09 | 2014-09-16 | 2014-09-22 | QUIRANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119046 | Matun-og ES | BALAMBAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1070815.9023 |  |  | COMPLETED | 1 | 2015-04-21 | 2015-04-21 | 070214S00342 | 14HF0132 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-15 | By Administration
NC 2014 | K10 (2014) | Region VII | Cebu | 119849 | Molobolo PS | TUBURAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1152712.2061 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 070214S00150 | 14HF0045 | 2014-08-27 | 2014-09-08 | 2014-09-09 | 2014-09-16 | 2014-09-22 | MAP ALVIOLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119027 | Nangka ES | BALAMBAN | 3 | 1 | 10 | 2STY6CL & 2STY4CL | 2014 K10 BATCH 3 | 14778367.9688 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-06-10 | 070214S00337 | 14HF0128 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-05 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Cebu | 302949 | Nangka NHS | BALAMBAN | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4A | 6298664.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119565 | Pandacan ES | PINAMUNGAHAN | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1 | 2015-03-12 | 2015-03-12 | 070214S00223 | 14HF0137 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-05 | BL PANGAN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119088 | Pangpang PS | BARILI | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1010515.9023 |  |  | COMPLETED | 1 | 2015-04-21 | 2015-04-21 | 070214S00217 | 14HF0130 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-15 | By Administration
NC 2014 | K10 (2014) | Region VII | Cebu | 303068 | Patupat NHS | BARILI | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2644754.4624 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119566 | Pinamungajan CES | Pinamungajan | 3 | 1 | 6 | 2UNITS 1STY3CL | 2014 K10 BATCH 3 | 5088508.9248 |  |  | COMPLETED | 1 | 2015-04-22 | 2015-04-21 | 070214S00357 | 14HF0116 | 2014-11-27 | 2014-12-08 | 2014-12-09 | 2014-12-12 | 2014-12-17 | BL PANGAN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 303075 | Pinamungajan NHS | PINAMUNGAHAN | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119567 | Punod ES | PINAMUNGAHAN | 3 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3385375.5846 |  |  | COMPLETED | 1 | 2015-04-22 | 2015-04-21 | 070214S00236 | 14HF0118 | 2014-11-27 | 2014-12-08 | 2014-12-09 | 2014-12-12 | 2014-12-17 | GOLDFIN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 303083 | Rosario NHS | ALOGUINSAN | 3 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8379203.2031 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119569 | Sacsac ES | PINAMUNGAHAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1780422.8953 |  |  | COMPLETED | 1 | 2015-03-22 | 2015-03-22 | 070214S00225 | 14HF0131 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-15 | By Administration
NC 2014 | K10 (2014) | Region VII | Cebu | 118986 | San Isidro ES | ASTURIAS | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1870872.8953 |  |  | COMPLETED | 1 | 2015-02-12 | 2015-02-11 | 070214S00331 | 14HF0093 | 2014-11-14 | 2014-11-27 | 2014-11-28 | 2014-12-03 | 2014-12-08 | BLIMEX CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Cebu | 119571 | Sibago ES | PINAMUNGAHAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1000465.9023 |  |  | COMPLETED | 1 | 2015-04-21 | 2015-04-21 | 070214S00215 | 14HF0131 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-15 | By Administration
NC 2014 | K10 (2014) | Region VII | Cebu | 119028 | Singsing PS | BALAMBAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1010515.9023 |  |  | COMPLETED | 1 | 2015-04-21 | 2015-04-20 | 070214S00338 | 14HF0132 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-15 | By Administration
NC 2014 | K10 (2014) | Region VII | Cebu | 118989 | Sta. Rita ES | ASTURIAS | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1 | 2015-03-23 | 2015-03-23 | 070214S00332 | 14HF0117 | 2014-11-27 | 2014-12-08 | 2014-12-09 | 2014-12-12 | 2014-12-17 | BL PANGAN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 312414 | Sta. Rita NHS | ASTURIAS | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2853213.9542 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119572 | Tajao Central School | PINAMUNGAHAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1750272.8953 |  |  | COMPLETED | 1 | 2015-03-22 | 2015-03-22 | 070214S00207 | 14HF0131 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-15 | By Administration
NC 2014 | K10 (2014) | Region VII | Cebu | 119573 | Tangub ES | PINAMUNGAHAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1000465.9023 |  |  | COMPLETED | 1 | 2015-03-22 | 2015-03-22 | 070214S00227 | 14HF0131 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-15 | By Administration
NC 2014 | K10 (2014) | Region VII | Cebu | 119574 | Tanibag ES | PINAMUNGAHAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1830672.8953 |  |  | COMPLETED | 1 | 2015-03-23 | 2015-03-23 | 070214S00224 | 14HF0116 | 2014-11-27 | 2014-12-08 | 2014-12-09 | 2014-12-12 | 2014-12-17 | BL PANGAN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 118992 | Tubigagmanok ES | ASTURIAS | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-12-13 | 2015-12-07 | 070214S00432 | 15HF0078 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-02 | 2015-09-08 | J.A.R.C. CONSTRUCTION COMPANY
NC 2014 | K10 (2014) | Region VII | Cebu | 119824 | Tuburan Central ES | TUBURAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1911149.1921 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 070214S00182 | 14HF0043 | 2014-08-22 | 2014-09-02 | 2014-09-03 | 2014-09-10 | 2014-09-16 | MAP ALVIOLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 303061 | Tuburan National High School | TUBURAN | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119576 | Tutay ES | Pinamungajan | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1 | 2015-02-12 | 2015-02-12 | 070214S00326 | 14HF0092 | 2014-11-14 | 2014-11-27 | 2014-11-28 | 2014-12-03 | 2014-12-08 | FIRST BUILDERS AND DEVELOPERS
NC 2014 | K10 (2014) | Region VII | Cebu | 500220 | Anapog Integrated School | SAN REMIGIO | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 500219 | Argawanon Integrated School | SAN REMIGIO | 4 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2644754.4624 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119059 | Atop-atop ES | Bantayan | 4 | 1 | 4 | 1STY3CL, 1STY1CL | 2014 K10 BATCH 2 | 4007000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00192 | 14HD0027 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | ROVILLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 302924 | Bakhawan NHS | DAANBANTAYAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1092712.2061 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 302938 | Bantayan NHS | BANTAYAN | 4 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 3 | 11579484.375 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119062 | Baod ES | BANTAYAN | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1951272.8953 |  |  | COMPLETED | 1 | 2015-05-17 | 2015-05-17 | 070214S00196 | 15HD0017 | 2015-02-04 | 2015-02-16 | 2015-02-16 | 2015-02-23 | 2015-03-04 | ROVILLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119672 | Batad ES | San Remegio | 4 | 1 | 7 | 2U-1STY1CL, 1STY5CL | 2014 K10 BATCH 2 | 6579000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00147 | 14HD0022 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | FIRST BUILDERS AND DEVELOPERS
NC 2014 | K10 (2014) | Region VII | Cebu | 302939 | Bateria NHS | DAANBANTAYAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1092712.2061 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119264 | Bitoon ES | DAANBANTAYAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1092712.2061 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00153 | 14HD0025 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | FIRST BUILDERS AND DEVELOPERS
NC 2014 | K10 (2014) | Region VII | Cebu | 119265 | Calape ES | DAANBANTAYAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1092712.2061 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00163 | 14HD0024 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | BANTAY CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119749 | Canaocanao ES | Tabogon | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1063000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00154 | 14HD0019 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2014 | K10 (2014) | Region VII | Cebu | 119457 | Curva ES | Medellin | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1063000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00145 | 14HD0021 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2014 | K10 (2014) | Region VII | Cebu | 303026 | Curva NHS | MEDELLIN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1072712.2061 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119267 | Dalingding ES | DAANBANTAYAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1092712.2061 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00155 | 14HD0024 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | BANTAY CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119459 | Dalingding ES | Medellin | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1063000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00144 | 14HD0021 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2014 | K10 (2014) | Region VII | Cebu | 119461 | Don Virgilio ES | MEDELLIN | 4 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2733213.9542 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00157 | 14HD0021 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2014 | K10 (2014) | Region VII | Cebu | 303007 | Doong NHS | BANTAYAN | 4 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3536125.5846 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 312458 | Gibitngil Integrated School | MEDELLIN | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1986149.1921 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119268 | Guinsolungan ES | Daanbantayan | 4 | 1 | 6 | 1STY1CL, 1STY2CL, 1STY3CL | 2014 K10 BATCH 2 | 5679000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00184 | 14HD0025 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | FIRST BUILDERS AND DEVELOPERS
NC 2014 | K10 (2014) | Region VII | Cebu | 119687 | Hagdan ES | Sta. Fe | 4 | 1 | 17 | 2U-1STY3CL, 2U-1STY1CL, 1STY3CL, 1STY5CL, 1STY4CL | 2014 K10 BATCH 2 | 16500000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00135 | 14HD0028 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | ROVILLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119688 | Hilantagaan ES | SANTA FE | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4A | 1750272.8953 |  |  | COMPLETED | 1 | 2015-05-12 | 2015-05-12 | 070214S00405 | 15HD0022 | 2015-02-04 | 2015-02-16 | 2015-02-16 | 2015-02-23 | 2015-03-04 | ROVILLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 312456 | Hilotongan Integrated School | BANTAYAN | 4 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3686875.5846 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 303004 | Horacio Franco MNHS | TABOGON | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1921149.1921 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119752 | Jose Malazarte ES | TABOGON | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1981149.1921 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00158 | 14HD0019 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2014 | K10 (2014) | Region VII | Cebu | 119064 | Kabac ES | Bantayan | 4 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2246000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00190 | 14HD0027 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | ROVILLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 303028 | Kinartacan NHS | SANTA FE | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 2001522.8953 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119281 | Lanao ES | DAANBANTAYAN | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1010515.9023 |  |  | COMPLETED | 1 | 2015-07-02 | 2015-07-02 | 070214S00303 | 15HD0016 | 2015-02-04 | 2015-02-16 | 2015-02-16 | 2015-02-23 | 2015-03-04 | FIRST BUILDERS AND DEVELOPERS
NC 2014 | K10 (2014) | Region VII | Cebu | 303041 | Libaong NHS | SAN REMIGIO | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1030615.9023 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119269 | Libertad Ps | Daanbantayan | 4 | 1 | 4 | 2U-1STY1CL, 1STY2CL | 2014 K10 BATCH 2 | 4008000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00194 | 14HD0026 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | BANTAY CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119052 | Lipayran ES | Bantayan | 4 | 1 | 8 | 2U-1STY2CL, 1STY1CL, 1STY3CL | 2014 K10 BATCH 2 | 7941000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00189 | 14HD0027 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | ROVILLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119282 | Logon ES | DAANBANTAYAN | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4A | 1750272.8953 |  |  | COMPLETED | 1 | 2015-09-18 | 2015-09-18 | 070214S00410 | 15HD0021 | 2015-05-18 | 2015-05-27 | 2015-05-27 | 2015-06-05 | 2015-06-24 | BANTAY CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119666 | Looc ES | SAN REMIGIO | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1010515.9023 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 070214S00206 | 14HD0084 | 2015-01-05 | 2015-01-16 | 2015-01-16 | 2015-02-10 | 2015-02-16 | GOLDFIN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119679 | Luyang ES | SAN REMIGIO | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1810572.8953 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 070214S00209 | 14HD0084 | 2015-01-05 | 2015-01-16 | 2015-01-16 | 2015-02-10 | 2015-02-16 | GOLDFIN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119428 | Maalat ES | MADRIDEJOS | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1951272.8953 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 070214S00199 | 14HD0088 | 2015-01-05 | 2015-01-16 | 2015-01-16 | 2015-02-06 | 2015-02-16 | ROVILLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119757 | Mabuli ES | TABOGON | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1961149.1921 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00159 | 14HD0019 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2014 | K10 (2014) | Region VII | Cebu | 119778 | Mabunao ES | Tabuelan | 4 | 1 | 7 | 5U-1STY1CL, 1STY2CL | 2014 K10 BATCH 2 | 7197000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00161 | 14HD0020 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | GONZALO CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119466 | Maharuhay ES | MEDELLIN | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1890972.8953 |  |  | COMPLETED | 1 | 2015-07-01 | 2015-07-01 | 070214S00214 | 15HD0015 | 2015-02-04 | 2015-02-16 | 2015-02-16 | 2015-02-23 | 2015-03-04 | BANTAY CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119053 | Mambacayao ES | Bantayan | 4 | 1 | 6 | 1STY3CL, 1STY1CL, 1STY2CL | 2014 K10 BATCH 2 | 6109000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00193 | 14HD0027 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | ROVILLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 312445 | Marikaban Integrated School | SANTA FE | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119759 | Muabog ES | Tabogon | 4 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2116000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00138 | 14HD0019 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2014 | K10 (2014) | Region VII | Cebu | 119692 | Okoy ES | SANTA FE | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1890972.8953 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 070214S00210 | 14HD0086 | 2015-01-05 | 2015-01-16 | 2015-01-16 | 2015-02-10 | 2015-02-16 | ROVILLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119693 | Pooc Elementary School | SANTA FE | 4 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2745254.4624 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 070214S00211 | 14HD0086 | 2015-01-05 | 2015-01-16 | 2015-01-16 | 2015-02-10 | 2015-02-16 | ROVILLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119668 | Punta ES | SAN REMIGIO | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1010515.9023 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 070214S00208 | 14HD0084 | 2015-01-05 | 2015-01-16 | 2015-01-16 | 2015-02-10 | 2015-02-16 | GOLDFIN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119286 | Purgason PS | DAANBANTAYAN | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1921149.1921 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00148 | 14HD0026 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | BANTAY CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119763 | San Vicente ES | Tabogon | 4 | 1 | 3 | 1STY2CL, 1STY1CL | 2014 K10 BATCH 2 | 2965000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00140 | 14HD0019 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2014 | K10 (2014) | Region VII | Cebu | 119069 | Sillon ES | Bantayan | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1123000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119764 | Somosa ES | Tabogon | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1063000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00162 | 14HD0019 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2014 | K10 (2014) | Region VII | Cebu | 312420 | Sta. Fe. NHS-Hilantagaan Ext | Sta. Fe | 4 | 1 | 3 | 1STY2CL, 1STY1CL | 2014 K10 BATCH 2 | 3105000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119433 | tabagak Es | Madridejos | 4 | 1 | 4 | 2U-1STY1CL, 1STY2CL | 2014 K10 BATCH 2 | 4218000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00146 | 14HD0029 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | ROVILLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119288 | Talisay ES | DAANBANTAYAN | 4 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-07-02 | 2015-07-02 | 070214S00202 | 15HD0016 | 2015-02-04 | 2015-02-16 | 2015-02-16 | 2015-02-23 | 2015-03-04 | FIRST BUILDERS AND DEVELOPERS
NC 2014 | K10 (2014) | Region VII | Cebu | 119289 | Tapilon CES | Daanbantayan | 4 | 1 | 3 | 1STY2CL, 1STY1CL | 2014 K10 BATCH 2 | 2955000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00175 | 14HD0023 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | BANTAY CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 302964 | Tapilon NHS | DAANBANTAYAN | 4 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2753213.9542 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119435 | Tarong ES | MADRIDEJOS | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1090915.9023 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 070214S00203 | 14HD0088 | 2015-01-05 | 2015-01-16 | 2015-01-16 | 2015-02-06 | 2015-02-16 | ROVILLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119290 | Tominjao ES | Daanbantayan | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1073000 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 070214S00133 | 14HD0023 | 2014-07-15 | 2014-07-16 | 2014-07-28 | 2014-08-04 | 2014-08-18 | BANTAY CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 302965 | Tominjao National High School | DAANBANTAYAN | 4 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4352199.6094 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119436 | Tugas ES | MADRIDEJOS | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1090915.9023 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 070214S00204 | 14HD0088 | 2015-01-05 | 2015-01-16 | 2015-01-16 | 2015-02-10 | 2015-02-16 | ROVILLA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119223 | Bagalnga ES | COMPOSTELA | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1072712.2061 |  |  | COMPLETED | 1 | 2014-11-25 | 2014-11-25 | 070214S00118 | 14HI0032B | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-09-30 | VEN RAY CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region VII | Cebu | 312448 | Bagalnga Integrated School | COMPOSTELA | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1072712.2061 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 303105 | Bongdo NHS | BORBON | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1122712.2061 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 302968 | Cabonga-an NHS | SAN FRANCISCO | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1830672.8953 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119639 | Cambat-an ES | San Francisco | 5 | 1 | 5 | 1STY4CL, 1STY1CL | 2014 K10 BATCH 2 | 4946000 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-02-27 | 070214S00142 | 14HI0030 | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-09-30 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Cebu | 302967 | Camotes NHS | SAN FRANCISCO | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 2041149.1921 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119187 | Carmen Central ES | CARMEN | 5 | 1 | 4 | 2UNITS 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-04-11 | 070214S00266 | 14HI0093A | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
NC 2014 | K10 (2014) | Region VII | Cebu | 302973 | Carmen NHS-Day | CARMEN | 5 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4342149.6094 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119411 | Catarman ES | LILOAN | 5 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4362249.6094 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-05-24 | 070214S00268 | 15HI0004 | 2015-01-22 | 2015-02-03 | 2015-02-04 | 2015-02-08 | 2015-02-24 | NEOVENTURES CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 312447 | Catmon Integrated School | CATMON | 5 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14456118.3984 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119226 | Compostela Central ES | COMPOSTELA | 5 | 1 | 12 | 3STY12CL | 2014 K10 BATCH 4B | 18222268.79 |  |  | COMPLETED | 1 | 2016-04-20 |  | 070214S00431 | 15HI0076 | 2015-08-23 | 2015-09-04 | 2015-09-05 | 2015-09-09 | 2015-09-13 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Cebu | 119641 | Consuelo ES | SAN FRANCISCO | 5 | 1 | 4 | 2UNITS 1STY2CL | 2014 K10 BATCH 3 | 3751795.7907 |  |  | COMPLETED | 1 | 2015-03-12 | 2015-03-12 | 070214S00274 | 14HI0096A | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | JOHN ARNE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 302994 | Consuelo NHS | San Francisco | 5 | 1 | 4 | 1STY3CL, 1STY1CL | 2014 K10 BATCH 2 | 3977000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119642 | Daan Montealegre ES | SAN FRANCISCO | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1030615.9023 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-04-11 | 070214S00275 | 14HI0094B | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Cebu | 119730 | Daat PS | Sogod | 5 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2126000 |  |  | COMPLETED | 1 | 2014-11-13 | 2014-11-13 | 070214S00177 | 14HI0037 | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-09-30 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Cebu | 119227 | Dapdap ES | COMPOSTELA | 5 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 2 | 3592562.5946 |  |  | COMPLETED | 1 | 2015-04-18 | 2015-04-18 | 070214S00119 | 14HI0025 | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2015-01-19 | VEN RAY CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region VII | Cebu | 303074 | Don Filomeno Torres MNHS | PILAR | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1182712.2061 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119645 | Esperanza ES | SAN FRANCISCO | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1030615.9023 |  |  | COMPLETED | 1 | 2015-03-12 | 2015-03-12 | 070214S00276 | 14HI0095B | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | JOHN ARNE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119228 | Estaca ES | COMPOSTELA | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1861149.1921 |  |  | COMPLETED | 1 | 2014-11-28 | 2014-11-28 | 070214S00131 | 14HI0031A | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-09-30 | NEOVENTURES CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119412 | Jubay ES | LILOAN | 5 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15245522.3438 |  |  | COMPLETED | 1 | 2015-10-21 | 2015-10-21 | 070214S00258 | 15HI0001 | 2015-01-22 | 2015-02-03 | 2015-02-04 | 2015-02-08 | 2015-02-24 | VEN RAY CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region VII | Cebu | 119655 | Lucio O. Arquillano Memorial School | SAN FRANCISCO | 5 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4492899.6094 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-05-25 | 070214S00248 | 15HI0003 | 2015-01-22 | 2015-02-03 | 2015-02-04 | 2015-02-08 | 2015-02-24 | JOHN ARNE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119229 | Lupa ES | COMPOSTELA | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1122712.2061 |  |  | COMPLETED | 1 | 2014-11-13 | 2014-11-13 | 070214S00111 | 14HI0033B | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-09-30 | NEOVENTURES CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119231 | Mulao ES | COMPOSTELA | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1911149.1921 |  |  | COMPLETED | 1 | 2014-11-25 | 2014-11-25 | 070214S00123 | 14HI0032A | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-09-30 | VEN RAY CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region VII | Cebu | 119415 | Mulao ES | LILOAN | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1090915.9023 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-04-11 | 070214S00270 | 14HI0090A | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | JOHN ARNE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119220 | Panalipan ES | CATMON | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1891149.1921 |  |  | COMPLETED | 1 | 2015-01-10 | 2015-01-10 | 070214S00117 | 14HI0038A | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-11-12 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
NC 2014 | K10 (2014) | Region VII | Cebu | 119232 | Panangban ES | COMPOSTELA | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1881149.1921 |  |  | COMPLETED | 1 | 2014-11-28 | 2014-11-28 | 070214S00124 | 14HI0034A | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-09-30 | JOHN ARNE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119649 | Paypay ES | San Francisco | 5 | 1 | 6 | 1STY5CL, 1STY1CL | 2014 K10 BATCH 2 | 5846000 |  |  | COMPLETED | 1 | 2015-03-13 | 2015-03-13 | 070214S00141 | 14HI0026 | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-09-30 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Cebu | 303081 | Puertobello NHS - Pob. Ext. | TUDELA | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1830672.8953 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 303080 | Puertobello NHS-Main | Tudela | 5 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119590 | Rizal ES | PORO | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 070214S00271 | 14HI0097C | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Cebu | 119651 | San Isidro ES | San Francisco | 5 | 1 | 5 | 1STY4CL, 1STY1CL | 2014 K10 BATCH 2 | 4876000 |  |  | COMPLETED | 1 | 2015-02-26 | 2015-02-26 | 070214S00132 | 14HI0027 | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-09-30 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Cebu | 119152 | SAN JOSE ES | BORBON | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1850772.8953 |  |  | COMPLETED | 1 | 2015-03-12 | 2015-03-12 | 070214S00265 | 14HI0091B | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
NC 2014 | K10 (2014) | Region VII | Cebu | 119653 | Sonog ES | SAN FRANCISCO | 5 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2745254.4624 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-04-11 | 070214S00277 | 14HI0094A | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Cebu | 119592 | Sta. Rita PS | PORO | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 070214S00272 | 14HI0097B | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Cebu | 119233 | Tag-ubi ES | COMPOSTELA | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1122712.2061 |  |  | COMPLETED | 1 | 2014-11-28 | 2014-11-28 | 070214S00125 | 14HI0034B | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-09-30 | JOHN ARNE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119203 | Taguini ES | CARMEN | 5 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2795504.4624 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-04-11 | 070214S00279 | 14HI0093B | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
NC 2014 | K10 (2014) | Region VII | Cebu | 187022 | Tamiao ES | COMPOSTELA | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1881149.1921 |  |  | COMPLETED | 1 | 2015-01-10 | 2015-01-10 | 070214S00126 | 14HI0035A | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-11-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Cebu | 119746 | Tangke PS | Sogod | 5 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2126000 |  |  | COMPLETED | 1 | 2014-11-13 | 2014-11-13 | 070214S00136 | 14HI0036 | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-09-30 | NEOVENTURES CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119421 | Tayud Elementary School | LILOAN | 5 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4B | 15121327.92 |  |  | COMPLETED | 1 | 2016-03-19 |  | 070214S00435 | 15HI0074 | 2015-08-11 | 2015-08-23 | 2015-08-24 | 2015-08-28 | 2015-09-01 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Cebu | 119593 | Teguis ES | PORO | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 070214S00273 | 14HI0097A | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Cebu | 312449 | Tulang Integrated School | SAN FRANCISCO | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1121065.9023 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 303009 | Zosimo E. Fabroa MNHS | PORO | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Cebu | 119234 | Bagong Lipunan Elementary School | CONSOLACION | 6 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8228453.2031 |  |  | COMPLETED | 1 | 2015-06-25 | 2015-06-25 | 070214S00220 | 15HN0007 | 2015-01-09 | 2015-01-12 | 2015-01-26 | 2015-02-05 | 2015-02-16 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Cebu | 119252 | Bangbang ES | CORDOBA | 6 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4342149.6094 |  |  | COMPLETED | 1 | 2015-05-06 | 2015-05-06 | 070214S00242 | 14HN0053 | 2014-12-02 | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-07 | SERCHER DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Cebu | 187025 | Catarman Elementary School | CORDOBA | 6 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4392399.6094 |  |  | COMPLETED | 1 | 2015-05-11 | 2015-05-11 | 070214S00257 | 14HN0057 | 2014-12-02 | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-12 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Cebu | 119238 | Consolacion Central ES | CONSOLACION | 6 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4B | 31252890.27 |  |  | COMPLETED | 1 | 2016-08-01 |  | 070214S00427 | 15HN0109 | 2015-09-02 | 2015-09-10 | 2015-09-22 | 2015-09-28 | 2015-10-07 | PLD CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119257 | Gabi ES | CORDOBA | 6 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4392399.6094 |  |  | COMPLETED | 1 | 2015-05-06 | 2015-05-04 | 070214S00243 | 14HN0054 | 2014-12-02 | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-07 | NASH BUILDERS & SUPPLIES
NC 2014 | K10 (2014) | Region VII | Cebu | 119258 | Gilutongan ES | CORDOBA | 6 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1142712.2061 |  |  | COMPLETED | 1 | 2014-12-21 | 2014-12-19 | 070214S00099 | 14HN0015 | 2014-08-13 | 2014-08-18 | 2014-09-01 | 2014-09-11 | 2014-09-22 | BANTAY CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119259 | Ibabao ES | CORDOBA | 6 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4342149.6094 |  |  | COMPLETED | 1 | 2015-05-06 | 2015-05-05 | 070214S00244 | 14HN0055 | 2014-12-02 | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-07 | GELA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119243 | Lanipga ES | CONSOLACION | 6 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2903213.9542 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-19 | 070214S00101 | 14HN0016 | 2014-08-13 | 2014-08-18 | 2014-09-01 | 2014-09-11 | 2014-09-22 | BANTAY CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 119260 | Pilipog ES | CORDOBA | 6 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6399164.7656 |  |  | COMPLETED | 1 | 2015-05-11 | 2015-05-11 | 070214S00245 | 14HN0056 | 2014-12-02 | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-12 | PLD CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Cebu | 302991 | Pulpogan NHS | CONSOLACION | 6 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8328953.2031 |  |  | COMPLETED | 1 | 2015-05-21 | 2015-05-21 | 070214S00247 | 14HN0058 | 2014-12-02 | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-12 | GONZALODO ENTERPRISES
NC 2014 | K10 (2014) | Region VII | Cebu | 119250 | Tugbongan ES | CONSOLACION | 6 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10877093.5547 |  |  | COMPLETED | 1 | 2015-11-22 | 2015-11-20 | 070214S00241 | 15HN0016 | 2015-01-27 | 2015-01-29 | 2015-02-09 | 2015-02-17 | 2015-02-26 | GEETY REALTY AND DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Cebu City | 119929 | Budla-an ES | CEBU CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4A | 6298664.7656 |  |  | COMPLETED | 1 | 2015-08-18 | 2015-08-18 | 070214S00407 | 14HH0122 | 2014-12-19 | 2014-12-05 | 2014-12-19 | 2014-12-29 | 2015-02-13 | GOWIL BUILDERS
NC 2014 | K10 (2014) | Region VII | Cebu City | 303143 | Bulacao NHS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4322049.6094 |  |  | reverted | 0
NC 2014 | K10 (2014) | Region VII | Cebu City | 119906 | Dr. Emilio Osmena ES | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | reverted | 0
NC 2014 | K10 (2014) | Region VII | Cebu City | 119880 | Guadalupe ES | CEBU CITY (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | reverted | 0
NC 2014 | K10 (2014) | Region VII | Cebu City | 119885 | Labangon Bliss ES | CEBU CITY (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | reverted | 0
NC 2014 | K10 (2014) | Region VII | Cebu City | 119882 | Mambaling ES | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | reverted | 0
NC 2014 | K10 (2014) | Region VII | Cebu City | 119890 | Toong ES | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | reverted | 0
NC 2014 | K10 (2014) | Region VII | City of Naga, Cebu | 325301 | Alpaco NHS | CITY OF NAGA | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | City of Naga, Cebu | 312433 | Lanas NHS | CITY OF NAGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1080865.9023 |  |  | COMPLETED | 1 | 2015-05-01 | 2015-05-01 | 070214S00418 | 14-HE-0098 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | FIRST BUILDERS AND DEVELOPERS
NC 2014 | K10 (2014) | Region VII | City of Naga, Cebu | 325307 | Lutac NHS | CITY OF NAGA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-13 | 2014-12-15 | 070214S00008 | 14-HE-0029 | 2014-06-24 | 2014-06-26 | 2014-07-08 | 2014-07-11 | 2014-07-18 | QM BUILDERS
NC 2014 | K10 (2014) | Region VII | City of Naga, Cebu | 312435 | Mainit NHS | CITY OF NAGA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1931172.8953 |  |  | COMPLETED | 1 | 2015-05-01 | 2015-04-24 | 070214S00417 | 14-HE-0101 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | QUIRANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | City of Naga, Cebu | 312436 | Mayana NHS | CITY OF NAGA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1951272.8953 |  |  | COMPLETED | 1 | 2015-05-01 | 2015-05-01 | 070214S00416 | 14-HE-0098 | 2014-11-11 | 2014-11-12 | 2014-12-25 | 2014-12-28 | 2014-12-03 | FIRST BUILDERS AND DEVELOPERS
NC 2014 | K10 (2014) | Region VII | City of Naga, Cebu | 119508 | Naalad ES | CITY OF NAGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050715.9023 |  |  | reverted | 0
NC 2014 | K10 (2014) | Region VII | City of Naga, Cebu | 119511 | Pangdan ES | CITY OF NAGA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1901022.8953 |  |  | COMPLETED | 1 | 2015-05-01 | 2015-05-01 | 070214S00419 | 14-HE-0098 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-11-28 | 2014-12-03 | FIRST BUILDERS AND DEVELOPERS
NC 2014 | K10 (2014) | Region VII | Danao City | 119351 | Bayabas ES | DANAO CITY | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2014-10-13 | 2014-10-13 | 070214S00019 | 14HI0015 | 2014-07-08 | 2014-07-20 | 2014-07-21 | 2014-07-30 | 2014-08-15 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
NC 2014 | K10 (2014) | Region VII | Danao City | 302957 | Beatriz D. Durano MNHS | DANAO CITY | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | reverted | 0 |  |  | 070214S00011
NC 2014 | K10 (2014) | Region VII | Danao City | 500394 | Bibiana Mercado Integrated School | DANAO CITY | 5 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2970174.43 |  |  | COMPLETED | 1 | 2014-11-12 | 2014-11-12 | 070214S00012 | 14HI0022 | 2014-07-08 | 2014-07-20 | 2014-07-21 | 2014-07-30 | 2014-08-15 | VEN RAY CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region VII | DANAO CITY | 119333 | Cabungahan ES | Danao | 5 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | DANAO CITY | 119335 | Cogon ES | Danao | 5 | 1 | 5 | 1STY5CL | 2014 K10 BATCH 3 | 4112918.6116 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Danao City | 119347 | Dungga ES | DANAO CITY | 5 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2880174.43 |  |  | COMPLETED | 1 | 2015-02-09 | 2015-02-09 | 070214S00009 | 14HI0047 | 2014-10-15 | 2014-10-27 | 2014-10-28 | 2014-11-01 | 2014-11-12 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
NC 2014 | K10 (2014) | Region VII | Danao City | 302959 | Elpidio H. Perez MNHS | DANAO CITY | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-12-26 | 2014-12-26 | 070214S00016 | 14HI0048 | 2014-10-15 | 2014-10-27 | 2014-10-28 | 2014-11-01 | 2014-11-12 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
NC 2014 | K10 (2014) | Region VII | DANAO CITY | 119361 | Eustaquio Capin ES | Danao | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 950215.9023 |  |  | COMPLETED | 1 | 2015-03-12 | 2015-03-12 | 070214S00255 | 14HI0091A | 2014-12-16 | 2014-12-28 | 2014-12-29 | 2015-01-02 | 2015-01-12 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
NC 2014 | K10 (2014) | Region VII | Danao City | 119363 | Gerardo Ypil ES | DANAO CITY | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-09-28 | 2014-09-28 | 070214S00010 | 14HI0016 | 2014-07-08 | 2014-07-20 | 2014-07-21 | 2014-07-30 | 2014-08-15 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
NC 2014 | K10 (2014) | Region VII | Danao City | 322002 | Guinsay National High School | DANAO CITY | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-09-28 | 2014-09-28 | 070214S00013 | 14HI0021 | 2014-07-08 | 2014-07-20 | 2014-07-21 | 2014-07-30 | 2014-08-15 | VEN RAY CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region VII | Danao City | 119365 | Langosig ES | DANAO CITY | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-09-28 | 2014-09-28 | 070214S00007 | 14HI0017 | 2014-07-08 | 2014-07-20 | 2014-07-21 | 2014-07-30 | 2014-08-15 | FIRST BUILDERS AND DEVELOPERS
NC 2014 | K10 (2014) | Region VII | DANAO CITY | 119338 | Lawaan ES | Danao | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1750272.8953 |  |  | COMPLETED | 1 | 2015-09-01 | 2015-09-01 | 070214S00251 | 14HI0092A | 2015-06-08 | 2015-06-20 | 2015-06-21 | 2015-06-25 | 2015-07-03 | VEN RAY CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region VII | DANAO CITY | 303036 | Lawaan NHS | Danao | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1750272.8953 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Danao City | 303036 | Lawaan NHS | DANAO CITY | 5 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2910174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Danao City | 303038 | Miguel C. Tiongko NHS | DANAO CITY | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2060417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Danao City | 302960 | Sandayong Sur NHS | DANAO CITY | 5 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2890174.43 |  |  | COMPLETED | 1 | 2014-11-12 | 2014-11-12 | 070214S00017 | 14HI0018 | 2014-07-08 | 2014-07-20 | 2014-07-21 | 2014-07-30 | 2014-08-15 | VEN RAY CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region VII | Danao City | 303038 | Nicolas U. Tiongko MNHS | DANAO CITY | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042712.2061 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Danao City | 119370 | Sibacan ES | DANAO CITY | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042712.2061 |  |  | COMPLETED | 1 | 2015-01-10 | 2015-01-10 | 070214S00094 | 14HI0035B | 2014-08-26 | 2014-09-07 | 2014-09-08 | 2014-09-12 | 2014-11-12 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119979 | Marigondon Elementary School | LAPU-LAPU CITY (OPON) | 0 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4A | 14045118.3984 |  |  | COMPLETED | 1 | 2015-09-08 | 2015-09-08 | 070214S00412 | 14HN0062 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-23 | 2015-01-12 | JJ &J CONSTRUCTION & GENERAL SUPPLY
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119984 | Sudtonggan ES | LAPU-LAPU CITY (OPON) | 0 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4A | 4291899.6094 |  |  | COMPLETED | 1 | 2015-05-11 | 2015-05-11 | 070214S00413 | 14HN0063 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-23 | 2015-01-12 | JJ &J CONSTRUCTION & GENERAL SUPPLY
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119963 | Bankal ES | LAPU-LAPU CITY (OPON) | 1 | 1 | 15 | 3STY15CL | 2014 K10 BATCH 4B | 21383013.45 |  |  | COMPLETED | 1 | 2016-07-02 |  | 070214S00430 | 15HN0110 | 2015-09-02 | 2015-09-10 | 2015-09-22 | 2015-09-28 | 2015-10-07 | JJ &J CONSTRUCTION & GENERAL SUPPLY
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119983 | Suba Masulog ES | LAPU-LAPU CITY (OPON) | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4B | 10417131.51 |  |  | COMPLETED | 1 | 2016-04-02 |  | 070214S00429 | 15HN0078 | 2015-07-07 | 2015-07-10 | 2015-07-23 | 2015-07-29 | 2015-08-07 | GONZALODO ENTERPRISES
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119985 | Babag l ES | Lapu-Lapu City | 6 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3335125.5846 |  |  | COMPLETED | 1 | 2015-04-26 | 2015-04-26 | 070214S00397 | 14HN0039 | 2014-11-27 | 2014-12-01 | 2014-12-12 | 2014-12-23 | 2015-01-07 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119986 | Babag ll ES | Lapu-Lapu City | 6 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1750272.8953 |  |  | COMPLETED | 1 | 2015-04-21 | 2015-04-21 | 070214S00399 | 14HN0030 | 2014-11-27 | 2014-12-01 | 2014-12-12 | 2014-12-23 | 2015-01-07 | GELA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 303173 | Babag NHS - Poblacion Night HS Ext. | LAPU-LAPU CITY (OPON) | 6 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-05-06 | 2015-05-06 | 070214S00394 | 14HN0052 |  | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-07 | GELA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 303174 | Bankal NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | reverted | 0
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 303175 | Bankal NHS - Abuno HS Ext. | LAPU-LAPU CITY (OPON) | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1147329.12 |  |  | reverted | 0
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119975 | Basak ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4342149.6094 |  |  | COMPLETED | 1 | 2015-05-06 | 2015-05-05 | 070214S00393 | 14HN0051 | 2014-12-02 | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-07 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119964 | Buaya Elementary School | LAPU-LAPU CITY (OPON) | 6 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15245522.3438 |  |  | COMPLETED | 1 | 2015-09-03 | 2015-09-03 | 070214S00398 | 14HN0048 | 2014-12-02 | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-07 | GONZALODO ENTERPRISES
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119987 | Canjulao ES | Lapu-Lapu City | 6 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 3 | 4294527.3578 |  |  | reverted | 0
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119990 | Looc ES | Lapu-Lapu City | 6 | 1 | 6 | 2UNITS 1STY3CL | 2014 K10 BATCH 3 | 5088508.9248 |  |  | reverted | 0
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119966 | Mactan Air Base ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6348914.7656 |  |  | COMPLETED | 1 | 2015-05-06 | 2015-05-06 | 070214S00396 | 14HN0049 | 2014-12-02 | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-07 | GONZALODO ENTERPRISES
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 303180 | Marigondon NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | reverted | 0
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 303181 | Marigondon NHS - Basak Night HS Ext. | LAPU-LAPU CITY (OPON) | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | reverted | 0
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119968 | Pajo ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-04-06 | 2015-04-06 | 070214S00392 | 14HN0050 | 2014-12-02 | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-07 | GONZALODO ENTERPRISES
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119956 | Poo ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1000465.9023 |  |  | COMPLETED | 1 | 2015-03-07 | 2015-03-06 | 070214S00304 | 14HN0032 | 2014-11-27 | 2014-12-01 | 2014-12-12 | 2014-12-23 | 2015-01-07 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119957 | Sabang ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4372299.6094 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-04-10 | 070214S00387 | 14HN0059 | 2014-12-02 | 2014-12-05 | 2014-12-17 | 2014-12-23 | 2015-01-12 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 303189 | Sta. Rosa NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | reverted | 0
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119982 | Subabasbas ES | Lapu-Lapu City | 6 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3335125.5846 |  |  | COMPLETED | 1 | 2015-05-26 | 2015-05-26 | 070214S00400 | 14HN0040 | 2014-11-27 | 2014-12-01 | 2014-12-12 | 2014-12-23 | 2015-01-07 | GELA CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119993 | Timpolok ES | Lapu-Lapu City | 6 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544254.4624 |  |  | reverted | 0
NC 2014 | K10 (2014) | Region VII | Lapu-Lapu City | 119962 | Tungasan ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1010515.9023 |  |  | COMPLETED | 1 | 2015-03-07 | 2015-03-06 | 070214S00391 | 14HN0031 | 2014-11-27 | 2014-12-01 | 2014-12-12 | 2014-12-23 | 2015-01-07 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2014 | K10 (2014) | Region VII | Mandaue City | 303195 | Canduman NHS | MANDAUE CITY | 6 | 1 | 6 | 3STY 6CL | 2014 K10 BATCH 1 | 8107000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Mandaue City | 120013 | Maguikay ES | MANDAUE CITY | 6 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-03 | 2015-12-29 | 070214S00428 | 15HN0079 | 2015-07-07 | 2015-07-10 | 2015-07-23 | 2015-07-29 | 2015-08-07 | P.B. OBIAL CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Mandaue City | 303199 | Mandaue City Comprehensive NHS | MANDAUE CITY | 6 | 1 | 9 | 3STY 9CL | 2014 K10 BATCH 1 | 12159000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | City of Naga, Cebu | 303065 | NAGA NATIONAL HIGH SCHOOL | NAGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042712.2061 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Tagbilaran City | 118704 | Cabawan ES | Tagbilaran City | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-09-30 | 070114S00377 | 15HA0008 | 2015-04-06 | 2015-03-23 | 2015-04-06 | 2015-05-27 | 2015-07-03 | HNR CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Tagbilaran City | 302846 | DCPNHS | Tagbilaran City | 1 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 3 | 11277984.375 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Tagbilaran City | 302875 | Mansasa National High School | TAGBILARAN CITY (Capital) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | [10 empty] | No Ceiling
NC 2014 | K10 (2014) | Region VII | Tagbilaran City | 302875 | Mansasa NHS | Tagbilaran City | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1001768.8144 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Tagbilaran City | 118712 | San Isidro ES | Tagbilaran City | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-09-30 | 070114S00378 | 15HA0008 | 2015-04-06 | 2015-03-23 | 2015-04-06 | 2015-05-27 | 2015-07-03 | HNR CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Tagbilaran City | 322102 | SAN ISIDRO NATIONAL HIGH SCHOOL | TAGBILARAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2016-04-18 |  | 070114S00470 | 15HA0084 | 2015-08-11 | 2015-07-30 | 2015-08-11 | 2015-08-19 | 2015-09-21 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region VII | Tagbilaran City | 118713 | Tagbilaran City Central Elementary School | TAGBILARAN CITY (Capital) | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2170417.57 |  |  | COMPLETED | 1 | 2015-02-07 | 2015-02-06 | 070114S00064 | 14HA0022 | 2014-09-09 | 2014-08-28 | 2014-09-09 | 2014-09-13 | 2014-10-30 | JB ROCK CONSTRUCTION SUPPLY | No Painting, No Ceiling, No Toilet Fixtures
NC 2014 | K10 (2014) | Region VII | Tagbilaran City | 118714 | Taloto ES | Tagbilaran City | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1 | 2015-10-28 | 2015-09-30 | 070114S00379 | 15HA0008 | 2015-04-06 | 2015-03-23 | 2015-04-06 | 2015-05-27 | 2015-07-03 | HNR CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Talisay City | 119785 | Borromeo Bros. ES | Talisay | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14045118.3984 |  |  | COMPLETED | 1 | 2016-01-06 |  | 070214S00373 | 14-HE-0125 | 2014-11-27 | 2014-12-01 | 2014-12-15 | 2014-12-18 | 2014-12-23 | GENETIAN BUILDERS
NC 2014 | K10 (2014) | Region VII | Talisay City | 119794 | Bulacao ES | Talisay | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14045118.3984 |  |  | COMPLETED | 1 | 2016-01-21 |  | 070214S00385 | 14-HE-0124 | 2014-11-27 | 2014-12-01 | 2014-12-15 | 2014-12-18 | 2014-12-23 | JEGMA CONSTRUCTION & DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Talisay City | 119797 | Candulawan ES | CITY OF TALISAY | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4317024.6094 |  |  | COMPLETED | 1 | 2015-06-06 | 2015-06-05 | 070214S00371 | 14-HE-0105 | 2014-11-18 | 2014-12-20 | 2014-12-02 | 2014-12-05 | 2014-12-09 | GOLDFIN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Talisay City | 302971 | Cansojong NHS | CITY OF TALISAY | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6328814.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Talisay City | 303019 | Jaclupan NHS | CITY OF TALISAY | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6338864.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Talisay City | 119800 | Lagtang ES | Talisay | 1 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 3 | 11277984.375 |  |  | COMPLETED | 1 | 2015-09-04 | 2015-09-02 | 070214S00384 | 14-HE-0115 | 2014-11-18 | 2014-12-20 | 2014-12-02 | 2014-12-05 | 2014-12-09 | QUIRANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Talisay City | 322209 | Lawaan III National High School (Night) | CITY OF TALISAY | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10917293.5547 |  |  | COMPLETED | 1 | 2015-12-17 | 2015-12-15 | 070214S00383 | 14-HE-0123 | 2014-11-27 | 2014-12-01 | 2014-12-15 | 2014-12-18 | 2014-12-23 | QUIRANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Talisay City | 233501 | Linao ES | CITY OF TALISAY | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4306974.6094 |  |  | COMPLETED | 1 | 2015-06-06 | 2015-06-05 | 070214S00372 | 14-HE-0110 | 2014-11-18 | 2014-12-20 | 2014-12-02 | 2014-12-05 | 2014-12-09 | QUIRANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Talisay City | 119788 | Maghaway ES | CITY OF TALISAY | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6318764.7656 |  |  | COMPLETED | 1 | 2015-05-22 | 2015-05-21 | 070214S00378 | 14-HE-0113 | 2014-11-18 | 2014-11-20 | 2014-12-02 | 2014-12-05 | 2014-12-09 | RAMIJO CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Talisay City | 322201 | Maghaway NHS | Talisay | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1788214.5699 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Talisay City | 119790 | San Roque ES | Talisay | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14045118.3984 |  |  | COMPLETED | 1 | 2016-01-06 |  | 070214S00390 | 14-HE-0126 | 2014-11-27 | 2014-12-01 | 2014-12-15 | 2014-12-18 | 2014-12-23 | QUIRANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Talisay City | 119803 | Tabunok CES | Talisay | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14045118.3984 |  |  | COMPLETED | 1 | 2016-01-06 |  | 070214S00375 | 14-HE-0127 | 2014-11-27 | 2014-12-01 | 2014-12-15 | 2014-12-18 | 2014-12-23 | GOLDFIN CONSTRUCTION
NC 2014 | K10 (2014) | Region VII | Talisay City | 119791 | Talisay City Central ES | CITY OF TALISAY | 1 | 1 | 12 | 3STY12CL | 2014 K10 BATCH 4A | 18729509.7656 |  |  | COMPLETED | 1 | 2016-01-21 |  | 070214S00406 | 14-HE-0129 | 2014-11-27 | 2014-12-01 | 2014-12-15 | 2014-12-18 | 2014-12-23 | JEGMA CONSTRUCTION & DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VII | Toledo City | 120713 | Biga ES | Toledo City | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1042049.6543 |  |  | COMPLETED | 1 | 2015-12-06 | 2015-12-05 | 070214S00425 | 15HF0079 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-09-25 | 2015-10-01 | BLIMEX CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Toledo City | 120743 | Bulongan ES | Toledo City | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4442649.6094 |  |  | COMPLETED | 1 | 2015-05-11 | 2015-05-11 | 070214S00376 | 14HF0126 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-05 | DINAH JANE CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Toledo City | 303317 | Bunga National High School | Toledo City | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1861149.1921 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-17 | 070214S00092 | 14HF0027 | 2014-07-16 | 2014-07-28 | 2014-07-29 | 2014-09-08 | 2014-09-12 | BLIMEX CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VII | Toledo City | 120726 | Canlumampao ES | Toledo City | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2453690.4049 |  |  | COMPLETED | 1 | 2015-04-21 | 2015-04-21 | 070214S00381 | 14HF0134 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-22 | 2015-01-15 | By Administration
NC 2014 | K10 (2014) | Region VII | Toledo City | 120727 | Captain Claudio ES | Toledo City | 3 | 1 | 6 | 2UNITS 1STY3CL | 2014 K10 BATCH 3 | 5088508.9248 |  |  | reverted | 0
NC 2014 | K10 (2014) | Region VII | Toledo City | 120728 | Carmen ES | Toledo City | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-03-22 | 2015-01-09 | 070214S00058 | 14HF0025 | 2014-07-10 | 2014-07-21 | 2014-07-22 | 2014-12-11 | 2014-12-16 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2014 | K10 (2014) | Region VII | Toledo City | 120732 | Mainggit ES | Toledo City | 3 | 1 | 4 | 2STY 4CL | 2014 K10 BATCH 1 | 5243164.26 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Toledo City | 120732 | Mainggit ES | Toledo City | 3 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3335125.5846 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VII | Toledo City | 120734 | Matab-ang ES | Toledo City | 3 | 1 | 12 | 4UNITS 1STY3CL | 2014 K10 BATCH 3 | 7632763.3872 |  |  | Reverted | 0
NC 2014 | K10 (2014) | Region VII | Toledo City | 303313 | Matab-ang NHS | Toledo City | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4A | 6298664.7656 |  |  | COMPLETED | 1 | 2015-05-18 | 2015-05-18 | 070214S00411 | 14HF0140 | 2014-12-11 | 2014-12-12 | 2014-12-23 | 2015-01-07 | 2015-01-12 | DINAH JANE CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VII | Toledo City | 120737 | Old Bucao ES | Toledo City | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2234658.24 |  |  | COMPLETED | 1 | 2015-03-22 | 2015-03-14 | 070214S00420 | 14HF0025 | 2014-07-10 | 2014-07-21 | 2014-07-22 | 2014-12-11 | 2014-12-16 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2014 | K10 (2014) | Region VII | Toledo City | 120756 | Sam-ang ES | Toledo City | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-03-22 | 2015-02-25 | 070214S00050 | 14HF0025 | 2014-07-10 | 2014-07-21 | 2014-07-22 | 2014-12-11 | 2014-12-16 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2014 | K10 (2014) | Region VII | Toledo City | 120740 | Talavera ES | Toledo City | 3 | 1 | 6 | 2UNITS 1STY3CL | 2014 K10 BATCH 3 | 5088508.9248 |  |  | Reverted | 0
NC 2014 | K10 (2014) | Region VII | Toledo City | 190503 | Dumlog ES | Toledo City | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042712.2061 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-17 | 070214S00093 | 14HF0027 | 2014-07-16 | 2014-07-28 | 2014-07-29 | 2014-09-08 | 2014-09-12 | BLIMEX CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VII | Bais City | 303212 | Bais City National High School | BAIS CITY | 2 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Bais City | 303212 | Bais City National High School | BAIS CITY | 2 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bais City | 303216 | Bais City Science NHS | BAIS CITY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070315S00161 | 0703-15-S-00161 | 2015-09-15 | 2015-09-21 | 2015-09-25 | 2015-10-08 | 2015-10-19 | PHILSOUTH BUILDERS (FORMERLY: LOTIFF CONSTRUCTION)
NC 2015 | K10 (2015) | Region VII | Bais City | 120076 | Dansulan ES | BAIS CITY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2188606.04 |  |  | COMPLETED | 1 |  |  | 070315S00205 | 0703-15-S-00205 | 2015-11-06 | 2015-11-20 | 2015-11-23 | 2015-12-03 | 2015-12-11 | SILLIMAN AVENUE CONST & SUPPLY (FORMERLY OVERDRIVE
NC 2015 | SHS (2015) | Region VII | Bais City | 303215 | Lonoy National High School | BAIS CITY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10767131.51 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bais City | 323007 | Mansangaban National HS | BAIS CITY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 11167131.51 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bais City | 323008 | Okiot National High School | BAIS CITY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00035 | 15HK0068 | 2015-10-16 | 2015-11-11 | 2015-11-18 | 2015-12-03 | 2015-12-11 | GIMP VENTURES
NC 2015 | K10 (2015) | Region VII | Bais City | 323006 | Sto. Thomas National High School | BAIS CITY | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070315S00164 | 15HK0089 | 2015-08-18 | 2015-08-31 | 2015-09-04 | 2015-09-11 | 2015-09-18 | R.R. GADINGAN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bayawan City | 321911 | Abundio Agarpao, Sr. MHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00036 | 15HL0050 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | C.S. RAYOS CONSTRUCTION & GENERAL SERICES, INC.
NC 2015 | SHS (2015) | Region VII | Bayawan City | 321908 | Antonio M. Lacson, Sr. MHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00037 | 15HL0050 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | C.S. RAYOS CONSTRUCTION & GENERAL SERICES, INC.
NC 2015 | SHS (2015) | Region VII | Bayawan City | 321907 | Atilano B. Cabangal MHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070315S00038 | 15HL0050 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | C.S. RAYOS CONSTRUCTION & GENERAL SERICES, INC.
NC 2015 | SHS (2015) | Region VII | Bayawan City | 321901 | Banaybanay NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00039 | 15HL0052 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | C.S. RAYOS CONSTRUCTION & GENERAL SERICES, INC.
NC 2015 | SHS (2015) | Region VII | Bayawan City | 303217 | Basay NHS | BASAY | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14952518.84 |  |  | COMPLETED | 1 |  |  | 070315S00146 | 15HL0072 | 2015-12-16 | 2015-12-17 | 2015-12-24
NC 2015 | SHS (2015) | Region VII | Bayawan City | 321902 | Bayawan City Science HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070315S00040 | 15HL0051 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | C.S. RAYOS CONSTRUCTION & GENERAL SERICES, INC.
NC 2015 | TECHVOC (2015) | Region VII | Bayawan City | 303221 | Bayawan National High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bayawan City | 303221 | Bayawan NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Bayawan City | 120125 | Bugay ES | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6219337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00204 | 15HL0093 | 2015-10-07 | 2015-10-08 | 2015-10-20 | 2015-11-04 | 2015-11-11 | JOSHUA ENGINEERING
NC 2015 | SHS (2015) | Region VII | Bayawan City | 303238 | Bugay NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00028 | 15HL0051 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | C.S. RAYOS CONSTRUCTION & GENERAL SERICES, INC.
NC 2015 | K10 (2015) | Region VII | Bayawan City | 120126 | Cadal-ugan E/S | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6209337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00220 | 15HL0094 | 2015-10-07 | 2015-10-08 | 2015-10-20 | 2015-11-04 | 2015-11-11 | JOSHUA ENGINEERING
NC 2015 | K10 (2015) | Region VII | Bayawan City | 120147 | Cansig-id PS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6189337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00208 | 15HL0096 | 2015-10-07 | 2015-10-08 | 2015-10-20 | 2015-11-04 | 2015-11-11 | 8G CONSTRUCTION AND GENERAL SERVICES
NC 2015 | SHS (2015) | Region VII | Bayawan City | 321912 | Cansumalig High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00027 | 15HL0055 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | PINS CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bayawan City | 303227 | Dawis NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00049 | 15HL0053 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | PINS CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bayawan City | 303239 | Kalamtukan NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bayawan City | 303237 | Kalumboyan NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8239965.051 |  |  | COMPLETED | 1 |  |  | 070315S00034 | 15HL0052 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | C.S. RAYOS CONSTRUCTION & GENERAL SERICES, INC.
NC 2015 | SHS (2015) | Region VII | Bayawan City | 321905 | Lapay High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00057 | 15HL0054 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | PINS CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bayawan City | 321909 | Malabugas HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bayawan City | 303240 | Manduaw NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00055 | 15HL0056 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | ADROIT CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Bayawan City | 120134 | Matunoy ES | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6264337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00219 | 15HL0095 | 2015-10-07 | 2015-10-08 | 2015-10-20 | 2015-11-04 | 2015-11-11 | JOSHUA ENGINEERING
NC 2015 | SHS (2015) | Region VII | Bayawan City | 321903 | Minaba HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00054 | 15HL0054 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | PINS CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bayawan City | 303254 | Narra HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00009 | 15HL0055 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | PINS CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bayawan City | 303256 | Omod National High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8222965.051 |  |  | COMPLETED | 1 |  |  | 070315S00053 | 15HL0055 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | PINS CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bayawan City | 321910 | Pagatban HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00026 | 15HL0054 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | PINS CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bayawan City | 321906 | San Jose HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00052 | 15HL0056 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | ADROIT CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bayawan City | 303241 | Tabuan PCHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00042 | 15HL0053 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | PINS CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bayawan City | 303242 | Tayawan NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00050 | 15HL0054 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | PINS CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Bayawan City | 120168 | Villasol ES | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00217 | 15HL0097 | 2015-10-07 | 2015-10-08 | 2015-10-20 | 2015-11-04 | 2015-11-11 | CTG CONSTRUCTION & ENTERPRISES
NC 2015 | SHS (2015) | Region VII | Bayawan City | 321904 | Villasol HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Dumaguete City | 119936 | Candau-ay ES | DUMAGUETE CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070315S00166 | 15HK0079 | 2015-08-07 | 2015-08-21 | 2015-08-25 | 2015-08-28 | 2015-09-08 | VESA ENGINEERING & CONST(FOR DELETION)
NC 2015 | SHS (2015) | Region VII | Dumaguete City | 303168 | Dumaguete City HS | DUMAGUETE CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070315S00015 | 15HK0044 | 2015-07-14 | 2015-08-12 | 2015-08-14 | 2015-08-20 | 2015-08-28 | PHILSOUTH BUILDERS (FORMERLY: LOTIFF CONSTRUCTION)
NC 2015 | SHS (2015) | Region VII | Dumaguete City | 303169 | RTPM - Dumaguete Science HS | DUMAGUETE CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070315S00008 | 15HK0045 | 2015-08-10 | 2015-08-13 | 2015-08-14 | 2015-08-21 | 2015-08-28 | C. LARA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Dumaguete City | 303171 | Taclobo NHS | DUMAGUETE CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070315S00024 | 15HK0046 | 2015-07-14 | 2015-08-19 | 2015-08-25 | 2015-08-28 | 2015-09-11 | MONTPHIL CONSTRUCTION CORPORATION
NC 2015 | K10 (2015) | Region VII | Guihulngan City | 120234 | Basak ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2048606.04 |  |  | COMPLETED | 1 |  |  | 070315S00214 | 070315S00214 | 2015-11-23
NC 2015 | K10 (2015) | Region VII | Guihulngan City | 120239 | Busay Elementary School | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2118606.04 |  |  | REVERTED | 0 |  |  | 070315S00228 | 070315S00228 | 2015-11-23
NC 2015 | K10 (2015) | Region VII | Guihulngan City | 120266 | Dadiangao PS | CITY OF GUIHULNGAN | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6519337.6381 |  |  | REVERTED | 0 |  |  | 070315S00212 | 070315S00212 | 2015-11-16
NC 2015 | SHS (2015) | Region VII | Guihulngan City | 303230 | GUIHULNGAN NATIONAL AGRICULTURAL SCHOOL | CITY OF GUIHULNGAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6719337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00051 | 070315S00051 | 2015-06-26 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-09-06 | ST. RAYMUND CONSTRUCTION, INC. | see 2021 completion UPDATE THE CONTRACTOR TO CMPLETE THE PROJECT ON TIME
NC 2015 | K10 (2015) | Region VII | Guihulngan City | 324803 | Guihulngan National High School - Buenavista Extension | CITY OF GUIHULNGAN | 1 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 070315S00183 | 070315S00183 | 2015-09-30 | 2015-10-15 | 2015-10-20 | 2015-11-05 | 2015-11-23 | MAI CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VII | Guihulngan City | 312952 | Guihulngan National High School-Poblacion (Linantuyan Annex) | CITY OF GUIHULNGAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00043 | 070315S00043 | 2015-06-26 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-09-06 | ST. RAYMUND CONSTRUCTION, INC.
NC 2015 | SHS (2015) | Region VII | Guihulngan City | 303233 | Guihulngan NHS - Hilaitan | CITY OF GUIHULNGAN | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14967518.84 |  |  | REVERTED | 0 |  |  | 070315S00160
NC 2015 | K10 (2015) | Region VII | Guihulngan City | 324802 | Guihulngan NHS - P. Zamora Extension | CITY OF GUIHULNGAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070315S00184 | 070315S00184 | 2015-09-30 | 2015-10-29
NC 2015 | SHS (2015) | Region VII | Guihulngan City | 303231 | Guihulngan NHS - Poblacion | CITY OF GUIHULNGAN | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 070315S00044 | 070315S00044 | 2015-06-15 | 2015-08-18 | 2015-08-25 | 2015-09-17 | 2015-09-28 | MAI CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VII | Guihulngan City | 303232 | Guihulngan NHS - Sandayao Annex | CITY OF GUIHULNGAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6619337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00047 | 070315S00047 | 2015-07-20 | 2015-10-27 | 2015-11-03 | 2015-11-20 | 2015-12-01 | SILLIMAN AVENUE CONST & SUPPLY (FORMERLY OVERDRIVE | Slow progress
NC 2015 | SHS (2015) | Region VII | Guihulngan City | 312910 | Guihulngan NHS, Hilaitan - Trinidad Annex | CITY OF GUIHULNGAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 |  |  | 070315S00048 | 070315S00048 | 2015-07-20 | 2015-08-11 | 2015-08-18 | 2015-09-15 | 2015-09-28 | 8G CONSTRUCTION AND GENERAL SERVICES
NC 2015 | K10 (2015) | Region VII | Guihulngan City | 120268 | Hinakpan Elementary School | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | REVERTED | 0 |  |  | 070315S00209 | 070315S00209 | 2015-11-23
NC 2015 | K10 (2015) | Region VII | Guihulngan City | 120259 | Jacinto Baquilta ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2388606.04 |  |  | REVERTED | 0 |  |  | 070315S00215 | 070315S00215 | 2015-11-23
NC 2015 | K10 (2015) | Region VII | Guihulngan City | 120271 | Kapudlusan PS | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | REVERTED | 0 |  |  | 070315S00227 | 070315S00227 | 2015-11-23
NC 2015 | K10 (2015) | Region VII | Guihulngan City | 120249 | Laos ES | CITY OF GUIHULNGAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | REVERTED | 0 |  |  | 070315S00185 | 070315S00185 | 2015-09-30 | 2015-10-29 | 2015-12-08
NC 2015 | K10 (2015) | Region VII | Guihulngan City | 120277 | Mckinley ES | CITY OF GUIHULNGAN | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00213 | 070315S00213 | 2015-11-16 | 2015-12-08 | 2015-12-15
NC 2015 | K10 (2015) | Region VII | Guihulngan City | 120282 | Planas ES | CITY OF GUIHULNGAN | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070315S00210 | 070315S00210 | 2015-11-16
NC 2015 | K10 (2015) | Region VII | Guihulngan City | 120283 | Taloto ES | CITY OF GUIHULNGAN | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6299337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00216 | 070315S00216 | 2015-11-23 | 2015-12-08 | 2015-12-15
NC 2015 | K10 (2015) | Region VII | Guihulngan City | 120258 | Trinidad ES | CITY OF GUIHULNGAN | 1 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 6 | 15121327.92 |  |  | REVERTED | 0 |  |  | 070315S00211 | 070315S00211
NC 2015 | SHS (2015) | Region VII | Bayawan City | 303218 | Actin NHS | BASAY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8269965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bayawan City | 303219 | Bal-os National High School | BASAY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8269965.051 |  |  | COMPLETED | 1 |  |  | 070315S00119 | 15HL0028 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-27 | 2015-07-07 | VESA ENGINEERING AND CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bayawan City | 303220 | Maglinao NHS | BASAY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8289965.051 |  |  | COMPLETED | 1 |  |  | 070315S00133 | 15HL0029 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-27 | 2015-07-07 | VESA ENGINEERING AND CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Tanjay City | 312926 | Apolinario Gerarda Arnaiz HS | PAMPLONA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00144 | 15HK0041 | 2015-07-14 | 2015-08-10 | 2015-09-04 | 2015-09-11 | 2015-09-18 | R.E. SINGSON CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | TANJAY CITY | 120410 | Calicanan ES | PAMPLONA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6289337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00190 | 0703-15-S-00190 | 2015-10-04 | 2015-10-16 | 2015-10-21 | 2015-11-04 | 2015-11-11 | SILLIMAN AVENUE CONST & SUPPLY (FORMERLY OVERDRIVE
NC 2015 | K10 (2015) | Region VII | Tanjay City | 120547 | Cangkue Elementary School | CITY OF TANJAY | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070315S00167 | 15HK0081 | 2015-08-18 | 2015-08-31 | 2015-09-04 | 2015-09-11 | 2015-09-18 | RICHFIELD BUILDERS
NC 2015 | K10 (2015) | Region VII | Tanjay City | 120550 | Doña Loreto Ledesma Mapa (Nagsala ES) | CITY OF TANJAY | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070315S00168 | 15HK0093 | 2015-08-04 | 2015-08-25 | 2015-08-27 | 2015-09-03 | 2015-09-14 | TSD BUILDERS CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VII | Tanjay City | 312911 | Hunop HS | PAMPLONA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6424337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Tanjay City | 312915 | Inawasan PCHS | PAMPLONA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00137 | 15HK0041 | 2015-08-06 | 2015-09-01 | 2015-09-04 | 2015-09-11 | 2015-09-18 | R.E. SINGSON CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Tanjay City | 303274 | Isidoro Salma MHS (Balayong ) | PAMPLONA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Tanjay City | 234008 | Julian Calibo Memorial School | CITY OF TANJAY | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4672048.49 |  |  | COMPLETED | 1 |  |  | 070315S00199 | 0703-15-S-00199 | 2015-09-29 | 2015-10-12 | 2015-10-21 | 2015-11-04 | 2015-11-11 | SILLIMAN AVENUE CONST & SUPPLY (FORMERLY OVERDRIVE
NC 2015 | SHS (2015) | Region VII | Tanjay City | 303284 | Lourdes L. del Prado MNHS | CITY OF TANJAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Tanjay City | 303285 | Lourdes L. del Prado MNHS ( Bahian) | CITY OF TANJAY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6719337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00013 | 15HK0065 | 2015-07-14 | 2015-08-10 | 2015-08-11 | 2015-08-20 | 2015-08-28 | 8G CONSTRUCTION AND GENERAL SERVICES
NC 2015 | SHS (2015) | Region VII | Tanjay City | 303287 | Lourdes L. del Prado MNHS (Pal-ew) | CITY OF TANJAY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10817131.51 |  |  | COMPLETED | 1 |  |  | 070315S00152 | 0703-15-S-00152 | 2015-09-22 | 2015-10-13 | 2015-10-21 | 2015-11-03 | 2015-11-11 | 8G CONSTRUCTION AND GENERAL SERVICES
NC 2015 | SHS (2015) | Region VII | Tanjay City | 303288 | Lourdes L. del Prado MNHS (Sto. Ni¤o) | CITY OF TANJAY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6669337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00012 | 15HK006 | 2015-07-14 | 2015-08-10 | 2015-08-11 | 2015-08-20 | 2015-08-28 | 8G CONSTRUCTION AND GENERAL SERVICES
NC 2015 | SHS (2015) | Region VII | Tanjay City | 303286 | Novallas High School | CITY OF TANJAY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10487131.51 |  |  | REVERTED | 0 |  |  | 070315S00010 | 0703-15-S-00010
NC 2015 | SHS (2015) | Region VII | Tanjay City | 303259 | Pamplona NHS | PAMPLONA | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14957518.84 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Tanjay City | 303273 | Sta. Agueda NHS | PAMPLONA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8269965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Tanjay City | 312905 | Sta. Agueda NHS - Calicanan HS Ext. | PAMPLONA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8354965.051 |  |  | COMPLETED | 1 |  |  | 070315S00142 | 15HK0050 | 2015-07-14 | 2015-08-10 | 2015-08-14 | 2015-08-21 | 2015-08-28 | RICHFIELD BUILDERS
NC 2015 | SHS (2015) | Region VII | Tanjay City | 303279 | Tanjay Legislated HS | CITY OF TANJAY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00002 | 15HK0067 | 2015-07-14 | 2015-08-10 | 2015-08-12 | 2015-08-20 | 2015-08-28 | RICHFIELD BUILDERS
NC 2015 | SHS (2015) | Region VII | Tanjay City | 303280 | Tanjay NHS (Opao) | CITY OF TANJAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070315S00003 | 15HK0049 | 2015-07-14 | 2015-08-10 | 2015-08-12 | 2015-08-20 | 2015-08-28 | L.C. CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Tanjay City | 303283 | Tanjay Science HS | CITY OF TANJAY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070315S00004 | 0703-15-S-00004 | 2015-08-26 | 2015-09-11 | 2015-09-24 | 2015-10-07 | 2015-10-19 | VESA ENGINEERING AND CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | BOGO CITY | 302930 | Banban National High School | CITY OF BOGO | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | BOGO CITY | 302931 | Binabag NHS | CITY OF BOGO | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00121 | 15HD0032 | 2015-07-14 | 2015-07-27 | 2015-07-28 | 2015-08-05 | 2015-08-12 | R.U. AQUINO CONSTRUCTION AND DEVELOPMENT CORP. (FO
NC 2015 | SHS (2015) | Region VII | BOGO CITY | 302932 | Cayang National High School | CITY OF BOGO | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00122 | 15HD0033 | 2015-06-22 | 2015-07-02 | 2015-07-03 | 2015-08-05 | 2015-08-12 | GOLDFIN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bogo City | 325001 | City of Bogo Science and Arts Academy | CITY OF BOGO | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8504965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Bogo City | 187009 | Don Celestino Martinez MNHS | CITY OF BOGO | 4 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10267131.51 |  |  | COMPLETED | 1 |  |  | 070215S00506 | 15HD0096 | 2015-10-14 | 2015-10-27 | 2015-10-27 | 2015-11-03 | 2015-11-10 | BANTAY CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | BOGO CITY | 302933 | Don Potenciano Catarata MNHS | CITY OF BOGO | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00100 | 15HD0033 | 2015-06-22 | 2015-07-02 | 2015-07-03 | 2015-08-05 | 2015-08-12 | GOLDFIN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bogo City | 302934 | Jovencio N. Masong NHS | CITY OF BOGO | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8524965.051 |  |  | COMPLETED | 1 |  |  | 070215S00117 | 15HD0035 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-08-05 | 2015-08-12 | GOLDFIN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bogo City | 302935 | La Paz NHS | CITY OF BOGO | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00115 | 15HD0036 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-08-05 | 2015-08-12 | GOLDFIN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bogo City | 302936 | Libertad NHS | CITY OF BOGO | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | BOGO CITY | 302937 | Odlot National High School | CITY OF BOGO | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00093 | 15HD0033 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-08-05 | 2015-08-12 | GOLDFIN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bohol | 302811 | Baclayon National High School | BACLAYON | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10517131.51 |  |  | Reverted | 0 |  |  | 070115S00149 | 15HA00-18 | 2015-09-30
NC 2015 | SHS (2015) | Region VII | Bohol | 302907 | Bantolinao National High School | ANTEQUERA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302817 | Biking Tech-Voc HS | DAUIS | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Bohol | 118494 | Bugho PS | LOON | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00215 | 15HA0148 | 2015-10-19 | 2015-10-07 | 2015-10-19 | 2015-10-23 | 2015-11-27 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | K10 (2015) | Region VII | Bohol | 118777 | Bunacan ES | TUBIGON | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070115S00154 | 15HA0120 | 2015-09-11 | 2015-09-01 | 2015-09-11 | 2015-09-17 | 2015-09-21 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | Region VII | Bohol | 302819 | Busao National High School | MARIBOJOC | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2690828.124 |  |  | COMPLETED | 1 |  |  | 070115S00063 | 15HA0088 | 2015-08-17 | 2015-08-05 | 2015-08-17 | 2015-08-21 | 2015-10-05 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2015 | SHS (2015) | Region VII | Bohol | 302820 | Cabilao NHS | LOON | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6429337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00064 | 15HA0125 | 2015-10-02 | 2015-09-21 | 2015-10-02 | 2015-10-09 |  | DT&C CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bohol | 302883 | Calape NHS | CALAPE | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070115S00065 | 15HA0133 | 2015-10-09 | 2015-09-28 | 2015-10-09 | 2015-10-15 | 2015-11-09 | BNYU ENTERPRISES & CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Bohol | 118201 | Canapnapan PS | CORELLA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00214 | 15HA0123 | 2015-10-23 | 2015-10-12 | 2015-10-23 | 2015-10-29
NC 2015 | K10 (2015) | Region VII | Bohol | 312306 | Canlaas High School | ANTEQUERA | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070115S00167 | 15HA0141 | 2015-10-16 | 2015-10-05 | 2015-10-16 | 2015-10-22 | 2015-11-18 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2015 | SHS (2015) | Region VII | Bohol | 302833 | Catigbian NHS | CATIGBIAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8304965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302835 | Cawayanan NHS | TUBIGON | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00075 | 15HA0093 | 2015-08-21 | 2015-08-10 | 2015-08-21 | 2015-08-28 | 2015-09-21 | DT&C CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Bohol | 118498 | Cogon Norte ES | LOON | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070115S00153 | 15HA0144 | 2015-10-16 | 2015-10-05 | 2015-10-16 | 2015-10-22 | 2015-11-18 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2015 | SHS (2015) | Region VII | Bohol | 302838 | Cong. Pablo Malasarte NHS | BALILIHAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 070115S00148 | 15HA0140 | 2015-10-12 | 2015-09-29 | 2015-10-12 | 2015-10-16 | 2015-11-03 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2015 | SHS (2015) | Region VII | Bohol | 302839 | Corella NHS | CORELLA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070115S00067 | 15HA0097 | 2015-08-25 | 2015-08-24 | 2015-08-25 | 2015-08-29 | 2015-09-21 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2015 | K10 (2015) | Region VII | Bohol | 117975 | Danao PS | ANTEQUERA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00213 | 15HA0147 | 2015-10-19 | 2015-10-07 | 2015-10-19 | 2015-10-23 | 2015-11-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | Region VII | Bohol | 312304 | Dauis NHS | DAUIS | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00060 | 15HA0124 | 2015-10-02 | 2015-09-21 | 2015-10-02 | 2015-10-09 | 2015-11-26 | HNR CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region VII | Bohol | 118539 | Dipatlong PS | MARIBOJOC | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00216 | 15HA0153 | 2015-10-23 | 2015-10-12 | 2015-10-23 | 2015-10-29 | 2015-12-03 | A.A. DE VERA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bohol | 302850 | Fatima NHS | CORTES | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2710828.124 |  |  | COMPLETED | 1 |  |  | 070115S00069 | 15HA0088 | 2015-08-17 | 2015-08-05 | 2015-08-17 | 2015-08-21 | 2015-10-05 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2015 | SHS (2015) | Region VII | Bohol | 302853 | Gov. Jacinto Borja National High School | LOON | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00070 | 15HA0122 | 2015-10-02 | 2015-09-21 | 2015-10-02 | 2015-10-09 | 2015-11-09 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | K10 (2015) | Region VII | Bohol | 118540 | Guiwanon PS | MARIBOJOC | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00217 | 15HA0154 | 2015-10-23 | 2015-10-12 | 2015-10-23 | 2015-10-30 | 2015-12-18 | GCMG CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bohol | 312320 | Haguilanan High School | CATIGBIAN | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2680828.124 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302856 | Hanopol NHS | BALILIHAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00072 | 15HA0089 | 2015-08-17 | 2015-08-05 | 2015-08-17 | 2015-08-21 | 2015-09-21 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2015 | SHS (2015) | Region VII | Bohol | 302871 | Loon South National HS | LOON | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302872 | Lourdes NHS | PANGLAO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Bohol | 302872 | Lourdes NHS | PANGLAO | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2529549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302877 | Mantacida NHS | CATIGBIAN | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2720828.124 |  |  | COMPLETED | 1 |  |  | 070115S00068 | 15HA0087 | 2015-08-17 | 2015-08-05 | 2015-08-17 | 2015-08-21 | 2015-09-21 | HNR CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VII | Bohol | 302824 | Mayor A. R. Tuazon Nat'l Sch. of Fisheries | CALAPE | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00066 | 15HA0094 | 2015-08-25 | 2015-08-14 | 2015-08-25 | 2015-09-02 | 2015-09-21 | GAIL CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region VII | Bohol | 118789 | Mocaboc PS | TUBIGON | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | Reverted | 0 |  |  | 070115S00218 | 15HA0127
NC 2015 | SHS (2015) | Region VII | Bohol | 302881 | Pagnito-an NHS | MARIBOJOC | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10467131.51 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | BOHOL | 312317 | Pamilacan HS | BACLAYON | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00057 | 15HA0132 | 2015-10-09 | 2015-09-28 | 2015-10-09 | 2015-10-15 | 2015-11-03 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2015 | SHS (2015) | Region VII | Bohol | 302882 | Pangangan NHS Main | CALAPE | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6409337.6381 |  |  | Reverted | 0 |  |  | 070115S00056 | 15HA0095 | 2015-08-25 | 2015-08-24 | 2015-08-25 | 2015-08-29 | 2015-09-21 | GAIL CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region VII | Bohol | 302900 | San Roque NHS | ALBURQUERQUE | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302902 | Sandingan National High School | LOON | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8324965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302906 | Sikatuna NHS | SIKATUNA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070115S00054 | 15HA0091 | 2015-10-26 | 2015-10-13 | 2015-10-26
NC 2015 | SHS (2015) | Region VII | Bohol | 302908 | Tabalong NHS | DAUIS | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070115S00053 | 15HA0129 | 2015-10-26 | 2015-10-13 | 2015-10-26 |  |  | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | K10 (2015) | Region VII | Bohol | 118794 | Talenceras ES | TUBIGON | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00230 | 15HA0146 | 2015-10-19 | 2015-10-07 | 2015-10-19 | 2015-10-23 | 2015-11-18 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | K10 (2015) | Region VII | Bohol | 118563 | Tangnan ES | PANGLAO | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070115S00161 | 15HA0143 | 2015-10-16 | 2015-10-05 | 2015-10-16 | 2015-10-22 | 2015-11-09 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2015 | K10 (2015) | Region VII | Bohol | 118265 | Tinago ES | DAUIS | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00171 | 15HA0092 | 2015-08-21 | 2015-08-10 | 2015-08-21 | 2015-08-28 | 2015-09-21 | JJF BUILDERS AND SUPPLY
NC 2015 | SHS (2015) | Region VII | Bohol | 312333 | Tubigon West Central HS | TUBIGON | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070115S00052 | 15HA0127 | 2015-10-05 | 2015-09-23 | 2015-10-05 | 2015-10-09 | 2015-11-09 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | Region VII | Bohol | 302822 | Tubigon West NHS | TUBIGON | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Bohol | 302822 | Tubigon West NHS | TUBIGON | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Bohol | 117980 | Tupas ES | ANTEQUERA | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070115S00170 | 15HA0142 | 2015-10-16 | 2015-10-05 | 2015-10-16 | 2015-10-21 | 2015-11-18 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2015 | K10 (2015) | Region VII | Bohol | 118798 | Ubay PS | TUBIGON | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | Reverted | 0 |  |  | 070115S00220 | 15HA0129
NC 2015 | SHS (2015) | Region VII | Bohol | 302808 | Aguining National High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 070115S00050 | 15HC0126 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | K10 (2015) | Region VII | Bohol | 118218 | Babag ES | DAGOHOY | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070115S00164 | 15HC0083 | 2015-08-13 | 2015-08-25 | 2015-08-26 | 2015-08-30 | 2015-09-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | K10 (2015) | Region VII | Bohol | 118061 | Baluarte ES | BUENAVISTA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00221 | 15HC0161 | 2015-11-12
NC 2015 | K10 (2015) | Region VII | Bohol | 118393 | Banahao Elementary School | INABANGA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00193 | 15HC0169 | 2015-12-15
NC 2015 | K10 (2015) | Region VII | Bohol | 118367 | Baogo ES | INABANGA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 68012714.0187 |  |  | COMPLETED | 1 |  |  | 070115S00210 | 15HC0193 | 2015-12-01
NC 2015 | SHS (2015) | Region VII | BOHOL | 312335 | Basiao High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00049 | 15HC0069 | 2015-08-26 | 2015-09-07 | 2015-09-08 | 2015-09-12 | 2015-09-16 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | Region VII | Bohol | 302816 | Biabas Trade High School | UBAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 070115S00048 | 15HC0122 | 2015-09-02 | 2015-09-14 | 2015-09-15 | 2015-09-19 | 2015-09-23 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | Region VII | Bohol | 312324 | Bonbonon HS | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Bohol | 118064 | Bonotbonot ES | BUENAVISTA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00222 | 15HC0162 | 2015-11-12
NC 2015 | K10 (2015) | Region VII | Bohol | 118188 | Buacao PS | CLARIN | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00223 | 15HC0163 | 2015-11-12
NC 2015 | K10 (2015) | Region VII | Bohol | 118643 | Bugang ES | SAN MIGUEL | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00188 | 15HC0171 | 2015-11-12
NC 2015 | SHS (2015) | Region VII | Bohol | 312334 | Bulilis High School | UBAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070115S00090 | 15HC0103 | 2015-08-31 | 2015-09-12 | 2015-09-13 | 2015-09-17 | 2015-09-21 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | K10 (2015) | Region VII | Bohol | 118323 | Buyog ES | JETAFE | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00226 | 15HC0165 | 2015-11-12
NC 2015 | SHS (2015) | Region VII | BOHOL | 500213 | Cabanugan Integrated School | SAN ISIDRO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00124 | 15HC0064 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-07-30 | 2015-08-03 | AQSIL BUILDERS AND CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Bohol | 312351 | Cagting High School | UBAY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00059 | 15HC0081 | 2015-08-26 | 2015-09-07 | 2015-09-08 | 2015-09-12 | 2015-09-16 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | K10 (2015) | Region VII | Bohol | 302894 | Calituban HS | TALIBON | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070115S00159 | 15HC0087 | 2015-08-17 | 2015-08-29 | 2015-08-30 | 2015-09-03 | 2015-09-07 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | Region VII | Bohol | 302825 | Camambugan NHS | UBAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 070115S00074 | 15HC0123 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | K10 (2015) | Region VII | Bohol | 118646 | Camanaga ES | SAN MIGUEL | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00160 | 15HC0089 | 2015-09-02 | 2015-09-14 | 2015-09-15 | 2015-09-19 | 2015-09-23 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2015 | K10 (2015) | Region VII | Bohol | 118647 | Cambangay Norte ES | SAN MIGUEL | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00206 | 15HC0172 | 2015-11-12
NC 2015 | K10 (2015) | Region VII | Bohol | 118370 | Cambitoon ES | INABANGA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00228 | 15HC0167
NC 2015 | SHS (2015) | Region VII | BOHOL | 312353 | Campamanog HS | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00092 | 15HC0070 | 2015-09-03 | 2015-09-15 | 2015-09-16 | 2015-09-20 | 2015-09-24 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | Region VII | Bohol | 302827 | Campao Oriental NHS | JETAFE | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070115S00093 | 15HC0108 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | K10 (2015) | Region VII | Bohol | 118071 | Cangawa ES | BUENAVISTA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070115S00172 | 15HC0082 | 2015-08-26 | 2015-09-07 | 2015-09-08 | 2015-09-12 | 2015-09-16 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | Region VII | Bohol | 302830 | Cangawa NHS | BUENAVISTA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Bohol | 302830 | Cangawa NHS | BUENAVISTA | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302842 | Cantubod NHS | DANAO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 070115S00094 | 15HC0118 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | K10 (2015) | Region VII | Bohol | 118747 | Catoogan PS | TRINIDAD | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00183 | 15HC0174 | 2015-11-12
NC 2015 | K10 (2015) | Region VII | Bohol | 118397 | Cawayan ES | INABANGA | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070115S00155 | 15HC0128 | 2015-09-02 | 2015-09-14 | 2015-09-15 | 2015-09-19 | 2015-09-23 | BNYU ENTERPRISES & CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bohol | 302836 | Clarin National School of Fisheries | CLARIN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 070115S00095 | 15HC0117 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | FFJJ CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Bohol | 118649 | Corazon ES | SAN MIGUEL | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00184 | 15HC0173 | 2015-11-12
NC 2015 | SHS (2015) | Region VII | Bohol | 302840 | Dagohoy NHS | DAGOHOY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 070115S00096 | 15HC0120 | 2015-09-02 | 2015-09-14 | 2015-09-15 | 2015-09-19 | 2015-09-23 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | Region VII | Bohol | 302841 | Danao NHS | DANAO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 070115S00106 | 15HC0119 | 2015-09-04 | 2015-09-16 | 2015-09-17 | 2015-09-21 | 2015-09-25 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | K10 (2015) | Region VII | Bohol | 118374 | Datag ES | INABANGA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00227 | 15HC0168 | 2015-12-15
NC 2015 | K10 (2015) | Region VII | Bohol | 118224 | Estaca ES | DAGOHOY | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00224 | 15HC0164 | 2015-11-12
NC 2015 | SHS (2015) | Region VII | Bohol | 302888 | Eugenio V. Amores MHS | SAGBAYAN (BORJA) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6409337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302843 | Francisco Dagohoy Mem. NHS | DANAO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00091 | 15HC0078 | 2015-09-04 | 2015-09-16 | 2015-09-17 | 2015-09-21 | 2015-09-25 | RG FELISILDA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | BOHOL | 312325 | Gaus HS | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00100 | 15HC0071 | 2015-08-26 | 2015-09-07 | 2015-09-08 | 2015-09-12 | 2015-09-16 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | K10 (2015) | Region VII | Bohol | 118376 | Hambongan ES | INABANGA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00207 | 15HC0192 | 2015-12-01
NC 2015 | SHS (2015) | Region VII | Bohol | 302828 | Handumon NHS | JETAFE | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302857 | Hingotanan NHS | BIEN UNIDO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Bohol | 118751 | Hinlayagan Ilaya ES | TRINIDAD | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00182 | 15HC0175 | 2015-11-12
NC 2015 | SHS (2015) | Region VII | Bohol | 302858 | Hinlayagan NHS | TRINIDAD | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 070115S00102 | 15HC0121 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | Region VII | Bohol | 302892 | Inabanga HS- Nabuad | INABANGA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070115S00103 | 15HC0096 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | MAI CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VII | Bohol | 312309 | JAPER Memorial High Shoool | SAGBAYAN (BORJA) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070115S00104 | 15HC0104 | 2015-09-02 | 2015-09-14 | 2015-09-15 | 2015-09-19 | 2015-09-23 | SLP CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Bohol | 118824 | Katarungan ES | UBAY | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00178 | 15HC0179 | 2015-11-12
NC 2015 | K10 (2015) | Region VII | Bohol | 118753 | Kinan-oan ES | TRINIDAD | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070115S00158 | 15HC0086 | 2015-08-04 | 2015-08-16 | 2015-08-17 | 2015-08-21 | 2015-08-25 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | Region VII | Bohol | 312305 | Kinan-oan HS | TRINIDAD | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00076 | 15HC0076 | 2015-07-30 | 2015-08-11 | 2015-08-12 | 2015-08-16 | 2015-08-20 | B. VICENCIO CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Bohol | 118755 | La Victoria ES | TRINIDAD | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00211 | 15HC0160 | 2015-11-12
NC 2015 | K10 (2015) | Region VII | Bohol | 118756 | Loblob ES | TRINIDAD | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00181 | 15HC0176 | 2015-11-12
NC 2015 | K10 (2015) | Region VII | Bohol | 118825 | Lomangog ES | UBAY | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00177 | 15HC0180 | 2015-11-12
NC 2015 | K10 (2015) | Region VII | Bohol | 118402 | Lomboy PS | INABANGA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00185 | 15HC0170 | 2015-11-12
NC 2015 | K10 (2015) | Region VII | Bohol | 118739 | Mahanay ES | TALIBON | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00229 | 15HC0191 | 2015-12-01
NC 2015 | K10 (2015) | Region VII | Bohol | 118653 | Mahayag ES | SAN MIGUEL | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070115S00166 | 15HC0129 | 2015-09-02 | 2015-09-14 | 2015-09-15 | 2015-09-19 | 2015-09-23 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2015 | SHS (2015) | Region VII | Bohol | 302873 | Mahayag NHS | SAN MIGUEL | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Bohol | 118757 | Manuel M. Roxas ES | TRINIDAD | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00180 | 15HC0177 | 2015-11-12
NC 2015 | SHS (2015) | Region VII | Bohol | 312313 | Mayor Catalino Casoyla MHS | TALIBON | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 070115S00146 | 15HC0125 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | Region VII | Bohol | 312303 | Mayor Inocencio B. Mendez HS | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8429965.051 |  |  | COMPLETED | 1 |  |  | 070115S00046 | 15HC0116 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | K10 (2015) | Region VII | Bohol | 186515 | Merryland PS | BUENAVISTA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2281106.04 |  |  | COMPLETED | 1 |  |  | 070115S00212 | 15HC0184 | 2015-11-17
NC 2015 | SHS (2015) | Region VII | Bohol | 302879 | Nahawan NHS | CLARIN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 |  |  | 070115S00024 | 15HC0112 | 2015-09-02 | 2015-09-14 | 2015-09-15 | 2015-09-19 | 2015-09-23 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | K10 (2015) | Region VII | Bohol | 118761 | Panaghi-usa ES | TRINIDAD | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00174 | 15HC0178 | 2015-11-12
NC 2015 | SHS (2015) | Region VII | Bohol | 312312 | Panghagban HS | BUENAVISTA | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3584886.575 |  |  | COMPLETED | 1 |  |  | 070115S00138 | 15HC0061 | 2015-07-03 | 2015-07-15 | 2015-07-16 | 2015-07-20 | 2015-07-24 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Bohol | 312331 | Ponciana E. Leoligao HS | TALIBON | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Bohol | 312360 | Ponciano L. Padin National High School | BIEN UNIDO | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070115S00168 | 15HC0127 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | Region VII | Bohol | 302886 | Pres. Carlos P. Garcia Technical Vocational School of Fisheries and Arts | BIEN UNIDO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 |  |  | 070115S00097 | 15HC0094 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | Region VII | Bohol | 302895 | President Carlos P. Garcia Memorial High School | TALIBON | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Bohol | 118339 | Saguise ES | JETAFE | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00219 | 15HC0166 | 2015-11-12
NC 2015 | SHS (2015) | Region VII | Bohol | 302887 | San Agustin NHS | SAGBAYAN (BORJA) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070115S00088 | 15HC0106 | 2015-09-02 | 2015-09-14 | 2015-09-15 | 2015-09-19 | 2015-09-23 | SLP CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bohol | 312350 | San Isidro HS | TALIBON | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302890 | San Isidro NHS | SAN ISIDRO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070115S00137 | 15HC0107 | 2015-08-31 | 2015-09-12 | 2015-09-13 | 2015-09-17 | 2015-09-21 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | Region VII | Bohol | 302891 | San Jose NHS | INABANGA | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10487131.51 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302893 | San Jose NHS | TALIBON | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Bohol | 302893 | San Jose NHS | TALIBON | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Bohol | 118229 | San Miguel ES | DAGOHOY | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 4447320.78 |  |  | COMPLETED | 1 |  |  | 070115S00225 | 15HC0196 | 2015-12-01
NC 2015 | SHS (2015) | Region VII | Bohol | 312321 | San Miguel Puertos HS | DAGOHOY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00084 | 15HC0079 | 2015-08-26 | 2015-09-07 | 2015-09-08 | 2015-09-12 | 2015-09-16 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | Region VII | Bohol | 302897 | San Miguel Technical Vocational School | SAN MIGUEL | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Bohol | 302897 | San Miguel Technical Vocational School | SAN MIGUEL | 2 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302899 | San Pascual National Agr'l HS | UBAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 070115S00083 | 15HC0115 | 2015-09-04 | 2015-09-16 | 2015-09-17 | 2015-09-21 | 2015-09-25 | LTS BUILDERS AND CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VII | Bohol | 118230 | San Vicente ES | DAGOHOY | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070115S00163 | 15HC0084 | 2015-08-04 | 2015-08-16 | 2015-08-17 | 2015-08-21 | 2015-08-25 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | Region VII | Bohol | 302896 | Sikatuna Nat'l Agricultural HS | TALIBON | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2820828.124 |  |  | COMPLETED | 1 |  |  | 070115S00082 | 15HC0066 | 2015-08-26 | 2015-09-07 | 2015-09-08 | 2015-09-12 | 2015-09-16 | B. VICENCIO CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Bohol | 118835 | Sinandigan ES | UBAY | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00176 | 15HC0181 | 2015-11-12
NC 2015 | SHS (2015) | Region VII | Bohol | 302859 | Southern Inabanga HS | INABANGA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Bohol | 118389 | Sto. Niño PS | INABANGA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2142006.04 |  |  | COMPLETED | 1 |  |  | 070115S00205 | 15HC0195 | 2015-12-01
NC 2015 | K10 (2015) | Region VII | Bohol | 118603 | Sto. Rosario Elementary School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00191 | 15HC0194 | 2015-12-01
NC 2015 | SHS (2015) | Region VII | Bohol | 302910 | Tagum Sur NHS | TRINIDAD | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302844 | Taming NHS | DANAO | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3584886.575 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Bohol | 118730 | Tanghaligue ES | TALIBON | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00208 | 15HC0158 | 2015-11-12
NC 2015 | SHS (2015) | Region VII | BOHOL | 500214 | Tapal Integrated School | UBAY | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00078 | 15HC0065 | 2015-07-03 | 2015-07-15 | 2015-07-16 | 2015-07-20 | 2015-07-24 | MAI CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region VII | Bohol | 118198 | Tontunan ES | CLARIN | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00165 | 15HC0090 | 2015-09-10 | 2015-09-22 | 2015-09-23 | 2015-09-27 | 2015-10-01 | 2H2L CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Bohol | 118840 | Tres Reyes ES | UBAY | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 4001368.78 |  |  | COMPLETED | 1 |  |  | 070115S00175 | 15HC0183 | 2015-11-17
NC 2015 | SHS (2015) | Region VII | Bohol | 500215 | Tubog Integrated School | UBAY | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3574886.575 |  |  | COMPLETED | 1 |  |  | 070115S00077 | 15HC0063 | 2015-07-01 | 2015-07-13 | 2015-07-14 | 2015-07-18 | 2015-07-22 | MAI CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VII | Bohol | 302913 | Tulang NHS | JETAFE | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302915 | Ubay National Science HS | UBAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302914 | Union NHS | UBAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 070115S00016 | 15HC0114 | 2015-09-04 | 2015-09-16 | 2015-09-17 | 2015-09-21 | 2015-09-25 | MAI CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region VII | Bohol | 118233 | Villa Aurora ES | DAGOHOY | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070115S00162 | 15HC0085 | 2015-08-04 | 2015-08-16 | 2015-08-17 | 2015-08-21 | 2015-08-25 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | K10 (2015) | Region VII | Bohol | 118731 | Zamora ES | TALIBON | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00209 | 15HC0159 | 2015-11-12
NC 2015 | SHS (2015) | Region VII | Bohol | 302814 | Zosimo A. Gulle Memorial National High Schhol | TALIBON | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070115S00015 | 15HC0110 | 2015-08-26 | 2015-09-07 | 2015-09-08 | 2015-09-12 | 2015-09-16 | BNYU ENTERPRISES & CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Bohol | 186507 | Alicia CES Annex | ALICIA | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00189 | 15HB0092 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | WYNN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bohol | 302809 | Alicia Technical-Voc'l HS | ALICIA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 070115S00135 | 15HB0071 | 2015-07-20 | 2015-07-21 | 2015-08-03 | 2015-08-12 | 2015-09-03 | ALGAMON CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bohol | 302810 | Ambassador Pablo R. Suarez, Jr. NHS | CARMEN | 3 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1 |  |  | 070115S00014 | 15HB0064 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2015 | SHS (2015) | Region VII | BOHOL | 302813 | Anda HS | ANDA | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00134 | 15HB0057 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2015 | SHS (2015) | Region VII | Bohol | 302912 | Anoling National High School | CANDIJAY | 3 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3614886.575 |  |  | COMPLETED | 1 |  |  | 070115S00013 | 15HB0057 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2015 | SHS (2015) | Region VII | Bohol | 302812 | Badiang NHS | ANDA | 3 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2830828.124 |  |  | COMPLETED | 1 |  |  | 070115S00133 | 15HB0057 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2015 | K10 (2015) | Region VII | Bohol | 118346 | Basdio ES | GUINDULMAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 070115S00192 | 15HB0100 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | WYNN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bohol | 302815 | Batuan NHS | BATUAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | BOHOL | 312310 | Bayawahan National High School | SEVILLA | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00005 | 15HB0062 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | RG FELISILDA CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Bohol | 118348 | Bayong ES | GUINDULMAN | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00203 | 15HB0089 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | ALGAMON CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bohol | 302818 | Bilar NHS | BILAR | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 070115S00012 | 15HB0034 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2015 | K10 (2015) | Region VII | Bohol | 118515 | Bulawan ES | MABINI | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 070115S00187 | 15HB0100 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | WYNN CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Bohol | 118270 | Cadap-agan PS | DIMIAO | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00197 | 15HB0096 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | FIRST BUILDERS AND DEVELOPERS
NC 2015 | K10 (2015) | Region VII | Bohol | 118663 | Calinginan Norte Elementary | SEVILLA | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00201 | 15HB0095 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | FIRST BUILDERS AND DEVELOPERS
NC 2015 | SHS (2015) | Region VII | Bohol | 302826 | Camaya-an NHS | LOBOC | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302826 | Camaya-an NHS | LOBOC | 3 | 1 | 4 | ADDITIONAL 2STY4CL | 2015 ADDITIONAL FUND BATCH 9 | 6169337.64 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | BOHOL | 302904 | Cambagui-Calinginan National Norte HS | SEVILLA | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00010 | 15HB0062 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | RG FELISILDA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bohol | 312352 | Cambuyo HS | GARCIA HERNANDEZ | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302829 | Candabong National High School | ANDA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302829 | Candabong National High School | ANDA | 3 | 1 | 4 | ADDITIONAL 2STY4CL | 2015 ADDITIONAL FUND BATCH 9 | 6169337.64 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Bohol | 118114 | Candijay Central ES | CANDIJAY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 070115S00196 | 15HB0099 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | WYNN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bohol | 302865 | Candijay NHS | CANDIJAY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8474965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302832 | Canhayupon NHS | DIMIAO | 3 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3574886.575 |  |  | COMPLETED | 1 |  |  | 070115S00004 | 15HB0060 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2015 | SHS (2015) | Region VII | Bohol | 302834 | Catungawan NHS | GUINDULMAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | BOHOL | 312316 | Cayacay HS | ALICIA | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00131 | 15HB0059 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2015 | K10 (2015) | Region VII | Bohol | 118116 | Cogtong ES | CANDIJAY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 070115S00195 | 15HB0099 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | WYNN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bohol | 302866 | Cogtong NHS | CANDIJAY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8474965.051 |  |  | COMPLETED | 1 |  |  | 070115S00007 | 15HB0037 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2015 | SHS (2015) | Region VII | Bohol | 302837 | Concepcion NHS | MABINI | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00140 | 15HB0059 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2015 | K10 (2015) | Region VII | Bohol | 118681 | Danicop ES | SIERRA BULLONES | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00199 | 15HB0091 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | GELA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bohol | 302845 | Dimiao NHS | DIMIAO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1 |  |  | 070115S00011 | 15HB0038 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2015 | SHS (2015) | Region VII | Bohol | 302847 | Duero NHS | DUERO | 3 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3514886.575 |  |  | COMPLETED | 1 |  |  | 070115S00032 | 15HB0058 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | LTS BUILDERS AND CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Bohol | 302848 | Dusita HS | SIERRA BULLONES | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10567131.51 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Bohol | 118666 | Ewon Elementary School | SEVILLA | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00200 | 15HB0093 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | FIRST BUILDERS AND DEVELOPERS
NC 2015 | SHS (2015) | Region VII | Bohol | 302849 | Faraon NHS | JAGNA | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00042 | 15HB0060 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2015 | SHS (2015) | Region VII | Bohol | 302861 | Francisco L. Adlaon HS | CARMEN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1 |  |  | 070115S00041 | 15HB0040 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2015 | SHS (2015) | Region VII | Bohol | 302852 | Garcia-Hernandez HS | GARCIA HERNANDEZ | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1 |  |  | 070115S00040 | 15HB0041 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2015 | SHS (2015) | Region VII | Bohol | 302854 | Guinacot NHS | GUINDULMAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8354965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302855 | Guinsularan High School | DUERO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302867 | Hinawanan NHS | LOAY | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 312358 | Jagna HS | JAGNA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 312359 | Katipunan HS | ALICIA | 3 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2790828.124 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302860 | Katipunan NHS | CARMEN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 070115S00036 | 15HB0044 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2015 | SHS (2015) | Region VII | Bohol | 312318 | Katipunan NHS Annex | CARMEN | 3 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1 |  |  | 070115S00035 | 15HB0063 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2015 | SHS (2015) | Region VII | Bohol | 302863 | La Hacienda NHS | ALICIA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Bohol | 118577 | La Suerte ES | PILAR | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070115S00156 | 15HB0079 | 2015-08-10 | 2015-08-12 | 2015-08-25 | 2015-09-03 | 2015-09-25 | ALGAMON CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bohol | 302864 | La Union NHS | CANDIJAY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070115S00034 | 15HB0046 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2015 | K10 (2015) | Region VII | Bohol | 118447 | Las Salinas ES | LOAY | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00202 | 15HB0094 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | WYNN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bohol | 302868 | Lila NHS | LILA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302869 | Loboc NHS | LOBOC | 3 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3534886.575 |  |  | COMPLETED | 1 |  |  | 070115S00018 | 15HB0061 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | AL CHRIS CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bohol | 302870 | Lonoy Heroes MHS | JAGNA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070115S00031 | 15HB0048 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2015 | K10 (2015) | Region VII | Bohol | 118118 | Luan ES | CANDIJAY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Bohol | 118119 | Lungsodaan ES | CANDIJAY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 070115S00194 | 15HB0099 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | WYNN CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Bohol | 118519 | Lungsodaan ES | MABINI | 3 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070115S00157 | 15HB0077 | 2015-07-20 | 2015-07-21 | 2015-08-03 | 2015-08-12 | 2015-09-03 | FIRST BUILDERS AND DEVELOPERS
NC 2015 | K10 (2015) | Region VII | Bohol | 118021 | Lungsod-Daan ES | BATUAN | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00173 | 15HB0090 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | R.M. MONDARES CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Bohol | 117962 | Mahayahay PS | ANDA | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00179 | 15HB0088 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | Region VII | Bohol | 312311 | Mayor Pablo O. Lim MHS | VALENCIA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8424965.051 |  |  | COMPLETED | 1 |  |  | 070115S00145 | 15HB0082 | 2015-09-09 | 2015-09-11 | 2015-09-23 | 2015-09-30 | 2015-10-23 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | Region VII | Bohol | 302878 | Mayuga NHS | GUINDULMAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Bohol | 117946 | Napo ES | ALICIA | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 070115S00190 | 15HB0100 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | WYNN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | BOHOL | 302880 | Oy NHS | LOBOC | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00029 | 15HB0062 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | RG FELISILDA CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Bohol | 118122 | Panadtaran ES | CANDIJAY | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00186 | 15HB0097 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | WYNN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bohol | 302884 | Pilar Technical-Vocational HS | PILAR | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Bohol | 302884 | Pilar Technical-Vocational HS | PILAR | 3 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302885 | Policronio S. Dano, Sr. HS | CARMEN | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1 |  |  | 070115S00038 | 15HB0051 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2015 | SHS (2015) | Region VII | Bohol | 312339 | Ponciano F. Ramasola Sr. High School | CARMEN | 3 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3564886.575 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | BOHOL | 312314 | Quezon HS - Batuan NHS Annex | BATUAN | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00127 | 15HB0062 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | RG FELISILDA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | BOHOL | 312315 | Rizal High Sschool | BATUAN | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00126 | 15HB0063 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2015 | SHS (2015) | Region VII | Bohol | 302889 | San Isidro Tech-Voc HS | PILAR | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8294965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Bohol | 302901 | San Roque National High School | MABINI | 3 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302901 | San Roque NHS | MABINI | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8374965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302905 | Sierra Bullones Technical Vocational High School | SIERRA BULLONES | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8384965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Bohol | 118694 | Sta. Cruz Elementary School | SIERRA BULLONES | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070115S00198 | 15HB0098 | 2015-09-29 | 2015-09-30 | 2015-10-12 | 2015-10-22 | 2015-11-03 | GELA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Bohol | 302909 | Tabuan NHS | GARCIA HERNANDEZ | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Bohol | 302911 | Tambongan NHS | CANDIJAY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 |  |  | 070115S00023 | 15HB0055 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-24 | 2015-08-11 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2015 | SHS (2015) | Region VII | Bohol | 302916 | Valencia Tech-Voc HS | VALENCIA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Bohol | 302916 | Valencia Tech-Voc HS | VALENCIA | 3 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7198647.81 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Carcar City | 119171 | Bolinawan ES | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00504 | 15-HE-0130 | 2015-09-21 | 2015-09-22 | 2015-10-05 | 2015-10-13 | 2015-10-19 | RCDG CONSTRUCTION CORPORATION
NC 2015 | K10 (2015) | Region VII | Carcar City | 119156 | Can-asujan ES | CITY OF CARCAR | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00402 | 15-HE-0090 | 2015-07-15 | 2015-07-16 | 2015-08-04 | 2015-08-12 | 2015-08-18 | LISA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Carcar City | 302970 | Can-asujan NHS | CITY OF CARCAR | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Carcar City | 302972 | Carcar Central National High School (Pob. Night) | CITY OF CARCAR | 1 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 8 | 15371327.92 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Carcar City | 302972 | Carcar Central National High School (Pob. Night) | CITY OF CARCAR | 1 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Carcar City | 119160 | Lunas Elementary School | CITY OF CARCAR | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00403 | 15-HE-0091 | 2015-07-15 | 2015-07-16 | 2015-09-15 | 2015-09-21 | 2015-09-28 | A.T. DUMLAO CONSTRUCTION, INC. FORMERLYANDONI T. D
NC 2015 | SHS (2015) | Region VII | Carcar City | 303016 | Maximino Noel Memorial National High School | CITY OF CARCAR | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Carcar City | 256001 | Moag ES | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00491 | 15-HE-0124 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | CARCAR CITY | 356059 | Ocana National High School (Kalangyawon Extension) | CITY OF CARCAR | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Carcar City | 303066 | OCAÑA NHS | CITY OF CARCAR | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Carcar City | 324903 | Pit-os National High School | CITY OF CARCAR | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00405 | 15-HE-0093 | 2015-07-15 | 2015-07-16 | 2015-09-15 | 2015-09-21 | 2015-09-28 | A.T. DUMLAO CONSTRUCTION, INC. FORMERLYANDONI T. D
NC 2015 | SHS (2015) | Region VII | Carcar City | 303082 | ROBERTO E. SATO MEMORIAL NATIONAL HIGH SCHOOL | CITY OF CARCAR | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00150 | 15-HE-0063 | 2015-06-10 | 2015-06-11 | 2015-06-30 | 2015-07-06 | 2015-07-22 | QUIRANTE CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Carcar City | 119163 | Sa-ay Elementary School | CITY OF CARCAR | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00404 | 15-HE-0092 | 2015-07-15 | 2015-07-16 | 2015-09-15 | 2015-09-21 | 2015-09-28 | QUIRANTE CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Carcar City | 343971 | SHS in Carcar City | Carcar City | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 32102890 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Carcar City | 324905 | TAL-UT NATIONAL HIGH SCHOOL | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00387 | 15-HE-0094 | 2015-07-15 | 2015-07-16 | 2015-08-04 | 2015-08-12 | 2015-08-18 | MAP ALVIOLA CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Carcar City | 119167 | Tawog Elementary School | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | REVERTED | 0 |  |  | 070215S00505
NC 2015 | K10 (2015) | Region VII | Carcar City | 119168 | Tuyom ES | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00503 | 15-HE-0122 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VII | Carcar City | 119169 | Valencia Elementary School | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00507 | 15-HE-0123 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | POWER MOVE BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Carcar City | 303126 | Valencia VOCATIONAL NHS | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 312427 | Balungag NHS | SAN FERNANDO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2018606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 119619 | Basak ES | SAN FERNANDO | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6279337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00519 | 15-HE-0120 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | PEDXING BUILDERS
NC 2015 | SHS (2015) | Region VII | Cebu | 302969 | Camp 7 NHS | MINGLANILLA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8409965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 119709 | Can-aga ES | SIBONGA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00401 | 15-HE-0095 | 2015-07-15 | 2015-07-16 | 2015-08-04 | 2015-08-12 | 2015-08-18 | MAP ALVIOLA CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Cebu | 119484 | Cuanos ES | MINGLANILLA | 1 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 070215S00407 | 15-HE-0086 | 2015-12-14 | 2015-12-15 | 2015-12-28
NC 2015 | SHS (2015) | Region VII | Cebu | 303015 | Greenhills NHS | SAN FERNANDO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6339337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00281 | 15-HE-0055 | 2015-06-10 | 2015-06-11 | 2015-08-04 | 2015-08-12 | 2015-08-18 | BT CONSTRUCTION AND GENERAL SERVICES
NC 2015 | K10 (2015) | Region VII | Cebu | 119712 | Guimbangcoan PS | SIBONGA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00508 | 15-HE-0125 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | MAP ALVIOLA CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Cebu | 119475 | Guindarohan ES | MINGLANILLA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6299337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00495 | 15-HE-0115 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | MAP ALVIOLA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 303017 | Guindaruhan National High School | MINGLANILLA | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10507131.51 |  |  | COMPLETED | 1 |  |  | 070215S00144 | 15-HE-0043 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-07-22 | PEDXING BUILDERS
NC 2015 | SHS (2015) | Region VII | Cebu | 303022 | Julian Enad MNHS | SIBONGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1978606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 303022 | Julian Enad MNHS | SIBONGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 312467 | Lantawan Integrated School | SAN FERNANDO | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00289 | 15-HE-0058 | 2015-06-10 | 2015-06-11 | 2015-08-04 | 2015-08-12 | 2015-08-18 | MAP ALVIOLA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 303042 | Lipata NHS | MINGLANILLA | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10467131.51 |  |  | COMPLETED | 1 |  |  | 070215S00154 | 15-HE-0044 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-08-13 | QUIRANTE CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 303049 | Magsico NHS | SAN FERNANDO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 070215S00279 | 15-HE-0056 | 2015-06-10 | 2015-06-11 | 2015-09-07 | 2015-09-14 | 2015-09-18 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 312457 | Manatad NHS | SIBONGA | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 303051 | Mangyan NHS | SIBONGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2063606.04 |  |  | COMPLETED | 1 |  |  | 070215S00347 | 15-HE-0082 | 2015-07-15 | 2015-07-16 | 2015-10-05 | 2015-10-09 | 2015-10-14 | QUIRANTE CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 303079 | PITALO NHS | SAN FERNANDO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 303079 | PITALO NHS | SAN FERNANDO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 119720 | Sabang ES | SIBONGA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00502 | 15-HE-0126 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | E.G. & I. CONSTRUCTION CORPORATION
NC 2015 | SHS (2015) | Region VII | Cebu | 312424 | San Fernando NHS | SAN FERNANDO | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10617132 |  |  | REVERTED | 0 |  |  | 070215S00446 | 15-HE-0113 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | E.G. & I. CONSTRUCTION CORPORATION
NC 2015 | SHS (2015) | Region VII | Cebu | 303093 | Sangat NHS | SAN FERNANDO | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10447131.51 |  |  | COMPLETED | 1 |  |  | 070215S00278 | 15-HE-0057 | 2015-06-10 | 2015-06-11 | 2015-06-30 | 2015-07-06 | 2015-08-13 | PEDXING BUILDERS
NC 2015 | SHS (2015) | Region VII | Cebu | 303101 | Sibonga National High School | SIBONGA | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10447131.51 |  |  | COMPLETED | 1 |  |  | 070215S00157 | 15-HE-0066 | 2015-06-10 | 2015-06-11 | 2015-06-30 | 2015-07-06 | 2015-07-22 | GENETIAN BUILDERS
NC 2015 | SHS (2015) | Region VII | Cebu | 303067 | Teodoro dela Vega MNHS | SIBONGA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1 |  |  | 070215S00158 | 15-HE-0067 | 2015-06-10 | 2015-06-11 | 2015-10-05 | 2015-10-09 | 2015-10-14 | QUIRANTE CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Cebu | 119634 | Tinubdan ES | SAN FERNANDO | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6299337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00518 | 15-HE-0129 | 2015-09-21 | 2015-09-22 | 2015-10-05 | 2015-10-13 | 2015-10-19 | MRRM TRADING & CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Cebu | 119635 | Tonggo ES | SAN FERNANDO | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6209337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00517 | 15-HE-0121 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | PEDXING BUILDERS
NC 2015 | SHS (2015) | Region VII | Cebu | 303116 | Tubod National High School | MINGLANILLA | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10542131.51 |  |  | COMPLETED | 1 |  |  | 070215S00159 | 15-HE-0045 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-07-22 | PEDXING BUILDERS
NC 2015 | SHS (2015) | Region VII | Cebu | 303117 | Tubod NHS (San Fernando) | SAN FERNANDO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 070215S00342 | 15-HE-0079 | 2015-07-15 | 2015-07-16 | 2015-08-04 | 2015-08-12 | 2015-08-18 | MAP ALVIOLA CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Cebu | 303118 | Tulay MHS | MINGLANILLA | 1 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 3 | 12771310.093 |  |  | COMPLETED | 1 |  |  | 070215S00399 | 15-HE-0087 | 2015-07-15 | 2015-07-16 | 2015-10-22 | 2015-10-28 | 2015-11-03 | QUIRANTE CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 312450 | Tungkil NHS | MINGLANILLA | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | Reverted | 0
NC 2015 | SHS (2015) | Region VII | Cebu | 303119 | Tungkop NHS | MINGLANILLA | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10477131.51 |  |  | COMPLETED | 1 |  |  | 070215S00160 | 15-HE-0046 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-07-22 | FIRST BUILDERS AND DEVELOPERS
NC 2015 | SHS (2015) | Region VII | Cebu | 312419 | VITO NATIONAL HIGH SCHOOL | MINGLANILLA | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10497131.51 |  |  | COMPLETED | 1 |  |  | 070215S00135 | 15-HE-0047 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-08-13 | WORLDWIDE BUILDERS
NC 2015 | SHS (2015) | Region VII | Cebu | 302922 | Alcantara NHS | ALCANTARA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00288 | 15HG0082 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-11 | 2015-08-12 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
NC 2015 | SHS (2015) | Region VII | Cebu | 302917 | Alcoy NHS | ALCOY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10467131.51 |  |  | COMPLETED | 1 |  |  | 070215S00151 | 15HG0091 | 2015-06-13 | 2015-06-11 | 2015-06-26 | 2015-08-14 | 2015-08-17 | E.G. & I. CONSTRUCTION CORPORATION
NC 2015 | K10 (2015) | Region VII | Cebu | 119526 | Alo ES | OSLOB | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6244337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00512 | 15HG0130 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-16 | 2015-11-17 | RUDPA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 302985 | Argao National High School | ARGAO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070215S00128 | 15HG0072 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-07-20 | 2015-07-22 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VII | Cebu | 119437 | Armena ES | MALABUYOC | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6219337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00511 | 15HG0129 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-09 | 2015-11-10 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu | 302921 | Badian NHS | BADIAN | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10977342.5917 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Cebu | 302921 | Badian NHS | BADIAN | 2 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7228647.81 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 119491 | Balabagon ES | MOALBOAL | 2 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 3 | 12771310.093 |  |  | COMPLETED | 1 |  |  | 070215S00301 | 15HG0113 | 2015-06-25 | 2015-06-25 | 2015-07-08 | 2015-08-14 | 2015-08-17 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VII | Cebu | 119313 | Banhigan ES | DALAGUETE | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6239337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00493 | 15HG0124 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-09 | 2015-11-10 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu | 302940 | Bitoon NVHS | DUMANJUG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00130 | 15HG0086 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-26 | 2015-08-27 | RUDPA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 302942 | Boljoon NHS | BOLJOON | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10457131.51 |  |  | COMPLETED | 1 |  |  | 070215S00131 | 15HG0092 | 2015-06-13 | 2015-06-11 | 2015-06-26 | 2015-08-14 | 2015-08-17 | QUIRANTE CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 302951 | Bulak NHS | DUMANJUG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070215S00132 | 15HG0084 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-11 | 2015-08-12 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
NC 2015 | SHS (2015) | Region VII | Cebu | 302953 | Bulasa NHS | ARGAO | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10507131.51 |  |  | COMPLETED | 1 |  |  | 070215S00143 | 15HG0093 | 2015-06-13 | 2015-06-11 | 2015-06-26 | 2015-08-14 | 2015-08-17 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VII | Cebu | 119372 | Bullogan ES | DUMANJUG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00299 | 15HG0111 | 2015-06-25 | 2015-06-25 | 2015-07-08 | 2015-08-26 | 2015-08-27 | DT&C CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 302926 | Busay NHS | MOALBOAL | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00134 | 15HG0071 | 2015-06-10 | 2015-06-11 | 2015-06-24 | 2015-07-20 | 2015-07-22 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | K10 (2015) | Region VII | Cebu | 119293 | Caleriohan ES | DALAGUETE | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00494 | 15HG0123 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-16 | 2015-11-17 | RAJLAURENTE CONSTRUCTION & DEVELOPMENT PHIL.
NC 2015 | SHS (2015) | Region VII | Cebu | 312411 | Caleriohan National HIgh School | DALAGUETE | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1998606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 312411 | Caleriohan National HIgh School | DALAGUETE | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 302998 | Caliongan NHS | DALAGUETE | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2922592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 302998 | Caliongan NHS | DALAGUETE | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 187027 | Cambigong ES | SAMBOAN | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6239337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00501 | 15HG0133 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-09 | 2015-11-10 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VII | Cebu | 119529 | Canangcaan ES | OSLOB | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00513 | 15HG0131 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-09 | 2015-11-10 | DT&C CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 312426 | Cañang-Marcelo Luna NHS | OSLOB | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2700828.124 |  |  | COMPLETED | 1 |  |  | 070215S00126 | 15HG0058 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-07-13 | 2015-07-14 | SERCHER DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region VII | Cebu | 119530 | Cansaloay Integrated School | OSLOB | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00524 | 15HG0132 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-16 | 2015-11-17 | RUDPA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 312469 | Cansaloay Integrated School | OSLOB | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00023 | 15HG0052 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-07-13 | 2015-07-14 | SERCHER DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VII | Cebu | 303125 | Cansuje National High School - Usmad Ext. | ARGAO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6379337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00136 | 15HG0063 | 2015-06-10 | 2015-06-11 | 2015-06-24 | 2015-07-20 | 2015-07-22 | BLIMEX CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu | 302977 | Casay NHS | DALAGUETE | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8299965.051 |  |  | COMPLETED | 1 |  |  | 070215S00137 | 15HG0075 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-07-20 | 2015-07-22 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VII | Cebu | 119295 | Catambisan ES | DALAGUETE | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00296 | 15HG0110 | 2015-06-25 | 2015-06-25 | 2015-07-08 | 2015-07-20 | 2015-07-22 | DT&C CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Cebu | 119296 | Catolohan ES | DALAGUETE | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6339337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00516 | 15HG0125 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-16 | 2015-11-17 | RAJLAURENTE CONSTRUCTION & DEVELOPMENT PHIL.
NC 2015 | SHS (2015) | Region VII | Cebu | 302981 | Cawayan NHS | DALAGUETE | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10537131.51 |  |  | COMPLETED | 1 |  |  | 070215S00138 | 15HG0090 | 2015-06-13 | 2015-06-11 | 2015-06-30 | 2015-08-14 | 2015-08-17 | SERCHER DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region VII | Cebu | 119440 | CerdeÑa ES | MALABUYOC | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00310 | 15HG0112 | 2015-06-25 | 2015-06-25 | 2015-07-08 | 2015-08-26 | 2015-08-27 | DT&C CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 302982 | Cerdeña NHS | MALABUYOC | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2760828.124 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 302983 | Cogon NHS | DUMANJUG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00140 | 15HG0085 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-07-20 | 2015-07-22 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu | 302984 | Colawin NHS | ARGAO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00141 | 15HG0074 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-07-20 | 2015-07-22 | BLIMEX CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu | 302997 | Dalaguete NHS | DALAGUETE | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Cebu | 302997 | Dalaguete NHS | DALAGUETE | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 119319 | Dumalan ES | DALAGUETE | 2 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 070215S00297 | 15HG0100 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-08-14 | 2015-08-17 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu | 302941 | Dumanjug NHS | DUMANJUG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00074 | 15HG0087 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-11 | 2015-08-12 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu | 302943 | El Pardo NHS | BOLJOON | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 |  |  | 070215S00027 | 15HG0059 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-07-13 | 2015-07-14 | DT&C CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Cebu | 118875 | Guiwang ES | ALCOY | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00499 | 15HG0122 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-16 | 2015-11-17 | DT&C CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 303018 | Guiwanon NHS | GINATILAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00098 | 15HG0079 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-11 | 2015-08-12 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
NC 2015 | SHS (2015) | Region VII | Cebu | 312403 | Hipolito Boquecosa MNHS | DUMANJUG | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2720828.124 |  |  | COMPLETED | 1 |  |  | 070215S00039 | 15HG0061 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-07-13 | 2015-07-14 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
NC 2015 | SHS (2015) | Region VII | Cebu | 312461 | Inghoy NHS | ALEGRIA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00024 | 15HG0056 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-07-13 | 2015-07-14 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
NC 2015 | K10 (2015) | Region VII | Cebu | 119380 | Lawaan ES | DUMANJUG | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6219337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00514 | 15HG0127 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-09 | 2015-11-10 | DT&C CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Cebu | 119698 | Liloan ES | SANTANDER | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00303 | 15HG0102 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-08-14 | 2015-08-17 | WORLDWIDE BUILDERS
NC 2015 | SHS (2015) | Region VII | Cebu | 302944 | Lunop NHS | BOLJOON | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2058606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 303096 | Madridejos NHS (Alegria) | ALEGRIA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070215S00040 | 15HG0080 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-11 | 2015-08-12 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
NC 2015 | SHS (2015) | Region VII | Cebu | 312462 | Mahanlud NHS | MALABUYOC | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00025 | 15HG055 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-08-26 | 2015-08-27 | DT&C CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 302986 | Mandilikit NHS | ARGAO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00026 | 15HG0057 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-07-13 | 2015-07-14 | BLIMEX CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu | 302999 | Manlapay National High School | DALAGUETE | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2862592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 302999 | Manlapay National High School | DALAGUETE | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 303000 | Mantalongon NHS | DALAGUETE | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 119391 | Masa ES | DUMANJUG | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6249337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00510 | 15HG0128 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-16 | 2015-11-17 | GELA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 302927 | Moalboal NHS | MOALBOAL | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1 |  |  | 070215S00042 | 15HG0088 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-26 | 2015-08-27 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 303057 | Monta¤eza NHS | MALABUYOC | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070215S00043 | 15HG0078 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-26 | 2015-08-27 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 312460 | Montpeller NHS | ALEGRIA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6389337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00054 | 15HG0069 | 2015-06-10 | 2015-06-11 | 2015-06-24 | 2015-07-20 | 2015-07-22 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
NC 2015 | SHS (2015) | Region VII | Cebu | 302918 | Nug-as NHS | ALCOY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8304965.051 |  |  | COMPLETED | 1 |  |  | 070215S00309 | 15HG0097 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-07-20 | 2015-07-22 | QUIRANTE CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 303099 | Oslob NHS | OSLOB | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00045 | 15HG0094 | 2015-06-13 | 2015-06-11 | 2015-06-26 | 2015-08-26 | 2015-08-27 | BLIMEX CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu | 312459 | Palanas Integrated School | GINATILAN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 119328 | Panas ES | DALAGUETE | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6219337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00515 | 15HG0126 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-11-16 | 2015-11-17 | RAJLAURENTE CONSTRUCTION & DEVELOPMENT PHIL.
NC 2015 | SHS (2015) | Region VII | Cebu | 312466 | Pasol-Pugalo Integrated School | ALCOY | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00028 | 15HG0053 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-07-13 | 2015-07-14 | DT&C CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 312425 | Pedro B. Uy Calderon Memorial National High School | SAMBOAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00037 | 15HG0067 | 2015-06-10 | 2015-06-11 | 2015-06-24 | 2015-07-20 | 2015-07-22 | RUDPA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 312413 | Pungtod NHS | OSLOB | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6339337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00047 | 15HG0065 | 2015-06-10 | 2015-06-11 | 2015-06-24 | 2015-07-20 | 2015-07-22 | RUDPA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 303034 | Ronda NHS- Langin NHS Ext. | RONDA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00048 | 15HG0083 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-11 | 2015-08-12 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
NC 2015 | SHS (2015) | Region VII | Cebu | 303084 | Salamanca NHS | GINATILAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 119330 | Salug ES | DALAGUETE | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00298 | 15HG0101 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-08-26 | 2015-08-27 | MUANA CONSTRUCTION AND DEVELOPMENT CORP. (FORMERLY
NC 2015 | SHS (2015) | Region VII | Cebu | 303090 | Samboan National High School | SAMBOAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00050 | 15HG0076 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-26 | 2015-08-27 | RUDPA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 303089 | San Sebastian NHS | SAMBOAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8244965.051 |  |  | COMPLETED | 1 |  |  | 070215S00051 | 15HG0077 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-26 | 2015-08-27 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 303095 | Santa Filomena NHS | ALEGRIA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070215S00052 | 15HG0081 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-08-11 | 2015-08-12 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
NC 2015 | K10 (2015) | Region VII | Cebu | 303098 | Santander NHS | SANTANDER | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00304 | 15HG0115 | 2015-06-25 | 2015-06-25 | 2015-07-08 | 2015-08-26 | 2015-08-27 | DT&C CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 303058 | Sorsogon NHS | MALABUYOC | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00302 | 15HG0098 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-07-22 | 2015-07-23 | QUIRANTE CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 303112 | Talaga NHS | ARGAO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00029 | 15HG0073 | 2015-06-10 | 2015-06-11 | 2015-06-25 | 2015-07-20 | 2015-07-22 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu | 312454 | Tan-awan NHS | OSLOB | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6369337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 302952 | Tubod Dugoan NHS | DUMANJUG | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00046 | 15HG0070 | 2015-06-10 | 2015-06-11 | 2015-06-24 | 2015-07-20 | 2015-07-22 | PRAGMATIC DEVELOPMENT & CONSTRUCTION CORP.
NC 2015 | SHS (2015) | Region VII | Cebu | 302923 | Tubod NHS | BADIAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 119540 | Tumalog ES | OSLOB | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00292 | 15HG0114 | 2015-06-25 | 2015-06-25 | 2015-07-08 | 2015-07-20 | 2015-07-22 | DT&C CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 303123 | Usmad NHS | ARGAO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00021 | 15HG0062 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-08-26 | 2015-08-27 | GEMSTRONG CONSTRUCTION, INC.
NC 2015 | SHS (2015) | Region VII | Cebu | 312455 | Willy B. Wenceslao MNHS | SANTANDER | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6339337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 119030 | Abucayan ES | BALAMBAN | 3 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22102343.62 |  |  | COMPLETED | 1 |  |  | 070215S00497 | 15HF0105 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | J.A.R.C. CONSTRUCTION COMPANY
NC 2015 | SHS (2015) | Region VII | Cebu | 302919 | Aloguinsan NHS | ALOGUINSAN | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10567131.51 |  |  | COMPLETED | 1 |  |  | 070215S00374 | 15HF0092 | 2015-07-28 | 2015-07-29 | 2015-08-10 | 2015-08-14 | 2015-08-20 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2015 | SHS (2015) | Region VII | Cebu | 302920 | Angilan NHS | ALOGUINSAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8564965.051 |  |  | COMPLETED | 1 |  |  | 070215S00376 | 15HF0081 | 2015-07-22 | 2015-07-23 | 2015-08-04 | 2015-08-10 | 2015-08-14 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu | 303077 | Anislag NHS | ` | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6619337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00020 | 15HF0050 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-07-02 | 2015-07-09 | FIRST BUILDERS AND DEVELOPERS
NC 2015 | SHS (2015) | Region VII | Cebu | 303076 | Anopog NHS | PINAMUNGAHAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1 |  |  | 070215S00030 | 15HF0069 | 2015-06-26 | 2015-06-26 | 2015-07-08 | 2015-07-14 | 2015-07-17 | FIRST BUILDERS AND DEVELOPERS
NC 2015 | K10 (2015) | Region VII | Cebu | 118967 | Bago ES | ASTURIAS | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00492 | 15HF0108 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu | 302928 | Balao NHS | BARILI | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070215S00031 | 15HF0053 | 2015-06-16 | 2015-06-17 | 2015-06-30 | 2015-07-03 | 2015-07-10 | HI-TRI DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region VII | Cebu | 119073 | Barili I Central ES | BARILI | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6189337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00498 | 15HF0111 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | FIRST BUILDERS AND DEVELOPERS
NC 2015 | SHS (2015) | Region VII | Cebu | 303069 | Bartolome & Manuela Pañares MNHS | BARILI | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 302945 | Buanoy NHS | BALAMBAN | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14997518.84 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Cebu | 302945 | Buanoy NHS | BALAMBAN | 3 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 302950 | BUANOY NHS-EVENING OPPORTUNITY CLASS | BALAMBAN | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 302946 | Cabagdalan National High School | BALAMBAN | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6669337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00034 | 15HF0064 | 2015-06-26 | 2015-06-26 | 2015-07-08 | 2015-07-14 | 2015-07-17 | LA PRUEBA CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Cebu | 187012 | Cabiangon PS | PINAMUNGAHAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 070215S00521 | 15HF0112 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | WERR CORPORATION INTERNATIONAL
NC 2015 | SHS (2015) | Region VII | Cebu | 303071 | Cagay NHS | BARILI | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6339337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 302987 | Colonia NHS | TUBURAN | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10567131.51 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 118972 | Cubong Elementary School | ASTURIAS | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00466 | 15HF0106 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | J.A.R.C. CONSTRUCTION COMPANY
NC 2015 | K10 (2015) | Region VII | Cebu | 119559 | Duangan ES | PINAMUNGAHAN | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00509 | 15HF0110 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | BL PANGAN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 303045 | Federico & Soledad MNHS | BARILI | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 119042 | Gaas Elementary School | BALAMBAN | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00391 | 15HF0080 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-09-25 | 2015-10-01 | J.A.R.C. CONSTRUCTION COMPANY
NC 2015 | K10 (2015) | Region VII | Cebu | 302947 | Gaas NHS | BALAMBAN | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00385 | 15HF0080 | [5 empty] | J.A.R.C. CONSTRUCTION COMPANY
NC 2015 | SHS (2015) | Region VII | Cebu | 303012 | Giloctog NHS | BARILI | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6719337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00082 | 15HF0072 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-20 | 2015-07-24 | J.A.R.C. CONSTRUCTION COMPANY
NC 2015 | SHS (2015) | Region VII | Cebu | 312415 | Ginatilan NHS | BALAMBAN | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00080 | 15HF0047 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-07-02 | 2015-07-09 | WTG CONSTRUCTION & DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VII | Cebu | 303070 | Guibuangan NHS | BARILI | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00053 | 15HF0056 | 2015-06-16 | 2015-06-17 | 2015-06-30 | 2015-07-03 | 2015-07-10 | DUROS DEVELOPMENT CORP.
NC 2015 | K10 (2015) | Region VII | Cebu | 118974 | Guinabasan ES | ASTURIAS | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 070215S00523 | 15HF0102 | 2015-08-24 | 2015-08-25 | 2015-09-07 | 2015-10-20 | 2015-10-23 | MAP ALVIOLA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 312451 | Ireneo V. Diamante NHS | TUBURAN | 3 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2880828.124 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 119094 | Japitan ES | BARILI | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00465 | 15HF0111 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | FIRST BUILDERS AND DEVELOPERS
NC 2015 | SHS (2015) | Region VII | Cebu | 312404 | Jose Chona Jo Memorial National High School | BALAMBAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070215S00076 | 15HF0048 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-07-02 | 2015-07-09 | LA PRUEBA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 312453 | Kalangahan NHS | TUBURAN | 3 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2940828.124 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 118908 | Kandingan Elementary | ALOGUINSAN | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6339337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00473 | 15HF0112 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | WERR CORPORATION INTERNATIONAL
NC 2015 | SHS (2015) | Region VII | Cebu | 312452 | Kansi NHS | TUBURAN | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00057 | 15HF0043 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-07-02 | 2015-07-09 | QUIRANTE CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 303029 | Lamac NHS | PINAMUNGAHAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 312470 | Lamak National High School | BARILI | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2008606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 312470 | Lamak National High School | BARILI | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 302948 | Lamesa NHS | BALAMBAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 070215S00367 | 15HF0082 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-02 | 2015-09-08 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu | 312468 | Liki Integrated School | BALAMBAN | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00058 | 15HF0048 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-07-02 | 2015-07-09 | LA PRUEBA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 303044 | Looc Norte NHS | ASTURIAS | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070215S00079 | 15HF0044 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-07-02 | 2015-07-09 | QUIRANTE CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Cebu | 118980 | Lunas I ES | ASTURIAS | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 070215S00522 | 15HF0106 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | J.A.R.C. CONSTRUCTION COMPANY
NC 2015 | K10 (2015) | Region VII | Cebu | 119097 | Malolos ES | BARILI | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00388 | 15HF0087 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-02 | 2015-09-08 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu | 303050 | Malolos NHS | BARILI | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00090 | 15HF0066 | 2015-06-26 | 2015-06-26 | 2015-07-08 | 2015-07-14 | 2015-07-17 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu | 312418 | Manguiao NHS | ASTURIAS | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6619337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 303052 | Mantalongon NHS | BARILI | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00073 | 15HF0067 | 2015-06-26 | 2015-06-26 | 2015-07-08 | 2015-07-14 | 2015-07-17 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VII | Cebu | 119848 | Marmol ES | TUBURAN | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00463 | 15HF0109 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu | 312429 | Milan-Cantuod NHS | BALAMBAN | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00083 | 15HF0070 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-20 | 2015-07-24 | LA PRUEBA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 303059 | Montealegre NHS | TUBURAN | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6549337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00084 | 15HF0042 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-07-02 | 2015-07-09 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu | 302949 | Nangka NHS | BALAMBAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 303068 | Patupat NHS | BARILI | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 303075 | Pinamungajan NHS | PINAMUNGAHAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 303060 | Putat NHS | TUBURAN | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 3102592.44 |  |  | COMPLETED | 1 |  |  | 070215S00375 | 15HF0084 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-02 | 2015-09-08 | MAP ALVIOLA CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Cebu | 119568 | Rizal ES | PINAMUNGAHAN | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00464 | 15HF0110 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | BL PANGAN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 303083 | Rosario NHS | ALOGUINSAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 303097 | Santa Lucia NHS | ASTURIAS | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 070215S00089 | 15HF0046 | 2015-06-15 | 2015-06-16 | 2015-06-29 | 2015-07-02 | 2015-07-09 | QUIRANTE CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Cebu | 119822 | Siotes PS | TUBURAN | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6569337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00457 | 15HF0109 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VII | Cebu | 118988 | Sta. Lucia ES | ASTURIAS | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00468 | 15HF0107 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-10-20 | 2015-10-23 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu | 312414 | Sta. Rita NHS | ASTURIAS | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8444965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 303013 | TEOTIMO A. ABELLANA SR. MEMORIAL NATIONAL HIGH SCHOOL | BARILI | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00064 | 15HF0058 | 2015-06-16 | 2015-06-17 | 2015-06-30 | 2015-07-03 | 2015-07-10 | DUROS DEVELOPMENT CORP.
NC 2015 | SHS (2015) | Region VII | Cebu | 303061 | Tuburan National High School | TUBURAN | 3 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10927342.5917 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Cebu | 303061 | Tuburan National High School | TUBURAN | 3 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4829098.54 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 119029 | Vito ES | BALAMBAN | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00390 | 15HF0090 | 2015-07-28 | 2015-07-29 | 2015-08-10 | 2015-08-14 | 2015-08-20 | OPELL CONSTRUCTION AND DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region VII | Cebu | 303025 | Almacen-Torrevillas National High School | MEDELLIN | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00411 | 15HD0104 | 2015-11-11 | 2015-11-25 | 2015-11-26 | 2015-12-05 | 2015-12-17 | J.A.R.C. CONSTRUCTION COMPANY
NC 2015 | K10 (2015) | Region VII | Cebu | 119670 | Anapog ES | SAN REMIGIO | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00462 | 15HD0098 | 2015-10-14 | 2015-10-26 | 2015-10-27 | 2015-11-03 | 2015-11-10 | BANTAY CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 500220 | Anapog Integrated School | SAN REMIGIO | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 500219 | Argawanon Integrated School | SAN REMIGIO | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6469337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 119671 | Bagtik ES | SAN REMIGIO | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00461 | 15HD0099 | 2015-10-14 | 2015-10-26 | 2015-10-27 | 2015-11-03 | 2015-11-10 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
NC 2015 | SHS (2015) | Region VII | Cebu | 302924 | Bakhawan NHS | DAANBANTAYAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8324965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 119660 | Bancasan ES | SAN REMIGIO | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00470 | 15HD0097 | 2015-10-14 | 2015-10-27 | 2015-10-27 | 2015-11-03 | 2015-11-10 | BANTAY CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 302938 | Bantayan NHS | BANTAYAN | 4 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15927518.84 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 312421 | Bantayan Science High School | BANTAYAN | 4 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2920828.124 |  |  | COMPLETED | 1 |  |  | 070215S00061 | 15HD0063 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-08-05 | 2015-08-12 | ROVILLA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 302939 | Bateria NHS | DAANBANTAYAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 312464 | Bunakan Integrated School | MADRIDEJOS | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6839337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00364 | 15HD0086 | 2015-10-06 | 2015-10-19 | 2015-10-19 | 2015-10-22 | 2015-10-30 | GONZALODO ENTERPRISES
NC 2015 | SHS (2015) | Region VII | Cebu | 500221 | Busogon Integrated School | SAN REMIGIO | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00239 | 15HD0056 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-08-05 | 2015-08-12 | GOLDFIN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 312442 | Calambua Integrated School | SAN REMIGIO | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00231 | 15HD0056 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-08-05 | 2015-08-12 | GOLDFIN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 302961 | Calape NHS | DAANBANTAYAN | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10497131.51 |  |  | COMPLETED | 1 |  |  | 070215S00063 | 15HD0071 | 2015-10-06 | 2015-10-19 | 2015-10-19 | 2015-10-22 | 2015-10-30 | FIRST BUILDERS AND DEVELOPERS
NC 2015 | SHS (2015) | Region VII | Cebu | 302976 | Carnaza NHS | DAANBANTAYAN | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6839337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00055 | 15HD0054 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-07-30 | 2015-08-07 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 303026 | Curva NHS | MEDELLIN | 4 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 8 | 15371327.92 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 302995 | Daanbantayan NHS | DAANBANTAYAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Cebu | 302995 | Daanbantayan NHS | DAANBANTAYAN | 4 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 119458 | Daanlungsod ES | MEDELLIN | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00384 | 15HD0074 | 2015-08-05 | 2015-08-17 | 2015-08-17 | 2015-08-22 | 2015-08-24 | ROVILLA CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Cebu | 119750 | Daantabogon ES | TABOGON | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00455 | 15HD0101 | 2015-10-14 | 2015-10-26 | 2015-10-27 | 2015-11-03 | 2015-11-10 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
NC 2015 | SHS (2015) | Region VII | Cebu | 312408 | Daantabogon NHS | TABOGON | 4 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2710828.124 |  |  | COMPLETED | 1 |  |  | 070215S00066 | 15HD0039 | 2015-07-14 | 2015-07-27 | 2015-07-28 | 2015-08-05 | 2015-08-12 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2015 | SHS (2015) | Region VII | Cebu | 303001 | Dapdap NHS, San Remigio | SAN REMIGIO | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6569337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00067 | 15HD0057 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-07-30 | 2015-08-07 | GONZALODO ENTERPRISES
NC 2015 | SHS (2015) | Region VII | Cebu | 303005 | Do¤a Liling Neis Negapatan MNHS | TABOGON | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00068 | 15HD0040 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-07-30 | 2015-08-07 | GONZALODO ENTERPRISES
NC 2015 | SHS (2015) | Region VII | Cebu | 303003 | Don Esteban Nolasco Memorial NHS | TABOGON | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00224 | 15HD0039 | 2015-07-14 | 2015-07-27 | 2015-07-28 | 2015-08-05 | 2015-08-12 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2015 | SHS (2015) | Region VII | Cebu | 303007 | Doong NHS | BANTAYAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 9044965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 312458 | Gibitngil Integrated School | MEDELLIN | 4 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2870828.124 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 312420 | Hilantagaan NHS Ext. | SANTA FE | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 9074965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 312456 | Hilotongan Integrated School | BANTAYAN | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 303004 | Horacio Franco MNHS | TABOGON | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 312465 | Ilihan Integrated School | TABOGON | 4 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 312465 | Ilihan Integrated School | TABOGON | 4 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 5 | 15171328 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 303021 | Jose R. Martinez | SAN REMIGIO | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00234 | 15HD0056 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-08-05 | 2015-08-12 | GOLDFIN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 303103 | Juan Pamplona NHS | TABUELAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 070215S00274 | 15HD0055 | 2015-08-17 | 2015-09-02 | 2015-09-02 | 2015-09-22 | 2015-09-30 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu | 303023 | Kal-anan NHS | TABOGON | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00275 | 15HD0041 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-07-30 | 2015-08-07 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 303024 | Kawit NHS | MEDELLIN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 070215S00273 | 15HD0044 | 2015-07-14 | 2015-07-28 | 2015-07-28 | 2015-08-05 | 2015-08-12 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2015 | SHS (2015) | Region VII | Cebu | 303028 | Kinartacan NHS | SANTA FE | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 9044965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 312443 | Kinawahan Integrated School | SAN REMIGIO | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00235 | 15HD0056 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-08-05 | 2015-08-12 | GOLDFIN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 312463 | Kodia Integrated School | MADRIDEJOS | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00248 | 15HD0069 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-07-30 | 2015-08-07 | GONZALODO ENTERPRISES
NC 2015 | SHS (2015) | Region VII | Cebu | 303030 | Lambusan NHS | SAN REMIGIO | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 070215S00227 | 15HD0059 | 2015-07-14 | 2015-07-27 | 2015-07-28 | 2015-08-05 | 2015-08-12 | ZION CONSTRUCTION(FORMERLY MASTERPIECE CONST. & SU
NC 2015 | SHS (2015) | Region VII | Cebu | 303041 | Libaong NHS | SAN REMIGIO | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 303043 | Logon NHS | DAANBANTAYAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8734965.051 |  |  | COMPLETED | 1 |  |  | 070215S00246 | 15HD0050 | 2015-07-14 | 2015-07-28 | 2015-07-28 | 2015-08-05 | 2015-08-12 | BANTAY CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Cebu | 119756 | Loong Elementary School | TABOGON | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2538606.04 |  |  | COMPLETED | 1 |  |  | 070215S00520 | 15HD0103 | 2015-10-14 | 2015-10-27 | 2015-10-27 | 2015-11-03 | 2015-11-10 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
NC 2015 | SHS (2015) | Region VII | Cebu | 303006 | Loreto-Remedios Montebon NHS | TABOGON | 4 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2690828.124 |  |  | COMPLETED | 1 |  |  | 070215S00230 | 15HD0038 | 2015-07-14 | 2015-07-28 | 2015-07-28 | 2015-08-05 | 2015-08-12 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2015 | SHS (2015) | Region VII | Cebu | 303046 | Luyang NHS | SAN REMIGIO | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10717131.51 |  |  | COMPLETED | 1 |  |  | 070215S00368 | 15HD0092 | 2015-11-11 | 2015-11-25 | 2015-11-26 | 2015-12-07 | 2015-12-17 | R.U. AQUINO CONSTRUCTION AND DEVELOPMENT CORP. (FO
NC 2015 | SHS (2015) | Region VII | Cebu | 312422 | Mabunao NHS-Juan Pamplona Ext. | TABUELAN | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6569337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00361 | 15HD0088 | 2015-11-11 | 2015-11-25
NC 2015 | SHS (2015) | Region VII | Cebu | 303047 | Madridejos NHS | MADRIDEJOS | 4 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 16171327.92 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Cebu | 303047 | Madridejos NHS | MADRIDEJOS | 4 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 302962 | Malingin NHS | DAANBANTAYAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1 |  |  | 070215S00232 | 15HD0051 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-07-30 | 2015-08-07 | BANTAY CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 312445 | Marikaban Integrated School | SANTA FE | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6839337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 303053 | Maya NHS | DAANBANTAYAN | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10467131.51 |  |  | COMPLETED | 1 |  |  | 070215S00254 | 15HD0072 | 2015-10-06 | 2015-10-19 | 2015-10-19 | 2015-10-22 | 2015-10-30 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 303054 | Medellin National High School | MEDELLIN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00252 | 15HD0045 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-07-30 | 2015-08-07 | GONZALODO ENTERPRISES
NC 2015 | SHS (2015) | Region VII | Cebu | 303027 | Medellin National Science and Technology School | MEDELLIN | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00241 | 15HD0043 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-07-30 | 2015-08-07 | FIRST BUILDERS AND DEVELOPERS
NC 2015 | SHS (2015) | Region VII | Cebu | 312438 | Oboob Integrated School | BANTAYAN | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00236 | 15HD0063 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-08-05 | 2015-08-12 | ROVILLA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 312409 | Patao NHS | BANTAYAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8944965.051 |  |  | COMPLETED | 1 |  |  | 070215S00242 | 15HD0065 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-08-05 | 2015-08-12 | ROVILLA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 302963 | Paypay NHS | DAANBANTAYAN | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00243 | 15HD0046 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-08-05 | 2015-08-12 | R.U. AQUINO CONSTRUCTION AND DEVELOPMENT CORP. (FO
NC 2015 | SHS (2015) | Region VII | Cebu | 312430 | Salag NHS | TABOGON | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00237 | 15HD0038 | 2015-07-14 | 2015-07-28 | 2015-07-28 | 2015-08-05 | 2015-08-12 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2015 | SHS (2015) | Region VII | Cebu | 303048 | San Agustin NHS | MADRIDEJOS | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8964965.051 |  |  | COMPLETED | 1 |  |  | 070215S00244 | 15HD0068 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-07-30 | 2015-08-07 | GONZALODO ENTERPRISES
NC 2015 | K10 (2015) | Region VII | Cebu | 119762 | San Isidro Elementary School | TABOGON | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00451 | 15HD0101 | 2015-10-14 | 2015-10-26 | 2015-10-27 | 2015-11-03 | 2015-11-10 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
NC 2015 | SHS (2015) | Region VII | Cebu | 303086 | San Miguel NHS | SAN REMIGIO | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10767131.51 |  |  | COMPLETED | 1 |  |  | 070215S00355 | 15HD0094 | 2015-11-11 | 2015-11-25
NC 2015 | SHS (2015) | Region VII | Cebu | 303087 | San Remegio NHS | SAN REMIGIO | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00245 | 15HD0060 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-07-30 | 2015-08-07 | GONZALODO ENTERPRISES
NC 2015 | SHS (2015) | Region VII | Cebu | 303094 | Santa Fe NHS | SANTA FE | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 11337131.51 |  |  | COMPLETED | 1 |  |  | 070215S00255 | 15HD0073 | 2015-10-14 | 2015-10-27 | 2015-10-27 | 2015-11-03 | 2015-11-10 | ROVILLA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 119069 | Sillon ES | BANTAYAN | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6869337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 302996 | SK Luis P. Canete NHS | DAANBANTAYAN | 4 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2690828.124 |  |  | COMPLETED | 1 |  |  | 070215S00240 | 15HD0046 | 2015-07-14 | 2015-07-28 | 2015-07-28 | 2015-08-05 | 2015-08-12 | R.U. AQUINO CONSTRUCTION AND DEVELOPMENT CORP. (FO
NC 2015 | SHS (2015) | Region VII | Cebu | 119057 | Sulangan ES | BANTAYAN | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6844337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00249 | 15HD0067 | 2015-06-22 | 2015-07-03 | 2015-07-03 | 2015-07-30 | 2015-08-07 | ROVILLA CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Cebu | 119766 | Tabogon Central ES | TABOGON | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00416 | 15HD0075 | 2015-08-05 | 2015-08-17 | 2015-08-17 | 2015-08-21 | 2015-08-24 | ROVILLA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 312444 | Tambongon Integrated School | SAN REMIGIO | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00337 | 15HD0089 | 2015-10-06 | 2015-10-19 | 2015-10-19 | 2015-10-22 | 2015-10-30 | GOLDFIN CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Cebu | 119070 | Tamiao ES | BANTAYAN | 4 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 3 | 12771310.093 |  |  | COMPLETED | 1 |  |  | 070215S00386 | 15HD0091 | 2015-10-14 | 2015-10-27 | 2015-10-27 | 2015-11-03 | 2015-11-10 | ROVILLA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 302964 | Tapilon National High School | DAANBANTAYAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 302965 | Tominjao National High School | DAANBANTAYAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8324965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 312407 | Arcelo Memorial National Night High School | LILOAN | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00313 | 15HI0054 | 2015-07-09 | 2015-07-21 | 2015-07-22 | 2015-07-26 | 2015-08-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 312448 | Bagalnga Integrated School | COMPOSTELA | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 303105 | Bongdo NHS | BORBON | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6389337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 119211 | Bongyas Elementary | CATMON | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00428 | 15HI0057 | 2015-07-10 | 2015-07-22 | 2015-07-23 | 2015-07-27 | 2015-08-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 303106 | Borbon NHS | BORBON | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00267 | 15HI0040 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | FIRST GRANDEUR BUILDERS
NC 2015 | K10 (2015) | Region VII | Cebu | 119225 | Cabadiangan ES | COMPOSTELA | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6244337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00454 | 15HI0077 | 2015-08-23 | 2015-09-04 | 2015-09-05 | 2015-09-09 | 2015-09-13 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 302974 | Cabalawan NHS | SOGOD | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1 |  |  | 070215S00276 | 15HI0035 | 2015-11-29
NC 2015 | SHS (2015) | Region VII | Cebu | 302968 | Cabonga-an NHS | SAN FRANCISCO | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8964965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 119212 | Cabunga-an ES | CATMON | 5 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00429 | 15HI0056 | 2015-07-10 | 2015-07-22 | 2015-07-23 | 2015-07-27 | 2015-08-20 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2015 | K10 (2015) | Region VII | Cebu | 119410 | Calero ES | LILOAN | 5 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10267131.51 |  |  | COMPLETED | 1 |  |  | 070215S00496 | 15HI0075 | 2015-08-23 | 2015-09-04 | 2015-09-05 | 2015-09-09 | 2015-09-13 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu |  | Calero IS | LILOAN | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6369338 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 302966 | Calumboyan NHS | SOGOD | 5 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | Reverted | 0 |  |  | 070215S00426 | 15HI0058 | [5 empty] | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 302967 | Camotes National High School | SAN FRANCISCO | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8974965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 303107 | Campusong NHS | BORBON | 5 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00259 | 15HI0036 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | FIRST GRANDEUR BUILDERS
NC 2015 | SHS (2015) | Region VII | Cebu | 302975 | Cantumog NHS | CARMEN | 5 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10467131.51 |  |  | COMPLETED | 1 |  |  | 070115S00020 | 15HI0089 | 2015-09-15 | 2015-09-27 | 2015-09-28 | 2015-10-02 | 2015-10-16 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 312410 | Carmen National High School - Night | CARMEN | 5 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | Reverted | 0 |  |  | 070115S00019 | 15HI0031
NC 2015 | SHS (2015) | Region VII | Cebu | 302973 | Carmen NHS-Day | CARMEN | 5 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Cebu | 302973 | Carmen NHS-Day | CARMEN | 5 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 312447 | Catmon Integrated School | CATMON | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 312416 | Caurasan NHS | CARMEN | 5 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070115S00021 | 15HI0030 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | YES CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 302979 | Ceferino Sususco MNHS | CATMON | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6719337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00277 | 15HI0033 | 2015-11-29 | 2015-12-11 | 2015-12-12 | 2015-12-16 | 2015-12-20 | BANTAY CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 303063 | Compostela National High School | COMPOSTELA | 5 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 |  |  | 070215S00271 | 15HI0095 | 2015-08-31 | 2015-09-12 | 2015-09-13 | 2015-09-17 | 2015-09-21 | VEN RAY CONSTRUCTION CORPORATION
NC 2015 | SHS (2015) | Region VII | Cebu | 312406 | Compostela Science & Technology High School | COMPOSTELA | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6389337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00269 | 15HI0028 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | LA PRUEBA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 302994 | Consuelo NHS | SAN FRANCISCO | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8914965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 119644 | Dapdap ES | SAN FRANCISCO | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00431 | 15HI0061 | 2015-07-10 | 2015-07-22 | 2015-07-23 | 2015-07-27 | 2015-08-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 303032 | Dapdap NHS | PILAR | 5 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00290 | 15HI0053 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | FIRST BUILDERS AND DEVELOPERS
NC 2015 | K10 (2015) | Region VII | Cebu | 119189 | Dawis Norte ES | CARMEN | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00452 | 15HI0079 | 2015-08-23 | 2015-09-04 | 2015-09-05 | 2015-09-09 | 2015-09-13 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 303108 | Do¤a Milagros MNHS | BORBON | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070215S00268 | 15HI0041 | 2015-11-29
NC 2015 | SHS (2015) | Region VII | Cebu | 303074 | Don Filomeno M. Torres MNHS | PILAR | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6989337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 303031 | Lanao NHS, Pilar | PILAR | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 7169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00315 | 15HI0063 | 2015-07-09 | 2015-07-21 | 2015-07-22 | 2015-07-26 | 2015-08-20 | FIRST BUILDERS AND DEVELOPERS
NC 2015 | SHS (2015) | Region VII | Cebu | 312428 | Lataban NHS | LILOAN | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00284 | 15HI0027 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
NC 2015 | SHS (2015) | Region VII | Cebu | 303092 | Liloan NHS | LILOAN | 5 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Cebu | 303092 | Liloan NHS | LILOAN | 5 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | Reverted | 0
NC 2015 | SHS (2015) | Region VII | Cebu |  | Liloan NHS EXT Don Bosco | LILOAN | 5 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 303122 | Lorenzo C. Tanza Memorial National High School | SAN FRANCISCO | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8964965.051 |  |  | COMPLETED | 1 |  |  | 070215S00283 | 15HI0045 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 303008 | Luciano B. Rama Sr. MNHS | PORO | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 7049337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00320 | 15HI0062 | 2015-07-09 | 2015-07-21 | 2015-07-22 | 2015-07-26 | 2015-08-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 312423 | Mar and Dorie Darunday NHS | BORBON | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6479337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00256 | 15HI0038 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | ECCON DEVT. CORPORATION (FOR. E. CANEDA CONSTRUCT
NC 2015 | K10 (2015) | Region VII | Cebu | 303110 | Mohon NHS | SOGOD | 5 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00436 | 15HI0059 | 2015-07-10 | 2015-07-22 | 2015-07-23 | 2015-07-27 | 2015-08-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 303062 | Mulao NHS | COMPOSTELA | 5 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10617131.51 |  |  | COMPLETED | 1 |  |  | 070215S00266 | 15HI0086 | 2015-09-15 | 2015-09-27 | 2015-09-28 | 2015-10-02 | 2015-10-16 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 303073 | Pilar NHS | PILAR | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 9044965.051 |  |  | COMPLETED | 1 |  |  | 070215S00280 | 15HI0051 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | FIRST BUILDERS AND DEVELOPERS
NC 2015 | K10 (2015) | Region VII | Cebu | 119743 | Poblacion ES | SOGOD | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00434 | 15HI0060 | 2015-07-10 | 2015-07-22 | 2015-07-23 | 2015-07-27 | 2015-08-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 303080 | Puertobello NHS | TUDELA | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8994965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 303081 | Puertobello NHS - Pob. Ext. | TUDELA | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 9024965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Cebu | 119200 | Sac-on ES | CARMEN | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00453 | 15HI0098 | 2015-10-14 | 2015-10-26 | 2015-10-27 | 2015-10-31
NC 2015 | SHS (2015) | Region VII | Cebu | 303085 | San Jose NHS | PORO | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8994965.051 |  |  | COMPLETED | 1 |  |  | 070215S00263 | 15HI0047 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 303100 | Santiago National High School | SAN FRANCISCO | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 9064965.051 |  |  | COMPLETED | 1 |  |  | 070215S00282 | 15HI0050 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 312417 | SAPAK HS | COMPOSTELA | 5 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | Reverted | 0 |  |  | 070215S00257
NC 2015 | SHS (2015) | Region VII | Cebu | 303104 | Tabunan NHS | BORBON | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00261 | 15HI0039 | 2015-06-14 | 2015-06-26 | 2015-06-27 | 2015-07-01 | 2015-07-17 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 302980 | Tinabyonan NHS | CATMON | 5 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00253 | 15HI0032 | 2015-11-29
NC 2015 | K10 (2015) | Region VII | Cebu | 187023 | Tubigan ES | COMPOSTELA | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00430 | 15HI0055 | 2015-07-10 | 2015-07-22 | 2015-07-23 | 2015-07-27 | 2015-08-20 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | K10 (2015) | Region VII | Cebu | 119658 | Union ES | SAN FRANCISCO | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00432 | 15HI0072 | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-08-29 | 2015-09-02 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 303009 | Zosimo E. Fabroa MNHS | PORO | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6889337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu | 302954 | Cabangahan NHS | CONSOLACION | 6 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00163 | 15HN0092 | 2015-08-04 | 2015-08-07 | 2015-08-19 | 2015-08-26 | 2015-09-04 | YES CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 302988 | Consolacion NHS - Day Class | CONSOLACION | 6 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1 |  |  | 070215S00178 | 15HN0093 | 2015-08-04 | 2015-08-07 | 2015-08-19 | 2015-08-26 | 2015-09-04 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Cebu | 302989 | Consolacion NHS - Evening Class | CONSOLACION | 6 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1 |  |  | 070215S00179 | 15HN0094 | 2015-08-04 | 2015-08-07 | 2015-08-19 | 2015-08-26 | 2015-09-04 | GENETIAN BUILDERS
NC 2015 | SHS (2015) | Region VII | Cebu | 302955 | Cordova NHS | CORDOBA | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10617131.51 |  |  | COMPLETED | 1 |  |  | 070215S00180 | 15HN0099 | 2015-08-04 | 2015-08-07 | 2015-08-19 | 2015-08-26 | 2015-09-04 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | K10 (2015) | Region VII | Cebu | 119240 | Garing ES | CONSOLACION | 6 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6189337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00472 | 15HN0130 | 2015-09-22 | 2015-09-29 | 2015-10-13 | 2015-10-19 | 2015-10-29 | P.B. OBIAL CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 303010 | Garing NHS | CONSOLACION | 6 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1 |  |  | 070215S00181 | 15HN0095 | 2015-08-04 | 2015-08-07 | 2015-08-19 | 2015-08-26 | 2015-09-04 | P.B. OBIAL CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Cebu | 119241 | Jugan ES | CONSOLACION | 6 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00460 | 15HN0131 | 2015-09-22 | 2015-09-29 | 2015-10-13 | 2015-10-19 | 2015-10-29 | P.B. OBIAL CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 302990 | Jugan NHS | CONSOLACION | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2008606.04 |  |  | Reverted | 0
NC 2015 | SHS (2015) | Region VII | Cebu | 302990 | Jugan NHS | CONSOLACION | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | Reverted | 0
NC 2015 | K10 (2015) | Region VII | Cebu | 119246 | Panoypoy ES | CONSOLACION | 6 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6259337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00456 | 15HN0132 | 2015-09-22 | 2015-09-29 | 2015-10-13 | 2015-10-19 | 2015-10-29 | PLD CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu | 303114 | Tayud NHS | CONSOLACION | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10467131.51 |  |  | COMPLETED | 1 |  |  | 070215S00182 | 15HN0096 | 2015-08-04 | 2015-08-07 | 2015-08-19 | 2015-08-26 | 2015-09-04 | GONZALODO ENTERPRISES
NC 2015 | SHS (2015) | Region VII | Cebu | 302992 | Tolotolo NHS | CONSOLACION | 6 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2872592.44 |  |  | COMPLETED | 1 |  |  | 070215S00311 | 15HN0100 | 2015-08-26 | 2015-09-03 | 2015-09-15 | 2015-09-23 | 2015-10-02 | MANINGO ENTERPRISES
NC 2015 | SHS (2015) | Region VII | Cebu | 302993 | Tugbongan NHS | CONSOLACION | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00192 | 15HN0080 | 2015-07-07 | 2015-07-10 | 2015-07-23 | 2015-07-29 | 2015-08-07 | GONZALODO ENTERPRISES
NC 2015 | SHS (2015) | Region VII | Cebu City | 303128 | Abellana NHS (Day & NIght) | CEBU CITY (Capital) | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | COMPLETED | 1 |  |  | 070215S00449 | 15HH0099 | 2015-09-22 | 2015-09-10 | 2015-09-22
NC 2015 | SHS (2015) | Region VII | Cebu City | 303129 | Adlaon NHS | CEBU CITY (Capital) | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10917131.51 |  |  | COMPLETED | 1 |  |  | 070215S00317 | 15HH0064 | 2015-07-29 | 2015-07-10 | 2015-07-29 | 2015-09-22 | 2015-10-10 | CHARLZ CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | CEBU CITY | 303130 | Agsungot NHS . | CEBU CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00184 | 15HH0035 | 2015-07-03 | 2015-06-22 | 2015-07-03 | 2015-09-07 | 2015-09-18 | GOLDFIN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu City | 312503 | Banilad Night HS | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15197518.84 |  |  | COMPLETED | 1 |  |  | 070215S00177 | 15HH0071 | 2015-08-26 | 2015-08-14 | 2015-08-26 | 2015-09-16 | 2015-09-18 | CPR CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu City | 303152 | Barrio Luz NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15197518.84 |  |  | COMPLETED | 1 |  |  | 070215S00186 | 15HH0072 | 2015-08-26 | 2015-08-14 | 2015-08-26 | 2015-09-22 | 2015-10-26 | GONZALODO ENTERPRISES
NC 2015 | SHS (2015) | Region VII | CEBU CITY | 303131 | Binaliw NHS | CEBU CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00187 | 15HH0054 | 2015-08-19 | 2015-08-07 | 2015-08-19 | 2015-09-01 | 2015-09-14 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu City | 303134 | Bonbon NHS | CEBU CITY (Capital) | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10767131.51 |  |  | COMPLETED | 1 |  |  | 070215S00356 | 15HH0065 | 2015-08-24 | 2015-08-12 | 2015-08-24 | 2015-09-07 | 2015-09-18 | GOWIL BUILDERS
NC 2015 | SHS (2015) | Region VII | Cebu City | 303136 | Busay NHS | CEBU CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6819337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00189 | 15HH0057 | 2015-08-19 | 2015-08-07 | 2015-08-19 | 2015-09-01 | 2015-09-18 | RAMIJO CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu City | 303138 | Camp Lapu-Lapu NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 15197518.84 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Cebu City | 303138 | Camp Lapu-Lapu NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | Reverted | 0
NC 2015 | SHS (2015) | Region VII | Cebu City | 303142 | Don Carlos Gothong Memorial NHS | CEBU CITY (Capital) | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 2 | 31402890.27 |  |  | COMPLETED | 1 |  |  | 070215S00334 | 15HH0091 | 2015-09-14 | 2015-09-02 | 2015-09-14 | 2015-10-14 | 2015-10-29 | PLD CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu City | 303133 | Don Vicente Rama Mem. NHS (Basak NHS) | CEBU CITY (Capital) | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26902469.42 |  |  | COMPLETED | 1 |  |  | 070215S00340 | 15HH0090 | 2015-09-14 | 2015-09-02 | 2015-09-14 | 2015-10-14 | 2015-10-29 | GOLDFIN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu City | 303157 | Guba NHS | CEBU CITY (Capital) | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10717131.51 |  |  | COMPLETED | 1 |  |  | 070215S00190 | 15HH0069 | 2015-08-26 | 2015-08-14 | 2015-08-26 | 2015-09-16 | 2015-09-18 | CHARLZ CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu City | 303139 | Lahug NHS (Night) | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15197518.84 |  |  | COMPLETED | 1 |  |  | 070215S00162 | 15HH0076 | 2015-08-26 | 2015-08-14 | 2015-08-26 | 2015-09-28 | 2015-10-26 | BLIMEX CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu City | 303132 | Lusaran NHS | CEBU CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6669337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00185 | 15HH0058 | 2015-08-19 | 2015-08-07 | 2015-08-19 | 2015-09-01 | 2015-09-18 | BT CONSTRUCTION AND GENERAL SERVICES
NC 2015 | K10 (2015) | Region VII | Cebu City | 500044 | Mabini Integrated School | CEBU CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00437 | 15HH0045 | 2015-07-29 | 2015-07-10 | 2015-07-29 | 2015-09-07 | 2015-10-26 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | CEBU CITY | 500044 | Mabini Integrated School | CEBU CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00183 | 15HH0036 | 2015-07-03 | 2015-06-22 | 2015-07-03 | 2015-09-07 | 2015-09-18 | GOLDFIN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu City | 303151 | MABOLO NATIONAL HIGH SCHOOL | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15097518.84 |  |  | COMPLETED | 1 |  |  | 070215S00175 | 15HH0077 | 2015-08-26 | 2015-08-14 | 2015-08-26 | 2015-09-16 | 2015-10-02 | PLD CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Cebu City | 500230 | Malubog Integrated School | CEBU CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | reverted | 0 |  |  | 070215S00459
NC 2015 | SHS (2015) | Region VII | Cebu City | 303146 | Mambaling NHS (Night) | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 15197518.84 |  |  | COMPLETED | 1 |  |  | 070215S00339 | 15HH0086 | 2015-08-28 | 2015-08-14 | 2015-08-28 | 2015-09-07 | 2015-09-18 | GOLDFIN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu City | 303159 | Pardo NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 15147518.84 |  |  | COMPLETED | 1 |  |  | 070215S00344 | 15HH0087 | 2015-08-28 | 2015-08-14 | 2015-08-28 | 2015-09-28 | 2015-10-26 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2015 | SHS (2015) | Region VII | CEBU CITY | 303137 | Paril NHS | CEBU CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00174 | 15HH0037 | 2015-07-03 | 2015-06-22 | 2015-07-03 | 2015-09-07 | 2015-09-18 | GOLDFIN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu City | 303160 | Pit-os NHS | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 15197518.84 |  |  | COMPLETED | 1 |  |  | 070215S00316 | 15HH0074 | 2015-08-26 | 2015-08-14 | 2015-08-26 | 2015-09-24 | 2015-10-05 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu City | 312515 | Quiot High School | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 15347518.84 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu City | 303161 | Ramon Duterte Memorial NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 2 | 31402890.27 |  |  | COMPLETED | 1 |  |  | 070215S00327 | 15HH0092 | 2015-09-14 | 2015-09-02 | 2015-09-14 | 2015-10-14 | 2015-10-19 | GOLDFIN CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Cebu City | 119930 | Regino Mercado ES | CEBU CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | reverted | 0 |  |  | 070215S00467
NC 2015 | SHS (2015) | Region VII | Cebu City |  | SHS within Agsungot ES | CEBU CITY (Capital) | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 5 | 10877343 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | CEBU CITY | 500222 | Sirao Integrated School | CEBU CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00173 | 15HH0055 | 2015-08-19 | 2015-08-07 | 2015-08-19 | 2015-09-01 | 2015-09-11 | REBECCA NAJEEBA CONSTRUCTION & DEVELOPMENT
NC 2015 | SHS (2015) | Region VII | Cebu City | 303140 | Talamban NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15197518.84 |  |  | Reverted | 0
NC 2015 | SHS (2015) | Region VII | Cebu City | 303140 | Talamban NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 16 | 4STY16CL | 2015 ADDITIONAL FUND BATCH 9 | 11354950.58 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | CEBU CITY | 500227 | Taptap IS | CEBU CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00171 | 15HH0056 | 2015-08-19 | 2015-08-07 | 2015-08-19 | 2015-09-01 | 2015-09-11 | REBECCA NAJEEBA CONSTRUCTION & DEVELOPMENT
NC 2015 | SHS (2015) | Region VII | Cebu City | 303155 | Tejero NHS (Night) | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15097518.84 |  |  | Reverted | 0
NC 2015 | SHS (2015) | Region VII | Cebu City | 303155 | Tejero NHS (Night) | CEBU CITY (Capital) | 1 | 1 | 20 | 4STY20CL | 2015 ADDITIONAL FUND BATCH 9 | 15855371.43 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu City | 303165 | Vicente Cosido NHS (Cambinocot NHS) | CEBU CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6519337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00335 | 15HH0047 | 2015-07-29 | 2015-07-10 | 2015-07-29 | 2015-08-12 | 2015-09-14 | BT CONSTRUCTION AND GENERAL SERVICES
NC 2015 | SHS (2015) | Region VII | Cebu City | 303156 | Zapatera NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 11177342.5917 |  |  | COMPLETED | 1 |  |  | 070215S00312 | 15HH0049 | 2015-07-22 | 2015-07-10 | 2015-07-22 | 2015-08-12 | 2015-08-24 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu City | 312513 | ALASKA HS | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15097518.84 |  |  | COMPLETED | 1 |  |  | 070215S00170 | 15HH0079 | 2015-08-28 | 2015-08-14 | 2015-08-28 | 2015-09-07 | 2015-09-18 | GOLDFIN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | CEBU CITY | 312502 | Babag HS | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00251 | 15HH0051 | 2015-08-19 | 2015-08-07 | 2015-08-19 | 2015-09-01 | 2015-09-18 | JJ & JM CONSTRUCTION & GENERAL SERVICES (FORMERLY
NC 2015 | K10 (2015) | Region VII | Cebu City | 119867 | Bitlang ES | CEBU CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00440 | 15HH0044 | 2015-07-29 | 2015-07-10 | 2015-07-29 | 2015-08-10 | 2015-08-26 | RIKDA CONSTRUCTION & DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VII | CEBU CITY | 312509 | Bitlang National High School | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00168 | 15HH0038 | 2015-07-03 | 2015-06-22 | 2015-07-03 | 2015-07-20 | 2015-07-28 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu City | 303143 | Bulacao Community HS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15147518.84 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | CEBU CITY | 500229 | Cantipla IS | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00166 | 15HH0039 | 2015-07-03 | 2015-06-22 | 2015-07-03 | 2015-07-20 | 2015-07-28 | CEBU HAYDTER CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu City | 303141 | Cebu City National Science HS | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15097518.84 |  |  | COMPLETED | 1 |  |  | 070215S00165 | 15HH0081 | 2015-08-28 | 2015-08-14 | 2015-08-28 | 2015-09-07 | 2015-09-18 | SB & T CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu City | 303150 | Don Sergio Osme¤a, Sr. Memorial HS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15147518.84 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Cebu City | 303150 | Don Sergio Osme¤a, Sr. Memorial HS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2679549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | CEBU CITY | 312504 | Dr. Emilio Osmena HS | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00207 | 15HH0052 | 2015-08-19 | 2015-08-07 | 2015-08-19 | 2015-09-04 | 2015-09-14 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | CEBU CITY | 303144 | First High School for the Hearing Impaired | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00176 | 15HH0040 | 2015-07-03 | 2015-06-22 | 2015-07-03 | 2015-07-20 | 2015-07-28 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VII | Cebu City | 119907 | Inayawan ES | CEBU CITY (Capital) | 2 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 6 | 26552469.42 |  |  | COMPLETED | 1 |  |  | 070215S00481 | 15HH0100 | 2015-09-22 | 2015-09-10 | 2015-09-22 | 2015-10-22 |  | WTG CONSTRUCTION & DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VII | Cebu City | 303145 | Inayawan NHS (Night) | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15197518.84 |  |  | COMPLETED | 1 |  |  | 070215S00191 | 15HH0083 | 2015-08-28 | 2015-08-14 | 2015-08-28 | 2015-09-28 | 2015-10-26 | GOWIL BUILDERS
NC 2015 | K10 (2015) | Region VII | Cebu City | 119881 | Kalunasan ES | CEBU CITY (Capital) | 2 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 6 | 14971327.92 |  |  | COMPLETED | 1 |  |  | 070215S00458 | 15HH0097 | 2015-09-22 | 2015-09-10 | 2015-09-22 | 2015-10-22
NC 2015 | SHS (2015) | Region VII | Cebu City | 303162 | OPRRA NHS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10867131.51 |  |  | COMPLETED | 1 |  |  | 070215S00209 | 15HH0067 | 2015-08-24 | 2015-08-12 | 2015-08-24 | 2015-09-04 | 2015-09-18 | SERCHER DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VII | CEBU CITY | 312507 | Pamutan IS | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00210 | 15HH0041 | 2015-07-03 | 2015-06-22 | 2015-07-03 | 2015-07-20 | 2015-07-28 | JJ & JM CONSTRUCTION & GENERAL SERVICES (FORMERLY
NC 2015 | K10 (2015) | Region VII | Cebu City | 119914 | Pasil ES | CEBU CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00438 | 15HH0048 | 2015-07-29 | 2015-07-10 | 2015-07-29 | 2015-08-10 | 2015-08-20 | SB & T CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Cebu City | 303147 | Pasil NHS (Night) | CEBU CITY (Capital) | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10667131.51 |  |  | Reverted | 0
NC 2015 | SHS (2015) | Region VII | Cebu City | 303147 | Pasil NHS (Night) | CEBU CITY (Capital) | 2 | 1 | 12 | 3STY12CL | 2015 ADDITIONAL FUND BATCH 9 | 7405137.28 |  |  | COMPLETED | 1 | [10 empty] | Slow pacing of works
NC 2015 | SHS (2015) | Region VII | Cebu City | 303148 | Punta Princesa NHS (Night) | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15147518.84 |  |  | COMPLETED | 1 |  |  | 070215S00212 | 15HH0084 | 2015-08-28 | 2015-08-14 | 2015-08-28 | 2015-09-28 | 2015-10-26 | JJ & JM CONSTRUCTION & GENERAL SERVICES (FORMERLY
NC 2015 | K10 (2015) | Region VII | Cebu City | 187501 | Quiot ES | CEBU CITY (Capital) | 2 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | COMPLETED | 1 |  |  | 070215S00489 | 15HH0098 | 2015-09-22 | 2015-09-10 | 2015-09-22 | 2015-10-22
NC 2015 | TECHVOC (2015) | Region VII | Cebu City | 312515 | Quiot High School | CEBU CITY (Capital) | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | reverted | 0
NC 2015 | SHS (2015) | Region VII | Cebu City | 344024 | SHS in Bonbon, Cebu City | CEBU CITY (Capital) | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10417132 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | CEBU CITY | 312516 | SIBUGAY HS | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00213 | 15HH0053 | 2015-07-30 | 2015-08-07 | 2015-08-12 | 2015-08-16 | 2015-08-20
NC 2015 | SHS (2015) | Region VII | CEBU CITY | 303163 | Sinsin NHS | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00223 | 15HH0042 | 2015-07-03 | 2015-06-22 | 2015-07-03 | 2015-07-20 | 2015-07-28 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu City | 303164 | Sudlon NHS | CEBU CITY (Capital) | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10717131.51 |  |  | COMPLETED | 1 |  |  | 070215S00215 | 15HH0068 | 2015-08-24 | 2015-08-12 | 2015-08-24 | 2015-09-16 | 2015-09-18 | GOWIL BUILDERS
NC 2015 | SHS (2015) | Region VII | CEBU CITY | 500225 | Tabunan Integrated School | CEBU CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Cebu City | 500225 | Tabunan Integrated School | CEBU CITY (Capital) | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Cebu City | 312506 | Tisa HS (Day & Night) (Tisa Night HS) | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 15147518.84 |  |  | COMPLETED | 1 |  |  | 070215S00217 | 15HH0085 | 2015-08-28 | 2015-08-14 | 2015-08-28 | 2015-10-21 | 2015-10-26 | GOLDFIN CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Cebu City | 119871 | Tisa II ES | CEBU CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00439 | 15HH0046 | 2015-07-29 | 2015-07-10 | 2015-07-29 | 2015-08-12 | 2015-08-24 | BLIMEX CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VII | Cebu City | 303149 | Toong NHS (Day) | CEBU CITY (Capital) | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10767131.51 |  |  | COMPLETED | 1 |  |  | 070215S00194 | 15HH0066 | 2015-08-24 | 2015-08-12 | 2015-08-24 | 2015-09-04 | 2015-09-18 | SERCHER DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VII | City of Naga, Cebu | 325301 | Alpaco NHS | CITY OF NAGA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8394965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | City of Naga, Cebu | 119503 | Balirong ES | CITY OF NAGA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | reverted | 0 |  |  | 070215S00441 | 15-HE-0088 | 2015-07-15 | 2015-07-16
NC 2015 | K10 (2015) | Region VII | City of Naga, Cebu | 325309 | Cabuan National High School | CITY OF NAGA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00442 | 15-HE-0089 | 2015-07-15 | 2015-07-16 | 2015-09-15 | 2015-09-21 | 2015-09-28 | MAP ALVIOLA CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | City of Naga, Cebu | 303002 | Don Emilio Canonigo Memorial NHS | CITY OF NAGA | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6349337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00196 | 15-HE-0050 | 2015-06-10 | 2015-06-11 | 2015-06-30 | 2015-07-06 | 2015-07-10 | GENETIAN BUILDERS
NC 2015 | K10 (2015) | Region VII | City of Naga, Cebu | 119506 | Inayagan Elem. School | CITY OF NAGA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00487 | 15-HE-0117 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | MPJR BUILDERS COMPANY
NC 2015 | K10 (2015) | Region VII | City of Naga, Cebu | 187030 | Inoburan ES | CITY OF NAGA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00485 | 15-HE-0119 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | GENETIAN BUILDERS
NC 2015 | K10 (2015) | Region VII | City of Naga, Cebu | 119518 | Langtad ES | CITY OF NAGA | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1 |  |  | 070215S00488 | 15-HE-0116 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | MPJR BUILDERS COMPANY
NC 2015 | K10 (2015) | Region VII | City of Naga, Cebu | 119519 | Lutac ES | CITY OF NAGA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00486 | 15-HE-0118 | 2015-08-23 | 2015-08-24 | 2015-09-07 | 2015-10-13 | 2015-10-19 | GENETIAN BUILDERS
NC 2015 | SHS (2015) | Region VII | City of Naga, Cebu | 303065 | Naga NHS | CITY OF NAGA | 1 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15141327.92 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | City of Naga, Cebu | 303065 | Naga NHS | CITY OF NAGA | 1 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | City of Naga, Cebu | 312437 | Naga SPED Center- High School | CITY OF NAGA | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00199 | 15-HE-0053 | 2015-06-10 | 2015-06-11 | 2015-06-30 | 2015-07-06 | 2015-08-13 | QUIRANTE CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | City of Naga, Cebu | 325303 | Tinaan NHS | CITY OF NAGA | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070215S00200 | 15-HE-0054 | 2015-06-10 | 2015-06-11 | 2015-06-30 | 2015-07-06 | 2015-07-10 | QUIRANTE CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | City of Naga, Cebu | 303120 | Tuyan NHS | CITY OF NAGA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 |  |  | 070215S00197 | 15-HE-0051 | 2015-06-10 | 2015-06-11 | 2015-06-30 | 2015-07-06 | 2015-07-10 | GENETIAN BUILDERS
NC 2015 | SHS (2015) | Region VII | City of Naga, Cebu | 303121 | Uling NHS | CITY OF NAGA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8324965.051 |  |  | COMPLETED | 1 |  |  | 070215S00198 | 15-HE-0052 | 2015-06-10 | 2015-06-11 | 2015-06-30 | 2015-07-06 |  | QUIRANTE CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Danao City | 322007 | Baliang National High School | DANAO CITY | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00414 | 15HI0067 | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-08-29 | 2015-09-02 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | K10 (2015) | Region VII | Danao City | 119360 | Delfin Dawe ES | DANAO CITY | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2118606.04 |  |  | COMPLETED | 1 |  |  | 070215S00483 | 15HI0090 | 2015-09-25 | 2015-10-07 | 2015-10-08 | 2015-10-12 | 2015-10-16 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | K10 (2015) | Region VII | Danao City | 500041 | Eduardo Gorre Memo. Integrated School | DANAO CITY | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00433 | 15HI0068 | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-08-29 | 2015-09-02 | VIRLO CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Danao City | 302956 | Estefa O. Monte MNHS (Cabungahan NHS) | DANAO CITY | 5 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10657131.51 |  |  | COMPLETED | 1 |  |  | 070215S00201 | 15HI0078 | 2015-09-02 | 2015-09-14 | 2015-09-15 | 2015-09-19 | 2015-09-23 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | K10 (2015) | Region VII | Danao City | 322008 | Guinacot Integrated School | DANAO CITY | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 |  |  | 070215S00525 | 15HI0091 | 2015-09-23 | 2015-10-05 | 2015-10-06 | 2015-10-10 | 2015-10-14 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | K10 (2015) | Region VII | Danao City | 119340 | Leona Durano Zamora ES | DANAO CITY | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00435 | 15HI0069 | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-08-29 | 2015-09-02 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | K10 (2015) | Region VII | Danao City | 119366 | Maslog Elementary School | DANAO CITY | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00484 | 15HI0088 | 2015-09-25 | 2015-10-07 | 2015-10-08 | 2015-10-12 | 2015-10-16 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Danao City | 303037 | Maslog National High School | DANAO CITY | 5 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10687131.51 |  |  | COMPLETED | 1 |  |  | 070215S00202 | 15HI0087 | 2015-09-15 | 2015-09-27 | 2015-09-28 | 2015-10-02 | 2015-10-16 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | K10 (2015) | Region VII | Danao City | 119354 | Pili ES | DANAO CITY | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00410 | 15HI0080 | 2015-08-22 | 2015-09-03 | 2015-12-28
NC 2015 | K10 (2015) | Region VII | Danao City | 119341 | Quisol ES | DANAO CITY | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00418 | 15HI0066 | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-08-29 | 2015-09-02 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Danao City | 322003 | Ramon M. Durano Sr. Foundation - Science and Technology Education Center | DANAO CITY | 5 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22172343.62 |  |  | COMPLETED | 1 |  |  | 070215S00329 | 15HI0097 | 2015-10-26 | 2015-11-07 | 2015-11-08 | 2015-11-12 | 2015-11-16 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Danao City | 303039 | Ramon M. Durano Sr. MNHS | DANAO CITY | 5 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10458131.51 |  |  | COMPLETED | 1 |  |  | 070215S00203
NC 2015 | K10 (2015) | Region VII | Danao City | 322010 | Raymunda B. Hermosilla Integrated School | DANAO CITY | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00415 | 15HI0070 | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-08-29 | 2015-09-02 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | K10 (2015) | Region VII | Danao City | 322004 | Sabang NHS | DANAO CITY | 5 | 1 | 15 | 3STY15CL | 2015 K10 BATCH 3 | 21383013.45 |  |  | COMPLETED | 1 |  |  | 070215S00413 | 15HI0096 | 2015-10-14 | 2015-10-26 | 2015-10-27 | 2015-10-31 | 2015-11-12 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | K10 (2015) | Region VII | Danao City | 322006 | Santican National High School | DANAO CITY | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00412 | 15HI0081 | 2015-08-22 | 2015-09-03 | 2015-12-28
NC 2015 | K10 (2015) | Region VII | Danao City | 322011 | Sta. Rosa Integrated School | DANAO CITY | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00425 | 15HI0071 | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-08-29 | 2015-09-02 | VIRLO CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 303176 | Bankal NHS - Maribago HS Ext. | LAPU-LAPU CITY (OPON) | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | reverted | 0
NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 119972 | Abuno ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10267131.51 |  |  | COMPLETED | 1 |  |  | 070215S00480 | 15HN0135 | 2015-09-22 | 2015-09-29 | 2015-10-13 | 2015-10-19 | 2015-10-29 | EDANNA CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 119973 | Agus ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 6 | 14971327.92 |  |  | COMPLETED | 1 |  |  | 070215S00477 | 15HN0139 | 2015-09-25 | 2015-10-06 | 2015-10-20 | 2015-10-22 | 2015-11-03 | JJ &J CONSTRUCTION & GENERAL SUPPLY
NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303172 | Babag National High School | LAPU-LAPU CITY (OPON) | 6 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303172 | Babag National High School | LAPU-LAPU CITY (OPON) | 6 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303172 | Babag National High School | LAPU-LAPU CITY (OPON) | 6 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | COMPLETED | 1 | [10 empty] | Already Inspected but with some minor findings. On-going rectification
NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 312701 | Babag NHS - Babag Night HS | LAPU-LAPU CITY (OPON) | 6 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | reverted | 0
NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303174 | Bankal NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 27102469.42 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303174 | Bankal NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 119950 | Baring ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00409 | 15HN0117 | 2015-09-09 | 2015-09-16 | 2015-09-28 | 2015-10-05 | 2015-10-14 | JJ &J CONSTRUCTION & GENERAL SUPPLY
NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 303182 | Gun-ob Night High School | LAPU-LAPU CITY (OPON) | 6 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | reverted | 0
NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 119965 | Ibo Elementary School | LAPU-LAPU CITY (OPON) | 6 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00476 | 15HN0138 | 2015-09-25 | 2015-10-06 | 2015-10-20 | 2015-10-22 | 2015-11-03 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303177 | Lo-ok National High School | LAPU-LAPU CITY (OPON) | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1 |  |  | 070215S00205 | 15HN0081 | 2015-07-07 | 2015-07-10 | 2015-07-23 | 2015-07-29 | 2015-08-07 | GONZALODO ENTERPRISES
NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303178 | Mactan NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 |  |  | 070215S00206 | 15HN0097 | 2015-08-04 | 2015-08-07 | 2015-08-19 | 2015-08-26 | 2015-09-04 | JJ &J CONSTRUCTION & GENERAL SUPPLY
NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 303179 | Mactan NHS - Punta Engano HS Ext. | LAPU-LAPU CITY (OPON) | 6 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | reverted | 0
NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303180 | Marigondon NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 15 | 3STY15CL | 2015 SHS BATCH 2 | 21783013.45 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303180 | Marigondon NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15121327.92 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303183 | Marigondon NHS - Science Tech. Educ. Center (STEC) Ext. | LAPU-LAPU CITY (OPON) | 6 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 2 | 3867968.78 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303183 | Marigondon NHS - Science Tech. Educ. Center (STEC) Ext. | LAPU-LAPU CITY (OPON) | 6 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 2 | 3667968.78 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303193 | Nemesio-Epifania Taneo MHS (Tingo HS (DE, January 15, 1995) | LAPU-LAPU CITY (OPON) | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1 |  |  | 070215S00214 | 15HN0082 | 2015-07-07 | 2015-07-10 | 2015-07-23 | 2015-07-29 | 2015-08-07 | MANINGO ENTERPRISES
NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 119980 | PAJAC ELEMENTARY SCHOOL | LAPU-LAPU CITY (OPON) | 6 | 1 | 4 | 4STY4CL | 2015 K10 BATCH 6 | 6900000 |  |  | COMPLETED | 1 |  |  | 070215S00471 | 15HN0134 | 2015-09-22 | 2015-09-29 | 2015-10-13 | 2015-10-19 | 2015-10-29 | JJ &J CONSTRUCTION & GENERAL SUPPLY
NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303184 | Pajo NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303184 | Pajo NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 9 | 3STY9CL | 2015 ADDITIONAL FUND BATCH 9 | 4454196.41 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 303185 | Pajo NHS - Pajo (Night) HS | LAPU-LAPU CITY (OPON) | 6 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | reverted | 0
NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 119955 | Pangan-an ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00475 | 15HN0137 | 2015-09-25 | 2015-11-05 | 2015-11-17 | 2015-11-19 | 2015-12-01 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 119991 | Poblacion PS | LAPU-LAPU CITY (OPON) | 6 | 1 | 4 | 4STY4CL | 2015 K10 BATCH 6 | 6900000 |  |  | COMPLETED | 1 |  |  | 070215S00479 | 15HN0136 | 2015-09-25 | 2015-10-06 | 2015-10-20 | 2015-10-22 | 2015-11-03 | JJ &J CONSTRUCTION & GENERAL SUPPLY
NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 119970 | Pusok Elementary School | LAPU-LAPU CITY (OPON) | 6 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 88509374.48 |  |  | COMPLETED | 1 |  |  | 070215S00474 | 15HN0159 | 2015-11-02 | 2015-11-24 | 2015-11-27 | 2015-12-01 | 2015-12-11 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303187 | Pusok NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00193 | 15HN0084 | 2015-07-07 | 2015-07-10 | 2015-07-23 | 2015-07-29 | 2015-08-07 | EDANNA CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 303188 | Pusok NHS - Pusok (Night) HS | LAPU-LAPU CITY (OPON) | 6 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070215S00422 | 15HN0104 | 2015-08-26 | 2015-09-03 | 2015-09-15 | 2015-09-23 | 2015-10-02 | MANINGO ENTERPRISES
NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 119971 | Soong ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 6 | 26552469.42 |  |  | COMPLETED | 1 |  |  | 070215S00482 | 15HN0133 | 2015-09-22 | 2015-09-29 | 2015-10-13 | 2015-10-19 | 2015-10-29 | GONZALODO ENTERPRISES
NC 2015 | SHS (2015) | Region VII | Lapu-Lapu City | 303189 | Sta. Rosa NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1 | [10 empty] | Inspection of Rectification on September 13,2019
NC 2015 | K10 (2015) | Region VII | Lapu-Lapu City | 119960 | Talima ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00419 | 15HN0118 | 2015-09-09 | 2015-09-16 | 2015-09-28 | 2015-10-05 | 2015-10-14 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | K10 (2015) | Region VII | Mandaue City | 119998 | Basak ES | MANDAUE CITY | 6 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10467131.51 |  |  | COMPLETED | 1 |  |  | 070215S00478 | 15HN0140 | 2015-09-25 | 2015-10-06 | 2015-10-20 | 2015-10-22 | 2015-11-03 | SAN NARCISO BUILDERS CORPORATION(FOR. SAN NARCISO
NC 2015 | SHS (2015) | Region VII | Mandaue City | 303195 | Canduman NHS | MANDAUE CITY | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VII | Mandaue City | 119994 | Cesar M. Cabahug ES (Looc) | MANDAUE CITY | 6 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 3 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00427 | 15HN0119 | 2015-10-13 | 2015-10-06 | 2015-10-28
NC 2015 | SHS (2015) | Region VII | Mandaue City | 303198 | Jagobiao NHS | MANDAUE CITY | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10617131.51 |  |  | COMPLETED | 1 |  |  | 070215S00219 | 15HN0086 | 2015-07-07 | 2015-07-10 | 2015-07-23 | 2015-07-29 | 2015-08-07 | PLD CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Mandaue City | 303200 | Mandaue City CNHS - Labogon NHS Ext. | MANDAUE CITY | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00218 | 15HN0087 | 2015-07-07 | 2015-07-10 | 2015-07-23 | 2015-07-29 | 2015-08-07 | PLD CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Mandaue City | 303199 | Mandaue City Comprehensive NHS | MANDAUE CITY | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | MANDAUE CITY | 312806 | Mandaue City School for the Arts | MANDAUE CITY | 6 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | Reverted | 0
NC 2015 | SHS (2015) | Region VII | Mandaue City | 303202 | Subangdaku Tech-Voc HS (Mandaue City CNHS - Subangdaku NHS Ext.) | MANDAUE CITY | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10917132 |  |  | COMPLETED | 1 |  |  | 070215S00450 | 15HN0145 | 2015-10-27 | 2015-11-05 | 2015-11-17 | 2015-11-19 | 2015-12-01 | P.B. OBIAL CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Mandaue City | 312810 | Tingub High School | MANDAUE CITY | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10717131.51 |  |  | COMPLETED | 1 |  |  | 070215S00262 | 15HN0089 | 2015-07-07 | 2015-07-10 | 2015-07-23 | 2015-07-29 | 2015-08-07 | PLD CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Tagbilaran City | 312302 | Cogon HS Evening Class | TAGBILARAN CITY (Capital) | 1 | 1 | 12 | 3STY12CL | 2015 K10 BATCH 3 | 18222268.79 |  |  | reverted | 0 |  |  | 070115S00169 | 15HA0121 | 2015-09-30
NC 2015 | SHS (2015) | Region VII | Tagbilaran City | 302846 | Dr. Cecilio Putong NHS (Bohol NHS) | TAGBILARAN CITY (Capital) | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10437131.51 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Tagbilaran City | 302846 | Dr. Cecilio Putong NHS (Bohol NHS) | TAGBILARAN CITY (Capital) | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Tagbilaran City | 302874 | Manga National High School | TAGBILARAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 070115S00115 | 15HA0136 | 2015-10-09 | 2015-09-28 | 2015-10-09 | 2015-10-16 | 2015-11-03 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2015 | SHS (2015) | Region VII | Tagbilaran City | 302875 | Mansasa National High School | TAGBILARAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Tagbilaran City | 302876 | Tagbilaran City Science High School | TAGBILARAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070115S00114 | 15HA0134 | 2015-10-09 | 2015-09-28 | 2015-10-09 | 2015-10-15 | 2015-11-09 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2015 | SHS (2015) | Region VII | Talisay City | 322204 | Bulacao NHS | CITY OF TALISAY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00124 | 15-HE-0030 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-08-13 | QUIRANTE CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Talisay City | 119795 | Camp 4 ES | CITY OF TALISAY | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00393 | 15-HE-0083 | 2015-07-15 | 2015-07-16 | 2015-08-04 | 2015-08-12 | 2015-08-18 | MAP ALVIOLA CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Talisay City | 233505 | Campinsa ES | CITY OF TALISAY | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | Reverted | 0 |  |  | 070215S00469
NC 2015 | SHS (2015) | Region VII | Talisay City | 302971 | Cansojong NHS | CITY OF TALISAY | 1 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 1 | 15321327.92 |  |  | REVERTED | 0
NC 2015 | K10 (2015) | Region VII | Talisay City | 233504 | HAWANAY ES | CITY OF TALISAY | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | Reverted | 0 |  |  | 070215S00400 | 15-HE-0084 | 2015-07-15 | 2015-07-16
NC 2015 | SHS (2015) | Region VII | Talisay City | 303019 | Jaclupan NHS | CITY OF TALISAY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Talisay City | 322206 | Lagtang Night HS | CITY OF TALISAY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00145 | 15-HE-0033 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-07-22 | QUIRANTE CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Talisay City | 303040 | Lawaan NHS, Talisay | CITY OF TALISAY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00106 | 15-HE-0034 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-08-13 | QUIRANTE CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Talisay City | 322201 | Maghaway NHS | CITY OF TALISAY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VII | Talisay City | 303056 | Mohon NHS (Mohon Divino Amore NHS) | CITY OF TALISAY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00105 | 15-HE-0036 | 2015-06-10 | 2015-06-11 | 2015-09-15 | 2015-09-21 | 2015-09-28 | QUIRANTE CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Talisay City | 303020 | Pooc NHS (Jaclupan NHS - Pooc Ext.) | CITY OF TALISAY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00104 | 15-HE-0037 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-08-13 | QUIRANTE CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Talisay City | 303088 | San Roque NHS ( Laray NHS - Jaclupan NHS Ext.) | CITY OF TALISAY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00102 | 15-HE-0038 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-08-13 | QUIRANTE CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Talisay City | 303111 | Tabunok Night HS | CITY OF TALISAY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070215S00101 | 15-HE-0039 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-08-13 | GOLDFIN CONSTRUCTION
NC 2015 | SHS (2015) | Region VII | Talisay City | 303113 | Talisay City National High School | CITY OF TALISAY | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 |  |  | 070215S00091 | 15-HE-0040 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-07-22 | GENETIAN BUILDERS
NC 2015 | K10 (2015) | Region VII | Talisay City | 312402 | Tanke NHS | CITY OF TALISAY | 1 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 3 | 15121327.92 |  |  | Reverted | 0 |  |  | 070215S00408 | 15-HE-0085 | 2015-07-15 | 2015-07-16 | 2015-08-04 | 2015-08-12 | 2015-08-18 | ZION CONSTRUCTION(FORMERLY MASTERPIECE CONST. & SU
NC 2015 | SHS (2015) | Region VII | Talisay City | 322208 | Tapul NHS | CITY OF TALISAY | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 070215S00099 | 15-HE-0041 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-29 | 2015-09-15 | QUIRANTE CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Talisay City | 119793 | Vicenta A. Manreal ES (VAMES) | CITY OF TALISAY | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | Reverted | 0 |  |  | 070215S00490 | 15-HE-0114 | 2015-08-23 | 2015-08-24
NC 2015 | K10 (2015) | Region VII | Toledo City | 120741 | Awihao ES | TOLEDO CITY | 3 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 070215S00395 | 15HF0094 | 2015-07-31 | 2015-07-31 | 2015-08-12 | 2015-08-18 | 2015-08-26 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Toledo City | 303308 | Bato NHS | TOLEDO CITY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070215S00107 | 15HF0065 | 2015-06-26 | 2015-06-26 | 2015-07-08 | 2015-07-14 | 2015-07-17 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Toledo City | 303310 | Don Andres Soriano NHS | TOLEDO CITY | 3 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 070215S00097 | 15HF0062 | 2015-06-26 | 2015-06-26 | 2015-07-08 | 2015-07-14 | 2015-07-17 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Toledo City | 303311 | General Climaco NHS | TOLEDO CITY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070215S00096 | 15HF0061 | 2015-06-26 | 2015-06-26 | 2015-07-08 | 2015-07-14 | 2015-07-17 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VII | Toledo City | 120729 | Himatungan ES | TOLEDO CITY | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | REVERTED | 0 |  |  | 070215S00396
NC 2015 | K10 (2015) | Region VII | Toledo City | 120719 | Lower Campo 8 ES | TOLEDO CITY | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | REVERTED | 0 |  |  | 070215S00398 | 15HF0089
NC 2015 | SHS (2015) | Region VII | Toledo City | 303318 | LURAY II NATIONAL HIGH SCHOOL (DAY & NIGHT)) | TOLEDO CITY | 3 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 1 | 15321327.92 |  |  | COMPLETED | 1 |  |  | 070215S00095 | 15HF0071 | 2015-07-23 | 2015-07-23 | 2015-08-04 | 2015-08-10 | 2015-08-14 | HI-TRI DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region VII | Toledo City | 190501 | Makatol Elementary School | TOLEDO CITY | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | REVERTED | 0 |  |  | 070215S00397 | 15HF0098 | [5 empty] | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VII | Toledo City | 120755 | Poog ES | TOLEDO CITY | 3 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 6 | 14971327.92 |  |  | COMPLETED | 1 |  |  | 070215S00500 | 15HF0104 | 2015-08-22 | 2015-08-25 | 2015-09-07 | 2015-10-20 | 2015-10-23 | QUIRANTE CONSTRUCTION
NC 2015 | K10 (2015) | Region VII | Toledo City | 303315 | Toledo City Science High School | TOLEDO CITY | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070215S00394 | 15HF0097 | 2015-08-05 | 2015-08-06 | 2015-08-18 | 2015-08-26 | 2015-09-02 | DINAH JANE CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VII | Toledo City | 303316 | Toledo National Vocational HS | TOLEDO CITY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VII | Toledo City | 303316 | Toledo National Vocational HS | TOLEDO CITY | 3 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7328647.81 |  |  | COMPLETED | 1
NC 2016 | SHS | Region VII | Bais City | 303212 | Bais City National High School | Bais City | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 29605866.712 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Bais City | 303212 | Bais City National High School | Bais City | 2 |  | 12 | 4STY12CL | BATCH 11 CL | 22306281.62 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Bais City | 303212 | Bais City National High School | Bais City | 2 |  | 16 | 4STY8CL | BATCH 11 CL | 29841708.82 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bais City | 303215 | Lonoy National High School | Bais City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2685555.5556 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bais City | 323007 | Mansangaban National Hs | Bais City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2685555.5556 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Bais City | 323012 | Mayor Praxedes P. Villanueva Ii Memorial High School | Bais City | 2 | 1 | 2 | 1STY2CL | BATCH 11 CL | 1846080.17 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Bais City | 120103 | Mayor Praxedes P. Villanueva Ii Memorial High School To Sab-Ahan Es | Bais City | 2 |  | 3 | 1STY3CL | BATCH 11 CL | 2802592.44 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bayawan City | 321911 | Abundio Agarpao, Sr. Memorial High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2770365.4 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bayawan City | 303218 | Actin National High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10550902.144 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bayawan City | 321908 | Antonio M. Lacson Sr. Memorial High School | Bayawan City | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6640355.0552 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bayawan City | 321908 | Antonio M. Lacson Sr. Memorial High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2471055.836 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bayawan City | 232001 | Baican Elementary School | Bayawan City | 3 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Bayawan City | 303219 | Bal-Os National High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10794673.288 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bayawan City | 321901 | Banaybanay National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2834174.2 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bayawan City | 303221 | Bayawan National High School | Bayawan City | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bayawan City | 303221 | Bayawan National High School | Bayawan City | 3 |  | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bayawan City | 303238 | Bugay National High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11322844.1 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bayawan City | 303238 | Bugay National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bayawan City | 120146 | Canabuan Elementary School | Bayawan City | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6710417.7692 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Bayawan City | 321912 | Cansumalig High School | Bayawan City | 3 | 1 | 9 | 3STY9CL | BATCH 9 CL | 14492541.4582 |  |  | Reverted | 0 | [10 empty] | Reverted: The project is included in the CY 2018 BEFF
NC 2016 | TECHVOC | Region VII | Bayawan City | 321912 | Cansumalig High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2616153.08 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bayawan City | 303227 | Dawis National High School | Bayawan City | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 33888650.3943 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bayawan City | 303227 | Dawis National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2914753.96 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bayawan City | 120153 | Hag-Um Primary School | Bayawan City | 3 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2147202.5861 |  |  | Reverted | 0 | [10 empty] | Reverted due to Failure of Bidding for the 5th Times
NC 2016 | K10 | Region VII | Bayawan City | 303239 | Kalamtukan National High School | Bayawan City | 3 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9031942.4637 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bayawan City | 303239 | Kalamtukan National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2627533.256 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bayawan City | 303237 | Kalumboyan National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2775682.8 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bayawan City | 120158 | Kangkawit Elementary School | Bayawan City | 3 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2160525.0915 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Bayawan City | 321905 | Lapay High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11221272.79 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bayawan City | 321905 | Lapay High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bayawan City | 321909 | Malabugas High School | Bayawan City | 3 | 1 | 8 | 4STY8CL | BATCH 9 CL | 15236894.0284 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bayawan City | 321909 | Malabugas High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2687150.44 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bayawan City | 303240 | Manduaw National High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11322844.1 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bayawan City | 303240 | Manduaw National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bayawan City | 321903 | Minaba National High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10672787.716 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bayawan City | 321903 | Minaba National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2519421.584 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bayawan City | 303254 | Narra National High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10957187.384 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bayawan City | 303254 | Narra National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2599082.816 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bayawan City | 303256 | Omod National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2775682.8 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bayawan City | 321910 | Pagatban High School | Bayawan City | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6621247.0422 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bayawan City | 321910 | Pagatban High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2462520.704 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bayawan City | 321906 | San Jose High School | Bayawan City | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7156271.404 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bayawan City | 321906 | San Jose High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bayawan City | 303241 | Tabuan Provincial Community High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10916558.86 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bayawan City | 303241 | Tabuan Provincial Community High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2587702.64 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bayawan City | 303242 | Tayawan National High School | Bayawan City | 3 | 1 | 12 | 4STY12CL | BATCH 9 CL | 23296465.4882 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bayawan City | 303242 | Tayawan National High School | Bayawan City | 3 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5613284.576 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bayawan City | 321904 | Villasol High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2892665.6 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Dumaguete City | 303168 | Dumaguete City Hs | Dumaguete City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Dumaguete City | 303168 | Dumaguete City Hs | Dumaguete City (Capital) | 2 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.59 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Dumaguete City | 303169 | Rtpm - Dumaguete Science Hs | Dumaguete City (Capital) | 2 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15095721.2 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Dumaguete City | 303171 | Taclobo Nhs | Dumaguete City (Capital) | 2 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15095721.2 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Tanjay City | 322303 | Nagsala Hs | City Of Tanjay | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2716157.6507 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Tanjay City | 322303 | Nagsala Hs | City Of Tanjay | 2 | 1 | 8 | 2STY8CL | BATCH 11 CL | 10877342.5917 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bogo City | 119115 | Anonang Sur Es | City Of Bogo | 4 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bogo City | 302933 | Don Potenciano | City Of Bogo | 4 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bogo City | 302934 | Jovencio N. Masong Nhs | City Of Bogo | 4 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10417131.51 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Bogo City | 302936 | Libertad Nhs | City Of Bogo | 4 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.05 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bohol | 302883 | Calape National High School | Calape | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9111461.555 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Bohol | 302872 | Lourdes Nhs | Panglao | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.59 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bohol | 302830 | Cangawa Nhs | Buenavista | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Bohol | 302830 | Cangawa Nhs | Buenavista | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bohol | 302892 | Inabanga Hs- Nabuad | Inabanga | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bohol |  | Lonoy Ps | Inabanga | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bohol | 302873 | Mahayag National High School | San Miguel | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bohol | 302893 | San Jose Nhs | Talibon | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Bohol | 302893 | San Jose Nhs | Talibon | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Bohol | 302897 | San Miguel Technical Vocational School | San Miguel | 2 | 1 | 12 | 2STY6CL | BATCH 13 CL | 18042923.11 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Bohol | 118409 | Tungod Ps | Inabanga | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bohol | 302809 | Alicia Technical-Voc'L Hs | Alicia | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Bohol | 302884 | Pilar Technical-Vocational Hs | Pilar | 3 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Bohol | 302901 | San Roque National High School | Mabini | 3 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Bohol | 302905 | Sierra Bullones Technical Vocational High School | Sierra Bullones | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2656428.32 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Bohol | 302916 | Valencia Tech-Voc Hs | Valencia | 3 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Carcar City | 302970 | Can-Asujan Nhs | City Of Carcar | 1 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Carcar City | 119179 | Maximina V. Barangan Es (Mercado) | City Of Carcar | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 303093 | Sangat Nhs | San Fernando | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu | 302985 | Argao National High School | Argao | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 302985 | Argao National High School | Argao | 2 | 1 | 20 | 4STY20CL | BATCH 13 CL | 34198179.297 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 302921 | Badian Nhs | Badian | 2 | 1 | 12 | 4STY12CL | BATCH 13 CL | 24352577.982 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 302925 | Bala Nhs | Moalboal | 2 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10717131.51 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu | 302940 | Bitoon Nvhs | Dumanjug | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 302940 | Bitoon Nvhs | Dumanjug | 2 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Cebu | 303124 | Calagasan National High School | Argao | 2 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6520624.0402 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu | 303124 | Calagasan National High School | Argao | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2505000 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Cebu | 118947 | Colawin Es | Argao | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6650000 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Cebu | 302997 | Dalaguete National High School | Dalaguete | 2 | 1 | 20 | 4STY20CL | BATCH 13 CL | 34198179.297 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu | 302941 | Dumanjug Nhs | Dumanjug | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu | 303000 | Mantalongon Nhs | Dalaguete | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2445000 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Cebu | 303000 | Mantalongon Nhs | Dalaguete | 2 | 1 | 12 | 2STY12CL | BATCH 13 CL | 16172138.898 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Cebu | 303000 | Mantalongon Nhs | Dalaguete | 2 |  | 10 | 2STY10CL | BATCH 13 CL | 12836310.09 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 303098 | Santander Nhs | Santander | 2 | 1 | 12 | 3STY12CL | BATCH 11 CL | 18559207.2002 |  |  | Completed | 1 | [10 empty] | Slow Progress
NC 2016 | SHS | Region VII | Cebu | 302919 | Aloguinsan Nhs | Aloguinsan | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 302919 | Aloguinsan Nhs | Aloguinsan | 3 |  | 6 | 3STY6CL | BATCH 9 CL | 10417131.51 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 303069 | Bartolome & Manuela Pañares Mnhs | Barili | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 303069 | Bartolome & Manuela Pañares Mnhs | Barili | 3 |  | 18 | 3STY9CL | BATCH 9 CL | 30242655.84 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 303069 | Bartolome & Manuela Pañares Mnhs | Barili | 3 |  | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 302945 | Buanoy Nhs | Balamban | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31152890.27 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 302945 | Buanoy Nhs | Balamban | 3 |  | 12 | 4STY12CL | BATCH 9 CL | 22182343.62 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 302947 | Gaas Nhs | Balamban | 3 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10567131.51 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu | 312404 | Jose Chona Jo Memorial National High School | Balamban | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Cebu | 312404 | Jose Chona Jo Memorial National High School | Balamban | 3 | 1 | 12 | 4STY12CL | BATCH 13 CL | 24352577.982 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu | 312453 | Kalangahan Nhs | Tuburan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2758700 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu | 303029 | Lamac Nhs | Pinamungahan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2808700 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu | 303044 | Looc Norte Nhs | Asturias | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2470000 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 303078 | Lut-Od Nhs | Pinamungahan | 3 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22352343.62 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Cebu | 302949 | Nangka National High School | Balamban | 3 | 1 | 24 | 4STY12CL | BATCH 9 CL | 44304687.24 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 303075 | Pinamungajan Nhs | Pinamungahan | 3 | 1 | 36 | 4STY12CL | BATCH 9 CL | 67820975.64 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu | 303075 | Pinamungajan Nhs | Pinamungahan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 312412 | Pinamungajan Nhs - Night | Pinamungahan | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10417131.51 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 303097 | Santa Lucia Nhs | Asturias | 3 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu | 312414 | Sta. Rita Nhs | Asturias | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2530000 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 302938 | Bantayan Nhs | Bantayan | 4 | 1 | 20 | 4STY20CL | BATCH 9 CL | 32902890.27 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 302938 | Bantayan Nhs | Bantayan | 4 |  | 16 | 4STY16CL | BATCH 9 CL | 28202469.42 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 302938 | Bantayan Nhs | Bantayan | 4 |  | 8 | 4STY8CL | BATCH 9 CL | 15747518.84 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu | 302938 | Bantayan Nhs | Bantayan | 4 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5084000 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Cebu | 119265 | Calape Es | Calape Es | 4 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10650000 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 302995 | Daanbantayan Nhs | Daanbantayan | 4 | 1 | 20 | 4STY20CL | BATCH 5 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 302995 | Daanbantayan Nhs | Daanbantayan | 4 |  | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 303047 | Madridejos Nhs | Madridejos | 4 | 1 | 40 | 4STY20CL | BATCH 5 CL | 65905780.54 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 312409 | Patao Nhs | Bantayan | 4 | 1 | 20 | 4STY20CL | BATCH 5 CL | 32902890.27 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 312409 | Patao Nhs | Bantayan | 4 |  | 9 | 3STY9CL | BATCH 5 CL | 16011327.92 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu | 312409 | Patao Nhs | Bantayan | 4 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 5110000 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Cebu | 303087 | San Remigio Nhs | San Remigio | 4 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Cebu | 303087 | San Remigio Nhs | San Remigio | 4 |  | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu | 303087 | San Remigio Nhs | San Remigio | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 303094 | Santa Fe Nhs | Santa Fe | 4 | 1 | 16 | 4STY8CL | BATCH 5 CL | 31495037.68 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu | 303094 | Santa Fe Nhs | Santa Fe | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2550000 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 312476 | Sulangan Is | Bantayan | 4 | 1 | 8 | 4STY8CL | BATCH 5 CL | 15747518.84 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu | 303091 | Arcelo Mnhs | Liloan | 5 | 1 | 40 | 4STY20CL | BATCH 9 CL | 62305780.54 |  |  | Completed | 1 |  |  |  | 16HI0038 | [5 empty] | ARN BUILDERS
NC 2016 | SHS | Region VII | Cebu | 303091 | Arcelo Mnhs | Liloan | 5 |  | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16HI0039 | [5 empty] | ARN BUILDERS
NC 2016 | SHS | Region VII | Cebu | 302968 | Cabonga-An Nhs | San Francisco | 5 | 1 | 16 | 4STY16CL | BATCH 11 CL | 28002469.42 |  |  | Completed | 1 |  |  |  | 16HI0052 | [5 empty] | AA MASONG CONSTRUCTION
NC 2016 | TECHVOC | Region VII | Cebu | 302968 | Cabonga-An Nhs | San Francisco | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 |  |  |  | 16HI0041 | [5 empty] | YES CONSTRUCTION
NC 2016 | SHS | Region VII | Cebu | 302967 | Camotes National High School | San Francisco | 5 | 1 | 20 | 4STY20CL | BATCH 11 CL | 32602890.27 |  |  | Completed | 1 |  |  |  | 16HI0051 | [5 empty] | ARN BUILDERS
NC 2016 | TECHVOC | Region VII | Cebu | 302967 | Camotes National High School | San Francisco | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 |  |  |  | 16HI0040 | [5 empty] | YES CONSTRUCTION
NC 2016 | SHS | Region VII | Cebu | 302967 | Camotes National High School | San Francisco | 5 | 1 | 6 | 3STY6CL | BATCH 13 CL | 10417131.51 |  |  | Completed | 1 |  |  |  | 16HI0069 | [5 empty] | C. LARA CONSTRUCTION
NC 2016 | SHS | Region VII | Cebu | 119196 | Carmen Nhs-Day To Luyang Es | Carmen | 5 | 1 | 40 | 4STY20CL | BATCH 5 CL | 62285780.54 |  |  | Completed | 1 |  |  |  | 17HI0043 | [5 empty] | PRAGMATIC DEV'T. CONST. CORP
NC 2016 | SHS | Region VII | Cebu | 302978 | Catmon Nhs | Catmon | 5 | 1 | 6 | 2STY6CL | BATCH 11 CL | 8214965.05 |  |  | Completed | 1 |  |  |  | 16HI0070 | [5 empty] | YES CONSTRUCTION
NC 2016 | K10 | Region VII | Cebu | 119226 | Compostela National High School(Day Class) To Compostela Cs | Compostela | 5 | 1 | 40 | 4STY20CL | BATCH 9 CL | 62205780.54 |  |  | Completed | 1 |  |  |  | 17HI0042 | [5 empty] | EDISON DEVELOPMENT CORP
NC 2016 | TECHVOC | Region VII | Cebu | 119226 | Compostela National High School(Day Class) To Compostela Cs | Compostela | 5 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4860000 |  |  | Completed | 1 |  |  |  | 17HI0053 | [5 empty] | BT CONSTRUCTION
NC 2016 | SHS | Region VII | Cebu | 303109 | Liki Nhs | Sogod | 5 | 1 | 8 | 4STY8CL | BATCH 5 CL | 14977518.84 |  |  | Completed | 1 |  |  |  | 16HI0049 | [5 empty] | JO BUILDERS | Slow Progress
NC 2016 | TECHVOC | Region VII | Cebu | 303109 | Liki Nhs | Sogod | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2460000 |  |  | Completed | 1 |  |  |  | 16HI0031 | [5 empty] | FIRST GRANDUER BUILDERS
NC 2016 | SHS | Region VII | Cebu | 119419 | Liloan Nhs To Suba Es | Liloan | 5 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16HI0067 | [5 empty] | DUROS DEVELOPMENT CORP.
NC 2016 | SHS | Region VII | Cebu | 303009 | Zosimo E. Fabroa Mnhs | Poro | 5 | 1 | 8 | 2STY8CL | BATCH 11 CL | 11387342.59 |  |  | Completed | 1 |  |  |  | 16HI0053 | [5 empty] | BARR STEEL CONSTRUCTION
NC 2016 | SHS | Region VII | Cebu | 303114 | Tayud Nhs | Consolacion | 6 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31102890.27 |  |  | Completed | 1 | [10 empty] | Slow Progress
NC 2016 | SHS | Region VII | Cebu | 302993 | Tugbongan Nhs | Consolacion | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 15147518.84 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Cebu City | 119926 | Agsungot Es | Cebu City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu City | 312502 | Babag Hs | Cebu City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 | [10 empty] | incomplete (DPWH request additional fund due to site development problem occurred during construction phase)
NC 2016 | SHS | Region VII | Cebu City | 303152 | Barrio Luz Nhs (Day & Night) | Cebu City (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 9 CL | 29357716.362 |  |  | COMPLETED | 1
NC 2016 | SHS | Region VII | Cebu City | 303134 | Bonbon Nhs | Cebu City (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9121461.5561 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu City | 303134 | Bonbon Nhs | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu City | 303143 | Bulacao Community Hs (Day & Night) | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Cebu City | 303143 | Bulacao Community Hs(Day & Night) | Cebu City (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Cebu City | 119891 | Busay Elementary School | Cebu City (Capital) | 1 | 1 | 12 | 3STY12CL | BATCH 13 CL | 20029495.669 |  |  | Completed | 1 | [10 empty] | subject for termination (for re bid) due to MGB report of sinkholes
NC 2016 | K10 | Region VII | Cebu City | 303138 | Camp Lapu-Lapu Nhs(Day & Night) | Cebu City (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Cebu City | 303153 | City Central Nhs(Day & Night) | Cebu City (Capital) | 1 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1 | [10 empty] | Works has been resume by DPWH started on June 3, 2019
NC 2016 | K10 | Region VII | Cebu City | 303153 | City Central Nhs(Day & Night) | Cebu City (Capital) | 1 |  | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1 | [10 empty] | Schedule for turnover after rectification works be completed
NC 2016 | K10 | Region VII | Cebu City | 303142 | Don Carlos A. Gothong Memorial Nhs | Cebu City (Capital) | 2 | 1 | 24 | 4STY12CL | BATCH 9 CL | 45900000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu City | 303142 | Don Carlos A. Gothong Memorial Nhs | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu City | 303150 | Don Sergio Osme¤A, Sr. Memorial Hs (Day & Night) | Cebu City (Capital) | 2 | 1 | 32 | 4STY16CL | BATCH 9 CL | 58715432.724 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu City | 303150 | Don Sergio Osme¤A, Sr. Memorial Hs (Day & Night) | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu City | 303133 | Don Vicente Rama Mem. Nhs (Basak Nhs) | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [10 empty] | Incomplete (only complete based on POW)
NC 2016 | K10 | Region VII | Cebu City | 303133 | Don Vicente Rama Mem. Nhs(Basak Nhs) | Cebu City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 29357716.362 |  |  | Completed | 1 | [10 empty] | DPWH follow up/pressure the contractor and gave the contractor an ultimatum or face legal action
NC 2016 | K10 | Region VII | Cebu City | 303133 | Don Vicente Rama Mem. Nhs(Basak Nhs) | Cebu City (Capital) | 2 |  | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [10 empty] | DPWH follow up/pressure the contractor and gave the contractor an ultimatum or face legal action
NC 2016 | K10 | Region VII | Cebu City | 119886 | Labangon Elementary School | Cebu City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1 | [10 empty] | Schedule for turnover after rectification works be completed
NC 2016 | K10 | Region VII | Cebu City | 303139 | Lahug Nhs(Night) | Cebu City (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 9 CL | 29357716.362 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu City | 303132 | Lusaran Nhs | Cebu City (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 5 CL | 10350000 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu City | 303158 | Mabini Integrated School | Cebu City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu City | 303151 | Mabolo National High School | Cebu City (Capital) | 1 | 1 | 32 | 4STY16CL | BATCH 9 CL | 58715432.724 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu City | 303151 | Mabolo National High School | Cebu City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Cebu City | 303162 | Oprra Nhs(Day & Night) | Cebu City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Cebu City | 312507 | Pamutan Integrated School | Cebu City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 | [10 empty] | incomplete (DPWH request additional fund due to site development problem occurred during construction phase)
NC 2016 | K10 | Region VII | Cebu City | 119910 | Pardo Extension Elementary School | Cebu City (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22950000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu City | 303159 | Pardo Nhs (Day & Night) | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | REVERTED | 0
NC 2016 | SHS | Region VII | Cebu City | 303159 | Pardo Nhs (Day & Night) | Cebu City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 27350000 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu City | 303137 | Paril Nhs | Cebu City (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Cebu City | 303160 | Pit-Os National High School | Cebu City (Capital) | 1 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34198179.297 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu City | 303160 | Pit-Os National High School | Cebu City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Cebu City |  | Shs In Bonbon, Cebu City | Cebu City (Capital) | 2 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11593844.661 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu City | 303163 | Sinsin Nhs | Cebu City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu City | 303163 | Sinsin Nhs | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2517000 |  |  | REVERTED | 0 | [10 empty] | Subject for reversion
NC 2016 | SHS | Region VII | Cebu City | 312501 | Sirao Integrated School | Cebu City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu City | 303164 | Sudlon Nhs | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [10 empty] | Incomplete works despite buffer fund has been downloaded last Dec. 2017
NC 2016 | SHS | Region VII | Cebu City | 312505 | Tabunan Integrated School | Cebu City (Capital) | 2 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11443844.661 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu City | 303140 | Talamban Nhs (Day & Night) | Cebu City (Capital) | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 20550000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VII | Cebu City | 303140 | Talamban Nhs (Day & Night) | Cebu City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Cebu City | 500227 | Taptap Is | Cebu City (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11443844.661 |  |  | Completed | 1 | [10 empty] | Incomplete works despite buffer fund has been downloaded last Dec. 2017
NC 2016 | K10 | Region VII | Cebu City | 303155 | Tejero Nhs(Day & Night) | Cebu City (Capital) | 1 | 1 | 12 | 4STY12CL | BATCH 9 CL | 19952109.258 |  |  | Completed | 1 | [10 empty] | Works has been resume by DPWH started on June 3, 2019
NC 2016 | K10 | Region VII | Cebu City | 312506 | Tisa High School ( Day & Night) | Cebu City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Cebu City | 312506 | Tisa High School ( Day & Night) | Cebu City (Capital) | 2 |  | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Danao City | 302956 | Estefa O. Monte Memorial National High School | Danao | 5 | 1 | 6 | 3STY6CL | BATCH 3 CL | 10437131.51 |  |  | Completed | 1 |  |  |  | 16HI0050 | [5 empty] | JO BUILDERS
NC 2016 | SHS | Region VII | Danao City | 303037 | Maslog National High School |  | 5 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10417131.51 |  |  | Completed | 1 |  |  |  | 16HI0047 | [5 empty] | JO BUILDERS
NC 2016 | K10 | Region VII | Danao City | 322003 | Ramon M. Durano Sr. Foundation - Science & Technology Center | Danao | 5 | 1 | 20 | 4STY20CL | BATCH 9 CL | 28007601.243 |  |  | Completed | 1 |  |  |  | 16HI0030 | [5 empty] | SAN NARCISO BUILDERS
NC 2016 | K10 | Region VII | Danao City | 303039 | Ramon M. Durano Sr. Memorial National High School | Danao | 5 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15237982.3363 |  |  | Completed | 1 |  |  |  | 16HI0048 | [5 empty] | JO BUILDERS
NC 2016 | K10 | Region VII | Lapu-Lapu City | 119985 | Babag I Es | Lapu-Lapu City (Opon) | 6 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Lapu-Lapu City | 303172 | Babag National High School | Lapu-Lapu City (Opon) | 6 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Lapu-Lapu City | 303172 | Babag National High School | Lapu-Lapu City (Opon) | 6 |  | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Lapu-Lapu City | 119974 | Bagong Silang Es | Lapu-Lapu City (Opon) | 6 | 1 | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Lapu-Lapu City | 119963 | Bankal Es | Lapu-Lapu City (Opon) | 6 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31102890.27 |  |  | COMPLETED | 1 | [10 empty] | PUNCHLIST HAVE NOT YET BEEN COMPLIED
NC 2016 | SHS | Region VII | Lapu-Lapu City | 303174 | Bankal National High School | Lapu-Lapu City (Opon) | 6 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Lapu-Lapu City | 119975 | Basak Es | Lapu-Lapu City (Opon) | 6 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Lapu-Lapu City | 119964 | Buaya Elementary School | Lapu-Lapu City (Opon) | 6 | 1 | 12 | 4STY12CL | BATCH 9 CL | 19952109.258 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Lapu-Lapu City | 119987 | Canjulao Es | Lapu-Lapu City (Opon) | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Lapu-Lapu City | 119977 | Gun-Ob Es | Lapu-Lapu City (Opon) | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Lapu-Lapu City | 303177 | Lo-Ok National High School | Lapu-Lapu City (Opon) | 6 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Lapu-Lapu City | 119966 | Mactan Air Base Es | Lapu-Lapu City (Opon) | 6 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.59 |  |  | Reverted | 0
NC 2016 | K10 | Region VII | Lapu-Lapu City | 303178 | Mactan Nhs | Lapu-Lapu City (Opon) | 6 | 1 | 24 | 4STY12CL | BATCH 9 CL | 39904218.516 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Lapu-Lapu City | 303178 | Mactan Nhs | Lapu-Lapu City (Opon) | 6 |  | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Lapu-Lapu City | 119979 | Marigondon Elementary School | Lapu-Lapu City (Opon) | 6 | 1 | 20 | 4STY20CL | BATCH 9 CL | 28007601.243 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Lapu-Lapu City | 303180 | Marigondon Nhs | Lapu-Lapu City (Opon) | 6 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Lapu-Lapu City | 303181 | Marigondon Nhs - Basak Night Hs Ext. | Lapu-Lapu City (Opon) | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Lapu-Lapu City | 303193 | Nemesio-Epifania Taneo Mhs (Tingo Hs (De, January 15, 1995) | Lapu-Lapu City (Opon) | 6 | 1 | 12 | 4STY12CL | BATCH 9 CL | 20352109.258 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Lapu-Lapu City | 303184 | Pajo National High School | Lapu-Lapu City (Opon) | 6 | 1 | 12 | 4STY12CL | BATCH 9 CL | 19952109.258 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Lapu-Lapu City | 303184 | Pajo National High School | Lapu-Lapu City (Opon) | 6 |  | 16 | 4STY8CL | BATCH 9 CL | 26845533.912 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Lapu-Lapu City | 119969 | Punta Engano Es | Lapu-Lapu City (Opon) | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Lapu-Lapu City | 303187 | Pusok Nhs | Lapu-Lapu City (Opon) | 6 | 1 | 20 | 4STY20CL | BATCH 9 CL | 28007601.243 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Lapu-Lapu City | 303189 | Sta. Rosa Nhs | Lapu-Lapu City (Opon) | 6 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10817131.51 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Lapu-Lapu City | 119984 | Sudtonggan Es | Lapu-Lapu City (Opon) | 6 | 1 | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Lapu-Lapu City | 119962 | Tungasan Es | Lapu-Lapu City (Opon) | 6 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22552343.62 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Mandaue City | 312811 | Banilad Nhs (Cabancalan Nhs Ext.) | Mandaue City | 6 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10882042.74 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Mandaue City | 120005 | Cabancalan Ii Es | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Mandaue City | 303194 | Cabancalan Nhs | Mandaue City | 6 | 1 | 16 | 4STY8CL | BATCH 9 CL | 29795037.68 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Mandaue City | 120010 | Canduman Es | Mandaue City | 6 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Mandaue City | 303195 | Canduman Nhs | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15395522.34 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Mandaue City | 120011 | Casili Night Hs To Casili Es | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16328864.74 |  |  | Completed | 1 |  |  | P00075842VS | 17HN0075 | [5 empty] | SERCHER DEV'T. CORP.
NC 2016 | SHS | Region VII | Mandaue City | 303198 | Jagobiao Nhs | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Mandaue City | 312807 | Maguikay Nhs | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Mandaue City | 303200 | Mandaue City Cnhs - Labogon Nhs Ext. | Mandaue City | 6 | 1 | 12 | 4STY12CL | BATCH 9 CL | 23012343.62 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Mandaue City | 303199 | Mandaue City Comprehensive Nhs | Mandaue City | 6 | 1 | 20 | 4STY20CL | BATCH 13 CL | 32212890.87 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Mandaue City | 119997 | Mandaue City Cs | Mandaue City | 6 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Mandaue City | 119997 | Mandaue City Cs | Mandaue City | 6 |  | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Mandaue City | 189001 | Mandaue City Cs Sped Center | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 9 CL | 15395522.34 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Mandaue City | 312809 | Mandaue Sped Center Hs | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15905522.34 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Mandaue City | 120006 | Subangdaku Es | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Mandaue City | 303202 | Subangdaku Tech-Voc Hs (Mandaue City Cnhs - Subangdaku Nhs Ext.) | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15905522.34 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Mandaue City | 120017 | Tabok Es Ii | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Mandaue City | 120007 | Tipolo Es | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Mandaue City | 120003 | Umapad Es | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Talisay City | 233503 | Biasong Elementary School | City Of Talisay | 1 | 1 | 6 | 3STY6CL | BATCH 13 CL | 11443844.661 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Talisay City | 119785 | Borromeo Bros. Elementary School | City Of Talisay | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15221327.92 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Talisay City | 322204 | Bulacao National High School | City Of Talisay | 1 | 1 | 8 | 4STY8CL | BATCH 9 CL | 15097518 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Talisay City | 302971 | Cansojong National High School | City Of Talisay | 1 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15221327 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Talisay City | 303019 | Jaclupan National High School | City Of Talisay | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15421327.92 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Talisay City | 119800 | Lagtang Elementary School | City Of Talisay | 1 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Talisay City | 322206 | Lagtang Night High School | City Of Talisay | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10417131 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Talisay City | 303040 | Lawaan National High School | City Of Talisay | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Talisay City | 322201 | Maghaway National High School | City Of Talisay | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10517131 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Talisay City | 322201 | Maghaway National High School | City Of Talisay | 1 |  | 4 | 2STY4CL | BATCH 9 CL | 6452000 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Talisay City | 303056 | Mohon Nhs (Mohon Divino Amore Nhs) | City Of Talisay | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Talisay City | 119790 | San Roque Elementary School | City Of Talisay | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15121327 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Talisay City | 303088 | San Roque Nhs (Laray Nhs - Jaclupan Nhs Ext.) | City Of Talisay | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15221327 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Talisay City | 303113 | Talisay City National High School | City Of Talisay | 1 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26996317.0922 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Talisay City | 303113 | Talisay City National High School | City Of Talisay | 1 |  | 8 | 4STY8CL | BATCH 11 CL | 14897518 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Toledo City | 303308 | Bato National High School | Toledo City | 3 | 1 | 24 | 4STY8CL | BATCH 9 CL | 40268300.868 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Toledo City | 120715 | Cantabaco Elementary School | Toledo City | 3 | 1 | 12 | 2STY12CL | BATCH 13 CL | 14579217.18 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Toledo City | 303318 | Don Sndres Soriano Nat. High School | Toledo City | 3 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31202890.27 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Toledo City | 303311 | General Climaco National High School | Toledo City | 3 |  | 12 | 4STY12CL | BATCH 9 CL | 19952109.258 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Toledo City | 303311 | General Climaco National High School | Toledo City | 3 | 1 | 8 | 4STY8CL | BATCH 9 CL | 13622766.956 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Toledo City | 303310 | Luray Ii National High School (Day & Night) | Toledo City | 3 |  | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Toledo City | 303310 | Luray Ii National High School (Day & Night) | Toledo City | 3 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region VII | Toledo City | 120756 | Sam-Ang Elementary School | Toledo City | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5802403.8743 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Toledo City | 303316 | Toledo National Vocational School | Toledo City | 3 | 1 | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1
NC 2016 | SHS | Region VII | Toledo City | 303316 | Toledo National Vocational School | Toledo City | 3 |  | 28 | 4STY28CL | BATCH 9 CL | 36076151.526 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bayawan City | 120162 | Nangka Elem School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | BATCH 2 | 2770696.75 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bayawan City | 120166 | Telesforo Gargantiel MES | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | BATCH 2 | 2762586.11 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Cebu | 302917 | Alcoy National High School | ALCOY | 2 | 1 | 8 | 4STY8CL | BATCH 8 | 17179570.67 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 302917 | Alcoy National High School | ALCOY | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 302917 | Alcoy National High School | ALCOY | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2607211.55 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 302917 | Alcoy National High School | ALCOY | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2607211.55 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Cebu | 303025 | Almacen-Torrevillas National High School | MEDELLIN | 4 | 1 | 4 | 2STY4CL | BATCH 8 | 9007915.89 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 303025 | Almacen-Torrevillas National High School | MEDELLIN | 4 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 118966 | Asturias Central ES | ASTURIAS | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3817546.25 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 302921 | Badian NHS | BADIAN | 7 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2700000 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bais City | 323011 | Bais City Olympia National High School | BAIS CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2669464.8 |  |  | REVERTED | 0
NC 2017 | SHS | Region VII | Bais City | 323001 | Cabugan National High School | BAIS CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2619376.53 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bais City | 120086 | Calasga-an ES | BAIS CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2629830.38 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bais City | 303214 | Dodong EscaÃ±o Memorial High School | BAIS CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2692074.95 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bais City | 303214 | Dodong EscaÃ±o Memorial High School | BAIS CITY | 2 |  | 2 | 1STY2CL | BATCH 4 | 2692074.95 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bais City | 323003 | Governor Julian L. Teves Memorial HS | BAIS CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2629830.38 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bais City | 303213 | Josefina T. Valencia National High School | BAIS CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2643704.83 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bais City | 323006 | Sto. Thomas National High School | BAIS CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2632536.43 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bais City | 323009 | Tagpo National HS | BAIS CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2678328.94 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bais City | 323013 | Tangculogan High School | BAIS CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2629854.46 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302811 | Baclayon National High School | BACLAYON | 1 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 6778750 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302811 | Baclayon National High School | BACLAYON | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 4 | 6733610 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302811 | Baclayon National High School | BACLAYON | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 4 | 5169500 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bohol | 302824 | Mayor A. R. Tuazon Nat'l Sch. of Fisheries | CALAPE | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2844149.2 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302833 | Catigbian NHS | CATIGBIAN | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 4 | 5241360 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118307 | Canayaon ES | GARCIA HERNANDEZ | 3 | 1 | 4 | 1STY4CL | BATCH 4 | 4957321.29 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119137 | Bagacay Elementary School | BORBON | 5 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17HI0063 | [5 empty] | JO BUILDERS
NC 2017 | SHS | Region VII | Cebu | 302924 | Bakhawan National High School | DAANBANTAYAN | 4 | 1 | 6 | 3STY6CL | BATCH 14 | 13989515.1 |  |  | Completed | 1 |  |  | P00184497VS-CW1 | 17HD0096 | 2017-08-30 |  | 2017-12-19 |  | 2017-12-27 | P.B OBIAL CONST.
NC 2017 | SHS | Region VII | Cebu | 302924 | Bakhawan National High School | DAANBANTAYAN | 4 |  | 4 | 2STY4CL | BATCH 14 | 9195901.76 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119292 | Balud ES | DALAGUETE | 2 | 1 | 6 | 2STY6CL | BATCH 8 | 11716168.02 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Cebu | 302938 | Bantayan Senior High School | BANTAYAN | 4 | 1 | 12 | 3STY12CL | BATCH 14 | 30827230.61 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Cebu | 302938 | Bantayan Senior High School | BANTAYAN | 4 |  | 16 | 4STY16CL | BATCH 14 | 38756274.86 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 118943 | Binlod ES | ARGAO | 2 | 1 | 6 | 2STY6CL | BATCH 8 | 11706168.02 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119210 | Binongkalan ES | CATMON | 5 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17HI0061 | [5 empty] | COCOS TIERRA DEV'T. CORPORATION
NC 2017 | TVL | Region VII | Cebu | 302940 | Bitoon NVHS | DUMANJUG | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 118920 | Bogo ES | ARGAO | 2 | 1 | 6 | 3STY6CL | BATCH 8 | 13794515.1 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 118920 | Bogo ES | ARGAO | 2 |  | 6 | 3STY6CL | BATCH 8 | 13794515.1 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119767 | Bongon ES | TABUELAN | 4 | 1 | 2 | 1STY2CL | BATCH 2 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 302945 | Buanoy National High School | BALAMBAN | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2830352.68 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 302953 | Bulasa NHS | ARGAO | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2607211.55 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119696 | Bunlan ES | SANTANDER | 2 | 1 | 6 | 2STY6CL | BATCH 8 | 11711168.02 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119696 | Bunlan ES | SANTANDER | 2 |  | 6 | 2STY6CL | BATCH 8 | 11711168.02 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119090 | Cabcaban ES | BARILI | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3876111.86 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119090 | Cabcaban ES | BARILI | 3 |  | 2 | 1STY2CL | BATCH 4 | 2957536.55 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119747 | Caduawan ES | TABOGON | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119265 | Calape ES | DAANBANTAYAN | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2919729.9 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Cebu | 302961 | Calape NHS | DAANBANTAYAN | 4 | 1 | 8 | 4STY8CL | BATCH 8 | 17159570.67 |  |  | Completed | 1 |  |  | P00177997VS-CW1 | 17HD0077 | 2017-08-30 |  | 2017-11-24 |  | 2017-12-14 | JO BUILDERS
NC 2017 | SHS | Region VII | Cebu | 302961 | Calape NHS | DAANBANTAYAN | 4 |  | 4 | 2STY4CL | BATCH 8 | 8945901.76 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119748 | Camoboan ES | TABOGON | 4 | 1 | 2 | 1STY2CL | BATCH 8 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119749 | Canaocanao ES | TABOGON | 4 | 1 | 2 | 1STY2CL | BATCH 2 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | City of Naga, Cebu | 119524 | Uling ES | CITY OF NAGA | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P00173477VS-CWI | 17-HE-0131 | 2017-08-07 | 2017-08-14 | 2017-08-29 | 2017-10-18 | 2017-10-24 | A.T. Dumlao Construction
NC 2017 | K10 | Region VII | Guihulngan City | 120242 | Calamba CES | CITY OF GUIHULNGAN | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3770000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Guihulngan City | 312910 | Guihulngan NHS, Hilaitan - Trinidad Annex | CITY OF GUIHULNGAN | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3070000 |  |  | REVERTED | 0
NC 2017 | K10 | Region VII | Guihulngan City |  | Lip-o (Sandayao) Ext. HS | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2948745.92 |  |  | REVERTED | 0
NC 2017 | K10 | Region VII | Guihulngan City |  | Lip-o (Sandayao) Ext. HS | CITY OF GUIHULNGAN | 1 |  | 2 | 1STY2CL | BATCH 4 | 2948745.92 |  |  | REVERTED | 0
NC 2017 | K10 | Region VII | Guihulngan City |  | Macalos Ext. HS (Bulado HS) | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2875000 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Guihulngan City |  | Macalos Ext. HS (Bulado HS) | CITY OF GUIHULNGAN | 1 |  | 2 | 1STY2CL | BATCH 4 | 2875000 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Guihulngan City |  | Macalos Ext. HS (Bulado HS) | CITY OF GUIHULNGAN | 1 |  | 3 | 1STY3CL | BATCH 4 | 4058435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Guihulngan City | 120632 | Macapso ES | VALLEHERMOSO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2725000 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Guihulngan City | 120635 | Molobolo ES | VALLEHERMOSO | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 4030000 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Tanjay City | 120555 | Lamwas Elementary School | CITY OF TANJAY | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3940687.05 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Tanjay City | 120555 | Lamwas Elementary School | CITY OF TANJAY | 2 |  | 2 | 1STY2CL | BATCH 4 | 2683720.56 |  |  | Completed | 1 | [10 empty] | Abandoned
NC 2017 | TVL | Region VII | Tanjay City | 303287 | Lourdes L. del Prado MNHS (Pal-ew) | CITY OF TANJAY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3138166.26 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Tanjay City | 303288 | Lourdes L. del Prado MNHS (Sto. Niño) | CITY OF TANJAY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3149989.06 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Tanjay City | 120556 | Luca ES | CITY OF TANJAY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2630063.54 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Tanjay City | 234004 | Mandalamon Elementary School | CITY OF TANJAY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2683720.56 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Tanjay City | 120559 | Novallas Elementary School | CITY OF TANJAY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2656445.45 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Tanjay City |  | Pilipigan Indigenous People Integrated School (PIPIS) | CITY OF TANJAY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2690263.075 |  |  | REVERTED | 0
NC 2017 | K10 | Region VII | Tanjay City |  | Pilipigan Indigenous People Integrated School (PIPIS) | CITY OF TANJAY | 2 |  | 2 | 1STY2CL | BATCH 4 | 2690263.075 |  |  | REVERTED | 0
NC 2017 | K10 | Region VII | Tanjay City | 120564 | Sto. Nino ES | CITY OF TANJAY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2669619.24 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Tanjay City | 312926 | Apolinario Gerarda Arnaiz HS | PAMPLONA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3158811.34 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Tanjay City | 120416 | Ilalan Elementary School | PAMPLONA | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3928448.67 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Tanjay City | 303273 | Sta. Agueda National High School | PAMPLONA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3084748.02 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Tanjay City | 303273 | Sta. Agueda National High School | PAMPLONA | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3084748.02 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Tanjay City | 234005 | Bulo Elementary School | Tanjay City North | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3822915.15 |  |  | COMPLETED | 1 | [10 empty] | Abandoned
NC 2017 | TVL | Region VII | Toledo City | 303316 | Toledo National Vocational School | TOLEDO CITY | 3 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 4 | 5337013.21 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bais City | 303212 | Bais City National High School | BAIS CITY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3136017.37 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bais City | 303215 | Lonoy National High School | BAIS CITY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3234745.04 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bais City | 323007 | Mansangaban National High School | BAIS CITY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3144165.4 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bohol | 302809 | Alicia Technical-Voc'l HS | ALICIA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302809 | Alicia Technical-Voc'l HS | ALICIA | 3 | 1 | 4 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 12587337.5 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bohol | 302809 | Alicia Technical-Voc'l HS | ALICIA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3099218.54 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bohol | 312359 | Katipunan High School | ALICIA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bohol | 302813 | Anda HS | ANDA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2863745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 117957 | Candabong ES | ANDA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 117958 | Casica PS | ANDA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 117961 | Londag ES | ANDA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118013 | Batuan Central ES - Annex | BATUAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bohol | 302815 | Batuan NHS | BATUAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302815 | Batuan NHS | BATUAN | 3 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 9176100 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118015 | Bonifacio ES | BATUAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bohol | 302818 | Bilar NHS | BILAR | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118046 | Campagao ES | BILAR | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3159218.54 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118053 | Roxas PS | BILAR | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118054 | Subayon PS | BILAR | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118058 | Zamora ES | BILAR | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302912 | Anoling National High School | CANDIJAY | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3210860.56 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118114 | Candijay Central ES | CANDIJAY | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3239218.54 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bohol | 302865 | Candijay National High School | CANDIJAY | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118116 | Cogtong ES | CANDIJAY | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3074218.54 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302866 | Cogtong NHS | CANDIJAY | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3210860.56 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118117 | La Union ES | CANDIJAY | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3089218.54 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302864 | La Union NHS | CANDIJAY | 3 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 6117400 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118118 | Luan ES | CANDIJAY | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302911 | Tambongan NHS | CANDIJAY | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3210860.56 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118138 | El Salvador ES | CARMEN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3029218.54 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302861 | Francisco L. Adlaon HS | CARMEN | 3 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 6117400 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118139 | Guadalupe ES | CARMEN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118140 | Katipunan ES | CARMEN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3099218.54 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302860 | Katipunan NHS | CARMEN | 3 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 9632581.68 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118158 | Vallehermoso ES | CARMEN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302832 | Canhayupon NHS | DIMIAO | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3210860.56 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302845 | Dimiao NHS | DIMIAO | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3168346.56 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118277 | Lapsaon ES | DIMIAO | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bohol | 312356 | Bangwalog HS | DUERO | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118302 | Taytay Elementary School | DUERO | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118310 | Datag ES | GARCIA HERNANDEZ | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bohol | 302852 | Garcia-Hernandez HS | GARCIA HERNANDEZ | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302852 | Garcia-Hernandez HS | GARCIA HERNANDEZ | 3 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 9176100 |  |  | COMPLETED | 1
NC 2017 | K10 | Region VII | Bohol | 118314 | Malinao ES | GARCIA HERNANDEZ | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118319 | Tabuan ES | GARCIA HERNANDEZ | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118346 | Basdio ES | GUINDULMAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118354 | Cansiwang ES | GUINDULMAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118355 | Casbu ES | GUINDULMAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302834 | Catungawan National High School | GUINDULMAN | 3 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 9932581.68 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118357 | Guinacot ES | GUINDULMAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302878 | Mayuga NHS | GUINDULMAN | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3058700 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 186516 | Pansul PS | GUINDULMAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118363 | Tambis ES | GUINDULMAN | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4231623.39 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118420 | Canjulao ES | JAGNA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302849 | Faraon NHS | JAGNA | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3360860.56 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118426 | Larapan ES | JAGNA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302870 | Lonoy Heroes MHS | JAGNA | 3 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 6117400 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302868 | Lila NHS | LILA | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3058700 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118439 | Malinao ES | LILA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bohol | 302867 | Hinawanan NHS | LOAY | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2863745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302867 | Hinawanan NHS | LOAY | 3 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 6421721.12 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118452 | Tayong ES | LOAY | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302826 | Camaya-an NHS | LOBOC | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3210860.56 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118502 | Napo Elementary School | LOON | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2891384 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118527 | San Roque ES | MABINI | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3099218.54 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bohol | 302901 | San Roque National High School | MABINI | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2863745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118569 | Buenasuerte ES | PILAR | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3159218.54 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118574 | Estaca ES | PILAR | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3159218.54 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118581 | Pilar Central ES | PILAR | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bohol | 302884 | Pilar Technical-Vocational HS | PILAR | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bohol | 302884 | Pilar Technical-Vocational HS | PILAR | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302884 | Pilar Technical-Vocational HS | PILAR | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3058700 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118582 | Rizal ES | PILAR | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118584 | San Isidro ES | PILAR | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302889 | San Isidro Tech-Voc HS | PILAR | 3 | 1 | 4 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 12234800 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118660 | Bayawahan ES | SEVILLA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3099218.54 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118665 | Cambagui ES | SEVILLA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bohol | 302904 | Cambagui-Calinginan Norte National HS | SEVILLA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302904 | Cambagui-Calinginan Norte National HS | SEVILLA | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3210860.56 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118672 | Sevilla Central ES | SEVILLA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118673 | Abachanan ES | SIERRA BULLONES | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302848 | Dusita High School | SIERRA BULLONES | 3 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 6521721.12 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118691 | San Jose Elementary School | SIERRA BULLONES | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bohol | 302905 | Sierra Bullones Technical Vocational High School | SIERRA BULLONES | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302905 | Sierra Bullones Technical Vocational High School | SIERRA BULLONES | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3260860.56 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118848 | Anonang ES | VALENCIA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118852 | Canduao ES | VALENCIA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3039218.54 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118856 | Lantang ES | VALENCIA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118857 | Limokon ES | VALENCIA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 312311 | Mayor Pablo O. Lim MHS | VALENCIA | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3210860.56 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 186508 | Taculing ES | VALENCIA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Carcar City | 303016 | Maximino Noel Memorial National High School | CITY OF CARCAR | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3386180 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Carcar City | 303082 | ROBERTO E. SATO MEMORIAL NATIONAL HIGH SCHOOL | CITY OF CARCAR | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3478800 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Carcar City | 343971 | Tuyom Senior High School | CITY OF CARCAR | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3386180 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Carcar City | 303126 | Valencia National Vocational HS | CITY OF CARCAR | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3386180 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 312469 | Cansaloay Integrated School | OSLOB | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302830 | Cangawa NHS | BUENAVISTA | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 7390000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 312312 | Panghagban HS | BUENAVISTA | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2600000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302836 | Clarin National School of Fisheries | CLARIN | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 7390000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302836 | Clarin National School of Fisheries | CLARIN | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3700000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302879 | Nahawan NHS | CLARIN | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 7390000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302879 | Nahawan NHS | CLARIN | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3700000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302840 | Dagohoy NHS / Integrated SHS | DAGOHOY | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 7390000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 312321 | San Miguel-Puertos HS | DAGOHOY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3695000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 312321 | San Miguel-Puertos HS | DAGOHOY | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2600000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302842 | Cantubod NHS | DANAO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3695000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302842 | Cantubod NHS | DANAO | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2600000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302841 | Danao NHS | DANAO | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 7390000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302844 | Taming NHS | DANAO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3695000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302844 | Taming NHS | DANAO | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3700000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302892 | Inabanga HS- Nabuad | INABANGA | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 7390000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302891 | San Jose National High School | INABANGA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3695000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302891 | San Jose National High School | INABANGA | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3700000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302827 | Campao Oriental High School | JETAFE | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3700000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302828 | Handumon NHS | JETAFE | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3700000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302808 | Aguining National High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 7390000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 312335 | Basiao High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3700000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 312324 | Bonbonon High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 7390000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 312324 | Bonbonon High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2600000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 312353 | Campamanog HS | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 7390000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 312353 | Campamanog HS | PRES. CARLOS P. GARCIA (PITOGO) | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2600000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 312325 | Gaus High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2600000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 312303 | Mayor Inocencio B. Mendez HS | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3695000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302888 | Eugenio V. Amores MHS | SAGBAYAN (BORJA) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2600000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 312309 | JAPeR Memorial High School | SAGBAYAN (BORJA) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2600000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302873 | Mahayag National High School | SAN MIGUEL | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3695000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 312313 | Mayor Catalino Y. Casoyla MHS | TALIBON | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3695000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302895 | President Carlos P. Garcia Memorial High School | TALIBON | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3700000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302893 | San Jose NHS | TALIBON | 2 | 1 | 4 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 14780000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302896 | Sikatuna Nat'l Agricultural HS | TALIBON | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3695000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302858 | Hinlayagan NHS | TRINIDAD | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3700000 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 118925 | Cansuje ES | ARGAO | 2 | 1 | 8 | 2STY8CL | BATCH 8 | 17064790.26 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 302975 | Cantumog NHS | CARMEN | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2800000 |  |  | Completed | 1 |  |  |  | 17HI0144 | [5 empty] | YES CONSTRUCTION
NC 2017 | TVL | Region VII | Cebu | 302975 | Cantumog NHS | CARMEN | 5 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2700000 |  |  | Completed | 1 |  |  |  | 17HI0143 | [5 empty] | JOHN ARNE CONSTRUCTION
NC 2017 | TVL | Region VII | Cebu | 302984 | Colawin NHS | ARGAO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Cebu | 302984 | Colawin NHS | ARGAO | 2 |  | 6 | 2STY6CL | BATCH 8 | 11716168.02 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119831 | Colonia Central ES | TUBURAN | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2885356.85 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 302987 | Colonia NHS | TUBURAN | 3 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 5493092.36 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 302955 | Cordova NHS | CORDOBA | 6 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119040 | Cornelio C. Melgar Elementary School | BALAMBAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2775955.98 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Cebu | 302995 | Daanbantayan National High School | DAANBANTAYAN | 4 | 1 | 3 | 1STY3CL | BATCH 8 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119298 | Dalaguete Central ES | DALAGUETE | 2 | 1 | 4 | 2STY4CL | BATCH 8 | 8985901.76 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Cebu | 302997 | Dalaguete National High School | DALAGUETE | 2 | 1 | 6 | 3STY6CL | BATCH 8 | 13739515.1 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Cebu | 302997 | Dalaguete NHS | DALAGUETE | 2 | 1 | 16 | 4STY16CL | BATCH 8 | 37070737.96 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119459 | Dalingding Sur ES | MEDELLIN | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 303005 | Doña Liling Neis Negapatan NHS | TABOGON | 4 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 5400000 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119299 | Dugyan ES | DALAGUETE | 2 | 1 | 4 | 2STY4CL | BATCH 8 | 8975901.76 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Cebu | 302941 | Dumanjug NHS | DUMANJUG | 2 | 1 | 8 | 4STY8CL | BATCH 8 | 17159570.67 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 302941 | Dumanjug NHS | DUMANJUG | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119091 | Giloctog ES | BARILI | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2995221.99 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119218 | Ginabukan ES | CATMON | 5 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17HI0060 | [5 empty] | COCOS TIERRA DEV'T. CORP
NC 2017 | TVL | Region VII | Cebu | 303070 | Guibuangan NHS | BARILI | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2904389.71 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 303018 | Guiwanon NHS | GINATILAN | 7 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2607211.55 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119623 | Ilaya ES | SAN FERNANDO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2673745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119751 | Ilihan IS | TABOGON | 4 | 1 | 2 | 1STY2CL | BATCH 8 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119751 | Ilihan IS | TABOGON | 4 |  | 6 | 2STY6CL | BATCH 8 | 11686168.02 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119751 | Ilihan IS | TABOGON | 4 |  | 4 | 2STY4CL | BATCH 8 | 9055901.75 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 312404 | Jose Chona Jo Memorial National High School | BALAMBAN | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2830352.68 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Cebu | 303103 | Juan Pamplona NHS | TABUELAN | 4 | 1 | 6 | 3STY6CL | BATCH 8 | 14452527.13 |  |  | Completed | 1 |  |  | P00178018VS-CW1 | 17HD0082 | 2017-08-30 |  | 2017-11-24 |  | 2017-12-12 | PAGAY CONST.
NC 2017 | TVL | Region VII | Cebu | 303022 | Julian Enad MNHS | SIBONGA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2730000 |  |  | Completed | 1 |  |  | P00181947VS-CW1 | 17-HE-0171 | 2017-11-18 | 2017-11-23 | 2017-12-05 | 2017-12-11 | 2017-12-22 | V.O. Chupuico Construction
NC 2017 | K10 | Region VII | Cebu | 119769 | Kabalawan ES | TABUELAN | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119753 | Kal-anan ES | TABOGON | 4 | 1 | 2 | 1STY2CL | BATCH 8 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 312453 | Kalangahan NHS | TUBURAN | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2960364.26 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 303024 | Kawit NHS | MEDELLIN | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 303028 | Kinatarcan NHS | SANTA FE | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2800000 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119754 | Labangon ES | TABOGON | 4 | 1 | 2 | 1STY2CL | BATCH 8 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 303029 | Lamac National High School | PINAMUNGAHAN | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2882474.81 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 303031 | Lanao NHS, Pilar | PILAR | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2800000 |  |  | Completed | 1 |  |  |  | 17HI0154 | [5 empty] | JOHN ARNE CONSTRUCTION
NC 2017 | TVL | Region VII | Cebu | 303031 | Lanao NHS, Pilar | PILAR | 5 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2700000 |  |  | Completed | 1 |  |  |  | 17HI0153 | [5 empty] | JOHN ARNE CONSTRUCTION
NC 2017 | K10 | Region VII | Cebu | 118930 | Langtad ES | ARGAO | 2 | 1 | 4 | 2STY4CL | BATCH 8 | 8975901.76 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119678 | Libaong ES | SAN REMIGIO | 4 | 1 | 2 | 1STY2CL | BATCH 2 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119755 | Libjo ES | TABOGON | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119282 | Logon ES | DAANBANTAYAN | 4 | 1 | 6 | 3STY6CL | BATCH 8 | 14426490.85 |  |  | Completed | 1 |  |  | P00177995VS-CW1 | 17HD0076 | 2017-08-30 |  | 2017-11-24 |  | 2017-12-14 | JO BUILDERS
NC 2017 | TVL | Region VII | Cebu | 119283 | Looc PS | DAANBANTAYAN | 4 | 1 | 2 | 2STY2CL | BATCH 8 | 6290008.53 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 303122 | Lorenzo C. Tanza Memorial National High School | SAN FRANCISCO | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2800000 |  |  | Completed | 1 |  |  |  | 17HI0148 | [5 empty] | BL PANGAN CONSTRUCTION
NC 2017 | K10 | Region VII | Cebu | 119736 | Lubo ES | SOGOD | 5 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17HI0062 | [5 empty] | JO BUILDERS
NC 2017 | TVL | Region VII | Cebu | 303008 | Luciano B. Rama Sr. MNHS | PORO | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2800000 |  |  | Completed | 1 |  |  |  | 17HI0149 | [5 empty] | FIRST BUILDERS AND DEVELOPERS
NC 2017 | K10 | Region VII | Cebu | 119132 | Lunop ES | BOLJOON | 2 | 1 | 4 | 2STY4CL | BATCH 8 | 8975901.76 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 303049 | Magsico NHS | SAN FERNANDO | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2838000 |  |  | Completed | 1 |  |  | P00181948VS-CW1 | 17-HE-0172 | 2017-11-18 | 2017-11-23 | 2017-12-05 | 2017-12-11 | 2017-12-22 | DT&C Construction
NC 2017 | K10 | Region VII | Cebu | 118955 | Malalag ES | ARGAO | 2 | 1 | 4 | 2STY4CL | BATCH 8 | 8975901.76 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119270 | Malbago Elementary School | DAANBANTAYAN | 4 | 1 | 6 | 3STY6CL | BATCH 8 | 13899515.1 |  |  | Completed | 1 |  |  | P00177994VS-CW1 | 17HD0186 | 2017-08-30 |  | 2017-11-27 |  | 2017-12-15 | BANTAY CONST.
NC 2017 | SHS | Region VII | Cebu | 302962 | Malingin NHS | DAANBANTAYAN | 4 | 1 | 8 | 4STY8CL | BATCH 14 | 17159570.67 |  |  | Completed | 1 |  |  | P00184501VS-CW1 | 17HD0140 | 2017-08-30 |  | 2017-12-19 |  | 2017-12-27 | BANTAY CONST.
NC 2017 | TVL | Region VII | Cebu | 312457 | Manatad National High School | SIBONGA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2781000 |  |  | Completed | 1 |  |  | P00181950VS-CW1 | 17-HE-0174 | 2017-11-18 | 2017-11-23 | 2017-12-05 | 2017-12-11 | 2017-12-22 | Square One Builders
NC 2017 | TVL | Region VII | Cebu | 312457 | Manatad National High School | SIBONGA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 2781000 |  |  | Completed | 1 |  |  | P00181951VS-CW1 | 17-HE-0175 | 2017-11-18 | 2017-11-23 | 2017-12-05 | 2017-12-11 | 2017-12-22 | Celjem Const. & Dev't. Corp.
NC 2017 | K10 | Region VII | Cebu | 118956 | Mandilikit ES | ARGAO | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3768435.02 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 302986 | Mandilikit NHS | ARGAO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 302986 | Mandilikit NHS | ARGAO | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2607211.55 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119486 | Manduang ES | MINGLANILLA | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2673745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119758 | Manlagtang ES | TABOGON | 4 | 1 | 2 | 1STY2CL | BATCH 8 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119305 | Mantalongon ES | DALAGUETE | 2 | 1 | 9 | 3STY9CL | BATCH 8 | 24558047.73 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119305 | Mantalongon ES | DALAGUETE | 2 |  | 4 | 2STY4CL | BATCH 8 | 8985901.76 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119611 | Manuel L. Quezon ES | SAMBOAN | 2 | 1 | 9 | 3STY9CL | BATCH 8 | 24558047.73 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Cebu | 303054 | Medellin National High School | MEDELLIN | 4 | 1 | 8 | 4STY8CL | BATCH 8 | 17159570.67 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 303057 | Montañeza NHS | MALABUYOC | 7 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 303059 | Montealegre NHS | TUBURAN | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3075390.12 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 312460 | Montpeller NHS | ALEGRIA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119759 | Muabog ES | TABOGON | 4 | 1 | 2 | 1STY2CL | BATCH 8 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 302949 | Nangka National High School | BALAMBAN | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2904389.71 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119537 | Nueva Caceres ES | OSLOB | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 118877 | Nug-as ES | ALCOY | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 302918 | Nug-as NHS | ALCOY | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2607211.55 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 302918 | Nug-as NHS | ALCOY | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2607211.55 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119780 | Olivo ES | TABUELAN | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 303081 | Puertobello NHS - Pob. Ext. | TUDELA | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2800000 |  |  | Completed | 1 |  |  |  | 17HI0152 | [5 empty] | FIRST BUILDERS AND DEVELOPERS
NC 2017 | TVL | Region VII | Cebu | 303081 | Puertobello NHS - Pob. Ext. | TUDELA | 5 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 303060 | Putat NHS | TUBURAN | 3 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 5643846.13 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 303085 | San Jose National High School | PORO | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2800000 |  |  | Completed | 1 |  |  |  | 17HI0150 | [5 empty] | FIRST BUILDERS AND DEVELOPERS
NC 2017 | TVL | Region VII | Bohol | 302811 | Baclayon National High School | BACLAYON | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 5169000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bohol | 302833 | Catigbian NHS | CATIGBIAN | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 5241000 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bohol | 302873 | Mahayag National High School | SAN MIGUEL | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4156545.02 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 118987 | San Roque ES | ASTURIAS | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3817546.25 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 303089 | San Sebastian NHS | SAMBOAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 303094 | Santa Fe National High School | SANTA FE | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119201 | Santikan Elementary School | CARMEN | 5 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17HI0059 | [5 empty] | COCOS TIERRA DEV'T. CORP
NC 2017 | TVL | Region VII | Cebu | 303101 | Sibonga National High School | SIBONGA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 2754000 |  |  | reverted | 0
NC 2017 | SHS | Region VII | Cebu | 302996 | Sir Knight Luis P. Cañete Sr. NHS | DAANBANTAYAN | 4 | 1 | 6 | 3STY6CL | BATCH 14 | 13739515.1 |  |  | Completed | 1 |  |  | P00184502VS-CW1 | 17HD0196 | 2017-11-16 |  | 2017-12-11 |  | 2017-12-22 | J.A.R.C CONST.
NC 2017 | SHS | Region VII | Cebu | 302996 | Sir Knight Luis P. Cañete Sr. NHS | DAANBANTAYAN | 4 |  | 6 | 3STY6CL | BATCH 14 | 13739515.1 |  |  | Completed | 1 |  |  | P00184503VS-CW1 | 17HD0197 | 2017-11-16 |  | 2017-12-11 |  | 2017-12-22 | J.A.R.C CONST.
NC 2017 | K10 | Region VII | Cebu | 119764 | Somosa ES | TABOGON | 4 | 1 | 3 | 1STY3CL | BATCH 2 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119766 | Tabogon Central ES | TABOGON | 4 | 1 | 12 | 3STY12CL | BATCH 8 | 29469267.25 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 303104 | Tabunan NHS | BORBON | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2800000 |  |  | Completed | 1 |  |  |  | 17HI0147 | [5 empty] | JO BUILDERS
NC 2017 | K10 | Region VII | Cebu | 118934 | Talaga ES | ARGAO | 2 | 1 | 6 | 2STY6CL | BATCH 8 | 11716168.02 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 118934 | Talaga ES | ARGAO | 2 |  | 6 | 2STY6CL | BATCH 8 | 11716168.02 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 303112 | Talaga NHS | ARGAO | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2607211.55 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 118935 | Talaytay Elementary School | ARGAO | 2 | 1 | 4 | 2STY4CL | BATCH 8 | 8985901.76 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 118962 | Taloot Central Elementary School | ARGAO | 2 | 1 | 6 | 2STY6CL | BATCH 8 | 11706168.02 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 118962 | Taloot Central Elementary School | ARGAO | 2 |  | 6 | 2STY6CL | BATCH 8 | 11706168.02 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bayawan City | 303217 | Basay National High School | BASAY | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3989801 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bayawan City | 303221 | Bayawan National High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3663818.32 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bayawan City | 303221 | Bayawan National High School | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3663818.32 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bayawan City | 303237 | Kalumboyan National High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3789801 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bayawan City | 303237 | Kalumboyan National High School | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3789801 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bayawan City | 321903 | Minaba National High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3746058.84 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Bayawan City | 303242 | Tayawan National High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3803801 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bohol | 302907 | Bantolinao National High School | ANTEQUERA | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2891384 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bohol | 302832 | Canhayupon NHS | DIMIAO | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bohol | 118502 | Napo Elementary School | LOON | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2891384 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Bohol | 302819 | Busao National High School | MARIBOJOC | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2891384 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 118962 | Taloot Central Elementary School | ARGAO | 2 |  | 6 | 2STY6CL | BATCH 8 | 11706168.02 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119539 | Tan-awan ES | OSLOB | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 302980 | Tinabyonan NHS | CATMON | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2800000 |  |  | Completed | 1 |  |  |  | 17HI0146 | [5 empty] | JOHN ARNE CONSTRUCTION
NC 2017 | TVL | Region VII | Cebu | 302980 | Tinabyonan NHS | CATMON | 5 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2700000 |  |  | Completed | 1 |  |  |  | 17HI0145 | [5 empty] | JOHN ARNE CONSTRUCTION
NC 2017 | K10 | Region VII | Cebu | 119471 | Tindog ES | MEDELLIN | 4 | 1 | 3 | 1STY3CL | BATCH 2 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu City | 303129 | Adlaon NHS | CEBU CITY (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 12 | 16046618.12 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu City | 119928 | Binaliw ES | CEBU CITY (Capital) | 1 | 1 | 9 | 3STY9CL | BATCH 12 | 25561526.15 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Cebu City | 303131 | BINALIW NATIONAL HIGH SCHOOL | CEBU CITY (Capital) | 1 | 1 | 12 | 4STY12CL | BATCH 12 | 32056227.4 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu City | 119909 | Pardo Elementary School | CEBU CITY (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 12 | 37501520.885 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu City | 119914 | Pasil Elementary School | CEBU CITY (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 12 | 37851920.18 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu City | 119890 | Toong ES | CEBU CITY (Capital) | 2 | 1 | 9 | 3STY9CL | BATCH 12 | 24508829.56 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Danao City | 302956 | Estefa O. Monte Memo. National High School | DANAO CITY | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17HI0155 | [5 empty] | BL PANGAN CONSTRUCTION
NC 2017 | SHS | Region VII | Danao City | 303037 | Maslog National High School | DANAO CITY | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17HI0156 | [5 empty] | FIRST BUILDERS AND DEVELOPERS
NC 2017 | K10 | Region VII | Dumaguete City | 119949 | South City ES | DUMAGUETE CITY (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2729262.44 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Guihulngan City | 303230 | GUIHULNGAN NATIONAL AGRICULTURAL SCHOOL | CITY OF GUIHULNGAN | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3530000 |  |  | Reverted | 0
NC 2017 | TVL | Region VII | Guihulngan City | 312952 | Guihulngan National High School-Poblacion (Linantuyan Annex) | CITY OF GUIHULNGAN | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3600000 |  |  | Reverted | 0
NC 2017 | K10 | Region VII | Mandaue City | 119998 | Basak ES | MANDAUE CITY | 6 | 1 | 12 | 4STY12CL | BATCH 12 | 32201289.72 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Mandaue City | 303198 | Jagobiao NHS | MANDAUE CITY | 6 | 1 | 8 | 4STY8CL | BATCH 12 | 17637320.67 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Mandaue City | 312807 | Maguikay HS | MANDAUE CITY | 6 | 1 | 16 | 4STY16CL | BATCH 12 | 37449237.96 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Mandaue City | 303199 | Mandaue City Comprehensive NHS | MANDAUE CITY | 6 | 1 | 8 | 4STY8CL | BATCH 12 | 17478820.67 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Mandaue City | 119997 | Mandaue City CS | MANDAUE CITY | 6 | 1 | 16 | 4STY16CL | BATCH 12 | 37379237.96 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Mandaue City | 120006 | Subangdaku ES | MANDAUE CITY | 6 | 1 | 20 | 4STY20CL | BATCH 12 | 42119659.74 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Mandaue City | 120007 | Tipolo ES | MANDAUE CITY | 6 | 1 | 8 | 4STY8CL | BATCH 12 | 17418820.67 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Bogo City | 119125 | Polambato ES | CITY OF BOGO | 4 | 1 | 6 | 2STY6CL | BATCH 14 | 11696168.02 |  |  | Completed | 1 |  |  | P00184485VS | 17HD0074 | 2017-08-30 | 2017-09-14 | 2017-12-29 | 2017-12-22 | 2017-12-27 | Dinah Jane Const.
NC 2017 | SHS | Region VII | Bogo City | 302934 | Jovencio N. Masong NHS | CITY OF BOGO | 4 | 1 | 8 | 4STY8CL | BATCH 14 | 18049155.23 |  |  | Completed | 1 |  |  | P00184486VS | 17HD0107 | 2017-08-30 | 2017-09-14 | 2017-12-29 | 2017-12-22 | 2017-12-27 | B.L. Pangan
NC 2017 | SHS | Region VII | Bogo City | 302935 | La Paz NHS | CITY OF BOGO | 4 | 1 | 8 | 4STY8CL | BATCH 14 | 18049155.23 |  |  | Completed | 1 |  |  | P00184487VS | 17HD0108 | 2017-08-30 | 2017-09-14 | 2017-12-29 | 2017-12-22 | 2017-12-27 | P.B. Obial
NC 2017 | SHS | Region VII | Bogo City | 302935 | La Paz NHS | CITY OF BOGO | 4 |  | 6 | 3STY6CL | BATCH 14 | 14452527.73 |  |  | Completed | 1 |  |  | P00184488VS | 17HD0093 | 2017-08-30 | 2017-09-14 | 2017-12-29 | 2017-12-22 | 2017-12-27 | Dinah Jane Const.
NC 2017 | SHS | Region VII | Bogo City | 302936 | Libertad NHS | CITY OF BOGO | 4 | 1 | 8 | 4STY8CL | BATCH 14 | 18249155.23 |  |  | Completed | 1 |  |  | P00184489VS | 17HD0109 | 2017-08-30 | 2017-09-14 | 2017-12-29 | 2017-12-22 | 2017-12-27 | Dinah Jane Const. | Slow paced progress
NC 2017 | SHS | Region VII | Bogo City | 302936 | Libertad NHS | CITY OF BOGO | 4 |  | 6 | 3STY6CL | BATCH 14 | 14552527.73 |  |  | Completed | 1 |  |  | P00184490VS | 17HD0D94 | 2017-08-30 | 2017-09-14 | 2017-12-29 | 2017-12-22 | 2017-12-27 | P.B. Obial
NC 2017 | SHS | Region VII | Bogo City | 302936 | Libertad NHS | CITY OF BOGO | 4 |  | 4 | 2STY4CL | BATCH 14 | 9273175.995 |  |  | Completed | 1 |  |  | P00184491VS | 17HD0192 | 2017-11-16 | 2017-11-28 | 2017-12-11 | 2017-12-18 | 2017-12-22 | Gonzalodo Enterp.
NC 2017 | SHS | Region VII | Bogo City | 302936 | Libertad NHS | CITY OF BOGO | 4 |  | 4 | 2STY4CL | BATCH 14 | 9273175.995 |  |  | Completed | 1 |  |  | P00184492VS | 17HD0193 | 2017-11-16 | 2017-11-28 | 2017-12-11 | 2017-12-16 | 2017-12-22 | Gonzalodo Enterp.
NC 2017 | SHS | Region VII | Bogo City | 302937 | Odlot NHS | CITY OF BOGO | 4 | 1 | 6 | 3STY6CL | BATCH 14 | 14452527.73 |  |  | Completed | 1 |  |  | P00184493VS | 17HD0075 | 2017-08-30 | 2017-09-14 | 2017-12-29 | 2017-12-22 | 2017-12-27 | Dinah Jane Const.
NC 2017 | SHS | Region VII | Bogo City | 500407 | City of Bogo Science and Arts Academy | CITY OF BOGO | 4 | 1 | 8 | 4STY8CL | BATCH 14 | 17159570.67 |  |  | Completed | 1 |  |  | P00184494VS | 17HD0194 | 2017-11-16 | 2017-09-28 | 2017-12-11 | 2017-12-18 | 2017-12-22 | Dinah Jane Const.
NC 2017 | SHS | Region VII | Bogo City | 500407 | City of Bogo Science and Arts Academy | CITY OF BOGO | 4 |  | 8 | 4STY8CL | BATCH 14 | 17159570.67 |  |  | Completed | 1 |  |  | P00184495VS | 17HD0195 | 2017-11-16 | 2017-09-28 | 2017-12-11 | 2017-12-18 | 2017-12-22 | Dinah Jane Const.
NC 2017 | K10 | Region VII | Cebu | 119471 | Tindog ES | MEDELLIN | 4 | 1 | 6 | 2STY6CL | BATCH 8 | 11676168.02 |  |  | Completed | 1
NC 2017 | TVL | Region VII | Cebu | 302965 | Tominjao National High School | DAANBANTAYAN | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 2700000 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 118937 | Tulic ES | ARGAO | 2 | 1 | 6 | 3STY6CL | BATCH 8 | 13799515.1 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 118915 | Tuyokon Elementary School | ALOGUINSAN | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3886162.11 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119658 | Union ES | SAN FRANCISCO | 5 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  |  | 17HI0064 | [5 empty] | YES CONSTRUCTION
NC 2017 | K10 | Region VII | Cebu | 119104 | Vito ES | BARILI | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3815668.69 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Cebu | 119104 | Vito ES | BARILI | 3 |  | 3 | 1STY3CL | BATCH 4 | 3815668.69 |  |  | Completed | 1
NC 2017 | SHS | Region VII | City of Naga, Cebu | 303121 | Uling National High School | CITY OF NAGA | 1 | 1 | 12 | 3STY12CL | BATCH 14 | 29359267.25 |  |  | Completed | 1 |  |  | P00184504VS-CWI | 17-HE-0166 | 2017-11-16 | 2017-11-23 | 2017-12-11 | 2017-12-14 | 2017-12-22 | Quirante Construction
NC 2017 | SHS | Region VII | City of Naga, Cebu | 325303 | Tinaan National High School | CITY OF NAGA | 1 | 1 | 8 | 4STY8CL | BATCH 14 | 17159570.67 |  |  | Reverted | 0
NC 2017 | K10 | Region VII | Lapu-Lapu City | 119960 | Talima ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 8 | 4STY8CL | BATCH 14 | 18088049.2 |  |  | Completed | 1 | [10 empty] | for final inspection, DPWH transferred the location of the fire escape infront of the building façade
NC 2017 | K10 | Region VII | Lapu-Lapu City | 119968 | Pajo ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 8 | 4STY8CL | BATCH 14 | 17242570.67 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Lapu-Lapu City | 119971 | Soong ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 8 | 4STY8CL | BATCH 14 | 17234570.67 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Lapu-Lapu City | 119976 | Buyong Elementary School | LAPU-LAPU CITY (OPON) | 6 | 1 | 12 | 4STY12CL | BATCH 14 | 31732289.72 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Lapu-Lapu City | 119989 | Lapu-Lapu City CES | LAPU-LAPU CITY (OPON) | 6 | 1 | 12 | 4STY12CL | BATCH 14 | 31857289.72 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Lapu-Lapu City | 119990 | Look ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 12 | 4STY12CL | BATCH 14 | 31744789.72 |  |  | Completed | 1 | [10 empty] | Contractor have not yet completed the works in the punchlist
NC 2017 | SHS | Region VII | Tagbilaran City | 302846 | Dr. Cecilio Putong NHS (Bohol NHS) | TAGBILARAN CITY (Capital) | 1 | 1 | 12 | 4STY12CL | BATCH 14 | 37511535 |  |  | Completed | 1 | [9 empty] | Gail Construction & Supply
NC 2017 | SHS | Region VII | Tagbilaran City | 302846 | Dr. Cecilio Putong NHS (Bohol NHS) | TAGBILARAN CITY (Capital) | 1 |  | 20 | 4STY20CL | BATCH 14 | 48094000 |  |  | Completed | 1 | [9 empty] | Rudhil Construction & Enterprises, Inc.
NC 2017 | K10 | Region VII | Talisay City | 119787 | Lawaan ES | CITY OF TALISAY | 1 | 1 | 12 | 4STY12CL | BATCH 14 | 31649789.72 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Talisay City | 119800 | Lagtang Elementary School | CITY OF TALISAY | 1 | 1 | 8 | 4STY8CL | BATCH 14 | 17159570.67 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Talisay City | 303019 | Jaclupan National High School | CITY OF TALISAY | 1 | 1 | 8 | 4STY8CL | BATCH 14 | 17159570.67 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Talisay City | 303020 | Pooc NHS (Jaclupan NHS - Pooc Ext.) | CITY OF TALISAY | 1 | 1 | 8 | 4STY8CL | BATCH 14 | 17159570.67 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Talisay City | 303040 | Lawaan NHS, Talisay | CITY OF TALISAY | 1 | 1 | 8 | 4STY8CL | BATCH 14 | 17159570.67 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Talisay City | 322204 | Bulacao National High School | CITY OF TALISAY | 1 | 1 | 8 | 4STY8CL | BATCH 14 | 17159570.67 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Talisay City | 322206 | Lagtang Night HS | CITY OF TALISAY | 1 | 1 | 8 | 4STY8CL | BATCH 14 | 17159570.67 |  |  | Completed | 1
NC 2017 | SHS | Region VII | Talisay City | 322208 | Tapul National High School | CITY OF TALISAY | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 8128972.94 |  |  | Completed | 1
NC 2017 | K10 | Region VII | Tanjay City | 234003 | Lugta Elementary School | Tanjay City West | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Bais City | 120096 | Mangganay ES | BAIS CITY | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12549710.02 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bais City | 303212 | Bais City National High School | BAIS CITY | 2 | 1 | 4 | 4sty- 2 ict lab & 2 science lab | BATCH 1 | 19145815.06 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bais City | 303213 | Josefina T. Valencia National High School | BAIS CITY | 2 | 1 | 2 | 2sty- 2 science lab | BATCH 1 | 9363257.76 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bais City | 303213 | Josefina T. Valencia National High School | BAIS CITY | 2 |  | 2 | 2sty- 2 ict lab | BATCH 1 | 9838257.76 |  |  | Reverted | 0
NC 2018 | TVL | Region VII | Bais City | 303214 | Dodong Escaño Memorial High School | BAIS CITY | 2 | 1 | 2 | 2sty- 1 ict lab & 1 science lab | BATCH 1 | 10080911.97 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bais City | 303215 | Lonoy National High School | BAIS CITY | 2 | 1 | 2 | 2sty- 2 science lab | BATCH 1 | 9714914.1 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bais City | 303215 | Lonoy National High School | BAIS CITY | 2 |  | 2 | 2sty- 2 ict lab | BATCH 1 | 10189914.1 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bais City | 303216 | Bais City National Science High School | BAIS CITY | 2 | 1 | 4 | 4sty- 2 ict lab & 2 science lab | BATCH 1 | 19145815.06 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bais City | 323003 | Governor Julian L. Teves Memorial HS | BAIS CITY | 2 | 1 | 2 | 2sty- 2 science lab | BATCH 1 | 9228246.76 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bais City | 323003 | Governor Julian L. Teves Memorial HS | BAIS CITY | 2 |  | 2 | 2sty- 2 ict lab | BATCH 1 | 9703246.76 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bais City | 323007 | Mansangaban National High School | BAIS CITY | 2 | 1 | 4 | 4sty- 2 ict lab & 2 science lab | BATCH 1 | 19689310.78 |  |  | completed | 1
NC 2018 | TVL | Region VII | Bais City | 323009 | Tagpo National HS | BAIS CITY | 2 | 1 | 2 | 2sty- 1 ict lab & 1 science lab | BATCH 1 | 10018690.79 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bais City | 323013 | Tangculogan High School | BAIS CITY | 2 | 1 | 2 | 2sty- 2 science lab | BATCH 1 | 9243778.21 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bais City | 323013 | Tangculogan High School | BAIS CITY | 2 |  | 2 | 2sty- 2 ict lab | BATCH 1 | 9718778.21 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Bayawan City | 120107 | Basay Central School | BASAY | 3 |  | 4 | 2STY4CL | Batch 3 | 9182301.76 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Bayawan City | 120132 | Lapay Elementary School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | 2STY4CL | Batch 3 | 9835966.85 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Bayawan City | 120143 | Banga CES | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL W/ TOILET | Batch 3 | 2343187.94 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bayawan City | 303218 | Actin National High School | BASAY | 3 | 1 | 4 | 4STY4LAB (2 Reg. Workshop, 2 ICT) | Batch 3 | 17878600.37 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bayawan City | 303219 | Bal-os National High School | BASAY | 3 | 1 | 4 | 4STY4LAB (2 Reg. Workshop, 2 SCI LAB) | Batch 3 | 18402430.06 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bayawan City | 303220 | Maglinao National High School | BASAY | 3 | 1 | 4 | 4STY4LAB (2 Reg. Workshop, 2 ICT) | Batch 3 | 18507787.49 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bayawan City | 303227 | Dawis National High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | 4STY4LAB (2 SCI LAB, 2 ICT) | Batch 3 | 18867432.03 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bayawan City | 321902 | Bayawan City Science and Technology Education Center - High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | 4STY4LAB (2 SCI LAB, 2 ICT) | Batch 3 | 17309570.67 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Bayawan City | 321912 | Cansumalig High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 9 | 3STY9CL | Batch 3 | 26953159.6 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Bohol | 118291 | Duero Central ES | DUERO | 3 | 1 | 6 | 3STY6CL | BATCH 1 | 13898951.6 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Bohol | 302813 | Anda HS | ANDA | 3 | 1 | 8 | 2STY8CL | BATCH 1 | 17112546.66 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Bohol | 302813 | Anda HS | ANDA | 3 |  | 4 | 2STY4CL | BATCH 1 | 9014779.96 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Bohol | 302813 | Anda HS | ANDA | 3 |  | 4 | 2STY4CL | BATCH 1 | 9014779.96 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Bohol | 302815 | Batuan NHS | BATUAN | 3 | 1 | 12 | 3STY12CL | BATCH 1 | 29359267.25 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Bohol | 302832 | Canhayupon NHS | DIMIAO | 3 | 1 | 8 | 2STY8CL | BATCH 1 | 16974790.26 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Bohol | 302847 | Duero NHS | DUERO | 3 | 1 | 8 | 2STY8CL | BATCH 1 | 17134226.26 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Bohol | 302905 | Sierra Bullones Technical Vocational High School | SIERRA BULLONES | 3 | 1 | 6 | 3STY6CL | BATCH 1 | 13739515.1 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Bohol | 302905 | Sierra Bullones Technical Vocational High School | SIERRA BULLONES | 3 |  | 8 | 2STY8CL | BATCH 1 | 16974790.26 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Bohol | 302916 | Valencia Tech-Voc HS | VALENCIA | 3 | 1 | 12 | 3STY12CL | BATCH 1 | 29359267.25 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Bohol | 302916 | Valencia Tech-Voc HS | VALENCIA | 3 |  | 8 | 2STY8CL | BATCH 1 | 16974790.26 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Bohol | 312315 | Rizal High Sschool | BATUAN | 3 | 1 | 8 | 2STY8CL | BATCH 1 | 16974790.26 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Bohol | 312352 | Cambuyo HS | GARCIA HERNANDEZ | 3 | 1 | 6 | 3STY6CL | BATCH 1 | 13739515.1 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Bohol | 312352 | Cambuyo HS | GARCIA HERNANDEZ | 3 |  | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302822 | Tubigon West NHS | TUBIGON | 1 | 1 | 4 | 1 unit 4STY 4 lab | Batch 3 | 18988498 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302824 | Mayor A. R. Tuazon Nat'l Sch. of Fisheries | CALAPE | 1 | 1 | 4 | 1 unit 4STY 4 lab | Batch 3 | 18882766 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302835 | Cawayanan NHS | TUBIGON | 1 | 1 | 8 | 1 unit 4STY 8 lab | Batch 3 | 40423613 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302839 | Corella National High School | CORELLA | 1 | 1 | 4 | 4STY 4 lab | Batch 6 Realignment | 18617613 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302877 | Mantacida National High School | CATIGBIAN | 1 | 1 | 2 | 1 unit 2STY 2 lab | Batch 3 | 10600582 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302881 | Pagnitoan National High School | MARIBOJOC | 1 | 1 | 8 | 1 unit 4STY 8 lab | Batch 3 | 38610442 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302883 | Calape National High School | CALAPE | 1 | 1 | 3 | 2 unit 3STY 3 lab | Batch 3 | 31322047 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Bohol | 302900 | San Roque National High School | ALBURQUERQUE | 1 | 1 | 4 | 2STY4CL | Batch 3 | 11529530 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302908 | Tabalong NHS | DAUIS | 1 | 1 | 4 | 4STY 4 lab | Batch 6 Realignment | 18911891 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Bohol | 312333 | Tubigon West Central HS | TUBIGON | 1 | 1 | 9 | 3STY9CL | Batch 3 | 27074015 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302808 | Aguining National High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 11055280.22 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302808 | Aguining National High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 |  | 6 | 2STY6CL (Regular workshop) | Batch 3 | 14159039.49 |  |  | Completed | 1 | [9 empty] | JECK CONSTRUCTION
NC 2018 | TVL | Region VII | Bohol | 302814 | Zosimo A. Gulle Memorial National High School | TALIBON | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10962735.9 |  |  | Completed | 1 | [9 empty] | ALGAMON CONSTRUCTION
NC 2018 | TVL | Region VII | Bohol | 302827 | Campao Oriental High School | JETAFE | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 11062735.9 |  |  | Completed | 1 | [9 empty] | WILTAN CONSTRUCTION
NC 2018 | TVL | Region VII | Bohol | 302828 | Handumon NHS | JETAFE | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 11055280.22 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302830 | Cangawa NHS | BUENAVISTA | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1 | [9 empty] | GMT BUILDERS & SUPPLY
NC 2018 | TVL | Region VII | Bohol | 302830 | Cangawa NHS | BUENAVISTA | 2 |  | 12 | 3STY12CL (Regular workshop) | Batch 3 | 32300000 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302836 | Clarin National School of Fisheries | CLARIN | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302841 | Danao NHS | DANAO | 2 |  | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1 | [9 empty] | AMAZING FIND BUILDERS CORPORATION
NC 2018 | TVL | Region VII | Bohol | 302843 | Francisco Dagohoy Memorial High School | DANAO | 2 | 1 | 4 | 2STY4CL (Regular workshop) | Batch 3 | 10962735.9 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302858 | Hinlayagan NHS | TRINIDAD | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 11000000 |  |  | Completed | 1 | [9 empty] | Rudhil Costruction
NC 2018 | TVL | Region VII | Bohol | 302859 | Southern Inabanga HS | INABANGA | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302879 | Nahawan NHS | CLARIN | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302886 | Pres. Carlos P. Garcia Technical Vocational School of Fisheries and Arts | BIEN UNIDO | 2 | 1 | 4 | 2STY4CL (Regular workshop) | Batch 3 | 10762735.9 |  |  | completed | 1 | [9 empty] | RUDHIL CONSTRUCTION & ENTERPRISES
NC 2018 | TVL | Region VII | Bohol | 302886 | Pres. Carlos P. Garcia Technical Vocational School of Fisheries and Arts | BIEN UNIDO | 2 |  | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302886 | Pres. Carlos P. Garcia Technical Vocational School of Fisheries and Arts | BIEN UNIDO | 2 |  | 6 | 2STY6CL (Regular workshop) | Batch 3 | 13786108.5 |  |  | Completed | 1 | [9 empty] | RUDHIL CONSTRUCTION & ENTERPRISES
NC 2018 | TVL | Region VII | Bohol | 302887 | San Agustin NHS | SAGBAYAN (BORJA) | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302887 | San Agustin NHS | SAGBAYAN (BORJA) | 2 |  | 4 | 2STY4CL (Regular workshop) | Batch 3 | 10762735.9 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302887 | San Agustin NHS | SAGBAYAN (BORJA) | 2 |  | 10 | 2STY10CL (Regular workshop) | Batch 3 | 21815765.83 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302888 | Eugenio V. Amores MHS | SAGBAYAN (BORJA) | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302891 | San Jose National High School | INABANGA | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1 | [9 empty] | GERSON CONST. & HARDWARE SUPPLY
NC 2018 | TVL | Region VII | Bohol | 302892 | Inabanga HS- Nabuad | INABANGA | 2 | 1 | 4 | 2STY4CL (Regular workshop) | Batch 3 | 10762735.9 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302892 | Inabanga HS- Nabuad | INABANGA | 2 |  | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302892 | Inabanga HS- Nabuad | INABANGA | 2 |  | 6 | 2STY6CL (Regular workshop) | Batch 3 | 13786108.5 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302893 | San Jose NHS | TALIBON | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302893 | San Jose NHS | TALIBON | 2 |  | 9 | 3STY9CL (Regular workshop) | Batch 3 | 27000000 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302893 | San Jose NHS | TALIBON | 2 |  | 12 | 3STY12CL (Regular workshop) | Batch 3 | 32100000 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302893 | San Jose NHS | TALIBON | 2 |  | 4 | 2STY4CL (Regular workshop) | Batch 3 | 10762735.9 |  |  | Completed | 1 | [9 empty] | RUDHIL CONSTRUCTION & ENTERPRISES
NC 2018 | TVL | Region VII | Bohol | 302895 | President Carlos P. Garcia Memorial High School | TALIBON | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10962735.9 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302896 | Sikatuna Nat'l Agricultural HS | TALIBON | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10962735.9 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 302913 | Tulang NHS | JETAFE | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10962735.9 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 312303 | Mayor Inocencio B. Mendez HS | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 6 | 2STY6CL (Regular workshop) | Batch 3 | 14159039.49 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 312303 | Mayor Inocencio B. Mendez HS | PRES. CARLOS P. GARCIA (PITOGO) | 2 |  | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 11055280.22 |  |  | Completed | 1 | [9 empty] | RUDHIL CONSTRUCTION & ENTERPRISES
NC 2018 | TVL | Region VII | Bohol | 312309 | JAPeR Memorial High School | SAGBAYAN (BORJA) | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 312312 | Panghagban HS | BUENAVISTA | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 312313 | Mayor Catalino Y. Casoyla MHS | TALIBON | 2 | 1 | 4 | 2STY4CL (Regular workshop) | Batch 3 | 11055280.22 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 312324 | Bonbonon High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 11055280.22 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 312325 | Gaus High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 11055280.22 |  |  | Completed | 1 | [9 empty] | MAI CONSTRUCTION & SUPPLY
NC 2018 | TVL | Region VII | Bohol | 312331 | Ponciana E. Leoligao HS | TALIBON | 2 | 1 | 6 | 2STY6CL (Regular workshop) | Batch 3 | 13786108.5 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 312335 | Basiao High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 11055280.22 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 312350 | San Isidro High School | TALIBON | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 10762735.9 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 312353 | Campamanog HS | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 4 | 2STY4CL (scie lab & ICT lab) | Batch 3 | 11055280.22 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Bohol | 312360 | Ponciano L. Padin National High School | BIEN UNIDO | 2 | 1 | 8 | 2STY8CL (Regular workshop) | Batch 3 | 19120864.64 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Bohol | 302870 | Lonoy Heroes MHS | JAGNA | 3 | 1 | 12 | 3STY12CL | Batch 3 | 29359267.25 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Bohol | 302880 | Oy NHS | LOBOC | 3 | 1 | 8 | 2STY8CL | Batch 3 | 17440775.18 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Bohol | 312311 | Mayor Pablo O. Lim MHS | VALENCIA | 3 | 1 | 12 | 3STY12CL | Batch 3 | 29359267.25 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Bohol | 312358 | Jagna HS | JAGNA | 3 | 1 | 12 | 3STY12CL | Batch 3 | 29359267.25 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Bohol | 312359 | Katipunan High School | ALICIA | 3 | 1 | 8 | 2STY8CL | Batch 3 | 17440775.18 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Bohol | 118745 | Banlasan ES | TRINIDAD | 2 | 1 | 2 | 1STY2CL | Batch 5 | 3394342 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Bohol | 118752 | Kauswagan ES | TRINIDAD | 2 | 1 | 2 | 1STY2CL | Batch 5 | 3394342 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Bohol | 500216 | Soom IS | TRINIDAD | 2 | 1 | 6 | 2STY6CL | Batch 5 | 13589942.7 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Carcar City | 119158 | Carcar Central ES | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 | [9 empty] | Quirante Construction
NC 2018 | K10 | Region VII | Carcar City | 119171 | Bolinawan ES | CITY OF CARCAR | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 13739515.1 |  |  | Completed | 1 | [9 empty] | Solidcore Construction
NC 2018 | SHS | Region VII | Carcar City | 303066 | OCAÑA NATIONAL HIGH SCHOOL | CITY OF CARCAR | 1 | 1 | 16 | 4STY16CL | BATCH 1 | 36910737.96 |  |  | Completed | 1 | [9 empty] | Quirante Construction
NC 2018 | SHS | Region VII | Carcar City | 303066 | OCAÑA NATIONAL HIGH SCHOOL | CITY OF CARCAR | 1 |  | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 | [9 empty] | Quirante Construction
NC 2018 | SHS | Region VII | Carcar City | 303066 | OCAÑA NATIONAL HIGH SCHOOL | CITY OF CARCAR | 1 |  | 8 | 4STY8CL | BATCH 1 | 17159570.67 |  |  | Completed | 1 | [9 empty] | Quirante Construction
NC 2018 | K10 | Region VII | Carcar City | 119158 | Carcar Central ES | CITY OF CARCAR | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22671910.24 |  |  | Completed | 1 | [10 empty] | Building Permit issue
NC 2018 | SHS | Region VII | Cebu | 303025 | Almacen-Torrevillas National High School | MEDELLIN | 4 | 1 | 6 | 3STY6CL | Batch 3 | 13839515.1 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Cebu | 119617 | Balud Elementary | SAN FERNANDO | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 14047305.4 |  |  | Completed | 1 |  |  | POO272296VS-CW1 | 18-HE-0099 | 2018-03-28 | 2018-04-04 | 2018-05-10 | 2018-06-05 | 2018-06-08 | BT Construction & Gen. Services
NC 2018 | SHS | Region VII | Cebu | 312421 | Bantayan Science High School | BANTAYAN | 4 | 1 | 8 | 4STY8CL | Batch 3 | 18938739.78 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Cebu | 119073 | Barili I Central ES | BARILI | 3 | 1 | 16 | 4STY16CL | BATCH 1 | 38940294.6 |  |  | Completed | 1 |  |  | P00272306VS | 18HF0129 | 2018-05-29 | 2018-06-05 | 2018-06-18 | 2018-06-22 | 2018-06-27 | GENETIAN BUILDERS
NC 2018 | SHS | Region VII | Cebu | 302939 | Bateria NHS | DAANBANTAYAN | 4 | 1 | 8 | 4STY8CL | Batch 3 | 17159570.67 |  |  | completed | 1
NC 2018 | K10 | Region VII | Cebu | 119453 | Bomedco ES | MEDELLIN | 4 | 1 | 9 | 3STY9CL | Batch 3 | 24468047.73 |  |  | Completed | 1 |  |  | P00274558VS-CW1 | 18HD0209 | [5 empty] | DINAH JANE CONSTRUCTION AND SUPPLY
NC 2018 | K10 | Region VII | Cebu | 118904 | Bonbon ES | ALOGUINSAN | 3 | 1 | 6 | 3STY6CL | BATCH 1 | 13814525.45 |  |  | completed | 1 |  |  | P00272304VS | 18HF0127 | 2018-05-29 | 2018-06-05 | 2018-06-18 | 2018-06-22 | 2018-06-27 | DINAH JANE CONST.& SUPPLY
NC 2018 | K10 | Region VII | Cebu | 119033 | Buanoy Central ES | BALAMBAN | 3 | 1 | 16 | 4STY16CL | BATCH 1 | 38940294.6 |  |  | Completed | 1 |  |  | P00272305VS | 18HF0128 | 2018-05-29 | 2018-06-05 | 2018-06-18 | 2018-06-22 | 2018-06-27 | JARC CONST.& MARINE SERVICES CORP.
NC 2018 | K10 | Region VII | Cebu | 119620 | Bugho ES | SAN FERNANDO | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 14104305.4 |  |  | Completed | 1 |  |  | POO272299VS-CW1 | 18-HE-0102 | 2018-03-28 | 2018-04-04 | 2018-05-10 | 2018-06-05 | 2018-06-08 | DT&C Construction
NC 2018 | SHS | Region VII | Cebu | 500221 | Busogon Integrated School | SAN REMIGIO | 4 | 1 | 8 | 4STY8CL | Batch 3 | 17259570.67 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Cebu | 302961 | Calape NHS | DAANBANTAYAN | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 1 | 2700000 |  |  | Completed | 1 |  |  | P00272318VS-CW1 | 18HD0145 | 2018-05-30 | 2018-06-08 | 2018-06-25 |  | 2018-07-06 | DINAH JANE CONSTRUCTION SUPPLY
NC 2018 | SHS | Region VII | Cebu | 302961 | Calape NHS | DAANBANTAYAN | 4 | 1 | 8 | 4STY8CL | Batch 3 | 17359570.67 |  |  | Completed | 1 |  |  |  | 18HD0165 | [5 empty] | SAN NARCISO BUILDERS CORPORATION
NC 2018 | K10 | Region VII | Cebu | 119410 | Calero ES | LILOAN | 5 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | completed | 1 |  |  |  | 18HI0058 | [5 empty] | CHUPUICO CONST.
NC 2018 | K10 | Region VII | Cebu | 119855 | CALMANTE ELEMENTARY SCHOOL | TUDELA | 5 | 1 | 6 | 2STY6CL | BATCH 1 | 11656168.02 |  |  | Completed | 1 |  |  |  | 18HI0067 | [5 empty] | GENETIAN BUILDERS
NC 2018 | SHS | Region VII | Cebu | 302967 | Camotes National High School | SAN FRANCISCO | 5 | 1 | 8 | 2STY8CL | Batch 3 | 17654337.16 |  |  | Completed | 1 |  |  |  | 18HI0059 | [5 empty] | GENETIAN BUILDERS
NC 2018 | K10 | Region VII | Cebu | 119597 | Cansayahon ES | RONDA | 7 | 1 | 6 | 2STY6CL | BATCH 1 | 11716168.02 |  |  | Completed | 1 |  |  | P00272338VS-CW1 | 18HG0136 | 2018-04-11 | 2018-04-18 | 2018-04-30 | 2018-05-29 | 2018-06-06 | APRIL ROSE ENT. & BUILDERS
NC 2018 | SHS | Region VII | Cebu | 302984 | Colawin NHS | ARGAO | 2 | 1 | 16 | 4STY16CL | BATCH 1 | 36910737.96 |  |  | Completed | 1 |  |  | P00272301VS-CW1 | 18HG0132 | 2018-04-11 | 2018-04-18 | 2018-04-30 | 2018-05-29 | 2018-06-06 | DINAH JANE CONST. SUPPLY
NC 2018 | K10 | Region VII | Cebu | 119831 | Colonia Central ES | TUBURAN | 3 | 1 | 9 | 3STY9CL | BATCH 1 | 26420056.92 |  |  | Completed | 1 |  |  | P00272310VS | 18HF0133 | 2018-05-30 | 2018-06-06 | 2018-06-19 | 2018-06-25 | 2018-06-28 | RUDHIL CONST. & ENTERPRISES
NC 2018 | K10 | Region VII | Cebu | 119856 | Daan Secante ES | TUDELA | 5 | 1 | 6 | 2STY6CL | BATCH 1 | 11656168.02 |  |  | Completed | 1 |  |  |  | 18HI0066 | [5 empty] | GENETIAN BUILDERS
NC 2018 | SHS | Region VII | Cebu | 302995 | Daanbantayan National High School | DAANBANTAYAN | 4 | 1 | 8 | 4STY8CL | Batch 3 | 17159570.67 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Cebu | 303001 | Dapdap NHS, San Remigio | SAN REMIGIO | 4 | 1 | 8 | 4STY8CL | Batch 3 | 18049155.23 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Cebu | 119377 | Dumanjug Central ES | DUMANJUG | 7 | 1 | 9 | 3STY9CL | Batch 3 | 24558047.73 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Cebu | 119645 | Esperanza ES | SAN FRANCISCO | 5 | 1 | 9 | 3STY9CL | BATCH 1 | 24468047.73 |  |  | Completed | 1 |  |  |  | 18HI0061 | [5 empty] | VIRLO CONST.
NC 2018 | K10 | Region VII | Cebu | 119228 | Estaca ES | COMPOSTELA | 5 | 1 | 12 | 4STY12CL | BATCH 1 | 31649789.72 |  |  | Completed | 1 |  |  |  | 18HI0071 | [5 empty] | ASCENTIA CONST.
NC 2018 | K10 | Region VII | Cebu | 119094 | Japitan ES | BARILI | 3 | 1 | 8 | 4STY8CL | BATCH 1 | 17420383.73 |  |  | Completed | 1 |  |  | P00272307VS | 18HF0130 | 2018-05-29 | 2018-06-05 | 2018-06-18 | 2018-06-22 | 2018-06-27 | FIRST BUILDERS & DEVELOPERS
NC 2018 | SHS | Region VII | Cebu | 312404 | Jose Chona Jo Memorial National High School | BALAMBAN | 3 | 1 | 12 | 4STY12CL | BATCH 1 | 31539789.72 |  |  | Completed | 1 |  |  | P00272314VS | 18HF0137 | 2018-05-30 | 2018-06-06 | 2018-06-19 | 2018-06-25 | 2018-06-28 | JEGMA CONST. & DEVT. CORP.
NC 2018 | SHS | Region VII | Cebu | 303103 | Juan Pamplona NHS | TABUELAN | 4 | 1 | 12 | 3STY12CL | Batch 3 | 31151517.79 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Cebu | 119241 | Jugan ES | CONSOLACION | 6 | 1 | 12 | 4STY12CL | BATCH 1 | 31649789.72 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Cebu | 119753 | Kal-anan ES | TABOGON | 4 | 1 | 9 | 3STY9CL | BATCH 1 | 24498047.73 |  |  | Completed | 1 |  |  | P00272317VS-CW1 | 18HD0147 | 2018-05-30 | 2018-06-08 | 2018-07-05 |  | 2018-07-20 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2018 | SHS | Region VII | Cebu | 303024 | Kawit NHS | MEDELLIN | 4 | 1 | 6 | 3STY6CL | Batch 3 | 13964515.1 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Cebu | 303011 | Lanipga NHS | CONSOLACION | 6 | 1 | 6 | 3STY6CL | BATCH 1 | 13739515.1 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Cebu | 303011 | Lanipga NHS | CONSOLACION | 6 |  | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Cebu | 119414 | Liloan Central ES | LILOAN | 5 | 1 | 16 | 4STY16CL | BATCH 1 | 36910737.96 |  |  | Completed | 1 |  |  |  | 18HI0068 | [5 empty] | EDISON DEV'T. & CONST.
NC 2018 | K10 | Region VII | Cebu | 119485 | Lipata Central ES | MINGLANILLA | 1 | 1 | 16 | 4STY16CL | BATCH 1 | 37668952.72 |  |  | Completed | 1 |  |  | POO272295VS-CW1 | 18-HE-0098 | 2018-03-28 | 2018-04-04 | 2018-05-10 | 2018-06-05 | 2018-06-08 | ARQ Builders
NC 2018 | SHS | Region VII | Cebu | 303042 | Lipata NHS | MINGLANILLA | 1 | 1 | 16 | 4STY16CL | BATCH 1 | 37708952.72 |  |  | Completed | 1 |  |  | POO272297VS-CW1 | 18-HE-0100 | 2018-03-28 | 2018-04-04 | 2018-05-10 | 2018-06-05 | 2018-06-08 | Quirante Construction
NC 2018 | SHS | Region VII | Cebu | 303042 | Lipata NHS | MINGLANILLA | 1 | 1 | 8 | 4STY8CL | Batch 3 | 18678345.15 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Cebu | 303044 | Looc Norte NHS | ASTURIAS | 3 | 1 | 16 | 4STY16CL | BATCH 1 | 38422952.32 |  |  | Completed | 1 |  |  | P00272310VS | 18HF0134 | 2018-05-30 | 2018-06-06 | 2018-06-19 | 2018-06-25 | 2018-06-28 | JARC CONST.& MARINE SERVICES CORP.
NC 2018 | SHS | Region VII | Cebu | 303008 | Luciano B. Rama Sr. MNHS | PORO | 5 | 1 | 16 | 4STY16CL | Batch 3 | 37988576.19 |  |  | Completed | 1 |  |  |  | 18HI0067 | [5 empty] | GENETIAN BUILDERS
NC 2018 | SHS | Region VII | Cebu | 303047 | Madridejos NHS | MADRIDEJOS | 4 | 1 | 16 | 4STY16CL | Batch 3 | 38872189.63 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Cebu | 119098 | Mantalongon ES | BARILI | 3 | 1 | 16 | 4STY16CL | BATCH 1 | 37318080.24 |  |  | Completed | 1 |  |  | P00272308VS | 18HF0131 | 2018-05-29 | 2018-06-05 | 2018-06-18 | 2018-06-22 | 2018-06-27 | JARC CONST & MARINE SERVICES CORP.
NC 2018 | SHS | Region VII | Cebu | 303052 | Mantalongon NHS | BARILI | 3 | 1 | 16 | 4STY16CL | BATCH 1 | 36800737.72 |  |  | Completed | 1 |  |  | P00272312VS | 18HF0135 | 2018-05-30 | 2018-06-06 | 2018-06-19 | 2018-06-25 | 2018-06-28 | JARC CONST & MARINE SERVICES CORP.
NC 2018 | K10 | Region VII | Cebu | 119100 | Paril ES | BARILI | 3 | 1 | 6 | 3STY6CL | BATCH 1 | 13889545.21 |  |  | Completed | 1 |  |  | P00272300VS-CW1 | 18HF0126 | 2018-05-29 | 2018-06-05 | 2018-06-18 | 2018-06-22 | 2018-06-27 | SOLIDCORE CONSTRUCTION
NC 2018 | SHS | Region VII | Cebu | 312409 | Patao NHS | BANTAYAN | 4 | 1 | 8 | 4STY8CL | Batch 3 | 18049155.23 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Cebu | 303060 | Putat NHS | TUBURAN | 3 | 1 | 12 | 4STY12CL | BATCH 1 | 33272004.08 |  |  | Completed | 1 |  |  | P00272313VS | 18HF0136 | 2018-05-30 | 2018-06-06 | 2018-06-19 | 2018-06-25 | 2018-06-28 | DINAH JANE CONSTRUCTION & SUPPLY
NC 2018 | K10 | Region VII | Cebu | 119601 | Ronda Central ES | RONDA | 7 | 1 | 9 | 3STY9CL | Batch 3 | 24558047.73 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Cebu | 119648 | Rosalia N Lucernas ES | SAN FRANCISCO | 5 | 1 | 6 | 2STY6CL | BATCH 1 | 11656168.02 |  |  | Completed | 1 |  |  |  | 18HI0063 | [5 empty] | GENETIAN BUILDERS
NC 2018 | K10 | Region VII | Cebu | 119467 | Rosalino L. Arreglado ES | MEDELLIN | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 9005901.75 |  |  | Completed | 1 |  |  | P00272315VS-CW1 | 18HD0144 | 2018-05-30 | 2018-06-08 | 2018-06-25 |  | 2018-07-06 | GONZALODO ENT.
NC 2018 | SHS | Region VII | Cebu | 303090 | Samboan National High School | SAMBOAN | 2 | 1 | 12 | 4STY12CL | BATCH 1 | 31669789.72 |  |  | Completed | 1 |  |  | P00272303VS-CW1 | 18HG0134 | 2018-04-11 | 2018-04-18 | 2018-04-30 | 2018-05-29 | 2018-06-06 | ORANI BUILDERS
NC 2018 | K10 | Region VII | Cebu | 119650 | San Francisco Central ES | SAN FRANCISCO | 5 | 1 | 20 | 4STY20CL | BATCH 1 | 41408409.74 |  |  | Completed | 1 |  |  |  | 18HI0072 | [5 empty] | PLD CONST.
NC 2018 | SHS | Region VII | Cebu | 303087 | San Remegio NHS | SAN REMIGIO | 4 | 1 | 8 | 4STY8CL | Batch 3 | 17284570.67 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Cebu | 303089 | San Sebastian NHS | SAMBOAN | 2 | 1 | 16 | 4STY16CL | BATCH 1 | 36910737.96 |  |  | Completed | 1 |  |  | P00272302VS-CW1 | 18HG0133 | 2018-04-11 | 2018-04-18 | 2018-04-30 | 2018-05-29 | 2018-06-06 | ORANI BUILDERS
NC 2018 | SHS | Region VII | Cebu | 303102 | Simala National High School | SIBONGA | 1 | 1 | 8 | 4STY8CL | BATCH 1 | 17229570.67 |  |  | Completed | 1 |  |  | POO272298VS-CW1 | 18-HE-0101 | 2018-03-28 | 2018-04-04 | 2018-05-10 | 2018-06-05 | 2018-06-08 | RCDG Const Corp./AT Dumlao
NC 2018 | SHS | Region VII | Cebu | 303102 | Simala National High School | SIBONGA | 1 | 1 | 8 | 4STY8CL | Batch 3 | 18299570.98 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Cebu | 119653 | Sonog ES | SAN FRANCISCO | 5 | 1 | 9 | 3STY9CL | BATCH 1 | 24468047.73 |  |  | Completed | 1 |  |  |  | 18HI0062 | [5 empty] | ASCENTIA CONST.
NC 2018 | K10 | Region VII | Cebu | 119572 | Tajao Central School | PINAMUNGAHAN | 3 | 1 | 6 | 3STY6CL | BATCH 1 | 14437360.69 |  |  | completed | 1 |  |  | P00272309VS | 18HF0132 | 2018-05-29 | 2018-06-05 | 2018-06-18 | 2018-06-22 | 2018-06-27 | CELGEM CONST. & DEVT. CORP.
NC 2018 | SHS | Region VII | Cebu | 119683 | Tambongon Integrated School | SAN REMIGIO | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8965901.76 |  |  | completed | 1 |  |  | P00272316VS-CW1 | 18HD0146 | 2018-05-30 | 2018-06-08 | 2018-06-25 |  | 2018-07-06 | GOLDFIN CONSTRUCTION & DEVELOPMENT CORP.
NC 2018 | SHS | Region VII | Cebu | 302964 | Tapilon National High School | DAANBANTAYAN | 4 | 1 | 8 | 4STY8CL | Batch 3 | 17159570.67 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Cebu | 119382 | Tapon ES | DUMANJUG | 7 | 1 | 10 | 2STY10CL | BATCH 1 | 19708155.67 |  |  | Completed | 1 |  |  | P00272337VS-CW1 | 18HG0135 | 2018-04-11 | 2018-04-18 | 2018-04-30 | 2018-05-29 | 2018-06-06 | QM BUILDERS JV (APRIL ROSE)
NC 2018 | K10 | Region VII | Cebu | 119248 | Tayud ES | CONSOLACION | 6 | 1 | 20 | 4STY20CL | BATCH 1 | 41408409.74 |  |  | completed | 1
NC 2018 | K10 | Region VII | Cebu | 119248 | Tayud ES | CONSOLACION | 6 |  | 16 | 4STY16CL | BATCH 1 | 36910737.96 |  |  | completed | 1
NC 2018 | SHS | Region VII | Cebu | 302965 | Tominjao National High School | DAANBANTAYAN | 4 | 1 | 8 | 4STY8CL | Batch 3 | 18299155.23 |  |  | Completed | 1 |  |  |  | 18HD0176 | [5 empty] | BANTAY CONSTRUCTION
NC 2018 | K10 | Region VII | Cebu | 119863 | Tudela Central ES | TUDELA | 5 | 1 | 9 | 3STY9CL | BATCH 1 | 24468047.73 |  |  | Completed | 1 |  |  |  | 18HI0065 | [5 empty] | GENETIAN BUILDERS
NC 2018 | K10 | Region VII | Cebu | 119657 | Unidos ES | SAN FRANCISCO | 5 | 1 | 6 | 2STY6CL | BATCH 1 | 11656168.02 |  |  | Completed | 1 |  |  |  | 18HI0064 | [5 empty] | ASCENTIA CONST.
NC 2018 | K10 | Region VII | Cebu | 119423 | Yati Elementary School | LILOAN | 5 | 1 | 20 | 4STY20CL | BATCH 1 | 41460909.74 |  |  | Completed | 1 |  |  |  | 18HI0069 | [5 empty] | EDISON DEV'T. & CONST.
NC 2018 | K10 | Region VII | Cebu | 119423 | Yati Elementary School | LILOAN | 5 |  | 20 | 4STY20CL | BATCH 1 | 41460909.74 |  |  | Completed | 1 |  |  |  | 18HI0070 | [5 empty] | DUROS DEV'T. CORP.
NC 2018 | K10 | Region VII | Cebu City | 119901 | Mabolo ES | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 1 | 20809475.06 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Cebu City | 119904 | Talamban Elementary School | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 1 | 20534567.08 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Cebu City | 119931 | Zapatera ES (Night/Sped) | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 1 | 20823220.52 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Cebu City | 303140 | Talamban NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 1 | 20511935.95 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Cebu City | 303165 | Vicente Cosido NHS (Cambinocot NHS) | CEBU CITY (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 17048243.55 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Cebu City | 119879 | Banawa ES | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 1 | 20534567.08 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Cebu City | 119880 | Guadalupe ES | CEBU CITY (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 1 | 37851920.18 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Cebu City | 119885 | Labangon Bliss ES | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 1 | 20532370.66 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Cebu City | 119916 | Sawang Calero ES | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 1 | 20615557.73 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Cebu City | 303133 | Don Vicente Rama Mem. NHS (Basak NHS) | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 1 | 20461813.92 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Cebu City | 303150 | Don Sergio Osme¤a, Sr. Memorial HS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 1 | 20567649.03 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Cebu City | 312506 | Tisa National High School ( Day & Night) | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 1 | 21062380.75 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Cebu City | 312513 | ALASKA HS | CEBU CITY (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 1 | 20604599.6 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Cebu City | 119900 | Guba Elementary School | CEBU CITY (Capital) | 1 | 1 | 6 | 3STY6CL | Batch 3 | 18697242.47 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Cebu City | 312503 | Banilad Night HS | CEBU CITY (Capital) | 1 | 1 | 12 | 4STY12CL | Batch 3 | 34937939.03 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Cebu City | 119886 | Labangon Elementary School | CEBU CITY (Capital) | 2 | 1 | 12 | 4STY12CL | Batch 3 | 34883165.92 |  |  | Completed | 1
NC 2018 | K10 | Region VII | City of Naga, Cebu | 119504 | Cantao-an Elementary School | CITY OF NAGA | 1 | 1 | 4 | 2STY4CL | Batch 3 | 10109687.41 |  |  | Reverted | 0
NC 2018 | K10 | Region VII | City of Naga, Cebu | 119508 | Naalad Elementary School | CITY OF NAGA | 1 | 1 | 6 | 3STY6CL | Batch 3 | 14870654.72 |  |  | Completed | 1 |  |  | P00274581VS-CW1 | 18-HE-0136 | 2018-10-26 | 2018-11-06 | 2018-11-19 | 2018-11-28 | 2018-12-05 | January Builders
NC 2018 | K10 | Region VII | City of Naga, Cebu | 119509 | Naga Central ES | CITY OF NAGA | 1 | 1 | 8 | 4STY8CL | Batch 3 | 18215680.56 |  |  | Completed | 1 |  |  | P00274582VS-CW1 | 18-HE-0141 | 2018-10-26 | 2018-11-06 | 2018-11-19 | 2018-11-28 | 2018-12-05 | Quirante Construction
NC 2018 | K10 | Region VII | City of Naga, Cebu | 119510 | NPC-Colon Elementary School | CITY OF NAGA | 1 | 1 | 6 | 2STY6CL | Batch 3 | 12787968.58 |  |  | completed | 1 |  |  | P00274583VS-CW1 | 18-HE-0134 | 2018-10-26 | 2018-11-06 | 2018-11-19 | 2018-12-03 | 2018-12-06 | E.G. & I. Construction Corporation
NC 2018 | K10 | Region VII | City of Naga, Cebu | 119512 | Tuyan Central Elementary School | CITY OF NAGA | 1 | 1 | 9 | 3STY9CL | Batch 3 | 25595570.32 |  |  | Completed | 1 |  |  | P00274584VS-CW1 | 18-HE-0145 | 2018-10-26 | 2018-11-06 | 2018-11-19 | 2018-11-26 | 2018-12-05 | Quirante Construction
NC 2018 | K10 | Region VII | City of Naga, Cebu | 119518 | Langtad ES | CITY OF NAGA | 1 | 1 | 9 | 3STY9CL | Batch 3 | 25608910.5 |  |  | Completed | 1 |  |  | P00274585VS-CW1 | 18-HE-0146 | 2018-10-26 | 2018-11-06 | 2018-11-19 | 2018-11-26 | 2018-12-05 | Celjem Construction & Development Corp.
NC 2018 | SHS | Region VII | Danao City | 303037 | Maslog National High School | DANAO CITY | 5 | 1 | 6 | 3STY6CL | BATCH 1 | 13739515.1 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Danao City | 322003 | Ramon M. Durano Sr. Foundation - Science and Technology Education Center | DANAO CITY | 5 | 1 | 12 | 3STY12CL | BATCH 1 | 29359267.25 |  |  | Completed | 1 |  |  |  | 18HI0060 | [5 empty] | DUROS DEV'T. CORP.
NC 2018 | K10 | Region VII | Danao City | 119355 | Portland ES | DANAO CITY | 5 | 1 | 4 | 2STY4CL | Batch 3 | 8945901.76 |  |  | Completed | 1 |  |  |  | 18HI0060 | [5 empty] | LLABAN CONST. SUPPLY
NC 2018 | K10 | Region VII | Danao City | 119366 | Maslog Elementary School | DANAO CITY | 5 | 1 | 4 | 2STY4CL | Batch 3 | 8945901.76 |  |  | Completed | 1 |  |  |  | 18HI0056 | [5 empty] | DINAH JANE CONSTRUCTION SUPPLY
NC 2018 | K10 | Region VII | Dumaguete City | 119939 | West City ES | DUMAGUETE CITY (Capital) | 2 | 1 | 9 | 3STY9CL | Batch 5 | 24659327.73 |  |  | completed | 1 | [10 empty] | with items for rectification; ongoing processing of occupancy permit
NC 2018 | K10 | Region VII | Dumaguete City | 119939 | West City ES | DUMAGUETE CITY (Capital) | 2 |  | 9 | 3STY9CL | Batch 5 | 24659327.73 |  |  | completed | 1 | [10 empty] | with items for rectification; ongoing processing of building and occupancy permits
NC 2018 | TVL | Region VII | Guihulngan City | 303230 | GUIHULNGAN NATIONAL AGRICULTURAL SCHOOL | CITY OF GUIHULNGAN | 1 | 1 | 1 | unique workshop (7x22.5) | Batch 3 | 5318886.42 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Guihulngan City | 303230 | GUIHULNGAN NATIONAL AGRICULTURAL SCHOOL | CITY OF GUIHULNGAN | 1 |  | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 15945215.59 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Guihulngan City | 303230 | GUIHULNGAN NATIONAL AGRICULTURAL SCHOOL | CITY OF GUIHULNGAN | 1 |  | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 15945215.59 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Guihulngan City | 303231 | Guihulngan NHS - Poblacion | CITY OF GUIHULNGAN | 1 | 1 | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 12663637.17 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Guihulngan City | 303231 | Guihulngan NHS - Poblacion | CITY OF GUIHULNGAN | 1 |  | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 12663637.17 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Guihulngan City | 303231 | Guihulngan NHS - Poblacion | CITY OF GUIHULNGAN | 1 |  | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 12663637.17 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Guihulngan City | 303231 | Guihulngan NHS - Poblacion | CITY OF GUIHULNGAN | 1 |  | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 12663637.17 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Guihulngan City | 303233 | Guihulngan NHS - Hilaitan | CITY OF GUIHULNGAN | 1 | 1 | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 15588497.76 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Guihulngan City | 303275 | Tagbino National High School | VALLEHERMOSO | 1 | 1 | 1 | unique workshop (7x22.5) | Batch 3 | 5561195.51 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Guihulngan City | 312904 | Guba High School | VALLEHERMOSO | 1 | 1 | 1 | unique workshop (7x22.5) | Batch 3 | 5318886.42 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Guihulngan City | 312960 | Pinucauan High School | VALLEHERMOSO | 1 | 1 | 1 | unique workshop (7x22.5) | Batch 3 | 5561195.51 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Guihulngan City | 312960 | Pinucauan High School | VALLEHERMOSO | 1 |  | 4 | 4STY WORKSHOP BLDG. (7 X 18) | Batch 3 | 22078748.8 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Guihulngan City | 120236 | Bonbon ES | CITY OF GUIHULNGAN | 1 | 1 | 4 | 2UNITS 1STY2CL | Batch 5 | 9070339.31 |  |  | Reverted | 0 | [10 empty] | No bidders
NC 2018 | K10 | Region VII | Lapu-Lapu City | 119967 | Mactan ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 20 | 4STY20CL | BATCH 1 | 41665909.74 |  |  | Completed | 1 |  |  | P0022354VS-CW1 | 18HN0065 | 2018-05-30 | 2018-06-08 | 2018-06-20 | 2018-06-22 | 2018-07-05 | QM Builders/ Docast Const. (JV)
NC 2018 | K10 | Region VII | Lapu-Lapu City | 119978 | Maribago Elementary School | LAPU-LAPU CITY (OPON) | 6 | 1 | 12 | 4STY12CL | Batch 3 | 31766289.72 |  |  | Completed | 1 |  |  | P00274600VS-CW1 | 18HN0078 | 2018-10-15 | 2018-10-26 | 2018-11-07 | 2018-11-22 | 2018-12-05 | Gonzalodo Enterprises
NC 2018 | K10 | Region VII | Mandaue City | 119994 | Cesar M. Cabahug ES (Looc) | MANDAUE CITY | 6 | 1 | 12 | 4STY12CL | Batch 3 | 31743013.78 |  |  | Completed | 1 |  |  | P00274601VS-C1 | 18HN0079 | 2018-10-15 | 2018-10-26 | 2018-11-07 |  | 2018-11-29 | PLD CONST. &DEV'T. CORP
NC 2018 | K10 | Region VII | Mandaue City | 119995 | Mayor A.S. Fortuna Memorial ES | MANDAUE CITY | 6 | 1 | 8 | 4STY8CL | Batch 3 | 18043793.49 |  |  | Completed | 1 |  |  | P00274602VS-C2 | 18HN0080 | 2018-10-15 | 2018-10-26 | 2018-11-07 |  | 2018-11-29 | BANTAY CONSTRUCTION
NC 2018 | K10 | Region VII | Mandaue City | 119998 | Basak ES | MANDAUE CITY | 6 | 1 | 12 | 4STY12CL | Batch 3 | 30797968.8 |  |  | Completed | 1 |  |  | P00274602VS-C3 | 18HN0081 | 2018-10-15 | 2018-10-26 | 2018-11-07 |  | 2018-11-29 | P.B. OBIAL CONSTRUCTION
NC 2018 | K10 | Region VII | Mandaue City | 120000 | Leonard Wood ES | MANDAUE CITY | 6 | 1 | 8 | 4STY8CL | Batch 3 | 18094736.83 |  |  | Completed | 1 |  |  | P00274602VS-C4 | 18HN0082 | 2018-10-15 | 2018-10-26 | 2018-11-07 |  | 2018-11-29 | PLD CONST. &DEV'T. CORP
NC 2018 | K10 | Region VII | Mandaue City | 120001 | Opao ES | MANDAUE CITY | 6 | 1 | 8 | 4STY8CL | Batch 3 | 18100260.76 |  |  | Completed | 1 |  |  | P00274602VS-C5 | 18HN0083 | 2018-10-15 | 2018-10-26 | 2018-11-07 |  | 2018-11-29 | BANTAY CONSTRUCTION
NC 2018 | TVL | Region VII | Tagbilaran City | 302874 | Manga National High School | TAGBILARAN CITY (Capital) | 1 | 1 | 2 | 2UNITS 1STY TVL BLDG. | Batch 5 | 10943463 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Talisay City | 119788 | Maghaway ES | CITY OF TALISAY | 1 | 1 | 9 | 3STY9CL | Batch 3 | 28343650.67 |  |  | completed | 1
NC 2018 | SHS | Region VII | Talisay City | 303056 | Mohon (Divino Amore) National High School | CITY OF TALISAY | 1 | 1 | 12 | 4STY12CL | Batch 3 | 32798595.44 |  |  | completed | 1
NC 2018 | SHS | Region VII | Talisay City | 303088 | San Roque NHS | CITY OF TALISAY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 23021167.14 |  |  | completed | 1
NC 2018 | SHS | Region VII | Talisay City | 303113 | Talisay City National High School | CITY OF TALISAY | 1 |  | 8 | 4STY8CL | Batch 3 | 22721533.51 |  |  | completed | 1
NC 2018 | SHS | Region VII | Talisay City | 303113 | Talisay City National High School | CITY OF TALISAY | 1 |  | 8 | 4STY8CL | Batch 3 | 22810602.9 |  |  | completed | 1
NC 2018 | SHS | Region VII | Talisay City | 322201 | Maghaway National High School | CITY OF TALISAY | 1 | 1 | 6 | 3STY6CL | Batch 3 | 15089654.21 |  |  | completed | 1
NC 2018 | TVL | Region VII | Tanjay City | 312926 | Apolinario Gerarda Arnaiz HS | PAMPLONA | 2 | 1 | 2 | 2sty-1 science lab & 1 ict lab | BATCH 1 | 9792614.55 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Tanjay City | 303281 | Azagra High School | Tanjay City North | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 17024055.32 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Tanjay City | 120412 | Cantilo ES | Pamplona | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11847329.18 |  |  | Completed | 1
NC 2018 | SHS | Region VII | Tanjay City | 322301 | Graciano Banogon HS | Tanjay City North | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12005853.06 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Tanjay City | 303274 | Isidoro Salma MSHS (Balayong ) | PAMPLONA | 2 | 1 | 2 | 2sty- 2 ict lab | BATCH 1 | 9831976.52 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Tanjay City | 303274 | Isidoro Salma MSHS (Balayong ) | PAMPLONA | 2 |  | 2 | 2sty- 2 science lab | BATCH 1 | 9331976.52 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Tanjay City | 303288 | Lourdes L. del Prado MNHS (Sto. Niño) | CITY OF TANJAY | 2 | 1 | 2 | 2sty-1 science lab & 1 ict lab | BATCH 1 | 10257801.44 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Tanjay City | 303284 | Lourdes Ledesma Del Prado MNHS | CITY OF TANJAY | 2 | 1 | 2 | 2sty-1 science lab & 1 ict lab | BATCH 1 | 9720152.75 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Tanjay City | 322303 | Nagsala HS | CITY OF TANJAY | 2 | 1 | 4 | 2sty-2 science lab & 2 ict lab | BATCH 1 | 18153176.82 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Tanjay City | 303259 | Pamplona NHS | PAMPLONA | 2 | 1 | 8 | 4sty- 2 science lab, 2 ict lab & 4 regular workshop | BATCH 1 | 38517097.09 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Tanjay City | 120572 | Plaza CS | CITY OF TANJAY | 2 |  | 9 | 3STY9CL | BATCH 1 | 26036130.06 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Tanjay City | 303273 | Sta. Agueda National High School | PAMPLONA | 2 | 1 | 2 | 2sty- 2 ict lab | BATCH 1 | 9792614.55 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Tanjay City | 303273 | Sta. Agueda National High School | PAMPLONA | 2 |  | 2 | 2sty- 2 science lab | BATCH 1 | 9292614.55 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Tanjay City | 312905 | Sta. Agueda NHS - Calicanan HS Ext. | PAMPLONA | 2 | 1 | 2 | 2sty- 2 ict lab | BATCH 1 | 10093196.85 |  |  | Completed | 1
NC 2018 | TVL | Region VII | Tanjay City | 303283 | Tanjay City Science HS | CITY OF TANJAY | 2 | 1 | 4 | 4sty- 2 science lab & 2 ict lab | BATCH 1 | 19089144.91 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Tanjay City | 120576 | Tanjay City South Central School | CITY OF TANJAY | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9004050.12 |  |  | Completed | 1
NC 2018 | K10 | Region VII | Toledo City | 120711 | Apid ES | TOLEDO CITY | 3 | 1 | 8 | 4STY8CL | BATCH 1 | 17470383.73 |  |  | Completed | 1 |  |  | P00272383VS | 18HF0138 | 2018-05-30 | 2018-06-06 | 2018-06-19 | 2018-06-25 | 2018-06-28 | Edison Devt., & Construction
NC 2018 | K10 | Region VII | Toledo City | 120757 | South City Central ES | TOLEDO CITY | 3 | 1 | 20 | 4STY20CL | BATCH 1 | 43322493.84 |  |  | Completed | 1 |  |  | P0027384VS | 18HF0139 | 2018-05-30 | 2018-06-06 | 2018-06-19 | 2018-06-25 | 2018-06-28 | BL Pangan Construction
NC 2019 | K10 | Region VII | Bayawan City | 120121 | Bahian E/S | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED |  | 2509551.1824 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | TVL | Region VII | Bayawan City | 303217 | Basay National High School | BASAY | 3 | 1 | 8 | 4STY8LAB (4 Reg. Workshop, 2 SCI LAB, 2 ICT) |  | 39416104.9561 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Bayawan City | 120128 | Dawis Elementary School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 6 | 2STY6CL |  | 15901486.5599 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Bayawan City | 120153 | Hag-um Primary School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL |  | 4362400.1032 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | SHS | Region VII | Bogo City | 500408 | Don Celestino Martinez Sr. Taytayan IS | CITY OF BOGO | 4 | 1 | 4 | 2STY4CL |  | 9791535.6045 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Bohol | 118696 | Abucay ES | SIKATUNA | 1 | 1 | 3 | 1STY3CL |  | 7200957.5 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Bohol | 118555 | Bolod ES | PANGLAO | 1 | 1 | 3 | 1STY3CL |  | 7164667 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Bohol | 118277 | Lapsaon ES | DIMIAO | 3 | 1 | 2 | 1STY2CL |  | 4272098.9634 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Bohol | 118560 | Lourdes ES | PANGLAO | 1 | 1 | 3 | 1STY3CL |  | 7118351.5 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Bohol | 118858 | Omjon ES | VALENCIA | 3 | 1 | 2 | 1STY2CL |  | 4390167.0976 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Bohol | 186501 | Pagahat ES | ALICIA | 3 | 1 | 2 | 1STY2CL |  | 4096105.3566 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Bohol | 118562 | Panglao Central ES | PANGLAO | 1 | 1 | 4 | 2STY4CL |  | 10454982.275 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Bohol | 118023 | Quirino PS | BATUAN | 3 | 1 | 2 | 1STY2CL |  | 4390167.0976 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Bohol | 118039 | Sagasa ES | BIEN UNIDO | 2 | 1 | 2 | 1STY2CL |  | 2988873.4698 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Bohol | 118723 | San Agustin Elementary School | TALIBON | 2 | 1 | 2 | 1STY2CL |  | 2817025 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Bohol | 118723 | San Agustin Elementary School | TALIBON | 2 |  | 2 | 1STY2CL |  | 3402827.855 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Bohol | 117964 | Talisay PS | ANDA | 3 | 1 | 4 | 1STY4CL |  | 7422886.8899 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Bohol | 118564 | Tawala ES | PANGLAO | 1 | 1 | 2 | 1STY2CL |  | 5112810.15 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Carcar City | 500726 | Puesto Integrated School | CITY OF CARCAR | 1 | 1 | 4 | 2STY4CL |  | 12899852.9694 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Cebu | 118917 | Argao I Central ES | ARGAO | 2 | 1 | 8 | 2STY8CL |  | 22343418.2475 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Cebu | 119472 | Bacay ES | MINGLANILLA | 1 | 1 | 12 | 4STY12CL |  | 42401040.6961 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Cebu | 118998 | Basiao PS | BADIAN | 7 | 1 | 2 | 1STY2CL |  | 4106081.3043 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Cebu | 118998 | Basiao PS | BADIAN | 7 |  | 2 | 1STY2CL |  | 4106081.3043 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Cebu | 119316 | Casay ES | DALAGUETE | 2 | 1 | 4 | 2STY4CL |  | 13627365.455 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Cebu | 119409 | Ernesto V. Veloso ES (Cabadiangan ES) | LILOAN | 5 | 1 | 4 | 2STY4CL |  | 9552777.9489 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Cebu | 119561 | Lamac ES | PINAMUNGAHAN | 3 | 1 | 12 | 4STY12CL |  | 39448812.1602 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Cebu | 119303 | Libo PS | DALAGUETE | 2 | 1 | 4 | 2STY4CL |  | 12542361.5095 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Cebu | 119322 | Malones Elementary School | DALAGUETE | 2 | 1 | 4 | 2STY4CL |  | 12391986.5095 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region VII | Cebu | 302963 | Paypay NHS | DAANBANTAYAN | 4 | 1 | 10 | 3STY10CL |  | 30567091.6612 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Cebu | 119247 | Polog ES | CONSOLACION | 6 | 1 | 2 | 1STY2CL |  | 4178445.8144 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Cebu | 119862 | Secante Bag-o PS | TUDELA | 5 | 1 | 6 | 2STY6CL |  | 12238899.9274 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Cebu | 119422 | Tiltilon ES | LILOAN | 5 | 1 | 12 | 4STY12CL |  | 33384584.508 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Cebu City | 119872 | Cambinocot ES | CEBU CITY (Capital) | 1 | 1 | 8 | 4STY8CL |  | 24130195.2605 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Cebu City | 119869 | Sinsin ES | CEBU CITY (Capital) | 2 | 1 | 6 | 3STY6CL |  | 20265495.2246 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | City of Naga, Cebu | 302929 | Balirong National High School | CITY OF NAGA | 1 | 1 | 4 | 2STY4CL |  | 13311193.1654 |  | COMPLETED | 1 |  |  |  | 19-HE-0103 |  | 2019-08-02 | 2019-08-14 |  |  |  |  | 0
NC 2019 | SHS | Region VII | Danao City | 322001 | Ubaldo Iway Memo. NHS | DANAO CITY | 5 | 1 | 6 | 2STY6CL |  | 11656095.169 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Guihulngan City |  | Binobohan HS | CITY OF GUIHULNGAN | 1 | 1 | 6 | 2STY6CL |  | 16295464.2279 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Guihulngan City | 120271 | Kapudlusan PS | CITY OF GUIHULNGAN | 1 | 1 | 3 | 1STY3CL W/ TOILET |  | 5293200 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Guihulngan City | 189509 | Mandi-i ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY2CL |  | 4411000 |  | COMPLETED | 1 | [10 empty] | Temporarily suspended | 0
NC 2019 | SHS | Region VII | Mandaue City | 303194 | Cabancalan NHS | MANDAUE CITY | 6 | 1 | 8 | 4STY8CL |  | 18426169.347 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | SHS | Region VII | Tagbilaran City | 302846 | Dr. Cecilio Putong NHS (Bohol NHS) | TAGBILARAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL |  | 4535390.6511 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VII | Toledo City | 120745 | Ibo Elementary School | TOLEDO CITY | 3 | 1 | 9 | 3STY9CL |  | 28260329.3067 |  | COMPLETED | 1 | [11 empty] | 0
NC 2020 | SHS | Region VII | Bais City | 323004 | Cambagahan National HS | BAIS CITY | 2 | 1 | 4 | 2STY4CL |  | 10395925 |  |  | completed | 1
NC 2020 | K10 | Region VII | Bayawan City | 120118 | Olandao Elementary School | BASAY | 3 | 1 | 8 | 2STY8CL |  | 23388679.27 |  |  | completed | 1 | [10 empty] | no manpower on site
NC 2020 | SHS | Region VII | Bohol | 302819 | Busao National High School | MARIBOJOC | 1 | 1 | 6 | 1unit 4STY4 lab |  | 28390800 |  |  | completed | 1
NC 2020 | K10 | Region VII | Bohol | 118029 | Bilangbilangan East PS | BIEN UNIDO | 2 | 1 | 2 | 1STY2CL |  | 4852018.28 |  |  | completed | 1
NC 2020 | K10 | Region VII | Bohol | 118034 | Maomawan ES | BIEN UNIDO | 2 | 1 | 2 | 1STY2CL |  | 4852018.28 |  |  | completed | 1
NC 2020 | K10 | Region VII | Bohol | 118070 | Cambus-oc ES | BUENAVISTA | 2 | 1 | 2 | 1STY2CL |  | 4341232.88 |  |  | completed | 1
NC 2020 | K10 | Region VII | Bohol | 118072 | Cantores PS | BUENAVISTA | 2 | 1 | 2 | 1STY2CL |  | 4341232.88 |  |  | completed | 1
NC 2020 | K10 | Region VII | Bohol | 118082 | Overland ES | BUENAVISTA | 2 | 1 | 2 | 1STY2CL |  | 4341232.88 |  |  | completed | 1
NC 2020 | K10 | Region VII | Bohol | 118186 | Bonbon Elementary School | CLARIN | 2 | 1 | 2 | 1STY2CL |  | 4497620.36 |  |  | completed | 1
NC 2020 | K10 | Region VII | Bohol | 118192 | Cantoyoc PS | CLARIN | 2 | 1 | 2 | 1STY2CL |  | 4341232.88 |  |  | completed | 1
NC 2020 | TVL | Region VII | Bohol | 118749 | Guinobatan ES | TRINIDAD | 2 | 1 | 6 | 2 Sty, 6 CL Regular Workshop |  | 16424189.23 |  |  | completed | 1
NC 2020 | TVL | Region VII | Bohol | 118759 | Mahagbu ES | TRINIDAD | 2 | 1 | 4 | 2 Sty 4 CL (Regular Workshop) |  | 13676945.58 |  |  | completed | 1
NC 2020 | K10 | Region VII | Bohol | 118768 | Trinidad Central Elementary School | TRINIDAD | 2 | 1 | 8 | Modified Standard 2 STY, 8CL |  | 22690056.01 |  |  | completed | 1
NC 2020 | K10 | Region VII | Bohol | 118424 | Jagna Central ES | JAGNA | 3 | 1 | 2 | 1STY2CL |  | 5513750 |  |  | completed | 1
NC 2020 | SHS | Region VII | Bohol | 302860 | Katipunan NHS | CARMEN | 3 | 1 | 8 | 2STY8CL |  | 24702058.04 |  |  | completed | 1
NC 2020 | K10 | Region VII | Cebu | 119477 | Minglanilla Central ES | MINGLANILLA | 1 | 1 | 8 | 4STY8CL |  | 26004445.5 |  |  | completed | 1
NC 2020 | K10 | Region VII | Cebu | 312472 | Badian NHS - Sanlagan Ext. | BADIAN | 2 | 1 | 6 | 2STY6CL |  | 17543750 |  |  | COMPLETED | 1
NC 2020 | K10 | Region VII | Cebu | 500487 | Minolos IS | BARILI | 3 | 1 | 12 | 4STY12CL |  | 39021945.87 |  |  | completed | 1
NC 2020 | K10 | Region VII | Cebu | 119266 | Daanbantayan Central ES | DAANBANTAYAN | 4 | 1 | 12 | 4STY12CL |  | 35406257.75 |  |  | COMPLETED | 1
NC 2020 | SHS | Region VII | Cebu | 500655 | Bagalnga Integrated School | COMPOSTELA | 5 | 1 | 12 | 4STY12CL |  | 36420261.13 |  |  | completed | 1
NC 2020 | K10 | Region VII | Cebu | 119257 | Gabi ES | CORDOBA | 6 | 1 | 6 | 3STY6CL |  | 18259500.34 |  |  | completed | 1
NC 2020 | K10 | Region VII | Cebu | 500894 | Ginatilan Integrated School | GINATILAN | 7 | 1 | 8 | 4STY8CL |  | 24710864.2 |  |  | completed | 1
NC 2020 | SHS | Region VII | Dumaguete City | 303171 | Taclobo NHS | DUMAGUETE CITY | 2 | 1 | 4 | 2STY4CL |  | 9123973.58 |  |  | completed | 1
NC 2020 | K10 | Region VII | Guihulngan City | 120248 | Lag-asan ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY2CL |  | 3920777.5 |  |  | COMPLETED | 1
NC 2020 | K10 | Region VII | Guihulngan City | 120628 | Don Julian dela Vina Villegas Memorial ES | Vallehermoso | 1 | 1 | 2 | 1STY2CL |  | 3569902.5 |  |  | completed | 1
NC 2020 | K10 | Region VII | Guihulngan City | 120634 | Malangsa ES | Vallehermoso | 1 | 1 | 3 | 1STY3CL |  | 5159867.5 |  |  | COMPLETED | 1
NC 2020 | K10 | Region VII | Guihulngan City | 120249 | Laos ES | City of Guihulngan | 1 | 1 | 6 | 2 units 1Sty3CL W/ CR |  | 14496150 |  |  | COMPLETED | 1
NC 2020 | K10 | Region VII | Tagbilaran City | 118713 | Tagbilaran City Central Elementary School | TAGBILARAN CITY (Capital) | 1 | 1 | 24 | 4STY24CL |  | 57228955.6 |  |  | COMPLETED | 1
NC 2020 | SHS | Region VII | Tagbilaran City | 302846 | Dr. Cecilio Putong NHS (Bohol NHS) | TAGBILARAN CITY (Capital) | 1 | 1 | 12 | 4STY12CL |  | 37503994.17 |  |  | completed | 1
NC 2020 | SHS | Region VII | Tagbilaran City | 302846 | Dr. Cecilio Putong NHS (Bohol NHS) | TAGBILARAN CITY (Capital) | 1 |  | 20 | 4STY20CL |  | 52701826 |  |  | completed | 1
NC 2020 | SHS | Region VII | Tagbilaran City | 302876 | Tagbilaran City Science High School | TAGBILARAN CITY (Capital) | 1 | 1 | 4 | 4 Sty, 4 Lab |  | 29704469.99 |  |  | Completed | 1
NC 2020 | K10 | Region VII | Talisay City | 119803 | Tabunoc Central Elem. School | CITY OF TALISAY | 1 | 1 | 16 | 4STY16CL |  | 41637101.72 |  |  | completed | 1
NC 2020 | K10 | Region VII | Tanjay City | 120409 | Banawe Elementary School | Pamplona | 2 | 1 | 2 | 1STY2CL W/ TOILET |  | 4200475 |  |  | completed | 1
NC 2020 | K10 | Region VII | Tanjay City | 120565 | Pilipigan Lnd. PIS | Tanjay | 2 | 1 | 2 | 1STY2CL W/ TOILET |  | 5002475 |  |  | REVERTED | 0 | [10 empty] | realigned
NC 2021 | K10 | Region VII | Bayawan City | 120121 | Bahian E/S | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | Construction/Completion (1STY2CL W/ TOILET ATTACHED) |  | 1182861.0682 | 1179911.29 |  | REVERTED | 0 | [10 empty] | Reverted
NC 2021 | K10 | Region VII | Bayawan City | 120121 | Bahian E/S | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | Construction/Completion (1STY2CL W/ TOILET ATTACHED) |  | 1182861.0682 | 1179911.29 | 1179717.93 | COMPLETED | 1 | 2022-03-13 |  | P00575132VS-CW1 | 21HL0148 |  |  |  |  | 2021-11-03 | HASA KONSTRUKT AND SUPPLY | Remaining work is energization from the Elec Coop
NC 2021 | K10 | Region VII | Bayawan City | 120132 | Lapay Elementary School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1509144.242 | 1505380.79 | 1504692 | COMPLETED | 1 | 2022-02-07 |  | P00575134VS-CW1 | 21HL0146 |  |  |  |  | 2021-11-03 | MG CONSTRUCTION | Remaining work is energization from the Elec Coop
NC 2021 | K10 | Region VII | Bayawan City | 120143 | Banga CES | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | Construction/Completion (1STY2CL W/ TOILET) |  | 1016440.4241 | 1013905.66 | 1013314.82 | COMPLETED | 1 | 2022-03-14 |  | P00575135VS-CW1 | 21HL0147 |  |  |  |  | 2021-11-03 | H.I.T. CONTRACTORS | Remaining work is energization from the Elec Coop
NC 2021 | TVL | Region VII | Bayawan City | 303218 | Actin National High School | BASAY | 3 | 1 | 4 | Construction/Completion (4STY4LAB (2 Reg. Workshop, 2 ICT)) |  | 2602796.1234 | 2596305.36 | 2591636.75 | COMPLETED | 1 | 2022-02-07 |  | P00575136VS-CW1 | 21HL0149 |  |  |  |  | 2021-11-03 | SBK CONSTRUCTION INC. | Remaining work is energization from the Elec Coop
NC 2021 | TVL | Region VII | Bayawan City | 303219 | Bal-os National High School | BASAY | 3 | 1 | 4 | Construction/Completion (4STY4LAB (2 Reg. Workshop, 2 SCI LAB)) |  | 1753681.9216 | 1749308.65 | 1744152 | COMPLETED | 1 | 2022-02-07 |  | P00575137VS-CW1 | 21HL0150 |  |  |  |  | 2021-11-03 | TRIBATA CONSTRUCTION AND DEVELOPMENT
NC 2021 | TVL | Region VII | Bayawan City | 303220 | Maglinao National High School | BASAY | 3 | 1 | 4 | Construction/Completion (4STY4LAB (2 Reg. Workshop, 2 ICT)) |  | 2633074.1697 | 2626507.9 | 2611258 | COMPLETED | 1 | 2022-01-31 |  | P00575138VS-CW1 | 21HL0145 |  |  |  |  | 2021-10-25 | TRIBATA CONSTRUCTION AND DEVELOPMENT
NC 2021 | TVL | Region VII | Bayawan City | 303227 | Dawis National High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | Construction/Completion (4STY4LAB (2 SCI LAB, 2 ICT)) |  | 1878599.3163 | 1873914.53 | 1865945.6 | COMPLETED | 1 | 2022-01-30 |  | P00575139VS-CW1 | 21HL0142 |  |  |  |  | 2021-10-26 | SBK CONSTRUCTION INC. | Remaining work is energization from the Elec Coop
NC 2021 | TVL | Region VII | Bayawan City | 321902 | Bayawan City Science and Technology Education Center - High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | Construction/Completion (4STY4LAB (2 SCI LAB, 2 ICT)) |  | 2770637.4002 | 2763728.08 | 2713684.8 | Completed | 1 | 2022-01-25 |  | P00575140VS-CW1 | 21HL0143 |  |  |  |  | 2021-10-25 | PHILSOUTH BUILDERS INC.
NC 2021 | SHS | Region VII | Bayawan City | 321912 | Cansumalig High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 9 | Construction/Completion (3STY9CL) |  | 1917448.3968 | 1912666.73 | 1856039 | Completed | 1 | 2022-01-30 |  | P00575141VS-CW1 | 21HL0144 |  |  |  |  | 2021-10-26 | SBK CONSTRUCTION INC.
NC 2021 | K10 | Region VII | Bohol | 117930 | Bahi PS | ALBURQUERQUE | 1 | 1 | 2 | Construction/Completion (1STY2CL) |  | 751574.25 | 749700 | 744700 | Completed | 1 | 2021-11-28 | 2021-11-19 | P00575142VS | 21HA0192 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-12 | 2021-09-28 | C. JANSEN CONSTRUCTION AND GENEREAL MERCHANDISE
NC 2021 | K10 | Region VII | Bohol | 117967 | Angilan ES | Antequera | 1 | 1 | 3 | Construction/Completion (1STY3CL) |  | 408188.9275 | 407171 | 404976.36 | Completed | 1 | 2021-11-28 | 2021-10-25 | P00575143VS | 21HA0193 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-12 | 2021-09-30 | GAIL CONSTRUCTION & SUPPLY
NC 2021 | K10 | Region VII | Bohol | 117985 | Tanday ES | BACLAYON | 1 | 1 | 1 | Construction/Completion (1STY1CL) |  | 426944.7 | 425880 | 420880 | Completed | 1 | 2021-11-26 | 2021-11-19 | P00575144VS | 21HA0188 | 2021-07-07 | 2021-07-14 | 2021-07-26 | 2021-08-10 | 2021-09-28 | C. JANSEN CONSTRUCTION AND GENEREAL MERCHANDISE
NC 2021 | K10 | Region VII | Bohol | 118213 | New Lourdes ES | CORTES | 1 | 1 | 1 | Construction/Completion (1STY1CL) |  | 399634.595 | 398638 | 397660.11 | Completed | 1 | 2021-11-28 | 2021-11-08 | P00575145VS | 21HA0194 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-12 | 2021-09-30 | 3N CONSTRUCTION & SUPPLY
NC 2021 | K10 | Region VII | Bohol | 118481 | Cantaongon ES | Loon North | 1 | 1 | 1 | Construction/Completion (1STY1CL) |  | 381314.91 | 380364 | 375337 | Completed | 1 | 2021-11-28 | 2021-10-25 | P00575146VS | 21HA0195 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-12 | 2021-09-30 | 3N CONSTRUCTION & SUPPLY
NC 2021 | K10 | Region VII | Bohol | 118564 | Tawala ES | PANGLAO | 1 | 1 | 1 | Construction/Completion (1STY1CL) |  | 435786.75 | 434700 | 429700 | Completed | 1 | 2021-11-26 | 2021-11-19 | P00575147VS | 21HA0189 | 2021-07-07 | 2021-07-14 | 2021-07-26 | 2021-08-10 | 2021-09-28 | C. JANSEN CONSTRUCTION AND GENEREAL MERCHANDISE
NC 2021 | SHS | Region VII | Bohol | 305543 | Felix E. Bompat High School | PANGLAO | 1 | 1 | 4 | Construction/Completion (4CL) |  | 38095000 | 38000000 | 37429645.88 | COMPLETED | 1 | 2022-04-24 |  | P00575144VS | 21HA0187 | 2021-07-07 | 2021-07-14 | 2021-07-26 | 2021-08-10 | 2021-09-27 | BNYU DEVELOPMENT CORP. | Delivery of materials may cause delay due to unpassable road, muddy when rain falls
NC 2021 | SHS | Region VII | Bohol | 500211 | San Roque Integrated School | BALILIHAN | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 19248000 | 19200000 | 18831184.62 | Completed | 1 | 2022-02-28 |  | P00575144VS | 21HA0191 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-12 | 2021-09-27 | LAWRENCE BUILDERS & SUPPLY | Building Permit on process
NC 2021 | K10 | Region VII | Bohol | 118039 | Sagasa ES | BIEN UNIDO | 2 | 1 | 2 | Construction/Completion (1STY2CL) |  | 1047888.3178 | 1045275.13 |  | Completed | 1 |  | 2021-11-15
NC 2021 | K10 | Region VII | Bohol | 118723 | San Agustin Elementary School | TALIBON | 2 | 1 | 2 | Construction/Completion (1STY2CL) |  | 460620.9507 | 459472.27 |  | Completed | 1
NC 2021 | K10 | Region VII | Bohol | 118723 | San Agustin Elementary School | TALIBON | 2 |  | 2 | Construction/Completion (1STY2CL) |  | 1100664.79 | 1097919.99 |  | Completed | 1
NC 2021 | K10 | Region VII | Bohol | 117964 | Talisay PS | ANDA | 3 | 1 | 4 | Construction/Completion (1STY4CL) |  | 1561182.1423 | 1557288.92 |  | Completed | 1
NC 2021 | K10 | Region VII | Bohol | 118277 | Lapsaon ES | DIMIAO | 3 | 1 | 2 | Construction/Completion (1STY2CL) |  | 803470.5071 | 801466.84 |  | Completed | 1
NC 2021 | K10 | Region VII | Bohol | 186501 | Pagahat ES | ALICIA | 3 | 1 | 2 | Construction/Completion (1STY2CL) |  | 859370.9497 | 857227.88 |  | Completed | 1
NC 2021 | SHS | Region VII | Carcar City | 500726 | Puesto Integrated School | CITY OF CARCAR | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 6494267.591 | 6478072.41 |  | COMPLETED | 1
NC 2021 | K10 | Region VII | Cebu | 119305 | Mantalongon ES | DALAGUETE | 2 | 1 | 9 | Construction of Slope Protection |  | 721634.5975 | 719835.01 |  | COMPLETED | 1
NC 2021 | SHS | Region VII | Cebu | 303089 | San Sebastian NHS | SAMBOAN | 2 | 1 | 16 | Construction/Completion (4STY16CL) |  | 941800.6099 | 939451.98 |  | COMPLETED | 1
NC 2021 | K10 | Region VII | Cebu | 119420 | Tabla ES | LILOAN | 5 | 1 | 4 | Construction (1 UNIT 1STY2CL) |  | 4210500 | 4200000 |  | COMPLETED | 1
NC 2021 | SHS | Region VII | Cebu | 303011 | Lanipga NHS | CONSOLACION | 6 | 1 | 4 | Construction/Completion (2STY4CL) |  | 6484523.3612 | 6468352.48 |  | COMPLETED | 1
NC 2021 | K10 | Region VII | Cebu | 119382 | Tapon ES | DUMANJUG | 7 | 1 | 10 | Construction/Completion (2STY10CL) |  | 293122.6492 | 292391.67 |  | COMPLETED | 1
NC 2021 | SHS | Region VII | Cebu City | 303131 | Binaliw NHS | CEBU CITY (Capital) | 1 | 1 | 2 | Construction/Completion (1STY2CL) |  | 2040433.4728 | 2035345.11 |  | COMPLETED | 1
NC 2021 | SHS | Region VII | Cebu City | 303132 | Lusaran NHS | CEBU CITY (Capital) | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 348504.3983 | 347635.31 |  | COMPLETED | 1
NC 2021 | SHS | Region VII | Cebu City | 303155 | TEJERO NHS(DAY & NIGHT) | CEBU CITY (CAPITAL) | 1 | 1 | 12 | Construction/Completion (4STY12CL) |  | 813869.6201 | 811840.02 |  | COMPLETED | 1
NC 2021 | SHS | Region VII | Cebu City | 500227 | TAPTAP IS | CEBU CITY (CAPITAL) | 1 | 1 | 6 | Construction/Completion (3STY6CL) |  | 1160622.5706 | 1157728.25 |  | COMPLETED | 1
NC 2021 | TVL | Region VII | Cebu City | 303133 | DON VICENTE RAMA MEM. NHS (BASAK NHS) | CEBU CITY (CAPITAL) | 2 | 1 | 1 | Construction/Completion (SHS UNIQUE WORKSHOP) |  | 368298.5502 | 367380.1 |  | COMPLETED | 1
NC 2021 | TVL | Region VII | Cebu City | 303164 | SUDLON NHS | CEBU CITY (CAPITAL) | 2 | 1 | 1 | Construction/Completion (SHS UNIQUE WORKSHOP) |  | 289807.2213 | 289084.51 |  | COMPLETED | 1
NC 2021 | SHS | Region VII | Cebu City | 312502 | BABAG HS | CEBU CITY (CAPITAL) | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1935394.8711 | 1930568.45 |  | COMPLETED | 1
NC 2021 | SHS | Region VII | Cebu City | 312507 | PAMUTAN INTEGRATED SCHOOL | CEBU CITY (CAPITAL) | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1999454.0798 | 1994467.91 |  | COMPLETED | 1
NC 2021 | K10 | Region VII | Cebu City | 312515 | Quiot High School | CEBU CITY (CAPITAL) | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 2671353.6699 | 2664691.94 |  | COMPLETED | 1
NC 2021 | TVL | Region VII | Cebu City | 500225 | Tabunan Integrated School | CEBU CITY (Capital) | 2 | 1 | 1 | Construction/Completion (1 unit Standard Technical and Vocational Building) |  | 1023904.3374 | 1021350.96 |  | COMPLETED | 1
NC 2021 | K10 | Region VII | Guihulngan City | 120625 | Don Vicente Lopez, Sr. MS (Bagawines ES) | VALLEHERMOSO | 1 | 1 | 1 | Construction/Completion (1STY1CL) |  | 1674175 | 1670000 |  | COMPLETED | 1
NC 2021 | K10 | Region VII | Guihulngan City | 120628 | Don Julian dela Vina Villegas Memorial ES | VALLEHERMOSO | 1 | 1 | 2 | Construction/Completion (1STY2CL) |  | 3011510 | 3004000 |  | COMPLETED | 1
NC 2021 | K10 | Region VII | Guihulngan City | 120638 | Tabon Elementary School | VALLEHERMOSO | 1 | 1 | 1 | Construction/Completion (1STY1CL) |  | 1674175 | 1670000 |  | COMPLETED | 1
NC 2021 | SHS | Region VII | Guihulngan City | 303230 | GUIHULNGAN NATIONAL AGRICULTURAL SCHOOL | CITY OF GUIHULNGAN | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 8461100 | 8440000 |  | COMPLETED | 1
NC 2021 | K10 | Region VII | Mandaue City | 119995 | Mayor A.S. Fortuna Memorial ES | MANDAUE CITY | 6 | 1 | 8 | Construction/Completion (4STY8CL) |  | 2122608.7887 | 2117315.5 |  | COMPLETED | 1
NC 2021 | K10 | Region VII | Tagbilaran City | 118712 | San Isidro ES | Tagbilaran City | 1 | 1 | 2 | Construction/Completion (1STY2CL) |  | 717469.2 | 715680 |  | Completed | 1
NC 2021 | K10 | Region VII | Tagbilaran City | 118714 | Taloto ES | Tagbilaran City | 1 | 1 | 2 | Construction/Completion (1STY2CL) |  | 701048.25 | 699300 |  | Completed | 1 | [9 empty] | C. Jansen Construction and General Merchandise
NC 2021 | K10 | Region VII | Tanjay City | 120423 | Pamplona CES | PAMPLONA | 2 | 1 | 18 | Construction/Completion (2UNITS 3STY9CL) |  | 54135000 | 54000000 |  | Completed | 1
NC 2022 | K10 | Region VII | Bais City | 120077 | Olympia Elementary School | BAIS CITY | 2 | 1 | 4 | 2STY4CL | 2 |  | 13127737.5 | 13095000 | Completed | 1 | 2023-06-20 | 2023-06-20 | P00675013VS-CW1 | 22HK0103 | 2022-06-07 | 2022-07-14 | 2022-07-26 | 2022-11-14 | 2022-11-24 | SILLIMAN AVENUE CONST & SUPPLY
NC 2022 | K10 | Region VII | Bohol | 117934 | Tagbuane Elementary School | ALBURQUERQUE | 1 | 1 | 2 | 1STY2CL | 2 |  | 7352335 | 7334000 | Completed | 1 | 2023-04-29 | 2023-06-25 | P00675014VS | 22HA0182 | 2022-04-11 | 2022-11-15 | 2022-11-28 | 2022-11-29 | 2022-12-12 | GERSON Construction and Hardware Supply | The project was issued with Monthly Time Suspension due to unfavorable weather condition. PCMA update is on process due to revised construction shcedule and will be updated once approved by the BOC.
NC 2022 | K10 | Region VII | Bohol | 186510 | Pandol Primary School | CORELLA | 1 | 1 | 2 | 1STY2CL | 2 |  | 7300205 | 7281995.1 | Completed | 1 | 2023-05-27 | 2023-03-29 | P00675015VS | 22HA0183 | 2022-04-11 | 2022-11-15 | 2022-11-28 | 2022-12-28 | 2023-09-01 | LAWRENCE Builders & Supply | The project is already completed at site. PCMA Data Correction is for approval due to approved Variation Order. Project status will be updated once approved by the BOC.
NC 2022 | K10 | Region VII | Bohol | 305722 | De La Paz High School | CORTES | 1 | 1 | 2 | 1STY2CL | 2 |  | 7300205 | 7139785.54 | Completed | 1 | 2023-05-27 | 2023-06-26 | P00675016VS | 22HA0184 | 2022-04-11 | 2022-11-15 | 2022-11-28 | 2022-12-28 | 2023-09-01 | SLP Construction | The project was issued with Monthly Time Suspension due to unfavorable weather condition. PCMA update is on process due to revised construction shcedule and will be updated once approved by the BOC.
NC 2022 | K10 | Region VII | Bohol | 118227 | Mahayag Elementary School | DAGOHOY | 2 | 1 | 2 | 1STY2CL | 2 |  | 5012500 | 4979901.4 | Completed | 1 | 2023-05-17 | 2023-03-07 | P00675018VS | 22HC0119 | 2022-11-29 | 2022-11-28 | 2022-12-19 | 2022-12-21 | 2023-04-01 | RAMYER CONST. & SUPPLY | Issued Monthly Time Suspension
NC 2022 | K10 | Region VII | Bohol | 117954 | Bacong ES | ANDA | 3 | 1 | 2 | 1STY2CL | 2 |  | 6107077.7202 | 6091553.91 | Completed | 1 | 2023-03-05 | 2023-03-05 | P00675021VS-CW1 | 22HB0158 | 2022-11-28 | 2022-07-12 | 2022-12-20 | 2022-12-27 | 2023-04-01 | WBV CONSTRUCTION | With approved Contract Time Extension of 30 CD.
NC 2022 | K10 | Region VII | Bohol | 118019 | Garcia ES | BATUAN | 3 | 1 | 2 | 1STY2CL | 2 |  | 6107077.7202 | 6027541.75 | Completed | 1 | 2023-03-04 | 2023-04-21 | P00675022VS-CW1 | 22HB0157 | 2022-11-28 | 2022-07-12 | 2022-12-20 | 2022-12-27 | 2023-04-01 | ALAY BALAY DEVELOPMENT CORP | Awaiting for the aprroval of Contract Time Extension for 18 CD
NC 2022 | K10 | Region VII | Bohol | 118671 | Magsaysay ES | SEVILLA | 3 | 1 | 2 | 1STY2CL | 2 |  | 6107077.7202 | 5973898.36 | Completed | 1 | 2023-03-04 | 2023-02-06 | P00675023VS-CW1 | 22HB0156 | 2022-11-28 | 2022-07-12 | 2022-12-20 | 2022-12-27 | 2023-04-01 | WILTAN CONSTRUCTION | Variation Order & Request for Contract Time Extension on process.
NC 2022 | K10 | Region VII | Cebu | 119266 | Daanbantayan Central ES | DAANBANTAYAN | 4 | 1 | 12 | 4STY12CL | 2 |  | 32186354.2225 | 32075000 | Completed | 1 | 2023-06-05 | 2023-11-21 | P00675024VS-CW1 | 22HD0068 | 2022-07-06 | 2022-07-13 | 2022-07-25 | 2022-11-14 | 2022-11-23 | TRIUNE MACRO BUILDERS JV WITH ANGAS CONSTRUCTION
NC 2022 | K10 | Region VII | Cebu | 501669 | Hagnaya IS | SAN REMIGIO | 4 | 1 | 12 | 3STY12CL | 2 |  | 32186354.2225 | 32076089 | Ongoing | 0.95 | 2023-05-31 |  | P00675025VS-CW1 | 22HD0069 | 2022-07-06 | 2022-07-13 | 2022-07-25 | 2022-11-14 | 2022-11-23 | SAN NARCISO BUILDERS CORPORATION
NC 2022 | K10 | Region VII | Guihulngan City | 120280 | Pitogo PS | CITY OF GUIHULNGAN | 1 | 1 | 5 | 1STY2CL WITH CR EACH CLASSROOM AND 1STY3CL WITH CR EACH CLASSROOM | 2 |  | 11401432.5 | 11373000 | Ongoing | 0.9 | 2023-11-05 |  | P00675028VS-CW1 | 22HJ0111 | 2022-06-24 | 2022-01-07 | 2022-07-15 | 2022-11-16 | 2022-11-28 | K.M. Golong Construction
NC 2022 | SHS | Region VII | Bais City | 303216 | Bais City National Science High School | BAIS CITY | 2 | 1 | 4 | 2STY4CL | 2 |  | 13689137.5 | 12963482.6 | Completed | 1 | 2023-05-14 | 2023-05-14 | P00675012VS-CW1 | 22HK0102 | 2022-06-07 | 2022-07-14 | 2022-07-26 | 2022-11-14 | 2022-11-24 | DOUBLE J AND T CONSTRUCTION AND SUPPLY CORPORATION
NC 2022 | SHS | Region VII | Bohol | 500217 | Danahaw IS | CLARIN | 2 | 1 | 2 | 1STY2CL | 2 |  | 5012500 | 4950000 | Completed | 1 | 2023-05-17 | 2023-08-08 | P00675017VS | 22HC0118 | 2022-11-29 | 2022-11-28 | 2022-12-19 | 2022-12-21 | 2023-04-01 | MAI CONST & SUPPLY | Issued Monthly Time Suspension
NC 2022 | SHS | Region VII | Bohol | 312327 | Candungao High School | SAN ISIDRO | 2 | 1 | 2 | 1STY2CL | 2 |  | 5012500 | 4999998.53 | Completed | 1 | 2023-05-17 | 2023-07-08 | P00675019VS | 22HC0120 | 2022-11-29 | 2022-11-28 | 2022-12-19 | 2022-12-21 | 2023-04-01 | MAI CONST & SUPPLY | Issued Monthly Time Suspension
NC 2022 | SHS | Region VII | Bohol | 303130 | Erico B. Aumentado High School | UBAY | 2 | 1 | 12 | 4STY12CL | 2 |  | 38190237.5 | 38029995.58 | Ongoing | 0.8 | 2024-09-05 |  | P00655020VS | 22HC0121 | 2023-09-06 | 2023-10-06 | 2023-06-29 | 2023-08-14 | 2023-08-05 | DINA RBS & SUPPLY INC. | Issued Notice To Proceed dated May 9, 2023
NC 2022 | SHS | Region VII | Cebu | 303032 | Dapdap NHS | PILAR | 5 | 1 | 12 | 2UNITS 3STY6CL | 2 |  | 33384584.508 | 33266500 | Ongoing | 0.95 | 2023-11-05 |  | P00675026VS-CW1 | 22HI0077 | 2022-11-19 | 2022-11-28 | 2022-12-12 | 2022-12-23 | 2023-01-10 | MPJR BUILDERS COMPANY
NC 2022 | SHS | Region VII | Cebu | 303080 | Puertobello NHS | TUDELA | 5 | 1 | 6 | 3STY6CL | 2 |  | 17544375.56 | 17470514 | Ongoing | 0.95 | 2023-07-08 |  | P00675027VS-CW1 | 22HI0078 | 2022-11-19 | 2022-11-28 | 2022-12-12 | 2022-12-23 | 2023-01-10 | CYJE FIRST BUILDERS CONSTRUCTION CORP | FOR PUNCHLIST COMPLIANCE
NC 2023 | K10 | Region VII | Bohol | 118004 | Dorol ES | BALILIHAN |  | 1 |  | 5 | Batch 1 | 14556262.5 | 14430000 | 14361419.81 | Completed | 1 | 2024-05-24 | 2023-12-15 | P00775086VS | 23HA0108 | 2023-07-06 | 2023-07-14 | 2023-07-26 | 2023-07-28 | 2023-08-08 | 3N Construction & Supply
NC 2023 | K10 | Region VII | Bohol | 500211 | San Roque Integrated School | BALILIHAN |  | 1 |  | 6 | Batch 1 | 18422474.39 | 18262675.97 | 18242123.89 | Completed | 1 | 2024-02-15 | 2024-02-15 | P00775087VS | 23HA0116 | 2023-08-08 | 2023-08-15 | 2023-08-29 | 2023-08-31 | 2023-09-11 | 3N Construction & Supply
NC 2023 | K10 | Region VII | Bohol | 305722 | De La Paz High School | CORTES |  | 1 |  | 2 | Batch 1 | 6556875 | 6500000 | 6440000 | Completed | 1 | 2023-12-26 | 2023-06-26 | P00775088VS | 23HA0109 | 2023-07-06 | 2023-07-14 | 2023-07-26 | 2023-07-28 | 2023-08-08 | 3N Construction & Supply
NC 2023 | K10 | Region VII | Bohol | 118063 | Bato Elementary School | BUENAVISTA |  | 1 |  | 0 | Batch 1 | 5043750 | 5000000 | 4321958.33 | Completed | 1 | 2024-03-22 | 2023-06-27 | P00775089VS | 23HC0124 | 2023-06-27 | 2023-06-26 | 2023-07-17 | 2023-09-20 | 2023-10-04 | 3N CONST. & SUPPLY
NC 2023 | SHS | Region VII | Bohol | 302836 | Clarin National School of Fisheries | CLARIN |  | 1 |  | 4 | Batch 1 | 11065987.5 | 10970000 | 9648940.65 | Completed | 1 | 2024-04-29 | 2023-06-27 | P00775090VS | 23HC0129 | 2023-06-27 | 2023-06-26 | 2023-07-17 | 2023-08-30 | 2023-10-04 | WYNN CONST.
NC 2023 | SHS | Region VII | Bohol | 302840 | Dagohoy NHS | DAGOHOY |  | 1 |  | 8 | Batch 1 | 26731875 | 26500000 | 22125830 | Ongoing | 1 | 2024-06-05 | 2024-06-05 | P00775093VS | 23HC0133 | 2023-08-29 | 2023-08-18 | 2023-09-11 | 2023-09-23 | 2023-10-04 | MAI CONST. & SUPPLY
NC 2023 | K10 | Region VII | Bohol | 118227 | Mahayag Elementary School | DAGOHOY |  | 1 |  | 2 | Batch 1 | 5548125 | 5500000 | 5498000 | Completed | 1 | 2024-01-08 | 2024-01-08 | P00775091VS | 23HC0126 | 2023-06-27 | 2023-06-26 | 2023-07-17 | 2023-08-08 | 2024-01-08 | C. JANSEN CONST & GEN. MDSE
NC 2023 | K10 | Region VII | Bohol | 118231 | Sta. Cruz ES | DAGOHOY |  | 1 |  | 2 | Batch 1 | 5548125 | 5500000 | 4,365.554.94 | Completed | 1 | 2024-02-23 | 2023-06-27 | P00775092VS | 23HC0125 | 2023-06-27 | 2023-06-26 | 2023-07-17 | 2023-08-30 | 2023-09-13 | SOMBRIO CONST. & SUPPLY
NC 2023 | K10 | Region VII | Bohol | 305721 | Canmaya Diot High School | SAGBAYAN (BORJA) |  | 1 |  | 6 | Batch 1 | 20175000 | 20000000 | 19887935.92 | Completed | 1 | 2024-04-25 | 2023-07-26 | P00775094VS | 23HC0130 | 2023-07-26 | 2023-08-04 | 2023-08-16 | 2023-08-28 | 2023-09-08 | CLAVITE CONST. & SUPPLY
NC 2023 | K10 | Region VII | Bohol | 118635 | Cambansag Elementary | SAN ISIDRO |  | 1 |  | 2 | Batch 1 | 5548125 | 5500000 | 5069409.47 | Completed | 1 | 2024-03-15 | 2024-03-15 | P00775095VS | 23HC0127 | 2023-06-27 | 2023-06-26 | 2023-07-17 | 2023-09-10 | 2023-09-22 | ROSEJEL CONST.
NC 2023 | K10 | Region VII | Bohol | 118640 | Masonoy PS | SAN ISIDRO |  | 1 |  | 2 | Batch 1 | 5749875 | 5700000 | 5688983.2 | Completed | 1 | 2024-04-10 | 2023-06-27 | P00775096VS | 23HC0128 | 2023-06-27 | 2023-06-26 | 2023-07-17 | 2023-08-17 | 2023-08-22 | MAI CONST. & SUPPLY
NC 2023 | K10 | Region VII | Bohol | 118801 | Achila Elementary School | UBAY |  | 1 |  | 0 | Batch 1 | 5043750 | 5000000 | 4990000 | Completed | 1 | 2024-02-14 | 2024-02-14 | P00775097 | 23HC0123 | 2023-06-27 | 2023-06-26 | 2023-07-17 | 2023-09-21 | 2024-02-14 | MAI CONST. & SUPPLY
NC 2023 | SHS | Region VII | Bohol | 302809 | Alicia Technical Vocational HS | ALICIA |  | 1 |  | 1 | Batch 1 | 3362499.67 | 3333333 | 3306436.48 | Completed | 1 | 2023-10-09 | 2023-10-09 | P00775098VS-CW1 | 23HB0154 | 2023-06-29 | 2023-07-07 | 2023-07-19 | 2023-07-24 | 2023-08-04 | REBER ENTERPRISES AND CONSTRUCTION
NC 2023 | SHS | Region VII | Bohol | 302829 | Candabong National High School | ANDA |  | 1 |  | 1 | Batch 1 | 3362499.67 | 3333333 | 3306794.91 | Completed | 1 | 2023-10-16 | 2023-10-16 | P00775099VS-CW1 | 23hb0150 | 2023-06-29 | 2023-07-07 | 2023-07-19 | 2023-07-24 | 2023-08-14 | WBV CONSTRUCTION
NC 2023 | SHS | Region VII | Bohol | 312314 | Quezon HS | BATUAN |  | 1 |  | 6 | Batch 1 | 18745937.17 | 15250000 | 15383437.5 | Completed | 1 | 2024-02-06 |  | P00775100VS-CW1 | 23HB0159 | 2023-06-29 | 2023-07-07 | 2023-07-19 | 2023-07-24 | 2023-08-04 | ALAY BALAY DEVELOPMENT CORP.
NC 2023 | K10 | Region VII | Bohol | 118308 | Candulao ES | GARCIA HERNANDEZ |  | 1 |  | 1 | Batch 1 | 3362499.67 | 3333333 | 3333333 | Completed | 1 | 2023-10-16 | 2023-10-16 | P00775102VS-CW1 | 23HB0156 | 2023-06-29 | 2023-07-07 | 2023-07-19 | 2023-07-24 | 2023-08-14 | JEGSTONE CONSTRUCTION
NC 2023 | K10 | Region VII | Bohol | 118466 | Loboc Central Elementary School | LOBOC |  | 1 |  | 1 | Batch 1 | 3362499.67 | 3333333 | 3303051.59 | Completed | 1 | 2023-12-14 |  | P00775103VS-CW1 | 23hb0151 | 2023-06-29 | 2023-07-07 | 2023-07-19 | 2023-07-24 | 2023-08-11 | RONNYL CONSTRUCTION
NC 2023 | SHS | Region VII | Bohol | 302837 | Concepcion NHS | MABINI |  | 1 |  | 1 | Batch 1 | 3362499.67 | 3333333 | 3306809.94 | Completed | 1 | 2023-10-16 | 2023-11-20 | P00775104VS-CW1 | 23HB0155 | 2023-06-29 | 2023-07-07 | 2023-07-19 | 2023-07-24 | 373870 | WBV CONSTRUCTION
NC 2023 | SHS | Region VII | Bohol | 302903 | Sevilla National High School | SEVILLA |  | 1 |  | 1 | Batch 1 | 3362499.67 | 3333333 | 3306507.15 | Completed | 1 | 2023-10-09 | 2023-10-09 | P00775105VS-CW1 | 23HB0157 | 2023-06-29 | 2023-07-07 | 2023-07-19 | 2023-07-24 | 2023-08-04 | VNCO CONSTRUCTION
NC 2023 | SHS | Region VII | Bohol | 302905 | Sierra Bullones Technical Vocational High School | SIERRA BULLONES |  | 1 |  | 1 | Batch 1 | 3362499.67 | 3333333 | 3307340.7 | Completed | 1 | 2023-10-16 | 2023-10-16 | P00775106VS-CW1 | 23HB0153 | 2023-06-29 | 2023-07-07 | 2023-07-19 | 2023-07-24 | 2023-08-14 | VNCO CONSTRUCTION
NC 2023 | SHS | Region VII | Bohol | 302916 | Valencia Tech-Voc HS | VALENCIA |  | 1 |  | 1 | Batch 1 | 3362499.67 | 3333333 | 3306542.84 | Completed | 1 | 2023-10-15 | 2023-10-15 | P00775107VS-CW1 | 23HB0152 | 2023-06-29 | 2023-07-07 | 2023-07-19 | 2023-07-24 | 2023-08-11 | JEGSTONE CONSTRUCTION
NC 2023 | K10 | Region VII | Canlaon City | 120215 | Pula ES | CANLAON CITY |  | 1 |  | 2 | Batch 1 | 5346375 | 5300000 | 5070392.13 | Completed | 1 | 2023-10-29 | 2023-10-29 |  | 23HJ0097 | [5 empty] | REKINA CONSTRUCTION SERVICES
NC 2023 | K10 | Region VII | Cebu | 118917 | Argao I Central ES | ARGAO |  | 1 |  | 4 | Batch 1 | 11451808.45 | 11352474.3 | 11322441 | Completed | 1 | 2024-01-16 | 2025-02-07 | 23HG0066 | P00775109VS | 2023-08-24 | 2023-08-31 | 2023-09-12 | 2023-10-02 | 2023-10-13 | BT CONSTRUCTION AND GENERAL SERVICES
NC 2023 | K10 | Region VII | Cebu | 118947 | Colawin ES | ARGAO |  | 1 |  | 4 | Batch 1 | 8687799.44 | 8612440.58 | 8571728.27 | Completed | 1 | 2024-01-27 | 2024-06-21 | 23HG0087 | P00775110VS | 2023-11-15 | 2023-11-22 | 2023-12-15 | 2023-12-13 | 2024-01-01 | SERCHER DEVELOPMENT CORPORATION
NC 2023 | SHS | Region VII | Cebu | 302944 | LUNOP NATIONAL HIGH SCHOOL | BOLJOON |  | 1 |  | 9 | Batch 1 | 34041184.9 | 33745908.2 | 33694237.58 | Ongoing | 0.95 | 2025-04-30 |  | 23HG0067 | P00775111VS | 2023-08-24 | 2023-08-31 | 2023-09-12 | 2023-10-02 | 2023-10-13 | BT CONSTRUCTION AND GENERAL SERVICES
NC 2023 | SHS | Region VII | Cebu | 303164 | Dumalan NHS | DALAGUETE |  | 1 |  | 4 | Batch 1 | 11451808.45 | 11352474.3 | 11302474.3 | Ongoing | 0.7 | 2024-01-16 |  | 23HG0068 | P00775112VS | 2023-08-24 | 2023-08-31 | 2023-09-12 | 2023-10-02 | 2023-10-13 | 647 CONSTRUCTION AND DEVELOPMENT CORP. | DUE TO RROW ACCESS
NC 2023 | K10 | Region VII | Cebu | 119040 | Cornelio C. Melgar Elementary School | BALAMBAN |  | 1 |  | 6 | Batch 1 | 10087500 | 10000000 | 9900000 | Completed | 1 | 2023-11-23 | 2024-04-24 | 23HF0084 | P00775113VS-CW1 | 2023-07-01 | 2023-07-07 | 2023-07-19 | 2023-07-25 | 2023-07-28 | FIRST GRANDEUR BUILDERS
NC 2023 | SHS | Region VII | Cebu | 302928 | Balao NHS | BARILI |  | 1 |  | 6 | Batch 1 | 20175000 | 20000000 | 19997841.38 | Completed | 1 | 2024-02-15 | 2024-12-19 | 23HF0085 | P00721824VS-CW1 | 2023-08-03 | 2023-08-09 | 2023-08-29 | 2023-09-14 | 2023-09-19 | FDC CONSTRUCTION AND SUPPLIES CO.
NC 2023 | SHS | Region VII | Cebu | 303068 | Patupat NHS | BARILI |  | 1 |  | 2 | Batch 1 | 4788571.5 | 4747034.94 | 4722534.5 | Completed | 1 | 2024-01-26 | 2024-03-21 | 23HF0086 | P00775115VS-CW1 | 2023-08-03 | 2023-08-09 | 2023-08-22 | 2023-08-25 | 2023-08-30 | JUGA BUILDERS & CONSTRUCTION SUPPLY
NC 2023 | K10 | Region VII | Cebu | 305595 | Lusong National High School | TUBURAN |  | 1 |  | 2 | Batch 1 | 4788571.5 | 4747034.94 | 4725934.5 | Completed | 1 | 2023-12-02 | 2024-06-18 | 23HF0087 | P00775116VS-CW1 | 2023-08-03 | 2023-08-09 | 2023-08-22 | 2023-08-25 | 2023-08-30 | JUGA BUILDERS AND CONSTRUCTION SUPPLY
NC 2023 | K10 | Region VII | Cebu | 500660 | Gibitngil Integrated School | MEDELLIN |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9933761.62 | Ongoing | 0.95 | 2023-12-02 |  | 23HD0079 | P00775117VS-CW1 | 2023-07-25 | 2023-08-01 | 2023-08-14 | 2023-08-25 | 2023-09-04 | Z & G CONSTRUCTION SERVICES
NC 2023 | K10 | Region VII | Cebu | 500666 | Calambua Integrated School | SAN REMIGIO |  | 1 |  | 2 | Batch 1 | 4788571.5 | 4747034.94 | 4735027.84 | Ongoing | 0.95 | 2023-12-02 |  | 23HD0080 | P00775118VS-CW1 | 2023-07-25 | 2023-08-01 | 2023-08-14 | 2023-08-25 | 2023-09-04 | DINAH RBS CONSTRUCTION AND SUPPLY INCORPORATION
NC 2023 | SHS | Region VII | Cebu | 303041 | Libaong National High School | SAN REMIGIO |  | 1 |  | 4 | Batch 1 | 10087501.01 | 10000001 | 9987996.88 | Ongoing | 0.95 | 2023-11-02 |  | 23HD0081 | P00775119VS-CW1 | 2023-07-25 | 2023-08-01 | 2023-08-14 | 2023-08-25 | 2023-09-04 | DINAH RBS CONSTRUCTION AND SUPPLY INCORPORATION
NC 2023 | K10 | Region VII | Cebu | 119771 | Kanlim-ao ES | TABUELAN |  | 1 |  | 4 | Batch 1 | 10087502.02 | 10000002 | 9987997.58 | Ongoing | 0.7 | 2023-12-02 |  | 23HD0082 | P00775120VS-CW1 | 2023-07-25 | 2023-08-01 | 2023-08-14 | 2023-08-25 | 2023-09-04 | DINAH RBS CONSTRUCTION AND SUPPLY INCORPORATION
NC 2023 | SHS | Region VII | Cebu | 303106 | Borbon NHS | BORBON |  | 1 |  | 2 | Batch 1 | 4788571.5 | 4747034.94 | 4744762.06 | Ongoing | 0.95 | 2023-12-26 |  | 23HI0125 | P00775121VS-CW1 | 2023-07-07 | 2023-07-14 | 2023-07-28 | 2023-08-15 | 2023-08-29 | NOGNOG ENTERPRISES
NC 2023 | K10 | Region VII | Cebu | 119216 | Catmondaan ES | CATMON |  | 1 |  | 3 | Batch 1 | 10087500 | 10000000 | 9979567.83 | Completed | 1 | 2024-01-27 | 2024-04-05 | 23HI0127 | P00775122VS-CW1 | 2023-07-28 | 2023-08-05 | 2023-08-17 | 2023-08-22 | 2023-08-24 | NEOVENTURES CONSTRUCTION
NC 2023 | K10 | Region VII | Cebu | 502211 | Basak Integrated School | COMPOSTELA |  | 1 |  | 3 | Batch 1 | 10087500 | 10000000 | 9985380.57 | Ongoing | 0.95 | 2024-01-27 |  | 23HI0126 | P00775123VS-CW1 | 2023-07-28 | 2023-08-05 | 2023-08-17 | 2023-08-22 | 2023-08-31 | WQC DESIGN AND CONSTRUCTION
NC 2023 | K10 | Region VII | Cebu | 501916 | Catarman Integrated School | LILOAN |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9980000 | Ongoing | 0.95 | 2024-04-25 |  | 23HI0122 | P00775126VS-CW1 | 2023-07-07 | 2023-07-14 | 2023-07-28 | 2023-08-17 | 2023-08-30 | POWER MOVE BUILDERS & CONSTRUCTION SUPPLY | 4STY12CL
NC 2023 | K10 | Region VII | Cebu | 119413 | Lataban ES | LILOAN |  | 1 |  | 8 | Batch 1 | 10087500 | 10000000 | 9971486.74 | Ongoing | 0.15 | 2024-07-29 |  | 23HI0136 | P00775124VS-CW1 | 2023-11-22 | 2023-11-29 | 2023-12-12 | 2023-12-29 | 2024-01-11 | VSP STRUCTURE VENTURES CORPORATION
NC 2023 | K10 | Region VII | Cebu | 119417 | Simeon Ayuda ES | LILOAN |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9980000 | Ongoing | 0.95 | 2024-04-25 |  | 23HI0123 | P00775125VS-CW1 | 2023-07-07 | 2023-07-14 | 2023-07-28 | 2023-08-17 | 2023-08-30 | POWER MOVE BUILDERS & CONSTRUCTION SUPPLY
NC 2023 | K10 | Region VII | Cebu | 502121 | Campo Integrated School | SAN FRANCISCO |  | 1 |  | 3 | Batch 1 | 10087500 | 10000000 | 9989101.61 | Completed | 1 | 2024-01-27 | 2024-01-27 | 23HI0128 | P00775127VS-CW1 | 2023-07-28 | 2023-08-05 | 2023-08-17 | 2023-08-22 | 2023-08-31 | BARR STEEL CONSTRUCTION
NC 2023 | K10 | Region VII | Cebu | 500498 | Pansoy Integrated School | SOGOD |  | 1 |  | 2 | Batch 1 | 4788571.5 | 4747034.94 | 4745000 | Completed | 1 | 2023-12-26 | 2024-05-29 | 23HI0124 | P00775128VS-CW1 | 2023-07-07 | 2023-07-14 | 2023-07-28 | 2023-08-15 | 2023-08-29 | DT & C CONSTRUCTION
NC 2023 | K10 | Region VII | Cebu | 137084 | Pitogo Primary School | CONSOLACION |  | 1 |  | 12 | Batch 1 | 10087500 | 10000000 | 9969817.19 | Ongoing | 0.95 | 2024-02-23 |  | 23HN0149 | P00775130VS-CW1 | 2023-07-06 | 2023-07-13 | 2023-07-25 | 2023-07-27 | 2023-08-04 | GTM Builders & Supply
NC 2023 | K10 | Region VII | Cebu | 136962 | Tilhaong Primary School | CONSOLACION |  | 1 |  | 12 | Batch 1 | 10087500 | 10000000 | 9893822.42 | Ongoing | 0.95 | 2024-02-16 |  | 23HN0152 | P00775129VS-CW1 | 2023-07-06 | 2023-07-13 | 2023-07-25 | 2023-08-02 | 2023-08-11 | Rudhil Const. & Enterprises, Inc.
NC 2023 | K10 | Region VII | Cebu | 187025 | Catarman Elementary School | CORDOVA |  | 1 |  | 6 | Batch 1 | 10087500 | 10000000 | 9985000 | Ongoing | 0.95 | 2024-03-19 |  | 23HN0173 | P00775131VS-CW1 | 2023-10-24 | 2023-10-31 | 2023-11-16 | 2023-11-28 | 2023-12-07 | Powermove builders and construction supply
NC 2023 | K10 | Region VII | Cebu | 118869 | Lawaan ES | ALCANTARA |  | 1 |  | 12 | Batch 1 | 59511206.25 | 58995000 | 58108000 | Ongoing | 0.7 | 2024-03-27 |  | 23HO0234 | P00775132VS-CW1 | 2023-06-15 | 2023-06-10 | 2023-07-04 | 2023-07-11 | 2023-07-24 | QM BUILDERS
NC 2023 | K10 | Region VII | Cebu | 119008 | Matutinao ES | BADIAN |  | 1 |  | 5 | Batch 1 | 10732989.77 | 10639890.72 | 10628150.72 | Ongoing | 0.95 | 2024-07-18 |  | 23HO0320 | P00775133VS-CW1 | 2023-10-18 | 2023-10-25 | 2023-11-14 | 2024-02-27 | 2024-03-12 | CELJEM CONSTRUCTION & DEVELOPMENT CORP.
NC 2023 | K10 | Region VII | Cebu | 119405 | Kagsing ES | GINATILAN |  | 1 |  | 12 | Batch 1 | 59511206.25 | 58995000 | 2600000 | Ongoing | 0.9 | 2024-01-18 |  | 23HO0322 | P00775279NP | 2023-10-18 | 2023-10-25 | 2023-11-14 | 2023-11-22 | 2023-12-05 | FIRST GRANDEUR BUILDERS
NC 2023 | K10 | Region VII | Cebu | 119447 | Montañeza ES | MALABUYOC |  | 1 |  | 15 | Batch 1 | 71154703.13 | 70537500 | 70435888 | Ongoing | 0.9 | 2024-04-11 |  | 23H00233 | P00775135VS-CW1 | 2023-06-15 | 2023-06-22 | 2023-07-04 | 2023-07-11 | 2023-07-24 | QUIRANTE CONSTRUCTION CORPORATION
NC 2023 | K10 | Region VII | Cebu | 119596 | Cansalonoy ES | RONDA |  | 1 |  | 8 | Batch 1 | 39674137.5 | 39330000 | 39328142.38 | Ongoing | 0.75 | 2024-04-09 |  | 23H00235 | P00775136VS-CW1 | 2023-06-15 | 2023-06-22 | 2023-07-04 | 2023-07-11 | 2023-07-24 | ZLREJ TRADING AND CONSTRUCTION CORP./DINAH RBS CONSTRUCTION AND SUPPLY INC (JV)
NC 2023 | SHS | Region VII | Cebu | 303033 | Langin NHS | RONDA |  | 1 |  | 6 | Batch 1 | 18422474.39 | 18262675.97 | 18260485.96 | Ongoing | 0.95 | 2024-08-08 |  | 23HO0319 | P00775137VS-CW1 | 2023-10-18 | 2023-10-25 | 2023-11-14 | 2024-02-27 | 2024-03-12 | FIRST GRANDEUR BUILDERS
NC 2023 | K10 | Region VII | Cebu City | 500044 | Mabini Integrated School | CEBU CITY (Capital) |  | 1 |  | 8 | Batch 1 | 15131250 | 15000000 | 14983888.88 | Ongoing | 0.85 | 2024-05-06 |  | P00775139VS-CW1 | 23HH0149 |  | 2023-10-06 | 2023-10-18 | 2023-10-23 | 2023-11-03 | Powerframe Construction | Delayed
NC 2023 | K10 | Region VII | Cebu City | 119901 | Mabolo ES | CEBU CITY (Capital) |  | 1 |  | 8 | Batch 1 | 15131250 | 15000000 | 14980000 | Ongoing | 0.87 | 2024-05-06 |  | P00775138VS-CW1 | 23HH0148 |  | 2023-10-06 | 2023-10-18 | 2023-10-23 | 2023-11-03 | Planac Construction | Delayed
NC 2023 | SHS | Region VII | Cebu City | 303141 | Cebu City National Science HS | CEBU CITY (Capital) |  | 1 |  | 0 | Batch 1 | 30262500 | 30000000 | 26356000 | Ongoing | 0.95 | 2024-06-12 |  | P00775140VS-CW1 | 23HH0158 |  | 2023-10-12 | 2023-10-24 | 2023-10-25 | 2023-11-16 | La PruebaConstruction/WTG | Delayed
NC 2023 | K10 | Region VII | Guihulngan City | 120263 | BALOGO ELEMENTARY SCHOOL | CITY OF GUIHULNGAN |  | 1 |  | 3 | Batch 1 | 6859500 | 6800000 | 6795000 | Completed | 1 | 2023-11-05 | 2023-11-06 | P00775141VS-CW1 | 23HJ0099 | 2023-06-15 | 2023-06-22 | 2023-07-04 | 2023-07-18 | 2023-07-31 | MAI Construction and Supply
NC 2023 | K10 | Region VII | Guihulngan City | 305713 | Balogo National High School | CITY OF GUIHULNGAN |  | 1 |  | 2 | Batch 1 | 5144625 | 5100000 | 5144630 | Completed | 1 | 2023-12-29 | 2023-10-27 | P00775142VS-CW1 | 23HJ0096 | 2023-06-15 | 2023-06-22 | 2023-07-04 | 2023-07-18 | 2023-07-31 | MAI Construction and Supply
NC 2023 | K10 | Region VII | Guihulngan City | 305915 | Calamba National High School | CITY OF GUIHULNGAN |  | 1 |  | 2 | Batch 1 | 4942875 | 4900000 | 4880060.96 | Completed | 1 | 2024-05-31 | 2024-05-31 | P00775143VS-CW1 | 23HJ0103 | 2023-08-17 | 2023-08-24 | 2023-09-05 | 2024-02-28 | 2024-03-01 | K.M. Golong Construction
NC 2023 | K10 | Region VII | Guihulngan City | 136947 | Puti-an Elementary School | VALLEHERMOSO |  | 1 |  | 2 | Batch 1 | 4942875 | 4900000 | 4942880 | Completed | 1 | 2024-01-11 | 2024-01-11 | P00775144VS-CW1 | 23HJ0102 | 2023-08-17 | 2023-08-24 | 2023-09-05 | 2023-10-05 | 2023-10-16 | Rekina Construction Services
NC 2023 | K10 | Region VII | Lapu-Lapu City | 119957 | Sabang Elementary School | LAPU-LAPU CITY (OPON) |  | 1 |  | 8 | Batch 1 | 30262500 | 30000000 | 29950003.84 | Completed | 1 | 2024-05-12 | 2024-06-11 | P00775145VS-CW1 | 23HN0151 | 2023-07-06 | 2023-07-13 | 2023-07-25 | 2023-08-02 | 2023-08-11 | Vanguard Builders Inc. | Phase I Only
NC 2023 | K10 | Region VII | Mandaue City | 120013 | Maguikay ES | MANDAUE CITY |  | 1 |  | 12 | Batch 1 | 30262500 | 30000000 | 29900000 | Ongoing | 0.57 | 2024-04-12 | 2024-10-09 | P00775146VS-CW1 | 23HNO147 | 2023-07-06 | 2023-07-13 | 2023-07-25 | 2023-08-02 | 2023-08-11 | ZLREJ Const. Corp./Dinah RBS Const. & Supply Inc. (JV)
NC 2023 | K10 | Region VII | Mandaue City | 303196 | Pagsabungan NHS | MANDAUE CITY |  | 1 |  | 4 | Batch 1 | 8687799.44 | 8612440.58 | 8601899.66 | Completed | 1 | 2023-12-13 | 2024-05-19 | P00775147VS-CW1 | 23HNO153 | 2023-07-06 | 2023-07-13 | 2023-08-15 | 2023-08-22 | 2023-08-31 | LRTY Construction & Supply | Completed Phase 1 only
NC 2023 | K10 | Region VII | Talisay City | 119802 | San Isidro Elementary School | CITY OF TALISAY |  | 1 |  | 8 | Batch 1 | 30262500 | 30000000 | 29970000 | Completed | 1 | 2024-04-11 | 2024-04-11 | P00775162VS-CW1 | 23HE0166 | 2023-07-14 | 2023-07-21 | 2023-08-02 | 2023-08-15 | 2023-08-23 | Celjem Construction & Development Corp.
NC 2024 |  | Region VII | Bayawan City | 501131 | Ali-is Integrated School | CITY OF BAYAWAN (TULONG) |  | 1 | 16 | 4STY16CL | BATCH 1 | 62946888.14 |  | 62578423.85 | Ongoing | 0.98 | 2025-07-06 |  | P00875668VS-CW1 | 24HL0062 | 2024-06-13 | 2024-06-20 | 2024-02-07 | 2024-09-07 | 2024-12-07 | LEBCURT CONSTRUCTION SERVICES/JANUARY BUILDERS (JV)
NC 2024 |  | Region VII | Bogo City | 119107 | Bogo Central School 111 | CITY OF BOGO |  | 1 | 12 | 4STY12CL | BATCH 1 | 42180000 |  | P 41,959,100.00 | Ongoing | 0.9 | 2024-10-12 |  | P00875669VS-CW1 | 24HD0080 | 2024-04-27 | 2024-07-05 | 2024-05-21 | 2024-05-27 | 2024-05-29 | JARC CONSTRUCTION AND MARINE SERVICES CORPORATION
NC 2024 |  | Region VII | Bohol | 117998 | Boyog ES | BALILIHAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4965000 | Completed | 1 | 2024-09-11 | 2024-10-13 | P00875403VS | 24HA0105 |  | 2024-04-02 | 2024-04-18 | 2024-04-26 | 2024-05-15 | GERSON CONSTRUCTION AND HARDWARE SUPPLY | Issued Work Suspension Order due to Unworkable site condition (i.e. unfavorable weather condition at the project site, access to project site not passable)
NC 2024 |  | Region VII | Bohol | 305719 | Modesto G. Autida High School | BIEN UNIDO |  | 1 | 2 | 2 Classrooms | GAA 17B | 5000000 |  | 4973000 | Completed | 1 | 2024-12-19 |  | P00875413VS | 24HC0096 | 2024-05-20 | 2024-05-27 | 2024-10-06 | 2024-06-28 | 2024-09-07 | C. Jansen Const. & Gen. Mdse. | Completed
NC 2024 |  | Region VII | Bohol | 118088 | Banlasan ES | CALAPE |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4967000 | Completed | 1 | 2024-10-11 | 2024-10-11 | P00875409VS | 24HA0113 |  | 2024-04-26 | 2024-05-08 | 2024-05-21 | 2024-06-10 | NENIAL CONSTRUCTION
NC 2024 |  | Region VII | Bohol | 312319 | Hagbuaya High School | CATIGBIAN |  | 1 | 6 | 2STY6CL | GAA 17B | 10000000 |  | 9928825 | Ongoing | 0.45 | 2025-05-07 |  | P00875412VS | 24HA0154 |  | 2024-09-04 | 2024-09-17 | 2024-10-25 | 2024-12-04 | JA ACHACOSO Enterprises and General Services | Modified to 1STY 3CL
NC 2024 |  | Region VII | Bohol | 312320 | Haguilanan High School | CATIGBIAN |  | 1 | 6 | 2STY6CL | GAA 17B | 10000000 |  | 9933518.69 | Ongoing | 0.45 | 2025-05-07 |  | P00875411VS | 24HA0155 |  | 2024-09-04 | 2024-09-17 | 2024-10-25 | 2024-12-04 | JA ACHACOSO Enterprises and General Services | Modified to 1STY 3CL
NC 2024 |  | Region VII | Bohol | 118176 | Liboron ES | CATIGBIAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4951140 | Completed | 1 | 2024-10-11 | 2024-10-11 | P00875410VS | 24HA0114 |  | 2024-04-26 | 2024-05-08 | 2024-05-21 | 2024-06-10 | JJF BUILDERS AND SUPPLY
NC 2024 |  | Region VII | Bohol | 500212 | Canangcaan Integrated School | CORELLA |  | 1 | 6 | 2STY6CL | BATCH 1 | 19500000 |  | 19372172.54 | Ongoing | 0.6 | 2025-04-05 |  | P00875674VS | 24HA0153 |  | 2024-08-30 | 2024-09-11 | 2024-09-24 | 2024-10-04 | CEMPRON CONSTRUCTION & DEVELOPMENT
NC 2024 |  | Region VII | Bohol | 118202 | Cancatac ES | CORELLA |  | 1 | 3 | 1STY3CL | BATCH 1 | 8700000 |  | 8636080.4 | Completed | 1 | 2024-11-10 | 2024-11-10 | P00875670VS | 24HA0118 |  | 2024-05-02 | 2024-05-21 | 2024-05-31 | 2024-06-10 | FSB CONSTRUCTION AND SUPPLY
NC 2024 |  | Region VII | Bohol | 302839 | Corella National High School | CORELLA |  | 1 | 3 | 1STY3CL | BATCH 1 | 8700000 |  | 8651618.47 | Completed | 1 | 2024-11-10 | 2024-11-10 | P00875673VS | 24HA0121 |  | 2024-05-02 | 2024-05-21 | 2024-05-28 | 2024-06-10 | INABANGA DRILLING, CONSTRUCTION, STEEL FABRICATION, AND GEN. MDSE.
NC 2024 |  | Region VII | Bohol | 118204 | Sambog ES | CORELLA |  | 1 | 3 | 1STY3CL | BATCH 1 | 8700000 |  | 8651851.11 | Ongoing | 0.9 | 2025-03-08 |  | P00875671VS | 24HA0119 |  | 2024-06-13 | 2024-06-25 | 2024-06-28 | 2024-07-09 | 3N CONSTRUCTION & SUPPLY | Demolition or other clearing related issues (except utilities)
NC 2024 |  | Region VII | Bohol | 118205 | Tanday ES | CORELLA |  | 1 | 3 | 1STY3CL | BATCH 1 | 8700000 |  | 8641500 | Completed | 1 | 2024-11-10 | 2024-11-10 | P00875672VS | 24HA0120 |  | 2024-05-02 | 2024-05-21 | 2024-05-28 | 2024-06-10 | EC SOLICON BUILDERS & SUPPLY, INC.
NC 2024 |  | Region VII | Bohol | 305722 | De La Paz High School | CORTES |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5964932.49 | Completed | 1 | 2024-09-26 | 2024-09-26 | P00875431VS | 24HA0107 |  | 2024-04-02 | 2024-04-18 | 2024-04-26 | 2024-05-15 | 3N CONSTRUCTION & SUPPLY
NC 2024 |  | Region VII | Bohol | 302817 | Biking Tech-Voc HS | DAUIS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969792.86 | Completed | 1 | 2024-09-11 | 2024-09-11 | P00875406VS | 24HA0104 |  | 2024-04-02 | 2024-04-18 | 2024-04-26 | 2024-05-15 | 3N CONSTRUCTION & SUPPLY
NC 2024 |  | Region VII | Bohol | 302820 | Cabilao NHS | LOON |  | 1 | 4 | 1STY4CL | GAA 17B | 14000000 |  | 13900000 | Ongoing | 0.6 | 2025-06-06 |  | P00875429VS | 24HA0156 |  | 2024-09-04 | 2024-09-17 | 2024-10-25 | 2024-12-04 | ONE ORCHARD Construction Corporation | Modified to 1STY 3CL
NC 2024 |  | Region VII | Bohol | 306050 | Loon North High School | LOON |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4968169.21 | Completed | 1 | 2024-10-11 | 2024-10-11 | P00875404VS | 24HA0115 |  | 2024-04-26 | 2024-05-08 | 2024-05-21 | 2024-06-10 | DOLCI CONSTRUCTION & GENERAL MERCHANDISE
NC 2024 |  | Region VII | Bohol | 305957 | Lopez-Dano-Simbajon High School | LOON |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4967000 | Completed | 1 | 2024-12-12 | 2024-12-12 | P00875405VS | 24HA0142 |  | 2024-07-12 | 2024-07-24 | 2024-04-30 | 2024-08-12 | NENIAL CONSTRUCTION
NC 2024 |  | Region VII | Bohol | 118545 | Pagnitoan ES | MARIBOJOC |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5966199.53 | Completed | 1 | 2024-10-26 | 2024-10-26 | P00875432VS | 24HA0116 |  | 2024-04-26 | 2024-05-08 | 2024-05-21 | 2024-06-10 | K & J CONSTRUCTION
NC 2024 |  | Region VII | Bohol | 118549 | San Vicente Elementary School | MARIBOJOC |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5940000 | Completed | 1 | 2024-09-26 | 2024-09-26 | P00875430VS | 24HA0109 |  | 2024-04-02 | 2024-04-18 | 2024-04-26 | 2024-05-15 | A.A. DE VERA CONSTRUCTION
NC 2024 |  | Region VII | Bohol | 118558 | Libaong ES | PANGLAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4973741.35 | Completed | 1 | 2024-09-11 | 2024-09-11 | P00875408VS | 24HA0108 |  | 2024-04-02 | 2024-04-18 | 2024-04-26 | 2024-05-15 | EFB CONSTRUCTION SERVICES
NC 2024 |  | Region VII | Bohol | 312332 | Bagongbanwa High School | TUBIGON |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 7954812.16 | Completed | 1 | 2025-01-24 | 2025-01-24 | P00875428VS | 24HA0103 |  | 2024-04-02 | 2024-04-18 | 2024-04-26 | 2024-05-15 | GREYSTONE CONSTRUCTION
NC 2024 |  | Region VII | Bohol | 118776 | Buenos Aires ES | TUBIGON |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4970713.87 | Completed | 1 | 2024-09-11 | 2024-09-11 | P00875407VS | 24HA0106 |  | 2024-04-02 | 2024-04-18 | 2024-04-26 | 2024-05-15 | GREYSTONE CONSTRUCTION
NC 2024 |  | Region VII | Bohol | 306191 | BUENAVISTA HIGH SCHOOL | BUENAVISTA |  | 1 | 8 | 2STY8CL CONSTRUCTION OF CLASSROOMS | BATCH 2 | 29600000 |  |  | Ongoing | 0.25
NC 2024 |  | Region VII | Bohol | 302831 | Lubang National High School | BUENAVISTA |  | 1 | 6 | Construction of 6CL | GAA 17B | 15000000 |  | 14892798.79 | Ongoing | 0.55 | 2025-10-04 |  | P00875433VS | 24HC0121 | 2024-07-19 | 2024-07-26 | 2024-07-08 | 2024-08-14 | 2024-08-14 | RL Earth Hauling & Equiptment Services, Inc. | Ongoing
NC 2024 |  | Region VII | Bohol | 302836 | Clarin National School of Fisheries | CLARIN |  | 1 | 4 | 1STY4CL | BATCH 2 | 11500000 |  | 9648940.65 | Ongoing | 0.47
NC 2024 |  | Region VII | Bohol | 312326 | Cuaming HS | INABANGA |  | 1 | 3 | Construction of 3CL | GAA 17B | 7500000 |  | 7452500 | Ongoing | 0.93 | 2025-01-17 |  | P00875436VS | 24HC0115 | 2024-01-07 | 2024-08-07 | 2024-07-23 | 2024-07-30 | 2024-07-30 | Greystone Construction | Ongoing
NC 2024 |  | Region VII | Bohol | 500209 | Inabanga North Central Integrated School | INABANGA |  | 1 | 1 | Construction of 1CL | GAA 17B | 2500000 |  | 2388000 | Ongoing | 0.94 | 2024-11-30 |  | P00875437VS | 24HC0105 | 2024-07-06 | 2024-06-14 | 2024-06-26 | 2024-06-27 | 2024-07-15 | A.A de vera Construction | Ongoing
NC 2024 |  | Region VII | Bohol | 501143 | San Jose Integrated School (Secondary) | PRES. CARLOS P. GARCIA (PITOGO) |  | 1 | 2 | Construction of 2CL | GAA 17B | 5000000 |  | 4970000 | Completed | 1 | 2024-08-11 |  | P00875414VS | 24HC0094 | 2024-05-20 | 2024-05-27 | 2024-10-06 | 2024-06-20 | 2024-06-28 | J.F Estapia Construction | Completed
NC 2024 |  | Region VII | Bohol | 118614 | Kagawasan ES | SAGBAYAN (BORJA) |  | 1 | 1 | Construction of 1CL | GAA 17B | 2500000 |  | 2486654 | Completed | 1 | 2024-11-15 |  | P00875419VS | 24HC0104 | 2024-07-06 | 2024-06-14 | 2024-06-26 | 2024-06-27 | 2024-11-07 | Brightstone Construction | Completed
NC 2024 |  | Region VII | Bohol | 118616 | Langtad ES | SAGBAYAN (BORJA) |  | 1 | 2 | Construction of 2CL | GAA 17B | 7500000 |  | 7460500 | Ongoing | 0.96 | 2025-02-02 |  | P00875418VS | 24HC0119 | 2024-07-16 | 2024-07-23 | 2024-05-08 | 2024-08-14 | 2024-08-23 | Mai Const. & Supply | Ongoing
NC 2024 |  | Region VII | Bohol | 118623 | San Ramon Elementary School | SAGBAYAN (BORJA) |  | 1 | 3 | Construction of 3CL | GAA 17B | 7500000 |  | 7432155.19 | Completed | 1 | 2025-12-01 |  | P00875416VS | 24HC0114 | 2024-01-07 | 2024-08-07 | 2024-07-23 | 2024-07-26 | 2024-02-08 | ZMS Construction | Completed
NC 2024 |  | Region VII | Bohol | 118625 | San Vicente Norte ES | SAGBAYAN (BORJA) |  | 1 | 3 | Construction of 3CL | GAA 17B | 7500000 |  | 7460500 | Completed | 1 | 2025-01-19 |  | P00875417VS | 24HC0116 | 2024-10-07 | 2024-07-17 | 2024-07-29 | 2024-07-31 | 2024-09-08 | Mai Construction and Suplly | Completed
NC 2024 |  | Region VII | Bohol | 500213 | Cabanugan Integrated School | SAN ISIDRO |  | 1 | 2 | Construction of 2CL | GAA 17B | 5000000 |  | 4964297.82 | Ongoing | 0.98 | 2024-07-12 |  | P00875435VS | 24HC0110 | 2024-06-21 | 2024-06-28 | 2024-01-07 | 2024-07-26 | 2024-02-08 | 4K Vermark Civil Eng'g. Const. | Ongoing
NC 2024 |  | Region VII | Bohol | 118644 | Cabangahan ES | SAN MIGUEL |  | 1 | 2 | 1STY2CL | BATCH 1 | 5549101.8 |  |  | Completed | 1
NC 2024 |  | Region VII | Bohol | 500210 | Cataban Integrated School (Secondary) | TALIBON |  | 1 | 2 | Construction of 2CL | GAA 17B | 5000000 |  | 4965000 | Completed | 1 | 2024-11-13 |  | P00875415VS | 24HC0093 | 2024-05-20 | 2024-05-27 | 2024-10-06 | -604299 | 2024-03-07 | Three K Const. & Ent., Inc. | Completed
NC 2024 |  | Region VII | Bohol | 312334 | Bulilis High School | UBAY |  | 1 | 2 | Construction of 2CL | GAA 17B | 5000000 |  | 4965000 | Completed | 1 | 2024-11-19 |  | P00875438VS | 24HC0092 | 2024-05-20 | 2024-07-27 | 2024-10-06 | 2024-06-28 | 2024-09-07 | BMG Const. & Supply | Completed
NC 2024 |  | Region VII | Bohol | 500214 | Tapal IS | UBAY |  | 1 | 2 | Construction of 2CL | GAA 17B | 5000000 |  | 4970000 | Completed | 1 | 2024-11-19 |  | P00875434VS | 24HC0091 | 2024-05-20 | 2024-07-27 | 2024-10-06 | 2024-06-28 | 2024-09-07 | A & D Const. & Supply | Completed
NC 2024 |  | Region VII | Bohol | 118804 | Ubay II Central ES (Biabas CES ) | UBAY |  | 1 | 2 | Construction of School Building with Facilities and Site Improvement | GAA 17B | 13600000 |  | 13522000 | Completed | 0.75 | 2025-02-04 |  | P00875441VS | 24HC0117 | 2024-07-15 | 2024-07-23 | 2024-05-08 | 2024-08-14 | 2024-08-23 | Three K Const. & Ent., Inc. | Completed
NC 2024 |  | Region VII | Bohol | 118012 | Batuan Central ES | BATUAN |  | 1 | 4 | 2STY4CL | BATCH 1 | 14800000 |  |  | Ongoing | 0.4
NC 2024 |  | Region VII | Bohol | 302885 | Policronio S. Dano, Sr. HS | CARMEN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4940168 | Completed | 1 | 2024-07-29 | 2024-08-09 | P00875425VS-CW1 | 24HB0118 | 2024-03-25 | 2024-03-04 | 2024-04-15 | 2024-04-23 | 2024-04-29 | CLAIRE CONSTRUCTION AND SUPPLY CORPORATION
NC 2024 |  | Region VII | Bohol | 305581 | Valeriano Ganas High School | CARMEN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4944966.86 | Ongoing | 0.25 |  |  | P00875424VS-CW1 | 24HB0119 | 2024-03-25 | 2024-03-04 | 2024-04-15 | 2024-04-23 | 2024-04-29 | ALOJA BUILDERS AND REALTY | Suspended due to location under protected area, for compliance of ECC
NC 2024 |  | Region VII | Bohol | 118300 | San Isidro ES | DUERO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4945596 | Completed | 1 | 2024-07-29 | 2024-10-25 | P00875426VS-CW1 | 24HB0117 | 2024-03-25 | 2024-03-04 | 2024-04-15 | 2024-04-22 | 2024-04-29 | JEGSTONE CONSTRUCTION
NC 2024 |  | Region VII | Bohol | 306194 | ABIJILAN HIGH SCHOOL | GARCIA HERNANDEZ |  | 1 | 4 | 2STY4CL | BATCH 2 | 12800000 |  |  | Ongoing | 0.39
NC 2024 |  | Region VII | Bohol | 118308 | Candulao ES | GARCIA HERNANDEZ |  | 1 | 4 | 2STY4CL | BATCH 1 | 12800000 |  |  | Ongoing | 0.55
NC 2024 |  | Region VII | Bohol | 306193 | CAYAM HIGH SCHOOL | GARCIA HERNANDEZ |  | 1 | 4 | 2STY4CL | BATCH 2 | 12800000 |  |  | Ongoing | 0.6
NC 2024 |  | Region VII | Bohol |  | Catungawan Norte Elementary School | GUINDULMAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
NC 2024 |  | Region VII | Bohol | 118424 | Jagna Central ES | JAGNA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4964830.84 | Completed | 1 | 2024-07-26 |  | P00875420VS-CW1 | 24HB0121 | 2024-03-25 | 2024-04-13 | 2024-04-15 | 2024-04-22 | 2024-04-29 | G.U. AUDITOR CONSTRUCTION & SUPPLY | On-going process of Contract Time Extension due to unworkable weather condition
NC 2024 |  | Region VII | Bohol | 118434 | Calvario Elementary School | LILA |  | 1 | 2 | 1STY2CL | BATCH 1 | 6500000 |  | 6447671.61 | Completed | 1 | 2024-09-30 |  | P00875678VS-CW1 | 24HB0160 | 2024-05-14 | 2024-05-23 | 2024-04-06 | 2024-06-26 | 2024-04-07 | ALOJA BUILDERS & REALTY | On-going process of Contract Time Extension due to unworkable weather condition
NC 2024 |  | Region VII | Bohol | 118435 | Cogon ES | LILA |  | 1 | 2 | 1STY2CL | BATCH 1 | 6500000 |  | 6456668.77 | Completed | 1 | 2024-09-30 |  | P00875679VS-CW1 | 24HB0161 | 2024-05-14 | 2024-05-23 | 2024-04-06 | 2024-06-26 | 2024-04-07 | ALOJA BUILDERS & REALTY | On-going process of Contract Time Extension due to unworkable weather condition
NC 2024 |  | Region VII | Bohol | 118436 | Jambawan ES | LILA |  | 1 | 2 | 1STY2CL | BATCH 1 | 6500000 |  | 6464344.86 | Ongoing | 0.89 | 2024-04-10 |  | P00875680VS-CW1 | 24HB0157 | 2024-05-14 | 2024-05-23 | 2024-04-06 | 2024-06-28 | 2024-09-07 | RAMYER CONSTRUCTION &TRADING | On-going process of Contract Time Extension due to unworkable weather condition
NC 2024 |  | Region VII | Bohol | 118437 | Lila Central ES | LILA |  | 1 | 2 | 1STY2CL | BATCH 1 | 6500000 |  | 5741145.59 | Completed | 1 | 2024-09-27 |  | P00875681VS-CW1 | 24HB0158 | 2024-05-14 | 2024-05-23 | 2024-04-06 | 2024-06-21 | 2024-03-07 | KEPRISHYLIE CIVIL ENGINEERING CONSTRUCTION | On-going process of Contract Time Extension due to unworkable weather condition
NC 2024 |  | Region VII | Bohol | 302868 | Lila NHS | LILA |  | 1 | 6 | 3STY6CL | BATCH 1 | 19500000 |  | 19206207.71 | Ongoing | 0.5 | 2025-06-02 |  | P00875684VS-CW1 | 24HB0170 | 2024-08-07 | 2024-07-17 | 2024-07-29 | 2024-08-27 | 2024-05-09 | A&D CONSTRUCTION AND SUPPLY
NC 2024 |  | Region VII | Bohol | 118438 | Macalingan P/S | LILA |  | 1 | 2 | 1STY2CL | BATCH 1 | 6500000 |  | 6451768.91 | Completed | 1 | 2024-11-10 |  | P00875682VS-CW1 | 24HB0162 | 2024-05-14 | 2024-05-23 | 2024-04-06 | 2024-06-28 | 2024-07-15 | ALOJA BUILDERS & REALTY | On-going process of Contract Time Extension due to unworkable weather condition
NC 2024 |  | Region VII | Bohol | 118440 | Nagsulay Elem. School | LILA |  | 1 | 3 | 1STY3CL | BATCH 1 | 8700000 |  | 7602053.43 | Completed | 1 | 2024-10-21 |  | P00875683VS-CW1 | 24HB0159 | 2024-05-14 | 2024-05-23 | 2024-04-06 | 2024-06-27 | 2024-07-15 | KEPRISHYLIE CIVIL ENGINEERING CONSTRUCTION | On-going process of Contract Time Extension due to unworkable weather condition
NC 2024 |  | Region VII | Bohol | 306192 | LOAY NHS | LOAY |  | 1 | 2 | 1STY2CL | BATCH 2 | 6500000 |  |  | Ongoing | 0.8
NC 2024 |  | Region VII | Bohol |  | San Jose National High Scool | MABINI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region VII | Bohol | 302901 | San Roque National High School | MABINI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4964859.94 | Completed | 1 | 2024-07-29 |  | P00875427VS-CW1 | 24HB0116 | 2024-03-25 | 2024-04-13 | 2024-04-15 | 2024-04-19 | 2024-04-29 | G.U. AUDITOR CONSTRUCTION & SUPPLY
NC 2024 |  | Region VII | Bohol | 118847 | Anas ES | VALENCIA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4962602.96 | Completed | 1 | 2024-07-29 |  | P00875422VS-CW1 | 24HB0120 | 2024-03-25 | 2024-04-13 | 2024-04-15 | 2024-04-22 | 2024-04-29 | LTS BUILDERS AND CONSTRUCTION SUPPLY | On-going process of Contract Time Extension due to unworkable weather condition
NC 2024 |  | Region VII | Bohol | 306239 | ANAS HIGH SCHOOL | VALENCIA |  | 1 | 3 | 1STY3CL | BATCH 2 | 9600000 |  |  | Ongoing | 0.46
NC 2024 |  | Region VII | Canlaon City | 136969 | Angas 1 Elementary School | CANLAON CITY |  | 1 | 2 | 1STY2CL with CR | GAA 17B | 5500000 |  | 5456718.16 | Completed | 1 | 2024-06-28 | 2024-06-28 | P00875480VS | 24HJ0107 | 2024-02-21 | 2024-02-28 | 2024-12-03 | 2024-03-26 | 2024-01-04 | REKINA CONSTRUCTION SERVICES | Completed
NC 2024 |  | Region VII | Carcar City | 119159 | Liburon Elementary School | CITY OF CARCAR |  | 1 | 12 | Construction of 12CL | GAA 17B | 40000000 |  |  | Ongoing | 0.8 | [9 empty] | Quirante Construction
NC 2024 |  | Region VII | Cebu | 302985 | Argao National High School | ARGAO |  | 1 | 9 | 3STY9CL | GAA 17B | 40000000 |  | 39747299.83 | Ongoing | 0.25 | 2025-03-25 |  | P00875443VS | 24HG0078 | 2024-03-14 | 2024-03-21 | 2024-04-02 | 2024-05-06 | 2024-05-24 | BT CONSTRUCTION AND GENERAL SERVICES
NC 2024 |  | Region VII | Cebu | 303071 | Cagay NHS | BARILI |  | 1 | 4 | 2STY4CL | GAA 17B | 20000000 |  | 19847000 | Ongoing | 0.25 | 2025-05-01 |  | P00875445VS-CW1 | 24HF0102 | 2024-05-08 | 2024-05-14 | 2024-05-27 | 2024-05-31 | 2024-06-05 | FDC CONSTRUCTION AND SUPPLIES CO.
NC 2024 |  | Region VII | Cebu | 119101 | Patupat ES | BARILI |  | 1 | 4 | 2STY4CL | GAA 17B | 20000000 |  | 19887754.26 | Ongoing | 0.3 | 2025-05-01 |  | P00875444VS-CW1 | 24HF0101 | 2024-05-08 | 2024-05-14 | 2024-05-27 | 2024-05-31 | 2024-06-05 | FDC CONSTRUCTION AND SUPPLIES CO.
NC 2024 |  | Region VII | Cebu | 500652 | Hilotongan Integrated School | BANTAYAN |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9926615.74 | Ongoing | 0.5 | 2024-12-19 |  | P00875454VS | 24HD0120 | 2024-07-19 | 2024-07-26 | 2024-08-07 | 2024-08-15 | 2024-08-22 | XLA CONSTRUCTION
NC 2024 |  | Region VII | Cebu | 119456 | Caputatan Sur ES | MEDELLIN |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9928258.61 | Ongoing | 0.9 | 2024-11-19 |  | P00875457VS | 24HD0118 | 2024-07-19 | 2024-07-26 | 2024-08-07 | 2024-08-15 | 2024-08-22 | Z & G CONSTRUCTION SERVICES
NC 2024 |  | Region VII | Cebu | 119692 | Okoy ELEMENTARY SCHOOL | SANTA FE |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9926690.16 | Ongoing | 0.85 | 2024-11-29 |  | P00875455VS | 24HD0121 | 2024-07-19 | 2024-07-26 | 2024-08-07 | 2024-08-15 | 2024-08-22 | XLA CONSTRUCTION
NC 2024 |  | Region VII | Cebu | 312408 | Daantabogon NHS | TABOGON |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9925961.51 | Ongoing | 0.7 | 2024-11-19 |  | P00875456VS | 24HD0119 | 2024-07-19 | 2024-07-26 | 2024-08-07 | 2024-08-15 | 2024-08-22 | SAN NARCISO BUILDERS CORPORATION
NC 2024 |  | Region VII | Cebu | 119147 | Doña Milagros Osmeña ES | BORBON |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.1 | 2025-02-23 |  | P00875476VS-CW1 | 24HI0146 | 2024-08-29 | 2024-09-05 | 2024-09-18 | 2024-09-24 | 2024-09-27 | WQC DESIGN & CONSTRUCTION | Rebid
NC 2024 |  | Region VII | Cebu | 119150 | Managase ES | BORBON |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.7 | 2024-10-19 |  | P00875477VS-CW1 | 24HI0108 | 2024-04-04 | 2024-04-11 | 2024-04-23 | 2024-05-08 | 2024-05-23 | WQC DESIGN & CONSTRUCTION | -
NC 2024 |  | Region VII | Cebu | 119186 | Cantumog ES | CARMEN |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.95 | 2024-11-09 |  | P00875448VS-CW1 | 24HI0086 | 2024-05-01 | 2024-05-08 | 2024-05-21 | 2024-05-28 | 2024-06-13 | WQC DESIGN & CONSTRUCTION | Rebid
NC 2024 |  | Region VII | Cebu | 500042 | Catmon Integrated School | CATMON |  | 1 | 21 | 4STY20CL & Regular TVL | BATCH 1 | 59000000 |  | 58677631.09 | Ongoing | 0.4 | 2025-05-24 |  | P00875685VS | 24HI0147 | 2024-08-29 | 2024-09-05 | 2024-09-18 | 2024-09-24 | 2024-09-27 | NEOVENTURES CONST./ DINAH RBS CONST. & SUPPLY INC., JV. | DEMOLITION WORKS
NC 2024 |  | Region VII | Cebu | 119216 | Catmondaan ES | CATMON |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9934720.45 | Ongoing | 0.01 | 2025-09-02 |  | P00875449VS-CW1 | 24HI0152 | 2025-02-21 | 2025-02-28 | 2025-05-06 | 2025-05-14 | 2025-05-21 | WQC DESIGN & CONSTRUCTION | MODIFIED DUE TO LAST BUILDABLE SPACE. RECOMMENDED TO CONSTRUCT 4STY8CL.
NC 2024 |  | Region VII | Cebu | 500991 | Cabadiangan Integrated School | COMPOSTELA |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.25 | 2024-11-16 |  | P00875447VS-CW1 | 24HI0129 | 2024-05-09 | 2024-05-16 | 2024-05-29 | 2024-06-05 | 2024-06-20 | WQC DESIGN & CONSTRUCTION
NC 2024 |  | Region VII | Cebu | 187019 | Canamucan ES | COMPOSTELA |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.75 | 2024-11-09 |  | P00875446VS-CW1 | 24HI0115 | 2024-05-01 | 2024-05-08 | 2024-05-21 | 2024-05-28 | 2024-06-13 | WQC DESIGN & CONSTRUCTION
NC 2024 |  | Region VII | Cebu | 501349 | Dapdap Integrated School | COMPOSTELA |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.95 | 2024-10-19 |  | P00875472VS-CW1 | 24HI0107 | 2024-04-04 | 2024-04-11 | 2024-04-23 | 2024-05-08 | 2024-05-23 | WQC DESIGN & CONSTRUCTION
NC 2024 |  | Region VII | Cebu | 500423 | Calero IS | LILOAN |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.25 | 2024-11-16 |  | P00875453VS-CW1 | 24HI0128 | 2024-05-09 | 2024-05-16 | 2024-05-29 | 2024-06-05 | 2024-06-20 | WQC DESIGN & CONSTRUCTION
NC 2024 |  | Region VII | Cebu | 119549 | Pilar Central School | PILAR |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9939619.02 | Ongoing | 0.85 | 2024-11-01 |  | P00875475VS-CW1 | 24HI0110 | 2024-04-04 | 2024-04-11 | 2024-04-23 | 2024-04-30 | 2024-05-16 | M.C. BUYSER CONSTRUCTION & SUPPLY
NC 2024 |  | Region VII | Cebu | 119582 | Esperanza ES | PORO |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.95 | 2024-10-05 |  | P00875452VS-CW1 | 24HI0087 | 2024-03-06 | 2024-03-14 | 2024-03-27 | 2024-04-15 | 2024-04-29 | WQC DESIGN & CONSTRUCTION
NC 2024 |  | Region VII | Cebu | 303085 | San Jose National High School | PORO |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.9 | 2024-10-05 |  | P00875474VS-CW1 | 24HI0088 | 2024-03-06 | 2024-03-14 | 2024-03-27 | 2024-04-15 | 2024-04-29 | WQC DESIGN & CONSTRUCTION
NC 2024 |  | Region VII | Cebu | 501353 | Sta. Rita Integrated School | PORO |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.95 | 2024-10-05 |  | P00875473VS-CW1 | 24HI0089 | 2024-03-06 | 2024-03-14 | 2024-03-27 | 2024-04-15 | 2024-04-29 | WQC DESIGN & CONSTRUCTION
NC 2024 |  | Region VII | Cebu | 502121 | Campo IS | SAN FRANCISCO |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.4 | 2024-11-23 |  | P00875451VS-CW1 | 24HI0124 | 2024-05-03 | 2024-05-10 | 2024-05-22 | 2024-05-30 | 2024-06-17 | WQC DESIGN & CONSTRUCTION
NC 2024 |  | Region VII | Cebu | 187036 | Dumalerio Elementary School | SAN FRANCISCO |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.91 | 2025-06-21 |  | P0087540VS-CW1 | 24HI0127 | 2024-05-09 | 2024-03-16 | 2024-05-29 | 2024-12-27 | 2025-01-13 | WQC DESIGN & CONSTRUCTION
NC 2024 |  | Region VII | Cebu | 119732 | Inocoyan ES | SOGOD |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9933715.08 | Ongoing | 0.38 | 2025-08-10 |  | P00875479VS-CW1 | 24HI0133 | 2024-11-16 | 2024-11-27 | 2024-12-10 | 2024-12-27 | 2025-01-13 | WQC DESIGN & CONSTRUCTION | Not yet mobilized
NC 2024 |  | Region VII | Cebu | 119746 | Tangke Elementary School | SOGOD |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9940000 | Ongoing | 0.4 | 2025-02-23 |  | P00875476VS-CW1 | 24HI0109 | 2024-04-04 | 2024-04-11 | 2024-04-23 | 2024-05-08 | 2024-05-23 | WQC DESIGN & CONSTRUCTION
NC 2024 |  | Region VII | Cebu | 119234 | Bagong Lipunan Elementary School | CONSOLACION |  | 1 | 8 | 4STY8CL (Phase 1) | GAA 17B | 15000000 |  | 14904512.79 | Ongoing | 0.3 | 2025-02-03 |  | P00875460VS-CW1 | 24HN0167 | 2024-05-16 | 2024-05-23 | 2024-06-04 | 2024-06-10 | 2024-06-18 | XLA CONSTRUCTION
NC 2024 |  | Region VII | Cebu | 137084 | Pitogo Primary School | CONSOLACION |  | 1 | 12 | 4STY12CL | GAA 17B | 25000000 |  | 24782396.29 | Ongoing | 0.4 | 2024-11-07 |  | P00875458VS-CW1 | 24HN0156 | 2024-04-15 | 2024-04-23 | 2024-05-07 | 2024-05-09 | 2024-05-15 | GTM BUILDERS AND SUPPLY
NC 2024 |  | Region VII | Cebu | 187025 | Catarman Elementary School | CORDOVA |  | 1 | 12 | 4STY12CL | GAA 17B | 15000000 |  | 14910000 | Ongoing | 0.05 | 2025-01-11 |  | P00875459VS-CW1 | 24HN0166 | 2024-05-16 | 2024-05-23 | 2024-06-04 | 2024-06-10 | 2024-06-18 | POWER MOVE BUILDERS AND CONSTRUCTION SUPPLY
NC 2024 |  | Region VII | Cebu | 305874 | Pilipog Night High School | CORDOVA |  | 1 | 20 | 4STY20CL (Phase 1) | GAA 17B | 20000000 |  | 19891365.13 | Ongoing | 0.15 | 2025-03-16 |  | P00875461VS-CW1 | 24HN0173 | 2024-06-07 | 2024-06-14 | 2024-07-31 | 2024-08-08 | 2024-08-14 | BANTAY CONSTRUCTION
NC 2024 |  | Region VII | Cebu | 119008 | Matutinao ES | BADIAN |  | 1 | 6 | 2STY6CL (Phase 2) | GAA 17B | 24000000 |  | 23585000 | Ongoing | 0.5 | 2024-09-23 |  | P00875462VS-CW1 | 24HO0132 | 2024-02-28 | 2024-03-06 | 2024-03-19 | 2024-03-26 | 2024-04-08 | CELJEM CONSTRUCTION & DEVELOPMENT CORP.
NC 2024 |  | Region VII | Cebu | 303033 | Langin NHS | RONDA |  | 1 | 6 | 2STY6CL (Phase 2) | GAA 17B | 16000000 |  | 15820000 | Ongoing | 0.9 | 2024-09-27 |  | P00875463VS-CW1 | 24HO0143 | 2024-03-06 | 2024-03-13 | 2024-04-02 | 2024-04-08 | 2024-04-16 | FIRST GRANDEUR BUILDERS
NC 2024 |  | Region VII | Cebu City | 119899 | Banilad ES | CEBU CITY (Capital) |  | 1 | 12 | 4STY12CL | GAA 17B | 25000000 |  | 24855000 | Ongoing | 0.35 | 2024-12-14 |  | P00875464VS-CW1 | 24HH0101 | 2024-03-20 | 2024-04-05 | 2024-04-17 | 2024-04-24 | 2024-05-20 | MBD General Construction | On-going
NC 2024 |  | Region VII | Cebu City | 119901 | Mabolo ES | CEBU CITY (Capital) |  | 1 | 8 | 4STY8CL | GAA 17B | 15000000 |  | 14915000 | Ongoing | 0.85 | 2024-10-10 |  | P00875465VS-CW1 | 24HH0100 | 2024-03-20 | 2024-04-05 | 2024-04-17 | 2024-04-25 | 2024-05-08 | Planac Construction | On-going
NC 2024 |  | Region VII | Cebu City | 303160 | Pit-os National High School | CEBU CITY (Capital) |  | 1 | 8 | 4STY8CL | BATCH 1 | 39334722.35 |  | 39113048.74 | Ongoing | 0.23 | 2024-04-16 |  | P00875686VS-CW1 | 24HH0129 | 2024-07-03 | 2024-07-12 | 2024-07-24 | 2024-07-29 | 2024-08-20 | W & J Construction & General Supply | On-going
NC 2024 |  | Region VII | Cebu City | 303162 | OPRRA NHS (Day & Night) | CEBU CITY (Capital) |  | 1 | 16 | 4STY16CL | BATCH 1 | 64000000 |  | 63550000 | Ongoing | 0.08 | 2024-07-15 |  | P00800480VS-CW1 | 24HH0132 | 2024-07-31 | 2024-08-09 | 2024-08-22 | 2024-08-29 | 2024-09-19 | E.U. Caballero/ARQ Builders(J.V.) | On-going
NC 2024 |  | Region VII | Cebu City | 187501 | Quiot ES | CEBU CITY (Capital) |  | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  | 39759647 | Ongoing | 0.55 | 2025-01-17 |  | P00875466VS-CW1 | 24HH0102 | 2024-04-04 | 2024-04-12 | 2024-04-25 | 2024-04-29 | 2024-05-17 | La Prueba Construction/WTG Const. & Devlopment Corp.(J.V.) | On-going
NC 2024 |  | Region VII | Dumaguete City | 119935 | Camanjac Elementary School | DUMAGUETE CITY (Capital) |  | 1 | 12 | 3STY12CL | BATCH 1 | 30000000 |  | 29315691.03 | Ongoing | 0.45 | 2025-04-22 |  | P00875688VS-CW1 | 24HK0140 |  |  | 2024-07-08 | 2024-08-28 | 2024-06-09 | ISA CONSTRUCTION AND DEVELOPMENT CORPORATION | On-going
NC 2024 |  | Region VII | Guihulngan City | 324801 | Magsaysay National High School | CITY OF GUIHULNGAN |  | 1 | 4 | 2STY Workshop Building | BATCH 1 | 15450746.27 |  | 15220135.55 | Ongoing | 0.97 | 2025-01-22 |  | P00875689VS | 24HJ0119 | 2024-04-23 | 2024-04-30 | 2024-05-14 | 2024-05-30 | 2024-03-06 | HIGEL CONSTRUCTION
NC 2024 |  | Region VII | Guihulngan City | 324802 | P. Zamora National High School | CITY OF GUIHULNGAN |  | 1 | 4 | 2STY4CL | GAA 17B | 16000000 |  | 15829619.26 | Completed | 1 | 2024-10-21 | 2024-10-30 | P00875481VS | 24HJ0110 | 2024-02-21 | 2024-02-28 | 2024-12-03 | 2024-03-27 | 2024-01-04 | K.M. GOLONG CONSTRUCTION
NC 2024 |  | Region VII | Guihulngan City | 120642 | Vallehermoso Central Elementary School | VALLEHERMOSO |  | 1 | 2 | 2STY2CL | GAA 17B | 7000000 |  | 6911026.67 | Completed | 1 | 2024-11-09 | 2025-02-20 | P00875483VS | 24HJ0111 | 2024-02-21 | 2024-02-28 | 2024-12-03 | 2024-03-27 | 2024-01-04 | REKINA CONSTRUCTION SERVICES
NC 2024 |  | Region VII | Lapu-Lapu City | 119985 | Babag I Elementary School | LAPU-LAPU CITY (OPON) |  | 1 | 8 | 4STY8CL | BATCH 1 | 40062069.4 |  | 39830555.51 | Ongoing | 0.65 | 2025-04-13 |  | P00875690VS-CW1 | 24HN0155 | 2024-04-15 | 2024-04-23 | 2024-08-09 | 2024-08-19 | 2024-08-27 | SBD BUILDERS
NC 2024 |  | Region VII | Lapu-Lapu City | 119953 | Cawhagan Elementary School | LAPU-LAPU CITY (OPON) |  | 1 | 8 | 4STY8CL | GAA 17B | 20000000 |  | 14915000.38 | Ongoing | 0.7 | 2025-02-13 |  | P00875467VS-CW1 | 24HN0165 | 2024-05-16 | 2024-05-23 | 2024-06-04 | 2024-06-10 | 2024-06-18 | SBD BUILDERS | Phase 1 Only
NC 2024 |  | Region VII | Lapu-Lapu City | 119982 | Suba Basbas Elementary School | LAPU-LAPU CITY (OPON) |  | 1 | 8 | 4STY8CL | GAA 17B | 20000000 |  | 14915006.06 | Completed | 1 | 2025-03-02 | 2025-04-15 | P00875468VS-CW1 | 24HN0168 | 2024-05-16 | 2024-05-23 | 2024-05-16 | 2024-06-10 | 2024-06-18 | SBD BUILDERS | Phase 1 Only
NC 2024 |  | Region VII | Mandaue City | 120013 | Maguikay ES | MANDAUE CITY |  | 1 | 12 | 4STY12CL | GAA 17B | 20000000 |  | 19850000 | Ongoing | 0.85 | 2025-01-29 |  | POO875470VS-CW1 | 24HN0148 | 2024-03-27 | 2024-04-04 | 2024-04-16 | 2024-09-05 | 2014-05-15 | ZLREJ TRADING AND CONST. CORP.
NC 2024 |  | Region VII | Mandaue City | 119995 | Mayor A.S. Fortuna Memorial ES | MANDAUE CITY |  | 1 | 4 | 4STY4CL | GAA 17B | 20000000 |  | 19869996.83 | Ongoing | 0.65 | 2025-02-27 |  | POO875471VS-CW1 | 24HN0172 | 2024-07-06 | 2024-06-14 | 2024-06-26 | 2024-07-01 | 2024-10-07 | GOLDFIN CONSTRUCTION AND DEV'T. CORP.
NC 2024 |  | Region VII | Tagbilaran City | 118705 | City East Elementary School | TAGBILARAN CITY (Capital) |  | 1 | 8 | Construction of 8CL | GAA 17B | 20000000 |  | 18298800 | Ongoing | 0.15 | 2025-07-14 |  | 24HA0158 | 24HA0158 | 2024-08-28 | 2024-09-04 | 2024-09-17 | 2024-11-26 | 2024-12-09 | HANZGRACE CONSTRUCTION AND TRADING CORPORATION | Approved for Modification
NC 2024 |  | Region VII | Tagbilaran City | 322102 | San Isidro National High School | TAGBILARAN CITY (Capital) |  | 1 | 8 | Construction of 8CL | GAA 17B | 20000000 |  | 19870000 | Ongoing | 0.09 | 2025-07-14 |  | 24HA0157 | 24HA0157 | 2024-08-28 | 2024-09-04 | 2024-09-17 | 2024-11-26 | 2024-12-09 | One Orchard Construction Corporation | Approved for Modification
NC 2024 |  | Region VII | Tagbilaran City | 118714 | Taloto Elementary School | TAGBILARAN CITY (Capital) |  | 1 | 11 | 1STY2CL & 3STY9CL | BATCH 1 | 38682075.08 |  | 38455812.43 | Ongoing | 0.17 | 2025-07-17 |  | 24HA0149 | 24HA0149 | 2024-08-02 | 2024-08-09 | 2024-08-22 | 2024-08-30 | 2024-09-13 | CEMPRON CONSTRUCTION AND DEVELOPMENT
NC 2024 |  | Region VII | Talisay City | 119789 | Mohon Elementary School | CITY OF TALISAY |  | 1 | 16 | 4STY16CL | BATCH 1 | 69821643 |  | 69440000 | Ongoing | 0.95 | 2025-03-23 | 2025-03-23 | P00875693VS-CW1 | 24HE0198 | 2024-10-05 | 2024-05-29 | 2024-05-29 | 2024-06-18 | 2024-06-28 | January Builders | On going
NC 2024 |  | Region VII | Toledo City | 120734 | Matab-ang ES | TOLEDO CITY |  | 1 | 12 | 4STY12CL | BATCH 1 | 35894925.92 |  | 35615000 | Ongoing | 0.85 | 2025-01-03 |  | P00875694VS-CW1 | 24HF0100 | 2024-05-05 | 2024-10-05 | 2024-05-22 | 2024-05-28 | 2024-03-06 | QM Builders | DPWH IMPLEMENTED

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.