## Sheet1
CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
QRF 2022 | Region VII | Bais City | 120093 | Lo-oc ES | BAIS CITY | 2 | 1 | 5 | REPAIR/ REHABILITATION | 2505799.8511 | 1 | 2204740.3 | Completed | 1 | 2022-12-19 |  |  |  |  | 2022-06-15 | 2022-06-28 | 2022-08-10 | 2022-08-19 | Per Construction and Supply
QRF 2022 | Region VII | Bayawan City | 120123 | Bayawan City East Central School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 11 | REPAIR/ REHABILITATION | 4843369.1238 | 1 | 4798000 | Completed | 1 |  |  |  |  | 2022-06-10 | 2022-06-16 | 2022-06-28 | 2022-07-07 | 2022-08-09 | RISM Builders
QRF 2022 | Region VII | Bohol | 118092 | Calape Central ES | CALAPE | 1 | 1 | 5 | REPAIR/ REHABILITATION | 2035879.1023 | 1 | 1688711.75 | Completed | 1 | 2023-06-05 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA
QRF 2022 | Region VII | Bohol | 118169 | Catigbian Central ES | CATIGBIAN | 1 | 1 | 3 | REPAIR/ REHABILITATION | 394702.3278 | 1 | 8481676.16 | Completed | 1 | 2023-05-27 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA
QRF 2022 | Region VII | Bohol | 118169 | Catigbian Central ES | CATIGBIAN | 1 |  | 4 | NEW CONSTRUCTION | 10000000 | 1 | one contract only | Completed | 1 | 2023-05-27 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA
QRF 2022 | Region VII | Bohol | 118170 | Catigbian West Central ES | CATIGBIAN | 1 | 1 | 7 | REPAIR/ REHABILITATION | 2464214.5948 | 1 | 2078987.8 | Completed | 1 | 2023-05-28 | 2023-07-13 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06
QRF 2022 | Region VII | Bohol | 118485 | Loon North Central ES | LOON | 1 | 1 | 13 | REPAIR/ REHABILITATION | 9920579.6796 | 1 | 10807364.11 | completed | 1 | 2023-07-10 | 2023-06-15 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA
QRF 2022 | Region VII | Bohol | 118485 | Loon North Central ES | LOON | 1 |  | 2 | NEW CONSTRUCTION | 5000000 | 1 | one contract only | completed | 1 | 2023-07-10 | 2023-06-15 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA
QRF 2022 | Region VII | Bohol | 118500 | Loon South Central ES | LOON | 1 | 1 | 13 | REPAIR/ REHABILITATION | 4011500.3828 | 1 |  | completed | 1 | 2023-06-10 | 2023-05-18 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA
QRF 2022 | Region VII | Bohol | 118544 | Maribojoc Central Elementary School | MARIBOJOC | 1 | 1 | 4 | REPAIR/ REHABILITATION | 1123979.4978 | 1 | 949762.26 | completed | 1 | 2023-06-05 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA
QRF 2022 | Region VII | Bohol | 118797 | Tubigon West Central ES | TUBIGON | 1 | 1 | 36 | REPAIR/ REHABILITATION | 7865817.4963 | 1 | 7848025.48 | completed | 1 | 2023-05-26 | 373821 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA
QRF 2022 | Region VII | Bohol | 312333 | Tubigon West Central HS | TUBIGON | 1 | 1 | 27 | REPAIR/ REHABILITATION | 3010520.9927 | 1 | 2080522.21 | completed | 1 | 2023-07-03 | 2023-06-03 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA
QRF 2022 | Region VII | Bohol | 118065 | Buenavista CES | BUENAVISTA | 2 | 1 | 7 | REPAIR/ REHABILITATION | 2690422.9533 | 1 |  | Completed | 1 | 2023-05-28 | 2023-06-05 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA
QRF 2022 | Region VII | Bohol | 312321 | San Miguel-Puertos HS | DAGOHOY | 2 | 1 | 15 | REPAIR/ REHABILITATION | 3895366.2255 | 1 |  | Completed | 1 | 2023-05-26 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06
QRF 2022 | Region VII | Bohol | 118239 | Danao Central Elementary School | DANAO | 2 | 1 | 22 | REPAIR/ REHABILITATION | 7899199.8429 | 1 |  | completed | 1 | 2023-09-23 | 2023-09-15 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06
QRF 2022 | Region VII | Bohol | 118239 | Danao Central Elementary School | DANAO | 2 |  | 6 | NEW CONSTRUCTION | 15000000 | 1 | one contract only | completed | 1 | 2023-09-23 | 2023-09-15 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | realigned scope of works same school
QRF 2022 | Region VII | Bohol | 118245 | Rowena Heights Elementary School | DANAO | 2 | 1 | 3 | NEW CONSTRUCTION | 7749834.84 | 1 | 7719318.54 | Completed | 1 | 2023-06-13 | 2023-06-09 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | realigned from cansibuan ps
QRF 2022 | Region VII | Bohol | 118331 | Getafe Central ES | GETAFE | 2 | 1 | 11 | REPAIR/ REHABILITATION | 4603452.9769 | 1 | 14585019 | completed | 1 | 2023-08-02 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06
QRF 2022 | Region VII | Bohol | 118331 | Getafe Central ES | GETAFE | 2 | 1 | 4 | NEW CONSTRUCTION | 10000000 | 1 | one contract only | completed | 1 | 2023-08-02 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | realigned scope of works same school
QRF 2022 | Region VII | Bohol | 118401 | Inabanga South Central Elementary School | INABANGA | 2 | 1 | 30 | REPAIR/ REHABILITATION | 9700192.5988 | 1 | 8439155.95 | completed | 1 | 2023-09-02 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06
QRF 2022 | Region VII | Bohol | 118600 | President Carlos P. Garcia Central Elementary School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 20 | REPAIR/ REHABILITATION | 9625173.5979 | 1 | 13325173.09 | completed | 1 | 2023-08-19 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | 60 DAYS EXT(WARNING FOR TERMINATION)
QRF 2022 | Region VII | Bohol | 118600 | President Carlos P. Garcia Central Elementary School | PRES. CARLOS P. GARCIA (PITOGO) | 2 |  | 3 | NEW CONSTRUCTION | 7500000 | 1 | one contract only | completed | 1 | 2023-08-19 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | 60 DAYS EXT(WARNING FOR TERMINATION)
QRF 2022 | Region VII | Bohol | 118656 | San Miguel Central ES | SAN MIGUEL | 2 | 1 | 19 | REPAIR/ REHABILITATION | 6065984.0904 | 1 |  | completed | 1 | 2023-06-05 | 2023-05-24 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA
QRF 2022 | Region VII | Bohol | 118656 | San Miguel Central ES | SAN MIGUEL | 2 |  | 1 | NEW CONSTRUCTION | 2500000 | 1 | 6766919.52 | completed | 1 | 2023-06-05 | 2023-05-24 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA
QRF 2022 | Region VII | Bohol | 118729 | Talibon Central ES | TALIBON | 2 | 1 | 2 | REPAIR/ REHABILITATION | 633410.9605 | 1 |  | completed | 1 |  | 2023-03-28 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA
QRF 2022 | Region VII | Bohol | 118743 | TALIBON II CENTRAL ES | TALIBON | 2 | 1 | 3 | REPAIR/ REHABILITATION | 959316.783 | 1 |  | completed | 1 | 2023-06-02 | 2028-03-28 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA
QRF 2022 | Region VII | Bohol | 118768 | Trinidad Central Elementary School | TRINIDAD | 2 | 1 | 10 | REPAIR/ REHABILITATION | 2766141.8503 | 1 |  | completed | 1 | 2023-06-02 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA
QRF 2022 | Region VII | Bohol | 302899 | San Pascual National Agr'l HS | UBAY | 2 | 1 | 26 | REPAIR/ REHABILITATION | 7670181.2855 | 1 | 6664002.04 | completed | 1 | 2023-08-02 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | FOR PUCNHLISTING
QRF 2022 | Region VII | Bohol | 118843 | Ubay Central ES | UBAY | 2 | 1 | 20 | REPAIR/ REHABILITATION | 6137354.1844 | 1 | 5187762.92 | completed | 1 | 2023-06-10 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06
QRF 2022 | Region VII | Bohol | 118804 | Ubay II Central ES (Biabas CES ) | UBAY | 2 | 1 | 17 | REPAIR/ REHABILITATION | 4963731.713 | 1 |  | completed | 1 | 2023-06-10 | 2023-05-17 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA
QRF 2022 | Region VII | Bohol | 117936 | Alicia Central Elem. | ALICIA | 3 | 1 | 9 | REPAIR/ REHABILITATION | 2206602.4549 | 1 | 3765037.24 | completed | 1 | 2023-06-27 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06
QRF 2022 | Region VII | Bohol | 117936 | Alicia Central Elem. | ALICIA | 3 |  | 1 | NEW CONSTRUCTION | 2500000 | 1 | one contract only | completed | 1 | 2023-06-27 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06
QRF 2022 | Region VII | Bohol | 186507 | Alicia CES Annex | ALICIA | 3 | 1 | 2 | REPAIR/ REHABILITATION | 800000 | 1 | 643141.32 | completed | 1 | 2023-06-02 | 2023-07-21 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06
QRF 2022 | Region VII | Bohol | 302809 | Alicia Technical-Voc'l HS | ALICIA | 3 | 1 | 19 | REPAIR/ REHABILITATION | 5594602.4759 | 1 | 23440717.89 | completed | 1 | 2023-11-13 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06
QRF 2022 | Region VII | Bohol | 302809 | Alicia Technical-Voc'l HS | ALICIA | 3 |  | 9 | NEW CONSTRUCTION | 22500000 | 1 | one contract only | completed | 1 | 2023-11-13 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06
QRF 2022 | Region VII | Bohol | 118136 | Carmen West Central ES | CARMEN | 3 | 1 | 6 | REPAIR/ REHABILITATION | 2319764.4847 | 1 | 1869129.45 | completed | 1 | 2023-06-02 | 2023-08-04 | 0 |  | 2022-08-12 | 2022-08-22 | 2022-09-06
QRF 2022 | Region VII | Bohol | 118291 | Duero Central ES | DUERO | 3 | 1 | 3 | REPAIR/ REHABILITATION | 1200000 | 1 | 1056904.73 | completed | 1 | 2023-06-26 | 2023-07-20 | 0 |  | 2022-08-12 | 2022-08-22 | 2022-09-06
QRF 2022 | Region VII | Bohol | 118312 | Garcia-Hernandez Central ES | GARCIA HERNANDEZ | 3 | 1 | 3 | REPAIR/ REHABILITATION | 1200000 | 1 | 1056904.73 | completed | 1 | 2023-06-26 | 2023-07-20 | 0 |  | 2022-08-12 | 2022-08-22 | 2022-09-06
QRF 2022 | Region VII | Bohol | 118437 | Lila Central ES | LILA | 3 | 1 | 4 | REPAIR/ REHABILITATION | 648384.0631 | 1 | 572086.04 | completed | 1 | 2023-06-26 | 2023-07-20 | 0 |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA
QRF 2022 | Region VII | Bohol | 118466 | Loboc Central Elementary School | LOBOC | 3 | 1 | 31 | REPAIR/ REHABILITATION | 3139918.14 | 1 |  | completed | 1 |  |  | 0 |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA
QRF 2022 | Region VII | Bohol | 118466 | Loboc Central Elementary School | LOBOC | 3 |  | 8 | NEW CONSTRUCTION | 20000000 | 1 | one contract only | completed | 1 | 2023-10-01 |  | 0 |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | 60 DAYS EXT
QRF 2022 | Region VII | Bohol | 118693 | Sierra Bullones Central ES | SIERRA BULLONES | 3 | 1 | 5 | REPAIR/ REHABILITATION | 2000000 | 1 | 7599717.51 | completed | 1 | 2023-08-02 | 2023-08-18 | 0 |  | 2022-08-12 | 2022-08-22 | 2022-09-06
QRF 2022 | Region VII | Bohol | 118693 | Sierra Bullones Central ES | SIERRA BULLONES | 3 |  | 3 | NEW CONSTRUCTION | 7500000 | 1 | one contract only | completed | 1 | 2023-08-02 | 2023-08-18 | 0 |  | 2022-08-12 | 2022-08-22 | 2022-09-06
QRF 2022 | Region VII | Bohol | 118864 | Valencia Central Elementary School | VALENCIA | 3 | 1 | 4 | REPAIR/ REHABILITATION | 624035.1223 | 1 | 546229.05 | completed | 1 | 2023-06-26 | 2023-07-20 | 0 |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA
QRF 2022 | Region VII | Carcar City | 324904 | Tuyom National High School | CITY OF CARCAR | 1 | 1 | 20 | REPAIR/ REHABILITATION | 5641920.23 | 1 | 4296456.4 | completed | 1 |  |  | 0
QRF 2022 | Region VII | Cebu | 119073 | BARILI CES | BARILI | 3 | 1 | 2 | REPAIR/ REHABILITATION | 2677562.96 | 1 | 8109500.82 | COMPLETED | 1 | 2024-01-17 |  | CY 2022 QRF DEPED | CY 2022 QRF-DEPED-R7-CEBU-04 | JULY 19, 2023 | JULY 26, 2023 | AUGUST 07, 2023 | AUGUST 29, 2023 | 2023-09-11 | RT CONSTRUCTION
QRF 2022 | Region VII | Cebu | 119073 | BARILI CES | BARILI | 3 |  | 2 | NEW CONSTRUCTION | 5462455.36 | 1 | 8109500.82 | COMPLETED | 1 | 2024-01-17 |  | CY 2022 QRF DEPED | CY 2022 QRF-DEPED-R7-CEBU-04 | JULY 19, 2023 | JULY 26, 2023 | AUGUST 07, 2023 | AUGUST 29, 2023 | 2023-09-11 | RT CONSTRUCTION
QRF 2022 | Region VII | Cebu | 119092 | GUIBUANGAN CS | BARILI | 3 | 1 | 5 | REPAIR/ REHABILITATION | 2449646.32 | 1 | 2431144.86 | COMPLETED | 1 | 2023-11-18 |  | CY 2022 QRF DEPED | CY 2022 QRF-DEPED-R7-CEBU-05 | JULY 19, 2023 | JULY 26, 2023 | AUGUST 07, 2023 | AUGUST 29, 2023 | 2023-09-11 | AL SHER CONSTRUCTION
QRF 2022 | Region VII | Cebu | 119554 | Binabag ES | PINAMUNGAHAN | 3 | 1 | 6 | REPAIR/ REHABILITATION | 4245989.99 | 1 | 4224375.21 | COMPLETED | 1 | 2023-12-18 |  | CY 2022 QRF DEPED | CY 2022 QRF-DEPED-R7-CEBU-06 | JULY 19, 2023 | JULY 26, 2023 | AUGUST 07, 2023 | AUGUST 29, 2023 | 2023-09-11 | HERO CONSTRUCTION AND DEV. CORP.
QRF 2022 | Region VII | Cebu | 119414 | Liloan Central ES | LILOAN | 5 | 1 | 5 | REPAIR/ REHABILITATION | 3582726.85 | 1 | 9562486.57 | Completed | 1 | 2024-01-17 |  | CY 2022 QRF DEPED | CY 2022 QRF-DEPED-R7-CEBU-01 | JULY 19, 2023 | JULY 26, 2023 | AUGUST 07, 2023 | AUGUST 29, 2023 | 2023-09-11 | MANINGO ENTERPRISES
QRF 2022 | Region VII | Cebu | 119414 | Liloan Central ES | LILOAN | 5 |  | 2 | NEW CONSTRUCTION | 6011939.84 | 1 | 9562486.57 | Completed | 1 | 2024-01-17 |  | CY 2022 QRF DEPED | CY 2022 QRF-DEPED-R7-CEBU-01 | JULY 19, 2023 | JULY 26, 2023 | AUGUST 07, 2023 | AUGUST 29, 2023 | 2023-09-11 | MANINGO ENTERPRISES
QRF 2022 | Region VII | Cebu | 119238 | Consolacion Central ES | CONSOLACION | 6 | 1 | 24 | REPAIR/ REHABILITATION | 1942416.66 | 1 | 1934634.58 | COMPLETED | 1 | 2023-12-18 |  | CY 2022 QRF DEPED | CY 2022 QRF-DEPED-R7-CEBU-03 | JULY 19, 2023 | JULY 26, 2023 | AUGUST 07, 2023 | AUGUST 29, 2023 | 2023-09-11 | JY BONTILAO CONSTRUCTION AND ENTERPRISES
QRF 2022 | Region VII | Cebu | 119255 | Cordova Central ES | CORDOVA | 6 | 1 | 10 | REPAIR/ REHABILITATION | 2032057.71 | 1 | 2024217.87 | COMPLETED | 1 |  |  | 0
QRF 2022 | Region VII | Cebu | 302955 | Cordova NHS | CORDOVA | 6 | 1 | 20 | REPAIR/ REHABILITATION | 8932633.17 | 1 | 8856359.04 | COMPLETED | 1 | 2024-01-17 |  | CY 2022 QRF DEPED | CY 2022 QRF-DEPED-R7-CEBU-02 | JULY 19, 2023 | JULY 26, 2023 | AUGUST 07, 2023 | AUGUST 29, 2024 | 2023-09-11 | SB & T CONSTRUCTION OPC
QRF 2022 | Region VII | Cebu | 118866 | ALCANTARA CENTRAL ES | ALCANTARA | 7 | 1 | 6 | REPAIR/ REHABILITATION | 9144788.68 | 1 | 9127739.72 | Completed | 1 | 2024-01-17 |  | CY 2022 QRF DEPED | CY 2022 QRF-DEPED-R7-CEBU-08 | JULY 19, 2023 | JULY 26, 2023 | AUGUST 07, 2023 | AUGUST 29, 2023 | 2023-09-11 | RT CONSTRUCTION
QRF 2022 | Region VII | Cebu | 118994 | BADIAN CS | BADIAN | 7 | 1 | 3 | REPAIR/ REHABILITATION | 1234605.36 | 1 | 1219140.57 | completed | 1 | 2023-11-03 |  | CY 2022 QRF DEPED | CY 2022 QRF-DEPED-R7-CEBU-09 | JULY 19, 2023 | JULY 26, 2023 | AUGUST 07, 2023 | AUGUST 29, 2023 | 2023-09-11 | TRI BAIRN CONSTRUCTION
QRF 2022 | Region VII | Cebu | 119384 | BITOON CES | DUMANJUG | 7 | 1 | 19 | REPAIR/ REHABILITATION | 9583177.1 | 1 | 9533171.37 | COMPLETED | 1 | 2024-01-17 |  | CY 2022 QRF DEPED | CY 2022 QRF-DEPED-R7-CEBU-07 | JULY 19, 2023 | JULY 26, 2023 | AUGUST 07, 2023 | AUGUST 29, 2023 | 2023-09-11 | MP SORELA CONSTRUCTION AND SUPPLY AND MARINE SERVICES
QRF 2022 | Region VII | Cebu City | 119874 | City Central ES | CEBU CITY (Capital) | 1 | 1 | 12 | REPAIR/ REHABILITATION | 2750822 | 1 | 2116754.46 | completed | 1 | 2023-01-13 |  | DepEd CCD 2022 - 11 | DepEd CCD 2022 - 27 | 2022-07-09 | 2022-07-18 | 2022-08-01 | 2022-08-12 | Sept. 8, 2022 | JAJ & L CONST. & ENG'G sERVICES
QRF 2022 | Region VII | Cebu City | 303153 | City Central NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 5 | REPAIR/ REHABILITATION | 668241 | 1 | 510702.36 | completed | 1 | 2022-11-14 |  | DepEd CCD 2022 - 12 | DepEd CCD 2022 - 28 | 2022-07-09 | 2022-07-18 | 2022-08-01 | 2022-08-12 | Sept. 8, 2022 | JAJ & L CONST. & ENG'G sERVICES
QRF 2022 | Region VII | Cebu City | 119882 | Mambaling ES | CEBU CITY (Capital) | 2 | 1 | 10 | REPAIR/ REHABILITATION | 3219187.68 | 1 | 2315902.45 | completed | 1 | 2023-01-25 |  | DepEd CCD 2022 - 13 | DepEd CCD 2022 - 29 | 2022-07-09 | 2022-07-18 | 2022-08-01 | 2022-08-12 | Sept. 20, 2022 | ANIELTHON CONST. & SUPPLY
QRF 2022 | Region VII | City of Naga, Cebu | 119516 | Cepoc Central Elementary School | CITY OF NAGA | 1 | 1 | 8 | REPAIR/ REHABILITATION | 3999819.9246 | 1 | 3992404.31 | completed | 1 | 2022-10-25 |  | cityofnaga2022-001 |  | 2022-04-12 | 2022-04-19 | 2022-05-04 | 2022-05-25 | 2022-06-20 | SB & T Construction OPC | LOT 2
QRF 2022 | Region VII | City of Naga, Cebu | 119509 | Naga Central Elementary School | CITY OF NAGA | 1 | 1 | 13 | REPAIR/ REHABILITATION | 6498802.268 | 1 | 6487267.56 | completed | 1 | 2022-10-25 |  | cityofnaga2022-001 |  | 2022-04-12 | 2022-04-19 | 2022-05-04 | 2022-05-25 | 2022-06-20 | TRI BAIRN CONSTRUCTION | LOT 1
QRF 2022 | Region VII | City of Naga, Cebu | 500218 | Naga Special Education Center | CITY OF NAGA | 1 | 1 | 8 | REPAIR/ REHABILITATION | 4999370.2543 | 1 | 4990393.35 | completed | 1 | 2022-10-25 |  | cityofnaga2022-001 |  | 2022-04-12 | 2022-04-19 | 2022-05-04 | 2022-05-25 | 2022-06-20 | TRI BAIRN CONSTRUCTION | LOT 1
QRF 2022 | Region VII | City of Naga, Cebu | 119512 | Tuyan Central Elementary School | CITY OF NAGA | 1 | 1 | 10 | REPAIR/ REHABILITATION | 5025620.2543 | 1 | 4979100.18 | completed | 1 | 2022-10-25 |  | cityofnaga2022-001 |  | 2022-04-12 | 2022-04-19 | 2022-05-04 | 2022-05-25 | 2022-06-20 | SB & T Construction OPC | LOT 2
QRF 2022 | Region VII | Lapu-Lapu City | 119954 | Caw-oy Elementary School | LAPU-LAPU CITY (OPON) | 6 | 1 | 12 | REPAIR/ REHABILITATION | 4351778.22 | 1 |  | completed | 1 |  |  | 0 | [7 empty] | realigned same school change target and scope
QRF 2022 | Region VII | Lapu-Lapu City | 119989 | Lapu-Lapu City Central Elementary School | LAPU-LAPU CITY (OPON) | 6 | 1 | 75 | REPAIR/ REHABILITATION | 36000000 | 1 |  | completed | 1 | January 26, 2023 |  | 2022-Infra-001 |  | June 22, 2022 | June 29, 2022 | July 11, 2022 | July 29, 2022 | December 29, 2022 | MANINGO ENTERPRISES | realigned same school change target and scope
QRF 2022 | Region VII | Lapu-Lapu City | 119989 | Lapu-Lapu City Central Elementary School | LAPU-LAPU CITY (OPON) | 6 |  | 8 | REPAIR/ REHABILITATION | 27500000 | 1 |  | Completed | 1 | January 26, 2023 |  | 2022-Infra-001 |  | June 22, 2022 | June 29, 2022 | July 11, 2022 | July 29, 2022 | December 29, 2022 | MANINGO ENTERPRISES | realigned same school change target and scope
QRF 2022 | Region VII | Talisay City | 322203 | Manipis National High School | CITY OF TALISAY | 1 | 1 | 4 | REPAIR/ REHABILITATION | 1926214.1136 | 1 |  | completed | 1 |  |  | 0
QRF 2022 | Region VII | Talisay City | 119803 | Tabunoc Central School | CITY OF TALISAY | 1 | 1 | 4 | REPAIR/ REHABILITATION | 1869425.3973 | 1 |  | completed | 1 |  |  | 0
QRF 2022 | Region VII | Talisay City | 119791 | Talisay City CES | CITY OF TALISAY | 1 | 1 | 38 | REPAIR/ REHABILITATION | 7433950.4127 | 1 |  | completed | 1 |  |  | 0
QRF 2022 | Region VII | Talisay City | 119791 | Talisay City CES | CITY OF TALISAY | 1 |  | 12 | NEW CONSTRUCTION | 30000000 | 1 |  | completed | 1 |  |  | 0
QRF 2022 | Region VII | Toledo City | 120757 | South City Central ES | TOLEDO CITY | 3 | 1 | 22 | REPAIR/ REHABILITATION | 11050000 | 1 |  | completed | 1 |  |  | 0
QRF 2022 REPLENISHMENT | Region VII | Bohol | 117968 | Antequera Central ES | ANTEQUERA | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 1412793.43 | 1 |  | completed | 1 | 2023-08-16 |  | 0
QRF 2022 REPLENISHMENT | Region VII | Bohol | 118171 | Causwagan ES | CATIGBIAN | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 212611.3412 | 1 |  | completed | 1 | 2023-10-05 |  | 0
QRF 2022 REPLENISHMENT | Region VII | Bohol | 118027 | Bien Unido Central ES | BIEN UNIDO | 2nd | 1 | 1 | Replacement | 2500000 | 1 |  | completed | 1 | 2023-09-30 |  | 0
QRF 2022 REPLENISHMENT | Region VII | Bohol | 118027 | Bien Unido Central ES | BIEN UNIDO | 2nd | 1 | 30 | REPAIR OF CLASSROOMS | 8892337.27 | 1 |  | completed | 1 | 2023-09-29 |  | 0
QRF 2022 REPLENISHMENT | Region VII | Bohol | 118223 | Dagohoy Central Elementary | DAGOHOY | 2nd | 1 | 2 | Replacement | 5000000 | 1 |  | completed | 1 | 2023-11-28 |  | 0
QRF 2022 REPLENISHMENT | Region VII | Bohol | 118223 | Dagohoy Central Elementary | DAGOHOY | 2nd | 1 | 18 | REPAIR OF CLASSROOMS | 7385372.54 | 1 |  | completed | 1 | 2023-08-06 |  | 0
QRF 2022 REPLENISHMENT | Region VII | Bohol | 500209 | Inabanga North Central Integrated School (Elementary) | INABANGA | 2nd | 1 | 13 | REPAIR OF CLASSROOMS | 3501389.7546 | 1 |  | completed | 1 | 2023-10-30 |  | 0
QRF 2022 REPLENISHMENT | Region VII | Bohol | 118641 | San Isidro Central ES | SAN ISIDRO | 2nd | 1 | 9 | REPAIR OF CLASSROOMS | 3191281.8119 | 1 |  | completed | 1 | 2023-10-29 |  | 0
QRF 2022 REPLENISHMENT | Region VII | Bohol | 117953 | Anda Central ES | ANDA | 3rd | 1 | 3 | REPAIR OF CLASSROOMS | 336249.7955 | 1 |  | completed | 1 | 2023-11-10 |  | 0
QRF 2022 REPLENISHMENT | Region VII | Bohol | 118012 | Batuan Central ES | BATUAN | 3rd | 1 | 4 | REPAIR OF CLASSROOMS | 982408.6011 | 1 |  | completed | 1 | 2023-11-10 |  | 0
QRF 2022 REPLENISHMENT | Region VII | Bohol | 118193 | Clarin Central ES | CLARIN | 3rd | 1 | 17 | REPAIR OF CLASSROOMS | 4446904.5091 | 1 |  | completed | 1 | 2023-10-30 |  | 0
QRF 2022 REPLENISHMENT | Region VII | Bohol | 118520 | Mabini Central ES | MABINI | 3rd | 1 | 7 | REPAIR OF CLASSROOMS | 2450000 | 1 |  | completed | 1 | 2023-10-29 |  | 0
QRF 2022 REPLENISHMENT | Region VII | Bohol | 118581 | Pilar Central ES | PILAR | 3rd | 1 | 18 | REPAIR OF CLASSROOMS | 4933014.0625 | 1 |  | completed | 1 | 2023-10-05 |  | 0
QRF 2022 REPLENISHMENT | Region VII | Cebu | 119632 | SANGAT CES | SAN FERNANDO | 1st | 1 | 15 | REPAIR OF CLASSROOMS | 7500000 | 1 | 5707088.03 | REVERTED | 0 | 2023-09-06 |  | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-03 | 2023-02-22 | 2023-03-01 | 2023-03-13 |  | 2023-06-01 | GELA CONSTRUCTION
QRF 2022 REPLENISHMENT | Region VII | Cebu | 119722 | Sibonga Central ES | SIBONGA | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 2074340.3777 | 1 | 12305913.39 | completed | 1 | 2023-09-06 |  | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-02 | 2023-02-22 | 2023-03-01 | 2023-03-13 |  | 2023-06-01 | ANIELTHON CONSTRUCTION AND SUPPLY
QRF 2022 REPLENISHMENT | Region VII | Cebu | 118917 | Argao I Central ES | ARGAO | 2nd | 1 | 15 | REPAIR OF CLASSROOMS | 12359157.52 | 1 | 693338 | completed | 1 | 2023-09-06 |  | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-01 | 2023-02-22 | 2023-03-01 | 2023-03-13 |  | 2023-06-01 | GELA CONSTRUCTION
QRF 2022 REPLENISHMENT | Region VII | Cebu | 119298 | DALAGUETE CENTRAL ES | DALAGUETE | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 705637.3958 | 1 | 3560851.53 | completed | 1 | 2023-09-06 |  | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-04 | 2023-02-22 | 2023-03-01 | 2023-03-13 |  | 2023-06-01 | SB & T CONSTRUCTION
QRF 2022 REPLENISHMENT | Region VII | Cebu | 118900 | Aloguinsan Central ES | ALOGUINSAN | 3rd | 1 | 5 | REPAIR OF CLASSROOMS | 5745235.56 | 1 | 2491050.24 | completed | 1 | 2023-09-06 |  | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-05 | 2023-02-22 | 2023-03-01 | 2023-03-13 |  | 2023-06-01 | HERO CONTRUCTION AND DEVELOPMENT CORP.
QRF 2022 REPLENISHMENT | Region VII | Cebu | 119572 | Tajao Central School | PINAMUNGAHAN | 3rd | 1 | 14 | REPAIR OF CLASSROOMS | 3599380.52 | 1 | 3560851.53 | completed | 1 | 2023-09-06 |  | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-04 | 2023-02-22 | 2023-03-01 | 2023-03-13 |  | 2023-06-01 | SB & T CONSTRUCTION | for procurement;revised pow
QRF 2022 REPLENISHMENT | Region VII | Cebu | 119566 | PINAMUNGAJAN CES | PINAMUNGAJAN | 3rd | 1 | 9 | REPAIR OF CLASSROOMS | 2706993.5847 | 1 | 2073549.03 | completed | 1 | 2023-09-06 |  | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-01 | 2023-02-22 | 2023-03-01 | 2023-03-13 |  | 2023-06-01 | GELA CONSTRUCTION
QRF 2022 REPLENISHMENT | Region VII | Guihulngan City | 120642 | Vallehermoso Central Elementary School | VALLEHERMOSO | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1477590.79 | 1 | PHP 1,472,159.77 | completed | 1 | 2023-08-22 |  | CY 2022 QRF BATCH 2 | ITB 2023-002 | 2023-03-03 | 2023-03-10 | 2023-03-22 | 2023-04-14 | 2023-04-19 | TRIPLE JO CONSTRUCTION SERVICES
QRF 2022 REPLENISHMENT | Region VII | Tagbilaran City | 118713 | Tagbilaran City Central Elementary School | TAGBILARAN CITY (Capital) | 1st | 1 | 4 | Replacement | 17000000 | 1 | 16952019.97 | COMPLETED | 1 | 2023-09-29 | February 10, 2024 | 2023-003-Infra |  | 2023-03-10 |  | 2023-03-31 | 2023-04-05 | 2023-04-20 | DOLCI Construction and General Merchandise
QRF 2022 REPLENISHMENT | Region VII | Tagbilaran City | 118713 | Tagbilaran City Central Elementary School | TAGBILARAN CITY (Capital) | 1st | 1 | 9 | REPAIR OF CLASSROOMS | 3600000 | 1 | 16952019.97 | completed | 1 | 2023-07-04 | 2023-05-25 | 2023-001-Infra |  | 2023-02-24 |  | 2023-03-17 | 2023-03-21 | 2023-04-03 | C.Jansen Construction and General Merchandise
QRF 2022 REPLENISHMENT | Region VII | Tagbilaran City | 233001 | Tagbilaran City Central School SPED Center | TAGBILARAN CITY (Capital) | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 900000 | 1 |  | completed | 1 | 2023-07-04 | 2023-05-25 | 2023-002-Infra |  | 2023-02-24 |  | 2023-03-17 | 2023-03-21 | 2023-04-03 | C.Jansen Construction and General Merchandise
QRF 2022 REPLENISHMENT | Region VII | Tanjay City | 120563 | Sta. Cruz CES | CITY OF TANJAY | 2nd | 1 | 6 | REPAIR OF CLASSROOMS | 2520000 | 1 |  | completed | 1 |  |  | 0

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%