## Sheet1
Program-Year | CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
NC 2014 | K10 (2014) | Region VIII | Biliran | 120817 | Binongtoan ES | CULABA | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1924740.174 |  |  | COMPLETED | 1 | 2015-11-03 | 2015-11-03 | 080114S00010 | 15IA0083 | 2015-06-30 | 2015-07-15 | 2015-07-30 | 2015-08-10 | 2015-08-14 | BNL CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Biliran | 120869 | Capiňahan ES | Naval | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1033000 |  |  | COMPLETED | 1 | 2015-01-03 | 2015-01-03 | 080114S00006 | 14IA0041 | 2014-08-10 | 2014-08-12 | 2014-09-24 | 2014-10-01 | 2014-10-08 | BNL CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Biliran | 120791 | J.D. Garcia ES | Cabucgayan | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1033000 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 080114S00005 | 14IA0040 | 2014-08-10 | 2014-08-12 | 2014-08-26 | 2014-09-01 | 2014-09-10 | Z.A.S. CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Biliran | 303328 | Manlabang NHS | CAIBIRAN | 0 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 3 | 11382304.375 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Biliran | 303331 | Naval School of Fisheries | NAVAL (Capital) | 0 | 1 | 8 | 2UNITS 2STY4CL | 2014 K10 BATCH 3 | 12717729.5312 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Biliran | 120850 | Canduhao ES | MARIPIPI | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1022063.6325 |  |  | COMPLETED | 1 | 2015-01-03 | 2015-01-03 | 080114S00003 | 14IA0042 | 2014-08-10 | 2014-08-12 | 2014-09-24 | 2014-10-01 | 2014-10-08 | BNL CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Biliran | 120807 | Looc ES | CAIBIRAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1022063.6325 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Biliran | 120809 | Manlabang PS | CAIBIRAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1022063.6325 |  |  | COMPLETED | 1 | 2014-12-13 | 2014-12-13 | 080114S00002 | 14IA0038 | 2014-08-10 | 2014-08-12 | 2014-09-24 | 2014-10-01 | 2014-10-08 | INFRASERVE BUILDERS AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Biliran | 120765 | Palayan ES | ALMERIA | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1022063.6325 |  |  | COMPLETED | 1 | 2015-01-13 | 2015-01-13 | 080114S00004 | 14IA0037 | 2014-08-10 | 2014-08-12 | 2014-09-24 | 2014-10-01 | 2014-10-08 | INFRASERVE BUILDERS AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Biliran | 303332 | Tabunan NHS | ALMERIA | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1022063.6325 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Borongan City | 122399 | Can-abong ES | CITY OF BORONGAN (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 988434.8061 |  |  | COMPLETED | 1 | 2015-07-24 | 2015-04-30 | 080514S00135 | 14IB0136 | 2014-12-04 | 2014-12-05 | 2014-12-22 | 2015-01-06 | 2015-01-20 | JUCONS CONSTRUCTION &SUPPLY
NC 2014 | K10 (2014) | Region VIII | Borongan City | 122385 | San Mateo ES | CITY OF BORONGAN (Capital) | 0 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 4A | 1976869.6122 |  |  | COMPLETED | 1 | 2015-08-07 | 2015-08-07 | 080514S00129 | 14IB0136 | 2014-12-04 | 2014-12-05 | 2014-12-22 | 2015-01-06 | 2015-01-20 | JUCONS CONSTRUCTION &SUPPLY
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124004 | Alibaba Elementary School | CALBAYOG CITY | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-01-02 | 2015-01-02 | 080414S00061 | 14IJ-0071 | 2014-06-17 | 2014-06-29 | 2014-06-30 | 2014-07-04 | 2014-08-29 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124117 | Amampacang Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 080414S00049 | 14IJ-0075 | 2014-06-19 | 2014-07-01 | 2014-07-02 | 2014-08-28 | 2014-09-09 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124031 | Basud Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-18 | 2015-01-18 | 080414S00057 | 14IJ-0074 | 2014-06-19 | 2014-07-01 | 2014-07-02 | 2014-08-28 | 2014-09-09 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124055 | Begaho Elementary School | CALBAYOG CITY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-19 | 2014-12-19 | 080414S00055 | 14IJ-0069 (1) | 2014-06-19 | 2014-07-01 | 2014-07-02 | 2014-07-06 | 2014-09-09 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124081 | Cabicahan Elementary School | CALBAYOG CITY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-12-14 | 2014-12-14 | 080414S00053 | 14IJ-0076 (2) | 2014-06-19 | 2014-07-01 | 2014-07-02 | 2014-09-05 | 2014-09-09 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124134 | Cag-olango Elementary School | CALBAYOG CITY | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3015174.43 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 080414S00048 | 14IJ-0102 | 2014-07-10 | 2014-07-22 | 2014-07-23 | 2014-07-27 | 2014-09-09 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 313806 | Calbayog City National High School - Carayman Campus | CALBAYOG CITY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124087 | Capacuhan Primary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 080414S00052 | 14IJ-0070 | 2014-06-19 | 2014-07-01 | 2014-07-02 | 2014-07-04 | 2014-09-09 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 123992 | Cogon Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-04 | 2015-01-04 | 080414S00063 | 14IJ-0073 | 2014-06-19 | 2014-07-01 | 2014-07-02 | 2014-08-28 | 2014-09-15 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124123 | Danao I Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4442649.6094 |  |  | COMPLETED | 1 | 2015-06-12 | 2015-06-12 | 080414S00247 | 14IJ-0156 | 2014-11-23 | 2014-12-03 | 2014-12-05 | 2014-12-09 | 2014-12-24 | R.V. CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124060 | Dawo Integrated School | CALBAYOG CITY | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3015174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 500237 | Gadgaran Integrated School | CALBAYOG CITY | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-06-28 | 2015-06-28 | 080414S00252 | 14IJ-0158 | 2014-11-23 | 2014-12-04 | 2014-12-05 | 2014-12-09 | 2014-12-24 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 123993 | Guinbaoyan Norte Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 080414S00062 | 14IJ-0072 | 2014-06-19 | 2014-07-01 | 2014-07-02 | 2014-07-06 | 2014-09-09 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124014 | Hamorawon Elementary School | CALBAYOG CITY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-14 | 2014-12-14 | 080414S00064 | 14IJ-0069 (2) | 2014-06-19 | 2014-07-01 | 2014-07-02 | 2014-09-03 | 2014-09-09 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 313813 | Happy Valley National High School | CALBAYOG CITY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2120417.57 |  |  | COMPLETED | 1 | 2015-06-03 | 2015-06-03 | 080414S00047 | 14IJ-0121(2) | 2014-10-28 | 2014-11-09 | 2014-11-10 | 2014-11-14 | 2014-11-18 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124015 | Higasaan Primary School | CALBAYOG CITY | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3115174.43 |  |  | Reverted | 0
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124016 | Himalandrog Elementary School | CALBAYOG CITY | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3015174.43 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 080414S00059 | 14IJ-0101 | 2014-08-21 | 2014-09-02 | 2014-09-03 | 2014-09-10 | 2014-09-18 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124097 | Lapaan Primary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 080414S00051 | 14IJ-0071 | 2014-06-19 | 2014-07-01 | 2014-07-02 | 2014-07-06 | 2014-09-09 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124127 | Marcatubig Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4392399.6094 |  |  | COMPLETED | 1 | 2015-06-11 | 2015-06-11 | 080414S00246 | 14IJ-0156 | 2014-12-02 | 2014-12-14 | 2014-12-15 | 2014-12-19 | 2014-12-23 | R.V. CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124106 | Panoypoy Elementary School | CALBAYOG CITY | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3015174.43 |  |  | COMPLETED | 1 | 2015-01-13 | 2015-01-13 | 080414S00050 | 14IJ-0066 | 2014-06-17 | 2014-06-29 | 2014-06-30 | 2014-09-04 | 2014-09-09 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124025 | San Antonio Primary School | CALBAYOG CITY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1242329.12 |  |  | COMPLETED | 1 | 2015-04-06 | 2015-04-06 | 080414S00058 | 14IJ-0134 | 2014-10-28 | 2014-11-09 | 2014-11-10 | 2014-11-14 | 2014-12-02 | VCD CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 313814 | Seven Hills National High School | CALBAYOG CITY | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3065174.43 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 080414S00016 | 14IJ-0065 | 2014-08-21 | 2014-09-02 | 2014-09-03 | 2014-09-07 | 2014-09-17 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124052 | Villahermosa Elementary School | CALBAYOG CITY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-12-14 | 2014-12-14 | 080414S00045 | 14IJ-0076 (1) | 2014-06-19 | 2014-07-01 | 2014-07-02 | 2014-07-06 | 2014-09-09 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 313808 | Dawo Integrated School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1 | 2015-01-13 | 2015-01-13 | 080414S00066 | 14IJ-0077 | 2014-07-14 | 2014-07-26 | 2014-07-27 | 2014-07-31 | 2014-09-09 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 123994 | Guinbaoyan Sur Elementary School | CALBAYOG CITY | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2697006.2303 |  |  | COMPLETED | 1 | 2015-01-13 | 2015-01-13 | 080414S00225 | 14IJ-0078 | 2014-07-14 | 2014-07-26 | 2014-07-27 | 2014-07-31 | 2014-09-09 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124093 | Hibabngan Primary School | CALBAYOG CITY | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2697006.2303 |  |  | COMPLETED | 1 | 2015-04-24 | 2015-04-24 | 080414S00232 | 14IJ-0118 | 2014-11-28 | 2014-12-10 | 2014-12-11 | 2014-12-15 | 2014-12-19 | VCD CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124109 | San Isidro Elementary School | CALBAYOG CITY | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2697006.2303 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-02-23 | 080414S00224 | 14IJ-0115 | 2014-11-28 | 2014-12-10 | 2014-12-11 | 2014-12-15 | 2014-12-19 | VCD CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124053 | Barral Primary School | CALBAYOG CITY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 080414S00230 | 14IJ-0065 | 2014-08-21 | 2014-09-02 | 2014-09-03 | 2014-09-24 | 2014-10-01 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124033 | Bontay Primary School | CALBAYOG CITY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2014-11-24 | 2014-11-24 | 080414S00231 | 14IJ-0100 | 2014-08-21 | 2014-09-02 | 2014-09-03 | 2014-09-07 | 2014-09-20 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124058 | Cabugawan Primary School | CALBAYOG CITY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 080414S00243 | 14IJ-0080 (2) | 2014-07-14 | 2014-07-26 | 2014-07-27 | 2014-09-04 | 2014-09-09 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124005 | Cacaransan Elementary School | CALBAYOG CITY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 080414S00233 | 14IJ-0065 | 2014-07-14 | 2014-07-26 | 2014-07-27 | 2014-08-29 | 2014-09-09 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 123988 | Cagboborac Primary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1 | 2015-01-14 | 2015-01-14 | 080414S00223 | 14IJ-0082 | 2014-07-14 | 2014-07-26 | 2014-07-27 | 2014-08-29 | 2014-09-15 | R.V. CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124084 | Calilihan Primary School | CALBAYOG CITY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-06-04 | 2015-06-04 | 080414S00235 | 14IJ-0120 | 2014-11-28 | 2014-12-10 | 2014-12-11 | 2014-12-15 | 2014-12-19 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124090 | Dinabongan Primary School | CALBAYOG CITY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 080414S00236 | 14IJ-0065 | 2014-07-16 | 2014-07-28 | 2014-07-29 | 2014-09-04 | 2014-09-09 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124095 | Hibuhatan Primary School | CALBAYOG CITY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | Reverted | 0
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124096 | Jacinto Primary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 080414S00227 | 14IJ-0112 | 2014-09-18 | 2014-09-30 | 2014-10-01 | 2014-10-05 | 2015-02-20 | VCD CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124062 | Kili-Kili Elementary School | CALBAYOG CITY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 080414S00234 | 14IJ-0084 (1) | 2014-07-16 | 2014-07-28 | 2014-07-29 | 2014-08-02 | 2014-09-09 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124017 | Looc Elementary School | CALBAYOG CITY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-01-24 | 2015-01-23 | 080414S00238 | 14IJ-0081 (1) | 2014-07-14 | 2014-07-26 | 2014-07-27 | 2014-08-29 | 2014-09-15 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124067 | Mantaong Primary School | CALBAYOG CITY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 080414S00244 | 14IJ-0098 (1) | 2014-08-21 | 2014-09-02 | 2014-09-03 | 2014-09-24 | 2014-10-01 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124069 | Nabang Primary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1 | 2015-02-17 | 2015-02-17 | 080414S00228 | 14IJ-0111 | 2014-09-18 | 2014-09-30 | 2014-09-30 | 2014-10-05 | 2014-10-29 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124043 | Palanas Primary School | CALBAYOG CITY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-01-24 | 2015-01-23 | 080414S00239 | 14IJ-0081 (2) | 2014-07-14 | 2014-07-26 | 2014-07-27 | 2014-07-31 | 2014-09-15 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124107 | Patong Elementary School | CALBAYOG CITY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-03-13 | 2015-03-13 | 080414S00240 | 14IJ-0121 | 2014-10-05 | 2014-10-17 | 2014-10-18 | 2014-10-22 | 2014-11-07 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124140 | Pe¤a II Elementary School | CALBAYOG CITY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | Reverted | 0
NC 2014 | K10 (2014) | Region VIII | Calbayog City | 124024 | Salvacion Primary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1 | 2015-06-04 | 2015-06-04 | 080414S00229 | 14IJ-0120(2) | 2014-11-28 | 2014-12-10 | 2014-12-11 | 2014-12-15 | 2014-12-19 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Catbalogan City | 303622 | Antonio G. Tuazon NHS | CITY OF CATBALOGAN (Capital) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Catbalogan City | 193540 | Catbalogan I SPED Center | CITY OF CATBALOGAN (Capital) | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6328664.7656 |  |  | COMPLETED | 1 | 2015-07-15 | 2015-07-15 | 080414S00248 | 15IK 0007 | 2015-03-04 | 2015-03-12 | 2015-03-25 | 2015-04-07 | 2015-04-10 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Catbalogan City | 313701 | Catbalogan NCHS | CITY OF CATBALOGAN (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Catbalogan City | 123410 | Darahuway Daku PS | CITY OF CATBALOGAN (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-08-28 | 2015-08-28 | 080414S00046 | 14IK 0038 - Cluster XXVII | 2014-10-30 | 2014-11-13 | 2014-11-13 | 2014-11-24 | 2014-12-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Catbalogan City | 123412 | Guinsorongan ES | CITY OF CATBALOGAN (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-09-30 | 2015-09-30 | 080414S00054 | 14IK 0038 - Cluster XXVII | 2014-10-30 | 2013-11-13 | 2014-11-13 | 2014-11-24 | 2014-12-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Catbalogan City | 123413 | Ibol es | CITY OF CATBALOGAN (Capital) | 2 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1 | 2015-11-28 | 2015-11-12 | 080414S00077 | 14IK 0038 - Cluster XXVII | 2014-10-30 | 2014-11-13 | 2014-11-13 | 2014-11-24 | 2014-12-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Catbalogan City | 123432 | Iguid ES | CITY OF CATBALOGAN (Capital) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00086 | 14IK 0038 - Cluster XXVII | 2014-10-30 | 2014-11-13 | 2014-11-13 | 2014-11-24 | 2014-12-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Catbalogan City | 123414 | Madalunot ES | CITY OF CATBALOGAN (Capital) | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-08-10 | 2015-08-10 | 080414S00079 | 14IK 0038 - Cluster XXVII | 2014-10-30 | 2014-11-13 | 2014-11-13 | 2014-11-24 | 2014-12-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Catbalogan City | 123426 | Mombon ES | CITY OF CATBALOGAN (Capital) | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-10-28 | 2015-10-28 | 080414S00056 | 14IK 0039 -Cluster XXVIII | 2014-10-30 | 2014-11-13 | 2014-11-13 | 2014-11-24 | 2014-12-01 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Catbalogan City | 313706 | Pangdan NHS | CITY OF CATBALOGAN (Capital) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Catbalogan City | 123427 | Rama ES | CITY OF CATBALOGAN (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-10-28 | 2015-10-28 | 080414S00087 | 14IK 0039 -Cluster XXVIII | 2014-10-30 | 2014-11-06 | 2014-12-13 | 2014-11-24 | 2014-12-01 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Catbalogan City | 303623 | Silanga NHS | CITY OF CATBALOGAN (Capital) | 2 | 1 | 6 | 2STY2CL & 2STY4CL | 2014 K10 BATCH 3 | 10620564.375 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122733 | Alugan ES | SAN POLICARPO | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2006657.57 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-14 | 080514S00005 | 14IB0041 | 2014-06-26 | 2014-06-27 | 2014-07-09 | 2014-07-14 | 2014-07-30 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122672 | Anislag ES | Quinapondan | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1062000 |  |  | COMPLETED | 1 | 2015-05-26 | 2015-05-26 | 080514S00015 | 14IB0096 | 2014-09-24 | 2014-09-25 | 2014-10-07 | 2014-10-10 | 2014-10-24 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 313520 | Arteche NHS (Carapdapan Annex) | ARTECHE | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1064388.9002 |  |  | COMPLETED | 1 | 2015-05-10 | 2015-05-10 | 080514S00112 | 14IB0066 | 2014-08-28 | 2014-08-29 | 2014-09-18 | 2014-09-23 | 2014-10-08 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 313522 | Arteche NHS (Concepcion Annex) | ARTECHE | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1996890.377 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122533 | Bagua ES | Guiuan North | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1052000 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-05-24 | 080514S00101 | 14IB0048 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122655 | Balingasag ES | ORAS | 0 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 4A | 1976869.6122 |  |  | COMPLETED | 1 | 2015-12-21 | 2015-12-21 | 080514S00126 | 14IB0137 | 2014-12-04 | 2014-12-05 | 2014-12-22 | 2015-01-06 | 2015-01-20 | JUCONS CONSTRUCTION &SUPPLY
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122535 | Banuyo ES | Mercedes | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1062000 |  |  | COMPLETED | 1 | 2015-03-15 | 2015-03-15 | 080514S00014 | 14IB0052 | 2014-08-14 | 2014-08-15 | 2014-08-28 | 2014-09-03 | 2014-09-12 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122555 | Baras ES | Guiuan South | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1052000 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-05-24 | 080514S00102 | 14IB0048 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122656 | Batang ES | ORAS | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1211129.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-14 | 080514S00003 | 14IB0038 | 2014-07-30 | 2014-07-31 | 2014-08-12 | 2014-08-15 | 2014-08-27 | BORONGAN MBC MERCHANDISING AND CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122506 | Biga ES | Giporlos | 0 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2094000 |  |  | COMPLETED | 1 | 2015-03-25 | 2015-03-25 | 080514S00028 | 14IB0050 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122476 | Binalay ES | GENERAL MACARTHUR | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 988434.8061 |  |  | COMPLETED | 1 | 2015-09-12 | 2015-09-12 | 080514S00128 | 14IB0138 | 2014-12-04 | 2014-12-05 | 2014-12-22 | 2015-01-06 | 2015-01-20 | JUCONS CONSTRUCTION &SUPPLY
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122658 | Binalayan ES | ORAS | 0 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 4A | 1976869.6122 |  |  | COMPLETED | 1 | 2015-12-21 | 2015-12-21 | 080514S00133 | 14IB0137 | 2014-12-04 | 2014-12-05 | 2014-12-22 | 2015-01-06 | 2015-01-20 | JUCONS CONSTRUCTION &SUPPLY
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122674 | Buenavista ES | QUINAPONDAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 988434.8061 |  |  | COMPLETED | 1 | 2015-09-12 | 2015-09-12 | 080514S00124 | 14IB0138 | 2014-12-04 | 2014-12-05 | 2014-12-22 | 2015-01-06 | 2015-01-20 | JUCONS CONSTRUCTION &SUPPLY
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122711 | Butig ES | Salcedo II | 0 | 1 | 3 | 3U-1STY1CL | 2014 K10 BATCH 2 | 3146000 |  |  | COMPLETED | 1 | 2015-03-11 | 2015-03-11 | 080514S00108 | 14IB0068 | 2014-08-28 | 2014-08-29 | 2014-09-18 | 2014-09-23 | 2014-10-08 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122663 | Cagtoog ES | ORAS | 0 | 1 | 3 | 1STY2CL & 1STY1CL | 2014 K10 BATCH 4A | 2754396.6057 |  |  | COMPLETED | 1 | 2015-12-21 | 2015-12-21 | 080514S00134 | 14IB0137 | 2014-12-04 | 2014-12-05 | 2014-12-22 | 2015-01-06 | 2015-01-20 | JUCONS CONSTRUCTION &SUPPLY
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122713 | Camanga ES | Salcedo II | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1052000 |  |  | COMPLETED | 1 | 2015-03-15 | 2015-03-15 | 080514S00107 | 14IB0052 | 2014-08-14 | 2014-08-15 | 2014-08-28 | 2014-09-03 | 2014-09-12 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122412 | Camantang ES | CAN-AVID | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1118638.9002 |  |  | COMPLETED | 1 | 2015-03-15 | 2015-03-15 | 080514S00067 | 14IB0053 | 2014-08-14 | 2014-08-15 | 2014-08-28 | 2014-09-03 | 2014-09-12 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122613 | Canloterio ES | MAYDOLONG | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 988434.8061 |  |  | COMPLETED | 1 | 2015-07-24 | 2015-05-31 | 080514S00123 | 14IB0136 | 2014-12-04 | 2014-12-05 | 2014-12-22 | 2015-01-06 | 2015-01-20 | JUCONS CONSTRUCTION &SUPPLY
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122507 | Cansingkol PS | Giporlos | 0 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2094000 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 080514S00038 | 14IB0107 | 2014-10-01 | 2014-10-03 | 2014-10-20 | 2014-10-24 | 2014-11-07 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122560 | Cantahay ES | Guiuan South | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1072000 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-05-24 | 080514S00010 | 14IB0048 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122678 | Cantinio PS | Quinapondan | 0 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2094000 |  |  | COMPLETED | 1 | 2015-05-26 | 2015-05-26 | 080514S00027 | 14IB0096 | 2014-09-24 | 2014-09-25 | 2014-10-07 | 2014-10-10 | 2014-10-24 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122481 | Carmen ES | Hernani | 0 | 1 | 3 | 3U-1STY1CL | 2014 K10 BATCH 2 | 3146000 |  |  | COMPLETED | 1 | 2015-04-14 | 2015-04-14 | 080514S00012 | 14IB0051 | 2014-08-14 | 2014-08-15 | 2014-08-28 | 2014-09-03 | 2014-09-12 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122508 | Coticot ES | Giporlos | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1072000 |  |  | COMPLETED | 1 | 2015-04-14 | 2015-04-14 | 080514S00049 | 14IB0052 | 2014-08-14 | 2014-08-15 | 2014-08-28 | 2014-09-03 | 2014-09-12 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122522 | Dalaragan PS | Guiuan East | 0 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2094000 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-05-24 | 080514S00097 | 14IB0047 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 500235 | Dao Integrated School | ORAS | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1855890.377 |  |  | COMPLETED | 1 | 2015-10-30 | 2015-11-29 | 080514S00070 | 14IB0066 | 2014-08-28 | 2014-08-29 | 2014-09-18 | 2014-09-23 | 2014-10-08 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122483 | Garawon ES | HERNANI | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 988434.8061 |  |  | COMPLETED | 1 | 2015-09-12 | 2015-09-12 | 080514S00127 | 14IB0138 | 2014-12-04 | 2014-12-05 | 2014-12-22 | 2015-01-06 | 2015-01-20 | JUCONS CONSTRUCTION &SUPPLY
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122525 | Hamorawon ES | Guiuan East | 0 | 1 | 3 | 3U-1STY1CL | 2014 K10 BATCH 2 | 3146000 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-06-14 | 080514S00098 | 14IB0069 | 2014-10-16 | 2014-10-17 | 2014-10-30 | 2014-11-05 | 2014-11-14 | BORONGAN MBC MERCHANDISING AND CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122434 | Hilabaan ES | DOLORES | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1066322.3061 |  |  | COMPLETED | 1 | 2015-07-30 | 2015-07-30 | 080514S00113 | 14IB0123 | 2014-11-12 | 2014-11-13 | 2014-11-25 | 2014-12-01 | 2014-12-16 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 303506 | Hilabaan NHS | DOLORES | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2900636.04 |  |  | COMPLETED | 1 | 2015-04-06 | 2015-04-06 | 080514S00068 | 14IB0090 | 2014-09-24 | 2014-09-25 | 2014-10-07 | 2014-10-10 | 2014-10-24 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 303509 | Homonhon NHS - Sulangan Annex | Guiuan | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1052000 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-05-24 | 080514S00096 | 14IB0048 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122511 | Huknan ES | Giporlos | 0 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2094000 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 080514S00036 | 14IB0107 | 2014-10-01 | 2014-10-03 | 2014-10-20 | 2014-10-24 | 2014-11-07 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122564 | Inapulangan ES | Guiuan South | 0 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2094000 |  |  | COMPLETED | 1 | 2015-05-10 | 2015-05-10 | 080514S00011 | 14IB0070 | 2014-08-28 | 2014-08-29 | 2014-09-18 | 2014-09-23 | 2014-10-08 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 192502 | Inu-olanguhan PS | Gen. MacArthur | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1129500 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 080514S00040 | 14IB0093 | 2014-10-16 | 2014-10-17 | 2014-10-30 | 2014-11-05 | 2014-11-14 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122665 | Iwayan ES | ORAS | 0 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 4A | 1976869.6122 |  |  | COMPLETED | 1 | 2015-12-21 | 2015-12-21 | 080514S00130 | 14IB0137 | 2014-12-04 | 2014-12-05 | 2014-12-22 | 2015-01-06 | 2015-01-20 | JUCONS CONSTRUCTION &SUPPLY
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122640 | Kalaw ES | ORAS | 0 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3471078.0751 |  |  | COMPLETED | 1 | 2015-08-14 | 2015-08-14 | 080514S00115 | 14IB0123 | 2014-11-12 | 2014-11-13 | 2014-11-25 | 2014-12-01 | 2014-12-16 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122486 | Laurel PS | Gen. MacArthur | 0 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2249000 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-06-14 | 080514S00018 | 14IB0082 | 2014-10-16 | 2014-10-17 | 2014-10-30 | 2014-11-05 | 2014-11-14 | BORONGAN MBC MERCHANDISING AND CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122456 | Libertad ES | DOLORES | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 988434.8061 |  |  | COMPLETED | 1 | 2015-09-25 | 2015-06-04 | 080514S00122 | 14IB0139 | 2015-02-19 | 2015-02-10 | 2015-03-05 | 2015-03-11 | 2015-03-24 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122487 | Limbujan PS | Gen. MacArthur | 0 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2249000 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-06-14 | 080514S00047 | 14IB0082 | 2014-10-16 | 2014-10-17 | 2014-10-30 | 2014-11-05 | 2014-11-14 | BORONGAN MBC MERCHANDISING AND CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 303513 | Llorente National High School | LLORENTE | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1855890.377 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 192514 | Lunang ES | DOLORES | 0 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2016-01-24 |  | 080514S00117 | 14IB0130 | 2015-03-11 | 2015-03-12 | 2015-03-24 | 2015-03-31 | 2015-04-17 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122696 | Lusod ES | Salcedo I | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1052000 |  |  | COMPLETED | 1 | 2015-03-15 | 2015-03-15 | 080514S00007 | 14IB0052 | 2014-08-14 | 2014-08-15 | 2014-08-28 | 2014-09-03 | 2014-09-12 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122488 | Macapagal PS | Gen. MacArthur | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1129500 |  |  | COMPLETED | 1 | 2015-08-13 | 2015-08-13 | 080514S00046 | 14IB0083 | 2014-10-16 | 2014-10-17 | 2014-10-30 | 2014-11-05 | 2014-11-14 | BORONGAN MBC MERCHANDISING AND CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122489 | Magsaysay PS | Gen. MacArthur | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1129500 |  |  | COMPLETED | 1 | 2015-08-13 | 2015-08-13 | 080514S00045 | 14IB0083 | 2014-10-16 | 2014-10-17 | 2014-10-30 | 2014-11-05 | 2014-11-14 | BORONGAN MBC MERCHANDISING AND CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 303514 | Malabag NHS | GIPORLOS | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112129.12 |  |  | COMPLETED | 1 | 2014-11-01 | 2014-11-01 | 080514S00006 | 14IB0040 | 2014-06-26 | 2014-06-27 | 2014-07-15 | 2014-07-18 | 2014-08-01 | BORONGAN MBC MERCHANDISING AND CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122351 | Maybunga ES | Balangiga | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042000 |  |  | COMPLETED | 1 | 2015-04-10 | 2015-04-10 | 080514S00037 | 14IB0108 | 2014-10-01 | 2014-10-03 | 2014-10-20 | 2014-10-24 | 2014-11-07 | BORONGAN MBC MERCHANDISING AND CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122625 | Maydolong CS | MAYDOLONG | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 988434.8061 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-04-14 | 080514S00118 | 14IB0123 | 2014-11-12 | 2014-11-13 | 2014-11-25 | 2014-12-01 | 2014-12-16 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 313514 | Maydolong NHS | MAYDOLONG | 0 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8228453.2031 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 313523 | Maydolong NHS (Lapgap Annex) | MAYDOLONG | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122627 | Omawas ES | MAYDOLONG | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 988434.8061 |  |  | COMPLETED | 1 | 2015-07-15 | 2015-07-15 | 080514S00119 | 14IB0123 | 2014-11-12 | 2014-11-13 | 2014-11-25 | 2014-12-01 | 2014-12-16 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 303520 | Oras National High School | ORAS | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122668 | Oras West CS | ORAS | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112129.12 |  |  | COMPLETED | 1 | 2014-11-01 | 2014-11-01 | 080514S00004 | 14IB0037 | 2014-06-26 | 2014-06-27 | 2014-07-15 | 2014-07-18 | 2014-08-01 | BORONGAN MBC MERCHANDISING AND CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122491 | Osmeña PS | Gen. MacArthur | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1129500 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 080514S00044 | 14IB0093 | 2014-10-16 | 2014-10-17 | 2014-10-30 | 2014-11-05 | 2014-11-14 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122645 | Pangudtan ES | ORAS | 0 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 4A | 1976869.6122 |  |  | COMPLETED | 1 | 2015-12-21 | 2015-12-21 | 080514S00121 | 14IB0137 | 2014-12-04 | 2014-12-05 | 2014-12-22 | 2015-01-06 | 2015-01-20 | JUCONS CONSTRUCTION &SUPPLY
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122493 | Pingan ES | GENERAL MACARTHUR | 0 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 4A | 1976869.6122 |  |  | COMPLETED | 1 | 2015-08-13 | 2015-08-10 | 080514S00132 | 14IB0138 | 2014-12-04 | 2014-12-05 | 2014-12-22 | 2015-01-06 | 2015-01-20 | JUCONS CONSTRUCTION &SUPPLY
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122515 | Pres. Roxas ES | Giporlos | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1052000 |  |  | COMPLETED | 1 | 2015-05-26 | 2015-05-26 | 080514S00106 | 14IB0096 | 2014-09-24 | 2014-09-25 | 2014-10-07 | 2014-10-10 | 2014-10-24 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122526 | Salug ES | Guiuan East | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1052000 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-05-24 | 080514S00099 | 14IB0047 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122547 | San Antonio PS | Guiuan North | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1052000 |  |  | COMPLETED | 1 | 2015-07-14 | 2015-07-14 | 080514S00104 | 14IB0069 | 2014-10-16 | 2014-10-17 | 2014-10-30 | 2014-11-05 | 2014-11-14 | BORONGAN MBC MERCHANDISING AND CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122352 | San Isidro PS | Lawaan | 0 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2094000 |  |  | COMPLETED | 1 | 2015-04-10 | 2015-04-10 | 080514S00013 | 14IB0108 | 2014-10-01 | 2014-10-03 | 2014-10-20 | 2014-10-24 | 2014-11-07 | BORONGAN MBC MERCHANDISING AND CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 192519 | San Juan PS | Guiuan North | 0 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2094000 |  |  | COMPLETED | 1 | 2015-05-10 | 2015-05-10 | 080514S00095 | 14IB0070 | 2014-08-28 | 2014-08-29 | 2014-09-18 | 2014-09-23 | 2014-10-08 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122353 | San Miguel ES | Balangiga | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1062000 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-02-23 | 080514S00039 | 14IB0050 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122773 | San Pablo ES | TAFT | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 988434.8061 |  |  | COMPLETED | 1 | 2015-09-25 | 2015-09-25 | 080514S00125 | 14IB0139 | 2015-02-19 | 2015-02-20 | 2015-03-05 | 2015-03-11 | 2015-03-24 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122438 | San Pascual ES | DOLORES | 0 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 4A | 1976869.6122 |  |  | COMPLETED | 1 | 2015-09-25 | 2015-09-25 | 080514S00131 | 14IB0139 | 2015-02-19 | 2015-02-20 | 2015-03-05 | 2015-03-11 | 2015-03-24 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122500 | San Roque PS | Gen. MacArthur | 0 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2249000 |  |  | COMPLETED | 1 | 2015-08-13 | 2015-08-13 | 080514S00043 | 14IB0083 | 2014-09-16 | 2014-09-17 | 2014-10-30 | 2014-11-05 | 2014-11-14 | BORONGAN MBC MERCHANDISING AND CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122426 | Solong Elementary School | CAN-AVID | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1011801.0561 |  |  | COMPLETED | 1 | 2015-07-15 | 2015-07-15 | 080514S00114 | 14IB0123 | 2014-11-12 | 2014-11-13 | 2014-11-25 | 2014-12-01 | 2014-12-16 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122688 | Sta. Margarita ES | Quinapondan | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1062000 |  |  | COMPLETED | 1 | 2015-04-12 | 2015-04-12 | 080514S00017 | 14IB0046 | 2014-08-07 | 2014-08-15 | 2014-08-26 | 2014-08-29 | 2014-09-12 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122529 | Surok ES | Guiuan East | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1052000 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-05-24 | 080514S00100 | 14IB0047 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122745 | Tanauan ES | SAN POLICARPO | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1836814.2996 |  |  | COMPLETED | 1 | 2015-08-14 | 2015-08-14 | 080514S00116 | 14IB0123 | 2014-11-12 | 2014-11-13 | 2014-11-25 | 2014-12-01 | 2014-12-16 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122503 | Tandang Sora PS | Gen. MacArthur | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1129500 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 080514S00041 | 14IB0093 | 2014-10-16 | 2014-10-17 | 2014-10-30 | 2014-11-05 | 2014-11-14 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122651 | Tawagan ES | ORAS | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112129.12 |  |  | COMPLETED | 1 | 2014-11-01 | 2014-11-01 | 080514S00001 | 14IB0039 | 2014-06-26 | 2014-06-27 | 2014-07-15 | 2014-07-18 | 2014-08-01 | BORONGAN MBC MERCHANDISING AND CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 303493 | Alugan Nat'L Sch. Of Crafts/HI | SAN POLICARPO | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-04-14 | 2015-04-14 | 080514S00058 | 14IB0055 | 2014-08-14 | 2014-08-15 | 2014-08-28 | 2014-09-03 | 2014-09-12 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122445 | Aroganga ES | DOLORES | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-04-14 | 2015-04-14 | 080514S00023 | 14IB0054 | 2014-08-14 | 2014-08-15 | 2014-08-28 | 2014-09-03 | 2014-09-12 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122608 | Bangon ES | BALANGKAYAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-05-24 | 080514S00111 | 14IB0045 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122393 | Banuyo ES | BORONGAN (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-04-10 | 2015-03-13 | 080514S00016 | 14IB0067 | 2014-08-28 | 2014-08-29 | 2014-09-18 | 2014-09-23 | 2014-10-08 | 3As BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122394 | Baras ES | BORONGAN (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-04-10 | 2015-03-13 | 080514S00073 | 14IB0067 | 2014-08-28 | 2014-08-29 | 2014-09-18 | 2014-09-23 | 2014-10-08 | 3As BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122371 | Bayobay PS | BORONGAN (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-03-13 | 2015-01-23 | 080514S00029 | 14IB0049 | 2014-08-13 | 2014-08-15 | 2014-08-26 | 2014-08-29 | 2014-09-12 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122760 | Beto PS | TAFT | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-06-14 | 080514S00062 | 14IB0084 | 2014-10-16 | 2014-10-17 | 2014-10-30 | 2014-11-05 | 2014-11-14 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122410 | Boco ES | CAN-AVID | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-04-24 | 2015-04-24 | 080514S00034 | 14IB0077 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122762 | Bongdo PS | TAFT | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-06-14 | 080514S00063 | 14IB0084 | 2014-10-16 | 2014-10-17 | 2014-10-30 | 2014-11-05 | 2014-11-14 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122446 | Bulawan PS | MASLOG | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-03-25 | 2015-03-25 | 080514S00083 | 14IB0080 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122397 | Cabong ES | BORONGAN (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-03-13 | 2015-01-23 | 080514S00103 | 14IB0049 | 2014-08-13 | 2014-08-15 | 2014-08-26 | 2014-08-29 | 2014-09-12 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122661 | Cagdine PS | ORAS | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-03-27 | 2015-03-27 | 080514S00082 | 14IB0091 | 2014-09-24 | 2014-09-25 | 2014-10-07 | 2014-10-10 | 2014-10-24 | BORONGAN MBC MERCHANDISING AND CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 313501 | Can-Avid NHS | CAN-AVID | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122614 | Cantubi ES | BALANGKAYAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-05-24 | 080514S00109 | 14IB0045 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122400 | Canyupay ES | BORONGAN (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-08-13 | 2015-08-13 | 080514S00030 | 14IB0086 | 2014-10-16 | 2014-10-17 | 2014-10-30 | 2014-11-05 | 2014-11-14 | BORONGAN MBC MERCHANDISING AND CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 192513 | Capanoypoyan PS | SALCEDO | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-13 | 080514S00053 | 14IB0056 | 2014-08-14 | 2014-08-15 | 2014-08-28 | 2014-09-03 | 2014-09-12 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122637 | Dao ES | ORAS | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-04-14 | 2015-04-14 | 080514S00092 | 14IB0055 | 2014-08-14 | 2014-08-15 | 2014-08-28 | 2014-09-03 | 2014-09-12 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122615 | Del Pilar ES | MAYDOLONG | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1855890.377 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122765 | Del Remedios PS | TAFT | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1855890.377 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-05-24 | 080514S00060 | 14IB0079 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122574 | Dorillo PS | JIPAPAD | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-07-21 | 2015-08-13 | 080514S00080 | 14IB0095 | 2014-10-16 | 2014-10-17 | 2014-10-30 | 2014-11-05 | 2014-11-19 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122766 | Gayam PS | TAFT | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1855890.377 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-06-14 | 080514S00050 | 14IB0084 | 2014-10-16 | 2014-10-17 | 2014-10-30 | 2014-11-05 | 2014-11-14 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122402 | Hebacong ES | BORONGAN (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-04-10 | 2015-04-10 | 080514S00031 | 14IB0067 | 2014-08-28 | 2014-08-29 | 2014-09-18 | 2014-09-23 | 2014-10-08 | 3As BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 313518 | Hinolaso NHS (Caglao-an Annex) | DOLORES | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-02-23 | 2014-11-24 | 080514S00048 | 14IB0078 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 192520 | Ipil PS | DOLORES | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-04-26 | 2015-04-26 | 080514S00074 | 14IB0089 | 2014-09-24 | 2014-09-25 | 2014-10-07 | 2014-10-10 | 2014-10-24 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122419 | Jepaco ES | CAN-AVID | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-04-24 | 2015-04-24 | 080514S00035 | 14IB0077 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122576 | Jiwaran PS | JIPAPAD | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-07-21 | 2015-08-13 | 080514S00081 | 14IB0095 | 2014-10-16 | 2014-10-17 | 2014-10-30 | 2014-11-05 | 2014-11-19 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122619 | Julag PS | BALANGKAYAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-05-07 | 2015-05-07 | 080514S00110 | 14IB0045 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122748 | Kandalakit PS | SULAT | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1855890.377 |  |  | COMPLETED | 1 | 2015-04-24 | 2015-04-24 | 080514S00071 | 14IB0079 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122725 | Layog PS | SAN JULIAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-05-24 | 080514S00054 | 14IB0079 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122457 | Luhang ES | DOLORES | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1855890.377 |  |  | COMPLETED | 1 | 2015-03-15 | 2015-03-15 | 080514S00019 | 14IB0054 | 2014-08-14 | 2014-08-15 | 2014-08-28 | 2014-09-03 | 2014-09-12 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 192507 | Lunang PS | SAN JULIAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-03-15 | 2015-03-15 | 080514S00055 | 14IB0053 | 2014-08-14 | 2014-08-15 | 2014-08-28 | 2014-09-03 | 2014-09-12 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122680 | Mabini PS | QUINAPONDAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-04-14 | 2015-04-14 | 080514S00052 | 14IB0051 | 2014-08-14 | 2014-08-15 | 2014-08-28 | 2014-09-03 | 2014-09-12 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122577 | Mabuhay ES | JIPAPAD | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1855890.377 |  |  | COMPLETED | 1 | 2015-07-25 | 2015-08-24 | 080514S00077 | 14IB0094 | 2014-09-24 | 2014-09-25 | 2014-10-07 | 2014-10-10 | 2014-10-24 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122641 | Mabuhay ES | ORAS | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-04-14 | 2015-04-14 | 080514S00091 | 14IB0055 | 2014-08-14 | 2014-08-15 | 2014-08-28 | 2014-09-03 | 2014-09-12 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122459 | Magsaysay ES | DOLORES | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1855890.377 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-05-24 | 080514S00020 | 14IB0077 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122578 | Magsaysay ES | JIPAPAD | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1855890.377 |  |  | COMPLETED | 1 | 2015-07-25 | 2015-08-24 | 080514S00078 | 14IB0094 | 2014-09-24 | 2014-09-25 | 2014-10-07 | 2014-10-10 | 2014-10-24 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122621 | Magsaysay PS | BALANGKAYAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122596 | Magtino PS | LLORENTE | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1855890.377 |  |  | COMPLETED | 1 | 2015-02-09 | 2015-02-09 | 080514S00094 | 14IB0071 | 2014-08-28 | 2014-08-29 | 2014-09-18 | 2014-09-23 | 2014-10-08 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122642 | Malingon ES | ORAS | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1855890.377 |  |  | COMPLETED | 1 | 2015-04-14 | 2015-04-14 | 080514S00089 | 14IB0055 | 2014-08-14 | 2014-08-15 | 2014-08-28 | 2014-09-03 | 2014-09-12 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122579 | Maylimon PS | JIPAPAD | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1855890.377 |  |  | COMPLETED | 1 | 2015-07-21 | 2015-08-13 | 080514S00079 | 14IB0095 | 2014-10-16 | 2014-10-17 | 2014-10-30 | 2014-11-05 | 2014-11-19 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122626 | Maytigbao PS | MAYDOLONG | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-03-13 | 2015-02-11 | 080514S00087 | 14IB0049 | 2014-08-13 | 2014-08-15 | 2014-08-26 | 2014-08-29 | 2014-09-12 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122643 | Nadacpan ES | ORAS | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-03-27 | 2015-03-27 | 080514S00061 | 14IB0091 | 2014-09-24 | 2014-09-25 | 2014-10-07 | 2014-10-10 | 2014-10-24 | BORONGAN MBC MERCHANDISING AND CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122667 | Naga PS | ORAS | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1855890.377 |  |  | COMPLETED | 1 | 2015-06-25 | 2015-06-25 | 080514S00090 | 14IB0092 | 2014-09-24 | 2014-09-25 | 2014-10-07 | 2014-10-10 | 2014-10-24 | BORONGAN MBC MERCHANDISING AND CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 192509 | Pangabutan PS | TAFT | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-06-14 | 080514S00064 | 14IB0084 | 2014-10-16 | 2014-10-17 | 2014-10-30 | 2014-11-05 | 2014-11-14 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122465 | Pasak ES | DOLORES | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-05-06 | 2015-05-06 | 080514S00024 | 14IB0090 | 2014-09-24 | 2014-09-25 | 2014-10-07 | 2014-10-10 | 2014-10-24 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122405 | Pinanag-an ES | BORONGAN (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-04-10 | 2015-04-10 | 080514S00032 | 14IB0067 | 2014-08-28 | 2014-08-29 | 2014-09-18 | 2014-09-23 | 2014-10-08 | 3As BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122494 | Quezon PS | GENERAL MACARTHUR | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1855890.377 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-03-16 | 080514S00075 | 14IB0085 | 2014-10-16 | 2014-10-17 | 2014-10-30 | 2014-11-05 | 2014-11-14 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 192505 | Quiatan ES (Coyatan PS) | DOLORES | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1855890.377 |  |  | COMPLETED | 1 | 2015-05-26 | 2015-05-26 | 080514S00021 | 14IB0089 | 2014-09-24 | 2014-09-25 | 2014-10-07 | 2014-10-10 | 2014-10-24 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122629 | San Gabriel ES | MAYDOLONG | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-05-07 | 2015-05-07 | 080514S00088 | 14IB0045 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122437 | San Isidro ES | DOLORES | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-04-26 | 2015-04-26 | 080514S00025 | 14IB0089 | 2014-09-24 | 2014-09-25 | 2014-10-07 | 2014-10-10 | 2014-10-24 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122774 | San Rafael PS | TAFT | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-03-15 | 2015-03-15 | 080514S00065 | 14IB0053 | 2014-08-14 | 2014-08-15 | 2014-08-28 | 2014-09-03 | 2014-09-12 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122468 | Sta. Catalina PS | DOLORES | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-05-26 | 2015-05-26 | 080514S00026 | 14IB0089 | 2014-09-24 | 2014-09-25 | 2014-10-07 | 2014-10-10 | 2014-10-24 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122441 | Sta. Cruz ES | DOLORES | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-03-25 | 2015-03-25 | 080514S00059 | 14IB0078 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122743 | Sta. Cruz ES | SAN POLICARPO | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-05-10 | 2015-05-10 | 080514S00056 | 14IB0066 | 2014-08-28 | 2014-08-29 | 2014-09-18 | 2014-09-23 | 2014-10-08 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122502 | Sta. Fe PS | GENERAL MACARTHUR | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-04-12 | 2015-04-12 | 080514S00076 | 14IB0046 | 2014-08-07 | 2014-08-15 | 2014-08-26 | 2014-08-29 | 2014-09-12 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122650 | Sta. Monica ES | ORAS | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-06-25 | 2015-06-25 | 080514S00084 | 14IB0092 | 2014-09-24 | 2014-09-25 | 2014-10-07 | 2014-10-10 | 2014-10-24 | BORONGAN MBC MERCHANDISING AND CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 313519 | Sta. Monica Integrated School |  | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-04-26 | 2015-04-14 | 080514S00066 | 14IB0092 | 2014-09-24 | 2014-09-25 | 2014-10-07 | 2014-10-10 | 2014-10-24 | BORONGAN MBC MERCHANDISING AND CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122366 | Suhotan PS | BORONGAN (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-03-13 | 2015-03-09 | 080514S00033 | 14IB0049 | 2014-08-13 | 2014-08-15 | 2014-08-26 | 2014-08-29 | 2014-09-12 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122744 | Tabo ES | SAN POLICARPO | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-05-10 | 2015-05-10 | 080514S00057 | 14IB0066 | 2014-08-28 | 2014-08-29 | 2014-09-18 | 2014-09-23 | 2014-10-08 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122443 | Tamsion PS | DOLORES | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-03-25 | 2015-03-25 | 080514S00093 | 14IB0078 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122469 | Tan-awan ES | DOLORES | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1855890.377 |  |  | COMPLETED | 1 | 2015-03-15 | 2015-03-15 | 080514S00022 | 14IB0054 | 2014-08-14 | 2014-08-15 | 2014-08-28 | 2014-09-03 | 2014-09-12 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122470 | Tangbo PS | MASLOG | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-03-25 | 2015-03-25 | 080514S00072 | 14IB0080 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 192515 | Taytay PS | MASLOG | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-03-25 | 2015-03-25 | 080514S00085 | 14IB0080 | 2014-09-10 | 2014-09-11 | 2014-09-25 | 2014-10-01 | 2014-10-21 | TUBIGAN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Eastern Samar | 122670 | Trinidad ES | ORAS | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041138.9002 |  |  | COMPLETED | 1 | 2015-03-27 | 2015-03-27 | 080514S00051 | 14IB0091 | 2014-09-24 | 2014-09-25 | 2014-10-07 | 2014-10-10 | 2014-10-24 | BORONGAN MBC MERCHANDISING AND CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | LEYTE | 121006 | Bacong ES | BABATNGON | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1020783.6694 |  |  | COMPLETED | 1 | 2014-11-01 | 2014-10-31 | 080214S00067 | 14IC0025 | 2014-07-30 | 2014-07-31 | 2014-08-13 | 2014-08-26 | 2014-09-03 | MCGR ENGINEERING SERVICES
NC 2014 | K10 (2014) | Region VIII | Leyte | 191513 | Baculanad ES | Sta. Fe | 1 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2052000 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 080214S00107 | 14IC0030 | 2014-08-30 | 2014-07-31 | 2014-09-18 | 2014-09-29 | 2014-10-08 | CHU CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Leyte | 121848 | Bagakay E/S | San Miguel | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1152600 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-11 | 080214S00104 | 14IC0039 | 2014-09-12 | 2014-08-15 | 2014-09-25 | 2014-10-02 | 2014-10-13 | MN MACATO BUILDERS
NC 2014 | K10 (2014) | Region VIII | Leyte | 121737 | CALOOGAN PS | PALO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1031000 |  |  | COMPLETED | 1 | 2014-12-11 | 2015-01-09 | 080214S00062 | 14IC0033 | 2014-09-12 | 2014-08-15 | 2014-09-25 | 2014-10-02 | 2014-10-13 | MN MACATO BUILDERS
NC 2014 | K10 (2014) | Region VIII | LEYTE | 121935 | Camire ES | TANAUAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1020783.6694 |  |  | COMPLETED | 1 | 2014-11-30 | 2014-11-30 | 080214S00037 | 14IC0026 | 2014-07-30 | 2014-07-31 | 2014-08-13 | 2014-08-26 | 2014-09-03 | RNMK CONSTRUCTION AND DEVELOPMENT
NC 2014 | K10 (2014) | Region VIII | Leyte | 121753 | CANDAHUG ES | PALO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1031000 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-11 | 080214S00055 | 14IC0034 | 2014-09-12 | 2014-08-15 | 2014-09-25 | 2014-10-02 | 2014-10-13 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | Region VIII | LEYTE | 121754 | Cangumbang PS | PALO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1020783.6694 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 080214S00040 | 14IC0022 | 2014-08-30 | 2014-07-31 | 2014-09-18 | 2014-09-25 | 2014-10-03 | CHU CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Leyte | 121871 | GAPAS ES | Sta. Fe | 1 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2042000 |  |  | Reverted | 0 | 2014-11-01 | 2014-12-01 | 080214S00130 | 14IC0028 | 2014-07-30 | 2014-07-31 | 2014-08-13 | 2014-08-26 | 2014-09-03 | RPBJ TRADING AND CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Leyte | 121856 | Impo PS | San Miguel | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1031000 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-11 | 080214S00105 | 14IC0032 | 2014-09-12 | 2014-08-15 | 2014-09-25 | 2014-10-02 | 2014-10-13 | RNMK CONSTRUCTION AND DEVELOPMENT
NC 2014 | K10 (2014) | Region VIII | Leyte | 121750 | KABARASAN DAKU ES | PALO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1031000 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-11 | 080214S00064 | 14IC0035 | 2014-09-12 | 2014-08-15 | 2014-09-25 | 2014-10-02 | 2014-10-13 | MN MACATO BUILDERS
NC 2014 | K10 (2014) | Region VIII | Leyte | 120971 | Lourdes E/S | Alangalang | 1 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2128100 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-12-14 | 080214S00076 | 14IC0040 | 2014-08-15 | 2014-08-15 | 2014-08-28 | 2014-09-09 | 2014-09-16 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | Region VIII | LEYTE | 121951 | Malbog PS | TOLOSA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1020783.6694 |  |  | COMPLETED | 1 | 2014-12-06 | 2015-01-05 | 080214S00036 | 14IC0023 | 2014-08-30 | 2014-07-31 | 2014-09-18 | 2014-09-29 | 2014-10-08 | VHITS D. G. BUILDERS & ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | LEYTE | 303401 | Malibago NHS | BABATNGON | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1020783.6694 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Leyte | 121940 | Maribi ES | TANAUAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1021000 |  |  | COMPLETED | 1 | 2014-11-26 | 2014-11-26 | 080214S00094 | 14IC0027 | 2014-07-30 | 2014-07-31 | 2014-08-13 | 2014-08-26 | 2014-09-03 | RNMK CONSTRUCTION AND DEVELOPMENT
NC 2014 | K10 (2014) | Region VIII | Leyte | 120952 | P. Barrantes P/S | Alangalang | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1110250 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-14 | 080214S00057 | 14IC0038 | 2014-08-15 | 2014-08-15 | 2014-08-28 | 2014-09-09 | 2014-09-16 | CHU CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Leyte | 121746 | SAN ISIDRO ES | PALO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041000 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-12-13 | 080214S00063 | 14IC0036 | 2014-08-15 | 2014-08-15 | 2014-08-28 | 2014-09-09 | 2014-09-16 | RNMK CONSTRUCTION AND DEVELOPMENT
NC 2014 | K10 (2014) | Region VIII | Leyte | 121954 | San Roque ES | Tolosa | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1236550 |  |  | Reverted | 0 | 2014-11-14 | 2014-11-14 | 080214S00093 | 14IC0037 | 2014-08-15 | 2014-08-15 | 2014-08-28 | 2014-09-09 | 2014-09-16 | D.L. AUREO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | LEYTE | 120981 | Santiago PS | ALANGALANG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1020783.6694 |  |  | COMPLETED | 1 | 2014-11-01 | 2014-10-31 | 080214S00039 | 14IC0021 | 2014-07-30 | 2014-07-31 | 2014-08-13 | 2014-08-26 | 2014-09-03 | CHU CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Leyte | 121959 | Banawan ES | Tunga | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1051000 |  |  | COMPLETED | 1 | 2014-12-27 | 2014-12-27 | 080214S00082 | 14ID0055 | 2014-08-12 | 2014-08-18 | 2014-09-04 | 2014-09-19 | 2014-09-29 | Z.A.S. CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Leyte | 121308 | Banayon ES | Dagami | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041000 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 080214S00077 | 14ID0052 | 2014-08-12 | 2014-08-18 | 2014-09-04 | 2014-09-19 | 2014-09-30 | WJ BUILDERS
NC 2014 | K10 (2014) | Region VIII | Leyte | 121702 | Calipayan | Mayorga | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1031000 |  |  | COMPLETED | 1 | 2014-12-07 | 2014-12-07 | 080214S00080 | 14ID0050 | 2014-07-10 | 2014-07-16 | 2014-09-04 | 2014-09-08 | 2014-09-09 | Z.A.S. CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Leyte | 121813 | Canino-an ES | Pastrana | 2 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2052000 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 080214S00081 | 14ID0047 | 2014-08-12 | 2014-08-18 | 2014-09-04 | 2014-09-19 | 2014-09-25 | Z.A.S. CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Leyte | 121259 | Canlampay ES | Carigara | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1031000 |  |  | COMPLETED | 1 | 2014-12-23 | 2014-12-23 | 080214S00084 | 14ID0049 | 2014-08-12 | 2014-08-18 | 2014-09-04 | 2014-09-19 | 2014-09-25 | R.V. CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Leyte | 121617 | Casuntingan ES | Macarthur | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1110250 |  |  | COMPLETED | 1 | 2014-12-07 | 2014-12-07 | 080214S00079 | 14ID0045 | 2014-07-10 | 2014-07-16 | 2014-09-04 | 2014-09-08 | 2014-09-09 | Z.A.S. CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Leyte | 121160 | Dinaayan ES | Burauen | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1107100 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-12-24 | 080214S00068 | 14ID0057 | 2014-08-12 | 2014-08-18 | 2014-09-04 | 2014-09-19 | 2014-09-26 | D.L. AUREO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Leyte | 121568 | Doyog ES | Lapaz | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1107100 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 080214S00083 | 14ID0058 | 2014-08-12 | 2014-08-18 | 2014-09-04 | 2014-09-19 | 2014-10-02 | MN MACATO BUILDERS
NC 2014 | K10 (2014) | Region VIII | Leyte | 121261 | Hiluctugan ES | Carigara | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041000 |  |  | COMPLETED | 1 | 2014-12-27 | 2014-12-27 | 080214S00075 | 14ID0053 | 2014-08-12 | 2014-08-18 | 2014-09-04 | 2014-09-19 | 2014-09-29 | R.V. CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Leyte | 191505 | Lemon San Joaquin ES | Capoocan | 2 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2052000 |  |  | COMPLETED | 1 | 2015-01-07 | 2015-01-07 | 080214S00073 | 14ID0044 | 2014-07-10 | 2014-07-16 | 2014-09-04 | 2014-09-08 | 2014-09-10 | Z.A.S. CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Leyte | 121163 | Maabab ES | Burauen | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1107100 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 080214S00069 | 14ID0059 | 2014-08-12 | 2014-08-18 | 2014-09-04 | 2014-09-19 | 2014-09-30 | MWJ CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Leyte | 121167 | Malaihao | Burauen | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1031000 |  |  | COMPLETED | 1 | 2014-12-23 | 2014-12-23 | 080214S00070 | 14ID0046 | 2014-08-12 | 2014-08-18 | 2014-09-04 | 2014-09-19 | 2014-09-25 | MWJ CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | LEYTE | 191540 | Mering PS | TABONTABON | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1020783.6694 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-12-24 | 080214S00035 | 14ID0061 | 2014-08-12 | 2014-08-18 | 2014-09-04 | 2014-09-19 | 2014-09-26 | MN MACATO BUILDERS
NC 2014 | K10 (2014) | Region VIII | Leyte | 121171 | San Fernando ES | Burauen | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1179500 |  |  | COMPLETED | 1 | 2014-12-27 | 2014-12-27 | 080214S00052 | 14ID0060 | 2014-08-12 | 2014-08-18 | 2014-09-04 | 2014-09-19 | 2014-09-29 | WJ BUILDERS
NC 2014 | K10 (2014) | Region VIII | Leyte | 121267 | Sogod E/S | Carigara | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1069050 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-12-24 | 080214S00066 | 14ID0051 | 2014-08-12 | 2014-08-18 | 2014-09-04 | 2014-09-19 | 2014-09-26 | CHU CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Leyte | 303432 | Sta Mesa NHS | Dagami | 2 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2062000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | LEYTE | 121177 | Toloyao ES | BURAUEN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1020783.6694 |  |  | COMPLETED | 1 | 2014-12-27 | 2014-12-27 | 080214S00023 | 14ID0054 | 2014-08-12 | 2014-08-18 | 2014-09-04 | 2014-09-19 | 2014-09-29 | MWJ CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Leyte | 121488 | Tuba ES | Jaro | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1051000 |  |  | COMPLETED | 1 | 2014-12-27 | 2014-12-27 | 080214S00078 | 14ID0056 | 2014-08-12 | 2014-08-18 | 2014-09-04 | 2014-09-19 | 2014-09-29 | MN MACATO BUILDERS
NC 2014 | K10 (2014) | Region VIII | Leyte | 121179 | Villlarosas ES | Burauen | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1031000 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-12-24 | 080214S00071 | 14ID0048 | 2014-08-12 | 2014-08-18 | 2014-09-04 | 2014-09-19 | 2014-09-26 | MWJ CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Leyte | 121253 | Visares ES | Capoocan | 2 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2062000 |  |  | COMPLETED | 1 | 2015-01-07 | 2015-01-07 | 080214S00072 | 14ID0043 | 2014-07-10 | 2014-07-16 | 2014-09-04 | 2014-09-08 | 2014-09-10 | D.L. AUREO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Leyte | 121978 | Buga-buga ES | Villaba | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1108100 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 080214S00085 | 14IE0037 | 2014-09-03 | 2014-09-05 | 2014-09-17 | 2014-09-26 | 2014-10-02 | Z.A.S. CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Leyte | 313322 | Cahigan NHS | VILLABA | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2015-12-07 | 2015-12-07 | 080214S00140 | 15IE0036 | 2015-07-03 | 2015-07-09 | 2015-07-21 | 2015-07-29 | 2015-08-04 | TAM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Leyte | 121966 | Calbugos ES | VILLABA | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1037049.6543 |  |  | COMPLETED | 1 | 2015-11-07 | 2015-11-07 | 080214S00138 | 15IE0037 | 2015-07-03 | 2015-07-09 | 2015-07-21 | 2015-07-29 | 2015-08-04 | TAM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Leyte | 121980 | Canquiason ES | Villaba | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1064550 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 080214S00091 | 14IE0038 | 2014-09-03 | 2014-09-05 | 2014-09-17 | 2014-09-26 | 2014-10-02 | Z.A.S. CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Leyte | 121592 | Consuegra ES | LEYTE | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-11-07 | 2015-11-07 | 080214S00139 | 15IE0038 | 2015-07-03 | 2015-07-09 | 2015-07-21 | 2015-07-29 | 2015-08-04 | TAM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Leyte | 121985 | Jordan ES | Villaba | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1108100 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 080214S00098 | 14IE0036 | 2014-09-03 | 2014-09-05 | 2014-09-17 | 2014-09-26 | 2014-10-02 | R. ALLOSA CONSTRUCTION & TRUCKING SERVICES (FORMER
NC 2014 | K10 (2014) | Region VIII | Leyte | 313308 | JUAN V. DELANTAR NATIONAL HIGH SCHOOL | LEYTE | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2690828.124 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | LEYTE | 121889 | Manlawaan ES | Tabango | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1151650 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 080214S00100 | 14IE0040 | 2014-09-03 | 2014-09-05 | 2014-09-17 | 2014-09-26 | 2014-10-02 | R. ALLOSA CONSTRUCTION & TRUCKING SERVICES (FORMER
NC 2014 | K10 (2014) | Region VIII | Leyte | 303389 | Villaba NHS (LNCAST) | Villaba | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1108100 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Leyte | 121991 | Villaba South Central School | Villaba | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1151650 |  |  | COMPLETED | 1 | 2015-02-07 | 2015-02-07 | 080214S00090 | 14IE0039 | 2014-10-06 | 2014-10-10 | 2014-10-21 | 2014-10-29 | 2014-11-04 | R. ALLOSA CONSTRUCTION & TRUCKING SERVICES (FORMER
NC 2014 | K10 (2014) | Region VIII | LEYTE | 121906 | YBANEZ MES | Tabango | 3 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2119100 |  |  | COMPLETED | 1 | 2015-02-04 | 2015-02-04 | 080214S00095 | 14IE0041 | 2014-09-03 | 2014-09-05 | 2014-09-17 | 2014-09-26 | 2014-10-02 | MN MACATO BUILDERS
NC 2014 | K10 (2014) | Region VIII | Leyte | 303345 | Balugo NHS | Albuera | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1031000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Leyte | 121785 | Belen PS | Palompon | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1031000 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 080214S00099 | 14IF0067 | 2014-07-16 | 2014-07-18 | 2014-08-06 | 2014-08-08 | 2014-08-19 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Leyte | 121714 | Benabaye Elementary School | Merida | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041000 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 080214S00060 | 14IF0061 | 2014-07-16 | 2014-07-18 | 2014-08-06 | 2014-08-08 | 2014-08-19 | ARCA BUILDERS
NC 2014 | K10 (2014) | Region VIII | Leyte | 191541 | Bonoy Primary School | Matag-Ob | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041000 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-01 | 080214S00059 | 14IF0064 | 2014-07-16 | 2014-07-18 | 2014-08-06 | 2014-08-08 | 2014-08-19 | QM BUILDERS
NC 2014 | K10 (2014) | Region VIII | Leyte | 121440 | Cangag ES | Isabel | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1051000 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 080214S00053 | 14IF0065 | 2014-07-16 | 2014-07-18 | 2014-08-06 | 2014-08-08 | 2014-08-19 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Leyte | 121789 | Cangmoya PS | Palompon | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1031000 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-02 | 080214S00096 | 14IF0068 | 2014-07-16 | 2014-07-18 | 2014-08-06 | 2014-08-08 | 2014-08-19 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Leyte | 303359 | Cantuhaon NHS | PALOMPON | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1839740.174 |  |  | COMPLETED | 1 | 2015-11-02 | 2015-10-12 | 080214S00135 | 15IF0086 | 2015-06-28 | 2015-07-02 | 2015-07-14 | 2015-07-22 | 2015-08-03 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2014 | K10 (2014) | Region VIII | Leyte | 121793 | Catigahan PS | Palompon | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1031000 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 080214S00101 | 14IF0069 | 2014-08-21 | 2014-08-26 | 2014-09-09 | 2014-09-24 | 2014-10-01 | LJPM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Leyte | 121536 | Don Felipe ES | Kananga | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1031000 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 080214S00054 | 14IF0059 | 2014-07-16 | 2014-07-18 | 2014-08-05 | 2014-08-08 | 2014-08-19 | QM BUILDERS
NC 2014 | K10 (2014) | Region VIII | Leyte | 121768 | Hinagbuan ES | Palompon | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041000 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-01 | 080214S00087 | 14IF0066 | 2014-07-16 | 2014-07-18 | 2014-08-06 | 2014-08-08 | 2014-08-19 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Leyte | 313328 | Kananga NHS - Montebello Annex | KANANGA | 4 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6379337.6381 |  |  | COMPLETED | 1 | 2015-12-02 | 2015-10-28 | 080214S00137 | 15IF0085 | 2015-06-28 | 2015-07-02 | 2015-07-14 | 2015-07-22 | 2015-08-03 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Leyte | 121539 | Kawayan ES | Kananga | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041000 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 080214S00065 | 14IF0058 | 2014-07-16 | 2014-07-18 | 2014-08-05 | 2014-08-08 | 2014-08-19 | QM BUILDERS
NC 2014 | K10 (2014) | Region VIII | Leyte | 121796 | Lat-osan ES | Palompon | 4 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2062000 |  |  | COMPLETED | 1 | 2015-01-30 | 2015-01-30 | 080214S00110 | 14IF0073 | 2014-11-12 | 2014-11-14 | 2014-11-27 | 2014-12-09 | 2014-12-15 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2014 | K10 (2014) | Region VIII | Leyte | 121541 | Libongao ES | Kananga | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1031000 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 080214S00056 | 14IF0060 | 2014-07-16 | 2014-07-18 | 2014-08-05 | 2014-08-08 | 2014-08-19 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Leyte | 121543 | Lonoy Elementary School | Kananga | 4 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2052000 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 080214S00109 | 14IF0056 | 2014-07-16 | 2014-07-18 | 2014-08-05 | 2014-08-08 | 2014-08-19 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Leyte | 120988 | Macagpo PS | Albuera | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1031000 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 080214S00074 | 14IF0055 | 2014-07-16 | 2014-07-18 | 2014-08-05 | 2014-08-08 | 2014-08-19 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Leyte | 121662 | Malazarte PS | Matag-ob | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1031000 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-02 | 080214S00058 | 14IF0063 | 2014-07-16 | 2014-07-18 | 2014-08-06 | 2014-08-08 | 2014-08-19 | QM BUILDERS
NC 2014 | K10 (2014) | Region VIII | Leyte | 303410 | Merida Vocational HS-Puerto Bello Annex | Merida | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1031000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Leyte | 120989 | Panhugan ES | Albuera | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1031000 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 080214S00049 | 14IF0052 | 2014-07-16 | 2014-07-18 | 2014-08-05 | 2014-08-08 | 2014-08-19 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Leyte | 120992 | Soob ES | albuera | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041000 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 080214S00050 | 14IF0053 | 2014-07-16 | 2014-07-18 | 2014-08-05 | 2014-08-08 | 2014-08-19 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Leyte | 303435 | Taberna NHS | Palompon | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1031000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Leyte | 121782 | Tinago ES | Palompon | 4 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2062000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Leyte | 121492 | Abuyogay ES | JAVIER (BUGHO) | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737398.3328 |  |  | COMPLETED | 1 | 2015-07-19 | 2015-07-19 | 080214S00127 | 15IG0037 | 2015-02-26 | 2015-03-16 | 2015-03-12 | 2015-03-20 | 2015-04-01 | CIRCLE Z VENTURES & DEVELOPMENT CORP.
NC 2014 | K10 (2014) | Region VIII | LEYTE | 313316 | Baybay City National Night High School | BAYBAY | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1020783.6694 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Leyte | 121495 | Bonifacio ES | JAVIER (BUGHO) | 5 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2527212.7478 |  |  | COMPLETED | 1 | 2015-06-28 | 2015-06-28 | 080214S00126 | 15IG0033 | 2015-02-03 | 2015-02-05 | 2015-02-17 | 2015-02-27 | 2015-03-12 | R. AGULLO CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | LEYTE | 191532 | Guinsanga-an PS | INOPACAN | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1020783.6694 |  |  | COMPLETED | 1 | 2015-01-07 | 2015-01-07 | 080214S00041 | 14IG0095 | 2014-08-25 | 2014-08-28 | 2014-09-09 | 2014-09-22 | 2014-10-06 | LADY OF ASSUMPTION ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Leyte | 121631 | Hiluctogan Primary School | MAHAPLAG | 5 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2527212.7478 |  |  | COMPLETED | 1 | 2015-07-19 | 2015-07-19 | 080214S00125 | 15IG0038 | 2015-02-26 | 2015-02-26 | 2015-03-12 | 2015-03-20 | 2015-03-30 | R. AGULLO CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | LEYTE | 303375 | Hindang NHS | HINDANG | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1020783.6694 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | LEYTE | 121066 | Imelda ES | BATO | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1020783.6694 |  |  | COMPLETED | 1 | 2015-01-10 | 2015-01-10 | 080214S00028 | 14IG0093 | 2014-08-25 | 2014-08-28 | 2014-09-09 | 2014-09-22 | 2014-10-06 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | LEYTE | 121409 | Katipunan ES | HINDANG | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1020783.6694 |  |  | COMPLETED | 1 | 2015-01-07 | 2015-01-07 | 080214S00025 | 14IG0095 | 2014-08-25 | 2014-08-28 | 2014-09-09 | 2014-09-21 | 2014-10-06 | LADY OF ASSUMPTION ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Leyte | 121504 | Laray PS | JAVIER (BUGHO) | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737398.3328 |  |  | COMPLETED | 1 | 2015-06-08 | 2015-06-08 | 080214S00124 | 15IG0035 | 2015-02-03 | 2015-02-05 | 2015-02-17 | 2015-02-27 | 2015-03-12 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2014 | K10 (2014) | Region VIII | LEYTE | 120893 | Lawaan ES | ABUYOG | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1825235.4243 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Leyte | 120893 | Lawaan Primary School | ABUYOG | 5 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2527212.7478 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | LEYTE | 120930 | Maitum PS | ABUYOG | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1825235.4243 |  |  | COMPLETED | 1 | 2015-02-19 | 2015-02-19 | 080214S00033 | 14IG0092 | 2014-08-25 | 2014-08-28 | 2014-09-09 | 2014-09-21 | 2014-10-06 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Leyte | 120894 | Malaguicay Elementary School | ABUYOG | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737398.3328 |  |  | COMPLETED | 1 | 2015-06-29 | 2015-06-29 | 080214S00121 | 15IG0032 | 2015-02-26 | 2015-02-26 | 2015-03-12 | 2015-03-20 | 2015-04-01 | R. AGULLO CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | LEYTE | 120935 | Pagsang-an ES | ABUYOG | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1020783.6694 |  |  | COMPLETED | 1 | 2015-02-19 | 2015-02-19 | 080214S00031 | 14IG0092 | 2014-08-25 | 2014-08-28 | 2014-09-09 | 2014-09-21 | 2014-10-06 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | LEYTE | 120895 | Pilar ES | ABUYOG | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1825235.4243 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 080214S00047 | 14IG0091 | 2014-08-25 | 2014-08-28 | 2014-09-09 | 2014-09-22 | 2014-10-06 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | LEYTE | 120916 | Pinamanagan ES | ABUYOG | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1825235.4243 |  |  | COMPLETED | 1 | 2015-02-09 | 2015-02-09 | 080214S00034 | 14IG0094 | 2014-08-25 | 2014-08-28 | 2014-09-09 | 2014-09-22 | 2014-10-06 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Leyte | 121510 | Pinocawan ES | JAVIER (BUGHO) | 5 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2527212.7478 |  |  | COMPLETED | 1 | 2015-06-28 | 2015-06-28 | 080214S00118 | 15IG0036 | 2015-02-03 | 2015-02-05 | 2015-02-17 | 2015-02-27 | 2015-03-12 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2014 | K10 (2014) | Region VIII | LEYTE | 191563 | Rivilla PS | BATO | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1020783.6694 |  |  | COMPLETED | 1 | 2015-01-10 | 2015-01-10 | 080214S00027 | 14IG0093 | 2014-08-25 | 2014-08-28 | 2014-09-09 | 2014-09-22 | 2014-10-13 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Leyte | 120917 | San Isidro Elementary School | ABUYOG | 5 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2527212.7478 |  |  | COMPLETED | 1 | 2015-06-28 | 2015-05-05 | 080214S00122 | 15IG0034 | 2015-02-03 | 2015-02-05 | 2015-02-17 | 2015-02-27 | 2015-03-12 | R.S. REYNA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | LEYTE | 120901 | Tinali-an PS | ABUYOG | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1020783.6694 |  |  | COMPLETED | 1 | 2015-02-19 | 2015-02-19 | 080214S00030 | 14IG0092 | 2014-08-25 | 2014-08-28 | 2014-09-09 | 2014-09-22 | 2014-10-06 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | LEYTE | 120918 | Tinocolan PS | ABUYOG | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1020783.6694 |  |  | COMPLETED | 1 | 2015-02-09 | 2015-02-09 | 080214S00029 | 14IG0094 | 2014-08-25 | 2014-08-28 | 2014-09-09 | 2014-09-22 | 2014-10-06 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Leyte | 121653 | Uguis Elementary School | MAHAPLAG | 5 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2527212.7478 |  |  | COMPLETED | 1 | 2015-07-03 | 2015-07-03 | 080214S00128 | 15IG0039 | 2015-02-03 | 2015-02-05 | 2015-02-17 | 2015-02-27 | 2015-03-12 | R. AGULLO CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Maasin City | 122128 | Gawisan ES | CITY OF MAASIN (Capital) | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-01 | 2014-12-29 | 080314S00023 | 14-IL-0041 | 2014-06-29 | 2014-07-01 | 2014-09-04 | 2014-09-12 | 2014-09-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Maasin City | 323104 | Hinapu Daku NHS | CITY OF MAASIN (Capital) | 0 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2945174.43 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 080314S00005 | 14-IL-00005 | 2014-06-29 | 2014-07-01 | 2014-09-04 | 2014-09-12 | 2014-09-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Maasin City | 323101 | Ibarra National High School | CITY OF MAASIN (Capital) | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Maasin City | 323103 | Lunas NHS | CITY OF MAASIN (Capital) | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 080314S00020 | 14-IL-0042 | 2014-06-29 | 2014-07-01 | 2014-09-04 | 2014-09-12 | 2014-09-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Maasin City | 122140 | Matin-Aw ES | CITY OF MAASIN (Capital) | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-04 | 2014-12-04 | 080314S00024 | 14-IL-0039 | 2014-06-29 | 2014-07-01 | 2014-08-13 | 2014-08-22 | 2014-09-01 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Maasin City | 122169 | Nonok Sur ES | CITY OF MAASIN (Capital) | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 080314S00026 | 14-IL-0044 | 2014-06-29 | 2014-07-01 | 2014-09-04 | 2014-09-12 | 2014-09-26 | GES CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Maasin City | 122146 | Tam-Is ES | CITY OF MAASIN (Capital) | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-10 | 080314S00025 | 14-IL-0040 | 2014-06-29 | 2014-07-04 | 2014-07-15 | 2014-08-04 | 2014-08-08 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2014 | K10 (2014) | Region VIII | Maasin City | 122154 | Cabadiangan MGS | CITY OF MAASIN (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-02-28 | 2015-09-16 | 080314S00048 | 14-IL-0067 | 2014-09-24 | 2014-09-26 | 2014-10-28 | 2014-11-06 | 2014-11-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Maasin City | 122130 | Hantag MGS | CITY OF MAASIN (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-02-28 | 2015-08-14 | 080314S00051 | 14-IL-0071 | 2014-09-24 | 2014-09-26 | 2014-10-28 | 2014-11-06 | 2014-11-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Maasin City | 122164 | Libertad MGS | CITY OF MAASIN (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-02-28 | 2015-08-14 | 080314S00047 | 14-IL-0070 | 2014-09-24 | 2014-09-26 | 2014-10-28 | 2014-11-06 | 2014-11-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Maasin City | 323102 | Maasin City NHS-Night | CITY OF MAASIN (Capital) | 0 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 2 | 3458140.8307 |  |  | COMPLETED | 1 | 2015-04-29 | 2015-04-29 | 080314S00043 | 14-IL-0072 | 2014-09-24 | 2014-09-26 | 2014-10-28 | 2014-11-06 | 2014-11-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Maasin City | 122171 | Pinascohan MGS | CITY OF MAASIN (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-02-28 | 2015-05-15 | 080314S00046 | 14-IL-0069 | 2014-09-24 | 2014-09-26 | 2014-10-28 | 2014-11-06 | 2014-11-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Maasin City | 238001 | Tomoy-Tomoy MGS | CITY OF MAASIN (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-02-28 | 2015-05-15 | 080314S00045 | 14-IL-0068 | 2014-09-24 | 2014-09-26 | 2014-10-28 | 2014-11-06 | 2014-11-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122801 | Acereda ES | BOBON | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-04-26 | 2015-04-26 | 080614S00048 | 14IH0031(5) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-24 | STEVEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123220 | Aguadahan ES | SAN JOSE | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-04-23 | 2015-03-13 | 080614S00134 | 14IH0028(4) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-18 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122776 | Alejandro PS | ALLEN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-05-04 | 2015-05-04 | 080614S00191 | 14IH0050 | 2014-09-29 | 2014-11-26 | 2015-01-13 | 2015-02-09 | 2015-02-27 | CTC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 303531 | Allen NHS | ALLEN | 1 | 1 | 20 | 2UNITS 2STY8CL & 2STY4CL | 2014 K10 BATCH 3 | 28854633.5156 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123221 | Bagong Sabang ES | SAN JOSE | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-04-23 | 2015-04-23 | 080614S00133 | 14IH0029(1) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-18 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122790 | Bagong Silang ES | BIRI | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-02-07 | 2015-02-07 | 080614S00182 | 14IH0053 | 2014-09-29 | 2014-10-16 | 2014-10-21 | 2014-11-13 | 2014-12-03 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123055 | Balicuatro PS | LAVEZARES | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1817877.8281 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-09 | 080614S00185 | 14IH0039 | 2014-09-29 | 2014-10-16 | 2014-10-21 | 2014-11-13 | 2014-12-03 | CHRISTFER CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122863 | Bangkerohan Elementary school | CATARMAN (Capital) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-05-25 | 080614S00064 | 14IH0023(5) | 2014-08-13 | 2014-10-16 | 2014-11-20 | 2014-12-11 | 2015-01-05 | STEVEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 303561 | Basilio B. Chan Mem. Agricultural and Industrial Sch. | LAVEZARES | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122844 | Baybay ES | CATARMAN (Capital) | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-04-29 | 2015-06-05 | 080614S00042 | 14IH0031(4) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-24 | STEVEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122831 | Binog ES | CATARMAN (Capital) | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-04-29 | 2015-04-29 | 080614S00046 | 14IH0031(3) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-24 | STEVEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122792 | Biri CES | BIRI | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-04-23 | 2015-03-13 | 080614S00051 | 14IH0029(3) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-18 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122854 | Bocsol PS | CATARMAN (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1817877.8281 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-09 | 080614S00197 | 14IH0070 | 2014-09-29 | 2014-10-16 | 2014-10-21 | 2014-11-13 | 2014-12-03 | AREX BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123207 | Buenavista ES | SAN ISIDRO | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-04-23 | 2015-04-23 | 080614S00138 | 14IH0033(2) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-18 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123252 | Cababayogan PS | SILVINO LOBOS | 1 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 3940835.14 |  |  | COMPLETED | 1 | 2015-06-01 |  | 080614S00062 | 14II0081 | 2014-10-16 | 2014-10-16 | 2014-10-30 | 2014-11-05 | 2014-11-27 | CHRISTFER CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122779 | Calarayan ES | ALLEN | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-04-23 | 2015-04-23 | 080614S00053 | 14IH0028(7) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-18 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122833 | Cal-igang ES | CATARMAN (Capital) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-06-10 | 080614S00020 | 14IH0023(1) | 2014-08-13 | 2014-10-16 | 2014-11-20 | 2014-12-11 | 2015-01-05 | STEVEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123118 | Canawa PS | MONDRAGON | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-02-07 | 2015-02-07 | 080614S00160 | 14IH0066 | 2014-09-29 | 2014-10-16 | 2014-10-21 | 2014-11-13 | 2014-12-03 | CTC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122780 | Caputian PS | ALLEN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-05-04 | 2015-05-04 | 080614S00192 | 14IH0051 | 2014-09-29 | 2014-12-06 | 2015-01-13 | 2015-02-09 | 2015-02-27 | CTC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122834 | Cularima PS | CATARMAN (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-09 | 080614S00178 | 14IH0060 | 2014-09-29 | 2014-10-16 | 2014-10-21 | 2014-11-13 | 2014-12-03 | AREX BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122823 | Diraya ES | CAPUL | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-02-07 | 2015-03-05 | 080614S00179 | 14IH0056 | 2014-09-29 | 2014-10-16 | 2014-10-21 | 2014-11-13 | 2014-12-03 | AREX BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123122 | Flormina PS | MONDRAGON | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-09 | 080614S00161 | 14IH0067 | 2014-09-29 | 2014-10-16 | 2014-10-21 | 2014-11-13 | 2014-12-03 | CTC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122837 | Gen. Malvar Elementary School | CATARMAN (Capital) | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-07-15 | 080614S00044 | 14IH0023(8) | 2014-08-13 | 2014-10-16 | 2014-11-20 | 2014-12-11 | 2015-01-05 | STEVEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122836 | Generoso R. Frigillana Memorial School | CATARMAN (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-02-07 | 2015-02-07 | 080614S00193 | 14IH0059 | 2014-09-29 | 2014-10-16 | 2014-10-21 | 2014-11-13 | 2014-12-03 | CTC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122847 | Gilalan-agan ES | CATARMAN (Capital) | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-04-29 | 2015-04-29 | 080614S00041 | 14IH0031(2) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-24 | STEVEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122839 | Guba PS | CATARMAN (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1817877.8281 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-04-05 | 080614S00195 | 14IH0041 | 2014-09-29 | 2014-10-16 | 2014-10-21 | 2014-11-13 | 2014-12-03 | AREX BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122869 | Hinatad ES | CATARMAN (Capital) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-07-10 | 2015-08-02 | 080614S00066 | 14IH0023(3) | 2014-08-13 | 2014-10-16 | 2014-11-20 | 2014-12-11 | 2015-01-05 | STEVEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123124 | Imelda ES | MONDRAGON | 1 | 1 | 5 | 1STY 2CL & 1STY 3CL | 2014 K10 BATCH 1 | 4835592 |  |  | COMPLETED | 1 | 2015-08-02 | 2015-07-15 | 080614S00070 | 14IH0032(4) | 2014-09-17 | 2014-09-26 | 2015-01-13 | 2015-02-09 | 2015-02-27 | STEVEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122810 | J. P. Laurel I ES | BOBON | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-04-29 | 2015-04-29 | 080614S00038 | 14IH0031(6) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-24 | STEVEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122809 | J. P. Laurel II PS | BOBON | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | Reverted | 0
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123192 | Jamo-og ES | ROSARIO | 1 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 3940835.14 |  |  | COMPLETED | 1 | 2015-04-23 | 2015-04-23 | 080614S00074 | 14IH0028(5) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-18 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123193 | Kailingan Primary School | ROSARIO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123125 | La Trinidad PS | MONDRAGON | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-02 | 2015-08-02 | 080614S00069 | 14IH0032(3) | 2014-09-17 | 2014-09-26 | 2015-01-13 | 2015-02-09 | 2015-02-27 | STEVEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122785 | Lagundi ES | ALLEN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-04-23 | 2015-03-13 | 080614S00052 | 14IH0028(1) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-18 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122825 | Landusan ES | CAPUL | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-02-07 | 2015-03-05 | 080614S00180 | 14IH0057 | 2014-09-29 | 2014-10-16 | 2014-10-21 | 2014-11-13 | 2014-12-03 | CTC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 303555 | Landusan NHS | CAPUL | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-03-24 | 2015-03-13 | 080614S00061 | 14IH0030(1) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-18 | CTC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122794 | Langub-Langub ES | BIRI | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-04-23 | 2015-03-13 | 080614S00050 | 14IH0029(5) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-18 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123226 | Layuhan ES | SAN JOSE | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-04-23 | 2015-04-23 | 080614S00132 | 14IH0029(4) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-18 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123091 | Lower Caynaga ES | LOPE DE VEGA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-16 | 2015-08-16 | 080614S00040 | 15IH0044 | 2014-08-13 | 2014-12-06 | 2015-05-07 | 2015-05-22 | 2015-06-11 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123278 | Lungib ES | VICTORIA | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-04-23 | 2015-04-23 | 080614S00101 | 14IH0033(4) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-18 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123211 | Mabuhay ES | SAN ISIDRO | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-04-23 | 2015-04-23 | 080614S00137 | 14IH0033(1) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-18 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122840 | Macagtas ES | CATARMAN (Capital) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-08-19 | 080614S00045 | 14IH0023(4) | 2014-08-13 | 2014-10-16 | 2014-11-20 | 2014-12-11 | 2015-01-05 | STEVEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123093 | Magsaysay Elementary School | LOPE DE VEGA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-06-10 | 080614S00071 | 14IH0023(7) | 2014-08-13 | 2014-10-16 | 2014-11-20 | 2014-12-11 | 2015-01-05 | STEVEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123068 | Magsaysay ES | LAVEZARES | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-04-23 | 2015-03-13 | 080614S00047 | 14IH0028(2) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-18 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123246 | Maragat ES | SAN VICENTE | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-03-24 | 2015-03-13 | 080614S00063 | 14IH0030(3) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-18 | CTC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123127 | Mirador ES | MONDRAGON | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-02 | 2015-08-02 | 080614S00068 | 14IH0032(1) | 2014-09-17 | 2014-09-26 | 2015-01-13 | 2015-02-09 | 2015-02-27 | STEVEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 303567 | Mongolbongol NHS | SAN VICENTE | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123094 | New Somoroy PS | LOPE DE VEGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-02-07 | 2015-02-07 | 080614S00184 | 14IH0063 | 2014-09-29 | 2014-10-16 | 2014-10-21 | 2014-11-13 | 2014-12-03 | J. CUSTORIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123212 | Palanit ES | SAN ISIDRO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-09 | 080614S00163 | 14IH0069 | 2014-09-29 | 2014-10-16 | 2014-10-21 | 2014-11-13 | 2014-12-03 | CTC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122796 | Palhugan ES | BIRI | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-02-07 | 2015-02-07 | 080614S00194 | 14IH0052 | 2014-09-29 | 2014-10-16 | 2014-10-21 | 2014-11-13 | 2014-12-03 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122859 | Paticua Elementary School | CATARMAN (Capital) | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-07-15 | 080614S00039 | 14IH0023(6) | 2014-08-13 | 2014-10-16 | 2014-11-20 | 2014-12-11 | 2015-01-05 | STEVEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 303570 | Polangi National HIgh School | CATARMAN (Capital) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122813 | R. Magsaysay ES | BOBON | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-06-04 | 2015-07-04 | 080614S00189 | 14IH0054 | 2014-09-29 | 2014-10-29 | 2015-01-13 | 2015-02-11 | 2015-02-27 | CTC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 303573 | Rosario NHS | ROSARIO | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122827 | Sagao-Sawan ES | CAPUL | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-02-07 | 2015-03-05 | 080614S00196 | 14IH0058 | 2014-09-29 | 2014-10-16 | 2014-10-21 | 2014-11-13 | 2014-12-03 | CTC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122797 | Salvacion ES | BIRI | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-04-23 | 2015-03-13 | 080614S00049 | 14IH0029(6) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-18 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122860 | Salvacion PS | CATARMAN (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1817877.8281 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-02-27 | 080614S00190 | 14IH0040 | 2014-09-29 | 2014-10-16 | 2014-10-21 | 2014-11-13 | 2014-12-03 | J. CUSTORIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123099 | Sampaguita PS | LOPE DE VEGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-02-07 | 2015-02-07 | 080614S00183 | 14IH0064 | 2014-09-29 | 2014-10-16 | 2014-10-21 | 2014-11-13 | 2014-12-03 | J. CUSTORIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123132 | San Antonio Elementary School | MONDRAGON | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-08-02 | 2015-08-02 | 080614S00067 | 14IH0032(6) | 2014-09-17 | 2014-09-26 | 2015-01-13 | 2015-02-09 | 2015-02-27 | STEVEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 303580 | San Jose Technical HS | SAN JOSE | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123135 | San Juan Elementary School | MONDRAGON | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-08-02 | 2015-08-02 | 080614S00056 | 14IH0032(5) | 2014-09-17 | 2014-09-26 | 2015-01-13 | 2015-02-09 | 2015-02-27 | STEVEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123073 | San Juan ES | LAVEZARES | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-04-23 | 2015-03-15 | 080614S00072 | 14IH0028(3) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-18 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122861 | San Julian PS | CATARMAN (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1817877.8281 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-09 | 080614S00181 | 14IH0038 | 2014-09-29 | 2014-10-16 | 2014-10-21 | 2014-11-13 | 2014-12-03 | AREX BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123217 | Seven Hills ES | SAN ISIDRO | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | terminated | 0.25 | 2015-04-23 | 2015-04-23 | 080614S00136 | 14IH0033(3) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-18 | RHYES BUILDERS & SUPPLY | Contract Termination in process.
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122850 | Somoge ES | CATARMAN (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-02-07 | 2015-02-07 | 080614S00187 | 14IH0061 | 2014-09-29 | 2014-10-16 | 2014-10-21 | 2014-11-13 | 2014-12-03 | J. CUSTORIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123218 | Sto. Nino Primary School | SAN ISIDRO | 1 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1 | 2015-05-29 | 2015-08-02 | 080614S00135 | 14IH0033(5) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-18 | RHYES BUILDERS & SUPPLY | Abandoned
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123137 | Talolora PS | MONDRAGON | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-02 | 2015-08-02 | 080614S00065 | 14IH0032(2) | 2014-09-17 | 2014-09-26 | 2015-01-13 | 2015-02-09 | 2015-02-27 | STEVEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 193002 | Tarugan PS | CATARMAN (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-02-07 | 2015-02-07 | 080614S00198 | 14IH0062 | 2014-09-29 | 2014-10-16 | 2014-10-21 | 2014-11-13 | 2014-12-03 | CTC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122818 | Trujillo Elementary School | BOBON | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-04-05 | 080614S00186 | 14IH0055 | 2014-09-29 | 2014-10-16 | 2014-10-21 | 2014-11-13 | 2014-12-03 | CTC BUILDER AND SUPPLIES INCORPORATED (FOR. CTC BU
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123103 | Upper Caynaga PS | LOPE DE VEGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-02-07 | 2015-02-07 | 080614S00157 | 14IH0065 | 2014-09-29 | 2014-10-16 | 2014-10-21 | 2014-11-13 | 2014-12-03 | J. CUSTORIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 303587 | Washington NHS | CATARMAN (Capital) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-04-29 | 2015-04-29 | 080614S00058 | 14IH0031(1) | 2014-09-17 | 2014-09-19 | 2014-10-01 | 2014-10-29 | 2014-11-24 | STEVEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122952 | Aguadahan ES | LAOANG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1817877.8281 |  |  | COMPLETED | 1 | 2015-06-01 | 2015-07-15 | 080614S00171 | 14II0073 | 2014-10-02 | 2014-10-02 | 2014-10-22 | 2014-11-12 | 2014-11-27 | CTC BUILDER AND SUPPLIES INCORPORATED (FOR. CTC BU
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122990 | Alang-alang PS | LAPINIG | 2 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1 | 2015-05-19 | 2015-05-19 | 080614S00031 | 14II0049 | 2014-09-24 | 2014-09-26 | 2010-10-14 | 2014-10-30 | 2014-11-14 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122895 | Anongo ES | CATUBIG | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-02-06 | 080614S00017 | 14II0029 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-12 | 2014-10-03 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122936 | Atipolo ES | LAOANG | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-04-15 | 080614S00007 | 14II0026 | 2014-07-10 | 2014-07-11 | 2014-08-04 | 2014-09-08 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123138 | B. Aquino PS | PALAPAG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-05-22 | 2015-06-11 | 080614S00140 | 14II0075 | 2014-10-02 | 2014-10-02 | 2014-10-22 | 2014-10-31 | 2014-11-17 | J. CUSTORIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123140 | Bagacay ES | PALAPAG | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-10-09 | 080614S00123 | 14II0051 | 2014-09-24 | 2014-09-26 | 2014-10-14 | 2014-10-29 | 2014-11-14 | CHRISTFER CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 313618 | Balnasan National High School | SAN ROQUE | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123233 | Balud ES | SAN ROQUE | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-02-06 | 080614S00077 | 14II0021 | 2014-07-10 | 2014-07-11 | 2014-08-04 | 2014-09-08 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123234 | Bantayan Elementary School | SAN ROQUE | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-07-31 | 2015-07-15 | 080614S00207 | 14II0102 | 2014-12-08 | 2014-12-11 | 2014-12-22 | 2015-01-12 | 2015-01-26 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 313604 | Bantayan NHS | SAN ROQUE | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122937 | Bawang ES | LAOANG | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-03-08 | 080614S00001 | 14II0033 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-23 | 2014-10-03 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123142 | Binay ES | PALAPAG | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-04-07 | 2015-05-31 | 080614S00116 | 14II0043 | 2014-07-29 | 2014-07-30 | 2014-08-18 | 2014-09-12 | 2014-10-03 | CTC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122971 | Bobolosan ES | LAOANG | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-02-06 | 080614S00006 | 14II0033 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-23 | 2014-10-03 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122972 | Bongliw ES | LAOANG | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-02-06 | 080614S00014 | 14II0032 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-12 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123143 | Bukid PS | PALAPAG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1817877.8281 |  |  | COMPLETED | 1 | 2015-05-22 | 2015-06-30 | 080614S00147 | 14II0075 | 2014-10-02 | 2014-10-02 | 2014-10-22 | 2014-10-31 | 2014-11-17 | J. CUSTORIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123006 | Bulao ES | LAS NAVAS | 2 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 3940835.14 |  |  | COMPLETED | 1 | 2015-06-01 | 2015-10-09 | 080614S00028 | 14II0058 | 2014-09-28 | 2014-09-26 | 2014-10-10 | 2014-10-30 | 2014-11-27 | NORSAM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123169 | Busak ES | PAMBUJAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-01-25 | 080614S00120 | 14II0034 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-12 | 2014-10-03 | CTC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122975 | Cabagoan ES | LAOANG | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 2 | 2834858.5037 |  |  | COMPLETED | 1 | 2015-06-01 | 2015-11-03 | 080614S00172 | 14II0073 | 2014-10-02 | 2014-10-02 | 2014-10-22 | 2014-11-12 | 2014-11-27 | CTC BUILDER AND SUPPLIES INCORPORATED (FOR. CTC BU
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122919 | Cabarasan ES | GAMAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-07-26 | 2015-11-05 | 080614S00170 | 14II0077 | 2014-12-15 | 2014-12-16 | 2014-12-29 | 2015-01-12 | 2015-01-26 | NORSATEK ENGINEERING AND CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123145 | Cabatuan ES | PALAPAG | 2 | 1 | 5 | 1STY 2CL & 1STY 3CL | 2014 K10 BATCH 1 | 4835592 |  |  | COMPLETED | 1 | 2015-05-17 | 2015-02-20 | 080614S00103 | 14II0055 | 2014-09-24 | 2014-09-26 | 2014-10-10 | 2014-10-22 | 2014-11-12 | CHRISTFER CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 313609 | Cabatuan NHS | PALAPAG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123253 | Cabonga-an ES | SILVINO LOBOS | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | Reverted | 0 |  |  | 080614S00109 | 14II0045 | 2015-01-04 | 2015-01-06 | 2015-01-19
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122976 | Cabulaloan ES | LAOANG | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-04-25 | 080614S00029 | 14II0032 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-12 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122920 | Cadac-an ES | GAMAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-03-06 | 080614S00013 | 14II0028 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-12 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122921 | Cadean ES | GAMAY | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-03-08 | 080614S00012 | 14II0028 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-12 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 313615 | Cagamutan National High School | GAMAY | 2 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1 | 2015-05-12 | 2015-02-20 | 080614S00097 | 14II0042 | 2014-09-24 | 2014-09-26 | 2014-10-14 | 2014-10-29 | 2014-11-07 | 5G GALVEZ CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123146 | Cag-anibong PS | PALAPAG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-08-30 | 2015-11-08 | 080614S00151 | 14II0076 | 2014-12-15 | 2014-12-16 | 2014-12-29 | 2015-01-12 | 2015-01-26 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123254 | Cagdao PS | SILVINO LOBOS | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 2 | 2834858.5037 |  |  | COMPLETED | 1 | 2015-07-31 |  | 080614S00141 | 14II0072 | 2014-12-15 | 2014-12-16 | 2014-12-29 | 2015-01-12 | 2015-01-26 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122977 | Cagdara-o ES | LAOANG | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-03-08 | 080614S00036 | 14II0032 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-12 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122878 | Cagmanaba ES | CATUBIG | 2 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1 | 2015-04-07 | 2015-04-07 | 080614S00057 | 14II0048 | 2014-07-29 | 2014-07-30 | 2014-08-18 | 2014-09-12 | 2014-10-03 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122897 | Cagugubngan ES | CATUBIG | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 2 | 2834858.5037 |  |  | COMPLETED | 1 | 2015-07-31 | 2015-10-13 | 080614S00164 | 14II0068 | 2014-12-15 | 2014-12-16 | 2014-12-29 | 2015-01-12 | 2015-01-26 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122992 | Cahagwayan ES | LAPINIG | 2 | 1 | 5 | 1STY 2CL & 1STY 3CL | 2014 K10 BATCH 1 | 4835592 |  |  | COMPLETED | 1 | 2015-05-17 | 2015-05-17 | 080614S00030 | 14II0052 | 2014-09-24 | 2014-09-26 | 2014-10-14 | 2014-10-30 | 2014-11-12 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123256 | Camangaran PS | SILVINO LOBOS | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | cOMPLETED | 1 | 2015-07-31 |  | 080614S00169 | 14II0072 | 2014-12-15 | 2014-12-16 | 2014-12-30 | 2015-01-12 | 2015-01-26 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123147 | Campedico PS | PALAPAG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1817877.8281 |  |  | COMPLETED | 1 | 2015-05-22 | 2015-03-15 | 080614S00158 | 14II0075 | 2014-10-02 | 2014-10-02 | 2014-10-22 | 2014-10-31 | 2014-11-17 | J. CUSTORIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123173 | Canjumadal ES | PAMBUJAN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-02-06 | 080614S00119 | 14II0033 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-23 | 2014-10-03 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123148 | Canonghan Elementary School | PALAPAG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1817877.8281 |  |  | COMPLETED | 1 | 2015-08-30 | 2015-11-08 | 080614S00149 | 14II0076 | 2014-12-15 | 2014-12-16 | 2014-12-29 | 2015-01-12 | 2015-01-26 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123149 | Capacujan ES | PALAPAG | 2 | 1 | 6 | 2UNITS 1STY 3CL | 2014 K10 BATCH 1 | 5730348.86 |  |  | COMPLETED | 1 | 2015-05-18 | 2015-05-18 | 080614S00125 | 14II0054 | 2014-09-24 | 2014-09-26 | 2014-10-10 | 2014-10-21 | 2014-11-13 | CHRISTFER CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122979 | Catigbian ES | LAOANG | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-05-02 | 080614S00035 | 14II0032 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-12 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123009 | Cuenco PS | LAS NAVAS | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | Reverted | 0 | 2015-02-06 |  | 080614S00037 | 14II0023 | 2014-07-10 | 2014-07-11 | 2014-08-04 | 2014-09-08 | 2014-10-03 | CTC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123236 | Dale PS | SAN ROQUE | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1817877.8281 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-07-15 | 080614S00156 | 14II0071 | 2014-10-02 | 2014-10-02 | 2014-10-22 | 2014-10-31 | 2014-11-19 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123010 | Dapdap ES | LAS NAVAS | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-05-19 | 2015-05-09 | 080614S00026 | 14II0047 | 2014-09-24 | 2014-09-26 | 2014-10-14 | 2014-10-30 | 2014-11-14 | CHRISTHER CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123258 | Deit De Suba PS | SILVINO LOBOS | 2 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 3940835.14 |  |  | Reverted | 0 |  |  | 080614S00083 | 14II0045 | 2015-01-04 | 2015-01-05 | 2015-01-05
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123011 | Del Pilar ES | LAS NAVAS | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-06-01 | 2015-05-31 | 080614S00025 | 14II0046 | 2014-09-24 | 2014-09-26 | 2014-10-14 | 2014-10-29 | 2014-11-27 | NORSAM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123175 | Dona Anecita PS | PAMBUJAN | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 2 | 2834858.5037 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-09-30 | 080614S00154 | 14II0071 | 2014-10-02 | 2014-10-02 | 2014-10-22 | 2014-10-31 | 2014-11-26 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123150 | Dona P.C. Gorgonia ES | PALAPAG | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-02-06 | 080614S00131 | 14II0020 | 2014-07-10 | 2014-07-11 | 2014-08-04 | 2014-09-08 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123012 | E. Perez PS | LAS NAVAS | 2 | 1 | 5 | 1STY 2CL & 1STY 3CL | 2014 K10 BATCH 1 | 4835592 |  |  | COMPLETED | 1 | 2015-05-19 | 2015-05-09 | 080614S00027 | 14II0047 | 2014-09-24 | 2014-09-26 | 2014-10-14 | 2014-10-30 | 2014-11-14 | CHRISTHER CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122941 | E.J. Dulay ES | LAOANG | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-04-15 | 080614S00002 | 14II0026 | 2014-07-10 | 2014-07-11 | 2014-08-04 | 2014-09-08 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123013 | Enoman PS | LAS NAVAS | 2 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 3940835.14 |  |  | COMPLETED | 1 | 2015-07-01 | 2015-10-09 | 080614S00024 | 14II0059 | 2014-09-28 | 2014-09-26 | 2014-10-10 | 2014-10-30 | 2014-11-27 | NORSAM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122926 | Gamay East ES | GAMAY | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-05-17 |  | 080614S00011 | 14II0052 | 2014-09-24 | 2014-09-26 | 2014-10-10 | 2014-10-30 | 2014-11-12 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123264 | Ginagasan PS | SILVINO LOBOS | 2 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1 | 2015-08-30 |  | 080614S00084 | 14II0044 | 2014-12-15 | 2014-12-16 | 2014-12-29 | 2015-01-12 | 2015-01-26 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123238 | Ginagdanan Elementary School | SAN ROQUE | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-07 | 2015-01-07 | 080614S00078 | 14II0017 | 2014-07-10 | 2014-07-11 | 2014-08-04 | 2014-09-08 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123265 | Giparayan de Turag ES | SILVINO LOBOS | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-08-30 |  | 080614S00085 | 14II0044 | 2014-12-15 | 2014-12-16 | 2014-12-29 | 2015-01-12 | 2015-01-26 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123178 | Giparayan ES | PAMBUJAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-02-06 | 080614S00118 | 14II0034 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-12 | 2014-10-03 | CTC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122882 | Guibuangan PS | CATUBIG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-07-31 |  | 080614S00177 | 14II0068 | 2014-12-15 | 2014-12-16 | 2014-12-29 | 2015-01-12 | 2015-01-26 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123266 | Gusaran PS | SILVINO LOBOS | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-04-07 | 2015-03-30 | 080614S00086 | 14II0018 | 2014-07-10 | 2014-07-11 | 2014-08-04 | 2014-09-08 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY | Abandoned
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123019 | Hangi ES | LAS NAVAS | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-02-06 | 080614S00016 | 14II0050 | 2014-07-31 | 2014-07-30 | 2014-08-14 | 2014-09-23 | 2014-10-03 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122929 | Henogawe ES | GAMAY | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-04-07 | 2015-05-31 | 080614S00010 | 14II0027 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-12 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 303554 | Hibubullao NHS | CATUBIG | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122900 | Hinagonoyan PS | CATUBIG | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-05-07 | 2015-05-07 | 080614S00015 | 14II0041 | 2014-07-29 | 2014-07-30 | 2014-08-18 | 2014-09-12 | 2014-10-03 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122901 | Hitapian ES | CATUBIG | 2 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1 | 2015-05-07 | 2015-05-07 | 080614S00018 | 14II0041 | 2014-07-29 | 2014-07-30 | 2014-08-18 | 2014-09-12 | 2014-10-03 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123179 | Igot ES | PAMBUJAN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2965174.43 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-02-06 | 080614S00111 | 14II0034 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-12 | 2014-10-03 | CTC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122959 | Inamlan PS | LAOANG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1817877.8281 |  |  | COMPLETED | 1 | 2015-08-30 | 2015-11-05 | 080614S00175 | 14II0074 | 2014-12-15 | 2014-12-16 | 2014-12-29 | 2015-01-12 | 2015-01-26 | NORSATEK ENGINEERING AND CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122884 | Inoburan ES | CATUBIG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-07-31 | 2015-06-30 | 080614S00168 | 14II0067 | 2014-12-15 | 2014-12-16 | 2014-12-29 | 2015-01-12 | 2015-01-26 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 313608 | Jangtud Integrated School | PALAPAG | 2 | 1 | 4 | 1STY1CL & 1STY3CL | 2014 K10 BATCH 2 | 3657875.5345 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123105 | Jubasan ES | MAPANAS | 2 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 3940835.14 |  |  | COMPLETED | 1 | 2015-05-19 |  | 080614S00105 | 14II0039 | 2014-09-24 | 2014-09-26 | 2014-10-14 | 2014-10-30 | 2014-11-14 | CTC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123022 | Lakandula PS | LAS NAVAS | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1817877.8281 |  |  | COMPLETED | 1 | 2015-08-30 |  | 080614S00167 | 14II0069 | 2014-12-15 | 2014-12-16 | 2014-12-29 | 2015-01-12 | 2015-01-26 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 303560 | Las Navas NHS | LAS NAVAS | 2 | 1 | 18 | 3STY12CL & 2STY6CL | 2014 K10 BATCH 3 | 26957962.9688 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123240 | Lawaan Elementary School | SAN ROQUE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-07 | 2015-01-07 | 080614S00079 | 14II0017 | 2014-07-10 | 2014-07-11 | 2014-08-04 | 2014-09-08 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122982 | Lawaan ES | LAOANG | 2 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1 | 2015-04-07 | 2015-04-07 | 080614S00034 | 14II0048 | 2014-07-29 | 2014-07-30 | 2014-08-18 | 2014-09-12 | 2014-10-03 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122902 | Libon PS | CATUBIG | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 2 | 2834858.5037 |  |  | COMPLETED | 1 | 2015-07-31 | 2015-10-09 | 080614S00165 | 14II0067 | 2014-10-31 | 2014-12-16 | 2014-12-29 | 2015-01-12 | 2015-01-26 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123025 | Lonoy ES | LAS NAVAS | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-02-06 | 080614S00023 | 14II0050 | 2014-07-31 | 2014-07-30 | 2014-08-14 | 2014-09-23 | 2014-10-03 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123026 | Lourdes ES | LAS NAVAS | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1717981.9137 |  |  | COMPLETED | 1 | 2015-06-21 | 2015-09-07 | 080614S00204 | 14II0099 | 2014-12-08 | 2014-12-11 | 2014-12-22 | 2015-01-12 | 2015-03-17 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123241 | Lubog Primary School | SAN ROQUE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-07 | 2015-01-07 | 080614S00080 | 14II0017 | 2014-07-10 | 2014-07-11 | 2014-08-04 | 2014-09-08 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123152 | Mabaras PS | PALAPAG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1817877.8281 |  |  | COMPLETED | 1 | 2015-08-30 | 2015-11-05 | 080614S00146 | 14II0076 | 2014-12-15 | 2014-12-16 | 2014-12-29 | 2015-01-12 | 2015-01-26 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122961 | Magsaysay ES | LAOANG | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-02-06 | 080614S00004 | 14II0025 | 2014-07-10 | 2014-07-11 | 2014-08-04 | 2014-09-08 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123106 | Magsaysay ES | MAPANAS | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-06-18 |  | 080614S00106 | 14II0039 | 2014-09-24 | 2014-09-26 | 2014-10-14 | 2014-10-30 | 2014-11-14 | CTC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123029 | Magsaysay PS | LAS NAVAS | 2 | 1 | 7 | 1STY 3CL & 1STY 4CL | 2014 K10 BATCH 1 | 6625979.92 |  |  | COMPLETED | 1 | 2015-06-16 | 2015-07-15 | 080614S00022 | 14II0053 | 2014-09-28 | 2014-09-26 | 2014-10-10 | 2014-10-30 | 2014-11-12 | CHRISTFER CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123243 | Malobago ES | SAN ROQUE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-07 | 2015-01-07 | 080614S00089 | 14II0017 | 2014-07-10 | 2014-07-11 | 2014-08-04 | 2014-09-08 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 193008 | Manaybanay Elementary School | MAPANAS | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-03-20 | 2015-03-20 | 080614S00090 | 14II0019 | 2014-09-24 | 2014-09-26 | 2014-10-14 | 2014-10-30 | 2014-11-14 | CHRISTFER CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 303564 | Mapanas Agro-Industrial High School | MAPANAS | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 193015 | Mapanas North PS | MAPANAS | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-03-20 | 2015-04-05 | 080614S00081 | 14II0019 | 2014-09-24 | 2014-09-26 | 2014-10-14 | 2014-10-30 | 2014-11-14 | CHRISTFER CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123154 | Mapno ES | PALAPAG | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-02-06 | 080614S00129 | 14II0020 | 2014-07-10 | 2014-07-11 | 2014-08-04 | 2014-09-08 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123156 | Matambag PS | PALAPAG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-08-30 | 2015-11-05 | 080614S00152 | 14II0076 | 2014-12-15 | 2014-12-16 | 2014-12-29 | 2015-01-12 | 2015-01-26 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122907 | Nahulid PS | CATUBIG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1817877.8281 |  |  | COMPLETED | 1 | 2015-07-31 | 2015-09-07 | 080614S00166 | 14II0067 | 2014-12-15 | 2014-12-16 | 2014-12-29 | 2015-01-12 | 2015-01-26 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123109 | Naparasan ES | MAPANAS | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-03-20 | 2015-04-12 | 080614S00107 | 14II0022 | 2014-09-24 | 2014-09-26 | 2014-10-14 | 2014-10-30 | 2014-11-14 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123160 | Natawo ES | PALAPAG | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-02-06 | 080614S00128 | 14II0020 | 2014-07-10 | 2014-07-11 | 2014-08-04 | 2014-09-08 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 313624 | Oleras NHS | LAOANG | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6399164.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122890 | P. Rebadulla ES | CATUBIG | 2 | 1 | 6 | 3UNITS 1STY 2CL | 2014 K10 BATCH 1 | 5911252.71 |  |  | Reverted | 0 |  |  | 080614S00073 | 14II0063 | 2015-01-15 | 2015-01-15
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123244 | Pagsang-an ES | SAN ROQUE | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-02-06 | 080614S00082 | 14II0021 | 2014-07-10 | 2014-07-11 | 2014-08-04 | 2014-09-08 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122984 | Palmera PS | LAOANG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-08-30 | 2015-10-13 | 080614S00176 | 14II0074 | 2014-12-15 | 2014-12-16 | 2014-12-29 | 2015-01-12 | 2015-01-26 | NORSATEK ENGINEERING AND CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123183 | Paninirongan ES | PAMBUJAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-02-06 | 080614S00087 | 14II0035 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-12 | 2014-10-03 | CTC CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123164 | Paysud PS | PALAPAG | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-02-06 | 080614S00126 | 14II0031 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-12 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123002 | Potong Elementary School | LAPINIG | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2945174.43 |  |  | COMPLETED | 1 | 2015-05-19 | 2015-05-19 | 080614S00019 | 14II0049 | 2014-09-24 | 2014-09-26 | 2014-10-14 | 2014-10-30 | 2014-11-14 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 303571 | Potong NHS | LAPINIG | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-10-04 | 2015-10-30 | 080614S00199 | 14II0101 | 2015-01-17 | 2015-01-15 | 2015-01-29 | 2015-02-10 | 2015-03-02 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123111 | Quezon ES | MAPANAS | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-03-20 | 2015-07-02 | 080614S00112 | 14II0022 | 2014-09-24 | 2014-09-26 | 2014-10-14 | 2014-10-30 | 2014-11-14 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 313603 | Rawis National High School | LAOANG | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123037 | Rebong ES | LAS NAVAS | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-03-08 | 080614S00043 | 14II0030 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-12 | 2014-10-03 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122934 | Rizal ES | GAMAY | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-05-31 | 080614S00009 | 14II0027 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-12 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122944 | Rombang ES | LAOANG | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-04-17 | 080614S00003 | 14II0024 | 2014-07-10 | 2014-07-11 | 2014-08-04 | 2014-09-08 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123039 | Roxas ES | LAS NAVAS | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-03-08 | 080614S00098 | 14II0023 | 2014-07-14 | 2014-07-11 | 2014-08-04 | 2014-09-08 | 2014-10-03 | CTC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122891 | Sagudsuron ES | CATUBIG | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-05-10 | 080614S00021 | 14II0028 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-12 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123042 | San Andres PS | LAS NAVAS | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 2 | 2834858.5037 |  |  | COMPLETED | 1 | 2015-07-31 |  | 080614S00148 | 14II0069 | 2014-12-15 | 2014-12-15 | 2014-12-29 | 2015-01-12 | 2015-01-26 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123044 | San Fernando ES | LAS NAVAS | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-05-19 | 2015-10-09 | 080614S00127 | 14II0061 | 2014-09-28 | 2014-09-26 | 2014-10-10 | 2014-10-17 | 2014-11-07 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123045 | San Francisco PS | LAS NAVAS | 2 | 1 | 5 | 1STY 2CL & 1STY 3CL | 2014 K10 BATCH 1 | 4835592 |  |  | COMPLETED | 1 | 2015-05-07 | 2015-09-05 | 080614S00130 | 14II0056 | 2014-07-31 | 2014-07-30 | 2014-08-14 | 2014-09-12 | 2014-10-03 | CTC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 193014 | San Isidro I ES | LAS NAVAS | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-06-26 |  | 080614S00143 | 14II0070 | 2014-10-02 | 2014-10-02 | 2014-10-22 | 2014-11-04 | 2014-11-21 | M SQUARE H CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123046 | San Isidro II ES | LAS NAVAS | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 303579 | San Isidro NHS(LN) | LAS NAVAS | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-06-26 |  | 080614S00144 | 14II0070 | 2014-10-02 | 2014-10-02 | 2014-10-22 | 2014-11-04 | 2014-11-21 | M SQUARE H CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123267 | San Isidro PS | SILVINO LOBOS | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-04-07 |  | 080614S00088 | 14II0018 | 2014-07-10 | 2014-07-11 | 2014-08-04 | 2014-09-08 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY | Abandoned
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123047 | San Jorge ES | LAS NAVAS | 2 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 3940835.14 |  |  | COMPLETED | 1 | 2015-06-01 | 2015-07-15 | 080614S00110 | 14II0060 | 2014-09-28 | 2014-09-26 | 2014-10-10 | 2014-10-30 | 2014-11-27 | NORSAM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123112 | San Jose ES | MAPANAS | 2 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 3940835.14 |  |  | COMPLETED | 1 | 2015-04-07 | 2015-05-10 | 080614S00113 | 14II0040 | 2014-07-29 | 2014-07-30 | 2014-08-18 | 2014-09-12 | 2014-10-03 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123049 | San Miguel ES | LAS NAVAS | 2 | 1 | 6 | 2UNITS 1STY 3CL | 2014 K10 BATCH 1 | 5730348.86 |  |  | COMPLETED | 1 | 2015-06-01 | 2015-12-15 | 080614S00108 | 14II0046 | 2014-09-24 | 2014-09-26 | 2014-10-14 | 2014-10-29 | 2014-11-27 | NORSAM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123184 | San Ramon ES | PAMBUJAN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-03-08 | 080614S00076 | 14II0035 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-12 | 2014-10-03 | CTC CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 313617 | San Vicente National High School | CATUBIG | 2 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8228453.2031 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123165 | Sangay ES | PALAPAG | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-03-08 | 080614S00117 | 14II0031 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-12 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122986 | Sibunot PS | LAOANG | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 2 | 2834858.5037 |  |  | COMPLETED | 1 | 2015-08-30 | 2015-11-10 | 080614S00174 | 14II0074 | 2014-12-15 | 2014-12-15 | 2014-12-29 | 2015-01-12 | 2015-01-26 | NORSATEK ENGINEERING AND CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123113 | Siljagon Elementary School | MAPANAS | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-04-07 | 2015-05-30 | 080614S00114 | 14II0040 | 2014-07-29 | 2014-07-30 | 2014-08-18 | 2014-09-12 | 2014-10-03 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122987 | Simora ES | LAOANG | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-03-08 | 080614S00033 | 14II0030 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-12 | 2014-10-03 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123166 | Simora ES | PALAPAG | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-03-20 | 2015-03-20 | 080614S00124 | 14II0051 | 2014-09-24 | 2014-09-26 | 2014-10-14 | 2014-10-29 | 2014-11-14 | CHRISTFER CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123167 | Sinalaran ES | PALAPAG | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-03-08 | 080614S00122 | 14II0031 | 2014-07-14 | 2014-07-11 | 2014-08-18 | 2014-09-12 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122946 | Son-og ES | LAOANG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1817877.8281 |  |  | COMPLETED | 1 | 2015-06-01 | 2015-07-15 | 080614S00173 | 14II0073 | 2014-10-02 | 2014-10-02 | 2014-10-22 | 2014-11-12 | 2014-11-27 | CTC BUILDER AND SUPPLIES INCORPORATED (FOR. CTC BU
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122947 | Suba ES | LAOANG | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-04-15 | 080614S00008 | 14II0024 | 2014-07-10 | 2014-07-11 | 2014-08-04 | 2014-09-08 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122968 | Tan-awan ES | LAOANG | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-03-08 | 080614S00005 | 14II0025 | 2014-07-10 | 2014-07-11 | 2014-08-04 | 2014-09-08 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122988 | Tarusan PS | LAOANG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-08-30 | 2015-11-05 | 080614S00150 | 14II0074 | 2014-12-15 | 2014-12-16 | 2014-12-29 | 2015-01-12 | 2015-01-26 | NORSATEK ENGINEERING AND CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123053 | Taylor ES | LAS NAVAS | 2 | 1 | 5 | 1STY 2CL & 1STY 3CL | 2014 K10 BATCH 1 | 4835592 |  |  | COMPLETED | 1 | 2015-08-31 |  | 080614S00115 | 14II0057 | 2014-09-28 | 2014-09-26 | 2014-10-10 | 2014-10-30 | 2014-11-27 | NORSAM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123168 | Tinampo ES | PALAPAG | 2 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 3940835.14 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-03-08 | 080614S00121 | 14II0043 | 2014-07-29 | 2014-07-30 | 2014-08-18 | 2014-09-12 | 2014-10-03 | CTC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122893 | Tongodnon PS | CATUBIG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1016980.6756 |  |  | COMPLETED | 1 | 2015-07-31 |  | 080614S00159 | 14II0068 | 2014-12-15 | 2014-12-16 | 2014-12-29 | 2015-01-12 | 2015-01-26 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123186 | Tula ES | PAMBUJAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1817877.8281 |  |  | COMPLETED | 1 | 2015-05-24 |  | 080614S00155 | 14II0071 | 2014-10-02 | 2014-10-02 | 2014-10-22 | 2014-10-31 | 2014-11-19 | JUPA CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 123054 | Victory PS | LAS NAVAS | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-05-02 |  | 080614S00104 | 14II0062 | 2014-09-28 | 2014-09-26 | 2014-10-10 | 2014-10-30 | 2014-11-27 | NORSAM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 122989 | Yabyaban ES | LAOANG | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-05-31 | 080614S00032 | 14II0026 | 2014-07-10 | 2014-08-04 | 2014-08-04 | 2014-09-08 | 2014-10-03 | NRP CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Northern Samar | 313621 | Zoilo T. Lobos Memorial High School | PAMBUJAN | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Ormoc City | 124174 | Cabatoan ES | Ormoc City | 4 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2052000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Ormoc City | 124202 | Cabintan Elementary School | ORMOC CITY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2014-08-30 | 2014-08-30 | 080214S00009 | 14IF0030 | 2014-05-06 | 2014-05-08 | 2014-06-17 | 2014-07-01 | 2014-07-15 | QM BUILDERS
NC 2014 | K10 (2014) | Region VIII | Ormoc City | 124204 | Curva ES | Ormoc City | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1051000 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 080214S00044 | 14IF0051 | 2014-07-16 | 2014-07-18 | 2014-08-05 | 2014-08-08 | 2014-08-19 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Ormoc City | 303654 | Dolores National High School | ORMOC CITY | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Ormoc City | 124206 | Domonar Elementary School | ORMOC CITY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-08-30 | 2014-08-30 | 080214S00010 | 14IF0031 | 2014-05-06 | 2014-05-08 | 2014-06-17 | 2014-07-01 | 2014-07-15 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Ormoc City | 124208 | Esperanza Elementary School | ORMOC CITY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-09-25 | 2014-09-15 | 080214S00012 | 14IF0032 | 2014-07-14 | 2014-07-17 | 2014-07-30 | 2014-08-01 | 2014-08-12 | JA ACHACOSO ENTERPRISES & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Ormoc City | 124209 | Green Valley Elementary School | ORMOC CITY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1167329.12 |  |  | COMPLETED | 1 | 2014-08-30 | 2014-08-30 | 080214S00013 | 14IF0033 | 2014-05-06 | 2014-05-08 | 2014-06-17 | 2014-07-01 | 2014-07-15 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Ormoc City | 124172 | H. Serafica Elementary School (Bayog) | ORMOC CITY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-08-30 | 2014-08-30 | 080214S00019 | 14IF0034 | 2014-05-06 | 2014-05-08 | 2014-06-17 | 2014-07-01 | 2014-07-15 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Ormoc City | 124181 | Juaton Primary School | ORMOC CITY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2014-08-30 | 2014-08-30 | 080214S00018 | 14IF0036 | 2014-05-06 | 2014-05-08 | 2014-06-17 | 2014-07-01 | 2014-07-15 | QM BUILDERS
NC 2014 | K10 (2014) | Region VIII | Ormoc City | 313906 | Julian Gantuangco NHS | ORMOC CITY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Ormoc City | 124158 | Liberty Elementary School | ORMOC CITY | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2120417.57 |  |  | COMPLETED | 1 | 2014-11-11 | 2014-11-11 | 080214S00021 | 14IF0023 | 2014-07-14 | 2014-07-17 | 2014-07-30 | 2014-08-01 | 2014-08-12 | QM BUILDERS
NC 2014 | K10 (2014) | Region VIII | Ormoc City | 124159 | Luna Elementary School | ORMOC CITY | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1975417.57 |  |  | COMPLETED | 1 | 2014-10-14 | 2014-10-14 | 080214S00011 | 14IF0024 | 2014-05-06 | 2014-05-08 | 2014-06-17 | 2014-07-01 | 2014-07-15 | ARCA BUILDERS
NC 2014 | K10 (2014) | Region VIII | Ormoc City | 124164 | Mahayag Elementary School | Ormoc City | 4 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2052000 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 080214S00115 | 14IF0049 | 2014-07-16 | 2014-07-18 | 2014-08-05 | 2014-08-08 | 2014-08-19 | JA ACHACOSO ENTERPRISES & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Ormoc City | 124165 | Mahayahay Elementary School | ORMOC CITY | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2045417.57 |  |  | COMPLETED | 1 | 2014-11-11 | 2014-09-25 | 080214S00020 | 14IF0025 | 2014-07-14 | 2014-07-17 | 2014-07-30 | 2014-08-01 | 2014-08-12 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2014 | K10 (2014) | Region VIII | Ormoc City | 124184 | Manlilinao ES | Ormoc City | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1051000 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 080214S00043 | 14IF0045 | 2014-07-16 | 2014-07-18 | 2014-08-05 | 2014-08-08 | 2014-08-19 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Ormoc City | 124215 | Margen Elementary School | Ormoc City | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041000 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-02 | 080214S00045 | 14IF0046 | 2014-07-16 | 2014-07-18 | 2014-08-05 | 2014-08-08 | 2014-08-19 | ARCA BUILDERS
NC 2014 | K10 (2014) | Region VIII | Ormoc City | 303658 | New Ormoc City National High School | ORMOC CITY | 4 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 3 | 27434390.625 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Ormoc City | 124187 | Nueva Vista Elementary School | ORMOC CITY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | COMPLETED | 1 | 2014-08-30 | 2014-08-30 | 080214S00014 | 14IF0029 | 2014-05-06 | 2014-05-08 | 2014-06-17 | 2014-07-01 | 2014-07-15 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Ormoc City | 313905 | Ormoc City Night High School | ORMOC CITY | 4 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6328664.7656 |  |  | COMPLETED | 1 | 2015-07-17 | 2015-05-21 | 080214S00119 | 14IF0097 | 2014-11-13 | 2014-11-14 | 2014-11-28 | 2014-12-09 | 2015-03-18 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region VIII | Ormoc City | 313902 | Pedro G. Bañez National High School | ORMOC CITY | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Ormoc City | 303660 | Rustico Capahi Sr. Memorial National High School | ORMOC CITY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Ormoc City | 124170 | Sumangga Elementary School | ORMOC CITY | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-08-30 | 2014-08-30 | 080214S00022 | 14IF0028 | 2014-05-06 | 2014-05-08 | 2014-06-17 | 2014-07-01 | 2014-07-15 | RJIR ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123682 | Aurora ES | SAN JORGE | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1874382.5664 |  |  | COMPLETED | 1 | 2015-04-09 | 2015-04-09 | 080414S00271 | 14IJ-0147 | 2014-11-09 | 2014-11-21 | 2014-11-22 | 2014-11-26 | 2014-12-19 | RNMK CONSTRUCTION AND DEVELOPMENT
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123497 | Balocawe PS | GANDARA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1874382.5664 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-05-24 | 080414S00250 | 14IJ-0145(1) | 2014-11-09 | 2014-11-21 | 2014-11-22 |  | 2014-12-19 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123650 | Bangon ES | PAGSANGHAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123683 | Blanca Aurora | SAN JORGE | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1 | 2015-01-04 | 2015-01-04 | 080414S00165 | 14IJ-0085 | 2014-07-16 | 2014-07-28 | 2014-07-29 | 2014-08-29 | 2014-09-15 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123499 | Buao ES | GANDARA | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2779051.9994 |  |  | COMPLETED | 1 | 2015-06-11 | 2015-06-11 | 080414S00251 | 14IJ-0138 | 2014-11-05 | 2014-11-17 | 2014-11-18 | 2014-11-22 | 2014-12-10 | RNMK CONSTRUCTION AND DEVELOPMENT
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 303619 | Buenavista NHS | SAN JORGE | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1854282.5664 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123805 | Cabunga-An ES | SANTO NIÑO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1193847.6807 |  |  | COMPLETED | 1 | 2015-05-31 | 2015-05-31 | 080414S00268 | 14Ij-0139(1) | 2014-11-05 | 2014-11-17 | 2014-11-18 | 2014-11-22 | 2014-12-10 | R.V. CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123840 | Cambatutay Nuevo PS | TARANGNAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1 | 2015-01-01 | 2015-01-01 | 080414S00155 | 14IJ-0093 | 2014-07-24 | 2014-08-05 | 2014-08-06 | 2014-09-08 | 2014-09-12 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123841 | Cambatutay Viejo PS | TARANGNAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-12 | 080414S00209 | 14IJ-0096 | 2014-07-24 | 2014-08-05 | 2014-08-06 | 2014-09-11 | 2014-09-24 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123502 | Caparangasan ES | GANDARA | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3678186.6259 |  |  | COMPLETED | 1 | 2015-06-23 | 2015-06-23 | 080414S00260 | 14IJ-0152 | 2014-11-27 | 2014-12-09 | 2014-12-10 | 2014-12-14 | 2014-12-20 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123747 | Curry ES | SANTA MARGARITA | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2697006.2303 |  |  | COMPLETED | 1 | 2015-04-13 | 2015-04-13 | 080414S00169 | 14IJ-0114(cluster2) | 2014-09-18 | 2014-09-30 | 2014-10-01 | 2014-10-05 | 2014-10-29 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123691 | Erenas ES | SAN JORGE | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 992847.6807 |  |  | COMPLETED | 1 | 2015-05-16 | 2015-05-16 | 080414S00270 | 14IJ-0141(2) | 2014-11-05 | 2014-11-17 | 2014-11-18 | 2014-11-22 | 2014-12-10 | VCD CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123694 | Hernandez PS | SAN JORGE | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1 | 2015-01-14 | 2015-01-14 | 080414S00158 | 14IJ-0090 | 2014-07-24 | 2014-08-05 | 2014-08-06 | 2014-09-11 | 2014-09-27 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 193514 | Hindang PS | SANTA MARGARITA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1 | 2015-04-13 | 2015-04-13 | 080414S00170 | 14IJ-0113(1) | 2014-09-18 | 2014-09-30 | 2014-10-01 | 2014-10-05 | 2014-10-29 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123697 | La Paz ES | SAN JORGE | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1 | 2015-01-04 | 2015-01-04 | 080414S00167 | 14IJ-0086 | 2014-07-16 | 2014-07-28 | 2014-07-29 | 2014-08-29 | 2014-09-15 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123819 | Labangbaybay PS | TAGAPUL-AN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-06-12 | 2015-06-12 | 080414S00221 | 14IJ-0117(2) | 2014-10-17 | 2014-10-29 | 2014-10-30 | 2014-11-03 | 2015-02-08 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123808 | Lobe-Lobe PS | SANTO NIÑO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1193847.6807 |  |  | COMPLETED | 1 | 2015-05-31 | 2015-05-31 | 080414S00267 | 14Ij-0139(3) | 2014-11-05 | 2014-11-17 | 2014-11-18 | 2014-11-22 | 2014-12-10 | R.V. CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123849 | Lucerdoni ES | TARANGNAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1773882.5664 |  |  | COMPLETED | 1 | 2015-04-09 | 2015-04-09 | 080414S00258 | 14IJ-0153 | 2014-12-08 | 2014-12-20 | 2014-12-21 | 2014-12-25 | 2014-12-19 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123514 | Lungib PS | GANDARA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1093347.6807 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-02-23 | 080414S00253 | 14IJ-0144 | 2014-12-04 | 2014-12-16 | 2014-12-17 | 2014-12-21 | 2014-12-19 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123731 | Mabuhay PS | SANTA MARGARITA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1 | 2015-04-13 | 2015-04-13 | 080414S00171 | 14IJ-0133(2) | 2014-09-18 | 2014-10-01 | 2014-10-01 | 2014-10-05 | 2014-10-29 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123295 | Malobago ES | ALMAGRO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1193847.6807 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-03-16 | 080414S00254 | 14IJ-0137(1) | 2014-11-04 | 2014-11-16 | 2014-11-17 | 2014-11-21 | 2014-12-10 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123822 | Mataluto ES | TAGAPUL-AN | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2697006.2303 |  |  | COMPLETED | 1 | 2015-03-13 | 2015-03-13 | 080414S00182 | 14IJ-0117 | 2014-10-05 | 2014-10-17 | 2014-10-18 | 2014-10-22 | 2014-11-07 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123517 | Nalihugan PS | GANDARA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 080414S00166 | 14IJ-0103 | 2014-08-21 | 2014-09-02 | 2014-09-03 | 2014-09-10 | 2014-09-19 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123519 | Natimonan PS | GANDARA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2014-12-17 | 2014-12-17 | 080414S00164 | 14IJ-0089 (1) | 2014-07-24 | 2014-08-05 | 2014-08-06 | 2014-09-08 | 2014-09-12 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123551 | Palambrag PS | GANDARA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2014-12-17 | 2014-12-17 | 080414S00180 | 14IJ-0089 (2) | 2014-07-24 | 2014-08-05 | 2014-08-06 | 2014-09-11 | 2014-09-15 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123656 | Pange ES | PAGSANGHAN | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2728801.9994 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 080414S00262 | 14IJ-0140 | 2014-11-19 | 2014-12-01 | 2014-12-02 | 2014-12-06 | 2014-12-10 | VCD CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123810 | Pinanangnan PS | SANTO NIÑO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2014-11-29 | 2014-11-29 | 080414S00196 | 14IJ-0065 | 2014-07-24 | 2014-08-05 | 2014-08-06 | 2014-09-11 | 2014-09-27 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123825 | Polang Bato ES | TAGAPUL-AN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1093347.6807 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-03-16 | 080414S00266 | 14Ij-0137(2) | 2014-11-05 | 2014-11-17 | 2014-11-18 | 2014-11-22 | 2014-12-10 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123521 | Purog PS | GANDARA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1093347.6807 |  |  | COMPLETED | 1 | 2015-05-24 | 2015-05-24 | 080414S00245 | 14IJ-0145(2) | 2014-11-09 | 2014-11-21 | 2014-11-22 | 2014-11-26 | 2014-12-19 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 303618 | Ramon T. Diaz MHS | GANDARA | 1 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8429453.2031 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123522 | Rawis ES | GANDARA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1924632.5664 |  |  | COMPLETED | 1 | 2015-04-09 | 2015-04-09 | 080414S00255 | 14IJ-0146 | 2014-11-09 | 2014-11-21 |  | 2014-11-26 | 2014-12-20 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 193509 | Rawis PS | SAN JORGE | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 080414S00168 | 14IJ-0065 | 2014-07-16 | 2014-07-28 | 2014-07-29 | 2014-08-29 | 2014-09-15 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123736 | Salvacion PS | SANTA MARGARITA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1 | 2015-04-23 | 2015-04-23 | 080414S00172 | 14IJ-0114 | 2014-09-18 | 2014-09-30 | 2014-10-01 | 2014-10-05 | 2014-10-29 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123525 | San Enrique PS | GANDARA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | Reverted | 0
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123527 | San Isidro PS | GANDARA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1924632.5664 |  |  | Reverted | 0 | 2015-02-23 | 2015-02-23 | 080414S00256 | 14IJ-0144(2) | 2014-11-09 | 2014-11-21 | 2014-11-22 | 2014-11-26 | 2014-12-19 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 313708 | San Jorge NHS | SAN JORGE | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123558 | San Jose ES | GANDARA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1874382.5664 |  |  | COMPLETED | 1 | 2015-04-09 | 2015-04-09 | 080414S00257 | 14IJ-0143 | 2014-11-09 | 2014-11-21 |  | 2014-11-26 | 2014-12-19 | VCD CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123657 | San Luis ES | PAGSANGHAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 080414S00163 | 14IJ-0088 (1) | 2014-07-16 | 2014-07-28 | 2014-07-29 | 2014-09-11 | 2014-09-15 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123559 | San Miguel PS | GANDARA | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2697006.2303 |  |  | COMPLETED | 1 | 2015-06-13 | 2015-06-13 | 080414S00161 | 14IJ-0119 | 2014-10-17 | 2014-10-29 | 2014-10-30 | 2014-11-03 | 2015-01-08 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123709 | Sapinit PS | SAN JORGE | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 992847.6807 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-03-16 | 080414S00269 | 14IJ-0141(1) | 2014-11-05 | 2014-11-17 | 2014-11-18 | 2014-11-22 | 2014-12-10 | VCD CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 303632 | Sto. Nino NHS | SANTO NIÑO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1193847.6807 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123858 | Sto. Nino PS | TARANGNAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2014-12-06 | 2014-12-06 | 080414S00159 | 14IJ-0099 | 2014-08-21 | 2014-09-02 | 2014-09-03 | 2014-09-24 | 2014-10-01 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123859 | Sugod ES | TARANGNAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 080414S00210 | 14IJ-0065 | 2014-07-24 | 2014-08-05 | 2014-08-06 | 2014-09-11 | 2014-09-27 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123563 | Tawiran PS | GANDARA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 080414S00162 | 14IJ-0083 | 2014-07-16 | 2014-07-28 | 2014-07-29 | 2014-08-29 | 2014-09-09 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 313713 | Villahermosa NHS-Pagsanghan NHS Annex | PAGSANGHAN | 1 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 3 | 4603184.5658 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Catbalogan City | 123391 | ALBALATE ES | CATBALOGAN CITY | 2 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2096000 |  |  | COMPLETED | 1 | 2016-02-28 |  | 080414S00179 | 15IK0003 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123756 | ALEGRIA ES | STA. RITA | 2 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2166000 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00186 | 15IK0001 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123963 | Alegria ES | ZUMARRAGA | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-05-25 | 080414S00114 | 14IK 0022 - Cluster XI | 2014-10-07 | 2014-10-21 | 2014-10-21 | 2014-10-29 | 2014-11-03 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123621 | Angyap PS | MOTIONG | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-19 | 2015-07-10 | 080414S00034 | 14IK 0033 - Cluster XXII | 2014-10-16 | 2014-10-29 | 2014-10-29 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123757 | Anibongon ES | SANTA RITA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-05 | 2015-08-05 | 080414S00019 | 14IK 0027 - Cluster XVI | 2014-10-07 | 2014-10-21 | 2014-10-21 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 313716 | Anibongon Integrated School | SANTA RITA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-07-19 | 2015-07-15 | 080414S00107 | 14IK 0027 - Cluster XVI | 2014-10-07 | 2014-10-21 | 2014-10-21 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123909 | Apolonia ES | PARANAS (WRIGHT) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-07-28 | 2015-07-14 | 080414S00130 | 14IK 0040 - Cluster XXIX | 2014-10-30 | 2014-11-13 | 2014-11-13 | 2014-11-24 | 2014-12-01 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123964 | Arteche ES | ZUMARRAGA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-05-09 | 2015-05-09 | 080414S00099 | 14IK 0022 - Cluster XI | 2014-10-07 | 2014-10-21 | 2014-10-21 | 2014-10-29 | 2014-11-03 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123441 | Astorga ES | DARAM | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2016-02-28 |  | 080414S00192 | 15IK0003 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123330 | Bacubac ES | BASEY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-09-28 | 2015-09-28 | 080414S00076 | 14IK 0040 - Cluster XXIX | 2014-10-30 | 2014-11-13 | 2014-11-13 | 2014-11-24 | 2014-12-01 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123775 | Bagolibas ES | SANTA RITA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-06-10 | 080414S00017 | 14IK 0029 - Cluster XVIII | 2014-10-16 | 2014-10-29 | 2014-10-29 | 2014-11-07 | 2014-11-12 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123470 | Bakhaw ES | DARAM | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-12-03 | 080414S00215 | 14IK 0057 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 313709 | Bakhaw NHS | DARAM | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123303 | Balante ES | BASEY | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-11-28 | 2015-11-15 | 080414S00082 | 14IK 0040 - Cluster XXIX | 2014-10-30 | 2014-11-13 | 2014-11-13 | 2014-11-24 | 2014-12-01 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123864 | Bangon ES | VILLAREAL | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-05 | 2015-08-05 | 080414S00116 | 14IK 0024 - Cluster XIII | 2014-10-07 | 2014-10-21 | 2014-10-21 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 313718 | Banquel National High School | VILLAREAL | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123358 | Barobaybay PS | CALBIGA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-11-28 | 2015-11-14 | 080414S00071 | 14IK 0039 -Cluster XXVIII | 2014-10-30 | 2014-11-13 | 2014-11-13 | 2014-11-24 | 2014-12-01 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 303592 | Basey National High School | BASEY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123623 | Bayog ES | MOTIONG | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-05 | 2015-08-05 | 080414S00035 | 14IK 0033 - Cluster XXII | 2014-10-16 | 2014-10-29 | 2014-10-29 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123624 | Beri PS | MOTIONG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2016-02-03 |  | 080414S00201 | 14IK0058 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123566 | Binubucalan PS | HINABANGAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-08-28 | 080414S00193 | 14IK0058 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123965 | Bioso ES | ZUMARRAGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-05-09 | 2015-05-09 | 080414S00091 | 14IK 0022 - Cluster XI | 2014-10-07 | 2014-10-21 | 2014-10-21 | 2014-10-29 | 2014-11-03 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 303595 | Birawan NHS | DARAM | 2 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123445 | Bita-Ug PS | DARAM | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2985174.43 |  |  | COMPLETED | 1 | 2015-08-18 | 2015-07-31 | 080414S00088 | 14IK 0035 - Cluster XXIV | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123625 | Bonga ES | Motiong | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-12-03 | 080414S00204 | 14IK0058 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123713 | Bontod ES | SAN SEBASTIAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-18 | 2015-08-18 | 080414S00011 | 14IK 0034 - Cluster XXIII | 2014-10-23 | 2014-11-06 | 2014-11-13 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123660 | Botoc ES | PINABACDAO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-06-19 | 2015-06-19 | 080414S00038 | 14IK 0031 - Cluster XX | 2014-10-16 | 2014-10-29 | 2014-10-29 | 2014-12-18 | 2014-12-22 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123332 | Buenavista ES | BASEY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-12-28 | 2015-12-28 | 080414S00075 | 14IK 0041 - Cluster XXX | 2014-10-30 | 2014-11-13 | 2014-11-13 | 2014-11-24 | 2014-12-01 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123446 | Buenavista ES | DARAM | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00008 | 14IK 0037 - Cluster XXVI | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123333 | Bulao ES | BASEY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-05 | 2015-08-05 | 080414S00074 | 14IK 0029 - Cluster XVIII | 2014-10-16 | 2014-10-29 | 2014-10-29 | 2014-11-07 | 2014-11-12 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123362 | Bulao PS | CALBIGA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-09-24 | 080414S00212 | 14IK0058 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123363 | Buluan PS | CALBIGA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00070 | 14IK 0039 -Cluster XXVIII | 2014-10-30 | 2014-11-13 | 2014-11-13 | 2014-11-24 | 2014-12-01 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123867 | Burabod PS | VILLAREAL | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-12-03 | 080414S00151 | 14IK 0057 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123471 | Burgos ES | DARAM | 2 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1 | 2015-12-18 | 2015-12-18 | 080414S00043 | 14IK 0037 - Cluster XXVI | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 303593 | Burgos IS | BASEY | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123778 | Cabacungan ES | SANTA RITA | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-08-19 | 2015-08-19 | 080414S00018 | 14IK 0027 - Cluster XVI | 2014-10-07 | 2014-10-21 | 2014-10-21 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 193512 | Cabadsan PS | VILLAREAL | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-12-03 | 080414S00152 | 14IK 0057 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123569 | Cabang PS | HINABANGAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00194 | 14IK0058 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123473 | Cabiton-An ES | DARAM | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00031 | 14IK 0036 - Cluster XXV | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 313720 | Cabiton-an Integrated School | DARAM | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00109 | 14IK 0036 - Cluster XXV | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123760 | Cabungaan ES | SANTA RITA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2697006.2303 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-09-15 | 080414S00242 | 15IK0004 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123474 | Cagutsan PS | DARAM | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00042 | 14IK 0036 - Cluster XXV | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123662 | Calampong ES | PINABACDAO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-07-19 | 2015-07-19 | 080414S00003 | 14IK 0031 - Cluster XX | 2014-10-16 | 2014-10-29 | 2014-10-29 | 2014-12-18 | 2014-12-22 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123627 | Calapi ES | MOTIONG | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-07-19 | 2015-07-13 | 080414S00036 | 14IK 0033 - Cluster XXII | 2014-10-16 | 2014-10-29 | 2014-10-29 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123366 | Calingonan ES | CALBIGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-09-28 | 2015-09-28 | 080414S00069 | 14IK 0039 -Cluster XXVIII | 2014-10-30 | 2014-11-13 | 2014-11-13 | 2014-11-24 | 2014-12-01 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123968 | Camayse PS | ZUMARRAGA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00137 | 15IK0003 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123868 | Cambaguio ES | VILLAREAL | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-05 | 2015-08-05 | 080414S00112 | 14IK 0024 - Cluster XIII | 2014-10-07 | 2014-10-21 | 2014-10-21 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123335 | Cambayan ES | BASEY | 2 | 1 | 3 | 3U-1STY1CL | 2014 K10 BATCH 2 | 3149000 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-10-22 | 080414S00177 | 15IK0001 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123451 | Cambuhay PS | DARAM | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2015-10-18 | 2015-10-18 | 080414S00007 | 14IK 0035 - Cluster XXIV | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123452 | Campelipa PS | DARAM | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2015-10-18 | 2015-10-18 | 080414S00006 | 14IK 0035 - Cluster XXIV | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123716 | Campiyak PS | SAN SEBASTIAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-08-18 | 2015-08-18 | 080414S00012 | 14IK 0034 - Cluster XXIII | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123914 | Campo-Uno PS | PARANAS (WRIGHT) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-07-28 | 2015-07-14 | 080414S00129 | 14IK 0040 - Cluster XXIX | 2014-10-30 | 2014-11-13 | 2014-11-13 | 2014-11-24 | 2014-12-01 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123937 | Can-Aponte PS | SAN JOSE DE BUAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-12-15 | 2015-12-15 | 080414S00123 | 15IK0005 | 2015-04-27 | 2015-05-11 | 2015-05-11 | 2015-05-18 | 2015-05-20 | By Administration
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123337 | Cancaiyas ES | BASEY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-10-24 | 080414S00211 | 15IK0004 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123585 | Candayao PS | JIABONG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-08-31 | 080414S00205 | 14IK0058 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123477 | CANLOLOY ES | DARAM | 2 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2196000 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-10-24 | 080414S00189 | 14IK 0057 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123915 | Cantaguic PS | PARANAS (WRIGHT) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-12-03 | 080414S00207 | 14IK 0057 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123916 | Cantao-An PS | PARANAS (WRIGHT) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00156 | 15IK0003 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123586 | Cantongtong ES | JIABONG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-09-28 | 080414S00197 | 15IK0004 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123609 | CANYOYO ES | MARABUT | 2 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2106000 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-11-16 | 080414S00181 | 15IK0001 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123633 | Caranas ES | MOTIONG | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-07-19 | 2015-07-14 | 080414S00037 | 14IK 0033 - Cluster XXII | 2014-10-16 | 2014-10-29 | 2014-10-29 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 303598 | Casandig NHS | PARANAS (WRIGHT) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123587 | Casapa ES | JIABONG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-10-30 | 080414S00190 | 14IK0058 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 313711 | Casapa NHS-Jiabong NHS Annex | JIABONG | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123313 | Catadman ES | BASEY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-06-10 | 080414S00081 | 14IK 0029 - Cluster XVIII | 2014-10-16 | 2014-10-29 | 2014-10-29 | 2014-11-07 | 2014-11-12 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123871 | Conant PS | VILLAREAL | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-10-23 | 080414S00153 | 14IK 0057 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123571 | Concord ES | HINABANGAN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-12-18 | 2015-12-18 | 080414S00026 | 14IK 0034 - Cluster XXIII | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123589 | Cristina PS | JIABONG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-10-28 | 080414S00199 | 14IK0058 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123665 | Dolores PS | PINABACDAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-10-30 | 080414S00140 | 15IK0002 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123610 | Ferreras ES | MARABUT | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-05-10 | 2015-03-25 | 080414S00044 | 14IK 0032 - Cluster XXI | 2014-10-16 | 2014-10-29 | 2014-10-29 | 2014-11-07 | 2014-11-12 | RICHMARK CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123371 | Guimbanga PS | CALBIGA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-12-03 | 080414S00222 | 14IK0058 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123454 | Guintampilan PS | DARAM | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2015-10-18 | 2015-10-18 | 080414S00005 | 14IK 0037 - Cluster XXVI | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 303605 | Guintarcan NHS | VILLAREAL | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123315 | Guirang ES | BASEY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-11-28 | 2015-11-15 | 080414S00080 | 14IK 0041 - Cluster XXX | 2014-10-30 | 2014-11-13 | 2014-11-13 | 2014-11-24 | 2014-12-01 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123943 | Gusa PS | SAN JOSE DE BUAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-12-08 | 2015-12-08 | 080414S00125 | 15IK0005 | 2015-04-27 | 2015-05-11 | 2015-06-09 | 2015-06-26 | 2015-07-08 | By Administration
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123946 | Hiduroma PS | SAN JOSE DE BUAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-08-19 | 2015-07-20 | 080414S00143 | 15IK0005 | 2015-04-27 | 2015-05-11 | 2015-05-11 | 2015-05-18 | 2015-05-20 | By Administration
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123947 | Hilumot PS | SAN JOSE DE BUAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-08-20 | 2015-07-23 | 080414S00144 | 15IK0005 | 2015-04-27 | 2015-05-11 | 2015-05-11 | 2015-05-18 | 2015-05-20 | By Administration
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123767 | Hinangutdan ES | SANTA RITA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-19 | 2015-08-19 | 080414S00014 | 14IK 0028 - Cluster XVII | 2014-10-16 | 2014-10-29 | 2014-10-29 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123782 | Hita-as PS | SANTA RITA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00148 | 15IK0004 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123874 | Igot ES | VILLAREAL | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-07-19 | 2015-07-10 | 080414S00118 | 14IK 0025 - Cluster XIV | 2014-10-07 | 2014-10-21 | 2014-10-21 | 2014-12-18 | 2014-12-22 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 303607 | Igot NHS | VILLAREAL | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-05 | 2015-08-05 | 080414S00111 | 14IK 0025 - Cluster XIV | 2014-10-07 | 2014-10-21 | 2014-10-21 | 2014-12-18 | 2014-12-22 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123894 | Inarumbacan ES | VILLAREAL | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-08-05 | 2015-08-05 | 080414S00133 | 14IK 0025 - Cluster XIV | 2014-10-07 | 2014-10-21 | 2014-10-21 | 2014-12-18 | 2014-12-22 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 303608 | Independencia NHS | TALALORA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123720 | Inobongan ES | SAN SEBASTIAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-08-20 | 2015-07-22 | 080414S00147 | 15IK0005 | 2015-04-27 | 2015-05-11 | 2015-05-11 | 2015-05-18 | 2015-05-20 | By Administration
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123592 | Jia-an ES | Jiabong | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-08-03 | 080414S00195 | 15IK0004 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 303609 | Jiabong NHS | JIABONG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123948 | L.C. Fernandez PS | SAN JOSE DE BUAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-08 | 2015-11-25 | 080414S00135 | 15IK0005 | 2015-04-27 | 2015-05-11 | 2015-06-09 | 2015-06-26 | 2015-07-08 | By Administration
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 303610 | Lawaan NHS | PARANAS (WRIGHT) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-07-28 | 2015-07-10 | 080414S00090 | 14IK 0040 - Cluster XXIX | 2014-10-30 | 2014-11-13 | 2014-11-13 | 2014-11-24 | 2014-12-01 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123612 | LEGASPI ES | MARABUT | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1053000 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-12-03 | 080414S00174 | 15IK0001 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Catbalogan City | 123399 | Libas PS | CATBALOGAN (Capital) | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2697006.2303 |  |  | COMPLETED | 1 | 2016-02-28 |  | 080414S00219 | 15IK0003 | 2015-03-06 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123637 | Linonoban PS | MOTIONG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-12-03 | 080414S00202 | 14IK0058 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123485 | Losa ES | DARAM | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-08-18 | 2015-07-31 | 080414S00015 | 14IK 0035 - Cluster XXIV | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123595 | Lulugayan ES | JIABONG | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-08-18 | 2015-07-12 | 080414S00029 | 14IK 0034 - Cluster XXIII | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123970 | Lumalantang ES | ZUMARRAGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-05-09 | 2015-05-09 | 080414S00092 | 14IK 0023 - Cluster XII | 2014-10-07 | 2014-10-21 | 2014-10-21 | 2014-10-29 | 2014-11-03 | BLACK NAZARENE BUILDERS & ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123486 | Mabini PS | DARAM | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-08-18 | 2015-06-03 | 080414S00041 | 14IK 0035 - Cluster XXIV | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123455 | Macalpe PS | DARAM | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00213 | 14IK 0057 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123672 | Magdawat PS | PINABACDAO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-08-19 | 2015-08-19 | 080414S00009 | 14IK 0031 - Cluster XX | 2014-10-16 | 2014-10-29 | 2014-10-29 | 2014-12-18 | 2014-12-22 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123786 | Magsaysay ES | SANTA RITA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-07-05 | 2015-07-05 | 080414S00065 | 14IK 0027 - Cluster XVI | 2014-10-07 | 2014-10-21 | 2014-10-21 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123378 | Malabal ES | CALBIGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-10-28 | 2015-10-28 | 080414S00068 | 14IK 0039 -Cluster XXVIII | 2014-10-30 | 2014-11-13 | 2014-11-13 | 2014-11-24 | 2014-12-01 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123787 | Maligaya ES | SANTA RITA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-05 | 2015-08-05 | 080414S00110 | 14IK 0028 - Cluster XVII | 2014-10-16 | 2014-10-29 | 2014-10-29 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123597 | Malino ES | JIABONG | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-18 | 2015-07-10 | 080414S00030 | 14IK 0034 - Cluster XXIII | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123880 | MALONOY ES | VILLAREAL | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1083000 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-10-30 | 080414S00188 | 14IK 0057 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123674 | Manaing PS | PINABACDAO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-19 | 2015-08-19 | 080414S00010 | 14IK 0031 - Cluster XX | 2014-10-16 | 2014-10-29 | 2014-10-29 | 2014-12-18 | 2014-12-22 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123487 | Mandoyucan PS | DARAM | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2015-08-18 | 2015-07-31 | 080414S00040 | 14IK 0035 - Cluster XXIV | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Catbalogan City | 123402 | Manguehay PS | CATBALOGAN (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1 | 2016-02-28 |  | 080414S00220 | 15IK0003 | 2015-03-06 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123640 | Mararangsi PS | MOTIONG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-12-03 | 080414S00203 | 14IK0058 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123457 | Marupangdan ES | DARAM | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2985174.43 |  |  | COMPLETED | 1 | 2015-08-18 | 2015-08-18 | 080414S00004 | 14IK 0037 - Cluster XXVI | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123488 | Mayabay ES | DARAM | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2015-08-18 | 2015-07-31 | 080414S00039 | 14IK 0035 - Cluster XXIV | 2014-10-23 | 2014-11-13 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123345 | May-It ES | BASEY | 2 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-06-10 | 080414S00073 | 14IK 0032 - Cluster XXI | 2014-10-23 | 2014-10-29 | 2014-10-29 | 2014-11-07 | 2014-11-12 | RICHMARK CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123921 | Minarog PS | PARANAS (WRIGHT) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00138 | 15IK0003 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123577 | Mogdo ES | HINABANGAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-11-18 | 2015-11-15 | 080414S00027 | 14IK 0034 - Cluster XXIII | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123975 | Mombon PS | ZUMARRAGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-05-09 | 2015-05-09 | 080414S00093 | 14IK 0023 - Cluster XII | 2014-10-07 | 2014-10-21 | 2014-10-21 | 2014-10-29 | 2014-11-03 | BLACK NAZARENE BUILDERS & ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123489 | Mongolbongol ES | DARAM | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-09-18 | 2015-09-18 | 080414S00021 | 14IK 0036 - Cluster XXV | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-11-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 303602 | Mualbual IS | ZUMARRAGA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123675 | Nabong ES | PINABACDAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00141 | 15IK0002 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123898 | Navatas Daku ES | TALALORA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-15 | 2015-10-15 | 080414S00150 | 15IK0004 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123899 | Navatas Guti Elementary School | TALALORA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-07-19 | 2015-07-19 | 080414S00132 | 14IK 0026 - Clsuter XV | 2014-10-07 | 2014-10-21 | 2014-10-21 | 2014-12-18 | 2014-12-22 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123788 | New Manunca PS | SANTA RITA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-09-25 | 080414S00208 | 15IK0004 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123347 | New San Agustin ES | BASEY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1043000 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-12-03 | 080414S00178 | 15IK0002 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123790 | Old Manunca ES | SANTA RITA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-19 | 2015-08-13 | 080414S00117 | 14IK 0028 - Cluster XVII | 2014-10-16 | 2014-10-29 | 2014-10-29 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123769 | ORMOCANAY ES | STA. RITA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1103000 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-09-30 | 080414S00187 | 14IK 0057 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 303614 | OSMEŇA NHS | MARABUT | 2 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2126000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123923 | Pagsaogan PS | PARANAS (WRIGHT) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00136 | 15IK0003 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123883 | Pangpang PS | VILLAREAL | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-05 | 2015-08-05 | 080414S00119 | 14IK 0024 - Cluster XIII | 2014-10-07 | 2014-10-21 | 2014-10-21 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123320 | Panugmonon ES | BASEY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123320 | PANUGMUNON ES | BASEY | 2 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2116000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123679 | Pelaon PS | PINABACDAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00142 | 14IK 0057 | 2015-02-09 | 2015-02-13 | 2015-02-13 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123616 | Pinalangga ES | MARABUT | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-05-10 | 2015-03-25 | 080414S00032 | 14IK 0032 - Cluster XXI | 2014-10-16 | 2014-10-29 | 2014-10-29 | 2014-11-07 | 2014-11-12 | RICHMARK CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123901 | Placer Elem. School | TALALORA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-07-19 | 2015-07-19 | 080414S00131 | 14IK 0026 - Clsuter XV | 2014-10-07 | 2014-10-21 | 2014-10-21 | 2014-12-18 | 2014-12-22 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 313702 | Plaridel NHS | VILLAREAL | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123459 | Pondang ES | DARAM | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00001 | 14IK 0037 - Cluster XXVI | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123460 | Poso ES | DARAM | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-10-18 | 2015-10-18 | 080414S00013 | 14IK 0037 - Cluster XXVI | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123436 | Pupua ES | CATBALOGAN (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00198 | 15IK0003 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 303640 | Quintin Quijano Sr. Agricultural School | PINABACDAO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123322 | Rawis ES | BASEY | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-11-28 | 2015-11-14 | 080414S00078 | 14IK 0041 - Cluster XXX | 2014-10-30 | 2014-11-13 | 2014-11-13 | 2014-11-24 | 2014-12-01 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123384 | Rawis PS | CALBIGA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-11-27 | 080414S00216 | 15IK0002 | 2015-03-06 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123954 | Salay PS | PARANAS (WRIGHT) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00145 | 15IK0003 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123324 | SAN FERNANDO ES | BASEY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1043000 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-11-15 | 080414S00176 | 15IK0002 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123385 | San Ignacio | CALBIGA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00214 | 15IK0002 | 2015-03-06 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123926 | San Isidro ES | PARANAS (WRIGHT) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-07-28 | 2015-07-14 | 080414S00128 | 14IK 0040 - Cluster XXIX | 2014-10-30 | 2014-11-13 | 2014-11-13 | 2014-11-24 | 2014-12-01 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 313721 | San Isidro NHS-Zumarraga NHS Annex | ZUMARRAGA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123491 | San Jose ES | DARAM | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-11-18 | 2015-11-15 | 080414S00022 | 14IK 0037 - Cluster XXVI | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123887 | San Lorenzo - Lawaan PS | VILLAREAL | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-12-03 | 080414S00157 | 14IK 0057 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123957 | San Nicolas ES | SAN JOSE DE BUAN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-12-08 | 2015-12-08 | 080414S00127 | 15IK0005 | 2015-04-27 | 2015-05-11 | 2015-06-09 | 2015-06-26 | 2015-07-08 | By Administration
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123796 | San Pedro ES | SANTA RITA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-06-10 | 080414S00115 | 14IK 0029 - Cluster XVIII | 2014-10-16 | 2014-10-29 | 2014-10-29 | 2013-11-01 | 2014-11-12 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123958 | San Pedro PS | SAN JOSE DE BUAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-15 | 2015-11-19 | 080414S00146 | 15IK0005 | 2015-04-27 | 2015-05-11 | 2015-05-11 | 2015-05-18 | 2015-05-20 | By Administration
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123579 | San Rafael ES | HINABANGAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00028 | 14IK 0034 - Cluster XXIII | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123888 | San Rafael ES | VILLAREAL | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-05 | 2015-08-05 | 080414S00120 | 14IK 0025 - Cluster XIV | 2014-10-07 | 2014-10-21 | 2014-10-21 | 2014-12-18 | 2014-12-22 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123464 | San Roque ES | DARAM | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2015-08-18 | 2015-07-31 | 080414S00033 | 14IK 0035 - Cluster XXIV | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123618 | SAN ROQUE ES | MARABUT | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1053000 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-11-15 | 080414S00183 | 15IK0001 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 303627 | San Sebastian NHS | SAN SEBASTIAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123493 | Saugan ES | DARAM | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2016-02-28 |  | 080414S00191 | 15IK0003 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123798 | Sta. Elena ES | SANTA RITA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-08-05 | 2015-08-05 | 080414S00124 | 14IK 0028 - Cluster XVII | 2014-10-16 | 2014-10-16 | 2014-10-29 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123799 | Sta. Rita II CES | SANTA RITA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-09-25 | 080414S00149 | 15IK0004 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | B. VICENCIO CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 303631 | Sta. Rita NHS | SANTA RITA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123889 | Sta. Rosa PS | VILLAREAL | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-05 | 2015-08-05 | 080414S00121 | 14IK 0024 - Cluster XIII | 2014-10-07 | 2014-10-21 | 2014-10-21 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123890 | Sto. Nino ES | VILLAREAL | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-07-19 | 2015-07-15 | 080414S00122 | 14IK 0026 - Clsuter XV | 2014-10-07 | 2014-10-21 | 2014-10-21 | 2014-12-18 | 2014-12-22 | JFR CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123494 | Sua ES | DARAM | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00023 | 14IK 0036 - Cluster XXV | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 303603 | Sua NHS | DARAM | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123388 | Tabuk ES | CALBIGA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1858463.5751 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00206 | 15IK0002 | 2015-02-09 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123773 | Tagacay ES | SANTA RITA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-05 | 2015-08-05 | 080414S00002 | 14IK 0028 - Cluster XVII | 2014-10-16 | 2014-10-29 | 2014-10-29 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123389 | Timbangan PS | CALBIGA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00217 | 15IK0002 | 2015-03-06 | 2015-03-17 | 2015-03-17 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123620 | TINABANAN ES | MARABUT | 2 | 1 | 2 | 2U-1STY1CL | 2014 K10 BATCH 2 | 2086000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123620 | Tinabanan ES | MARABUT | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123354 | Tinaogan ES | BASEY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-11-28 | 2015-11-15 | 080414S00072 | 14IK 0041 - Cluster XXX | 2014-10-30 | 2014-11-13 | 2014-11-13 | 2014-11-24 | 2014-12-01 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123891 | Tomabe PS | VILLAREAL | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-07-19 | 2015-07-15 | 080414S00126 | 14IK 0024 - Cluster XIII | 2014-10-07 | 2014-10-21 | 2014-10-21 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123495 | Tugas ES | DARAM | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2016-01-31 |  | 080414S00024 | 14IK 0036 - Cluster XXV | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123496 | Ubo PS | DARAM | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-10-18 | 2015-10-18 | 080414S00025 | 14IK 0035 - Cluster XXIV | 2014-10-23 | 2014-11-06 | 2014-11-06 | 2014-12-18 | 2014-12-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123892 | Ulayan PS | VILLAREAL | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-07-19 | 2015-07-19 | 080414S00134 | 14IK 0025 - Cluster XIV | 2014-10-07 | 2014-10-21 | 2014-10-21 | 2014-12-18 | 2014-12-22 | MAGA CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 193519 | upper minata ps | CALBIGA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1042719.877 |  |  | COMPLETED | 1 | 2016-02-28 |  | 080414S00218 | 14IK0058 | 2015-01-19 | 2015-01-21 | 2015-02-03 | 2015-03-24 | 2015-04-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region VIII | Samar (Western Samar) | 123327 | Villa Aurora ES | BASEY | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-11-28 | 2015-11-12 | 080414S00089 | 14IK 0041 - Cluster XXX | 2014-10-30 | 2014-11-13 | 2014-11-13 | 2014-11-24 | 2014-12-01 | RHYES BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122053 | BALAGAWAN ELEMENTARY SCHOOL | SILAGO | 0 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 080314S00006 | 14-IL-0055 | 2014-06-29 | 2014-07-02 | 2014-07-15 | 2014-08-12 | 2014-08-25 | 888 ACY ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122024 | Biasong Primary School | HINUNANGAN | 0 | 1 | 2 | 2UNITS 1STY 1CL | 2014 K10 BATCH 1 | 2184658.24 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-30 | 080314S00019 | 14-IL-0051 | 2014-06-29 | 2014-07-02 | 2014-07-15 | 2014-08-12 | 2014-08-25 | 888 ACY ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122248 | Bobon Elementary School | SAN JUAN (CABALIAN) | 0 | 1 | 3 | 1STY 1CL & 1STY 2CL | 2014 K10 BATCH 1 | 3062746.69 |  |  | COMPLETED | 1 | 2015-01-03 | 2015-01-03 | 080314S00010 | 14-IL-00010 | 2014-06-24 | 2014-07-02 | 2014-08-13 | 2014-08-22 | 2014-09-01 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122284 | Bolod-Bolod E/S | SAINT BERNARD | 0 | 1 | 4 | 1STY 1CL & 1STY 3CL | 2014 K10 BATCH 1 | 3987503.55 |  |  | COMPLETED | 1 | 2014-12-29 | 2015-01-15 | 080314S00012 | 14-IL-0048 | 2014-06-29 | 2014-07-02 | 2014-07-15 | 2014-08-12 | 2014-08-25 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122089 | Bongawisan Elementary School | SAN FRANCISCO | 0 | 1 | 5 | 1STY 1CL & 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 5033164.26 |  |  | COMPLETED | 1 | 2014-12-29 | 2015-03-31 | 080314S00029 | 14-IL-0059 | 2014-06-29 | 2014-07-02 | 2014-07-15 | 2014-08-12 | 2014-08-25 | Z.A.S. CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 192020 | Dan-an Primary School | PINTUYAN | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2014-12-04 | 2014-12-04 | 080314S00013 | 14-IL-00013 | 2014-06-29 | 2014-07-02 | 2014-08-15 | 2014-08-22 | 2014-09-01 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 303447 | Hinunangan National High School(Canipaan NHS - Hinunangan Annex) | HINUNANGAN | 0 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122220 | Laca Primary School | PADRE BURGOS | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 080314S00001 | 14-IL-0045 | 2014-07-30 | 2014-07-31 | 2014-09-04 | 2014-09-12 | 2014-09-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 313409 | Liloan National Technical Vocational High School | LILOAN | 0 | 1 | 5 | 1STY5CL | 2014 K10 BATCH 3 | 4056617.0242 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122011 | Malbago Elementary School | BONTOC | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 080314S00009 | 14-IL-0047 | 2014-06-29 | 2014-09-04 | 2014-09-04 | 2014-09-12 | 2014-09-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122039 | Matin-ao Primary School | HINUNANGAN | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 080314S00004 | 14-IL-00004 | 2014-07-30 | 2014-07-31 | 2014-09-04 | 2014-09-12 | 2014-09-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122045 | Pondol Elementary School | HINUNANGAN | 0 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 080314S00002 | 14-IL-00002 | 2014-06-29 | 2014-07-02 | 2014-07-15 | 2014-08-12 | 2014-08-25 | 888 ACY ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122112 | San Isidro Elementary School | LILOAN | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 080314S00016 | 14-IL-0058 | 2014-06-29 | 2014-07-01 | 2014-09-04 | 2014-09-12 | 2014-09-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 303486 | Silago NVHS | SILAGO | 0 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122253 | Somoje ES | SAN JUAN (CABALIAN) | 0 | 1 | 3 | 1STY 1CL & 1STY 2CL | 2014 K10 BATCH 1 | 3062746.69 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 080314S00011 | 14-IL-00011 | 2014-06-29 | 2014-07-01 | 2014-09-04 | 2014-09-12 | 2014-09-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122115 | Sudmon Elementary School | SAN FRANCISCO | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 080314S00030 | 14-IL-0060 | 2014-06-29 | 2014-07-01 | 2014-09-04 | 2014-09-12 | 2014-09-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122217 | Timba Elementary School | MALITBOG | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-11-29 | 2014-11-29 | 080314S00008 | 14-IL-00008 | 2014-06-29 | 2014-07-02 | 2014-07-15 | 2014-08-12 | 2014-08-25 | AQUA JUN BUILDERS
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122061 | Tubod Elementary School | SILAGO | 0 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 3980835.14 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 080314S00007 | 14-IL-0056 | 2014-06-29 | 2014-07-02 | 2014-07-15 | 2014-08-12 | 2014-08-25 | Z.A.S. CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122062 | Amaga Elementary School | HINUNDAYAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-09-30 | 080314S00036 | 14-IL-0103 | 2014-11-10 | 2014-11-10 | 2014-11-25 | 2014-12-05 | 2014-12-12 | VCD CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122023 | Ambacon Primary School | HINUNANGAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-08-31 | 080314S00040 | 14-IL-0105 | 2014-11-10 | 2014-11-10 | 2014-11-25 | 2014-12-05 | 2014-12-12 | VCD CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122308 | Anahawan ES | TOMAS OPPUS | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-02-28 | 2015-09-30 | 080314S00068 | 14-IL-0082 | 2014-09-24 | 2014-09-26 | 2014-10-02 | 2014-11-06 | 2014-11-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122200 | Aurora Elementary School | MALITBOG | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-04-08 | 2015-09-30 | 080314S00050 | 14-IL-0078 | 2014-11-10 | 2014-11-10 | 2014-12-17 | 2014-12-26 | 2015-01-05 | SAL CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122088 | Bahay Elementary School | LILOAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-09 | 080314S00032 | 14-IL-0091 | 2014-11-10 | 2014-11-10 | 2014-12-17 | 2014-12-26 | 2015-01-05 | RNMK CONSTRUCTION AND DEVELOPMENT
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 192014 | Bantawon ES | SAINT BERNARD | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-09-30 | 080314S00056 | 14-IL-0094 | 2014-11-10 | 2014-11-10 | 2014-11-25 | 2014-12-05 | 2014-12-12 | VCD CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122247 | Basak Elementary School | SAN JUAN (CABALIAN) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-09-30 | 080314S00052 | 14-IL-0098 | 2014-11-10 | 2014-11-10 | 2014-12-17 | 2014-12-26 | 2015-01-05 | SAL CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 121998 | Bunga Elementary School | BONTOC | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-02-28 | 2015-03-16 | 080314S00042 | 14-IL-0084 | 2014-09-24 | 2014-09-26 | 2014-10-28 | 2014-11-06 | 2014-11-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122309 | Cabascan Elementary School | TOMAS OPPUS | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-02-28 | 2015-09-30 | 080314S00049 | 14-IL-0080 | 2014-09-24 | 2014-09-26 | 2014-10-28 | 2014-11-06 | 2014-11-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122091 | Cagbungalon Elementary School | LILOAN | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1815241.6956 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-03-30 | 080314S00033 | 14-IL-0089 | 2014-09-24 | 2014-09-26 | 2014-10-28 | 2014-11-06 | 2014-11-26 | 888 ACY ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 192001 | Calinta-an Elementary School | HINUNDAYAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-02-28 | 2015-03-16 | 080314S00035 | 14-IL-0100 | 2014-09-24 | 2014-09-26 | 2014-10-28 | 2014-11-06 | 2014-11-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 192009 | Candayuman Primary School | LILOAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-02-28 | 2015-03-16 | 080314S00039 | 14-IL-0106 | 2014-09-24 | 2014-09-26 | 2014-10-28 | 2014-11-06 | 2014-11-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122204 | Cantamuac Primary School | MALITBOG | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-09-29 | 080314S00063 | 14-IL-0079 | 2014-11-10 | 2014-11-10 | 2014-12-17 | 2014-12-26 | 2015-01-05 | SAL CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 192031 | Cat-iwing Primary School | HINUNDAYAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-02-28 | 2015-02-28 | 080314S00037 | 14-IL-0101 | 2014-09-24 | 2014-09-26 | 2014-10-28 | 2014-11-06 | 2014-11-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122249 | Dayanog Elementary School | SAN JUAN (CABALIAN) | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1815241.6956 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-09-29 | 080314S00060 | 14-IL-0097 | 2014-09-24 | 2014-09-26 | 2014-10-28 | 2014-11-06 | 2014-11-26 | 888 ACY ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122207 | Guinabonan Elementary School | MALITBOG | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-09-30 | 080314S00064 | 14-IL-0075 | 2014-11-10 | 2014-11-10 | 2014-12-17 | 2014-12-26 | 2015-01-05 | JT PAREDES CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122317 | Hugpa PS | TOMAS OPPUS | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-02-28 | 2015-09-29 | 080314S00044 | 14-IL-0081 | 2014-09-24 | 2014-09-26 | 2014-10-28 | 2014-11-06 | 2014-11-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122266 | Kanangkaan Elementary School | SOGOD | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-02-28 | 2015-06-16 | 080314S00071 | 14-IL-0088 | 2014-09-24 | 2014-09-26 | 2014-10-28 | 2014-11-06 | 2014-11-26 | 888 ACY ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122208 | Kauswagan Elementary School | MALITBOG | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-09-29 | 080314S00065 | 14-IL-0074 | 2014-11-10 | 2014-11-10 | 2014-12-17 | 2014-12-26 | 2015-01-05 | JT PAREDES CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122267 | Kauswagan ES | SOGOD | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1815241.6956 |  |  | Reverted | 0
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 192030 | Mahika ES | SAINT BERNARD | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-09-29 | 080314S00057 | 14-IL-0095 | 2014-11-10 | 2014-11-10 | 2014-11-25 | 2014-12-05 | 2014-12-12 | VCD CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122211 | Maningning Primary School | MALITBOG | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-09-29 | 080314S00062 | 14-IL-0077 | 2014-11-10 | 2014-11-10 | 2014-12-17 | 2014-12-26 | 2015-01-05 | SAL CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 192008 | Navalita Elementary School | HINUNDAYAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-02-28 | 2015-02-28 | 080314S00034 | 14-IL-0102 | 2014-09-24 | 2014-09-26 | 2014-10-28 | 2014-11-06 | 2014-11-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122274 | Pancho Villa Elementary School | SOGOD | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-02-28 | 2015-06-16 | 080314S00070 | 14-IL-0087 | 2014-09-24 | 2014-09-26 | 2014-10-28 | 2014-11-06 | 2014-11-26 | 888 ACY ENTERPRISES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122107 | Pandan Elementary School | LILOAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-09 | 080314S00054 | 14-IL-0090 | 2014-11-10 | 2014-11-10 | 2014-12-17 | 2014-12-26 | 2015-01-05 | RNMK CONSTRUCTION AND DEVELOPMENT
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122017 | Pangi Primary School | BONTOC | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-02-28 | 2015-06-16 | 080314S00041 | 14-IL-0083 | 2014-09-24 | 2014-09-26 | 2014-10-28 | 2014-11-06 | 2014-11-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122193 | San Isidro Elementary School | Macrohon | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1815241.6956 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-08-29 | 080314S00055 | 14-IL-0073 | 2014-09-24 | 2014-09-26 | 2014-10-28 | 2014-11-06 | 2014-11-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122242 | San Ramon Elementary School | SAN RICARDO | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-06-30 | 080314S00061 | 14-IL-0092 | 2014-11-10 | 2014-11-10 | 2014-11-25 | 2014-12-05 | 2014-12-12 | VCD CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 192003 | Sogod SPED Center | Sogod | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1815241.6956 |  |  | reverted | 0
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122303 | Sta. Cruz ES | SAINT BERNARD | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-03-16 |  | 080314S00058 | 14-IL-0096 | 2014-11-10 | 2014-11-10 | 2014-11-25 | 2014-12-05 | 2014-12-12 | VCD CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122255 | Sua ES | SAN JUAN (CABALIAN) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-09-30 | 080314S00059 | 14-IL-0099 | 2014-11-10 | 2014-11-10 | 2014-12-17 | 2014-12-26 | 2015-01-05 | SAL CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122307 | Tambis II PS | SAINT BERNARD | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1815241.6956 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-08-31 | 080314S00053 | 14-IL-0093 | 2014-11-10 | 2014-11-10 | 2014-11-25 | 2014-01-05 | 2014-12-12 | VCD CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122050 | Tawog Primary School | HINUNANGAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-08-31 | 080314S00031 | 14-IL-0104 | 2014-11-10 | 2014-11-10 | 2014-11-25 | 2014-12-05 | 2014-12-12 | VCD CONSTRUCTION
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122216 | Tigbawan Elementary School | MALITBOG | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-08-31 | 080314S00067 | 14-IL-0076 | 2014-11-10 | 2014-11-10 | 2014-12-17 | 2014-12-26 | 2015-01-05 | JT PAREDES CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region VIII | Southern Leyte | 122051 | Tuburan Elementary School | HINUNANGAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1015957.1935 |  |  | COMPLETED | 1 | 2015-04-08 | 2015-08-31 | 080314S00038 | 14-IL-0114 | 2014-11-10 | 2014-11-12 | 2014-12-17 | 2014-12-26 | 2015-01-05 | RNMK CONSTRUCTION AND DEVELOPMENT
NC 2014 | K10 (2014) | Region VIII | Tacloban City | 314003 | Antonio Balmes NHS | Tacloban City | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1041000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region VIII | Tacloban City | 303668 | Tacloban City Night HS | Tacloban City | 1 | 1 | 3 | 1STY2CL, 1STY1CL | 2014 K10 BATCH 2 | 5498000 |  |  | Reverted | 0
NC 2015 | K10 (2015) | Region VIII | Baybay City | 121115 | Ampihanon ES | CITY OF BAYBAY | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1948606.04 |  |  | COMPLETED | 1 |  |  | 080215S00214 | 15IG0153 | 2015-09-10 | 2015-09-14 | 2015-09-29 | 2015-10-07 | 2015-10-20 | R.S. REYNA CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Baybay City | 313316 | Baybay City National Night High School | CITY OF BAYBAY | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6329337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Baybay City | 303360 | Caridad NHS | CITY OF BAYBAY | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 080215S00050 | 15IG0104 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-20 | 2015-09-04 | JUCONS CONSTRUCTION &SUPPLY
NC 2015 | K10 (2015) | Region VIII | Baybay City | 121120 | Kabunga-an ES | CITY OF BAYBAY | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 080215S00213 | 15IG0150 | 2015-09-10 | 2015-09-14 | 2015-09-29 | 2015-10-07 | 2015-10-20 | R.S. REYNA CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Baybay City | 121087 | Kambonggan ES | CITY OF BAYBAY | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 080215S00216 | 15IG0152 | 2015-09-10 | 2015-09-14 | 2015-09-29 | 2015-10-07 | 2015-10-22 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2015 | K10 (2015) | Region VIII | Baybay City | 121089 | Kilim ES | CITY OF BAYBAY | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 080215S00215 | 15IG0147 | 2015-09-10 | 2015-09-14 | 2015-09-29 | 2015-10-07 | 2015-10-20 | R. AGULLO CONSTRUCTION & ENTERPRISES
NC 2015 | K10 (2015) | Region VIII | Baybay City | 121143 | Maganhan ES | CITY OF BAYBAY | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00148 | 15IG0124 | 2015-08-19 | 2015-08-21 | 2015-09-15 | 2015-09-22 | 2015-10-05 | R.S. REYNA CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Baybay City | 313312 | Mailhi NHS | CITY OF BAYBAY | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2902592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Baybay City | 313312 | Mailhi NHS | CITY OF BAYBAY | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Baybay City | 313323 | Makinhas NHS Annex-Ciabu Annex | CITY OF BAYBAY | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 080215S00069 | 15IG0101 | 2015-07-22 | 2015-07-23 | 2015-08-06 | 2015-08-14 | 2015-09-01 | RJIR ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Baybay City | 303419 | Plaridel National High School | CITY OF BAYBAY | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8434965.051 |  |  | COMPLETED | 1 |  |  | 080215S00070 | 15IG0103 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-20 | 2015-09-04 | C N E CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Baybay City | 303420 | Pomponan National High School | CITY OF BAYBAY | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 3202592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Baybay City | 303420 | Pomponan National High School | CITY OF BAYBAY | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Baybay City | 121127 | Punta ES | CITY OF BAYBAY | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00150 | 15IG0124 | 2015-08-19 | 2015-08-21 | 2015-09-15 | 2015-09-22 | 2015-10-05 | R.S. REYNA CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Baybay City | 121128 | Sabang PS | CITY OF BAYBAY | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 080215S00212 | 15IG0151 | 2015-09-10 | 2015-09-14 | 2015-09-29 | 2015-10-07 | 2015-11-02 | LANOY CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Baybay City |  | SHS in Baybay City | CITY OF BAYBAY | 5 | 1 | 12 | 2STY12CL | 2015 SHS BATCH 5 | 29158434 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Biliran | 303319 | Almeria NHS | ALMERIA | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Biliran | 303319 | Almeria NHS | ALMERIA | 0 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Biliran | 120847 | Bato-Banlas Elementary School | MARIPIPI | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080115S00022 | 15IA0126 | 2015-11-16
NC 2015 | SHS (2015) | Region VIII | Biliran | 303320 | Biliran NAHS | BILIRAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1 |  |  | 080115S00015 | 15IA0082 | 2015-08-18 | 2015-08-25 | 2015-09-02
NC 2015 | SHS (2015) | Region VIII | Biliran | 313202 | Biliran Science High School | BILIRAN | 0 | 1 | 8 | 2STY8CL | 2015 ADDITIONAL FUND BATCH 9 | 2462377.5407 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Biliran | 313202 | Biliran Science High School | BILIRAN | 0 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Biliran | 303321 | Bool NHS | CULABA | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 080115S00017 | 15IA0081 | 2015-06-24 | 2015-07-17 | 2015-07-30 | 2015-11-20 | 2015-11-25 | CHU CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Biliran | 303323 | Cabucgayan NHS | CABUCGAYAN | 0 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10567131.51 |  |  | COMPLETED | 1 |  |  | 080115S00018 | 15IA0108 | 2015-09-01 | 2015-09-07 | 2015-09-17 | 2015-11-11 | 2015-11-16 | C N E CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Biliran | 303322 | Cabucgayan NSAT | CABUCGAYAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Biliran | 303322 | Cabucgayan NSAT | CABUCGAYAN | 0 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Biliran | 120789 | Capayas ES | CABUCGAYAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 080115S00028 | 15IA0102 | 2015-08-20 | 2015-08-21 | 2015-09-04 | 2015-09-19 | 2015-10-01 | R.K. ENGINEERING & CONSTRUCTION WORKS
NC 2015 | SHS (2015) | Region VIII | Biliran | 303324 | Culaba NVS | CULABA | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8464965.051 |  |  | reverted | 0 |  |  | 080115S00020 | 15IA0079 | 2015-06-24 | 2015-07-17 | 2015-07-30
NC 2015 | K10 (2015) | Region VIII | Biliran | 120852 | Danao ES | MARIPIPI | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080115S00026 | 15IA0130 | 2015-11-17
NC 2015 | SHS (2015) | Region VIII | Biliran | 303325 | Higatangan NHS | NAVAL (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8664965 |  |  | COMPLETED | 1 |  |  | 080115S00027 | 15IA0129 | 2015-11-17
NC 2015 | SHS (2015) | Region VIII | Biliran | 313203 | ICT High School of Eastern Biliran | CAIBIRAN | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6619337.6381 |  |  | COMPLETED | 1 |  |  | 080115S00003 | 15IA0070 | 2015-06-14 | 2015-06-15 | 2015-06-30
NC 2015 | K10 (2015) | Region VIII | Biliran | 120832 | Inasuyan ES | KAWAYAN | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080115S00021 | 15IA0103 | 2015-08-20 | 2015-08-21 | 2015-09-04 | 2015-09-15 | 2015-10-01 | R.K. ENGINEERING & CONSTRUCTION WORKS
NC 2015 | SHS (2015) | Region VIII | Biliran | 303326 | Kawayan NHS | KAWAYAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 080115S00013 | 15IA0078 | 2015-06-24 | 2015-07-17 | 2015-07-30 | 2015-11-19 | 2015-11-25 | CHU CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Biliran | 120859 | Larrazabal ES | NAVAL (Capital) | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080115S00023 | 15IA0104 | 2015-08-20 | 2015-08-21 | 2015-09-04 | 2015-09-19 | 2015-10-01 | R.K. ENGINEERING & CONSTRUCTION WORKS
NC 2015 | SHS (2015) | Region VIII | Biliran | 303327 | Lucsoon NHS | NAVAL (Capital) | 0 | 1 | 10 | 2STY10CL | 2015 ADDITIONAL FUND BATCH 9 | 4106345.042 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Biliran | 303327 | Lucsoon NHS | NAVAL (Capital) | 0 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Biliran | 303328 | Manlabang NHS | CAIBIRAN | 0 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 11227342.5917 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Biliran | 303329 | Maripipi NVS | MARIPIPI | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8614965.051 |  |  | Terminated | 1 |  |  | 080115S00005 | 15IA0075 | 2015-08-18 | 2015-08-25 |  |  |  |  | Terminated October 16, 2017 due to TRANSPORT COST OR HAULING COST NOT CONSIDERED IN THE PROGRAM OF WORKS, ISLAND AREA
NC 2015 | SHS (2015) | Region VIII | Biliran | 303330 | Naval National High School | NAVAL (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080115S00006 | 15IA0074 | 2015-08-18 | 2015-08-25
NC 2015 | SHS (2015) | Region VIII | Biliran | 313204 | Naval Night High School | NAVAL (Capital) | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080115S00007 | 15IA0069 | 2015-06-14 | 2015-06-18 | 2015-06-30 | 2015-08-24 | 2015-08-28 | BNL CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Biliran | 303331 | Naval School of Fisheries | NAVAL (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Biliran | 120824 | Pinamihagan ES | CULABA | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080115S00024 | 15IA0111 | 2015-09-21 | 2015-09-24 | 2015-11-16
NC 2015 | SHS (2015) | Region VIII | Biliran | 303332 | Tabunan NHS | ALMERIA | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6569337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Biliran | 303333 | Tucdao NHS | KAWAYAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Biliran | 303333 | Tucdao NHS | KAWAYAN | 0 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Biliran | 120813 | Union ES | CAIBIRAN | 0 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080115S00025 | 15IA0105 | 2015-08-20 | 2015-08-27 | 2015-09-04 | 2015-11-11 | 2015-11-16 | CHU CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Biliran | 303334 | Viga National High School | MARIPIPI | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6719337.6381 |  |  | Terminated | 0 |  |  | 080115S00010 | 15IA0071 | 2015-08-18 | 2015-08-25 |  |  |  |  | Terminated June 28, 2017 due to TRANSPORT COST OR HAULING COST NOT CONSIDERED IN THE PROGRAM OF WORKS, ISLAND AREA
NC 2015 | SHS (2015) | Region VIII | Biliran | 313201 | Western Biliran School for the Arts and Culture | ALMERIA | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8464965.051 |  |  | reverted | 0
NC 2015 | SHS (2015) | Region VIII | Biliran | 313201 | Western Biliran School for the Arts and Culture | ALMERIA | 0 | 1 | 10 | 2STY10CL | 2015 ADDITIONAL FUND BATCH 9 | 4156345.042 |  |  | reverted | 0
NC 2015 | K10 (2015) | Region VIII | Borongan City | 122392 | Bagong Barrio Elementary School | CITY OF BORONGAN (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080515S00059 | 15IB0146 | 2015-10-01 | 2015-10-02 | 2015-10-15 | 2015-10-21 | 2015-11-04 | ARNOLD G. COSIPAG CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Borongan City | 313504 | Benowangan NHS (Lalawigan NHS - Benowangan Annex) | CITY OF BORONGAN (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1998606.04 |  |  | COMPLETED | 1 |  |  | 080515S00034 | 15IB0122 | 2015-07-28 | 2015-07-29 | 2015-08-11 | 2015-08-20 | 2015-09-04 | ARNOLD G. COSIPAG CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Borongan City | 122372 | Bugas ES | CITY OF BORONGAN (Capital) | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080515S00046 | 15IB0126 | 2015-07-28 | 2015-07-30 | 2015-08-12 | 2015-08-20 | 2015-09-04 | TUBIGAN BUILDERS
NC 2015 | SHS (2015) | Region VIII | Borongan City | 313515 | E. Samar NCHS - Supt. Fidel E. Anacta, Sr. MHS Annex | CITY OF BORONGAN (Capital) | 0 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3484886.575 |  |  | COMPLETED | 1 |  |  | 080515S00011 | 15IB0105 | 2015-08-03 | 2015-08-04 | 2015-08-18 | 2015-09-01 | 2015-09-15 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VIII | Borongan City | 303511 | Lalawigan NHS | CITY OF BORONGAN (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1 |  |  | 080515S00009 | 15IB0105 | 2015-08-03 | 2015-08-04 | 2015-08-18 | 2015-09-01 | 2015-09-15 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VIII | Borongan City | 303526 | Maypangdan NHS | CITY OF BORONGAN (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8244965.051 |  |  | COMPLETED | 1 |  |  | 080515S00008 | 15IB0105 | 2015-08-03 | 2015-08-04 | 2015-08-18 | 2015-09-01 | 2015-09-15 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region VIII | Borongan City | 122386 | San Pablo ES | CITY OF BORONGAN (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 080515S00052 | 15IB0145 | 2015-10-01 | 2015-10-02 | 2015-10-15 | 2015-10-21 | 2015-11-04 | ARNOLD G. COSIPAG CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Borongan City | 303525 | Sta. Fe NHS | CITY OF BORONGAN (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080515S00007 | 15IB0106 | 2015-08-03 | 2015-08-04 | 2015-08-18 | 2015-09-01 | 2015-09-15 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VIII | Borongan City | 303500 | Stand Alone 1 | CITY OF BORONGAN (Capital) | 0 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 5 | 32982028 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 124119 | Bante Elementary School | CALBAYOG CITY | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080415S00099 | 15IJ-0131 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-15 | 2015-08-28 | JFR CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 124121 | Binaliw Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00211 | 15IJ-0172 | 2015-09-01 | 2015-09-13 | 2015-09-14 | 2015-09-18 | 2015-09-22 | RNMK CONSTRUCTION AND DEVELOPMENT
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 124079 | Buenavista Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1 |  |  | 080415S00208
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 194002 | Cabadiangan Primary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1 |  |  | 080415S00212
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 124059 | Cag-anibong Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080415S00206 | 15IJ-0179 | 2015-09-09 | 2015-09-21 | 2015-09-22 | 2015-09-26 | 2015-09-30 | VCD CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 124132 | Cagmanipis Sur Elementary School | CALBAYOG CITY | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080415S00101 | 15IJ-0126 | 2015-07-22 | 2015-08-03 | 2015-08-04 | 2015-08-08 | 2015-08-14 | VCD CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region VIII | Calbayog City | 313801 | Calbayog City National High School | CALBAYOG CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080415S00030 | 15IJ-0139 | 2015-09-01 | 2015-09-13 | 2015-09-14 | 2015-09-18 | 2015-09-22 | C D U CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Calbayog City | 313804 | Calbayog City National High School - Bagacay Campus | CALBAYOG CITY | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 080415S00029 | 15IJ-0115 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-07-30 | 2015-08-14 | B. VICENCIO CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 123990 | Calucnayan Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080415S00205
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 124008 | Carmen Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00200 | 15IJ-0166 | 2015-08-25 | 2015-09-06 | 2015-09-07 | 2015-09-11 | 2015-09-15 | JFR CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 124010 | Gabay Primary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080415S00201 | 15IJ-0180 | 2015-09-09 | 2015-09-21 | 2015-09-22 | 2015-09-26 | 2015-09-30 | ND CARANZO BUILDERS AND CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 124012 | Giragaan Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00202 | 15IJ-0193 | 2015-10-10 | 2015-10-22 | 2015-10-23 | 2015-10-27 | 2015-10-31 | JFR CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 123995 | Langoyon Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080415S00199
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 500239 | Macatingog Integrated School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080415S00198
NC 2015 | SHS (2015) | Region VIII | Calbayog City | 303644 | Mag-Ubay National High School | CALBAYOG CITY | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080415S00028 | 15IJ-0100 | 2015-07-09 | 2015-07-21 | 2015-07-22 | 2015-07-26 | 2015-08-01 | JFR CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Calbayog City | 303645 | Malaga National High School | CALBAYOG CITY | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 080415S00027 | 15IJ-0105 | 2015-07-12 | 2015-07-24 | 2015-07-25 | 2015-07-29 | 2015-09-02 | JFR CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Calbayog City | 313811 | Malaga NHS - Pena I Annex School | CALBAYOG CITY | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080415S00026 | 15IJ-0098 | 2015-07-09 | 2015-07-21 | 2015-07-22 | 2015-07-26 | 2015-08-01 | B. VICENCIO CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 124100 | Mancol Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1 |  |  | 080415S00216
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 124020 | Maybog Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080415S00203 | 15IJ-0178 | 2015-09-09 | 2015-09-21 | 2015-09-22 | 2015-09-26 | 2015-09-30 | RNMK CONSTRUCTION AND DEVELOPMENT
NC 2015 | SHS (2015) | Region VIII | Calbayog City | 313802 | Migara National High School | CALBAYOG CITY | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080415S00025 | 15IJ-0099 | 2015-07-09 | 2015-07-21 | 2015-07-22 | 2015-07-26 | 2015-08-06 | JFR CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 124102 | Nag-uma Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1 |  |  | 080415S00209
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 124041 | Navarro Primary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080415S00215 | 15IJ-0171 | 2015-09-01 | 2015-09-13 | 2015-09-14 | 2015-09-18 | 2015-09-22 | JFR CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Calbayog City | 303646 | Oquendo National High School | CALBAYOG CITY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 080415S00024 | 15IJ-0186 | 2015-09-23 | 2015-10-05 | 2015-10-06 | 2015-10-10 | 2015-10-14 | B. VICENCIO CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 303647 | Oquendo National High School - Cabatuan Campus | CALBAYOG CITY | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080415S00102 | 15IJ-0143 new | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-08-29 | 2015-09-02 | RNMK CONSTRUCTION AND DEVELOPMENT
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 124023 | Pagbalican Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080415S00204 | 15IJ-0170 | 2015-09-02 | 2015-09-14 | 2015-09-15 | 2015-09-19 | 2015-09-23 | JFR CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Calbayog City | 303648 | Pilar National Agricultural High School | CALBAYOG CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080415S00041 | 15IJ-0108 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-08-29 | 2015-09-02 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2015 | SHS (2015) | Region VIII | Calbayog City | 303649 | R. Lentejas Mem. School Of Fisheries | CALBAYOG CITY | 1 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 1 | 12771310.093 |  |  | COMPLETED | 1 |  |  | 080415S00032 | 15IJ-0106 | 2015-07-12 | 2015-07-24 | 2015-07-25 | 2015-07-29 | 2015-08-02 | C D U CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 124074 | Roxas II Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080415S00207 | 15IJ-0168 | 2015-08-25 | 2015-09-06 | 2015-09-07 | 2015-09-11 | 2015-09-15 | ND CARANZO BUILDERS AND CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VIII | Calbayog City | 303650 | San Joaquin National High School | CALBAYOG CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080415S00042 | 15IJ-0146 | 2015-08-16 | 2015-08-28 | 2015-08-29 | 2015-09-04 | 2015-09-15 | B. VICENCIO CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 124048 | San Policarpo Central Elem. School | CALBAYOG CITY | 1 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 3 | 12771310.093 |  |  | COMPLETED | 1 |  |  | 080415S00096 | 15IJ-0109 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-07-30 | 2015-08-06 | B. VICENCIO CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Calbayog City | 303651 | San Policarpo National High School | CALBAYOG CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080415S00037 | 15IJ-0114 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-07-30 | 2015-08-14 | B. VICENCIO CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 124110 | San Rufino Elementary School | CALBAYOG CITY | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080415S00098 | 15IJ-0150 | 2015-08-25 | 2015-09-06 | 2015-09-07 | 2015-09-11 | 2015-09-15 | ND CARANZO BUILDERS AND CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 124075 | Sigo Elementary School | CALBAYOG CITY | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080415S00097 | 15IJ-0127 | 2015-07-22 | 2015-08-03 | 2015-08-04 | 2015-08-08 | 2015-08-14 | JFR CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 124112 | Sinidman Or. Primary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080415S00210 | 15IJ-0167 | 2015-08-25 | 2015-09-06 | 2015-09-07 | 2015-09-11 | 2015-09-15 | ND CARANZO BUILDERS AND CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VIII | Calbayog City |  | Stand Alone - Regional Arts & Design | CALBAYOG CITY | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Calbayog City | 500238 | Tabawan Integrated School | CALBAYOG CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080415S00039 | 15IJ-0103 | 2015-07-12 | 2015-07-24 | 2015-07-25 | 2015-07-29 | 2015-08-06 | B. VICENCIO CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Calbayog City | 303652 | Tarabucan National High School | CALBAYOG CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080415S00040 | 15IJ-0107 -0107 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-08-29 | 2015-09-02 | B. VICENCIO CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Calbayog City | 303653 | Trinidad National High School | CALBAYOG CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080415S00005 | 15IJ-0113 -0113 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-07-30 | 2015-08-14 | B. VICENCIO CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Calbayog City | 313815 | Trinidad NHS -Tomaligues Annex School | CALBAYOG CITY | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080415S00103 | 15IJ-0125 | 2015-07-22 | 2015-08-05 | 2015-08-06 | 2015-08-10 | 2015-08-14 | JFR CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Catbalogan City | 303622 | Antonio G. Tuazon NHS | CITY OF CATBALOGAN (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Catbalogan City | 313701 | Catbalogan NCHS | CITY OF CATBALOGAN (Capital) | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Catbalogan City | 123398 | Cawayan ES | CITY OF CATBALOGAN (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00213
NC 2015 | SHS (2015) | Region VIII | Catbalogan City | 303621 | Guinsorongan NHS | CITY OF CATBALOGAN (Capital) | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Catbalogan City | 303621 | Guinsorongan NHS | CITY OF CATBALOGAN (Capital) | 2 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Catbalogan City | 123403 | Palanyogon ES | CITY OF CATBALOGAN (Capital) | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080415S00104
NC 2015 | SHS (2015) | Region VIII | Catbalogan City | 313706 | Pangdan National High School | CITY OF CATBALOGAN (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6619337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Catbalogan City | 303620 | Samar National School | CITY OF CATBALOGAN (Capital) | 2 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 1 | 18422268.79 |  |  | COMPLETED | 1 |  |  | 080415S00033 | 15 IK 0072 | 2015-12-01 | 2015-12-04 | 2015-12-22
NC 2015 | SHS (2015) | Region VIII | Catbalogan City | 303623 | Silanga NHS | CITY OF CATBALOGAN (Capital) | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 8 | 10467131.51 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Catbalogan City | 123428 | Socorro ES | CITY OF CATBALOGAN (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | REVERTED | 0 |  |  | 080415S00105 | 13IK0033 | 2015-08-06 | 2015-08-20 | 2015-08-20 | 2015-09-02 |  | MAGA CONSTRUCTION AND SUPPLIES
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122571 | Agsaman ES | JIPAPAD | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080515S00070 | 15IB0178 | 2015-09-17 | 2015-09-18 | 2015-10-01 | 2015-10-07 | 2015-10-23 | BELGES CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122473 | Aguinaldo ES | GENERAL MACARTHUR | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080515S00047 | 15IB0118 | 2015-07-28 | 2015-07-29 | 2015-08-11 | 2015-08-20 | 2015-09-04 | ARNOLD G. COSIPAG CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122474 | Alang-alang PS | GENERAL MACARTHUR | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 080515S00080 | 15IB0149 | 2015-09-08 | 2015-09-09 | 2015-09-22 | 2015-09-25 | 2015-10-09 | TUBIGAN BUILDERS
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 303494 | Arteche NHS | ARTECHE | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8244965.051 |  |  | COMPLETED | 1 |  |  | 080515S00014 | 15IB0102 | 2015-08-03 | 2015-08-04 | 2015-08-18 | 2015-09-01 | 2015-09-15 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 303495 | Balangkayan NHS | BALANGKAYAN | 0 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 5 | 13071310 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122633 | Balocawe ES | ORAS | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080515S00036 | 15IB0121 | 2015-07-28 | 2015-07-29 | 2015-08-11 | 2015-08-20 | 2015-09-04 | TUBIGAN BUILDERS
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122556 | Barbo ES | GUIUAN | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | REVERTED | 0 |  |  | 080515S00041 | 15IB0133 | 2015-07-28 | 2015-07-30 | 2015-08-12
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122409 | Baruk ES | CAN-AVID | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 080515S00054 | 15IB0164 | 2015-09-15 | 2015-09-16 | 2015-09-29 | 2015-10-05 | 2015-10-20 | BELGES CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122343 | Beta-og ES | LAWAAN | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | REVERTED | 0 |  |  | 080515S00044 | 15IB0129 | 2015-07-28 | 2015-07-30 | 2015-08-12
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122329 | Buenavista ES | ARTECHE | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080515S00067 | 15IB0170 | 2015-09-17 | 2015-09-18 | 2015-10-01 | 2015-10-07 | 2015-10-23 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122721 | Bunacan ES | SAN JULIAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080515S00089 | 15IB0168 | 2015-09-15 | 2015-09-16 | 2015-09-29 | 2015-10-05 | 2015-10-20 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122763 | Burak ES | TAFT | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 080515S00085 | 15IB0165 | 2015-09-15 | 2015-09-16 | 2015-09-29 | 2015-10-05 | 2015-10-20 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122479 | Camcueves ES | GENERAL MACARTHUR | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 080515S00079 | 15IB0141 | 2015-09-03 | 2015-09-04 | 2015-09-17 | 2015-09-22 | 2015-10-06 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 313501 | Can-Avid NHS | CAN-AVID | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122559 | Canawayon ES | GUIUAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 080515S00071 | 15IB0153 | 2015-09-08 | 2015-09-09 | 2015-09-22 | 2015-09-25 | 2015-10-09 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122573 | Casapa PS | JIPAPAD | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080515S00043 | 15IB0125 | 2015-07-28 | 2015-07-29 | 2015-08-11 | 2015-08-20 | 2015-09-04 | TUBIGAN BUILDERS
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122333 | Casidman Elementary School | ARTECHE | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080515S00084 | 15IB0175 | 2015-09-17 | 2015-09-18 | 2015-10-01 | 2015-10-07 | 2015-10-23 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122561 | Casuguran ES | GUIUAN | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080515S00049 | 15IB0128 | 2015-07-28 | 2015-07-30 | 2015-08-12 | 2015-08-20 | 2015-09-04 | TUBIGAN BUILDERS
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122334 | Catumsan ES | ARTECHE | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 080515S00057 | 15IB0173 | 2015-09-17 | 2015-09-18 | 2015-10-01 | 2015-10-07 | 2015-10-23 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122432 | Denigpi-an ES | DOLORES | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080515S00060 | 15IB0160 | 2015-09-14 | 2015-09-15 | 2015-09-30 | 2015-10-06 | 2015-10-20 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 303499 | Dolores NHS | DOLORES | 0 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22172343.62 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 303499 | Dolores NHS | DOLORES | 0 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Eastern Samar | 303499 | Dolores NHS | DOLORES | 0 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 303501 | Gen. MacArthur NAS | GENERAL MACARTHUR | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1 |  |  | 080515S00022 | 15IB0110 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-31 | 2015-08-14 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122616 | Gen. Malvar PS | BALANGKAYAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080515S00063 | 15IB0172 | 2015-09-17 | 2015-09-18 | 2015-10-01 | 2015-10-07 | 2015-10-23 | BELGES CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122510 | Giporlos CS | GIPORLOS | 0 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | REVERTED | 0 |  |  | 080515S00038 | 15IB0131 | 2015-07-28 | 2015-07-30 | 2015-08-12
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 303502 | Giporlos NTS | GIPORLOS | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8224965.051 |  |  | COMPLETED | 1 |  |  | 080515S00024 | 15IB0111 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-31 | 2015-08-14 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 303503 | Guiuan NHS | GUIUAN | 0 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10927342.5917 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Eastern Samar | 303503 | Guiuan NHS | GUIUAN | 0 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4829098.54 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 192510 | Hamorawon ES | SULAT | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 080515S00072 | 15IB0167 | 2015-09-15 | 2015-09-16 | 2015-09-29 | 2015-10-05 | 2015-10-20 | TUBIGAN BUILDERS
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 303508 | Homonhon NHS | GUIUAN | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 080515S00029 | 15IB0115 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-31 | 2015-08-14 | TUBIGAN BUILDERS
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 192501 | Inayawan Elementary School | ARTECHE | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080515S00074 | 15IB0171 | 2015-09-17 | 2015-09-18 | 2015-10-01 | 2015-10-07 | 2015-10-23 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122639 | Japay ES | ORAS | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080515S00064 | 15IB0156 | 2015-09-14 | 2015-09-15 | 2015-09-30 | 2015-10-06 | 2015-10-20 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 303510 | Jipapad NHS | JIPAPAD | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080515S00028 | 15IB0107 | 2015-08-03 | 2015-08-04 | 2015-08-18 | 2015-09-01 | 2015-09-15 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 303512 | Lawaan Nat'L. Sch. Of Crafts/HI | LAWAAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8224965.051 |  |  | COMPLETED | 1 |  |  | 080515S00027 | 15IB0112 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-31 | 2015-08-14 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 303513 | Llorente NHS | LLORENTE | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122336 | Macarthur Elementary School | ARTECHE | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080515S00056 | 15IB0177 | 2015-09-17 | 2015-09-18 | 2015-10-01 | 2015-10-07 | 2015-10-23 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 303515 | Maslog NHS | MASLOG | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 080515S00025 | 15IB0101 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-27 | 2015-08-10 | JUCONS CONSTRUCTION &SUPPLY
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 303516 | Matarinao SOF | SALCEDO | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1 |  |  | 080515S00016 | 15IB0113 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-31 | 2015-08-14 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 313514 | Maydolong NHS | MAYDOLONG | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 303518 | Mercedes HS | MERCEDES | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8224965.051 |  |  | COMPLETED | 1 |  |  | 080515S00031 | 15IB0114 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-31 | 2015-08-14 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122597 | Minaanod ES | LLORENTE | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080515S00062 | 15IB0169 | 2015-09-15 | 2015-09-16 | 2015-09-29 | 2015-10-05 | 2015-10-20 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122740 | Natividad ES | SAN POLICARPO | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080515S00088 | 15IB0154 | 2015-09-14 | 2015-09-25 | 2015-09-30 | 2015-10-06 | 2015-10-20 | BELGES CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122565 | Ngolos ES | GUIUAN | 0 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | REVERTED | 0 |  |  | 080515S00042 | 15IB0130 | 2015-08-21 | 2015-08-20
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122422 | Obong ES | CAN-AVID | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 080515S00053 | 15IB0163 | 2015-09-15 | 2015-09-16 | 2015-09-29 | 2015-10-05 | 2015-10-20 | BELGES CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 303520 | Oras National High School | ORAS | 0 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10907342.5917 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Eastern Samar | 303520 | Oras National High School | ORAS | 0 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4809098.54 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122464 | Osmena ES | DOLORES | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080515S00048 | 15IB0127 | 2015-07-28 | 2015-07-30 | 2015-08-12 | 2015-08-20 | 2015-09-04 | TUBIGAN BUILDERS
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122566 | Pagbabangnan ES | GUIUAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080515S00069 | 15IB0147 | 2015-09-03 | 2015-09-04 | 2015-09-17 | 2015-09-22 | 2015-10-06 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122423 | Pandol ES | CAN-AVID | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 080515S00075 | 15IB0161 | 2015-09-14 | 2015-09-15 | 2015-09-30 | 2015-10-06 | 2015-10-20 | BELGES CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122741 | Pangpang Elementary School | SAN POLICARPO | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080515S00037 | 15IB0123 | 2015-07-28 | 2015-07-29 | 2015-08-11 | 2015-08-20 | 2015-09-04 | TUBIGAN BUILDERS
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 303505 | Pedro E. Candido Memorial NHS | HERNANI | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8224965.051 |  |  | COMPLETED | 1 |  |  | 080515S00021 | 15IB0110 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-31 | 2015-08-14 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 303521 | Quinapondan NHS | QUINAPONDAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1 |  |  | 080515S00020 | 15IB0111 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-31 | 2015-08-14 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122495 | Quirino PS | GENERAL MACARTHUR | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 080515S00078 | 15IB0150 | 2015-09-08 | 2015-09-09 | 2015-09-22 | 2015-09-25 | 2015-10-09 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122580 | Recare ES | JIPAPAD | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080515S00061 | 15IB0174 | 2015-09-17 | 2015-09-18 | 2015-10-01 | 2015-10-07 | 2015-10-23 | BELGES CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122436 | Rizal ES | DOLORES | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080515S00083 | 15IB0157 | 2015-09-14 | 2015-09-15 | 2015-09-30 | 2015-10-06 | 2015-10-20 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122669 | Rizal ES | ORAS | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080515S00065 | 15IB0155 | 2015-09-14 | 2015-09-15 | 2015-09-30 | 2015-10-06 | 2015-10-20 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122684 | Rizal ES | QUINAPONDAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080515S00058 | 15IB0143 | 2015-10-01 | 2015-10-02 | 2015-10-15 | 2015-10-21 | 2015-11-04 | ARNOLD G. COSIPAG CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122496 | Roxas PS | GENERAL MACARTHUR | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080515S00068 | 15IB0151 | 2015-09-08 | 2015-09-09 | 2015-09-22 | 2015-09-25 | 2015-10-09 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 313509 | Salcedo Vocational HS | SALCEDO | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 |  |  | 080515S00019 | 15IB0113 | 2015-07-09 | 2015-07-09 | 2015-07-22 | 2015-07-31 | 2015-08-14 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122425 | Salvacion ES | CAN-AVID | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 080515S00077 | 15IB0162 | 2015-09-15 | 2015-09-16 | 2015-09-29 | 2015-10-05 | 2015-10-20 | BELGES CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 303523 | Samar Natl Pilot Opp. Sch. Of Agri. | SAN POLICARPO | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Eastern Samar | 303523 | Samar Natl Pilot Opp. Sch. Of Agri. | SAN POLICARPO | 0 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 192503 | San Isidro PS | QUINAPONDAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080515S00073 | 15IB0152 | 2015-09-08 | 2015-09-09 | 2015-09-22 | 2015-09-25 | 2015-10-09 | TUBIGAN BUILDERS
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 303524 | San Julian NHS | SAN JULIAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080515S00017 | 15IB0106 | 2015-08-03 | 2015-08-04 | 2015-08-18 | 2015-09-01 | 2015-09-15 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122754 | San Mateo ES | SULAT | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 080515S00086 | 15IB0166 | 2015-09-15 | 2015-09-16 | 2015-09-29 | 2015-10-05 | 2015-10-20 | TUBIGAN BUILDERS
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122517 | San Miguel ES | GIPORLOS | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 080515S00076 | 15IB0144 | 2015-09-03 | 2015-09-04 | 2015-09-17 | 2015-09-22 | 2015-10-06 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122439 | San Roque ES | DOLORES | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2338606.04 |  |  | COMPLETED | 1 |  |  | 080515S00082 | 15IB0158 | 2015-09-14 | 2015-09-15 | 2015-09-30 | 2015-10-06 | 2015-10-20 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 313502 | Southern Samar NCHS (Balangiga NHS) | BALANGIGA | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8224965.051 |  |  | COMPLETED | 1 |  |  | 080515S00010 | 15IB0112 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-31 | 2015-08-14 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122689 | Sto. Niño ES | QUINAPONDAN | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | REVERTED | 0 |  |  | 080515S00035 | 15IB0132 | 2015-07-28 | 2015-07-30 | 2015-08-12
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 303527 | Sulat NHS | SULAT | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080515S00012 | 15IB0104 | 2015-08-03 | 2015-08-04 | 2015-08-18 | 2015-09-01 | 2015-09-15 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122720 | Taclaon ES | SALCEDO | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080515S00087 | 15IB0148 | 2015-09-03 | 2015-09-04 | 2015-09-17 | 2015-09-22 | 2015-10-06 | MCGR ENGINEERING SERVICES
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122775 | Taft CS | TAFT | 0 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 3 | 12771310.093 |  |  | COMPLETED | 1 |  |  | 080515S00040 | 15IB0120 | 2015-07-28 | 2015-07-29 | 2015-08-11 | 2015-08-20 | 2015-09-04 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VIII | Eastern Samar | 303529 | Taft NHS | TAFT | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080515S00013 | 15IB0104 | 2015-08-03 | 2015-08-04 | 2015-08-18 | 2015-09-01 | 2015-09-15 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122339 | Tibalawon Elementary School | ARTECHE | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080515S00055 | 15IB0176 | 2015-09-17 | 2015-09-18 | 2015-10-01 | 2015-10-07 | 2015-10-23 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122444 | Tikling ES | DOLORES | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080515S00081 | 15IB0159 | 2015-09-14 | 2015-09-15 | 2015-09-30 | 2015-10-06 | 2015-10-20 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 303532 | Tubabao NHS | GUIUAN | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080515S00039 | 15IB0124 | 2015-07-28 | 2015-07-29 | 2015-08-11 | 2015-08-20 | 2015-09-04 | TUBIGAN BUILDERS
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122683 | Valley ES | QUINAPONDAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 080515S00066 | 15IB0142 | 2015-10-01 | 2015-10-02 | 2015-10-15 | 2015-10-21 | 2015-11-04 | ARNOLD G. COSIPAG CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Eastern Samar | 122505 | Vigan ES | GENERAL MACARTHUR | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080515S00045 | 15IB0119 | 2015-07-28 | 2015-07-29 | 2015-08-11 | 2015-08-20 | 2015-09-04 | TUBIGAN BUILDERS
NC 2015 | SHS (2015) | Region VIII | Leyte | 303392 | Alangalang Agro-Ind'l. School (LSU - Alangalang Campus) | ALANGALANG | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00071 | 15IC0016 | 2015-06-17 | 2015-06-18 | 2015-06-30 | 2015-07-10 | 2015-07-27 | B Y A BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VIII | Leyte | 120939 | Alangalang I Central School | ALANGALANG | 1 | 1 | 12 | 3STY12CL | 2015 K10 BATCH 6 | 18072268.79 |  |  | COMPLETED | 1 |  |  | 080215S00221 | 15IC0062 | 2015-09-16 | 2015-09-17 | 2015-09-29 | 2015-10-08 | 2015-10-19 | JELM CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303336 | Alang-Alang NHS | ALANGALANG | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00072 | 15IC0017 | 2015-06-17 | 2015-06-18 | 2015-06-30 | 2015-08-04 | 2015-08-10 | B. VICENCIO CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 120961 | Andres C. Yu Memorial School | ALANGALANG | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 080215S00223 | 15IC0052 | 2015-09-16 | 2015-09-17 | 2015-09-29 | 2015-10-08 | 2015-10-16 | B. VICENCIO CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303340 | Astorga NHS | ALANGALANG | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 080215S00194 | 15IC0050 | 2015-09-02 | 2015-09-03 | 2015-09-15 | 2015-10-19 | 2015-10-26 | ACME BUILDERS CORPORATION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121007 | Bagong Silang ES | BABATNGON | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 3062592.44 |  |  | COMPLETED | 1 |  |  | 080215S00225 | 15IC0051 | 2015-09-16 | 2015-09-17 | 2015-09-29 | 2015-10-08 | 2015-10-16 | ARYANESA CONST. & ENTERPRISES
NC 2015 | K10 (2015) | Region VIII | Leyte | 121008 | Biasong ES | BABATNGON | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2098606.04 |  |  | COMPLETED | 1 |  |  | 080215S00205 | 15IC0059 | 2015-09-16 | 2015-09-17 | 2015-09-29 | 2015-10-08 | 2015-10-16 | TOM BUILDERS AND SUPPLY
NC 2015 | K10 (2015) | Region VIII | Leyte | 313398 | Borseth National High School | ALANGALANG | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00155 | 15IC0034 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-08-28 | I.D.A. JR BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VIII | Leyte | 191526 | Cahumayhumayan Elementary School | TANAUAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 080215S00200 | 15IC0089 | 2015-11-13
NC 2015 | K10 (2015) | Region VIII | Leyte | 120967 | Calaasan ES | ALANGALANG | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00224 | 15IC0058 | 2015-09-16 | 2015-09-17 | 2015-09-29 | 2015-10-08 | 2015-10-16 | B Y A BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VIII | Leyte | 121947 | Canmogsay ES | TOLOSA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00163 | 15IC0038 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-08-31 | WAWOT BUILDERS
NC 2015 | K10 (2015) | Region VIII | Leyte | 121755 | Cogon ES | PALO | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00156
NC 2015 | K10 (2015) | Region VIII | Leyte | 121756 | Guindapunan ES | PALO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00218 | 15IC0057 | 2015-09-16 | 2015-09-17 | 2015-09-29 | 2015-10-08 | 2015-10-16 | B. VICENCIO CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121010 | Guintigui-an ES | BABATNGON | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080215S00159 | 15IC0035 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-08-28 | VMEJIA CONSTRUCTION AND SUPPLIES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303343 | Juan S. Tismo NHS (Babatngon NHS) | BABATNGON | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8239965.051 |  |  | COMPLETED | 1 |  |  | 080215S00073 | 15IC0018 | 2015-06-17 | 2015-06-18 | 2015-06-30 | 2015-08-04 | 2015-08-10 | B. VICENCIO CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303386 | Kiling National High School | TANAUAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00115 | 15IC0029 | 2015-07-15 | 2015-07-16 | 2015-07-28 | 2015-08-10 | 2015-08-18 | JELM CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121859 | Malaguinabot PS | SAN MIGUEL | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00158 | 15IC0040 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-08-28 | RPBJ TRADING AND CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303401 | Malibago NHS | BABATNGON | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8264965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Leyte | 121861 | Mawodpawod ES | SAN MIGUEL | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00203 | 15IC0056 | 2015-09-16 | 2015-09-17 | 2015-09-29 | 2015-10-08 | 2015-10-16 | JELM CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121941 | Mohon Elementary School | TANAUAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00146 | 15IC0039 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-08-28 | RAQ J BUILDERS
NC 2015 | K10 (2015) | Region VIII | Leyte | 120974 | Mudboron ES | ALANGALANG | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00153 | 15IC0032 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-08-31 | B Y A BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VIII | Leyte | 121952 | Olot Elementary School | TOLOSA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00149 | 15IC0041 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-08-31 | WAWOT BUILDERS
NC 2015 | SHS (2015) | Region VIII | Leyte | 303413 | Pagsulhugon National High School | BABATNGON | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00074 | 15IC0019 | 2015-06-17 | 2015-07-10 | 2015-07-23 | 2015-08-04 | 2015-08-12 | Z.A.S. CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303415 | Palo National High School | PALO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Leyte | 303415 | Palo National High School | PALO | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Leyte | 313335 | Palo NHS-Pawing Annex | PALO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00082 | 15IC0021 | 2015-06-17 | 2015-07-10 | 2015-07-23 | 2015-08-03 | 2015-08-11 | MCGR ENGINEERING SERVICES
NC 2015 | K10 (2015) | Region VIII | Leyte | 191516 | Pasil Elementary School | TANAUAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00199 | 15IC0071 | 2015-11-06 | 2015-11-06 | 2015-11-19
NC 2015 | K10 (2015) | Region VIII | Leyte | 121862 | Patong ES | SAN MIGUEL | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 080215S00196 | 15IC0053 | 2015-09-16 | 2015-09-17 | 2015-09-29 | 2015-10-08 | 2015-10-16 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2015 | SHS (2015) | Region VIII | Leyte | 303421 | San Agustin National High School | BABATNGON | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 2 | 3667968.78 |  |  | COMPLETED | 1 |  |  | 080215S00113 | 15IC0037 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-08-28 | VMEJIA CONSTRUCTION AND SUPPLIES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303424 | San Joaquin NHS | PALO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 080215S00105 | 15IC0031 | 2015-07-15 | 2015-07-16 | 2015-07-28 | 2015-08-04 | 2015-08-13 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303426 | San Miguel National High School | SAN MIGUEL | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00086 | 15IC0022 | 2015-06-17 | 2015-09-21 | 2015-09-28 | 2015-10-08 | 2015-10-16 | D.L. AUREO CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121955 | San Vicente ES | TOLOSA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00198 | 15IC0055 | 2015-09-16 | 2015-09-17 | 2015-09-29 | 2015-10-08 | 2015-10-16 | BELGES CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region VIII | Leyte | 121020 | Sangputan ES | BABATNGON | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 080215S00227 | 15IC0061 | 2015-09-16 | 2015-09-17 | 2015-09-29 | 2015-10-08 | 2015-10-16 | LTA CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121866 | SANTOL ELEMENTARY SCHOOL | SAN MIGUEL | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 080215S00197 | 15IC0054 | 2015-09-16 | 2015-09-17 | 2015-09-29 | 2015-10-08 | 2015-10-16 | EXCEL Cs BUILDERS
NC 2015 | SHS (2015) | Region VIII | Leyte | 303429 | Sta. Cruz National High School | SAN MIGUEL | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00087 | 15IC0023 | 2015-06-17 | 2015-06-18 | 2015-06-30 | 2015-07-10 | 2015-07-27 | C D U CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303430 | Sta. Fe National High School | SANTA FE | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 080215S00076 | 15IC0024 | 2015-06-17 | 2015-07-10 | 2015-07-23 | 2015-08-05 | 2015-08-17 | JELM CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 191518 | Tacuranga ES | PALO | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00157
NC 2015 | K10 (2015) | Region VIII | Leyte | 121931 | Talolora Elementary School | TANAUAN | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080215S00160 | 15IC0036 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-08-31 | B Y A BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VIII | Leyte | 303437 | Tanauan NHS (San Roque NHS) | TANAUAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00077 | 15IC0025 | 2015-06-17 | 2015-06-18 | 2015-06-30 | 2015-07-10 | 2015-07-27 | C N E CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303388 | Tanauan Sch. Of Craftsmanship & Home Industries (LIT-Tanauan Campus)Campus | TANAUAN | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Leyte | 303388 | Tanauan Sch. Of Craftsmanship & Home Industries (LIT-Tanauan Campus)Campus | TANAUAN | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Leyte | 120959 | Tinaisan Elementary School | ALANGALANG | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 080215S00222 | 15IC0060 | 2015-09-16 | 2015-09-17 | 2015-09-29 | 2015-10-08 | 2015-10-16 | ENLIVEN CONSTRUCTION AND ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303440 | Tolosa National High School | TOLOSA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00079 | 15IC0027 | 2015-06-17 | 2015-06-18 | 2015-06-30 | 2015-07-10 | 2015-07-27 | SILK AND STEEL CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 313342 | Trinidad B. Caidic NHS | ALANGALANG | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00154 | 15IC0033 | 2015-07-29 | 2015-08-26 | 2015-10-12 | 2015-10-19 | 2015-10-28 | CHU CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121150 | Abuyogon ES | BURAUEN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00162 | 15ID0140 | 2015-07-27 | 2015-08-07 | 2015-08-10 | 2015-09-02 | 2015-09-09 | WJ BUILDERS
NC 2015 | SHS (2015) | Region VIII | Leyte | 313304 | Agapito Amado Memorial National High School | JARO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1 |  |  | 080215S00080 | 15ID0107 | 2015-06-26 | 2015-06-25 | 2015-08-19 | 2015-09-04 | 2015-09-09 | SILK AND STEEL CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121338 | Alegre Elementary School | DULAG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00126 | 15ID0137 | 2015-07-27 | 2015-07-30 | 2015-08-10 |  | 2015-09-30 | CHU CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303341 | Asuncion S. Melgar NHS | CAPOOCAN | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Leyte | 303341 | Asuncion S. Melgar NHS | CAPOOCAN | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Leyte | 303342 | Atty. Roque A. Marcos MS (La Paz NHS) | LAPAZ | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00085 | 15ID0119 | 2015-06-26 | 2015-06-25 | 2015-08-19 | 2015-09-03 | 2015-09-09 | MWJ CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121810 | Bahay ES | PASTRANA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00123 | 15ID0133 | 2015-07-27 | 2015-08-07 | 2015-08-10 | 2015-09-03 | 2015-09-09 | TAM CONSTRUCTION & SUPPLIES
NC 2015 | SHS (2015) | Region VIII | Leyte | 313324 | Barugo NHS | BARUGO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 080215S00083 | 15ID0108 | 2015-06-26 | 2015-06-25 | 2015-08-19 | 2015-09-03 | 2015-09-09 | CHU CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121309 | Bolirao Elementary School | DAGAMI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00208 | 15ID0170 | 2015-09-01 | 2015-09-14 | 2015-09-15 | 2015-10-14 | 2015-10-30 | TEJOME-BALBERONA CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121319 | Bulod Elementary School | DULAG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00233 | 15ID0171 | 2015-09-01 | 2015-09-16 | 2015-09-16 | 2015-09-30 | 2015-10-30 | JUCONS CONSTRUCTION &SUPPLY
NC 2015 | SHS (2015) | Region VIII | Leyte | 313332 | Buracan NHS | LAPAZ | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 080215S00112 | 15ID0128 | 2015-07-27 | 2015-08-07 | 2015-08-10 | 2015-09-02 | 2015-09-09 | B Y A BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VIII | Leyte | 303353 | Burauen CNHS | BURAUEN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00068 | 15ID0118 | 2015-06-24 | 2015-06-25 | 2015-08-19 | 2015-09-03 | 2015-09-11 | MWJ CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303354 | Burauen NHS | BURAUEN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 2802592 |  |  | COMPLETED | 1 |  |  | 080215S00191 | 15ID0196 | 2015-10-27 | 2015-10-29 | 2015-11-10 |  |  | RCC BUILDERS AND ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303355 | Cabacungan NHS | DULAG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00062 | 15ID0117 | 2015-06-26 | 2015-06-25 | 2015-08-19 | 2015-09-03 | 2015-09-09 | JONI CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121562 | Cabadiangan ES | LAPAZ | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 080215S00247 | 15ID0169 | 2015-09-01 | 2015-09-15 | 2015-09-15 | 2015-09-30 | 2015-10-30 | 3As BUILDERS
NC 2015 | SHS (2015) | Region VIII | Leyte | 313321 | Cabatoan NHS | DULAG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8284965 |  |  | COMPLETED | 1 |  |  | 080215S00186 | 15ID0164 | 2015-10-27 | 2015-10-29 | 2015-11-10 |  |  | JUCONS CONSTRUCTION &SUPPLY
NC 2015 | SHS (2015) | Region VIII | Leyte | 303357 | Calingcaguing NHS | BARUGO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 080215S00034 | 15ID0109 | 2015-06-26 | 2015-06-25 | 2015-08-19 |  |  | SILK AND STEEL CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 500233 | Calubian Integrated School | DULAG | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080215S00130 | 15ID0151 | 2015-07-30 | 2015-08-10 | 2015-08-14 |  | 2015-09-30 | JUCONS CONSTRUCTION &SUPPLY
NC 2015 | SHS (2015) | Region VIII | Leyte | 500233 | Calubian Integrated School | DULAG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 080215S00187 | 15ID0165 | 2015-10-27 | 2015-10-29 | 2015-11-10 |  |  | R.T. MORABE CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121289 | Caluctogan Elementary School | DAGAMI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00206 | 15ID0183 | 2015-10-05 | 2015-10-16 | 2015-10-16 | 2015-10-20 | 2015-10-26 | R.T. MORABE CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121323 | Camitoc Elementary | DULAG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00209 | 15ID0172 | 2015-09-01 | 2015-09-24 | 2015-11-04
NC 2015 | K10 (2015) | Region VIII | Leyte | 121290 | Camonoan Elementary School | DAGAMI | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080215S00151 | 15ID0149 | 2015-07-30 | 2015-08-10 | 2015-08-14 |  |  | JULITA BUILDERS
NC 2015 | K10 (2015) | Region VIII | Leyte | 121324 | Camote Elementary School | DULAG | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00128 | 15ID0152 | 2015-07-30 | 2015-08-10 | 2015-08-14 |  | 2015-09-08 | JULITA BUILDERS
NC 2015 | K10 (2015) | Region VIII | Leyte | 121258 | Candigahub Elementary School | CARIGARA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080215S00161 | 15ID0148 | 2015-07-30 | 2015-08-10 | 2015-08-14 | 2015-09-02 | 2015-09-09 | E.G. CANABE CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121189 | Cansiboy ES | BURAUEN | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 080215S00210 | 15ID0166 | 2015-09-01 | 2015-09-24 | 2015-11-04 |  |  | 3As BUILDERS
NC 2015 | SHS (2015) | Region VIII | Leyte | 303361 | Carigara NHS | CARIGARA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 080215S00185 | 15ID0198 | 2015-10-27 | 2015-10-29 | 2015-11-10 |  |  | R.T. MORABE CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303362 | Carigara School of Fisheries | CARIGARA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00033 | 15ID0116 | 2015-06-26 | 2015-06-25 | 2015-08-19 | 2015-09-04 | 2015-10-27 | SILK AND STEEL CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121814 | Colawen ES | PASTRANA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 080215S00254 | 15ID0179 | 2015-09-01 | 2015-09-24 | 2015-11-10 |  |  | CHU CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121523 | Dita ES | JULITA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 080215S00252 | 15ID0168 | 2015-10-05 | 2015-10-19 | 2015-10-19 | 2015-10-22 | 2015-10-27 | R. AGULLO CONSTRUCTION & ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303367 | Don Mariano Salvacion MNHS | CAPOOCAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 080215S00188 | 15ID00195 | 2015-10-27 | 2015-10-29 | 2015-11-10
NC 2015 | SHS (2015) | Region VIII | Leyte | 303369 | Dulag NHS | DULAG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00032 | 15ID0121 | 2015-06-26 | 2015-06-25 | 2015-08-19 |  | 2015-11-10 | E.G. CANABE CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121569 | Gimiranat East PS | LAPAZ | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00248 | 15ID0180 | 2015-09-01 | 2015-09-24 | 2015-11-04
NC 2015 | SHS (2015) | Region VIII | Leyte | 303371 | Granja-Kalinawan NHS | JARO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 080215S00031 | 15ID0120 | 2015-06-26 | 2015-06-25 | 2015-08-19 | 2015-09-02 | 2015-09-09 | VIGUZ CONSTRUCTION CORPORATION
NC 2015 | SHS (2015) | Region VIII | Leyte | 313336 | Granja-Kalinawan NHS-Uguiao Annex | JARO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6414337.6381 |  |  | COMPLETED | 1 |  |  | 080215S00092 | 15ID0146 | 2015-07-30 | 2015-08-10 | 2015-08-14 | 2015-09-02 | 2015-09-09 | ARYANESA CONST. & ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303441 | Gregorio C. Catenza NHS (Tunga NHS) | TUNGA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1 |  |  | 080215S00030 | 15ID0110 | 2015-06-26 | 2015-06-25 | 2015-08-19 | 2015-09-04 | 2015-09-09 | SILK AND STEEL CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303372 | Guinarona National High School | DAGAMI | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 2 | 3817968.78 |  |  | COMPLETED | 1 |  |  | 080215S00111 | 15ID0130 | 2015-07-27 | 2015-08-07 | 2015-08-10 | 2015-08-28 | 2015-09-09 | STEVEN CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VIII | Leyte | 313325 | Hibunauan National High School | BURAUEN | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 080215S00029 | 15ID0125 | 2015-06-24 | 2015-06-25 | 2015-08-19 | 2015-09-04 | 2015-09-11 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2015 | K10 (2015) | Region VIII | Leyte | 121295 | Hinabuyan Elmentary School | DAGAMI | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080215S00145 | 15ID0150 | 2015-07-30 | 2015-08-10 | 2015-08-14 |  |  | JULITA BUILDERS
NC 2015 | SHS (2015) | Region VIII | Leyte | 303380 | Juan Villablanca NHS | PASTRANA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 080215S00028 | 15ID0114 | 2015-06-26 | 2015-06-25 | 2015-08-19 | 2015-10-22 | 2015-10-27 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2015 | SHS (2015) | Region VIII | Leyte | 313307 | Jugaban National High School | CARIGARA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1 |  |  | 080215S00027 | 15ID0111 | 2015-06-24 | 2015-06-25 | 2015-08-19 | 2015-10-31 | 2015-11-10 | E.G. CANABE CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303381 | Julita NHS | JULITA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Leyte | 303381 | Julita NHS | JULITA | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Leyte | 303382 | Justimbaste-Remandaban NHS (Tabontabon NHS) | TABONTABON | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00265 | 15ID0229 | 2015-11-17 | 2015-11-27 |  |  |  | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303394 | Libertad NHS | CAPOOCAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 080215S00192 | 15ID0194 | 2015-10-27 | 2015-10-29 | 2015-11-10
NC 2015 | K10 (2015) | Region VIII | Leyte | 121819 | Lima PS | PASTRANA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Reverted | 0
NC 2015 | K10 (2015) | Region VIII | Leyte | 121821 | Macalpiay ES | PASTRANA | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00122 | 15ID0147 | 2015-07-30 | 2015-08-10 | 2015-08-14 |  | 2015-09-16 | MWJ CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121480 | Macanip Elementary School | JARO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00251 | 15ID0187 | 2015-09-01 | 2015-09-14 | 2015-09-15 | 2015-10-14 | 2015-10-30 | R.S. REYNA CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303397 | Macarthur National High School | MACARTHUR | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 080215S00025 | 15ID0124 | 2015-06-24 | 2015-06-25 | 2015-08-19 | 2015-09-02 | 2015-09-09 | CHU CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121198 | Mahagnao ES | BURAUEN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00204 | 15ID0182 | 2015-09-01 | 2015-09-15 | 2015-09-15 | 2015-09-30 | 2015-10-30 | WJ BUILDERS
NC 2015 | K10 (2015) | Region VIII | Leyte | 121166 | Malaguinabot ES | BURAUEN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00201 | 15ID0173 | 2015-09-01 | 2015-09-15 | 2015-09-17 | 2015-09-30 | 2015-10-27 | RCC BUILDERS AND ENTERPRISES
NC 2015 | K10 (2015) | Region VIII | Leyte | 121822 | Malitbogay ES | PASTRANA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00147 | 15ID0132 | 2015-07-27 | 2015-08-07 | 2015-08-10 | 2015-08-28 | 2015-09-09 | TAM CONSTRUCTION & SUPPLIES
NC 2015 | SHS (2015) | Region VIII | Leyte | 313330 | Manaybanay NHS | PASTRANA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 080215S00110 | 15ID0145 | 2015-07-30 | 2015-07-30 | 2015-08-14 | 2015-09-02 | 2015-09-09 | STEVEN CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region VIII | Leyte | 121824 | Maricum ES | PASTRANA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00256 | 15ID0177 | 2015-09-01 | 2015-09-14 | 2015-09-15 | 2015-10-14 | 2015-10-21 | MN MACATO BUILDERS
NC 2015 | SHS (2015) | Region VIII | Leyte | 303407 | Mayorga NHS | MAYORGA | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 080215S00023 | 15ID0126 | 2015-06-24 | 2015-06-25 | 2015-08-19 |  | 2015-11-10 | R. AGULLO CONSTRUCTION & ENTERPRISES
NC 2015 | K10 (2015) | Region VIII | Leyte | 191581 | Oguisan Elementary School | MACARTHUR | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00124 | 15ID0134 | 2015-07-27 | 2015-07-30 | 2015-08-10
NC 2015 | K10 (2015) | Region VIII | Leyte | 121317 | Ormocay Elementary School | DAGAMI | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00132 | 15ID0139 | 2015-07-27 | 2015-08-07 | 2015-08-10 | 2015-09-02 | 2015-09-09 | SILK AND STEEL CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121579 | Pansud Primary School | LAPAZ | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1 |  |  | 080215S00262 | 15ID0167 | 2015-10-05 | 2015-10-16 | 2015-10-20 | 2015-10-23 | 2015-10-29 | R. AGULLO CONSTRUCTION & ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303417 | Patoc National High School | DAGAMI | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 080215S00035 | 15ID0112 | 2015-06-24 | 2015-06-25 | 2015-08-19 | 2015-10-26 | 2015-10-29 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303418 | Pinamopoan National High School | CAPOOCAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8764965 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Leyte | 303418 | Pinamopoan National High School | CAPOOCAN | 2 |  | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Leyte | 121303 | Rizal Elementary School | DAGAMI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00207 | 15ID0176 | 2015-10-05 | 2015-10-16 | 2015-10-20 | 2015-10-23 | 2015-10-28 | WAWOT BUILDERS
NC 2015 | SHS (2015) | Region VIII | Leyte | 313333 | Rizal National High School | DULAG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00109 | 15ID0129 | 2015-07-27 | 2015-08-07 | 2015-08-10 | 2015-09-02 | 2015-09-09 | B Y A BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VIII | Leyte | 121330 | Romualdez Elementary School | DULAG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00121 | 15ID0138 | 2015-07-27 | 2015-08-07 | 2015-08-10 | 2015-09-02 | 2015-09-09 | WJ BUILDERS
NC 2015 | K10 (2015) | Region VIII | Leyte | 191575 | Salvacion Primary School | MACARTHUR | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00133 | 15ID0136 | 2015-07-27 | 2015-07-30 | 2015-08-10 |  | 2015-09-30 | CHU CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 191576 | San Isidro Elementary School | MACARTHUR | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00125 | 15ID0135 | 2015-07-27 | 2015-07-30 | 2015-08-10 |  | 2015-09-30 | CHU CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303425 | San Jose National High School | DULAG | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 2 | 3667968.78 |  |  | COMPLETED | 1 |  |  | 080215S00108 | 15ID0131 | 2015-07-27 | 2015-08-07 | 2015-08-10 | 2015-09-02 | 2015-09-09 | RPBJ TRADING AND CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121172 | San Pablo ES | BURAUEN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00202 | 15ID0174 | 2015-08-31 | 2015-09-12 | 2015-09-15 | 2015-09-30 | 2015-10-30 | 3As BUILDERS
NC 2015 | K10 (2015) | Region VIII | Leyte | 121354 | San Vicente Elementary School | DULAG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00226 | 15ID0186 | 2015-09-01 | 2015-09-25 | 2015-09-25 | 2015-09-30 | 2015-10-27 | R. AGULLO CONSTRUCTION & ENTERPRISES
NC 2015 | K10 (2015) | Region VIII | Leyte | 191577 | San Vicente Elementary School | MACARTHUR | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00257 | 15ID0181 | 2015-09-01 | 2015-09-24 | 2015-11-10 |  |  | CHU CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | LEYTE | 303428 | Sta. Ana National High School | LAPAZ | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 080215S00021 | 15ID0123 | 2015-06-24 | 2015-06-25 | 2015-07-13 | 2015-08-13 | 2015-08-17 | RAQ J BUILDERS
NC 2015 | SHS (2015) | Region VIII | Leyte | 303432 | Sta. Mesa National High School | DAGAMI | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Leyte | 303432 | Sta. Mesa National High School | DAGAMI | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2479549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Leyte | 303433 | Sta. Rosa National High School | BARUGO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8324965.051 |  |  | COMPLETED | 1 |  |  | 080215S00094 | 15ID0144 | 2015-07-30 | 2015-08-10 | 2015-08-14 | 2015-09-02 | 2015-09-09 | VIGUZ CONSTRUCTION CORPORATION
NC 2015 | SHS (2015) | Region VIII | Leyte | 313303 | Teofilo R. Macaso Memorial NHS | JARO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6389337.6381 |  |  | COMPLETED | 1 |  |  | 080215S00106 | 15ID0143 | 2015-07-30 | 2015-08-10 | 2015-08-14 | 2015-09-04 | 2015-09-09 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2015 | K10 (2015) | Region VIII | Leyte | 121827 | Tingib ES | PASTRANA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080215S00134 | 15ID0153 | 2015-07-30 | 2015-08-10 | 2015-08-14 |  | 2015-09-08 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2015 | K10 (2015) | Region VIII | Leyte | 121252 | Tolibao ES | CAPOOCAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 080215S00195 | 15ID0175 | 2015-09-01 | 2015-09-24 | 2015-11-04
NC 2015 | K10 (2015) | Region VIII | Leyte | 121532 | Tolosahay ES | JULITA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00250 | 15ID0185 | 2015-09-01 | 2015-09-15 | 2015-09-24 | 2015-09-30 | 2015-10-29 | HARDLINE BUILDERS AND SALES
NC 2015 | K10 (2015) | Region VIII | Leyte | 121355 | Victory Elementary School | DULAG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 080215S00231 | 15ID0191 | 2015-10-05 | 2015-10-16 | 2015-10-16 | 2015-10-22 | 2015-10-28 | RPBJ TRADING AND CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121533 | Villahermosa ES | JULITA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00253 | 15ID0184 | 2015-09-01 | 2015-09-15 | 2015-09-24 | 2015-09-30 | 2015-10-30 | JUCONS CONSTRUCTION &SUPPLY
NC 2015 | K10 (2015) | Region VIII | Leyte | 121962 | A. Tumamak ES | VILLABA | 3 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00140 | 15IE0052 | 2015-08-11 | 2015-08-13 | 2015-08-25 | 2015-09-03 | 2015-09-09 | RJIR ENTERPRISES
NC 2015 | K10 (2015) | Region VIII | Leyte | 121590 | Burabod ES | LEYTE | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00136 | 15IE0057 | 2015-08-11 | 2015-08-13 | 2015-08-25 | 2015-09-03 | 2015-09-09 | L.P. VILLASIN CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303358 | Calubian NHS (Calubian Nat'l. Voc'l. School) | CALUBIAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 080215S00008 | 15IE0040 | 2015-08-04 | 2015-08-07 | 2015-08-18 | 2015-08-27 | 2015-09-03 | REX E. MORALES CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121212 | Casiongan ES | CALUBIAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 080215S00258 | 15IE0069 | 2015-09-02 | 2015-09-04 | 2015-09-16 | 2015-09-24 | 2015-10-01 | BELGES CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region VIII | Leyte | 121594 | Danus ES | LEYTE | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00137 | 15IE0058 | 2015-08-11 | 2015-08-13 | 2015-08-25 | 2015-09-03 | 2015-09-09 | RJIR ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 313317 | Felix Caneja Lafuente NHS | CALUBIAN | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080215S00009 | 15IE0048 | 2015-08-04 | 2015-08-07 | 2015-08-18 | 2015-08-27 | 2015-09-03 | REX E. MORALES CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 313309 | Gibacungan National High School | TABANGO | 3 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3967969 |  |  | COMPLETED | 1 |  |  | 080215S00172 | 15IE0073 | 2015-11-16 | 2015-11-19 | 2015-12-01 |  |  | R. AGULLO CONSTRUCTION & ENTERPRISES
NC 2015 | K10 (2015) | Region VIII | Leyte | 121969 | Iligay ES | VILLABA | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00236 | 15IE0068 | 2015-09-02 | 2015-09-04 | 2015-09-16 | 2015-09-24 | 2015-10-01 | BELGES CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region VIII | Leyte | 121901 | Inangatan Elem. School | TABANGO | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00139 | 15IE0053 | 2015-08-11 | 2015-08-13 | 2015-08-25 | 2015-09-03 | 2015-09-09 | MAGA CONSTRUCTION AND SUPPLIES
NC 2015 | SHS (2015) | Region VIII | Leyte | 313308 | Juan V. Delantar NHS | LEYTE | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8544965 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Leyte | 303387 | Leyte Agro-Ind'L Sch. | LEYTE | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1 |  |  | 080215S00010 | 15IE0050 | 2015-08-04 | 2015-08-07 | 2015-08-18 | 2015-08-27 | 2015-09-03 | JUCONS CONSTRUCTION &SUPPLY
NC 2015 | SHS (2015) | Region VIII | Leyte | 303390 | Leyte NHS | LEYTE | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1 |  |  | 080215S00060 | 15IE0049 | 2015-08-04 | 2015-08-07 | 2015-08-18 | 2015-08-27 | 2015-09-03 | JUCONS CONSTRUCTION &SUPPLY
NC 2015 | K10 (2015) | Region VIII | Leyte | 121598 | Libas Elementary School | LEYTE | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 080215S00259 | 15IE0070 | 2015-09-02 | 2015-09-04 | 2015-09-16 | 2015-09-24 | 2015-10-01 | REX E. MORALES CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303403 | Marcelino R. Veloso NHS (Marcelino R. Veloso NHS) | TABANGO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Leyte | 303403 | Marcelino R. Veloso NHS (Marcelino R. Veloso NHS) | TABANGO | 3 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Leyte | 303411 | Muertigue NHS | SAN ISIDRO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1 |  |  | 080215S00088 | 15IE0045 | 2015-08-04 | 2015-08-07 | 2015-08-18 | 2015-08-27 | 2015-09-03 | MAGA CONSTRUCTION AND SUPPLIES
NC 2015 | K10 (2015) | Region VIII | Leyte | 121605 | Parasan ES | LEYTE | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00260 | 15IE0071 | 2015-09-29 | 2015-10-01 | 2015-10-13 | 2015-10-22 | 2015-10-28 | RJIR ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303416 | Pastor Salazar NHS | TABANGO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00013 | 15IE0046 | 2015-08-04 | 2015-08-07 | 2015-08-18 | 2015-08-27 | 2015-09-03 | MAGA CONSTRUCTION AND SUPPLIES
NC 2015 | K10 (2015) | Region VIII | Leyte | 121230 | Petrolio ES | CALUBIAN | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00127 | 15IE0056 | 2015-08-11 | 2015-08-13 | 2015-08-25 | 2015-09-03 | 2015-09-09 | LJPM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VIII | Leyte | 313340 | Rafaelito Cabanas Martinez NHS | CALUBIAN | 3 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 080215S00135 | 15IE0055 | 2015-08-11 | 2015-08-13 | 2015-08-25 | 2015-09-03 | 2015-09-09 | REX E. MORALES CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303423 | San Isidro National High School | SAN ISIDRO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00089 | 15IE0044 | 2015-08-04 | 2015-08-07 | 2015-08-18 | 2015-08-27 | 2015-09-03 | MAGA CONSTRUCTION AND SUPPLIES
NC 2015 | SHS (2015) | Region VIII | Leyte |  | Sulpa NHS | VILLABA | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1988606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Leyte | 303434 | Tabango National High School | TABANGO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00104 | 15IE0041 | 2015-08-04 | 2015-08-07 | 2015-08-18 | 2015-08-27 | 2015-09-03 | MAGA CONSTRUCTION AND SUPPLIES
NC 2015 | K10 (2015) | Region VIII | Leyte | 121905 | Tahad ES | TABANGO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00255 | 15IE0067 | 2015-09-02 | 2015-09-04 | 2015-09-16 | 2015-09-24 | 2015-10-01 | MAGA CONSTRUCTION AND SUPPLIES
NC 2015 | K10 (2015) | Region VIII | Leyte | 121847 | Tinago Elementary School | SAN ISIDRO | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080214S00112 | 14IF0070 | 2014-08-21 | 2014-08-26 | 2014-09-09 | 2014-09-24 | 2014-10-01 | LJPM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VIII | Leyte | 121613 | Ugbon Elementary School | LEYTE | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00261 | 15IE0066 | 2015-09-29 | 2015-10-01 | 2015-10-13 | 2015-10-22 | 2015-10-28 | RJIR ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303442 | Villaba National Comprehensive High School | VILLABA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00014 | 15IE0042 | 2015-08-04 | 2015-08-07 | 2015-08-18 | 2015-08-27 | 2015-09-03 | REX E. MORALES CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303389 | Villaba NHS (LNCAST) | VILLABA | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Leyte | 303345 | Balugo National High School | ALBUERA | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Leyte | 120997 | Calingatnan Elementary School | ALBUERA | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00230 | 15IF0119 | 2015-08-24 | 2015-08-27 | 2015-09-14 | 2015-09-22 | 2015-10-05 | GMP BUILDERS
NC 2015 | SHS (2015) | Region VIII | Leyte | 303366 | Damulaan NHS | ALBUERA | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 080215S00193 | 15IF0118 | 2015-08-21 | 2015-08-27 | 2015-09-15 | 2015-10-13 | 2015-10-14 | RJIR ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303368 | Dr. Geronimo B. Zaldivar MSOF | ALBUERA | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00006 | 15IF0074 | 2015-06-07 | 2015-06-10 | 2015-07-28 | 2015-08-07 | 2015-08-18 | RJIR ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 313302 | Isabel NCHS (Isabel Nat'l Comprehensive Sch.) | ISABEL | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8454965.051 |  |  | COMPLETED | 1 |  |  | 080215S00017 | 15IF0094 | 2015-07-28 | 2015-07-31 | 2015-08-13 | 2015-08-25 | 2015-10-01 | ROLANDO M. VILLASENCIO CONSTRUCTION & GENERAL SERV
NC 2015 | SHS (2015) | Region VIII | Leyte | 303378 | Isabel NHS | ISABEL | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1 |  |  | 080215S00018 | 15IF0078 | 2015-06-07 | 2015-06-10 | 2015-07-28 | 2015-08-10 | 2015-10-01 | RJIR ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303383 | Kananga NHS | KANANGA | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1 |  |  | 080215S00019 | 15IF0077 | 2015-06-07 | 2015-06-10 | 2015-07-28 | 2015-08-10 | 2015-10-01 | ARCA BUILDERS
NC 2015 | SHS (2015) | Region VIII | Leyte | 303395 | Lim-ao NHS | KANANGA | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1 |  |  | 080215S00022 | 15IF0076 | 2015-06-07 | 2015-06-10 | 2015-07-28 | 2015-08-07 | 2015-10-01 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303396 | Lomonon National High School | PALOMPON | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6419338 |  |  | COMPLETED | 1 |  |  | 080215S00165 | 15IF0112 | 2015-08-21 | 2015-08-27 | 2015-09-15 | 2015-10-13 | 2015-10-14 | LJPM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VIII | Leyte | 303404 | Matag-ob NHS | MATAG-OB | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00051 | 15IF0080 | 2015-06-07 | 2015-06-10 | 2015-07-28 | 2015-08-10 | 2015-10-01 | RJIR ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303406 | Matlang NHS | ISABEL | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 2802592 |  |  | COMPLETED | 1 |  |  | 080215S00182 | 15IF0113 | 2015-08-21 | 2015-08-27 | 2015-09-28 | 2015-10-13 | 2015-11-24 | ROLANDO M. VILLASENCIO CONSTRUCTION & GENERAL SERV
NC 2015 | SHS (2015) | Region VIII | Leyte | 303408 | Merida VS | MERIDA | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1 |  |  | 080215S00064 | 15IF0082 | 2015-06-07 | 2015-06-10 | 2015-07-10 | 2015-07-20 | 2015-07-30 | RJIR ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303409 | Merida VS - Calunangan Annex | MERIDA | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1 |  |  | 080215S00166 | 15IF0114 | 2015-08-21 | 2015-08-27 | 2015-09-15 | 2015-10-13 | 2015-10-14 | RJIR ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303410 | Merida VS - Pto. Bello Annex | MERIDA | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8424965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Leyte | 313334 | PCCC St. Filomena NHS | ISABEL | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2038606 |  |  | COMPLETED | 1 |  |  | 080215S00168 | 15IF0116 | 2015-08-21 | 2015-08-27 | 2015-09-15 | 2015-10-13 | 2015-10-14 | ROLANDO M. VILLASENCIO CONSTRUCTION & GENERAL SERV
NC 2015 | K10 (2015) | Region VIII | Leyte | 121802 | Rizal ES | PALOMPON | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00232 | 15IF0121 | 2015-08-24 | 2015-08-27 | 2015-09-14 | 2015-09-22 | 2015-10-07 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2015 | SHS (2015) | Region VIII | Leyte | 313327 | RIZAL NHS | KANANGA | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8334965 |  |  | COMPLETED | 1 |  |  | 080215S00167 | 15IF0115 | 2015-08-21 | 2015-08-27 | 2015-09-15 | 2015-10-13 | 2015-10-14 | JA ACHACOSO ENTERPRISES & GENERAL SERVICES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303422 | San Francisco National High School | ISABEL | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00049 | 15IF0079 | 2015-06-07 | 2015-06-10 | 2015-07-10 | 2015-07-20 | 2015-07-30 | RJIR ENTERPRISES
NC 2015 | K10 (2015) | Region VIII | Leyte | 121669 | San Marcelino ES | MATAG-OB | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00238 | 15IF0120 | 2015-08-24 | 2015-08-27 | 2015-09-14 | 2015-09-22 | 2015-10-05 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121806 | San Roque PS | PALOMPON | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00249 | 15IF0122 | 2015-08-24 | 2015-08-27 | 2015-09-14 | 2015-09-22 | 2015-10-07 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2015 | SHS (2015) | Region VIII | Leyte | 303427 | Seguinon National High School | ALBUERA | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00093 | 15IF0095 | 2015-07-28 | 2015-07-31 | 2015-08-13 | 2015-08-25 | 2015-09-08 | RJIR ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303435 | Taberna National High School | PALOMPON | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Leyte | 303435 | Taberna National High School | PALOMPON | 4 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2549549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Leyte | 303438 | Tinabilan National High School | PALOMPON | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 080215S00103 | 15IF0096 | 2015-07-28 | 2015-07-31 | 2015-08-13 | 2015-08-25 | 2015-10-01 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VIII | Leyte | 313306 | Tinabilan NHS - Palompon Annex | PALOMPON | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00024 | 15IF0083 | 2015-06-07 | 2015-06-10 | 2015-07-28 | 2015-08-07 | 2015-10-01 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121452 | Tolingon ES | ISABEL | 4 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 080215S00141 | 15IF0098 | 2015-07-28 | 2015-07-31 | 2015-08-13 | 2015-08-25 | 2015-09-08 | ROLANDO M. VILLASENCIO CONSTRUCTION & GENERAL SERV
NC 2015 | SHS (2015) | Region VIII | Leyte | 303335 | Abuyog NHS | ABUYOG | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8244965.051 |  |  | COMPLETED | 1 |  |  | 080215S00059 | 15IG0097 | 2015-07-22 | 2015-07-23 | 2015-08-06 | 2015-08-14 | 2015-09-04 | JUCONS CONSTRUCTION &SUPPLY
NC 2015 | K10 (2015) | Region VIII | Leyte | 121397 | Anahaw Elementary School | HINDANG | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00144 | 15IG0120 | 2015-08-13 | 2015-08-14 | 2015-08-27 | 2015-09-07 | 2015-09-21 | R.S. REYNA CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303338 | Anahawan NHS | BATO | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 080215S00090 | 15IG0093 | 2015-07-22 | 2015-07-23 | 2015-08-06 | 2015-09-07 | 2015-09-18 | LJPM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VIII | Leyte | 121378 | Baas ES | HILONGOS | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00239 | 15IG0144 | 2015-09-10 | 2015-09-14 | 2015-09-29 | 2015-10-07 | 2015-10-20 | RJIR ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303344 | Balocawehay NHS | ABUYOG | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8244965.051 |  |  | COMPLETED | 1 |  |  | 080215S00058 | 15IG0091 | 2015-07-22 | 2015-07-23 | 2015-08-06 | 2015-08-14 | 2015-09-01 | JONI CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303346 | Bato National High School | BATO | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6359338 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Leyte | 303346 | Bato National High School | BATO | 5 |  | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Leyte | 303347 | Bato SOF | BATO | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00091 | 15IG0094 | 2015-09-29 | 2015-09-30 | 2015-10-13 | 2015-10-22 | 2015-11-09 | R. AGULLO CONSTRUCTION & ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303350 | Bontoc NHS | HINDANG | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8224965.051 |  |  | COMPLETED | 1 |  |  | 080215S00057 | 15IG0095 | 2015-07-22 | 2015-07-23 | 2015-08-06 | 2015-08-14 | 2015-09-01 | LJPM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VIII | Leyte | 313320 | Buli National High School | BATO | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1978606 |  |  | COMPLETED | 1 |  |  | 080215S00175 | 15IG0136 | 2015-09-03 | 2015-09-04 | 2015-09-17 | 2015-09-24 | 2015-11-02 | ROLANDO M. VILLASENCIO CONSTRUCTION & GENERAL SERV
NC 2015 | SHS (2015) | Region VIII | Leyte | 303352 | Bung-aw National High School | HILONGOS | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6389338 |  |  | COMPLETED | 1 |  |  | 080215S00169 | 15IG0133 | 2015-08-24 | 2015-08-25 | 2015-09-15 | 2015-09-22 | 2015-11-02 | RJIR ENTERPRISES
NC 2015 | K10 (2015) | Region VIII | Leyte | 121380 | Cacao ES | HILONGOS | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1968606.04 |  |  | COMPLETED | 1 |  |  | 080215S00240 | 15IG0154 | 2015-09-10 | 2015-09-14 | 2015-09-29 | 2015-10-07 | 2015-10-20 | RJIR ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303356 | Cahagnaan NHS | MATALOM | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8244965 |  |  | COMPLETED | 1 |  |  | 080215S00179 | 15IG0134 | 2015-08-24 | 2015-08-25 | 2015-09-15 | 2015-09-22 | 2015-11-02 | RJIR ENTERPRISES
NC 2015 | K10 (2015) | Region VIII | Leyte | 121496 | Calzada ES | JAVIER (BUGHO) | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00241 | 15IG0145 | 2015-10-20 | 2015-10-22 | 2015-11-05 | 2015-11-13 | 2015-11-23 | LANOY CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 313329 | Capudlosan NHS | HINDANG | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1988606 |  |  | COMPLETED | 1 |  |  | 080215S00176 | 15IG0139 | 2015-09-03 | 2015-09-04 | 2015-09-17 | 2015-09-24 | 2015-11-02 | BERDS CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121420 | Conalum ES | INOPACAN | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00129 | 15IG0121 | 2015-08-13 | 2015-08-14 | 2015-08-27 | 2015-09-07 | 2015-09-21 | LANOY CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303364 | Conalum NHS | INOPACAN | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8374965.051 |  |  | COMPLETED | 1 |  |  | 080215S00056 | 15IG0106 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-20 | 2015-09-04 | C N E CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303365 | Concepcion NHS | HILONGOS | 5 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15151327.92 |  |  | COMPLETED | 1 |  |  | 080215S00120 | 15IG0159 | 2015-09-22 | 2015-09-23 | 2015-10-08 | 2015-10-19 | 2015-10-30 | C N E CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121064 | Dolho Elementary School | BATO | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2812592.44 |  |  | COMPLETED | 1 |  |  | 080215S00237 | 15IG0149 | 2015-09-10 | 2015-09-14 | 2015-09-29 | 2015-10-07 | 2015-10-20 | JA ACHACOSO ENTERPRISES & GENERAL SERVICES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303370 | Esperanza NHS | MATALOM | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6399338 |  |  | COMPLETED | 1 |  |  | 080215S00171 | 15IG0131 | 2015-08-24 | 2015-08-25 | 2015-09-15 | 2015-09-22 | 2015-11-02 | C N E CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303373 | Hampipila NHS | ABUYOG | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 080215S00102 | 15IG0105 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-20 | 2015-09-04 | RJIR ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303374 | Hilongos NVS | HILONGOS | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1 |  |  | 080215S00055 | 15IG0100 | 2015-07-22 | 2015-07-23 | 2015-08-06 | 2015-08-14 | 2015-09-01 | RJIR ENTERPRISES
NC 2015 | K10 (2015) | Region VIII | Leyte | 121633 | Himamara Elementary School | MAHAPLAG | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00242 | 15IG0156 | 2015-09-10 | 2015-09-14 | 2015-09-29 | 2015-10-07 | 2015-11-02 | BELGES CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region VIII | Leyte | 303375 | Hindang NHS | HINDANG | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Leyte | 303377 | Inopacan NHS | INOPACAN | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00101 | 15IG0157 | 2015-09-10 | 2015-09-14 | 2015-09-29 | 2015-10-07 | 2015-10-20 | JA ACHACOSO ENTERPRISES & GENERAL SERVICES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303379 | Javier NHS | JAVIER (BUGHO) | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8244965.051 |  |  | COMPLETED | 1 |  |  | 080215S00053 | 15IG0098 | 2015-07-22 | 2015-07-23 | 2015-08-06 | 2015-08-14 | 2015-09-01 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2015 | SHS (2015) | Region VIII | Leyte | 303385 | Kikilo National High School | ABUYOG | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 080215S00100 | 15IG0110 | 2015-08-02 | 2015-08-04 | 2015-08-18 | 2015-08-26 | 2015-09-07 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2015 | K10 (2015) | Region VIII | Leyte | 120928 | Libertad Elementary School | ABUYOG | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 080215S00245 | 15IG0142 | 2015-09-10 | 2015-09-14 | 2015-09-29 | 2015-10-07 | 2015-10-20 | LANOY CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 313313 | Libertad NHS | ABUYOG | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 080215S00099 | 15IG0118 | 2015-08-13 | 2015-08-14 | 2015-08-27 | 2015-09-07 | 2015-09-28 | RJIR ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303398 | Mahaplag NHS | MAHAPLAG | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1 |  |  | 080215S00052 | 15IG0099 | 2015-07-22 | 2015-07-23 | 2015-08-06 | 2015-08-14 | 2015-09-04 | RJIR ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303399 | Mahaplag NHS - Upper Campus RA 7047 | MAHAPLAG | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 2817592 |  |  | COMPLETED | 1 |  |  | 080215S00164 | 15IG0138 | 2015-09-03 | 2015-09-04 | 2015-09-17 | 2015-09-24 | 2015-11-02 | JUCONS CONSTRUCTION &SUPPLY
NC 2015 | SHS (2015) | Region VIII | Leyte | 313343 | Manlilisid NHS | JAVIER (BUGHO) | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6369338 |  |  | COMPLETED | 1 |  |  | 080215S00170 | 15IG0135 | 2015-08-24 | 2015-08-25 | 2015-09-15 | 2015-09-22 | 2015-11-02 | LANOY CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Leyte | 303402 | Marao NHS | INOPACAN | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6369338 |  |  | COMPLETED | 1 |  |  | 080215S00173 | 15IG0132 | 2015-08-24 | 2015-08-25 | 2015-09-15 | 2015-09-22 | 2015-11-02 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303405 | Matalom NHS | MATALOM | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8244965.051 |  |  | COMPLETED | 1 |  |  | 080215S00036 | 15IG0096 | 2015-07-22 | 2015-07-23 | 2015-08-06 | 2015-08-19 | 2015-09-01 | FAIRCHILD BUILDERS & DEVELOPERS, INC.
NC 2015 | SHS (2015) | Region VIII | Leyte | 313337 | Matalom NHS-Sta. Paz Annex | MATALOM | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8244965.051 |  |  | COMPLETED | 1 |  |  | 080215S00098 | 15IG0108 | 2015-08-02 | 2015-08-04 | 2015-08-18 | 2015-08-26 | 2015-09-07 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2015 | K10 (2015) | Region VIII | Leyte | 121694 | Monte Alegre Elementary School | MATALOM | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 080215S00244 | 15IG0148 | 2015-09-10 | 2015-09-14 | 2015-09-29 | 2015-10-07 | 2015-10-20 | R. AGULLO CONSTRUCTION & ENTERPRISES
NC 2015 | K10 (2015) | Region VIII | Leyte | 120914 | Paguite ES | ABUYOG | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2028606.04 |  |  | COMPLETED | 1 |  |  | 080215S00235 | 15IG0155 | 2015-09-10 | 2015-09-14 | 2015-09-29 | 2015-10-07 | 2015-10-22 | R. AGULLO CONSTRUCTION & ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 313314 | Polahongon NHS | MAHAPLAG | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 2832592 |  |  | COMPLETED | 1 |  |  | 080215S00174 | 15IG0137 | 2015-09-03 | 2015-09-04 | 2015-09-17 | 2015-09-24 | 2015-11-02 | RJIR ENTERPRISES
NC 2015 | K10 (2015) | Region VIII | Leyte | 121370 | Sta. Cruz ES | HILONGOS | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00143 | 15IG0119 | 2015-08-13 | 2015-08-14 | 2015-08-27 | 2015-09-07 | 2015-09-21 | R.S. REYNA CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 120898 | Sta. Lucia Primary School | ABUYOG | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080215S00142 | 15IG0117 | 2015-08-13 | 2015-08-14 | 2015-08-27 | 2015-09-07 | 2015-09-21 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2015 | SHS (2015) | Region VIII | Leyte | 303431 | Sta. Margarita National High School | HILONGOS | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8284965.051 |  |  | COMPLETED | 1 |  |  | 080215S00097 | 15IG0111 | 2015-08-02 | 2015-08-04 | 2015-08-18 | 2015-08-26 | 2015-09-07 | JUCONS CONSTRUCTION &SUPPLY
NC 2015 | K10 (2015) | Region VIII | Leyte | 121651 | Sto. Niño Primary School | MAHAPLAG | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 080215S00243 | 15IG0141 | 2015-09-10 | 2015-09-14 | 2015-09-29 | 2015-10-07 | 2015-10-20 | LANOY CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 120900 | Tib-o Elementary School | ABUYOG | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 080215S00234 | 15IG0143 | 2015-09-10 | 2015-09-14 | 2015-09-29 | 2015-10-07 | 2015-10-22 | R. AGULLO CONSTRUCTION & ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Leyte | 303439 | Tinago NHS | INOPACAN | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 080215S00096 | 15IG0109 | 2015-08-02 | 2015-08-04 | 2015-08-18 | 2015-08-26 | 2015-09-07 | R.T. MORABE CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Leyte | 121078 | Tugas Elementary School | BATO | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 080215S00229 | 15IG0146 | 2015-09-10 | 2015-09-14 | 2015-09-29 | 2015-10-07 | 2015-10-20 | JA ACHACOSO ENTERPRISES & GENERAL SERVICES
NC 2015 | K10 (2015) | Region VIII | Maasin City | 500399 | Asuncion Integrated School | CITY OF MAASIN (Capital) | 0 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 080315S00039 | 15-IL-0142 | 2015-08-11 | 2015-08-13 | 2015-08-25 | 2015-08-27 | 2015-09-07 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2015 | K10 (2015) | Region VIII | Maasin City | 500399 | Asuncion Integrated School | CITY OF MAASIN (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080315S00038 | 15-IL-0131 | 2015-08-03 | 2015-08-06 | 2015-08-18 | 2015-08-25 | 2015-09-04 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VIII | Maasin City | 303454 | Dongon NHS | CITY OF MAASIN (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1 |  |  | 080315S00024 | 15-IL-0112 | 2015-07-28 | 2015-07-31 | 2015-08-12 | 2015-08-18 | 2015-08-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2015 | SHS (2015) | Region VIII | Maasin City | 323101 | Ibarra National High School | CITY OF MAASIN (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Maasin City | 303464 | Libhu NHS | CITY OF MAASIN (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080315S00013 | 15-IL-0111 | 2015-07-28 | 2015-07-31 | 2015-08-12 | 2015-08-18 | 2015-08-26 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2015 | SHS (2015) | Region VIII | Maasin City | 313401 | Maasin City NHS | CITY OF MAASIN (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080315S00016 | 15-IL-0109 | 2015-07-28 | 2015-07-31 | 2015-08-12 | 2015-08-18 | 2015-08-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2015 | SHS (2015) | Region VIII | Maasin City | 303467 | Maasin Vocational High School | CITY OF MAASIN (Capital) | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6389337.6381 |  |  | COMPLETED | 1 |  |  | 080315S00012 | 15-IL-0137 | 2015-08-11 | 2015-08-13 | 2015-09-16 | 2015-09-24 | 2015-10-05 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2015 | SHS (2015) | Region VIII | Maasin City | 303469 | Manhilo NHS | CITY OF MAASIN (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 080315S00010 | 15-IL-0138 | 2015-08-11 | 2015-08-13 | 2015-08-25 | 2015-08-27 | 2015-09-07 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2015 | K10 (2015) | Region VIII | Maasin City | 323106 | Matin-aw National High School | CITY OF MAASIN (Capital) | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080315S00036 | 15-IL-0143 | 2015-10-22 | 2015-10-22 | 2015-11-04 | 2015-12-22 | 2015-12-31
NC 2015 | K10 (2015) | Region VIII | Maasin City | 122167 | Nati MGS | CITY OF MAASIN (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 080315S00053 | 15-IL-069 | 2015-11-17 | 2015-11-17 | 2015-12-08 | 2015-12-16 | 2015-12-28 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2015 | SHS (2015) | Region VIII | Maasin City |  | SHS within San Rafael ES | CITY OF MAASIN (Capital) | 0 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 8 | 10877342.5917 |  |  | COMPLETED | 1 | [10 empty] | No Remarks
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122819 | Aguin ES | CAPUL | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2098606.04 |  |  | COMPLETED | 1 |  |  | 080615S00134 | 15IH0157 | 2015-11-26 |  | 2015-12-08
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123206 | Alegria ES | SAN ISIDRO | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 080615S00133
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303530 | Alegria NHS | SAN ISIDRO | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 11177342.5917 |  |  | Terminated | 1 |  |  | 080615S00041 | 15IH0115 | 2015-07-30 | [5 empty] | Liquidated damages to be imposed on the contractor upon completion of the project.
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303531 | Allen NHS | ALLEN | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 14947918.84 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122802 | Arellano Elementary School | BOBON | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080615S00077 | 15IH0145
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303561 | Basilio B. Chan Mem. Agricultural and Industrial Sch. | LAVEZARES | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 11122342.5917 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Northern Samar | 303561 | Basilio B. Chan Mem. Agricultural and Industrial Sch. | LAVEZARES | 1 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303534 | BIRI NHS | BIRI | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8470965.051 |  |  | Reverted | 0 |  |  | 080615S00023
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303535 | Bobon School for Philippine Craftsmen | BOBON | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080615S00024
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303536 | Buenavista NHS | ROSARIO | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2898701.124 |  |  | COMPLETED | 1 |  |  | 080615S00046 | 15IH0130 | 2015-09-30
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123115 | Bugko ES | MONDRAGON | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 080615S00138 | 15IH0147 | 2015-10-11 |  | 2015-10-24 |  |  | CTC CONSTRUCTION & SUPPLIES
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303537 | Cabacungan NHS | ALLEN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080615S00049 | 15IH0135 | 2015-09-30
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122855 | Cabayhan Elementary School | CATARMAN (Capital) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 3052592.44 |  |  | COMPLETED | 1 |  |  | 080615S00149 | 15IH0160 | 2015-11-26 |  | 2015-12-08
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123116 | Cablangan ES | MONDRAGON | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080615S00081
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303540 | Capul Agro-Industrial School | CAPUL | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8614965.051 |  |  | COMPLETED | 1 |  |  | 080615S00025
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122856 | Catarman I CS | CATARMAN (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122856 | Catarman I CS | CATARMAN (Capital) | 1 | 1 | 6 | 1STY6CL (Toilet Attached) | 2015 K10 BATCH 6 | 5322651.88 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122856 | Catarman I CS | CATARMAN (Capital) | 1 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 6 | 12621310.093 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303541 | Catarman NHS | CATARMAN (Capital) | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 080615S00003 | 15IH0116 | 2015-07-30
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122846 | Cervantes ES | CATARMAN (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080615S00137 | 15IH0138 | 2015-09-30 |  | 2015-11-18
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123084 | Curry Elementary School | LOPE DE VEGA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 3042592.44 |  |  | COMPLETED | 1 |  |  | 080615S00144 | 15IH0161 | 2015-11-26 |  | 2015-12-08
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122822 | Dalaquit PS | CAPUL | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2098606.04 |  |  | COMPLETED | 1 |  |  | 080615S00135 | 15IH0158 | 2015-11-26 |  | 2015-12-08
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303548 | Eladio T. Balite Memorial School of Fisheries | BOBON | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 080615S00026 | 15IH0117 | 2015-07-30
NC 2015 | SHS (2015) | Region VIII | NORTHERN SAMAR | 303550 | Francisca Dominice NHS | MONDRAGON | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 080615S00014 | 15IH0119 | 2015-07-30 | 2015-08-29 | 2015-09-04 | 2015-09-25 | 2015-10-16 | UBAS CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122781 | Frederick PS | ALLEN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080615S00120 | 15IH0141 | 2015-09-30 |  | 2015-11-18 |  |  | CTC CONSTRUCTION & SUPPLIES
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303543 | Galutan NHS | CATARMAN (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303543 | Galutan NHS | CATARMAN (Capital) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123086 | General Luna Elementary School | LOPE DE VEGA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 3042592.44 |  |  | COMPLETED | 1 |  |  | 080615S00140 | 15IH0162 | 2015-11-26 |  | 2015-12-08
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123225 | Gengarog ES | SAN JOSE | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080615S00086 | 15IH0148
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123088 | Getigo Elementary School | LOPE DE VEGA | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080615S00074
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 313626 | Guindaulan NHS | ROSARIO | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080615S00083
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122867 | Hibalagnan PS | CATARMAN (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080615S00085 | [7 empty] | Abandoned
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123123 | Hinabangan Elementary School | MONDRAGON | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080615S00082 | [7 empty] | Abandoned
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122870 | Imelda Elementary School | CATARMAN (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080615S00143 | 15IH0137 | 2015-09-30 |  | 2015-11-25
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122808 | J. A. Santos ES | BOBON | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2892592.44 |  |  | COMPLETED | 1 |  |  | 080615S00117 | 15IH0146 | 2015-10-11 |  | 2015-10-23
NC 2015 | SHS (2015) | Region VIII | NORTHERN SAMAR | 313605 | Leonardo M. Amigo High School | MONDRAGON | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 080615S00027 | 15IH0120 | 2015-07-30 | 2015-08-29 | 2015-09-04 | 2015-09-26 | 2015-10-16 | UBAS CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123065 | Libas ES | LAVEZARES | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | Reverted | 0 |  |  | 080615S00079
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123277 | Luisita ES | VICTORIA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080615S00124 | 15IH0142 | 2015-09-30 |  | 2015-11-18
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123227 | Mandugang PS | SAN JOSE | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080615S00139 | 15IH0143 | 2015-09-30 |  | 2015-11-18
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 313623 | Maravilla NHS | LAVEZARES | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2898701.124 |  |  | COMPLETED | 1 |  |  | 080615S00038 | 15IH0131 | 2015-09-30 |  |  |  |  | JUPA CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123279 | Maxvilla ES | VICTORIA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080615S00092
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303566 | Mondragon Agro-Ind'L HS | MONDRAGON | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080615S00029
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303567 | Mongolbongol NHS | SAN VICENTE | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | NORTHERN SAMAR | 303568 | Nenita NHS | MONDRAGON | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 080615S00021 | 15IH0121 | 2015-07-30 | 2015-08-29 | 2015-09-04 | 2015-09-23 | 2015-10-16 | UBAS CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123095 | Old Somoroy PS | LOPE DE VEGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2098606.04 |  |  | COMPLETED | 1 |  |  | 080615S00148 | 15IH0163 | 2015-11-26 |  | 2015-12-08
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123096 | Osme¤a ES | LOPE DE VEGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 080615S00147 | 15IH0164 | 2015-11-26 |  | 2015-12-08
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123097 | Paguite PS | LOPE DE VEGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2098606.04 |  |  | COMPLETED | 1 |  |  | 080615S00123 | 15IH0165 | 2015-11-26 |  | 2015-12-08
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123280 | Pasabuena ES | VICTORIA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080615S00091
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303570 | Polangi National HIgh School | CATARMAN (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303570 | Polangi National HIgh School | CATARMAN (Capital) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Northern Samar | 303570 | Polangi National HIgh School | CATARMAN (Capital) | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 193004 | R.F. Tobes Mem. School | ROSARIO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 080615S00112 | 15IH0166 | 2015-11-26 |  | 2015-12-08
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303573 | Rosario NHS | ROSARIO | 1 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123098 | Roxas PS | LOPE DE VEGA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | Reverted | 0 |  |  | 080615S00080 | 15IH0194
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303575 | San Antonio Agricultural & Vocational Sch. | SAN ANTONIO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8614965.051 |  |  | COMPLETED | 1 |  |  | 080615S00043 | [7 empty] | Original Contract Terminated on September 24, 2019; New contract completed on Feb 27, 2023 New Contract Completed on February 27, 2023.
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303576 | San Antonio NHS | BIRI | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2898701.124 |  |  | COMPLETED | 1 |  |  | 080615S00031 | 15IH0132 | 2015-09-30
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303577 | San Isidro Agro-Industrial High School | SAN ISIDRO | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 080615S00044
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303578 | San Isidro NHS (San Isidro) | SAN ISIDRO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8354965.051 |  |  | COMPLETED | 1 |  |  | 080615S00045
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303580 | San Jose Technical HS | SAN JOSE | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 11077342.5917 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123230 | San Lorenzo ES | SAN JOSE | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080615S00116 | 15IH0144 | 2015-09-30 |  | 2015-11-18
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123282 | San Miguel Elementary School | VICTORIA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080615S00090 | 15IH0195
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303582 | San Vicente School of Fisheries | SAN VICENTE | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 3060465.44 |  |  | COMPLETED | 1 |  |  | 080615S00053
NC 2015 | SHS (2015) | Region VIII | Northern Samar |  | SHS in Catarman, Northern Samar | LOPE DE VEGA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | Reverted | 0
NC 2015 | SHS (2015) | Region VIII | Northern Samar |  | SHS in Lope De Vega, Northern Samar | LOPE DE VEGA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 3102592 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Northern Samar |  | SHS in Lope De Vega, Northern Samar | LOPE DE VEGA | 1 |  | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3967969 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Northern Samar |  | SHS within Victoria Central School | LOPE DE VEGA | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122817 | SOMOROY PS | BOBON | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080615S00119 | 15IH0140 | 2015-09-30 |  | 2015-11-19
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122799 | Talisay Elementary School | BIRI | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2098606.04 |  |  | COMPLETED | 1 |  |  | 080615S00118 | 15IH0156 | 2015-11-26 |  | 2015-12-08 |  |  |  | Abandoned
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122830 | Talugaan PS | CAPUL | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2098606.04 |  |  | COMPLETED | 1 |  |  | 080615S00136 | 15IH0159 | 2015-11-26 |  | 2015-12-08 |  |  |  | Abandoned
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122800 | Tampipi Elementary School | BIRI | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | Reverted | 0 |  |  | 080615S00076
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122969 | Abaton ES | LAOANG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 080615S00156 | 15II0125 | 2015-11-30 | 2015-12-03 | 2015-12-22
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 313602 | Anito NHS | GAMAY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6431837.6381 |  |  | COMPLETED | 1 |  |  | 080615S00032 | 15II0080 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-28 | 2015-10-14 | CANANUA CONSTRUCTION AND GENERAL SUPPLY
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122953 | Aroganga ES | LAOANG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | Reverted | 0 |  |  | 080615S00087 | 15II0089 | 2015-09-07 | 2015-09-10
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122991 | Bagacay Elementary School | LAPINIG | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3967968.78 |  |  | Reverted | 0 |  |  | 080615S00159 | 15II0157 | 2015-12-14 | 2015-12-17
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 313618 | Balnasan National High School | SAN ROQUE | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123003 | Balugo ES | LAS NAVAS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Reverted | 0 |  |  | 080615S00105 | 15II0145 | 2015-12-13 | 2015-12-17
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122916 | Bangon Elementary school | GAMAY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080615S00155 | 15II0158 | 2015-12-14 | 2015-12-17
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303553 | Bangon NHS | GAMAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 080615S00034 | 15II0067 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-15 | 2015-10-26 | JUPA CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 313604 | Bantayan NHS | SAN ROQUE | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303533 | Batag NHS | LAOANG | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6375587.6381 |  |  | COMPLETED | 1 |  |  | 080615S00054 | 15II0100 | 2015-09-07 | 2015-09-10 | 2015-09-24 | 2015-10-15 | 2015-10-24 | R.C. TAGALA CONSTRUCTION | Abandoned
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122875 | Bongog ES | CATUBIG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 080615S00113 | 15II0126 | 2015-11-30 | 2015-12-03 | 2015-12-22
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122896 | Bonifacio PS | CATUBIG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080615S00088 | 15II0088 | 2015-09-07 | 2015-09-10
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123005 | Bukid Elementary School | LAS NAVAS | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080615S00062 | 15II0094 | 2015-09-10 | 2015-09-10 | 2015-09-24 | 2015-10-08 | 2015-10-19 | C D U CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123104 | Burgos ES | MAPANAS | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2952592.44 |  |  | Reverted | 0 |  |  | 080615S00101 | 15II0156 | 2015-12-14 | 2015-12-17
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122974 | Cabagngan ES | LAOANG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | Reverted | 0 |  |  | 080615S00078 | 15II0089 | 2015-09-07 | 2015-09-10
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123144 | Cabariwan PS | PALAPAG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080615S00068 | 15II0096 | 2015-09-07 | 2015-09-10 | 2015-09-22 | 2015-10-21 | 2015-10-30 | R.C. TAGALA CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 313609 | Cabatuan NHS | PALAPAG | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2705828.124 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122877 | Cagbugna PS | CATUBIG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 080615S00107 | 15II0126 | 2015-11-30 | 2015-12-03 | 2015-12-22
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303538 | Cahayagan NHS | LAOANG | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2692828.124 |  |  | COMPLETED | 1 |  |  | 080615S00013 | 15II0056 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-08-03 | 2015-08-13 | CANANUA CONSTRUCTION AND GENERAL SUPPLY
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122993 | Can Maria ES | LAPINIG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2388606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122993 | Can Maria ES | LAPINIG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122978 | Cangcahipos Elementary School | LAOANG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Reverted | 0 |  |  | 080615S00157 | 15II0155 | 2015-12-14 | 2015-12-17
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122994 | Can-omanio ES | LAPINIG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 4177212.08 |  |  | COMPLETED | 1 |  |  | 080615S00158 | 15II0152 | 2015-12-14 | 2015-12-17
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303539 | Capacujan NHS | PALAPAG | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6449597.6381 |  |  | COMPLETED | 1 |  |  | 080615S00030 | 15II0081 | 2015-08-25 | 2015-08-27 | 2015-09-03 | 2015-09-29 | 2015-10-12 | R.C. TAGALA CONSTRUCTION | Abandoned
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123008 | Catoto-ogan ES | LAS NAVAS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Reverted | 0 |  |  | 080615S00130 | 15II0144 | 2015-12-13 | 2015-12-17
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303544 | Catubig Valley NHS | CATUBIG | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 11114150.5917 |  |  | COMPLETED | 1 |  |  | 080615S00028 | 15II0084 | 2015-09-01 | 2015-09-03 | 2015-09-15 | 2015-10-23 | 2015-10-30 | JUPA CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 313619 | Dapdap NHS | LAS NAVAS | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 313619 | Dapdap NHS | LAS NAVAS | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 2915092 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123259 | Deit De Turag PS | SILVINO LOBOS | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | Reverted | 0 |  |  | 080615S00058 | 15II0097 | 2015-09-07 | 2015-09-10
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 193003 | Dolores PS | LAS NAVAS | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2952592.44 |  |  | Reverted | 0 |  |  | 080615S00111 | 15II0128 | 2015-11-30 | 2015-12-03 | 2015-12-22
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303546 | Don Juan F. Avalon National High School | SAN ROQUE | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8337464.051 |  |  | COMPLETED | 1 |  |  | 080615S00005 | 15II0060 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-14 | 2015-10-23 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123015 | F. Robis PS | LAS NAVAS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 080615S00121 | 15II0147 | 2015-12-13 | 2015-12-17
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303551 | Gala Vocational School | GAMAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8417465.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Northern Samar | 303551 | Gala Vocational School | GAMAY | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303552 | Gamay National High School | GAMAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8455443.251 |  |  | COMPLETED | 1 |  |  | 080615S00007 | 15II0068 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-14 | 2015-10-23 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123261 | Gebolwangan Elementary School | SILVINO LOBOS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | Reverted | 0 |  |  | 080615S00106 | 15II0150 | 2015-12-14 | 2015-12-17
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123260 | Gebonawan PS | SILVINO LOBOS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2098606.04 |  |  | Reverted | 0 |  |  | 080615S00114 | 15II0150 | 2015-12-14 | 2015-12-17
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123262 | Gicbo-An PS | SILVINO LOBOS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2098606.04 |  |  | Reverted | 0 |  |  | 080615S00099 | 15II0150 | 2015-12-14 | 2015-12-17
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123263 | Giguimitan PS | SILVINO LOBOS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2098606.04 |  |  | Reverted | 0 |  |  | 080615S00108 | 15II0149 | 2015-12-14 | 2015-12-17
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123018 | H. Jolejole ES | LAS NAVAS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080615S00146 | 15II0146 | 2015-12-13 | 2015-12-17
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303554 | Hibubullao NHS | CATUBIG | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 11308592.5917 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122899 | Hibulo Elementary School | CATUBIG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 4037212.08 |  |  | COMPLETED | 1 |  |  | 080615S00151 | 15II0153 | 2015-12-14 | 2015-12-17
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123020 | Imelda Elementary School | LAS NAVAS | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | Reverted | 0 |  |  | 080615S00064 | 15II0090 | 2015-09-07 | 2015-09-10
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122995 | Imelda ES | LAPINIG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 4127212.08 |  |  | COMPLETED | 1 |  |  | 080615S00163 | 15II0152 | 2015-12-14 | 2015-12-17
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 193010 | Imelda PS | SILVINO LOBOS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2098606.04 |  |  | Reverted | 0 |  |  | 080615S00160 | 15II0149 | 2015-12-14 | 2015-12-17
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123151 | Jangtud Integrated School | PALAPAG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080614S00145 | 14II0077 | 2014-12-15 | 2014-12-16 | 2014-12-29 | 2015-01-12 | 2015-01-26 | NORSATEK ENGINEERING AND CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303556 | Laoang National Technical High School | LAOANG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8383715.051 |  |  | COMPLETED | 1 |  |  | 080615S00009 | 15II0062 | 2015-08-13 | 2015-08-14 | 2015-09-01 | 2015-09-28 | 2015-10-14 | C D U CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | NORTHERN SAMAR | 303557 | Laoang NHS | LAOANG | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 080615S00010 | 15II0053 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-14 | 2015-10-23 | JUPA CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303560 | Las Navas NHS | LAS NAVAS | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10995746.5917 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123024 | Lomalaog Elementary School | LAS NAVAS | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080615S00060 | 15II0094 | 2015-09-10 | 2015-09-10 | 2015-09-24 | 2015-10-08 | 2015-10-19 | C D U CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122997 | Lo-ok ES | LAPINIG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | Reverted | 0 |  |  | 080615S00110 | 15II0157 | 2015-12-14 | 2015-12-17
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303559 | Lorenzo S. Menzon AIS | LAPINIG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8341533.051 |  |  | COMPLETED | 1 |  |  | 080615S00012 | 15II0070 | 2015-08-13 | 2015-08-20 | 2015-09-01 | 2015-09-28 | 2015-10-12 | C D U CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122903 | Lubedico PS | CATUBIG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080615S00084 | 15II0124 | 2015-11-27 | 2015-11-26 | 2015-12-10 | 2015-12-16 | 2015-12-28 | R.C. TAGALA CONSTRUCTION | Abandoned
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123028 | Macarthur ES | LAS NAVAS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 080615S00131 | 15II0146 | 2015-12-13 | 2015-12-17 |  |  |  |  | Abandoned
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123107 | Magtaon ES | MAPANAS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | Reverted | 0 |  |  | 080615S00102 | 15II0154 | 2015-12-14 | 2015-12-17
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 313622 | Magtaon NHS | MAPANAS | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080615S00067 | 15II0095 | 2015-09-07 | 2015-09-10 | 2015-09-24 | 2015-10-14 | 2015-10-23 | C D U CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122933 | Malidong ES | GAMAY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 080615S00154 | 15II0127 | 2015-11-30 | 2015-12-03 | 2015-12-22
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123030 | Mamaro ES | LAS NAVAS | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080615S00072 | 15II0093 | 2015-09-07 | 2015-09-10 | 2015-09-22 | 2015-10-01 | 2015-10-14 | EDISON DEVELOPMENT CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122888 | Manering ES | CATUBIG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2098606.04 |  |  | COMPLETED | 1 |  |  | 080615S00145 | 15II0153 | 2015-12-14 | 2015-12-17
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303564 | Mapanas Agro-Industrial High School | MAPANAS | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 11042342.5917 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303565 | Marubay NHS | LAOANG | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 080615S00097 | 15II0101 | 2015-09-28 | 2015-10-01 | 2015-10-13 | 2015-10-23 | 2015-11-06 | SOLID M CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123031 | Matelarag Elementary | LAS NAVAS | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 080615S00129 | 15II0129 | 2015-11-30 | 2015-12-03 | 2015-12-22
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123158 | Nagbobtac Elementary School | PALAPAG | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | Terminated | 0 |  |  | 080615S00069 | 15II0096 | 2015-09-07 | 2015-09-10 | 2015-09-22 | 2015-10-21 | 2015-10-30 | R.C. TAGALA CONSTRUCTION | (1) Contract was TERMINATED partly for convenience as stipulated under Section III.B. Annex I of the 2016 Revised IRR of RA 9184 which was caused by inaccessibility to the project site (Nagbobtac ES). (2) Site Validation with representative from DepEd will be undertaken since the said school is included in the proposed CY 2024 BEFF New Construction of Classrooms.
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122983 | Oleras ES | LAOANG | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080615S00070 | 15II0095 | 2015-09-07 | 2015-09-10 | 2015-09-24 | 2015-10-14 | 2015-10-23 | C D U CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 313624 | Oleras NHS | LAOANG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8228232.851 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123032 | Osmeña PS | LAS NAVAS | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2952592.44 |  |  | Reverted | 0 |  |  | 080615S00115 | 15II0128 | 2015-11-30 | 2015-12-03 | 2015-12-22
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123033 | Paco ES | LAS NAVAS | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080615S00061 | 15II0091 | 2015-09-07 | 2015-09-10 | 2015-09-22 | 2015-10-01 | 2015-10-14 | EDISON DEVELOPMENT CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303569 | Pambujan NHS | PAMBUJAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080615S00004 | 15II0063 | 2015-07-14 | 2015-07-17 | 2015-07-30 | 2015-08-25 | 2015-09-09 | C D U CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123110 | Pangudtan PS | MAPANAS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2098606.04 |  |  | Reverted | 0 |  |  | 080615S00103 | 15II0154 | 2015-12-14 | 2015-12-17
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123035 | Quezon Elementary | LAS NAVAS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080615S00125 | 15II0148 | 2015-12-13 | 2015-12-17
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123036 | Quirino Elementary School | LAS NAVAS | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | Reverted | 0 |  |  | 080615S00059 | 15II0090 | 2015-09-07 | 2015-09-10
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 313603 | Rawis National High School | LAOANG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264385.851 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123038 | Rizal ES | LAS NAVAS | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | Reverted | 0 |  |  | 080615S00075 | 15II0092 | 2015-09-07 | 2015-09-10
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122910 | Roxas ES | CATUBIG | 2 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | Reverted | 0 |  |  | 080615S00093 | 15II0159 | 2015-12-14 | 2015-12-17
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123040 | Rufino Elementary School | LAS NAVAS | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | Reverted | 0 |  |  | 080615S00063 | 15II0092 | 2015-09-07 | 2015-09-10
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123041 | Sag-od PS | LAS NAVAS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 080615S00126 | 15II0145 | 2015-12-13 | 2015-12-17
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123043 | San Antonio ES | LAS NAVAS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080615S00127 | 15II0148 | 2015-12-13 | 2015-12-17
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123048 | San Jose ES | LAS NAVAS | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | Reverted | 0 |  |  | 080615S00128 | 15II0129 | 2015-11-30 | 2015-12-03 | 2015-12-22
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 313616 | San Miguel National High School | LAS NAVAS | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2745828.124 |  |  | Reverted | 0 |  |  | 080615S00015 | 15II0057 | 2015-10-20 | 2015-10-26
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303581 | San Roque-Pambujan Vocational High Sch. | PAMBUJAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8239675.051 |  |  | COMPLETED | 1 |  |  | 080615S00037 | 15II0061 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-14 | 2015-10-23 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122913 | San Vicente ES | CATUBIG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 080615S00152 | 15II0127 | 2015-11-30 | 2015-12-22
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 313617 | San Vicente National High School | CATUBIG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123185 | Senonogan ES | PAMBUJAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | Reverted | 0 |  |  | 080615S00104 | 15II0155 | 2015-12-14 | 2015-12-17
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123268 | Silvino Lubos CS | SILVINO LOBOS | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8524965.051 |  |  | Reverted | 0 |  |  | 080615S00109 | 15II0130 | 2015-11-30 | 2015-12-17 | 2015-12-22
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303583 | Silvino Lubos Vocational High School | SILVINO LOBOS | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 9056149.051 |  |  | Reverted | 0 |  |  | 080615S00017 | 15II0064 | 2015-11-30 | 2015-12-03 | 2015-12-22
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 193011 | Sta. Potenciana ES | MAPANAS | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2922592.44 |  |  | COMPLETED | 1 |  |  | 080615S00153 | 15II0156 | 2015-12-14 | 2015-12-17
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123050 | Sto. Tomas PS | LAS NAVAS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 4077212.08 |  |  | COMPLETED | 1 |  |  | 080615S00122 | 15II0147 | 2015-12-13 | 2015-12-17
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303584 | SUMOROY AGRO-INDUSTRIAL SCHOOL | PALAPAG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8792465.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Northern Samar | 303584 | SUMOROY AGRO-INDUSTRIAL SCHOOL | PALAPAG | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 3007049.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123052 | Tagan-ayan ES | LAS NAVAS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Reverted | 0 |  |  | 080615S00100
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122892 | Tangbo ES | CATUBIG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080615S00089 | 15II0088
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 313625 | Taylor NHS (Las Navas NHS Annex) | LAS NAVAS | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080615S00065 | 15II0091 | 2015-09-07 | 2015-09-10 | 2015-09-22 | 2015-10-01 | 2015-10-14 | EDISON DEVELOPMENT CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 123269 | Victory PS | SILVINO LOBOS | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | Reverted | 0 |  |  | 080615S00071 | 15II0097 | 2015-09-07 | 2015-09-10
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 303586 | Vigo National High School | LAOANG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 080615S00019 | 15II0066 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-15 | 2015-10-26 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2015 | K10 (2015) | Region VIII | Northern Samar | 122951 | Yapas ES | LAOANG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 080615S00150 | 15II0125 | 2015-11-30 | 2015-12-03 | 2015-12-22
NC 2015 | SHS (2015) | Region VIII | Northern Samar | 313621 | Zoilo T. Lobos Memorial High School | PAMBUJAN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Ormoc City | 313903 | Cabintan National High School | ORMOC CITY | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1 |  |  | 080215S00043 | 15IF0072 | 2015-06-04 | 2015-06-10 | 2015-07-24 | 2015-07-29 | 2015-08-18 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region VIII | Ormoc City | 124146 | Cambantog Primary School | ORMOC CITY | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | REVERTED | 0 |  |  | 080215S00217 | 15IF0124 | 2015-08-24
NC 2015 | K10 (2015) | Region VIII | Ormoc City | 124176 | Catmon Elementary School | ORMOC CITY | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 080215S00219 | 15IF0123 | 2015-08-24 | 2015-08-27 | 2015-09-14 | 2015-09-22 | 2015-10-07 | ROLANDO M. VILLASENCIO CONSTRUCTION & GENERAL SERV
NC 2015 | SHS (2015) | Region VIII | Ormoc City | 303654 | Dolores National High School | ORMOC CITY | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Ormoc City | 303661 | Genero B. Lureñana National High School | ORMOC CITY | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8219965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Ormoc City | 303661 | Genero B. Lureñana National High School | ORMOC CITY | 4 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Ormoc City | 303655 | Ipil National High School | ORMOC CITY | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00040 | 15IF0063 | 2015-06-04 | 2015-06-10 | 2015-07-24 | 2015-07-29 | 2015-08-18 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VIII | Ormoc City | 313906 | Julian Gantuangco NHS | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Ormoc City | 313901 | Lilo-an National High School | ORMOC CITY | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00039 | 15IF0064 | 2015-06-04 | 2015-06-10 | 2015-07-24 | 2015-07-29 | 2015-08-18 | RJIR ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Ormoc City | 303656 | Linao National High School | ORMOC CITY | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 080215S00037 | 15IF0065 | 2015-06-04 | 2015-06-10 | 2015-07-24 | 2015-07-29 | 2015-08-18 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VIII | Ormoc City | 303657 | Margen National High School | ORMOC CITY | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00007 | 15IF0067 | 2015-06-04 | 2015-06-10 | 2015-07-24 | 2015-07-29 | 2015-10-01 | RJIR ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Ormoc City | 313904 | Matica-a National High School | ORMOC CITY | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080215S00047 | 15IF0073 | 2015-06-04 | 2015-06-10 | 2015-07-24 | 2015-07-29 | 2015-08-18 | JA ACHACOSO ENTERPRISES & GENERAL SERVICES
NC 2015 | K10 (2015) | Region VIII | Ormoc City | 124186 | Monterico Elementary School | ORMOC CITY | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00211 | 15IF0125 | 2015-08-24 | 2015-08-27 | 2015-09-14 | 2015-09-22 | 2015-10-07 | RJIR ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Ormoc City | 303658 | New Ormoc City NHS | ORMOC CITY | 4 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 5 | 35596257 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Ormoc City | 303658 | New Ormoc City NHS | ORMOC CITY | 4 |  | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31602890 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Ormoc City | 124167 | Patag Elementary School | ORMOC CITY | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080215S00228 | 15IF0126 | 2015-08-24 | 2015-08-27 | 2015-09-14 | 2015-09-22 | 2015-10-07 | ROLANDO M. VILLASENCIO CONSTRUCTION & GENERAL SERV
NC 2015 | SHS (2015) | Region VIII | Ormoc City | 313902 | Pedro G. Bañez National High School | ORMOC CITY | 4 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3714886.575 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Ormoc City | 303660 | Rustico Capahi Sr. Memorial National High School | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Ormoc City | 124219 | San Isidro Elementary School | ORMOC CITY | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080215S00131 | 15IF0097 | 2015-07-28 | 2015-07-31 | 2015-08-13 | 2015-08-25 | 2015-10-01 | ARCA BUILDERS
NC 2015 | SHS (2015) | Region VIII | Ormoc City |  | SHS in Ormoc City | ORMOC CITY | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Ormoc City | 303662 | Valencia National High School | ORMOC CITY | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 080215S00065 | 15IF0066 | 2015-06-04 | 2015-06-10 | 2015-07-24 | 2015-08-10 | 2015-10-01 | COLLERA CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303588 | Almagro NHS | ALMAGRO | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 080415S00023
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 313724 | Balocawe Integrated School | TAGAPUL-AN | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 313724 | Balocawe Integrated School | TAGAPUL-AN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123833 | Balugo ES | TARANGNAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00138
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 193515 | Bangon PS | TARANGNAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080415S00076
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303590 | Baquiw NHS | TAGAPUL-AN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 080415S00127 | 15IJ-0184 | 2015-09-22 | 2015-10-04 | 2015-10-05 | 2015-10-09 | 2015-10-13 | C D U CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123836 | Bisitahan ES | TARANGNAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Reverted | 0 |  |  | 080415S00139
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123837 | Bonga ES | TARANGNAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Reverted | 0 |  |  | 080415S00140
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123804 | Buenavista ES | SANTO NIÑO | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080415S00094 | 15IJ-0141 | 2015-08-10 | 2015-08-22 | 2015-08-23 | 2015-09-18 | 2015-09-22 | B. VICENCIO CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303619 | Buenavista NHS | SAN JORGE | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123651 | Buenos Aires ES | PAGSANGHAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00159 | 15IJ-0175 | 2015-09-09 | 2015-09-21 | 2015-09-22 | 2015-09-26 | 2015-09-30 | JFR CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 313714 | Buenos Aires Integrated School | PAGSANGHAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080415S00090 | 15IJ-0144 | 2015-08-25 | 2015-09-06 | 2015-09-07 | 2015-09-11 | 2015-09-15 | ND CARANZO BUILDERS AND CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123685 | Bulao ES | SAN JORGE | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080415S00081 | 15IJ-0101 | 2015-07-09 | 2015-07-21 | 2015-07-22 | 2015-07-26 | 2015-08-01 | MAGA CONSTRUCTION AND SUPPLIES
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 313703 | Cabunga-an Integrated School | SANTO NIÑO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1 |  |  | 080415S00110
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123538 | Casandig ES | GANDARA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080415S00086 | 15IJ-0137 | 2015-08-06 | 2015-08-18 | 2015-08-19 | 2015-08-23 | 2015-08-28 | JFR CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123506 | Caugbusan ES | GANDARA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | Reverted | 0 |  |  | 080415S00083 | 15ij-0152 | 2015-08-16 | 2015-08-28 | 2015-08-29
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303599 | Clarencio Calagos Mem SOF | SANTA MARGARITA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080415S00022 | 15IJ-0112 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-07-30 | 2015-08-14 | B. VICENCIO CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303600 | Costa Rica NHS | ALMAGRO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 080415S00126 | 15IJ-0183 | 2015-09-22 | 2015-10-04 | 2015-10-05 | 2015-10-09 | 2015-10-13 | JFR CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123541 | Diaz ES | GANDARA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00155 | 15IJ-0036 | 2015-09-09 | 2015-09-21 | 2015-09-22 | 2015-09-26 | 2015-09-30 | JFR CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123692 | Gayondato ES | SAN JORGE | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080415S00091 | 15IJ-0153 | 2015-08-16 | 2015-08-28 | 2015-08-29
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123693 | Guadalupe ES | SAN JORGE | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Reverted | 0 |  |  | 080415S00160
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123695 | Himay PS | SAN JORGE | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00161
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123545 | Hinogacan ES | GANDARA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080415S00088 | 15IJ-0145 | 2015-08-25 | 2015-09-06 | 2015-09-07 | 2015-09-11 | 2015-09-15 | VCD CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123290 | Imelda ES | ALMAGRO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2098606.04 |  |  | COMPLETED | 1 |  |  | 080415S00190
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 193536 | Inubod PS | MATUGUINAO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Reverted | 0 |  |  | 080415S00143
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123698 | Libertad ES | SAN JORGE | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | Reverted | 0 |  |  | 080415S00092 | 15IJ-0154 | 2015-08-16 | 2015-08-28 | 2015-08-29
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123699 | Lincoro PS | SAN JORGE | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00162
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123292 | Lunang I ES | ALMAGRO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00151
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123732 | Mahayag ES | SANTA MARGARITA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | Reverted | 0 |  |  | 080415S00100 | 15IJ-0155 | 2015-08-16 | 2015-08-28 | 2015-08-29
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 313722 | Majacob Integrated School | TARANGNAN | 1 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 3 | 12771310.093 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 313722 | Majacob Integrated School | TARANGNAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123515 | Makugo ES | GANDARA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00152
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123701 | Matalud ES | SAN JORGE | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Reverted | 0 |  |  | 080415S00144
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123733 | Matayonas ES | SANTA MARGARITA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080415S00082 | 15IJ-0156 | 2015-08-16 | 2015-08-28 | 2015-08-29
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303612 | Matuguinao NHS | MATUGUINAO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080415S00021 | 15IJ-0104 | 2015-07-12 | 2015-07-24 | 2015-07-25 | 2015-07-29 | 2015-09-02 | ADB DYNAMIC BUILDERS & SUPPLY
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123702 | Mobo-Ob PS | SAN JORGE | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00164
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 193508 | Mombon ES | SAN JORGE | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Reverted | 0 |  |  | 080415S00149
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123752 | Nabulo Elem. School | SANTA MARGARITA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | REVERTED | 0 |  |  | 080415S00136
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123518 | Napalisan Elementary School | GANDARA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00153 | 15IJ-0181 | 2015-09-09 | 2015-09-21 | 2015-09-22 | 2015-09-26 | 2015-09-30 | JFR CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303635 | Oeste NHS | TARANGNAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 080415S00132 | 15IJ-0187 | 2015-09-23 | 2015-10-05 | 2015-10-06 | 2015-10-10 | 2015-10-14 | B. VICENCIO CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303615 | Pagsanghan NHS | PAGSANGHAN | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 080415S00020 | 15IJ-0142 | 2015-08-10 | 2015-08-22 | 2015-08-23 | 2015-09-18 | 2015-09-22 | B. VICENCIO CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123520 | Palanas ES | GANDARA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080415S00084 | 15IJ-0133 | 2015-08-10 | 2015-08-22 | 2015-08-23 | 2015-08-27 | 2015-09-02 | RNMK CONSTRUCTION AND DEVELOPMENT
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123754 | Panabatan Elementary School | SANTA MARGARITA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 080415S00137
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 313712 | Piñaplata Integrated School | GANDARA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 313712 | Piñaplata Integrated School | GANDARA | 1 |  | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 313712 | Piñaplata Integrated School | GANDARA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303618 | Ramon T. Diaz MHS | GANDARA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303618 | Ramon T. Diaz MHS | GANDARA | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Samar (Western Samar) | 303618 | Ramon T. Diaz MHS | GANDARA | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2629549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 193504 | Rizal PS 2 | MATUGUINAO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00141
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123706 | Rosalim ES | SAN JORGE | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080415S00095 | 15IJ-0110 | 2015-07-13 | 2015-07-25 | 2015-07-26 | 2015-07-30 | 2015-08-14 | B. VICENCIO CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123556 | San Agustin ES | GANDARA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00165 | 15IJ-0182 | 2015-09-09 | 2015-09-21 | 2015-09-22 | 2015-09-26 | 2015-09-30 | ND CARANZO BUILDERS AND CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123707 | San Isidro ES | SAN JORGE | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Reverted | 0 |  |  | 080415S00156
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123557 | San Isidro PS | MATUGUINAO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Reverted | 0 |  |  | 080415S00157
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123708 | San Jorge CS | SAN JORGE | 1 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 6 | 14971327.92 |  |  | COMPLETED | 1 |  |  | 080415S00142
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 313708 | San Jorge NHS | SAN JORGE | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123560 | San Pelayo ES | GANDARA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00150 | 15IJ-0177 | 2015-09-09 | 2015-09-21 | 2015-09-22 | 2015-09-26 | 2015-09-30 | JFR CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123528 | Sidmon ES | GANDARA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080415S00085 | 15IJ-0149 | 2015-08-16 | 2015-08-28 | 2015-08-29 | 2015-09-04 | 2015-09-15 | ND CARANZO BUILDERS AND CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123529 | Sta. Elena ES | GANDARA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 5605184.88 |  |  | COMPLETED | 1 |  |  | 080415S00154
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303629 | Sta. Margarita NHS | SANTA MARGARITA | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080415S00018 | 15IJ-0137 | 2015-08-06 | 2015-08-18 | 2015-08-19 | 2015-08-23 | 2015-08-28 | JFR CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303632 | Sto. Nino NHS | SANTO NIÑO | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303633 | Tagapul-an NHS | TAGAPUL-AN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080415S00016 | 15IJ-0148 | 2015-08-16 | 2015-08-28 | 2015-08-29 | 2015-09-04 | 2015-09-15 | B. VICENCIO CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303634 | Tarangnan NHS | TARANGNAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080415S00031 | 15IJ-0147 | 2015-08-25 | 2015-09-06 | 2015-09-07 | 2015-09-11 | 2015-09-15 | B. VICENCIO CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123862 | Tigdaranao ES | TARANGNAN | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080415S00061 | 15IJ-0135 | 2015-08-10 | 2015-08-22 | 2015-08-23 | 2015-08-27 | 2015-09-02 | JFR CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 313729 | Tizon National High School | TARANGNAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080415S00070 | 15IJ-0135 | 2015-08-10 | 2015-08-22 | 2015-08-23 | 2015-08-27 | 2015-09-02 | JFR CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303638 | Villahermosa NHS | SANTO NIÑO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 080415S00122 | 15IJ-0185 | 2015-09-22 | 2015-10-04 | 2015-10-05 | 2015-10-09 | 2015-10-13 | JFR CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123933 | Aguingayan PS | SAN JOSE DE BUAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080415S00214
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123328 | Amandayehan ES | BASEY | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080415S00065 | 15IK0035 | 2015-08-06 | 2015-08-19 | 2015-08-20 | 2015-08-27 | 2015-09-03 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123356 | Antol PS | CALBIGA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080415S00069
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123565 | Bagacay ES | HINABANGAN | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080415S00064 | 15iK029 | 2015-08-05 | 2015-08-18 | 2015-08-18 | 2015-08-27 | 2015-09-03 | RICHMARK CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 313719 | Bagacay NHS-Daram NHS Annex | DARAM | 2 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 313719 | Bagacay NHS-Daram NHS Annex | DARAM | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 313709 | Bakhaw NHS | DARAM | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123307 | Basey I Central Elem. school | BASEY | 2 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123307 | Basey I Central Elem. school | BASEY | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303592 | Basey National High School | BASEY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Samar (Western Samar) | 303592 | Basey National High School | BASEY | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123582 | Bawang ES | JIABONG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00197 | [7 empty] | No Remarks
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123913 | Binogho ES | PARANAS (WRIGHT) | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080415S00077 | 15IK0036 | 2015-08-06 | 2015-08-18 | 2015-08-20 | 2015-09-04 | 2015-09-07 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP. | No Remarks
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123310 | Binugho ES | BASEY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00135 | 15-0038-39 | 2015-11-17 | 2015-11-19 | 2015-12-01 | 2015-12-05 | 2015-12-10 | By Administration
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 313707 | Bioso Integrated School | ZUMARRAGA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 080415S00118 | 15IK0061 | 2015-10-21 | 2015-10-23 | 2015-11-05 | 2015-11-13 | 2015-11-17 | VCD CONSTRUCTION | No Remarks
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303595 | Birawan NHS | DARAM | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | [10 empty] | No Remarks
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 193511 | Bonga ES | VILLAREAL | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00176 | 15 0072 & 15 0073 | 2015-12-13 | 2015-12-18 | 2015-12-28 |  |  | By Administration
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303593 | Burgos IS | BASEY | 2 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 2 | 12771310.093 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123367 | Caamlungan ES | CALBIGA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080415S00063
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123448 | Cabac ES | DARAM | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00167 | 15 0053 & 15 0054 | 2015-11-30 | 2015-12-03 | 2015-12-15 | 2015-12-22 | 2015-12-23 | By Administration
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123761 | Cadaragan ES | SANTA RITA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 080415S00195 | 15 0049 & 15 0050 | 2015-11-30 | 2015-12-03 | 2015-12-15 | 2015-12-22 | 2015-12-23 | By Administration
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123450 | Cagboboto PS | DARAM | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00183 | 15 0055 & 15 0056 | 2015-11-30 | 2015-12-03 | 2015-12-15 | 2015-12-22 | 2015-12-24 | By Administration
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303596 | Calapi NHS | MOTIONG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080415S00012 | 15IK0019 | 2015-07-21 | 2015-07-23 | 2015-08-04 | 2015-08-19 | 2015-08-25 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123762 | Calbang ES | SANTA RITA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00196 | 15 0059 & 15 0060 | [5 empty] | By Administration
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303597 | CALBIGA NATIONAL HIGH SCHOOL | CALBIGA | 2 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 1 | 18822268.79 |  |  | COMPLETED | 1 |  |  | 080415S00011 | 15 IK 0067 | 2015-12-01 | 2015-12-04 | 2015-12-22
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123629 | Canatuan ES | MOTIONG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080415S00066 | [7 empty] | No Remarks
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123630 | Candumacol ES | MOTIONG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080415S00067
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123663 | Canlobo ES | PINABACDAO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080415S00075 | [7 empty] | No Remarks
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 193547 | Canmanila ES | BASEY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00180 | 15 0057 & 15 0058
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303598 | Casandig National High School | PARANAS (WRIGHT) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 313711 | Casapa National High School | JIABONG | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3667969 |  |  | REVERTED | 0
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123588 | Catalina ES | JIABONG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00189 | 15 0070 & 15 0071 | 2015-12-14 | 2015-12-18 | 2015-12-28 |  |  | By Administration
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 313725 | Dampigan NHS | SANTA RITA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080415S00079 | 15IK0037 | 2015-08-06 | 2015-08-20 | 2015-08-20 | 2015-09-04 | 2015-09-07 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303601 | Daram NHS | DARAM | 2 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 2 | 18722268.79 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Samar (Western Samar) | 303601 | Daram NHS | DARAM | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123590 | Dogongan ES | JIABONG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00182
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123574 | Fatima ES | HINABANGAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00187 | 15 0051 & 15 0052 | 2015-11-30 | 2015-12-03 | 2015-12-15 | 2015-12-22 | 2015-12-24 | By Administration
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123942 | Galutan Primary School | SAN JOSE DE BUAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080415S00172 | [7 empty] | No Remarks
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123481 | Guindapunan PS | DARAM | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080415S00060
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303605 | Guintarcan NHS | VILLAREAL | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1 | [10 empty] | No Remarks
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303605 | Guintarcan NHS | VILLAREAL | 2 |  | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123873 | Himyangan ES | VILLAREAL | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00174 | 15-0063 & 15 0064 | [5 empty] | By Administration
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303606 | Hinabangan NHS | HINABANGAN | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 080415S00010 | 15IK0042 | 2015-09-28 | 2015-10-14 | 2015-10-14 | 2015-10-20 | 2015-10-21 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 193545 | Hinaga PS | JIABONG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00179 | [7 empty] | No Remarks
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123372 | Hindang PS | CALBIGA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080415S00059 | [7 empty] | No Remarks
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303608 | Independencia NHS | TALALORA | 2 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 1 | 18522268.79 |  |  | COMPLETED | 1 | [10 empty] | Project is at island Municipality, Delayed due to bad weather condition.
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303609 | Jiabong NHS | JIABONG | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123666 | Lale ES | PINABACDAO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 080415S00194 | 15-0032 | 2015-11-17 | 2015-11-19 | 2015-12-01 | 2015-12-08 | 2015-12-10 | By Administration
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 313728 | Lamingao National High School | VILLAREAL | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080415S00087 | 15IK0032 | 2015-08-05 | 2015-08-17 | 2015-08-18 | 2015-08-27 | 2015-09-03 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123317 | Loog ES | BASEY | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080415S00072 | 15IK0034 | 2015-08-06 | 2015-08-18 | 2015-08-20 | 2015-09-04 | 2015-09-07 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP. | Delayed due to inacccsibility of hauling Materials to project site.
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123375 | Lubang Primary School | CALBIGA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00147
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 313727 | Mabini NHS | BASEY | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 313727 | Mabini NHS | BASEY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123377 | Mahangcao ES | CALBIGA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00148
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 193542 | Malihao PS | HINABANGAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00177 | 15-0043 and 15 0044 | 2015-11-28 | 2015-12-03 | 2015-12-14 | 2015-12-21 | 2015-12-22 | By Administration
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 313710 | Malino National High School | JIABONG | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 | [10 empty] | Project is already completed based on DPWH POW and Contract.
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 313710 | Malino NHS | JIABONG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123344 | Manila-Ay ES | BASEY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00146 | 15-0034&15-0035 | 2015-11-17 | 2015-11-19 | 2015-12-01 | 2015-12-08 | 2015-12-10 | By Administration
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123319 | Manlilinab ES | BASEY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00145 | 15-0036 &37 | 2015-11-17 | 2015-11-19 | 2015-12-01 | 2015-12-08 | 2015-12-10 | By Administration
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123456 | Man-ngere ES | DARAM | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00163 | 15 0061 & 15 0062 | [5 empty] | By Administration
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303611 | Marabut NHS | MARABUT | 2 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 2 | 12771310.093 |  |  | COMPLETED | 1 |  |  | 080415S00046
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123974 | Marapilit ES | ZUMARRAGA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080415S00181
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123950 | Maylobe Elementary School | PARANAS (WRIGHT) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080415S00188
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303613 | Motiong NHS | MOTIONG | 2 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 2 | 18222268.79 |  |  | COMPLETED | 1 |  |  | 080415S00045 | 15 IK 0063 | 2015-11-25 | 2015-11-27 | 2015-12-10 | 2015-12-17 | 2015-12-21 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303602 | Mualbual National High School | ZUMARRAGA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303602 | Mualbual National High School | ZUMARRAGA | 2 |  | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3667969 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303594 | Old San Agustin NHS | BASEY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 080415S00109 | 15IK0054 | 2015-10-14 | 2015-10-16 | 2015-10-29 | 2015-11-05 | 2015-11-09 | STEVEN CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303614 | Osmeña NHS | MARABUT | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123644 | Oyandik ES | MOTIONG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00191
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123953 | Pagsang-an ES | PARANAS (WRIGHT) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 080415S00168
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123977 | Pangdan ES | ZUMARRAGA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 4077212.08 |  |  | COMPLETED | 1 |  |  | 080415S00173
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303616 | Parasan NHS | DARAM | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 080415S00115 | 15IK0057 | 2015-10-21 | 2015-10-23 | 2015-11-05 | 2015-11-13 | 2015-11-17 | STEVEN CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 313723 | Parasanon National High School | PINABACDAO | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080415S00078 | 15IK0031 | 2015-08-05 | 2015-08-18 | 2015-08-18 | 2015-08-27 | 2015-09-03 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303617 | Pinabacdao NHS | PINABACDAO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 080415S00015 | 00050 | 2015-11-17 | 2015-11-19 | 2015-12-01 | 2015-12-08 | 2015-12-10 | By Administration
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 313702 | Plaridel NHS | VILLAREAL | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 313718 | Primitivo T. Torrechiva National High School | VILLAREAL | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6709337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303640 | Quintin Quijano Sr. Agricultural School | PINABACDAO | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 11177342.5917 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 193543 | Rawis ES | HINABANGAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 080415S00178 | 15 0068 & 15 0069 | 2015-12-14 | 2015-12-18 | 2015-12-28 |  |  | By Administration
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 500022 | Rizal Integrated School | DARAM | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 080415S00131
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123955 | Salvacion PS | SAN JOSE DE BUAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00169 | [7 empty] | No Remarks
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303625 | San Andres NHS | VILLAREAL | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 080415S00116 | 15Ik0053 | 2015-10-14 | 2015-10-16 | 2015-10-29 | 2015-11-05 | 2015-11-09 | MAGA CONSTRUCTION AND SUPPLIES
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 313715 | San Fernando NHS | BASEY | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080415S00071
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 313721 | San Isidro NHS | ZUMARRAGA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303626 | San Jose de Buan NHS | SAN JOSE DE BUAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 |  |  | 080415S00038 | 15 IK 0023 | 2015-07-22 | 2015-07-24 | 2015-08-17 | 2015-08-26 | 2015-09-02 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123492 | San Miguel PS | DARAM | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00186
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303627 | San Sebastian NHS | SAN SEBASTIAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123648 | Sarao ES | MOTIONG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00192
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303628 | Simeon Ocdol NHS | BASEY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080415S00047 | 15IK0047 | 2015-09-28 | 2015-10-09 | 2015-10-22 | 2015-11-05 | 2015-11-09 | C D U CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303631 | Sta. Rita NHS | SANTA RITA | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 11077342.5917 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123649 | Sto. Niño ES | MOTIONG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00193
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123959 | Sto. Nino PS | PARANAS (WRIGHT) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 080415S00170
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303603 | Sua NHS | DARAM | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123981 | Talib Elementary School | ZUMARRAGA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 080415S00166
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123467 | Talisay ES | DARAM | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00185
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123960 | Tapul Elementary School | PARANAS (WRIGHT) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00171
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123390 | Tinago Elementary School | CALBIGA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080415S00158
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303636 | Tominamos Integrated School | SANTA RITA | 2 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 2 | 18222268.79 |  |  | COMPLETED | 1 |  |  | 080415S00049 | 151K0064 | 2015-11-25 | 2015-11-27 | 2015-12-10 | 2015-12-17 | 2015-12-21 | B. VICENCIO CONSTRUCTION
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123983 | Tubigan ES | ZUMARRAGA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2962592.44 |  |  | COMPLETED | 1 |  |  | 080415S00175 | 15-0047 -150048 | 2015-11-28 | 2015-12-03 | 2015-12-14 | 2015-12-22 | 2015-12-23 | By Administration
NC 2015 | K10 (2015) | Region VIII | Samar (Western Samar) | 123801 | Union ES | SANTA RITA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 3877212.08 |  |  | COMPLETED | 1 |  |  | 080415S00184
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303637 | Valeriano C. Yancha Mem. Agr'l. Sch. | BASEY | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Samar (Western Samar) | 303637 | Valeriano C. Yancha Mem. Agr'l. Sch. | BASEY | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303639 | Villareal NHS | VILLAREAL | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080415S00006 | 15IK0021 | 2015-07-21 | 2015-07-23 | 2015-08-04 | 2015-08-19 | 2015-08-25 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303641 | Wright NHS | PARANAS (WRIGHT) | 2 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 2 | 18222268.79 |  |  | COMPLETED | 1 |  |  | 080415S00052 | 15IK0065 | 2015-11-25 | 2015-11-27 | 2015-12-10 | 2015-12-17 | 2015-12-21 | STEVEN CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region VIII | Samar (Western Samar) | 303643 | Zumarraga National School | ZUMARRAGA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 |  |  | 080415S00017 | 15 IK 0024 | 2015-07-22 | 2015-07-24 | 2015-08-17 | 2015-08-26 | 2015-09-02 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2015 | SHS (2015) | Region VIII | Southern Leyte | 303444 | Anahawan National Vocational High School | ANAHAWAN | 0 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 |  |  | 080315S00027 | 15-IL-0122 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-18 | 2015-08-26 | 888 ACY ENTERPRISES
NC 2015 | K10 (2015) | Region VIII | Southern Leyte | 121996 | Bontoc Central School | BONTOC | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 12638675.2761 |  |  | COMPLETED | 1 |  |  | 080315S00051 | 15-IL-0153 | 2015-10-22 | 2015-10-22 | 2015-11-04 | 2015-12-22 | 2015-12-31 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2015 | SHS (2015) | Region VIII | Southern Leyte | 313403 | Bontoc National High School | BONTOC | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Southern Leyte | 313403 | Bontoc National High School | BONTOC | 0 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region VIII | Southern Leyte | 122025 | Bugho Elementary School | HINUNANGAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080315S00048 | 15-IL-0156 | 2015-10-22 | 2015-10-22 | 2015-11-04 | 2015-11-13 | 2015-11-25 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2015 | K10 (2015) | Region VIII | Southern Leyte | 122205 | Caraatan Elementary School | MALITBOG | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | Reverted | 0 |  |  | 080315S00050
NC 2015 | K10 (2015) | Region VIII | Southern Leyte | 122029 | Catublian Elementary School | HINUNANGAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080315S00049 | 15-IL-0157 | 2015-10-22 | 2015-10-22 | 2015-11-04 | 2015-11-13 | 2015-11-25 | 888 ACY ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Southern Leyte | 303453 | Don Agustin F. Escaño NHS | TOMAS OPPUS | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 080315S00015 | 15-IL-0117 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-18 | 2015-08-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2015 | K10 (2015) | Region VIII | Southern Leyte | 192005 | Guinsangaan Elementary School | BONTOC | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 080315S00047 | 15-IL-0154 | 2015-09-22 | 2015-09-24 | 2015-10-05 | 2015-10-15 | 2015-10-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2015 | K10 (2015) | Region VIII | Southern Leyte | 122098 | Habay Elementary School | SAN FRANCISCO | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080315S00044 | 15-IL-0145 | 2015-08-11 | 2015-08-13 | 2015-09-16 | 2015-09-24 | 2015-10-05 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2015 | SHS (2015) | Region VIII | Southern Leyte | 303460 | Himbangan National High School | SAINT BERNARD | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080315S00025 | 15-IL-0121 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-18 | 2015-08-26 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2015 | K10 (2015) | Region VIII | Southern Leyte | 122291 | Hindag-An ES | SAINT BERNARD | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080315S00045 | 15-IL-0155 | 2015-10-22 | 2015-10-22 | 2015-11-04 | 2015-11-13 | 2015-11-25 | 888 ACY ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Southern Leyte | 303461 | Hingatungan NHS | SILAGO | 0 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1 |  |  | 080315S00029 | 15-IL-0125 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-18 | 2015-08-26 | 888 ACY ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Southern Leyte | 303447 | Hinunangan National High School(Canipaan NHS - Hinunangan Annex) | HINUNANGAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Southern Leyte | 303447 | Hinunangan National High School(Canipaan NHS - Hinunangan Annex) | HINUNANGAN | 0 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Southern Leyte | 303462 | Ichon NHS | MACROHON | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080315S00022 | 15-IL-0114 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-18 | 2015-08-26 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region VIII | Southern Leyte | 192015 | Imelda Primary School | SILAGO | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1 |  |  | 080315S00046 | 15-IL-0158 | 2015-10-22 | 2015-10-22 | 2015-11-04 | 2015-12-22 | 2015-12-31
NC 2015 | K10 (2015) | Region VIII | Southern Leyte | 122209 | Lambonao Elementary School | MALITBOG | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080315S00043 | 15-IL-0133 | 2015-08-03 | 2015-08-06 | 2015-09-16 | 2015-09-24 | 2015-10-05 | 888 ACY ENTERPRISES
NC 2015 | K10 (2015) | Region VIII | Southern Leyte | 122080 | Libagon Central Sentral | LIBAGON | 0 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 080315S00040 | 15-IL-0144 | 2015-08-11 | 2015-08-13 | 2015-08-25 | 2015-08-27 | 2015-09-07 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region VIII | Southern Leyte | 313411 | Libagon National High School | LIBAGON | 0 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080315S00041 | 15-IL-0134 | 2015-08-03 | 2015-08-06 | 2015-08-18 | 2015-08-25 | 2015-09-04 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2015 | SHS (2015) | Region VIII | Southern Leyte | 313409 | Liloan National Technical Vocational High School | LILOAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Southern Leyte | 303465 | Limasawa NHS | LIMASAWA | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 080315S00020 | 15-IL-0139 | 2015-08-11 | 2015-08-13
NC 2015 | SHS (2015) | Region VIII | Southern Leyte | 303466 | Lungsodaan National High School | HINUNDAYAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080315S00019 | 15-IL-0123 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-18 | 2015-08-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2015 | K10 (2015) | Region VIII | Southern Leyte | 122190 | Molopolo Elementary School | MACROHON | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080315S00042 | 15IL-0132- | 2015-08-03 | 2015-08-06 | 2015-08-18 | 2015-08-25 | 2015-09-04 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2015 | K10 (2015) | Region VIII | Southern Leyte | 303473 | Nava NHS | HINUNANGAN | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 080315S00037 | 15-IL-0135 | 2015-08-03 | 2015-08-06 | 2015-09-16 | 2015-09-24 | 2015-10-05 | 888 ACY ENTERPRISES
NC 2015 | K10 (2015) | Region VIII | Southern Leyte | 313407 | New Guinsaugon NHS | SAINT BERNARD | 0 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 7 | 8214965 |  |  | COMPLETED | 1 |  |  | 080315S00054 | 15-IL-0166 | 2015-11-04 | 2015-11-11 | 2015-11-24 | 2015-12-04 | 2015-12-16 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2015 | SHS (2015) | Region VIII | Southern Leyte | 303475 | Paku NHS | BONTOC | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8244965.051 |  |  | COMPLETED | 1 |  |  | 080315S00033 | 15-IL-0119 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-18 | 2015-08-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2015 | SHS (2015) | Region VIII | Southern Leyte | 303477 | Pintuyan National Vocational High School | PINTUYAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 |  |  | 080315S00017 | 15-IL-0129 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-18 | 2015-08-26 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2015 | K10 (2015) | Region VIII | Southern Leyte | 192016 | Puntana Primary School | SILAGO | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 080315S00052 | 15-IL-0159 | 2015-10-22 | 2015-10-22 | 2015-11-04 | 2015-11-13 | 2015-11-25 | 888 ACY ENTERPRISES
NC 2015 | SHS (2015) | Region VIII | Southern Leyte | 303472 | Rito Monte de Ramos Sr. MHS (Nahaong NHS) | LIBAGON | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Southern Leyte | 303472 | Rito Monte de Ramos Sr. MHS (Nahaong NHS) | LIBAGON | 0 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2479549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Southern Leyte | 303481 | San Juan NHS | SAN JUAN (CABALIAN) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 080315S00007 | 15-IL-0141 | 2015-08-11 | 2015-08-13 | 2015-08-25 | 2015-08-27 | 2015-09-07 | A.C. RIVERO DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region VIII | Southern Leyte | 303483 | San Ricardo National High School | SAN RICARDO | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1 |  |  | 080315S00008 | 15-IL-0130 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-18 | 2015-08-26 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2015 | SHS (2015) | Region VIII | Southern Leyte | 303486 | Silago NVHS | SILAGO | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region VIII | Southern Leyte | 303486 | Silago NVHS | SILAGO | 0 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Southern Leyte | 303487 | Sogod National High School | SOGOD | 0 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 080315S00032 | 15-IL-0140 | 2015-08-11 | 2015-08-13 | 2015-08-25 | 2015-08-27 | 2015-09-07 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2015 | SHS (2015) | Region VIII | Southern Leyte | 303488 | Sta. Cruz NHS | MALITBOG | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080315S00009 | 15-IL-0116 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-18 | 2015-08-26 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2015 | SHS (2015) | Region VIII | Southern Leyte | 303489 | Sta. Paz National High School | SAN FRANCISCO | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080315S00035 | 15-IL-0128 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-18 | 2015-08-26 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2015 | TECHVOC (2015) | Region VIII | Southern Leyte | 303492 | VILLA JACINTA NATIONAL VOCATIONAL HIGH SCHOOL | MACROHON | 0 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Southern Leyte | 303492 | Villa Jacinta NVHS | MACROHON | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Tacloban City |  | Proposed Stand Alone SHS 1 | TACLOBAN CITY | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Tacloban City |  | Proposed Stand Alone SHS 1 | TACLOBAN CITY | 1 | 1 | 15 | 3STY15CL | 2015 SHS BATCH 8 | 21383013.45 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Tacloban City | 314003 | Antonio Balmes National High School | TACLOBAN CITY (Capital) | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2700828.124 |  |  | REVERTED | 0
NC 2015 | K10 (2015) | Region VIII | Tacloban City | 124225 | Judge Antonio R. Montilla, Sr. ES (JARMS) | TACLOBAN CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 080215S00220 | 15IM0046 | 2015-08-26 | 2015-09-02 | 2015-09-14
NC 2015 | SHS (2015) | Region VIII | Tacloban City | 303663 | Leyte NHS | TACLOBAN CITY (Capital) | 1 | 1 | 15 | 3STY15CL | 2015 SHS BATCH 2 | 21433013.45 |  |  | COMPLETED | 1 |  |  | 080215S00095 | 15IM0045 | 2015-08-03 | 2015-08-10
NC 2015 | SHS (2015) | Region VIII | Tacloban City | 314004 | Northern Tacloban City National High School | TACLOBAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1 |  |  | 080215S00016 | 15IM0042 | 2015-07-20 | 2015-07-24 | 2015-08-05
NC 2015 | SHS (2015) | Region VIII | Tacloban City |  | Proposed Stand Alone SHS 2 ( V & G Memorial ES) | TACLOBAN CITY | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 8 | 10877342.5917 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region VIII | Tacloban City | 303667 | San Jose NHS | TACLOBAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1 |  |  | 080215S00066 | 15IM0041 | 2015-07-20 | 2015-07-24 | 2015-08-05 | 2015-10-06 | 2015-10-12 | B. VICENCIO CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Tacloban City | 314005 | Scandinavian National High School | TACLOBAN CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6321337.6381 |  |  | COMPLETED | 1 |  |  | 080215S00084 | 15IM0040 | 2015-07-20 | 2015-07-24 | 2015-08-05 | 2015-09-28 | 2015-09-28 | D.L. AUREO CONSTRUCTION
NC 2015 | SHS (2015) | Region VIII | Tacloban City | 303669 | Tacloban National Agricultural School | TACLOBAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 080215S00044 | 15IM0043 | 2015-07-20 | 2015-07-24 | 2015-08-05 | 2015-09-16 | 2015-10-23 | ACME BUILDERS CORPORATION
NC 2015 | K10 (2015) | Region VIII | Tacloban City | 195003 | Utap Elementary School | TACLOBAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | Reverted | 0 |  |  | 080215S00152 | 15IM0044 | 2015-08-03 | 2015-08-10 | 2015-08-18
NC 2016 | K10 | Region VIII | Baybay City | 313316 | Baybay City Nat'L Night Hs | City Of Baybay | 5 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8770000 |  |  | Completed | 1 |  |  | P00073919VS-CW1 | 16IG0074 |  | 2018-10-26 | 2016-11-08 | 2016-11-21 | 2017-03-01 | LADY OF ASSUMPTION ENTERPRISES
NC 2016 | K10 | Region VIII | Baybay City | 313316 | Baybay City Nat'L Night Hs | City Of Baybay | 5 |  | 4 | 2STY4CL | BATCH 9 CL | 6730000 |  |  | Completed | 1 |  |  | P00073920VS-CW1 | 16IG0075 |  | 2018-10-26 | 2016-11-08 | 2016-11-21 | 2017-03-01 | LADY OF ASSUMPTION ENTERPRISES
NC 2016 | K10 | Region VIII | Baybay City | 303348 | Baybay Nhs | City Of Baybay | 5 | 1 | 8 | 2STY8CL | BATCH 13 CL | 12010076.849 |  |  | Completed | 1 |  |  | P00075855VS-CW1 | 17IG0082 |  | 2016-03-21 | 2017-04-04 | 2017-08-04 | 2017-08-09 | PABLO S. LABASBAS CONSTRUCTION
NC 2016 | K10 | Region VIII | Baybay City | 303348 | Baybay Nhs | City Of Baybay | 5 |  | 3 | 1STY3CL | BATCH 13 CL | 2960000 |  |  | Completed | 1 |  |  | P00075856VS-CW1 | 16IG0087 |  | 2016-12-09 | 2016-12-22 | 2017-01-24 | 2017-02-03 | R.S. REYNA CONSTRUCTION
NC 2016 | K10 | Region VIII | Baybay City | 303349 | Bitanhuan Nhs | City Of Baybay | 5 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1990000 |  |  | Completed | 1 |  |  | P00073921VS-CW1 | 16IG0027 |  | 2016-06-07 | 2016-06-21 | 2016-06-04 | 2016-07-08 | R.AGULLO CONSTRUCTION & ENTERPRISES
NC 2016 | SHS | Region VIII | Baybay City | 303360 | Caridad Nhs | City Of Baybay | 5 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12010076.8509 |  |  | Completed | 1 |  |  | P00073922VS-CW1 | 16IG0080 |  | 2016-11-18 | 2016-12-01 |  | 2017-01-20 | JUCONS CONSTRUCTION & SUPPLY
NC 2016 | TECHVOC | Region VIII | Baybay City | 303360 | Caridad Nhs | City Of Baybay | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2477000 |  |  | Completed | 1 |  |  | P00074572VS-CW1 | 16IG0032 |  | 2016-07-06 | 2016-07-21 | 2016-08-08 | 2016-08-10 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2016 | K10 | Region VIII | Baybay City | 313323 | Ciabu Nhs | City Of Baybay | 5 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8770000 |  |  | Completed | 1 |  |  | P00073923VS-CW1 | 16IG0044 |  | 2016-06-28 | 2016-08-18 | 2016-10-25 | 2016-10-28 | RJIR ENTERPRISES
NC 2016 | K10 | Region VIII | Baybay City | 313323 | Ciabu Nhs | City Of Baybay | 5 |  | 4 | 2STY4CL | BATCH 9 CL | 6730000 |  |  | Completed | 1 |  |  | P00073924VS-CW1 | 16IG0043 |  | 2016-06-28 | 2016-08-18 | 2016-10-25 | 2017-01-16 | JUCONS CONSTRUCTION & SUPPLY
NC 2016 | TECHVOC | Region VIII | Baybay City | 313323 | Ciabu Nhs | City Of Baybay | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2497000 |  |  | Completed | 1 |  |  | P00074573VS-CW1 | 16IG0031 |  | 2016-07-06 | 2016-07-21 |  | 2016-08-12 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2016 | K10 | Region VIII | Baybay City | 121079 | Lintaon Es To Baybay I Cs | City Of Baybay | 5 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2030000 |  |  | Completed | 1 |  |  | P00073925VS-CW1 | 16IG0024 |  |  | 2016-10-11 | 2016-11-11 | 2016-11-23 | KRC CONSTRUCTION AND SUPPLY
NC 2016 | K10 | Region VIII | Baybay City | 121145 | Mahayahay Es To Marcos Es | City Of Baybay | 5 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1040000 |  |  | Completed | 1 |  |  | P00073926VS-CW1 | 16IG0029 |  |  | 2016-10-11 | 2016-11-11 | 2016-10-28 | JUCONS CONSTRUCTION & SUPPLY
NC 2016 | K10 | Region VIII | Baybay City | 313312 | Mailhi Nhs | City Of Baybay | 5 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3870000 |  |  | Completed | 1 |  |  | P00073927VS-CW1 | 16IG0035 |  | 2016-07-06 | 2016-07-21 | 2106-08-11 | 2016-08-17 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2016 | K10 | Region VIII | Baybay City | 313312 | Mailhi Nhs | City Of Baybay | 5 |  | 3 | 1STY3CL | BATCH 9 CL | 2960000 |  |  | Completed | 1 |  |  | P00073928VS-CW1 | 16IG0028 |  | 2016-06-07 | 2016-06-21 | 2016-06-04 | 2016-07-08 | CIRCLE Z VENTURES & DEV. CORP.
NC 2016 | SHS | Region VIII | Baybay City | 303419 | Plaridel Nhs | City Of Baybay | 5 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13460000 |  |  | Completed | 1 |  |  | P00073929VS-CW1 | 16IG0042 |  | 2016-06-28 | 2016-08-18 | 2016-11-21 | 2017-06-07 | LADY OF ASSUMPTION ENTERPRISES
NC 2016 | TECHVOC | Region VIII | Baybay City | 303419 | Plaridel Nhs | City Of Baybay | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2477000 |  |  | Completed | 1 |  |  | P00074574VS-CW1 | 16IG0051 |  | 2016-08-17 | 2016-08-30 |  | 2016-09-21 | JUCONS CONSTRUCTION & SUPPLY
NC 2016 | K10 | Region VIII | Baybay City | 303420 | Pomponan Nhs | City Of Baybay | 5 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2030000 |  |  | Completed | 1 |  |  | P00073930VS-CW1 | 16IG0025 |  | 2016-06-07 | 2016-06-21 | 2016-06-04 | 2016-07-08 | R.AGULLO CONSTRUCTION & ENTERPRISES
NC 2016 | TECHVOC | Region VIII | Baybay City | 303420 | Pomponan Nhs | City Of Baybay | 5 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4974000 |  |  | Completed | 1 |  |  | P00074575VS-CW1 | 16IG0034 |  | 2016-08-09 | 2016-08-23 |  | 2016-09-08 | JA ACHACOSO ENT. & GENERAL SERVICES
NC 2016 | K10 | Region VIII | Baybay City | 121092 | San Isidro Es | City Of Baybay | 5 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1990000 |  |  | Completed | 1 |  |  | P00073931VS-CW1 | 16IG0026 |  | 2016-06-07 | 2016-06-21 | 2016-06-04 | 2016-07-08 | R.S. REYNA CONSTRUCTION
NC 2016 | SHS | Region VIII | Baybay City |  | Stand Alone 1 (Baybay Nhs) | City Of Baybay | 5 | 1 | 24 | 2STY12CL | BATCH 9 CL | 32204277.7955 |  |  | Completed | 1 |  |  | P00073932VS-CW1 | 16IG0076 |  | 2018-10-26 | 2016-11-08 | 2016-11-24 | 2017-03-30 | HIGH-INNOVATIVE CONST. & DEV. PHILS
NC 2016 | SHS | Region VIII | Baybay City |  | Stand Alone 1 (Baybay Nhs) | City Of Baybay | 5 |  | 16 | 2STY8CL | BATCH 9 CL | 24020153.7017 |  |  | Completed | 1 |  |  | P00073933VS-CW1 | 16IG0077 |  | 2016-12-02 | 2016-12-16 | 2017-03-29 | 2017-04-06 | RJIR ENTERPRISES
NC 2016 | TECHVOC | Region VIII | Baybay City |  | Stand Alone 1 (Baybay Nhs) | City Of Baybay | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2477000 |  |  | Completed | 1 |  |  | P00074576VS-CW1 | 16IG0033 |  | 2016-07-06 | 2016-07-21 |  | 2016-08-10 | VICTORIA DEV. & CONST. SUPPLY CORP.
NC 2016 | SHS | Region VIII | Biliran | 303319 | Almeria Nhs | Almeria | 0 | 1 | 6 | 2STY6CL | BATCH 11 CL | 8600000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Biliran | 303320 | Biliran Nahs | Biliran | 0 | 1 | 12 | 2STY6CL | BATCH 3 CL | 17500000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Biliran | 303320 | Biliran Nahs | Biliran | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 5350000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Biliran | 120775 | Burabod Es | Biliran | 0 | 1 | 1 | 1STY1CL | BATCH 11 CL | 1102000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Biliran | 303322 | Cabucgayan Nsat | Cabucgayan | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12080076.8509 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Biliran | 303322 | Cabucgayan Nsat | Cabucgayan | 0 |  | 6 | 2STY6CL | BATCH 9 CL | 8760000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Biliran | 303322 | Cabucgayan Nsat | Cabucgayan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2517000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Biliran | 120820 | Culaba Cs | Culaba | 0 | 1 | 3 | 1STY3CL | BATCH 11 CL | 2730000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Biliran | 303324 | Culaba Nvs | Culaba | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2520000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Biliran | 313203 | Ict High School Of Eastern Biliran | Caibiran | 0 | 1 | 20 | 2STY10CL | BATCH 9 CL | 23168358.1675 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Biliran | 313203 | Ict High School Of Eastern Biliran | Caibiran | 0 |  | 6 | 2STY6CL | BATCH 9 CL | 8780000 |  |  | Reverted | 0
NC 2016 | TECHVOC | Region VIII | Biliran | 313203 | Ict High School Of Eastern Biliran | Caibiran | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2517000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Biliran | 303328 | Manlabang Nhs | Caibiran | 0 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11596000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Biliran | 303329 | Maripipi Nvs | Maripipi | 0 | 1 | 8 | 2STY8CL | BATCH 13 CL | 12250076.849 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Biliran | 303330 | Naval National High School | Naval (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2507000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Biliran | 303330 | Naval National High School | Naval (Capital) | 0 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11965076.849 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Biliran | 303330 | Naval National High School | Naval (Capital) | 0 |  | 3 | 1STY3CL | BATCH 13 CL | 3087851.684 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Biliran | 303331 | Naval School Of Fisheries | Naval (Capital) | 0 | 1 | 12 | 2STY12CL | BATCH 9 CL | 16092138.8978 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Biliran | 303331 | Naval School Of Fisheries | Naval (Capital) | 0 |  | 10 | 2STY10CL | BATCH 9 CL | 14088441.1023 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Biliran | 303331 | Naval School Of Fisheries | Naval (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2462000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Biliran | 303333 | Tucdao Nhs | Kawayan | 0 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2161466.644 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Biliran | 303333 | Tucdao Nhs | Kawayan | 0 |  | 1 | 1STY1CL | BATCH 13 CL | 1223294.659 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Borongan City | 122370 | Balacdas Ps | City Of Borongan (Capital) | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Borongan City | 313504 | Benowangan Nhs (Lalawigan Nhs - Benowangan Annex) | City Of Borongan (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6482000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Borongan City | 122400 | Canyupay Es | City Of Borongan (Capital) | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Borongan City | 303500 | E. Samar Nchs | City Of Borongan (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2512768.1307 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Borongan City | 313515 | E. Samar Nchs - Supt. Fidel E. Anacta, Sr. Mhs Annex | City Of Borongan (Capital) | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11095000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Borongan City | 313515 | E. Samar Nchs - Supt. Fidel E. Anacta, Sr. Mhs Annex | City Of Borongan (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2472000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Borongan City | 122402 | Hebacong Es | City Of Borongan (Capital) | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1170000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Borongan City | 303511 | Lalawigan Nhs | City Of Borongan (Capital) | 0 | 1 | 6 | 3STY6CL | BATCH 9 CL | 9460418.359 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Borongan City | 303511 | Lalawigan Nhs | City Of Borongan (Capital) | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4880666.6667 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Borongan City | 303526 | Maypangdan Nhs | City Of Borongan (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15171327.92 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Borongan City | 303526 | Maypangdan Nhs | City Of Borongan (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2433666.6667 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Borongan City | 303525 | Sta. Fe Nhs | City Of Borongan (Capital) | 0 | 1 | 6 | 3STY6CL | BATCH 9 CL | 9450418.359 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Borongan City | 303525 | Sta. Fe Nhs | City Of Borongan (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2447000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Borongan City | 122364 | Suhotan Ps To Siha Es | City Of Borongan (Capital) | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1110000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Calbayog City | 124134 | Cag-Olango Elementary School | Calbayog City | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864816.26 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Calbayog City | 313801 | Calbayog City National High School | Calbayog City | 1 | 1 | 40 | 4STY20CL | BATCH 11 CL | 62205780.54 |  |  | Completed | 1 |  |  |  | 17IJ-0092 |  |  |  | 2017-07-11 | 2017-07-21 | JVCD JV
NC 2016 | SHS | Region VIII | Calbayog City | 313801 | Calbayog City National High School | Calbayog City | 1 |  | 4 | 1STY4CL | BATCH 11 CL | 3667968.78 |  |  | Reverted | 0
NC 2016 | K10 | Region VIII | Calbayog City | 313803 | Calbayog City Night High School | Calbayog City | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10882042.74 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Calbayog City | 124086 | Canjumadac Elementary School | Calbayog City | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2982437.766 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Calbayog City | 123992 | Cogon Elementary School | Calbayog City | 1 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1224580.0817 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Calbayog City | 123992 | Cogon Elementary School | Calbayog City | 1 |  | 2 | 1STY2CL | BATCH 9 CL | 1744744.436 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Calbayog City | 313808 | Dawo Integrated School | Calbayog City | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2051297.908 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Calbayog City | 124095 | Hibuhatan Elementary School | Calbayog City | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6673289.51 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Calbayog City | 124015 | Higasaan Primary School | Calbayog City | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2982437.766 |  |  | Completed | 1 |  |  |  | 16IJ-0102 |  |  |  | 2017-11-03 | 2017-11-10 | VCD
NC 2016 | K10 | Region VIII | Calbayog City | 124016 | Himalandrog Elementary School | Calbayog City | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2982437.766 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Calbayog City | 124017 | Looc Elementary School | Calbayog City | 1 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1146385.163 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Calbayog City | 313810 | Malaga Nhs - Caglanipao Sur Annex School | Calbayog City | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864816.28 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Calbayog City | 313811 | Malaga Nhs-Pena I Annex School | Calbayog City | 1 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6373289.51 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Calbayog City | 124025 | San Antonio Primary School | Calbayog City | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2051297.908 |  |  | Completed | 1 |  |  |  | 16IJ-0121 |  |  |  | 2017-11-03 | 2017-11-10 | VCD
NC 2016 | SHS | Region VIII | Calbayog City | 303651 | San Policarpo National High School | Calbayog City | 1 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20029495.669 |  |  | Completed | 1 |  |  |  | 16IJ-0065 |  |  |  | 2017-05-16 | 2017-05-26 | B. VICENCIO
NC 2016 | K10 | Region VIII | Calbayog City | 313814 | Seven Hills National High School | Calbayog City | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2051297.908 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Calbayog City | 313807 | Tabawan Integrated School | Calbayog City | 1 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6936271.404 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122746 | A-Et Elementary School | Sulat | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122324 | Aguinaldo Elementary School | Arteche | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1190000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122671 | Alang-Alang Elementary School | Quinapondan | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1150000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122672 | Anislag Elementary School | Quinapondan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2153800 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Eastern Samar | 303494 | Arteche National High School | Arteche | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2726593.2584 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122408 | Balagon Elementary School | Can-Avid | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2153800 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303495 | Balangkayan National High School | Balangkayan | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11075000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Eastern Samar | 303495 | Balangkayan National High School | Balangkayan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2462000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122655 | Balingasag Elementary School | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2038000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122608 | Bangon Elementary School | Balangkayan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1998000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122735 | Bangon Elementary School | San Policarpo | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2108000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122656 | Batang Elementary School | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2028000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122657 | Bato Ps | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1939000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122760 | Beto Elementary School | Taft | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1200000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122506 | Biga Elementary School | Giporlos | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1170000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122658 | Binalayan Elementary School | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2018000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122536 | Bobon Elementary School | Mercedes | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2018000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122762 | Bongdo Primary School | Taft | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122428 | Botnga Primary School | Dolores | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122519 | Buenavista Elementary School | Guiuan | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122711 | Butig Elementary School | Salcedo | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122477 | Cacatmonan Primary School | Hernani | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2153800 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122636 | Cagdaja Elementary School To Dalid Es | Quinapondan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122540 | Cagdara-O Primary School | Guiuan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1998000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122411 | Caghalong Primary School | Can-Avid | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122330 | Cagsalay Elementary School | Arteche | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122663 | Cagtoog Elementary School | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2028000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 313520 | Cambilla Elementary School To Carapdapan Nhs | Arteche | 0 |  | 3 | 1STY3CL | BATCH 9 CL | 3031000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 313501 | Can-Avid National High School | Can-Avid | 0 | 1 | 24 | 2STY12CL | BATCH 9 CL | 26332590.9236 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Eastern Samar | 313501 | Can-Avid National High School | Can-Avid | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4864000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122507 | Cansingkol Elementary School | Giporlos | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2931000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122652 | Cantinio Primary School To Agsam Es | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2018000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122714 | Cantomoja Elementary School | Salcedo | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1200000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122720 | Capanoypoyan Primary School To Taclaon Es | Salcedo | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2008000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 313520 | Carapdapan National High School | Arteche | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8336000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122481 | Carmen Elementary School | Hernani | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2881000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122723 | Caruyagon Elementary School | San Julian | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122541 | Cogon Elementary School | Guiuan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1998000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Eastern Samar | 313522 | Concepcion National High School | Arteche | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2931000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 192508 | Dacul Primary School | Taft | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1150000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122522 | Dalaragan Primary School | Guiuan | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2871000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122771 | Danao Elementary School To Polangi Es | Taft | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1190000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122615 | Del Pilar Elementary School | Maydolong | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1180000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122765 | Del Remedios Elementary School | Taft | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1221000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303499 | Dolores National High School | Dolores | 0 | 1 | 20 | 2STY10CL | BATCH 13 CL | 25856000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Eastern Samar | 303499 | Dolores National High School | Dolores | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2699435.9551 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122574 | Dorillo Elementary School | Jipapad | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1221000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122523 | Gahoy Elementary School | Guiuan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1998000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122766 | Gayam Primary School | Taft | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Eastern Samar | 303501 | Gen. Macarthur National Agricultural School | General Macarthur | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2726593.2584 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303502 | Giporlos National Trade School | Giporlos | 0 | 1 | 24 | 2STY8CL | BATCH 9 CL | 33055000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Eastern Samar | 303502 | Giporlos National Trade School | Giporlos | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4372822.2222 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122715 | Guba Primary School | Salcedo | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1170000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122632 | Guinmaayohan Elementary School To Bagacay Es | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303503 | Guiuan National High School | Guiuan | 0 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12998000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303507 | Hinolaso National High School | Dolores | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6532000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303508 | Homonhon National High School | Guiuan | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11185000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122509 | Huknan Elementary School To Gigoso Es | Giporlos | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122564 | Inapulangan Elementary School | Guiuan | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 192520 | Ipil Elementary School | Dolores | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122419 | Jepaco Elementary School | Can-Avid | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303510 | Jipapad National High School | Jipapad | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11135000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Eastern Samar | 303510 | Jipapad National High School | Jipapad | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2492000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122576 | Jiwaran Primary School | Jipapad | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122619 | Julag Primary School | Balangkayan | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1150000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122654 | Kalaw Es To Anacta Ps | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 11 CL | 1939000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122748 | Kandalakit Elementary School | Sulat | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2038000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122695 | Karapdapan Elementary School | Salcedo | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1160000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122620 | Lapgap Elementary School | Maydolong | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1190000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 313523 | Lapgap National High School | Maydolong | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2038000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303512 | Lawaan National School Of Craftsmanship And Home Industries | Lawaan | 0 | 1 | 20 | 2STY10CL | BATCH 9 CL | 23098358.1675 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303512 | Lawaan National School Of Craftsmanship And Home Industries | Lawaan | 0 |  | 8 | 2STY8CL | BATCH 9 CL | 11065000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Eastern Samar | 303512 | Lawaan National School Of Craftsmanship And Home Industries | Lawaan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2422714.2857 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122343 | Layog Primary School To Beta-Og Es | Lawaan | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1110000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 192516 | Libertad Elementary School | Maslog | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1221000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122487 | Limbujan Primary School | General Macarthur | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1190000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303513 | Llorente National High School | Llorente | 0 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12948000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Eastern Samar | 303513 | Llorente National High School | Llorente | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2507980.0817 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122457 | Luhang Elementary School | Dolores | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 192514 | Lunang Elementary School | Dolores | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1998000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 192507 | Lunang Primary School | San Julian | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1110000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122768 | Lupok Central Elementary School To Malinao Es | Taft | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6422000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122454 | Lupok Central Elementary School To Hinolaso Es | Dolores | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2871000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122577 | Mabuhay Elementary School | Jipapad | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1190000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122488 | Macapagal Primary School | General Macarthur | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122578 | Magsaysay Elementary School | Jipapad | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122621 | Magsaysay Primary School | Balangkayan | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1160000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303514 | Malabag National High School | Giporlos | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2881000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122461 | Malobago Primary School | Maslog | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1221000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 313516 | Manicani National High School | Guiuan | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3031000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303516 | Matarinao School Of Fisheries | Salcedo | 0 | 1 | 6 | 3STY6CL | BATCH 9 CL | 9490418.359 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Eastern Samar | 303516 | Matarinao School Of Fisheries | Salcedo | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2442000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 313514 | Maydolong National High School | Maydolong | 0 | 1 | 12 | 2STY6CL | BATCH 13 CL | 16632000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Eastern Samar | 313514 | Maydolong National High School | Maydolong | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2512768.1307 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122579 | Maylimon Elementary School | Jipapad | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122626 | Maytigbao Elementary School | Maydolong | 0 | 1 | 2 | 2STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303518 | Mercedes National High School | Mercedes | 0 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6355390.5783 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122667 | Naga Elementary School | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2028000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122490 | Nagaja Elementary School | Hernani | 0 | 1 | 5 | 1STY5CL | BATCH 9 CL | 4629000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122422 | Obong Es | Can-Avid | 0 | 1 | 2 | 1STY2CL | BATCH 11 CL | 1939000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122649 | Oras East District Sped Center To Saurong Es | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1998000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Eastern Samar | 303520 | Oras National High School | Oras | 0 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10497131.51 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303529 | Oras West Central Elementary School To Taft Nhs | Taft | 0 |  | 10 | 2STY10CL | BATCH 13 CL | 12948000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303520 | Oras West Central Elementary School To Oras Nhs | Oras | 0 |  | 4 | 2STY4CL | BATCH 13 CL | 6422000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122575 | Oras West Central Elementary School To Jipapad Ces | Jipapad | 0 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2871000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122491 | Osmeña Primary School | General Macarthur | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122682 | Paco Elementary School | Quinapondan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1998000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122761 | Pangabutan Primary School To Binaloan Es | Taft | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303505 | Pedro E. Candido Memorial National High School | Hernani | 0 | 1 | 12 | 2STY6CL | BATCH 13 CL | 16667000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122494 | Quezon Primary School | General Macarthur | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1170000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 192505 | Quiatan Elemenary School | Dolores | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1190000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303522 | Quinapondan National High School To Salcedo National High School | Quinapondan | 0 | 1 | 12 | 2STY6CL | BATCH 13 CL | 20000000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122581 | Roxas Elementary School | Jipapad | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1150000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 313509 | Salcedo Vocational High School | Salcedo | 0 | 1 | 12 | 2STY6CL | BATCH 13 CL | 16772000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Eastern Samar | 313509 | Salcedo Vocational High School | Salcedo | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2557456.5884 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303523 | Samar National Pilot Opportunity School Of Agriculture | San Policarpo | 0 | 1 | 16 | 2STY8CL | BATCH 9 CL | 19669216.6651 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Eastern Samar | 303523 | Samar National Pilot Opportunity School Of Agriculture | San Policarpo | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2437000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 313521 | San Antonio Primary School To Dapdap Ntvhs | Dolores | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2098000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122629 | San Gabriel Elementary School | Maydolong | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1190000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122679 | San Isidro Elementary School To Sta. Cruz Es | General Macarthur | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2038000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122498 | San Isidro Elementary School | Hernani | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1180000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122352 | San Isidro Primary School | Lawaan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2028000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 192503 | San Isidro Ps | Quinapondan | 0 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1939000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 192519 | San Juan Elementary School | Guiuan | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2981000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303524 | San Julian National High School | San Julian | 0 |  | 6 | 2STY6CL | BATCH 9 CL | 7448468.5459 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303524 | San Julian National High School | San Julian | 0 | 1 | 10 | 2STY10CL | BATCH 9 CL | 12938000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122467 | San Roque Elementary School | Maslog | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1221000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122500 | San Roque Primary School | General Macarthur | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1180000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 313502 | Southern Samar National Comprehensive National High School | Balangiga | 0 | 1 | 20 | 2STY10CL | BATCH 9 CL | 23168358.1675 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Eastern Samar | 313502 | Southern Samar National Comprehensive National High School | Balangiga | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4894000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122468 | Sta. Catalina Primary School | Dolores | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1190000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122501 | Sta. Cruz Elementary School | General Macarthur | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1150000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122502 | Sta. Fe Primary School | General Macarthur | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1190000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122650 | Sta. Monica Integrated School | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2108000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122743 | Sta.Cruz Elementary School | San Policarpo | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122325 | Sulangan Central Elementary School To Arteche Ces | Arteche | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8336000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122758 | Sulat Central Elementary School | Sulat | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2871000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303527 | Sulat National High School | Sulat | 0 | 1 | 20 | 2STY10CL | BATCH 9 CL | 23118358.1675 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Eastern Samar | 303527 | Sulat National High School | Sulat | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4934000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122569 | Sulu-An Integrated School | Guiuan | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6582000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122551 | Sung-An Es | Mercedes | 0 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1939000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122744 | Tabo Elementary School | San Policarpo | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1998000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303529 | Taft National High School | Taft | 0 | 1 | 12 | 2STY6CL | BATCH 13 CL | 16642000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122630 | Tagasli-An Es | Maydolong | 0 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1939000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 192518 | Tagporo Elementary School | Guiuan | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1170000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122469 | Tan-Awan Elementary School | Dolores | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122503 | Tandang Sora Primary School | General Macarthur | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122470 | Tangbo Elementary School | Maslog | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122651 | Tawagan Elementary School | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1978000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 303504 | Taytay Integrated School | Guiuan | 0 | 1 | 10 | 2STY10CL | BATCH 9 CL | 12948000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122553 | Trinidad Elementary School | Guiuan | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122554 | Tubabao Elementary School | Guiuan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Eastern Samar | 122504 | Tugop Elementary School | General Macarthur | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2981000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303336 | Alang-Alang National High School | Alangalang | 1 | 1 | 24 | 2STY8CL | BATCH 7 CL | 33155000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303336 | Alang-Alang National High School | Alangalang | 1 |  | 10 | 2STY10CL | BATCH 7 CL | 12898000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303441 | Gregorio C. Catenza Nhs (Tunga Nhs) | Tunga | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303441 | Gregorio C. Catenza Nhs (Tunga Nhs) | Tunga | 1 |  | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303441 | Gregorio C. Catenza Nhs (Tunga Nhs) | Tunga | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303343 | Juan S. Tismo National High School (Babatngon National High School | Babatngon | 1 | 1 | 18 | 2STY6CL | BATCH 9 CL | 24888000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303415 | Palo National High School | Palo | 1 | 1 | 45 | 3STY15CL | BATCH 7 CL | 64149040.35 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303415 | Palo National High School | Palo | 1 |  | 18 | 3STY9CL | BATCH 7 CL | 30242655.84 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303426 | San Miguel National High School | San Miguel | 1 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303426 | San Miguel National High School | San Miguel | 1 |  | 8 | 2STY8CL | BATCH 7 CL | 10985000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 121928 | San Roque Elementary School | Tanauan | 1 | 1 | 6 | 3STY6CL | BATCH 13 CL | 10498731.51 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303429 | Sta. Cruz National High School | San Miguel | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.051 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303430 | Sta. Fe National High School | Santa Fe | 1 | 1 | 16 | 2STY8CL | BATCH 9 CL | 21970000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303430 | Sta. Fe National High School | Santa Fe | 1 |  | 12 | 2STY12CL | BATCH 9 CL | 17963836.31 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 121930 | Sto. Niño Elementary School | Tanauan | 1 | 1 | 12 | 2STY12CL | BATCH 13 CL | 14579217.1798 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303437 | Tanauan National High School (San Roque Nhs) | Tanauan | 1 | 1 | 15 | 3STY15CL | BATCH 7 CL | 21383013.45 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303388 | Tanauan Sch. Of Craftsmanship & Home Industries (Lit-Tanauan | Tanauan | 1 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303388 | Tanauan Sch. Of Craftsmanship & Home Industries (Lit-Tanauan | Tanauan | 1 |  | 16 | 4STY16CL | BATCH 9 CL | 29357716.362 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303440 | Tolosa National High School | Tolosa | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10985000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303440 | Tolosa National High School | Tolosa | 1 |  | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303342 | Atty. Roque A. Marcos Memorial School (La Paz Nhs) | Lapaz | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18322268.79 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303342 | Atty. Roque A. Marcos Memorial School (La Paz Nhs) | Lapaz | 2 |  | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 313324 | Barugo National High School | Barugo | 2 | 1 | 12 | 2STY6CL | BATCH 7 CL | 16592000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 313324 | Barugo National High School | Barugo | 2 |  | 12 | 3STY12CL | BATCH 7 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303353 | Burauen Comprehensive National High School | Burauen | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303353 | Burauen Comprehensive National High School | Burauen | 2 |  | 15 | 3STY15CL | BATCH 7 CL | 21383013.45 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303353 | Burauen Comprehensive National High School | Burauen | 2 |  | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303354 | Burauen National High School | Burauen | 2 | 1 | 15 | 3STY15CL | BATCH 7 CL | 21383013.45 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303369 | Dulag National High School | Dulag | 2 | 1 | 32 | 4STY16CL | BATCH 9 CL | 58715432.724 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303369 | Dulag National High School | Dulag | 2 |  | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303371 | Granja-Kalinawan National High School | Jaro | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303371 | Granja-Kalinawan National High School | Jaro | 2 |  | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303371 | Granja-Kalinawan National High School | Jaro | 2 |  | 16 | 4STY16CL | BATCH 9 CL | 29357716.362 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303380 | Juan Villablanca Memorial High School | Pastrana | 2 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303380 | Juan Villablanca Memorial High School | Pastrana | 2 |  | 6 | 2STY6CL | BATCH 7 CL | 8296000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303380 | Juan Villablanca Memorial High School | Pastrana | 2 |  | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 313307 | Jugaban National High School | Carigara | 2 | 1 | 18 | 3STY9CL | BATCH 7 CL | 30242655.84 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 121527 | Julita Central School | Julita | 2 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 121527 | Julita Central School | Julita | 2 |  | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 121243 | Lemon Es | Lemon Es | 2 | 1 | 2 | 1STY2CL | BATCH 11 CL | 2132466.644 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303397 | Mac Arthur National High School | Mac Arthur | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303397 | Mac Arthur National High School | Mac Arthur | 2 |  | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303397 | Mac Arthur National High School | Mac Arthur | 2 |  | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303407 | Mayorga Nhs | Mayorga Nhs | 2 | 1 | 2 | 1STY2CL | BATCH 11 CL | 2132466.644 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303432 | Sta. Mesa National High School | Dagami | 2 | 1 | 18 | 3STY9CL | BATCH 9 CL | 30242655.84 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303432 | Sta. Mesa National High School | Dagami | 2 |  | 8 | 2STY8CL | BATCH 9 CL | 10985000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 313322 | Cahigan Nhs | Villaba | 3 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8346000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303358 | Calubian National High School | Calubian | 3 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18273000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303358 | Calubian National High School | Calubian | 3 |  | 9 | 3STY9CL | BATCH 9 CL | 15122000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303358 | Calubian National High School | Calubian | 3 |  | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Leyte | 303387 | Leyte Agro-Industrial School | Leyte | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Leyte | 303403 | Marcelino R. Veloso Nhs | Tabango | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303403 | Marcelino R. Veloso Nhs | Tabango | 3 | 1 | 10 | 2STY10CL | BATCH 13 CL | 14279402.099 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Leyte | 303423 | San Isidro Nhs | San Isidro | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303423 | San Isidro Nhs | San Isidro | 3 | 1 | 10 | 2STY10CL | BATCH 13 CL | 13380904 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Leyte | 313345 | Sulpa Nhs | Villaba | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 313345 | Sulpa Nhs | Villaba | 3 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9184586.555 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303434 | Tabango National High School | Tabango National High School | 3 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6936271.404 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 121893 | Tabango North Central School | Tabango | 3 | 1 | 12 | 2STY12CL | BATCH 7 CL | 14774000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 121893 | Tabango North Central School | Tabango | 3 |  | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303442 | Villaba Comprehensive Hs | Villaba | 3 | 1 | 6 | 3STY6CL | BATCH 11 CL | 11443844.661 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303442 | Villaba Comprehensive Hs | Villaba | 3 |  | 15 | 3STY15CL | BATCH 11 CL | 21384000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Leyte | 303442 | Villaba Comprehensive Hs | Villaba | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2924570 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Leyte | 303389 | Villaba Nhs (Lncast) | Villaba | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Leyte | 303378 | Isabel Nhs | Isabel | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 313302 | Isabel Nhs Comprehensive | Isabel | 4 | 1 | 12 | 2STY12CL | BATCH 13 CL | 16022138.898 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 313302 | Isabel Nhs Comprehensive | Isabel | 4 |  | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303383 | Kananga National High School | Kananga | 4 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15272000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303383 | Kananga National High School | Kananga | 4 |  | 6 | 2STY6CL | BATCH 11 CL | 8296000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303383 | Kananga National High School | Kananga | 4 |  | 24 | 4STY12CL | BATCH 11 CL | 44304687.24 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Leyte | 303395 | Lim-Ao National High School | Kananga | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303404 | Matag-Ob National High School | Matag-Ob | 4 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18303000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303404 | Matag-Ob National High School | Matag-Ob | 4 |  | 9 | 3STY9CL | BATCH 7 CL | 15122000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303406 | Matlang National High School | Isabel | 4 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18273000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Leyte | 303408 | Merida Vocational School | Merida | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303408 | Merida Vocational School | Merida | 4 | 1 | 24 | 2STY12CL | BATCH 13 CL | 29448000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 313306 | Palompon National High School | Palompon | 4 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15172000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 313306 | Palompon National High School | Palompon | 4 |  | 9 | 3STY9CL | BATCH 9 CL | 15122000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 313306 | Palompon National High School | Palompon | 4 |  | 15 | 3STY15CL | BATCH 9 CL | 21384000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 313306 | Palompon National High School | Palompon | 4 |  | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Leyte | 313327 | Rizal Nhs | Kananga | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303427 | Seguinon National High School | Albuera | 4 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18273000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303427 | Seguinon National High School | Albuera | 4 |  | 6 | 2STY6CL | BATCH 7 CL | 8296000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303335 | Abuyog National High School | Abuyog | 5 | 1 | 15 | 3STY15CL | BATCH 7 CL | 21383013.45 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303347 | Bato School Of Fisheries | Bato | 5 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303347 | Bato School Of Fisheries | Bato | 5 |  | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303356 | Cahagnaan National High School | Matalom | 5 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6682000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303374 | Hilongos National High School | Hilongos | 5 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303374 | Hilongos National High School | Hilongos | 5 |  | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303374 | Hilongos National High School | Hilongos | 5 |  | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303379 | Javier National High School | Javier(Bugho) | 5 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303379 | Javier National High School | Javier(Bugho) | 5 |  | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303379 | Javier National High School | Javier(Bugho) | 5 |  | 12 | 3STY12CL | BATCH 7 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303398 | Mahaplag National High School | Mahaplag | 5 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21383013.45 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303398 | Mahaplag National High School | Mahaplag | 5 |  | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303399 | Mahaplag National High School (Upper Campus Ra 7094) | Mahaplag | 5 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10985000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303399 | Mahaplag National High School (Upper Campus Ra 7094) | Mahaplag | 5 |  | 8 | 2STY8CL | BATCH 7 CL | 10985000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 303399 | Mahaplag National High School (Upper Campus Ra 7094) | Mahaplag | 5 |  | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 313344 | Manlilisid National High School | Javier | 5 | 1 | 12 | 2STY6CL | BATCH 13 CL | 16592000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 313344 | Manlilisid National High School | Javier | 5 |  | 1 | 1STY1CL | BATCH 13 CL | 1098449.69 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303405 | Matalom National High School | Matalom | 5 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 303405 | Matalom National High School | Matalom | 5 |  | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 121648 | Polahongon Elementary School | Mahaplag | 5 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15122327.92 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 121648 | Polahongon Elementary School | Mahaplag | 5 |  | 6 | 2STY6CL | BATCH 13 CL | 8296000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Leyte | 121648 | Polahongon Elementary School | Mahaplag | 5 |  | 1 | 1STY1CL | BATCH 13 CL | 1098449.69 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 313314 | Polahongon National High School | Mahaplag | 5 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21383013.45 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Leyte | 313314 | Polahongon National High School | Mahaplag | 5 |  | 6 | 3STY6CL | BATCH 9 CL | 10417131.51 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Northern Samar | 303531 | Allen Nhs | Allen | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 303531 | Allen Nhs | Allen | 1 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6936271.404 |  |  | Terminated | 0 | [10 empty] | Original Contract Terminated on June 29, 2022. New contract completed on February 18, 2023.
NC 2016 | K10 | Region VIII | Northern Samar | 303531 | Allen Nhs | Allen | 1 |  | 20 | 2STY10CL | BATCH 13 CL | 25542620.18 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 303561 | Basilio B. Chan Mem. Agricultural And Industrial Sch. | Lavezares | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11950076.849 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 303561 | Basilio B. Chan Mem. Agricultural And Industrial Sch. | Lavezares | 1 |  | 3 | 1STY3CL | BATCH 13 CL | 3082851.684 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Northern Samar | 303534 | Biri National High School | Biri | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11950076.849 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Northern Samar | 303535 | Bobon School For Philippine Craftsmen | Bobon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Northern Samar | 303536 | Buenavista Nhs | Rosario | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2853063.86 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Northern Samar | 303540 | Capul Agro-Industrial School | Capul | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 122845 | Catarman Ii Cs | Catarman (Capital) | 1 | 1 | 12 | 2STY6CL | BATCH 13 CL | 18042923.11 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 303541 | Catarman National High School | Catarman (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6936271.404 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 303541 | Catarman National High School | Catarman (Capital) | 1 |  | 8 | 2STY8CL | BATCH 13 CL | 11950076.849 |  |  | Terminated | 0 | [10 empty] | Contract Terminated on September 24, 2019. Under Preliminary Detailed Engineering.
NC 2016 | K10 | Region VIII | Northern Samar | 303541 | Catarman National High School | Catarman (Capital) | 1 |  | 12 | 2STY12CL | BATCH 13 CL | 14579217.18 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 313606 | Cawayan Integrated School | Catarman (Capital) | 1 | 1 | 8 | 2STY4CL | BATCH 13 CL | 12638675.28 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Northern Samar | 303548 | Eladio T. Balite Memorial School Of Fisheries | Bobon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2429548.27 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 303548 | Eladio T. Balite Memorial School Of Fisheries | Bobon | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11950076.849 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 303563 | Lope De Vega Nhs | Lope De Vega | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Northern Samar |  | Lope De Vega Nhs (Stand Alone) | Lope De Vega | 1 | 1 | 8 | 2STY8CL | BATCH 11 CL | 11950076.849 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Northern Samar |  | Lope De Vega Nhs (Stand Alone) | Lope De Vega | 1 |  | 2 | 1STY2CL | BATCH 11 CL | 2132466.644 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Northern Samar |  | Lope De Vega Nhs (Stand Alone) | Lope De Vega | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2551025.68 |  |  | Terminated | 0 | [10 empty] | Contract Terminated on June 29, 2022. Project site for validation by the Department of Education.
NC 2016 | TECHVOC | Region VIII | Northern Samar | 313623 | Maravilla National High School | Lavezares | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2551025.68 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Northern Samar | 303566 | Mondragon Agro-Ind'L Hs | Mondragon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 303566 | Mondragon Agro-Ind'L Hs | Mondragon | 1 | 1 | 24 | 2STY12CL | BATCH 13 CL | 32044277.796 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 303566 | Mondragon Agro-Ind'L Hs | Mondragon | 1 |  | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 303570 | Polangi National High School | Catarman (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11950076.849 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 122814 | Salvacion Es | Bobon | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Northern Samar | 303577 | San Isidro Agro-Industrial High School | San Isidro | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2623912.13 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 303578 | San Isidro Nhs (San Isidro) | San Isidro | 1 | 1 | 24 | 2STY12CL | BATCH 13 CL | 32044277.796 |  |  | Terminated | 0 | [10 empty] | Contract Terminated on October 14, 2022. Project site for validation by the Departement of Education.
NC 2016 | TECHVOC | Region VIII | Northern Samar | 303580 | San Jose Technical Hs | San Jose | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 123073 | San Juan Es | Lavezares | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Northern Samar | 303582 | San Vicente School Of Fisheries | San Vicente | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Terminated | 0 | [10 empty] | Contrac Terminated on October 14, 2022. For advertisement.
NC 2016 | K10 | Region VIII | Northern Samar |  | Victoria Cs | Victoria | 1 | 1 | 8 | 2STY8CL | BATCH 11 CL | 11950076.849 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Northern Samar | 123284 | Victoria Cs | Victoria | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2429548.27 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Northern Samar | 313602 | Anito Nhs | Gamay | 2 | 1 | 8 | 2STY4CL | BATCH 13 CL | 13413775.28 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Northern Samar | 303533 | Batag Nhs | Laoang | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Northern Samar | 303544 | Catubig Valley Nhs | Catubig | 2 | 1 | 16 | 2STY8CL | BATCH 13 CL | 23217185.18 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 303546 | Don Juan F. Avalon National High School | San Roque | 2 | 1 | 24 | 2STY8CL | BATCH 13 CL | 34675777.77 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Northern Samar | 303551 | Gala Vocational School | Gamay | 2 | 1 | 12 | 2STY6CL | BATCH 13 CL | 17829630.1 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 303556 | Laoang National Technical High School | Laoang | 2 | 1 | 16 | 2STY8CL | BATCH 13 CL | 23317185.18 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Northern Samar | 303560 | Las Navas National High School | Las Navas | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2429548.27 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 303560 | Las Navas National High School | Las Navas | 2 | 1 | 24 | 2STY8CL | BATCH 13 CL | 35125777.77 |  |  | Terminated | 0 | [10 empty] | (1) The project was terminated (wholly) for convenience due to original plan is no longer economically and technically feasible for construction as per result of Geotechnical Investigation. Moreover, no buffer fund was released to cover the proposed revised design which requires an additional allocation amounting to Php 5,244,796.26. (2) Site Validation will be conducted with representative from DepEd.
NC 2016 | TECHVOC | Region VIII | Northern Samar | 303559 | Lorenzo S. Menzon Ais | Lapinig | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2648207.61 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 313624 | Oleras Nhs | Laoang | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8814965.05 |  |  | Terminated | 0 | [10 empty] | (1) The project was terminated (wholly) for convenience due to original plan is no longer economically and technically feasible for construction as per result of Geotechnical Investigation. Moreover, no buffer fund was released to cover the proposed revised design which requires an additional allocation amounting to Php 1,433,488.38. (2) Site Validation will be conducted with representative from DepEd.
NC 2016 | SHS | Region VIII | Northern Samar | 303569 | Pambujan Nhs | Pambujan | 2 | 1 | 18 | 3STY9CL | BATCH 13 CL | 32020767.62 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 313603 | Rawis National High School | Laoang | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8814965.05 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 303583 | Silvino Lubos Vocational High School | Silvino Lobos | 2 | 1 | 16 | 2STY8CL | BATCH 13 CL | 24917185.18 |  |  | Terminated | 0 | [10 empty] | (1) One unit of the school building was already completed. However, the second unit cannot be implemented due to the recommendations as per result of soil investigation report. The project was terminated partly for convenience due to the project site of the second unit school building did not conform with the result of Geotechnical investigation. (2) Site Validation will be conducted with representative from DepEd.
NC 2016 | TECHVOC | Region VIII | Northern Samar | 303584 | Sumoroy Agro-Industrial School | Palapag | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2808700 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 303584 | Sumoroy Agro-Industrial School | Palapag | 2 | 1 | 24 | 3STY12CL | BATCH 13 CL | 40408991.338 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Northern Samar | 303584 | Sumoroy Agro-Industrial School | Palapag | 2 |  | 9 | 3STY9CL | BATCH 13 CL | 16110383.81 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Ormoc City | 124200 | Airport Primary School | Ormoc City | 4 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3025000 |  |  | Completed | 1 |  |  | P00074120VS-CW1 | 16IF0065 | 2016-04-27 | 2016-05-05 | 2016-05-17 | 2016-05-20 | 2016-07-21 | RJIR ENT.
NC 2016 | K10 | Region VIII | Ormoc City | 124175 | Cagbuhangin Elementary School | Ormoc City | 4 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1920000 |  |  | Completed | 1 |  |  | P00070556VS-CW1 | 16IF0043 | 2016-03-02 | 2016-03-10 | 2016-03-23 | 2016-05-10 | 2016-05-26 | GMP BUILDERS
NC 2016 | K10 | Region VIII | Ormoc City | 303654 | Dolores National High School | Ormoc City | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6690000 |  |  | Completed | 1 |  |  | P00070554VS-CW1 | 16IF0040 | 2016-03-02 | 2016-03-10 | 2016-03-23 | 2016-05-10 | 2016-05-26 | A.C. RIVERO DEV. CORP.
NC 2016 | K10 | Region VIII | Ormoc City | 124154 | Hugpa Elementary School | Ormoc City | 4 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1980000 |  |  | Completed | 1 |  |  | P00070557VS-CW1 | 16IF0042 | 2016-03-02 | 2016-03-10 | 2016-03-23 | 2016-05-10 | 2016-05-26 | GMP BUILDERS
NC 2016 | SHS | Region VIII | Ormoc City | 303655 | Ipil National High School | Ormoc City | 4 | 1 | 12 | 3STY12CL | BATCH 3 CL | 19140000 |  |  | Completed | 1 |  |  | P00070553VS-CW1 | 16IF0037 | 2016-03-02 | 2016-03-10 | 2016-03-22 | 2016-05-10 | 2016-05-26 | A.C. RIVERO DEV. CORP.
NC 2016 | K10 | Region VIII | Ormoc City | 313901 | Lilo-An Nat. High School | Ormoc City | 4 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6690000 |  |  | Completed | 1 |  |  | P00070553VS-CW2 | 16IF0103 | 2017-09-20 | 2016-10-05 | 2016-12-13 | 2016-12-16 | 2017-01-12 | A.C. RIVERO DEV. CORP.
NC 2016 | K10 | Region VIII | Ormoc City | 303656 | Linao National High School | Ormoc City | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6690000 |  |  | Completed | 1 |  |  | P00070555VS-CW1 | 16IF0038 | 2016-03-02 | 2016-03-10 | 2016-03-22 | 2016-05-10 | 2016-05-26 | J.A. ACHACOSO
NC 2016 | K10 | Region VIII | Ormoc City | 124164 | Mahayag Elementary School | Ormoc City | 4 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2870000 |  |  | Completed | 1 |  |  | P00070558VS-CW1 | 16IF0045 | 2016-03-02 | 2016-03-10 | 2016-03-22 | 2016-05-10 | 2016-05-26 | A.C. RIVERO DEV. CORP.
NC 2016 | K10 | Region VIII | Ormoc City | 124185 | Matica-A Elementary School | Ormoc City | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6710000 |  |  | Completed | 1 |  |  | P00070559VS-CW1 | 16IF0041 | 2016-03-02 | 2016-03-10 | 2016-03-22 | 2016-05-10 | 2016-06-13 | ARCA BUILDERS
NC 2016 | K10 | Region VIII | Ormoc City | 303658 | New Ormoc City National High School | Ormoc City | 4 | 1 | 12 | 3STY12CL | BATCH 11 CL | 17127665.62 |  |  | Completed | 1 |  |  | P00070559VS-CW2 | 16IF0091 | 2017-09-20 | 2016-09-15 | 2016-09-28 | 2016-09-30 | 2016-10-13 | ARCA BUILDERS
NC 2016 | K10 | Region VIII | Ormoc City | 313905 | Ormoc City Night High School | Ormoc City | 4 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8400000 |  |  | Completed | 1 |  |  | P00070560VS-CW1 | 16IF0039 | 2016-03-02 | 2016-03-10 | 2016-03-22 | 2016-05-10 | 2016-05-26 | RJIR ENT.
NC 2016 | K10 | Region VIII | Ormoc City | 303662 | Valencia Nat. High School | Ormoc City | 4 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8500000 |  |  | Completed | 1 |  |  | P00072437VS-CW1 | 16IF0051 | 2016-03-02 | 2016-03-10 | 2016-03-22 | 2016-05-23 | 2016-06-21 | A.C. RIVERO DEV. CORP.
NC 2016 | TECHVOC | Region VIII | Ormoc City | 303662 | Valencia Nat. High School | Ormoc City | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 1940000 |  |  | Completed | 1 |  |  | P00072633VS-CW1 | 16IF0052 | 2016-03-02 | 2016-03-10 | 2016-03-22 | 2016-06-15 | 2016-06-23 | CIRCLE Z
NC 2016 | K10 | Region VIII | Ormoc City | 194502 | Vl Villacencio Elementary School | Ormoc City | 4 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1960000 |  |  | Completed | 1 |  |  | P00070561VS-CW1 | 16IF0044 | 2016-03-02 | 2016-03-10 | 2016-03-22 | 2016-05-10 | 2016-05-26 | CIRCLE Z
NC 2016 | TECHVOC | Region VIII | Samar (Western Samar) | 303599 | Clarencio Calagos Mem Sof | Santa Margarita | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Samar (Western Samar) | 303599 | Clarencio Calagos Mem Sof | Santa Margarita | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8570000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Samar (Western Samar) | 303599 | Clarencio Calagos Mem Sof | Santa Margarita | 1 |  | 4 | 2STY4CL | BATCH 13 CL | 6469337 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Samar (Western Samar) | 303612 | Matuguinao National High School | Matuguinao | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Samar (Western Samar) | 303615 | Pagsanghan Nhs | Pagsanghan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Samar (Western Samar) | 303618 | Ramon T. Diaz Mhs | Gandara | 1 | 1 | 12 | 2STY6CL | BATCH 13 CL | 17140000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Samar (Western Samar) | 303618 | Ramon T. Diaz Mhs | Gandara | 1 |  | 4 | 2STY4CL | BATCH 13 CL | 6469337 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Samar (Western Samar) | 313708 | San Jorge Nhs | San Jorge | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Samar (Western Samar) | 313708 | San Jorge Nhs | San Jorge | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8570000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Samar (Western Samar) | 303632 | Sto. Nino Nhs | Santo Niño | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2750000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Samar (Western Samar) | 303643 | Zumarraga National School | Zumarraga | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Samar (Western Samar) | 303592 | Basey National High School | Basey | 2 | 1 | 18 | 2STY6CL | BATCH 3 CL | 8870000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Samar (Western Samar) | 303592 | Basey National High School | Basey | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Samar (Western Samar) | 303593 | Burgos Is | Basey | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Samar (Western Samar) | 303596 | Calapi Nhs | Motiong | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2750000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Samar (Western Samar) | 303597 | Calbiga National High School | Calbiga | 2 | 1 | 40 | 4STY20CL | BATCH 11 CL | 64836952.5344 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Samar (Western Samar) | 303606 | Hinabangan Nhs | Hinabangan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Samar (Western Samar) | 303608 | Independencia Nhs | Talalora | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Samar (Western Samar) | 303609 | Jiabong National High School | Jiabong | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2700000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Samar (Western Samar) | 123786 | Magsaysay Es | Santa Rita | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8570000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Samar (Western Samar) | 303613 | Motiong Nhs | Motiong | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Samar (Western Samar) | 303614 | Osmeña Nhs | Marabut | 2 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12921310.09 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Samar (Western Samar) | 303640 | Quintin Quijano Sr. Agricultural School | Pinabacdao | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Samar (Western Samar) | 303640 | Quintin Quijano Sr. Agricultural School | Pinabacdao | 2 | 1 | 8 | 2STY4CL | BATCH 13 CL | 12938674 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Samar (Western Samar) | 303626 | San Jose De Buan Nhs | San Jose De Buan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Samar (Western Samar) | 303631 | Sta. Rita National High School | Santa Rita | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Samar (Western Samar) | 303639 | Villareal Nhs | Villareal | 2 | 1 | 8 | 2STY4CL | BATCH 13 CL | 13138674 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Samar (Western Samar) | 303641 | Wright Nhs | Paranas (Wright) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Southern Leyte | 303453 | Don Agustin F. Escaño Nhs | Tomas Oppus | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Southern Leyte | 303460 | Himbangan National High School | Saint Bernard | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Southern Leyte | 303447 | Hinunangan National High School(Canipaan Nhs - Hinunangan Annex) | Hinunangan | 0 | 1 | 12 | 3STY12CL | BATCH 13 CL | 22017445.2359 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Southern Leyte | 313409 | Liloan National Technical Vocational High School | Liloan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Southern Leyte | 313409 | Liloan National Technical Vocational High School | Liloan | 0 | 1 | 36 | 2STY12CL | BATCH 13 CL | 51010121.324 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Southern Leyte | 303477 | Pintuyan National Vocational High School | Pintuyan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Southern Leyte | 303477 | Pintuyan National Vocational High School | Pintuyan | 0 | 1 | 12 | 3STY12CL | BATCH 13 CL | 22017445.2359 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Southern Leyte | 303477 | Pintuyan National Vocational High School | Pintuyan | 0 |  | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Southern Leyte | 303481 | San Juan Nhs | San Juan (Cabalian) | 0 | 1 | 12 | 3STY6CL | BATCH 11 CL | 24035879.932 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Southern Leyte | 303481 | San Juan Nhs | San Juan (Cabalian) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Southern Leyte | 303483 | San Ricardo National High School | San Ricardo | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Southern Leyte | 303487 | Sogod National High School | Sogod | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Southern Leyte | 303487 | Sogod National High School | Sogod | 0 | 1 | 36 | 3STY9CL | BATCH 13 CL | 68804476.198 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Southern Leyte | 303487 | Sogod National High School | Sogod | 0 |  | 12 | 3STY12CL | BATCH 13 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Southern Leyte | 303489 | Sta. Paz National High School | San Francisco | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Southern Leyte | 303492 | Villa Jacinta National Vocational High School | Macrohon | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Southern Leyte | 303492 | Villa Jacinta National Vocational High School | Macrohon | 0 | 1 | 12 | 3STY12CL | BATCH 13 CL | 21100403.969 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Tacloban City | 314003 | Antonio Balmes National High School | Tacloban City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6432000 |  |  | Reverted | 0
NC 2016 | K10 | Region VIII | Tacloban City | 124255 | Cabalawan Es | Tacloban City (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1853000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Tacloban City | 124224 | Caibaan Es | Tacloban City (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8346000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Tacloban City | 303665 | Cirilo Roy Montejo Nhs (Panalaron Nhs) | Tacloban City (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 13 CL | 10467131.51 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Tacloban City | 303663 | Leyte Nhs | Tacloban City (Capital) | 1 | 1 | 9 | 3STY9CL | BATCH 1 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Tacloban City | 303663 | Leyte Nhs | Tacloban City (Capital) | 1 |  | 12 | 4STY12CL | BATCH 1 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Tacloban City | 303663 | Leyte Nhs | Tacloban City (Capital) | 1 |  | 20 | 4STY20CL | BATCH 1 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Tacloban City | 124235 | Lucio Vivero Es | Tacloban City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Tacloban City | 195001 | Manlurip Elementary School | Tacloban City (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1833000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Tacloban City | 314004 | Northern Tacloban City National High School | Tacloban City (Capital) | 1 | 1 | 20 | 2STY10CL | BATCH 7 CL | 25796000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Tacloban City |  | Ridgeview Is | Tacloban City | 1 | 1 | 45 | 3STY15CL | BATCH 11 CL | 66900000 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Tacloban City | 303666 | Sagkahan National High School | Tacloban City (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Tacloban City | 303666 | Sagkahan National High School | Tacloban City (Capital) | 1 |  | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Tacloban City | 303666 | Sagkahan National High School | Tacloban City (Capital) | 1 |  | 16 | 4STY8CL | BATCH 7 CL | 29795037.68 |  |  | Completed | 1
NC 2016 | K10 | Region VIII | Tacloban City | 124248 | Salvacion Es | Tacloban City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6422000 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Tacloban City | 314005 | Scandinavian National High School | Tacloban City (Capital) | 1 | 1 | 24 | 4STY24CL | BATCH 1 CL | 35596257.14 |  |  | Completed | 1
NC 2016 | SHS | Region VIII | Tacloban City |  | Shs In V&G Subdivision, Tacloban City | Tacloban City (Capital) | 1 | 1 | 24 | 3STY12CL | BATCH 9 CL | 32830083.822 |  |  | Completed | 1
NC 2016 | TECHVOC | Region VIII | Tacloban City |  | Shs In V&G Subdivision, Tacloban City | Tacloban City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Baybay City | 121096 | Banahao ES | CITY OF BAYBAY | 5 | 1 | 2 | 1STY2CL | BATCH 2 | 2738254.17 |  |  | Completed | 1 |  |  | P00170802VS-CW1 | 17IG0121 |  | 2017-08-25 | 2017-09-07 |  | 2017-09-29 | JA ACHACOSO ENT. & GENERAL SERVICES
NC 2017 | K10 | Region VIII | Baybay City | 121079 | Baybay I CS (Baybay North CS) | CITY OF BAYBAY | 5 | 1 | 2 | 1STY2CL | BATCH 2 | 2788254.17 |  |  | Completed | 1 |  |  | P00170803VS-CW1 | 17IG0122 |  | 2017-08-25 | 2017-09-07 |  | 2017-09-29 | JUCONS CONSTRUCTION & SUPPLY
NC 2017 | K10 | Region VIII | Baybay City | 121132 | Bunga ES | CITY OF BAYBAY | 5 | 1 | 3 | 1STY3CL | BATCH 2 | 3931402.87 |  |  | Completed | 1 |  |  | P00170804VS-CW1 | 17IG0123 |  | 2017-08-25 | 2017-09-07 |  | 2017-09-29 | REX E. MORALES CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120784 | Villa Enage Elemenetary School | BILIRAN | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3026402.65 |  |  | Completed | 1 |  |  | P00173528VS-CW1 | 17IA0095 | 2017-11-06 | 2017-11-16 | 2017-11-27 | 2017-12-15 | 2017-12-15 | QYT CONSTRUCTION & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120785 | Balaquid ES | CABUCGAYAN | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2834093.93 |  |  | Completed | 1 |  |  | P00173529VS-CW1 | 17IA0088 | 2017-10-12 | 2017-10-23 | 2017-11-03 | 2017-11-22 | 2017-11-29 | BNL CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120796 | Talibong ES | CABUCGAYAN | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2834093.93 |  |  | Completed | 1 |  |  | P00173530VS-CW1 | 17IA0087 | 2017-10-12 | 2017-10-23 | 2017-11-03 | 2017-11-28 | 2017-11-29 | QYT CONSTRUCTION & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120806 | Kawayanon ES | CAIBIRAN | 0 | 1 | 4 | 1STY4CL | BATCH 4 | 5317327.6 |  |  | Completed | 1 |  |  | P00173531VS-CW1 | 17IA0094 | 2017-11-06 | 2017-11-16 | 2017-11-27 | 2017-12-15 | 2017-12-20 | QYT CONSTRUCTION & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120810 | Maurang ES | CAIBIRAN | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 4088659.12 |  |  | Completed | 1 |  |  | P00173532VS-CW1 | 17IA0089 | 2017-10-12 | 2017-10-23 | 2017-11-03 | 2017-11-22 | 2017-11-29 | W.B. ALAGAO CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120869 | CAPIÑAHAN ES | NAVAL (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1 |  |  | P00173533VS-CW1 | 17IA0096 | 2017-11-06 | 2017-11-16 | 2017-11-27 | 2017-12-15 | 2017-12-20 | BNL CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120873 | Haguikhican ES | NAVAL (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3201020.1 |  |  | Completed | 1 |  |  | P00173534VS-CW1 | 17IA0093 | 2017-11-06 | 2017-11-16 | 2017-11-27 | 2017-12-15 | 2017-12-20 | BNL CONSTRUCTION
NC 2017 | K10 | Region VIII | Borongan City | 122406 | San Gregorio ES | CITY OF BORONGAN (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2767400 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Borongan City | 122364 | Siha ES | CITY OF BORONGAN (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2684000 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Eastern Samar | 303499 | Dolores NHS | DOLORES | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2604700 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Eastern Samar | 303499 | Dolores NHS | DOLORES | 0 |  | 2 | 1STY2CL | BATCH 4 | 2604700 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Eastern Samar | 303499 | Dolores NHS | DOLORES | 0 |  | 2 | 1STY2CL | BATCH 4 | 2604700 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Eastern Samar | 303499 | Dolores NHS | DOLORES | 0 |  | 2 | 1STY2CL | BATCH 4 | 2669700 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Eastern Samar | 303499 | Dolores NHS | DOLORES | 0 |  | 3 | 1STY3CL | BATCH 4 | 3875000 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Eastern Samar | 122501 | Sta. Cruz ES | GENERAL MACARTHUR | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2748400 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Eastern Samar | 122501 | Sta. Cruz ES | GENERAL MACARTHUR | 0 |  | 2 | 1STY2CL | BATCH 4 | 2748400 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Eastern Samar | 303502 | Giporlos National Trade School | GIPORLOS | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 3991000 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Eastern Samar | 303502 | Giporlos National Trade School | GIPORLOS | 0 |  | 2 | 1STY2CL | BATCH 4 | 2663000 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Eastern Samar | 122582 | San Roque Elementary School | JIPAPAD | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3745200 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Eastern Samar | 122647 | San Eduardo ES | ORAS | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2617000 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Eastern Samar | 122705 | Asgad ES | SALCEDO | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2871000 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Eastern Samar | 303516 | Matarinao School of Fisheries | SALCEDO | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2996000 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Eastern Samar | 122700 | Salcedo CES | SALCEDO | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 4067000 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Eastern Samar | 303493 | Alugan NSCHI | SAN POLICARPO | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2666400 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Eastern Samar | 122752 | San Isidro ES | SULAT | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2738000 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Eastern Samar | 122752 | San Isidro ES | SULAT | 0 |  | 2 | 1STY2CL | BATCH 4 | 2738000 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Eastern Samar | 122754 | San Mateo ES | SULAT | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2738000 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Eastern Samar | 122756 | Sto. Nino ES | SULAT | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2752700 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Eastern Samar | 122758 | Sulat CES | SULAT | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2752500 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Eastern Samar | 122758 | Sulat CES | SULAT | 0 |  | 2 | 1STY2CL | BATCH 4 | 2752500 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Eastern Samar | 303529 | Taft National High School | TAFT | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 3903300 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303345 | Balugo National High School | ALBUERA | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2813745.92 |  |  | Completed | 1 |  |  | P00173577VS | 17IE0088 | [5 empty] | RJIR Enterprises
NC 2017 | TVL | Region VIII | Leyte | 303366 | Damulaan National High School | ALBUERA | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P00173579VS | 17IE0096 | [5 empty] | R. Allosa Construction & Trucking Services
NC 2017 | TVL | Region VIII | Leyte | 303368 | Dr. Geronimo B. Zaldivar Memorial School of Fisheries | ALBUERA | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P00101057VS | 17IE0112 | [5 empty] | RJIR Enterprises
NC 2017 | K10 | Region VIII | Leyte | 121003 | Tabgas ES | ALBUERA | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2813745.92 |  |  | Completed | 1 |  |  | P001733580VS | 17IE0113 | [5 empty] | RJIR Enterprises
NC 2017 | K10 | Region VIII | Leyte | 121301 | Patoc Elementary School | DAGAMI | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 3175835.18 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121442 | Honan Elementary School | ISABEL | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2813745.92 |  |  | Completed | 1 |  |  | P00176755VS-CW1 | 17ID0116 |  |  |  | 2018-01-05 | 2018-01-11 | WJ BUILDERS
NC 2017 | TVL | Region VIII | Leyte | 303378 | Isabel National High School | ISABEL | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2813745.92 |  |  | Completed | 1 |  |  | P00176756VS-CW1 | 17ID0134 |  |  |  | 2017-11-28 | 2017-12-01 | ROCKCON BUILDERS AND CONSTRUCTION SUPPLY
NC 2017 | K10 | Region VIII | Leyte | 121444 | Libertad ES | ISABEL | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2813745.92 |  |  | Completed | 1 |  |  | P00176788VS | 17IE0106 | [5 empty] | R. Allosa Construction & Trucking Services
NC 2017 | K10 | Region VIII | Leyte | 121446 | Matlang ES | ISABEL | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2763745.92 |  |  | Completed | 1 |  |  | P00176757VS-CW1 | 17ID0121 |  |  |  | 2017-12-21 | 2017-11-29 | THREADSTONE CONSTRUCTION AND SUPPLY
NC 2017 | TVL | Region VIII | Leyte | 303406 | Matlang NHS | ISABEL | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2763745.92 |  |  | Completed | 1 |  |  | P00176758VS-CW1 | 17ID0133 |  |  |  | 2017-11-27 | 2017-12-01 | RJIR ENTERPRISES
NC 2017 | SHS | Region VIII | Leyte | 303406 | Matlang NHS | ISABEL | 4 |  | 2 | 1STY2CL | BATCH 4 | 2763745.92 |  |  | Completed | 1 |  |  | P00176759VS-CW1 | 17ID0140 |  |  |  | 2017-12-27 | 2018-01-03 | CHU CONSTRUCTION
NC 2017 | TVL | Region VIII | Leyte | 313334 | Putingbato, Cangag, Canandan, Consolacion St. Filomena National High School | ISABEL | 4 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3113745.92 |  |  | Completed | 1 |  |  | P00176760VS-CW1 | 17ID0115 |  |  |  | 2017-11-24 | 2017-11-29 | CHU CONSTRUCTION
NC 2017 | TVL | Region VIII | Leyte | 313334 | Putingbato, Cangag, Canandan, Consolacion St. Filomena National High School | ISABEL | 4 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3113745.92 |  |  | Completed | 1 |  |  | P00176761VS-CW1 | 17ID0112 |  |  |  | 2018-08-03 | 2018-01-08 | ROCKON BUILDERS AND CONSTRUCTION SUPPLY
NC 2017 | TVL | Region VIII | Leyte | 303422 | San Francisco National High School | ISABEL | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2763745.92 |  |  | Completed | 1 |  |  | P00176762VS-CW1 | 17ID0125 |  |  |  | 2017-12-22 | 2017-12-28 | MN MACATO BUILDERS
NC 2017 | K10 | Region VIII | Leyte | 121538 | Kananga Central School | KANANGA | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2813745.92 |  |  | Completed | 1 |  |  | P00176763VS-CW1 | 17ID0120 |  |  |  | 2017-11-22 | 2017-11-24 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2017 | TVL | Region VIII | Leyte | 303383 | Kananga National High School - Main | KANANGA | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2763745.92 |  |  | Completed | 1 |  |  | P00176764VS-CW1 | 17ID0122 |  |  |  | 2017-12-08 | 2017-12-22 | 3A'S BUILDERS
NC 2017 | SHS | Region VIII | Leyte | 303395 | Lim-ao National High School | KANANGA | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2763745.92 |  |  | Completed | 1 |  |  | P00176765VS-CW1 | 17ID0123 |  |  |  | 2017-11-27 | 2017-12-01 | YFL BUILDERS
NC 2017 | TVL | Region VIII | Leyte | 303395 | Lim-ao National High School | KANANGA | 4 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2763745.92 |  |  | Completed | 1 |  |  | P00176766VS-CW1 | 17ID0124 |  |  |  | 2018-01-03 | 2018-01-08 | KUBLAI CONSTRUCTION AND SUPPLIES
NC 2017 | K10 | Region VIII | Leyte | 121547 | Montebello ES | KANANGA | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2763745.92 |  |  | Completed | 1 |  |  | P00176769VS-CW1 | 17ID0103 |  |  |  | 2017-12-27 | 2017-12-29 | MN MACATO BUILDERS
NC 2017 | TVL | Region VIII | Leyte | 313327 | Rizal National High School | KANANGA | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2763745.92 |  |  | Completed | 1 |  |  | P00176767VS-CW1 | 17ID0097 |  |  |  | 2017-11-27 | 2017-12-01 | VENUS ENGINEERING & CONSTRUCTION
NC 2017 | K10 | Region VIII | Leyte | 121556 | Tugbong Central School | KANANGA | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P00176768VS-CW1 | 17ID0098 |  |  |  | 2017-11-22 | 2017-11-27 | ROCKCON BUILDERS AND CONSTRUCTION SUPPLY
NC 2017 | TVL | Region VIII | Leyte | 303428 | Sta. Ana National High School | LAPAZ | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3229040.835 |  |  | Completed | 1 |  |  | P00176770VS-CW1 | 17ID0099 |  |  |  | 2017-11-23 | 2017-11-27 | E.G. CANABE CONSTRUCTION
NC 2017 | TVL | Region VIII | Leyte | 303428 | Sta. Ana National High School | LAPAZ | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3229040.835 |  |  | Completed | 1 |  |  | P00176771VS-CW1 | 17ID0104 |  |  |  | 2018-01-03 | 2018-01-05 | XED"S CONSTRUCTION
NC 2017 | K10 | Region VIII | Leyte | 121587 | Baco ES | LEYTE | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3863803.72 |  |  | Completed | 1 |  |  | P00176772VS-CW1 | 17ID0135 |  |  |  | 2017-11-29 | 2018-12-05 | RCC BUILDERS AND ENTERPRISES
NC 2017 | K10 | Region VIII | Leyte | 121588 | Bagabao PS | LEYTE | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 4032225.47 |  |  | Completed | 1 |  |  | P00176773VS-CW1 | 17ID0113 |  |  |  | 2017-11-27 | 2017-12-01 | R.T. MOTRABE CONSTRUCTION
NC 2017 | TVL | Region VIII | Leyte | 303404 | Matag-ob National High School | MATAG-OB | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3113745.92 |  |  | Completed | 1 |  |  | P00176774VS-CW1 | 17ID0114 |  |  |  | 2017-11-24 | 2017-11-28 | ROCKCON BUILDERS AND CONSTRUCTION SUPPLY
NC 2017 | K10 | Region VIII | Leyte | 121721 | Casilda Elementary School | MERIDA | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121723 | Libas Elementary School | MERIDA | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P00176775VS-CW1 | 17ID0164 |  |  |  | 2018-01-05 | 2018-01-11 | GENETIAN BUILDERS
NC 2017 | TVL | Region VIII | Leyte | 303409 | Merida Vocational School - Calunangan Annex | MERIDA | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3113745.92 |  |  | Completed | 1 |  |  | P00176777VS-CW1 | 17ID0175 |  |  |  | 2018-01-03 | 2018-01-05 | 3A'S BUILDERS
NC 2017 | TVL | Region VIII | Leyte | 303410 | Puerto Bello National High School | MERIDA | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2813745.92 |  |  | Completed | 1 |  |  | P00176776VS-CW1 | 17ID0106 |  |  |  | 2017-11-27 | 2017-11-29 | GENETIAN BUILDERS
NC 2017 | K10 | Region VIII | Leyte | 121790 | Canipaan ES | PALOMPON | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2813745.92 |  |  | Completed | 1 |  |  | P00176789VS | 17IE0107 | [5 empty] | RJIR Enterprises
NC 2017 | TVL | Region VIII | Leyte | 303396 | Lomonon National High School | PALOMPON | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2813745.92 |  |  | Completed | 1 |  |  | P00176778VS-CW1 | 17ID0137 |  |  |  | 2017-12-27 | 2018-01-03 | CHU CONSTRUCTION
NC 2017 | K10 | Region VIII | Leyte | 121771 | Mabini ES | PALOMPON | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2813745.92 |  |  | Completed | 1 |  |  | P00176779VS-CW1 | 17ID0139 |  |  |  | 2017-12-27 | 2018-01-03 | G. BUILDERS
NC 2017 | TVL | Region VIII | Leyte | 313306 | Palompon National High School | PALOMPON | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2713745.92 |  |  | Completed | 1 |  |  | P00176780VS-CW1 | 17ID0131 |  |  |  | 2018-11-20 | 2018-11-24 | G. BUILDERS
NC 2017 | K10 | Region VIII | Leyte | 121773 | Palompon North CS | PALOMPON | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121805 | San Pedro Elementary School | PALOMPON | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2813745.92 |  |  | Completed | 1 |  |  | P00176781VS-CW1 | 17ID0100 |  |  |  | 2017-11-22 | 2017-11-27 | ROCKCON BUILDERS AND CONSTRUCTION SUPPLY
NC 2017 | TVL | Region VIII | Leyte | 303435 | Taberna National High School | PALOMPON | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2713745.92 |  |  | Completed | 1 |  |  | P00176782VS-CW1 | 17ID0107 |  |  |  | 2017-11-27 | 2017-12-01 | R.T. MOTRABE CONSTRUCTION
NC 2017 | TVL | Region VIII | Leyte | 303438 | Tinabilan National High School | PALOMPON | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121782 | Tinago ES | PALOMPON | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2813745.92 |  |  | Completed | 1 |  |  | P00176783VS-CW1 | 17ID0117 |  |  |  | 2017-11-29 | 2017-12-07 | MASS CONSTRUCTION
NC 2017 | K10 | Region VIII | Leyte | 121783 | Tinubdan ES | PALOMPON | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2813745.92 |  |  | Completed | 1 |  |  | P00176790VS | 17IE0108 | [5 empty] | Jucons Construction and Supply
NC 2017 | TVL | Region VIII | Leyte | 313330 | Manaybanay National High School | PASTRANA | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3503872.2 |  |  | Completed | 1 |  |  | P00176701VS | 17IE0120 | [5 empty] | R. Allosa Construction & Trucking Services
NC 2017 | K10 | Region VIII | Leyte | 121829 | Banat-i Elementary School | SAN ISIDRO | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3881488.07 |  |  | Completed | 1 |  |  | P00176792VS | 17IE0119 | [5 empty] | RJIR Enterprises
NC 2017 | K10 | Region VIII | Leyte | 121830 | Basud ES | SAN ISIDRO | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3788435.02 |  |  | Completed | 1 |  |  | P001767933VS | 17IE0109 | [5 empty] | Jucons Construction and Supply
NC 2017 | K10 | Region VIII | Leyte | 191512 | Danao Elementary School | SAN ISIDRO | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2796708.13 |  |  | Completed | 1 |  |  | P00176794VS | 17IE0110 | [5 empty] | RJIR Enterprises
NC 2017 | K10 | Region VIII | Leyte | 121838 | Kabungaan Elementary School | SAN ISIDRO | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 4052225.47 |  |  | Completed | 1 |  |  | P00176784VS-CW1 | 17ID0132 |  |  |  | 2017-12-01 | 2017-12-12 | JELM CONSTRUCTION
NC 2017 | K10 | Region VIII | Leyte | 121840 | Matungao Elementary School | SAN ISIDRO | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P00176785VS-CW1 | 17ID0138 |  |  |  | 2017-12-23 | 2017-12-29 | WAWOT BUILDERS
NC 2017 | K10 | Region VIII | Leyte | 121842 | San Isidro CS | SAN ISIDRO | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2633745.92 |  |  | Completed | 1 |  |  | P00176786VS-CW1 | 17ID0101 |  |  |  | 2018-01-03 | 2018-01-08 | MN MACATO BUILDERS
NC 2017 | K10 | Region VIII | Leyte | 121843 | San Jose ES | SAN ISIDRO | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3956856.77 |  |  | Completed | 1 |  |  | P00176787VS-CW1 | 17ID0102 |  |  |  | 2017-11-28 | 2017-12-01 | WAWOT BUILDERS
NC 2017 | K10 | Region VIII | Leyte | 121844 | San Miguel ES | SAN ISIDRO | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 4052225.47 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121847 | Tinago Elementary School | SAN ISIDRO | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2666020.84 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121883 | Catmon ES | TABANGO | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2633745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 313309 | Gibacungan National High School | TABANGO | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2796708.13 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121893 | Tabango North CS | TABANGO | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2633745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121894 | Tabing ES | TABANGO | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2633745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121895 | Tugas ES | TABANGO | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2633745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121968 | Hinabuyan CS | VILLABA | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3788435.02 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 313345 | Sulpa National High School | VILLABA | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2744433.22 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303389 | Villaba National High School (LNCAST) | VILLABA | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2796708.13 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 122778 | Cabacungan ES | ALLEN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2623094.36 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 122786 | Lipata ES | ALLEN | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3858435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 122786 | Lipata ES | ALLEN | 1 |  | 3 | 1STY3CL | BATCH 4 | 3858435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 122792 | Biri CES | BIRI | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2985260.03 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 122806 | Dancalan elem.school | BOBON | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2679758.4 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Northern Samar | 303548 | Eladio T. Balite Memorial School of Fisheries | BOBON | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2728169.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 122846 | cervantes ES | CATARMAN (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 4056425.29 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 122866 | Galutan ES | CATARMAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 122873 | Polangi ES | CATARMAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2813756.47 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Northern Samar | 303570 | Polangi National HIgh School | CATARMAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2633507.79 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 122881 | Catubig CS | CATUBIG | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2682042.14 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 122881 | Catubig CS | CATUBIG | 2 |  | 3 | 1STY3CL | BATCH 4 | 3933803.72 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 122922 | Cagamutan Central Elementary School | GAMAY | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 4046856.77 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 122922 | Cagamutan Central Elementary School | GAMAY | 2 |  | 3 | 1STY3CL | BATCH 4 | 4046856.77 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 122970 | Bayog ES | LAOANG | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2731364.49 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 122956 | Cahayagan Elementary School | LAOANG | 2 | 1 | 4 | 1STY4CL | BATCH 4 | 4937234.66 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Northern Samar | 303538 | Cahayagan NHS | LAOANG | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 4371384.62 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 122980 | Gibatangan Elementary School | LAOANG | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 3005807.81 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Northern Samar | 303586 | Vigo National High School | LAOANG | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 4220647.22 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 122996 | Lapinig CS | LAPINIG | 2 | 1 | 4 | 1STY4CL | BATCH 4 | 5010559.93 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 122996 | Lapinig CS | LAPINIG | 2 |  | 4 | 1STY4CL | BATCH 4 | 5010559.93 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 122997 | Lo-ok ES | LAPINIG | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2739089.57 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 123007 | Capotoan ES | LAS NAVAS | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 4546753.32 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 123026 | Lourdes ES | LAS NAVAS | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 3005807.81 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 123064 | Lavezares Central Elementary School | LAVEZARES | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3860442.41 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Northern Samar | 313623 | MARAVILLA NATIONAL HIGH SCHOOL | LAVEZARES | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2889143.17 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 123090 | Lope De Vega Central School | LOPE DE VEGA | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2884746.94 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 303563 | Lope De Vega NHS | LOPE DE VEGA | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2893581.03 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Northern Samar | 303550 | Francisca Dominice NHS | MONDRAGON | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2755815.2 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 123125 | La Trinidad PS | MONDRAGON | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3837149.26 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 123129 | Nenita Central School | MONDRAGON | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 4048864.16 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Northern Samar | 303568 | Nenita National High School | MONDRAGON | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2756290.34 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 123159 | Napo PS | PALAPAG | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2666020.84 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 123182 | Pambujan 1 Central School | PAMBUJAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2679883.38 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 123182 | Pambujan 1 Central School | PAMBUJAN | 2 |  | 2 | 1STY2CL | BATCH 4 | 2679883.38 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 123199 | Egang Elementary School | SAN ANTONIO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2882131.84 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 123203 | San Antonio CS | SAN ANTONIO | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 4238787.17 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 123204 | San Nicolas ES | SAN ANTONIO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2947499.81 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 123214 | San Isidro CES | SAN ISIDRO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2675084.18 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 123215 | San Juan ES | SAN ISIDRO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2771481.38 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 123216 | San Roque ES | SAN ISIDRO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2630551.34 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 123229 | San Jose CS | SAN JOSE | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3854894.59 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 123229 | San Jose CS | SAN JOSE | 1 |  | 2 | 1STY2CL | BATCH 4 | 2676580.92 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Northern Samar | 313618 | Balnasan National High School | SAN ROQUE | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2744433.22 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Northern Samar | 313604 | Bantayan NHS | SAN ROQUE | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2671020.84 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 123245 | San Roque CS | SAN ROQUE | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2674655.89 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 123245 | San Roque CS | SAN ROQUE | 2 |  | 2 | 1STY2CL | BATCH 4 | 2703745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 123274 | Erenas ES | VICTORIA | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2710741.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 123284 | Victoria CS | VICTORIA | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2708671.17 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Ormoc City | 124147 | Camp Downes Elementary School | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P00173666VS-CW1 | 171F0087 | 2017-11-09 | 2017-09-21 | 2017-03-10 | 2017-11-10 | 2017-11-17 | RJIR ENT.
NC 2017 | K10 | Region VIII | Ormoc City | 124195 | Linao Central School | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P00173669VS-CW1 | 171F0084 | 2017-11-09 | 2017-09-21 | 2017-03-10 | 2017-11-10 | 2017-11-15 | A.C. RIVERO DEV. CORP.
NC 2017 | K10 | Region VIII | Ormoc City | 124187 | Nueva Vista Elementary School | ORMOC CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2675246.35 |  |  | Completed | 1 |  |  | P00173668VS-CW1 | 171F0085 | 2017-11-09 | 2017-09-21 | 2017-03-10 | 2017-11-10 | 2017-11-13 | GMP BUILDERS
NC 2017 | K10 | Region VIII | Ormoc City | 124169 | San Antonio Elementary School | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P00173667VS-CW1 | 171F0086 | 2017-11-09 | 2017-09-21 | 2017-03-10 | 2017-11-11 | 2017-11-13 | GMP BUILDERS
NC 2017 | SHS | Region VIII | Ormoc City | 303662 | Valencia National High School | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P00173670VS-CW1 | 171F0083 | 2017-11-09 | 2017-09-21 | 2017-03-10 | 2017-11-11 | 2017-11-17 | COLLERA CONST.
NC 2017 | TVL | Region VIII | Samar (Western Samar) | 303588 | Almagro NHS | ALMAGRO | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2843745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Samar (Western Samar) | 303588 | Almagro NHS | ALMAGRO | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2843745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Samar (Western Samar) | 303588 | Almagro NHS | ALMAGRO | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2843745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Samar (Western Samar) | 123292 | Lunang I ES | ALMAGRO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2843745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Samar (Western Samar) | 123307 | Basey I Central Elem. school | BASEY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613000.74 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 303592 | Basey National High School | BASEY | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3768000.43 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 303592 | Basey National High School | BASEY | 2 |  | 2 | 1STY2CL | BATCH 4 | 2613000.74 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 303637 | Valeriano C. Yancha Mem. Agr'l. Sch. | BASEY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613000.74 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Samar (Western Samar) | 123474 | Cagutsan PS | DARAM | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2875000.11 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Samar (Western Samar) | 123479 | Casab-Ahan ES | DARAM | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2875000.11 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Samar (Western Samar) | 123490 | Nipa ES | DARAM | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2875000.11 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Samar (Western Samar) | 123491 | San Jose ES | DARAM | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2875000.11 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Samar (Western Samar) | 123469 | Yangta Elementary School | DARAM | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2875000.11 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Samar (Western Samar) | 123577 | Mugdo ES | HINABANGAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613000.74 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Samar (Western Samar) | 123588 | Catalina ES | JIABONG | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613000.74 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Samar (Western Samar) | 123714 | Cabaywa ES | SAN SEBASTIAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2875000.11 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Samar (Western Samar) | 123716 | Campiyak Elementary School | SAN SEBASTIAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613000.74 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Samar (Western Samar) | 123718 | Dolores ES | SAN SEBASTIAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613000.74 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 303599 | Clarencio Calagos Mem SOF | SANTA MARGARITA | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Samar (Western Samar) | 123772 | Sta. Rita I CS | SANTA RITA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613000.74 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Samar (Western Samar) | 313703 | Cabunga-an IS | SANTO NIÑO | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 4 | 5088351.15 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Samar (Western Samar) | 313724 | Balocawe Integrated School | TAGAPUL-AN | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 4 | 5128351.15 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 303590 | Baquiw NHS | TAGAPUL-AN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2982863.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Samar (Western Samar) | 123827 | Tagapul-an CS | TAGAPUL-AN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2883745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Samar (Western Samar) | 303633 | Tagapul-an NHS | TAGAPUL-AN | 1 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 4 | 10694983.68 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Samar (Western Samar) | 123901 | Placer Elem. School | TALALORA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2875000.11 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 303634 | Tarangnan National High School | TARANGNAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2763745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Samar (Western Samar) | 123890 | Sto. Nino ES | VILLAREAL | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613000.74 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 121998 | Bunga Elementary School | BONTOC | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2903639.4 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122005 | Hilaan Elementary School | BONTOC | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 4660427.33 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122022 | Union Elementary School | BONTOC | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2848295.76 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 192006 | Baculod MG Elementary School | HINUNDAYAN | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2920570.68 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122068 | Bugho Elementary School | HINUNDAYAN | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2870570.68 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122072 | Hubasan Elementary School | HINUNDAYAN | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2870570.68 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122076 | Plaridel Elementary School | HINUNDAYAN | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2870570.68 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122116 | Tabugon Elementary School | LILOAN | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2870570.68 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122225 | San Agustin Elementary School | LIMASAWA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3582347.88 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122230 | Triana Elementary School | LIMASAWA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3500200.25 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303462 | Ichon NHS | MACROHON | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3089462.13 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122215 | STA. CRUZ ELEMENTARY SCHOOL | MALITBOG | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3062079.59 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122219 | Dinahugan Primary School | PADRE BURGOS | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2901708.13 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122224 | Padre Burgos Central School | PADRE BURGOS | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2896708.13 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122228 | Santo Rosario Elementary School | PADRE BURGOS | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2793295.76 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122239 | Pintuyan Central School | PINTUYAN | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 4621113.3 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122291 | Hindag-An ES | SAINT BERNARD | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3116844.67 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122297 | Malinao Elementary School | SAINT BERNARD | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2935914.32 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122302 | Saint Bernard Central School | SAINT BERNARD | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3116844.67 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303489 | Sta. Paz National High School | SAN FRANCISCO | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3166844.67 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122115 | Sudmon Elementary School | SAN FRANCISCO | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3166844.67 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 313408 | Katipunan NHS | SILAGO | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2909776.86 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 313408 | Katipunan NHS | SILAGO | 0 |  | 2 | 1STY2CL | BATCH 4 | 2909776.86 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 303449 | Consolacion National High School | SOGOD | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3062079.59 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 192033 | Mabicay ES | SOGOD | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2845570.68 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 192033 | Mabicay ES | SOGOD | 0 |  | 2 | 1STY2CL | BATCH 4 | 2845570.68 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303453 | Don Agustin F. Escaño NHS | TOMAS OPPUS | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3212079.59 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303427 | Seguinon National High School | ALBUERA | 4 | 1 | 2 | 1STY2CL | BATCH 7 | 2763745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121154 | Burauen North CS | BURAUEN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3768435 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121197 | Lusad ES | BURAUEN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2723887 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121221 | Villalon CS | CALUBIAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2816708.13 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121240 | Culasian ES | CAPOOCAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 191505 | Lemon-San Joaquin ES | CAPOOCAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 303418 | Pinamopoan National High School | CAPOOCAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2723887 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121256 | Barugohay Sur ES | CARIGARA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121283 | Abaca Elementary School | DAGAMI | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2723887 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121310 | Cabuloran Elementary School | DAGAMI | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2805246 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121292 | Canlingga Elementary School | DAGAMI | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2723887 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121293 | Dagami North CS | DAGAMI | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2805246 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121314 | Guinarona Elementary School | DAGAMI | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2723887 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121294 | Hiabangan Elementary School | DAGAMI | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2723887 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303355 | Cabacungan National High School | DULAG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2805246 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121321 | Calipayan Elementary School | DULAG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2845287 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121323 | Camitoc Elementary | DULAG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2845287 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121456 | Buenavista Elementary School | JARO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 313303 | Teofilo R. Macaso Memorial NHS | JARO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121489 | Uguiao Elementary School | JARO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2723887 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121516 | Alegria ES | JULITA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121530 | Sto. Nino ES | JULITA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 313327 | Rizal National High School | KANANGA | 4 | 1 | 2 | 1STY2CL | BATCH 7 | 2763745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 313332 | Buracan National High School | LAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121574 | Luneta ES | LAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2723887 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303428 | STA. ANA NATIONAL HIGH SCHOOL | LAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2723887 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121592 | Consuegra ES | LEYTE | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2738295.76 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303397 | Macarthur National High School | MACARTHUR | 2 | 1 | 5 | 1STY5CL | BATCH 7 | 6072650 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121623 | Olmedo Elementary School | MACARTHUR | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2723887 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121625 | Palale Elementary School | MACARTHUR | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2723887 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303404 | Matag-ob National High School | MATAG-OB | 4 | 1 | 2 | 1STY2CL | BATCH 7 | 3113745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121702 | Calipayan Elementary School | MAYORGA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2845287 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303407 | Mayorga National High School | MAYORGA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2723887 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121725 | Lundag Elementary School | MERIDA | 4 | 1 | 2 | 1STY2CL | BATCH 7 | 3113745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303380 | Juan Villablanca Memorial High School | PASTRANA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121831 | Biasong ES | SAN ISIDRO | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2666020.84 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121832 | Bunacan ES | SAN ISIDRO | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2796708.13 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121833 | Busay ES | SAN ISIDRO | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2764433.22 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121837 | Hugpa ES | SAN ISIDRO | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2744433.22 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121839 | Linao ES | SAN ISIDRO | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2666020.84 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303382 | Justimbaste-Remandaban National High School | TABONTABON | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2723887 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121917 | Tabontabon Central School | TABONTABON | 2 | 1 | 5 | 1STY5CL | BATCH 7 | 6072650 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121960 | Balire Elementary School | TUNGA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121959 | Banawang Elementary School | TUNGA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2845287 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Maasin City | 122121 | Batuan ES | CITY OF MAASIN (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2967974.42 |  |  | Completed | 1 |  |  | P00176799VS-CW1 | 17-IL-0104 | 2017-10-17 | 2017-10-25 | 2017-08-11 | 2017-11-15 | 2017-01-12 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2017 | K10 | Region VIII | Maasin City | 122122 | Baugo ES | CITY OF MAASIN (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3042974.42 |  |  | Completed | 1 |  |  | P00176800 | 17-IL-0100 | 2017-10-17 | 2017-10-25 | 2017-08-11 | 2017-11-15 | 2017-01-12 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2017 | K10 | Region VIII | Maasin City | 122129 | Guadalupe ES | CITY OF MAASIN (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2845570.68 |  |  | Completed | 1 |  |  | P00176801VS | 17-IL-0102 | 2017-10-17 | 2017-10-25 | 2017-08-11 | 2017-11-15 | 2017-01-12 | CEAN CONSTRUCTION
NC 2017 | K10 | Region VIII | Maasin City | 122138 | Malapoc Sur ES | CITY OF MAASIN (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2870570.68 |  |  | Completed | 1 |  |  | P00176802VS | 17-IL-0106 | 2017-10-17 | 2017-10-25 | 2017-08-11 | 2017-11-15 | 2017-01-12 | A.C. RIVERO DEVT. CORPORATION
NC 2017 | K10 | Region VIII | Maasin City | 122166 | Maria Clara ES | CITY OF MAASIN (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2818295.76 |  |  | Completed | 1 |  |  | P00176803VS | 17-IL-0101 | 2017-10-17 | 2017-10-25 | 2017-08-11 | 2017-11-15 | 2017-01-12 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2017 | K10 | Region VIII | Maasin City | 122168 | Nonok Norte ES | CITY OF MAASIN (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3013527.66 |  |  | Completed | 1 |  |  | P00176804VS | 17-IL-0105 | 2017-10-17 | 2017-10-25 | 2017-08-11 | 2017-11-15 | 2017-01-12 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2017 | K10 | Region VIII | Maasin City | 122174 | San Rafael ES | CITY OF MAASIN (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2845570.68 |  |  | Completed | 1 |  |  | P00176805VS | 17-IL-0103 | 2017-10-17 | 2017-10-25 | 2017-08-11 | 2017-11-15 | 2017-01-12 | CEAN CONSTRUCTION
NC 2017 | TVL | Region VIII | Northern Samar | 303544 | Catubig Valley NHS | CATUBIG | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2952952.11 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Northern Samar | 313617 | San Vicente NHS | CATUBIG | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2970120.51 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Northern Samar | 313617 | San Vicente NHS | CATUBIG | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2970120.51 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Northern Samar | 313602 | Anito NHS | GAMAY | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2696020.84 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Northern Samar | 303553 | Bangon NHS | GAMAY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2875120.51 |  |  | REVERTED | 0 | [10 empty] | (1) Project was not implemented by this office due to the fund was reverted as of December 31, 2017. Failure of bidding for projects funded under BEFF CY 2017 with SARO No. 2017-10-013360 dated October 18, 2017 (Batch 7) received by this office on November 16, 2017 due to no interested bidders. (2) Request for Deletion/Unpublish of Project Component was approved by the Planning Service as of November 2019. (3) Site Validation will be undertaken with representative from DepEd.
NC 2017 | TVL | Region VIII | Northern Samar | 303553 | Bangon NHS | GAMAY | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2875120.51 |  |  | REVERTED | 0 | [10 empty] | (1) Project was not implemented by this office due to the fund was reverted as of December 31, 2017. Failure of bidding for projects funded under BEFF CY 2017 with SARO No. 2017-10-013360 dated October 18, 2017 (Batch 7) received by this office on November 16, 2017 due to no interested bidders. (2) Request for Deletion/Unpublish of Project Component was approved by the Planning Service as of November 2019. (3) Site Validation will be undertaken with representative from DepEd.
NC 2017 | K10 | Region VIII | Northern Samar | 122933 | Malidong ES | GAMAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3045014 |  |  | REVERTED | 0 | [10 empty] | (1) Project was not implemented by this office due to the fund was reverted as of December 31, 2017. Failure of bidding for projects funded under BEFF CY 2017 with SARO No. 2017-10-013360 dated October 18, 2017 (Batch 7) received by this office on November 16, 2017 due to no interested bidders. (2) Request for Deletion/Unpublish of Project Component was approved by the Planning Service as of November 2019. (3) Site Validation will be undertaken with representative from DepEd.
NC 2017 | TVL | Region VIII | Northern Samar | 303533 | Batag NHS | LAOANG | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3065807.81 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 122964 | Napotiocan ES | LAOANG | 2 | 1 | 4 | 1STY4CL | BATCH 7 | 5621603.82 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Northern Samar | 313603 | Rawis NHS | LAOANG | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2812158.3 |  |  | REVERTED | 0 | [10 empty] | (1) Project was not implemented by this office due to the fund was reverted as of December 31, 2017. Failure of bidding for projects funded under BEFF CY 2017 with SARO No. 2017-10-013360 dated October 18, 2017 (Batch 7) received by this office on November 16, 2017 due to no interested bidders. (2) Request for Deletion/Unpublish of Project Component was approved by the Planning Service as of November 2019. (3) Site Validation will be undertaken with representative from DepEd.
NC 2017 | TVL | Region VIII | Northern Samar | 303559 | Lorenzo S. Menzon AIS | LAPINIG | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2952952.11 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Northern Samar | 313619 | Dapdap NHS | LAS NAVAS | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3105807.81 |  |  | REVERTED | 0 | [10 empty] | (1) Project was not implemented by this office due to the fund was reverted as of December 31, 2017. Failure of bidding for projects funded under BEFF CY 2017 with SARO No. 2017-10-013360 dated October 18, 2017 (Batch 7) received by this office on November 16, 2017 due to no interested bidders. (2) Request for Deletion/Unpublish of Project Component was approved by the Planning Service as of November 2019. (3) Site Validation will be undertaken with representative from DepEd.
NC 2017 | TVL | Region VIII | Northern Samar | 313619 | Dapdap NHS | LAS NAVAS | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3105807.81 |  |  | REVERTED | 0 | [10 empty] | (1) Project was not implemented by this office due to the fund was reverted as of December 31, 2017. Failure of bidding for projects funded under BEFF CY 2017 with SARO No. 2017-10-013360 dated October 18, 2017 (Batch 7) received by this office on November 16, 2017 due to no interested bidders. (2) Request for Deletion/Unpublish of Project Component was approved by the Planning Service as of November 2019. (3) Site Validation will be undertaken with representative from DepEd.
NC 2017 | TVL | Region VIII | Northern Samar | 303560 | Las Navas NHS | LAS NAVAS | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2812158.3 |  |  | REVERTED | 0 | [10 empty] | (1) Project was not implemented by this office due to the fund was reverted as of December 31, 2017. Failure of bidding for projects funded under BEFF CY 2017 with SARO No. 2017-10-013360 dated October 18, 2017 (Batch 7) received by this office on November 16, 2017 due to no interested bidders. (2) Request for Deletion/Unpublish of Project Component was approved by the Planning Service as of November 2019. (3) Site Validation will be undertaken with representative from DepEd.
NC 2017 | TVL | Region VIII | Northern Samar | 303581 | San Roque-Pambujan Vocational High School | PAMBUJAN | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2653745.92 |  |  | REVERTED | 0 | [10 empty] | (1) Project was not implemented by this office due to the fund was reverted as of December 31, 2017. Failure of bidding for projects funded under BEFF CY 2017 with SARO No. 2017-10-013360 dated October 18, 2017 (Batch 7) received by this office on November 16, 2017 due to no interested bidders. (2) Request for Deletion/Unpublish of Project Component was approved by the Planning Service as of November 2019. (3) Site Validation will be undertaken with representative from DepEd.
NC 2017 | K10 | Region VIII | Northern Samar | 123244 | Pagsang-an ES | SAN ROQUE | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2901257.97 |  |  | REVERTED | 0
NC 2017 | TVL | Region VIII | Northern Samar | 303583 | Silvino Lubos Vocational High School | SILVINO LOBOS | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3135120.51 |  |  | REVERTED | 0
NC 2017 | TVL | Region VIII | Northern Samar | 303583 | Silvino Lubos Vocational High School | SILVINO LOBOS | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3125120.51 |  |  | REVERTED | 0
NC 2017 | SHS | Region VIII | Ormoc City | 313903 | Cabintan National High School | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | BATCH 7 | 2813745.92 |  |  | Completed | 1 |  |  | P00173826VS-CW1 | 171F0160 | 2017-03-11 | 2017-10-11 | 2017-11-24 | 2017-12-20 | 2017-11-22 | RJIR ENT.
NC 2017 | TVL | Region VIII | Ormoc City | 303654 | Dolores National High School | ORMOC CITY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2763745.92 |  |  | Completed | 1 |  |  | P00173827VS-CW1 | 171F0154 | 2017-03-11 | 2017-10-11 | 2017-11-24 | 2017-06-12 | 2017-11-22 | J.A. ACHACOSO
NC 2017 | TVL | Region VIII | Ormoc City | 303661 | Genaro B. LureÃ±ana National High School | ORMOC CITY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2613745.92 |  |  | Completed | 1 |  |  | P00173828VS-CW1 | 171F0148 | 2017-02-11 | 2017-10-11 | 2017-11-23 | 2017-06-12 | 2017-11-22 | J.A. ACHACOSO
NC 2017 | TVL | Region VIII | Ormoc City | 303655 | Ipil National High School | ORMOC CITY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2813745.92 |  |  | Completed | 1 |  |  | P00173829VS-CW1 | 171F0147 | 2017-02-11 | 2017-10-11 | 2017-11-23 | 2017-06-12 | 2017-11-22 | GMP BUILDERS
NC 2017 | TVL | Region VIII | Ormoc City | 313906 | Julian C. Gantuangco NHS | ORMOC CITY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2613745.92 |  |  | Completed | 1 |  |  | P00173830VS-CW1 | 171F0152 | 2017-02-11 | 2017-10-11 | 2017-11-23 | 2017-06-12 | 2017-11-22 | RJIR ENT.
NC 2017 | TVL | Region VIII | Ormoc City | 313901 | Lilo-an National High School | ORMOC CITY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2713745.92 |  |  | Completed | 1 |  |  | P00173831VS-CW1 | 171F0146 | 2017-02-11 | 2017-10-11 | 2017-11-23 | 2017-06-12 | 2017-11-22 | RJIR ENT.
NC 2017 | TVL | Region VIII | Ormoc City | 303657 | Margen National High School | ORMOC CITY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2613745.92 |  |  | Completed | 1 |  |  | P00173832VS-CW1 | 171F0153 | 2017-02-11 | 2017-10-11 | 2017-11-23 | 2017-06-12 | 2017-11-22 | RJIR ENT.
NC 2017 | TVL | Region VIII | Ormoc City | 313904 | Matica-a National High School | ORMOC CITY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2613745.92 |  |  | Completed | 1 |  |  | P00173833VS-CW1 | 171F0150 | 2017-02-11 | 2017-10-11 | 2017-11-23 | 2017-06-12 | 2017-11-22 | RJIR ENT.
NC 2017 | TVL | Region VIII | Ormoc City | 330523 | Ormoc City Senior High School | ORMOC CITY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2613745.92 |  |  | Completed | 1 |  |  | P00173836VS-CW1 | 171F0151 | 2017-02-11 | 2017-10-11 | 2017-11-23 | 2017-06-12 | 2017-11-22 | COLLERA CONST.
NC 2017 | SHS | Region VIII | Ormoc City | 344795 | Ormoc City Sports Senior High School | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | BATCH 7 | 2763745.92 |  |  | Completed | 1 |  |  | P00173837VS-CW1 | 171F0159 | 2017-03-11 | 2017-10-11 | 2017-11-24 | 2017-12-20 | 2017-11-28 | COLLERA CONST.
NC 2017 | SHS | Region VIII | Ormoc City | 313902 | Pedro G. Bañez National High School | ORMOC CITY | 4 | 1 | 4 | 1STY4CL | BATCH 7 | 5388351.15 |  |  | Completed | 1 |  |  | P00173824VS-CW1 | 171F0141 | 2017-10-24 | 2017-02-11 | 2017-11-15 | 2017-06-12 | 2017-12-13 | RJIR ENT.
NC 2017 | TVL | Region VIII | Ormoc City | 313902 | Pedro G. Bañez National High School | ORMOC CITY | 4 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2813745.92 |  |  | Completed | 1 |  |  | P00173825VS-CW1 | 171F0149 | 2017-11-21 | 2017-10-11 | 2017-11-23 | 2017-06-12 | 2017-12-22 | J.A. ACHACOSO
NC 2017 | TVL | Region VIII | Ormoc City | 303660 | Rustico Capahi Sr. Memorial National High School | ORMOC CITY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2613745.92 |  |  | Completed | 1 |  |  | P00173834VS-CW1 | 171F0155 | 2017-03-11 | 2017-10-11 | 2017-11-24 | 2017-06-12 | 2017-12-22 | RJIR ENT.
NC 2017 | TVL | Region VIII | Ormoc City | 303662 | Valencia National High School | ORMOC CITY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2813745.92 |  |  | Completed | 1 |  |  | P00173835VS-CW1 | 171F0145 | 2017-02-11 | 2017-10-11 | 2017-11-23 | 2017-11-20 | 2017-12-12 | COLLERA CONST.
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 313719 | Bagacay NHS | DARAM | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4145000.27 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 303606 | Hinabangan NHS | HINABANGAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4145000.17 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 303640 | Quintin Quijano Sr. Agricultural School | PINABACDAO | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3768000.43 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Samar (Western Samar) | 313708 | San Jorge NHS | SAN JORGE | 1 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 7 | 5088351.15 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 303627 | San Sebastian NHS | SAN SEBASTIAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3768000.43 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Samar (Western Samar) | 303632 | Sto. Nino NHS | SANTO NIÑO | 1 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 7 | 5088351.15 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 303608 | Independencia NHS | TALALORA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2875000.11 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 192011 | Lewing Multi Grade ES | ANAHAWAN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2833639.4 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 121998 | Bunga ES | BONTOC | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2832501.95 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122022 | Union ES | BONTOC | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2848295.78 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122033 | Ingan ES | HINUNANGAN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2857501.95 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122042 | Otama ES | HINUNANGAN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2832501.95 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 192006 | Baculod MG ES | HINUNDAYAN | 0 | 1 | 3 | 1STY3CL | BATCH 7 | 4144541.12 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122078 | Gakat ES | LIBAGON | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2872845.59 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122205 | Caraatan ES | MALITBOG | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3197509.93 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122297 | Malinao ES | SAINT BERNARD | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2845570.68 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122305 | Tabontabon ES | SAINT BERNARD | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2870570.68 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122117 | Tuno ES | SAN FRANCISCO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2871708.13 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122059 | Silago Central School | SILAGO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2859776.86 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 192024 | Tuba-on ES | SILAGO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2871708.13 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Tacloban City | 314003 | Antonio Balmes NHS | TACLOBAN CITY (Capital) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3007594.94 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Tacloban City | 314003 | Antonio Balmes NHS | TACLOBAN CITY (Capital) | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 7 | 2683544.3 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Tacloban City | 303663 | Leyte NHS | TACLOBAN CITY (Capital) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2936708.86 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Tacloban City | 314004 | Northern Tacloban City NHS | TACLOBAN CITY (Capital) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 9215189.87 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Tacloban City | 303669 | Tacloban National Agricultural School | TACLOBAN CITY (Capital) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 11746835.44 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Tacloban City | 344882 | V&G NHS | TACLOBAN CITY (Capital) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3321518.99 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303345 | Balugo National High School | ALBUERA | 4 | 1 | 4 | 2STY4CL | BATCH 8 | 9145901.76 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303368 | Dr. Geronimo B. Zaldivar Memorial School of Fisheries | ALBUERA | 4 | 1 | 8 | 2STY8CL | BATCH 8 | 17174790.26 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303422 | San Francisco National High School | ISABEL | 4 | 1 | 4 | 2STY4CL | BATCH 8 | 9145901.76 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303396 | Lomonon National High School | PALOMPON | 4 | 1 | 4 | 2STY4CL | BATCH 8 | 9145901.76 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303435 | Taberna National High School | PALOMPON | 4 | 1 | 6 | 2STY6CL | BATCH 8 | 11856168.02 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Ormoc City | 313903 | Cabintan National High School | ORMOC CITY | 4 | 1 | 4 | 2STY4CL | BATCH 8 | 9295901.76 |  |  | Completed | 1 |  |  | P00173840VS-CW1 | 171F0140 | 2017-10-24 | 2017-02-11 | 2017-11-15 | 2017-11-20 | 2017-12-15 | J.A. ACHACOSO
NC 2017 | SHS | Region VIII | Ormoc City | 313906 | Julian C. Gantuangco NHS | ORMOC CITY | 4 | 1 | 4 | 2STY4CL | BATCH 8 | 9745901.76 |  |  | Completed | 1 |  |  | P00173842VS-CW1 | 171F0142 | 2017-10-24 | 2017-02-11 | 2017-11-15 | 2017-11-20 | 2017-12-15 | ARCA BUILDERS
NC 2017 | SHS | Region VIII | Ormoc City | 313904 | Matica-a National High School | ORMOC CITY | 4 | 1 | 6 | 2STY6CL | BATCH 8 | 11856168.02 |  |  | Completed | 1 |  |  | P00173841VS-CW1 | 171F0143 | 2017-10-24 | 2017-02-11 | 2017-11-15 | 2017-11-20 | 2017-12-15 | J.A. ACHACOSO
NC 2017 | TVL | Region VIII | Samar (Western Samar) | 303619 | Buenavista Senior High School | SAN JORGE | 1 | 1 | 4 | 2-UNITS WORKSHOP BLDG (7x18) | BATCH 8 | 9976702.3 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Samar (Western Samar) | 313708 | San Jorge NHS | SAN JORGE | 1 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 8 | 5088351.15 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Samar (Western Samar) | 303632 | Sto. Nino NHS | SANTO NIÑO | 1 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 8 | 5088351.15 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Samar (Western Samar) | 303633 | Tagapul-an NHS | TAGAPUL-AN | 1 | 1 | 8 | WORKSHOP BLDG (7x18) | BATCH 8 | 10694983.68 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Biliran | 120759 | Barubuhan ES | ALMERIA | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3073644.55 |  |  | REVERTED | 0
NC 2017 | K10 | Region VIII | Biliran | 120762 | Jamorawon ES | ALMERIA | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3063694.55 |  |  | Completed | 1 |  |  | P00180089VS-CW1 | 17IA0147 | 2017-12-07 | 2017-12-16 | 2017-12-27 | 2018-01-12 | 2018-01-26 | BNL CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120768 | Salangi ES | ALMERIA | 0 | 1 | 3 | 1STY3CL | BATCH 10 | 4455258.765 |  |  | Completed | 1 |  |  | P00180090VS-CW1 | 17IA0149 | 2017-12-07 | 2017-12-16 | 2017-12-27 | 2018-01-12 | 2018-01-26 | QYT CONSTRUCTION & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120773 | Bato ES | BILIRAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3088638.205 |  |  | Completed | 1 |  |  | P00180091VSCW1 | 17IA0151 | 2017-12-07 | 2017-12-16 | 2017-12-27 | 2018-01-12 | 2018-01-26 | MKB BUILDERS & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120775 | Burabod ES | BILIRAN | 0 | 1 | 3 | 1STY3CL | BATCH 10 | 4476992.55 |  |  | Completed | 1 |  |  | P00180092VS-CW1 | 17IA0153 | 2017-12-07 | 2017-12-16 | 2017-12-27 | 2018-01-12 | 2018-01-26 | QYT CONSTRUCTION & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120777 | Canila ES | BILIRAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3088638.205 |  |  | Completed | 1 |  |  | P00180093VS-CW1 | 17IA0152 | 2017-12-07 | 2017-12-16 | 2017-12-27 | 2018-01-12 | 2018-01-26 | MKB BUILDERS & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120778 | Core Shelter ES | BILIRAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3088638.205 |  |  | Completed | 1 |  |  | P00180094VS-CW1 | 17IA0155 | 2017-12-07 | 2017-12-16 | 2017-12-27 | 2018-01-12 | 2018-01-26 | BNL CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120779 | FELIMON NIERRAS MEMORIAL ELEMENTARY SCHOOL | BILIRAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3088638.205 |  |  | Completed | 1 |  |  | P00180095VS-CW1 | 17IA0154 | 2017-12-07 | 2017-12-16 | 2017-12-27 | 2018-01-12 | 2018-01-26 | BNL CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120782 | Pinangomhan ES | BILIRAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3088638.205 |  |  | REVERTED | 0 |  |  | P00180096VSCW1 | 17IA0150 | 2017-12-07 | 2017-12-16 | 2017-12-27 | 2018-01-12 | 2018-01-26 | QYT CONSTRUCTION & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120784 | Villa Enage Elemenetary School | BILIRAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2883668.205 |  |  | Completed | 1 |  |  | P00180097VS-CW1 | 17IA0156 | 2017-12-07 | 2017-12-16 | 2017-12-27 | 2018-01-12 | 2018-01-26 | MKB BUILDERS & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120785 | Balaquid ES | CABUCGAYAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3103631.86 |  |  | Completed | 1 |  |  | P00180098VS-CW1 | 17IA0158 | 2017-12-07 | 2017-12-16 | 2017-12-27 | 2018-01-12 | 2018-01-26 | MKB BUILDERS & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120785 | Balaquid ES | CABUCGAYAN | 0 |  | 2 | 1STY2CL | BATCH 10 | 2691701.86 |  |  | Completed | 1 |  |  | P00180099VS-CW1 | 17IA0157 | 2017-12-07 | 2017-12-16 | 2017-12-27 | 2018-01-12 | 2018-01-26 | QYT CONSTRUCTION & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120788 | Cabucgayan CS | CABUCGAYAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3089701.86 |  |  | Completed | 1 |  |  | P00180100VS-CW1 | 17IA0159 | 2017-12-07 | 2017-12-16 | 2017-12-27 | 2018-01-12 | 2018-01-26 | BNL CONSTRUCTION
NC 2017 | SHS | Region VIII | Biliran | 303322 | Cabucgayan NSAT | CABUCGAYAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3089701.86 |  |  | Completed | 1 |  |  | P00180140VS-CW1 | 17IA0166 | 2017-12-08 | 2017-12-15 | 2017-12-28 | 2018-01-16 | 2018-01-30 | QYT CONSTRUCTION & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120789 | Capayas ES | CABUCGAYAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3103631.86 |  |  | Completed | 1 |  |  | P00180101VS-CW1 | 17IA0167 | 2017-12-08 | 2017-12-15 | 2017-12-28 | 2018-01-16 | 2018-01-30 | QYT CONSTRUCTION & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120796 | Talibong ES | CABUCGAYAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2691701.86 |  |  | Completed | 1 |  |  | P00180102VS-CW1 | 17IA0168 | 2017-12-08 | 2017-12-15 | 2017-12-28 | 2018-01-16 | 2018-01-30 | QYT CONSTRUCTION & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120796 | Talibong ES | CABUCGAYAN | 0 |  | 3 | 1STY3CL | BATCH 10 | 4521332 |  |  | Completed | 1 |  |  | P00180103VS-CW1 | 17IA0168 | 2017-12-08 | 2017-12-15 | 2017-12-28 | 2018-01-16 | 2018-01-30 | MKB BUILDERS & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120801 | Cabibihan ES | CAIBIRAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3102704.52 |  |  | Completed | 1 |  |  | P00180104VS-CW1 | 17IA0171 | 2017-12-08 | 2017-12-15 | 2017-12-28 | 2018-01-16 | 2018-01-30 | MKB BUILDERS & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120804 | Katipunan ES | CAIBIRAN | 0 | 1 | 3 | 1STY3CL | BATCH 10 | 4106538.13 |  |  | Completed | 1 |  |  | P00180105VS-CW1 | 17IA0172 | 2017-12-08 | 2017-12-15 | 2017-12-28 | 2018-01-16 | 2018-01-30 | MKB BUILDERS & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120806 | Kawayanon ES | CAIBIRAN | 0 | 1 | 4 | 1STY4CL | BATCH 10 | 5058467.565 |  |  | Completed | 1 |  |  | P00180106VS-CW1 | 17IA0165 | 2017-12-08 | 2017-12-15 | 2017-12-28 | 2018-01-16 | 2018-01-30 | QYT CONSTRUCTION & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120807 | Looc ES | CAIBIRAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3118624.52 |  |  | Completed | 1 |  |  | P00180107VS-CW1 | 17IA0170 | 2017-12-08 | 2017-12-15 | 2017-12-28 | 2018-01-16 | 2018-01-30 | QUIRANTE MV BUILDERS
NC 2017 | K10 | Region VIII | Biliran | 120810 | Maurang ES | CAIBIRAN | 0 | 1 | 3 | 1STY3CL | BATCH 10 | 3899578.13 |  |  | Completed | 1 |  |  | P00180110VS-CW1 | 17IA0163 | 2017-12-08 | 2017-12-15 | 2017-12-28 | 2018-01-16 | 2018-01-30 | BNL CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120810 | Maurang ES | CAIBIRAN | 0 |  | 5 | 1STY5CL | BATCH 10 | 7355558 |  |  | Completed | 1 |  |  | P00180109VS-CW1 | 17IA0164 | 2017-12-08 | 2017-12-15 | 2017-12-28 | 2018-01-16 | 2018-01-30 | W.B. ALAGAO CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120810 | Maurang ES | CAIBIRAN | 0 |  | 3 | 1STY3CL | BATCH 10 | 4543174 |  |  | Completed | 1 |  |  | P00180108VS-CW1 | 17IA0162 | 2017-12-08 | 2017-12-15 | 2017-12-28 | 2018-01-16 | 2018-01-30 | BNL CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120812 | Tomalistis ES | CAIBIRAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3118624.52 |  |  | Completed | 1 |  |  | P00180111VS-CW1 | 17IA0161 | 2017-12-08 | 2017-12-15 | 2017-12-28 | 2018-01-16 | 2018-01-30 | BNL CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120813 | Union ES | CAIBIRAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2704704.52 |  |  | Completed | 1 |  |  | P00180112VS-CW1 | 17IA0160 | 2017-12-08 | 2017-12-15 | 2017-12-28 | 2018-01-16 | 2018-01-30 | QYT CONSTRUCTION & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120815 | Acaban ES | CULABA | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3118624.52 |  |  | Completed | 1 |  |  | P00180113VS-CW1 | 17IA0124 | 2017-11-29 | 2017-12-08 | 2017-12-20 | 2018-01-10 | 2018-01-17 | LIMAR CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120815 | Acaban ES | CULABA | 0 |  | 3 | 1STY3CL | BATCH 10 | 4543174 |  |  | Completed | 1 |  |  | P00180114VS-CW1 | 17IA0102 | 2017-11-16 | 2017-11-24 | 2017-12-07 | 2017-12-18 | 2018-01-19 | LIMAR CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120822 | Looc ES | CULABA | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3118624.52 |  |  | Completed | 1 |  |  | P00180115VS-CW1 | 17IA0130 | 2017-11-29 | 2017-12-08 | 2017-12-20 | 2018-01-10 | 2018-01-17 | MKB BUILDERS & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120824 | Pinamihagan ES | CULABA | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3118624.52 |  |  | Completed | 1 |  |  | P00180116VS-CW1 | 17IA0131 | 2017-11-29 | 2017-12-08 | 2017-12-20 | 2018-01-10 | 2018-01-17 | THE TUSCAN STRUCTURES & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120824 | Pinamihagan ES | CULABA | 0 |  | 2 | 1STY2CL | BATCH 10 | 3118624.52 |  |  | Completed | 1 |  |  | P00180117VS-CW1 | 17IA0132 | 2017-11-29 | 2017-12-08 | 2017-12-20 | 2018-01-10 | 2018-01-17 | THE TUSCAN STRUCTURES & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120824 | Pinamihagan ES | CULABA | 0 |  | 5 | 1STY5CL | BATCH 10 | 7355558 |  |  | Completed | 1 |  |  | P00180118VS-CW1 | 17IA0143 | 2017-12-01 | 2017-12-15 | 2017-12-26 | 2018-01-11 | 2018-01-23 | THE TUSCAN STRUCTURES & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120833 | Kansanoc ES | KAWAYAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3118624.52 |  |  | Completed | 1 |  |  | P00180119VS-CW1 | 17IA0128 | 2017-11-29 | 2017-12-08 | 2017-12-20 | 2018-01-10 | 2018-01-17 | W.B. ALAGAO CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120846 | Agutay ES | MARIPIPI | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3118624.52 |  |  | REVERTED | 0
NC 2017 | K10 | Region VIII | Biliran | 120846 | Agutay ES | MARIPIPI | 0 |  | 2 | 1STY2CL | BATCH 10 | 3118624.52 |  |  | REVERTED | 0
NC 2017 | K10 | Region VIII | Biliran | 120846 | Agutay ES | MARIPIPI | 0 | 1 | 5 | 1STY5CL | BATCH 10 | 7426284 |  |  | REVERTED | 0
NC 2017 | K10 | Region VIII | Biliran | 120848 | Binalayan ES | MARIPIPI | 0 | 1 | 3 | 1STY3CL | BATCH 10 | 4563923.71 |  |  | REVERTED | 0
NC 2017 | K10 | Region VIII | Biliran | 120850 | Canduhao ES | MARIPIPI | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3118624.52 |  |  | REVERTED | 0
NC 2017 | K10 | Region VIII | Biliran | 120850 | Canduhao ES | MARIPIPI | 0 |  | 2 | 1STY2CL | BATCH 10 | 3118624.52 |  |  | REVERTED | 0
NC 2017 | K10 | Region VIII | Biliran | 120852 | Danao ES | MARIPIPI | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3148611.83 |  |  | REVERTED | 0
NC 2017 | K10 | Region VIII | Biliran | 120868 | Calumpang ES | NAVAL (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3058650.895 |  |  | Completed | 1 |  |  | P00180134VS-CW1 | 17IA0125 | 2017-11-29 | 2017-12-08 | 2017-12-20 | 2018-01-10 | 2018-01-17 | BNL CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120868 | Calumpang ES | NAVAL (Capital) | 0 |  | 2 | 1STY2CL | BATCH 10 | 3058650.895 |  |  | Completed | 1 |  |  | P00180135VS-CW1 | 17IA0126 | 2017-11-29 | 2017-12-08 | 2017-12-20 | 2018-01-10 | 2018-01-17 | BNL CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120868 | Calumpang ES | NAVAL (Capital) | 0 |  | 3 | 1STY3CL | BATCH 10 | 4455805 |  |  | Completed | 1 |  |  | P00180136VS-CW1 | 17IA0101 | 2017-11-16 | 2017-11-24 | 2017-12-07 | 2017-12-18 | 2018-01-09 | BNL CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120868 | Calumpang ES | NAVAL (Capital) | 0 |  | 5 | 1STY5CL | BATCH 10 | 7214105 |  |  | Completed | 1 |  |  | P00180137VS-CW1 | 17IA0146 | 2017-12-01 | 2017-12-15 | 2017-12-26 | 2018-01-11 | 2018-01-23 | QYT CONSTRUCTION & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120873 | Haguikhican ES | NAVAL (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3058650.895 |  |  | Completed | 1 |  |  | P00180138VS-CW1 | 17IA0127 | 2017-11-29 | 2017-12-08 | 2017-12-20 | 2018-01-10 | 2018-01-17 | MKB BUILDERS & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120874 | Imelda ES | NAVAL (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3058650.895 |  |  | Completed | 1 |  |  | P00180139VS-CW1 | 17IA0122 | 2017-11-28 | 2017-12-06 | 2017-12-18 | 2018-01-05 | 2018-01-16 | MKB BUILDERS & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120859 | Larrazabal ES | NAVAL (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3058650.895 |  |  | Completed | 1 |  |  | P00180127VS-CW1 | 17IA0129 | 2017-11-29 | 2017-12-08 | 2017-12-20 | 2018-01-10 | 2018-01-17 | BNL CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120859 | Larrazabal ES | NAVAL (Capital) | 0 |  | 3 | 1STY3CL | BATCH 10 | 4455805 |  |  | Completed | 1 |  |  | P00180128VS-CW1 | 17IA0100 | 2017-11-16 | 2017-11-24 | 2017-12-07 | 2017-12-28 | 2018-01-09 | BNL CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120860 | Naval CS | NAVAL (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2998677.27 |  |  | Completed | 1 |  |  | P00180129VS-CW1 | 17IA0142 | 2017-12-01 | 2017-12-15 | 2017-12-26 | 2018-01-11 | 2018-01-23 | MKB BUILDERS & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120860 | Naval CS | NAVAL (Capital) | 0 |  | 3 | 1STY3CL | BATCH 10 | 4443804 |  |  | Completed | 1 |  |  | P00180130VS-CW1 | 17IA0099 | 2017-11-16 | 2017-11-24 | 2017-12-07 | 2017-12-28 | 2018-01-09 | BNL CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120861 | Naval CS Sped Center | NAVAL (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3050690.895 |  |  | Completed | 1 |  |  | P00180131VS-CW1 | 17IA0120 | 2017-11-28 | 2017-12-06 | 2017-12-18 | 2018-01-05 | 2018-01-16 | BNL CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120861 | Naval CS Sped Center | NAVAL (Capital) | 0 |  | 2 | 1STY2CL | BATCH 10 | 3050690.895 |  |  | Completed | 1 |  |  | P00180132VS-CW1 | 17IA0121 | 2017-11-28 | 2017-12-06 | 2017-12-18 | 2018-01-05 | 2018-01-16 | BNL CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120864 | Talustusan ES | NAVAL (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2652690.895 |  |  | Completed | 1 |  |  | P00180133VS-CW1 | 17IA0133 | 2017-11-29 | 2017-12-08 | 2017-12-20 | 2018-01-10 | 2018-01-17 | QYT CONSTRUCTION & SUPPLIES
NC 2017 | K10 | Region VIII | Calbayog City | 124029 | Acedillo Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2772357.4157 |  |  | Completed | 1 |  |  |  | 17IJ-0172 | 2017-12-28 | 2017-12-30 |  |  |  | JFR
NC 2017 | K10 | Region VIII | Calbayog City | 124117 | Amampacang Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2922650.0264 |  |  | Completed | 1 |  |  |  | 17IJ-0149 | 2017-12-28 | 2017-12-30 |  |  |  | JFR
NC 2017 | K10 | Region VIII | Calbayog City | 124030 | Anislag Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2772357.4157 |  |  | Completed | 1 |  |  |  | 17IJ-0173 | 2017-12-28 | 2017-12-30 |  |  |  | JFR
NC 2017 | K10 | Region VIII | Calbayog City | 123985 | Bagacay Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2822107.4157 |  |  | Completed | 1 |  |  |  | 17IJ-0171 | 2017-12-28 | 2017-12-30 |  |  |  | DRS
NC 2017 | K10 | Region VIII | Calbayog City | 124055 | Begaho Elementary School | CALBAYOG CITY | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 4332434.8009 |  |  | Completed | 1 |  |  |  | 17IJ-0157 | 2017-12-28 | 2017-12-30 |  |  |  | DRS
NC 2017 | K10 | Region VIII | Calbayog City | 124005 | Cacaransan Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3002293.5975 |  |  | Completed | 1 |  |  |  | 17IJ-0174 | 2017-12-28 | 2017-12-30 |  |  |  | DRS
NC 2017 | K10 | Region VIII | Calbayog City | 124057 | Cagbilwang Primary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3075603.4463 |  |  | Completed | 1 |  |  |  | 17IJ-0175 | 2017-12-28 | 2017-12-30 |  |  |  | ND
NC 2017 | K10 | Region VIII | Calbayog City | 124131 | Cagmanipis Norte Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3045908.119 |  |  | Completed | 1 |  |  |  | 17IJ0148 | 2017-12-28 | 2017-12-30 |  |  |  | JFR
NC 2017 | K10 | Region VIII | Calbayog City | 124132 | Cagmanipis Sur Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2897526.2764 |  |  | Completed | 1 |  |  |  | 17IJ-0147 | 2017-12-28 | 2017-12-30 |  |  |  | ND
NC 2017 | K10 | Region VIII | Calbayog City | 124133 | Cagnipa Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2921607.4157 |  |  | Completed | 1 |  |  |  | 17IJ-0151 | 2017-12-28 | 2017-12-30 |  |  |  | JFR
NC 2017 | K10 | Region VIII | Calbayog City | 124034 | Cagsalaosao Elementary School | CALBAYOG CITY | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 4314728.4674 |  |  | Completed | 1 |  |  |  | 17IJ-0158 | 2017-12-28 | 2017-12-30 |  |  |  | JFR
NC 2017 | K10 | Region VIII | Calbayog City | 313806 | Calbayog City National High School - Carayman Campus | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2772357.4157 |  |  | Completed | 1 |  |  |  | 17IJ-0152 | 2017-12-28 | 2017-12-30 |  |  |  | JFR
NC 2017 | K10 | Region VIII | Calbayog City | 123989 | Calbayog Pilot Central Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2672857.4157 |  |  | Completed | 1 |  |  |  | 17IJ-0178 | 2017-12-28 | 2017-12-30 |  |  |  | RV
NC 2017 | K10 | Region VIII | Calbayog City | 124007 | Capoocan Elementary School | CALBAYOG CITY | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 4302491.3007 |  |  | Completed | 1 |  |  |  | 17IJ-0153 | 2017-12-28 | 2017-12-30 |  |  |  | JFR
NC 2017 | K10 | Region VIII | Calbayog City | 124008 | Carmen Elementary School | CALBAYOG CITY | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 4302491.3007 |  |  | Completed | 1 |  |  |  | 17IJ-0154 | 2017-12-28 | 2017-12-30 |  |  |  | RNMK
NC 2017 | K10 | Region VIII | Calbayog City | 124061 | Dinagan Elementary School | CALBAYOG CITY | 1 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 10 | 5595421.892 |  |  | Completed | 1 |  |  |  | 17IJ-0169 | 2017-12-28 | 2017-12-30 |  |  |  | DRS
NC 2017 | K10 | Region VIII | Calbayog City | 124037 | Gadgaran Integrated School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2772357.4157 |  |  | Completed | 1 |  |  |  | 17IJ-0179 | 2017-12-28 | 2017-12-30 |  |  |  | DRS
NC 2017 | K10 | Region VIII | Calbayog City | 124040 | Lonoy Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3010451.702 |  |  | Completed | 1 |  |  |  | 17IJ-0180 | 2017-12-28 | 2017-12-30 |  |  |  | RNMK
NC 2017 | K10 | Region VIII | Calbayog City | 124066 | Macatingog Integrated School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2871857.4157 |  |  | Completed | 1 |  |  |  | 17IJ-0150 | 2017-12-28 | 2017-12-30 |  |  |  | ND
NC 2017 | K10 | Region VIII | Calbayog City | 124124 | Malajog Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3061752.5587 |  |  | Completed | 1 |  |  |  | 17IJ-0146 | 2017-12-28 | 2017-12-30 |  |  |  | RNMK
NC 2017 | K10 | Region VIII | Calbayog City | 124124 | Malajog Elementary School | CALBAYOG CITY | 1 |  | 3 | 1STY3CL W/ TOILET | BATCH 10 | 4333084.2174 |  |  | Completed | 1 |  |  |  | 17IJ-0159 | 2017-12-28 | 2017-12-30 |  |  |  | ND
NC 2017 | K10 | Region VIII | Calbayog City | 124125 | Malopalo Elementary School | CALBAYOG CITY | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 4303724.5236 |  |  | Completed | 1 |  |  |  | 17IJ-0156 | 2017-12-28 | 2017-12-30 |  |  |  | RNMK
NC 2017 | K10 | Region VIII | Calbayog City | 123997 | Nijaga Elementary School | CALBAYOG CITY | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 4056863.1828 |  |  | Completed | 1 |  |  |  | 17IJ-0170 | 2017-12-28 | 2017-12-30 |  |  |  | VCD
NC 2017 | K10 | Region VIII | Calbayog City | 124070 | Oquendo Central Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2897526.2764 |  |  | Completed | 1 |  |  |  | 17IJ-0177 | 2017-12-28 | 2017-12-30 |  |  |  | JFR
NC 2017 | K10 | Region VIII | Calbayog City | 124139 | Peña I Elementary School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2871857.4157 |  |  | Completed | 1 |  |  |  | 17IJ-0224 | 2017-12-28 | 2017-12-30 |  |  |  | JFR
NC 2017 | K10 | Region VIII | Calbayog City | 124048 | San Policarpo Central Elem. School | CALBAYOG CITY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2772357.4157 |  |  | Completed | 1 |  |  |  | 17IJ-0176 | 2017-12-28 | 2017-12-30 |  |  |  | VCD
NC 2017 | K10 | Region VIII | Calbayog City | 124112 | Sinidman Or. Primary School | CALBAYOG CITY | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 4345321.3842 |  |  | Completed | 1 |  |  |  | 17IJ-0155 | 2017-12-28 | 2017-12-30 |  |  |  | JFR
NC 2017 | TVL | Region VIII | Baybay City | 313316 | Baybay City National Night High School | CITY OF BAYBAY | 5 | 1 | 1 | 1STY REGULAR WORKSHOP | BATCH 12 | 2813745.92 |  |  | Completed | 1 |  |  | P00181984VS-CW1 | 17IG0148 |  | 2017-12-12 | 2017-12-27 | 2017-12-29 | 2018-01-04 | JA ACHACOSO ENT. & GENERAL SERVICES
NC 2017 | TVL | Region VIII | Baybay City | 344593 | Baybay City Senior High School | CITY OF BAYBAY | 5 | 1 | 1 | 1STY UNIQUE WORKSHOP | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  | P00181985VS-CW1 | 17IG0148 |  | 2017-12-12 | 2017-12-27 | 2017-12-29 | 2018-01-04 | JA ACHACOSO ENT. & GENERAL SERVICES
NC 2017 | K10 | Region VIII | Baybay City | 303351 | Bunga NHS | CITY OF BAYBAY | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  | P00181979VS-CW1 | 17IG0129 |  | 2017-11-02 | 2017-11-15 | 2017-12-29 | 2018-01-04 | RJIR ENTERPRISES
NC 2017 | K10 | Region VIII | Baybay City | 121133 | Butigan PS | CITY OF BAYBAY | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2889745.92 |  |  | Completed | 1 |  |  | P00181977VS-CW1 | 17IG0129 |  | 2017-11-02 | 2017-11-15 | 2017-12-29 | 2018-01-04 | RJIR ENTERPRISES
NC 2017 | TVL | Region VIII | Baybay City | 303360 | Caridad NHS | CITY OF BAYBAY | 5 | 1 | 1 | 1STY REGULAR WORKSHOP | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  | P00181980VS-CW1 | 17IG0148 |  | 2017-12-12 | 2017-12-27 | 2017-12-29 | 2018-01-04 | JA ACHACOSO ENT. & GENERAL SERVICES
NC 2017 | K10 | Region VIII | Baybay City | 121103 | Hipusngo ES | CITY OF BAYBAY | 5 | 1 | 4 | 1STY4CL | BATCH 12 | 5348351.15 |  |  | Completed | 1 |  |  | P00181976VS-CW1 | 17IG0149 |  | 2017-12-12 | 2017-12-27 | 2017-12-29 | 2018-01-04 | JA ACHACOSO ENT. & GENERAL SERVICES
NC 2017 | K10 | Region VIII | Baybay City | 121143 | Maganhan ES | CITY OF BAYBAY | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2863745.92 |  |  | Completed | 1 |  |  | P00181978VS-CW1 | 17IG0149 |  | 2017-12-12 | 2017-12-27 | 2017-12-29 | 2018-01-04 | JA ACHACOSO ENT. & GENERAL SERVICES
NC 2017 | TVL | Region VIII | Baybay City | 313312 | Mailhi NHS | CITY OF BAYBAY | 5 | 1 | 1 | 1STY REGULAR WORKSHOP | BATCH 12 | 2863745.92 |  |  | Completed | 1 |  |  | P00181983VS-CW1 | 17IG0139 |  | 2017-12-12 | 2017-12-27 | 2017-12-29 | 2018-01-04 | RJIR ENTERPRISES
NC 2017 | TVL | Region VIII | Baybay City | 303419 | Plaridel NHS | CITY OF BAYBAY | 5 | 1 | 1 | 1STY REGULAR WORKSHOP | BATCH 12 | 2913745.92 |  |  | Completed | 1 |  |  | P00181981VS-CW1 | 17IG0139 |  | 2017-12-12 | 2017-12-27 | 2017-12-29 | 2018-01-04 | RJIR ENTERPRISES
NC 2017 | TVL | Region VIII | Baybay City | 303420 | Pomponan NHS | CITY OF BAYBAY | 5 | 1 | 1 | 1STY REGULAR WORKSHOP | BATCH 12 | 2863745.92 |  |  | Completed | 1 |  |  | P00181982VS-CW1 | 17IG0139 |  | 2017-12-12 | 2017-12-27 | 2017-12-29 | 2018-01-04 | RJIR ENTERPRISES
NC 2017 | K10 | Region VIII | Biliran | 120758 | Almeria CS | ALMERIA | 0 | 1 | 3 | 1STY3CL | BATCH 12 | 4462646 |  |  | Completed | 1 |  |  | P00181986VS-CW1 | 17IA0108 | 2017-11-20 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-03 | BNL CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120774 | Biliran CS | BILIRAN | 0 | 1 | 3 | 1STY3CL | BATCH 12 | 4481489 |  |  | Completed | 1 |  |  | P00181987VS-CW1 | 17IA0106 | 2017-11-20 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-03 | QYT CONSTRUCTION & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120802 | Caibiran CS | CAIBIRAN | 0 | 1 | 4 | 1STY4CL | BATCH 12 | 5883886 |  |  | Completed | 1 |  |  | P00181988VS-CW1 | 17IA0145 | 2017-12-01 | 2017-12-15 | 2017-12-26 | 2018-01-11 | 2018-01-23 | W. B. ALAGAO CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120821 | Habuhab ES | CULABA | 0 | 1 | 3 | 1STY3CL | BATCH 12 | 4543174 |  |  | Completed | 1 |  |  | P00181989VS-CW1 | 17IA0104 | 2017-11-16 | 2017-11-24 | 2017-12-07 | 2017-12-28 | 2018-01-09 | QYT CONSTRUCTION & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120841 | Tubig Guinoo ES | KAWAYAN | 0 | 1 | 3 | 1STY3CL | BATCH 12 | 4543174 |  |  | Completed | 1 |  |  | P00181990VS-CW1 | 17IA0107 | 2017-11-20 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-03 | W. B. ALAGAO CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120871 | Catmon ES | NAVAL (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 12 | 4443804 |  |  | Completed | 1 |  |  | P00181991VS-CW1 | 17IA0105 | 2017-11-20 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-03 | QYT CONSTRUCTION & SUPPLIES
NC 2017 | TVL | Region VIII | Leyte | 303344 | Balocawehay NHS | ABUYOG | 5 | 1 | 1 | 1STY1 UNIQUE WORKSHOP | BATCH 12 | 2813745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303344 | Balocawehay NHS | ABUYOG | 5 |  | 1 | 1STY1 REGULAR WORKSHOP | BATCH 12 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 120888 | Cadac-an PS | ABUYOG | 5 | 1 | 3 | 1STY3CL | BATCH 12 | 4018435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 120924 | Capili-an ES | ABUYOG | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2853745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 120891 | Gabaldon Central School | ABUYOG | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 313313 | Libertad NHS | ABUYOG | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2859745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 120932 | Nebga ES | ABUYOG | 5 | 1 | 3 | 1STY3CL | BATCH 12 | 3818435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 120934 | Odiongan ES | ABUYOG | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 120915 | Picas Sur ES | ABUYOG | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3003745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 120937 | Sta. Fe-Sto. Nino ES | ABUYOG | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2713745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303392 | Alangalang Agro-Industrial School (LSU - Alangalang Campus) | ALANGALANG | 1 | 1 | 2 | 2-UNITS 1STY UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 6544976.98 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303392 | Alangalang Agro-Industrial School (LSU - Alangalang Campus) | ALANGALANG | 1 |  | 2 | 2-UNITS 1STY COMPUTER LAB. | BATCH 12 | 5236230.24 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303392 | Alangalang Agro-Industrial Scool (LSU - Alangalang Campus) | ALANGALANG | 1 |  | 8 | 2STY8CL | BATCH 12 | 17146905.53 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303336 | Alangalang NHS | ALANGALANG | 1 | 1 | 2 | 2-UNITS 1STY SCIENCE LAB. | BATCH 12 | 5750241.02 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303336 | Alangalang NHS | ALANGALANG | 1 |  | 4 | 2STY4CL | BATCH 12 | 9713779.86 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303366 | Damulaan NHS | ALBUERA | 4 | 1 | 4 | 2STY4CL | BATCH 12 | 9245901.76 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121005 | Babatngon CS | BABATNGON | 1 | 1 | 8 | 2STY8CL | BATCH 12 | 17062470.28 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303343 | Juan S. Tismo NHS (Babatngon NHS) | BABATNGON | 1 | 1 | 2 | 2-UNITS 1STY UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 7187802.68 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303343 | Juan S. Tismo NHS (Babatngon NHS) | BABATNGON | 1 |  | 2 | 2-UNITS 1STY SCIENCE LAB. | BATCH 12 | 5750241.02 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303343 | Juan S. Tismo NHS (Babatngon NHS) | BABATNGON | 1 |  | 2 | 2-UNITS 1STY COMPUTER LAB. | BATCH 12 | 5750241.02 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303401 | Malibago NHS | BABATNGON | 1 | 1 | 1 | 1-UNIT 1STY COMPUTER LAB. | BATCH 12 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303413 | Pagsulhugon NHS | BABATNGON | 1 | 1 | 1 | 1-UNIT 1STY SCIENCE LAB. | BATCH 12 | 2875120.51 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303413 | Pagsulhugon NHS | BABATNGON | 1 |  | 4 | 2STY4CL | BATCH 12 | 9100997.86 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303421 | San Agustin NHS | BABATNGON | 1 | 1 | 1 | 1-UNIT 1STY SCIENCE LAB. | BATCH 12 | 2674966.75 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303421 | San Agustin NHS | BABATNGON | 1 |  | 6 | 2STY6CL | BATCH 12 | 11864598.18 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303357 | Calingcaguing NHS | BARUGO | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2845287 |  |  | Completed | 1 |  |  | P00182066VS-CW1 | 17ID0171 |  |  |  | 2018-01-03 | 2018-01-05 | E.G. CANABE CONSTRUCTION
NC 2017 | SHS | Region VIII | Leyte | 303433 | Sta. Rosa NHS | BARUGO | 2 | 1 | 3 | 1STY3CL | BATCH 12 | 4074592 |  |  | Completed | 1 |  |  | P00182098VS-CW1 | 17ID0170 |  |  |  | 2018-01-05 | 2018-01-11 | ROCKON BUILDERS AND CONSTRUCTION SUPPLY
NC 2017 | TVL | Region VIII | Leyte | 303338 | Anahawan NHS | BATO | 5 | 1 | 1 | 1STY1 UNIQUE WORKSHOP | BATCH 12 | 2813745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303338 | Anahawan NHS | BATO | 5 |  | 1 | 1STY1 REGULAR WORKSHOP | BATCH 12 | 2813745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121060 | BAGO ES | BATO | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3063745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121061 | Bato Central School | BATO | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2763745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303346 | Bato NHS | BATO | 5 | 1 | 1 | 1STY1 REGULAR WORKSHOP | BATCH 12 | 2793745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303347 | Bato School of Fisheries | BATO | 5 | 1 | 1 | 1STY1 UNIQUE WORKSHOP | BATCH 12 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121151 | Anonang ES | BURAUEN | 2 | 1 | 3 | 1STY3CL | BATCH 12 | 4240000 |  |  | Completed | 1 |  |  | P00182002VS-CW1 | 17ID0158 |  |  |  | 2018-01-03 | 2018-01-05 | LATORRE BUILDERS & CONSTRUCTION
NC 2017 | K10 | Region VIII | Leyte | 121181 | Arado ES | BURAUEN | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2845287 |  |  | Completed | 1 |  |  | P00182005VS-CW1 | 17ID0150 |  |  |  | 2018-01-04 | 2018-01-10 | RCC BUILDERS AND ENTERPRISES
NC 2017 | K10 | Region VIII | Leyte | 121157 | Cadahunan ES | BURAUEN | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2845287 |  |  | Completed | 1 |  |  | P00182003VS-CW1 | 17ID0151 |  |  |  | 2018-01-03 | 2018-01-08 | LTZ CONSTRUCTION AND SUPPLY
NC 2017 | K10 | Region VIII | Leyte | 121197 | Lusad ES | BURAUEN | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2845287 |  |  | Completed | 1 |  |  | P00182006VS-CW1 | 17ID0152 |  |  |  | 2018-01-05 | 2018-01-11 | RCC BUILDERS AND ENTERPRISES
NC 2017 | K10 | Region VIII | Leyte | 121163 | Maabab ES | BURAUEN | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2845287 |  |  | Completed | 1 |  |  | P00182004VS-CW1 | 17ID0153 |  |  |  | 2018-01-05 | 2018-01-11 | LTZ CONSTRUCTION AND SUPPLY
NC 2017 | K10 | Region VIII | Leyte | 121218 | Lawis ES | CALUBIAN | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2816708.13 |  |  | Completed | 1 |  |  | P0018200VS | 17IE0123 | [5 empty] | Lug Konstract
NC 2017 | K10 | Region VIII | Leyte | 121233 | Uson ES | CALUBIAN | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2816708.13 |  |  | Completed | 1 |  |  | P00182008VS | 17IE0124 | [5 empty] | RJIR Enterprises
NC 2017 | SHS | Region VIII | Leyte | 303372 | Guinarona NHS | DAGAMI | 2 | 1 | 4 | 1STY4CL | BATCH 12 | 5388647 |  |  | Completed | 1 |  |  | P00182069VS-CW1 | 17ID0174 |  |  |  | 2018-01-04 | 2018-01-10 | E.G. CANABE CONSTRUCTION
NC 2017 | K10 | Region VIII | Leyte | 344695 | Patoc NHS | DAGAMI | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  | P00182116VS-CW1 | 17ID0163 |  |  |  | 2017-12-27 | 2018-01-03 | KUBLAI CONSTRUCTION AND SUPPLIES
NC 2017 | SHS | Region VIII | Leyte | 313321 | Cabatoan NHS | DULAG | 2 | 1 | 4 | 1STY4CL | BATCH 12 | 5388647 |  |  | Completed | 1 |  |  | P00182108VS-CW1 | 17ID0172 |  |  |  | 2018-01-05 | 2018-01-11 | R.S. REYNA CONSTRUCTION
NC 2017 | K10 | Region VIII | Leyte | 121347 | Fatima ES | DULAG | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2845287 |  |  | Completed | 1 |  |  | P00182009VS-CW1 | 17ID0148 |  |  |  | 2017-12-27 | 2017-12-29 | R. AGULLO CONSTRUCTION & ENTERPRISES
NC 2017 | SHS | Region VIII | Leyte | 303425 | San Jose NHS | DULAG | 2 | 1 | 4 | 1STY4CL | BATCH 12 | 5388647 |  |  | Completed | 1 |  |  | P00182092VS-CW1 | 17ID0173 |  |  |  | 2018-01-05 | 2018-01-11 | VENUS ENGINEERING & CONSTRUCTION
NC 2017 | TVL | Region VIII | Leyte | 303374 | Hilongos National Vocational School | HILONGOS | 5 | 1 | 1 | 1STY1 UNIQUE WORKSHOP | BATCH 12 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303374 | Hilongos National Vocational School | HILONGOS | 5 |  | 1 | 1STY1 REGULAR WORKSHOP | BATCH 12 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121384 | Hilongos South Central School | HILONGOS | 5 | 1 | 4 | 1STY4CL | BATCH 12 | 5138351.15 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121365 | Owak ES | HILONGOS | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121366 | Paa ES | HILONGOS | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121370 | Sta. Cruz ES | HILONGOS | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3013745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303350 | Bontoc Senior High School | HINDANG | 5 | 1 | 3 | 1STY3CL | BATCH 12 | 4114435.02 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303350 | Bontoc Senior High School | HINDANG | 5 |  | 1 | 1STY1 REGULAR WORKSHOP | BATCH 12 | 2613745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 313329 | Capudlosan NHS | HINDANG | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2859745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121405 | Doos ES | HINDANG | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121408 | Hindang Central School | HINDANG | 5 | 1 | 3 | 1STY3CL | BATCH 12 | 4122435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121422 | Esperanza ES | INOPACAN | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2663745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303377 | Inopacan NHS | INOPACAN | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2918745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 313302 | Isabel NCHS | ISABEL | 4 | 1 | 2 | 1STY2CL | BATCH 12 | 2813745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 313302 | Isabel NCHS | ISABEL | 4 |  | 6 | 2STY6CL | BATCH 12 | 12684168.02 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303378 | Isabel NHS | ISABEL | 4 | 1 | 6 | 2STY6CL | BATCH 12 | 12234168.02 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte |  | Bienvenido Guillera Celebre NHS | JARO | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2845287 |  |  | Completed | 1 |  |  | P00182117VS-CW1 | 17ID0157 |  |  |  | 2018-01-04 | 2018-01-10 | JELM CONSTRUCTION
NC 2017 | K10 | Region VIII | Leyte | 121463 | Malobago ES | JARO | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  | P00182017VS-CW1 | 17ID0161 |  |  |  | 2018-01-05 | 2018-01-11 | JONI CONSTRUCTION
NC 2017 | K10 | Region VIII | Leyte | 121463 | Malobago ES | JARO | 2 |  | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  | P00182018VS-CW1 | 17ID0162 |  |  |  | 2018-01-05 | 2018-01-11 | JONI CONSTRUCTION
NC 2017 | SHS | Region VIII | Leyte | 303379 | Javier NHS | JAVIER (BUGHO) | 5 | 1 | 3 | 1STY3CL | BATCH 12 | 4118435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121508 | Naliwatan PS | JAVIER (BUGHO) | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121512 | San Sotero ES | JAVIER (BUGHO) | 5 | 1 | 3 | 1STY3CL | BATCH 12 | 3818435.02 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121515 | Ulhay ES | JAVIER (BUGHO) | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3013745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303395 | Lim-ao NHS | KANANGA | 4 | 1 | 8 | 2STY8CL | BATCH 12 | 17552790.26 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121557 | Bagacay East PS | LAPAZ | 2 | 1 | 3 | 1STY3CL | BATCH 12 | 4074592 |  |  | Completed | 1 |  |  | P00182022VS-CW1 | 17ID0166 |  |  |  | 2018-01-05 | 2018-01-10 | WJ BUILDERS
NC 2017 | SHS | Region VIII | Leyte | 313332 | Buracan NHS | LAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  | P0082111VS-CW1 | 17ID0105 |  |  |  | 2017-11-27 | 2017-11-29 | GENETIAN BUILDERS
NC 2017 | K10 | Region VIII | Leyte | 121564 | Calaghusan ES | LAPAZ | 2 | 1 | 3 | 1STY3CL | BATCH 12 | 4074592 |  |  | Completed | 1 |  |  | P0082023VS-CW1 | 17ID0168 |  |  |  | 2018-01-05 | 2018-01-11 | 3A'S BUILDERS
NC 2017 | K10 | Region VIII | Leyte | 121565 | Caltayan PS | LAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2845287 |  |  | Completed | 1 |  |  | P00182024VS-CW1 | 17ID0142 |  |  |  | 2017-12-29 | 2018-01-03 | AC TEJOME CONSTRUCTION (FORMERLY TEJOME-BALBERONA CONSTRUCTION)
NC 2017 | K10 | Region VIII | Leyte | 121568 | Doyog ES | LAPAZ | 2 | 1 | 3 | 1STY3CL | BATCH 12 | 4074592 |  |  | Completed | 1 |  |  | P00182025VS-CW1 | 17ID0169 |  |  |  | 2018-01-05 | 2018-01-10 | KUBLAI CONSTRUCTION AND SUPPLIES
NC 2017 | K10 | Region VIII | Leyte | 121573 | Limba ES | LAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2845287 |  |  | Completed | 1 |  |  | P00182026VS-CW1 | 17ID0141 |  |  |  | 2017-12-27 | 2017-12-29 | ROCKCON BUILDERS AND CONSTRUCTION SUPPLY
NC 2017 | K10 | Region VIII | Leyte | 121578 | Nicasio Vivero MPS | LAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2845287 |  |  | Completed | 1 |  |  | P00182027VS-CW1 | 17ID0143 |  |  |  | 2017-12-29 | 2018-01-03 | RCC BUILDERS AND ENTERPRISES
NC 2017 | K10 | Region VIII | Leyte | 121579 | Pansud Primary School | LAPAZ | 2 | 1 | 3 | 1STY3CL | BATCH 12 | 4240886 |  |  | Completed | 1 |  |  | P00182028VS-CW1 | 17ID0165 |  |  |  | 2018-01-05 | 2018-01-11 | WJ BUILDERS
NC 2017 | K10 | Region VIII | Leyte | 121580 | Pawa Primary School | LAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2845287 |  |  | Completed | 1 |  |  | P0082029VS-CW1 | 17ID0144 |  |  |  | 2018-01-05 | 2018-01-11 | 3A'S BUILDERS
NC 2017 | K10 | Region VIII | Leyte | 121581 | Piliway PS | LAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2845287 |  |  | Completed | 1 |  |  | P00182030VS-CW1 | 17ID0145 |  |  |  | 2017-12-29 | 2018-01-03 | YFL BUILDERS
NC 2017 | K10 | Region VIII | Leyte | 121583 | San Victoray ES | LAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2845287 |  |  | Completed | 1 |  |  | P00182022VS-CW | 17ID0166 |  |  |  | 2018-12-29 | 2018-01-04 | E.G. CANABE CONSTRUCTION
NC 2017 | K10 | Region VIII | Leyte | 121584 | Sta. Ana ES | LAPAZ | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2845287 |  |  | Completed | 1 |  |  | P00182032VS-CW1 | 17ID0146 |  |  |  | 2018-01-03 | 2018-01-09 | MAGILAS CONSTRUCTION CORPORATION
NC 2017 | K10 | Region VIII | Leyte | 121597 | Leyte CS | LEYTE | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2686020.84 |  |  | Completed | 1 |  |  | P00182033VS | 17IE0126 | [5 empty] | RJIR Enterprises
NC 2017 | K10 | Region VIII | Leyte | 121606 | Salog ES | LEYTE | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2796708.13 |  |  | Completed | 1 |  |  | P00182034VS | 17IE0125 | [5 empty] | Wawot Builders
NC 2017 | K10 | Region VIII | Leyte | 191529 | Gen. Luna ES | MACARTHUR | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2845287 |  |  | Completed | 1 |  |  | P00182050VS-CW1 | 17ID0154 |  |  |  | 2018-01-05 | 2018-01-11 | LTZ CONSTRUCTION AND SUPPLY
NC 2017 | K10 | Region VIII | Leyte | 191564 | Kiling ES | MACARTHUR | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2845287 |  |  | Completed | 1 |  |  | P00182051VS-CW1 | 17ID0155 |  |  |  | 2018-01-05 | 2018-01-11 | E.G. CANABE CONSTRUCTION
NC 2017 | K10 | Region VIII | Leyte | 191576 | San Isidro ES | MACARTHUR | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2845287 |  |  | Completed | 1 |  |  | P00182052VS-CW1 | 17ID0156 |  |  |  | 2018-01-03 | 2018-01-08 | HARDLINE BUILDERS AND SALES
NC 2017 | K10 | Region VIII | Leyte | 121630 | Cuatro de Agosto Primary School | MAHAPLAG | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2859745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303398 | Mahaplag NHS | MAHAPLAG | 5 | 1 | 1 | 1STY1 REGULAR WORKSHOP | BATCH 12 | 2988745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 313314 | Polahongon NHS | MAHAPLAG | 5 | 1 | 1 | 1STY1 UNIQUE WORKSHOP | BATCH 12 | 2613745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303370 | Esperanza NHS | MATALOM | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2938745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte |  | EUPERPIA PUDA NHS | MATALOM | 5 | 1 | 4 | 1STY4CL | BATCH 12 | 5708351.15 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121677 | Hipo ES | MATALOM | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2913745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 313337 | Sta. Paz Integrated School | MATALOM | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2859745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 121681 | Sta. Paz Integrated School | MATALOM | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2863745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121682 | Taglibas ES | MATALOM | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 2913745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303410 | Puerto Bello NHS | MERIDA | 4 | 1 | 4 | 2STY4CL | BATCH 12 | 9673901.76 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303415 | Palo NHS | PALO | 1 | 1 | 3 | 3-UNITS 1STY REGULAR WORKSHOP BLDG (7x18) | BATCH 12 | 8625361.53 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 313335 | Palo NHS-Pawing Annex | PALO | 1 | 1 | 2 | 2-UNITS 1STY SCIENCE LAB. | BATCH 12 | 5750241.02 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 313335 | Palo NHS-Pawing Annex | PALO | 1 |  | 2 | 2-UNITS 1STY COMPUTER LAB. | BATCH 12 | 5750241.02 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 313335 | Palo NHS-Pawing Annex | PALO | 1 |  | 4 | 2STY4CL | BATCH 12 | 9403604.86 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121763 | San Joaquin CS | PALO | 1 | 1 | 8 | 2STY8CL | BATCH 12 | 16974970.26 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303424 | San Joaquin NHS | PALO | 1 | 1 | 2 | 2-UNITS 1STY SCIENCE LAB. | BATCH 12 | 5750241.02 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303424 | San Joaquin NHS | PALO | 1 |  | 2 | 2-UNITS 1STY COMPUTER LAB. | BATCH 12 | 5750241.02 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303424 | San Joaquin NHS | PALO | 1 |  | 6 | 2STY6CL | BATCH 12 | 12532343.18 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 313315 | San Guillermo NHS | PALOMPON | 4 | 1 | 2 | 1STY2CL | BATCH 12 | 2763745.92 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 313330 | Manaybanay NHS | PASTRANA | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2845287 |  |  | Completed | 1 |  |  | P00173562VS-CW1 | 17ID0128 |  |  |  | 2017-12-22 | 2017-12-28 | JDR CONSTRUCTION
NC 2017 | K10 | Region VIII | Leyte | 121835 | E. Labucay PS | SAN ISIDRO | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2796708.13 |  |  | Completed | 1 |  |  | P00182040VS | 17IE0118 | [5 empty] | JDR Construction
NC 2017 | K10 | Region VIII | Leyte | 121841 | Paril ES | SAN ISIDRO | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2796708.13 |  |  | Completed | 1 |  |  | P00182041VS | 17IE0121 | [5 empty] | Wawot Builders
NC 2017 | TVL | Region VIII | Leyte | 303426 | San Miguel NHS | SAN MIGUEL | 1 | 1 | 1 | 1-UNIT 1STY SCIENCE LAB. | BATCH 12 | 2623745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303429 | Sta. Cruz NHS | SAN MIGUEL | 1 | 1 | 1 | 1-UNIT 1STY UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3593901.34 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303429 | Sta. Cruz NHS | SAN MIGUEL | 1 |  | 2 | 2-UNITS 1STY SCIENCE LAB. | BATCH 12 | 5734455.86 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303430 | Sta. Fe NHS | SANTA FE | 1 | 1 | 1 | 1-UNIT 1STY UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3593901.34 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303430 | Sta. Fe NHS | SANTA FE | 1 |  | 3 | 3-UNITS 1STY REGULAR WORKSHOP BLDG (7x18) | BATCH 12 | 8625361.53 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121886 | Gimarco ES | TABANGO | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2633745.92 |  |  | Completed | 1 |  |  | P00182042VS | 17IE0117 | [5 empty] | RJIR Enterprises
NC 2017 | K10 | Region VIII | Leyte | 121911 | Capahuan ES | TABONTABON | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2845287 |  |  | Completed | 1 |  |  | P00182043VS-CW1 | 17ID0159 |  |  |  | 2018-01-05 | 2018-01-11 | JELM CONSTRUCTION
NC 2017 | K10 | Region VIII | Leyte | 121913 | Jabong ES | TABONTABON | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2845287 |  |  | Completed | 1 |  |  | P00182044VS-CW1 | 17ID0149 |  |  |  | 2018-01-05 | 2018-01-11 | JELM CONSTRUCTION
NC 2017 | K10 | Region VIII | Leyte | 121914 | Mercaduhay ES | TABONTABON | 2 | 1 | 3 | 1STY3CL | BATCH 12 | 4074592 |  |  | Completed | 1 |  |  | P00182045VS-CW1 | 17ID0167 |  |  |  | 2018-01-05 | 2018-01-11 | JELM CONSTRUCTION
NC 2017 | TVL | Region VIII | Leyte | 303386 | Kiling NHS | TANAUAN | 1 | 1 | 2 | 2-UNITS 1STY SCIENCE LAB. | BATCH 12 | 5657522.58 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303386 | Kiling NHS | TANAUAN | 1 |  | 2 | 2-UNITS 1STY COMPUTER LAB. | BATCH 12 | 5438374.36 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303437 | Tanauan NHS (San Roque NHS) | TANAUAN | 1 | 1 | 2 | 2-UNITS 1STY SCIENCE LAB. | BATCH 12 | 5403091.62 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303437 | Tanauan NHS (San Roque NHS) | TANAUAN | 1 |  | 2 | 2-UNITS 1STY COMPUTER LAB. | BATCH 12 | 5393453.88 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121954 | San Roque ES | TOLOSA | 1 | 1 | 6 | 3STY6CL | BATCH 12 | 13899515.1 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121957 | Telegrafo ES School | TOLOSA | 1 | 1 | 6 | 2STY6CL | BATCH 12 | 11843668.02 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303440 | Tolosa NHS | TOLOSA | 1 | 1 | 1 | 1-UNIT 1STY UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3455634.88 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303440 | Tolosa NHS | TOLOSA | 1 |  | 2 | 2-UNITS 1STY SCIENCE LAB. | BATCH 12 | 5702759.94 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121976 | Abijao ES | VILLABA | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2816708.13 |  |  | Completed | 1 |  |  | P00182048VS | 17IE0114 | [5 empty] | RJIR Enterprises
NC 2017 | K10 | Region VIII | Leyte | 121977 | Balite ES | VILLABA | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2633745.92 |  |  | Completed | 1 |  |  | P00182049VS | 17IE0115 | [5 empty] | R. Allosa Construction & Trucking Services
NC 2017 | K10 | Region VIII | Maasin City | 323105 | Asuncion Integrated School | CITY OF MAASIN (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 9743196.85 |  |  | Completed | 1 |  |  | P00182120VS-CW1 | 17-IL-0134 | 2017-11-27 | 2017-06-12 | 2017-12-18 | 2017-12-22 | 2017-12-30 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2017 | SHS | Region VIII | Maasin City | 313401 | Maasin City NHS | CITY OF MAASIN (Capital) | 0 | 1 | 8 | 2STY8CL | BATCH 12 | 18343277.68 |  |  | Completed | 1 |  |  | P00182119VS-CW1 | 17-IL-0133 | 2017-11-23 | 2017-04-12 | 2017-12-14 | 2017-12-19 | 2017-12-30 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2017 | TVL | Region VIII | Northern Samar | 303540 | Capul Agro-Industrial School | CAPUL | 1 | 1 | 2 | 2-UNITS (1STY UNIQUE WORKSHOP) | BATCH 12 | 6253617.4 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Northern Samar | 122955 | Cabadiangan ES | LAOANG | 2 | 1 | 3 | 1STY3CL | BATCH 12 | 4762859.42 |  |  | Reverted | 0 | [10 empty] | Terminated due to non- availability of site
NC 2017 | TVL | Region VIII | Northern Samar | 313623 | MARAVILLA NHS | LAVEZARES | 1 | 1 | 1 | 1STY 1WORKSHOP BLDG (7x18) | BATCH 12 | 2889082.47 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Northern Samar | 313623 | MARAVILLA NHS | LAVEZARES | 1 |  | 1 | 1STY (1-REGULAR WORKSHOP) | BATCH 12 | 2889082.47 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Northern Samar | 303564 | Mapanas Agro-Industrial High School | MAPANAS | 2 | 1 | 3 | 3-UNITS UNIQUE WORKSHOP | BATCH 12 | 8201237.76 |  |  | REVERTED | 0
NC 2017 | TVL | Region VIII | Northern Samar | 303566 | Mondragon Agro-Ind'L HS | MONDRAGON | 1 | 1 | 3 | 3-UNITS (1STY UNIQUE WORKSHOP) | BATCH 12 | 8383500 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Northern Samar | 303536 | Buenavista NHS | ROSARIO | 1 | 1 | 1 | 1STY 1WORKSHOP BLDG (7x18) | BATCH 12 | 2973594.03 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Northern Samar | 303536 | Buenavista NHS | ROSARIO | 1 |  | 1 | 1STY (1-REGULAR WORKSHOP) | BATCH 12 | 2973594.03 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Northern Samar | 303573 | Rosario NHS | ROSARIO | 1 | 1 | 1 | 1STY 1WORKSHOP BLDG (7x18) | BATCH 12 | 2711618.3 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Northern Samar | 303573 | Rosario NHS | ROSARIO | 1 |  | 1 | 1STY (1-REGULAR WORKSHOP) | BATCH 12 | 2711618.3 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Northern Samar | 303578 | San Isidro NHS (San Isidro) | SAN ISIDRO | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2725799.3 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Northern Samar | 303578 | San Isidro NHS (San Isidro) | SAN ISIDRO | 1 |  | 2 | 1STY2CL | BATCH 12 | 2725799.3 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Northern Samar | 303580 | San Jose Technical HS | SAN JOSE | 1 | 1 | 2 | 2-UNITS (1STY UNIQUE WORKSHOP) | BATCH 12 | 5962775.43 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Northern Samar | 303567 | Mongolbongol NHS | SAN VICENTE | 1 | 1 | 1 | 1STY 1WORKSHOP BLDG (7x18) | BATCH 12 | 3426116.61 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Northern Samar | 303567 | Mongolbongol NHS | SAN VICENTE | 1 |  | 1 | 1STY (1-ICT LAB.) | BATCH 12 | 3426116.61 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Ormoc City | 303661 | Genaro B. LureÃ±ana NHS | ORMOC CITY | 4 | 1 | 4 | 2STY4CL | BATCH 12 | 9395901.76 |  |  | Completed | 1 |  |  | P00182138VS-CW1 | 171F0138 | 2017-10-24 | 2017-02-11 | 2017-11-15 | 2017-04-12 | 2017-12-22 | RJIR ENT.
NC 2017 | SHS | Region VIII | Ormoc City | 303657 | Margen NHS | ORMOC CITY | 4 | 1 | 4 | 2STY4CL | BATCH 12 | 9373901.76 |  |  | Completed | 1 |  |  | P00182136VS-CW1 | 171F0139 | 2017-10-24 | 2017-02-11 | 2017-11-15 | 2017-11-20 | 2017-12-15 | RJIR ENT.
NC 2017 | SHS | Region VIII | Ormoc City | 303660 | Rustico Capahi Sr. Memorial NHS | ORMOC CITY | 4 | 1 | 4 | 2STY4CL | BATCH 12 | 9245901.76 |  |  | Completed | 1 |  |  | P00182137VS-CW1 | 171F0137 | 2017-10-24 | 2017-02-11 | 2017-11-15 | 2017-04-12 | 2017-11-19 | RJIR ENT.
NC 2017 | SHS | Region VIII | Ormoc City | 303662 | Valencia NHS | ORMOC CITY | 4 | 1 | 12 | 4STY12CL | BATCH 12 | 32277789.72 |  |  | Completed | 1 |  |  | P00182139VS-CW1 | 171F0127 | 2017-10-18 | 2017-10-23 | 2017-11-14 | 2017-04-12 | 2017-12-13 | COLLERA CONST.
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 303593 | Burgos IS | BASEY | 2 | 1 | 3 | 1STY3CL | BATCH 12 | 3768435.02 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 313727 | Mabini NHS | BASEY | 2 | 1 | 5 | 1STY5CL | BATCH 12 | 6679000.91 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 303616 | Parasan NHS | DARAM | 2 | 1 | 4 | 1STY4CL | BATCH 12 | 5377000.18 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 313710 | Cuyting Uy NHS | JIABONG | 2 | 1 | 4 | 1STY4CL | BATCH 12 | 4888351.15 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 303609 | Jiabong Senior High School | JIABONG | 2 | 1 | 3 | 1STY3CL | BATCH 12 | 3768435.02 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 303611 | Marabut NHS | MARABUT | 2 | 1 | 3 | 1STY3CL | BATCH 12 | 3768435.02 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 303617 | Pinabacdao NHS | PINABACDAO | 2 | 1 | 4 | 1STY4CL | BATCH 12 | 4888351.15 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 303631 | Sta. Rita NHS | SANTA RITA | 2 | 1 | 3 | 1STY3CL | BATCH 12 | 3768435.02 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 303605 | Guintarcan NHS | VILLAREAL | 2 | 1 | 3 | 1STY3CL | BATCH 12 | 4145000.17 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 313702 | Plaridel NHS | VILLAREAL | 2 | 1 | 4 | 1STY4CL | BATCH 12 | 5377000.18 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 313718 | Primitivo T. Torrechiva NHS | VILLAREAL | 2 | 1 | 4 | 1STY4CL | BATCH 12 | 5377000.18 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 313707 | Bioso IS | ZUMARRAGA | 2 | 1 | 3 | 1STY3CL | BATCH 12 | 4125000.27 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Samar (Western Samar) | 303643 | Zumarraga NHS | ZUMARRAGA | 2 | 1 | 3 | 1STY3CL | BATCH 12 | 4145000.27 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303444 | Anahawan NVHS | ANAHAWAN | 0 | 1 | 8 | 2STY8CL | BATCH 12 | 18528151.63 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 192011 | Lewing Multi Grade ES | ANAHAWAN | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2833000.63 |  |  | Reverted | 0
NC 2017 | SHS | Region VIII | Southern Leyte | 313403 | Bontoc NHS | BONTOC | 0 | 1 | 8 | 2STY8CL | BATCH 12 | 18438403.72 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 121998 | Bunga ES | BONTOC | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2832000.5 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122022 | Union ES | BONTOC | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2848000.29 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122033 | Ingan ES | HINUNANGAN | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2857000.5 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122042 | Otama ES | HINUNANGAN | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2832000.5 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 192006 | Baculod MG ES | HINUNDAYAN | 0 | 1 | 3 | 1STY3CL | BATCH 12 | 4144000.54 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303466 | Lungsodaan NHS | HINUNDAYAN | 0 | 1 | 8 | 2STY8CL | BATCH 12 | 19343277.68 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122078 | Gakat ES | LIBAGON | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2872000.84 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122080 | Libagon Central Sentral | LIBAGON | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 9782655.87 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 313411 | Libagon NHS | LIBAGON | 0 | 1 | 6 | 2STY6CL | BATCH 12 | 12705538.1 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303472 | Rito Monte de Ramos Sr. MHS (Nahaong NHS) | LIBAGON | 0 | 1 | 8 | 2STY8CL | BATCH 12 | 18513025.58 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122099 | Himayangan ES | LILOAN | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 9782655.87 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 313409 | Liloan National Technical Vocational High School | LILOAN | 0 | 1 | 8 | 2STY8CL | BATCH 12 | 18513025.58 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303465 | LIMASAWA NHS | LIMASAWA | 0 | 1 | 12 | 2STY12CL | BATCH 12 | 26021818.16 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303462 | Ichon Integrated Senior High School | MACROHON | 0 | 1 | 12 | 3STY12CL | BATCH 12 | 31717619.62 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303492 | VILLA JACINTA NVHS | MACROHON | 0 | 1 | 12 | 3STY12CL | BATCH 12 | 31917619.62 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122205 | Caraatan ES | MALITBOG | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 3197000.5 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303488 | Sta. Cruz NHS | MALITBOG | 0 | 1 | 12 | 3STY12CL | BATCH 12 | 31570823.29 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303476 | Pintuyan NHS | PINTUYAN | 0 | 1 | 6 | 2STY6CL | BATCH 12 | 12722099.78 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303477 | Pintuyan NVHS | PINTUYAN | 0 | 1 | 12 | 3STY12CL | BATCH 12 | 32108008.63 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303460 | Himbangan NHS | SAINT BERNARD | 0 | 1 | 8 | 2STY8CL | BATCH 12 | 18513025.58 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122297 | Malinao ES | SAINT BERNARD | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2845000.57 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122305 | Tabontabon ES | SAINT BERNARD | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2870000.57 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303489 | Sta. Paz NHS | SAN FRANCISCO | 0 | 1 | 8 | 2STY8CL | BATCH 12 | 18613025.58 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122117 | Tuno ES | SAN FRANCISCO | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2871000.7 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303481 | San Juan NHS | SAN JUAN (CABALIAN) | 0 | 1 | 12 | 3STY12CL | BATCH 12 | 31717619.62 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303483 | San Ricardo NHS | SAN RICARDO | 0 | 1 | 8 | 2STY8CL | BATCH 12 | 18613025.58 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122059 | Silago CS | SILAGO | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2859000.77 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303486 | Silago NVHS | SILAGO | 0 | 1 | 8 | 2STY8CL | BATCH 12 | 18613025.58 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 192024 | Tuba-on ES | SILAGO | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2871000.7 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303487 | Sogod NHS | SOGOD | 0 | 1 | 12 | 3STY12CL | BATCH 12 | 31227230.61 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Tacloban City | 124254 | Bliss ES School | TACLOBAN CITY (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 12 | 8846371.1 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Tacloban City | 303663 | Leyte NHS | TACLOBAN CITY (Capital) | 1 | 1 | 4 | 2STY (2-REGULAR WORKSHOP) | BATCH 12 | 9664811.57 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Tacloban City | 314004 | Northern Tacloban City NHS | TACLOBAN CITY (Capital) | 1 | 1 | 8 | 2STY (2-SCI. LAB. & 2-ICT LAB.) | BATCH 12 | 17953455.02 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Tacloban City | 303667 | San Jose NHS | TACLOBAN CITY (Capital) | 1 | 1 | 8 | 4STY (2-REGULAR, 1-SCI. LAB., 1-ICT LAB.) | BATCH 12 | 22759945.36 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Tacloban City | 314005 | Scandinavian NHS | TACLOBAN CITY (Capital) | 1 | 1 | 8 | 4STY8CL (2-REGULAR, 1SCI. LAB., 1-ICT LAB.) | BATCH 12 | 22759945.36 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Tacloban City | 344881 | Tacloban City Stand Alone 1 Senior High School | TACLOBAN CITY (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 12 | 22763200.93 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Tacloban City | 344882 | V&G NHS | TACLOBAN CITY (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 12 | 17877017.19 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Baybay City | 327501 | Banahao NHS | CITY OF BAYBAY | 5 | 1 | 3 | 1STY3CL | BATCH 13 | 3768435.02 |  |  | Completed | 1 |  |  | P00183003VS-CW1 | 17IG0129 |  | 2017-11-02 | 2017-11-15 | 2017-12-29 | 2018-01-04 | RJIR ENTERPRISES
NC 2017 | SHS | Region VIII | Baybay City | 303420 | Pomponan NHS | CITY OF BAYBAY | 5 | 1 | 2 | 1STY2CL | BATCH 13 | 3113745.92 |  |  | Completed | 1 |  |  | P00183002VS-CW1 | 17IG0129 |  | 2017-11-02 | 2017-11-15 | 2017-12-29 | 2018-01-04 | RJIR ENTERPRISES
NC 2017 | K10 | Region VIII | Biliran | 120770 | Tabunan ES | ALMERIA | 0 | 1 | 3 | 1STY3CL | BATCH 13 | 4462646 |  |  | Completed | 1 |  |  | P00183004VS-CW1 | 17IA0110 | 2017-11-20 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-03 | BNL CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120797 | Alegria ES | CAIBIRAN | 0 | 1 | 3 | 1STY3CL | BATCH 13 | 4543174 |  |  | Completed | 1 |  |  | P00183005VS-CW1 | 17IA0109 | 2017-11-20 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-03 | QUIRANTE MV BUILDERS
NC 2017 | K10 | Region VIII | Biliran | 120800 | Binohangan ES | CAIBIRAN | 0 | 1 | 9 | 3-UNITS 1STY3CL | BATCH 13 | 13629519 |  |  | Completed | 1 |  |  | P00183006VS-CW1 | 17IA0139 | 2017-12-01 | 2017-12-15 | 2017-12-26 | 2018-01-11 | 2018-01-23 | QUIRANTE MV BUILDERS
NC 2017 | K10 | Region VIII | Biliran | 120805 | Kaulangohan ES | CAIBIRAN | 0 | 1 | 3 | 1STY3CL | BATCH 13 | 4543174 |  |  | Completed | 1 |  |  | P00183007VS-CW1 | 17IA0111 | 2017-11-20 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-03 | QYT CONSTRUCTION & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120808 | Mainit ES | CAIBIRAN | 0 | 1 | 3 | 1STY3CL | BATCH 13 | 4543174 |  |  | Completed | 1 |  |  | P00183008VS-CW1 | 17IA0118 | 2017-11-28 | 2017-12-06 | 2017-12-18 | 2018-01-05 | 2018-01-16 | QYT CONSTRUCTION & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120818 | Bool ES | CULABA | 0 | 1 | 9 | 3-UNITS 1STY3CL | BATCH 13 | 13629519 |  |  | Completed | 1 |  |  | P00183009VS-CW1 | 17IA0140 | 2017-12-01 | 2017-12-15 | 2017-12-26 | 2018-01-11 | 2018-01-23 | MB ANG CONSTRUCTION & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120827 | Baganito ES | KAWAYAN | 0 | 1 | 6 | 2-UNITS OF 1STY3CL | BATCH 13 | 9086346 |  |  | Completed | 1 |  |  | P00183010VS-CW1 | 17IA0144 | 2017-12-01 | 2017-12-15 | 2017-12-26 | 2018-01-11 | 2018-01-23 | W. B. ALAGAO CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120843 | Ungale I ES | KAWAYAN | 0 | 1 | 3 | 1STY3CL | BATCH 13 | 4519173 |  |  | Completed | 1 |  |  | P00183010VS-CW1 | 17IA0119 | 2017-11-28 | 2017-12-06 | 2017-12-18 | 2018-01-05 | 2018-01-16 | W. B. ALAGAO CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120853 | Maripipi CS | MARIPIPI | 0 | 1 | 3 | 1STY3CL | BATCH 13 | 4556857 |  |  | REVERTED | 0
NC 2017 | SHS | Region VIII | Biliran | 303329 | Maripipi NVS | MARIPIPI | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 3144434 |  |  | REVERTED | 0
NC 2017 | K10 | Region VIII | Biliran | 120869 | CAPIÑAHAN ES | NAVAL (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 13 | 4443804 |  |  | Completed | 1 |  |  | P00183013VS-CW1 | 17IA0112 | 2017-11-20 | 2017-11-29 | 2017-12-12 | 2017-12-22 | 2018-01-03 | W. B. ALAGAO CONSTRUCTION
NC 2017 | K10 | Region VIII | Biliran | 120870 | Caraycaray CS | NAVAL (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 13 | 4443804 |  |  | Completed | 1 |  |  | P00183014VS-CW1 | 17IA0115 | 2017-11-28 | 2017-12-06 | 2017-12-18 | 2018-01-05 | 2018-01-16 | QYT CONSTRUCTION & SUPPLIES
NC 2017 | K10 | Region VIII | Biliran | 120877 | Lico ES | NAVAL (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 13 | 4455805 |  |  | Completed | 1 |  |  | P00183015VS-CW1 | 17IA0114 | 2017-11-28 | 2017-12-06 | 2017-12-18 | 2018-01-05 | 2018-01-16 | MKB BUILDERS & SUPPLIES
NC 2017 | TVL | Region VIII | Leyte | 303392 | Alangalang Agro-Industrial School (LSU - Alangalang Campus) | ALANGALANG | 1 |  | 3 | 3-UNITS 1STY REGULAR WORKSHOP BLDG (7x18) | BATCH 13 | 7854345.36 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303392 | Alangalang Agro-Industrial School (LSU - Alangalang Campus) | ALANGALANG | 1 | 1 | 1 | 1-UNIT 1STY SCIENCE LAB. | BATCH 13 | 2861029.61 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303392 | Alangalang Agro-Industrial School (LSU - Alangalang Campus) | ALANGALANG | 1 |  | 1 | 1-UNIT 1STY SCIENCE LAB. | BATCH 13 | 2875120.51 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303336 | Alangalang NHS | ALANGALANG | 1 | 1 | 2 | 1STY2CL | BATCH 13 | 2875119.92 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303336 | Alangalang NHS | ALANGALANG | 1 |  | 1 | 1-UNIT 1STY COMPUTER LAB. | BATCH 13 | 2875120.51 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303336 | Alangalang NHS | ALANGALANG | 1 |  | 1 | 1-UNIT 1STY COMPUTER LAB. | BATCH 13 | 2713767.43 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303340 | Astorga NHS | ALANGALANG | 1 | 1 | 2 | 2-UNITS 1STY SCIENCE LAB. | BATCH 13 | 5236230.24 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303340 | Astorga NHS | ALANGALANG | 1 |  | 1 | 1-UNIT 1STY COMPUTER LAB. | BATCH 13 | 2875120.51 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303340 | Astorga NHS | ALANGALANG | 1 |  | 1 | 1-UNIT 1STY COMPUTER LAB. | BATCH 13 | 2618115.12 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 120966 | Bugho ES | ALANGALANG | 1 | 1 | 3 | 1STY3CL | BATCH 13 | 3868435.02 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303343 | Juan S. Tismo NHS (Babatngon NHS) | BABATNGON | 1 |  | 3 | 3-UNITS 1STY REGULAR WORKSHOP BLDG (7x18) | BATCH 13 | 8625361.26 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303401 | Malibago NHS | BABATNGON | 1 | 1 | 3 | 1STY3CL | BATCH 13 | 3768435.02 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303401 | Malibago NHS | BABATNGON | 1 |  | 1 | 1-UNIT 1STY SCIENCE LAB. | BATCH 13 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303401 | Malibago NHS | BABATNGON | 1 |  | 1 | 1-UNIT 1STY SCIENCE LAB. | BATCH 13 | 2875120.51 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303401 | Malibago NHS | BABATNGON | 1 |  | 1 | 1-UNIT 1STY COMPUTER LAB. | BATCH 13 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303413 | Pagsulhugon NHS | BABATNGON | 1 | 1 | 1 | 1-UNIT 1STY SCIENCE LAB. | BATCH 13 | 2875120.51 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303413 | Pagsulhugon NHS | BABATNGON | 1 |  | 1 | 1-UNIT 1STY COMPUTER LAB. | BATCH 13 | 2875120.51 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303413 | Pagsulhugon NHS | BABATNGON | 1 |  | 1 | 1-UNIT 1STY COMPUTER LAB. | BATCH 13 | 2875120.51 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303421 | San Agustin NHS | BABATNGON | 1 | 1 | 1 | 1-UNIT 1STY SCIENCE LAB. | BATCH 13 | 2724019.47 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303421 | San Agustin NHS | BABATNGON | 1 |  | 1 | 1-UNIT 1STY COMPUTER LAB. | BATCH 13 | 2651832.09 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303421 | San Agustin NHS | BABATNGON | 1 |  | 1 | 1-UNIT 1STY COMPUTER LAB. | BATCH 13 | 2796634.67 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121021 | Taguite ES | BABATNGON | 1 | 1 | 3 | 1STY3CL | BATCH 13 | 4075050.15 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121231 | Tagharigue ES | CALUBIAN | 3 | 1 | 2 | 1STY2CL | BATCH 13 | 2816708.13 |  |  | Completed | 1 |  |  | P00183058VS | 17IE0111 | [5 empty] | R. Allosa Construction & Trucking Services
NC 2017 | TVL | Region VIII | Leyte | 303415 | Palo NHS | PALO | 1 | 1 | 2 | 2-UNITS 1STY SCIENCE LAB. | BATCH 13 | 5750241.02 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303415 | Palo NHS | PALO | 1 |  | 2 | 2-UNITS 1STY COMPUTER LAB. | BATCH 13 | 5750241.02 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121860 | Malpag PS | SAN MIGUEL | 1 | 1 | 2 | 1STY2CL | BATCH 13 | 2693745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121862 | Patong ES | SAN MIGUEL | 1 | 1 | 2 | 1STY2CL | BATCH 13 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121865 | San Miguel CS | SAN MIGUEL | 1 | 1 | 2 | 1STY2CL | BATCH 13 | 2635308.92 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303429 | Sta. Cruz NHS | SAN MIGUEL | 1 | 1 | 2 | 2-UNITS 1STY REGULAR WORKSHOP BLDG (7x18) | BATCH 13 | 5750241.02 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303429 | Sta. Cruz NHS | SAN MIGUEL | 1 |  | 2 | 2-UNITS 1STY COMPUTER LAB. | BATCH 13 | 5750241.02 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121873 | Milagrosa ES School | SANTA FE | 1 | 1 | 2 | 1STY2CL | BATCH 13 | 2645925.92 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303430 | Sta. Fe NHS | SANTA FE | 1 | 1 | 2 | 2-UNITS 1STY SCIENCE LAB. | BATCH 13 | 5750241.02 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303430 | Sta. Fe NHS | SANTA FE | 1 |  | 2 | 2-UNITS 1STY COMPUTER LAB. | BATCH 13 | 5750241.02 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Leyte | 303386 | Kiling NHS | TANAUAN | 1 | 1 | 3 | 1STY3CL | BATCH 13 | 4145235.02 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121954 | San Roque ES | TOLOSA | 1 | 1 | 2 | 1STY2CL | BATCH 13 | 2623745.92 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303440 | Tolosa NHS | TOLOSA | 1 | 1 | 1 | 1-UNIT 1STY REGULAR WORKSHOP (7X18) | BATCH 13 | 2696966.91 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303440 | Tolosa NHS | TOLOSA | 1 |  | 1 | 1-UNIT 1STY REGULAR WORKSHOP (7X18) | BATCH 13 | 2855873.68 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303440 | Tolosa NHS | TOLOSA | 1 |  | 1 | 1-UNIT 1STY REGULAR WORKSHOP (7X18) | BATCH 13 | 2855873.68 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303440 | Tolosa NHS | TOLOSA | 1 |  | 1 | 1-UNIT 1STY REGULAR WORKSHOP (7X18) | BATCH 13 | 2855873.68 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303440 | Tolosa NHS | TOLOSA | 1 |  | 1 | 1-UNIT 1STY COMPUTER LAB. | BATCH 13 | 2851710.34 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Leyte | 303440 | Tolosa NHS | TOLOSA | 1 |  | 1 | 1-UNIT 1STY COMPUTER LAB. | BATCH 13 | 2784081.47 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Leyte | 121971 | Libagong ES | VILLABA | 3 | 1 | 2 | 1STY2CL | BATCH 13 | 2633745.92 |  |  | Completed | 1 |  |  | P00183057VS | 17IE0122 | [5 empty] | R. Allosa Construction & Trucking Services
NC 2017 | SHS | Region VIII | Maasin City | 303454 | Dongon NHS | CITY OF MAASIN (Capital) | 0 | 1 | 12 | 3STY12CL | BATCH 13 | 31470823.29 |  |  | Completed | 1 |  |  | P00183068VS-CW1 | 17-IL-0137 | 2017-11-23 | 2017-04-12 | 2017-12-14 | 2017-12-19 | 2017-12-30 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2017 | SHS | Region VIII | Maasin City | 303454 | Dongon NHS | CITY OF MAASIN (Capital) | 0 |  | 4 | 2STY4CL | BATCH 13 | 9682655.87 |  |  | Completed | 1 |  |  | P00183060VS-CW1 | 17-IL-0178 | 2017-11-27 | 2017-06-12 | 2017-12-18 | 2017-12-22 | 2017-12-30 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2017 | SHS | Region VIII | Maasin City | 323101 | Ibarra NHS | CITY OF MAASIN (Capital) | 0 | 1 | 8 | 2STY8CL | BATCH 13 | 18123529.77 |  |  | Completed | 1 |  |  | P00183063VS-CW1 | 17-IL-0135 | 2017-11-23 | 2017-04-12 | 2017-12-14 | 2017-12-19 | 2017-12-30 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2017 | SHS | Region VIII | Maasin City | 303464 | Libhu NHS | CITY OF MAASIN (Capital) | 0 | 1 | 8 | 2STY8CL | BATCH 13 | 18443277.68 |  |  | Completed | 1 |  |  | P00183061VS-CW1 | 17-IL-0139 | 2017-11-23 | 2017-04-12 | 2017-12-14 | 2017-12-19 | 2017-12-30 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2017 | K10 | Region VIII | Maasin City | 323103 | Lunas NHS | CITY OF MAASIN (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 13 | 10101032.92 |  |  | Completed | 1 |  |  | P00183064VS-CW1 | 17-IL-0140 | 2017-11-27 | 2017-06-12 | 2017-12-18 | 2017-12-22 | 2017-12-30 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2017 | K10 | Region VIII | Maasin City | 323103 | Lunas NHS | CITY OF MAASIN (Capital) | 0 |  | 4 | 2STY4CL | BATCH 13 | 10101032.92 |  |  | Completed | 1 |  |  | P00183065VS-CW1 | 17-IL-0141 | 2017-11-27 | 2017-06-12 | 2017-12-18 | 2017-12-22 | 2017-12-30 | CEAN CONSTRUCTION
NC 2017 | SHS | Region VIII | Maasin City | 303469 | Manhilo NHS | CITY OF MAASIN (Capital) | 0 | 1 | 8 | 2STY8CL | BATCH 13 | 19643277.68 |  |  | Completed | 1 |  |  | P00183062VS-CW1 | 17-IL-0180 | 2017-11-27 | 2017-06-12 | 2017-12-18 | 2017-12-22 | 2017-12-30 | A.C. RIVERO DEVT. CORPORATION
NC 2017 | K10 | Region VIII | Maasin City | 323106 | Matin-aw NHS | CITY OF MAASIN (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 13 | 13105223.14 |  |  | Completed | 1 |  |  | P00183066VS-CW1 | 17-IL-0181 | 2017-11-27 | 2017-06-12 | 2017-12-18 | 2017-12-22 | 2017-12-30 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2017 | K10 | Region VIII | Maasin City | 323106 | Matin-aw NHS | CITY OF MAASIN (Capital) | 0 |  | 4 | 2STY4CL | BATCH 13 | 10101032.92 |  |  | Completed | 1 |  |  | P00183067VS-CW1 | 17-IL-0138 | 2017-11-27 | 2017-06-12 | 2017-12-18 | 2017-12-22 | 2017-12-30 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2017 | SHS | Region VIII | Maasin City | 344781 | Stand Alone SHS within San Rafael ES | CITY OF MAASIN (Capital) | 0 | 1 | 12 | 3STY12CL | BATCH 13 | 31764415.96 |  |  | Completed | 1 |  |  | P00183068VS-CW1 | 17-IL-0136 | 2017-11-23 | 2017-04-12 | 2017-12-14 | 2017-12-19 | 2017-12-30 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2017 | SHS | Region VIII | Maasin City | 344781 | Stand Alone SHS within San Rafael ES | CITY OF MAASIN (Capital) | 0 |  | 6 | 3STY6CL | BATCH 13 | 15001281.16 |  |  | Completed | 1 |  |  | P00183069VS-CW1 | 17-IL-0179 | 2027-11-27 | 2017-06-12 | 2017-12-18 | 2017-12-22 | 2017-12-30 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2017 | SHS | Region VIII | Ormoc City | 313901 | Lilo-an NHS | ORMOC CITY | 4 | 1 | 9 | 3STY9CL | BATCH 13 | 25096047.73 |  |  | Completed | 1 |  |  | P00183070VS-CW1 | 171F0129 | 2017-10-18 | 2017-10-23 | 2017-11-14 | 2017-04-12 | 2017-12-13 | COLLERA CONST.
NC 2017 | SHS | Region VIII | Ormoc City | 344795 | Ormoc City Sports Senior High School | ORMOC CITY | 4 | 1 | 9 | 3STY9CL | BATCH 13 | 25146047.73 |  |  | Completed | 1 |  |  | P00183071VS-CW1 | 171F0128 | 2017-10-18 | 2017-10-23 | 2017-11-14 | 2017-04-12 | 2017-12-13 | COLLERA CONST.
NC 2017 | SHS | Region VIII | Southern Leyte | 303444 | Anahawan NVHS | ANAHAWAN | 0 |  | 4 | 2STY4CL | BATCH 13 | 9752385.37 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 313403 | Bontoc NHS | BONTOC | 0 | 1 | 8 | 2STY8CL | BATCH 13 | 18438403.72 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 313403 | Bontoc NHS | BONTOC | 0 |  | 4 | 2STY4CL | BATCH 13 | 9737926.36 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303475 | Paku NHS | BONTOC | 0 | 1 | 10 | 2STY10CL | BATCH 13 | 21340645.01 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Southern Leyte | 122046 | San Pablo ES | HINUNANGAN | 0 | 1 | 10 | 2STY10CL | BATCH 13 | 22867297.46 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303466 | Lungsodaan NHS | HINUNDAYAN | 0 |  | 8 | 2STY8CL | BATCH 13 | 19343277.68 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303472 | Rito Monte de Ramos Sr. MHS (Nahaong NHS) | LIBAGON | 0 |  | 8 | 2STY8CL | BATCH 13 | 18513000.02 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 313409 | Liloan National Technical Vocational High School | LILOAN | 0 |  | 8 | 2STY8CL | BATCH 13 | 18513025.58 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303492 | VILLA JACINTA NVHS | MACROHON | 0 |  | 12 | 3STY12CL | BATCH 13 | 31917619.62 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303488 | Sta. Cruz NHS | MALITBOG | 0 |  | 6 | 3STY6CL | BATCH 13 | 14863886.01 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303477 | Pintuyan NVHS | PINTUYAN | 0 | 1 | 12 | 3STY12CL | BATCH 13 | 32108008.63 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303477 | Pintuyan NVHS | PINTUYAN | 0 |  | 4 | 2STY4CL | BATCH 13 | 9797114.88 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303477 | Pintuyan NVHS | PINTUYAN | 0 |  | 8 | 2STY8CL | BATCH 13 | 18597899.53 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303460 | Himbangan NHS | SAINT BERNARD | 0 | 1 | 8 | 2STY8CL | BATCH 13 | 18513025.58 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303460 | Himbangan NHS | SAINT BERNARD | 0 |  | 4 | 2STY4CL | BATCH 13 | 9772114.88 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303489 | Sta. Paz NHS | SAN FRANCISCO | 0 |  | 8 | 2STY8CL | BATCH 13 | 18513025.58 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303481 | San Juan NHS | SAN JUAN (CABALIAN) | 0 |  | 6 | 3STY6CL | BATCH 13 | 14932583.58 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303483 | San Ricardo NHS | SAN RICARDO | 0 |  | 6 | 3STY6CL | BATCH 13 | 15051281.16 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303461 | Hingatungan NHS | SILAGO | 0 | 1 | 8 | 2STY8CL | BATCH 13 | 18613025.58 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303461 | Hingatungan NHS | SILAGO | 0 |  | 6 | 3STY6CL | BATCH 13 | 15051281.16 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303486 | Silago NVHS | SILAGO | 0 |  | 6 | 3STY6CL | BATCH 13 | 15001281.16 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Southern Leyte | 303487 | Sogod NHS | SOGOD | 0 |  | 8 | 2STY8CL | BATCH 13 | 18393277.68 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Tacloban City | 303663 | Leyte NHS | TACLOBAN CITY (Capital) | 1 | 1 | 18 | 4STY (4-REGULAR, 2-SCI. LAB., 2-ICT LAB) | BATCH 13 | 38093130.67 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Tacloban City | 314004 | Northern Tacloban City NHS | TACLOBAN CITY (Capital) | 1 | 1 | 12 | 3STY (6-REGULAR WORKSHOP) | BATCH 13 | 32386691.65 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Tacloban City | 500489 | Ridge View Park Integrated School | TACLOBAN CITY (Capital) | 1 | 1 | 12 | 3STY12CL | BATCH 13 | 51473899.42 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Tacloban City | 303667 | San Jose NHS | TACLOBAN CITY (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 13 | 45911406.36 |  |  | Reverted | 0
NC 2017 | K10 | Region VIII | Tacloban City | 303670 | Tacloban City NHS | TACLOBAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 13 | 18522603.6 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Tacloban City | 303669 | Tacloban National Agricultural School | TACLOBAN CITY (Capital) | 1 | 1 | 16 | 4STY (4-REGULAR, 2-SCI. LAB., 2-ICT LAB) | BATCH 13 | 36967805.57 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Tacloban City | 195003 | Utap ES School | TACLOBAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 13 | 12187634.49 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Tacloban City | 344882 | V&G NHS | TACLOBAN CITY (Capital) | 1 | 1 | 6 | 3STY (3-REGULAR WORKSHOP) | BATCH 13 | 14177333.94 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Biliran | 303324 | Culaba NVS | CULABA | 0 | 1 | 6 | 2STY6CL | BATCH 14 | 14925000 |  |  | Completed | 1 |  |  | P00184536VS-CW1 | 17IA0097 | 2017-11-16 | 2017-11-24 | 2017-12-07 | 2017-12-18 | 2017-01-03 | CHU CONSTRUCTION
NC 2017 | SHS | Region VIII | Biliran | 313201 | Western Biliran School for the Arts and Culture | ALMERIA | 0 | 1 | 10 | 2STY10CL | BATCH 14 | 24875000 |  |  | Completed | 1 |  |  | P00184536VS-CW1 | 17IA0098 | 2017-11-16 | 2017-11-24 | 2017-12-07 | 2017-12-18 | 2017-01-03 | CHU CONSTRUCTION
NC 2017 | K10 | Region VIII | Borongan City | 122361 | Eugenio S. Daza Pilot ES | CITY OF BORONGAN (Capital) | 0 | 1 | 8 | 2STY8CL | BATCH 14 | 16974790.26 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Borongan City | 122387 | San Saturnino ES | CITY OF BORONGAN (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 14 | 8950000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Borongan City | 303511 | Lalawigan NHS | CITY OF BORONGAN (Capital) | 0 | 1 | 2 | 2STY WORKSHOP BUILDING | BATCH 14 | 8300000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Borongan City | 303511 | Lalawigan NHS | CITY OF BORONGAN (Capital) | 0 |  | 6 | 3-UNIT 2STY WORKSHOP BUILDING | BATCH 14 | 25200000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Borongan City | 303525 | Sta. Fe NHS | CITY OF BORONGAN (Capital) | 0 | 1 | 6 | 3-UNITS 2STY WORKSHOP BUILDING | BATCH 14 | 25950000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Borongan City | 303526 | Maypangdan NHS | CITY OF BORONGAN (Capital) | 0 | 1 | 4 | 2-UNITS 2STY WORKSHOP BUILDING | BATCH 14 | 18200000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Borongan City | 313504 | Benowangan NHS (Lalawigan NHS - Benowangan Annex) | CITY OF BORONGAN (Capital) | 0 | 1 | 2 | 2STY WORKSHOP BUILDING | BATCH 14 | 10100000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Borongan City | 313504 | Benowangan NHS (Lalawigan NHS - Benowangan Annex) | CITY OF BORONGAN (Capital) | 0 |  | 2 | 2STY WORKSHOP BUILDING | BATCH 14 | 10000000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Borongan City | 313515 | E. Samar NCHS - Supt. Fidel E. Anacta, Sr. MHS Annex | CITY OF BORONGAN (Capital) | 0 | 1 | 2 | 2STY WORKSHOP BUILDING | BATCH 14 | 9000000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Borongan City | 313515 | E. Samar NCHS - Supt. Fidel E. Anacta, Sr. MHS Annex | CITY OF BORONGAN (Capital) | 0 |  | 2 | 2STY WORKSHOP BUILDING | BATCH 14 | 9100000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Borongan City | 313515 | E. Samar NCHS - Supt. Fidel E. Anacta, Sr. MHS Annex | CITY OF BORONGAN (Capital) | 0 |  | 2 | 2STY WORKSHOP BUILDING | BATCH 14 | 9200000 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Catbalogan City | 303604 | Eastern Visayas Regional Science High School | CITY OF CATBALOGAN (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 14 | 32915781.31 |  |  | Completed | 1 |  |  | P00184548VS | 171K0039 | 2017-12-01 | 2017-12-11 | 2017-12-22 | 2018-04-25 | 2018-01-09 | A.G ARAJA CONSTRUCTION AND DEVELOPMENT CORP.
NC 2017 | SHS | Region VIII | Catbalogan City | 303620 | Samar National School | CITY OF CATBALOGAN (Capital) | 2 | 1 | 16 | 2 UNITS OF 4STY8CL | BATCH 14 | 34319141.34 |  |  | Completed | 1 |  |  | P00184549VS | 171K0038 | 2017-12-01 | 2017-12-11 | 2017-12-22 | 2018-04-25 | 2018-01-09 | A.G ARAJA CONSTRUCTION AND DEVELOPMENT CORP.
NC 2017 | SHS | Region VIII | Catbalogan City | 303621 | Guinsorongan NHS | CITY OF CATBALOGAN (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 14 | 32599283.41 |  |  | Completed | 1 |  |  | P00184550VS | 171K0037 | 2017-12-01 | 2017-12-11 | 2017-12-22 | 2018-04-25 | 2018-01-09 | A.G ARAJA CONSTRUCTION AND DEVELOPMENT CORP.
NC 2017 | SHS | Region VIII | Catbalogan City | 303622 | Antonio G. Tuazon NHS | CITY OF CATBALOGAN (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 14 | 34181772.9 |  |  | Completed | 1 |  |  | P00184551VS | 171K0035 | 2017-12-01 | 2017-12-11 | 2017-12-22 | 2018-04-25 | 2018-01-09 | A.G ARAJA CONSTRUCTION AND DEVELOPMENT CORP. | Project Engineer's PCMA account is locked due to promotion to OIC Chief of Construction Section. Updating at DPWH Central Office for schedule.
NC 2017 | SHS | Region VIII | Catbalogan City | 303623 | Silanga NHS | CITY OF CATBALOGAN (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 14 | 32599283.41 |  |  | Completed | 1 |  |  | P00184552VS | 171K0037 | 2017-12-01 | 2017-12-11 | 2017-12-22 | 2018-04-25 | 2018-01-09 | A.G ARAJA CONSTRUCTION AND DEVELOPMENT CORP.
NC 2017 | SHS | Region VIII | Catbalogan City | 313706 | Pangdan NHS | CITY OF CATBALOGAN (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 14 | 33232279.21 |  |  | Completed | 1 |  |  | P00184553VS | 171K0036 | 2017-12-01 | 2017-12-11 | 2017-12-22 | 2018-04-25 | 2018-01-09 | A.G ARAJA CONSTRUCTION AND DEVELOPMENT CORP.
NC 2017 | K10 | Region VIII | Eastern Samar | 122325 | Arteche CS | ARTECHE | 0 | 1 | 6 | 2STY6CL | BATCH 14 | 12000000 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Eastern Samar | 122325 | Arteche CS | ARTECHE | 0 |  | 2 | 2STY2CL | BATCH 14 | 6700000 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Eastern Samar | 122433 | Dolores CS | DOLORES | 0 | 1 | 8 | 2STY8CL | BATCH 14 | 17200000 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Eastern Samar | 122433 | Dolores CS | DOLORES | 0 |  | 6 | 2STY6CL | BATCH 14 | 11800000 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Eastern Samar | 122433 | Dolores CS | DOLORES | 0 |  | 2 | 2STY2CL | BATCH 14 | 6300000 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Eastern Samar | 122757 | Sto. Tomas ES | SULAT | 0 | 1 | 4 | 2STY4CL | BATCH 14 | 9400000 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Eastern Samar | 303498 | Camantang NHS | CAN-AVID | 0 | 1 | 2 | 2STY2CL | BATCH 14 | 6559500 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Eastern Samar | 303499 | Dolores NHS | DOLORES | 0 | 1 | 4 | 2STY4CL | BATCH 14 | 9300000 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Eastern Samar | 303499 | Dolores NHS | DOLORES | 0 |  | 8 | 2STY8CL | BATCH 14 | 17000000 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Eastern Samar | 303499 | Dolores NHS | DOLORES | 0 |  | 10 | 2STY10CL | BATCH 14 | 19800000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 303499 | Dolores NHS | DOLORES | 0 |  | 10 | 5-UNITS WORKSHOP BUILDING | BATCH 14 | 44600000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 303499 | Dolores NHS | DOLORES | 0 |  | 2 | 2STY WORKSHOP BUILDING | BATCH 14 | 8950000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 303501 | Gen. MacArthur National Agricultural School | GENERAL MACARTHUR | 0 | 1 | 2 | 2STY WORKSHOP BUILDING | BATCH 14 | 8870000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 303501 | Gen. MacArthur National Agricultural School | GENERAL MACARTHUR | 0 | 1 | 2 | 2STY WORKSHOP BUILDING | BATCH 14 | 8880000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 303501 | Gen. MacArthur National Agricultural School | GENERAL MACARTHUR | 0 |  | 2 | 2STY WORKSHOP BUILDING | BATCH 14 | 8900000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 303501 | Gen. MacArthur National Agricultural School | GENERAL MACARTHUR | 0 |  | 2 | 2STY WORKSHOP BUILDING | BATCH 14 | 8890000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 303502 | Giporlos National Trade School | GIPORLOS | 0 | 1 | 4 | 2-UNITS 2STY WORKSHOP BUILDING | BATCH 14 | 17850000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 303502 | Giporlos National Trade School | GIPORLOS | 0 |  | 2 | 2STY WORKSHOP BUILDING | BATCH 14 | 9756000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 303502 | Giporlos National Trade School | GIPORLOS | 0 |  | 4 | 2-UNITS 2STY WORKSHOP BUILDING | BATCH 14 | 19486000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 303503 | Guiuan NHS | GUIUAN | 0 | 1 | 4 | 2-UNITS 2STY WORKSHOP BUILDING | BATCH 14 | 18400000 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Eastern Samar | 303505 | Pedro E. Candido Memorial NHS | HERNANI | 0 | 1 | 10 | 2STY10CL | BATCH 14 | 19800000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 303505 | Pedro E. Candido Memorial NHS | HERNANI | 0 |  | 8 | 4-UNITS 2STY WORKSHOP BUILDING | BATCH 14 | 35400000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 303510 | Jipapad National High School | JIPAPAD | 0 | 1 | 2 | 2-UNITS 2STY WORKSHOP BUILDING | BATCH 14 | 13000000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 303512 | Lawaan National School of Craftsmanship and Home Industries | LAWAAN | 0 | 1 | 4 | 2-UNITS 2STY WORKSHOP BUILDING | BATCH 14 | 17600000 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Eastern Samar | 303513 | Llorente NHS | LLORENTE | 0 | 1 | 6 | 2STY6CL | BATCH 14 | 11900000 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Eastern Samar | 303513 | Llorente NHS | LLORENTE | 0 |  | 12 | 3STY12CL | BATCH 14 | 29800000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 303513 | Llorente NHS | LLORENTE | 0 |  | 10 | 5-UNITS 2STY WORKSHOP BUILDING | BATCH 14 | 44000000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 303515 | Maslog NHS | MASLOG | 0 | 1 | 4 | 2-UNITS 2STY WORKSHOP BUILDING | BATCH 14 | 22000000 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Eastern Samar | 303515 | Maslog NHS | MASLOG | 0 |  | 4 | 2STY4CL | BATCH 14 | 11100000 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Eastern Samar | 303516 | Matarinao SOF | SALCEDO | 0 | 1 | 12 | 2-UNITS 3STY6CL | BATCH 14 | 28700000 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Eastern Samar | 303520 | Oras NHS | ORAS | 0 | 1 | 8 | 2STY8CL | BATCH 14 | 17100000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 303520 | Oras NHS | ORAS | 0 |  | 6 | 3-UNITS 2STY WORKSHOP BUILDING | BATCH 14 | 26850000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 303521 | Quinapondan NHS | QUINAPONDAN | 0 | 1 | 2 | 2STY WORKSHOP BUILDING | BATCH 14 | 9100000 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Eastern Samar | 303521 | Quinapondan NHS | QUINAPONDAN | 0 |  | 4 | 2STY4CL | BATCH 14 | 9250000 |  |  | Completed | 1
NC 2017 | K10 | Region VIII | Eastern Samar | 303522 | Salcedo NHS | SALCEDO | 0 | 1 | 12 | 2-UNITS 2STY6CL | BATCH 14 | 23600000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 303523 | Samar National Pilot Opportunity School of Agriculture | SAN POLICARPO | 0 | 1 | 8 | 4-UNITS 2STY WORKSHOP BUILDING | BATCH 14 | 34800000 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Eastern Samar | 303523 | Samar National Pilot Opportunity School of Agriculture | SAN POLICARPO | 0 |  | 4 | 2STY4CL | BATCH 14 | 9350000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 303524 | San Julian NHS | SAN JULIAN | 0 | 1 | 4 | 2-UNITS 2STY WORKSHOP BUILDING | BATCH 14 | 17600000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 303527 | Sulat NHS | SULAT | 0 | 1 | 2 | 2STY WORKSHOP BUILDING | BATCH 14 | 8800000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 303529 | Taft NHS | TAFT | 0 | 1 | 2 | 2STY WORKSHOP BUILDING | BATCH 14 | 8850000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 313501 | Can-avid NHS | CAN-AVID | 0 | 1 | 6 | 3-UNITS 2STY WORKSHOP BUILDING | BATCH 14 | 26700000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 313501 | Can-avid NHS | CAN-AVID | 0 |  | 2 | 2STY WORKSHOP BUILDING | BATCH 14 | 8900000 |  |  | Completed | 1
NC 2017 | TVL | Region VIII | Eastern Samar | 313502 | Southern Samar NCHS | BALANGIGA | 0 | 1 | 10 | 5-UNITS 2STY WORKSHOP BUILDING | BATCH 14 | 44000000 |  |  | Completed | 1
NC 2017 | SHS | Region VIII | Eastern Samar | 313509 | Salcedo Vocational High School | SALCEDO | 0 | 1 | 8 | 2STY8CL | BATCH 14 | 17000000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Baybay City | 121126 | Pomponan Elementary School | CITY OF BAYBAY | 5 | 1 | 2 | 2STY2CL SCI. LAB. | Batch 8 Realignment | 12209858.3 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Baybay City | 303360 | Caridad National High School | CITY OF BAYBAY | 5 | 1 | 2 | 2STY2CL SCI. LAB. | Batch 8 Realignment | 11694583.4 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Baybay City | 303420 | Pomponan NHS | CITY OF BAYBAY | 5 | 1 | 2 | 2STY2 ICT LAB. | Batch 3 | 11656837.78 |  |  | Completed | 1 |  |  | P00274652V-CW1 | 18IG0114 |  |  | 2018-12-11 |  | 2018-12-28 | JUCONS CONSTRUCTION & SUPPLY
NC 2018 | TVL | Region VIII | Baybay City | 313316 | Baybay City National Night HS | CITY OF BAYBAY | 5 | 1 | 2 | 2STY2 REGULAR WORKSHOP | Batch 3 | 11613065.1 |  |  | Completed | 1 |  |  | P00274653VS-CW1 | 18IG0111 |  |  | 2018-12-11 |  | 2018-12-28 | VICTORIA DEV. & CONST. SUPPLY CORP.
NC 2018 | TVL | Region VIII | Baybay City | 313316 | Baybay City National Night HS | CITY OF BAYBAY | 5 |  | 2 | 2STY2 ICT LAB. | Batch 3 | 11759253.07 |  |  | Completed | 1 |  |  | P00274654VS-CW1 | 18IG0110 |  |  | 2018-12-11 |  | 2018-12-28 | KAUIE BUILDERS AND CONSTRUCTION SUPPLY
NC 2018 | TVL | Region VIII | Baybay City | 313316 | Baybay City National Night HS | CITY OF BAYBAY | 5 |  | 2 | 2STY2CL SCI. LAB. | Batch 8 Realignment | 12223657.63 |  |  | Reverted | 0 | [10 empty] | realign to Newcon 2020
NC 2018 | TVL | Region VIII | Baybay City | 313323 | Ciabu NHS | CITY OF BAYBAY | 5 | 1 | 4 | 2-UNITS 2STY2 REG. WORKSHOP | Batch 3 | 23351299.62 |  |  | Completed | 1 |  |  | P00274655VS-CW1 | 18IG0106 |  |  | 2018-12-11 |  | 2018-12-27 | RJIR ENTERPRISES
NC 2018 | TVL | Region VIII | Baybay City | 313323 | Ciabu NHS | CITY OF BAYBAY | 5 |  | 2 | 2STY2 ICT LAB. | Batch 3 | 11986837.78 |  |  | Completed | 1 |  |  | P00274656VS-CW1 | 18IG0113 |  |  | 2018-12-11 |  | 2018-12-28 | 5 STAR J ENTERPRISES
NC 2018 | TVL | Region VIII | Baybay City | 313323 | Ciabu NHS | CITY OF BAYBAY | 5 |  | 2 | 2STY2 ICT LAB. | Batch 8 Realignment | 12698779.41 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Baybay City | 344593 | Baybay City Senior HS | CITY OF BAYBAY | 5 | 1 | 10 | 3STY6 REG. WORKSHOPS, 2STY4 REG. WORKSHOP | Batch 3 | 63308914.73 |  |  | Completed | 1 |  |  | P00274657VS-CW1 | 18IG0117 |  |  | 2018-12-11 |  | 2018-12-27 | HIGH INNOVATIVE CONST. & DEV. PHILIPPINES
NC 2018 | TVL | Region VIII | Baybay City | 344593 | Baybay City Senior HS | CITY OF BAYBAY | 5 |  | 2 | 2STY2 ICT LAB. | Batch 3 | 11669253.07 |  |  | Completed | 1 |  |  | P00274658VS-CW1 | 18IG0112 |  |  | 2018-12-11 |  | 2018-12-28 | RJIR ENTERPRISES
NC 2018 | SHS | Region VIII | Biliran | 303328 | Manlabang NHS | CAIBIRAN | 0 | 1 | 8 | 2STY8CL | BATCH 1 | 20723782 |  |  | Completed | 1 |  |  | P00272385VS-CW1
NC 2018 | SHS | Region VIII | Biliran | 303330 | Naval NHS | NAVAL (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 10174820 |  |  | Completed | 1 |  |  | P00272386VS-CW1
NC 2018 | K10 | Region VIII | Biliran | 120761 | Iyosan ES | ALMERIA | 0 | 1 | 2 | 1STY2CL | Batch 3 | 2808296 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Biliran | 120775 | Burabod ES | BILIRAN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 2833659 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Biliran | 120779 | FELIMON NIERRAS MEMORIAL ES | BILIRAN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 2782159 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Biliran | 120792 | LANGGAO ES | CABUCGAYAN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 2795228 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Biliran | 120801 | Cabibihan ES | CAIBIRAN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 2808296 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Biliran | 120802 | Caibiran CS | CAIBIRAN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 2808296 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Biliran | 120803 | Caibiran Sped Center | CAIBIRAN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 2808296 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Biliran | 120819 | Calipayan ES | CULABA | 0 | 1 | 2 | 1STY2CL | Batch 3 | 2966571 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Biliran | 120820 | Culaba CS | CULABA | 0 | 1 | 3 | 1STY3CL | Batch 3 | 4009173 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Biliran | 120829 | Bilwang ES | KAWAYAN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 2808296 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Biliran | 120845 | Villa Cornejo ES | KAWAYAN | 0 | 1 | 3 | 1STY3CL | Batch 3 | 4113173 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Biliran | 120862 | Sabang ES | NAVAL (Capital) | 0 | 1 | 4 | 1STY4CL | Batch 3 | 5465112 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Biliran | 303323 | Cabucgayan NHS | CABUCGAYAN | 0 | 1 | 6 | 3STY6CL | Batch 3 | 15086649 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Biliran | 303324 | Culaba NVS | CULABA | 0 | 1 | 6 | 2STY6CL | Batch 3 | 12368415 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Biliran | 303327 | Lucsoon NHS | NAVAL (Capital) | 0 | 1 | 8 | 2STY8CL | Batch 3 | 18341144.06 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Borongan City | 303500 | E. Samar NCHS | CITY OF BORONGAN (Capital) | 0 | 1 | 12 | 3STY12CL | BATCH 1 | 30420000 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Borongan City | 303500 | E. Samar NCHS | CITY OF BORONGAN (Capital) | 0 |  | 12 | 3STY12CL | BATCH 1 | 30420000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Borongan City | 303500 | E. Samar NCHS | CITY OF BORONGAN (Capital) | 0 |  | 6 | 3STY 6-WORKSHOP BUILDING | BATCH 1 | 30120000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Borongan City | 303500 | E. Samar NCHS | CITY OF BORONGAN (Capital) | 0 |  | 6 | 3STY 6-WORKSHOP BUILDING | BATCH 1 | 30120000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Borongan City | 303525 | Sta. Fe NHS | CITY OF BORONGAN (Capital) | 0 | 1 | 1 | 1STY WORKSHOP BUILDING | BATCH 1 | 3378000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Borongan City | 313515 | E. Samar NCHS - Supt. Fidel E. Anacta, Sr. MHS Annex | CITY OF BORONGAN (Capital) | 0 | 1 | 1 | 1STY WORKSHOP BUILDING | BATCH 1 | 3409000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Calbayog City | 124006 | Calbayog East CES | CALBAYOG CITY | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 14339515.1 |  |  | Completed | 1 |  |  | P00272393VS | 17IJ-0164 | 2017-12-06 | 2017-12-15 | 2017-12-26 | 2018-01-19 | 2018-06-26 | DRS BUILDERS AND SUPPLY
NC 2018 | K10 | Region VIII | Calbayog City | 124009 | Dagum ES | CALBAYOG CITY | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 14839515.1 |  |  | Completed | 1 |  |  | P00272394VS | 17IJ-0168 | 2017-12-06 | 2017-12-15 | 2017-12-26 | 2018-01-19 | 2018-06-26 | ND CARANZO BUILDERS & CONSTRUCTION SUPPLY
NC 2018 | K10 | Region VIII | Calbayog City | 124013 | Guin-on ES School | CALBAYOG CITY | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 12464982.43 |  |  | Completed | 1 |  |  | P00272395VS | 17IJ-0206 | 2017-12-06 | 2017-12-15 | 2017-12-26 | 2018-01-19 | 2018-06-26 | ND CARANZO BUILDERS & CONSTRUCTION SUPPLY
NC 2018 | K10 | Region VIII | Calbayog City | 124014 | Hamorawon ES | CALBAYOG CITY | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 10071467.32 |  |  | Completed | 1 |  |  | P00272396VS | 17IJ-0208 | 2017-12-06 | 2017-12-15 | 2017-12-26 | 2018-01-19 | 2018-06-26 | BV BUILDERS
NC 2018 | K10 | Region VIII | Calbayog City | 124019 | Matobato ES | CALBAYOG CITY | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 14389515.1 |  |  | Completed | 1 |  |  | P00272397VS | 17IJ-0166 | 2017-12-06 | 2017-12-15 | 2017-12-26 | 2018-01-19 | 2018-06-26 | BV BUILDERS
NC 2018 | K10 | Region VIII | Calbayog City | 124128 | Tinambacan CS | CALBAYOG CITY | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 14439515.1 |  |  | Completed | 1 |  |  | P00272398VS | 17IJ-0161 | 2017-12-06 | 2017-12-15 | 2017-12-26 | 2018-01-19 | 2018-06-26 | JFR CONSTRUCTION
NC 2018 | K10 | Region VIII | Calbayog City | 194001 | Calbayog City SPED Center | CALBAYOG CITY | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 14339515.1 |  |  | Completed | 1 |  |  | P00272399VS | 17IJ-0163 | 2017-12-06 | 2017-12-15 | 2017-12-26 | 2018-01-19 | 2018-06-26 | ND CARANZO BUILDERS & CONSTRUCTION SUPPLY
NC 2018 | SHS | Region VIII | Calbayog City | 303644 | Mag-ubay NHS | CALBAYOG CITY | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 12256168.02 |  |  | Completed | 1 |  |  | P00272400VS | 17IJ-0205 | 2017-12-06 | 2017-12-15 | 2017-12-26 | 2018-01-19 | 2018-06-26 | JFR CONSTRUCTION
NC 2018 | SHS | Region VIII | Calbayog City | 303646 | Oquendo NHS | CALBAYOG CITY | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 12406168.02 |  |  | Completed | 1 |  |  | P00272401VS | 17IJ-0192 | 2017-12-06 | 2017-12-15 | 2017-12-26 | 2018-01-19 | 2018-06-26 | DRS BUILDERS AND SUPPLY
NC 2018 | SHS | Region VIII | Calbayog City | 303648 | Pilar National Agricultural High School | CALBAYOG CITY | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 12806168.02 |  |  | Completed | 1 |  |  | P00272402VS | 17J-0201 | 2017-12-06 | 2017-12-15 | 2017-12-26 | 2018-01-19 | 2018-06-26 | DRS BUILDERS AND SUPPLY
NC 2018 | SHS | Region VIII | Calbayog City | 303650 | San Joaquin NHS | CALBAYOG CITY | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 14339515.1 |  |  | Completed | 1 |  |  | P00272403VS | 17IJ-0162 | 2017-12-04 | 2017-12-14 | 2017-12-26 | 2018-01-19 | 2018-06-26 | PABLO S. LABASBAS CONSTRUCTION
NC 2018 | SHS | Region VIII | Calbayog City | 303651 | San Policarpo NHS | CALBAYOG CITY | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 14339515.1 |  |  | Completed | 1 |  |  | P00272404VS | 17IJ-0165 | 2017-12-04 | 2017-12-14 | 2017-12-26 | 2018-01-19 | 2018-06-26 | DRS BUILDERS AND SUPPLY
NC 2018 | SHS | Region VIII | Calbayog City | 303652 | Tarabucan NHS | CALBAYOG CITY | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 12356168.02 |  |  | Completed | 1 |  |  | P00272405VS | 17IJ-0195 | 2017-12-06 | 2017-12-15 | 2017-12-26 | 2018-01-19 | 2018-06-26 | DRS BUILDERS AND SUPPLY
NC 2018 | SHS | Region VIII | Calbayog City | 303653 | Trinidad NHS-Main Campus | CALBAYOG CITY | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 14239515.1 |  |  | Completed | 1 |  |  | P00272406VS | 17IJ-0184 | 2017-12-06 | 2017-12-15 | 2017-12-26 | 2018-01-19 | 2018-06-26 | DRS BUILDERS AND SUPPLY
NC 2018 | K10 | Region VIII | Calbayog City | 313804 | Calbayog City NHS - Bagacay Campus | CALBAYOG CITY | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 12486712.7 |  |  | Completed | 1 |  |  | P00272407VS | 17IJ-0210 | 2017-12-06 | 2017-12-15 | 2017-12-26 | 2018-01-19 | 2018-06-26 | BV BUILDERS
NC 2018 | K10 | Region VIII | Calbayog City | 313807 | Tabawan Integrated School | CALBAYOG CITY | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 12306168.02 |  |  | Completed | 1 |  |  | P00272408VS | 17IJ-0202 | 2017-12-06 | 2017-12-15 | 2017-12-26 | 2018-01-19 | 2018-06-26 | JFR CONSTRUCTION
NC 2018 | SHS | Region VIII | Calbayog City | 313811 | Malaga NHS - Pena I Annex School | CALBAYOG CITY | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 12486712.7 |  |  | Completed | 1 |  |  | P00272409VS | 17IJ-0204 | 2017-12-06 | 2017-12-15 | 2017-12-26 | 2018-01-19 | 2018-06-26 | ND CARANZO BUILDERS & CONSTRUCTION SUPPLY
NC 2018 | K10 | Region VIII | Calbayog City | 124006 | Calbayog East Central ES | CALBAYOG CITY | 1 | 1 | 4 | 2STY4CL | Batch 3 | 11769419.18 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Calbayog City | 124063 | Limarayon Elementary School | CALBAYOG CITY | 1 | 1 | 6 | 2STY6CL | Batch 3 | 18572358.11 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Calbayog City | 124071 | Panlayahan ES | CALBAYOG CITY | 1 | 1 | 4 | 2STY4CL | Batch 3 | 11878763.15 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Calbayog City | 124111 | Sinidman Occ. ES | CALBAYOG CITY | 1 | 1 | 4 | 2STY4CL | Batch 3 | 11828763.15 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Calbayog City | 124115 | Tarabucan Central Elementary School | CALBAYOG CITY | 1 | 1 | 6 | 2STY6CL | Batch 3 | 18752902.79 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Calbayog City | 124123 | Danao I ES | CALBAYOG CITY | 1 | 1 | 6 | 2STY6CL | Batch 3 | 18572358.11 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Calbayog City | 124129 | Bugtong ES | CALBAYOG CITY | 1 | 1 | 4 | 2STY4CL | Batch 3 | 12378763.15 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Calbayog City | 124141 | San Joaquin Central Elementary School | CALBAYOG CITY | 1 | 1 | 6 | 2STY6CL | Batch 3 | 18572358.11 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Calbayog City | 303645 | Malaga National High School | CALBAYOG CITY | 1 | 1 | 6 | 2STY6CL | Batch 3 | 18702902.79 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Calbayog City | 303649 | R. Lentejas Mem. School Of Fisheries | CALBAYOG CITY | 1 | 1 | 4 | 2STY4CL | Batch 3 | 11869419.18 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Calbayog City | 303651 | San Policarpo National High School | CALBAYOG CITY | 1 | 1 | 6 | 2STY6CL | Batch 3 | 18552902.79 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Calbayog City | 313801 | Calbayog City NHS | CALBAYOG CITY | 1 | 1 | 4 | 2STY4CL | Batch 3 | 11678763.15 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Calbayog City | 313811 | Malaga NHS - Pena I Annex School | CALBAYOG CITY | 1 | 1 | 4 | 2STY4CL | Batch 3 | 12301306.09 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Calbayog City | 344634 | Calbayog Arts and Design School of Eastern Visayas | CALBAYOG CITY | 1 | 1 | 6 | 3STY6CL | Batch 3 | 18522358.11 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Catbalogan City | 123416 | Catbalogan V CES (Mercedes ES) | CITY OF CATBALOGAN (Capital) | 2 | 1 | 8 | 4STY8CL | Batch 3 | 17674357.79 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Catbalogan City | 303604 | Eastern Visayas Regional Science HS | CITY OF CATBALOGAN (Capital) | 2 | 1 | 8 | 4STY8CL | Batch 3 | 17845953.5 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Catbalogan City | 303620 | Samar National School | CITY OF CATBALOGAN (Capital) | 2 | 1 | 20 | 4STY20CL | Batch 3 | 41408409.74 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Catbalogan City | 303620 | Samar National School | CITY OF CATBALOGAN (Capital) | 2 |  | 8 | 4STY8CL | Batch 3 | 17159570.67 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Catbalogan City | 303620 | Samar National School | CITY OF CATBALOGAN (Capital) | 2 |  | 24 | 2-UNITS 4STY12CL | Batch 3 | 63299579.44 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Catbalogan City | 303620 | Samar National School | CITY OF CATBALOGAN (Capital) | 2 |  | 16 | 4STY16CL | Batch 3 | 36910737.96 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Catbalogan City | 303623 | Silanga NHS | CITY OF CATBALOGAN (Capital) | 2 | 1 | 20 | 4STY20CL | Batch 3 | 43064746.13 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Catbalogan City | 313701 | Catbalogan National Comprehensive HS | CITY OF CATBALOGAN (Capital) | 2 | 1 | 8 | 4STY8CL | Batch 3 | 17674357.79 |  |  | Terminated | 0 | [9 empty] | Rianne Construction | TERMINATED BY CONVENIENCE due to non-resolution of dispute in lot ownership between SSU & CNCHS
NC 2018 | SHS | Region VIII | Catbalogan City | 313701 | Catbalogan National Comprehensive HS | CITY OF CATBALOGAN (Capital) | 2 |  | 12 | 4STY12CL | Batch 3 | 32599283.41 |  |  | Terminated | 0 | [9 empty] | Rianne Construction | TERMINATED BY CONVENIENCE due to non-resolution of dispute in lot ownership between SSU & CNCHS
NC 2018 | SHS | Region VIII | Catbalogan City | 313706 | Pangdan NHS | CITY OF CATBALOGAN (Capital) | 2 | 1 | 8 | 4STY8CL | Batch 3 | 18189144.91 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122328 | Bigo ES | ARTECHE | 0 | 1 | 2 | 1STY2CL | BATCH 1 | 3578000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122338 | Tawagan ES | ARTECHE | 0 | 1 | 2 | 1STY2CL | BATCH 1 | 3578000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122344 | Bolusao ES | LAWAAN | 0 | 1 | 2 | 1STY2CL | BATCH 1 | 3075000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122512 | Malabag ES | GIPORLOS | 0 | 1 | 2 | 1STY2CL | BATCH 1 | 3010000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122539 | Cabunga-an PS | MERCEDES | 0 | 1 | 2 | 1STY2CL | BATCH 1 | 3072000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122575 | Jipapad CS | JIPAPAD | 0 | 1 | 2 | 1STY2CL | BATCH 1 | 3909000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122575 | Jipapad CS | JIPAPAD | 0 |  | 2 | 1STY2CL | BATCH 1 | 3909000 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Eastern Samar | 122637 | Dao Integrated School | ORAS | 0 | 1 | 2 | 1STY2CL | BATCH 1 | 3040000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122646 | Sabang ES | ORAS | 0 | 1 | 2 | 1STY2CL | BATCH 1 | 3040000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122647 | San Eduardo ES | ORAS | 0 | 1 | 2 | 1STY2CL | BATCH 1 | 3090000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122686 | San Pedro ES | QUINAPONDAN | 0 | 1 | 2 | 1STY2CL | BATCH 1 | 2980000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122705 | Asgad ES | SALCEDO | 0 | 1 | 2 | 1STY2CL | BATCH 1 | 3084000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122733 | Alugan ES | SAN POLICARPO | 0 | 1 | 2 | 1STY2CL | BATCH 1 | 3075000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Eastern Samar | 303494 | Arteche NHS | ARTECHE | 0 | 1 | 2 | 2STY WORKSHOP BUILDING | BATCH 1 | 9892000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Eastern Samar | 303494 | Arteche NHS | ARTECHE | 0 |  | 4 | 2-UNITS 2STY WORKSHOP BUILDING | BATCH 1 | 19700000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Eastern Samar | 303494 | Arteche NHS | ARTECHE | 0 |  | 6 | 3-UNITS 2STY WORKSHOP BUILDING | BATCH 1 | 29450000 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Eastern Samar | 303494 | Arteche NHS | ARTECHE | 0 |  | 6 | 3STY6CL | BATCH 1 | 14453000 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Eastern Samar | 303494 | Arteche NHS | ARTECHE | 0 |  | 12 | 3STY12CL | BATCH 1 | 30569000 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Eastern Samar | 303499 | Dolores NHS | DOLORES | 0 | 1 | 2 | 1STY2CL | BATCH 1 | 2983000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Eastern Samar | 303501 | Gen. MacArthur National Agricultural School | GENERAL MACARTHUR | 0 | 1 | 1 | 1STY WORKSHOP BUILDING | BATCH 1 | 3414000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Eastern Samar | 303502 | Giporlos National Trade School | GIPORLOS | 0 | 1 | 1 | 1STY WORKSHOP BUILDING | BATCH 1 | 3566000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Eastern Samar | 303508 | Homonhon NHS | GUIUAN | 0 | 1 | 2 | 2-UNITS 1STY WORKSHOP BUILDING | BATCH 1 | 9314000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Eastern Samar | 303510 | Jipapad NHS | JIPAPAD | 0 | 1 | 1 | 1STY WORKSHOP BUILDING | BATCH 1 | 4824000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Eastern Samar | 303512 | Lawaan National School of Craftsmanship and Home Industries | LAWAAN | 0 | 1 | 9 | 9-UNITS 1STY WORKSHOP BUILDING | BATCH 1 | 32823000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Eastern Samar | 303513 | Llorente NHS | LLORENTE | 0 | 1 | 1 | 1STY WORKSHOP BUILDING | BATCH 1 | 3394000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Eastern Samar | 303513 | Llorente NHS | LLORENTE | 0 |  | 1 | 1STY WORKSHOP BUILDING | BATCH 1 | 3337000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Eastern Samar | 303513 | Llorente NHS | LLORENTE | 0 |  | 1 | 1STY WORKSHOP BUILDING | BATCH 1 | 3394000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Eastern Samar | 303515 | Maslog NHS | MASLOG | 0 | 1 | 2 | 2-UNITS 1STY WORKSHOP BUILDING | BATCH 1 | 9216400 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Eastern Samar | 303516 | Matarinao School of Fisheries | SALCEDO | 0 | 1 | 1 | 1STY WORKSHOP BUILDING | BATCH 1 | 3521000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Eastern Samar | 303518 | Mercedes NHS | MERCEDES | 0 | 1 | 2 | 2-UNITS 1STY WORKSHOP BUILDING | BATCH 1 | 7424000 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Eastern Samar | 303520 | Oras National High School | ORAS | 0 | 1 | 8 | 2STY8CL | BATCH 1 | 17210000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Eastern Samar | 303523 | Samar National Pilot Opportunity School of Agriculture | SAN POLICARPO | 0 | 1 | 5 | 5-UNITS 1STY WORKSHOP BUILDING | BATCH 1 | 17120000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Eastern Samar | 303527 | Sulat National High School | SULAT | 0 | 1 | 1 | 1STY WORKSHOP BUILDING | BATCH 1 | 3449000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Eastern Samar | 303529 | Taft National High School | TAFT | 0 | 1 | 7 | 7-UNITS 1STY WORKSHOP BUILDING | BATCH 1 | 23870000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Eastern Samar | 313501 | Can-avid NHS | CAN-AVID | 0 | 1 | 2 | 2-UNITS 1STY WORKSHOP BUILDING | BATCH 1 | 6757000 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Eastern Samar | 313502 | Southern Samar National Comprehensive High School | BALANGIGA | 0 | 1 | 3 | 1STY3CL | BATCH 1 | 4461000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 313507 | Nena NHS (Nena SAT) | SAN JULIAN | 0 | 1 | 2 | 1STY2CL | BATCH 1 | 2941000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Eastern Samar | 313509 | Salcedo Vocational High School | SALCEDO | 0 | 1 | 2 | 2-UNITS 1STY WORKSHOP BUILDING | BATCH 1 | 7862000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122327 | Beri ES | ARTECHE | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5106000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122335 | Concepcion ES | ARTECHE | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5213000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122335 | Concepcion ES | ARTECHE | 0 |  | 2 | 1STY2CL | Batch 3 | 5213000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122421 | Malogo ES | CAN-AVID | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4496000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122435 | Malaintos ES | DOLORES | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4399000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122492 | Padang ES | HERNANI | 0 | 1 | 3 | 1STY3CL | Batch 3 | 5733000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122505 | Vigan ES | GENERAL MACARTHUR | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4356000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122509 | Gigoso ES | GIPORLOS | 0 | 1 | 3 | 1STY3CL | Batch 3 | 5883000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122509 | Gigoso ES | GIPORLOS | 0 |  | 3 | 1STY3CL | Batch 3 | 5883000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122533 | Bagua ES | GUIUAN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4426000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122543 | Mayana ES | GUIUAN | 0 | 1 | 3 | 1STY3CL | Batch 3 | 5960000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122554 | Tubabao ES | GUIUAN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5184000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122560 | Cantahay ES | GUIUAN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4426000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122568 | Sulangan Central ES | GUIUAN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4485000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122583 | Antipolo ES | LLORENTE | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4278000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122585 | Bacayawan ES | LLORENTE | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4245000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122587 | Barobo ES | LLORENTE | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4581000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122588 | Borak ES | LLORENTE | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4994000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122589 | Can-ato ES | LLORENTE | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4625000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122590 | Candoros ES | LLORENTE | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4799000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122591 | Canliwag ES | LLORENTE | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4266000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122592 | Cantomco Elementary School | LLORENTE | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4532000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122593 | Hugpa Primary School | LLORENTE | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4256000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122595 | Maca-anga ES | LLORENTE | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4710000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122596 | Magtino ES | LLORENTE | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5047000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122597 | Minaanod ES | LLORENTE | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4724000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122598 | Naubay ES | LLORENTE | 0 | 1 | 3 | 1STY3CL | Batch 3 | 5687000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122599 | Piliw ES | LLORENTE | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4422000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122601 | San Miguel ES | LLORENTE | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4294000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122602 | San Roque ES | LLORENTE | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4365000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122605 | Waso ES | LLORENTE | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4310000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122611 | Camada ES | MAYDOLONG | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4228000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122612 | Campakirit ES | MAYDOLONG | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4238000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122613 | Canloterio ES | MAYDOLONG | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4414000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122617 | Guindalitan ES | MAYDOLONG | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4350000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122620 | Lapgap ES | MAYDOLONG | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4439000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122622 | Malobago ES | MAYDOLONG | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4666000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122628 | Patag ES | MAYDOLONG | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4953000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122636 | Dalid ES | ORAS | 0 | 1 | 3 | 1STY3CL | Batch 3 | 5874000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122645 | Pangudtan ES | ORAS | 0 | 1 | 3 | 1STY3CL | Batch 3 | 5903000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122648 | Saugan ES | ORAS | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4458000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122669 | Rizal ES | ORAS | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5212000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122703 | Talangdawan ES | SALCEDO | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4461000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 122734 | Bahay ES | SAN POLICARPO | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4456000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 303493 | Alugan National School of Craftsmanship and Home Industries | SAN POLICARPO | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4571000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 303493 | Alugan National School of Craftsmanship and Home Industries | SAN POLICARPO | 0 |  | 2 | 1STY2CL | Batch 3 | 4571000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 303497 | Bolusao NHS | LAWAAN | 0 | 1 | 3 | 1STY3CL | Batch 3 | 5948000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 303497 | Bolusao NHS | LAWAAN | 0 |  | 2 | 1STY2CL | Batch 3 | 4464000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 303509 | Homonhon NHS - Sulangan Annex | GUIUAN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4485000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 303528 | Sto. Nino NHS | SULAT | 0 | 1 | 3 | 1STY3CL | Batch 3 | 5808000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 313513 | Barobo NHS | LLORENTE | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4581000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Eastern Samar | 313521 | Dapdap National Technical Vocational HS | DOLORES | 0 | 1 | 1 | 1STY WORKSHOP BLDG. | Batch 3 | 3996000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Eastern Samar | 313521 | Dapdap National Technical Vocational HS | DOLORES | 0 |  | 1 | 1STY WORKSHOP BLDG. | Batch 3 | 3996000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 313523 | Lapgap NHS | MAYDOLONG | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4278000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 500504 | San Vicente Integrated School | SULAT | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4852000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Eastern Samar | 500823 | Taytay Integrated School | GUIUAN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4444000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121026 | Barugo I CS | BARUGO | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12932067 |  |  | Completed | 1 |  |  | P00272448VS-CW1
NC 2018 | K10 | Region VIII | Leyte | 121344 | Dulag CS | DULAG | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12932067 |  |  | Completed | 1 |  |  | P00272449VS-CW1
NC 2018 | K10 | Region VIII | Leyte | 121627 | Sta. Isabel ES | MACARTHUR | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9611795 |  |  | Completed | 1 |  |  | P00272450VS-CW1
NC 2018 | SHS | Region VIII | Leyte | 303341 | Asuncion S. Melgar NHS | CAPOOCAN | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9611795 |  |  | Completed | 1 |  |  | P00272451VS-CW1
NC 2018 | SHS | Region VIII | Leyte | 303342 | Atty. Roque A. Marcos Memorial School (La Paz NHS) | LAPAZ | 2 | 1 | 9 | 3STY9CL | BATCH 1 | 25458127.16 |  |  | Completed | 1 |  |  | P00272452VS-CW1
NC 2018 | SHS | Region VIII | Leyte | 303353 | Burauen Comprehensive NHS | BURAUEN | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 17687241 |  |  | Completed | 1 |  |  | P00272453VS-CW1
NC 2018 | SHS | Region VIII | Leyte | 303354 | Burauen NHS | BURAUEN | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12932067 |  |  | Completed | 1 |  |  | P00272454VS-CW1
NC 2018 | SHS | Region VIII | Leyte | 303355 | Cabacungan NHS | DULAG | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12932067 |  |  | Completed | 1 |  |  | P00272455VS-CW1
NC 2018 | SHS | Region VIII | Leyte | 303362 | Carigara National Vocational School | CARIGARA | 2 | 1 | 10 | 2STY4CL & 2STY6CL | BATCH 1 | 23546958 |  |  | Completed | 1 |  |  | P00272456VS-CW1
NC 2018 | SHS | Region VIII | Leyte | 303367 | Don Mariano Salvacion Memorial NHS | CAPOOCAN | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9611795 |  |  | Completed | 1 |  |  | P00272457VS-CW1
NC 2018 | SHS | Region VIII | Leyte | 303371 | Granja-Kalinawan NHS | JARO | 2 | 1 | 18 | 3-UNITS 2STY6CL | BATCH 1 | 38796201 |  |  | Completed | 1 |  |  | P00272458VS-CW1
NC 2018 | SHS | Region VIII | Leyte | 303380 | Juan Villablanca Memorial High School | PASTRANA | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12932067 |  |  | Completed | 1 |  |  | P00272459VS-CW1
NC 2018 | SHS | Region VIII | Leyte | 303382 | Justimbaste-Remandaban NHS | TABONTABON | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9642287 |  |  | Completed | 1 |  |  | P00272460VS-CW1
NC 2018 | SHS | Region VIII | Leyte | 303397 | Macarthur NHS | MACARTHUR | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 17797673 |  |  | Completed | 1 |  |  | P00272461VS-CW1
NC 2018 | SHS | Region VIII | Leyte | 303407 | Mayorga NHS | MAYORGA | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 17687241 |  |  | Completed | 1 |  |  | P00272462VS-CW1
NC 2018 | SHS | Region VIII | Leyte | 313304 | Agapito Amado Memorial NHS | JARO | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9611795 |  |  | Completed | 1 |  |  | P00272463VS-CW1
NC 2018 | SHS | Region VIII | Leyte | 313307 | Jugaban NHS | CARIGARA | 2 | 1 | 8 | 2-UNITS 2STY4CL | BATCH 1 | 19404810 |  |  | Completed | 1 |  |  | P00272464VS-CW1
NC 2018 | SHS | Region VIII | Leyte | 313324 | Barugo NHS | BARUGO | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9642287 |  |  | Completed | 1 |  |  | P00272465VS-CW1
NC 2018 | SHS | Region VIII | Leyte | 313325 | Hibunauan NHS | BURAUEN | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9611795 |  |  | Completed | 1 |  |  | P00272466VS-CW1
NC 2018 | SHS | Region VIII | Leyte | 313330 | Manaybanay NHS | PASTRANA | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9611795 |  |  | Completed | 1 |  |  | P00272468VS-CW1
NC 2018 | SHS | Region VIII | Leyte | 344690 | Pinamopoan SeniorHigh School | CAPOOCAN | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12932067 |  |  | Completed | 1 |  |  | P00272467VS-CW1
NC 2018 | K10 | Region VIII | Leyte | 344695 | Patoc NHS | DAGAMI | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12932067 |  |  | Completed | 1 |  |  | P00272469VS-CW1
NC 2018 | SHS | Region VIII | Leyte | 344725 | Julita Senior High School | JULITA | 2 | 1 | 6 | 3STY6CL | BATCH 1 | 15229140.66 |  |  | Completed | 1 |  |  | P00272470VS-CW1
NC 2018 | SHS | Region VIII | Leyte | 344725 | Julita Senior High School | JULITA | 2 |  | 6 | 3STY6CL | BATCH 1 | 15229140.66 |  |  | Completed | 1 |  |  | P00272471VS-CW1
NC 2018 | K10 | Region VIII | Leyte | 121005 | Babatngon CS | BABATNGON | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4208847.06 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121007 | Bagong Silang ES | BABATNGON | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4103303.24 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121008 | Biasong ES | BABATNGON | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4251401.17 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121009 | Gov. E. Jaro ES | BABATNGON | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4051050.7 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121011 | Lukay Primary School | BABATNGON | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3917644.48 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121012 | Magcasuang ES | BABATNGON | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3907862.65 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121013 | Malibago ES | BABATNGON | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3917979.15 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121015 | Pagsulhugon ES | BABATNGON | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4090636.39 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121017 | Rizal ES | BABATNGON | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4083852.19 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121018 | San Agustin ES | BABATNGON | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3951323.33 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121019 | San Ricardo ES | BABATNGON | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4083852.19 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121021 | Taguite ES | BABATNGON | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3898028.71 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121740 | Castilla ElementarySchool | PALO | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3894095.14 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121741 | Gacao ES | PALO | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3969031.14 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121745 | San Agustin ES | PALO | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3893111.75 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121749 | Baras ES | PALO | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3953862.89 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121753 | Candahug ES | PALO | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4074150.75 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121759 | Naga-Naga ES | PALO | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3896580.42 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121762 | San Fernando ES | PALO | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3893111.75 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121851 | Cabatianuhan ES | SAN MIGUEL | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3916661.1 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121858 | Lukay ES | SAN MIGUEL | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4171285.25 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121861 | Mawodpawod ES | SAN MIGUEL | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3893111.75 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121865 | San Miguel CS | SAN MIGUEL | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3888805.17 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121867 | Sta. Cruz ES | SAN MIGUEL | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4048313.34 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121949 | Capangihan ES | TOLOSA | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3888433.52 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121950 | Daniel Z. Romualdez Memorial ES | TOLOSA | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4085346.47 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121951 | Malbog ES | TOLOSA | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3886327.55 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121952 | Olot ES | TOLOSA | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3894095.14 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121953 | Opong ES | TOLOSA | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4140495.06 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121956 | Tanghas ES | TOLOSA | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4034860.83 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121957 | Telegrafo ES | TOLOSA | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4090578.35 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 191502 | Cabadsan ES | ALANGALANG | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3917590.2 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 191526 | Cahumayhumayan ES | TANAUAN | 1 | 1 | 3 | 1STY3CL W/ TOILET ATTACHED | Batch 3 | 5917601.97 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Leyte | 303336 | Alangalang NHS | ALANGALANG | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4223060.77 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Leyte | 303339 | Anahaway NHS | PALO | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3886327.55 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Leyte | 303343 | Juan S. Tismo NHS (Babatngon NHS) | BABATNGON | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4223080.77 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Leyte | 303386 | Kiling NHS | TANAUAN | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3893111.75 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Leyte | 303391 | Daniel Z. Romualdez State Comprehensive School of Fisheries | TOLOSA | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3980126.74 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Leyte | 303424 | San Joaquin NHS | PALO | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4090636.39 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Leyte | 303440 | Tolosa NHS | TOLOSA | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3897221.42 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Leyte | 313398 | Borseth NHS | ALANGALANG | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3965589.94 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Leyte | 303417 | Patoc National High School | DAGAMI | 2 | 1 | 4 | 2STY4CL | Batch 3 | 14043353.98 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121608 | Tag-abaca ES | LEYTE | 3 | 1 | 6 | 2STY6CL | Batch 3 | 13000925.24 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121834 | Daja ES School | SAN ISIDRO | 3 | 1 | 4 | 2STY4CL | Batch 3 | 9731060.78 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121836 | Hda. Maria ES | SAN ISIDRO | 3 | 1 | 4 | 2STY4CL | Batch 3 | 9918924.72 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121845 | Sangabon ES School | SAN ISIDRO | 3 | 1 | 4 | 2STY4CL | Batch 3 | 9731060.78 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121846 | Taglawigan ES | SAN ISIDRO | 3 | 1 | 4 | 2STY4CL | Batch 3 | 10012856.69 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Leyte | 303387 | Leyte Agro-Industrial School | LEYTE | 3 | 1 | 6 | 2STY6CL | Batch 3 | 12878535.48 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Leyte | 303390 | Leyte NHS | LEYTE | 3 | 1 | 6 | 2STY6CL | Batch 3 | 12878535.48 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Leyte | 303411 | Muertegui NHS | SAN ISIDRO | 3 | 1 | 6 | 2STY6CL | Batch 3 | 12888535.48 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Leyte | 303416 | Pastor Salazar NHS | TABANGO | 3 | 1 | 4 | 2STY4CL | Batch 3 | 9918924.72 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Leyte | 303442 | Villaba NCHS | VILLABA | 3 | 1 | 6 | 3STY6CL | Batch 3 | 15153550.49 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Leyte | 313308 | Juan V. Delantar NHS | LEYTE | 3 | 1 | 4 | 2STY4CL | Batch 3 | 10012856.69 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Leyte | 313317 | Felix Caneja Lafuente NHS | CALUBIAN | 3 | 1 | 4 | 2STY4CL | Batch 3 | 10200720.63 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 120984 | Albuera North CS | ALBUERA | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3820000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 120986 | Cambalading ES | ALBUERA | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3820000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 120990 | Seguinon ES | ALBUERA | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3820000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 120991 | Sherwood ES | ALBUERA | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3870000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 120992 | Soob ES | ALBUERA | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3900000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 120994 | Talisayan ES | ALBUERA | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3870000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121002 | San Pedro ES | ALBUERA | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3820000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121671 | San Vicente Elementary School | MATAG-OB | 4 | 1 | 3 | 1STY3CL | Batch 3 | 7020000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121721 | Casilda ES | MERIDA | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3870000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121722 | Lamanoc ES | MERIDA | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3820000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121723 | Libas ES | MERIDA | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3870000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121728 | Mahayag Primary School | MERIDA | 4 | 1 | 2 | 1STY2CL | Batch 3 | 4320000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121730 | Merida CS | MERIDA | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3870000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121731 | Minesite ES | MERIDA | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3920000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121732 | Puerto Bello ES | MERIDA | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3900000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121765 | Caduhaan ES | PALOMPON | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3920000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121766 | Cambacbac ES | PALOMPON | 4 | 1 | 2 | 1STY2CL | Batch 3 | 4120000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121770 | Lomonon ES | PALOMPON | 4 | 1 | 2 | 1STY2CL | Batch 3 | 4020000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121773 | Palompon North CS | PALOMPON | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3820000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121774 | Sabang ES | PALOMPON | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3820000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121778 | Santiago ES | PALOMPON | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3900000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121781 | Tinabilan ES | PALOMPON | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3870000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121783 | Tinubdan ES | PALOMPON | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3870000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121788 | Cangcosme ES | PALOMPON | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3970000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121790 | Canipaan ES | PALOMPON | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3970000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121792 | Cantuhaon ES | PALOMPON | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3970000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121795 | Duljugan ES | PALOMPON | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3970000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121797 | Magsaysay ES | PALOMPON | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3870000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 121800 | Parrilla ES | PALOMPON | 4 | 1 | 2 | 1STY2CL | Batch 3 | 4020000 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Leyte | 303368 | Dr. Geronimo B. Zaldivar Memorial School of Fisheries | ALBUERA | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3820000 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Leyte | 303396 | Lomonon NHS | PALOMPON | 4 | 1 | 2 | 1STY2CL | Batch 3 | 4020000 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Leyte | 303438 | Tinabilan NHS | PALOMPON | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3820000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte | 313339 | Sta. Rosa National High School | MATAG-OB | 4 | 1 | 4 | 1STY4CL | Batch 3 | 8250000 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Leyte |  | Bilwang NHS | ISABEL | 4 | 1 | 6 | 2STY6CL | Batch 3 | 18270000 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Leyte | 303338 | Anahawan National High School | BATO | 5 | 1 | 2 | 2STY2 ICT LAB. | Batch 8 Realignment | 12711276.75 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Leyte | 303335 | Abuyog National High School | ABUYOG | 5 | 1 | 2 | 2STY2CL SCI. LAB. | Batch 8 Realignment | 12732877.05 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Leyte | 303335 | Abuyog National High School | ABUYOG | 5 | 1 | 2 | 2STY2 ICT LAB. | Batch 8 Realignment | 11772992.55 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Leyte | 303346 | Bato National High School | BATO | 5 | 1 | 2 | 2STY2 ICT LAB. | Batch 8 Realignment | 12679905.88 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Leyte | 303370 | Esperanza National High School | MATALOM | 5 | 1 | 2 | 2STY2CL SCI. LAB. | Batch 8 Realignment | 12428657.63 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Leyte | 303374 | Hilongos National Vocational School | HILONGOS | 5 |  | 2 | 2STY2CL SCI. LAB. | Batch 8 Realignment | 12495414.61 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Leyte | 303374 | Hilongos National Vocational School | HILONGOS | 5 |  | 2 | 2STY2 ICT LAB. | Batch 8 Realignment | 12584100.38 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Leyte | 303375 | Hindang National High School | HINDANG | 5 | 1 | 2 | 2STY2CL SCI. LAB. | Batch 8 Realignment | 12680100.6 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Leyte | 303375 | Hindang National High School | HINDANG | 5 |  | 6 | 2STY6CL | Batch 8 Realignment | 16188986.74 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Leyte | 303377 | Inopacan National High School | INOPACAN | 5 | 1 | 2 | 2STY2CL SCI. LAB. | Batch 8 Realignment | 13001260.54 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Leyte | 303377 | Inopacan National High School | INOPACAN | 5 |  | 2 | 2STY2 ICT LAB. | Batch 8 Realignment | 13069936.21 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Leyte | 303379 | Javier National High School | JAVIER (BUGHO) | 5 |  | 2 | 2STY2CL SCI. LAB. | Batch 8 Realignment | 11749164.69 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Leyte | 303379 | Javier National High School | JAVIER (BUGHO) | 5 |  | 2 | 2STY2 ICT LAB. | Batch 8 Realignment | 11817840.37 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Leyte | 303379 | Javier National High School | JAVIER (BUGHO) | 5 |  | 2 | 2STY2CL REGULAR WORKSHOP | Batch 8 Realignment | 11300383.13 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Leyte | 303385 | Kikilo National High School | ABUYOG | 5 | 1 | 2 | 2STY2CL SCI. LAB. | Batch 8 Realignment | 12606367.69 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Leyte | 303398 | Mahaplag National High School | MAHAPLAG | 5 | 1 | 2 | 2STY2CL SCI. LAB. | Batch 8 Realignment | 12267909.73 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Leyte | 303398 | Mahaplag National High School | MAHAPLAG | 5 |  | 2 | 2STY2 ICT LAB. | Batch 8 Realignment | 12354042.53 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Leyte | 303405 | Matalom National High School | MATALOM | 5 | 1 | 2 | 2STY2CL SCI. LAB. | Batch 8 Realignment | 12386535.68 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Leyte | 303405 | Matalom National High School | MATALOM | 5 |  | 2 | 2STY2 ICT LAB. | Batch 8 Realignment | 12455211.36 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Leyte | 313337 | Sta. Paz Integrated School | MATALOM | 5 | 1 | 2 | 2STY2CL SCI. LAB. | Batch 8 Realignment | 12213657.63 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Maasin City | 303464 | Libhu NHS | CITY OF MAASIN (Capital) | 0 | 1 | 1 | UNIQUE WORKSHOP | BATCH 1 | 5452590.36 |  | 5371390.7 | Completed | 1 | 2018-12-17 |  | P00272472VS-CW1 | 18-IL-0113 | 2018-07-13 | 2018-07-19 | 2018-07-31 | 2018-06-08 | 2018-09-08 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2018 | TVL | Region VIII | Maasin City | 303464 | Libhu NHS | CITY OF MAASIN (Capital) | 0 |  | 1 | UNIQUE WORKSHOP | BATCH 1 | 5452590.36 |  | 5366466.12 | Completed | 1 | 2018-12-17 |  | P00272473VS-CW1 | 18-IL-0114 | 2018-07-13 | 2018-07-19 | 2018-07-31 | 2018-06-08 | 2018-09-08 | JQD CONSTRUCTION & GENERAL SERVICES
NC 2018 | TVL | Region VIII | Maasin City | 303464 | Libhu NHS | CITY OF MAASIN (Capital) | 0 |  | 1 | REGULAR WORKSHOP | BATCH 1 | 3002395.43 |  | 2961041.2 | Completed | 1 | 2018-12-11 |  | P00272474VS-CW1 | 18-IL-0112 | 2018-07-13 | 2018-07-19 | 2018-07-31 | 2018-06-08 | 2018-09-08 | A.C. RIVERO DEVT. CORPORATION
NC 2018 | K10 | Region VIII | Maasin City | 238003 | Maasin City SPED Center | CITY OF MAASIN (Capital) | 0 | 1 | 12 | 3STY12CL | Batch 3 | 40806593.36 |  | 40525369.5 | Completed | 1 | 2019-11-27 |  | P00274857VS-CW1 | 18-IL-0165 |  | 2018-11-05 | 2018-11-16 |  |  | JQD CONSTRUCTION & GENERAL SERVICES
NC 2018 | TVL | Region VIII | Northern Samar | 303540 | Capul Agro-Industrial School | CAPUL | 1 | 1 | 2 | 2STY2 ICT LAB. | Batch 3 | 12797069.7 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303541 | Catarman National High School | CATARMAN (Capital) | 1 | 1 | 2 | 2STY2 ICT LAB. | Batch 3 | 12200049.12 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303541 | Catarman National High School | CATARMAN (Capital) | 1 |  | 2 | 2STY2 SCI. LAB. | Batch 3 | 12310887.6 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303541 | Catarman National High School | CATARMAN (Capital) | 1 |  | 2 | 2STY REGULAR WORKSHOP | Batch 3 | 11668040.71 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Northern Samar | 303541 | Catarman National High School | CATARMAN (Capital) | 1 | 1 | 4 | 2STY4CL | Batch 3 | 11488022.91 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Northern Samar | 303541 | Catarman National High School | CATARMAN (Capital) | 1 |  | 15 | 3STY15CL | Batch 3 | 41038497.98 |  |  | Terminated | 1 | [9 empty] | Norsam Builders and Construction Supply | Slippage: with obstructing structures in project sites; negotiation on removing obstruction (as per DPWH); TERMINATION ON PROCESS
NC 2018 | TVL | Region VIII | Northern Samar | 303543 | Galutan NHS | CATARMAN (Capital) | 1 | 1 | 4 | 4STY4 (2 ICT & 2 SCI. LAB.) | Batch 3 | 23699389.37 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303548 | Eladio T. Balite Memorial School of Fisheries | BOBON | 1 | 1 | 4 | 4STY4 (2 ICT & 2 SCI. LAB.) | Batch 3 | 20842545.57 |  |  | Terminated | 0 | [9 empty] | Steven Construction and Supply/ On Time Builders Inc (JV) | For termination due to slow performance of contractor; on DEO for consolidation and review; TERMINATION ON PROCESS
NC 2018 | TVL | Region VIII | Northern Samar | 303548 | Eladio T. Balite Memorial School of Fisheries | BOBON | 1 |  | 4 | 4STY4 REGULAR WORKSHOP | Batch 3 | 23239003.48 |  |  | Terminated | 0 | [9 empty] | Steven Construction and Supply/ On Time Builders Inc (JV) | For termination due to slow performance of contractor; on DEO for consolidation and review; TERMINATION ON PROCESS
NC 2018 | TVL | Region VIII | Northern Samar | 303550 | Francisca Dominice NHS | MONDRAGON | 1 | 1 | 4 | 2STY4 (2 ICT & 2 SCI. LAB.) | Batch 3 | 23995846.89 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303561 | Basilio B. Chan Mem. Agricultural and Industrial Sch. | LAVEZARES | 1 | 1 | 4 | 4STY4 (2 ICT & 2 SCI. LAB.) | Batch 3 | 22819399.15 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Northern Samar | 303563 | Lope De Vega NHS | LOPE DE VEGA | 1 | 1 | 4 | 2STY4CL | Batch 3 | 12039551.12 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303566 | Mondragon Agro-Ind'L HS | MONDRAGON | 1 | 1 | 2 | 2STY2 ICT LAB. | Batch 3 | 13200878.66 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303566 | Mondragon Agro-Ind'L HS | MONDRAGON | 1 |  | 2 | 2STY2 SCI. LAB. | Batch 3 | 13311717.14 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303568 | Nenita National High School | MONDRAGON | 1 | 1 | 4 | 2STY4 (2 ICT & 2 SCI. LAB.) | Batch 3 | 26108326.9 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303573 | Rosario National High School | ROSARIO | 1 | 1 | 4 | 4STY4 (2 ICT & 2 SCI. LAB.) | Batch 3 | 22973051.51 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303580 | San Jose Technical HS | SAN JOSE | 1 | 1 | 4 | 4STY4 (2 ICT & 2 SCI. LAB.) | Batch 3 | 24000776.87 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 313605 | Leonardo M. Amigo High School | MONDRAGON | 1 | 1 | 2 | 2STY2 ICT LAB. | Batch 3 | 13241572.41 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 313623 | GUILLERMO C. ADRIATICO, SR. NATIONAL HIGH SCHOOL | LAVEZARES | 1 | 1 | 2 | 2STY2 ICT LAB. | Batch 3 | 12373022.53 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 344946 | Lope de Vega NHS (Stand Alone) | LOPE DE VEGA | 1 | 1 | 2 | 2STY2 ICT LAB. | Batch 3 | 12105330.94 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 344946 | Lope de Vega NHS (Stand Alone) | LOPE DE VEGA | 1 |  | 3 | 3STY3 REGULAR WORKSHOP | Batch 3 | 17871096.35 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 344947 | Victoria SHS (Stand Alone) | VICTORIA | 1 | 1 | 4 | 4STY REGULAR WORKSHOP | Batch 3 | 21410667.13 |  |  | Terminated | 0 | [9 empty] | Steven Construction and Supply/ On Time Builders Inc (JV) | Slippage Unworkable weather and slow performance of contractor (as per DPWH); TERMINATION ON PROCESS
NC 2018 | TVL | Region VIII | Northern Samar | 344947 | Victoria SHS (Stand Alone) | VICTORIA | 1 |  | 4 | 4STY4 (2 ICT & 2 SCI. LAB.) | Batch 3 | 20838239.32 |  |  | Terminated | 0 | [9 empty] | Steven Construction and Supply/ On Time Builders Inc (JV) | Slippage Unworkable weather and slow performance of contractor (as per DPWH); TERMINATION ON PROCESS
NC 2018 | K10 | Region VIII | Northern Samar | 122889 | Opong ES | CATUBIG | 2 | 1 | 6 | 2STY6CL | Batch 3 | 18631901.68 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Northern Samar | 122943 | Laoang I CS | LAOANG | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11966509.58 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Northern Samar | 122973 | Burabud ES | LAOANG | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11945396.12 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Northern Samar | 122985 | Rawis CS | LAOANG | 2 | 1 | 6 | 2STY6CL | Batch 3 | 19141617.53 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Northern Samar | 123023 | Las Navas I Central School | LAS NAVAS | 2 | 1 | 6 | 2STY6CL | Batch 3 | 19603293.53 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Northern Samar | 123182 | Pambujan 1 Central School | PAMBUJAN | 2 | 1 | 6 | 2STY6CL | Batch 3 | 18965913.15 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Northern Samar | 123245 | SAN ROQUE CS | SAN ROQUE | 2 | 1 | 12 | 2STY12CL | Batch 3 | 32792964.18 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303539 | Capacujan NHS | PALAPAG | 2 | 1 | 2 | 2STY ICT LAB. | Batch 3 | 12618459.29 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303544 | Catubig Valley NHS | CATUBIG | 2 | 1 | 3 | 1STY REGULAR WORKSHOP | Batch 3 | 17219137.36 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303544 | Catubig Valley NHS | CATUBIG | 2 |  | 2 | 2STY SCI. LAB. | Batch 3 | 12108698.04 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303546 | Don Juan F. Avalon National High School | SAN ROQUE | 2 | 1 | 2 | 2STY ICT LAB. | Batch 3 | 12156086.55 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303546 | Don Juan F. Avalon National High School | SAN ROQUE | 2 |  | 2 | 2STY REGULAR WORKSHOP | Batch 3 | 12156086.55 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303551 | Gala Vocational School | GAMAY | 2 | 1 | 6 | 2-UNITS 3STY REGULAR WORKSHOP | Batch 3 | 34686872.98 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303551 | Gala Vocational School | GAMAY | 2 |  | 2 | 2STY SCI. LAB. | Batch 3 | 12293953.23 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303552 | Gamay National High School | GAMAY | 2 | 1 | 3 | 3STY SCI. LAB. & REGULAR WORKSHOP | Batch 3 | 17374227.63 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303559 | Lorenzo S. Menzon AIS | LAPINIG | 2 | 1 | 2 | 2STY REGULAR WORKSHOP | Batch 3 | 11993484.21 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303559 | Lorenzo S. Menzon AIS | LAPINIG | 2 |  | 2 | 2STY SCI. LAB. | Batch 3 | 11993484.21 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Northern Samar | 303560 | Las Navas National High School | LAS NAVAS | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12190266.04 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303569 | Pambujan NHS | PAMBUJAN | 2 | 1 | 2 | 2STY SCI. LAB. | Batch 3 | 11996074.83 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303569 | Pambujan NHS | PAMBUJAN | 2 |  | 2 | 2STY REGULAR WORKSHOP | Batch 3 | 11996074.83 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Northern Samar | 303571 | Potong NHS | LAPINIG | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12210073.67 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303581 | San Roque-Pambujan Vocational High School | PAMBUJAN | 2 | 1 | 2 | 2STY SCI. LAB. | Batch 3 | 12195361.5 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 303581 | San Roque-Pambujan Vocational High School | PAMBUJAN | 2 |  | 2 | 2STY2 ICT LAB. | Batch 3 | 12195361.5 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Northern Samar | 313603 | Rawis National High School | LAOANG | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11972169.01 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 313603 | Rawis National High School | LAOANG | 2 |  | 2 | 2STY SCI. LAB. | Batch 3 | 11972169.01 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Northern Samar | 313618 | Balnasan National High School | SAN ROQUE | 2 | 1 | 2 | 2STY SCI. LAB. | Batch 3 | 11592309.07 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Northern Samar | 304914 | E.J. Dulay National High School | LAOANG | 2 | 1 | 6 | 2UNITS 1STY3CL | Batch 5 | 13375418.83 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Ormoc City | 124145 | Biliboy Primary School | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3870000 |  |  | Completed | 1 |  |  | P0024907VS | 18IF0148 | 2018-11-09 |  | 2018-11-06 | 2018-11-19 | 2018-12-11 | GREENPLAINS CONSTRUCTION
NC 2018 | K10 | Region VIII | Ormoc City | 124147 | Camp Downes ES | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3820000 |  |  | Completed | 1 |  |  | P0024908VS | 18IF0129 | 2018-11-02 |  | 2018-10-24 | 2018-11-19 | 2018-12-03 | RJIR ENTERPRISES
NC 2018 | K10 | Region VIII | Ormoc City | 124149 | Can-untog ES | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3820000 |  |  | Completed | 1 |  |  | P0024909VS | 18IF0130 | 2018-11-02 |  | 2018-10-24 | 2018-11-19 | 2018-12-03 | RJIR ENTERPRISES
NC 2018 | K10 | Region VIII | Ormoc City | 124152 | Donghol ES | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3820000 |  |  | Completed | 1 |  |  | P0024910VS | 18IF0128 | 2018-11-02 |  | 2018-10-24 | 2018-11-19 | 2018-12-03 | GREENPLAINS CONSTRUCTION
NC 2018 | K10 | Region VIII | Ormoc City | 124154 | Hugpa ES | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3920000 |  |  | Completed | 1 |  |  | P0024911VS | 18IF0142 | 2018-11-09 |  | 2018-11-06 | 2018-11-19 | 2018-12-10 | R. ALLOSA CONSTRUCTION & TRUCKING SERVICES
NC 2018 | K10 | Region VIII | Ormoc City | 124155 | Ipil CS | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 4120000 |  |  | Completed | 1 |  |  | P0024912VS | 18IF0180 | 2018-11-23 |  | 2018-11-19 | 2018-11-28 | 2018-12-07 | RJIR ENTERPRISES
NC 2018 | K10 | Region VIII | Ormoc City | 124160 | Mabini ES | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3870000 |  |  | Completed | 1 |  |  | P0024913VS | 18IF0150 | 2018-11-09 |  | 2018-11-06 | 2018-11-19 | 2018-12-11 | GREENPLAINS CONSTRUCTION
NC 2018 | K10 | Region VIII | Ormoc City | 124167 | Patag ES | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3870000 |  |  | Completed | 1 |  |  | P0024914VS | 18IF0152 | 2018-11-10 |  | 2018-11-07 | 2018-11-23 | 2018-12-11 | CIRCLE Z VENTURES & DEVELOPMENT CORP.
NC 2018 | K10 | Region VIII | Ormoc City | 124169 | San Antonio ES | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3820000 |  |  | Completed | 1 |  |  | P0024915VS | 18IF0127 | 2018-11-02 |  | 2018-10-24 | 2018-11-19 | 2018-12-03 | GMP BUILDERS
NC 2018 | K10 | Region VIII | Ormoc City | 124170 | Sumangga Elementary School | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3920000 |  |  | Completed | 1 |  |  | P0024916VS | 18IF0174 | 2018-11-17 |  | 2018-11-13 | 2018-11-26 | 2018-12-07 | GMP BUILDERS
NC 2018 | K10 | Region VIII | Ormoc City | 124172 | H. Serafica ES (Bayog) | ORMOC CITY | 4 | 1 | 4 | 1STY4CL | Batch 3 | 8200000 |  |  | Completed | 1 |  |  | P0024917VS | 18IF0188 | 2018-11-25 |  | 2018-11-22 | 2018-11-28 | 2018-12-19 | BNC CONSTRUCTION & REPAIR SERVICES
NC 2018 | K10 | Region VIII | Ormoc City | 124182 | L. Cabahug ES | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3870000 |  |  | Completed | 1 |  |  | P0024918VS | 18IF0151 | 2018-11-10 |  | 2018-11-07 | 2018-11-23 | 2018-12-10 | JA ACHACOSO ENTERPRISES & GENERAL SERVICES
NC 2018 | K10 | Region VIII | Ormoc City | 124184 | Manlilinao ES | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3920000 |  |  | Completed | 1 |  |  | P0024919VS | 18IF0153 | 2018-11-10 |  | 2018-11-07 | 2018-11-23 | 2018-12-07 | ROLANDO M. VILLASENCIO CONSTRUCTION & GENERAL SERVICES
NC 2018 | K10 | Region VIII | Ormoc City | 124186 | Monterico ES | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3920000 |  |  | Completed | 1 |  |  | P0024920VS | 18IF0154 | 2018-11-10 |  | 2018-11-07 | 2018-11-23 | 2018-12-10 | RJIR ENTERPRISES
NC 2018 | K10 | Region VIII | Ormoc City | 124187 | Nueva Vista ES | ORMOC CITY | 4 | 1 | 2 | CONSTRUCTION OF 2CL (K-10) | Batch 3 | 3920000 |  |  | Completed | 1 |  |  | P0024921VS | 18IF0182 | 2018-11-23 |  | 2018-11-19 | 2018-11-28 | 2018-12-07 | RJIR ENTERPRISES
NC 2018 | K10 | Region VIII | Ormoc City | 124195 | Linao CS | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3820000 |  |  | Completed | 1 |  |  | P0024922VS | 18IF0126 | 2018-11-02 |  | 2018-10-24 | 2018-11-19 | 2018-12-03 | JA ACHACOSO ENTERPRISES & GENERAL SERVICES
NC 2018 | K10 | Region VIII | Ormoc City | 124196 | Naungan ES | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3820000 |  |  | Completed | 1 |  |  | P0024923VS | 18IF0133 | 2018-11-02 |  | 2018-10-24 | 2018-11-19 | 2018-12-03 | JA ACHACOSO ENTERPRISES & GENERAL SERVICES
NC 2018 | K10 | Region VIII | Ormoc City | 124197 | Ormoc City SPED Center | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3870000 |  |  | Completed | 1 |  |  | P0024924VS | 18IF0132 | 2018-11-02 |  | 2018-10-24 | 2018-11-19 | 2018-12-10 | JM COLLERA KONSTRACT
NC 2018 | K10 | Region VIII | Ormoc City | 124199 | Tambulilid ES | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3870000 |  |  | Completed | 1 |  |  | P0024925VS | 18IF0183 | 2018-11-23 |  | 2018-11-19 | 2018-11-28 | 2018-12-04 | CIRCLE Z VENTURES & DEVELOPMENT CORP.
NC 2018 | K10 | Region VIII | Ormoc City | 124200 | Airport Primary School | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3920000 |  |  | Completed | 1 |  |  | P0024926VS | 18IF0181 | 2018-11-23 |  | 2018-11-19 | 2018-11-28 | 2018-12-07 | R ALLOSA CONSTRUCTION
NC 2018 | K10 | Region VIII | Ormoc City | 124203 | Cogon CS | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3920000 |  |  | Completed | 1 |  |  | P0024927VS | 18IF0177 | 2018-11-17 |  | 2018-11-13 | 2018-11-26 | 2018-12-10 | CIRCLE Z VENTURES & DEVELOPMENT CORP.
NC 2018 | K10 | Region VIII | Ormoc City | 124206 | Domonar ES | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 4120000 |  |  | Completed | 1 |  |  | P0024928VS | 18IF0176 | 2018-11-17 |  | 2018-11-13 | 2018-11-26 | 2018-12-07 | RJIR ENTERPRISES
NC 2018 | K10 | Region VIII | Ormoc City | 124210 | Lao ES | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3900000 |  |  | Completed | 1 |  |  | P0024929VS | 18IF0175 | 2018-11-17 |  | 2018-11-13 | 2018-11-26 | 2018-12-10 | GMP BUILDERS
NC 2018 | K10 | Region VIII | Ormoc City | 124211 | JICA-Lao ES | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3920000 |  |  | Completed | 1 |  |  | P0024930VS | 18IF0172 | 2018-11-17 |  | 2018-11-13 | 2018-11-26 | 2018-12-07 | CIRCLE Z VENTURES & DEVELOPMENT CORP.
NC 2018 | K10 | Region VIII | Ormoc City | 124212 | Libertad ES | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3820000 |  |  | Completed | 1 |  |  | P0024931VS | 18IF0131 | 2018-11-02 |  | 2018-10-24 | 2018-11-19 | 2018-12-03 | GMP BUILDERS
NC 2018 | K10 | Region VIII | Ormoc City | 124213 | Licuma ES | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3870000 |  |  | Completed | 1 |  |  | P0024932VS | 18IF0149 | 2018-11-09 |  | 2018-11-06 | 2018-11-19 | 2018-12-07 | ROLANDO M. VILLASENCIO CONSTRUCTION & GENERAL SERVICES
NC 2018 | K10 | Region VIII | Ormoc City | 124214 | Liloan CS | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3820000 |  |  | Completed | 1 |  |  | P0024933VS | 18IF0134 | 2018-11-03 |  | 2018-10-25 | 2018-11-19 | 2018-12-03 | RJIR ENTERPRISES
NC 2018 | K10 | Region VIII | Ormoc City | 124216 | Mas-in ES | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3970000 |  |  | Completed | 1 |  |  | P0024934VS | 18IF0184 | 2018-11-23 |  | 2018-11-19 | 2018-11-28 | 2018-12-07 | ROLANDO M. VILLASENCIO CONSTRUCTION & GENERAL SERVICES
NC 2018 | K10 | Region VIII | Ormoc City | 124219 | San Isidro ES | ORMOC CITY | 4 | 1 | 4 | 2STY4CL | Batch 3 | 12080000 |  |  | Completed | 1 |  |  | P0024935VS | 18IF0191 | 2018-11-23 |  | 2018-11-22 | 2018-11-28 | 2018-12-07 | JM COLLERA KONSTRACT
NC 2018 | K10 | Region VIII | Ormoc City | 124221 | San Pablo ES (Simangan) | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3920000 |  |  | Completed | 1 |  |  | P0024936VS | 18IF0173 | 2018-11-17 |  | 2018-11-13 | 2018-11-26 | 2018-12-07 | RJIR ENTERPRISES
NC 2018 | K10 | Region VIII | Ormoc City | 194501 | Ormoc City CS | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3820000 |  |  | Completed | 1 |  |  | P0024937VS | 18IF0192 | 2018-11-25 |  | 2018-11-22 | 2018-11-28 | 2018-12-07 | RJIR ENTERPRISES
NC 2018 | K10 | Region VIII | Ormoc City | 194502 | VL Villacencio ES | ORMOC CITY | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3406295.92 |  |  | Completed | 1 |  |  | P0024938VS | 18IF0193 | 2018-11-29 |  | 2018-11-26 | 2018-11-28 | 2018-12-07 | ROLANDO M. VILLASENCIO CONSTRUCTION & GENERAL SERVICES
NC 2018 | SHS | Region VIII | Ormoc City | 303654 | Dolores NHS | ORMOC CITY | 4 | 1 | 4 | 2STY4CL | Batch 3 | 12080000 |  |  | Completed | 1 |  |  | P0024939VS | 18IF0189 | 2018-11-25 |  | 2018-11-22 | 2018-11-28 | 2018-12-10 | JM COLLERA KONSTRACT
NC 2018 | SHS | Region VIII | Ormoc City | 303655 | Ipil NHS | ORMOC CITY | 4 | 1 | 4 | 2STY4CL | Batch 3 | 12480000 |  |  | Completed | 1 |  |  | P0024940VS | 18IF0190 | 2018-11-25 |  | 2018-11-22 | 2018-11-28 | 2018-12-10 | JM COLLERA KONSTRACT
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303590 | Baquiw NHS | TAGAPUL-AN | 1 | 1 | 4 | 2STY4CL | Batch 3 | 10489617.93 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303599 | Clarencio Calagos Mem SOF | SANTA MARGARITA | 1 | 1 | 10 | 2STY10CL | Batch 3 | 25417231.42 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303600 | Costa Rica NHS | ALMAGRO | 1 | 1 | 4 | 2STY4CL | Batch 3 | 10489617.93 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303629 | Sta. Margarita NHS | SANTA MARGARITA | 1 | 1 | 4 | 2STY4CL | Batch 3 | 10134336.23 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303632 | Sto. Nino NHS | SANTO NIÑO | 1 | 1 | 4 | 2STY4CL | Batch 3 | 10489617.93 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303634 | Tarangnan NHS | TARANGNAN | 1 | 1 | 9 | 3STY9CL | Batch 3 | 28123084.67 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 313708 | San Jorge NHS | SAN JORGE | 1 | 1 | 4 | 2STY4CL | Batch 3 | 10307743.36 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 313722 | Majacob Integrated School | TARANGNAN | 1 | 1 | 4 | 2STY4CL | Batch 3 | 10433851.4 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303592 | BASEY NHS | BASEY | 2 | 1 | 10 | 2STY10CL | Batch 3 | 29230340.07 |  |  | Completed | 1 | [9 empty] | Rianne Construction | Suspended due to redesign of Foundation Plan
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303594 | Old San Agustin NHS | BASEY | 2 | 1 | 6 | 2STY6CL | Batch 3 | 19688592.41 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303595 | Birawan NHS | DARAM | 2 | 1 | 6 | 2STY6CL | Batch 3 | 19713592.41 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303601 | Daram NHS | DARAM | 2 | 1 | 10 | 2STY10CL | Batch 3 | 29255340.07 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303602 | Mualbual National High School | ZUMARRAGA | 2 | 1 | 6 | 2STY6CL | Batch 3 | 19713592.41 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303603 | Sua NHS | DARAM | 2 | 1 | 6 | 2STY6CL | Batch 3 | 19713592.41 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303605 | Guintarcan NHS | VILLAREAL | 2 | 1 | 2 | 2STY2CL | Batch 3 | 8670851.36 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303606 | Hinabangan NHS | HINABANGAN | 2 | 1 | 6 | 2STY6CL | Batch 3 | 19663592.41 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303608 | Independencia NHS | TALALORA | 2 | 1 | 8 | 2STY8CL | Batch 3 | 24484466.24 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303609 | Jiabong National High School | JIABONG | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12242233.12 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303613 | Motiong NHS | MOTIONG | 2 | 1 | 12 | 2STY12CL | Batch 3 | 39277184.82 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303625 | SAN ANDRES NHS | VILLAREAL | 2 | 1 | 6 | 2STY6CL | Batch 3 | 19713592.41 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303626 | San Jose de Buan NHS | SAN JOSE DE BUAN | 2 | 1 | 6 | 2STY6CL | Batch 3 | 19713592.41 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303627 | San Sebastian NHS | SAN SEBASTIAN | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12242233.12 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303628 | Simeon Ocdol NHS | BASEY | 2 | 1 | 8 | 2STY8CL | Batch 3 | 24459466.24 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303631 | Sta. Rita NHS | SANTA RITA | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12242233.12 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303639 | Villareal NHS | VILLAREAL | 2 | 1 | 10 | 2STY10CL | Batch 3 | 29205340.07 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303640 | Quintin Quijano SAS | PINABACDAO | 2 | 1 | 8 | 2STY8CL | Batch 3 | 24434466.24 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303641 | Wright NHS | PARANAS (WRIGHT) | 2 | 1 | 10 | 2STY10CL | Batch 3 | 29205340.07 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 303643 | Zumarraga NHS | ZUMARRAGA | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12292233.12 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 313705 | Rizal Integrated School | DARAM | 2 | 1 | 6 | 2STY6CL | Batch 3 | 19713592.41 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 313709 | Bakhaw NHS | DARAM | 2 | 1 | 8 | 2STY8CL | Batch 3 | 24484466.24 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 313719 | Bagacay NHS | DARAM | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12292233.12 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Samar (Western Samar) | 313721 | San Isidro NHS | ZUMARRAGA | 2 | 1 | 6 | 2STY6CL | Batch 3 | 19713592.41 |  |  | Completed | 1
NC 2018 | TVL | Region VIII | Southern Leyte | 303465 | LIMASAWA NHS | LIMASAWA | 0 | 1 | 1 | REGULAR WORKSHOP | BATCH 1 | 3316044.94 |  |  | Completed | 1 |  |  | P00272475VS-CW1 | 18ILO116 | 2018-07-11 | 2018-07-19 | 2018-07-31
NC 2018 | TVL | Region VIII | Southern Leyte | 303477 | Pintuyan National Vocational HS | PINTUYAN | 0 | 1 | 1 | UNIQUE WORKSHOP | BATCH 1 | 5595963.32 |  |  | Completed | 1 |  |  | P00272476VS-CW1 | 18ILO122 | 2018-07-12 | 2018-07-20 | 2018-08-01
NC 2018 | TVL | Region VIII | Southern Leyte | 303477 | Pintuyan National Vocational HS | PINTUYAN | 0 |  | 1 | UNIQUE WORKSHOP | BATCH 1 | 5595963.32 |  |  | Completed | 1 |  |  | P00272477VS-CW1 | 18ILO123 | 2018-07-12 | 2018-07-20 | 2018-08-01
NC 2018 | TVL | Region VIII | Southern Leyte | 303477 | Pintuyan National Vocational HS | PINTUYAN | 0 |  | 1 | UNIQUE WORKSHOP | BATCH 1 | 5595963.32 |  |  | Completed | 1 |  |  | P00272478VS-CW1 | 18ILO124 | 2018-07-12 | 2018-07-20 | 2018-08-01
NC 2018 | TVL | Region VIII | Southern Leyte | 303487 | Sogod NHS | SOGOD | 0 | 1 | 1 | UNIQUE WORKSHOP | BATCH 1 | 5307008.39 |  |  | Completed | 1 |  |  | P00272479VS-CW1 | 18ILO118 | 2018-07-11 | 2018-07-19 | 2018-07-31
NC 2018 | TVL | Region VIII | Southern Leyte | 303488 | Sta. Cruz NHS | MALITBOG | 0 | 1 | 1 | REGULAR WORKSHOP | BATCH 1 | 3025120.51 |  |  | Completed | 1 |  |  | P00272480VS-CW1 | 18ILO117 | 2018-07-11 | 2018-07-19 | 2018-07-31
NC 2018 | TVL | Region VIII | Southern Leyte | 303492 | VILLA JACINTA NATIONAL VOCATIONAL HS | MACROHON | 0 | 1 | 1 | REGULAR WORKSHOP | BATCH 1 | 3051257.97 |  |  | Completed | 1 |  |  | P00272481VS-CW1 | 18ILO115 | 2018-07-11 | 2018-07-19 | 2018-07-31
NC 2018 | TVL | Region VIII | Southern Leyte | 313409 | Liloan National Technical Vocational HS | LILOAN | 0 | 1 | 1 | UNIQUE WORKSHOP | BATCH 1 | 5357008.39 |  |  | Completed | 1 |  |  | P00272483VS-CW1 | 18ILO121 | 2018-07-12 | 2018-07-20 | 2018-08-01
NC 2018 | TVL | Region VIII | Southern Leyte | 313409 | Liloan National Technical Vocational HS | LILOAN | 0 |  | 1 | UNIQUE WORKSHOP | BATCH 1 | 5357008.39 |  |  | Completed | 1 |  |  | P00272482VS-CW1 | 18ILO120 | 2018-07-12 | 2018-07-20 | 2018-08-01
NC 2018 | TVL | Region VIII | Southern Leyte | 313409 | Liloan National Technical Vocational HS | LILOAN | 0 |  | 1 | REGULAR WORKSHOP | BATCH 1 | 2950120.51 |  |  | Completed | 1 |  |  | P00272484VS-CW1 | 18ILO119 | 2018-07-12 | 2018-07-20 | 2018-08-01
NC 2018 | K10 | Region VIII | Southern Leyte | 121995 | Beniton MG Elementary School | BONTOC | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5910931.89 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Southern Leyte | 122002 | Divisoria Elementary School | BONTOC | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5910931.89 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Southern Leyte | 122005 | Hilaan Elementary School | BONTOC | 0 | 1 | 2 | 1STY2CL | Batch 3 | 6046461.15 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Southern Leyte | 122019 | San Vicente Primary School | BONTOC | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5775402.63 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Southern Leyte | 122030 | Hinunangan East Central School | HINUNANGAN | 0 | 1 | 6 | 2STY6CL | Batch 3 | 23192080.99 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Southern Leyte | 122052 | Awayon Elementary School | SILAGO | 0 | 1 | 2 | 1STY2CL | Batch 3 | 6407872.51 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Southern Leyte | 122073 | Lungsodaan Elementary School | HINUNDAYAN | 0 | 1 | 4 | 2STY4CL | Batch 3 | 15991102.58 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Southern Leyte | 122109 | Pres. Quezon Elementary School | LILOAN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 6407872.51 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Southern Leyte | 122189 | Macrohon Central School | MACROHON | 0 | 1 | 6 | 2STY6CL | Batch 3 | 23094013.03 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Southern Leyte | 122213 | San Vicente Elementary School | MALITBOG | 0 | 1 | 4 | 2STY4CL | Batch 3 | 14710918.1 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Southern Leyte | 122236 | Kinachawa Elementary School | SAN RICARDO | 0 | 1 | 2 | 1STY2CL | Batch 3 | 6633754.61 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Southern Leyte | 122252 | San Juan Central Elementary School with SPED CENTER | SAN JUAN (CABALIAN) | 0 | 1 | 3 | 1STY3CL | Batch 3 | 8391538.52 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Southern Leyte | 122280 | Sogod Central School | SOGOD | 0 | 1 | 6 | 2STY6CL | Batch 3 | 22897877.1 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Southern Leyte | 122301 | San Isidro Elementary School | SAINT BERNARD | 0 | 1 | 2 | 1STY2CL | Batch 3 | 6181990.41 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Southern Leyte | 192007 | San Antonio Elementary School | TOMAS OPPUS | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5685049.79 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Southern Leyte | 303446 | Canipaan NHS | HINUNANGAN | 0 | 1 | 6 | 2STY6CL | Batch 3 | 23388216.91 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Southern Leyte | 303451 | Divisoria NHS | BONTOC | 0 | 1 | 6 | 2STY6CL | Batch 3 | 23388216.91 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Southern Leyte | 303455 | Esperanza National High School | SAN RICARDO | 0 | 1 | 6 | 2STY6CL | Batch 3 | 24663100.42 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Southern Leyte | 313407 | New Guinsaugon National High School | SAINT BERNARD | 0 | 1 | 4 | 2STY4CL | Batch 3 | 14771879.27 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Southern Leyte | 313409 | Liloan National Technical Vocational High School | LILOAN | 0 | 1 | 15 | 3STY15CL | Batch 3 | 47155986.35 |  |  | Completed | 1
NC 2018 | SHS | Region VIII | Southern Leyte | 313409 | Liloan National Technical Vocational High School | LILOAN | 0 |  | 15 | 3STY15CL | Batch 3 | 47155986.35 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Tacloban City | 102307 | New Hope Elementary School | TACLOBAN CITY (Capital) | 1 | 1 | 15 | 3STY15CL | Batch 3 | 40004423.63 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Tacloban City | 124227 | Rizal Central School | TACLOBAN CITY (Capital) | 1 | 1 | 12 | 4STY12CL | Batch 3 | 40024154.41 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Tacloban City | 500891 | North Hill Arbours Integrated School | TACLOBAN CITY (Capital) | 1 | 1 | 30 | 2-UNITS 3STY15CL | Batch 3 | 70807287.04 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Tacloban City | 500892 | Guadalupe Heights Integrated School | TACLOBAN CITY (Capital) | 1 | 1 | 16 | 4STY16CL | Batch 3 | 41738536.44 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Tacloban City | 500892 | Guadalupe Heights Integrated School | TACLOBAN CITY (Capital) | 1 |  | 20 | 4STY20CL | Batch 3 | 56278887.08 |  |  | Completed | 1
NC 2018 | K10 | Region VIII | Tacloban City | 500893 | Greendale Residences Integrated School | TACLOBAN CITY (Capital) | 1 | 1 | 15 | 3STY15CL | Batch 3 | 42704381.93 |  |  | Completed | 1
NC 2019 | K10 | Region VIII | Baybay | 121097 | Biasong Elementary School | Baybay | 5 | 1 | 2 | 1STY2CL |  | 4678614.7284 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Biliran | 120860 | Naval CS | NAVAL (Capital) | 0 | 1 | 2 | 1STY2CL |  | 3125637.6075 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Biliran | 120862 | Sabang ES | NAVAL (Capital) | 0 | 1 | 2 | 1STY2CL |  | 2957938.5454 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Borongan City | 122368 | Amantacop ES | CITY OF BORONGAN (Capital) | 0 | 1 | 2 | 1STY2CL |  | 4551350 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Calbayog City | 500749 | Tomaligues Integrated School | CALBAYOG CITY | 1 | 1 | 4 | 2STY4CL |  | 12107757.0579 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Catbalogan City | 123415 | Majaba Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | 2 | 1STY2CL |  | 4438678.2932 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Eastern Samar | 122634 | Bantayan Elementary School | ORAS | 0 | 1 | 2 | 1STY2CL |  | 4513255 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Eastern Samar | 122659 | Buntay Elementary School | ORAS | 0 | 1 | 2 | 1STY2CL |  | 4957362.5 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Eastern Samar | 122738 | Cajagwayan Elementary School | SAN POLICARPO | 0 | 1 | 2 | 1STY2CL |  | 4483180 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Eastern Samar | 122415 | Cansangaya Elementary School | CAN-AVID | 0 | 1 | 2 | 1STY2CL |  | 4729795 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Eastern Samar | 192508 | Dacul Primary School | TAFT | 0 | 1 | 2 | 1STY2CL |  | 4419020 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Eastern Samar | 122451 | Dapdap Central Elementary School | DOLORES | 0 | 1 | 2 | 1STY2CL |  | 4801975 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Eastern Samar | 122431 | Del Pilar Elementary School | DOLORES | 0 | 1 | 2 | 1STY2CL |  | 5195957.5 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Eastern Samar | 122510 | Giporlos Central School | GIPORLOS | 0 | 1 | 2 | 1STY2CL |  | 4773905 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Eastern Samar | 122739 | Japunan Elementary School | SAN POLICARPO | 0 | 1 | 3 | 1STY3CL |  | 6178407.5 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Eastern Samar | 313512 | Quinapundan National High School- Anislag Annex | QUINAPONDAN | 0 | 1 | 2 | 1STY2CL |  | 4709745 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Eastern Samar | 122742 | San Policarpo Central Elementary School | SAN POLICARPO | 0 | 1 | 3 | 1STY3CL |  | 6168382.5 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Leyte | 120978 | San Francisco West Elementary School | ALANGALANG | 1 | 1 | 3 | 1STY3CL |  | 6360225.8123 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Leyte | 120982 | Santol Elementary School | ALANGALANG | 1 | 1 | 2 | 1STY2CL |  | 4109000.2634 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Leyte | 121311 | Calutan Primary School | DAGAMI | 2 | 1 | 2 | 1STY2CL |  | 3550855 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Leyte | 191529 | Gen. Luna Elementary School | MACARTHUR | 2 | 1 | 2 | 1STY2CL |  | 3395467.5 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Leyte | 121245 | Manloy Elementary School | CAPOOCAN | 2 | 1 | 2 | 1STY2CL |  | 3884888 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Leyte | 121611 | Tinocdugan Elementary School | LEYTE | 3 | 1 | 2 | 1STY2CL |  | 2650780.3949 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Leyte | 121788 | Cangcosme Elementary School | PALOMPON | 4 | 1 | 2 | 1STY2CL |  | 3929800 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Leyte | 121633 | Higmamara ES | MAHAPLAG | 5 | 1 | 2 | 1STY2CL |  | 4548289.7284 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Leyte | 121390 | Pontod ES | HILONGOS | 5 | 1 | 8 | 2STY8CL |  | 22933822.8081 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Leyte | 121075 | Tabunuk ES | BATO | 5 | 1 | 3 | 1STY3CL |  | 6525694.5926 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Maasin City | 122172 | San Agustin MGS | CITY OF MAASIN (Capital) | 0 | 1 | 3 | 1STY3CL |  | 8820121.6258 | 8798126 | completed | 1 |  |  |  | 19IL0085 |  | 2019-08-15 | 2019-08-27 |  |  |  |  | 0
NC 2019 | K10 | Region VIII | Northern Samar | 122872 | Nazareno ES | CATARMAN (CAPITAL) | 1 | 1 | 3 | 1STY3CL |  | 7103644.5142 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Northern Samar | 122852 | Trangue ES | CATARMAN (CAPITAL) | 1 | 1 | 3 | 1STY3CL |  | 7302812.1216 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Northern Samar | 123142 | Binay ES | PALAPAG | 2 | 1 | 3 | 1STY3CL |  | 6484613.1952 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Northern Samar | 123010 | Dapdap ES | LAS NAVAS | 2 | 1 | 3 | 1STY3CL |  | 6546371.4157 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Northern Samar | 123238 | Ginagdanan ES | SAN ROQUE | 2 | 1 | 3 | 1STY3CL |  | 6791667.5468 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Northern Samar | 122984 | Palmera ES | LAOANG | 2 | 1 | 4 | 1STY4CL |  | 9057872.4005 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Northern Samar | 123177 | Pambujan II CS | PAMBUJAN | 2 | 1 | 4 | 1STY4CL |  | 8975528.2034 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Ormoc City | 124202 | Cabintan Elementary School | ORMOC CITY | 4 | 1 | 2 | 1STY2CL |  | 3929800 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Ormoc City | 124163 | Maglahug Elementary School | ORMOC CITY | 4 | 1 | 2 | 1STY2CL |  | 3879675 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 123285 | Almagro CS | ALMAGRO | 1 | 1 | 4 | 2STY4CL |  | 8968266.5144 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 123831 | Bahay ES | TARANGNAN | 1 | 1 | 2 | 1STY2CL |  | 4518214.7284 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 123831 | Bahay ES | TARANGNAN | 1 |  | 1 | 1STY1CL |  | 2309232.3642 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 313737 | Apolonia Integrated School | PARANAS (WRIGHT) | 2 | 1 | 6 | 2STY6CL |  | 20303988.7183 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 123440 | Arawane ES | DARAM | 2 | 1 | 2 | 1STY2CL |  | 4382062.0255 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 123357 | Bacyaran Elementary School | CALBIGA | 2 | 1 | 4 | 2STY4CL |  | 12681391.1669 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 123359 | Beri Elementary School | CALBIGA | 2 | 1 | 3 | 1STY3CL |  | 6672169.8676 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 123361 | Borong ES | CALBIGA | 2 | 1 | 2 | 1STY2CL |  | 4382062.0255 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 123761 | Cadaragan ES | SANTA RITA | 2 | 1 | 4 | 2STY4CL |  | 12642605.4744 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 123368 | Canbagtic ES | CALBIGA | 2 | 1 | 3 | 1STY3CL |  | 4382062.0255 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 123916 | Cantao-an ES | PARANAS (WRIGHT) | 2 | 1 | 2 | 1STY2CL |  | 4458872.4326 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 123315 | Guirang ES | BASEY | 2 | 1 | 4 | 2STY4CL |  | 12617542.9744 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 123380 | Otoc ES | CALBIGA | 2 | 1 | 2 | 1STY2CL |  | 4382062.0255 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 123322 | Rawis ES | BASEY | 2 | 1 | 4 | 2STY4CL |  | 12617542.9744 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 313715 | San Fernando NHS | BASEY | 2 | 1 | 4 | 2STY4CL |  | 12617542.9744 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 123386 | San Mauricio Elementary School | CALBIGA | 2 | 1 | 2 | 1STY2CL |  | 4382062.0255 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 123465 | San Vicente ES | DARAM | 2 | 1 | 4 | 2STY4CL |  | 12657642.9744 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 123325 | Serum ES | BASEY | 2 | 1 | 4 | 2STY4CL |  | 12617542.9744 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 123387 | Sinalangtan ES | CALBIGA | 2 | 1 | 2 | 1STY2CL |  | 4382062.0255 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 123580 | Tabay Elementary School | HINABANGAN | 2 | 1 | 2 | 1STY2CL |  | 4382062.0255 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 123355 | Tingib ES | BASEY | 2 | 1 | 20 | 4STY20CL |  | 51248921.7975 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 123931 | Tula ES | PARANAS (WRIGHT) | 2 | 1 | 4 | 2STY4CL |  | 12617542.9744 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Samar (Western Samar) | 193519 | Upper Minata Elementary School | CALBIGA | 2 | 1 | 2 | 1STY2CL |  | 4458872.4326 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Southern Leyte | 122200 | Aurora Elementary School | MALITBOG | 0 | 1 | 2 | 1STY2CL |  | 6650338.9965 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region VIII | Southern Leyte | 303463 | Libas NHS | SOGOD | 0 | 1 | 3 | 1STY3CL |  | 9499462.0616 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Southern Leyte | 122036 | Lumbog Elementary School | HINUNANGAN | 0 | 1 | 2 | 1STY2CL |  | 6333313.4692 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region VIII | Tacloban City | 124224 | Caibaan ES | TACLOBAN CITY (Capital) | 1 | 1 | 4 | 2STY4CL |  | 14139835.2846 |  | Completed | 1 | [11 empty] | 0
NC 2020 | TVL | Region VIII | Baybay City | 313316 | Baybay City National Night High School | CITY OF BAYBAY | 5 | 1 | 2 | 2STY2 SCI. LAB. |  | 12254216.77 |  |  | completed | 1
NC 2020 | K10 | Region VIII | Biliran | 120784 | Villa Enage Elemenetary School | BILIRAN | 0 | 1 | 6 | 1STY2CL & 1STY4CL |  | 13430001.28 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Borongan City | 122368 | Amantacop ES | CITY OF BORONGAN (Capital) | 0 | 1 | 2 | 1STY2CL |  | 4852100 |  |  | COMPLETED | 1
NC 2020 | K10 | Region VIII | Borongan City | 122394 | Baras ES | CITY OF BORONGAN (Capital) | 0 | 1 | 2 | 1STY2CL |  | 5172900 |  |  | COMPLETED | 1
NC 2020 | K10 | Region VIII | Calbayog City | 123991 | Carayman Elementary School | Calbayog City | 1 | 1 | 8 | 2STY8CL |  | 22929909.3 |  |  | completed | 1
NC 2020 | K10 | Region VIII | Catbalogan City | 123409 | Catbalogan II Central Elementary School | Catbalogan City (Capital) | 2 | 1 | 20 | 4STY20CL |  | 55398178.07 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Eastern Samar | 122634 | Bantayan Elementary School | ORAS | 0 | 1 | 4 | 2STY4CL |  | 13328237.5 |  |  | COMPLETED | 1
NC 2020 | K10 | Region VIII | Eastern Samar | 122658 | Binalayan Elementary School | ORAS | 0 | 1 | 2 | 1STY2CL |  | 5153852.5 |  |  | COMPLETED | 1
NC 2020 | TVL | Region VIII | Eastern Samar | 313507 | Nena National High School | SAN JULIAN | 0 | 1 | 2 | 2STY,TVL |  | 13166835 |  |  | COMPLETED | 1
NC 2020 | K10 | Region VIII | Leyte | 120972 | Lukay Elementary School | ALANGALANG | 1 | 1 | 3 | 1STY3CL |  | 6534764.73 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Leyte | 120973 | Montano Elementary School | ALANGALANG | 1 | 1 | 3 | 1STY3CL with Toilet & Parapet |  | 6391164.74 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Leyte | 121005 | Babatngon Central School | BABATNGON | 1 | 1 | 4 | 1STY4CL |  | 8633130.97 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Leyte | 121764 | San Jose Elementary School | PALO | 1 | 1 | 6 | 2STY6CL |  | 14440494.93 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Leyte | 121940 | Maribi Elementary School | TANAUAN | 1 | 1 | 6 | 2STY6CL with Toilet & Parapet |  | 14939192.23 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Leyte | 121179 | Villa Rosas Elementary School | BURAUEN | 2 | 1 | 2 | 1STY2CL |  | 4843168.34 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Leyte | 121242 | Guinadiongan Elementary School | CAPOOCAN | 2 | 1 | 2 | 1STY2CL |  | 4921802.81 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Leyte | 121340 | Batug Elementary School | DULAG | 2 | 1 | 2 | 1STY2CL |  | 4660198.47 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Leyte | 121520 | Calbasag Elementary School | JULITA | 2 | 1 | 2 | 1STY2CL |  | 4843168.34 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Leyte | 121710 | Sta. Cruz Elementary School | MAYORGA | 2 | 1 | 2 | 1STY2CL |  | 4877647.72 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Leyte | 121209 | Bunacan Elementary School | CALUBIAN | 3 | 1 | 3 | 1STY3CL |  | 4686445.57 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Leyte | 121889 | Manlawaan Elementary School | TABANGO | 3 | 1 | 2 | 1STY2CL |  | 3101905.39 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Leyte | 121975 | Tabunoc Elementary School | VILLABA | 3 | 1 | 3 | 1STY3CL |  | 4460883.07 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Leyte | 120992 | Soob Elementary School | ALBUERA | 4 | 1 | 2 | 1STY2CL |  | 4010902.25 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Leyte | 121541 | Libongao Elementary School | KANANGA | 4 | 1 | 2 | 1STY2CL |  | 3860527.25 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Leyte | 121551 | San Ignacio Elementary School | KANANGA | 4 | 1 | 2 | 1STY2CL |  | 3960777.25 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Leyte | 121658 | Cambadbad Elementary School | MATAG-OB | 4 | 1 | 2 | 1STY2CL |  | 4010902.25 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Leyte | 121667 | Naulayan Elementary School | MATAG-OB | 4 | 1 | 2 | 1STY2CL |  | 4061027.25 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Leyte | 121732 | Puerto Bello Elementary School | MERIDA | 4 | 1 | 2 | 1STY2CL |  | 4161277.25 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Leyte | 121770 | Lomonon Elementary School | PALOMPON | 4 | 1 | 2 | 1STY2CL |  | 4161277.25 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Leyte | 121788 | Cangcosme Elementary School | PALOMPON | 4 | 1 | 2 | 1STY2CL |  | 4010902.25 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Leyte | 191544 | Magnangoy Primary School | HILONGOS | 5 | 1 | 2 | 1STY2CL |  | 4662825.35 |  |  | Completed | 1
NC 2020 | TVL | Region VIII | Leyte | 303338 | Anahawan National High School | BATO | 5 | 1 | 2 | 2STY2 ICT LAB |  | 12743054.94 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Northern Samar | 122836 | GENEROSO R. FRIGILLANA MS | CATARMAN | 1 | 1 | 4 | 2STY4CL |  | 10273238.1 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Northern Samar | 123219 | VERIATO ES | SAN ISIDRO | 1 | 1 | 4 | 1STY4CL |  | 8421000 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Northern Samar | 122987 | SIMORA ES | LAOANG | 2 | 1 | 3 | 1STY3CL |  | 6315750 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Northern Samar | 123113 | SILJAGON ES | MAPANAS | 2 | 1 | 3 | 1STY3CL |  | 6315750 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Northern Samar | 123149 | CAPACUJAN ES | PALAPAG | 2 | 1 | 4 | 1STY4CL |  | 8421000 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Northern Samar | 313607 | SILJAGON NHS | MAPANAS | 2 | 1 | 3 | 1STY3CL |  | 6315750 |  |  | Completed | 1
NC 2020 | K10 | Region VIII | Ormoc City | 124204 | Curva Elementary School | ORMOC CITY | 4 | 1 | 3 | 1STY3CL |  | 6400862.25 |  |  | completed | 1
NC 2020 | K10 | Region VIII | Ormoc City | 124214 | Liloan Central School | ORMOC CITY | 4 | 1 | 2 | 1STY2CL |  | 3860527.25 |  |  | completed | 1
NC 2020 | K10 | Region VIII | Ormoc City | 194501 | Ormoc City Central School | ORMOC CITY | 4 | 1 | 6 | 2STY4CL, 1STY 2CL |  | 16060952.25 |  |  | completed | 1
NC 2020 | K10 | Region VIII | Ormoc City |  | Lilo-an National High School (ANNEX) | ORMOC CITY | 4 | 1 | 6 | 2STY6CL |  | 18834168 |  |  | completed | 1
NC 2020 | K10 | Region VIII | Samar (Western Samar) | 123296 | Marasbaras PS | ALMAGRO | 1 | 1 | 2 | 1STY2CL |  | 4729436.21 |  |  | completed | 1
NC 2020 | K10 | Region VIII | Samar (Western Samar) | 123750 | Inoraguiao ES | SANTA MARGARITA | 1 | 1 | 4 | 2STY4CL |  | 12222713.7 |  |  | completed | 1
NC 2020 | K10 | Region VIII | Samar (Western Samar) | 313736 | Pequit IS | PARANAS (WRIGHT) | 2 | 1 | 6 | 2STY6CL |  | 20404239.22 |  |  | COMPLETED | 1
NC 2020 | K10 | Region VIII | Southern Leyte | 122180 | Asuncion Multigrade ES | MACROHON | 0 | 1 | 2 | 1STY2CL |  | 5970998.58 |  |  | COMPLETED | 1
NC 2020 | SHS | Region VIII | Southern Leyte | 302079 | Padre Burgos National Technical Vocational High School | PADRE BURGOS | 0 | 1 | 6 | 2STY6CL |  | 24177635.65 |  |  | COMPLETED | 1
NC 2020 | K10 | Region VIII | Tacloban City | 124233 | Bayanihan ES | Tacloban City (Capital) | 1 | 1 | 6 | 3STY6CL |  | 18947250 |  |  | COMPLETED | 1
NC 2021 | SHS | Region VIII | Baybay City | 303420 | Pomponan National High School | CITY OF BAYBAY | 5 | 1 | 2 | Construction/Completion (2STY2CL ICT. LAB.) |  | 146911.1219 | 146544.76 |  | Completed | 1 | [10 empty] | for advertisement
NC 2021 | SHS | Region VIII | Baybay City | 313316 | Baybay City National Night HS | CITY OF BAYBAY | 5 | 1 | 2 | Construction/Completion (2STY2 REGULAR WORKSHOP) |  | 146911.1219 | 146544.76 |  | Completed | 1 | [10 empty] | for advertisement
NC 2021 | SHS | Region VIII | Baybay City | 313316 | Baybay City National Night HS | CITY OF BAYBAY | 5 |  | 2 | Construction/Completion (2STY2 ICT LAB.) |  | 146911.1219 | 146544.76 |  | Completed | 1 | [10 empty] | for advertisement
NC 2021 | SHS | Region VIII | Baybay City | 313323 | Ciabu NHS | CITY OF BAYBAY | 5 | 1 | 4 | Construction/Completion (2-UNITS 2STY2 REG. WORKSHOP) |  | 293822.2438 | 293089.52 |  | Completed | 1 | [10 empty] | for advertisement
NC 2021 | SHS | Region VIII | Baybay City | 313323 | Ciabu NHS | CITY OF BAYBAY | 5 |  | 2 | Construction/Completion (2STY2 ICT LAB.) |  | 146911.1219 | 146544.76 |  | Completed | 1 | [10 empty] | for advertisement
NC 2021 | SHS | Region VIII | Baybay City | 344593 | Baybay City Senior HS | CITY OF BAYBAY | 5 | 1 | 2 | Construction/Completion (2STY2 ICT LAB.) |  | 146911.1219 | 146544.76 |  | Completed | 1 | [10 empty] | for advertisement
NC 2021 | K10 | Region VIII | Biliran | 120821 | Habuhab ES | CULABA | 0 | 1 | 2 | Construction/Completion (1STY2CL) |  | 4411000 | 4400000 |  | COMPLETED | 1
NC 2021 | SHS | Region VIII | Biliran | 303324 | Culaba NVS | CULABA | 0 | 1 | 6 | Construction/Completion (2STY6CL) |  | 2993451.5866 | 2985986.62 |  | COMPLETED | 1
NC 2021 | SHS | Region VIII | Leyte | 303335 | Abuyog National High School | ABUYOG | 5 | 1 | 2 | Construction/Completion (2STY2CL SCI. LAB.) |  | 146911.1219 | 146544.76 |  | Completed | 1 | [10 empty] | for advertisement
NC 2021 | SHS | Region VIII | Leyte | 303335 | Abuyog National High School | ABUYOG | 5 |  | 2 | Construction/Completion (2STY2 ICT LAB.) |  | 146911.1219 | 146544.76 |  | Completed | 1 | [10 empty] | for advertisement
NC 2021 | SHS | Region VIII | Leyte | 303346 | Bato National High School | BATO | 5 | 1 | 2 | Construction/Completion (2STY2 ICT LAB.) |  | 146911.1219 | 146544.76 |  | Completed | 1 | [10 empty] | for advertisement
NC 2021 | SHS | Region VIII | Leyte | 303374 | Hilongos National Vocational School | HILONGOS | 5 | 1 | 2 | Construction/Completion (2STY2CL SCI. LAB.) |  | 146911.1219 | 146544.76 |  | Completed | 1 | [10 empty] | for advertisement
NC 2021 | SHS | Region VIII | Leyte | 303374 | Hilongos National Vocational School | HILONGOS | 5 |  | 2 | Construction/Completion (2STY2 ICT LAB.) |  | 146911.1219 | 146544.76 |  | Completed | 1 | [10 empty] | for advertisement
NC 2021 | TVL | Region VIII | Leyte | 303375 | Hindang National High School | HINDANG | 5 | 1 | 2 | Construction/Completion (2STY2CL SCI. LAB.) |  | 146911.1219 | 146544.76 |  | Completed | 1 | [10 empty] | for advertisement
NC 2021 | K10 | Region VIII | Leyte | 303375 | Hindang National High School | HINDANG | 5 |  | 6 | Construction/Completion (2STY6CL) |  | 146911.1219 | 146544.76 |  | Completed | 1 | [10 empty] | for advertisement
NC 2021 | SHS | Region VIII | Leyte | 303377 | Inopacan National High School | INOPACAN | 5 | 1 | 2 | Construction/Completion (2STY2CL SCI. LAB.) |  | 146911.1219 | 146544.76 |  | Completed | 1 | [10 empty] | for advertisement
NC 2021 | SHS | Region VIII | Leyte | 303377 | Inopacan National High School | INOPACAN | 5 |  | 2 | Construction/Completion (2STY2 ICT LAB.) |  | 146911.1219 | 146544.76 |  | Completed | 1 | [10 empty] | for advertisement
NC 2021 | SHS | Region VIII | Leyte | 303379 | Javier National High School | JAVIER (BUGHO) | 5 | 1 | 2 | Construction/Completion (2STY2CL SCI. LAB.) |  | 146911.1219 | 146544.76 |  | Completed | 1 | [10 empty] | for advertisement
NC 2021 | SHS | Region VIII | Leyte | 303398 | Mahaplag National High School | MAHAPLAG | 5 | 1 | 2 | Construction/Completion (2STY2CL SCI. LAB.) |  | 146911.1219 | 146544.76 |  | Completed | 1 | [10 empty] | for advertisement
NC 2021 | SHS | Region VIII | Leyte | 303398 | Mahaplag National High School | MAHAPLAG | 5 |  | 2 | Construction/Completion (2STY2 ICT LAB.) |  | 146911.1219 | 146544.76 |  | Completed | 1 | [10 empty] | for advertisement
NC 2021 | SHS | Region VIII | Leyte | 303405 | Matalom National High School | MATALOM | 5 | 1 | 2 | Construction/Completion (2STY2CL SCI. LAB.) |  | 146911.1219 | 146544.76 |  | Completed | 1 | [10 empty] | for advertisement
NC 2021 | SHS | Region VIII | Leyte | 303405 | Matalom National High School | MATALOM | 5 |  | 2 | Construction/Completion (2STY2 ICT LAB.) |  | 146911.1219 | 146544.76 |  | Completed | 1 | [10 empty] | for advertisement
NC 2021 | K10 | Region VIII | Ormoc City | 124145 | Biliboy Primary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124146 | Cambantog Primary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 140350 | 140000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124146 | Cambantog Primary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 501250 | 500000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124146 | Cambantog Primary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124147 | Camp Downes Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 80200 | 80000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124148 | Can-adieng Elementary School | ORMOC CITY | 4 | 1 |  | Construction of Slope Protection |  | 1002500 | 1000000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124150 | Dolores Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 501250 | 500000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124150 | Dolores Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124151 | Don Carlos Rivilla Elemetary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 1002500 | 1000000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124151 | Don Carlos Rivilla Elemetary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124152 | Donghol Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 200500 | 200000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124154 | Hugpa Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124155 | Ipil Central School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124155 | Ipil Central School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 501250 | 500000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124155 | Ipil Central School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 300750 | 300000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124156 | L. Y. Palou ES | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124158 | Liberty Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 140350 | 140000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124158 | Liberty Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 501250 | 500000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124158 | Liberty Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124159 | Luna Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124161 | Macabug Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124164 | Mahayag Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124164 | Mahayag Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124165 | Mahayahay Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 140350 | 140000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124165 | Mahayahay Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 1002500 | 1000000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124167 | Patag Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 1002500 | 1000000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124167 | Patag Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124167 | Patag Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124168 | Quezon Jr Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124169 | San Antonio Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124170 | Sumangga Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 1002500 | 1000000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124170 | Sumangga Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124171 | Balion Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124171 | Balion Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124171 | Balion Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 501250 | 500000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124172 | H. Serafica Elementary School (Bayog) | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124174 | Cabato-an Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124174 | Cabato-an Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124174 | Cabato-an Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 501250 | 500000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124175 | Cagbuhangin Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124175 | Cagbuhangin Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124176 | Catmon Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124176 | Catmon Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124176 | Catmon Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 140350 | 140000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124176 | Catmon Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 501250 | 500000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124177 | Concepcion Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 501250 | 500000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124178 | Guintiguian Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124180 | Inaad Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 501250 | 500000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124180 | Inaad Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124181 | Juaton Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 501250 | 500000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124182 | L. Cabahug Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124183 | Leondoni Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 140350 | 140000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124183 | Leondoni Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 501250 | 500000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124183 | Leondoni Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124184 | Manlilinao Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124185 | Matica-a Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 200500 | 200000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124185 | Matica-a Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124186 | Monterico Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124186 | Monterico Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 140350 | 140000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124186 | Monterico Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124187 | Nueva Vista Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124188 | Rufina Tan Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 501250 | 500000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124188 | Rufina Tan Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124189 | Sabang Bao Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124190 | San Jose Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124190 | San Jose Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 300750 | 300000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124193 | Valencia Central School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 501250 | 500000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124193 | Valencia Central School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124194 | Alegria Batuan ES | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124195 | Linao Central School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124195 | Linao Central School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 280700 | 280000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124195 | Linao Central School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124196 | Naungan Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124197 | Ormoc City SPED Center | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 501250 | 500000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124197 | Ormoc City SPED Center | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124198 | Punta Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124199 | Tambulilid Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 501250 | 500000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124199 | Tambulilid Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124200 | Airport Primary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124201 | Bagong Buhay Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124201 | Bagong Buhay Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124202 | Cabintan Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124203 | Cogon Central School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 300750 | 300000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124203 | Cogon Central School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124203 | Cogon Central School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 280700 | 280000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124203 | Cogon Central School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 501250 | 500000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124204 | Curva Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 1002500 | 1000000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124205 | Dayhagan Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124205 | Dayhagan Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124205 | Dayhagan Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 501250 | 500000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124206 | Domonar Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124207 | Doña Feliza Z. Mejia Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124208 | Esperanza Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124208 | Esperanza Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 1002500 | 1000000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124209 | Green Valley Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124209 | Green Valley Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 1002500 | 1000000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124209 | Green Valley Elementary School | ORMOC CITY | 4 |  |  | Construction of Slope Protection |  | 3007500 | 3000000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124210 | Lao Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124211 | JICA-Lao Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124211 | JICA-Lao Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124212 | Libertad Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124213 | Licuma Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124214 | Liloan Central School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124214 | Liloan Central School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124215 | Margen Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124215 | Margen Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 501250 | 500000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124217 | Nasunogan Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124217 | Nasunogan Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 140350 | 140000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124217 | Nasunogan Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124218 | Salvacion Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 501250 | 500000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124219 | San Isidro Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124219 | San Isidro Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 501250 | 500000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124219 | San Isidro Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124220 | San Juan Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124220 | San Juan Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 140350 | 140000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124220 | San Juan Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 501250 | 500000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124220 | San Juan Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124221 | San Pablo Elementary School (Simangan) | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 124222 | San Vicente Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 1002500 | 1000000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124222 | San Vicente Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 124223 | Sto. Nino Elementary School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 124223 | Sto. Nino Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 194501 | Ormoc City Central School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 200500 | 200000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 194501 | Ormoc City Central School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 194502 | VL Villacencio ES | ORMOC CITY | 4 | 1 | 2 | Construction/Completion (1STY2CL) |  | 915989.2625 | 913705 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 194502 | VL Villacencio Elementary School | ORMOC CITY | 4 |  |  | Construction of Slope Protection |  | 2005000 | 2000000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 194502 | VL Villacencio Elementary School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 303654 | Dolores National High School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 300750 | 300000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 303654 | Dolores National High School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 200500 | 200000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 303655 | Ipil National High School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 300750 | 300000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 303655 | Ipil National High School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 200500 | 200000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 303656 | Linao National High School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 300750 | 300000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 303656 | Linao National High School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 200500 | 200000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 303656 | Linao National High School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 1002500 | 1000000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 303657 | Margen National High School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 300750 | 300000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 303657 | Margen National High School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 200500 | 200000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 303657 | Margen National High School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 1002500 | 1000000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 303658 | New Ormoc City National High School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 1002500 | 1000000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 303658 | New Ormoc City National High School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 200500 | 200000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 303658 | New Ormoc City National High School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 1002500 | 1000000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 303660 | Rustico Capahi Sr. Memorial National High School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 200500 | 200000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 303660 | Rustico Capahi Sr. Memorial National High School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 300750 | 300000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 303661 | Genaro B. Lureñana National High School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 300750 | 300000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 303661 | Genaro B. Lureñana National High School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 200500 | 200000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 303662 | Valencia National High School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 200500 | 200000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 303662 | Valencia National High School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 1002500 | 1000000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 313901 | Lilo-an National High School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 300750 | 300000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 313901 | Lilo-an National High School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 200500 | 200000 |  | Completed | 1 | [10 empty] | On-Going
NC 2021 | K10 | Region VIII | Ormoc City | 313902 | Pedro G. Bañez National High School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 313902 | Pedro G. Bañez National High School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 280700 | 280000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 313902 | Pedro G. Bañez National High School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 1002500 | 1000000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 313902 | Pedro G. Bañez National High School | ORMOC CITY | 4 |  |  | Construction of Slope Protection |  | 1002500 | 1000000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 313903 | Cabintan National High School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 313903 | Cabintan National High School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 200500 | 200000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 313904 | Matica-a National High School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 300750 | 300000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 313904 | Matica-a National High School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 200500 | 200000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 313904 | Matica-a National High School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 280700 | 280000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 313904 | Matica-a National High School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 501250 | 500000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 313905 | Ormoc City Night High School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 200500 | 200000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 313906 | Julian C. Gantuangco NHS | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 313906 | Julian C. Gantuangco NHS | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 200500 | 200000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 330523 | Ormoc City Senior High School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 200500 | 200000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 344795 | Ormoc City Regional Sports Academy | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 344795 | Ormoc City Regional Sports Academy | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 200500 | 200000 |  | COMPLETED | 1
NC 2021 | K10 | Region VIII | Ormoc City | 501363 | Mas-in Integrated School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 200500 | 200000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 501363 | Mas-in Integrated School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 501363 | Mas-in Integrated School | ORMOC CITY | 4 |  | 1 | Construction/Completion of School Buildings |  | 280700 | 280000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Ormoc City | 501364 | Gaas Integrated School | ORMOC CITY | 4 | 1 | 1 | Construction/Completion of School Buildings |  | 100250 | 100000 |  | Completed | 1 | [10 empty] | NYS
NC 2021 | K10 | Region VIII | Samar (Western Samar) | 123871 | Conant Elementary School | VILLAREAL | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 13085393.6544 | 13052761.75 | 12987332.95 | COMPLETED | 1 | 2022-04-09 |  |  | 21IK0055(FLR) |  | 2021-06-16 | 2021-06-28 |  | 2021-09-21 | ADB DYNAMIC BUILDERS
NC 2021 | K10 | Region VIII | Southern Leyte | 303451 | Divisoria NHS | BONTOC | 0 | 1 | 6 | Construction/Completion (2STY6CL) |  | 5213000 | 5200000 |  | COMPLETED | 1
NC 2022 | K10 | Region VIII | Biliran | 120777 | Canila ES | BILIRAN | 0 | 1 | 3 | Construction of 1-Storey-3 Classroom with 1 unit of toilet per classroom, and 1-Unit Water Tank. | 2 |  | 6015000 |  | Completed | 1 |  |  |  |  | 2022-06-12 | 2022-12-14 | 2022-12-27 | 2023-11-01 | 2023-01-31 | DOUBLE J AND T CONSTRUCTION AND SUPPLY CORPORATION
NC 2022 | K10 | Region VIII | Biliran | 120795 | Salawad Elementary School | CABUCGAYAN | 0 | 1 | 2 | Construction of New - 1 -Storey, 2-Classroom School Building with 2 unit toilet per classroom, 1 Unit Water Tank, and concrete pavement for pathway | 2 |  | 5513750 |  | Completed | 1 |  |  |  |  | 2022-06-12 | 2022-12-14 | 2022-12-27 | 2023-11-01 | 2023-01-31 | MAI CONST & SUPPLY | Issued Monthly Time Suspension
NC 2022 | K10 | Region VIII | Biliran | 120797 | Alegria ES | CAIBIRAN | 0 | 1 | 2 | Construction of New - 1 -Storey, 2-Classroom School Building with 1-unit toilet per classroom and 1-Unit Water Tank. | 2 |  | 5012500 |  | Completed | 1 |  |  |  |  | 2022-06-12 | 2022-12-14 | 2022-12-27 | 2023-11-01 | 2023-01-31 | MAI CONST & SUPPLY | Issued Monthly Time Suspension
NC 2022 | K10 | Region VIII | Biliran | 500410 | Union Integrated School | CAIBIRAN | 0 | 1 | 4 | Construction of New 2-Units 1-Storey 2-Classroom with window grille (front & rear) and 2-Unit toilet attached per classroom with concrete pavement for pathway, with embankment and stone masonry structure | 2 |  | 7518750 |  | Completed | 1 |  |  |  |  | 2022-06-12 | 2022-12-14 | 2022-12-27 | 2023-11-01 | 2023-01-31 | DINA RBS & SUPPLY INC. | Issued Notice To Proceed dated May 9, 2023
NC 2022 | K10 | Region VIII | Biliran | 120819 | Calipayan ES | CULABA | 0 | 1 | 2 | Construction of New - 1 -Storey 2-Classroom School Building with 1 unit toilet per classroom , 1 Unit Water Tank, and Slope Protection Structure | 2 |  | 5764375 |  | Completed | 1 |  |  |  |  | 2022-06-12 | 2022-12-14 | 2022-12-27 | 2023-11-01 | 2023-01-31 | MPJR BUILDERS COMPANY
NC 2022 | K10 | Region VIII | Biliran | 500411 | Inasuyan Integrated School | KAWAYAN | 0 | 1 | 4 | Construction of New 2-Units 1-Storey 2-Classroom with window grille (front & rear) and 2-Unit toilet attached per classroom with concrete pavement for pathway, and with embankment. | 2 |  | 7518750 |  | Completed | 1 |  |  |  |  | 2022-06-12 | 2022-12-14 | 2022-12-27 | 2023-11-01 | 2023-01-31 | CYJE FIRST BUILDERS CONSTRUCTION CORP | FOR PUNCHLIST COMPLIANCE
NC 2022 | K10 | Region VIII | Eastern Samar | 122517 | San Miguel Elementary School | GIPORLOS | 0 | 1 | 2 | 1STY2CL | 2 |  | 6215500 |  | Completed | 1 | 2023-09-17
NC 2022 | K10 | Region VIII | Eastern Samar | 122477 | Cacatmonan Primary School | HERNANI | 0 | 1 | 2 | 1STY2CL | 2 |  | 6416000 |  | ongoing | 0.6 | 2023-10-02
NC 2022 | K10 | Region VIII | Eastern Samar | 122572 | Cagmanaba Elementary School | JIPAPAD | 0 | 1 | 2 | 1STY2CL | 2 |  | 6215500 |  | Completed | 1 | 2023-07-19
NC 2022 | K10 | Region VIII | Eastern Samar | 122352 | San Isidro Primary School | LAWAAN | 0 | 1 | 2 | 1STY2CL | 2 |  | 6315750 |  | Completed | 1 | 2023-09-17
NC 2022 | K10 | Region VIII | Eastern Samar | 122462 | Maputi Elementary School | MASLOG | 0 | 1 | 2 | 1STY2CL | 2 |  | 6315750 |  | ongoing | 0.74 | 2023-08-23
NC 2022 | K10 | Region VIII | Eastern Samar | 122538 | Busay Primary School | MERCEDES | 0 | 1 | 2 | 1STY2CL | 2 |  | 6516250 |  | Completed | 1 | 2023-05-29
NC 2022 | K10 | Region VIII | Eastern Samar | 122735 | Bangon Elementary School | SAN POLICARPO | 0 | 1 | 2 | 1STY2CL | 2 |  | 5513750 |  | Completed | 1 | 2023-10-02
NC 2022 | K10 | Region VIII | Leyte | 121882 | Victoria Elementary School | SANTA FE | 1 | 1 | 2 | 1STY2CL | 2 |  | 4974918.7111 |  | completed | 1 | 2023-03-28 | 2023-07-06 | P00675046VS-CW1 | 22IC0097 | 2023-01-10 |  | 2023-01-31 | 2023-03-15 | 2023-03-22
NC 2022 | K10 | Region VIII | Leyte | 121946 | Burak Elementary School | TOLOSA | 1 | 1 | 2 | 1STY2CL | 2 |  | 4781018.7901 |  | completed | 1 | 2023-02-24 | 2023-06-02 | P00675047VS-CW1 | 22IC0098 | 2023-01-10 |  | 2023-01-31 | 2023-02-20 | 2023-02-24
NC 2022 | K10 | Region VIII | Leyte | 121521 | Caridad Primary School | Julita | 2 | 1 | 2 | 1STY2CL | 2 |  | 5012500 | 4969193.56 | Completed | 1 |  | 2023-06-02 | P00675048VS | 22ID0071 |  | 2022-02-12 | 2022-12-15 | 2022-12-23 | 2023-12-01
NC 2022 | K10 | Region VIII | Leyte | 121560 | Buracan Elementary School | La Paz | 2 | 1 | 2 | 1STY2CL | 2 |  | 5036715.8487 | 4982923.77 | Completed | 1 |  | 2023-06-16 | P00675049VS | 22ID0072 |  | 2022-02-12 | 2022-12-15 | 2022-12-23 | 2023-12-01
NC 2022 | K10 | Region VIII | Leyte | 121621 | Macarthur Central School | MACARTHUR | 2 | 1 | 2 | 1STY2CL | 2 |  | 5036715.8487 | 4940041.58 | Completed | 1 |  | 2023-06-02 | P00675050VS | 22ID0070 |  | 2022-02-12 | 2022-12-15 | 2022-12-23 | 2023-12-01
NC 2022 | K10 | Region VIII | Leyte | 121711 | Talisay Elementary School | Mayorga | 2 | 1 | 2 | 1STY2CL | 2 |  | 5012500 | 4936292.45 | Completed | 1 |  | 2023-06-02 | P00675051VS | 22ID0068 |  | 2022-02-12 | 2022-12-15 | 2022-12-23 | 2023-12-01
NC 2022 | K10 | Region VIII | Leyte | 121809 | Aringit Primary School | Pastrana | 2 | 1 | 2 | 1STY2CL | 2 |  | 5012500 | 4982923.77 | Completed | 1 |  | 2023-06-16 | P00675052VS | 22ID0073 |  | 2022-02-12 | 2022-12-15 | 2022-12-23 | 2023-12-01
NC 2022 | K10 | Region VIII | Leyte | 121907 | Amandangay Elementary School | Tabontabon | 2 | 1 | 2 | 1STY2CL | 2 |  | 5071123.0521 | 4995277.8 | Completed | 1 |  | 2023-06-02 | P00675053VS | 22ID0069 |  | 2022-02-12 | 2022-12-15 | 2022-12-23 | 2023-12-01
NC 2022 | K10 | Region VIII | Leyte | 121961 | Tunga Central School | Tunga | 2 | 1 | 2 | 1STY2CL | 2 |  | 5012500 | 4977249.25 | Completed | 1 |  | 2023-06-16 | P00675054VS | 22ID0074 |  | 2022-02-12 | 2022-12-15 | 2022-12-23 | 2023-12-01
NC 2022 | K10 | Region VIII | Leyte | 121726 | Macario Elementary School | Merida | 4 | 1 | 2 | Construction of 1-Storey 2-Classroom with window grille (front & rear) and 2-Unit toilet attached per classroom | 2 |  | 4611500 | Original Contract Cost = 4,576,998.75 Revised Contract Cost = 4,600,000.00 | Completed | 1 |  | 2023-03-23 | P00675055VS | 22IF0096 | 2022-08-25 | 2022-02-09 | 2022-09-14 | 2022-09-21 | 2022-11-24
NC 2022 | K10 | Region VIII | Leyte | 121410 | Ma-asin Elementary School | Hindang | 5 | 1 | 3 | 1STY3CL | 2 |  | 7869892.2866 | 7693261.29 | completed | 1 | 2023-06-01 | 2023-01-06 | P00675056VS-CW1 | 22IG0083 | 2022-11-23 | 2022-12-01 | 2022-12-13 | 2022-12-19 | 2022-12-28
NC 2022 | K10 | Region VIII | Northern Samar | 122783 | Jubasan ES | ALLEN | 1 | 1 | 4 | 2STY4CL | 2 |  | 11027500 | 10991431.72 | Completed | 1 | 2023-07-21 | 2023-07-21 | P00675057VS | 22IH0132 |  | 2022-12-02 | 2022-12-26 | 2022-12-27 | 2023-01-23
NC 2022 | K10 | Region VIII | Northern Samar | 122794 | Langub-Langub ES | BIRI | 1 | 1 | 2 | 1STY2CL | 2 |  | 5714250 | 5694545.76 | Completed | 1 | 2024-02-29 | 2024-02-29 | P00675058VS | 22IH0129 |  | 2022-11-22 | 2022-12-14 | 2022-12-22 | 2023-01-23 |  | Delayed due to obstruction at site. Work suspension order No.1 submitted for approval.
NC 2022 | K10 | Region VIII | Northern Samar | 122825 | Landusan ES | CAPUL | 1 | 1 | 2 | 1STY2CL | 2 |  | 5413500 | 5339822.27 | Completed | 1 | 2023-04-18 | 2023-04-18 | P00675059VS | 22IH0131 |  | 2022-12-02 | 2022-12-26 | 2022-12-27 | 2023-01-25
NC 2022 | K10 | Region VIII | Northern Samar | 123117 | Cahicsan Elementary School | MONDRAGON | 1 | 1 | 3 | CONSTRUCTION OF 1STY3CL AND SLOPE PROTECTION | 2 |  | 8255933.7034 | 8227765.83 | Completed | 1 | 2023-06-15 | 2023-06-15 | P00675060VS | 22IH0135 |  | 2022-12-02 | 2022-12-26 | 2022-12-27 | 2023-01-23
NC 2022 | K10 | Region VIII | Northern Samar | 123192 | Jamo-og ES | ROSARIO | 1 | 1 | 2 | 1STY2CL | 2 |  | 5213000 | 5196323.49 | Completed | 1 | 2023-05-27 | 2023-10-01 | P00675061VS | 22IH0130 |  | 2022-11-28 | 2022-12-22 | 2022-12-27 | 2023-01-23 |  | The project is already ongoing. Submitted request for data correction in CWA due to incorrect contract amount.
NC 2022 | K10 | Region VIII | Northern Samar | 123204 | San Nicolas ES | SAN ANTONIO | 1 | 1 | 2 | 1STY2CL | 2 |  | 5714250 | 5693453.66 | Completed | 1 | 2023-05-27 | 2023-05-27 | P00675062VS | 22IH0127 |  | 2022-11-22 | 2022-12-14 | 2022-12-22 | 2023-01-23
NC 2022 | K10 | Region VIII | Northern Samar | 123222 | Bonglas PS | SAN JOSE | 1 | 1 | 2 | 1STY2CL | 2 |  | 5213000 | 5193735.3 | Completed | 1 | 2023-05-27 | 2023-07-26 | P00675063VS | 22IH0134 |  | 2022-12-02 | 2022-12-26 | 2022-12-27 | 2023-01-23 |  | Delay due to ROW issue. 60cd Contract Time Extension No. 1 submitted for approval.
NC 2022 | K10 | Region VIII | Northern Samar | 123247 | San Vicente CS | SAN VICENTE | 1 | 1 | 2 | 1STY2CL | 2 |  | 5714250 | 5665056.28 | Completed | 1 | 2023-05-29 | 2023-05-29 | P00675064VS | 22IH0128 |  | 2022-11-22 | 2022-12-14 | 2022-12-22 | 2023-01-25 |  | Contract Time Extension No. 1 due to unworkable days under preparation.
NC 2022 | K10 | Region VIII | Northern Samar | 123278 | Lungib ES | VICTORIA | 1 | 1 | 2 | 1STY2CL | 2 |  | 5313250 | 5293066.38 | Completed | 1 | 2023-05-27 | 2023-05-27 | P00675065VS | 22IH0133 |  | 2022-02-12 | 2022-12-26 | 2022-12-27 | 2023-01-23 |  | Contract Time Extension No. 1 due to unworkable days under preparation.
NC 2022 | K10 | Region VIII | Northern Samar | 123001 | Pio Del Pilar ES | LAPINIG | 2 | 1 | 2 | 1STY2CL | 2 |  | 5513750 | 5466912.51 | Completed | 1 | 2023-09-21 | 2023-04-12 | P00675066VS | 23II0056 | 2023-04-15 | 2023-04-30 | 2023-07-05 | 2023-08-05 | 2023-05-18
NC 2022 | K10 | Region VIII | Northern Samar | 123104 | Burgos ES | MAPANAS | 2 | 1 | 2 | 1STY2CL | 2 |  | 5112750 | 5053481.69 | Completed | 1 | 2023-06-10 | 2023-11-15 | P00675067VS | 23II0057 | 2023-04-15 | 2023-04-30 | 2023-07-05 | 2023-05-26 | 2023-05-06
NC 2022 | K10 | Region VIII | Samar (Western Samar) | 123297 | San Isidro Elementary School | ALMAGRO | 1 | 1 | 2 | 1STY2CL | 2 |  | 5714250 | 5631600 | Completed | 1 | 2023-03-25 | 2023-05-24 | P00675068VS-CW1 | 22IJ0100 | 2022-05-10 | 2022-10-13 | 2022-10-25 | 2022-11-21 | 2022-11-25
NC 2022 | K10 | Region VIII | Samar (Western Samar) | 123549 | Matuguinao Central Elementary School | MATUGUINAO | 1 | 1 | 2 | 1STY2CL | 2 |  | 5328265.7758 | 5251033.66 | Completed | 1 | 2023-05-14 | 2023-05-14 | P00675069VS-CW1 | 22IJ0099 | 2022-05-10 | 2022-10-13 | 2022-10-25 | 2022-11-21 | 2022-11-25
NC 2022 | K10 | Region VIII | Samar (Western Samar) | 123652 | Calanyugan Elementary School | PAGSANGHAN | 1 | 1 | 2 | 1STY2CL | 2 |  | 5232238.1655 | 5166686.97 | Completed | 1 | 2023-03-25 | 2023-03-25 | P00675070VS-CW1 | 22IJ0097 | 2022-05-10 | 2022-10-13 | 2022-10-25 | 2022-11-21 | 2022-11-25
NC 2022 | K10 | Region VIII | Samar (Western Samar) | 123807 | Ilijan Elementary School | SANTO NIÑO | 1 | 1 | 2 | 1STY2CL | 2 |  | 5714250 | 5644807.86 | Completed | 1 | 2023-03-25 | 2023-03-29 | P00675071VS-CW1 | 22IJ0098 | 2022-05-10 | 2022-10-13 | 2022-10-25 | 2022-11-21 | 2022-11-25
NC 2022 | K10 | Region VIII | Samar (Western Samar) | 123826 | San Vicente Elementary school | TAGAPUL-AN | 1 | 1 | 2 | 1STY2CL | 2 |  | 6015000 | 5938022.03 | Completed | 1 | 2023-03-25 | 2023-03-25 | P00675072VS-CW1 | 22IJ0101 | 2022-05-10 | 2022-10-13 | 2022-10-25 | 2022-11-21 | 2022-11-25
NC 2022 | K10 | Region VIII | Samar (Western Samar) | 281506 | Flora Mabaet Mabansag Elementary School | JIABONG | 2 | 1 | 2 | 1STY2CL | 2 |  | 5012500 | 4988999.85 | Completed | 1 | 2023-08-15 | 2023-08-15 | 22IK0121 | 22IK0121 | 2022-11-14 | 2022-02-12 | 2022-12-14 | 2022-12-19 | 2022-12-23
NC 2022 | K10 | Region VIII | Samar (Western Samar) | 123620 | Tinabanan Elementary School | MARABUT | 2 | 1 | 2 | 1STY2CL | 2 |  | 5012500 | 4987999.67 | Completed | 1 | 2023-08-15 | 2023-08-15 | 22IK0123 | 22IK0123 | 2022-11-14 | 2022-02-12 | 2022-12-14 | 2022-12-19 | 2022-12-23
NC 2022 | K10 | Region VIII | Samar (Western Samar) | 501374 | Inobongan Integrated School | SAN SEBASTIAN | 2 | 1 | 2 | 1STY2CL | 2 |  | 5012500 | 4987999.34 | Completed | 1 | 2023-08-15 | 2023-08-15 | 22IK0124 | 22IK0124 | 2022-11-14 | 2022-02-12 | 2022-12-14 | 2022-12-19 | 2022-12-23
NC 2022 | K10 | Region VIII | Samar (Western Samar) | 123899 | Navatas Guti Elementary School | TALALORA | 2 | 1 | 2 | 1STY2CL | 2 |  | 5012500 | 4989999.58 | Completed | 1 | 2023-08-15 | 2023-08-15 | 22IK0122 | 22IK0122 | 2022-11-14 | 2022-02-12 | 2022-12-14 | 2022-12-19 | 2022-12-23
NC 2022 | K10 | Region VIII | Samar (Western Samar) | 123974 | Marapilit Elementary School | ZUMARRAGA | 2 | 1 | 2 | 1STY2CL | 2 |  | 5012500 | 4989999.23 | Completed | 1 | 2023-08-15 | 2023-08-15 | 22IK0125 | 22IK0125 | 2022-11-14 | 2022-02-12 | 2022-12-14 | 2022-12-19 | 2022-12-23
NC 2022 | K10 | Region VIII | Southern Leyte | 122071 | Hinundayan Central School | HINUNDAYAN | 0 | 1 | 4 | 2STY4CL | 2 |  | 15786626.0648 |  | Completed | 1 | 2023-10-27
NC 2022 | K10 | Region VIII | Southern Leyte | 122218 | Bunga Elementary Multi-Grade School | PADRE BURGOS | 0 | 1 | 2 | 1STY2CL | 2 |  | 6213677.5853 |  | Completed | 1 | 2023-07-29
NC 2022 | K10 | Region VIII | Southern Leyte | 501048 | Saub Integrated School | SAN RICARDO | 0 | 1 | 2 | 1STY2CL | 2 |  | 6106866.6639 |  | Completed | 1 | 2023-08-28
NC 2022 | K10 | Region VIII | Southern Leyte | 122321 | San Isidro Elementary School | TOMAS OPPUS | 0 | 1 | 2 | 1STY2CL | 2 |  | 6156991.6639 |  | Completed | 1 | 2023-07-19
NC 2022 | SHS | Region VIII | Biliran | 303334 | Viga National High School | MARIPIPI | 0 | 1 | 2 | Complete Construction of 1-Storey, 2-Classroom School Building with Window Grilles (Front & Rear) with 4-unit toilet dettached, and Stone Masonry Structure. | 2 |  | 5513750 |  | Completed | 1
NC 2022 | SHS | Region VIII | Southern Leyte | 303480 | San Isidro NHS | TOMAS OPPUS | 0 | 1 | 4 | 2STY4CL | 2 |  | 14833447.6513 |  | Completed | 1 | 2023-10-27
NC 2023 | K10 | Region VIII | Baybay City | 305817 | Maganhan National High School | CITY OF BAYBAY |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4887500 | completed | 1 | 2024-03-12 | 2024-04-29 | 23IG0139 | 45197 | 2023-09-28 | 2023-10-10 | 2023-10-30 | 2023-11-07 |  | JDR CONSTRUCTION
NC 2023 | K10 | Region VIII | Baybay City |  | Punta National High School | CITY OF BAYBAY |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4532500 | completed | 1 | 2024-03-12 | 2024-03-12 | 23IG0138 | 45197 | 2023-09-28 | 2023-10-10 | 2023-10-30 | 2023-11-07 |  | AICON INDUSTRIES
NC 2023 | K10 | Region VIII | Baybay City | 121093 | Sta. Cruz Elementary School | CITY OF BAYBAY |  | 1 |  | 4 | Batch 1 | 15131250 | 15000000 | 14737500 | completed | 1 | 2024-08-31 | 2024-04-24 | 23IG0130 | 45140 | 2023-08-02 | 2023-08-15 | 2023-08-25 | 2023-09-01 |  | ACESCAPE CONSTRUCTION
NC 2023 | K10 | Region VIII | Biliran | 120763 | Lo-ok ES | ALMERIA |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | completed | 1
NC 2023 | SHS | Region VIII | Biliran | 303332 | Tabunan National High School | ALMERIA |  | 1 |  | 3 | Batch 1 | 7943906.25 | 7875000 |  | completed | 1
NC 2023 | SHS | Region VIII | Biliran | 303320 | Biliran National Agricultural High School | BILIRAN |  | 1 |  | 3 | Batch 1 | 7565625 | 7500000 |  | completed | 1
NC 2023 | K10 | Region VIII | Biliran | 120782 | Pinangomhan ES | BILIRAN |  | 1 |  | 2 | Batch 1 | 5548125 | 5500000 |  | completed | 1
NC 2023 | SHS | Region VIII | Biliran | 303322 | Cabucgayan National School of Arts and Trade | CABUCGAYAN |  |  |  | 1 | Batch 1 | 3026250 | 3000000 |  | completed | 1
NC 2023 | K10 | Region VIII | Biliran | 120795 | Salawad Elementary School | CABUCGAYAN |  | 1 |  | 2 | Batch 1 | 5548125 | 5500000 |  | completed | 1
NC 2023 | K10 | Region VIII | Biliran | 120798 | Asug ES | CAIBIRAN |  | 1 |  | 8 | Batch 1 | 20175000 | 20000000 |  | completed | 1
NC 2023 | K10 | Region VIII | Biliran | 120801 | Cabibihan ES | CAIBIRAN |  | 1 |  | 1 | Batch 1 | 3026250 | 3000000 |  | completed | 1
NC 2023 | K10 | Region VIII | Biliran | 120809 | Manlabang ES | CAIBIRAN |  | 1 |  | 1 | Batch 1 | 3026250 | 3000000 |  | completed | 1
NC 2023 | SHS | Region VIII | Biliran | 303321 | Bool NHS | CULABA |  | 1 |  | 20 | Batch 1 | 55481250 | 55000000 |  | completed | 1
NC 2023 | SHS | Region VIII | Biliran | 303333 | Tucdao National High School | KAWAYAN |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | completed | 1
NC 2023 | K10 | Region VIII | Biliran | 120844 | Ungale II Elementary School | KAWAYAN |  | 1 |  | 1 | Batch 1 | 3026250 | 3000000 |  | completed | 1
NC 2023 | K10 | Region VIII | Biliran | 120846 | Agutay ES | MARIPIPI |  | 1 |  | 2 | Batch 1 | 5548125 | 5500000 |  | completed | 1
NC 2023 | K10 | Region VIII | Biliran | 120872 | Eden Elementary School | NAVAL (Capital) |  | 1 |  | 1 | Batch 1 | 3026250 | 3000000 |  | completed | 1
NC 2023 | K10 | Region VIII | Biliran | 120875 | Libtong Daku ES | NAVAL (Capital) |  | 1 |  | 1 | Batch 1 | 3026250 | 3000000 |  | completed | 1
NC 2023 | K10 | Region VIII | Biliran | 120876 | Libtong Gamay Elementary School | NAVAL (Capital) |  | 1 |  | 1 | Batch 1 | 3026250 | 3000000 |  | completed | 1
NC 2023 | K10 | Region VIII | Biliran | 120878 | Lucsoon ES | NAVAL (Capital) |  | 1 |  | 1 | Batch 1 | 3026250 | 3000000 |  | completed | 1
NC 2023 | SHS | Region VIII | Biliran | 303330 | Naval National High School | NAVAL (Capital) |  | 1 |  | 3 | Batch 1 | 7565625 | 7500000 |  | completed | 1
NC 2023 | K10 | Region VIII | Biliran | 120864 | Talustusan ES | NAVAL (Capital) |  | 1 |  | 1 | Batch 1 | 3026250 | 3000000 |  | completed | 1
NC 2023 | K10 | Region VIII | Biliran | 120882 | VILLACANEJA ELEMENTARY SCHOOL | NAVAL (Capital) |  | 1 |  | 1 | Batch 1 | 3026250 | 3000000 |  | completed | 1
NC 2023 | K10 | Region VIII | Calbayog City | 194001 | Calbayog City SPED Center | CALBAYOG CITY |  | 1 |  | 11 | Batch 1 | 32141038.54 | 31862243.9 | 31709305 | completed | 1 | 2024-08-02 | 2025-01-20 | P00775186VS-CW1 | 23IJ-0108 | 2023-12-16 | 2023-12-28 | 2024-01-09 | 2024-01-23 | 2024-03-01
NC 2023 | K10 | Region VIII | Catbalogan City | 123427 | Rama Elementary School | CITY OF CATBALOGAN (Capital) |  | 1 |  | 5 | Batch 1 | 10732989.77 | 10639890.72 | 10639276.38 | COMPLETED | 1 |  | 2024-06-17 | 23IK0116 | 23IK0116 | 2023-12-08 | 2023-12-15 | 2023-12-28 | 2024-01-08 | 2024-01-19
NC 2023 | K10 | Region VIII | Eastern Samar | 122329 | Buenavista Elementary School | ARTECHE |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | under procurement | 0
NC 2023 | K10 | Region VIII | Eastern Samar | 122341 | Balangiga Central Elementary School | BALANGIGA |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | under procurement | 0
NC 2023 | K10 | Region VIII | Eastern Samar | 122618 | Guinpoliran Elementary School | BALANGKAYAN |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | under procurement | 0
NC 2023 | SHS | Region VIII | Eastern Samar | 313501 | Can-avid National High School | CAN-AVID |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | under procurement | 0
NC 2023 | K10 | Region VIII | Eastern Samar | 192517 | Caybane Primary School | DOLORES |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | under procurement | 0
NC 2023 | K10 | Region VIII | Eastern Samar | 122451 | Dapdap Central Elementary School | DOLORES |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | under procurement | 0
NC 2023 | K10 | Region VIII | Eastern Samar | 192512 | Darahoway Elementary School | DOLORES |  | 1 |  | 2 | Batch 1 | 6859500 | 6800000 |  | under procurement | 0
NC 2023 | SHS | Region VIII | Eastern Samar | 303499 | Dolores National High School | DOLORES |  | 1 |  | 8 | Batch 1 | 23201250 | 23000000 |  | under procurement | 0
NC 2023 | K10 | Region VIII | Eastern Samar | 122478 | Calutan Primary School | GENERAL MACARTHUR |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | under procurement | 0
NC 2023 | K10 | Region VIII | Eastern Samar | 305563 | Vigan National High School | GENERAL MACARTHUR |  | 1 |  | 8 | Batch 1 | 24001188.75 | 23793000 |  | under procurement | 0
NC 2023 | K10 | Region VIII | Eastern Samar | 122516 | Salvacion Elementary School | GIPORLOS |  | 1 |  | 2 | Batch 1 | 5936493.75 | 5885000 |  | under procurement | 0
NC 2023 | K10 | Region VIII | Eastern Samar | 122560 | Cantahay Elementary School | GUIUAN |  | 1 |  | 2 | Batch 1 | 5850750 | 5800000 |  | under procurement | 0
NC 2023 | K10 | Region VIII | Eastern Samar | 122492 | Padang Elementary School | HERNANI |  | 1 |  | 2 | Batch 1 | 5850750 | 5800000 |  | under procurement | 0
NC 2023 | K10 | Region VIII | Eastern Samar | 122572 | Cagmanaba Elementary School | JIPAPAD |  | 1 |  | 2 | Batch 1 | 6622443.75 | 6565000 |  | under procurement | 0
NC 2023 | K10 | Region VIII | Eastern Samar | 303497 | Bolusao National High School | LAWAAN |  | 1 |  | 2 | Batch 1 | 5810400 | 5760000 |  | under procurement | 0
NC 2023 | K10 | Region VIII | Eastern Samar | 122352 | San Isidro Primary School | LAWAAN |  | 1 |  | 2 | Batch 1 | 6626478.75 | 6569000 |  | under procurement | 0
NC 2023 | K10 | Region VIII | Eastern Samar | 122594 | Llorente Central Elementary School | LLORENTE |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | under procurement | 0
NC 2023 | SHS | Region VIII | Eastern Samar | 313514 | Maydolong National High School | MAYDOLONG |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | under procurement | 0
NC 2023 | K10 | Region VIII | Eastern Samar | 122649 | Saurong Elementary School | ORAS |  | 1 |  | 2 | Batch 1 | 5850750 | 5800000 |  | under procurement | 0
NC 2023 | K10 | Region VIII | Eastern Samar | 122728 | Pagbabangnan Elementary School | SAN JULIAN |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | under procurement | 0
NC 2023 | SHS | Region VIII | Eastern Samar | 303529 | Taft National High School | TAFT |  | 1 |  | 2 | Batch 1 | 5850750 | 5800000 |  | under procurement | 0
NC 2023 | K10 | Region VIII | Leyte | 313331 | Alangalang Night High School | ALANGALANG |  | 1 |  | 6 | Batch 1 | 15131250 | 15000000 | 16377168.67 | ONGOING | 0.95 | 2024-08-05 | 2024-08-05 | P00775210VS-CW1 | 23IC0159 | 2023-09-13 | 2023-09-21 | 2023-05-10 | 2023-11-15 | 2023-11-21
NC 2023 | K10 | Region VIII | Leyte | 191561 | Hinapolon Primary School | ALANGALANG |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 5006672.73 | COMPLETED | 1 | 2024-02-29 | 2024-06-03 | P00775209VS-CW1 | 23IC0157 | 2024-08-25 | 2023-07-09 | 2023-09-19 | 2023-11-13 | 2023-11-16
NC 2023 | SHS | Region VIII | Leyte | 303421 | Emeterio-Federica Gerez National High School | BABATNGON |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4999994.88 | COMPLETED | 1 | 2024-05-03 | 2024-05-03 | P00775212VS-CW1 | 23IC0160 | 2024-08-25 | 2023-07-09 | 2023-09-19 | 2023-11-14 | 2023-11-21
NC 2023 | SHS | Region VIII | Leyte | 303413 | Pagsulhugon National High School | BABATNGON |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 5002551.02 | COMPLETED | 1 | 2024-10-02 | 2024-03-04 | P00775211VS-CW1 | 23IC0151 | 2023-08-29 | 2023-08-09 | 2023-09-21 | 2023-10-24 | 2023-10-30
NC 2023 | SHS | Region VIII | Leyte | 313335 | Palo National High School-Pawing Annex | PALO |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 12951043.66 | COMPLETED | 1 | 2024-03-18 | 2024-03-18 | P00775215VS-CW1 | 23IC0162 | 2023-06-09 | 2023-09-15 | 2023-09-28 | 2023-10-23 | 2023-10-26
NC 2023 | K10 | Region VIII | Leyte | 121761 | San Antonio Elementary School | PALO |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 5576495.66 | COMPLETED | 1 | 2024-05-03 | 2024-05-03 | P00775213VS-CW1 | 23IC0161 | 2024-08-25 | 2023-07-09 | 2023-09-19 | 2023-11-15 | 2023-11-21 |  | NO BUILDABLE SPACE
NC 2023 | K10 | Region VIII | Leyte | 191518 | Tacuranga Elementary School | PALO |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | reverted | 0 | [10 empty] | NO BUILDABLE SPACE
NC 2023 | SHS | Region VIII | Leyte | 303426 | San Miguel National High School | SAN MIGUEL |  | 1 |  | 6 | Batch 1 | 15131250 | 15000000 | 16749962.31 | COMPLETED | 1 | 2024-11-04 | 2024-01-05 | P00775216VS-CW1 | 23IC0163 | 2023-09-13 | 2023-09-21 | 2023-05-10 | 2023-10-23 | 2023-10-27
NC 2023 | SHS | Region VIII | Leyte | 303429 | Sta. Cruz National High School | SAN MIGUEL |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 5580558 | COMPLETED | 1 | 2024-10-02 | 2024-01-31 | P00775217VS-CW1 | 23IC0164 | 2024-08-25 | 2023-07-09 | 2023-09-19 | 2023-10-24 | 2023-10-30
NC 2023 | K10 | Region VIII | Leyte | 121870 | Catoogan Elementary School | SANTA FE |  | 1 |  | 2 | Batch 1 | 5159756.25 | 5115000 |  | reverted | 0 | [10 empty] | delisted
NC 2023 | K10 | Region VIII | Leyte | 303430 | Sta. Fe National High School | SANTA FE |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 5046508.95 | COMPLETED | 1 | 2024-07-02 | 2024-02-28 | P00775219VS-CW1 | 23IC0156 | 2024-08-25 | 2023-07-09 | 2023-09-19 | 2023-10-23 | 2023-10-26
NC 2023 | SHS | Region VIII | Leyte | 305523 | Sta. Fe Stand Alone Senior High School | SANTA FE |  | 1 |  | 6 | Batch 1 | 15131250 | 15000000 | 17113345.88 | COMPLETED | 1 | 2024-08-05 | 2024-04-22 | P00775220VS-CW1 | 23IC0165 | 2023-09-13 | 2023-09-21 | 2023-05-10 | 2023-11-15 | 2023-11-21
NC 2023 | K10 | Region VIII | Leyte | 121918 | Amanluran Elementary School | TANAUAN |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4998887.82 | COMPLETED | 1 | 2024-02-29 | 2024-02-29 | P00775221VS-CW1 | 23IC0155 | 2023-08-29 | 2023-08-09 | 2023-09-21 | 2023-11-13 | 2023-11-16
NC 2023 | K10 | Region VIII | Leyte | 121936 | Guindag-an Elementary School | TANAUAN |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4987762.64 | COMPLETED | 1 | 2024-03-02 | 2024-03-02 | P00775222VS-CW1 | 23IC0154 | 2023-08-29 | 2023-08-09 | 2023-09-21 | 2023-10-17 | 2023-10-23
NC 2023 | K10 | Region VIII | Leyte |  | San Isidro National High School | TANAUAN |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 10308120.28 | COMPLETED | 1 | 2024-02-29 | 2024-02-29 | P00775223VS-CW1 | 23IC0166 | 2023-06-09 | 2023-09-15 | 2023-09-28 | 2023-11-13 | 2023-11-16
NC 2023 | K10 | Region VIII | Leyte | 121950 | Daniel Z. Romualdez Memorial Elementary School | TOLOSA |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 5006395.06 | COMPLETED | 1 | 2024-03-02 | 2024-03-02 | P00775224VS-CW1 | 23IC0153 | 2023-08-29 | 2023-08-09 | 2023-09-21 | 2023-10-17 | 2023-10-23
NC 2023 | SHS | Region VIII | Leyte | 303440 | Tolosa National High School | TOLOSA |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 5023819.96 | COMPLETED | 1 | 2024-01-30 | 2024-01-30 | P00775225VS-CW1 | 23IC0152 | 2023-08-29 | 2023-08-09 | 2023-09-21 | 2023-10-13 | 2023-10-17
NC 2023 | SHS | Region VIII | Leyte | 303354 | Burauen National High School | BARAUEN |  | 1 |  | 3 | Batch 1 | 7565625 | 7500000 | 7443679.49 | COMPLETED | 1 | 2024-06-26 |  | P00775226VS | 23ID0107 |  | 2023-11-03 | 2023-11-15 | 2024-01-19 | 2024-02-06
NC 2023 | K10 | Region VIII | Leyte | 303363 | Celestino De Guzman Memorial National High School | BARUGO |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4986971.6 | COMPLETED | 1 | 2023-12-25 | 2024-02-12 | P00775227VS | 23ID0082 |  | 2023-06-21 | 2023-07-14 | 2023-08-14 | 2023-09-23
NC 2023 | K10 | Region VIII | Leyte |  | Visares NHS | CAPOOCAN |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4984992.02 | COMPLETED | 1 | 2023-11-22 | 2023-12-24 | P00775228VS | 23ID0080 |  | 2023-06-21 | 2023-07-14 | 2023-07-21 | 2023-08-07
NC 2023 | K10 | Region VIII | Leyte | 121254 | Alberto T. Aguja Mem. Central School | CARIGARA |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 13398678.88 | ONGOING | 0.95 | 2024-07-11 |  | P00775229VS | 23ID0105 |  | 2023-11-03 | 2023-11-15 | 2024-01-19 | 2024-02-22
NC 2023 | K10 | Region VIII | Leyte | 121301 | Patoc Elementary School | DAGAMI |  | 1 |  | 3 | Batch 1 | 7565625 | 7500000 | 7485469.93 | COMPLETED | 1 | 2024-03-13 | 2024-04-01 | P00775230VS | 23ID0093 |  | 2023-09-19 | 2023-06-30 | 2023-10-13 | 2023-11-03
NC 2023 | K10 | Region VIII | Leyte | 121455 | Batug Elementary School | JARO |  | 1 |  | 4 | Batch 1 | 12105000 | 12000000 | 11984953.08 | COMPLETED | 1 | 2024-04-07 | 2024-04-21 | P00775231VS | 23ID0095 |  | 2023-08-02 | 2023-09-21 | 2023-10-13 | 2023-11-03
NC 2023 | K10 | Region VIII | Leyte | 121456 | Buenavista Elementary School | JARO |  | 1 |  | 4 | Batch 1 | 12105000 | 12000000 | 11989937.4 | COMPLETED | 1 | 2024-04-07 | 2024-04-07 | P00775232VS | 23ID0096 |  | 2023-08-02 | 2023-09-21 | 2023-10-13 | 2023-11-03
NC 2023 | K10 | Region VIII | Leyte | 121462 | Montejo Mendiola Memorial Elementary School | JARO |  | 1 |  | 2 | Batch 1 | 6052500 | 6000000 | 5975792.29 | COMPLETED | 1 | 2024-01-11 | 2024-02-02 | P00775233VS | 23ID0092 |  | 2023-09-19 | 2023-06-30 | 2023-09-12 | 2023-09-27
NC 2023 | SHS | Region VIII | Leyte | 303381 | Julita National High School | JULITA |  | 1 |  | 12 | Batch 1 | 41358750 | 41000000 | 40975229.98 | ONGOING | 0.95 | 2024-08-29 |  | P00775234VS | 23ID0104 |  | 2023-11-03 | 2023-12-02 | 2024-01-19 | 2024-02-01
NC 2023 | SHS | Region VIII | Leyte | 303342 | Atty. Roque A. Marcos Memorial School (La Paz NHS) | LA PAZ |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 10917294.53 | COMPLETED | 1 | 2024-07-21 |  | P00775238VS | 23ID0109 |  | 2023-11-03 | 2023-11-15 | 2024-01-19 | 2024-02-22
NC 2023 | K10 | Region VIII | Leyte | 121558 | Bagacay West Elementary School | LA PAZ |  | 1 |  | 2 | Batch 1 | 6052500 | 6000000 | 5986852.06 | COMPLETED | 1 | 2024-01-11 | 2024-02-27 | P00775235VS | 23ID0094 |  | 2023-09-19 | 2023-06-30 | 2023-09-12 | 2023-09-27
NC 2023 | K10 | Region VIII | Leyte | 121559 | Bongtod Primary School | LA PAZ |  | 1 |  | 2 | Batch 1 | 5649000 | 5600000 | 5595107.39 | COMPLETED | 1 | 2023-12-28 | 2024-01-09 | P00775236VS | 23ID0085 |  | 2023-07-18 | 2023-06-26 | 2023-08-18 | 2023-09-11
NC 2023 | K10 | Region VIII | Leyte | 121566 | Canbanez Primary School | LA PAZ |  | 1 |  | 2 | Batch 1 | 5649000 | 5600000 | 5583469.48 | COMPLETED | 1 | 2024-01-07 | 2024-02-11 | P00775237VS | 23ID0086 |  | 2023-07-18 | 2023-06-26 | 2023-09-06 | 2023-09-22
NC 2023 | SHS | Region VIII | Leyte | 303414 | Palale National High School | MACARTHUR |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 10421250 | COMPLETED | 1 | 2024-07-21 |  | P00775241VS | 23ID0108 |  | 2023-11-03 | 2023-11-15 | 2024-01-19 | 2024-02-22
NC 2023 | K10 | Region VIII | Leyte | 121626 | San Antonio Elementary School | MACARTHUR |  | 1 |  | 2 | Batch 1 | 6052500 | 6000000 | 5968728.96 | COMPLETED | 1 | 2024-01-28 | 2024-01-28 | P00775239VS | 23ID0091 |  | 2023-09-19 | 2023-06-30 | 2023-09-29 | 2023-10-13
NC 2023 | K10 | Region VIII | Leyte | 191565 | San Pedro Elementary School | MACARTHUR |  | 1 |  | 2 | Batch 1 | 5649000 | 5600000 | 5567633.22 | COMPLETED | 1 | 2023-12-28 | 2023-12-28 | P00775240VS | 23ID0087 |  | 2023-07-18 | 2023-06-26 | 2023-08-18 | 2023-09-11
NC 2023 | K10 | Region VIII | Leyte | 121703 | Camansi Primary School | MAYORGA |  | 1 |  | 2 | Batch 1 | 5649000 | 5600000 | 5583469.48 | COMPLETED | 1 | 2024-01-07 | 2024-01-07 | P00775242VS | 23ID0088 |  | 2023-07-18 | 2023-08-01 | 2023-09-06 | 2023-09-22
NC 2023 | K10 | Region VIII | Leyte | 121704 | Gen. A. Luna Primary School | MAYORGA |  | 1 |  | 2 | Batch 1 | 5649000 | 5600000 | 5581154.75 | COMPLETED | 1 | 2023-12-28 | 2023-12-28 | P00775243VS | 23ID0089 |  | 2023-07-18 | 2023-08-01 | 2023-08-18 | 2023-09-11
NC 2023 | K10 | Region VIII | Leyte | 121711 | Talisay Elementary School | MAYORGA |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 4984983.83 | COMPLETED | 1 | 2024-06-06 |  | P00775244VS | 23ID0106 |  | 2023-11-03 | 2023-11-15 | 2024-01-19 | 2024-02-22
NC 2023 | SHS | Region VIII | Leyte | 313343 | Macalpi-ay National High School | PASTRANA |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4968153.42 | COMPLETED | 1 | 2023-11-30 | 2023-12-20 | P00775245VS | 23ID0081 |  | 2023-06-21 | 2023-07-14 | 2023-07-21 | 2023-08-11
NC 2023 | SHS | Region VIII | Leyte | 303358 | Calubian National High School (Calubian Nat'l. Voc'l. School) | CALUBIAN |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9899999.57 | COMPLETED | 1 | 2024-03-13 | 2024-03-13 | P00775248VS | 23IE0106 | 2023-09-25 | 2023-10-06 | 2023-10-18 | 2023-10-26 | 2023-11-13
NC 2023 | K10 | Region VIII | Leyte | 121223 | Calubian South Central School | CALUBIAN |  | 1 |  | 2 | Batch 1 | 4337625 | 4300000 | 4287335.34 | COMPLETED | 1 | 2024-01-12 | 2024-01-12 | P00775246VS | 23IE0096 | 2023-08-24 | 2023-09-09 | 2023-09-19 | 2023-09-25 | 2023-10-04
NC 2023 | K10 | Region VIII | Leyte | 121226 | Igang Elementary School | CALUBIAN |  | 1 |  | 2 | Batch 1 | 4539375 | 4500000 | 4413783.85 | COMPLETED | 1 | 2024-01-12 | 2024-01-12 | P00775247VS | 23IE0095 | 2023-08-24 | 2023-09-09 | 2023-09-19 | 2023-09-25 | 2023-10-04
NC 2023 | SHS | Region VIII | Leyte | 313340 | Rafaelito Cabanas Martinez National High School | CALUBIAN |  | 1 |  | 3 | Batch 1 | 7565625 | 7500000 | 7426082.19 | COMPLETED | 1 | 2024-01-22 | 2024-01-22 | P00775249VS | 23IE0102 | 2023-08-25 | 2023-09-09 | 2023-09-21 | 2023-09-27 | 2023-10-04
NC 2023 | K10 | Region VIII | Leyte | 121837 | Hugpa Elementary School | SAN ISIDRO |  | 1 |  | 1 | Batch 1 | 2521875 | 2500000 | 2475005.51 | COMPLETED | 1 | 2024-02-08 | 2024-02-08 | P00775250VS | 23IE0113 | 2023-10-24 | 2023-11-07 | 2023-11-20 | 2023-11-29 | 2023-12-05
NC 2023 | SHS | Region VIII | Leyte | 303411 | Muertegui National High School | SAN ISIDRO |  | 1 |  | 3 | Batch 1 | 7565625 | 7500000 | 7415198.09 | COMPLETED | 1 | 2024-01-22 | 2024-01-22 | P00775252VS | 23IE0097 | 2023-08-24 | 2023-09-09 | 2023-09-19 | 2023-09-25 | 2023-10-04
NC 2023 | SHS | Region VIII | Leyte | 303423 | San Isidro National High School | SAN ISIDRO |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9957220.93 | ONGOING | 0.6 | 2024-03-20 |  | P00775253VS | 23IE0109 | 2023-10-01 | 2023-10-13 | 2023-10-16 | 2023-11-10 | 2023-11-22
NC 2023 | K10 | Region VIII | Leyte | 121845 | Sangabon Elementary School | SAN ISIDRO |  | 1 |  | 3 | Batch 1 | 2421000 | 2400000 | 2374382.03 | COMPLETED | 1 | 2024-02-08 | 2024-02-08 | P00775251VS | 23IE0112 | 2023-10-24 | 2023-11-07 | 2023-11-20 | 2023-11-29 | 2023-12-05
NC 2023 | SHS | Region VIII | Leyte | 313309 | Gibacungan National High School | TABANGO |  | 1 |  | 3 | Batch 1 | 7565625 | 7500000 | 7425203.07 | COMPLETED | 1 | 2024-01-22 | 2024-01-22 | P00775255VS | 23IE0103 | 2023-08-25 | 2023-09-09 | 2023-09-21 | 2023-09-27 | 2023-10-04
NC 2023 | SHS | Region VIII | Leyte | 303434 | Tabango National High School | TABANGO |  | 1 |  | 2 | Batch 1 | 4337625 | 4300000 | 4256031.8 | COMPLETED | 1 | 2024-02-24 | 2024-02-24 | P00775254VS | 23IE0108 | 2023-10-01 | 2023-10-13 | 2023-10-16 | 2023-11-09 | 2023-11-16
NC 2023 | K10 | Region VIII | Leyte | 121968 | Hinabuyan Central School | VILLABA |  | 1 |  | 4 | Batch 1 | 12105000 | 12000000 | 11877872.11 | COMPLETED | 1 | 2024-04-08 | 2024-04-08 | P00775256VS | 23IE0111 | 2023-10-24 | 2023-11-07 | 2023-11-20 | 2023-11-29 | 2023-12-05
NC 2023 | SHS | Region VIII | Leyte | 303442 | Villaba National Comprehensive High School | VILLABA |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9987971.82 | COMPLETED | 1 | 2024-03-20 | 2024-03-20 | P00775258VS | 23IE0110 | 2023-10-01 | 2023-10-13 | 2023-10-16 | 2023-11-10 | 2023-11-16
NC 2023 | SHS | Region VIII | Leyte | 303389 | Villaba National High School (LNCAST) | VILLABA |  | 1 |  | 3 | Batch 1 | 7565625 | 7500000 | 7487284.53 | COMPLETED | 1 | 2024-01-22 | 2024-01-22 | P00775257VS | 23IE0104 | 2023-08-25 | 2023-09-09 | 2023-09-21 | 2023-09-27 | 2023-10-04
NC 2023 | SHS | Region VIII | Leyte | 303368 | Dr. Geronimo B. Zaldivar Memorial School of Fisheries | ALBUERA |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4937623.8 | COMPLETED | 1 | 2023-11-29 | 2023-11-29 | P00775259VS | 23IF0110 | 2023-06-20 | 2023-06-29 | 2023-07-11 | 2023-08-17 | 2023-09-04
NC 2023 | K10 | Region VIII | Leyte | 121438 | Binog Elementary School | ISABEL |  | 1 |  | 3 | Batch 1 | 7565625 | 7500000 | 7406437.32 | COMPLETED | 1 |  | 2023-12-30 | P00775260VS | 23IF0109 | 2023-06-20 | 2023-06-29 | 2023-07-11 | 2023-08-17 | 2023-09-04
NC 2023 | SHS | Region VIII | Leyte | 303406 | Matlang National High School | ISABEL |  | 1 |  | 6 | Batch 1 | 15131250 | 15000000 | 14812873.32 | COMPLETED | 1 |  | 2024-08-01 | P00775261VS | 23IF0113 | 2023-06-20 | 2023-06-29 | 2023-07-11 | 2023-08-17 | 2023-09-04
NC 2023 | SHS | Region VIII | Leyte | 305522 | Matag-ob Stand Alone Senior High School | MATAG-OB |  | 1 |  | 6 | Batch 1 | 15131250 | 15000000 | Original Contract Cost = 14,812,873.33 Revised Contract Cost = 14,962,499.77 | COMPLETED | 1 |  | 2024-08-11 | P00775262VS | 23IF0112 | 2023-06-20 | 2023-06-29 | 2023-07-11 | 2023-08-17 | 2023-09-04
NC 2023 | SHS | Region VIII | Leyte | 303410 | Puerto Bello National High School | MERIDA |  | 1 |  | 3 | Batch 1 | 7565625 | 7500000 | Original Contract Cost = 7,406,435.16 Revised Contract Cost =7,481,246.81 | COMPLETED | 1 |  | 2024-06-24 | P00775263VS | 23IF0111 | 2023-06-20 | 2023-06-29 | 2023-07-11 | 2023-08-17 | 2023-09-04
NC 2023 | K10 | Region VIII | Leyte | 121777 | San Miguel Elementary School | PALOMPON |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | Original Contract Cost = 9,875,250.00 Revised Contract Cost = 9,975,000.00 | COMPLETED | 1 |  | 2024-06-01 | P00775264VS | 23IF0106 | 2023-06-13 | 2023-06-21 | 2023-07-03 | 2023-08-02 | 2023-08-18
NC 2023 | K10 | Region VIII | Leyte | 120922 | Burubud-an Elementary School | ABUYOG |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4937500 | COMPLETED | 1 | 2023-12-13 | 2023-12-13 | P00775265VS-CW1 | 23IG0122 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-27 | 2023-08-10
NC 2023 | SHS | Region VIII | Leyte |  | Canmarating Senior High School | ABUYOG |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9865000 | COMPLETED | 1 | 2024-06-03 | 2024-04-11 | P00775266VS-CW1 | 23IG0143 | 2023-10-17 | 2023-10-25 | 2023-11-07 | 2023-11-17 | 2023-12-01
NC 2023 | SHS | Region VIII | Leyte | 303338 | Anahawan National High School | BATO |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4912243.41 | COMPLETED | 1 | 2023-12-13 | 2023-12-13 | P00775268VS-CW1 | 23IG0125 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-26 | 2023-08-10
NC 2023 | SHS | Region VIII | Leyte | 303346 | Bato National High School | BATO |  | 1 |  | 4 | Batch 1 | 15131250 | 15000000 | 14774611.83 | COMPLETED | 1 | 2024-08-31 | 2024-08-12 | P00775269VS-CW1 | 23IG0129 | 2023-07-26 | 2023-08-02 | 2023-08-15 | 2023-08-22 | 2023-09-01
NC 2023 | K10 | Region VIII | Leyte | 121070 | Marcelo Elementary School | BATO |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4872500 | COMPLETED | 1 | 2024-04-04 | 2024-04-04 | P00775267VS-CW1 | 23IG0141 | 2023-10-17 | 2023-10-25 | 2023-11-07 | 2023-11-17 | 2023-12-01
NC 2023 | K10 | Region VIII | Leyte | 121383 | Hampangan Elementary School | HILONGOS |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4912500 | COMPLETED | 1 | 2024-04-04 | 2024-04-04 | P00775270VS-CW1 | 23IG0142 | 2023-10-17 | 2023-10-25 | 2023-11-07 | 2023-11-17 | 2023-12-01
NC 2023 | K10 | Region VIII | Leyte | 121423 | Guadalupe Elementary School | INOPACAN |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4895000 | ONGOING | 0.95 | 2023-12-13 |  | P00775271VS-CW1 | 23IG0124 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-26 | 2023-08-10
NC 2023 | K10 | Region VIII | Leyte | 121513 | Sta. Cruz Elementary School | JAVIER (BUGHO) |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4947500 | COMPLETED | 1 | 2023-12-12 | 2023-12-12 | P00775272VS-CW1 | 23IG0121 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-26 | 2023-08-09
NC 2023 | K10 | Region VIII | Leyte | 121639 | Mahaplag Central School | MAHAPLAG |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4925000 | COMPLETED | 1 | 2023-12-12 | 2023-12-12 | P00775273VS-CW1 | 23IG0123 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-27 | 2023-08-09
NC 2023 | SHS | Region VIII | Leyte | 303356 | Cahagnaan National High School | MATALOM |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4931250 | COMPLETED | 1 | 2023-12-12 | 2023-12-12 | P00775274VS-CW1 | 23IG0126 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-26 | 2023-08-09
NC 2023 | K10 | Region VIII | Maasin City | 500399 | Asuncion Integrated School | CITY OF MAASIN (Capital) |  | 1 |  | 3 | Batch 1 | 10087500 | 10000000 | 9986703.5 | Completed | 1 | 2024-03-05 | 2024-02-23 | P00775278VS-CW1 | 23IL0070 | 2023-07-17 | 2023-07-24 | 2023-08-15 | 2023-08-18 | 2023-08-23 | DAV-LEY Construction Services, INC.
NC 2023 | K10 | Region VIII | Maasin City | 303457 | Guadalupe National High School | CITY OF MAASIN (Capital) |  | 1 |  | 3 | Batch 1 | 10087500 | 10000000 | 9987132.9 | Completed | 1 | 2024-03-05 | 2024-06-14 | P00775278VS-CW1 | 23IL0071 | 2023-07-17 | 2023-07-24 | 2023-08-15 | 2023-08-18 | 2023-08-23 | QUEEN MARIECRIS CONST. CORP.
NC 2023 | SHS | Region VIII | Maasin City | 323101 | Ibarra National High School | CITY OF MAASIN (Capital) |  | 1 |  | 3 | Batch 1 | 10087500 | 10000000 | 9988407.2 | Completed | 1 | 2024-03-05 | 2023-12-11 | P00775277VS-CW1 | 23IL0072 | 2023-07-17 | 2023-07-24 | 2023-08-15 | 2023-08-18 | 2023-08-23 | PABLO S. LABASBAS CONSTRUCTION CORP.
NC 2023 | K10 | Region VIII | Maasin City | 122171 | Pinascohan MGS | CITY OF MAASIN (Capital) |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4987406.39 | Completed | 1 | 2024-01-10 | 2024-02-20 | P00775275VS-CW1 | 23IL0073 | 2023-07-17 | 2023-07-24 | 2023-08-15 | 2023-08-18 | 2023-08-23 | PABLO S. LABASBAS CONSTRUCTION CORP.
NC 2023 | K10 | Region VIII | Northern Samar | 122787 | Londres ES | ALLEN |  | 1 |  | 4 | Batch 1 | 9488728.46 | 9406422.26 | 9401964.28 | Ongoing | 0.95 | 2024-04-10 |  | P00775279VS | 23IH0152 |  | 2023-08-25 | 2023-09-25 | 2023-10-27 | 2023-11-08 | SMU Construction and Supply
NC 2023 | K10 | Region VIII | Northern Samar | 122820 | Capul I CS | CAPUL |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | reverted | 0 | [10 empty] | Delisted
NC 2023 | K10 | Region VIII | Northern Samar | 122826 | Oson ES | CAPUL |  | 1 |  | 4 | Batch 1 | 10086422.41 | 9998931.76 | 10316668.38 | Completed | 1 | 2024-04-16 | 2024-04-16 | P00775281VS | 23IH0153 |  | 2023-08-25 | 2023-09-25 | 2023-10-27 | 2023-11-08 | Christfer Construction and Supply
NC 2023 | K10 | Region VIII | Northern Samar | 500236 | Cawayan Integrated School | CATARMAN (Capital) |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 12332584.3 | Completed | 1 | 2024-07-07 | 2024-07-07 | P00775285VS | 23IH0157 |  | 2023-08-25 | 2023-09-25 | 2023-10-27 | 2023-11-08 | EFC Development Corporation
NC 2023 | K10 | Region VIII | Northern Samar | 122873 | Polangi ES | CATARMAN (Capital) |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 12294154.39 | Ongoing | 0.95 | 2024-05-08 |  | P00775283VS | 23IH0151 |  | 2023-08-25 | 2023-09-25 | 2023-10-27 | 2023-11-08 | EFC Development Corporation
NC 2023 | K10 | Region VIII | Northern Samar | 303545 | Rosario Lim Uy National High School | CATARMAN (Capital) |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9626279.38 | Completed | 1 | 2024-04-14 | 2024-04-14 | P00775284VS | 23IH0158 |  | 2023-08-25 | 2023-09-25 | 2023-10-27 | 2023-11-08 | JEJA and SOLO Enterprises and Development Corporation
NC 2023 | K10 | Region VIII | Northern Samar | 122853 | Washington ES | CATARMAN (Capital) |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 6285875.51 | Completed | 1 | 2024-05-15 | 2024-05-15 | P00775282VS | 23IH0154 |  | 2023-08-25 | 2023-09-25 | 2023-10-27 | 2023-11-08 | EFC Development Corporation
NC 2023 | K10 | Region VIII | Northern Samar | 123058 | Barobaybay ES | LAVEZARES |  | 1 |  | 4 | Batch 1 | 9870618.75 | 9785000 | 12422943.41 | Completed | 1 | 2024-05-03 | 2024-05-03 | P00775286VS | 23IH0159 |  | 2023-08-25 | 2023-09-25 | 2023-10-27 | 2023-11-08 | Four JJ Construction
NC 2023 | K10 | Region VIII | Northern Samar | 123066 | Libertad ES | LAVEZARES |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 6501137.18 | Completed | 1 | 2024-03-30 | 2024-03-30 | P0075287VS | 23IH0156 |  | 2023-08-25 | 2023-09-25 | 2023-10-27 | 2023-11-08 | Four JJ Construction
NC 2023 | K10 | Region VIII | Northern Samar | 305818 | Ruperto S. Sampayan National High School | SAN ISIDRO |  | 1 |  | 4 | Batch 1 | 9078750 | 9000000 | 13107414.87 | Ongoing | 0.95 | 2024-05-05 |  | P00775288VS | 23IH0155 |  | 2023-08-25 | 2023-09-25 | 2023-10-27 | 2023-11-08 | Four JJ Construction
NC 2023 | K10 | Region VIII | Northern Samar | 123248 | Sangputan ES | SAN VICENTE |  | 1 |  | 4 | Batch 1 | 10066770.49 | 9979450.3 |  | reverted | 0 | [10 empty] | Delisted
NC 2023 | K10 | Region VIII | Northern Samar | 123249 | Sila ES | SAN VICENTE |  | 1 |  | 2 | Batch 1 | 5548125 | 5500000 |  | reverted | 0 | [10 empty] | Delisted
NC 2023 | K10 | Region VIII | Northern Samar | 123250 | Tarnate ES | SAN VICENTE |  | 1 |  | 2 | Batch 1 | 5548125 | 5500000 | 6789759.24 | Completed | 1 | 2024-05-01 | 2024-05-01 | P00775291VS | 23IH0149 |  | 2023-08-30 | 2023-09-20 | 2023-10-27 | 2023-11-08
NC 2023 | K10 | Region VIII | Northern Samar | 313613 | La Perla NHS | LAOANG |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9989886.61 | Completed | 1 | 2024-05-17 | 2024-11-04 | P00775293VS | 23II0069 | 2023-10-22 | 2023-11-04 | 2023-11-11 | 2023-11-13 | 2023-11-14
NC 2023 | SHS | Region VIII | Northern Samar | 303557 | Laoang NHS | LAOANG |  | 1 |  | 5 | Batch 1 | 13113750 | 13000000 | 12974622.15 | Completed | 1 | 2024-04-17 | 2024-11-09 | P00775292VS | 23II0071 | 2023-10-22 | 2023-11-04 | 2023-11-11 | 2023-11-13 | 2023-11-14
NC 2023 | SHS | Region VIII | Northern Samar | 313624 | Oleras NHS | LAOANG |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9989059.56 | Completed | 1 | 2024-05-17 | 2024-11-04 | P00775294VS | 23II0068 | 2023-10-22 | 2023-11-04 | 2023-11-11 | 2023-11-13 | 2023-11-14
NC 2023 | K10 | Region VIII | Northern Samar | 122998 | Mabini ES | LAPINIG |  | 1 |  | 3 | Batch 1 | 7061250 | 7000000 | 6984994.61 | Completed | 1 | 2024-03-18 | 2024-10-15 | P00775295VS | 23II0066 | 2023-10-22 | 2023-11-04 | 2023-11-11 | 2023-11-13 | 2023-11-14
NC 2023 | K10 | Region VIII | Northern Samar | 313620 | Bukid NHS | LAS NAVAS |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9989414.85 | Completed | 1 | 2024-05-17 | 2024-10-21 | P00775296VS | 23II0070 | 2023-10-22 | 2023-11-04 | 2023-11-11 | 2023-11-13 | 2023-11-14
NC 2023 | SHS | Region VIII | Northern Samar | 303564 | Mapanas Agro-Industrial High School | MAPANAS |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9988888 | Completed | 1 | 2024-03-18 | 2024-07-13 | P00775297VS | 23II0067 | 2023-10-22 | 2023-11-04 | 2023-11-11 | 2023-11-13 | 2023-11-14
NC 2023 | K10 | Region VIII | Northern Samar | 313612 | Malobago - Pagsang-an NHS | SAN ROQUE |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4997319.97 | Completed | 1 | 2024-02-17 | 2024-04-05 | P00775298VS | 23II0065 | 2023-10-22 | 2023-11-04 | 2023-11-11 | 2023-11-13 | 2023-11-14
NC 2023 | K10 | Region VIII | Ormoc City | 502291 | San Isidro Integrated School | ORMOC CITY |  | 1 |  | 12 | Batch 1 | 30262500 | 30000000 | 29099999.98 | Completed | 1 | 2024-04-19 | 2024-12-06 | 23IF0114 | 8/15-22/23 |  | 2023-08-02 | 2023-08-23 | 2023-09-25 | 2023-10-09 | JV ENTERPRISES | Completed
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 123285 | Almagro Central Elementary School | ALMAGRO |  | 1 |  | 3 | Batch 1 | 8663851.13 | 8588700 | 8539532.35 | COMPLETED | 1 | 2024-03-04 | 2024-07-05 | P00775300VS-CW1 | 23IJ0102 | 2023-08-18 | 2023-08-25 | 2023-09-07 | 2023-09-21 | 2023-09-26
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 123294 | Magsaysay Elementary School | ALMAGRO |  | 1 |  | 2 | Batch 1 | 5775900.75 | 5725800 | 5691445.2 | ONGOING | 0.2 | 2024-01-29 |  | 23IJ0093 | 23IJ0093 | 2023-07-21 | 2023-07-28 | 2023-08-10 | 2023-08-24 | 2023-08-31
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 123297 | San Isidro Elementary School | ALMAGRO |  | 1 |  | 2 | Batch 1 | 5775900.75 | 5725800 | 5694308.1 | COMPLETED | 1 | 2024-01-29 | 2024-01-29 | 23IJ0092 | 23IJ0092 | 2023-07-21 | 2023-07-28 | 2023-08-10 | 2023-08-24 | 2023-08-31
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 193536 | Inubod Elementary School | MATUGUINAO |  | 1 |  | 2 | Batch 1 | 5951625 | 5900000 | 5870449.08 | COMPLETED | 1 | 2024-02-23 | 2024-11-06 | P00775306VS-CW1 | 23IJ0097 | 2023-08-18 | 2023-08-25 | 2023-09-07 | 2023-09-21 | 2023-09-26
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 193503 | Libertad Elementary School | MATUGUINAO |  | 1 |  | 2 | Batch 1 | 5901187.5 | 5850000 | 5817825 | COMPLETED | 1 | 2024-02-23 | 2024-11-06 | P00775304VS-CW1 | 23IJ0099 | 2023-08-18 | 2023-08-25 | 2023-09-07 | 2023-09-21 | 2023-09-26
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 123550 | Nagpapacao Elementary School | MATUGUINAO |  | 1 |  | 2 | Batch 1 | 5951625 | 5900000 | 5870449.08 | COMPLETED | 1 | 2024-02-23 | 2024-11-06 | P00775303VS | 23IJ0101 | 2023-08-18 | 2023-08-25 | 2023-09-07 | 2023-09-21 | 2023-09-26
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 193504 | Rizal II Elementary School | MATUGUINAO |  | 1 |  | 2 | Batch 1 | 5901187.5 | 5850000 | 5820750 | COMPLETED | 1 | 2024-02-23 | 2024-11-06 | P00775305VS-CW1 | 23IJ0100 | 2023-08-18 | 2023-08-25 | 2023-09-07 | 2023-09-21 | 2023-09-26
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 123651 | Buenos Aires Integrated School | PAGSANGHAN |  | 1 |  | 2 | Batch 1 | 5447250 | 5400000 | 5370080 | COMPLETED | 1 | 2024-03-14 | 2024-07-05 | P00775307VS-CW1 | 23IJ0098 | 2023-08-18 | 2023-08-25 | 2023-09-07 | 2023-09-21 | 2023-09-26
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 313714 | Buenos Aires Integrated School | PAGSANGHAN |  | 1 |  | 2 | Batch 1 | 5447250 | 5400000 | 5370080 | COMPLETED | 1 | 2024-03-14 | 2024-07-05 | P00775307VS-CW1 | 23IJ0098 | 2023-08-18 | 2023-08-25 | 2023-09-07 | 2023-09-21 | 2023-09-26
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 123812 | Sto. Niño Central Elementary School | SANTO NIÑO |  | 1 |  | 2 | Batch 1 | 5914603.88 | 5863300 | 5831275.58 | COMPLETED | 1 | 2024-01-29 | 2024-07-05 | 23IJ0095 | 23IJ0095 | 2023-07-27 | 2023-08-03 | 2023-08-16 | 2023-08-24 | 2023-08-31
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 123819 | Labangbaybay Elementary School | TAGAPUL-AN |  | 1 |  | 2 | Batch 1 | 6128156.25 | 6075000 | 6038550 | COMPLETED | 1 | 2024-01-29 | 2024-07-05 | 23IJ0091 | 23IJ0091 | 2023-07-21 | 2023-07-28 | 2023-08-10 | 2023-08-24 | 2023-08-31
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 123358 | Barobaybay Elementary School | CALBIGA |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9903252.95 | COMPLETED | 1 | 2024-05-12 | 2024-05-12 | 23IK0096 | 23IK0096 | 2023-07-26 | 2023-08-04 | 2023-08-15 | 2023-08-22 | 2023-09-05
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 123584 | Camarubo-an Elementary School | JIABONG |  | 1 |  | 2 | Batch 1 | 5245500 | 5200000 | 5147881.79 | COMPLETED | 1 | 2023-12-23 | 2023-12-23 | 23IK0098 | 23IK0098 | 2023-07-26 | 2023-08-04 | 2023-08-15 | 2023-08-22 | 2023-09-05
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 123585 | Candayao Elementary School | JIABONG |  | 1 |  | 2 | Batch 1 | 5548125 | 5500000 | 5455999 | COMPLETED | 1 | 2023-11-26 | 2023-11-26 | 23IK0097 | 23IK0097 | 2023-07-26 | 2023-08-04 | 2023-08-15 | 2023-08-22 | 2023-09-05
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 123586 | Cantongtong Elementary School | JIABONG |  | 1 |  | 2 | Batch 1 | 5548125 | 5500000 | 5390350.39 | completed | 1 | 2023-11-21 | 2023-11-21 | 23IK0086 | 23IK0086 | 2023-07-20 | 2023-07-28 | 2023-08-09 | 2023-08-15 | 2023-08-31
NC 2023 | SHS | Region VIII | Samar (Western Samar) | 313711 | Casapa National High School | JIABONG |  | 1 |  | 3 | Batch 1 | 6661139.48 | 6603360.08 | 6540325.05 | completed | 1 | 2023-12-09 | 2023-12-09 | 23IK0093 | 23IK0093 | 2023-07-26 | 2023-08-04 | 2023-08-15 | 2023-08-22 | 2023-09-05
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 123597 | Malino Elementary School | JIABONG |  | 1 |  | 3 | Batch 1 | 8070000 | 8000000 | 7944554.74 | completed | 1 | 2023-12-17 | 2023-12-17 | 23IK0094 | 23IK0094 | 2023-07-26 | 2023-08-04 | 2023-08-15 | 2023-08-22 | 2023-09-05
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 123601 | Parina Elementary School | JIABONG |  | 1 |  | 2 | Batch 1 | 5548125 | 5500000 | 5444502.58 | completed | 1 | 2023-12-21 | 2023-12-21 | 23IK0087 | 23IK0087 | 2023-07-20 | 2023-07-28 | 2023-08-09 | 2023-08-15 | 2023-08-31
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 123607 | Victory Elementary School | JIABONG |  | 1 |  | 3 | Batch 1 | 6661139.48 | 6603360.08 | 6540648.38 | completed | 1 | 2023-12-09 | 2023-12-09 | 23IK0091 | 23IK0091 | 2023-07-20 | 2023-07-28 | 2023-08-09 | 2023-08-15 | 2023-08-31
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 123713 | Bontod Elementary School | SAN SEBASTIAN |  | 1 |  | 3 | Batch 1 | 8977875 | 8900000 | 8910233.87 | completed | 1 | 2024-04-01 | 2024-04-01 | 23IK0095 | 23IK0095 | 2023-07-26 | 2023-08-04 | 2023-08-15 | 2023-08-22 | 2023-09-05
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 123721 | San Sebastian Central Elementary School | SAN SEBASTIAN |  | 1 |  | 3 | Batch 1 | 6661139.48 | 6603360.08 | 6537036.23 | completed | 1 | 2023-12-14 | 2023-12-14 | 23IK0092 | 23IK0092 | 2023-07-26 | 2023-08-04 | 2023-08-15 | 2023-08-22 | 2023-09-05
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 501372 | Tatabunan Integrated School | TALALORA |  | 1 |  | 2 | Batch 1 | 6657750 | 6600000 | 6533396.66 | completed | 1 | 2024-02-02 | 2024-02-02 | 23IK0085 | 23IK0085 | 2023-07-20 | 2023-07-28 | 2023-08-09 | 2023-08-15 | 2023-08-31
NC 2023 | SHS | Region VIII | Samar (Western Samar) | 313707 | Bioso Integrated School | ZUMARRAGA |  | 1 |  | 4 | Batch 1 | 12105000 | 12000000 | 11879615.89 | completed | 1 | 2023-12-10 | 2023-12-10 | 23IK0090 | 23IK0090 | 2023-07-20 | 2023-07-28 | 2023-08-09 | 2023-08-15 | 2023-09-04
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 123967 | Botaera Elementary School | ZUMARRAGA |  | 1 |  | 4 | Batch 1 | 12609375 | 12500000 | 12451892.81 | completed | 1 | 2024-05-10 | 2024-05-10 | 23IK0088 | 23IK0088 | 2023-07-20 | 2023-07-28 | 2023-08-09 | 2023-09-19 | 2023-10-02
NC 2023 | K10 | Region VIII | Samar (Western Samar) | 123973 | Maputi Elementary School | ZUMARRAGA |  | 1 |  | 2 | Batch 1 | 6657750 | 6600000 | 6527342 | COMPLETED | 1 | 2023-12-09 | 2023-12-09 | 23IK0089 | 23IK0089 | 2023-07-20 | 2023-07-28 | 2023-08-09 | 2023-08-15 | 2023-09-04 |  | Project is Suspended
NC 2023 | K10 | Region VIII | Southern Leyte | 122065 | Anahawan Central School | ANAHAWAN |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9949924.62 | COMPLETED | 1 | 2024-04-19 |  | 23I00176 | 23I00176 | 2023-10-04 | 2023-10-12 | 2023-10-25 | 2023-12-04 | 2023-12-19 | Circle Z Ventures & Dev't Corp.
NC 2023 | SHS | Region VIII | Southern Leyte | 303444 | Anahawan National Vocational High Schoolchool | ANAHAWAN |  | 1 |  | 2 | Batch 1 | 6633694.59 | 6576153.25 | 6550654.32 | ONGOING | 0.9 | 2024-06-02 |  | 23I00177 | 23I00177 | 2023-10-04 | 2023-10-12 | 2023-10-25 | 2023-12-20 | 2023-12-29 | Juncynth Construction & Gen. Services
NC 2023 | K10 | Region VIII | Southern Leyte | 122029 | Catublian Elementary School | HINUNANGAN |  | 1 |  | 2 | Batch 1 | 6052500 | 6000000 | 5984030.34 | COMPLETED | 1 | 2024-08-14 | 2024-08-14 | 23I00175 | 23I00175 | 2023-10-04 | 2023-10-12 | 2023-10-25 | 2023-11-29 | 2023-12-15 | FFJJ Construction
NC 2023 | K10 | Region VIII | Southern Leyte | 305496 | Sto. Niño National High School | HINUNANGAN |  | 1 |  | 2 | Batch 1 | 6203812.5 | 6150000 | 6135946.42 | COMPLETED | 1 | 2024-06-02 |  | 23I00173 | 23I00173 | 2023-10-04 | 2023-10-12 | 2023-10-25 | 2023-12-20 | 2023-12-29 | Juncynth Construction & Gen. Services
NC 2023 | SHS | Region VIII | Southern Leyte | 303466 | Lungsodaan National High School | HINUNDAYAN |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9984187.35 | COMPLETED | 1 | 2024-09-27 |  | 23I00163 | 23I00163 | 2023-10-01 | 2023-10-09 | 2023-10-23 | 2023-11-22 | 2023-12-01 | ZTATIK MKTG. & ENGINEERING SERVICES
NC 2023 | SHS | Region VIII | Southern Leyte | 303472 | Rito Monte de Ramos Sr. MHS (Nahaong NHS) | LIBAGON |  | 1 |  | 10 | Batch 1 | 39862335.1 | 39516565.15 | 39318980.41 | COMPLETED | 1 | 2024-10-01 |  | 23I0082 | 23I0082 | 2023-10-01 | 2023-10-09 | 2023-10-23 | 2023-12-20 | 2023-12-29 | RJIR ENTERPRISES
NC 2023 | SHS | Region VIII | Southern Leyte | 303459 | Himay-angan NHS | LILOAN |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4989732.71 | COMPLETED | 1 | 2024-06-09 |  | 23I00166 | 23I00166 | 2023-10-01 | 2023-10-09 | 2023-10-23 | 2023-11-22 | 2023-11-27 | FFJJ Construction
NC 2023 | K10 | Region VIII | Southern Leyte | 122101 | Liloan Central School | LILOAN |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4981188.64 | COMPLETED | 1 | 2024-09-14 | 2024-09-14 | 23I00179 | 23I00179 | 2023-10-04 | 2023-10-12 | 2023-10-25 | 2023-12-20 | 2023-12-29 | Juncynth Construction & Gen. Services
NC 2023 | K10 | Region VIII | Southern Leyte | 122232 | Buenavista Elementary School | PINTUYAN |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4989613.72 | COMPLETED | 1 | 2024-09-21 | 2024-09-21 | 23I00171 | 23I00171 | 2023-10-01 | 2023-10-09 | 2023-10-23 | 2023-11-22 | 2023-12-01 | ZTATIK MKTG. & ENGINEERING SERVICES
NC 2023 | K10 | Region VIII | Southern Leyte | 122288 | Himbangan ES | SAINT BERNARD |  | 1 |  | 2 | Batch 1 | 6173550 | 6120000 | 6109643.79 | COMPLETED | 1 | 2024-04-02 |  | 23I00165 | 23I00165 | 2023-10-01 | 2023-10-09 | 2023-10-23 | 2023-11-22 | 2023-12-01 | FFJJ Construction
NC 2023 | SHS | Region VIII | Southern Leyte | 313407 | New Guinsaugon National High School | SAINT BERNARD |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9984547.62 | COMPLETED | 1 | 2024-06-04 |  | 23I00160 | 23I00160 | 2023-10-01 | 2023-10-09 | 2023-10-23 | 2023-11-22 | 2023-12-01 | ZTATIK MKTG. & ENGINEERING SERVICES
NC 2023 | K10 | Region VIII | Southern Leyte | 122307 | Tambis II Multi-Grade Elementary School | SAINT BERNARD |  | 1 |  | 2 | Batch 1 | 6052500 | 6000000 | 5983205.16 | COMPLETED | 1 | 2024-04-17 | 2024-04-17 | 23I00172 | 23I00172 | 2023-10-04 | 2023-10-12 | 2023-10-25 | 2023-11-29 | 2023-12-15 | FFJJ Construction
NC 2023 | K10 | Region VIII | Southern Leyte | 192021 | Anislagon Primary School | SAN FRANCISCO |  | 1 |  | 6 | Batch 1 | 23988013.56 | 23779939.09 | 23753085.5 | ONGOING | 0.95 | 2024-11-09 |  | 23I00178 | 23I00178 | 2023-10-04 | 2023-10-12 | 2023-10-25 | 2023-11-29 | 2023-12-15 | FFJJ Construction
NC 2023 | SHS | Region VIII | Southern Leyte | 303470 | Marayag National High School | SAN FRANCISCO |  | 1 |  | 2 | Batch 1 | 8113692.08 | 8043313.09 | 8024506.91 | COMPLETED | 1 | 2024-05-21 |  | 23I00174 | 23I00174 | 2023-10-04 | 2023-10-12 | 2023-10-25 | 2023-11-29 | 2023-12-15 | FFJJ Construction
NC 2023 | K10 | Region VIII | Southern Leyte | 122108 | Pinamudlan Elementary School | SAN FRANCISCO |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9984154.19 | COMPLETED | 1 | 2024-09-26 | 2024-09-26 | 23I00167 | 23I00167 | 2023-10-01 | 2023-10-09 | 2023-10-23 | 2023-11-22 | 2023-12-01 | RYJEN Construction
NC 2023 | K10 | Region VIII | Southern Leyte | 122250 | Garsavic Elementary School | SAN JUAN (CABALIAN) |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4989228.04 | COMPLETED | 1 | 2024-02-03 | 2024-08-18 | 23I00162 | 23I00162 | 2023-10-01 | 2023-10-09 | 2023-10-23 | 2023-11-22 | 2023-12-01 | RYJEN Construction
NC 2023 | K10 | Region VIII | Southern Leyte | 501047 | Kahupian Integrated School | SOGOD |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4998437.49 | COMPLETED | 1 | 2024-02-03 | 2024-06-10 | 23I00164 | 23I00164 | 2023-10-01 | 2023-10-09 | 2023-10-23 | 2023-11-28 | 2023-12-01 | RYJEN Construction
NC 2023 | K10 | Region VIII | Southern Leyte | 305494 | San Isidro National High School | SOGOD |  |  |  | 2 | Batch 1 | 6254250 | 6200000 | 6189636.55 | COMPLETED | 1 | 2024-04-02 |  | 23I00161 | 23I00161 | 2023-10-01 | 2023-10-09 | 2023-10-23 | 2023-11-22 | 2023-12-01 | FFJJ Construction
NC 2023 | K10 | Region VIII | Tacloban City |  | Anibong Dreamville Elementary School | TACLOBAN CITY (Capital) |  | 1 |  | 20 | Batch 1 | 60525000 | 60000000 | 59967479.46 | ONGOING | 0.98 | 2025-03-08 |  | P00775349VS | 23IM0119 | 2023-09-21 | 2023-09-29 | 2023-10-11 | 2023-11-16 | 2023-11-21 | JFR CONSTRUCTION INC.
NC 2023 | K10 | Region VIII | Tacloban City | 124225 | Judge Antonio R. Montilla, Sr. Elementary School | TACLOBAN CITY (Capital) |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | REVERTED |  | 2024-04-04 | [9 empty] | No/limited buildable space
NC 2023 | SHS | Region VIII | Tacloban City | 303663 | Leyte National High School | TACLOBAN CITY (Capital) |  | 1 |  | 15 | Batch 1 | 40350000 | 40000000 | 39968408.32 | COMPLETED | 1 | 2024-06-22 | 2024-12-01 | P00775346VS | 23IM0124 | 2023-10-04 | 2023-10-12 | 2023-10-24 | 2023-11-30 | 2023-12-06 | PABLO LABASBAS CONST./HD GOLDEN BUILDERS & SUPPLY INC.
NC 2023 | K10 | Region VIII | Tacloban City | 102307 | New Hope Elementary School | TACLOBAN CITY (Capital) |  | 1 |  | 6 | Batch 1 | 15131250 | 15000000 | 14938528 | REVERTED |  | 2024-04-06 | [9 empty] | No buildable space
NC 2023 | K10 | Region VIII | Tacloban City | 500891 | North Hill Arbours Integrated School | TACLOBAN CITY (Capital) |  | 1 |  | 6 | Batch 1 | 15131250 | 15000000 | 14968770.81 | COMPLETED | 1 | 2024-05-09 | 2024-12-01 | P00775347VS | 23IM0128 | 2023-11-14 | 2023-11-22 | 2023-12-04 | 2023-12-20 | 2023-12-27 | FILZLAND CONSTRUCTION
NC 2023 | K10 | Region VIII | Tacloban City |  | Saint Francis Integrated School | TACLOBAN CITY (Capital) |  | 1 |  | 20 | Batch 1 | 60525000 | 60000000 | 59967617.73 | COMPLETED | 1 | 2024-06-30 | 2024-12-01 | P00775348VS | 23IM0121 | 2023-09-21 | 2023-09-29 | 2023-10-11 | 2023-11-16 | 2023-11-24 | JFR CONSTRUCTION INC./VITTS DG. BUILDERS
NC 2023 | K10 | Region VIII | Tacloban City | 124260 | Sto. Nino SPED Center | TACLOBAN CITY (Capital) |  | 1 |  | 20 | Batch 1 | 60525000 | 60000000 | 59943998.04 | ONGOING | 0.6 | 2024-06-30 |  | P00775345VS | 23IM0122 | 2023-09-21 | 2023-09-29 | 2023-10-11 | 2023-11-16 | 2023-11-24 | AQUALINE CONST./EVERBUILT CONST. JV
NC 2024 |  | Region VIII | Baybay City | 500746 | Mapgap Integrated School | CITY OF BAYBAY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4974500 | Completed | 1 | 2024-11-26 | 2024-12-19 | P00875560VS-CW1 | 24IG0108 | 2024-05-29 | 2024-06-06 | 2024-06-18 | 2024-08-07 | 2024-07-24 | JUST IN ENTERPRISES
NC 2024 |  | Region VIII | Baybay City | 121128 | Sabang Elementary School | CITY OF BAYBAY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4973000 | Completed | 1 | 2024-11-26 | 2024-03-04 | P00875553VS-CW1 | 24IG0109 | 2024-05-29 | 2024-06-06 | 2024-06-18 | 2024-08-07 | 2024-07-24 | WJ BUILDERS
NC 2024 |  | Region VIII | Biliran | 303319 | Almeria NHS | ALMERIA |  | 1 | 4 | 2UNITS 1STY2CL | BATCH 1 | 13000000 |  | 12,933.026.13 | Completed | 1 | 2024-12-29 | 2024-12-29 | P00875695VS-CW1 | 24IA0128 | [5 empty] | K & A LUMBAB CONSTRUCTION & SUPPLY
NC 2024 |  | Region VIII | Biliran | 120759 | Barubuhan ES | ALMERIA |  | 1 | 2 | 1STY2CL | GAA 17B | 7000000 |  | 6658350.75 | Completed | 1 | 2024-09-28 | 2024-09-28 | P00875493VS-CW1 | 24IA0125 | [5 empty] | 4K VERMARK CIVIL ENGINEERING CONSTRUCTION
NC 2024 |  | Region VIII | Biliran | 313202 | Biliran Science High School | BILIRAN |  | 1 | 4 | 1STY4CL | GAA 17B | 11000000 |  | 10,350.105.20 | Ongoing | 0.9 | 2024-10-25 | 2024-10-25 | P00875492VS-CW1 | 24IA0122 | [5 empty] | L.C TING CONSTRUCTION AND DEVELOPMENT CORPORATION
NC 2024 |  | Region VIII | Biliran | 303323 | Cabucgayan NHS | CABUCGAYAN |  | 1 | 6 | 2STY6CL | GAA 17B | 18000000 |  | 17520340.3 | Ongoing | 0.9 | 2024-10-15 | 2024-10-15 | P00875495VS-CW1 | 24IA0121 | [5 empty] | QYT CONSTRUCTION AND SUPPLY
NC 2024 |  | Region VIII | Biliran | 120817 | Binongto-an ES | CULABA |  | 1 | 3 | 1STY1CL & 1STY2CL | GAA 17B | 9000000 |  | 8410390.5 | Completed | 1 |  |  | P00875490VS-CW1 | 24IA0123 | [5 empty] | QYT CONSTRUCTION AND SUPPLY
NC 2024 |  | Region VIII | Biliran | 120830 | Bulalacao ES | KAWAYAN |  | 1 | 2 | 1STY2CL | BATCH 1 | 7500000 |  | 7165810.8 | Completed | 1 |  |  | P00875696VS-CW1 | 24IA0130 | [5 empty] | K & A LUMBAB CONSTRUCTION & SUPPLY
NC 2024 |  | Region VIII | Biliran | 120831 | Burabod Elementary School | KAWAYAN |  | 1 | 2 | 1STY2CL | GAA 17B | 7500000 |  | 7110895.1 | Completed | 1 |  |  | P00875491VS-CW1 | 24IA0124 | [5 empty] | E.B. CORDERO CONSTRUCTION & SUPPLIES
NC 2024 |  | Region VIII | Biliran | 303329 | Maripipi NVS | MARIPIPI |  | 1 | 6 | Completion of 2STY6CL | BATCH 1 | 21224500 |  | 20960970.65 | Ongoing | 0.8 |  |  | P00875697VS-CW1 | 24IA0127 | [5 empty] | RMA BUILDERS AND SUPPLIES CORPORATION
NC 2024 |  | Region VIII | Biliran | 303334 | Viga National High School | MARIPIPI |  | 1 | 4 | Completion of 2STY4CL | BATCH 1 | 10961500 |  | 10798225 | Ongoing | 0.9 |  |  | P00875698VS-CW1 | 24IA0129 | [5 empty] | RMA BUILDERS AND SUPPLIES CORPORATION
NC 2024 |  | Region VIII | Biliran | 120857 | Atipolo ES | NAVAL (Capital) |  | 1 | 1 | 1STY1CL | BATCH 1 | 4000000 |  | 3880560.75 | Completed | 1 |  |  | P00875699VS-CW1 | 24IA0132 | [5 empty] | RMA BUILDERS AND SUPPLIES CORPORATION
NC 2024 |  | Region VIII | Biliran | 120859 | Larrazabal ES | NAVAL (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5500000 |  | 5390600.75 | Completed | 1 |  |  | P00875494VS-CW1 | 24IA0126 | [5 empty] | MKB BUILDERS AND SUPPLY
NC 2024 |  | Region VIII | Biliran | 303331 | Naval School of Fisheries | NAVAL (Capital) |  | 1 | 4 | 1STY4CL | BATCH 2 | 13000000 |  | 12930545.65 | Ongoing | 0.9 |  |  | P00875765VS-CW1 | 24IA0141 | [5 empty] | M.B ANG CONSTRUCTION & SUPPLY
NC 2024 |  | Region VIII | Biliran | 120880 | San Pablo ES | NAVAL (Capital) |  | 1 | 2 | 1STY2CL | BATCH 1 | 6250000 |  | 6210534.25 | Completed | 1 |  |  | P00875700VS-CW1 | 24IA0131 | [5 empty] | M.B ANG CONSTRUCTION & SUPPLY
NC 2024 |  | Region VIII | Borongan City | 303500 | Eastern Samar National Comprehensive High School | CITY OF BORONGAN (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 0
NC 2024 |  | Region VIII | Calbayog City | 502296 | Cagbayang Integrated School | CALBAYOG CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5985000 | Completed | 1 | 2024-11-28 | 2025-01-27 | P00875589VS-CW1 | 24IJ-0086 | 2024-11-07 | 2024-07-18 | 2024-07-31 | 2024-09-08 | 2024-08-20 | BCG DESIGN AND CONSTRUCTION | Completed as per POW but without Turn over yet
NC 2024 |  | Region VIII | Calbayog City | 500238 | Tabawan Integrated School | CALBAYOG CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5985000 | Ongoing | 0.99 | 2024-11-28 | 2024-12-28 | P00875587VS-CW1 | 24IJ-0089 | 2024-11-07 | 2024-07-18 | 2024-07-31 | 2024-08-08 | 2024-08-20 | DRS BUILDERS & CONSTRUCTION SUPPLY | FOR FINAL INSPECTION
NC 2024 |  | Region VIII | Catbalogan City | 123409 | Catbalogan II Central Elementary School | CITY OF CATBALOGAN (Capital) |  | 1 | 20 | 4STY20CL (PHASE-1) | GAA 17B | 40000000 |  | 39795816.46 | Ongoing | 0.08 | 2025-10-10 |  | 24IK0103 | 24IK0103 | 2025-01-24 | 2025-01-31 | 2025-02-13 | 2025-02-17 | 2025-02-27 | PYUKEI CONSTRUCTION | Just started on March 05, 2025
NC 2024 |  | Region VIII | Eastern Samar | 313501 | Can-avid National High School | CAN-AVID |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 0
NC 2024 |  | Region VIII | Eastern Samar | 303506 | Hilabaan National High School | DOLORES |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 0
NC 2024 |  | Region VIII | Eastern Samar | 122437 | San Isidro Elementary School | DOLORES |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 0
NC 2024 |  | Region VIII | Eastern Samar | 122510 | Giporlos Central School | GIPORLOS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 0
NC 2024 |  | Region VIII | Eastern Samar | 122524 | Guiuan East Central School | GUIUAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region VIII | Eastern Samar | 303503 | Guiuan National High School | GUIUAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region VIII | Eastern Samar | 303532 | Tubabao National High School | GUIUAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region VIII | Eastern Samar | 303513 | Llorente National High School | LLORENTE |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region VIII | Eastern Samar | 122446 | Bulawan Elementary School | MASLOG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.98
NC 2024 |  | Region VIII | Eastern Samar | 122625 | Maydolong Central Elementary School | MAYDOLONG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.98
NC 2024 |  | Region VIII | Eastern Samar | 122548 | San Jose Primary School | MERCEDES |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region VIII | Eastern Samar | 192506 | Tinago Elementary School | QUINAPONDAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | REVERTED | 0
NC 2024 |  | Region VIII | Eastern Samar | 122698 | Naparaan Elementary School | SALCEDO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region VIII | Eastern Samar | 122702 | Tagbacan Elementary School | SALCEDO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region VIII | Eastern Samar | 500810 | Malinao Intgrated School | TAFT |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region VIII | Leyte | 303336 | Alangalang National High School | ALANGALANG |  | 1 | 6 | 2STY6CL | GAA 17B | 15500000 |  | 15401141.25 | Ongoing | 0.95 | 2025-01-18 | 2025-02-06 | P00875523VS-CW1 | 24IC0188 | 2024-06-04 | 2024-05-30 | 2024-06-25 | 2024-07-30 | 2024-08-02 | GES CONST.
NC 2024 |  | Region VIII | Leyte | 120943 | Gregorio Caidic Sr. Elementary School | ALANGALANG |  | 1 | 2 | 1STY2CL | GAA 17B | 5500000 |  | 5457565.05 | Completed | 1 | 2024-12-17 | 2024-12-17 | P00875521VS-CW1 | 24IC0186 | 2024-07-02 | 2024-06-27 | 2024-07-25 | 2024-08-30 | 2024-09-03 | QUELLING CONST.
NC 2024 |  | Region VIII | Leyte | 191561 | Hinapolon Primary School | ALANGALANG |  | 1 | 2 | 1STY2CL | GAA 17B | 5500000 |  |  | Not Yet Started | 0 | [10 empty] | FOR REVERSION DUE TO NO BULDABLE SPACE
NC 2024 |  | Region VIII | Leyte | 120951 | Mariquita Cinco Memorial Elementary School | ALANGALANG |  | 1 | 2 | 1STY2CL | GAA 17B | 5500000 |  | 5464000 | Completed | 1 | 2024-11-08 | 2024-11-07 | P00875522VS-CW1 | 24IC0187 | 2024-06-04 | 2024-05-30 | 2024-06-25 | 2024-07-22 | 2024-07-26 | R. YAO CONST.
NC 2024 |  | Region VIII | Leyte | 303343 | Juan S. Tismo National High School (Babatngon National High School) | BABATNGON |  | 1 | 6 | 2STY6CL | GAA 17B | 15500000 |  | 15402499.81 | Ongoing | 0.6 | 2025-01-11 |  | P00875524VS-CW1 | 24IC0189 | 2024-06-04 | 2024-05-30 | 2024-06-25 | 2024-07-22 | 2024-07-26 | B. VICENCIO BUILDERS (BVB), INC.
NC 2024 |  | Region VIII | Leyte | 121754 | Cangumbang Elementary School | PALO |  | 1 | 3 | 1STY3CL | GAA 17B | 8000000 |  | 7939189.56 | Ongoing | 0.95 | 2024-12-04 | 2024-12-02 | P00875530VS-CW1 | 24IC0193 | 2024-06-04 | 2024-05-30 | 2024-06-25 | 2024-08-07 | 2024-08-12 | RPBJ TRADING & CONST.
NC 2024 |  | Region VIII | Leyte | 303424 | San Joaquin National High School | PALO |  | 1 | 4 | 2STY4CL | GAA 17B | 10500000 |  |  | Not Yet Started | 0 | [10 empty] | FOR REVERSION DUE TO LACK OF FUNDS
NC 2024 |  | Region VIII | Leyte | 121859 | Malaguinabot Elementary School | SAN MIGUEL |  | 1 | 3 | 1STY3CL | GAA 17B | 8000000 |  | 7950000 | Completed | 1 | 2024-12-28 | 2024-12-28 | P00875531VS-CW1 | 24IC0194 | 2024-06-04 | 2024-05-30 | 2024-06-25 | 2024-08-29 | 2024-09-03 | R. YAO CONST.
NC 2024 |  | Region VIII | Leyte | 121931 | Talolora Elementary School | TANAUAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5500000 |  | 5456435.17 | Ongoing | 0.9 | 2024-11-08 | 2024-11-08 | P00875529VS-CW1 | 24IC0192 | 2024-06-04 | 2024-05-30 | 2024-06-25 | 2024-07-22 | 2024-07-26 | RPBJ TRADING & CONST.
NC 2024 |  | Region VIII | Leyte | 303437 | Tanauan National High School (San Roque NHS) | TANAUAN |  | 1 | 6 | 2STY6CL | GAA 17B | 15500000 |  | 15372174.5 | Ongoing | 0.35 | 2025-03-19 |  | P00875527VS-CW1 | 24IC0190 | 2024-08-02 | 2024-07-26 | 2024-08-27 | 2024-09-24 | 2024-09-30 | XDR CONSTRUCTION & SUPPLY
NC 2024 |  | Region VIII | Leyte |  | TSCHI PICAS-ANNEX | TANAUAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5500000 |  | 5465836.35 | Completed | 1 | 2024-12-17 | 2024-12-12 | P00875528VS-CW1 | 24IC0191 | 2024-06-04 | 2024-05-30 | 2024-06-25 | 2024-08-29 | 2024-09-03 | XDR. CONST. & SUPPLY
NC 2024 |  | Region VIII | Leyte | 121951 | Malbog Elementary School | TOLOSA |  | 1 | 2 | 1STY2CL | GAA 17B | 5500000 |  |  | Not Yet Started | 0 | [10 empty] | FOR REVERSION DUE TO NO BULDABLE SPACE
NC 2024 |  | Region VIII | Leyte |  | MINUHANG SENIOR HIGH SCHOOL | BARUGO |  | 1 | 6 | 2STY6CL | GAA 17B | 18000000 |  | 17805467.42 | Ongoing | 0.4 |  |  | P00875562VS | 24ID0131 |  | 2024-09-24 | 2024-10-07 | 2024-10-17 | 2024-11-11 | ASTILLA CONSTRUCTION AND SUPPLY
NC 2024 |  | Region VIII | Leyte | 121257 | Caghalo Elementary School | CARIGARA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4974092.23 | Completed | 1 | 2023-09-25 |  | P00875536VS | 24ID0093 |  | 2024-03-25 | 2024-03-06 | 2024-05-06 | 2024-06-13 | Virata Developer
NC 2024 |  | Region VIII | Leyte | 303361 | Carigara National High School | CARIGARA |  | 1 | 6 | 2STY6CL | GAA 17B | 18000000 |  |  | Not Yet Started | 0 |  |  | P00875563VS | [7 empty] | No buildable space
NC 2024 |  | Region VIII | Leyte | 121293 | Dagami North Central School | DAGAMI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 |  |  | P00875539VS | [7 empty] | No buildable space
NC 2024 |  | Region VIII | Leyte | 121305 | Sto. Domingo Primary School | DAGAMI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4978873.83 | Completed | 1 | 2024-10-22 |  | P00875534VS | 24ID0091 |  | 2024-03-25 | 2024-03-06 | 2024-06-18 | 2024-07-08 | Magilas Const. Construction
NC 2024 |  | Region VIII | Leyte | 121332 | San Antonio Elementary School | DULAG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4980059.51 | Completed | 1 | 2024-09-21 |  | P00875538VS | 24ID0088 |  | 2024-03-21 | 2024-04-02 | 2024-04-15 | 2024-06-10 | Xeds Construction
NC 2024 |  | Region VIII | Leyte | 121333 | San Isidro Elementary School | DULAG |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5884930.6 | Completed | 1 | 2024-09-16 |  | P00875561VS | 24ID0094 |  | 2024-03-25 | 2024-03-06 | 2024-05-06 | 2024-05-28 | Beerock Enterprises Inc.
NC 2024 |  | Region VIII | Leyte | 191537 | Canapuan Elementary School | JARO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4966556.56 | Completed | 1 | 2024-07-09 |  | P00875537VS | 24ID0089 |  | 2024-03-21 | 2024-04-02 | 2024-05-06 | 2024-05-24 | Filzand Construction
NC 2024 |  | Region VIII | Leyte | 305906 | Francisco Y. Baranda, Sr. National High School | MACARTHUR |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4973351.31 | Completed | 1 | 2024-08-10 |  | P00875535VS | 24ID0092 |  | 2024-03-25 | 2024-03-06 | 2024-05-24 | 2024-06-24 | NFBM Construction
NC 2024 |  | Region VIII | Leyte | 303397 | Macarthur National High School | MACARTHUR |  | 1 | 6 | 2STY6CL | GAA 17B | 18000000 |  | 17905738.41 | Ongoing | 0.6 | 2024-12-31 |  | P00875564VS | 24ID0109 |  | 2024-05-17 | 2024-05-30 | 2024-06-10 | 2024-07-03 | 4Angle Construction
NC 2024 |  | Region VIII | Leyte | 121812 | Calsadahay Elementary School | PASTRANA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4964861.69 | Completed | 1 | 2024-08-22 |  | P00875532VS | 24ID0086 |  | 2024-03-21 | 2024-04-02 | 2024-04-17 | 2024-05-09 | BVC Construction
NC 2024 |  | Region VIII | Leyte | 191511 | Cancaraja Primary School | PASTRANA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4935754.9 | Completed | 1 | 2024-09-25 |  | P00875533VS | 24ID0087 |  | 2024-03-21 | 2024-04-02 | 2024-05-21 | 2024-06-13 | IDA Jr Builders & Construction Supply
NC 2024 |  | Region VIII | Leyte | 121223 | Calubian South Central School | CALUBIAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4949838.46 | Ongoing | 0.6 | 2024-05-11 |  | P00875542VS | 24IE0078 | 2024-04-06 | 2024-06-14 | 2024-06-27 | 2024-07-23 | 2024-07-29 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2024 |  | Region VIII | Leyte | 121223 | Calubian South Central School | CALUBIAN |  |  | 8 | 2STY8CL | GAA 17B | 25000000 |  | 24750123.77 | Ongoing | 0.4 | 2025-08-03 |  | P00875566VS | 24IE0096 | 2024-04-09 | 2024-09-13 | 2024-09-26 | 2024-09-30 | 2024-04-10 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2024 |  | Region VIII | Leyte | 121214 | Hacienda Enage Elementary School | CALUBIAN |  | 1 | 6 | 2STY6CL | GAA 17B | 18000000 |  | 17885084.87 | Ongoing | 0.45 | 2025-02-26 |  | P00875565VS | 24IE0097 | 2024-04-09 | 2024-09-13 | 2024-09-26 | 2024-09-30 | 2024-04-10 | SILK AND STEEL CONSTRUCTION
NC 2024 |  | Region VIII | Leyte | 121587 | Baco Elementary School | LEYTE |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4949849.09 | Completed | 1 | 2024-05-11 | 2024-05-11 | P00875543VS | 24IE0079 | 2024-04-06 | 2024-06-14 | 2024-06-27 | 2024-07-23 | 2024-07-29 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2024 |  | Region VIII | Leyte | 121589 | Belen Elementary School | LEYTE |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4949936.25 | Ongoing | 0.95 | 2024-06-11 |  | P00875544VS | 24IE0075 | 2024-04-06 | 2024-06-14 | 2024-06-27 | 2024-07-23 | 2024-07-29 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES
NC 2024 |  | Region VIII | Leyte |  | SAN ISIDRO HIGH SCHOOL BASUD-EXTENSION | SAN ISIDRO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4944320.42 | Ongoing | 0.6 | 2025-12-01 |  | P00875546VS | 24IE0095 | 2024-04-09 | 2024-09-13 | 2024-09-25 | 2024-09-30 | 2024-04-10 | YFL BUILDERS
NC 2024 |  | Region VIII | Leyte | 121905 | Tahad Elementary School | TABANGO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4955100.66 | Ongoing | 0.3 | 2025-12-01 |  | P00875545VS | 24IE0094 | 2024-04-09 | 2024-09-13 | 2024-09-25 | 2024-09-30 | 2024-04-10 | Omegaros Construction Supply and Services
NC 2024 |  | Region VIII | Leyte |  | HINABUYAN HIGH SCHOOL-ANNEX | VILLABA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4954988.78 | Completed | 1 | 2024-06-11 | 2024-06-11 | P00875540VS | 24IE0077 | 2024-04-06 | 2024-06-14 | 2024-06-27 | 2024-07-23 | 2024-07-29 | D.L. AUREO CONSTRUCTION
NC 2024 |  | Region VIII | Leyte | 121972 | Payao Elementary School | VILLABA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4953865.37 | Completed | 1 | 2024-06-11 | 2024-06-11 | P00875547VS | 24IE0076 | 2024-04-06 | 2024-06-14 | 2024-06-27 | 2024-07-23 | 2024-07-29 | D.L. Aureo Construction
NC 2024 |  | Region VIII | Leyte |  | SAMBULAWAN HIGH SCHOOL | VILLABA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4925248.84 | Ongoing | 0.6 | 2024-05-11 |  | P00875541VS | 24IE0081 | 2024-04-06 | 2024-06-14 | 2024-06-27 | 2024-07-23 | 2024-07-29 | Circle Z Ventures & Development Corp.
NC 2024 |  | Region VIII | Leyte | 121433 | Anislag Elementary School | ISABEL |  | 1 | 3 | 1STY3CL | GAA 17B | 7500000 |  | 7459499.55 | Ongoing | 0.95 | 2024-08-24 |  | P00875552VS | 24IF0074 | 2024-12-04 | 2024-04-19 | 2024-02-05 | 2024-05-13 | 2024-05-24 | JSONS BUILDERS | for final inspection
NC 2024 |  | Region VIII | Leyte | 121435 | Apale Elementary School | ISABEL |  | 1 | 3 | 1STY3CL | GAA 17B | 9000000 |  | 8923657.48 | Ongoing | 0.95 | 2024-04-09 |  | P00875567VS | 24IF0080 | 2024-04-19 | 2024-04-26 | 2024-08-05 | 2024-05-22 | 2024-03-06 | CIRCLE Z VENTURES & DEVELOPMENT CORP. | for final inspection
NC 2024 |  | Region VIII | Leyte | 121450 | San Francisco Elementary School | ISABEL |  | 1 | 3 | 1STY3CL | GAA 17B | 7500000 |  | 7459499.48 | Ongoing | 0.95 | 2024-08-24 |  | P00875551VS | 24IF0072 | 2024-12-04 | 2024-04-19 | 2024-02-05 | 2024-05-13 | 2024-05-24 | RED AXE BUILDERS & SUPPLY | for final inspection
NC 2024 |  | Region VIII | Leyte | 120928 | Libertad Elementary School | ABUYOG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4973250 | Completed | 1 | 2024-11-12 | 2024-11-12 | P00875557VS-CW1 | 24IG0120 | 2024-06-27 | 2024-05-07 | 2024-07-17 | 2024-07-26 | 2024-08-08 | ACESCAPE CONSTRUCTION
NC 2024 |  | Region VIII | Leyte | 137039 | Sto. Nino Elementary School | BATO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4838187.5 | Completed | 1 | 2024-10-22 | 2024-10-22 | P00875559VS-CW1 | 24IG0097 | 2024-04-25 | 2024-03-05 | 2024-05-15 | 2024-04-06 | 2024-06-19 | 820 BUILDERS AND SUPPLIES
NC 2024 |  | Region VIII | Leyte | 121388 | Libertad Elementary School | HILONGOS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4970000 | Completed | 1 | 2024-11-12 | 2024-11-12 | P00875554VS-CW1 | 24IG0121 | 2024-06-27 | 2024-05-07 | 2024-07-17 | 2024-07-26 | 2024-08-08 | JDR CONSTRUCTION
NC 2024 |  | Region VIII | Leyte | 303436 | Tahud National High School | INOPACAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4965500 | Completed | 1 | 2024-11-12 | 2024-11-11 | P00875556VS-CW1 | 24IG0122 | 2024-06-27 | 2024-05-07 | 2024-07-17 | 2024-07-26 | 2024-08-08 | JDR CONSTRUCTION
NC 2024 |  | Region VIII | Leyte | 121507 | Manlilisid Elementary school | JAVIER (BUGHO) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4850625 | Completed | 1 | 2024-10-23 | 2024-10-23 | P00875555VS-CW1 | 24IG0096 | 2024-04-25 | 2024-03-05 | 2024-05-15 | 2024-04-06 | 2024-06-20 | JUST IN ENTERPRISES
NC 2024 |  | Region VIII | Leyte | 121681 | Sta. Paz Integrated School | MATALOM |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4912812 | Completed | 1 | 2024-10-22 | 2024-10-22 | P00875558VS-CW1 | 24IG0098 | 2024-04-25 | 2024-03-05 | 2024-05-15 | 2024-04-06 | 2024-06-19 | GPK CONSTRUCTION AND SUPPLY
NC 2024 |  | Region VIII | Maasin City | 122159 | Hinapu Daku ES | CITY OF MAASIN (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4967830.46 | Ongoing | 0.99 | 2024-10-11 |  | P00875605VS | 24IL0084 | 2024-03-13 | 2024-03-20 | 2024-02-04 | 2024-05-04 | 2024-04-15 | JQD CONST. & GEN. SERVICES | Actual Recipient School is Hinapu Daku National High School (ID No. 323104), For Final Inspection
NC 2024 |  | Region VIII | Maasin City | 501050 | Maria Clara Integrated School | CITY OF MAASIN (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4967305.27 | Completed | 1 | 2024-10-28 | 2024-10-13 | P00875604VS | 24IL0083 | 2024-03-13 | 2024-03-20 | 2024-02-04 | 2024-05-04 | 2024-04-15 | DAV-LEY CONST. SERVICES, INC. | Completed
NC 2024 |  | Region VIII | Maasin City | 303474 | Nonok Norte National High School | CITY OF MAASIN (Capital) |  | 1 | 4 | 2STY4CL | BATCH 1 | 16671019.09 |  | 16575100.32 | Ongoing | 0.2 | 2025-09-04 |  | P00875701VS-CW1 | 24IL0098 | 2024-07-05 | 2024-05-14 | 2024-05-28 | 2024-03-06 | 2024-11-06 | M.G. VILLAMIN CONSTRUCTION | Ongoing
NC 2024 |  | Region VIII | Maasin City | 122177 | Tomas Oppus Pilot School (TOPS) | CITY OF MAASIN (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4967148.58 | Completed | 1 | 2024-02-11 | 2024-10-14 | P00875606VS | 24IL0082 | 2024-03-13 | 2024-03-20 | 2024-02-04 | 2024-05-04 | 2024-04-15 | J'NER CEPADA CONST. | Completed
NC 2024 |  | Region VIII | Northern Samar | 501191 | Acereda Integrated School | BOBON |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9914528.14 | Completed | 1 | 2025-05-03 | 2025-05-03 | P00875582VS | 24IH0071 |  | 2024-04-30 | 2024-05-22 | 2024-08-07 | 2024-10-07 | EFC DEVELOPMENT CORPORATION
NC 2024 |  | Region VIII | Northern Samar | 122806 | Dancalan ES | BOBON |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9916810.13 | Completed | 1 | 2024-12-12 | 2024-12-12 | P00875572VS | 24IH0070 |  | 2024-04-30 | 2024-05-22 | 2024-06-18 | 2018-06-27 | CATARMAN BUILDERS CONSTRUCTION
NC 2024 |  | Region VIII | Northern Samar | 122811 | Kalantiao ES | BOBON |  | 1 | 3 | 1STY3CL | BATCH 1 | 7500000 |  | 7451773.72 | Ongoing | 0.7 | 2025-02-07 |  | P00875702VS | 24IH0101 |  | 2024-06-25 | 2024-07-18 | 2024-07-08 | 2024-12-08 | SAL CONSTRUCTION | Change of location to Santander ES
NC 2024 |  | Region VIII | Northern Samar | 193007 | Balud Elementary School | CATARMAN (Capital) |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9912827.35 | Ongoing | 0.95 | 2024-05-12 |  | P00875583VS | 24IH0069 |  | 2024-04-23 | 2024-05-16 | 2024-11-06 | 2024-06-18 | EFC DEVELOPMENT CORPORATION
NC 2024 |  | Region VIII | Northern Samar | 123079 | VILLAHERMOSA ES | LAVEZARES |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9913900.74 | Completed | 1 | 2024-12-31 | 2024-12-31 | P00875581VS | 24IH0072 |  | 2024-04-30 | 2024-05-22 | 2024-08-07 | 2024-07-18 | EFC DEVELOPMENT CORPORATION
NC 2024 |  | Region VIII | Northern Samar | 123085 | Gebonawan ES | LOPE DE VEGA |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9915860.47 | Ongoing | 0.7 | 2025-03-18 |  | P00875571VS | 24IH0087 |  | 2024-06-25 | 2024-07-18 | 2024-07-08 | 2024-12-08 | FOUR JJ CONSTRUCTION
NC 2024 |  | Region VIII | Northern Samar |  | HINABANGAN NHS | MONDRAGON |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9916836.59 | Completed | 1 | 2024-10-12 | 2024-10-12 | P00875573VS | 24IH0068 |  | 2024-04-23 | 2024-05-16 | 2024-11-06 | 2024-06-18 | SAL CONSTRUCTION
NC 2024 |  | Region VIII | Northern Samar | 303530 | Alegria NHS | SAN ISIDRO |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9909856.8 | Ongoing | 0.95 | 2025-03-28 |  | P00875584VS | 24IH0067 |  | 2024-04-23 | 2024-05-16 | 2024-11-06 | 2024-06-18 | EFC DEVELOPMENT CORPORATION
NC 2024 |  | Region VIII | Northern Samar | 330502 | Maxvilla National High School | VICTORIA |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9884303.88 | Completed | 1 | 2024-10-12 | 2024-10-12 | P00875574VS | 24IH0067 |  | 2024-04-23 | 2024-05-16 | 2024-11-06 | 2024-06-18 | FOUR JJ CONSTRUCTION
NC 2024 |  | Region VIII | Northern Samar | 313613 | La Perla NHS | LAOANG |  | 1 | 5 | 1STY5CL | GAA 17B | 15000000 |  | 14904781.83 | Ongoing | 0.4 | 2025-07-24 |  | P00875569VS | 24II0094 | 2024-02-08 | 2024-08-18 | 2024-08-25 | 2024-08-28 | 2024-08-29 | EFC DEVELOPMENT CORPORATION
NC 2024 |  | Region VIII | Northern Samar | 313624 | Oleras NHS | LAOANG |  | 1 | 5 | 1STY5CL | GAA 17B | 15000000 |  | 14904524.11 | Ongoing | 0.4 | 2025-06-24 |  | P00875570VS- | 24II0095 | 2024-02-08 | 2024-08-18 | 2024-08-25 | 2024-08-28 | 2024-08-29 | EFC DEVELOPMENT CORPORATION
NC 2024 |  | Region VIII | Northern Samar | 122966 | P.M. Geta Memorial ES | LAOANG |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9936888 | Ongoing | 0.65 | 2025-05-25 |  | P00875580VS | 24II0092 | 2024-02-08 | 2024-08-18 | 2024-08-25 | 2024-08-28 | 2024-08-29 | ESD CRUZ CONSTRUCTION & SUPPLY
NC 2024 |  | Region VIII | Northern Samar | 122990 | Alang-alang ES | LAPINIG |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5949900 | Ongoing | 0.7 | 2025-01-31 |  | P00875575VS | 24II0087 | 2024-02-08 | 2024-08-18 | 2024-08-25 | 2024-08-28 | 2024-08-29 | DU CONSTRUCTION (13915) / DEACONS TEMPLE CONSTRUCTION & SUPPLY (42634)
NC 2024 |  | Region VIII | Northern Samar | 303560 | Las Navas National High School | LAS NAVAS |  | 1 | 10 | 2UNITS 1STY5CL | BATCH 1 | 25000000 |  | 24866890 | Ongoing | 0.45 | 2025-05-08 |  | P00875704VS | 24II0100 | 2024-02-08 | 2024-08-18 | 2024-08-25 | 2024-08-28 | 2024-08-29 | CDU CONSTRUCTION
NC 2024 |  | Region VIII | Northern Samar | 123036 | Quirino Elementary School | LAS NAVAS |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5967992.82 | Ongoing | 0.55 | 2025-02-03 |  | P00875578VS | 24II0089 | 2024-02-08 | 2024-08-18 | 2024-08-25 | 2024-08-28 | 2024-08-29 | 3BVAM BUILDERS AND SUPPLY
NC 2024 |  | Region VIII | Northern Samar | 193014 | San Isidro I ES | LAS NAVAS |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5961565.59 | Ongoing | 0.75 | 2025-02-03 |  | P00875579VS | 24II0090 | 2024-02-08 | 2024-08-18 | 2024-08-25 | 2024-08-28 | 2024-08-29 | JT BUILDERS & CONSTRUCTION SUPPLY
NC 2024 |  | Region VIII | Northern Samar | 123047 | San Jorge ES | LAS NAVAS |  | 1 | 4 | 1STY4CL | BATCH 1 | 10000000 |  | 9942742.67 | Ongoing | 0.55 | 2025-04-07 |  | P00875703VS- | 24II0099 | 2024-02-08 | 2024-08-18 | 2024-08-25 | 2024-08-28 | 2024-08-29 | CDU CONSTRUCTION | Change of location to Magsaysay NHS, Las Navas
NC 2024 |  | Region VIII | Northern Samar | 123166 | Simora Elementary School | PALAPAG |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9929748.72 | Ongoing | 0.65 | 2025-05-06 |  | P00875568VS- | 24II0093 | 2024-02-08 | 2024-08-18 | 2024-08-25 | 2024-08-28 | 2024-08-29 | EFC DEVELOPMENT CORPORATION
NC 2024 |  | Region VIII | Northern Samar | 306029 | Canjumadal National High School | PAMBUJAN |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5948888 | Ongoing | 0.4 | 2025-02-03 |  | P00875577VS | 24II0088 | 2024-02-08 | 2024-08-18 | 2024-08-25 | 2024-08-28 | 2024-08-29 | ESD CRUZ CONSTRUCTION & SUPPLY (32368)
NC 2024 |  | Region VIII | Northern Samar | 123268 | Silvino Lubos CS | SILVINO LOBOS |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5957506.09 | Ongoing | 0.95 | 2025-02-03 |  | P00875576VS | 24II0091 | 2024-02-08 | 2024-08-18 | 2024-08-25 | 2024-08-28 | 2024-08-29 | RL TUBA CIVIL ENGINEERING CONSTRUCTION
NC 2024 |  | Region VIII | Ormoc City | 124175 | Cagbuhangin Elementary School | ORMOC CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4950120.31 | Completed | 1 | 2024-08-14 | 2024-11-25 | P00875550VS-CW1 | 24IF0076 | 2024-12-04 | 2024-04-19 | 2024-02-05 | 2024-05-13 | 2024-05-24 | Hammertech Construction | completed
NC 2024 |  | Region VIII | Ormoc City | 124203 | Cogon Central School | ORMOC CITY |  | 1 | 6 | 2STY6CL | GAA 17B | 15000000 |  | 14850370.15 | Completed | 1 | 2024-08-10 | 2025-04-15 | P00875548VS-CW1 | 24IF0073 | 2024-12-04 | 2024-04-19 | 2024-02-05 | 2024-05-13 | 2024-05-24 | Pito Enterprise | completed
NC 2024 |  | Region VIII | Ormoc City | 502294 | Lake Danao Integrated School | ORMOC CITY |  | 1 | 5 | 1STY5CL | BATCH 1 | 12500000 |  | 12313123.2 | Completed | 1 | 2024-09-29 | 2024-12-23 | P00875555VS-CW1 | 24IF0081 | 2024-04-21 | 2024-04-28 | 2024-11-05 | 2024-05-22 | 2024-04-06 | RJIR Enterprises Corporation | completed
NC 2024 |  | Region VIII | Ormoc City | 124161 | Macabug Elementary School | ORMOC CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4925161.48 | Ongoing | 0.97 | 2024-09-08 |  | P00875549VS-CW1 | 24IF0075 | 2024-12-04 | 2024-04-19 | 2024-02-05 | 2024-05-13 | 2024-05-21 | GMP Builders | Punchlisted, No update on the punchlisted items for rectification. Already 9 months from target completion date, no coordination from DPWH.
NC 2024 |  | Region VIII | Samar (Western Samar) | 303612 | Matuguinao National High School | MATUGUINAO |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5941094.85 | Completed | 1 | 2024-08-19 | 2024-08-26 | 22IJ0097 | 22IJ0097 | 2024-11-07 | 2024-07-18 | 2024-07-31 | 2023-11-28 | 2024-02-26 | BCG DESIGN AND CONSTRUCTION | completed
NC 2024 |  | Region VIII | Samar (Western Samar) | 501360 | Blanca-Aurora Integrated School | SAN JORGE |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9900250 | Ongoing | 0.47 | 2025-07-28 |  | 24IJ0103 | 24IJ0103 | 2024-11-28 | 2024-05-12 | 2024-12-18 | 2024-01-15 | 2024-01-24 | DANILORSO CORP | completed
NC 2024 |  | Region VIII | Samar (Western Samar) | 123705 | Ranera Elementary School | SAN JORGE |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5941094.85 | Completed | 1 | 2024-11-28 | 2024-11-15 | 24IJ0087 | 24IJ0087 | 2024-11-07 | 2024-07-18 | 2024-07-31 | 2024-12-08 | 2024-08-20 | BCG DESIGN AND CONSTRUCTION | completed
NC 2024 |  | Region VIII | Samar (Western Samar) | 123730 | Lambao Elementary School | SANTA MARGARITA |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5941941 | Completed | 1 | 2024-11-28 | 2024-11-28 | 24IJ0088 | 24IJ0088 | 2024-11-07 | 2024-07-18 | 2024-07-31 | 2024-08-19 | 2024-08-20 | DANILORSO CORP | completed
NC 2024 |  | Region VIII | Samar (Western Samar) | 123332 | Buenavista Elementary School | BASEY |  | 1 | 3 | 1STY3CL | BATCH 1 | 7242922 |  | 7008056.17 | Completed | 1 | 2025-05-08 | 2025-02-05 | 24IK0102 | 24IK0102 | 2024-03-12 | 2024-11-12 | 2024-12-23 | 2025-01-30 | 2025-11-02 | Bench Construction & Supply
NC 2024 |  | Region VIII | Southern Leyte | 122002 | Divisoria Elementary School | BONTOC |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | Completed as per POW but without Painting, Ceiling & Electrical
NC 2024 |  | Region VIII | Southern Leyte | 122014 | Paku Elementary School | BONTOC |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | Completed as per POW but without Painting, Ceiling & Electrical
NC 2024 |  | Region VIII | Southern Leyte | 122207 | Guinabonan Elementary School | MALITBOG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4968218.34 | Completed | 1 | 2024-11-12 | [8 empty] | APTJ Construction | Completed as per POW but without Painting, Ceiling & Electrical
NC 2024 |  | Region VIII | Southern Leyte | 305533 | Malitbog National High School | MALITBOG |  | 1 | 8 | 2STY8CL | BATCH 2 | 38927578.65 |  |  | Ongoing | 0.15
NC 2024 |  | Region VIII | Southern Leyte | 302079 | Padre Burgos National Technical Vocational High School | PADRE BURGOS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region VIII | Southern Leyte | 122316 | Hinapo Elementary School | TOMAS OPPUS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region VIII | Southern Leyte | 303446 | Canipaan NHS | HINUNANGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 6666000 |  | 6620183.77 | Ongoing | 0.45 |  |  | 24I00282 | 24I00282 | 2024-07-18 | 2024-07-26 | 2024-08-08 | 2024-09-23 | 2024-10-04 | Pablo S. Labasbas Construction Corp.
NC 2024 |  | Region VIII | Southern Leyte | 122042 | Otama Elementary School | HINUNANGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 6666000 |  |  | Ongoing | 0.5 |  |  | 24I00284 | 24I00284 | 2024-07-18 | 2024-07-26 | 2024-08-08 | 2024-09-23 | 2024-10-04 | Pablo S. Labasbas Construction Corp.
NC 2024 |  | Region VIII | Southern Leyte | 305496 | Sto. Niño National High School | HINUNANGAN |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  |  | Ongoing | 0.25 |  |  | 24I00378 | 24I00378 | 2024-07-18 | 2024-07-26 | 2024-08-08 | 2024-12-26 | 2025-01-07 | Pablo S. Labasbas Construction Corp.
NC 2024 |  | Region VIII | Southern Leyte | 122102 | Magaupas Elementary School | LILOAN |  | 1 | 2 | 1STY2CL | GAA 17B | 6667000 |  | 6623121.37 | Ongoing | 0.9 |  |  | 24I00283 | 24I00283 | 2024-07-18 | 2024-07-26 | 2024-08-08 | 2024-09-23 | 2024-10-04 | Pablo S. Labasbas Construction Corp.
NC 2024 |  | Region VIII | Southern Leyte | 501383 | Catmon Integrated School | SAINT BERNARD |  | 1 | 2 | 1STY2CL | GAA 17B | 6667000 |  |  | Ongoing | 0.35 |  |  | 24I00332 | 24I00332 | 2024-07-18 | 2024-07-26 | 2024-08-08 | 2024-10-08 | 2024-10-18 | Pablo S. Labasbas Construction Corp.
NC 2024 |  | Region VIII | Southern Leyte | 122295 | Mahayag Elementary School | SAINT BERNARD |  | 1 | 2 | 1STY2CL | GAA 17B | 6667000 |  | 6650330 | Ongoing | 0.4 |  |  | 24I00281 | 24I00281 | 2024-07-18 | 2024-07-26 | 2024-08-08 | 2024-09-23 | 2024-10-04 | Pablo S. Labasbas Construction Corp.
NC 2024 |  | Region VIII | Southern Leyte | 122275 | Pandan-San Miguel Elementary School | SOGOD |  | 1 | 2 | 1STY2CL | GAA 17B | 6667000 |  |  | Ongoing | 0.1 |  |  | 24I00377 | 24I00377 | 2024-07-18 | 2024-07-26 | 2024-08-08 | 2024-12-26 | 2025-01-07 | Pablo S. Labasbas Construction Corp. | Site Clearing Stage
NC 2024 |  | Region VIII | Tacloban City | 500892 | Guadalupe Heights Integrated School | TACLOBAN CITY (Capital) |  | 1 | 8 | 2STY8CL | GAA 17B | 20500000 |  |  | REVERTED | 0 | [10 empty] | Requested for reversion due to no buildable space
NC 2024 |  | Region VIII | Tacloban City | 500490 | Kapuso Village Integrated School | TACLOBAN CITY (Capital) |  | 1 | 6 | 2STY6CL | GAA 17B | 15500000 |  | 15390342.95 | Ongoing | 0.45 | 2025-03-08 |  | P00875515VS | 24IM0119 | 2024-09-03 | 2024-09-10 | 2024-09-23 | 2024-09-30 | 2024-10-10 | B.Y.A. Builders & Construction Supply
NC 2024 |  | Region VIII | Tacloban City | 314004 | Northern Tacloban City National High School | TACLOBAN CITY (Capital) |  | 1 | 6 | 2STY6CL | GAA 17B | 15500000 |  | 15415420.62 | Ongoing | 0.8 | 2025-03-05 |  | P00875514VS | 24IM0121 | 2024-09-03 | 2024-09-10 | 2024-09-23 | 2024-09-30 | 2024-10-07 | PAFJ Construction and Supply, Inc.
NC 2024 |  | Region VIII | Tacloban City | 124228 | Remedios T. Romualdez Elementary School | TACLOBAN CITY (Capital) |  | 1 | 8 | 2STY8CL | GAA 17B | 20500000 |  | 20391119 | Ongoing | 0.57 | 2025-03-05 |  | P00875513VS | 24IM0128 | 2024-09-03 | 2024-09-10 | 2024-09-23 | 2024-09-30 | 2024-10-07 | R. Yao Construction
NC 2024 |  | Region VIII | Tacloban City | 303666 | Sagkahan National High School | TACLOBAN CITY (Capital) |  | 1 | 6 | 2STY6CL | GAA 17B | 15500000 |  | 15413065.2 | Ongoing | 0.5 | 2025-03-05 |  | P00875517VS | 24IM0122 | 2024-09-03 | 2024-09-10 | 2024-09-23 | 2024-09-30 | 2024-10-07 | PAFJ Construction and Supply, Inc.
NC 2024 |  | Region VIII | Tacloban City | 314005 | Scandinavian National High School | TACLOBAN CITY (Capital) |  | 1 | 6 | 2STY6CL | GAA 17B | 15500000 |  | 20387804.97 | REVERTED | 0 | [10 empty] | REVERTED
NC 2024 |  | Region VIII | Tacloban City | 137154 | St. Francis Elementary School | TACLOBAN CITY (Capital) |  | 1 | 8 | 2STY8CL | GAA 17B | 20500000 |  | 20387804.97 | Ongoing | 0.55 | 2025-05-21 |  | P00875512VS | 24IM0129 | 2024-10-09 | 2024-10-16 | 2024-11-04 | 2024-11-19 | 2024-11-28 | J Pro Builders
NC 2024 |  | Region VIII | Tacloban City | 344881 | Sto. Nino Senior High School | TACLOBAN CITY (Capital) |  | 1 | 8 | 2STY8CL | GAA 17B | 20500000 |  | 20362715.93 | Ongoing | 0.3 | 2025-02-16 |  | P00875519VS | 24IM0097 | 2024-07-18 | 2024-07-25 | 2024-08-07 | 2024-09-10 | 2024-09-20 | Everbuilt Construction

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.