## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of Sites Terminated | No. of CL Terminated | Status as of July 11, 2025
REPAIR 2020 | Region VIII | Baybay City | 121084 | Hibunawan Elementary School | CITY OF BAYBAY | 5 | 1 | 6 | Repair of Classrooms | 2116610 | 1 | 2116609.83 | COMPLETED | 1 | January 0, 1900 | January 0, 1900 | 2019-11-I014 | 2019-11-I014 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2019-12-18 | January 0, 1900 | MELGAZO CONSTRUCTION AND SUPPLY | RTA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VIII | Baybay City | 121142 | Kantagnos Elementary School | CITY OF BAYBAY | 5 | 1 | 2 | Repair of Classrooms | 780000 | 1 | 780000 | COMPLETED | 1 | January 0, 1900 | January 0, 1900 | 2019-11-I019 | 2019-11-I019 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2019-12-18 | January 0, 1900 | J CUSTORIO CONSTRUCTION | RTA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VIII | Baybay City | 121123 | Maslug Elementary School | CITY OF BAYBAY | 5 | 1 | 3 | Repair of Classrooms | 905670 | 1 | 905669.71 | COMPLETED | 1 | January 0, 1900 | January 0, 1900 | 2019-11-I017 | 2019-11-I017 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2019-12-18 | January 0, 1900 | AAVB CONSTRUCTION AND SUPPLY | RTA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Baybay City | 121124 | Maypatag Elementary School | CITY OF BAYBAY | 5 | 1 | 5 | Repair of Classrooms | 1771880 | 1 | 1771879.65 | COMPLETED | 1 | January 0, 1900 | January 0, 1900 | 2019-11-I018 | 2019-11-I018 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2019-12-18 | January 0, 1900 | MELGAZO CONSTRUCTION AND SUPPLY | RTA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VIII | Baybay City | 121110 | Pansagan Elementary School | CITY OF BAYBAY | 5 | 1 | 5 | Repair of Classrooms | 1505631 | 1 | 1505630.15 | COMPLETED | 1 | January 0, 1900 | January 0, 1900 | 2019-11-I015 | 2019-11-I015 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2019-12-18 | January 0, 1900 | JFR CONSTRUCTION | RTA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VIII | Baybay City | 121149 | San Agustin Elementary School | CITY OF BAYBAY | 5 | 1 | 5 | Repair of Classrooms | 1596320 | 1 | 1596319.19 | COMPLETED | 1 | January 0, 1900 | January 0, 1900 | 2019-11-I020 | 2019-11-I020 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2019-12-18 | January 0, 1900 | RAQ J BUILDERS | RTA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VIII | Baybay City | 121111 | San Juan Elementary School | CITY OF BAYBAY | 5 | 1 | 3 | Repair of Classrooms | 904047 | 1 | 904046.26 | COMPLETED | 1 | January 0, 1900 | January 0, 1900 | 2019-11-I016 | 2019-11-I016 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2019-12-18 | January 0, 1900 | MAGA CONSTRUCTION AND SUPPLIES | RTA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Biliran | 120789 | CAPAYAS ES | CABUCGAYAN | 0 | 1 | 2 | Repair of Classrooms | 742261 | 1 | 742260.66 | COMPLETED | 1 | [9 empty] | A AND B ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VIII | Biliran | 120794 | PAWIKAN ES | CABUCGAYAN | 0 | 1 | 1 | Repair of Classroom | 363074 | 1 | 361130.34 | COMPLETED | 1 | [9 empty] | A AND B ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VIII | Biliran | 120807 | LOOC ES | CAIBIRAN | 0 | 1 | 1 | Repair of Classroom | 361500 | 1 | 361500 | COMPLETED | 1 | [9 empty] | A AND B ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VIII | Biliran | 120812 | TOMALISTIS ES | CAIBIRAN | 0 | 1 | 1 | Repair of Classroom | 361500 | 1 | 361500 | COMPLETED | 1 | [9 empty] | A AND B ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VIII | Biliran | 120834 | KAWAYAN CS | KAWAYAN | 0 | 1 | 2 | Repair of Classrooms | 715583 | 1 | 362918.37 | COMPLETED | 1 | [9 empty] | INFRASERVE CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VIII | Biliran | 500411 | INASUYAN ES | KAWAYAN | 0 | 1 | 1 | Repair of Classroom | 361500 | 1 | 715582.37 | COMPLETED | 1 | [9 empty] | INFRASERVE CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VIII | Biliran | 120840 | SAN LORENZO ES | KAWAYAN | 0 | 1 | 1 | Repair of Classroom | 362919 | 1 | 361500 | COMPLETED | 1 | [9 empty] | A AND B ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VIII | Biliran | 120847 | BATO BANLAS ES | MARIPIPI | 0 | 1 | 1 | Repair of Classroom | 386852 | 1 | 749483.85 | COMPLETED | 1 | [9 empty] | SEGUA CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VIII | Biliran | 120846 | AGUTAY ES | MARIPIPI | 0 | 1 | 2 | Repair of Classrooms | 749484 | 1 | 386851.28 | COMPLETED | 1 | [9 empty] | SEGUA CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VIII | Biliran | 120848 | BINALAYAN ES | MARIPIPI | 0 | 1 | 2 | Repair of Classrooms | 838646 | 1 | 838645.37 | COMPLETED | 1 | [9 empty] | BCG DESIGN AND CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VIII | Biliran | 120849 | CALBANI ES | MARIPIPI | 0 | 1 | 1 | Repair of Classroom | 389617 | 1 | 389617.2 | COMPLETED | 1 | [9 empty] | BCG DESIGN AND CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VIII | Biliran | 120850 | CANDUHAO ES | MARIPIPI | 0 | 1 | 3 | Repair of Classrooms | 1159960 | 1 | 1159959.18 | COMPLETED | 1 | [9 empty] | MB ANG CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Borongan City | 122358 | Calingatngan ES | BORONGAN CITY(Capital) | 0 | 1 | 9 | Repair of Classrooms | 2808676 | 1 | 2808675.05 | COMPLETED | 1 | [9 empty] | J.A DEVELOPERS AND ENGINEERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VIII | Borongan City | 122404 | Locso-on ES | BORONGAN CITY(Capital) | 0 | 1 | 9 | Repair of Classrooms | 2810086 | 1 | 2810085.84 | COMPLETED | 1 | [9 empty] | J.A DEVELOPERS AND ENGINEERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VIII | Borongan City | 303525 | Sta. Fe NHS | CITY OF BORONGAN (Capital) | 0 | 1 | 2 | Repair of Classrooms | 681346 | 1 | 681345.91 | COMPLETED | 1 | [9 empty] | STONE BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VIII | Calbayog City | 124076 | Alang-Alang Elementary School | CALBAYOG CITY | 1 | 1 | 3 | Repair of Classrooms | 1172229 | 1 | 1160700.88 | COMPLETED | 1 | [10 empty] | MORI Builders | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Calbayog City | 124054 | Bayo Elementary School | CALBAYOG CITY | 1 | 1 | 1 | Repair of classroom | 390525 | 1 | 384884.2 | COMPLETED | 1 | [10 empty] | GBV Construction | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VIII | Calbayog City | 124083 | Cagbayang Elementary School | CALBAYOG CITY | 1 | 1 | 5 | Repair of Classrooms | 1952754 | 1 | 1947085.41 | COMPLETED | 1 | [10 empty] | PEDAD Construction & Supply | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VIII | Calbayog City | 124035 | Cahumpan Elementary School | CALBAYOG CITY | 1 | 1 | 2 | Repair of Classrooms | 763213 | 1 | 710954.46 | COMPLETED | 1 | [10 empty] | ND Caranzo | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VIII | Calbayog City | 194001 | Calbayog City SPED Center | CALBAYOG CITY | 1 | 1 | 8 | Repair of Classrooms | 3059713 | 1 | 2076954.8 | COMPLETED | 1 | [10 empty] | HD Golden Builders | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VIII | Calbayog City | 124087 | Capacuhan Elementary School | CALBAYOG CITY | 1 | 1 | 2 | Repair of Classrooms | 780025 | 1 | 737498.68 | COMPLETED | 1 | [10 empty] | ND Caranzo | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VIII | Calbayog City | 124088 | Caybago Elementary School | CALBAYOG CITY | 1 | 1 | 4 | Repair of Classrooms | 1600837 | 1 | 1085071.3 | COMPLETED | 1 | [10 empty] | HD Golden Builders | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VIII | Calbayog City | 124064 | Longsob Elementary School | CALBAYOG CITY | 1 | 1 | 1 | Repair of Classroom | 389792 | 1 | 347226.6 | COMPLETED | 1 | [10 empty] | ND Caranzo | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VIII | Calbayog City | 124023 | Pagbalican Elementary School | CALBAYOG CITY | 1 | 1 | 2 | Repair of Classrooms | 774944 | 1 | 769467.49 | COMPLETED | 1 | [10 empty] | GBV Construction | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VIII | Catbalogan | 123420 | Buluan Elementary School | Catbalogan City | 2 | 1 | 3 | Repair of Classrooms | 1043049 | 1 | 1043048.84 | COMPLETED | 1 | [10 empty] | QCC Construction and Supply | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Catbalogan | 123397 | Catbalogan I Central Elementary School | Catbalogan City | 2 | 1 | 10 | Repair of Classrooms | 3506054 | 1 | 3506053.14 | COMPLETED | 1 | [10 empty] | NV & C CONSTRUCTION AND GENERAL SUPPLY | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region VIII | Catbalogan | 123425 | Lagundi Elementary School | Catbalogan City | 2 | 1 | 2 | Repair of Classrooms | 699872 | 1 | 699871.6 | COMPLETED | 1 | [10 empty] | AGB CONSTRUCTION AND SUPPLY | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VIII | Eastern Samar | 122610 | Caisawan Elementary School | BALANGKAYAN | 0 | 1 | 6 | Repair of Classrooms | 2046940 | 1 | 2031518.8385 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VIII | Eastern Samar | 122415 | Cansangaya Elementary School | CAN-AVID | 0 | 1 | 5 | Repair of Classrooms | 1994195 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VIII | Eastern Samar | 122451 | Dapdap Central Elementary School | DOLORES | 0 | 1 | 14 | Repair of Classrooms | 4360911 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2020 | Region VIII | Eastern Samar | 122453 | Hapitan Elementary School | DOLORES | 0 | 1 | 1 | Repair of Classroom | 353104 | 1 | 350428.9355 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VIII | Eastern Samar | 122455 | Jicontol Elementary School | DOLORES | 0 | 1 | 6 | Repair of Classrooms | 2202201 | 1 | 2185518.9932 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VIII | Eastern Samar | 122484 | Gen. MacArthur Central Elementary School | GENERAL MACARTHUR | 0 | 1 | 21 | Repair of Classrooms | 6402167 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0
REPAIR 2020 | Region VIII | Eastern Samar | 122518 | Banaag Elementary School | GUIUAN | 0 | 1 | 3 | Repair of Classrooms | 1069944 | 1 | 1061883.0115 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Eastern Samar | 122579 | Maylimon Elementary School | JIPAPAD | 0 | 1 | 1 | Repair of Classroom | 372407 | 1 | 369585.0013 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VIII | Eastern Samar | 122709 | Bugay Elementary School | SALCEDO | 0 | 1 | 4 | Repair of Classrooms | 1510232 | 1 | 1505451.556 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VIII | Eastern Samar | 122693 | College Elementary School | SALCEDO | 0 | 1 | 1 | Repair of Classroom | 339709 | 1 | 338633.6771 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VIII | Eastern Samar | 122716 | Jagnaya Elementary School | SALCEDO | 0 | 1 | 3 | Repair of Classrooms | 1055580 | 1 | 1052238.1504 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Eastern Samar | 122697 | Malbog Elementary School | SALCEDO | 0 | 1 | 3 | Repair of Classrooms | 1267689 | 1 | 1263676.6166 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Eastern Samar | 122698 | Naparaan Elementary School | SALCEDO | 0 | 1 | 9 | Repair of Classrooms | 3314403 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 303421 | San Agustin National High School | BABATNGON | 1 | 1 | 3 | Repair of Classrooms | 1021071 | 1 | 1021070.85 | COMPLETED | 1 | [9 empty] | GPUY CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 121863 | Pinarigusan Primary School | SAN MIGUEL | 1 | 1 | 1 | Repair of Classroom | 423232 | 1 | 423231.17 | COMPLETED | 1 | [9 empty] | KAMARI CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 121946 | Burak Elementary School | TOLOSA | 1 | 1 | 2 | Repair of Classrooms | 885311 | 1 | 885310.1433 | COMPLETED | 1 | [9 empty] | 4ANGLE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 121947 | Canmogsay Elementary School | TOLOSA | 1 | 1 | 3 | Repair of Classrooms | 839984 | 1 | 839983.91 | COMPLETED | 1 | [9 empty] | 4ANGLE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 121952 | Olot Elementary School | TOLOSA | 1 | 1 | 3 | Repair of Classrooms | 991438 | 1 | 991437.33 | COMPLETED | 1 | [9 empty] | 4ANGLE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 121957 | Telegrafo Elementary School | TOLOSA | 1 | 1 | 12 | Repair of Classrooms | 3326367 | 1 | 3326366.83 | COMPLETED | 1 | [9 empty] | C N E CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 121042 | Abango Elementary School | BARUGO | 2 | 1 | 3 | Repair of Classrooms | 1018677 | 1 | 1018676.87 | COMPLETED | 1 | [9 empty] | GPUY CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 121293 | Dagami North Central School | DAGAMI | 2 | 1 | 3 | Repair of Classrooms | 623315 | 1 | 623314.11 | COMPLETED | 1 | [9 empty] | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 121314 | Guinarona Elementary School | DAGAMI | 2 | 1 | 8 | Repair of Classrooms | 2056575 | 1 | 2056574.43 | COMPLETED | 1 |  |  |  |  | 2018-07-22 | 2018-08-05 | 2018-08-19 |  |  | JJ PALACIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 121316 | Maliwaliw Elementary School | DAGAMI | 2 | 1 | 3 | Repair of Classrooms | 624970 | 1 | 624969.89 | COMPLETED | 1 | [9 empty] | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 121334 | San Jose Central School | DULAG | 2 | 1 | 5 | Repair of Classrooms | 1541090 | 1 | 1541089.94 | COMPLETED | 1 | [9 empty] | GPUY CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 121617 | Casuntingan Elementary School | MACARTHUR | 2 | 1 | 1 | Repair of Classroom | 541219 | 1 | 541218.55 | COMPLETED | 1 | [9 empty] | GPUY CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 121814 | Colawen Elementary School | PASTRANA | 2 | 1 | 4 | Repair of Classrooms | 1051632 | 1 | 1051631.79 | COMPLETED | 1 | [9 empty] | KAMARI CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 121958 | Astorga Elementary School | TUNGA | 2 | 1 | 3 | Repair of Classrooms | 1025655 | 1 | 1025654.45 | COMPLETED | 1 | [9 empty] | KAMARI CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 191556 | Burabod PS | McARTHUR | 3 | 1 | 1 | Repair of Classroom | 387305 | 1 | 387304.76 | COMPLETED | 1 | [9 empty] | GPUY CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 121717 | Calunasan Elementary School | MERIDA | 4 | 1 | 9 | Repair of Classrooms | 2076549 | 1 | 2076548.42 | COMPLETED | 1 | [9 empty] | SAMARINAN CONSTRUCTION AND DEVELOPMENT CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 121724 | Libjo Elementary School | MERIDA | 4 | 1 | 2 | Repair of Classrooms | 494631 | 1 | 494631 | COMPLETED | 1 | [9 empty] | CERILLES ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 121730 | Merida Central School | MERIDA | 4 | 1 | 4 | Repair of Classroom | 771294 | 1 | 771293.2 | COMPLETED | 1 | [9 empty] | CERILLES ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 121800 | Parrilla Elementary School | PALOMPON | 4 | 1 | 3 | Repair of Classrooms | 1156231 | 1 | 1156230.15 | COMPLETED | 1 | [9 empty] | QCC CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 121808 | Tabunok Elementary School | PALOMPON | 4 | 1 | 3 | Repair of Classrooms | 930301 | 1 | 930300.6 | COMPLETED | 1 | [9 empty] | QCC CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 120904 | Bernardo V. Closa Central School | ABUYOG | 5 | 1 | 7 | Repair of Classrooms | 1267288 | 1 | 1297441.71 | COMPLETED | 1 | [9 empty] | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 120900 | Tib-o Elementary School | ABUYOG | 5 | 1 | 3 | Repair of Classrooms | 513525 | 1 | 792280.74 | COMPLETED | 1 | [9 empty] | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 303347 | Bato School of Fisheries | BATO | 5 | 1 | 1 | Repair of Classroom | 1534343 | 1 | 1534342.17 | COMPLETED | 1 | [9 empty] | BCG DESIGN AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VIII | Leyte | 121646 | Paril Elementary School | MAHAPLAG | 5 | 1 | 3 | Repair of Classrooms | 1225422 | 1 | 1225421.53 | COMPLETED | 1 | [9 empty] | BCG DESIGN AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Maasin City | 303457 | Guadalupe NHS | CITY OF MAASIN (Capital) | 0 | 1 | 7 | Repair of Classrooms | 1383064 | 1 | 1383063.87 | COMPLETED | 1 | January 0, 1900 | January 0, 1900 | REPAIR-20-006 | REPAIR-20-006 | 2019-11-21 | 2019-11-29 | 2019-11-12 | 2020-02-13 |  | VHITS D. G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region VIII | Maasin City | 122160 | Hinapu Gamay ES | CITY OF MAASIN (Capital) | 0 | 1 | 7 | Repair of Classrooms | 1666719 | 1 | 1666718.92 | COMPLETED | 1 | January 0, 1900 | January 0, 1900 | REPAIR-20-003 | REPAIR-20-003 | 2019-11-21 | 2019-11-29 | 2019-11-12 | 2020-02-13 |  | VHITS D. G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region VIII | Maasin City | 303468 | Malapoc Sur NHS | CITY OF MAASIN (Capital) | 0 | 1 | 6 | Repair of Classrooms | 1451962 | 1 | 1451961.18 | COMPLETED | 1 | January 0, 1900 | January 0, 1900 | REPAIR-20-007 | REPAIR-20-007 | 2019-11-21 | 2019-11-29 | 2019-11-12 | 2020-02-13 |  | VHITS D. G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VIII | Maasin City | 122140 | Matin-Aw ES | CITY OF MAASIN (Capital) | 0 | 1 | 5 | Repair of Classrooms | 1382512 | 1 | 1382511.09 | COMPLETED | 1 | January 0, 1900 | January 0, 1900 | REPAIR-20-001 | REPAIR-20-001 | 2019-11-21 | 2019-11-29 | 2019-11-12 | 2020-02-13 |  | VHITS D. G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VIII | Maasin City | 122144 | San Isidro MGS | CITY OF MAASIN (Capital) | 0 | 1 | 4 | Repair of Classrooms | 901739 | 1 | 901738.86 | COMPLETED | 1 | January 0, 1900 | January 0, 1900 | REPAIR-20-002 | REPAIR-20-002 | 2019-11-21 | 2019-11-29 | 2019-11-12 | 2020-02-13 |  | VHITS D. G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VIII | Maasin City | 122175 | Sta. Cruz ES | CITY OF MAASIN (Capital) | 0 | 1 | 5 | Repair of Classrooms | 1675367 | 1 | 1675366.97 | COMPLETED | 1 | January 0, 1900 | January 0, 1900 | REPAIR-20-004 | REPAIR-20-004 | 2019-11-21 | 2019-11-29 | 2019-11-12 | 2020-02-13 |  | VHITS D. G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VIII | Maasin City | 238001 | Tomoy-Tomoy MGS | CITY OF MAASIN (Capital) | 0 | 1 | 3 | Repair of Classrooms | 685413 | 1 | 685412.48 | COMPLETED | 1 | January 0, 1900 | January 0, 1900 | REPAIR-20-005 | REPAIR-20-005 | 2019-11-21 | 2019-11-29 | 2019-11-12 | 2020-02-13 |  | VHITS D. G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Northern Samar | 122812 | Manuel L. Quezon ES | Bobon | 1 | 1 | 4 | Repair of Classrooms | 1317473 | 1 | 809721.4 | COMPLETED | 1 | [9 empty] | J. Custorio Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VIII | Northern Samar | 122826 | Oson ES | Capul | 1 | 1 | 5 | Repair of Classrooms | 1292094 | 1 | 1006550 | COMPLETED | 1 | [9 empty] | Grinder Civil Eng'g & Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VIII | Northern Samar | 123084 | Curry ES | Lope de Vega | 1 | 1 | 4 | Repair of Classrooms | 1567753 | 1 | 954140.27 | COMPLETED | 1 | [9 empty] | JCAD Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VIII | Northern Samar | 303577 | San Isidro AIHS | San Isidro | 1 | 1 | 14 | Repair of Classrooms | 3471838 | 1 | 2214649.01 | COMPLETED | 1 | [9 empty] | ACHROCONS Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2020 | Region VIII | Northern Samar | 123275 | Gonzaga ES | Victoria | 1 | 1 | 2 | Repair of Classrooms | 769310 | 1 | 769218.57 | COMPLETED | 1 |  |  | BEFF2019-NS-B2-REPAIR-LOT6 | BEFF2019-NS-B2-REPAIR-LOT6 | 2019-08-01 | 2019-08-08 | 2019-08-20 |  |  | ACF Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VIII | Northern Samar | 123278 | Lungib ES | Victoria | 1 | 1 | 7 | Repair of Classrooms | 1399544 | 1 | 1398625.31 | COMPLETED | 1 | [9 empty] | ACF Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region VIII | Northern Samar | 122898 | Hibubullao ES | Catubig | 2 | 1 | 12 | Repair of Classrooms | 4050183 | 1 | 2545200 | COMPLETED | 1 | [9 empty] | J. Custorio Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region VIII | Northern Samar | 123108 | Mapanas CS | Mapanas | 2 | 1 | 10 | Repair of Classrooms | 2836215 | 1 | 1899450 | COMPLETED | 1 | [9 empty] | J. Custorio Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region VIII | Northern Samar | 303584 | Sumoroy AIHS | Palapag | 2 | 1 | 47 | Repair of Classrooms | 16132693 | 1 | 10305280 | COMPLETED | 1 | [9 empty] | J. Custorio Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 47 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124143 | Alta Vista Elementary School | ORMOC CITY | 4 | 1 | 1 | Repair of Classroom | 385187 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124144 | Bagong ES | ORMOC CITY | 4 | 1 | 6 | Repair of Classrooms | 1954500 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124174 | Cabato-an Elementary School | ORMOC CITY | 4 | 1 | 3 | Repair of Classrooms | 944555 | 1 |  | COMPLETED | 1 | January 0, 1900 | January 0, 1900 |  | BEFF-2020-REPAIR-B1-L4 | 2019-11-20 | 2019-11-29 | 2019-12-11 | 2019-01-06 | January 0, 1900 |  | rebid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124175 | Cagbuhangin Elementary School | ORMOC CITY | 4 | 1 | 6 | Repair of Classrooms | 1806239 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124148 | Can-adieng ES | ORMOC CITY | 4 | 1 | 3 | Repair of Classrooms | 760000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124149 | Can-untog Elementary School | ORMOC CITY | 4 | 1 | 3 | Repair of Classrooms | 955206 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124177 | Concepcion ES | ORMOC CITY | 4 | 1 | 5 | Repair of Classrooms | 1213000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124150 | Dolores ES | ORMOC CITY | 4 | 1 | 4 | Repair of Classrooms | 845000 | 1 | 221248.6542 | COMPLETED | 1 |  |  |  | 2019-BEFF-R-B1-C1 | January 31, 2019 | January 30, 2019 | February 11, 2019 | February 18, 2019 | August 27, 2019 | J. CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124152 | Donghol Elementary School | ORMOC CITY | 4 | 1 | 6 | Repair of Classrooms | 1659807 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124153 | Gaas ES | ORMOC CITY | 4 | 1 | 3 | Repair of Classrooms | 825000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124180 | Inaad Elementary School | ORMOC CITY | 4 | 1 | 3 | Repair of Classrooms | 1120229 | 1 | 1120228.6 | COMPLETED | 1 | January 0, 1900 | January 0, 1900 |  | BEFF-2020-REPAIR-B1-L2 | 2019-11-20 | 2019-11-29 | 2019-12-11 | 2019-01-06 | January 0, 1900 | Melgazo Construction and Supply | RTA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124181 | Juaton Elementary School | ORMOC CITY | 4 | 1 | 2 | Repair of Classrooms | 763431 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124158 | Liberty ES | ORMOC CITY | 4 | 1 | 3 | Repair of Classrooms | 810000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124159 | Luna ES | ORMOC CITY | 4 | 1 | 2 | Repair of Classrooms | 465000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124162 | Magaswe Primary School | ORMOC CITY | 4 | 1 | 2 | Repair of Classrooms | 777275 | 1 |  | COMPLETED | 1 | January 0, 1900 | January 0, 1900 |  | BEFF-2020-REPAIR-B1-L4 | 2019-11-20 | 2019-11-29 | 2019-12-11 | 2019-01-06 | January 0, 1900 |  | rebid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124163 | Maglahug ES | ORMOC CITY | 4 | 1 | 3 | Repair of Classrooms | 900000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124164 | Mahayag Elementary School | ORMOC CITY | 4 | 1 | 4 | Repair of Classrooms | 1860468 | 1 | 1860467.34 | COMPLETED | 1 | January 0, 1900 | January 0, 1900 |  | BEFF-2020-REPAIR-B1-L3 | 2019-11-20 | 2019-11-29 | 2019-12-11 | 2019-01-06 | January 0, 1900 | Melgazo Construction and Supply | RTA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124166 | Milagro ES | ORMOC CITY | 4 | 1 | 2 | Repair of Classrooms | 465000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124217 | Nasunogan Elementary School | ORMOC CITY | 4 | 1 | 5 | Repair of Classrooms | 1331276 | 1 | 1331275.59 | COMPLETED | 1 |  |  |  | BEFF-2020-REPAIR-B1-L1 | 2019-11-20 | 2019-11-29 | 2019-12-11 | 2019-01-06 | January 0, 1900 | QCC Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124187 | Nueva Vista ES | ORMOC CITY | 4 | 1 | 6 | Repair of Classrooms | 1512000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124167 | Patag Elementary School | ORMOC CITY | 4 | 1 | 5 | Repair of Classrooms | 2279928 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124191 | T. Aviles Elementary School | ORMOC CITY | 4 | 1 | 9 | Repair of Classrooms | 3229803 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VIII | Ormoc City | 124193 | Valencia Central School | ORMOC CITY | 4 | 1 | 15 | Repair of Classrooms | 2351774 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123285 | ALMAGRO CS | ALMAGRO | 1 | 1 | 8 | Repair of Classrooms | 3377152 | 1 | 3377151.28 | COMPLETED | 1 | [8 empty] | 2020-09-23 | VHITS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123288 | COSTA RICA ELEM.SCHOOL | ALMAGRO | 1 | 1 | 4 | Repair of Classrooms | 1718248 | 1 | 1718247.44 | COMPLETED | 1 | [8 empty] | 2020-09-23 | MAGA CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123292 | LUNANG I CS | ALMAGRO | 1 | 1 | 4 | Repair of Classrooms | 1544706 | 1 | 1544705.86 | COMPLETED | 1 | [8 empty] | 2020-09-23 | REVCON |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123537 | CANHUMAWID ES | GANDARA | 1 | 1 | 2 | Repair of Classrooms | 909886 | 1 | 909885.62 | COMPLETED | 1 | [8 empty] | 2020-09-23 | SLHAV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123553 | PIZARRO ES | GANDARA | 1 | 1 | 5 | Repair of Classrooms | 1912618 | 1 | 1912617.36 | COMPLETED | 1 | [8 empty] | 2020-09-23 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123816 | BAQUIW ES | TAGAPUL-AN | 1 | 1 | 3 | Repair of Classrooms | 1158604 | 1 | 1158603.81 | COMPLETED | 1 | [8 empty] | 2020-09-23 | GG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123308 | BASIAO ES | BASEY | 2 | 1 | 9 | Repair of Classrooms | 3980962 | 1 | 3980961.4 | COMPLETED | 1 | [8 empty] | 2020-09-23 | EMT |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123313 | CATADMAN ES | BASEY | 2 | 1 | 2 | Repair of Classrooms | 954532 | 1 | 949436.02 | COMPLETED | 1 | [8 empty] | 2020-09-23 | G BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123317 | LOOG ES | BASEY | 2 | 1 | 4 | Repair of Classrooms | 1575134 | 1 | 1575133.23 | COMPLETED | 1 | [8 empty] | 2020-09-23 | TRIPLE Z- MC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123322 | RAWIS ES | BASEY | 2 | 1 | 12 | Repair of Classrooms | 4903375 | 1 | 4903374.25 | COMPLETED | 1 | [8 empty] | 2020-09-23 | MAGA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123325 | SERUM ES | BASEY | 2 | 1 | 3 | Repair of Classrooms | 1143309 | 1 | 1143308.36 | COMPLETED | 1 | [8 empty] | 2020-09-23 | GPUY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123354 | Tinaogan ES | BASEY | 2 | 1 | 2 | Repair of Classrooms | 602388 | 1 | 597314.94 | COMPLETED | 1 | [8 empty] | 2020-09-23 | G BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123580 | TABAY ES | hinabangan | 2 | 1 | 2 | Repair of Classrooms | 771789 | 1 | 771788.76 | COMPLETED | 1 | [8 empty] | 2020-09-23 | PLGL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123604 | SAN FERNANDO ES | JIABONG | 2 | 1 | 1 | Repair of Classroom | 365779 | 1 | 365778.92 | COMPLETED | 1 | [8 empty] | 2020-09-23 | PLGL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123642 | Motiong Central Elem. School | MOTIONG | 2 | 1 | 8 | Repair of Classrooms | 3077837 | 1 | 3077836.5 | COMPLETED | 1 | [8 empty] | 2020-09-23 | JC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123659 | Bangon ES | PINABACDAO | 2 | 1 | 8 | Repair of Classrooms | 3226729 | 1 | 3226728.53 | COMPLETED | 1 | [8 empty] | 2020-09-23 | EMT |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VIII | Southern Leyte | 122074 | Mahalo Elementary School | ANAHAWAN | 0 | 1 | 4 | Repair of Classroom | 1280614 | 1 | 1280613.96 | COMPLETED | 1 | 2021-01-13 | January 0, 1900 | BEFF-CY2020- REPAIR-L1 |  | 2019-11-24 | 2019-12-09 | 2020-01-07 | 2020-03-02 | 2020-10-08 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VIII | Southern Leyte | 121993 | Banahao Multi-Grade Elementary School | BONTOC | 0 | 1 | 2 | Repair of Classrooms | 663664 | 1 | 663663.17 | COMPLETED | 1 | 2021-01-06 | January 0, 1900 | BEFF-CY2020- REPAIR-L6 |  | 2019-11-24 | 2019-12-09 | 2020-01-07 | 2020-03-02 | 2020-10-08 | J'NER CEPADA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VIII | Southern Leyte | 122085 | Tigbao Elementary School | LIBAGON | 0 | 1 | 9 | Repair of Classrooms | 3075638 | 1 | 3075637.02 | COMPLETED | 1 | 2021-02-12 | January 0, 1900 | BEFF-CY2020- REPAIR-L3 |  | 2019-11-24 | 2019-12-09 | 2020-01-07 | 2020-03-02 | 2020-10-08 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VIII | Southern Leyte | 122101 | Liloan Central School | LILOAN | 0 | 1 | 22 | Repair of Classrooms | 7217394 | 1 | 7217393.56 | COMPLETED | 1 | 2021-03-14 | January 0, 1900 | BEFF-CY2020- REPAIR-L4 |  | 2019-11-24 | 2019-12-09 | 2020-01-07 | 2020-03-02 | 2020-10-08 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 0 | 0
REPAIR 2020 | Region VIII | Southern Leyte | 122300 | Panian Elementary School | SAINT BERNARD | 0 | 1 | 3 | Repair of Classrooms | 997824 | 1 | 997823.57 | COMPLETED | 1 | 2021-01-06 | January 0, 1900 | BEFF-CY2020- REPAIR-L2 |  | 2019-11-24 | 2019-12-09 | 2020-01-07 | 2020-03-02 | 2020-10-08 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Southern Leyte | 122243 | San Ricardo Central School | SAN RICARDO | 0 | 1 | 16 | Repair of Classrooms | 5806035 | 1 | 5806034.2 | COMPLETED | 1 | 2021-03-14 | January 0, 1900 | BEFF-CY2020- REPAIR-L5 |  | 2019-11-24 | 2019-12-09 | 2020-01-07 | 2020-03-02 | 2020-10-08 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2020 | Region VIII | Southern Leyte | 122266 | Kanangkaan Elementary School | SOGOD | 0 | 1 | 4 | Repair of Classrooms | 1440270 | 1 | 1440269.29 | COMPLETED | 1 | 2021-01-06 | January 0, 1900 | BEFF-CY2020- REPAIR-L6 |  | 2019-11-24 | 2019-12-09 | 2020-01-07 | 2020-03-02 | 2020-10-08 | J'NER CEPADA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VIII | Tacloban City | 195001 | Manlurip Elementary School | TACLOBAN CITY (Capital) | 1 | 1 | 5 | Repair of Classrooms | 652167 | 1 | 652166.89 | COMPLETED | 1 | [9 empty] | RD COBACHA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VIII | Tacloban City | 303664 | Marasbaras NHS | TACLOBAN CITY (Capital) | 1 | 1 | 19 | Repair of Classrooms | 2061155 | 1 | 2061154.36 | COMPLETED | 1 | [9 empty] | ARCHO CONS CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 0 | 0
REPAIR 2020 | Region VIII | Tacloban City | 124237 | Old Kawayan Elementary School | TACLOBAN CITY (Capital) | 1 | 1 | 3 | Repair of Classrooms | 513031 | 1 | 513030.49 | COMPLETED | 1 | [9 empty] | PYUKIE CONSTRUCTION INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VIII | Tacloban City | 124238 | Palanog ES | TACLOBAN CITY (Capital) | 1 | 1 | 12 | Repair of Classrooms | 1233854 | 1 | 870269.84 | COMPLETED | 1 | [9 empty] | PYUKIE CONSTRUCTION INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region VIII | Tacloban City | 124249 | San Fernando Central School | TACLOBAN CITY (Capital) | 1 | 1 | 18 | Repair of Classrooms | 2389725 | 1 | 2389724.01 | COMPLETED | 1 | [9 empty] | UNITRON CONSTRUCTION & DEV'T CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0
REPAIR 2020 | Region VIII | Tacloban City | 124251 | San Roque ES | TACLOBAN CITY (Capital) | 1 | 1 | 9 | Repair of Classrooms | 677216 | 1 | 677215.32 | COMPLETED | 1 | [9 empty] | RD COBACHA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VIII | Tacloban City | 124241 | Sto. Nino Elementary School | TACLOBAN CITY (Capital) | 1 | 1 | 9 | Repair of Classrooms | 870270 | 1 | 870269.84 | COMPLETED | 1 | [9 empty] | VHITS D. G BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2021 | Region VIII | Baybay City | 121109 | Palhi Elementary School | CITY OF BAYBAY | 5 | 1 | 4 | Repair of Classrooms | 2930798.51 | 1 | 2841049.98 | COMPLETED | 1 |  |  | 2021-06-I001 | 2021-06-I001 | 2021-06-07 | 2021-06-17 | 2021-07-13 | 2021-07-30 | 2021-08-10 | TRI BAIRN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region VIII | Biliran | 120778 | Core Shelter ES | BILIRAN | 0 | 1 | 2 | Repair of Classrooms | 1085661.84 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VIII | Biliran | 120788 | Cabucgayan Central School | CABUCGAYAN | 0 | 1 | 13 | Repair of Classrooms | 4923979.52 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2021 | Region VIII | Biliran | 120794 | Pawikan ES | CABUCGAYAN | 0 | 1 | 2 | Repair of Classrooms | 768493.11 | 1 | 361130.34 | COMPLETED | 1 | [9 empty] | A AND B ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VIII | Borongan City | 122407 | Suribao ES | CITY OF BORONGAN (Capital) | 0 | 1 | 8 | Repair of Classrooms | 2740661.46 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region VIII | Borongan City | 122367 | Taboc ES | CITY OF BORONGAN (Capital) | 0 | 1 | 2 | Repair of Classrooms | 925079.86 | 1 | 1356342 | COMPLETED | 1 | 2019-11-13 |  | CY 2019 REPAIR/REHABILITATION-Batch 1-BORCITY | Repair/rehabilitation-Lot 2 | 2018-10-18 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2019-08-08 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VIII | Calbayog City | 124121 | Binaliw Elementary School | CALBAYOG CITY | 1 | 1 | 8 | Repair of Classrooms | 3498263.94 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region VIII | Catbalogan City | 123429 | Buri Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | 2 | Repair of Classrooms | 1385471.67 | 1 |  | COMPLETED | 1 | 2021-11-26 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VIII | Catbalogan City | 123427 | Rama Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | 3 | Repair of Classrooms | 1883358.94 | 1 |  | COMPLETED | 1 | 2021-11-26 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region VIII | Catbalogan City | 123437 | San Roque ES | CITY OF CATBALOGAN (Capital) | 2 | 1 | 2 | Repair of Classrooms | 1443033.65 | 1 |  | COMPLETED | 1 | 2021-11-26 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VIII | Eastern Samar | 122328 | Bigo Elementary School | ARTECHE | 0 | 1 | 1 | Repair of Classroom | 333601.37 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region VIII | Eastern Samar | 122413 | Can-avid Central Elementary School | CAN-AVID | 0 | 1 | 9 | Repair of Classrooms | 2883439.01 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2021 | Region VIII | Eastern Samar | 303510 | Jipapad National High School | JIPAPAD | 0 | 1 | 10 | Repair of Classrooms | 2364888.63 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region VIII | Eastern Samar | 500235 | Dao Integrated School | ORAS | 0 | 1 | 5 | Repair of Classrooms | 1758934.62 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region VIII | Eastern Samar | 303520 | Oras National High School | ORAS | 0 | 1 | 16 | Repair of Classrooms | 3287104.68 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2021 | Region VIII | Eastern Samar | 122733 | Alugan Elementary School | SAN POLICARPO | 0 | 1 | 1 | Repair of Classroom | 385124.95 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region VIII | Eastern Samar | 303493 | Alugan National School of Craftsmanship and Home Industries | SAN POLICARPO | 0 | 1 | 14 | Repair of Classrooms | 4276384.84 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2021 | Region VIII | Leyte | 120962 | Astorga Elementary School | ALANGALANG | 1 | 1 | 4 | Repair of Classrooms | 1786594.94 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region VIII | Leyte | 121926 | Limbuhan Elementary School | TANAUAN | 1 | 1 | 5 | Repair of Classrooms | 1863222.03 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region VIII | Leyte | 121928 | San Roque Elementary School | TANAUAN | 1 | 1 | 2 | Repair of Classrooms | 508738.47 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VIII | Leyte | 121933 | Tugop Elementary School | TANAUAN | 1 | 1 | 2 | Repair of Classrooms | 469762.42 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VIII | Leyte | 191530 | Lanauan Elementary School | MACARTHUR | 2 | 1 | 3 | Repair of Classrooms | 1756698.03 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region VIII | Leyte | 121809 | Aringit Primary School | PASTRANA | 2 | 1 | 2 | Repair of Classrooms | 1133412.54 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VIII | Leyte | 121967 | Capinahan Elementary School | VILLABA | 3 | 1 | 6 | Repair of Classrooms | 1798923.7 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region VIII | Leyte | 121666 | Matag-ob Central School | MATAG-OB | 4 | 1 | 3 | Repair of Classrooms | 1814456.19 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region VIII | Leyte | 121802 | Rizal Elementary School | PALOMPON | 4 | 1 | 3 | Repair of Classrooms | 1170515.75 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region VIII | Leyte | 120921 | Anibongon Primary School | ABUYOG | 5 | 1 | 1 | Repair of Classroom | 518183.02 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region VIII | Leyte | 120931 | Matagnao Primary School | ABUYOG | 5 | 1 | 1 | Repair of Classroom | 520107.54 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region VIII | Leyte | 303374 | Hilongos National Vocational School | HILONGOS | 5 | 1 | 19 | Repair of Classrooms | 11031710 | 1 |  | COMPLETED | 1 | [10 empty] | Under Procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 0 | 0
REPAIR 2021 | Region VIII | Leyte | 303439 | Tinago National High School | INOPACAN | 5 | 1 | 9 | Repair of Classrooms | 2737263.59 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2021 | Region VIII | Maasin City | 122132 | Libhu ES | CITY OF MAASIN (Capital) | 0 | 1 | 7 | Repair of Classrooms | 2900220.89 | 1 | 2025871.07 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region VIII | Northern Samar | 193007 | Balud Elementary School | CATARMAN (Capital) | 1 | 1 | 5 | Repair of Classrooms | 2280897.58 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region VIII | Northern Samar | 123131 | San Agustin PS | MONDRAGON | 1 | 1 | 2 | Repair of Classrooms | 785296.39 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VIII | Northern Samar | 123205 | Vinisitahan ES | SAN ANTONIO | 1 | 1 | 7 | Repair of Classrooms | 3073891.5 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region VIII | Northern Samar | 303567 | Mongolbongol NHS | SAN VICENTE | 1 | 1 | 10 | Repair of Classrooms | 3774528.47 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region VIII | Northern Samar | 123277 | Luisita ES | VICTORIA | 1 | 1 | 3 | Repair of Classrooms | 1348487.09 | 1 |  | COMPLETED | 1 | 2022-09-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region VIII | Northern Samar | 122980 | Gibatangan Elementary School | LAOANG | 2 | 1 | 5 | Repair of Classrooms | 1874684.16 | 1 |  | COMPLETED | 1 | 2022-12-31 | [9 empty] | ongoing termination | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region VIII | Northern Samar | 122998 | Mabini ES | LAPINIG | 2 | 1 | 3 | Repair of Classrooms | 1445464.37 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region VIII | Northern Samar | 123156 | Matambag ES | PALAPAG | 2 | 1 | 4 | Repair of Classrooms | 1864201.8 | 1 |  | reverted | 0.5 | 2022-12-31 | [9 empty] | ongoing termination | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2021 | Region VIII | Ormoc City | 303654 | Dolores National High School | ORMOC CITY | 4 | 1 | 10 | Repair of Classrooms | 1957929.53 | 1 | 1369755.19 | COMPLETED | 1 | 2021-12-22 |  |  | 2019-BEFF-R-BQ-C4 | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-07-23 | 2021-08-16 | QCC Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region VIII | Ormoc City | 124207 | Doña Feliza Z. Mejia Elementary School | ORMOC CITY | 4 | 1 | 2 | Repair of Classrooms | 1268277.58 | 1 | 1024497.43 | COMPLETED | 1 | 2021-11-08 |  |  |  | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-07-23 | 2021-08-02 | Vhits DG Builders & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VIII | Ormoc City | 124210 | Lao Elementary School | ORMOC CITY | 4 | 1 | 3 | Repair of Classrooms | 1624971.26 | 1 | 2065089.22 | COMPLETED | 1 | 2021-12-02 |  |  |  | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-07-23 | 2021-08-16 | QCC Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region VIII | Ormoc City | 124184 | Manlilinao Elementary School | ORMOC CITY | 4 | 1 | 1 | Repair of Classroom | 525654.72 | 1 | 770604.11 | COMPLETED | 1 | 2021-12-02 |  |  | 2019-BEFF-R-B1-C4 | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-07-23 | 2021-08-16 | QCC Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region VIII | Ormoc City | 124199 | Tambulilid Elementary School | ORMOC CITY | 4 | 1 | 4 | Repair of Classrooms | 2008847.4 | 1 | 1632682.48 | COMPLETED | 1 | 2021-11-18 |  |  |  | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-07-23 | 2021-08-02 | Vhits DG Builders & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region VIII | Samar (Western Samar) | 123542 | Gandara II CS | GANDARA | 1 | 1 | 6 | Repair of Classrooms | 2607347.76 | 1 | 2590089.36 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region VIII | Samar (Western Samar) | 123808 | Lobe-Lobe Elementary School | SANTO NIÑO | 1 | 1 | 2 | Repair of Classrooms | 1305624.03 | 1 | 1296549.76 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VIII | Samar (Western Samar) | 123812 | Sto. Nino CS | SANTO NIÑO | 1 | 1 | 12 | Repair of Classrooms | 6909467.96 | 1 | 6894084.25 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2021 | Region VIII | Samar (Western Samar) | 123331 | Basey II CS | BASEY | 2 | 1 | 2 | Repair of Classrooms | 1266393.89 | 1 | 1246371.6 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VIII | Samar (Western Samar) | 123365 | Calbiga Central Elem. School | CALBIGA | 2 | 1 | 17 | Repair of Classrooms | 8303027.49 | 1 | 8267595.86 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0
REPAIR 2021 | Region VIII | Samar (Western Samar) | 123680 | Pinabacdao Central Elementary School | PINABACDAO | 2 | 1 | 3 | Repair of Classrooms | 1827517.73 | 1 | 1813092.65 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region VIII | Samar (Western Samar) | 123760 | Cabungaan ES | SANTA RITA | 2 | 1 | 1 | Repair of Classroom | 596427.63 | 1 | 591427.63 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region VIII | Samar (Western Samar) | 123772 | Sta. Rita I CS | SANTA RITA | 2 | 1 | 1 | Repair of Classroom | 1275269.66 | 1 | 1267269.66 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region VIII | Southern Leyte | 501531 | Beniton Integrated School | BONTOC | 0 | 1 | 2 | Repair of Classrooms | 920118.17 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VIII | Southern Leyte | 122005 | Hilaan Elementary School | BONTOC | 0 | 1 | 11 | Repair of Classrooms | 4917615.65 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2021 | Region VIII | Southern Leyte | 122098 | Habay Elementary School | SAN FRANCISCO | 0 | 1 | 11 | Repair of Classrooms | 4797318.42 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2021 | Region VIII | Southern Leyte | 122059 | Silago Central School | SILAGO | 0 | 1 | 17 | Repair of Classrooms | 6962763.34 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0
REPAIR 2021 | Region VIII | Southern Leyte | 122272 | Milagroso Elementary School | SOGOD | 0 | 1 | 3 | Repair of Classrooms | 1320983.01 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region VIII | Tacloban City | 124236 | Mercyville Elementary School | TACLOBAN CITY (Capital) | 1 | 1 | 10 | Repair of Classrooms | 3374635.4 | 1 |  | COMPLETED | 1 |  | 2021-11-04 | [7 empty] | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region VIII | Tacloban City | 314001 | San Jose Night High School | TACLOBAN CITY (Capital) | 1 | 1 | 6 | Repair of Classrooms | 2360315.14 | 1 |  | COMPLETED | 1 |  | 2021-12-04 | [7 empty] | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2022 | Region VIII | Biliran | 120759 | Barubuhan ES | ALMERIA | 0 | 1 | 2 | Repair of Classrooms | 1061497.39 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region VIII | Biliran | 120760 | Caucab ES | ALMERIA | 0 | 1 | 7 | Repair of Classrooms | 2857078.39 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2022 | Region VIII | Biliran | 120765 | Palayan ES | ALMERIA | 0 | 1 | 3 | Repair of Classrooms | 1593529.73 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region VIII | Biliran | 303320 | Biliran National Agricultural High School | BILIRAN | 0 | 1 | 9 | Repair of Classrooms | 1235101.57 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2022 | Region VIII | Biliran | 313202 | Biliran Science High School | BILIRAN | 0 | 1 | 2 | Repair of Classrooms | 1198599.08 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region VIII | Biliran | 120794 | Pawikan ES | CABUCGAYAN | 0 | 1 | 6 | Repair of Classrooms | 2590372.35 | 1 | 361130.34 | COMPLETED | 1 | [9 empty] | A AND B ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2022 | Region VIII | Biliran | 120799 | Bariis ES | CAIBIRAN | 0 | 1 | 6 | Repair of Classrooms | 2431071.6 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2022 | Region VIII | Biliran | 120812 | Tomalistis ES | CAIBIRAN | 0 | 1 | 3 | Repair of Classrooms | 1240222.99 | 1 | 361500 | COMPLETED | 1 | [9 empty] | A AND B ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region VIII | Biliran | 120838 | Masagaosao ES | KAWAYAN | 0 | 1 | 6 | Repair of Classrooms | 2469990.15 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2022 | Region VIII | Biliran | 120841 | Tubig Guinoo ES | KAWAYAN | 0 | 1 | 3 | Repair of Classrooms | 1336564.41 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region VIII | Eastern Samar | 122476 | Binalay Elementary School | GENERAL MACARTHUR | 0 | 1 | 8 | Repair of Classrooms | 3332391.33 | 1 |  | COMPLETED | 1 | [10 empty] | 44896 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2022 | Region VIII | Eastern Samar | 122575 | Jipapad Central School | JIPAPAD | 0 | 1 | 5 | Repair of Classrooms | 2153635.59 | 1 |  | COMPLETED | 1 | [10 empty] | 44896 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region VIII | Eastern Samar | 122463 | Maslog Central Elementary School | MASLOG | 0 | 1 | 4 | Repair of Classrooms | 1650444.69 | 1 |  | COMPLETED | 1 | [10 empty] | 44896 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2022 | Region VIII | Eastern Samar | 122706 | Bagtong Central Elementary School | SALCEDO | 0 | 1 | 6 | Repair of Classrooms | 2533266.41 | 1 |  | COMPLETED | 1 | [10 empty] | 44896 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2022 | Region VIII | Eastern Samar | 122722 | Campidhan Elementary School | SAN JULIAN | 0 | 1 | 7 | Repair of Classrooms | 2896634.68 | 1 |  | COMPLETED | 1 | [10 empty] | 44896 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2022 | Region VIII | Eastern Samar | 122731 | San Julian Central Elementary School | SAN JULIAN | 0 | 1 | 5 | Repair of Classrooms | 2138180.87 | 1 |  | COMPLETED | 1 | [10 empty] | 44896 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region VIII | Eastern Samar | 122736 | Baras Elementary School | SAN POLICARPO | 0 | 1 | 5 | Repair of Classrooms | 2429490.29 | 1 |  | COMPLETED | 1 | [10 empty] | 44896 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region VIII | Eastern Samar | 122737 | Binogawan Elementary School | SAN POLICARPO | 0 | 1 | 5 | Repair of Classrooms | 2641047.63 | 1 |  | COMPLETED | 1 | [10 empty] | 44896 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region VIII | Eastern Samar | 122742 | San Policarpo Central Elementary School | SAN POLICARPO | 0 | 1 | 16 | Repair of Classrooms | 7703588.17 | 1 |  | COMPLETED | 1 | [10 empty] | 44896 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2022 | Region VIII | Leyte | 121880 | Sta. Fe Central School | SANTA FE | 1 | 1 | 6 | Repair of Classrooms | 1094883.7 | 1 | 892437.57 | COMPLETED | 1 |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-07-01 | ASTILLA CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2022 | Region VIII | Leyte | 121953 | Opong Elementary School | TOLOSA | 1 | 1 | 6 | Repair of Classrooms | 3181905.91 | 1 | 1879039.89 | COMPLETED | 1 |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-07-01 | JVM BOLLARD CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2022 | Region VIII | Leyte | 121570 | Gimiranat West Elementary School | LA PAZ | 2 | 1 | 1 | Repair of Classroom | 604446.32 | 1 | 356497.1 | COMPLETED | 1 |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-07-01 | BELGES CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2022 | Region VIII | Leyte | 121577 | Moroboro Elementary School | LA PAZ | 2 | 1 | 2 | Repair of Classrooms | 1147167.04 | 1 | 664266.77 | COMPLETED | 1 |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-07-01 | BELGES CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region VIII | Leyte | 121615 | Batug Elementary School | MACARTHUR | 2 | 1 | 4 | Repair of Classrooms | 2111833.56 | 1 | 1521938 | COMPLETED | 1 |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-07-01 | SAMARINAN CONSTRUCTION AND DEVELOPMENT CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2022 | Region VIII | Leyte | 121619 | Danao Elementary School | MACARTHUR | 2 | 1 | 2 | Repair of Classrooms | 840419.15 | 1 |  | COMPLETED | 1 | [10 empty] | Failure of bidding; rebid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region VIII | Leyte | 303414 | Palale National High School | MACARTHUR | 2 | 1 | 8 | Repair of Classrooms | 2863914.54 | 1 | 2051726.88 | COMPLETED | 1 |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-23 | 2022-07-04 | VHITS D. G BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2022 | Region VIII | Leyte | 191539 | Quezon Elementary School | MACARTHUR | 2 | 1 | 2 | Repair of Classrooms | 663505.08 | 1 |  | COMPLETED | 1 | [10 empty] | Failure of bidding; rebid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region VIII | Leyte | 191576 | San Isidro Elementary School | MACARTHUR | 2 | 1 | 1 | Repair of Classroom | 462087.9 | 1 | 447080.52 | COMPLETED | 1 |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-06-27 | APU CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2022 | Region VIII | Leyte | 121628 | Tinawan Elementary School | MACARTHUR | 2 | 1 | 3 | Repair of Classrooms | 1075515.26 | 1 | 1060503.91 | COMPLETED | 1 |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-06-27 | APU CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region VIII | Leyte | 121712 | Union Elementary School | MAYORGA | 2 | 1 | 9 | Repair of Classrooms | 2950154.04 | 1 | 2079045 | COMPLETED | 1 |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-23 | 2022-07-01 | J. CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2022 | Region VIII | Leyte | 121719 | Canbantug Elementary School | MERIDA | 4 | 1 | 3 | Repair of Classrooms | 916746.05 | 1 | 584208.4 | COMPLETED | 1 |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-06-24 | FOUR K BUILDERS AND CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region VIII | Leyte | 121726 | Macario Elementary School | MERIDA | 4 | 1 | 1 | Repair of Classroom | 195488.43 | 1 | 123502.73 | COMPLETED | 1 |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-06-24 | FOUR K BUILDERS AND CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2022 | Region VIII | Leyte | 121728 | Mahayag Primary School | MERIDA | 4 | 1 | 2 | Repair of Classrooms | 1002528.02 | 1 | 638934.08 | COMPLETED | 1 |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-06-24 | FOUR K BUILDERS AND CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region VIII | Leyte | 121410 | Ma-asin Elementary School | HINDANG | 5 | 1 | 2 | Repair of Classrooms | 756445.15 | 1 | 745916.55 | COMPLETED | 1 |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-06-24 | FOUR K BUILDERS AND CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region VIII | Leyte | 121412 | Mahilum Elementary School | HINDANG | 5 | 1 | 3 | Repair of Classrooms | 904103.3 | 1 | 887769.2 | COMPLETED | 1 |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-06-24 | FOUR K BUILDERS AND CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region VIII | Northern Samar | 122776 | Alejandro Primary School | ALLEN | 1 | 1 | 2 | Repair of Classrooms | 1249477.92 | 1 |  | COMPLETED | 1 | [5 empty] | 2022-02-09 | 2022-03-07 |  |  | MARCARP ENG'G DEV. SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region VIII | Northern Samar | 122791 | Basud ES | BIRI | 1 | 1 | 3 | Repair of Classrooms | 1105801.04 | 1 |  | COMPLETED | 1 | [5 empty] | 2022-02-09 | 2022-03-07 |  |  | ARKOUZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region VIII | Northern Samar | 122824 | Jubang ES | CAPUL | 1 | 1 | 6 | Repair of Classrooms | 3170388.97 | 1 |  | COMPLETED | 1 | [5 empty] | 2022-02-09 | 2022-03-07 |  |  | LA CIVIL ENG'G |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2022 | Region VIII | Northern Samar | 123188 | Aguada PS | ROSARIO | 1 | 1 | 2 | Repair of Classrooms | 1239468.89 | 1 |  | COMPLETED | 1 | [5 empty] | 2022-02-09 | 2022-03-07 |  |  | SIERRA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region VIII | Northern Samar | 123198 | Dalupirit ES | SAN ANTONIO | 1 | 1 | 1 | Repair of Classroom | 727393.74 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2022 | Region VIII | Northern Samar | 123201 | Pilar Elementary School | SAN ANTONIO | 1 | 1 | 2 | Repair of Classrooms | 1130220.13 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region VIII | Northern Samar | 123228 | P. Tingzon ES | SAN JOSE | 1 | 1 | 2 | Repair of Classrooms | 1098757.86 | 1 |  | COMPLETED | 1 | [5 empty] | 2022-02-09 | 2022-03-07 |  |  | R.N. CHIA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region VIII | Northern Samar | 123231 | Tubigdanao ES | SAN JOSE | 1 | 1 | 2 | Repair of Classrooms | 1229210.68 | 1 |  | COMPLETED | 1 | [5 empty] | 2022-02-09 | 2022-03-07 |  |  | AL CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region VIII | Northern Samar | 123250 | Tarnate ES | SAN VICENTE | 1 | 1 | 2 | Repair of Classrooms | 972957.05 | 1 |  | COMPLETED | 1 | [5 empty] | 2022-02-09 | 2022-03-07 |  |  | GRINDER CIVIL ENG'G |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region VIII | Northern Samar | 123276 | Libertad ES | VICTORIA | 1 | 1 | 4 | Repair of Classrooms | 2198908.06 | 1 |  | COMPLETED | 1 | [5 empty] | 2022-02-09 | 2022-03-07 |  |  | MUDOLUS CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2022 | Region VIII | Northern Samar | 122993 | Can Maria Elementary School | LAPINIG | 2 | 1 | 2 | Repair of Classrooms | 1126886.22 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region VIII | Northern Samar | 123001 | Pio Del Pilar ES | LAPINIG | 2 | 1 | 2 | Repair of Classrooms | 1211740.89 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region VIII | Northern Samar | 123104 | Burgos ES | MAPANAS | 2 | 1 | 2 | Repair of Classrooms | 1289758.13 | 1 |  | COMPLETED | 1 | [10 empty] | SUbject for LD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region VIII | Northern Samar | 193008 | Manaybanay Elementary School | MAPANAS | 2 | 1 | 3 | Repair of Classrooms | 1363396.25 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region VIII | Samar (Western Samar) | 123810 | Pinanangnan Elementary School | SANTO NIÑO | 1 | 1 | 1 | Repair of Classroom | 612514.22 | 1 | 586278.34 | COMPLETED | 1 | 2022-09-11 | 2022-07-05 | CY2022 BEFF R-L1 |  | 2022-02-10 | 2022-02-17 | 2022-03-01 | 2022-05-27 | 2022-06-06 | NV&C CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2022 | Region VIII | Samar (Western Samar) | 501924 | Sevilla Integrated School | SANTO NIÑO | 1 | 1 | 3 | Repair of Classrooms | 1736601.91 | 1 | 1654608.92 | COMPLETED | 1 | 2022-09-11 |  | CY2022 BEFF R-L2 |  | 2022-02-10 | 2022-02-17 | 2022-03-01 | 2022-05-27 | 2022-06-06 | AGB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region VIII | Samar (Western Samar) | 123814 | Villahermosa ES | SANTO NIÑO | 1 | 1 | 3 | Repair of Classrooms | 1736601.91 | 1 | 1673785.08 | COMPLETED | 1 | 2022-09-11 | 2022-08-22 | CY2022 BEFF R-L3 |  | 2022-02-10 | 2022-02-17 | 2022-03-01 | 2022-05-27 | 2022-06-06 | GUY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region VIII | Samar (Western Samar) | 123823 | Nipa ES | TAGAPUL-AN | 1 | 1 | 4 | Repair of Classrooms | 2361413.15 | 1 | 2346281.62 | COMPLETED | 1 | 2022-09-11 | 2022-08-05 | CY2022 BEFF R-L4 |  | 2022-02-10 | 2022-02-17 | 2022-03-01 | 2022-05-27 | 2022-06-06 | LRD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2022 | Region VIII | Samar (Western Samar) | 123584 | Camarubo-an ES | JIABONG | 2 | 1 | 3 | Repair of Classrooms | 1815576.15 | 1 | 1718826.35 | COMPLETED | 1 | 2022-09-11 | 2022-07-22 | CY2022 BEFF R-L5 |  | 2022-02-10 | 2022-02-17 | 2022-03-01 | 2022-05-27 | 2022-06-06 | SAMARINAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region VIII | Samar (Western Samar) | 123601 | Parina Elementary School | JIABONG | 2 | 1 | 4 | Repair of Classrooms | 2408532.6 | 1 | 2212003.6 | COMPLETED | 1 | 2022-09-11 |  | CY2022 BEFF R-L6 |  | 2022-02-10 | 2022-02-17 | 2022-03-01 | 2022-05-27 | 2022-06-06 | QCC CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2022 | Region VIII | Samar (Western Samar) | 303614 | Osmeña National High School | MARABUT | 2 | 1 | 8 | Repair of Classrooms | 1856094.29 | 1 | 1840732.92 | COMPLETED | 1 | 2022-09-11 | 2022-08-05 | CY2022 BEFF R-L7 |  | 2022-02-10 | 2022-02-17 | 2022-03-01 | 2022-05-27 | 2022-06-06 | VHITS DG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2022 | Region VIII | Samar (Western Samar) | 123717 | Canduyocan Elementary School | SAN SEBASTIAN | 2 | 1 | 3 | Repair of Classrooms | 1752094.85 | 1 | 1679386.99 | COMPLETED | 1 | 2022-09-11 |  | CY2022 BEFF R-L8 |  | 2022-02-10 | 2022-02-17 | 2022-03-01 | 2022-05-27 | 2022-06-06 | NV&C CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region VIII | Samar (Western Samar) | 501374 | Inobongan Integrated School | SAN SEBASTIAN | 2 | 1 | 5 | Repair of Classrooms | 2193467.91 | 1 | 1964709.71 | COMPLETED | 1 | 2022-09-11 | 2022-08-22 | CY2022 BEFF R-L9 |  | 2022-02-10 | 2022-02-17 | 2022-03-01 | 2022-05-27 | 2022-06-06 | HEROES CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region VIII | Samar (Western Samar) | 123977 | Pangdan ES | ZUMARRAGA | 2 | 1 | 1 | Repair of Classroom | 870845.29 | 1 | 853463.9 | COMPLETED | 1 | 2022-09-11 |  | CY2022 BEFF R-L10 |  | 2022-02-10 | 2022-02-17 | 2022-03-01 | 2022-05-27 | 2022-06-06 | MAGA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2022 | Region VIII | Southern Leyte | 122223 | Magallanes Elementary School | LIMASAWA | 1 | 1 | 9 | Repair of Classrooms | 4734639.95 | 2 |  | COMPLETED | 1 |  |  | CY2022-Repair-B2-L2 |  | 2022-07-08 | 2022-07-15 | 2022-07-27 |  |  |  | Post Qualification Stage | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2022 | Region VIII | Southern Leyte | 122083 | Nahulid Elementary School | LIBAGON | 2 | 1 | 14 | Repair of Classrooms | 7536536.08 | 2 |  | COMPLETED | 1 |  |  | CY2022-Repair-B2-L1 |  | 2022-07-08 | 2022-07-15 | 2022-07-27 |  |  |  | Post Qualification Stage | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2022 | Region VIII | Southern Leyte | 192019 | Catbawan Elementary School | PINTUYAN | 2 | 1 | 5 | Repair of Classrooms | 2648711.16 | 2 |  | COMPLETED | 1 |  |  | CY2022-Repair-B2-L3 |  | 2022-07-08 | 2022-07-15 | 2022-07-27 |  |  |  | Post Qualification Stage | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region VIII | Southern Leyte | 192020 | Dan-an Elementary School | PINTUYAN | 2 | 1 | 4 | Repair of Classrooms | 2270650.72 | 2 |  | COMPLETED | 1 |  |  | CY2022-Repair-B2-L3 |  | 2022-07-08 | 2022-07-15 | 2022-07-27 |  |  |  | Post Qualification Stage | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2022 | Region VIII | Southern Leyte | 122117 | Tuno Elementary School | SAN FRANCISCO | 2 | 1 | 6 | Repair of Classrooms | 3404208.88 | 2 |  | COMPLETED | 1 |  |  | CY2022-Repair-B2-L4 |  | 2022-07-08 | 2022-07-15 | 2022-07-27 |  |  |  | Post Qualification Stage | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VIII | Baybay City | 121116 | Balao Elementary School | CITY OF BAYBAY | 5th | 1 | 4 | Repair of Classrooms | 2998588.67 | DPWH (Batch 2) | 2577723.06 | COMPLETED | 1 | 2024-07-08 |  | 23IG0160 |  |  | 2024-02-23 | 2024-03-06 |  | 2024-04-03 | Just In Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VIII | Baybay City | 121104 | Lintaon Elementary School | CITY OF BAYBAY | 5th | 1 | 1 | Repair of Classrooms | 766045.83 | DEPED (Batch 2) | 677505.8 | COMPLETED | 1 |  | 2024-04-04 | [5 empty] | 2024-02-27 | 2024-02-29 | Vhits D.G. Builders and Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region VIII | Biliran | 120759 | Barubuhan ES | ALMERIA | Lone | 1 | 1 | Repair of Classroom | 900000 | DEPED (Batch 2) |  | COMPLETED | 1 | 2024-06-28 | [8 empty] | J. Custorio Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region VIII | Biliran | 120771 | Talahid Elementary school | ALMERIA | Lone | 1 | 9 | Repair of Classrooms | 8500000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2023 | Region VIII | Biliran | 313201 | Western Biliran High School for the Arts and Culture | ALMERIA | Lone | 1 | 16 | Repair of Classrooms | 15500000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2023 | Region VIII | Biliran | 120775 | Burabod ES | BILIRAN | Lone | 1 | 1 | Repair of Classroom | 890000 | DEPED (Batch 2) |  | COMPLETED | 1 | [9 empty] | MB Ang Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region VIII | Biliran | 120786 | Bunga ES | CABUCGAYAN | Lone | 1 | 12 | Repair of Classrooms | 12000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2023 | Region VIII | Biliran | 120789 | Capayas Elementary School | CABUCGAYAN | Lone | 1 | 1 | Repair of Classroom | 850000 | DEPED (Batch 2) |  | COMPLETED | 1 | [9 empty] | K & A Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region VIII | Biliran | 120794 | Pawikan ES | CABUCGAYAN | Lone | 1 | 1 | Repair of Classroom | 800000 | DEPED (Batch 2) |  | COMPLETED | 1 | 2024-07-30 | [8 empty] | Rovinval Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region VIII | Biliran | 120797 | Alegria ES | CAIBIRAN | Lone | 1 | 7 | Repair of Classrooms | 6000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | Region VIII | Biliran | 120801 | Cabibihan ES | CAIBIRAN | Lone | 1 | 5 | Repair of Classrooms | 5000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VIII | Biliran | 120809 | Manlabang ES | CAIBIRAN | Lone | 1 | 3 | Repair of Classrooms | 9000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VIII | Biliran | 120810 | Maurang ES | CAIBIRAN | Lone | 1 | 1 | Repair of Classroom | 886000 | DEPED (Batch 2) |  | COMPLETED | 1 | [9 empty] | K & A Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region VIII | Biliran | 500410 | Union Integrated School | CAIBIRAN | Lone | 1 | 3 | Repair of Classrooms | 5000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VIII | Biliran | 120820 | Culaba CS | CULABA | Lone | 1 | 1 | Repair of Classroom | 900000 | DEPED (Batch 2) |  | COMPLETED | 1 | [9 empty] | MB Ang Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region VIII | Biliran | 120829 | Bilwang ES | KAWAYAN | Lone | 1 | 1 | Repair of Classroom | 1800000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region VIII | Biliran | 500411 | Inasuyan Integrated School | KAWAYAN | Lone | 1 | 4 | Repair of Classrooms | 5000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VIII | Biliran | 303329 | MARIPIPI NATIONAL VOCATIONAL SCHOOL | MARIPIPI | Lone | 1 | 20 | Repair of Classrooms | 20000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0
REPAIR 2023 | Region VIII | Eastern Samar | 303507 | Hinolaso National High School | DOLORES | Lone | 1 | 5 | Repair of Classrooms | 4908768.76 | DPWH (Batch 2) |  | Ongoing | 0 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Eastern Samar | 122580 | Recare Elementary School | JIPAPAD | Lone | 1 | 3 | Repair of Classrooms | 1787581.08 | DPWH (Batch 2) |  | Ongoing | 0 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Eastern Samar | 122581 | Roxas Elementary School | JIPAPAD | Lone | 1 | 3 | Repair of Classrooms | 1790684.62 | DPWH (Batch 2) |  | Ongoing | 0 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Eastern Samar | 122446 | Bulawan Elementary School | MASLOG | Lone | 1 | 4 | Repair of Classrooms | 2547330.44 | DPWH (Batch 2) |  | Ongoing | 0 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Eastern Samar | 122466 | San Miguel Elementary School | MASLOG | Lone | 1 | 3 | Repair of Classrooms | 2068582.23 | DPWH (Batch 2) |  | Ongoing | 0 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Eastern Samar | 122535 | Banuyo Elementary School | MERCEDES | Lone | 1 | 2 | Repair of Classrooms | 1293675.1 | DPWH (Batch 2) |  | Ongoing | 0 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Eastern Samar | 122536 | Bobon Elementary School | MERCEDES | Lone | 1 | 3 | Repair of Classrooms | 1304374.99 | DPWH (Batch 2) |  | Ongoing | 0 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Eastern Samar | 122548 | San Jose Primary School | MERCEDES | Lone | 1 | 2 | Repair of Classrooms | 1319938.46 | DPWH (Batch 2) |  | Ongoing | 0 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Eastern Samar | 122551 | Sung-an Elementary School | MERCEDES | Lone | 1 | 5 | Repair of Classrooms | 3285964.01 | DPWH (Batch 2) |  | Ongoing | 0 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Eastern Samar | 122704 | Alog Elementary School | SALCEDO | Lone | 1 | 3 | Repair of Classrooms | 2062660.23 | DPWH (Batch 2) |  | Ongoing | 0 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Eastern Samar | 122705 | Asgad Elementary School | SALCEDO | Lone | 1 | 6 | Repair of Classrooms | 3285964.01 | DPWH (Batch 2) |  | Ongoing | 0 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Eastern Samar | 122710 | Burak Elementary School | SALCEDO | Lone | 1 | 8 | Repair of Classrooms | 4971012.36 | DPWH (Batch 2) |  | Ongoing | 0 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Eastern Samar | 122712 | Cagaut Elementary School | SALCEDO | Lone | 1 | 5 | Repair of Classrooms | 4927139.53 | DPWH (Batch 2) |  | Ongoing | 0 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Eastern Samar | 122694 | Iberan Elementary School | SALCEDO | Lone | 1 | 3 | Repair of Classrooms | 2825904.02 | DPWH (Batch 2) |  | Ongoing | 0 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Eastern Samar | 122696 | Lusod Elementary School | SALCEDO | Lone | 1 | 5 | Repair of Classrooms | 3620429.05 | DPWH (Batch 2) |  | Ongoing | 0 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Eastern Samar | 122719 | Sta. Cruz Elementary School | SALCEDO | Lone | 1 | 3 | Repair of Classrooms | 1308351.56 | DPWH (Batch 2) |  | Ongoing | 0 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Eastern Samar | 122733 | Alugan Elementary School | SAN POLICARPO | Lone | 1 | 7 | Repair of Classrooms | 4623552.37 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | Region VIII | Eastern Samar | 122734 | Bahay Elementary School | SAN POLICARPO | Lone | 1 | 5 | Repair of Classrooms | 2870950.04 | DPWH (Batch 2) |  | Ongoing | 0 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Eastern Samar | 122740 | Natividad Elementary School | SAN POLICARPO | Lone | 1 | 3 | Repair of Classrooms | 1781806.08 | DPWH (Batch 2) |  | Ongoing | 0 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Eastern Samar | 122741 | Pangpang Elementary School | SAN POLICARPO | Lone | 1 | 8 | Repair of Classrooms | 4294322.54 | DPWH (Batch 2) |  | Ongoing | 0 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Eastern Samar | 122743 | Sta.Cruz Elementary School | SAN POLICARPO | Lone | 1 | 2 | Repair of Classrooms | 1789417.61 | DPWH (Batch 2) |  | Ongoing | 0 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Eastern Samar | 122752 | San Isidro Elementary School | SULAT | Lone | 1 | 3 | Repair of Classrooms | 2890150.12 | DPWH (Batch 2) |  | Ongoing | 0 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Leyte | 121229 | Nipa Elementary School | CALUBIAN | 3rd | 1 | 6 | Repair of Classrooms | 7200000 | DPWH (Batch 2) |  | Ongoing | 0.4 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Leyte | 121220 | Villahermosa Elementary School | CALUBIAN | 3rd | 1 | 2 | Repair of Classrooms | 2400000 | DPWH (Batch 2) |  | Ongoing | 0.95 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Leyte | 121901 | Inangatan Elementary School | TABANGO | 3rd | 1 | 10 | Repair of Classrooms | 12000000 | DPWH (Batch 2) |  | Ongoing | 0.6 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Leyte | 121902 | Leoncio Erejer Memorial Elementary School | TABANGO | 3rd | 1 | 6 | Repair of Classrooms | 7200000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VIII | Leyte | 121904 | Tabayla Elementary School | TABANGO | 3rd | 1 | 12 | Repair of Classrooms | 14400000 | DPWH (Batch 2) |  | Ongoing | 0.4 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Leyte | 121977 | Balite Elementary School | VILLABA | 3rd | 1 | 5 | Repair of Classrooms | 6300000 | DPWH (Batch 2) |  | Ongoing | 0 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Leyte | 121397 | Anahaw Elementary School | HINDANG | 5th | 1 | 3 | Repair of Classrooms | 2136729.83 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VIII | Leyte | 121402 | Canha-ayon Elementary School | HINDANG | 5th | 1 | 1 | Repair of Classroom | 733962.67 | DEPED (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region VIII | Leyte | 121405 | Doos Elementary School | HINDANG | 5th | 1 | 3 | Repair of Classrooms | 2034662.48 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VIII | Leyte | 121404 | Doos Sur Elementary School | HINDANG | 5th | 1 | 2 | Repair of Classrooms | 1276362.61 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VIII | Leyte | 121406 | Himacugo Elementary School | HINDANG | 5th | 1 | 1 | Repair of Classroom | 394888.3 | DEPED (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region VIII | Leyte | 303375 | Hindang National High School | HINDANG | 5th | 1 | 2 | Repair of Classrooms | 1092990.23 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VIII | Leyte | 121410 | Ma-asin Elementary School | HINDANG | 5th | 1 | 4 | Repair of Classrooms | 1665651.98 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VIII | Leyte | 121413 | Tabok Elementary School | HINDANG | 5th | 1 | 6 | Repair of Classrooms | 1656698.97 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VIII | Leyte | 121414 | Tagbibi Elementary School | HINDANG | 5th | 1 | 2 | Repair of Classrooms | 1262787.41 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VIII | Maasin City | 122128 | Gawisan MGS | CITY OF MAASIN (Capital) | Lone | 1 | 3 | Repair of Classrooms | 2656875.24 | DPWH (Batch 2) | 2557803.09 | COMPLETED | 1 | 2024-06-12 |  | P00775963NP | 23IL0085 | 2023-12-06 | 2023-12-13 | 2023-12-27 | 2023-12-29 | 2024-01-10 | PABLO S. LABASBAS CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VIII | Maasin City | 303457 | Guadalupe National High School | CITY OF MAASIN (Capital) | Lone | 1 | 9 | Repair of Classrooms | 8685498.16 | DPWH (Batch 2) | 8368866.47 | COMPLETED | 1 | 2024-08-16 |  | P00775967NP | 23IL0087 | 2023-12-06 | 2023-12-13 | 2023-12-27 | 2023-12-29 | 2024-01-10 | M.G. VILLAMIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2023 | Region VIII | Maasin City | 122136 | Mahayahay ES | CITY OF MAASIN (Capital) | Lone | 1 | 3 | Repair of Classrooms | 3986617.72 | DPWH (Batch 2) | 3839844.25 | COMPLETED | 1 | Jully 22, 2024 |  | P00775964N | 23IL0086 | 2023-12-06 | 2023-12-13 | 2023-12-27 | 2023-12-29 | 2024-01-10 | JQD CONST. & GEN. SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VIII | Maasin City | 303474 | Nonok Norte National High School | CITY OF MAASIN (Capital) | Lone | 1 | 9 | Repair of Classrooms | 8185498.52 | DPWH (Batch 2) | 7888024.72 | Ongoing | 0.95 | 2024-10-10 |  | P00775968N | 23IL0088 | 2023-12-06 | 2023-12-13 | 2023-12-27 | 2023-12-29 | 2024-01-10 | M.G. VILLAMIN CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Maasin City | 122143 | Rizal MGS | CITY OF MAASIN (Capital) | Lone | 1 | 1 | Repair of Classrooms | 1054153.28 | DPWH (Batch 2) | 1013775.63 | COMPLETED | 1 | 2024-04-13 |  | P00775965N | 23IL0084 | 2023-12-06 | 2023-12-13 | 2023-12-27 | 2023-12-29 | 2024-01-10 | JQD CONST. & GEN. SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region VIII | Maasin City | 122176 | Tigbawan IS | CITY OF MAASIN (Capital) | Lone | 1 | 12 | Repair of Classrooms | 10647251.1 | DPWH (Batch 2) | 10258866.07 | Ongoing | 0.8 | 2024-11-19 |  | P00775966NP | 23IL0089 | 2023-12-06 | 2023-12-13 | 2023-12-27 | 2023-12-29 | 2024-01-10 | M.G. VILLAMIN CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Ormoc City | 313901 | Lilo-an National High School | ORMOC CITY | 4th | 1 | 6 | Repair of Classrooms | 1919998.18 | DPWH (Batch 2) | 1843533.86 | Ongoing | 0.5 | February 1, 2024 (suspended due to variation order) |  | P00775970NP | 23IF0121 | 2023-11-08 | 2023-11-15 | 2023-11-28 | 2023-12-29 | 2024-01-29 | RED AXE BUILDERS AND SUPPLY | suspended due to variation | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Ormoc City | 501363 | Mas-in Integrated School | ORMOC CITY | 4th | 1 | 3 | Repair of Classrooms | 2191829.57 | DPWH (Batch 2) | 2104538.68 | Ongoing | 0.9 | 2024-02-21 |  | P00775971NP | 23IF0122 | 2023-11-08 | 2023-11-15 | 2023-11-28 | 2023-12-29 | 2024-01-29 | CIRCLE Z VENTURES AND DEV. CORP. | The DPWH did not adhere to the approved Program of Works and they failed to submit any variation orders or change orders. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Ormoc City | 194502 | VL Villacencio Elementary School | ORMOC CITY | 4th | 1 | 4 | Repair of Classrooms | 2023244.22 | DPWH (Batch 2) | 1942668.52 | COMPLETED | 1 | 2024-02-22 |  | P00775969NP | 23IF0123 | 2023-11-08 | 2023-11-15 | 2023-11-28 | 2023-12-29 | 2024-01-29 | MELGAZO CONSTRUCTION AND SUPPLY | 100% Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VIII | Samar (Western Samar) | 123596 | Macabetas Elementary School | JIABONG | 2nd | 1 | 2 | Repair of Classrooms | 1244245.58 | DPWH (Batch 2) | 1200696.98 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VIII | Samar (Western Samar) | 123597 | Malino Elementary School | JIABONG | 2nd | 1 | 1 | Repair of Classroom | 759392.25 | DEPED (Batch 2) | 727784.79 | COMPLETED | 1 | 2024-04-21 |  |  |  | 2024-01-10 | 2024-01-18 | 2024-01-30 |  |  | G.I AND 4K CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region VIII | Samar (Western Samar) | 123606 | Tagbayaon Elementary School | JIABONG | 2nd | 1 | 1 | Repair of Classroom | 759392.25 | DEPED (Batch 2) | 722704.05 | COMPLETED | 1 | 2024-04-19 |  |  |  | 2024-01-10 | 2024-01-18 | 2024-01-30 |  |  | GPUY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region VIII | Samar (Western Samar) | 123609 | Canyoyo Elementary School | MARABUT | 2nd | 1 | 3 | Repair of Classrooms | 2007177.84 | DPWH (Batch 2) | 1936926.62 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VIII | Samar (Western Samar) | 123716 | Campiyak Elementary School | SAN SEBASTIAN | 2nd | 1 | 3 | Repair of Classrooms | 2037970.66 | DPWH (Batch 2) | 1966641.69 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VIII | Samar (Western Samar) | 123897 | Mallorga Elementary School | TALALORA | 2nd | 1 | 4 | Repair of Classrooms | 2293471.61 | DPWH (Batch 2) | 2213200.1 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VIII | Samar (Western Samar) | 123965 | Bioso Elementary School | ZUMARRAGA | 2nd | 1 | 6 | Repair of Classrooms | 3774847.84 | DPWH (Batch 2) | 3642728.17 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VIII | Samar (Western Samar) | 123969 | Ibarra Elementary School | ZUMARRAGA | 2nd | 1 | 1 | Repair of Classroom | 759392 | DEPED (Batch 2) | 727676.25 | COMPLETED | 1 | 2024-04-21 |  |  |  | 2024-01-10 | 2024-01-18 | 2024-01-30 |  |  | G.I AND 4K CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region VIII | Southern Leyte | 122180 | Asuncion Multigrade Elementary School | MACROHON | 1st | 1 | 3 | Repair of Classrooms | 1857144.76 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VIII | Southern Leyte | 122195 | San Roque Elementary School | MACROHON | 1st | 1 | 19 | Repair of Classrooms | 11693996.12 | DPWH (Batch 2) | 11258065.84 | Ongoing | 0.95 | 2024-08-24 | [8 empty] | M.G VILLAMIN CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Southern Leyte | 303485 | San Roque National High School | MACROHON | 1st | 1 | 21 | Repair of Classrooms | 12861943.5 | DPWH (Batch 2) | 12383426.33 | Ongoing | 0.95 | 2024-09-10 | [8 empty] | M.G VILLAMIN CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Southern Leyte | 122227 | San Juan Elementary School | PADRE BURGOS | 1st | 1 | 9 | Repair of Classrooms | 5711613.49 | DPWH (Batch 2) |  | Ongoing | 0.95 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0
REPAIR 2023 | Region VIII | Southern Leyte | 303480 | San Isidro NHS | TOMAS OPPUS | 1st | 1 | 10 | Repair of Classrooms | 6087058.2 | DPWH (Batch 2) | 5865961.61 | Ongoing | 0.95 | 2024-06-15 | [8 empty] | PABLO S. LABASBAS CONSTRUCTION CORP. |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0
REPAIR 2024 | Region VIII | Baybay City | 121130 | Ambacan Elementary School | CITY OF BAYBAY | 5th | 1 | 3 | Repair of Classrooms | 2323232.32 | 1 | 2274593.57 | COMPLETED | 1 | 2024-12-30 | 2024-12-26 | 2024-07-I001 | 2024-07-I001 |  | 2024-08-01 | 2024-08-13 | 2024-09-22 | 2024-09-25 | Melgazo Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2024 | Region VIII | Baybay City | 121113 | Villa Elementary School | CITY OF BAYBAY | 5th | 1 | 5 | Repair of Classrooms | 3957141.41 | 1 | 3887121.08 | COMPLETED | 1 | 2025-03-05 | 2025-02-26 | 2024-07-I002 | 2024-07-I002 |  | 2024-08-01 | 2024-08-13 | 2024-09-22 | 2024-09-30 | QCC Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2024 | Region VIII | Biliran | 120758 | Almeria CS | ALMERIA | Lone | 1 | 9 | Repair of Classrooms | 5941898.1 | 1 | 5876966.13 | COMPLETED | 1 | [9 empty] | WB ALAGAO CONSTRUCTION | REALIGNED FROM TALAHID ES TO ALMERIA CS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2024 | Region VIII | Biliran | 303323 | Cabucgayan NHS | CABUCGAYAN | Lone | 1 | 2 | Repair of Classrooms | 1010101.01 | 1 | 997500 | COMPLETED | 1 | [9 empty] | INFRASERVE BUILDERS & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2024 | Region VIII | Borongan City | 122359 | Eugenio A. Abunda Sr. Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 6 | Repair of Classrooms | 3936616.74 | 1 |  | under procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0
REPAIR 2024 | Region VIII | Borongan City | 122361 | Eugenio S. Daza Pilot Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 7 | Repair of Classrooms | 4199778.72 | 1 |  | under procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0
REPAIR 2024 | Region VIII | Borongan City | 303511 | Lalawigan National High School | CITY OF BORONGAN (Capital) | Lone | 1 | 11 | Repair of Classrooms | 7206134.8 | 1 |  | under procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0
REPAIR 2024 | Region VIII | Calbayog City | 501970 | Caglanipao Sur Integrated School | CALBAYOG CITY | 1st | 1 | 8 | Repair of Classrooms | 5454545.45 | 1 |  | under procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
REPAIR 2024 | Region VIII | Eastern Samar | 122485 | Hernani Central Elementary School | HERNANI | Lone | 1 | 3 | Repair of Classrooms | 1909553.3 | 1 |  | under procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
REPAIR 2024 | Region VIII | Eastern Samar | 303510 | Jipapad National High School | JIPAPAD | Lone | 1 | 8 | Repair of Classrooms | 5228390.51 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2024 | Region VIII | Leyte | 120974 | Mudboron Elementary School | ALANGALANG | 1st | 1 | 8 | Repair of Classrooms | 5107070.71 | 1 |  | under procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
REPAIR 2024 | Region VIII | Leyte | 121005 | Babatngon Central School | BABATNGON | 1st | 1 | 3 | Repair of Classrooms | 1939393.94 | 1 |  | under procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
REPAIR 2024 | Region VIII | Maasin City | 122168 | Nonok Norte ES | CITY OF MAASIN (Capital) | 1st | 1 | 10 | Repair of Classrooms | 6938581.82 | 1 | 5013138.41 | COMPLETED | 1 | 2025-04-10 |  | INFRA-2024-005 | INFRA-2024-005 | 2024-07-08 | 2024-07-16 | 2024-07-30 | 2024-09-27 | 2024-10-28 | VHITS D.G BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2024 | Region VIII | Northern Samar | 122792 | Biri CES | BIRI | 1st | 1 | 5 | Repair of Classrooms | 2295521.25 | 1 |  | under procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0
REPAIR 2024 | Region VIII | Northern Samar | 122795 | MACARET ELEMENTARY SCHOOL | BIRI | 1st | 1 | 3 | Repair of Classrooms | 1963471.22 | 1 |  | under procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
REPAIR 2024 | Region VIII | Ormoc City | 124178 | Guintiguian Elementary School | ORMOC CITY | 4th | 1 | 6 | Repair of Classrooms | 5045315.15 | 1 | 3962380.2 | COMPLETED | 1 | 2024-12-31 | 2024-12-02 | REPAIR 2024 - RVIII - ORMOC CITY - 001 | BEFF – CY 2024- REPAIR- BATCH 1 | 2024-06-27 | 2024-07-05 | 2024-07-17 | 2024-08-19 | 2024-10-18 | EH Antig Construction and Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | Region VIII | Samar (Western Samar) | 123531 | Tambongan Elementary School | GANDARA | 1st | 1 | 5 | Repair of Classrooms | 3144887.51 | 1 | 3062665.16 | COMPLETED | 1 | 2025-01-19 | 2024-12-18 | [7 empty] | CABANDON CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2024 | Region VIII | Samar (Western Samar) | 123655 | Pagsanghan Central Elementary School | PAGSANGHAN | 1st | 1 | 6 | Repair of Classrooms | 3637235.79 | 1 | 3585629.3 | COMPLETED | 1 | [9 empty] | GPUY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | Region VIII | Southern Leyte | 122084 | Otikon Elementary School | LIBAGON | 2nd | 1 | 11 | Repair of Classrooms | 6850569.67 | 1 | 6658906.37 | COMPLETED | 1 | 2025-02-27 | 2025-11-14 | CY2024- BEFF Repair-Batch 1-L1 | CY2024- BEFF Repair-Batch 1-L1 | 2024-06-04 | 2024-06-11 | 2024-06-24 |  | 2024-09-23 | 3MC KING CIVIL ENGINEERING CONSTRUCTION | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2024 | Region VIII | Tacloban City | 124247 | Marasbaras Central School | TACLOBAN CITY (Capital) | 1st | 1 | 16 | Repair of Classrooms | 4792879.08 | 1 |  | COMPLETED | 1 |  | 2024-12-01 |  | CY 2024 BEFF_REPAIR (BATCH 1) | 2024-06-25 | 2024-07-02 | 2024-07-15 | 2024-07-18 | 2025-07-19 | VITTS DG. BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2024 | Region VIII | Tacloban City | 330503 | V&G National High School | TACLOBAN CITY (Capital) | 1st | 1 | 38 | Repair of Classrooms | 1012069.7 | 1 |  | COMPLETED | 1 |  | 2024-12-01 |  | CY 2024 BEFF_REPAIR (BATCH 1) | 2024-06-25 | 2024-07-02 | 2024-07-15 | 2024-07-18 | 2025-07-19 | JDR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 38 | 0 | 0

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%