## Sheet1
Program-Year | CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 304200 | Awao NHS | MONKAYO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1814321.2338 |  |  | COMPLETED | 1 |  | 2015-09-24 | 110414S00037 | 15LA0075 | 2014-12-05 | 2015-06-22 | 2015-06-30 | 2015-07-10 | 2015-07-20 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128512 | Barabat ES | NEW BATAAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1814321.2338 |  |  | COMPLETED | 1 |  |  | 110414S00038 | 15LA0072 | 2014-12-05 | 2014-12-18 | 2014-12-18 |  |  | By Administration
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128440 | Bliss ES | MONKAYO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 969963.4991 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-06-22 | 110414S00028 | 14LA0248 | 2014-12-05 | 2014-12-22 | 2014-12-22 | 2014-12-25 | 2015-01-12 | AB APONESTO CONSTRUCTION, PARTS & SUPPLY
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128429 | Boay ES | MONKAYO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1085538.499 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-06-22 | 110414S00031 | 14LA0247 | 2014-12-05 | 2014-12-22 | 2014-12-22 | 2014-12-25 | 2015-01-12 | AB APONESTO CONSTRUCTION, PARTS & SUPPLY
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128464 | Canidkid ES | MONTEVISTA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 990063.4991 |  |  | COMPLETED | 1 | 2015-04-03 | 2015-04-01 | 110414S00030 | 14LA0239 | 2014-12-05 | 2014-12-22 | 2014-12-22 | 2014-12-25 | 2015-01-12 | MAG CORPORATION
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 315813 | Langgawisan NHS | MARAGUSAN (SAN MARIANO) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1170963.499 |  |  | COMPLETED | 1 |  | 2015-03-19 | 110414S00007 | 14LA0243 | 2014-12-05 | 2014-12-18 | 2014-12-22 | 2014-12-25 | 2015-01-12 | M.R. VARGAS CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128435 | Mabuhay ES | MONKAYO | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2530827.2604 |  |  | COMPLETED | 1 | 2015-04-18 | 2015-04-18 | 110414S00010 | 14LA0219 | 2014-12-05 | 2014-12-18 | 2014-12-18 | 2014-12-24 | 2015-01-12 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128468 | Magtaya PS | MONTEVISTA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1010163.499 |  |  | COMPLETED | 1 | 2015-04-16 | 2015-04-18 | 110414S00026 | 14LA0245 | 2014-12-05 | 2014-12-22 | 2014-12-22 | 2014-12-25 | 2015-01-12 | MAG CORPORATION
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128437 | Mamonga ES | MONKAYO | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2530827.2604 |  |  | COMPLETED | 1 | 2015-04-18 | 2015-04-17 | 110414S00011 | 14LA0217 | 2014-12-05 | 2014-12-18 | 2014-12-18 | 2014-12-23 | 2015-01-12 | MAG CORPORATION
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 304182 | Mangayon NHS | COMPOSTELA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 969963.4991 |  |  | COMPLETED | 1 |  | 2015-03-19 | 110414S00035 | 14LA0207 | 2014-12-05 | 2014-12-18 | 2014-12-18 | 2014-12-24 | 2015-01-12 | AB APONESTO CONSTRUCTION, PARTS & SUPPLY
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128269 | Maparat ES | COMPOSTELA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1738946.2338 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-06-22 | 110414S00034 | 14LA0226 | 2014-12-05 | 2014-12-18 | 2014-12-18 | 2014-12-24 | 2015-01-12 | AB APONESTO CONSTRUCTION, PARTS & SUPPLY
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 304198 | Maragusan NHS | MARAGUSAN (SAN MARIANO) | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3518193.0681 |  |  | COMPLETED | 1 |  | 2015-04-18 | 110414S00036 | 14LA0210 | 2014-12-05 | 2014-12-18 | 2014-12-18 | 2014-12-24 | 2015-01-12 | M.R. VARGAS CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 304204 | Mayaon NHS | MONTEVISTA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1010163.499 |  |  | COMPLETED | 1 |  | 2015-06-24 | 110414S00040 | 14LA0233 | 2014-12-05 | 2014-12-18 | 2015-03-05 | 2015-03-17 | 2015-04-17 | MAG CORPORATION
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 315801 | Monkayo NHS- Casoon NHS Annex | MONKAYO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1050363.499 |  |  | COMPLETED | 1 |  | 2015-03-19 | 110414S00033 | 14LA0240 | 2014-12-05 | 2014-12-22 | 2014-12-22 | 2014-12-25 | 2015-01-12 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128441 | Moria ES | MONKAYO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 969963.4991 |  |  | COMPLETED | 1 | 2015-10-15 | 2015-12-18 | 110414S00012 | PR#15-07-193 | 2014-12-05 | 2014-12-19 | 2015-07-24 | 2015-07-31 | 2015-08-17 | By Administration
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128442 | Mt. Diwata ES | MONKAYO | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3317193.0681 |  |  | COMPLETED | 1 | 2015-04-18 | 2015-06-30 | 110414S00013 | 14LA0209 | 2014-12-05 | 2014-12-18 | 2014-12-18 | 2014-12-23 | 2015-01-12 | FFJJ CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128444 | Naboc ES | MONKAYO | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2530827.2604 |  |  | COMPLETED | 1 | 2015-04-18 | 2015-06-01 | 110414S00025 | 14LA0215 | 2014-12-05 | 2014-12-18 | 2014-12-18 | 2014-12-24 | 2015-01-12 | AB APONESTO CONSTRUCTION, PARTS & SUPPLY
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 304206 | New Bataan NHS | NEW BATAAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1738946.2338 |  |  | COMPLETED | 1 |  | 2015-03-19 | 110414S00027 | 14LA0249 | 2014-12-05 | 2014-12-22 | 2014-12-22 | 2014-12-25 | 2015-01-12 | AB APONESTO CONSTRUCTION, PARTS & SUPPLY
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128445 | New Kapatagan ES | MONKAYO | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2530827.2604 |  |  | COMPLETED | 1 | 2015-04-18 | 2015-08-14 | 110414S00015 | 14LA0216 | 2014-12-05 | 2014-12-18 | 2014-12-18 | 2014-12-23 | 2015-01-12 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128474 | New Visayas ES | MONTEVISTA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1738946.2338 |  |  | COMPLETED | 1 | 2015-09-24 | 2015-11-15 | 110414S00021 | 15LA0073 | 2014-12-05 | 2015-06-22 | 2015-06-30 | 2015-07-10 | 2015-07-20 | AB APONESTO CONSTRUCTION, PARTS & SUPPLY
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 204011 | Paco ES | MONKAYO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 969963.4991 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-06-23 | 110414S00017 | 14LA0234 | 2014-12-05 | 2014-12-18 | 2014-12-22 | 2014-12-25 | 2015-01-12 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128447 | Pasian ES | MONKAYO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1040313.499 |  |  | COMPLETED | 1 | 2015-10-15 | 2015-12-18 | 110414S00029 | PR#15-07-194 | 2014-12-05 | 2014-12-22 | 2015-07-24 | 2015-07-31 | 2015-08-17 | By Administration
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128526 | Pongpong ES | NEW BATAAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1045338.499 |  |  | COMPLETED | 1 |  |  | 110414S00039 | 15LA0076 | 2014-12-05 | 2014-12-22 | 2015-07-31 |  |  | By Administration
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128475 | Prosperidad ES | MONTEVISTA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1789196.2338 |  |  | COMPLETED | 1 | 2015-04-18 | 2015-04-01 | 110414S00032 | 14LA0213 | 2014-12-05 | 2014-12-18 | 2014-12-18 | 2014-12-23 | 2015-01-12 | DIGOS CONSTRAK CORPORATION
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128452 | San Jose ES | MONKAYO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 969963.4991 |  |  | COMPLETED | 1 | 2015-10-15 | 2015-12-18 | 110414S00008 | PR#15-07-192 | 2014-12-05 | 2015-06-03 | 2015-07-24 | 2015-07-31 | 2015-08-17 | By Administration
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128453 | Sugod ES | MONKAYO | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2530827.2604 |  |  | COMPLETED | 1 | 2015-04-18 | 2015-04-18 | 110414S00009 | 14LA0218 | 2014-12-05 | 2014-12-18 | 2014-12-18 | 2014-12-23 | 2015-01-12 | AB APONESTO CONSTRUCTION, PARTS & SUPPLY
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128402 | Tigbao ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 969963.4991 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-04-30 | 110414S00043 | 14LA0231 | 2014-12-05 | 2014-12-18 | 2014-12-18 | 2014-12-23 | 2015-01-07 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128457 | Ulip ES | MONKAYO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 969963.4991 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-18 | 110414S00006 | 14LA0236 | 2014-12-05 | 2014-12-18 | 2014-12-22 | 2014-12-25 | 2015-01-12 | TWINA BUILDERS AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128290 | Candiis ES | LAAK (SAN VICENTE) | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2751927.2604 |  |  | COMPLETED | 1 | 2015-04-18 | 2015-04-22 | 110414S00018 | 14LA0232 | 2014-12-05 | 2014-12-18 | 2014-12-18 | 2014-12-24 | 2015-01-12 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128293 | Datu Ampunan ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1779146.2338 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-04-12 | 110414S00019 | 14LA0211 | 2014-12-05 | 2014-12-18 | 2014-12-18 | 2014-12-24 | 2015-01-12 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128298 | Ilpapa ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1769096.2338 |  |  | COMPLETED | 1 | 2015-05-03 | 2015-05-02 | 110414S00020 | 14LA0212 | 2014-12-05 | 2014-12-18 | 2014-12-18 | 2014-12-24 | 2015-01-12 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128303 | Kibaguio ES | LAAK (SAN VICENTE) | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2751927.2604 |  |  | COMPLETED | 1 | 2015-05-03 | 2015-05-02 | 110414S00005 | 14LA0220 | 2014-12-05 | 2014-12-18 | 2014-12-19 | 2014-12-23 | 2015-01-12 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 304190 | Kidawa NHS | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1769096.2338 |  |  | COMPLETED | 1 |  | 2015-04-03 | 110414S00016 | 14LA0224 | 2014-12-05 | 2014-12-18 | 2014-12-18 | 2014-12-23 | 2015-01-12 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128306 | Kiokmay ES | LAAK (SAN VICENTE) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1170963.499 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-04 | 110414S00022 | 14LA0242 | 2014-12-05 | 2014-12-22 | 2014-12-22 | 2014-12-25 | 2015-01-12 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128334 | Libudon ES | MABINI (DOÑA ALICIA) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 969963.4991 |  |  | COMPLETED | 1 | 2015-04-18 | 2015-04-17 | 110414S00041 | 14LA0208 | 2014-12-05 | 2014-12-18 | 2014-12-18 | 2014-12-23 | 2015-01-07 | EXACT CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128312 | Lower Ampawid ES | LAAK (SAN VICENTE) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1000113.499 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-04 | 110414S00014 | 14LA0244 | 2014-12-05 | 2014-12-18 | 2014-12-22 | 2014-12-25 | 2015-01-12 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128548 | Magnaga ES | PANTUKAN | 2 | 1 | 5 | 1STY1CL & 1STY4CL | 2014 K10 BATCH 4A | 4287156.5671 |  |  | COMPLETED | 1 | 2015-04-18 | 2015-06-01 | 110414S00044 | 14LA0227 | 2014-12-05 | 2014-12-18 | 2014-12-18 | 2014-12-23 | 2015-01-07 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128318 | Naga ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1769096.2338 |  |  | COMPLETED | 1 | 2015-04-03 | 2015-04-03 | 110414S00023 | 14LA0214 | 2014-12-05 | 2014-12-18 | 2014-12-18 | 2014-12-23 | 2015-01-12 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 128320 | Panamoren ES | LAAK (SAN VICENTE) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1221213.499 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-03 | 110414S00024 | 14LA0235 | 2014-12-05 | 2014-12-18 | 2014-12-22 | 2014-12-25 | 2015-01-12 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Compostela Valley | 315805 | Pindasan NHS | MABINI (DOÑA ALICIA) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4A | 1738946.2338 |  |  | COMPLETED | 1 |  | 2015-04-18 | 110414S00042 | 14LA0228 | 2014-12-05 | 2014-12-18 | 2014-12-18 | 2014-12-22 | 2015-01-07 | EXACT CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao City | 304360 | Davao City NHS | DAVAO CITY | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4A | 31900584.375 |  |  | COMPLETED | 1 | 2016-01-26 |  | 110614S00051 | 14LB0174 | 2014-12-12 | 2014-12-10 | 2015-01-20 | 2015-02-28 | 2015-03-30 | LEGACY CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao City | 129640 | Don Manuel Gutierrez ES | DAVAO CITY | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4A | 14045118.3984 |  |  | COMPLETED | 1 | 2015-10-02 | 2015-10-15 | 110614S00050 | 14LB0176 | 2014-12-12 | 2014-12-10 | 2014-12-23 | 2015-02-08 | 2015-03-30 | JAMEETRIX CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao City | 129718 | Dona Soledad Dolor ES | DAVAO CITY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-09 | 110614S00018 | 14LB0032 | 2014-07-07 | 2014-07-03 | 2014-07-15 | 2014-08-08 | 2014-08-27 | BISLIG (FOR DELETION) VENTURE CONSTRUCTION DEVELOP
NC 2014 | K10 (2014) | Region XI | Davao City | 129697 | Jose L. Porras Elementary School | DAVAO CITY | 1 | 1 | 12 | 2UNIT 3STY6CL | 2014 K10 BATCH 4A | 21334187.1094 |  |  | COMPLETED | 1 | 2016-03-17 |  | 110614S00052 | 14LB0175 | 2014-12-12 | 2014-12-10 | 2014-12-23 | 2015-05-05 | 2015-05-18 | A.Y.U. ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao City | 129642 | Josefa Ll. EScoda ES | DAVAO CITY | 1 | 1 | 7 | 1STY1CL & 2STY6CL | 2014 K10 BATCH 3 | 9441912.484 |  |  | COMPLETED | 1 | 2015-09-21 | 2015-09-21 | 110614S00047 | 14LB0074 | 2014-12-12 | 2014-12-10 | 2014-12-22 | 2015-01-31 | 2015-03-30 | JAMEETRIX CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao City | 129643 | Kabacan ES | DAVAO CITY | 1 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 3 | 27459390.625 |  |  | COMPLETED | 1 | 2016-01-12 |  | 110614S00049 | 14LB0075 | 2014-12-04 | 2014-12-04 | 2014-12-23 | 2015-02-08 | 2015-03-18 | FFJJ CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao City | 129645 | Maa CES | DAVAO CITY | 1 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4B | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-28 |  | 110614S00055 | 15LB099 | 2015-07-02 | 2015-07-02 | 2015-07-28 | 2015-08-10 | 2015-08-25 | ARCINUE COMMERCIAL
NC 2014 | K10 (2014) | Region XI | Davao City | 129558 | Magallanes ES | DAVAO CITY | 1 | 1 | 12 | 2UNIT 3STY6CL | 2014 K10 BATCH 3 | 21404187.1094 |  |  | COMPLETED | 1 | 2016-01-26 |  | 110614S00046 | 14LB0073 | 2014-12-05 | 2014-12-05 | 2014-12-23 | 2015-02-09 | 2015-03-30 | LOTRIM CONSTRUCTION, INC.
NC 2014 | K10 (2014) | Region XI | Davao City | 129722 | R.C. Quimpo ES | DAVAO CITY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-30 | 110614S00020 | 14LB0033 | 2014-07-07 | 2014-07-03 | 2014-07-15 | 2014-08-08 | 2014-08-27 | A.Y.U. ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao City | 129708 | Sta. Ana CES | DAVAO CITY | 1 | 1 | 27 | 3STY15CL & 2UNIT 3STY6CL | 2014 K10 BATCH 3 | 44181098.8281 |  |  | COMPLETED | 1 | 2016-03-13 |  | 110614S00045 | 14LB0076 | 2014-12-05 | 2014-12-05 | 2015-02-03 | 2015-03-23 | 2015-05-18 | M.R. VARGAS CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao City | 129653 | ALEDIA ELEM SCHOOL | DAVAO CITY | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2915174.43 |  |  | COMPLETED | 1 | 2014-11-29 | 2014-11-29 | 110614S00013 | 14LB0037 | 2014-07-07 | 2014-07-03 | 2014-07-15 | 2014-08-06 | 2014-08-27 | DANIMERH CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao City | 129654 | Apalili ES | DAVAO CITY | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2875174.43 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 110614S00012 | 14LB0038 | 2014-07-07 | 2014-07-03 | 2014-07-15 | 2014-08-20 | 2014-08-27 | O. G. SANTOS CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao City | 129506 | Buhangin CES | DAVAO CITY | 2 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4B | 10417131.51 |  |  | COMPLETED | 1 | 2016-06-26 |  | 110614S00056 | 15LB0100 | 2015-07-02 | 2015-07-02 | 2015-07-28 | 2015-08-10 | 2015-08-25 | O. G. SANTOS CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao City | 129521 | Buhisan ES | DAVAO CITY | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2880174.43 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-30 | 110614S00015 | 14LB0035 | 2014-07-07 | 2014-07-03 | 2014-07-15 | 2014-08-08 | 2014-08-27 | O. G. SANTOS CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao City | 129508 | Callawa ES | DAVAO CITY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-30 | 110614S00016 | 14LB0034 | 2014-07-07 | 2014-07-03 | 2014-07-15 | 2014-08-08 | 2014-08-27 | RCBAR BUILDERS
NC 2014 | K10 (2014) | Region XI | Davao City | 129656 | Colosas ES | DAVAO CITY | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3800805.49 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 110614S00011 | 14LB0039 | 2014-07-11 | 2014-07-15 | 2014-07-29 | 2014-08-18 | 2014-08-27 | MINDANAO CONST. SERVICES & LAND DEVT. CORP.
NC 2014 | K10 (2014) | Region XI | Davao City | 129658 | Damilag PS | DAVAO CITY | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2975174.43 |  |  | COMPLETED | 1 | 2014-11-29 | 2014-11-29 | 110614S00010 | 14LB0040 | 2014-07-11 | 2014-07-15 | 2014-07-29 | 2014-08-18 | 2014-08-27 | JAVCON BUILDERS, INC.
NC 2014 | K10 (2014) | Region XI | Davao City | 129659 | Datu Libayao ES | DAVAO CITY | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2900174.43 |  |  | COMPLETED | 1 | 2014-11-29 | 2014-11-29 | 110614S00002 | 14LB0041 | 2014-07-11 | 2014-07-15 | 2014-07-29 | 2014-08-20 | 2014-08-27 | JAVCON BUILDERS, INC.
NC 2014 | K10 (2014) | Region XI | Davao City | 304366 | F. Bangoy NHS | DAVAO CITY | 2 | 1 | 6 | COMPLETION OF 3STY9CL | 2014 K10 BATCH 3 | 7035000 |  |  | REVERTED | 0 |  | 2015-03-17 | 110614S00041 | 14LB0079 | 2014-11-27 | 2014-11-27 | 2014-12-11 | 2014-12-13 | 2014-12-17 | DANIMERH CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao City | 129525 | Gatungan ES | DAVAO CITY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-30 | 110614S00014 | 14LB0036 | 2014-07-07 | 2014-07-03 | 2014-07-15 | 2014-08-08 | 2014-08-27 | JLA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region XI | Davao City | 129526 | Mahayag Elementary School | DAVAO CITY | 2 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8228453.2082 |  |  | COMPLETED | 1 | 2015-05-28 | 2015-05-12 | 110614S00042 | 14LB0078 | 2014-12-10 | 2014-12-05 | 2014-12-19 | 2015-01-16 | 2015-01-30 | DANIMERH CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao City | 304379 | Malabog NHS | DAVAO CITY | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2895174.43 |  |  | COMPLETED | 1 |  | 2014-11-29 | 110614S00005 | 14LB0044 | 2014-07-11 | 2014-07-15 | 2014-07-29 | 2014-08-19 | 2014-08-27 | ATR CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao City | 206005 | Pamantawan PS | DAVAO CITY | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2965174.43 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-14 | 110614S00004 | 14LB0043 | 2014-07-11 | 2014-07-15 | 2014-07-29 | 2014-08-20 | 2014-08-27 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2014 | K10 (2014) | Region XI | Davao City | 129677 | Tapak ES | DAVAO CITY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-12-09 | 2014-12-09 | 110614S00003 | 14LB0042 | 2014-07-11 | 2014-07-15 | 2014-07-29 | 2014-08-18 | 2014-08-27 | A.Y.U. ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao City | 129488 | Vicente Hizon, Sr. ES | DAVAO CITY | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 19931783.5938 |  |  | COMPLETED | 1 | 2015-11-28 | 2015-11-28 | 110614S00048 | 14LB0077 | 2014-12-04 | 2014-12-04 | 2014-12-23 | 2015-03-09 | 2015-03-19 | LEGACY CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao City | 304399 | Waan National High School | DAVAO CITY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 |  | 2014-10-30 | 110614S00006 | 14LB0045 | 2014-07-11 | 2014-07-15 | 2014-07-29 | 2014-08-20 | 2014-08-27 | LEAMOR CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao City | 129679 | A. Loyola ES | DAVAO CITY | 3 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4B | 10417131.51 |  |  | COMPLETED | 1 | 2016-03-07 |  | 110614S00059 | 15LH0127 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | O. G. SANTOS CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao City | 129680 | Alambre ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-05 | 110614S00019 | 14LH0020 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | JAVCON BUILDERS, INC.
NC 2014 | K10 (2014) | Region XI | Davao City | 129725 | Aniceto Barbarona ES | DAVAO CITY | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-02 | 2014-10-31 | 110614S00040 | 14LH0026 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | RK STAR ECOENGINEERING
NC 2014 | K10 (2014) | Region XI | Davao City | 316205 | Baguio HS of Agriculture - Tambobong HS Annex | DAVAO CITY | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 |  | 2014-12-04 | 110614S00024 | 14LH0019 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao City | 129682 | Bankas Heights ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 110614S00030 | 14LH0020 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | JAVCON BUILDERS, INC.
NC 2014 | K10 (2014) | Region XI | Davao City | 129600 | Bantol ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-03 | 2015-01-03 | 110614S00038 | 14LH0023 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | JAVCON BUILDERS, INC.
NC 2014 | K10 (2014) | Region XI | Davao City | 129491 | Bayabas ES | DAVAO CITY | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-02 | 2015-01-21 | 110614S00008 | 14LH0021 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | A.Y.U. ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao City | 129601 | Bayanihan ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1 | 2014-12-04 | 2014-12-04 | 110614S00037 | 14LH0029 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | J & S ESCUADRA CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao City | 129492 | Binugao CES | DAVAO CITY | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2875174.43 |  |  | COMPLETED | 1 | 2015-02-02 | 2014-11-30 | 110614S00017 | 14LH0021 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | A.Y.U. ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao City | 129531 | Calinan Central ES | DAVAO CITY | 3 | 1 | 3 | 3STY3CL | 2014 K10 BATCH 4B | 6803472.88 |  |  | COMPLETED | 1 | 2015-12-08 |  | 110614S00058 | 15LH0144 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao City | 316212 | Calinan NHS Annex -Tamayong HS | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-04 | 2014-11-30 | 110614S00022 | 14LH0019 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao City | 129733 | Carmen ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-12-19 | 2014-12-19 | 110614S00028 | 14LH0022 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | JLA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region XI | Davao City | 316207 | Crossing Bayabas NHS - Camansi HS Annex | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 |  | 2014-12-12 | 110614S00023 | 14LH0020 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | JAVCON BUILDERS, INC.
NC 2014 | K10 (2014) | Region XI | Davao City | 129533 | Dalagdag ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-12-04 | 2014-11-30 | 110614S00039 | 14LH0019 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao City | 129611 | Ladian ES | DAVAO CITY | 3 | 1 | 3 | 1STY2CL & 1STY1CL | 2014 K10 BATCH 1 | 3072746.69 |  |  | COMPLETED | 1 | 2015-02-02 | 2015-02-02 | 110614S00036 | 14LH0028 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | JAVCON BUILDERS, INC.
NC 2014 | K10 (2014) | Region XI | Davao City | 129735 | Los Amigos ES | DAVAO CITY | 3 | 1 | 12 | 3STY12CL | 2014 K10 BATCH 3 | 18879909.7656 |  |  | COMPLETED | 1 | 2015-10-30 | 2015-10-30 | 110614S00044 | 110614S00044 | 2014-12-03 | 2014-12-04 | 2014-12-16 | 2014-12-29 | 2015-01-29 | RSP ENTERPRISES, INC.
NC 2014 | K10 (2014) | Region XI | Davao City | 129495 | Lourdes ES | DAVAO CITY | 3 | 1 | 3 | 1STY2CL & 1STY1CL | 2014 K10 BATCH 1 | 3112746.69 |  |  | COMPLETED | 1 | 2015-02-02 | 2015-01-21 | 110614S00031 | 14LH0027 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | JAVCON BUILDERS, INC.
NC 2014 | K10 (2014) | Region XI | Davao City | 129612 | Lumatag PS | DAVAO CITY | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2885174.43 |  |  | COMPLETED | 1 | 2015-01-03 | 2015-01-03 | 110614S00035 | 14LH0023 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | JAVCON BUILDERS, INC.
NC 2014 | K10 (2014) | Region XI | Davao City | 129468 | Macatabo ES | DAVAO CITY | 3 | 1 | 4 | 2UNIT 1STY2CL | 2014 K10 BATCH 1 | 4040835.14 |  |  | COMPLETED | 1 | 2015-04-03 | 2015-03-31 | 110614S00007 | 14LH0031 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | JAVCON BUILDERS, INC.
NC 2014 | K10 (2014) | Region XI | Davao City | 129618 | Malikongkong PS | DAVAO CITY | 3 | 1 | 3 | 1STY2CL & 1STY1CL | 2014 K10 BATCH 1 | 3212746.69 |  |  | COMPLETED | 1 | 2015-02-02 | 2015-02-02 | 110614S00034 | 14LH0018 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | A.Y.U. ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao City | 129471 | Mangas-As ES | DAVAO CITY | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-12-04 | 2014-11-30 | 110614S00009 | 14LH0019 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao City | 304381 | Marilog HS Of Agriculture | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 |  | 2015-01-03 | 110614S00026 | 14LH0023 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | JAVCON BUILDERS, INC.
NC 2014 | K10 (2014) | Region XI | Davao City | 129622 | Namnam PS | DAVAO CITY | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2885174.43 |  |  | COMPLETED | 1 | 2015-02-02 | 2015-02-02 | 110614S00033 | 14LH0025 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | JAVCON BUILDERS, INC.
NC 2014 | K10 (2014) | Region XI | Davao City | 129627 | Patag ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2014-12-04 | 2014-12-04 | 110614S00032 | 14LH0030 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | LLM ENTERPRISES
NC 2014 | K10 (2014) | Region XI | Davao City | 129688 | Piedad Central ES | DAVAO CITY | 3 | 1 | 3 | 3STY3CL | 2014 K10 BATCH 4B | 6803472.88 |  |  | COMPLETED | 1 | 2015-12-08 |  | 110614S00057 | 15LH0145 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | MARK ANTHONY CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao City | 129629 | Salaysay ES | DAVAO CITY | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2880174.43 |  |  | COMPLETED | 1 | 2015-02-02 | 2015-01-31 | 110614S00029 | 14LH0024 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao City | 129742 | Talandang ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-19 | 2014-12-19 | 110614S00027 | 14LH0022 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | JLA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region XI | Davao City | 129544 | Tamayong ES | DAVAO CITY | 3 | 1 | 8 | 2UNIT 1STY4CL | 2014 K10 BATCH 3 | 6660936.2061 |  |  | COMPLETED | 1 | 2015-11-19 | 2015-11-19 | 110614S00043 | 15LH0019 | 2015-05-14 | 2015-08-25 | 2015-08-27 | 2015-09-05 | 2015-09-25 | FORTSTONE CONSTRUCTION ENTERPRISES
NC 2014 | K10 (2014) | Region XI | Davao City | 304397 | Telesforo S. Singson NHS | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1985417.57 |  |  | COMPLETED | 1 |  | 2014-12-19 | 110614S00025 | 14LH0022 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | JLA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region XI | Davao City | 129634 | Upian ES | DAVAO CITY | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2885174.43 |  |  | COMPLETED | 1 | 2015-02-02 | 2015-02-02 | 110614S00021 | 14LH0018 | 2014-06-18 | 2014-06-19 | 2014-07-01 | 2014-07-16 | 2014-08-07 | A.Y.U. ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128646 | Agman PS | SAN ISIDRO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-11-30 | 110114S00108 | 15LC0100 | 2015-06-24 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | DAVAO CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128647 | Aninipot ES | KAPALONG | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3619488.5356 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 110114S00054 | 14LC0075 | 2014-11-06 | 2014-11-14 | 2014-11-27 | 2014-12-09 | 2014-12-17 | RDF CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128565 | Buan ES | ASUNCION (SAUG) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1004567.84 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-05-31 | 110114S00038 | 14LC0070 | 2014-10-31 | 2014-11-07 | 2014-11-20 | 2014-12-05 | 2014-12-17 | RCBAR BUILDERS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128672 | Bunawan ES | KAPALONG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-10-31 | 110114S00110 | 15LC0101 | 2015-06-24 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | DAVAO CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128800 | Cabadiangan ES | TALAINGOD | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 989492.8399 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-19 | 110114S00044 | 14LC0050 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-14 | 2014-11-20 | DIGOS CONSTRAK CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128569 | Camansa Elementary School | ASUNCION (SAUG) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737081.3658 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 110114S00093 | 14LC0069 | 2014-10-31 | 2014-11-07 | 2014-11-20 | 2014-12-04 | 2014-12-17 | CHARIFER BUILDERS, INC.
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128570 | Cambanogoy CES | ASUNCION (SAUG) | 1 | 1 | 5 | 1STY5CL | 2014 K10 BATCH 3 | 4094319.2073 |  |  | COMPLETED | 1 |  | 2015-06-24 | 110114S00090 | 14LC0070 | 2014-10-31 | 2014-11-07 | 2014-11-20 | 2014-12-04 | 2014-12-17 | RCBAR BUILDERS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128801 | Dagohoy ES | TALAINGOD | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 999542.8399 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-19 | 110114S00036 | 14LC0050 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-14 | 2014-11-20 | DIGOS CONSTRAK CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 304258 | Datu Jose A. Libayao Memorial NHS | TALAINGOD | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1757181.3658 |  |  | COMPLETED | 1 |  | 2015-04-15 | 110114S00063 | 14LC0066 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 204505 | Dibabawon I ES | KAPALONG | 1 | 1 | 2 | 2UNIT 1STY1CL | 2014 K10 BATCH 4B | 2024099.3086 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-10-30 | 110114S00103 | 15LC0101 | 2015-06-24 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | DAVAO CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 204506 | Dibabawon II ES | KAPALONG | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4B | 4572048.49 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-30 | 110114S00107 | 15LC0106 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-27 | 2015-07-31 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128650 | Dugayan ES | KAPALONG | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2729030.4962 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 110114S00062 | 14LC0074 | 2014-11-06 | 2014-11-14 | 2014-11-27 | 2014-12-09 | 2014-12-17 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128704 | El Salvador ES | NEW CORELLA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737081.3658 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-03-15 | 110114S00085 | 14LC0065 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128652 | Gov. Dujali ES | SAN ISIDRO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1817481.3658 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 110114S00071 | 14LC0073 | 2014-11-06 | 2014-11-14 | 2014-11-27 | 2014-12-09 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128706 | Guadalupe ES | NEW CORELLA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737081.3658 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-19 | 110114S00041 | 14LC0049 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-14 | 2014-11-20 | RITZTOK CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128653 | Gupitan ES | KAPALONG | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2678780.4962 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 110114S00060 | 14LC0072 | 2014-10-31 | 2014-11-07 | 2014-11-20 | 2014-12-04 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128654 | Kapatagan ES | KAPALONG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-08 | 2015-12-08 | 110114S00118 | 15LC0137 | 2015-08-06 | 2015-08-07 | 2015-08-20 | 2015-08-28 | 2015-09-10 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128707 | Kauswagan PS | NEW CORELLA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737081.3658 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-03-15 | 110114S00091 | 14LC0065 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128576 | Kipalili ES | SAN ISIDRO | 1 | 1 | 4 | 2UNIT 1STY2CL | 2014 K10 BATCH 3 | 3474162.7317 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 110114S00061 | 14LC0073 | 2014-11-06 | 2014-11-14 | 2014-11-27 | 2014-12-09 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128655 | Langan ES | KAPALONG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-08 | 2015-12-08 | 110114S00104 | 15LC0137 | 2015-08-06 | 2015-08-07 | 2015-08-20 | 2015-08-28 | 2015-09-10 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128577 | Liguyon ES | ASUNCION (SAUG) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2528030.4962 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 110114S00042 | 14LC0069 | 2014-10-31 | 2014-11-07 | 2014-11-20 | 2014-12-04 | 2014-12-17 | CHARIFER BUILDERS, INC.
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128658 | Luan ES | KAPALONG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 969392.8399 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 110114S00089 | 14LC0064 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | TWINA BUILDERS AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128675 | Mabantao ES | KAPALONG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 969392.8399 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 110114S00052 | 14LC0064 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | TWINA BUILDERS AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128578 | Magatos ES | ASUNCION (SAUG) | 1 | 1 | 8 | 1STY5CL & 1STY3CL | 2014 K10 BATCH 3 | 6823349.7034 |  |  | COMPLETED | 1 | 2015-05-28 | 2015-05-28 | 110114S00043 | 14LC0051 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-14 | 2014-11-20 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128579 | Magbaad ES | ASUNCION (SAUG) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 999542.8399 |  |  | COMPLETED | 1 | 2015-05-28 | 2015-05-28 | 110114S00045 | 14LC0051 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-14 | 2014-11-20 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128580 | Mahayahay PS | ASUNCION (SAUG) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 969392.8399 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-09 | 110114S00070 | 14LC0052 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-14 | 2014-11-20 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128661 | Mambago ES | KAPALONG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1938081.3658 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 110114S00059 | 14LC0075 | 2014-11-06 | 2014-11-14 | 2014-11-27 | 2014-12-09 | 2014-12-17 | RDF CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128677 | Mangulibas ES | KAPALONG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1797381.3658 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 110114S00039 | 14LC0064 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | TWINA BUILDERS AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128663 | Marcos P. Estoque ES | KAPALONG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737081.3658 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-03-31 | 110114S00058 | 14LC0072 | 2014-10-31 | 2014-11-07 | 2014-11-20 | 2014-12-04 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128803 | Mesolong ES | TALAINGOD | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-10-31 | 110114S00113 | 15LC0099 | 2015-06-24 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128804 | NASECO ES | TALAINGOD | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3418488.5356 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-19 | 110114S00046 | 14LC0050 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-14 | 2014-11-20 | DIGOS CONSTRAK CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 204504 | Natulinan ES | TALAINGOD | 1 | 1 | 4 | 2UNIT 1STY2CL | 2014 K10 BATCH 3 | 3624912.7317 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 110114S00050 | 14LC0066 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128583 | New Bantayan ES | ASUNCION (SAUG) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 999542.8399 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-09 | 110114S00069 | 14LC0052 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-14 | 2014-11-20 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128664 | New Boholano ES | KAPALONG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-30 | 110114S00111 | 15LC0102 | 2015-06-24 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128715 | New Cortez ES | NEW CORELLA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737081.3658 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-03-15 | 110114S00092 | 14LC0065 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128584 | New Loon ES | ASUNCION (SAUG) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-10-30 | 110114S00109 | 15LC0098 | 2015-06-24 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128585 | New Santiago ES | ASUNCION (SAUG) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 969392.8399 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-05-31 | 110114S00097 | 14LC0070 | 2014-10-31 | 2014-11-07 | 2014-11-20 | 2014-12-04 | 2014-12-17 | RCBAR BUILDERS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128586 | New Talisay ES | ASUNCION (SAUG) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 989492.8399 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-19 | 110114S00068 | 14LC0053 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-14 | 2014-11-20 | RK STAR ECOENGINEERING
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128587 | New Visayas PS | ASUNCION (SAUG) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-10-30 | 110114S00102 | 15LC0098 | 2015-06-24 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128805 | Paiton ES | TALAINGOD | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-10-31 | 110114S00106 | 15LC0099 | 2015-06-24 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128806 | Palma Gil ES | TALAINGOD | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737081.3658 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-19 | 110114S00047 | 14LC0050 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-14 | 2014-11-20 | DIGOS CONSTRAK CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128588 | Pamacaun ES | ASUNCION (SAUG) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 989492.8399 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-19 | 110114S00067 | 14LC0053 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-14 | 2014-11-20 | RK STAR ECOENGINEERING
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128665 | Pandulian ES | KAPALONG | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-30 | 110114S00105 | 15LC0102 | 2015-06-24 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128666 | Patel ES | KAPALONG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1887831.3658 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 110114S00057 | 14LC0076 | 2014-11-06 | 2014-11-14 | 2014-11-27 | 2014-12-09 | 2014-12-17 | J & S ESCUADRA CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128717 | Patrocenio ES | NEW CORELLA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 969392.8399 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-19 | 110114S00053 | 14LC0049 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-14 | 2014-11-20 | RITZTOK CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128667 | Pinamuno ES | SAN ISIDRO | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2628530.4962 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 110114S00056 | 14LC0073 | 2014-11-06 | 2014-11-14 | 2014-11-27 | 2014-12-09 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128590 | Sabangan ES | SAN ISIDRO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 989492.8399 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-03-31 | 110114S00066 | 14LC0073 | 2014-11-06 | 2014-11-14 | 2014-11-27 | 2014-12-09 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128591 | Sagayen ES | ASUNCION (SAUG) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2528030.4962 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-09 | 110114S00065 | 14LC0052 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-11 | 2014-11-20 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 304218 | Sagayen NHS | ASUNCION (SAUG) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1767231.3658 |  |  | COMPLETED | 1 |  | 2015-04-05 | 110114S00051 | 14LC0069 | 2014-10-31 | 2014-11-07 | 2014-11-20 | 2014-12-04 | 2014-12-17 | CHARIFER BUILDERS, INC.
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128679 | Sampao ES | KAPALONG | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3478788.5356 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 110114S00040 | 14LC0064 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | TWINA BUILDERS AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128592 | San Miguel PS | SAN ISIDRO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-10-31 | 110114S00117 | 15LC0100 | 2015-06-24 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | DAVAO CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128719 | San Roque ES | NEW CORELLA | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3317988.5356 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-19 | 110114S00094 | 14LC0049 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-14 | 2014-11-20 | RITZTOK CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128596 | Sonlon ES | ASUNCION (SAUG) | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3388338.5356 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-19 | 110114S00064 | 14LC0053 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-14 | 2014-11-20 | RK STAR ECOENGINEERING
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128722 | Sta. Cruz ES | NEW CORELLA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737081.3658 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-03-15 | 110114S00095 | 14LC0065 | 2014-10-27 | 2014-11-07 | 2014-11-18 | 2014-12-04 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128597 | Sta. Filomena ES | ASUNCION (SAUG) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-10-30 | 110114S00112 | 15LC0098 | 2015-06-24 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128807 | Sto. Niño CES | TALAINGOD | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 969392.8399 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 110114S00048 | 14LC0066 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 304257 | Sto. Nino NHS | TALAINGOD | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 969392.8399 |  |  | COMPLETED | 1 |  | 2015-04-15 | 110114S00037 | 14LC0066 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 304235 | Sua-on NHS | KAPALONG | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3418488.5356 |  |  | COMPLETED | 1 |  | 2015-04-15 | 110114S00080 | 14LC0074 | 2014-11-06 | 2014-11-14 | 2014-11-27 | 2014-12-09 | 2014-12-17 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128725 | Suawon ES | NEW CORELLA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 969392.8399 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-19 | 110114S00096 | 14LC0049 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-14 | 2014-11-20 | RITZTOK CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128671 | Tagasan ES | KAPALONG | 1 | 1 | 6 | 2UNIT 1STY3CL | 2014 K10 BATCH 3 | 5357560.9923 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 110114S00055 | 14LC0076 | 2014-11-06 | 2014-11-14 | 2014-11-27 | 2014-12-09 | 2014-12-17 | J & S ESCUADRA CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128808 | Tibi-Tibi ES | TALAINGOD | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 979442.8399 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 110114S00049 | 14LC0066 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 304215 | Alejal National High School | CARMEN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737081.3658 |  |  | COMPLETED | 1 |  | 2015-02-17 | 110114S00074 | 14LC0060 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-14 | 2014-11-20 | MAG CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128614 | Bacale ES | BRAULIO E. DUJALI | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737081.3658 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 110114S00088 | 14LC0071 | 2014-10-31 | 2014-11-07 | 2014-11-20 | 2014-12-04 | 2014-12-17 | TWINA BUILDERS AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128757 | Balagunan ES | SANTO TOMAS | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2528030.4962 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 110114S00086 | 14LC0059 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 304221 | Cabayangan NHS | BRAULIO E. DUJALI | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2528030.4962 |  |  | COMPLETED | 1 |  | 2015-04-05 | 110114S00073 | 14LC0071 | 2014-10-31 | 2014-11-07 | 2014-11-20 | 2014-12-04 | 2014-12-17 | TWINA BUILDERS AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128629 | Cebulano ES | CARMEN | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2528030.4962 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-09 | 110114S00083 | 14LC0054 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-14 | 2014-11-20 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 304237 | Kimamon NHS | SANTO TOMAS | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2528030.4962 |  |  | COMPLETED | 1 |  | 2015-04-05 | 110114S00087 | 14LC0058 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | EXACT CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128631 | La Paz ES | CARMEN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737081.3658 |  |  | COMPLETED | 1 | 2015-02-17 | 2015-02-16 | 110114S00082 | 14LC0060 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-14 | 2014-11-20 | MAG CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 315904 | La Paz NHS | CARMEN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 969392.8399 |  |  | COMPLETED | 1 |  | 2015-03-09 | 110114S00016 | 14LC0054 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-11 | 2014-11-20 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 304244 | Mabuhay NHS | CARMEN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737081.3658 |  |  | COMPLETED | 1 |  | 2015-02-17 | 110114S00033 | 14LC0060 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-11 | 2014-11-20 | MAG CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128760 | Marsman ES | SANTO TOMAS | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737081.3658 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 110114S00078 | 14LC0058 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | EXACT CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128761 | New Katipunan ES | SANTO TOMAS | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737081.3658 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 110114S00077 | 14LC0058 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | EXACT CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128762 | New Visayas ES | SANTO TOMAS | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737081.3658 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 110114S00076 | 14LC0059 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128753 | Pantaron ES | SANTO TOMAS | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 969392.8399 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 110114S00079 | 14LC0058 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | EXACT CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128639 | San Isidro ES | CARMEN | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2528030.4962 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-09 | 110114S00072 | 14LC0054 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-14 | 2014-11-20 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128640 | Sto Niño ES | CARMEN | 2 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 3 | 4265111.862 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-08 | 110114S00081 | 14LC0057 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-14 | 2014-11-20 | MAG CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128622 | Talisay ES | BRAULIO E. DUJALI | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737081.3658 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 110114S00084 | 14LC0071 | 2014-10-31 | 2014-11-07 | 2014-11-20 | 2014-12-04 | 2014-12-17 | TWINA BUILDERS AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128643 | Tubod ES | CARMEN | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2528030.4962 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-08 | 110114S00034 | 14LC0057 | 2014-10-10 | 2014-10-17 | 2014-10-30 | 2014-11-14 | 2014-11-20 | MAG CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao del Norte | 128767 | Tulalian ES | SANTO TOMAS | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3317988.5356 |  |  | COMPLETED | 1 | 2015-04-15 | 2015-04-15 | 110114S00075 | 14LC0059 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 129089 | Agripina ES | SANTA CRUZ | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-05-04 | 2015-05-04 | 110214S00125 | 14LD0054 | 2014-11-24 | 2014-11-25 | 2014-12-16 | 2014-12-19 | 2014-12-29 | LEAMOR CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 129022 | Alfredo Eugenio Sr. ES | MATANAO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-14 | 110214S00101 | 14LD0025 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | LEAMOR CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 128824 | Altavista ES | BANSALAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-15 | 110214S00096 | 14LD0014 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 129029 | Asinan ES | MATANAO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-14 | 110214S00104 | 14LD0020 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | VERGUZ CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 304289 | Bangkal NHS | MATANAO | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2955174.43 |  |  | COMPLETED | 1 |  | 2014-11-14 | 110214S00114 | 14LD0020 | 2014-06-24 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | VERGUZ CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 129012 | Buas ES | MATANAO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-15 | 110214S00100 | 14LD0019 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | LEAMOR CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 128934 | Dalumay ES | MAGSAYSAY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-14 | 110214S00119 | 14LD0016 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | RITZTOK CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 129078 | Darong ES | SANTA CRUZ | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-10-15 | 110214S00108 | 14LD0023 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 129079 | Don Amancio ES | SANTA CRUZ | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3015174.43 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-14 | 110214S00109 | 14LD0023 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 129036 | Glot Towak ES | MATANAO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-15 | 110214S00116 | 14LD0022 | 2014-06-24 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 128858 | La Union ES | HAGONOY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-14 | 110214S00097 | 14LD0015 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 128927 | Labidangan ES | MAGSAYSAY | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2985174.43 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-14 | 110214S00118 | 14LD0016 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | RITZTOK CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 128860 | Lapulabao ES | HAGONOY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-30 | 110214S00098 | 14LD0027 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | LEAMOR CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 128831 | Libertad ES | BANSALAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-15 | 110214S00094 | 14LD0014 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 304284 | Lower Bala NHS | MAGSAYSAY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 |  | 2014-11-14 | 110214S00122 | 14LD0028 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | LEAMOR CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 129040 | M.H. del Pilar ES | MATANAO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-15 | 110214S00106 | 14LD0022 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 128937 | Maibo ES | MAGSAYSAY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-10-15 | 110214S00120 | 14LD0017 | 2014-06-24 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 128863 | Maliit Digos ES | HAGONOY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-14 | 110214S00099 | 14LD0015 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 128939 | Malongon ES | MAGSAYSAY | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2985174.43 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-10-15 | 110214S00121 | 14LD0017 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 304286 | Marber NHS | BANSALAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 |  | 2014-10-30 | 110214S00105 | 14LD0014 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 304288 | Matanao National High School | MATANAO | 1 | 1 | 16 | 2UNIT 2STY8CL | 2014 K10 BATCH 3 | 22555968.75 |  |  | COMPLETED | 1 |  | 2015-09-01 | 110214S00126 | 14LD0055 | 2014-11-24 | 2014-11-25 | 2014-12-16 | 2014-12-19 | 2014-12-29 | JV: ORIENTECH CONSTRUCTION & DEVELOPMENT CORPORATION/PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 129084 | Pogpog ES | SANTA CRUZ | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-28 | 110214S00110 | 14LD0024 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | LEAMOR CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 316004 | SACUB High School Annex | HAGONOY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 129024 | San Vicente ES | MATANAO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-15 | 110214S00102 | 14LD0021 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 129027 | Savoy ES | MATANAO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-15 | 110214S00103 | 14LD0019 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | LEAMOR CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 304290 | Sinawilan NHS | MATANAO | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 129098 | Sinoron ES | SANTA CRUZ | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-08 | 110214S00112 | 14LD0024 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | LEAMOR CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 129099 | Sta. Cruz CES | SANTA CRUZ | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-30 | 110214S00113 | 14LD0024 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | LEAMOR CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 304298 | Tacul Agrc'L VHS (Tacul NHS) | MAGSAYSAY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 128944 | Tagaytay ES | MAGSAYSAY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-10-15 | 110214S00123 | 14LD0018 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | LEAMOR CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 129044 | Tibongbong ES | MATANAO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-15 | 110214S00107 | 14LD0021 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao del Sur | 129087 | Tubison ES | SANTA CRUZ | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2945174.43 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-14 | 110214S00111 | 14LD0025 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | LEAMOR CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128961 | Aglaungan ES | MALITA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-07-14 | 110214S00033 | 14LE0044 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-24 | 2014-12-10 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Del Sur | 128945 | Albatera ES (Sto. Niño) | MALALAG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 110214S00042 | 14LE0031 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-09-30 | 2014-10-16 | DIGOS CONSTRAK CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129053 | Balangonan ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3015174.43 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-07-15 | 110214S00071 | 14LE0046 | 2014-10-16 | 2014-10-20 | 2014-11-04 | 2014-11-25 | 2014-12-11 | FFJJ CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 304264 | Balangonan NHS | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128837 | Baluntaya ES | DON MARCELINO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2915174.43 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-06-10 | 110214S00025 | 14LE0023 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-24 | 2014-11-06 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Del Sur | 128946 | Baybay ES | MALALAG | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3015174.43 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 110214S00043 | 14LE0031 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-09-30 | 2014-10-16 | DIGOS CONSTRAK CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128963 | Biao ES | MALITA | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3880805.49 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-07-14 | 110214S00002 | 14LE0044 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-24 | 2014-12-10 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 304269 | B'Laan NHS | MALITA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 205033 | Bolo-bolo ES | MALITA | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 1 | 3152746.69 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-07-15 | 110214S00049 | 14LE0042 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-25 | 2014-12-11 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Del Sur | 129131 | Buguis ES | SULOP | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-04-19 | 2015-04-19 | 110214S00082 | 14LE0020 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-27 | 2014-11-14 | O. G. SANTOS CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129055 | Bukid ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 7 | 1STY3CL & 1STY4CL | 2014 K10 BATCH 1 | 6905979.92 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-07-15 | 110214S00072 | 14LE0046 | 2014-10-16 | 2014-10-20 | 2014-11-04 | 2014-11-25 | 2014-12-11 | FFJJ CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128877 | Butuan ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 1 | 5035592 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-07-15 | 110214S00021 | 14LE0045 | 2014-10-16 | 2014-10-20 | 2014-11-04 | 2014-11-25 | 2014-12-11 | FFJJ CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129060 | Butulan ES (Kilakay ES) | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3015174.43 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 110214S00076 | 14LE0025 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-23 | 2014-11-11 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129105 | Cabalantian ES | SANTA MARIA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-07-14 | 110214S00084 | 14LE0030 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-24 | 2014-12-10 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128838 | Calian ES | DON MARCELINO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2955174.43 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 110214S00027 | 14LE0022 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-20 | 2014-11-05 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129057 | Camahual ES | SARANGANI | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3015174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129058 | Camalian ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3015174.43 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 110214S00075 | 14LE0025 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-23 | 2014-11-11 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128878 | Cayaponga ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-07-15 | 110214S00034 | 14LE0034 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-27 | 2014-12-11 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128879 | Culaman ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-05-19 | 2015-07-01 | 110214S00035 | 14LE0033 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-27 | 2014-11-14 | O. G. SANTOS CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128839 | Dalupan ES | DON MARCELINO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 110214S00028 | 14LE0022 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-20 | 2014-11-05 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Del Sur | 205019 | Datu Bacala PS | MALALAG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 110214S00048 | 14LE0031 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-09-30 | 2014-10-16 | DIGOS CONSTRAK CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128990 | Datu Danwata ES | MALITA | 2 | 1 | 12 | 2UNIT 2STY6CL | 2014 K10 BATCH 3 | 16698106.4062 |  |  | COMPLETED | 1 | 2015-08-19 | 2015-10-03 | 110214S00128 | 14LE0085 | 2014-12-14 | 2014-12-15 | 2014-12-22 | 2014-12-29 | 2015-01-14 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 304271 | Demolok Valley NHS | MALITA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128840 | Don Marcelino Maruya ES | DON MARCELINO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-06-10 | 2015-06-10 | 110214S00029 | 14LE0023 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-24 | 2014-11-06 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 304272 | Don Marcelino NHS | DON MARCELINO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 205055 | Fagligdong PS | MALITA | 2 | 1 | 4 | 2UNIT 1STY2CL | 2014 K10 BATCH 1 | 4140835.14 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-06-14 | 110214S00045 | 14LE0041 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-25 | 2014-12-10 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128883 | Faustino K. Labiton Sr. Elementary School | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2016-02-12 |  | 110214S00137 | 15LE0027 | 2015-08-05 | 2015-08-07 | 2015-08-19 | 2015-09-23 | 2015-10-09 | AL HANDASA CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Del Sur | 304274 | Gov. N. Llanos NHS | KIBLAWAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 205045 | Gusatbak PS | DON MARCELINO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-07-14 | 110214S00054 | 14LE0032 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-20 | 2014-12-10 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129056 | Ignacia Guillermo ES (Butulan ES) | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3015174.43 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-06-15 | 110214S00073 | 14LE0025 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-23 | 2014-11-11 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128970 | J. Doromal ES | MALITA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3015174.43 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 110214S00001 | 14LE0029 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-24 | 2014-11-05 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129004 | Jack Harvey ES | MALITA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-07-15 | 110214S00023 | 14LE0043 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-24 | 2014-12-11 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128881 | Jose Abad Santos CES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 6 | 2UNIT 1STY3CL | 2014 K10 BATCH 1 | 5910348.86 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 110214S00036 | 14LE0027 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-20 | 2014-11-05 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 304281 | Jose Abad Santos NHS | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 6 | 2UNIT 1STY3CL | 2014 K10 BATCH 1 | 5850348.86 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129111 | Jose Timbol Sr. CES | SANTA MARIA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-06-18 | 2015-06-18 | 110214S00085 | 14LE0024 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-27 | 2014-11-14 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128850 | Jose Villanueva ES | DON MARCELINO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-07-14 | 110214S00032 | 14LE0032 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-20 | 2014-12-10 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128984 | Julian M. Turado Elem. School | MALITA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-07-14 | 110214S00015 | 14LE0044 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-24 | 2014-12-10 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128992 | Kablulan ES | MALITA | 2 | 1 | 7 | 3UNIT 1STY2CL & 1STY1CL | 2014 K10 BATCH 1 | 7283581.83 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-07-15 | 110214S00019 | 14LE0042 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-25 | 2014-12-11 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128882 | Kalbay ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-07-15 | 110214S00037 | 14LE0034 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-27 | 2014-12-11 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 205025 | Kangko ES | MALITA | 2 | 1 | 6 | 3UNIT 1STY2CL | 2014 K10 BATCH 1 | 6031252.71 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-07-14 | 110214S00055 | 14LE0039 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-25 | 2014-12-10 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128993 | Kibalatong ES | MALITA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-06-04 | 2015-06-04 | 110214S00018 | 14LE0036 | 2014-08-27 | 2014-08-29 | 2014-09-10 | 2014-10-03 | 2014-10-31 | O. G. SANTOS CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129112 | Kidadan ES | SANTA MARIA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-07-14 | 110214S00086 | 14LE0030 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-24 | 2014-12-10 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128971 | Kidalapong ES | MALITA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 110214S00009 | 14LE0029 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-24 | 2014-11-05 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128841 | Kinanga ES | DON MARCELINO | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6399164.7656 |  |  | COMPLETED | 1 | 2015-08-13 | 2015-08-23 | 110214S00124 | 14LE0084 | 2014-12-14 | 2014-12-15 | 2014-12-22 | 2014-12-29 | 2015-01-09 | J & S ESCUADRA CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128994 | Kinangan ES | MALITA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-06-18 | 2015-06-18 | 110214S00017 | 14LE0037 | 2014-08-27 | 2014-08-29 | 2014-09-10 | 2014-10-27 | 2014-11-14 | O. G. SANTOS CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129113 | Kinilidan ES | SANTA MARIA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-07-14 | 110214S00087 | 14LE0030 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-24 | 2014-12-10 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 205054 | Kisoy PS | MALITA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-07-15 | 110214S00056 | 14LE0038 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-25 | 2014-12-11 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129062 | Konel ES | SARANGANI | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129115 | L. Payan ES | SANTA MARIA | 2 | 1 | 4 | 2UNIT 1STY2CL | 2014 K10 BATCH 1 | 4060835.14 |  |  | COMPLETED | 1 | 2015-06-18 | 2015-06-18 | 110214S00088 | 14LE0024 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-27 | 2014-11-14 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Del Sur | 129136 | Labon ES | SULOP | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-04-19 | 2015-04-19 | 110214S00080 | 14LE0020 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-27 | 2014-11-14 | O. G. SANTOS CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128996 | Lagumit ES | MALITA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2955174.43 |  |  | COMPLETED | 1 | 2015-06-18 | 2015-06-18 | 110214S00014 | 14LE0037 | 2014-08-27 | 2014-08-29 | 2014-09-10 | 2014-10-27 | 2014-11-14 | O. G. SANTOS CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128997 | Lalon ES | MALITA | 2 | 1 | 5 | 2UNIT 1STY2CL & 1STY1CL | 2014 K10 BATCH 1 | 5183164.26 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-07-14 | 110214S00007 | 14LE0040 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-25 | 2014-12-10 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 304291 | Lawa NHS | DON MARCELINO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128998 | Lenna ES | MALITA | 2 | 1 | 3 | 1STY2CL & 1STY1CL | 2014 K10 BATCH 1 | 3212746.69 |  |  | COMPLETED | 1 | 2015-05-19 | 2015-07-01 | 110214S00016 | 14LE0037 | 2014-08-27 | 2014-08-29 | 2014-09-10 | 2014-10-27 | 2014-11-14 | O. G. SANTOS CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 205013 | Libudon PS | MALITA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-07-15 | 110214S00047 | 14LE0038 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-25 | 2014-12-11 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129117 | Lilan ES | SANTA MARIA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3015174.43 |  |  | COMPLETED | 1 | 2015-06-18 | 2015-06-18 | 110214S00089 | 14LE0024 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-27 | 2014-11-14 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128846 | Linadasan ES | DON MARCELINO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-07-14 | 110214S00044 | 14LE0032 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-20 | 2014-12-10 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128999 | Little Baguio ES | MALITA | 2 | 1 | 6 | 2UNIT 1STY3CL | 2014 K10 BATCH 1 | 5910348.86 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-07-15 | 110214S00004 | 14LE0038 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-25 | 2014-12-11 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128847 | Mabuhay ES | DON MARCELINO | 2 | 1 | 8 | 2UNIT 2STY4CL | 2014 K10 BATCH 3 | 12838529.5312 |  |  | COMPLETED | 1 | 2015-08-19 | 2015-08-19 | 110214S00127 | 14LE0086 | 2014-12-14 | 2014-12-15 | 2014-12-22 | 2014-12-23 | 2015-01-14 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 205021 | Malagsom PS | MALITA | 2 | 1 | 4 | 2UNIT 1STY2CL | 2014 K10 BATCH 4B | 3629480.3479 |  |  | COMPLETED | 1 | 2016-02-12 |  | 110214S00138 | 15LE0026 | 2015-08-05 | 2015-08-07 | 2015-08-19 | 2015-09-23 | 2015-10-09 | AL HANDASA CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128884 | Malalan ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 4 | 2UNIT 1STY2CL | 2014 K10 BATCH 1 | 4100835.14 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-07-15 | 110214S00038 | 14LE0034 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-27 | 2014-12-11 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129119 | Malaygan ES | SANTA MARIA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3015174.43 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-07-14 | 110214S00090 | 14LE0030 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-24 | 2014-12-10 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128977 | Malita CES | MALITA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 110214S00010 | 14LE0029 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-24 | 2014-11-05 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128848 | Maltusan ES | DON MARCELINO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-07-14 | 110214S00005 | 14LE0032 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-20 | 2014-12-10 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129003 | Manuel Peralta ES | MALITA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-07-15 | 110214S00003 | 14LE0043 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-24 | 2014-12-11 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129121 | Migsulang PS | SANTA MARIA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-07-14 | 110214S00091 | 14LE0030 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-24 | 2014-12-10 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129065 | Molmol ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-07-15 | 110214S00078 | 14LE0034 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-27 | 2014-12-11 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Del Sur | 316001 | Molopolo National High School | KIBLAWAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Davao Del Sur | 205005 | Molopolo PS | KIBLAWAN | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 110214S00046 | 14LE0021 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-09-30 | 2014-10-16 | DIGOS CONSTRAK CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128979 | Mote PS | MALITA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-07-14 | 110214S00011 | 14LE0044 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-24 | 2014-12-10 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128980 | Nawan PS | MALITA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-07-14 | 110214S00012 | 14LE0040 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-25 | 2014-12-10 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 205053 | New Mabuhay PS | MALITA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3015174.43 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-07-15 | 110214S00068 | 14LE0043 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-24 | 2014-12-11 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128851 | Palamid ES | DON MARCELINO | 2 | 1 | 9 | 3UNIT 1STY3CL | 2014 K10 BATCH 1 | 8865523.29 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 110214S00031 | 14LE0028 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-24 | 2014-11-05 | O. G. SANTOS CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128888 | Patulang ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2985174.43 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 110214S00039 | 14LE0027 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-20 | 2014-11-05 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128962 | Procopio Mejellano ES (Bagsak ES) | MALITA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 110214S00020 | 14LE0029 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-24 | 2014-11-05 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129067 | Pulabato ES | SARANGANI | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 110214S00079 | 14LE0035 | 2014-08-27 | 2014-08-29 | 2014-09-10 | 2014-10-23 | 2014-11-05 | O. G. SANTOS CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128889 | Rolando Pardinas ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-05-19 | 2015-07-01 | 110214S00040 | 14LE0033 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-27 | 2014-11-14 | O. G. SANTOS CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128890 | San Felipe ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 12 | 2UNIT 2STY6CL | 2014 K10 BATCH 4B | 16429930.102 |  |  | COMPLETED | 1 |  |  | 110214S00139 | 15LE0029 | 2015-11-29 | 2015-12-01 | 2015-12-28
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129069 | San Isidro ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-07-14 | 110214S00093 | 14LE0034 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-27 | 2014-12-11 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129006 | Santagose ES | MALITA | 2 | 1 | 6 | 2UNIT 1STY3CL | 2014 K10 BATCH 4B | 5281656.248 |  |  | REVERTED | 0 | 2016-03-13 |  | 110214S00134 | 15LE0028 | 2015-08-05 | 2015-08-07 | 2015-08-19 | 2015-09-23 | 2015-10-09 | AL HANDASA CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128892 | Sugal ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3920805.49 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-07-15 | 110214S00041 | 14LE0045 | 2014-10-16 | 2014-10-20 | 2014-11-04 | 2014-11-25 | 2014-12-11 | FFJJ CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Del Sur | 304297 | Sulop NHS | SULOP | 2 | 1 | 8 | 2UNIT 2STY4CL | 2014 K10 BATCH 3 | 12597329.5312 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129071 | Tagen ES | SARANGANI | 2 | 1 | 3 | 1STY2CL & 1STY1CL | 2014 K10 BATCH 1 | 3212746.69 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 110214S00081 | 14LE0035 | 2014-08-27 | 2014-08-29 | 2014-09-10 | 2014-10-23 | 2014-11-05 | O. G. SANTOS CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128985 | Talogoy ES | MALITA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 110214S00006 | 14LE0029 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-24 | 2014-11-05 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129129 | Tanglad ES | SANTA MARIA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-06-18 | 2015-06-18 | 110214S00057 | 14LE0024 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-27 | 2014-11-14 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128982 | Teodorico Lopez ES (Sangay ES) | MALITA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-06-04 | 2015-06-04 | 110214S00013 | 14LE0036 | 2014-08-27 | 2014-08-29 | 2014-09-10 | 2014-10-03 | 2014-10-31 | O. G. SANTOS CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 205037 | TFS-Bilibak PS | MALITA | 2 | 1 | 4 | 2UNIT 1STY2CL | 2014 K10 BATCH 4B | 3629480.3479 |  |  | COMPLETED | 1 | 2016-02-12 |  | 110214S00140 | 15LE0030 | 2015-08-05 | 2015-08-07 | 2015-08-19 | 2015-09-23 | 2015-10-09 | AL HANDASA CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 205039 | TFS-Danaw PS | MALITA | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 1 | 3212746.69 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-07-14 | 110214S00052 | 14LE0039 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-25 | 2014-12-10 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 205035 | TFS-Kitastas PS | MALITA | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 1 | 3212746.69 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-07-15 | 110214S00050 | 14LE0043 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-24 | 2014-12-11 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 205036 | TFS-Malandeg PS | MALITA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-07-14 | 110214S00051 | 14LE0040 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-25 | 2014-12-10 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 205034 | TFS-Talabong ES | MALITA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-07-15 | 110214S00022 | 14LE0043 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-24 | 2014-12-11 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 205041 | TFS-Tambelang PS | MALITA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-06-14 | 2015-06-14 | 110214S00053 | 14LE0041 | 2014-10-01 | 2014-10-03 | 2014-10-23 | 2014-11-25 | 2014-12-10 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129007 | Tical ES | MALITA | 2 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 1 | 5035592 |  |  | COMPLETED | 1 | 2015-06-04 | 2015-06-04 | 110214S00092 | 14LE0036 | 2014-08-27 | 2014-08-29 | 2014-09-10 | 2014-10-03 | 2014-10-31 | O. G. SANTOS CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129008 | Ticulon ES | MALITA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-06-18 | 2015-06-18 | 110214S00070 | 14LE0037 | 2014-08-27 | 2014-08-29 | 2014-09-10 | 2014-10-27 | 2014-11-14 | O. G. SANTOS CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129072 | Tinina ES | SARANGANI | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 110214S00069 | 14LE0035 | 2014-08-27 | 2014-08-29 | 2014-09-10 | 2014-10-23 | 2014-11-05 | O. G. SANTOS CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 304268 | Tubalan Comprehensive NHS | SANTA MARIA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128987 | Tubalan ES | MALITA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 110214S00008 | 14LE0029 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-24 | 2014-11-05 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 129074 | Ubas ES | SARANGANI | 2 | 1 | 4 | 2UNIT 1STY2CL | 2014 K10 BATCH 1 | 4140835.14 |  |  | COMPLETED | 1 | 2015-05-17 | 2015-07-01 | 110214S00083 | 14LE0026 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-24 | 2014-11-12 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Occidental | 128844 | William Joyce ES | DON MARCELINO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2955174.43 |  |  | COMPLETED | 1 | 2015-06-09 | 2015-06-09 | 110214S00030 | 14LE0022 | 2014-08-14 | 2014-08-18 | 2014-09-09 | 2014-10-20 | 2014-11-05 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129249 | Abihod ES | CATEEL | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-08-18 | 2014-08-18 | 110314S00037 | 14LF0009 | 2014-05-16 | 2014-05-16 | 2014-05-29 | 2014-06-16 | 2014-06-20 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129348 | Anastacio Mamada ES | MANAY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-09-13 | 2014-09-13 | 110314S00019 | 14LF0014 | 2014-06-24 | 2014-07-07 | 2014-07-07 | 2014-07-11 | 2014-07-16 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129445 | Cabagayan ES | TARRAGONA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-08-23 | 2014-08-23 | 110314S00025 | 14LF0015 | 2014-06-01 | 2014-06-05 | 2014-06-16 | 2014-06-19 | 2014-06-25 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129344 | Cayawan ES | MANAY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-13 | 2014-10-13 | 110314S00018 | 14-07-196 | 2014-07-31 | 2014-08-05 | 2014-08-05 | 2014-08-12 | 2014-08-15 | By Administration
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129446 | Cuta ES | TARRAGONA | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2885174.43 |  |  | COMPLETED | 1 | 2014-08-23 | 2014-08-23 | 110314S00023 | 14LF0016 | 2014-06-01 | 2014-06-05 | 2014-06-16 | 2014-06-19 | 2014-06-25 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129263 | Hulid ES | CATEEL | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-08-18 | 2014-08-18 | 110314S00017 | 14LF0009 | 2014-05-16 | 2014-05-16 | 2014-05-29 | 2014-06-16 | 2014-06-20 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129254 | Judge Ernesto Nombrado MPS | CATEEL | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2015-09-25 | 2015-09-24 | 110314S00073 | 15LF0018 | 2015-06-14 | 2015-06-25 | 2015-06-29 | 2015-07-07 | 2015-07-22 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129155 | Kiagbaan ES | BAGANGA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-08-18 | 2014-08-18 | 110314S00032 | 14LF0008 | 2014-05-16 | 2014-05-16 | 2014-05-29 | 2014-06-16 | 2014-06-20 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129353 | Limentuog ES | MANAY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-26 | 2015-04-27 | 110314S00021 | 14-07-195 | 2014-07-31 | 2014-08-12 | 2014-08-13 | 2014-08-22 | 2014-08-28 | By Administration
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129354 | Lingayao PS | MANAY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-09-13 | 2014-09-13 | 110314S00022 | 14LF0014 | 2014-06-24 | 2014-07-07 | 2014-07-07 | 2014-07-11 | 2014-07-16 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129218 | Lucatan ES | CARAGA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-08-21 | 2014-08-21 | 110314S00030 | 14LF0010 | 2014-05-29 | 2014-05-30 | 2014-06-11 | 2014-06-17 | 2014-06-23 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129239 | Magsayap ES | CARAGA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-08-21 | 2014-08-21 | 110314S00028 | 14LF0011 | 2014-05-29 | 2014-05-30 | 2014-06-11 | 2014-06-17 | 2014-06-23 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129456 | Maliongan ES | TARRAGONA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-08-23 | 2014-08-23 | 110314S00033 | 14LF0016 | 2014-06-01 | 2014-06-05 | 2014-06-16 | 2014-06-19 | 2014-06-25 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129338 | Masanguid PS | MANAY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-08-21 | 2014-08-21 | 110314S00034 | 14LF0012 | 2014-05-29 | 2014-05-30 | 2014-06-11 | 2014-06-17 | 2014-06-23 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129241 | Mercedes ES | CARAGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-08-21 | 2014-08-21 | 110314S00027 | 14LF0010 | 2014-05-29 | 2014-05-30 | 2014-06-11 | 2014-06-17 | 2014-06-23 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129457 | Ompao ES | TARRAGONA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-08-23 | 2014-08-23 | 110314S00041 | 14LF0015 | 2014-06-01 | 2014-06-05 | 2014-06-05 | 2014-06-19 | 2014-06-25 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129352 | P. Mandaguio ES | MANAY | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-08-21 | 2014-08-21 | 110314S00020 | 14LF0012 | 2014-05-29 | 2014-05-30 | 2014-06-11 | 2014-06-17 | 2014-06-23 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129459 | P-Basog ES | TARRAGONA | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3780805.49 |  |  | COMPLETED | 1 | 2014-08-23 | 2014-08-23 | 110314S00056 | 14LF0017 | 2014-06-01 | 2014-06-05 | 2014-06-16 | 2014-06-19 | 2014-06-25 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129160 | San Isidro ES | BAGANGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-08-18 | 2014-08-18 | 110314S00031 | 14LF0008 | 2014-05-16 | 2014-05-16 | 2014-05-29 | 2014-06-16 | 2014-06-20 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129245 | San Miguel ES | CARAGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-08-21 | 2014-08-21 | 110314S00026 | 14LF0011 | 2014-05-29 | 2014-05-30 | 2014-06-11 | 2014-06-17 | 2014-06-23 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129226 | San Pedro ES | CARAGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-08-21 | 2014-08-21 | 110314S00035 | 14LF0011 | 2014-05-29 | 2014-05-30 | 2014-06-11 | 2014-06-17 | 2014-06-23 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129161 | San Victor ES | BAGANGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-08-18 | 2014-08-18 | 110314S00024 | 14LF0008 | 2014-05-16 | 2014-05-16 | 2014-05-29 | 2014-06-16 | 2014-06-20 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2014 | K10 (2014) | Region XI | Davao Oriental | 129229 | Tubilan PS | CARAGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-08-21 | 2014-08-21 | 110314S00029 | 14LF0010 | 2014-05-29 | 2014-05-30 | 2014-06-11 | 2014-06-17 | 2014-06-23 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2014 | K10 (2014) | Region XI | Digos City | 129750 | Digos City CES | CITY OF DIGOS (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Digos City | 316303 | Digos City NHS - Balabag HS Annex | CITY OF DIGOS (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-03 | 110214S00067 | 14LD0026 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | LEAMOR CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Digos City | 316304 | Digos City NHS - Soong HS Annex | CITY OF DIGOS (Capital) | 1 | 1 | 4 | 2UNIT 1STY2CL | 2014 K10 BATCH 4B | 3629480.3479 |  |  | COMPLETED | 1 | 2015-12-21 | 2015-12-21 | 110214S00135 | 15LD0067 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-03 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region XI | Digos City | 304400 | Digos City NHS (Davao Del Sur NHS) | CITY OF DIGOS (Capital) | 1 | 1 | 30 | 2UNIT 3STY15CL | 2014 K10 BATCH 3 | 45090823.4375 |  |  | COMPLETED | 1 | 2015-11-30 |  | 110214S00131 | 14LD0057 | 2014-11-24 | 2014-11-25 | 2014-12-16 | 2014-12-19 | 2014-12-29 | LEGACY CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Digos City | 129766 | Don Mariano Marcos ES | CITY OF DIGOS (Capital) | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14115118.3984 |  |  | COMPLETED | 1 | 2015-09-01 | 2015-09-01 | 110214S00130 | 14LD0056 | 2014-11-24 | 2014-11-25 | 2014-12-16 | 2014-12-19 | 2014-12-29 | FGM BUILDERS RESOURCES & DEVELOPMENT CORP.
NC 2014 | K10 (2014) | Region XI | Digos City | 129754 | Lungag ES | CITY OF DIGOS (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-03 | 110214S00066 | 14LD0026 | 2014-06-04 | 2014-06-05 | 2014-06-24 | 2014-07-03 | 2014-07-16 | LEAMOR CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XI | Digos City | 129767 | Pedro S. Garcia ES | CITY OF DIGOS (Capital) | 1 | 1 | 4 | 2UNIT 1STY2CL | 2014 K10 BATCH 4B | 3629480.3479 |  |  | COMPLETED | 1 | 2015-12-21 | 2015-12-21 | 110214S00136 | 15LD0066 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-03 | LTB BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Island Garden City of Samal | 304216 | Anonang National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Island Garden City of Samal | 304220 | Balet NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1837581.3658 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Island Garden City of Samal | 323402 | Del Monte National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Island Garden City of Samal | 304227 | Don Esteban Dasalla National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Island Garden City of Samal | 304236 | Kaputian National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Island Garden City of Samal | 128606 | Mambago-B ES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737081.3658 |  |  | COMPLETED | 1 | 2015-04-10 | 2015-04-10 | 110114S00018 | 14LC0077 | 2014-11-06 | 2014-11-14 | 2014-11-27 | 2014-12-09 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Island Garden City of Samal | 323403 | Nieves Villarica NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4A | 4291899.6094 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Mati City | 129412 | Asuncion Rondina Perez Memorial School | CITY OF MATI (Capital) | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2015-10-16 | 2015-10-16 | 110314S00072 | 15LG0063 | 2015-06-29 | 2015-07-02 | 2015-07-15 | 2015-07-24 | 2015-08-03 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2014 | K10 (2014) | Region XI | Mati City | 304320 | BAGUMBAYAN AGRO-INDUSTRIAL HS | LUPON | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region XI | Mati City | 129324 | Bagumbayan Elementary School | LUPON | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3464886.575 |  |  | COMPLETED | 1 | 2015-10-03 | 2015-10-03 | 110314S00076 | 15LG0053 | 2015-05-18 | 2015-05-20 | 2015-06-11 | 2015-06-25 | 2015-07-06 | JECEL CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region XI | Mati City | 304301 | Banaybanay National High School | BANAYBANAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region XI | Mati City | 129391 | Buso Elementary School | CITY OF MATI (Capital) | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3464886.575 |  |  | COMPLETED | 1 | 2015-10-03 | 2015-10-03 | 110314S00077 | 15LG0054 | 2015-05-18 | 2015-05-20 | 2015-06-11 | 2015-06-25 | 2015-07-06 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2014 | K10 (2014) | Region XI | Mati City | 129329 | Comara T. Manuel Central Elementary School I | LUPON | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2014-11-29 | 2014-11-29 | 110314S00063 | 14LG0025 | 2014-07-02 | 2014-07-04 | 2014-07-17 | 2014-09-12 | 2014-10-01 | LOTRIM CONSTRUCTION, INC.
NC 2014 | K10 (2014) | Region XI | Mati City | 129330 | Comara T. Manuel Central Elementary School II | LUPON | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2014-11-29 | 2014-11-29 | 110314S00064 | 14LG0026 | 2014-07-02 | 2014-07-04 | 2014-07-17 | 2014-09-12 | 2014-10-01 | R.K. ENGINEERING & CONSTRUCTION WORKS
NC 2014 | K10 (2014) | Region XI | Mati City | 129396 | Don Salvador Lopez ES | CITY OF MATI (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region XI | Mati City | 316104 | DON SALVADOR LOPEZ NHS | CITY OF MATI (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region XI | Mati City | 129283 | E. Orencia ES | GOVERNOR GENEROSO | 2 | 1 | 5 | 1STY5CL | 2014 K10 BATCH 4B | 4299392.2448 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 110314S00060 | 14LG0028 | 2014-07-02 | 2014-07-04 | 2014-07-17 | 2014-09-12 | 2014-10-01 | LOTRIM CONSTRUCTION, INC.
NC 2014 | K10 (2014) | Region XI | Mati City | 129290 | Fatima ES | GOVERNOR GENEROSO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region XI | Mati City | 129408 | Fausta Salazar Como Mem. School | CITY OF MATI (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | REVERTED | 0 | 2015-11-22 | 2015-11-22 | 110315S00097 | 15LG0093 | 2015-08-13 | 2015-07-15 | 2015-08-26 | 2015-09-03 | 2015-09-09 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2014 | K10 (2014) | Region XI | Mati City | 129414 | Francisco Hinayon ES | CITY OF MATI (Capital) | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3464886.575 |  |  | COMPLETED | 1 | 2015-10-03 | 2015-10-03 | 110314S00078 | 15LG0054 | 2015-05-18 | 2015-05-20 | 2015-06-11 | 2015-06-25 | 2015-07-06 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2014 | K10 (2014) | Region XI | Mati City | 129291 | Hadji Jamire Musa Elementary School | GOVERNOR GENEROSO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | REVERTED | 0 | 2015-12-07 | 2015-12-07 | 110315S00095 | 15LG0104 | 2015-08-13 | 2015-07-15 | 2015-08-26 | 2015-09-03 | 2015-09-09 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2014 | K10 (2014) | Region XI | Mati City | 129292 | Lavigan ES | GOVERNOR GENEROSO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region XI | Mati City | 316107 | Leandro G. Japos NHS | BANAYBANAY | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 4060805.49 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region XI | Mati City | 304318 | Libudon National High School | CITY OF MATI (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region XI | Mati City | 304321 | Lupon NCHS (Lupon Voc'l. HS - Annex B) | LUPON | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Mati City | 129331 | Mahayahay Elementary School | LUPON | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region XI | Mati City | 304327 | Matiao National High School | CITY OF MATI (Capital) | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3464886.575 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Mati City | 325106 | Mayo National High School | CITY OF MATI (Capital) | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | REVERTED | 0 | 2015-10-15 | 2015-10-15 | 110315S00001 | 15LG0080 | 2015-07-13 | 2015-07-15 | 2015-07-28 | 2015-08-05 | 2015-08-17 | RK STAR ECOENGINEERING
NC 2014 | K10 (2014) | Region XI | Mati City | 129296 | Nangan ES | GOVERNOR GENEROSO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region XI | Mati City | 129296 | Nangan ES | GOVERNOR GENEROSO | 2 | 1 | 5 | 1STY5CL | 2014 K10 BATCH 4B | 4317392.2448 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Mati City | 129298 | Pundaguitan Elementary School | GOVERNOR GENEROSO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region XI | Mati City | 129298 | Pundaguitan Elementary School | GOVERNOR GENEROSO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1831740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Mati City | 129380 | Rabat-Rocamora Mati Central ES I | CITY OF MATI (Capital) | 2 | 1 | 8 | 2UNIT 1STY4CL | 2014 K10 BATCH 3 | 6597709.3848 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Mati City | 129380 | Rabat-Rocamora Mati Central ES I | CITY OF MATI (Capital) | 2 | 1 | 1 | Construction of 2UNIT 1STY4CL & 1UNIT 1STY1CL with toilets attached (additional) | 2014 K10 BATCH 4A | 1510604.1133 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Mati City | 304336 | Sigaboy Agricultural Vocational HS | GOVERNOR GENEROSO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region XI | Mati City | 129286 | Sigaboy CES | GOVERNOR GENEROSO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region XI | Mati City | 129287 | Tandang Sora ES | GOVERNOR GENEROSO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | REVERTED | 0 | 2015-11-22 | 2015-11-22 | 110315S00115 | 15LG0105 | 2015-08-13 | 2015-07-15 | 2015-08-26 | 2015-09-03 | 2015-09-09 | LLM ENTERPRISES
NC 2014 | K10 (2014) | Region XI | Panabo City | 129781 | Cabili ES | CITY OF PANABO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737081.3658 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-03-16 | 110114S00015 | 14LC0062 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Panabo City | 129791 | Concordia A. Sison ES | CITY OF PANABO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1170392.8399 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-03-16 | 110114S00022 | 14LC0062 | 2014-10-27 | 2014-11-07 | 2014-11-18 | 2014-12-14 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Panabo City | 129792 | Dalisay Village ES | CITY OF PANABO | 2 | 1 | 7 | 1STY2CL & 1STY5CL | 2014 K10 BATCH 3 | 5881650.5731 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-05-06 | 110114S00013 | 14LC0063 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Panabo City | 129783 | Gredu ES | CITY OF PANABO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737081.3658 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-05-06 | 110114S00017 | 14LC0063 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Panabo City | 129812 | Little Panay ES | CITY OF PANABO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1837581.3658 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-03-16 | 110114S00024 | 14LC0062 | 2014-10-27 | 2014-11-07 | 2014-11-18 | 2014-12-04 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Panabo City | 316404 | Mabunao National High School | CITY OF PANABO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1958181.3658 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-03-16 | 110114S00027 | 14LC0067 | 2014-10-27 | 2014-11-07 | 2014-11-18 | 2014-12-04 | 2014-12-17 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2014 | K10 (2014) | Region XI | Panabo City | 304407 | Manay National High School | CITY OF PANABO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1170392.8399 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Panabo City | 129784 | Panabo CES | CITY OF PANABO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737081.3658 |  |  | COMPLETED | 1 | 2015-06-24 | 2015-05-06 | 110114S00019 | 14LC0063 | 2014-10-27 | 2014-11-07 | 2014-11-18 | 2014-12-04 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Panabo City | 129785 | Rizal ES | CITY OF PANABO | 2 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 4A | 11277984.375 |  |  | COMPLETED | 1 | 2015-08-28 | 2015-08-28 | 110114S00098 | 14LC0080 | 2014-11-24 | 2014-12-05 | 2014-12-16 | 2015-01-09 | 2015-01-21 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Panabo City | 129786 | Salvacion ES | CITY OF PANABO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737081.3658 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-03-16 | 110114S00020 | 14LC0062 | 2014-10-27 | 2014-11-07 | 2014-11-18 | 2014-12-04 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Panabo City | 129788 | San Vicente ES | CITY OF PANABO | 2 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 3 | 11277984.375 |  |  | COMPLETED | 1 | 2015-07-24 | 2015-07-23 | 110114S00021 | 14LC0068 | 2014-10-27 | 2014-11-20 | 2014-11-18 | 2014-12-04 | 2014-12-17 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Panabo City | 316401 | Southern Davao National High School | CITY OF PANABO | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4392399.6094 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Tagum City | 304238 | La Filipina NHS | CITY OF TAGUM (Capital) | 1 | 1 | 18 | 1STY3CL & 3STY15CL | 2014 K10 BATCH 3 | 25073442.2149 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Tagum City | 128769 | LAURETA ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-30 | 110114S00115 | 15LC0104 | 2015-06-24 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2014 | K10 (2014) | Region XI | Tagum City | 128793 | LUIS L. LINA ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10737093.5547 |  |  | COMPLETED | 1 | 2015-08-13 | 2015-07-13 | 110114S00035 | 14LC0078 | 2014-11-06 | 2014-11-14 | 2014-11-27 | 2014-12-09 | 2014-12-17 | JV: R.R. SEISMUNDO CONSTRUCTION & SUPPLY/DAVAO CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Tagum City | 128771 | MAGUGPO PILOT CENTRAL ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 15 | 3STY15CL | 2014 K10 BATCH 3 | 22545411.7188 |  |  | COMPLETED | 1 | 2015-10-21 | 2015-10-21 | 110114S00028 | 14LC0091 | 2014-12-04 | 2014-12-05 | 2014-12-18 | 2015-01-09 | 2015-01-15 | LEGACY CONSTRUCTION
NC 2014 | K10 (2014) | Region XI | Tagum City | 128779 | NEW BALAMBAN ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-10-31 | 110114S00116 | 15LC0105 | 2015-06-24 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | DAVAO CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Tagum City | 128781 | PAGSABANGAN ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1019642.84 |  |  | COMPLETED | 1 | 2015-08-13 | 2015-06-08 | 110114S00029 | 14LC0078 | 2014-11-06 | 2014-11-14 | 2014-11-27 | 2014-12-09 | 2014-12-17 | JV: R.R. SEISMUNDO CONSTRUCTION & SUPPLY/DAVAO CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Tagum City | 128784 | SUAYBAGUIO-RIÑA ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1737081.3658 |  |  | COMPLETED | 1 | 2015-08-13 | 2015-06-08 | 110114S00030 | 14LC0078 | 2014-11-06 | 2014-11-14 | 2014-11-27 | 2014-12-09 | 2014-12-17 | JV: R.R. SEISMUNDO CONSTRUCTION & SUPPLY/DAVAO CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XI | Tagum City | 304225 | Tagum City National Comprehensive High School | CITY OF TAGUM (Capital) | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 19931783.5938 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Tagum City | 304260 | Tagum City NHS | CITY OF TAGUM (Capital) | 1 | 1 | 20 | 2STY8CL & 3STY12CL | 2014 K10 BATCH 3 | 30077494.1406 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XI | Tagum City | 128798 | VISAYAN VILLAGE CENTRAL ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-24 | 110114S00114 | 15LC0103 | 2015-06-24 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | DAVAO CONCRETE PRODUCTS
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128458 | Alimadmad ES | MONTEVISTA | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110415S00059 | 15LA0119 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-08-10 | DANIMERH CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128423 | Anagase Elementary School | MONKAYO | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 110415S00062 | 15LA0141 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-28 | 2015-08-10 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 315814 | Andap NHS | NEW BATAAN | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | COMPLETED | 1 |  |  | 110415S00120 | 15LA0183 | 2015-09-14 | 2015-09-17 | 2015-09-28 | 2015-10-21 |  | DANIMERH CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304200 | Awao NHS | MONKAYO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2238606 |  |  | COMPLETED | 1 |  |  | 110415S00098 | 15LA0217 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-19 | 2015-10-26 | AB APONESTO CONSTRUCTION, PARTS & SUPPLY
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304176 | Babag NHS | MONKAYO | 1 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3544886.575 |  |  | COMPLETED | 1 |  |  | 110415S00043 | 15LA0079 | 2015-06-16 | 2015-06-22 | 2015-06-30 | 2015-07-07 | 2015-07-20 | LEGACY CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128260 | Bagongon Elementary School | COMPOSTELA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 110415S00110 | 15LA0190 | 2015-09-14 | 2015-09-17 | 2015-09-28 | 2015-10-09 | 2015-10-21 | AB APONESTO CONSTRUCTION, PARTS & SUPPLY
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128379 | Bahi ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | COMPLETED | 1 |  |  | 110415S00117 | 15LA0198 | 2015-09-14 | 2015-09-17 | 2015-09-28
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 315819 | Bango NHS | COMPOSTELA | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110415S00049 | 15LA0087 | 2015-07-02 | 2015-07-03 | 2015-09-02
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304177 | Bantacan NHS | NEW BATAAN | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3767969 |  |  | COMPLETED | 1 |  |  | 110415S00095 | 15LA0214 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-19 | 2015-10-26 | DANIMERH CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 204019 | Cabanggatan PS | MONTEVISTA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 110415S00115 | 15LA0197 | 2015-09-14 | 2015-09-17 | 2015-09-28 | 2015-10-09 | 2015-10-26 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 304180 | Camanlangan NHS | NEW BATAAN | 1 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 3 | 12771310.093 |  |  | COMPLETED | 1 |  |  | 110415S00053 | 15LA0149 | 2015-07-14 | 2015-07-15 | 2015-07-27 | 2015-07-29 | 2015-08-14 | FFJJ CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128381 | Caragan ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2238606.04 |  |  | COMPLETED | 1 |  |  | 110415S00108 | 15LA0203 | 2015-09-14 | 2015-09-17 | 2015-09-28
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304181 | Compostela NHS | COMPOSTELA | 1 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 1 | 15321327.92 |  |  | COMPLETED | 1 |  |  | 110415S00048 | 15LA0150 | 2015-07-14 | 2015-07-15 | 2015-07-27 | 2015-07-28 | 2015-10-16 | LEGACY CONSTRUCTION
NC 2015 | TECHVOC (2015) | Region XI | Compostela Valley | 304181 | Compostela NHS | COMPOSTELA | 1 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4979098.54 |  |  | COMPLETED | 1 |  |  | 110415S00126 | 15LA0200 | 2015-09-14 | 2015-09-17 | 2015-09-28 | 2015-10-09 | 2015-10-21 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 315820 | Compostela NHS-Corazon C. Aquino HS-Annex | COMPOSTELA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | COMPLETED | 1 |  |  | 110415S00121 | 15LA0184 | 2015-09-14 | 2015-09-17 | 2015-09-28 | 2015-10-30 | 2015-11-04 | TWINA BUILDERS AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304184 | Consuelo M. Valderrama NHS | COMPOSTELA | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110415S00047 | 15LA0086 | 2015-07-02 | 2015-07-03 | 2015-09-02 | 2015-09-08 | 2015-11-16 | By Administration
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 204010 | Depot ES | MONKAYO | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110415S00060 | 15LA0147 | 2015-07-14 | 2015-07-15 | 2015-07-27 | 2015-07-31 | 2015-11-11 | DANIMERH CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 204010 | Depot ES | MONKAYO | 1 |  | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110415S00066 | 15LA0148 | 2015-07-14 | 2015-07-15 | 2015-07-27 | 2015-07-31 | 2015-11-11 | O. G. SANTOS CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304187 | Gabi NHS | COMPOSTELA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 |  |  | 110415S00046 | 15LA0116 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-08-10 | JV: AB APONESTO CONSTRUCTION, PARTS & SUPPLY/R.R. SEISMUNDO CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128384 | Lahi ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 110415S00063 | 15LA0129 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-28 | 2015-08-10 | DAVAO CONCRETE PRODUCTS
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 315813 | Langgawisan NHS | MARAGUSAN (SAN MARIANO) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2556606 |  |  | COMPLETED | 1 |  |  | 110415S00085 | 15LA0219
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304182 | Mangayon NHS | COMPOSTELA | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 |  |  | 110415S00045 | 15LA0126 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-28 | 2015-08-10 | DTV CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128521 | Manurigao ES | NEW BATAAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2288606.04 |  |  | COMPLETED | 1 |  |  | 110415S00058 | 15LA0090 | 2015-07-02 | 2015-07-03 | 2015-09-02 |  |  | By Administration
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128521 | Manurigao ES | NEW BATAAN | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 110415S00057 | 15LA0091 | 2015-07-02 | 2015-07-03 | 2015-09-02 |  |  | By Administration
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 304196 | Maparat NHS | COMPOSTELA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110415S00056 | 15LA0145 | 2015-07-14 | 2015-07-15 | 2015-07-27 | 2015-11-02 | 2015-11-11 | DAVAO CONCRETE PRODUCTS
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304196 | Maparat NHS | COMPOSTELA | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3817969 |  |  | COMPLETED | 1 |  |  | 110415S00096 | 15LA0213 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-19 | 2015-10-26 | DAVAO CONCRETE PRODUCTS
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304197 | Mapawa NHS | MARAGUSAN (SAN MARIANO) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 4863412 |  |  | COMPLETED | 1 |  |  | 110415S00097 | 15LA0237 | 2015-09-15 | 2015-09-17 | 2015-10-26 | 2015-11-03 | 2015-11-11 | DINGO BUILDERS AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304198 | Maragusan NHS | MARAGUSAN (SAN MARIANO) | 1 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5356910.09 |  |  | COMPLETED | 1 |  |  | 110415S00028 | 15LA0101 | 2015-07-05 | 2015-07-10 | 2015-07-21 | 2015-07-28 | 2015-08-14 | DAVAO CONCRETE PRODUCTS
NC 2015 | TECHVOC (2015) | Region XI | Compostela Valley | 304198 | Maragusan NHS | MARAGUSAN (SAN MARIANO) | 1 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7398647.81 |  |  | COMPLETED | 1 |  |  | 110415S00124 | 15LA0179 | 2015-09-14 | 2015-09-17 | 2015-09-28 | 2015-10-09 | 2015-10-23 | DAVAO CONCRETE PRODUCTS
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 204021 | Maugat PS | COMPOSTELA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 3112592.44 |  |  | COMPLETED | 1 |  |  | 110415S00061 | 15LA0133 | 2015-07-10 | 2015-07-13 | 2015-09-02
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304204 | Mayaon NHS | MONTEVISTA | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2700828.124 |  |  | COMPLETED | 1 |  |  | 110415S00030 | 15LA0125 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-08-24 | 2015-09-01 | GOLDEN VIDO BUILDERS & SUPPLY
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304199 | Monkayo NHS | MONKAYO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110415S00037 | 15LA0114 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-08-10 | AB APONESTO CONSTRUCTION, PARTS & SUPPLY
NC 2015 | TECHVOC (2015) | Region XI | Compostela Valley | 304199 | Monkayo NHS | MONKAYO | 1 | 1 | 1 | Construction of 1UNIT Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1 |  |  | 110415S00128 | 15LA0199 | 2015-09-14 | 2015-09-17 | 2015-09-28 | 2015-10-09 | 2015-10-21 | AB APONESTO CONSTRUCTION, PARTS & SUPPLY
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 315801 | Monkayo NHS- Casoon NHS Annex | MONKAYO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2238606 |  |  | COMPLETED | 1 |  |  | 110415S00087 | 15LA0216 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-19 | 2015-10-26 | TWO DEGREES CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304202 | Montevista NHS | MONTEVISTA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110415S00021 | 15LA0096 | 2015-07-05 | 2015-07-10 | 2015-07-21 | 2015-07-28 | 2015-08-17 | JV: R.R. SEISMUNDO CONSTRUCTION & SUPPLY/AB APONESTO CONSTRUCTION, PARTS & SUPPLY
NC 2015 | TECHVOC (2015) | Region XI | Compostela Valley | 304202 | Montevista NHS | MONTEVISTA | 1 | 1 | 1 | Construction of 1UNIT Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1 |  |  | 110415S00125 | 15LA0205 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-09 | 2015-10-23 | DANIMERH CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304203 | Montevista NHS-Annex (DNAS Campus) | MONTEVISTA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 3977212 |  |  | COMPLETED | 1 |  |  | 110415S00081 | 15LA0228 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-19 | 2015-10-26 | AB APONESTO CONSTRUCTION, PARTS & SUPPLY
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 315815 | New Albay NHS | MARAGUSAN (SAN MARIANO) | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2800828.124 |  |  | COMPLETED | 1 |  |  | 110415S00013 | 15LA0122 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-28 | 2015-08-10 | DTV CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304206 | New Bataan NHS | NEW BATAAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1 |  |  | 110415S00014 | 15LA0111 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-27 | 2015-08-25 | JV: R.R. SEISMUNDO CONSTRUCTION & SUPPLY/AB APONESTO CONSTRUCTION, PARTS & SUPPLY
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128392 | New Katipunan ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | COMPLETED | 1 |  |  | 110415S00116 | 15LA0195 | 2015-09-14 | 2015-09-17 | 2015-09-28 | 2015-10-09 | 2015-10-21 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304207 | Paloc NHS | MARAGUSAN (SAN MARIANO) | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2770828.124 |  |  | COMPLETED | 1 |  |  | 110415S00015 | 15LA0123 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-08-10 | 2015-08-14 | AB APONESTO CONSTRUCTION, PARTS & SUPPLY
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304201 | Pasian NHS | MONKAYO | 1 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5086910.09 |  |  | COMPLETED | 1 |  |  | 110415S00042 | 15LA0102 | 2015-07-05 | 2015-07-10 | 2015-07-21 | 2015-08-12 | 2015-08-17 | AB APONESTO CONSTRUCTION, PARTS & SUPPLY
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304183 | San Miguel NHS | COMPOSTELA | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2840828.124 |  |  | COMPLETED | 1 |  |  | 110415S00050 | 15LA0124 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-29 | 2015-08-14 | AB APONESTO CONSTRUCTION, PARTS & SUPPLY
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128478 | San Vicente ES | MONTEVISTA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 110415S00119 | 15LA0192 | 2015-09-08 | 2015-09-17 | 2015-09-28 | 2015-10-09 | 2015-10-21 | AB APONESTO CONSTRUCTION, PARTS & SUPPLY
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128399 | Saranga ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 110415S00052 | 15LA0139 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-29 | 2015-08-14 | TWO DEGREES CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304210 | Siocon NHS | COMPOSTELA | 1 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1 |  |  | 110415S00051 | 15LA0078 | 2015-06-11 | 2015-06-22 | 2015-06-30 | 2015-07-07 | 2015-07-20 | AB APONESTO CONSTRUCTION, PARTS & SUPPLY
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128454 | Totoy ES | MONKAYO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | COMPLETED | 1 |  |  | 110415S00099 | 15LA0196 | 2015-09-14 | 2015-09-17 | 2015-09-28 | 2015-10-09 | 2015-10-21 | AB APONESTO CONSTRUCTION, PARTS & SUPPLY
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304212 | Tubo-Tubo NHS | MONKAYO | 1 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3594886.575 |  |  | COMPLETED | 1 |  |  | 110415S00026 | 15LA0088 | 2015-07-02 | 2015-07-03 | 2015-09-02 | 2015-10-14 | 2015-10-16 | By Administration
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304213 | Tupaz NHS | MARAGUSAN (SAN MARIANO) | 1 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3614886.575 |  |  | COMPLETED | 1 |  |  | 110415S00012 | 15LA0089 | 2015-07-02 | 2015-07-03 | 2015-09-02 |  | 2015-10-22 | By Administration
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 315808 | Ulip NHS | MONKAYO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2188606 |  |  | COMPLETED | 1 |  |  | 110415S00086 | 15LA0235 | 2015-09-15 | 2015-09-17 | 2015-10-26 | 2015-11-03 | 2015-11-12 | TWO DEGREES CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304214 | Union NHS | MONKAYO | 1 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5086910.09 |  |  | COMPLETED | 1 |  |  | 110415S00022 | 15LA0103 | 2015-07-06 | 2015-07-10 | 2015-07-21 | 2015-07-28 | 2015-08-10 | DTV CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 315809 | Union NHS - Mt. Diwata HS Annex | MONKAYO | 1 | 1 | 6 | 1STY6CL (Toilet Attached) | 2015 K10 BATCH 3 | 5472651.88 |  |  | COMPLETED | 1 |  |  | 110415S00054 | 15LA0105 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-08-10 | DINGO BUILDERS AND SUPPLY
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 315809 | Union NHS - Mt. Diwata HS Annex | MONKAYO | 1 |  | 6 | 1STY6CL (Toilet Attached) | 2015 K10 BATCH 3 | 5472651.88 |  |  | COMPLETED | 1 |  |  | 110415S00055 | 15LA0106 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-08-10 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 315809 | Union NHS-Mt.Diwata HS Annex | MONKAYO | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 5635185 |  |  | COMPLETED | 1 |  |  | 110415S00091 | 15LA0182 | 2015-09-14 | 2015-09-17
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128279 | Amorcruz ES | LAAK (SAN VICENTE) | 2 | 1 | 6 | 1STY6CL (Toilet Attached) | 2015 K10 BATCH 3 | 5672651.88 |  |  | COMPLETED | 1 |  |  | 110415S00064 | 15LA0107 | 2015-07-09 | 2015-07-10 | 2015-08-26
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128279 | Amorcruz ES | LAAK (SAN VICENTE) | 2 |  | 6 | 1STY6CL (Toilet Attached) | 2015 K10 BATCH 3 | 5472651.88 |  |  | COMPLETED | 1 |  |  | 110415S00073 | 15LA0108 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-27 | 2015-08-25 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304172 | Andili NHS | MAWAB | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110415S00027 | 15LA0095 | 2015-07-05 | 2015-07-10 | 2015-07-21 | 2015-07-28 | 2015-08-10 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304173 | Anibongan NHS | MACO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2013606 |  |  | COMPLETED | 1 |  |  | 110415S00084 | 15LA0218 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-19 | 2015-10-26 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128363 | Anislagan ES | MACO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 3877212.08 |  |  | COMPLETED | 1 |  |  | 110415S00103 | 15LA0208 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-09 | 2015-10-23 | DANIMERH CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304174 | Anitapan NHS | MABINI (DOÑA ALICIA) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 3987212 |  |  | COMPLETED | 1 |  |  | 110415S00082 | 15LA0229
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304175 | Araibo NHS | PANTUKAN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110415S00020 | 15LA0085 | 2015-07-02 | 2015-07-03 | 2015-08-11 | 2015-08-14 | 2015-08-20 | LLM CONCRETE PRODUCTS
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304178 | Bayabas NHS | NABUNTURAN (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1988606 |  |  | COMPLETED | 1 |  |  | 110415S00090 | 15LA0220 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-19 | 2015-10-26 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128285 | Bayanihan ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2188606.04 |  |  | COMPLETED | 1 |  |  | 110415S00101 | 15LA0209 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-09 | 2015-10-21 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128536 | Biasong ES | PANTUKAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 110415S00069 | 15LA0131 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-28 | 2015-08-14 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304179 | Bongabong NHS | PANTUKAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 110415S00019 | 15LA0110 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-09-09 | DANIMERH CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128289 | Bullokan ES | LAAK (SAN VICENTE) | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 3042592.44 |  |  | COMPLETED | 1 |  |  | 110415S00079 | 15LA0140 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-29 | 2015-09-01 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128292 | Concepcion ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 4127212.08 |  |  | COMPLETED | 1 |  |  | 110415S00118 | 15LA0206 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-16 | 2015-10-26 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128294 | Datu Davao ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 4177212.08 |  |  | COMPLETED | 1 |  |  | 110415S00107 | 15LA0225 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-09 | 2015-10-23 | DAVAO CONCRETE PRODUCTS
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304185 | Don Vicente Romualdez NHS | LAAK (SAN VICENTE) | 2 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5436910.09 |  |  | COMPLETED | 1 |  |  | 110415S00018 | 15LA0081 | 2015-06-16 | 2015-06-22 | 2015-06-30 | 2015-07-16 | 2015-07-20 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128333 | Don William Gemperle ES | MABINI (DOÑA ALICIA) | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 3002592.44 |  |  | COMPLETED | 1 |  |  | 110415S00076 | 15LA0128 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-28 | 2015-08-10 | EXACT CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128347 | Elizalde ES | MACO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 3877212.08 |  |  | COMPLETED | 1 |  |  | 110415S00104 | 15LA0207 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-09 | 2015-10-21 | ZPM GENERAL MERCHANDISE
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304186 | Elizalde NHS | MACO | 2 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5206910.09 |  |  | COMPLETED | 1 |  |  | 110415S00017 | 15LA0080 | 2015-06-16 | 2015-06-22 | 2015-06-30 | 2015-07-10 | 2015-07-20 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128300 | Inakayan ES | LAAK (SAN VICENTE) | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 3072592.44 |  |  | COMPLETED | 1 |  |  | 110415S00071 | 15LA0092 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-28 | 2015-08-10 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128300 | Inakayan ES | LAAK (SAN VICENTE) | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 110415S00078 | 15LA0138 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-28 | 2015-08-10 | DTV CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 204023 | Inupuan ES | NABUNTURAN (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110415S00070 | 15LA0120 | 2015-07-09 | 2015-07-10
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 315806 | Kao NHS | NABUNTURAN (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110415S00016 | 15LA0097 | 2015-07-05 | 2015-07-10 | 2015-07-21 | 2015-08-06 | 2015-08-10 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304188 | Kapatagan NHS | LAAK (SAN VICENTE) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 |  |  | 110415S00025 | 15LA0117 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-08-10 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128304 | Kidawa ES | LAAK (SAN VICENTE) | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 3152592.44 |  |  | COMPLETED | 1 |  |  | 110415S00106 | 15LA0201 | 2015-09-14 | 2015-09-17 | 2015-09-28 | 2015-10-09 | 2015-10-21 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304190 | Kidawa NHS | LAAK (SAN VICENTE) | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 3040828.124 |  |  | COMPLETED | 1 |  |  | 110415S00024 | 15LA0127 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-28 | 2015-09-07 | CHARIFER BUILDERS, INC.
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128308 | Laak CES | LAAK (SAN VICENTE) | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 16629930.102 |  |  | COMPLETED | 1 |  |  | 110415S00105 | 15LA0181 | 2015-09-14 | 2015-09-17 | 2015-09-28 | 2015-10-09 | 2015-10-21 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304189 | Laak NHS | LAAK (SAN VICENTE) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 110415S00023 | 15LA0118 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-08-10 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 204003 | Langgam ES | MACO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 110415S00067 | 15LA0134 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-11-09 | 2015-11-17 | DTV CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 204003 | Langgam ES | MACO | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 110415S00072 | 15LA0093 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-11-09 | 2015-11-17 | DTV CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304191 | Lorenzo S. Sarmiento Sr. NHS | MAWAB | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 |  |  | 110415S00029 | 15LA0115 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-08-10 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304192 | Mabini NHS | MABINI (DOÑA ALICIA) | 2 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5086910.09 |  |  | COMPLETED | 1 |  |  | 110415S00031 | 15LA0104 | 2015-07-05 | 2015-07-10 | 2015-07-21 | 2015-07-28 | 2015-08-10 | EXACT CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128353 | Maco CES | MACO | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 18958012.9142 |  |  | COMPLETED | 1 |  |  | 110415S00113 | 15LA0186 | 2015-09-14 | 2015-09-17 | 2015-09-28 | 2015-10-09 | 2015-10-21 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304193 | Maco NHS | MACO | 2 | 1 | 8 | 2STY4CL | 2015 SHS BATCH 5 | 12638675 |  |  | COMPLETED | 1 |  |  | 110415S00083 | 15LA0180 | 2015-09-14 | 2015-09-17 | 2015-12-09
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128354 | Magangit ES | MACO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 110415S00075 | 15LA0136 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-29 | 2015-08-14 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 315807 | Magnaga NHS | PANTUKAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110415S00032 | 15LA0109 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-08-10 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304194 | Mainit NHS | NABUNTURAN (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110415S00033 | 15LA0100 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-08-10 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304195 | Manat NHS | NABUNTURAN (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110415S00034 | 15LA0099 | 2015-07-05 | 2015-07-10 | 2015-07-21 | 2015-07-28 | 2015-08-10 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128550 | Maubog ES | PANTUKAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 110415S00109 | 15LA0191 | 2015-09-14 | 2015-09-17 | 2015-09-28 | 2015-10-09 | 2015-10-26 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128317 | Melale ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | COMPLETED | 1 |  |  | 110415S00114 | 15LA0189 | 2015-09-14 | 2015-09-17 | 2015-09-28 | 2015-10-09 | 2015-10-23 | DAVAO CONCRETE PRODUCTS
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 315804 | Melale NHS | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 4027212 |  |  | COMPLETED | 1 |  |  | 110415S00092 | 15LA0226 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-19 | 2015-10-26 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304205 | Nabunturan NCHS | NABUNTURAN (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110415S00044 | 15LA0113 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-08-10 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | TECHVOC (2015) | Region XI | Compostela Valley | 304205 | Nabunturan NCHS | NABUNTURAN (Capital) | 2 | 1 | 1 | Construction of 1UNIT Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1 |  |  | 110415S00127 | 15LA0224 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-09 | 2015-10-21 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 315816 | Napnapan NHS | PANTUKAN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110415S00036 | 15LA0084 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-08-10 | 2015-08-14 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128356 | New Barili ES | MACO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 110415S00074 | 15LA0130
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128319 | New Bethlehem ES | LAAK (SAN VICENTE) | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 3042592.44 |  |  | COMPLETED | 1 |  |  | 110415S00077 | 15LA0135 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-29 | 2015-09-01 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 315811 | New Leyte NHS | MACO | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110415S00068 | 15LA0146 | 2015-07-14 | 2015-07-15 | 2015-07-27 | 2015-08-10 | 2015-08-17 | TWO DEGREES CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 315811 | New Leyte NHS | MACO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 110415S00093 | 15LA0238 | 2015-09-13 | 2015-09-17 | 2015-10-26 | 2015-11-05 | 2015-11-11 | TWO DEGREES CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 315818 | New Sibonga NHS | NABUNTURAN (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1968606 |  |  | COMPLETED | 1 |  |  | 110415S00088 | 15LA0221 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-19 | 2015-10-26 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 315821 | NNCHS-Magsaysay HS Annex | NABUNTURAN (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 |  |  | 110415S00122 | 15LA0222 | 2015-09-14 | 2015-09-17 | 2015-09-28 | 2015-10-19 | 2015-10-26 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 315802 | Nuevo Iloco NHS | MAWAB | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110415S00038 | 15LA0121 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-08-10 | 2015-08-14 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304208 | Pantukan NHS | PANTUKAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 110415S00039 | 15LA0112 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-08-10 | DANIMERH CONSTRUCTION & SUPPLY
NC 2015 | TECHVOC (2015) | Region XI | Compostela Valley | 304208 | Pantukan NHS | PANTUKAN | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4879098.54 |  |  | COMPLETED | 1 |  |  | 110415S00123 | 15LA0202 | 2015-09-14 | 2015-09-17 | 2015-09-28 | 2015-10-16 | 2015-10-26 | DANIMERH CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 315805 | Pindasan NHS | MABINI (DOÑA ALICIA) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 |  |  | 110415S00040 | 15LA0098 | 2015-07-05 | 2015-07-10 | 2015-07-21 | 2015-07-28 | 2015-08-10 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 315812 | San Antonio NHS | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110415S00041 | 15LA0083 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-28 | 2015-08-10 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128498 | San Vicente ES | NABUNTURAN (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 110415S00100 | 15LA0193 | 2015-09-14 | 2015-09-17 | 2015-09-28 | 2015-10-21 | 2015-11-10 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128420 | Tabontabon ES | MAWAB | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 110415S00080 | 15LA0132 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-29 | 2015-08-14 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128376 | Tagbaros ES | MACO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 110415S00112 | 15LA0188 | 2015-09-14 | 2015-09-17 | 2015-09-28 | 2015-10-09 | 2015-10-21 | DINGO BUILDERS AND SUPPLY
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128560 | Tagdangua ES | PANTUKAN | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110415S00102 | 15LA0187 | 2015-09-28 | 2015-09-17 | 2015-09-28 | 2015-10-09 | 2015-10-21 | DANIMERH CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304209 | Tagugpo NHS | PANTUKAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 2902592 |  |  | COMPLETED | 1 |  |  | 110415S00094 | 15LA0223 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-19 | 2015-10-26 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 304211 | Tambongon NHS | PANTUKAN | 2 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5166910.09 |  |  | COMPLETED | 1 |  |  | 110415S00035 | 15LA0082 | 2015-06-16 | 2015-06-22 | 2015-06-30 | 2015-07-10 | 2015-07-20 | RCBAR BUILDERS
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128377 | Teresa ES | MACO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 110415S00111 | 15LA0194
NC 2015 | SHS (2015) | Region XI | Compostela Valley | 315803 | Tuboran NHS | MAWAB | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 3877212 |  |  | COMPLETED | 1 |  |  | 110415S00089 | 15LA0210 | 2015-09-15 | 2015-09-17 | 2015-09-29 | 2015-10-19 | 2015-10-26 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | K10 (2015) | Region XI | Compostela Valley | 128326 | Tuk-An ES | LAAK (SAN VICENTE) | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 3042592.44 |  |  | COMPLETED | 1 |  |  | 110415S00065 | 15LA0137 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-28 | 2015-09-01 | DAVAO CONCRETE PRODUCTS
NC 2015 | K10 (2015) | Region XI | Davao City | 129711 | A. Mabini Elementary School | DAVAO CITY | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 3 | 22152343.62 |  |  | COMPLETED | 1 |  |  | 110615S00099 | 15LB0131 | 2015-09-22 | 2015-09-22 | 2015-10-27 | 2015-12-02 | 2015-12-16 | FFJJ CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Davao City | 129712 | Bago ES | DAVAO CITY | 1 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10492131.51 |  |  | COMPLETED | 1 |  |  | 110615S00127 | 110615S00127 | 2015-11-14 | 2015-11-13 | 2015-11-25 | 2015-12-28
NC 2015 | K10 (2015) | Region XI | Davao City | 129713 | Baliok ES | DAVAO CITY | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110615S00089 | 15LB0122 | 2015-09-22 | 2015-09-22 | 2015-10-06 | 2015-11-06 | 2015-11-19 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | K10 (2015) | Region XI | Davao City | 129715 | Catalunan Grande ES | DAVAO CITY | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00131 | 15LB0165 | 2015-12-19 | 2015-12-17 | 2015-12-29
NC 2015 | K10 (2015) | Region XI | Davao City | 129716 | Catalunan Pequeno Elementary School | DAVAO CITY | 1 | 1 | 12 | 3STY12CL | 2015 K10 BATCH 6 | 18297268.79 |  |  | COMPLETED | 1 |  |  | 110615S00142 | 15LB0170 | 2015-11-19 | 2015-11-13
NC 2015 | SHS (2015) | Region XI | Davao City | 316202 | Catalunan Pequeno National High School | DAVAO CITY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 110615S00049 | 15LB0073 | 2015-08-08 | 2015-08-06 | 2015-08-18 | 2015-09-15 | 2015-10-01 | LEAMOR CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region XI | Davao City | 129555 | Cesareo Villa-Abrille ES | DAVAO CITY | 1 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 6 | 26952469.42 |  |  | COMPLETED | 1 |  |  | 110615S00125 | 15LB0160 | 2015-12-19 | 2015-12-17 | 2015-12-29
NC 2015 | K10 (2015) | Region XI | Davao City | 129555 | Cesareo Villa-Abrille ES | DAVAO CITY | 1 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 30045037.68 |  |  | COMPLETED | 1 |  |  | 110615S00133 | 15LB0167 | 2015-12-19 | 2015-12-17 | 2015-12-29
NC 2015 | SHS (2015) | Region XI | Davao City | 304359 | Daniel R. Aguinaldo NHS (Matina NHS) | DAVAO CITY | 1 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15141327.92 |  |  | REVERTED | 0
NC 2015 | K10 (2015) | Region XI | Davao City | 129639 | Diego Silang ES | DAVAO CITY | 1 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 3 | 15121327.92 |  |  | REVERTED | 0 |  |  | 110615S00092 | 15LB0129 | 2015-12-18 | 2015-12-17 | 2015-12-29
NC 2015 | K10 (2015) | Region XI | Davao City | 129696 | Don Francisco S. Dizon Sr., Elementary School | DAVAO CITY | 1 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 3 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 110615S00091 | 15LB0128 | 2015-09-22 | 2015-09-22 | 2015-10-27 | 2015-12-23
NC 2015 | K10 (2015) | Region XI | Davao City | 129556 | Dona Pilar L. Marfori ES | DAVAO CITY | 1 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 3 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 110615S00093 | 15LB0130 | 2015-09-22 | 2015-09-22 | 2015-10-06 | 2015-11-06 | 2015-11-19 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | K10 (2015) | Region XI | Davao City | 304365 | Erico T. Nograles NHS | DAVAO CITY | 1 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 3 | 31102890.27 |  |  | COMPLETED | 1 |  |  | 110615S00088
NC 2015 | SHS (2015) | Region XI | Davao City | 304378 | GOV. VICENTE DUTERTE NATIONAL HIGH SCHOOL | DAVAO CITY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 110615S00050 | 15LB0074 | 2015-08-08 | 2015-08-06 | 2015-08-18 | 2015-09-08 | 2015-09-24 | MARK ANTHONY CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao City | 304377 | JESUS J. SORIANO NATIONAL HIGH SCHOOL | DAVAO CITY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 110615S00051 | 15LB0075 | 2015-08-08 | 2015-08-06 | 2015-08-18 | 2015-10-02 | 2015-10-15 | O. G. SANTOS CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Davao City | 129720 | Jose Bastida ES | DAVAO CITY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 110615S00140 | 15LB0169 | 2015-12-19 | 2015-12-17 | 2015-12-29
NC 2015 | K10 (2015) | Region XI | Davao City | 129699 | Lapu Lapu ES | DAVAO CITY | 1 | 1 | 12 | 3STY12CL | 2015 K10 BATCH 3 | 18222268.79 |  |  | COMPLETED | 1 |  |  | 110615S00090 | 110615S00090 | 2015-11-26 | 2015-11-26 | 2015-12-08
NC 2015 | K10 (2015) | Region XI | Davao City | 129721 | Leon A. Garcia Sr. ES | DAVAO CITY | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22277343.62 |  |  | COMPLETED | 1 |  |  | 110615S00132 | 110615S00132 | 2015-11-16 | 2015-11-13 | 2015-11-26 | 2015-12-28
NC 2015 | SHS (2015) | Region XI | Davao City | 304375 | MAA NATIONAL HIGH SCHOOL | DAVAO CITY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10437131.51 |  |  | COMPLETED | 1 |  |  | 110615S00052 | 15LB0076 | 2015-08-08 | 2015-08-06 | 2015-08-18 | 2015-09-08 | 2015-09-24 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | SHS (2015) | Region XI | Davao City | 304376 | Mabini NHS | DAVAO CITY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10437131.51 |  |  | COMPLETED | 1 |  |  | 110615S00053 | 15LB0077 | 2015-08-08 | 2015-08-06 | 2015-08-18 | 2015-10-05 | 2015-10-19 | LEAMOR CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region XI | Davao City | 129646 | Magtuod ES | DAVAO CITY | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 12743675.2761 |  |  | COMPLETED | 1 |  |  | 110615S00109 | 15LB0149 | 2015-12-19 | 2015-12-17 | 2015-12-29
NC 2015 | K10 (2015) | Region XI | Davao City | 129648 | Matina CES | DAVAO CITY | 1 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 6 | 31277890.27 |  |  | COMPLETED | 1 |  |  | 110615S00111 | 15LB0150 | 2015-12-03 | 2015-12-03
NC 2015 | K10 (2015) | Region XI | Davao City | 129649 | Matina Pangi ES | DAVAO CITY | 1 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 6 | 15271327.92 |  |  | COMPLETED | 1 |  |  | 110615S00112 | 15LB151 | 2015-12-19 | 2015-12-17 | 2015-12-29
NC 2015 | K10 (2015) | Region XI | Davao City | 129650 | New Matina ES | DAVAO CITY | 1 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4637048.49 |  |  | COMPLETED | 1 |  |  | 110615S00124 | 15LB0159 | 2015-12-18 | 2015-12-15 | 2015-12-28
NC 2015 | K10 (2015) | Region XI | Davao City | 129700 | San Juan ES | DAVAO CITY | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22302343.62 |  |  | COMPLETED | 1 |  |  | 110615S00119 | 110615S00119 | 2015-11-14 | 2015-11-13 | 2015-11-25 | 2015-12-23
NC 2015 | K10 (2015) | Region XI | Davao City | 129723 | San Lorenzo ES | DAVAO CITY | 1 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10517131.51 |  |  | COMPLETED | 1 |  |  | 110615S00120 | 110615S00120 | 2015-11-14 | 2015-11-13 | 2015-11-25 | 2015-12-28
NC 2015 | K10 (2015) | Region XI | Davao City | 129701 | San Roque CES | DAVAO CITY | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22332343.62 |  |  | COMPLETED | 1 |  |  | 110615S00121 | 110615S00121 | 2015-12-21 | 2015-12-08 | 2015-12-21
NC 2015 | SHS (2015) | Region XI | Davao City |  | SHS within CP Garcia ES (formerly in Sta. Ana ES) | DAVAO CITY | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31202958 |  |  | COMPLETED | 1 |  |  | 110615S00100 | 110615S00100 | 2015-11-16 | 2015-11-13 | 2015-11-26 | 2015-12-29
NC 2015 | SHS (2015) | Region XI | Davao City |  | SHS within SIR ES | DAVAO CITY | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Davao City | 304396 | Talomo NHS | DAVAO CITY | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 14917518.84 |  |  | COMPLETED | 1 |  |  | 110615S00054 | 15LB0078 | 2015-09-08 | 2015-09-10 | 2015-09-22 | 2015-10-06 | 2015-10-20 | MEGILA CONSTRUCTION DEVELOPMENT AND SUPPLY
NC 2015 | K10 (2015) | Region XI | Davao City | 129476 | A. Pichon Jr. ES | DAVAO CITY | 2 | 1 | 3 | 3STY3CL | 2015 K10 BATCH 6 | 6653472.88 |  |  | COMPLETED | 1 |  |  | 110615S00126 | 15LB0161 | 2015-12-18 | 2015-12-15 | 2015-12-28
NC 2015 | K10 (2015) | Region XI | Davao City | 129476 | A. Pichon Jr. ES | DAVAO CITY | 2 |  | 9 | 3STY9CL | 2015 K10 BATCH 3 | 15121327.92 |  |  | COMPLETED | 1 |  |  | 110615S00077 | 15LB0133 | 2015-09-22 | 2015-09-22 | 2015-10-27 | 2015-12-02 | 2015-12-16 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao City | 304341 | ALEJANDRA L. NAVARRO NHS | DAVAO CITY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10432131.51 |  |  | COMPLETED | 1 |  |  | 110615S00055 | 15LB0079 | 2015-08-08 | 2015-08-06 | 2015-08-18 | 2015-10-05 | 2015-10-19 | MEGILA CONSTRUCTION DEVELOPMENT AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao City | 316201 | Bernardino B. Bosque NHS | DAVAO CITY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 110615S00056 | 15LB0080 | 2015-08-08 | 2015-08-06 | 2015-08-18 | 2015-09-29
NC 2015 | SHS (2015) | Region XI | Davao City | 304345 | Bernardo D. Carpio National High School | DAVAO CITY | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 14947518.84 |  |  | COMPLETED | 1 |  |  | 110615S00057 | 15LB0081 | 2015-09-08 | 2015-09-10 | 2015-09-22 | 2015-10-06 | 2015-10-20 | MEGILA CONSTRUCTION DEVELOPMENT AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao City | 304349 | Binowang National High School | DAVAO CITY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00058 | 15LB0082 | 2015-08-18 | 2015-08-18 | 2015-09-03 | 2015-10-02 | 2015-10-15 | MARK ANTHONY CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XI | Davao City | 129507 | Cabantian ES | DAVAO CITY | 2 | 1 | 15 | 3STY15CL | 2015 K10 BATCH 6 | 21733013.45 |  |  | COMPLETED | 1 |  |  | 110615S00129 | 15LB0163 | 2015-12-19 | 2015-12-17 | 2015-12-29
NC 2015 | K10 (2015) | Region XI | Davao City | 129507 | Cabantian ES | DAVAO CITY | 2 | 1 | 12 | 3STY12CL | 2015 K10 BATCH 6 | 18422268.79 |  |  | COMPLETED | 1 |  |  | 110615S00130 | 15LB0164 | 2015-11-16 | 2015-11-13 | 2015-11-25 | 2015-12-10 | 2015-12-16 | LEGACY CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao City | 304346 | Cabantian NHS | DAVAO CITY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10437131.51 |  |  | COMPLETED | 1 |  |  | 110615S00059 | 15LB0083 | 2015-09-08 | 2015-09-10 | 2015-09-22 | 2015-10-06 | 2015-10-20 | EIRISH BUILDERS & SUPPLY INC.
NC 2015 | K10 (2015) | Region XI | Davao City | 129509 | Communal Elementary School | DAVAO CITY | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 110615S00143 | 110615S00143 | 2015-11-16 | 2015-11-13 | 2015-11-26 | 2015-12-28
NC 2015 | K10 (2015) | Region XI | Davao City | 129479 | D. Asuncion ES | DAVAO CITY | 2 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10567131.51 |  |  | COMPLETED | 1 |  |  | 110615S00135 | 110615S00135 | 2015-11-16 | 2015-11-13 | 2015-11-26 | 2015-12-28
NC 2015 | K10 (2015) | Region XI | Davao City | 129523 | Daniel M. Perez CES | DAVAO CITY | 2 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 3 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 110615S00080 | 15LB0134 | 2015-09-22 | 2015-09-22 | 2015-10-06 | 2015-11-12 | 2015-11-19 | SBB CONSTRUCTION & SUPPLY, INC. (FORMERLY: SBB CON
NC 2015 | K10 (2015) | Region XI | Davao City | 129657 | Dr. S.P. Dacudao ES | DAVAO CITY | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00082 | 15LB0102 | 2015-09-08 | 2015-09-10 | 2015-09-22 | 2015-10-12 | 2015-10-20 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | SHS (2015) | Region XI | Davao City | 304367 | Dr. Santiago Dakudao Sr. Nat'l High School | DAVAO CITY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10467131.51 |  |  | COMPLETED | 1 |  |  | 110615S00060 | 15LB0084 | 2015-09-08 | 2015-09-10 | 2015-09-22 | 2015-10-06 | 2015-10-20 | ATR CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Davao City | 129510 | Dumanlas ES | DAVAO CITY | 2 | 1 | 12 | 3STY12CL | 2015 K10 BATCH 3 | 18222268.79 |  |  | COMPLETED | 1 |  |  | 110615S00084 | 110615S00084 | 2015-11-26 | 2015-11-26 | 2015-12-08
NC 2015 | SHS (2015) | Region XI | Davao City | 304364 | E. Ramos NHS | DAVAO CITY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00048 | 15LB0085 | 2015-08-18 | 2015-08-18 | 2015-09-03 | 2015-10-02 | 2015-10-15 | MARK ANTHONY CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao City | 304366 | F. Bangoy NHS | DAVAO CITY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10437131.51 |  |  | COMPLETED | 1 |  |  | 110615S00061 | 15LB0086 | 2015-08-08 | 2015-08-06 | 2015-08-18 | 2015-10-02 | 2015-10-15 | O. G. SANTOS CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao City | 304368 | F. Bustamante NHS | DAVAO CITY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10457131.51 |  |  | COMPLETED | 1 |  |  | 110615S00068 | 15LB0087 | 2015-08-08 | 2015-08-06 | 2015-08-18 | 2015-09-17 | 2015-10-06 | MARK ANTHONY CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao City | 304369 | Gorgonio Tajo, Sr. NHS | DAVAO CITY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00018 | 15LB0088 | 2015-08-18 | 2015-08-18 | 2015-09-03 | 2015-10-02 | 2015-10-15 | KATNISS EVERDEEN CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XI | Davao City | 129482 | J. Cruz ES | DAVAO CITY | 2 | 1 | 12 | 3STY12CL | 2015 K10 BATCH 3 | 18222268.79 |  |  | COMPLETED | 1 |  |  | 110615S00087 | 15LB0139 | 2015-09-22 | 2015-09-22 | 2015-10-06 | 2015-11-06 | 2015-11-19 | R.R. SEISMUNDO CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XI | Davao City | 129482 | J. Cruz ES | DAVAO CITY | 2 |  | 6 | 3STY6CL | 2015 K10 BATCH 3 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 110615S00086 | 15LB0138 | 2015-09-22 | 2015-09-22 | 2015-10-06 | 2015-11-06 | 2015-11-19 | DANIMERH CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XI | Davao City | 129662 | Kiman-Anao PS | DAVAO CITY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2128606.04 |  |  | COMPLETED | 1 |  |  | 110615S00117 | 15LB0154 | 2015-12-19 | 2015-12-17 | 2015-12-29
NC 2015 | SHS (2015) | Region XI | Davao City | 304391 | Leon Garcia, Sr. NHS (San Juan NHS) | DAVAO CITY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1 |  |  | 110615S00072 | 15LB0089 | 2015-08-18 | 2015-08-18 | 2015-09-03 | 2015-10-02 | 2015-10-15 | O. G. SANTOS CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao City | 316213 | MAHAYAG NATIONAL HIGH SCHOOL | DAVAO CITY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 110615S00071 | 15LB0090 | 2015-07-02 | 2015-07-02 | 2015-07-16 | 2015-08-03 | 2015-08-25 | A.Y.U. ENGINEERING & CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao City | 304379 | Malabog NHS | DAVAO CITY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00070 | 15LB0091 | 2015-08-18 | 2015-08-18 | 2015-09-03 | 2015-10-02 | 2015-10-15 | MARK ANTHONY CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao City | 316204 | Malabog NHS-Sumimao NHS | DAVAO CITY | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2730828.124 |  |  | COMPLETED | 1 |  |  | 110615S00062 | 15LB0092 | 2015-07-02 | 2015-07-02 | 2015-07-16 | 2015-08-03 | 2015-08-25 | A.Y.U. ENGINEERING & CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao City | 316204 | Malabog NHS-Sumimao NHS | DAVAO CITY | 2 |  | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2730828.124 |  |  | COMPLETED | 1 |  |  | 110615S00069 | 15LB0093 | 2015-08-18 | 2015-08-18 | 2015-09-03 | 2015-10-02 | 2015-10-15 | A.Y.U. ENGINEERING & CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao City | 304380 | Mandug NHS (Pablo Lorenzo NHS) | DAVAO CITY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10447131.51 |  |  | COMPLETED | 1 |  |  | 110615S00067 | 15LB0094 | 2015-08-18 | 2015-08-18 | 2015-09-03 | 2015-10-02 | 2015-10-15 | P.J. SAN PEDRO CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region XI | Davao City | 129483 | Osmeña E/S | DAVAO CITY | 2 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 3 | 31102890.27 |  |  | REVERTED | 0 |  |  | 110615S00074 | 15LB0132 | 2015-12-18 | 2015-12-17 | 2015-12-29
NC 2015 | K10 (2015) | Region XI | Davao City | 129528 | Pablo Piatos ES | DAVAO CITY | 2 | 1 | 3 | 3STY3CL | 2015 K10 BATCH 6 | 6888472.88 |  |  | COMPLETED | 1 |  |  | 110615S00116 | 15Lb0153 | 2015-12-18 | 2015-12-15 | 2015-12-28
NC 2015 | SHS (2015) | Region XI | Davao City | 304389 | Paquibato NHS | DAVAO CITY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6594338 |  |  | COMPLETED | 1 |  |  | 110615S00106
NC 2015 | SHS (2015) | Region XI | Davao City | 304390 | Paquibato NHS - Panaga NHS | DAVAO CITY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6414337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00066 | 15LB0095 | 2015-08-18 | 2015-08-18 | 2015-09-03 | 2015-10-02 | 2015-10-15 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | SHS (2015) | Region XI | Davao City | 316211 | Paradise Embac National High School | DAVAO CITY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6389337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00065 | 15LB0096 | 2015-08-18 | 2015-08-18 | 2015-09-03 | 2015-10-02 | 2015-10-15 | TWO DEGREES CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region XI | Davao City | 129674 | Salapawan ES | DAVAO CITY | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 3027592.44 |  |  | COMPLETED | 1 |  |  | 110615S00118 | 15LB155 | 2015-12-19 | 2015-12-17 | 2015-12-29
NC 2015 | K10 (2015) | Region XI | Davao City | 129517 | San Isidro ES | DAVAO CITY | 2 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 3 | 31102890.27 |  |  | COMPLETED | 1 |  |  | 110615S00083 | 110615S00083 | 2015-11-26 | 2015-11-26 | 2015-12-08
NC 2015 | K10 (2015) | Region XI | Davao City | 129484 | Sasa ES | DAVAO CITY | 2 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 3 | 15121327.92 |  |  | REVERTED | 0 |  |  | 110615S00085 | 15LB0137 | 2015-12-18 | 2015-12-17 | 2015-12-29
NC 2015 | SHS (2015) | Region XI | Davao City | 304370 | Teofilo V. Fernandez NHS (Indangan NHS) | DAVAO CITY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10567131.51 |  |  | COMPLETED | 1 |  |  | 110615S00064 | 15LB0097 | 2015-09-08 | 2015-09-10 | 2015-09-22 | 2015-10-06 | 2015-10-20 | MICAH CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XI | Davao City | 129487 | V.L. Angliongto, Sr. ES | DAVAO CITY | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4617048.49 |  |  | COMPLETED | 1 |  |  | 110615S00115 | 15LB0152 | 2015-12-18 | 2015-12-15 | 2015-12-28
NC 2015 | SHS (2015) | Region XI | Davao City | 304399 | Waan National High School | DAVAO CITY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00063 | 15LB0098 | 2015-08-18 | 2015-08-18 | 2015-09-03 | 2015-10-02 | 2015-10-15 | JAVCON BUILDERS, INC.
NC 2015 | SHS (2015) | Region XI | Davao City | 316205 | Baguio HS of Agriculture - Tambobong HS Annex | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6379337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00046 | 15LH0152 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | MARK ANTHONY CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao City | 304343 | Baguio National School of Arts and Trades | DAVAO CITY | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10437131.51 |  |  | COMPLETED | 1 |  |  | 110615S00031 | 15LH0133 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | ST. GERRARD CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Davao City | 206003 | Balah Licosan Elementary School | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00097 | 15LH0153 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | A.Y.U. ENGINEERING & CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Davao City | 129684 | Batolusa ES | DAVAO CITY | 3 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 15022518.84 |  |  | COMPLETED | 1 |  |  | 110615S00128 | 15LH0168 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-10-08 | 2015-11-03 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao City | 304347 | Biao NHS | DAVAO CITY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8224965.051 |  |  | COMPLETED | 1 |  |  | 110615S00019 | 15LH0141 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | LLM CONCRETE PRODUCTS
NC 2015 | SHS (2015) | Region XI | Davao City | 304348 | Biao NHS - Talandang HS Annex | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6374337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00020 | 15LH0151 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | P.J. SAN PEDRO CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao City | 304350 | Binugao NHS | DAVAO CITY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 |  |  | 110615S00021 | 15LH0140 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | LLM CONCRETE PRODUCTS
NC 2015 | SHS (2015) | Region XI | Davao City | 304351 | Binugao NHS - Baracatan NHS | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00022 | 15LH0161 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | RITZTOK CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao City | 304353 | Buda NHS | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00016 | 15LH0148 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | R.C. MELGAZO BUILDERS
NC 2015 | SHS (2015) | Region XI | Davao City | 304354 | Calinan NHS | DAVAO CITY | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 14917518.84 |  |  | COMPLETED | 1 |  |  | 110615S00033 | 15LH0167 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-25 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao City | 304354 | Calinan NHS | DAVAO CITY | 3 | 1 | 8 | Completion of 4STY16CL | 2015 COMPLETION BATCH 4 | 11834950.58 |  |  | COMPLETED | 1 |  |  | 110615S00146 | 15LH0167 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-08-30 | 2015-09-25 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao City | 304356 | Crossing Bayabas NHS | DAVAO CITY | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 14917518.84 |  |  | COMPLETED | 1 |  |  | 110615S00034 | 15LH0125 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | ST. GERRARD CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao City | 316207 | Crossing Bayabas NHS - Camansi HS Annex | DAVAO CITY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 |  |  | 110615S00035 | 15LH0139 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | LLM CONCRETE PRODUCTS
NC 2015 | SHS (2015) | Region XI | Davao City | 316206 | Crossing Bayabas NHs - Don Enrique Bustamante NHS | DAVAO CITY | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 110615S00036 | 15LH0132 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | MARK ANTHONY CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao City | 304357 | Crossing Bayabas NHS - E. B. Lopez Mem. NHS | DAVAO CITY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 |  |  | 110615S00037 | 15LH0138 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | MEGILA CONSTRUCTION DEVELOPMENT AND SUPPLY
NC 2015 | K10 (2015) | Region XI | Davao City | 304358 | Dacudao NHS | DAVAO CITY | 3 | 1 | 4 | 4STY4CL | 2015 K10 BATCH 7 | 7050000 |  |  | COMPLETED | 1 |  |  | 110615S00144
NC 2015 | SHS (2015) | Region XI | Davao City | 304358 | Dacudao NHS | DAVAO CITY | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14997519 |  |  | COMPLETED | 1 |  |  | 110615S00101 | 110615S00101 | 2015-08-14 | 2015-08-17 | 2015-09-01 | 2015-10-21 | 2015-11-17 | MEGILA CONSTRUCTION DEVELOPMENT AND SUPPLY
NC 2015 | K10 (2015) | Region XI | Davao City | 129604 | Datu Duyan ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 110615S00141 | 15LH0174 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-10-08 | 2015-11-03 | R.C. MELGAZO BUILDERS
NC 2015 | K10 (2015) | Region XI | Davao City | 129606 | Datu Salumay ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2163606.04 |  |  | COMPLETED | 1 |  |  | 110615S00136 | 15LH0178 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-10-08 | 2015-11-03 | R.C. MELGAZO BUILDERS
NC 2015 | SHS (2015) | Region XI | Davao City | 304361 | Dona Carmen Denia NHS | DAVAO CITY | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 14917518.84 |  |  | COMPLETED | 1 |  |  | 110615S00047 | 15LH0126 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | ST. GERRARD CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Davao City | 304362 | Dona Carmen Denia NHS - J. V. Ferriols HS | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00081 | 15LH0154 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | MARK ANTHONY CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XI | Davao City | 206009 | Dumalogdog E/S | DAVAO CITY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 4227212.08 |  |  | COMPLETED | 1 |  |  | 110615S00137 | 15LH0179 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-10-08 | 2015-11-03 | R.C. MELGAZO BUILDERS
NC 2015 | SHS (2015) | Region XI | Davao City | 304344 | Elias P. Dacudao Gumalang School of Home Industries | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6379337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00039 | 15LH0159 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | P.J. SAN PEDRO CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao City | 304395 | Emilio J. Estipona- Guinga NHS | DAVAO CITY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1 |  |  | 110615S00032 | 15LH0137 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | MARK ANTHONY CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao City | 304383 | G.Astilla Sr. Cultural Minority HS - Marilog NHS Annex | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6359337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00041 | 15LH0147 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | R.C. MELGAZO BUILDERS
NC 2015 | K10 (2015) | Region XI | Davao City | 129607 | Gumitan ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2188606.04 |  |  | COMPLETED | 1 |  |  | 110615S00138 | 15LH0173 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-10-08 | 2015-11-03 | JAVCON BUILDERS, INC.
NC 2015 | K10 (2015) | Region XI | Davao City | 129734 | Imelda ES | DAVAO CITY | 3 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 110615S00139 | 15LH0169 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-10-08 | 2015-11-03 | SBB CONSTRUCTION & SUPPLY, INC. (FORMERLY: SBB CON
NC 2015 | K10 (2015) | Region XI | Davao City | 129567 | Inayangan ES | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00094 | 15LH0155 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | ST. GERRARD CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Davao City | 316210 | Inayangan HS (Telesforo Annex) | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6419338 |  |  | COMPLETED | 1 |  |  | 110615S00145
NC 2015 | K10 (2015) | Region XI | Davao City | 206002 | Laho Elementary School | DAVAO CITY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2063606.04 |  |  | COMPLETED | 1 |  |  | 110615S00134 | 15LH0175 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-10-08 | 2015-11-03 | R.C. MELGAZO BUILDERS
NC 2015 | SHS (2015) | Region XI | Davao City | 304371 | Lamanan National High School | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6379337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00042 | 15LH0143 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | ST. GERRARD CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao City | 304373 | Los Amigos NHS | DAVAO CITY | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 110615S00043 | 15LH0131 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | MARK ANTHONY CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XI | Davao City | 129570 | Lower Tamugan ES | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00095 | 15LH0158 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | R.C. MELGAZO BUILDERS
NC 2015 | SHS (2015) | Region XI | Davao City | 304374 | Lower Tamugan NHS | DAVAO CITY | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10482131.51 |  |  | COMPLETED | 1 |  |  | 110615S00044 | 15LH0130 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | ST. GERRARD CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Davao City | 129736 | Luman ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 110615S00108 | 15LH0176 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-10-08 | 2015-11-03 | R.C. MELGAZO BUILDERS
NC 2015 | SHS (2015) | Region XI | Davao City | 304342 | Ma. Cristina P. Belcar Agricultural High School | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6359337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00045 | 15LH0162 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | JAVCON BUILDERS, INC.
NC 2015 | K10 (2015) | Region XI | Davao City | 129619 | Manaong Elementary School | DAVAO CITY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 110615S00110 | 15LH0177 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-10-08 | 2015-11-03 | 2H2L CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao City | 304381 | Marilog HS Of Agriculture | DAVAO CITY | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 5755185 |  |  | COMPLETED | 1 |  |  | 110615S00102 | 110615S00102 | 2015-08-14 | 2015-08-17 | 2015-09-01 | 2015-10-21 | 2015-11-17 | O. G. SANTOS CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao City | 304382 | Marilog National High School | DAVAO CITY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8289965.051 |  |  | COMPLETED | 1 |  |  | 110615S00017 | 15LH0136 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | ST. GERRARD CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao City | 304384 | Marilog NHS - Marahan NHS | DAVAO CITY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2013606 |  |  | COMPLETED | 1 |  |  | 110615S00104 | 110615S00104 | 2015-08-14 | 2015-08-17 | 2015-09-01 | 2015-10-21 | 2015-11-17 | R.C. MELGAZO BUILDERS
NC 2015 | SHS (2015) | Region XI | Davao City | 304384 | Marilog NHS - Marahan NHS | DAVAO CITY | 3 |  | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 110615S00105 | 110615S00105 | 2015-08-14 | 2015-08-17 | 2015-09-01 | 2015-10-21 | 2015-11-17 | R.C. MELGAZO BUILDERS
NC 2015 | K10 (2015) | Region XI | Davao City | 304385 | Mintal Comprehensive High School | DAVAO CITY | 3 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 3 | 31102890.27 |  |  | COMPLETED | 1 |  |  | 110615S00075 | 15LH0165 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-08-30 | 2015-09-25 | RSP ENTERPRISES, INC.
NC 2015 | K10 (2015) | Region XI | Davao City | 304385 | Mintal Comprehensive High School | DAVAO CITY | 3 |  | 16 | 4STY16CL | 2015 K10 BATCH 3 | 26702469.42 |  |  | COMPLETED | 1 |  |  | 110615S00079 | 15LH0166 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-08-30 | 2015-09-25 | DAVAO ROCK MIXER ENTERPRISES
NC 2015 | SHS (2015) | Region XI | Davao City | 304385 | Mintal Comprehensive High School | DAVAO CITY | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14947519 |  |  | COMPLETED | 1 |  |  | 110615S00103 | 110615S00103 | 2015-08-14 | 2015-08-17 | 2015-09-01 | 2015-10-21 | 2015-11-17 | RSP ENTERPRISES, INC.
NC 2015 | K10 (2015) | Region XI | Davao City | 129738 | Mintal ES | DAVAO CITY | 3 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 6 | 31202890.27 |  |  | COMPLETED | 1 |  |  | 110615S00113 | 15LH0170 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-10-08 | 2015-11-03 | FGM BUILDERS RESOURCES & DEVELOPMENT CORP.
NC 2015 | K10 (2015) | Region XI | Davao City | 129738 | Mintal ES | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00114 | 15LH0172 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-10-08 | 2015-11-03 | FGM BUILDERS RESOURCES & DEVELOPMENT CORP.
NC 2015 | SHS (2015) | Region XI | Davao City | 304386 | Mintal NCHS - Sto. Nino HS | DAVAO CITY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8224965.051 |  |  | COMPLETED | 1 |  |  | 110615S00040 | 15LH0135 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | A.Y.U. ENGINEERING & CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao City | 304387 | Mintal NCHS - Tugbok National HS | DAVAO CITY | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 14917518.84 |  |  | COMPLETED | 1 |  |  | 110615S00038 | 15LH0124 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | DAVAO ROCK MIXER ENTERPRISES
NC 2015 | SHS (2015) | Region XI | Davao City | 304388 | Optaciano Hilay NHS | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6379337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00030 | 15LH0146 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | E.I.C.I. BUILDERS
NC 2015 | SHS (2015) | Region XI | Davao City | 316203 | Optaciano Hilay NHS - Mulig NHS Annex | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6389337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00029 | 15LH0160 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | DTV CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region XI | Davao City | 129576 | Quibaton ES | DAVAO CITY | 3 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3817968.78 |  |  | COMPLETED | 1 |  |  | 110615S00107 | 15LH0180 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-10-08 | 2015-11-03 | 2H2L CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao City | 304372 | Saloy Nationa High School | DAVAO CITY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1 |  |  | 110615S00028 | 15LH0134 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | ST. GERRARD CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao City | 304392 | Sirib NHS | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00027 | 15LH0149 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | P.J. SAN PEDRO CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region XI | Davao City | 129551 | Sta. Clara ES | DAVAO CITY | 3 | 1 | 12 | 3STY12CL | 2015 K10 BATCH 3 | 18222268.79 |  |  | COMPLETED | 1 |  |  | 110615S00076 | 15LH0164 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-08-30 | 2015-09-25 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | K10 (2015) | Region XI | Davao City | 129579 | Suawan ES | DAVAO CITY | 3 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110615S00096 | 15LH0142 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | ST. GERRARD CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Davao City | 129632 | Sumilop PS | DAVAO CITY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | COMPLETED | 1 |  |  | 110615S00122 | 15LH0181 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-10-08 | 2015-11-03 | JAVCON BUILDERS, INC.
NC 2015 | SHS (2015) | Region XI | Davao City | 304394 | Tagakpan NHS | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00026 | 15LH0150 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | P.J. SAN PEDRO CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region XI | Davao City | 129580 | Tagbaw PS | DAVAO CITY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 110615S00123 | 15LH0182 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-10-08 | 2015-11-03 | JAVCON BUILDERS, INC.
NC 2015 | SHS (2015) | Region XI | Davao City | 304397 | Telesforo S. Singson NHS | DAVAO CITY | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10547131.51 |  |  | COMPLETED | 1 |  |  | 110615S00025 | 15LH0129 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | ST. GERRARD CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao City | 304398 | Toril NHS | DAVAO CITY | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 110615S00024 | 15LH0128 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | MARK ANTHONY CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XI | Davao City | 129582 | Unapan ES | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00098 | 15LH0156 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | JAVCON BUILDERS, INC.
NC 2015 | K10 (2015) | Region XI | Davao City | 129552 | V.S. Bangoy ES | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110615S00078 | 15LH0157 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | MARK ANTHONY CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao City | 304355 | Wangan National High School-Calinan NHS Annex | DAVAO CITY | 3 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3474886.575 |  |  | COMPLETED | 1 |  |  | 110615S00023 | 15LH0163 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-10 | MEGILA CONSTRUCTION DEVELOPMENT AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304217 | Asuncion NHS | ASUNCION (SAUG) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8394965.051 |  |  | COMPLETED | 1 |  |  | 110115S00055 | 15LC0133 | 2015-08-03 | 2015-08-07 | 2015-10-01 | 2015-10-15 | 2015-10-23 | E.P. MANANTAN CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | K10 (2015) | Region XI | Davao del Norte | 128570 | Cambanogoy CES | ASUNCION (SAUG) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 110115S00138 | 15LC0187 | 2015-10-07 | 2015-10-09 | 2015-10-22 | 2015-11-09 | 2015-11-16 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304234 | Capungangan HS | KAPALONG | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110115S00056 | 1101-15-S-00056 (CNTR) | 2015-07-10 | 2015-11-17 | 2015-11-17
NC 2015 | K10 (2015) | Region XI | Davao del Norte | 128648 | Dacudao ES | SAN ISIDRO | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 110115S00110 | 1101-15-S-00110 (CNTR) | 2015-11-19 | 2015-11-20 | 2015-12-08
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304224 | Datu Balong NHS | KAPALONG | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8384965.051 |  |  | COMPLETED | 1 |  |  | 110115S00058 | 1101-15-S-00041 (CNTR) | 2015-11-11 | 2015-11-20 | 2015-12-01
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304258 | Datu Jose A. Libayao Memorial NHS | TALAINGOD | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6409337.6381 |  |  | COMPLETED | 1 |  |  | 110115S00059 | 1101-15-S-00041 (CNTR) | 2015-11-19 | 2015-11-20 | 2015-12-08
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304228 | Doña Carmen Soriano NHS | KAPALONG | 1 | 1 | 6 | 2STY6CL | 2015 ADDITIONAL FUND BATCH 9 | 1735627.4129 |  |  | COMPLETED | 1 |  |  | 110115S00142 | 1101-15-S-00110 (CNTR) | 2015-11-19 | 2015-11-20 | 2015-12-08
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304228 | Doña Carmen Soriano NHS | KAPALONG | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6329337.6381 |  |  | COMPLETED | 1 |  |  | 110115S00060 | 15LC0134 | 2015-08-03 | 2015-08-07 | 2015-10-01 | 2015-10-15 | 2015-10-23 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | K10 (2015) | Region XI | Davao del Norte | 128705 | El Unido ES | NEW CORELLA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 110115S00136 | 1101-15-S-00110 (CNTR) | 2015-11-04 | 2015-11-13 | 2015-11-24
NC 2015 | K10 (2015) | Region XI | Davao del Norte | 204509 | Gatong ES | TALAINGOD | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 110115S00109 | 15LC0194 | 2015-10-07 | 2015-10-09 | 2015-10-22 | 2015-11-09 | 2015-11-16 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | K10 (2015) | Region XI | Davao del Norte | 204509 | Gatong ES | TALAINGOD | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 110115S00108 | 15LC0194 | 2015-10-07 | 2015-10-09 | 2015-10-22 | 2015-11-09 | 2015-11-16 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | K10 (2015) | Region XI | Davao del Norte | 128574 | Igangon ES | SAN ISIDRO | 1 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 6 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 110115S00135 | 15LC0175 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-27 | 2015-11-09 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304233 | Kapalong National High School | KAPALONG | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8434965.051 |  |  | COMPLETED | 1 |  |  | 110115S00061 | 15LC0174 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-27 | 2015-11-09 | DAVAO CONCRETE PRODUCTS
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304239 | Limbaan NHS | NEW CORELLA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110115S00062 | 1101-15-S-00041 (CNTR) | 2015-11-10 | 2015-11-13 | 2015-11-24
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304240 | Linao NHS | SAN ISIDRO | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 |  |  | 110115S00094 | 1101-15-S-00094 (CNTR) | 2015-07-10 | 2015-11-17 | 2015-11-17
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304241 | Luna NHS | KAPALONG | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 110115S00075 | 15LC0114 | 2015-07-10 | 2015-07-17 | 2015-10-01 | 2015-10-15 | 2015-10-23 | EXACT CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304242 | Mabantao NHS | KAPALONG | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110115S00064 | 1101-15-S-00094 (CNTR) | 2015-07-10 | 2015-11-17 | 2015-11-26
NC 2015 | K10 (2015) | Region XI | Davao del Norte | 128662 | Maniki CES SPED Center | KAPALONG | 1 | 1 | 12 | 3STY12CL | 2015 K10 BATCH 6 | 18222268.79 |  |  | COMPLETED | 1 |  |  | 110115S00134 | 15LC0184 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-27 | 2015-11-09 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304249 | Mesaoy NHS | NEW CORELLA | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110115S00054 | 1101-15-S-00094 (CNTR) | 2015-07-10 | 2015-11-17 | 2015-11-17
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304248 | New Corella NHS | NEW CORELLA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 110115S00068 | 15LC0170 | 2015-09-28 | 2015-10-02 | 2015-10-15 | 2015-10-27 | 2015-11-09 | FFJJ CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Davao del Norte | 128716 | New Sambog ES | NEW CORELLA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 110115S00124 | 1101-15-S-00110 (CNTR) | 2015-11-04 | 2015-11-13 | 2015-11-24
NC 2015 | K10 (2015) | Region XI | Davao del Norte | 128589 | Rizal ES | ASUNCION (SAUG) | 1 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 3 | 4673636.82 |  |  | COMPLETED | 1 |  |  | 110115S00112 | 1101-15-S-00110 (CNTR) | 2015-11-19 | 2015-11-20 | 2015-12-08
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304218 | Sagayen NHS | ASUNCION (SAUG) | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 11027342.5917 |  |  | COMPLETED | 1 |  |  | 110115S00070 | 15LC0142 | 2015-07-10 | 2015-08-07 | 2015-10-01 | 2015-10-15 | 2015-10-23 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304251 | Sawata NHS | SAN ISIDRO | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10947342.5917 |  |  | COMPLETED | 1 |  |  | 110115S00095 | 1101-15-S-00041 (CNTR) | 2015-08-06 | 2015-08-07 | 2015-11-17
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304243 | Semong NHS | KAPALONG | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110115S00065 | 1101-15-S-00056 (CNTR) | 2015-07-10 | 2015-11-17 | 2015-11-26
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304252 | Sonlon NHS | ASUNCION (SAUG) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110115S00043 | 1101-15-S-00041 (CNTR) | 2015-11-10 | 2015-11-13 | 2015-11-24
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304257 | Sto. Nino NHS | TALAINGOD | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1 |  |  | 110115S00041 | 15LC0144 | 2015-08-06 | 2015-08-07 | 2015-10-01 | 2015-10-15 | 2015-10-23 | DAVAO CONCRETE PRODUCTS
NC 2015 | K10 (2015) | Region XI | Davao del Norte | 128670 | Sua-on ES | KAPALONG | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 110115S00111 | 15LC0187 | 2015-10-07 | 2015-10-09 | 2015-10-22 | 2015-11-09 | 2015-11-16 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304235 | Sua-on NHS | KAPALONG | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110115S00040 | 1101-15-S-00056 (CNTR) | 2015-07-10 | 2015-11-17 | 2015-11-17
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304215 | Alejal National High School | CARMEN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110115S00096 | 15LC0115 | 2015-07-10 | 2015-07-17 | 2015-10-01 | 2015-10-15 | 2015-10-23 | DAVAO CONCRETE PRODUCTS
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 315903 | Anibongan NHS | CARMEN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110115S00097 | 15LC0111 | 2015-07-10 | 2015-07-17 | 2015-09-03 | 2015-09-14 | 2015-09-24 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304219 | Balagunan NHS | SANTO TOMAS | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110115S00044 | 1101-15-S-00044 (CNTR) | 2015-07-10 | 2015-11-17 | 2015-11-17
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304221 | Cabayangan NHS | BRAULIO E. DUJALI | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 110115S00053 | 15LC0116 | 2015-07-10 | 2015-07-17 | 2015-09-03 | 2015-09-14 | 2015-09-24 | TWINA BUILDERS AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304222 | Carmen NHS | CARMEN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1 |  |  | 110115S00098 | 15LC0148 | 2015-07-10 | 2015-07-17 | 2015-09-03 | 2015-09-14 | 2015-09-24 | LLM CONCRETE PRODUCTS
NC 2015 | TECHVOC (2015) | Region XI | Davao del Norte | 304222 | Carmen NHS | CARMEN | 2 | 1 | 1 | Construction of 1UNIT Standard Technical and Vocational Building | 2015 TVL | 2779549.27 |  |  | COMPLETED | 1 |  |  | 110115S00145 | 15LC0186 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-27 | 2015-11-09 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304229 | Dujali NHS | BRAULIO E. DUJALI | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110115S00045 | 15LC0173 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-27 | 2015-11-09 | DAVAO CONCRETE PRODUCTS
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304237 | Kimamon NHS | SANTO TOMAS | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 110115S00046 | 15LC0171 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-27 | 2015-11-09 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304255 | La Libertad NHS | SANTO TOMAS | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6359337.6381 |  |  | COMPLETED | 1 |  |  | 110115S00047 | 15LC0117 | 2015-07-10 | 2015-09-17 | 2015-10-01 | 2015-10-15 | 2015-10-23 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 315904 | La Paz NHS | CARMEN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110115S00099 | 15LC0111 | 2015-07-10 | 2015-07-17 | 2015-09-03 | 2015-09-14 | 2015-09-24 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | K10 (2015) | Region XI | Davao del Norte | 128633 | Mabuhay ES | CARMEN | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110115S00121 | 15LC0166 | 2015-08-27 | 2015-09-04 | 2015-09-17 | 2015-10-01 | 2015-10-12 | MAG CORPORATION
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304244 | Mabuhay NHS | CARMEN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110115S00100 | 15LC0111 | 2015-07-10 | 2015-07-17 | 2015-09-03 | 2015-09-14 | 2015-09-24 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | K10 (2015) | Region XI | Davao del Norte | 128759 | Magwawa ES | SANTO TOMAS | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110115S00107 | 15LC0169 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-27 | 2015-11-09 | DAVAO CONCRETE PRODUCTS
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304246 | Marsman NHS | SANTO TOMAS | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2720828.124 |  |  | COMPLETED | 1 |  |  | 110115S00048 | 15LC0149 | 2015-09-03 | 2015-09-04 | 2015-09-17 | 2015-10-01 | 2015-10-12 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304256 | Salvacion NHS | SANTO TOMAS | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110115S00050 | 1101-15-S-00045 (CNTR) | 2015-11-10 | 2015-11-13 | 2015-11-24
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304254 | Sto Tomas NHS | SANTO TOMAS | 2 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 1 | 12771310.093 |  |  | COMPLETED | 1 |  |  | 110115S00052 | 15LC0172 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-27 | 2015-11-09 | DANIMERH CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XI | Davao del Norte | 128765 | Sto. Tomas CES | SANTO TOMAS | 2 | 1 | 12 | 3STY12CL | 2015 K10 BATCH 6 | 18222268.79 |  |  | COMPLETED | 1 |  |  | 110115S00137 | 15LC0183 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-27 | 2015-11-09 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 304230 | Tanglaw NHS | BRAULIO E. DUJALI | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110115S00090 | 1101-15-S-00044 (CNTR) | 2015-07-10 | 2015-07-17 | 2015-11-26
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 315901 | Tubod NHS | CARMEN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110115S00101 | 15LC0138 | 2015-08-06 | 2015-08-07 | 2015-10-01 | 2015-10-15 | 2015-10-23 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Davao del Norte | 315902 | Tulalian NHS | SANTO TOMAS | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110115S00089 | 1101-15-S-00044 (CNTR) | 2015-07-10 | 2015-07-17 | 2015-11-17
NC 2015 | SHS (2015) | Region XI | Davao del Sur | 304289 | Bangkal NHS | MATANAO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 110215S00041 | 15LD0048 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-03 | VERGUZ CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao del Sur | 304265 | Barayong NHS | MAGSAYSAY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8324965.051 |  |  | COMPLETED | 1 |  |  | 110215S00052 | 15lLD0049 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-03 | LTB BUILDERS & CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao del Sur | 304295 | Bato NHS | SANTA CRUZ | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6529337.6381 |  |  | COMPLETED | 1 |  |  | 110215S00042 | 15LD0050 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-03 | RITZTOK CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region XI | Davao del Sur | 129015 | Ceboza ES | MATANAO | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 110215S00071 | 15LD0065 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-03 | LEAMOR CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao del Sur | 304263 | Federico Yap NHS | SANTA CRUZ | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 110215S00044 | 15LD0051 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-03 | LEAMOR CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao del Sur | 304275 | Hagonoy NHS | HAGONOY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1 |  |  | 110215S00045 | 15LD0069 | 2015-08-05 | 2015-08-06 | 2015-08-18 | 2015-08-28 | 2015-09-11 | LTB BUILDERS & CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao del Sur | 304278 | Inawayan NHS | SANTA CRUZ | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 110215S00046 | 15LD0052 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-03 | LEAMOR CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region XI | Davao del Sur | 129039 | Langa-an ES | MATANAO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 110215S00093 | 15LD0095 | 2015-09-23 | 2015-09-24 | 2015-10-06 | 2015-10-14 | 2015-10-23 | LTB BUILDERS & CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao del Sur | 304284 | Lower Bala NHS | MAGSAYSAY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8374965.051 |  |  | COMPLETED | 1 |  |  | 110215S00047 | 15LD0053 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-03 | LEAMOR CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao del Sur | 304286 | Marber NHS | BANSALAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8324965.051 |  |  | COMPLETED | 1 |  |  | 110215S00035 | 15LD0054 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-03 | LTB BUILDERS & CONSTRUCTION
NC 2015 | TECHVOC (2015) | Region XI | Davao del Sur | 304288 | Matanao National High School | MATANAO | 1 | 1 | 1 | Construction of 1UNIT Standard Technical and Vocational Building | 2015 TVL | 2549549.27 |  |  | COMPLETED | 1 |  |  | 110215S00124 | 15LD0099 | 2015-09-23 | 2015-09-24 | 2015-10-06 | 2015-10-14 | 2015-10-23 | LLM CONCRETE PRODUCTS
NC 2015 | SHS (2015) | Region XI | Davao del Sur | 304288 | Matanao National High School | MATANAO | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10537131.51 |  |  | COMPLETED | 1 |  |  | 110215S00027 | 15LD0070 | 2015-08-05 | 2015-08-06 | 2015-08-18 | 2015-08-28 | 2015-09-11 | LTB BUILDERS & CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao del Sur | 316002 | Padada NHS | PADADA | 1 | 1 | 4 | additional 2STY4CL | 2015 ADDITIONAL FUND BATCH 9 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 110215S00123 | 15LD0091 | 2015-09-02 | 2015-09-03 | 2015-09-15 | 2015-09-21 | 2015-09-28 | LTB BUILDERS & CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao del Sur | 316002 | Padada NHS | PADADA | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1 |  |  | 110215S00034 | 15LD0071 | 2015-08-05 | 2015-08-06 | 2015-08-18 | 2015-08-28 | 2015-09-11 | LTB BUILDERS & CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Davao del Sur | 129096 | Patulangon ES | SANTA CRUZ | 1 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao del Sur | 129096 | Patulangon ES | SANTA CRUZ | 1 |  | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Davao del Sur | 304285 | Pedro A. Arches NHS | BANSALAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8374965.051 |  |  | COMPLETED | 1 |  |  | 110215S00037 | 15LD0055 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-03 | TWINA BUILDERS AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao del Sur | 316004 | SACUB High School Annex | HAGONOY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8374965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao del Sur | 129097 | Saliducon ES | SANTA CRUZ | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 110215S00082 | 15LD0093 | 2015-09-23 | 2015-09-24 | 2015-10-06 | 2015-10-14 | 2015-10-23 | TWO DEGREES CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao del Sur | 316003 | SALUD CAGAS TECH.& VOC. H.S | MATANAO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 110215S00054 | 15LD0064 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-03 | BILL HILL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao del Sur | 304279 | Sibulan NHS | SANTA CRUZ | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1 |  |  | 110215S00049 | 15LD0057 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-03 | RITZTOK CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao del Sur | 304290 | Sinawilan NHS | MATANAO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Davao del Sur | 304294 | Sta. Cruz National High School | SANTA CRUZ | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10617131.51 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region XI | Davao del Sur | 304294 | Sta. Cruz National High School | SANTA CRUZ | 1 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4979098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Davao del Sur | 304298 | Tacul Agrc'L VHS (Tacul NHS) | MAGSAYSAY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8394965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Davao del Sur | 304280 | Tudaya NHS | SANTA CRUZ | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110215S00043 | 15LD0060 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-03 | LEAMOR CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Davao Occidental | 304262 | Alberto Olarte, Sr. NHS | SARANGANI | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8544965.051 |  |  | COMPLETED | 1 |  |  | 110215S00039 | 15LE0042 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-10-12 | 2015-11-13 | ARCINUE COMMERCIAL
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 128891 | Aldo Pagagao Elementary School | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2008606.04 |  |  | COMPLETED | 1 |  |  | 110215S00115 | 15LE0101 | 2015-11-09 | 2015-11-11 | 2015-11-24
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 128886 | Andres Yacon Sr. ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110215S00086 | 15LE0154 | 2015-12-09 | 2015-12-10 | 2015-12-23
NC 2015 | SHS (2015) | Region XI | Davao Occidental | 304264 | Balangonan NHS | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Davao Occidental | 304266 | Basiawan NHS | SANTA MARIA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 110215S00055 | 15LE0046 | 2015-10-08 | 2015-10-09 | 2015-11-11 | 2015-11-18 | 2015-12-09 | FORTSTONE CONSTRUCTION ENTERPRISES
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 128988 | Bisang ES | MALITA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1 |  |  | 110215S00089 | 15LE0099 | 2015-11-09 | 2015-11-11 | 2015-11-24
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 128989 | Bito ES | MALITA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1 |  |  | 110215S00090 | 15LE0097 | 2015-11-05 | 2015-11-06 | 2015-11-23
NC 2015 | SHS (2015) | Region XI | Davao Occidental | 304269 | B'Laan NHS | MALITA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6499337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 129057 | Camahual | SARANGANI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2068606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 205015 | Camalig PS | SARANGANI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2068606.04 |  |  | COMPLETED | 1 |  |  | 110215S00100 | 15LE0085 | 2015-12-01 | 2015-12-02 | 2015-12-28
NC 2015 | K10 (2015) | Region XI | Davao Del Sur | 128950 | Col. Antonio S. Lanzar ES | MALALAG | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110215S00081 | 15LE0152 | 2015-12-09 | 2015-12-10 | 2015-12-23
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 129107 | COLAGSING ES | SANTA MARIA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 110215S00096 | 15LE0095 | 2015-11-05 | 2015-11-06 | 2015-11-23
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 129109 | Datu Daligsao ES | SANTA MARIA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2008606.04 |  |  | COMPLETED | 1 |  |  | 110215S00097 | 15LE0100 | 2015-11-09 | 2015-11-11 | 2015-11-24
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 205020 | Datu Mending ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 3072592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 205020 | Datu Mending ES | JOSE ABAD SANTOS (TRINIDAD) | 2 |  | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Davao Del Sur | 304270 | Davao Del Sur SOF | MALALAG | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 110215S00026 | 15LE0044 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-10-06 | 2015-11-02 | ARCINUE COMMERCIAL
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 128880 | David Lachica ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2048606.04 |  |  | COMPLETED | 1 |  |  | 110215S00095 | 15LE0116 | 2015-11-25 | 2015-11-26 | 2015-12-08
NC 2015 | SHS (2015) | Region XI | Davao Occidental | 304271 | Demolok Valley NHS | MALITA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8404965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao Del Sur | 128901 | Domino ES | KIBLAWAN | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1 |  |  | 110215S00067 | 15LE0081 | 2015-12-01 | 2015-12-02 | 2015-12-28
NC 2015 | SHS (2015) | Region XI | Davao Occidental | 304272 | Don Marcelino NHS | DON MARCELINO | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10577131.51 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Davao Occidental | 304273 | Edna Guillermo MHS | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8454965.051 |  |  | COMPLETED | 1 |  |  | 110215S00020 | 15LE0039 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-10-09 | 2015-11-18 | ARCINUE COMMERCIAL
NC 2015 | SHS (2015) | Region XI | Davao Del Sur | 316005 | Felipe-Inocencia Deluao NHS | SULOP | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 110215S00056 | 15LE0048 | 2015-08-16 | 2015-08-18 | 2015-09-01 | 2015-09-29 | 2015-10-22 | AL HANDASA CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao Occidental | 304267 | Fishing Village Comprehensive NHS | MALITA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8374965.051 |  |  | COMPLETED | 1 |  |  | 110215S00016 | 15LE0038 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-10-09 | 2015-11-02 | ARCINUE COMMERCIAL
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 128842 | Fred Johnson ES | DON MARCELINO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 110215S00083 | 15LE0102 | 2015-11-09 | 2015-11-11 | 2015-11-24
NC 2015 | SHS (2015) | Region XI | Davao Del Sur | 304274 | Gov. N. Llanos NHS | KIBLAWAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8374965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 129059 | Guillerma Olarte PS | SARANGANI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 110215S00079 | 15LE0083 | 2015-12-01 | 2015-12-02 | 2015-12-28
NC 2015 | SHS (2015) | Region XI | Davao Occidental | 304276 | Heracleo Casco MNHS | SANTA MARIA | 2 | 1 | 8 | additional 2UNIT 2STY4CL | 2015 ADDITIONAL FUND BATCH 9 | 12338675.2761 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Davao Occidental | 304276 | Heracleo Casco MNHS | SANTA MARIA | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10537131.51 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Davao Del Sur | 304277 | Ihan NHS | KIBLAWAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6389337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Davao Del Sur | 304277 | Ihan NHS | KIBLAWAN | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1973606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Davao Occidental | 304292 | John Martin Johnson HS (Lamidan) | DON MARCELINO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 110215S00025 | 15LE0036 | 2015-08-09 | 2015-08-11 | 2015-08-24 | 2015-10-08 | 2015-10-30 | ARCINUE COMMERCIAL
NC 2015 | SHS (2015) | Region XI | Davao Occidental | 304281 | Jose Abad Santos NHS | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8434965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Davao Occidental | 304282 | Jose De Arce MHS (Sangkokdatal HS) | SARANGANI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2258606 |  |  | COMPLETED | 1 |  |  | 110215S00078 | 15LE0149 | 2015-12-09 | 2015-12-10 | 2015-12-23
NC 2015 | K10 (2015) | Region XI | Davao Del Sur | 128913 | Jose T. Arranguez SR. ES | KIBLAWAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 110215S00066 | 15LE0068 | 2015-09-24 | 2015-09-25 | 2015-10-07 | 2015-11-05 | 2015-11-14 | AL HANDASA CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 205016 | Kababa ES | SARANGANI | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3817968.78 |  |  | COMPLETED | 1 |  |  | 110215S00112 | 15LE0151 | 2015-12-09 | 2015-12-10 | 2015-12-23
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 205047 | Kalabunay ES | DON MARCELINO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 205047 | Kalabunay ES | DON MARCELINO | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Davao Occidental | 304283 | Kalbay NHS | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 4 | additional 2UNIT 1STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 3629480.3479 |  |  | COMPLETED | 1 | [10 empty] | no remarks
NC 2015 | SHS (2015) | Region XI | Davao Occidental | 304283 | Kalbay NHS | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8424965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 205028 | Kibatang PS | DON MARCELINO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 110215S00073 | 15LE0067 | 2015-11-29 | 2015-12-01 | 2015-12-28
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 205027 | Kidaman ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | COMPLETED | 1 |  |  | 110215S00101 | 15LE0147 | 2015-12-09 | 2015-12-10 | 2015-12-23
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 128972 | Kilalag ES | MALITA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110215S00065 | 15LE0049 | 2015-08-16 | 2015-08-18 | 2015-09-01 | 2015-09-29 | 2015-10-22 | AL HANDASA CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 128995 | Kipaliko ES | MALITA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 110215S00064 | 15LE0071 | 2015-11-15 | 2015-11-16 | 2015-12-28
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 205048 | Kiyaga Elementary School | DON MARCELINO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 205048 | Kiyaga Elementary School | DON MARCELINO | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 129062 | Konel ES | SARANGANI | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2982592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 128974 | Lacaron ES | MALITA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 110215S00088 | 15LE0093 | 2015-11-05 | 2015-11-16 | 2015-11-23
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 128843 | Lanao Elementary School | DON MARCELINO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 110215S00075 | 15LE0066 | 2015-11-29 | 2015-12-01 | 2015-12-28
NC 2015 | K10 (2015) | Region XI | Davao Del Sur | 129137 | Laperas ES | SULOP | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 110215S00099 | 15LE0094 | 2015-11-06 | 2015-11-06 | 2015-11-23
NC 2015 | SHS (2015) | Region XI | Davao Occidental | 304291 | Lawa NHS | DON MARCELINO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8394965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 129063 | Mabila CES | SARANGANI | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2962592.44 |  |  | COMPLETED | 1 |  |  | 110215S00105 | 15LE0122 | 2015-11-26 | 2015-11-27 | 2015-12-09
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 205056 | Malandog PS | MALITA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 110215S00104 | 15LE0146 | 2015-12-09 | 2015-12-10 | 2015-12-23
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 129001 | Malaway ES | MALITA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1 |  |  | 110215S00091 | 15LE0096 | 2015-11-05 | 2015-11-06 | 2015-11-23
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 129120 | Mamacao ES | SANTA MARIA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 110215S00098 | 15LE0092 | 2015-11-05 | 2015-11-06 | 2015-11-18
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 129064 | Mangahos PS | SARANGANI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2068606.04 |  |  | COMPLETED | 1 |  |  | 110215S00109 | 15LE0086 | 2015-12-01 | 2015-12-02 | 2015-12-28
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 128885 | Mangili ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 6 | 15121327.92 |  |  | COMPLETED | 1 |  |  | 110215S00113 | 15LE0162 | 2015-12-13 | 2015-12-14 | 2015-12-28
NC 2015 | SHS (2015) | Region XI | Davao Occidental | 304287 | Mariano Peralta NHS | MALITA | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10617131.51 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region XI | Davao Occidental | 304287 | Mariano Peralta NHS | MALITA | 2 | 1 | 1 | Construction of 1UNIT Standard Technical and Vocational Building | 2015 TVL | 2629549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Davao Del Sur | 316001 | Molopolo National High School | KIBLAWAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 128852 | Pamongot ES | DON MARCELINO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1968606.04 |  |  | COMPLETED | 1 |  |  | 110215S00084 | 15LE0115 | 2015-11-25 | 2015-11-26 | 2015-12-08
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 129066 | Patuko ES | SARANGANI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 110215S00094 | 15LE0082 | 2015-12-01 | 2015-12-02 | 2015-12-28
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 205049 | Pedro Tague PS | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2028606.04 |  |  | COMPLETED | 1 |  |  | 110215S00103 | 15LE0120 | 2015-11-25 | 2015-11-26 | 2015-12-08
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 129068 | Quiapo ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 110215S00080 | 15LE0124 | 2015-11-26 | 2015-11-27 | 2015-12-09
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 129127 | San Pedro ES | SANTA MARIA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110215S00061 | 15LE0045 | 2015-08-16 | 2015-08-18 | 2015-09-01 | 2015-09-28 | 2015-10-16 | AL HANDASA CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 129070 | Sangkokdatal ES | SARANGANI | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2932592.44 |  |  | COMPLETED | 1 |  |  | 110215S00108 | 15LE0119 | 2015-11-25 | 2015-11-26 | 2015-12-08
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 205029 | Sitio Guisok-BEAM PS | MALITA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 110215S00102 | 15LE0118 | 2015-11-25 | 2015-11-26 | 2015-12-08
NC 2015 | SHS (2015) | Region XI | Davao Occidental | 304296 | Sta. Maria NHS | SANTA MARIA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 110215S00053 | 15LE0047 | 2015-08-16 | 2015-08-18 | 2015-09-01 | 2015-09-28 | 2015-10-23 | AL HANDASA CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao Del Sur | 304297 | Sulop NHS | SULOP | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10587131.51 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region XI | Davao Del Sur | 304297 | Sulop NHS | SULOP | 2 | 1 | 1 | Construction of 1UNIT Standard Technical and Vocational Building | 2015 TVL | 2599549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 128853 | Tador & Masaglang ES | DON MARCELINO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 110215S00085 | 15LE0091 | 2015-11-05 | 2015-11-16 | 2015-11-18
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 128893 | Tanuman ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6429337.6381 |  |  | COMPLETED | 1 |  |  | 110215S00114 | 15LE0153 | 2015-12-09 | 2015-12-10 | 2015-12-23
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 205042 | TFS-Kalamagan | MALITA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 205042 | TFS-Kalamagan | MALITA | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 205040 | TFS-Kamugna ES | MALITA | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3727968.78 |  |  | COMPLETED | 1 |  |  | 110215S00110 | 15LE0148 | 2015-12-09 | 2015-12-10 | 2015-12-23
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 205032 | TFS-Makalong ES | MALITA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2912592.44 |  |  | COMPLETED | 1 |  |  | 110215S00111 | 15LE0117 | 2015-11-25 | 2015-11-26 | 2015-12-08
NC 2015 | SHS (2015) | Region XI | Davao Occidental | 304293 | Ticulon NHS | MALITA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8394965.051 |  |  | COMPLETED | 1 |  |  | 110215S00015 | 15LE0033 | 2015-08-09 | 2015-08-11 | 2015-08-24 | 2015-10-08 | 2015-11-13 | ARCINUE COMMERCIAL
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 129009 | Tingolo ES | MALITA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1 |  |  | 110215S00092 | 15LE0098 | 2015-11-05 | 2015-11-06 | 2015-11-23
NC 2015 | SHS (2015) | Region XI | Davao Occidental | 304268 | Tubalan Comprehensive NHS | SANTA MARIA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 129073 | Tucal ES | SARANGANI | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2932592.44 |  |  | COMPLETED | 1 |  |  | 110215S00107 | 15LE0121 | 2015-11-26 | 2015-11-27 | 2015-12-09
NC 2015 | K10 (2015) | Region XI | Davao Occidental | 205050 | Tunggal Capitan ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 110215S00117 | 15LE0150 | 2015-12-09 | 2015-12-10 | 2015-12-23
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129443 | A.S. Manjoorsa ES | TARRAGONA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2008606.04 |  |  | COMPLETED | 1 |  |  | 110315S00086 | 15LF0058 | 2015-09-16 | 2015-09-28 | 2015-09-30 | 2015-10-06 | 2015-10-20 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129194 | Baclinan PS | BOSTON | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 110315S00059 | 15LF0034 | 2015-07-16 | 2015-07-28 | 2015-07-29 | 2015-08-04 | 2015-08-20 | LLM CONCRETE PRODUCTS
NC 2015 | SHS (2015) | Region XI | Davao Oriental | 304299 | Baculin NHS | BAGANGA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110315S00027 | 15LF0020 | 2015-06-18 | 2015-06-30 | 2015-07-16 | 2015-07-28 | 2015-08-12 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao Oriental | 304300 | Baganga NHS | BAGANGA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110315S00028 | 15LF0019 | 2015-06-14 | 2015-06-26 | 2015-07-16 | 2015-07-28 | 2015-08-12 | FFJJ CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129231 | Bantay ES | CARAGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 110315S00081 | 15LF0055 | 2015-09-08 | 2015-09-18 | 2015-09-21 | 2015-09-28 | 2015-10-12 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129207 | Bantulinao ES | CARAGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 110315S00078 | 1103-15-S-00078 | 2015-09-28 | 2015-10-01 | 2015-10-12 | 2015-10-23 | 2015-10-29 | By Administration
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129166 | Batawan Elementary School | BAGANGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2008606.04 |  |  | COMPLETED | 1 |  |  | 110315S00077 | 15LF0057 | 2015-09-16 | 2015-09-29 | 2015-09-30 | 2015-10-06 | 2015-10-20 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129232 | Binaton ES | CARAGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 110315S00075 | 15LF0055 | 2015-09-08 | 2015-09-18 | 2015-09-21 | 2015-09-28 | 2015-10-12 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | SHS (2015) | Region XI | Davao Oriental | 304304 | Boston NHS | BOSTON | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110315S00029 | 15LF0022 | 2015-06-21 | 2015-07-19 | 2015-07-21 | 2015-07-29 | 2015-08-12 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129209 | Butay ES | CARAGA | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1 |  |  | 110315S00061 | 15LF0036 | 2015-09-20 | 2015-09-30 | 2015-10-05 | 2015-10-12 | 2015-10-15 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129210 | Caliongan Primary School | CARAGA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 110315S00062 | 15LF0036 | 2015-09-20 | 2015-09-30 | 2015-10-05 | 2015-10-12 | 2015-10-15 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | SHS (2015) | Region XI | Davao Oriental | 304307 | Caraga NHS | CARAGA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 110315S00039 | 15LF0023 | 2015-06-21 | 2015-07-03 | 2015-07-21 | 2015-07-29 | 2015-08-12 | LEGACY CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao Oriental | 304309 | Cateel Nat'l. Agri. HS | CATEEL | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110315S00031 | 15LF0029 | 2015-07-05 | 2015-07-17 | 2015-07-20 | 2015-07-28 | 2015-08-12 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao Oriental | 304311 | Cateel Voc.HS | CATEEL | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region XI | Davao Oriental | 304311 | Cateel Voc.HS | CATEEL | 1 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 5079098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Davao Oriental | 304312 | Crispin E. Rojas NHS | BAGANGA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1 |  |  | 110315S00033 | 15LF0021 | 2015-06-18 | 2015-06-29 | 2015-07-16 | 2015-07-28 | 2015-08-12 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao Oriental | 316102 | Del Pilar NHS | MANAY | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110315S00030 | 15LF0014 | 2015-05-25 | 2015-06-06 | 2015-06-08 | 2015-07-13 | 2015-07-29 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129236 | Diat PS | CARAGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2028606.04 |  |  | COMPLETED | 1 |  |  | 110315S00082 | 15LF0059 | 2015-09-20 | 2015-10-01 | 2015-10-05 | 2015-10-12 | 2015-10-21 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Davao Oriental | 304316 | Dr. Beato C. Macayra NHS | BAGANGA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110315S00034 | 15LF0021 | 2015-06-18 | 2015-06-29 | 2015-07-16 | 2015-07-28 | 2015-08-12 | FFJJ CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129212 | DRFS Estate PS | CARAGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2028606.04 |  |  | COMPLETED | 1 |  |  | 110315S00079 | 15LF0054 | 2015-09-08 | 2015-09-18 | 2015-09-21 | 2015-09-28 | 2015-10-12 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | SHS (2015) | Region XI | Davao Oriental | 304315 | E. Moralizon NVHS | MANAY | 1 | 1 | 5 | additional 1STY2CL & 1STY3CL | 2015 ADDITIONAL FUND BATCH 9 | 4455568.2979 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Davao Oriental | 304315 | E. Moralizon NVHS | MANAY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129350 | Felix Olea ES | MANAY | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129350 | Felix Olea ES | MANAY | 1 |  | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129215 | Lahi PS | CARAGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1 |  |  | 110315S00080 | 15LF0056 | 2015-09-08 | 2015-09-18 | 2015-09-21 | 2015-09-28 | 2015-10-12 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | SHS (2015) | Region XI | Davao Oriental | 304324 | Manay NHS | MANAY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110315S00036 | 15LF0026 | 2015-06-22 | 2015-07-06 | 2015-07-21 | 2015-07-29 | 2015-08-12 | LEGACY CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129333 | New Dahican ES | MANAY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2048606.04 |  |  | COMPLETED | 1 |  |  | 110315S00085 | 15LF0060 | 2015-09-20 | 2015-10-01 | 2015-10-05 | 2015-10-12 | 2015-10-21 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | SHS (2015) | Region XI | Davao Oriental | 316103 | Old Macopa NHS | MANAY | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110315S00008 | 15LF0017 | 2015-05-25 | 2015-06-06 | 2015-06-08 | 2015-07-13 | 2015-07-29 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129203 | Owabangon ES | BOSTON | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110315S00060 | 15LF0034 | 2015-07-16 | 2015-07-28 | 2015-07-29 | 2015-08-04 | 2015-08-20 | LLM CONCRETE PRODUCTS
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129222 | Panlaisan ES | CARAGA | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1 |  |  | 110315S00063 | 15LF0036 | 2015-09-20 | 2015-09-30 | 2015-10-05 | 2015-10-12 | 2015-10-15 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | SHS (2015) | Region XI | Davao Oriental | 304308 | Pantuyan NHS | CARAGA | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110315S00037 | 15LF0028 | 2015-07-05 | 2015-07-17 | 2015-07-20 | 2015-07-28 | 2015-08-12 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | SHS (2015) | Region XI | Davao Oriental | 304310 | San Antonio NHS | CATEEL | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110315S00009 | 15LF0015 | 2015-05-25 | 2015-06-06 | 2015-06-08 | 2015-07-13 | 2015-07-29 | FFJJ CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129257 | San Isidro ES | CATEEL | 1 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 110315S00065 | 15LF0033 | 2015-07-16 | 2015-07-28 | 2015-07-29 | 2015-08-04 | 2015-08-20 | LLM CONCRETE PRODUCTS
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129244 | San Jose ES | CARAGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 110315S00083 | 15LF0054 | 2015-09-08 | 2015-09-18 | 2015-09-21 | 2015-09-28 | 2015-10-12 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129225 | San Luis ES | CARAGA | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1 |  |  | 110315S00064 | 15LF0037 | 2015-07-16 | 2015-07-28 | 2015-08-20 | 2015-08-27 | 2015-09-11 | ILBI CONSTRUCTION SUPPLY & SERVICES
NC 2015 | SHS (2015) | Region XI | Davao Oriental | 304333 | San Luis NHS | CARAGA | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 110315S00038 | 15LF0030 | 2015-07-05 | 2015-07-17 | 2015-07-20 | 2015-07-28 | 2015-08-12 | FFJJ CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129227 | Sangab ES | CARAGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2028606.04 |  |  | COMPLETED | 1 |  |  | 110315S00087 | 15LF0056 | 2015-09-08 | 2015-09-18 | 2015-09-21 | 2015-09-28 | 2015-10-12 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | SHS (2015) | Region XI | Davao Oriental | 304334 | Sangab NHS | CARAGA | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110315S00010 | 15LF0016 | 2015-05-25 | 2015-06-06 | 2015-06-08 | 2015-07-13 | 2015-07-29 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Davao Oriental | 304335 | Santiago NHS | CARAGA | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6389337.6381 |  |  | COMPLETED | 1 |  |  | 110315S00015 | 15LF0028 | 2015-07-05 | 2015-07-17 | 2015-07-20 | 2015-07-28 | 2015-08-12 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129335 | Severino Taming Elementary School | MANAY | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 110315S00072 | 15LF0035 | 2015-07-16 | 2015-07-28 | 2015-07-29 | 2015-08-04 | 2015-08-20 | FFJJ CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129163 | Sunlon Elementary School | BAGANGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2008606.04 |  |  | COMPLETED | 1 |  |  | 110315S00076 | 15LF0057 | 2015-09-16 | 2015-09-28 | 2015-09-30 | 2015-10-06 | 2015-10-20 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129247 | Tagbanahaw ES | CARAGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | COMPLETED | 1 |  |  | 110315S00084 | 15LF0059 | 2015-09-20 | 2015-09-30 | 2015-10-05 | 2015-10-12 | 2015-10-21 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Davao Oriental | 304339 | Tarragona NHS | TARRAGONA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 110315S00013 | 15LF0025 | 2015-06-22 | 2015-07-06 | 2015-07-21 | 2015-07-29 | 2015-08-12 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129372 | Tengson ES | MANAY | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129372 | Tengson ES | MANAY | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Davao Oriental | 129463 | Tubaon ES | TARRAGONA | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1 |  |  | 110315S00070 | 15LF0038 | 2015-07-16 | 2015-07-28 | 2015-08-24 | 2015-09-02 | 2015-09-17 | LLM CONCRETE PRODUCTS
NC 2015 | K10 (2015) | Region XI | Digos City | 206501 | Bagumbuhay ES | CITY OF DIGOS (Capital) | 1 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4622048.49 |  |  | COMPLETED | 1 |  |  | 110215S00119 | 15LD0097 | 2015-09-23 | 2015-09-24 | 2015-10-06 | 2015-10-14 | 2015-10-23 | LTB BUILDERS & CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Digos City | 129750 | Digos City CES | CITY OF DIGOS (Capital) | 1 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10267131.51 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Digos City | 316302 | Digos City NHS - Matti HS Annex | CITY OF DIGOS (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6449337.6381 |  |  | COMPLETED | 1 |  |  | 110215S00033 | 15LD0061 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-03 | RDEN CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XI | Digos City | 304401 | Kapatagan NHS | CITY OF DIGOS (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 110215S00032 | 15LD0062 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-03 | VERGUZ CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Digos City | 129770 | Kibanban ES | CITY OF DIGOS (Capital) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 110215S00087 | 15LD0094 | 2015-09-23 | 2015-09-24 | 2015-10-06 | 2015-10-14 | 2015-10-23 | HNR CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XI | Digos City | 129755 | Mahayahay ES | CITY OF DIGOS (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1948606.04 |  |  | COMPLETED | 1 |  |  | 110215S00118 | 15LD0096 | 2015-09-23 | 2015-09-24 | 2015-10-06 | 2015-10-14 | 2015-10-23 | TWO DEGREES CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Digos City | 304402 | Ruparan NHS | CITY OF DIGOS (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8344965.051 |  |  | COMPLETED | 1 |  |  | 110215S00031 | 15LD0063 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-25 | 2015-09-03 | LEAMOR CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Island Garden City of Samal | 304216 | Anonang National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Island Garden City of Samal |  | Anonang National High School-San Jose | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6392137.6381 |  |  | COMPLETED | 1 |  |  | 110115S00140 | 1101-15-S-00110 (CNTR) | 2015-11-17 | 2015-11-20 | 2015-12-01
NC 2015 | SHS (2015) | Region XI | Island Garden City of Samal | 304220 | Balet NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3514886.575 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Island Garden City of Samal | 128728 | Catagman ES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 110115S00128 | 1101-15-S-00110 (CNTR) | 2015-11-04 | 2015-11-13 | 2015-11-24
NC 2015 | SHS (2015) | Region XI | Island Garden City of Samal | 304223 | Cogon NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110115S00076 | 1101-15-S-00076 (CNTR) | 2015-11-11 | 2015-11-20 | 2015-12-01
NC 2015 | SHS (2015) | Region XI | Island Garden City of Samal | 323402 | Del Monte National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6379337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Island Garden City of Samal | 304227 | Don Esteban Dasalla National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2730828.124 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Island Garden City of Samal | 128690 | Kaputian CES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 3 | 4673636.82 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Island Garden City of Samal | 128690 | Kaputian CES | ISLAND GARDEN CITY OF SAMAL | 2 |  | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 3 | 4673636.82 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Island Garden City of Samal | 304236 | Kaputian National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Island Garden City of Samal | 323406 | Kaputian NHS-Diosdado Alorro Ext. | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6410338 |  |  | COMPLETED | 1 |  |  | 110115S00122 | 1101-15-S-00123 (CNTR) | 2015-11-11 | 2015-11-20 | 2015-12-01
NC 2015 | SHS (2015) | Region XI | Island Garden City of Samal | 304245 | Mambago-B NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110115S00083 | 1101-15-S-00076 (CNTR) | 2015-11-11 | 2015-11-20 | 2015-12-01
NC 2015 | SHS (2015) | Region XI | Island Garden City of Samal | 304247 | Matanos NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10547131.51 |  |  | COMPLETED | 1 |  |  | 110115S00084 | 15LC0158 | 2015-08-27 | 2015-09-04 | 2015-09-17 | 2015-10-01 | 2015-10-12 | DAVAO CONCRETE PRODUCTS
NC 2015 | SHS (2015) | Region XI | Island Garden City of Samal |  | MATANOS NHS-Bandera Ext. | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6391337.6381 |  |  | COMPLETED | 1 |  |  | 110115S00141 | 1101-15-S-00110 (CNTR) | 2015-11-17 | 2015-11-20 | 2015-12-01
NC 2015 | SHS (2015) | Region XI | Island Garden City of Samal |  | Matanos NHS-Libertad Ext. | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6411137.6381 |  |  | COMPLETED | 1 |  |  | 110115S00139 | 1101-15-S-00110 (CNTR) | 2015-11-17 | 2015-11-20 | 2015-12-01
NC 2015 | SHS (2015) | Region XI | Island Garden City of Samal | 323403 | Nieves Villarica NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Island Garden City of Samal | 128607 | San Agustin ES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 110115S00129 | 1101-15-S-00110 (CNTR) | 2015-11-04 | 2015-11-13 | 2015-11-24
NC 2015 | K10 (2015) | Region XI | Island Garden City of Samal | 128608 | San Antonio ES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 110115S00120 | 1101-15-S-00110 (CNTR) | 2015-11-11 | 2015-11-20 | 2015-12-01
NC 2015 | K10 (2015) | Region XI | Island Garden City of Samal | 128696 | San Remegio ES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 110115S00118 | 1101-15-S-00110 (CNTR) | 2015-11-19 | 2015-11-20 | 2015-12-08
NC 2015 | K10 (2015) | Region XI | Island Garden City of Samal | 128697 | Sion ES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1 |  |  | 110115S00119 | 1101-15-S-00110 (CNTR) | 2015-11-19 | 2015-11-20 | 2015-12-08
NC 2015 | SHS (2015) | Region XI | Island Garden City of Samal | 304253 | Sta. Cruz NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2880828.124 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Island Garden City of Samal | 304253 | Sta. Cruz NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2820828.124 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Island Garden City of Samal | 304259 | Tagbitan-Ag NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3564886.575 |  |  | COMPLETED | 1 |  |  | 110115S00088 | 1101-15-S-00076 (CNTR) | 2015-11-13 | 2015-11-20 | 2015-12-08
NC 2015 | SHS (2015) | Region XI | Mati City | 325104 | Badas HS (Mati NCHS-Annex) | CITY OF MATI (Capital) | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.575 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | Region XI | Mati City | 304320 | BAGUMBAYAN AGRO-INDUSTRIAL HS | LUPON | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Mati City | 304301 | Banaybanay National High School | BANAYBANAY | 2 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5086910.09 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | Region XI | Mati City | 304302 | Bitaogan NHS | SAN ISIDRO | 2 | 1 | 6 | 1STY6CL (Toilet Attached) | 2015 SHS BATCH 2 | 5322651.88 |  |  | COMPLETED | 1 |  |  | 110315S00073 | 15LG0061 | 2015-06-04 | 2015-06-09 | 2015-06-23 | 2015-07-02 | 2015-07-10 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Mati City | 304303 | Bobon National High School | CITY OF MATI (Capital) | 2 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5086910.09 |  |  | COMPLETED | 1 |  |  | 110315S00014 | 15LG0036 | 2015-05-18 | 2015-05-20 | 2015-06-11 | 2015-07-07 | 2015-07-15 | LLM ENTERPRISES
NC 2015 | SHS (2015) | Region XI | Mati City | 304305 | Buso NHS | CITY OF MATI (Capital) | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1 |  |  | 110315S00032 | 15LG0037 | 2015-06-29 | 2015-07-02 | 2015-07-15 | 2015-07-28 | 2015-08-03 | LLM ENTERPRISES
NC 2015 | SHS (2015) | Region XI | Mati City | 304306 | Calapagan NHS | LUPON | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110315S00016 | 15LG0038 | 2015-05-18 | 2015-05-20 | 2015-06-11 | 2015-07-07 | 2015-07-15 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Mati City | 304328 | Davao Oriental Regional Science High School | CITY OF MATI (Capital) | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | Region XI | Mati City | 304328 | Davao Oriental Regional Science High School | CITY OF MATI (Capital) | 2 |  | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | Region XI | Mati City | 304314 | Don Enrique Lopez NHS | CITY OF MATI (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110315S00022 | 15LG0068 | 2015-07-13 | 2015-07-15 | 2015-07-28 | 2015-08-07 | 2015-08-17 | LLM ENTERPRISES
NC 2015 | SHS (2015) | Region XI | Mati City | 316106 | Don Mariano Marcos NHS | LUPON | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2840828.124 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | Region XI | Mati City | 316106 | Don Mariano Marcos NHS | LUPON | 2 |  | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2890828.124 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | Region XI | Mati City | 316104 | DON SALVADOR LOPEZ NHS | CITY OF MATI (Capital) | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.575 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | Region XI | Mati City | 316107 | Leandro G. Japos NHS | BANAYBANAY | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | Region XI | Mati City | 304318 | Libudon National High School | CITY OF MATI (Capital) | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3524886.575 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | Region XI | Mati City | 304321 | Lupon NCHS (Lupon Voc'l. HS - Annex B) | LUPON | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Mati City | 304321 | Lupon NCHS (Lupon Voc'l. HS - Annex B) | LUPON | 2 |  | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region XI | Mati City | 304319 | Lupon Voc. HS | LUPON | 2 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Mati City | 304319 | Lupon Voc. HS | LUPON | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Mati City | 304322 | Luzon National High School | GOVERNOR GENEROSO | 2 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5086910.09 |  |  | COMPLETED | 1 |  |  | 110314S00062 | 14LG0023 | 2014-07-02 | 2014-07-04 | 2014-07-17 | 2014-09-12 | 2014-10-01 | RITZTOK CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region XI | Mati City | 325105 | Macambol NHS (Dawan NHS-Annex) | CITY OF MATI (Capital) | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | Region XI | Mati City | 325105 | Macambol NHS (Dawan NHS-Annex) | CITY OF MATI (Capital) | 2 |  | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | Region XI | Mati City | 304323 | Macangao Agri. VHS | LUPON | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110315S00047 | 15LG0041 | 2015-05-18 | 2015-05-20 | 2015-06-11 | 2015-07-07 | 2015-07-25 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Mati City | 304317 | Manuel S. Nasser, Sr. NHS | SAN ISIDRO | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1 |  |  | 110315S00058 | 15LG0077 | 2015-07-13 | 2015-07-15 | 2015-07-28 | 2015-08-07 | 2015-08-17 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Mati City | 316101 | Marayag NHS (Calapagan NHS - Annex) | LUPON | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110315S00040 | 15LG0042 | 2015-05-18 | 2015-05-20 | 2015-06-11 | 2015-07-07 | 2015-07-15 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Mati City | 304325 | Mati NCHS | CITY OF MATI (Capital) | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.58 |  |  | COMPLETED | 1 |  |  | 110314S00057 | 14LG0024 | 2014-07-02 | 2014-07-04 | 2014-07-17 | 2014-09-12 | 2014-10-01 | LOTRIM CONSTRUCTION, INC.
NC 2015 | SHS (2015) | Region XI | Mati City | 304326 | Mati School of Arts and Trade | CITY OF MATI (Capital) | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.58 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Mati City | 304327 | Matiao National High School | CITY OF MATI (Capital) | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Mati City | 304329 | Nangan NHS | GOVERNOR GENEROSO | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1 |  |  | 110315S00005 | 15LG0044 | 2015-05-18 | 2015-05-20 | 2015-06-11 | 2015-07-07 | 2015-07-15 | JECEL CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region XI | Mati City | 129315 | New Visayas ES | LUPON | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 110315S00071 | 15LG0083 | 2015-07-13 | 2015-07-15 | 2015-07-28 | 2015-12-15 | 2015-12-21 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Mati City | 316105 | Paniquian NHS | BANAYBANAY | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110315S00006 | 15LG0045 | 2015-05-18 | 2015-05-20 | 2015-06-11 | 2015-07-07 | 2015-07-15 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Mati City | 304330 | Pundaguitan NHS | GOVERNOR GENEROSO | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.58 |  |  | COMPLETED | 1 |  |  | 110315S00103 | 15LG0104 | 2015-08-13 | 2015-07-15 | 2015-08-26 | 2015-09-03 | 2015-09-09 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Mati City | 304331 | Puntalinao NHS | BANAYBANAY | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110315S00043 | 15LG0047 | 2015-05-18 | 2015-05-20 | 2015-06-11 | 2015-07-07 | 2015-07-15 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Mati City | 304332 | San Isidro National High School | SAN ISIDRO | 2 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5086910.09 |  |  | REVERTED | 0 |  |  | 110315S00102 | 15LG0101 | 2015-08-13 | 2015-07-15 | 2015-08-26 | 2015-09-03 | 2015-09-09 | LLM ENTERPRISES
NC 2015 | SHS (2015) | Region XI | Mati City | 304336 | Sigaboy Agricultural Vocational HS | GOVERNOR GENEROSO | 2 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5086910.09 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Mati City | 304337 | Tagugpo NHS | LUPON | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1 |  |  | 110315S00024 | 15LG0049 | 2015-05-18 | 2015-05-20 | 2015-06-11 | 2015-07-07 | 2015-07-15 | JECEL CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | Region XI | Mati City | 304338 | Taguibo Agricultural Vocational High School | CITY OF MATI (Capital) | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | Region XI | Mati City | 304338 | Taguibo Agricultural Vocational High School | CITY OF MATI (Capital) | 2 |  | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Mati City | 304340 | Tibanban NHS | GOVERNOR GENEROSO | 2 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 5 | 15196328 |  |  | REVERTED | 0 |  |  | 110315S00074 | 15LG0119 | 2015-10-25
NC 2015 | SHS (2015) | Region XI | Panabo City | 304403 | A. O. Floirendo National High School | CITY OF PANABO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110115S00057 | 1101-15-S-00057 (CNTR) | 2015-11-11 | 2015-11-20 | 2015-12-01
NC 2015 | SHS (2015) | Region XI | Panabo City | 304405 | Don Manuel A. Javellana Memorial National High School | CITY OF PANABO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110115S00063 | 1101-15-S-00042 (CNTR) | 2015-11-19 | 2015-11-20 | 2015-12-08
NC 2015 | K10 (2015) | Region XI | Panabo City | 129782 | Dona Nenita R. Floirendo ES | CITY OF PANABO | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110115S00115 | 1101-15-S-00110 (CNTR) | 2015-11-17 | 2015-11-20 | 2015-12-01
NC 2015 | K10 (2015) | Region XI | Panabo City | 129805 | J.P Laurel ES | CITY OF PANABO | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110115S00133 | 15LC0179 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-27 | 2015-11-09 | RCBAR BUILDERS
NC 2015 | SHS (2015) | Region XI | Panabo City | 316403 | Kauswagan National High School | CITY OF PANABO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110115S00042 | 1101-15-S-00042 (CNTR) | 2015-11-19 | 2015-11-20 | 2015-12-08
NC 2015 | K10 (2015) | Region XI | Panabo City | 129810 | Kiotoy ES | CITY OF PANABO | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110115S00106 | 1101-15-S-00106 (CNTR) | 2015-11-19 | 2015-11-20 | 2015-12-08
NC 2015 | SHS (2015) | Region XI | Panabo City | 304409 | Little Panay National High School | CITY OF PANABO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110115S00074 | 15LC0149 | 2015-08-27 | 2015-09-04 | 2015-09-17 | 2015-10-01 | 2015-10-12 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | K10 (2015) | Region XI | Panabo City | 304406 | Malativas National High School | CITY OF PANABO | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110115S00116 | 15LC0185 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-27 | 2015-11-09 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Panabo City | 304407 | Manay National High School | CITY OF PANABO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Panabo City | 304408 | Panabo National High School | CITY OF PANABO | 2 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region XI | Panabo City | 304408 | Panabo National High School | CITY OF PANABO | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Panabo City | 316405 | QUEZON HIGH SCHOOL - PANABO NHS ANNEX | CITY OF PANABO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 110115S00071 | 1101-15-S-00048 (CNTR) | 2015-07-16 | 2015-07-17 | 2015-11-26
NC 2015 | K10 (2015) | Region XI | Panabo City | 129796 | Rodrigo D. Mabitad Sr. ES | CITY OF PANABO | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110115S00127 | 15LC0176 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-27 | 2015-11-09 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Panabo City | 316402 | San Vicente National High School | CITY OF PANABO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1 |  |  | 110115S00067 | 15LC0152 | 2015-08-27 | 2015-09-04 | 2015-09-17 | 2015-10-01 | 2015-10-12 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Panabo City |  | SHS in Panabo City | CITY OF PANABO | 2 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31570890 |  |  | COMPLETED | 1 |  |  | 110115S00123 | 15LC0188 | 2015-10-01 | 2015-10-09 | 2015-10-22 | 2015-11-09 | 2015-11-16 | FFJJ CONSTRUCTION
NC 2015 | K10 (2015) | Region XI | Panabo City | 129799 | Southern Davao ES | CITY OF PANABO | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110115S00126 | 15LC0177 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-27 | 2015-11-09 | MAG CORPORATION
NC 2015 | SHS (2015) | Region XI | Panabo City | 316401 | Southern Davao National High School | CITY OF PANABO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Panabo City | 129800 | Tibungol ES | CITY OF PANABO | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110115S00125 | 15LC0178 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-27 | 2015-11-09 | MAG CORPORATION
NC 2015 | SHS (2015) | Region XI | Tagum City | 304231 | Jose Tuason Jr. Memorial National High School | CITY OF TAGUM (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110115S00085 | 15OLC0155 | 2015-08-27 | 2015-09-04 | 2015-09-17 | 2015-10-01 | 2015-10-12 | DAVAO CONCRETE PRODUCTS
NC 2015 | K10 (2015) | Region XI | Tagum City | 128777 | LA FILIPINA ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 110115S00130 | 15LC0180 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-27 | 2015-11-09 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Tagum City | 304238 | La Filipina NHS | CITY OF TAGUM (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 14947518.84 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Tagum City | 304226 | Laureta National High School | CITY OF TAGUM (Capital) | 1 | 1 | 10 | 2STY10CL | 2015 ADDITIONAL FUND BATCH 9 | 4406345.042 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Tagum City | 304226 | Laureta National High School | CITY OF TAGUM (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Tagum City | 128778 | MANKILAM ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110115S00132 | 15LC0182 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-27 | 2015-11-09 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XI | Tagum City | 304232 | Pipisan Maug National High School | CITY OF TAGUM (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 110115S00078 | 15LC0156 | 2015-08-27 | 2015-09-04 | 2015-09-17 | 2015-10-01 | 2015-10-12 | DAVAO CONCRETE PRODUCTS
NC 2015 | SHS (2015) | Region XI | Tagum City | 500424 | Pipisan Maug NHS - Busaon Ext. | CITY OF TAGUM (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2188606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XI | Tagum City | 128772 | RIZAL I ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 3 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 110115S00114 | 15LC0161 | 2015-08-27 | 2015-09-04 | 2015-09-17 | 2015-10-01 | 2015-10-12 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XI | Tagum City | 304225 | Tagum City National Comprehensive High School | CITY OF TAGUM (Capital) | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 14917518.84 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Tagum City | 500426 | Tagum City National Comprehensive HS - Pandapan Ext. | CITY OF TAGUM (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Tagum City | 304260 | Tagum City NHS | CITY OF TAGUM (Capital) | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 1 | 22202343.62 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Tagum City |  | Tagum City NHS - Canocotan Ext. | CITY OF TAGUM (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XI | Tagum City | 304261 | TAGUM NATIONAL TRADE SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 110115S00049 | 15LC0160 | 2015-08-27 | 2015-09-04 | 2015-09-17 | 2015-10-01 | 2015-10-12 | DAVAO CONCRETE PRODUCTS
NC 2015 | K10 (2015) | Region XI | Tagum City | 128785 | UNION ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 110115S00131 | 15LC0181 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-27 | 2015-11-09 | FIVE MASSIVE INFRA & SUPPLY CORP.
NC 2016 | SHS | Region XI | Compostela Valley | 304200 | Awao Nhs | Monkayo | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9271461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-03
NC 2016 | SHS | Region XI | Compostela Valley | 304176 | Babag Nhs | Monkayo | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-02 |  | R. Semilla Const. & Marketing
NC 2016 | SHS | Region XI | Compostela Valley | 304177 | Bantacan Nhs | New Bataan | 1 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13872542.8037 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-03
NC 2016 | SHS | Region XI | Compostela Valley | 304180 | Camanlangan Nhs | New Bataan | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2964910.9364 |  |  | Completed | 1 |  |  |  |  | 2016-05-04 |  | 2016-05-24 | 2016-06-07 | 2016-06-29 | R.R. Seismundo Const. & Supply
NC 2016 | SHS | Region XI | Compostela Valley | 304181 | Compostela Nhs | Compostela | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Compostela Valley | 304181 | Compostela Nhs | Compostela | 1 |  | 12 | 3STY12CL | BATCH 11 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Compostela Valley | 304184 | Consuelo M. Valderrama Nhs | Compostela | 1 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13972542.8037 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-03
NC 2016 | SHS | Region XI | Compostela Valley | 304187 | Gabi Nhs | Compostela | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-05-31 |  | 2016-06-24 | 2016-08-08 |  | Davao Concrete Products
NC 2016 | SHS | Region XI | Compostela Valley | 304187 | Gabi Nhs | Compostela | 1 |  | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2006-08-03 |  | Davao Concrete Products
NC 2016 | K10 | Region XI | Compostela Valley | 315813 | Langgawisan National High School | Maragusan (San Mariano) | 1 | 1 | 4 | 1STY2CL | BATCH 9 CL | 4391671.221 |  |  | Completed | 1 |  |  |  |  | 2016-05-04 |  | 2016-05-24 | 2016-06-07 | 2016-06-29 | Mark Anthony Const. & Supply
NC 2016 | SHS | Region XI | Compostela Valley | 304182 | Mangayon Nhs | Compostela | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9121461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-07-22 |  | 2016-08-10
NC 2016 | SHS | Region XI | Compostela Valley | 304196 | Maparat Nhs | Compostela | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2096214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-06-03 |  | 2016-06-23 | 2016-08-03 |  | Davao Concrete Products
NC 2016 | SHS | Region XI | Compostela Valley | 304197 | Mapawa Nhs | Maragusan (San Mariano) | 1 | 1 | 4 | 1STY4CL | BATCH 9 CL | 4111375.2325 |  |  | Completed | 1 |  |  |  |  | 2016-05-04 |  | 2016-05-24 | 2016-06-09 | 2016-06-29 | Dingo Builders & Supply
NC 2016 | SHS | Region XI | Compostela Valley | 304198 | Maragusan Nhs | Maragusan (San Mariano) | 1 | 1 | 30 | 3STY15CL | BATCH 9 CL | 47212629.59 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-07-29 | 2016-08-08
NC 2016 | SHS | Region XI | Compostela Valley | 304204 | Mayaon Nhs | Montevista | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2964910.9364 |  |  | Completed | 1 |  |  |  |  | 2016-05-04 |  | 2016-05-24 | 2016-06-24 | 2016-07-01 | Two Degrees Const. & Supply
NC 2016 | SHS | Region XI | Compostela Valley | 304199 | Monkayo Nhs | Monkayo | 1 | 1 | 15 | 3STY15CL | BATCH 9 CL | 23556314.795 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-07-29 | 2016-08-08
NC 2016 | SHS | Region XI | Compostela Valley | 304199 | Monkayo Nhs | Monkayo | 1 |  | 16 | 4STY16CL | BATCH 9 CL | 26902160 |  |  | Completed | 1 |  |  |  |  | 2016-06-03 |  | 2016-06-23 | 2016-07-01 |  | Davao Concrete Products
NC 2016 | K10 | Region XI | Compostela Valley | 315801 | Monkayo Nhs- Casoon Hs Annex | Monkayo | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7086271.4019 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-02
NC 2016 | SHS | Region XI | Compostela Valley | 304202 | Montevista Nhs | Montevista | 1 | 1 | 18 | 3STY9CL | BATCH 9 CL | 27248390.256 |  |  | Completed | 1 |  |  |  |  | 2016-07-11 |  | 2016-08-01
NC 2016 | K10 | Region XI | Compostela Valley | 304203 | Montevista Nhs - Annex (Dnas Campus) | Montevista | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6996271.4019 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-03
NC 2016 | K10 | Region XI | Compostela Valley | 128442 | Mt. Diwata Es | Monkayo | 1 | 1 | 24 | 2STY8CL | BATCH 13 CL | 47507307.775 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Compostela Valley | 315815 | New Albay Nhs | Maragusan (San Mariano) | 1 | 1 | 8 | 2STY4CL | BATCH 9 CL | 14272542.8037 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-07-29 | 2016-08-08
NC 2016 | SHS | Region XI | Compostela Valley | 304206 | New Bataan Nhs | New Bataan | 1 | 1 | 16 | 2STY8CL | BATCH 9 CL | 23960153.7017 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-03
NC 2016 | SHS | Region XI | Compostela Valley | 304207 | Paloc Nhs | Maragusan (San Mariano) | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3154910.9364 |  |  | Completed | 1 |  |  |  |  | 2016-06-03 |  | 2016-06-23 | 2016-08-05 | 2016-08-12 | AB Aponesto Const. Parts & Supply
NC 2016 | SHS | Region XI | Compostela Valley | 304183 | San Miguel Nhs | Compostela | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2904910.9364 |  |  | Completed | 1 |  |  |  |  | 2016-06-03 |  | 2016-06-23
NC 2016 | SHS | Region XI | Compostela Valley | 304210 | Siocon Nhs | Compostela | 1 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3811375.2325 |  |  | Completed | 1 |  |  |  |  | 2016-06-03 |  | 2016-06-23 | 2016-08-03 | 2016-08-12 | AB Aponesto Const. Parts and Supply
NC 2016 | SHS | Region XI | Compostela Valley | 304212 | Tubo-Tubo Nhs | Monkayo | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6996271.4019 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-03
NC 2016 | SHS | Region XI | Compostela Valley | 304212 | Tubo-Tubo Nhs | Monkayo | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 9081461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-05-31 |  | 2016-06-24 | 2016-07-01 |  | Legacy Construction
NC 2016 | SHS | Region XI | Compostela Valley | 304213 | Tupaz Nhs | Maragusan (San Mariano) | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9521461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-05-31 |  | 2016-06-24 | 2016-06-28 | 2016-07-29 | R.R. Seismundo Const. & Supply
NC 2016 | K10 | Region XI | Compostela Valley | 315808 | Ulip National High School | Monkayo | 1 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13932542.8037 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-02
NC 2016 | SHS | Region XI | Compostela Valley | 304172 | Andili Nhs | Mawab | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 |  |  |  |  | 2016-05-04 |  | 2016-05-24 | 2016-06-08 | 2016-06-29
NC 2016 | SHS | Region XI | Compostela Valley | 304173 | Anibongan Nhs | Maco | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-03
NC 2016 | SHS | Region XI | Compostela Valley | 304174 | Anitapan Nhs | Mabini (Doña Alicia) | 2 | 1 | 4 | 1STY2CL | BATCH 9 CL | 4292428.3827 |  |  | Completed | 1 |  |  |  |  | 2016-05-04 |  | 2016-05-24 | 2016-06-08 | 2016-06-29
NC 2016 | SHS | Region XI | Compostela Valley | 304175 | Araibo Nhs | Pantukan | 2 | 1 | 8 | 2STY4CL | BATCH 9 CL | 14272542.8037 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-07-25 | 2016-08-08
NC 2016 | K10 | Region XI | Compostela Valley | 304193 | Atty. Orlando S. Rimando National High School | Maco | 2 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26952160 |  |  | Completed | 1 |  |  |  |  | 2016-06-03 |  | 2016-06-23 | 2016-07-14
NC 2016 | K10 | Region XI | Compostela Valley | 304193 | Atty. Orlando S. Rimando National High School | Maco | 2 |  | 20 | 4STY20CL | BATCH 9 CL | 32253160 |  |  | Completed | 1 |  |  |  |  | 2016-06-03 |  | 2016-06-23 | 2016-07-14
NC 2016 | SHS | Region XI | Compostela Valley | 304178 | Bayabas Nhs | Nabunturan (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6996271.4019 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28
NC 2016 | SHS | Region XI | Compostela Valley | 304179 | Bongabong Nhs | Pantukan | 2 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13872542.8037 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-03
NC 2016 | SHS | Region XI | Compostela Valley | 304185 | Don Vicente Romualdez Nhs | Laak (San Vicente) | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9571461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-03 | 2016-08-12
NC 2016 | SHS | Region XI | Compostela Valley | 304186 | Elizalde Nhs | Maco | 2 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13872542.8037 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-07-29 | 2016-08-08
NC 2016 | SHS | Region XI | Compostela Valley | 315806 | Kao Nhs | Nabunturan (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-05-31 |  | 2016-06-24 | 2016-06-30
NC 2016 | SHS | Region XI | Compostela Valley | 304188 | Kapatagan National High School | Laak (San Vicente) | 2 | 1 | 4 | 1STY4CL | BATCH 9 CL | 4061375.2325 |  |  | Completed | 1 |  |  |  |  | 2016-05-04 |  | 2016-05-24 | 2016-06-08 | 2016-06-29
NC 2016 | SHS | Region XI | Compostela Valley | 304190 | Kidawa Nhs | Laak (San Vicente) | 2 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3195402.03 |  |  | Completed | 1 |  |  |  |  | 2016-05-04 |  | 2016-05-24 | 2016-06-07 | 2016-06-29
NC 2016 | SHS | Region XI | Compostela Valley | 304189 | Laak Nhs | Laak (San Vicente) | 2 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16350160 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-07-29 | 2016-08-08
NC 2016 | SHS | Region XI | Compostela Valley | 304189 | Laak Nhs | Laak (San Vicente) | 2 |  | 12 | 3STY12CL | BATCH 9 CL | 20129495.669 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-07-29 | 2016-08-08
NC 2016 | K10 | Region XI | Compostela Valley | 128311 | Longanapan Es | Laak (San Vicente) | 2 | 1 | 4 | 1STY4CL | BATCH 13 CL | 4284765.658 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Compostela Valley | 128311 | Longanapan Es | Laak (San Vicente) | 2 |  | 6 | 1STY3CL | BATCH 13 CL | 6585703.368 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Compostela Valley | 304191 | Lorenzo S. Sarmiento Sr. Nhs | Mawab | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-05-31 |  | 2016-06-24 | 2016-08-03
NC 2016 | SHS | Region XI | Compostela Valley | 304191 | Lorenzo S. Sarmiento Sr. Nhs | Mawab | 2 |  | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-03
NC 2016 | SHS | Region XI | Compostela Valley | 304192 | Mabini Nhs | Mabini (Doña Alicia) | 2 | 1 | 12 | 2STY6CL | BATCH 9 CL | 18042923.1122 |  |  | Completed | 1 |  |  |  |  | 2016-06-03 |  | 2016-06-23 | 2016-06-30 | 2016-07-11
NC 2016 | SHS | Region XI | Compostela Valley | 315807 | Magnaga Nhs | Pantukan | 2 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13872542.8037 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28
NC 2016 | SHS | Region XI | Compostela Valley | 304194 | Mainit Nhs | Nabunturan (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-05-31 |  | 2016-06-24 | 2016-08-03
NC 2016 | SHS | Region XI | Compostela Valley | 304195 | Manat Nhs | Nabunturan (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-05-31 |  | 2016-06-24
NC 2016 | SHS | Region XI | Compostela Valley | 315804 | Melale Nhs | Laak (San Vicente) | 2 | 1 | 4 | 1STY4CL | BATCH 9 CL | 4111375.2325 |  |  | Completed | 1 |  |  |  |  | 2016-05-04 |  | 2016-05-24 | 2016-06-07 | 2016-07-29
NC 2016 | SHS | Region XI | Compostela Valley | 304205 | Nabunturan Nchs | Nabunturan (Capital) | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 32253160 |  |  | Completed | 1 |  |  |  |  | 2016-06-03 |  | 2016-06-23
NC 2016 | SHS | Region XI | Compostela Valley | 304205 | Nabunturan Nchs | Nabunturan (Capital) | 2 |  | 15 | 3STY15CL | BATCH 9 CL | 23606314.795 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28
NC 2016 | SHS | Region XI | Compostela Valley | 315816 | Napnapan Nhs | Pantukan | 2 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13872542.8037 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-04 | 2016-08-15
NC 2016 | SHS | Region XI | Compostela Valley | 315818 | New Sibonga Nhs | Nabunturan (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-06-03 |  | 2016-06-23 | 2016-06-28
NC 2016 | SHS | Region XI | Compostela Valley | 315802 | Nuevo Iloco Nhs | Mawab | 2 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13872542.8037 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-05
NC 2016 | K10 | Region XI | Compostela Valley | 128554 | Panganason Es | Pantukan | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2345713.3084 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Compostela Valley | 304208 | Pantukan National High School | Pantukan | 2 | 1 | 24 | 3STY12CL | BATCH 9 CL | 40258991.338 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28
NC 2016 | SHS | Region XI | Compostela Valley | 315805 | Pindasan Nhs | Mabini (Doña Alicia) | 2 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13872542.8037 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-07-14
NC 2016 | SHS | Region XI | Compostela Valley | 315812 | San Antonio National High School | Laak (San Vicente) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7436271.4019 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 |  | 2016-06-28 | 2016-08-03 | 2016-08-12
NC 2016 | SHS | Region XI | Compostela Valley | 304209 | Tagugpo Nhs | Pantukan | 2 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3004910.9364 |  |  | Completed | 1 |  |  |  |  | 2016-05-04 |  | 2016-05-24 | 2016-06-09 | 2016-06-29
NC 2016 | SHS | Region XI | Compostela Valley | 304211 | Tambongon Nhs | Pantukan | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-05-31 |  | 2016-06-24 | 2016-07-29
NC 2016 | K10 | Region XI | Compostela Valley | 315803 | Tuboran National High School | Mawab | 2 | 1 | 6 | 1STY2CL | BATCH 9 CL | 6088642.5741 |  |  | Completed | 1 |  |  |  |  | 2016-05-04 |  | 2016-05-24 | 2016-06-20 | 2016-06-29
NC 2016 | SHS | Region XI | Davao City | 304360 | Davao City National High School | Davao City | 1 | 1 | 40 | 4STY20CL | BATCH 11 CL | 62205780.54 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao City | 304360 | Davao City National High School | Davao City | 1 |  | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao City | 304363 | Davao City Special National High School | Davao City | 1 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22277343.62 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao City | 304365 | Erico T. Nograles Nhs | Davao City | 1 | 1 | 6 | 3STY6CL | BATCH 13 CL | 10887131.51 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao City | 304377 | Jesus J. Soriano National High School | Davao City | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao City | 304377 | Jesus J. Soriano National High School | Davao City | 1 |  | 6 | 3STY6CL | BATCH 9 CL | 10417131.51 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao City | 304375 | Maa National High School | Davao City | 1 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26952469.42 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao City | 304375 | Maa National High School | Davao City | 1 |  | 16 | 4STY8CL | BATCH 9 CL | 29895038 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao City |  | Shs Within Cp Garcia Es (Formerly In Sta. Ana Es) | Davao City | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao City |  | Shs Within Cp Garcia Es (Formerly In Sta. Ana Es) | Davao City | 1 |  | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao City |  | Shs Within Cp J.P Rizal Es (Formerly In Sta. Ana Es) | Davao City | 1 |  | 24 | 4STY24CL | BATCH 11 CL | 35596257.14 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao City | 304359 | Sir Es To Daniel R. Aguinaldo Nhs (Matina Nhs) | Davao City | 1 | 1 | 40 | 4STY20CL | BATCH 9 CL | 62555780.54 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao City | 304359 | Sir Es To Daniel R. Aguinaldo Nhs (Matina Nhs) | Davao City | 1 |  | 16 | 4STY16CL | BATCH 9 CL | 26952469.42 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao City | 304341 | Alejandra L. Navarro Nhs | Davao City | 2 | 1 | 32 | 4STY16CL | BATCH 5 CL | 53904938.84 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao City | 304346 | Cabantian Nhs | Davao City | 2 | 1 | 15 | 3STY15CL | BATCH 13 CL | 21733013.45 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao City | 304366 | F. Bangoy Nhs | Davao City | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31277890.27 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao City | 304366 | F. Bangoy Nhs | Davao City | 2 |  | 8 | 4STY8CL | BATCH 9 CL | 14947519 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao City | 304368 | F. Bustamante Nhs | Davao City | 2 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26952469.42 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao City | 304368 | F. Bustamante Nhs | Davao City | 2 |  | 16 | 4STY8CL | BATCH 5 CL | 29895038 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao City | 304368 | F. Bustamante Nhs | Davao City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao City | 304354 | Calinan Nhs | Davao City | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31725000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao City | 304354 | Calinan Nhs | Davao City | 3 |  | 24 | 4STY12CL | BATCH 9 CL | 44970000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao City | 304356 | Crossing Bayabas Nhs | Davao City | 3 | 1 | 40 | 4STY20CL | BATCH 9 CL | 63450000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao City | 304356 | Crossing Bayabas Nhs | Davao City | 3 |  | 12 | 4STY12CL | BATCH 9 CL | 22485000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao City | 304356 | Crossing Bayabas Nhs | Davao City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao City | 304361 | Dona Carmen Denia Nhs | Davao City | 3 | 1 | 80 | 4STY20CL | BATCH 9 CL | 126900000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao City | 304361 | Dona Carmen Denia Nhs | Davao City | 3 |  | 24 | 4STY12CL | BATCH 9 CL | 44970000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao City | 304361 | Dona Carmen Denia Nhs | Davao City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao City | 304362 | Dona Carmen Denia Nhs - J. V. Ferriols Hs | Davao City | 3 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22485000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao City | 304362 | Dona Carmen Denia Nhs - J. V. Ferriols Hs | Davao City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao City | 316212 | Jose T. Quiboloy Sr. National High School | Davao City | 3 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11030000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao City | 304373 | Los Amigos Nhs | Davao City | 3 | 1 | 24 | 4STY12CL | BATCH 5 CL | 44970000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao City | 304387 | Mintal Nchs - Tugbok National Hs | Davao City | 3 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao City | 316208 | Suawan High School- Annex Of Lower Tamugan National High School | Davao City | 3 | 1 | 8 | 2STY8CL | BATCH 5 CL | 11030000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Norte | 304217 | Asuncion National High School | Asuncion (Saug) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2663550.36 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Norte | 304217 | Asuncion National High School | Asuncion (Saug) | 1 | 1 | 15 | 3STY15CL | BATCH 13 CL | 22819748.25 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Norte | 304234 | Capungangan Hs | Kapalong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Norte | 304224 | Datu Balong Nhs | Kapalong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2670825.9001 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Norte | 304258 | Datu Jose A. Libayao Memorial Nhs | Talaingod | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2673442.2285 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Norte | 304228 | Doña Carmen Soriano National High School | Kapalong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Norte | 304233 | Kapalong National High School | Kapalong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Norte | 304233 | Kapalong National High School | Kapalong | 1 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31720020 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Norte | 304239 | Limbaan Nhs | New Corella | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2661610.216 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Norte | 304241 | Luna Nhs | Kapalong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Norte | 304248 | New Corella Nhs | New Corella | 1 | 1 | 24 | 4STY24CL | BATCH 3 CL | 37599959.52 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Norte | 304248 | New Corella Nhs To New Corella Nhs (Magcum Annex) | New Corella | 1 |  | 1 | 1STY1CL | BATCH 3 CL | 1076106.23 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Norte | 304248 | New Corella Nhs | New Corella | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2783149.6 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Norte | 304218 | Sagayen Nhs | Asuncion (Saug) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2663550.36 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Norte | 304251 | Sawata Nhs | San Isidro | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2676213.7655 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Norte | 304251 | Sawata Nhs | San Isidro | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8518325.4119 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Norte | 304243 | Semong Nhs | Kapalong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2513682.5141 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Norte | 304252 | Sonlon Nhs | Asuncion (Saug) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2693622.5922 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Norte | 304221 | Antonio V. Fruto Sr. Nhs | Braulio E. Dujali | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2663550.36 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Norte | 304222 | Carmen Nhs | Carmen | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Norte | 304229 | Dujali National High School | Braulio E. Dujali | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Norte | 304237 | Kimamon Nhs | Santo Tomas | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Norte | 304256 | Salvacion Nhs | Santo Tomas | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Norte | 304254 | Sto Tomas Nhs | Santo Tomas | 2 | 1 | 32 | 4STY32CL | BATCH 3 CL | 48329389.36 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Norte | 304254 | Sto Tomas Nhs | Santo Tomas | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 5510538.02 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Norte | 315901 | Tubod National High School | Carmen | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Norte | 315902 | Tulalian Nhs | Santo Tomas | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 129089 | Agripina Es | Santa Cruz | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6398000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 129093 | Anastacio G. Canda Elementary School | Santa Cruz | 1 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1970000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 129076 | Astorga Ces | Santa Cruz | 1 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1970000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 304289 | Bangkal Nhs | Matanao | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15197828 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 304289 | Bangkal Nhs | Matanao | 1 |  | 6 | 3STY6CL | BATCH 9 CL | 10468132 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 304265 | Barayong Nhs | Magsaysay | 1 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22248344 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 304265 | Barayong Nhs | Magsaysay | 1 |  | 8 | 4STY8CL | BATCH 9 CL | 14961519 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 304265 | Barayong Nhs | Magsaysay | 1 |  | 6 | 3STY6CL | BATCH 9 CL | 10465132 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Sur | 304265 | Barayong Nhs | Magsaysay | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2518000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 304295 | Bato Nhs | Santa Cruz | 1 | 1 | 8 | 2STY4CL | BATCH 5 CL | 12812000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 129079 | Don Amancio Bendigo Sr. Es | Santa Cruz | 1 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 205008 | Don Sergio Osmena Es | Padada | 1 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1115000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Sur | 304263 | Federico Yap National High School | Santa Cruz | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2525000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 304263 | Federico Yap National High School | Santa Cruz | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 24496577.982 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 205011 | Fidel Razonable Ps | Padada | 1 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1115000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 129036 | Glot Towak Es | Matanao | 1 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2861000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 304275 | Hagonoy National High School | Hagonoy | 1 | 1 | 24 | 4STY12CL | BATCH 1 CL | 44544687.24 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Sur | 304275 | Hagonoy National High School | Hagonoy | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2517000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 205010 | Harada Butai Ps | Padada | 1 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1115000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 129081 | Inawayan Es | Santa Cruz | 1 | 1 | 1 | 1STY1CL | BATCH 13 CL | 1114000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 129081 | Inawayan Es | Santa Cruz | 1 |  | 12 | 3STY12CL | BATCH 13 CL | 20077495.669 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 304278 | Inawayan National High School | Santa Cruz | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15202328 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 304278 | Inawayan National High School | Santa Cruz | 1 |  | 4 | 2STY4CL | BATCH 9 CL | 6342058.0075 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Sur | 304278 | Inawayan National High School | Santa Cruz | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2520000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 304284 | Lower Bala Nhs | Magsaysay | 1 | 1 | 12 | 3STY12CL | BATCH 5 CL | 18324269 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Sur | 304284 | Lower Bala Nhs | Magsaysay | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2518500 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 205009 | Lower Katipunan Es | Padada | 1 | 1 | 3 | 1STY2CL | BATCH 5 CL | 1995000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 128937 | Maibo Es | Magsaysay | 1 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2891000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Sur | 304286 | Marber Nhs | Bansalan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2518500 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 304288 | Matanao National High School | Matanao | 1 | 1 | 40 | 4STY20CL | BATCH 5 CL | 62485781 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 304288 | Matanao National High School | Matanao | 1 |  | 12 | 3STY12CL | BATCH 5 CL | 18306269 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 316002 | Padada Nhs | Padada | 1 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15184328 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 316002 | Padada Nhs | Padada | 1 |  | 6 | 3STY6CL | BATCH 5 CL | 10459132 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Sur | 316002 | Padada Nhs | Padada | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2517000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Sur | 304285 | Pedro A. Arches Nhs | Bansalan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2519000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 304285 | Pedro A. Arches Nhs | Bansalan | 1 | 1 | 24 | 4STY12CL | BATCH 13 CL | 44520687.24 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Sur | 316004 | Sacub High School Annex | Hagonoy | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 316003 | Salud Cagas Tech.& Voc. H.S | Matanao | 1 | 1 | 6 | 3STY6CL | BATCH 5 CL | 10471132 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 316003 | Salud Cagas Tech.& Voc. H.S | Matanao | 1 |  | 4 | 2STY4CL | BATCH 5 CL | 6418000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Sur | 316003 | Salud Cagas Tech.& Voc. H.S | Matanao | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2520000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 304279 | Sibulan Nhs | Santa Cruz | 1 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15281328 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 304279 | Sibulan Nhs | Santa Cruz | 1 |  | 1 | 1STY1CL | BATCH 5 CL | 1043000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 304290 | Sinawilan Nhs | Matanao | 1 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22236344 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 304294 | Sta. Cruz National High School | Santa Cruz | 1 | 1 | 24 | 4STY24CL | BATCH 9 CL | 36270000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 304294 | Sta. Cruz National High School | Santa Cruz | 1 |  | 12 | 3STY12CL | BATCH 9 CL | 18282269 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 304294 | Sta. Cruz National High School | Santa Cruz | 1 |  | 15 | 3STY15CL | BATCH 9 CL | 21457082.1016 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Occidental | 304294 | Sta. Cruz National High School | Don Marcelino | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Sur | 304298 | Tacul Agrc'L Vhs (Tacul Nhs) | Magsaysay | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2525000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 304298 | Tacul Agrc'L Vhs (Tacul Nhs) | Magsaysay | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15202328 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 128944 | Tagaytay Es | Magsaysay | 1 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1993000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 304280 | Tudaya National High School | Santa Cruz | 1 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8446000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128961 | Aglaungan Elementary School | Malita | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1998000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Occidental | 304262 | Alberto Olarte, Sr. Nhs | Sarangani | 0 | 1 | 12 | 3STY12CL | BATCH 5 CL | 16982000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Occidental | 304262 | Alberto Olarte, Sr. Nhs | Sarangani | 0 |  | 6 | 3STY6CL | BATCH 5 CL | 10687132 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 128895 | Bagong Negros Es | Kiblawan | 1 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1978000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128837 | Baluntaya Es | Don Marcelino | 0 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1120000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128837 | Baluntaya Es | Don Marcelino | 0 |  | 4 | 2STY4CL | BATCH 5 CL | 6422000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Occidental | 304266 | Basiawan Nhs | Santa Maria | 0 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15211328 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Occidental | 304266 | Basiawan Nhs | Santa Maria | 0 |  | 4 | 2STY4CL | BATCH 5 CL | 6422000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Occidental | 304269 | B'Laan Nhs | Malita | 0 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8392000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Occidental | 304269 | B'Laan Nhs | Malita | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2526000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 205033 | Bolo Bolo Es | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2891000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 205033 | Bolo Bolo Es | Malita | 0 |  | 2 | 1STY2CL | BATCH 5 CL | 1998000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 129060 | Butulan Es (Kilakay Es) | Jose Abad Santos (Trinidad) | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2921000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental |  | Cabalantian Es | Santa Maria | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2861000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128838 | Calian Elementary School | Don Marcelino | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2891000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 129058 | Camalian Es | Jose Abad Santos (Trinidad) | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2921000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128879 | Culaman Es | Jose Abad Santos (Trinidad) | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2906000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128839 | Dalupan Es | Don Marcelino | 0 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6442000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 205019 | Datu Bacala Elementary School | Malalag | 1 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1978000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128990 | Datu Danwata Es | Malita | 0 | 1 | 6 | 3STY6CL | BATCH 5 CL | 10567131.51 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128990 | Datu Danwata Es | Malita | 0 |  | 1 | 1STY1CL | BATCH 5 CL | 1135000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 304270 | Davao Del Sur Sof | Malalag | 1 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18347269 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 304270 | Davao Del Sur Sof | Malalag | 1 |  | 9 | 3STY9CL | BATCH 9 CL | 15196163 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Sur | 304270 | Davao Del Sur Sof | Malalag | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2518315 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Occidental | 304271 | Demolok Valley Nhs | Malita | 0 | 1 | 12 | 2STY12CL | BATCH 9 CL | 16130139.898 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Occidental | 304271 | Demolok Valley Nhs | Malita | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2528000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128966 | Domingo Bautista Sr. Es | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2885000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128840 | Don Marcelino Maruya Es | Don Marcelino | 0 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6430000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 304273 | Edna Guillermo Memorial National High School | Jose Abad Santos (Trinidad) | 0 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15346328 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 304273 | Edna Guillermo Memorial National High School | Jose Abad Santos (Trinidad) | 0 |  | 6 | 2STY6CL | BATCH 5 CL | 8446000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 205055 | Fagligdong | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2921000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 205055 | Fagligdong | Malita | 0 |  | 2 | 1STY2CL | BATCH 5 CL | 2018000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128883 | Faustino K. Labiton Sr. Elementary School | Jose Abad Santos (Trinidad) | 0 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6482000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 316005 | Felipe-Inocencia Deluao Nhs | Sulop | 1 | 1 | 12 | 3STY12CL | BATCH 5 CL | 16586000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128967 | Felis Elementary School | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2855000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Occidental | 304267 | Fishing Village Comprehensive Nhs | Malita | 0 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15202328 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Occidental | 304267 | Fishing Village Comprehensive Nhs | Malita | 0 |  | 6 | 3STY6CL | BATCH 5 CL | 10471132 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Occidental | 304267 | Fishing Village Comprehensive Nhs | Malita | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2519000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 304274 | Gov. N. Llanos Nhs | Kiblawan | 1 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15229328 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Sur | 304274 | Gov. N. Llanos Nhs | Kiblawan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2522000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 205045 | Gusatbak Ps | Don Marcelino | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2936000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Occidental | 304276 | Heracleo Casco Mnhs | Santa Maria | 0 | 1 | 24 | 4STY24CL | BATCH 9 CL | 36260328 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Occidental | 304276 | Heracleo Casco Mnhs | Santa Maria | 0 |  | 6 | 3STY6CL | BATCH 9 CL | 10444714 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Occidental | 304276 | Heracleo Casco Mnhs | Santa Maria | 0 |  | 16 | 4STY16CL | BATCH 9 CL | 26776021 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 129056 | Ignacia Guillermo Es (Butulan Es) | Jose Abad Santos (Trinidad) | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2921000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 304277 | Ihan Nhs | Kiblawan | 1 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22296344 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 304277 | Ihan Nhs | Kiblawan | 1 |  | 4 | 1STY4CL | BATCH 9 CL | 3859375.2325 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Del Sur | 304277 | Ihan Nhs | Kiblawan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2522000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 129004 | Jack Harvey Es | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2856500 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Occidental | 304292 | John Martin Johnson Hs (Lamidan) | Don Marcelino | 0 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20149496.669 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Occidental | 304292 | John Martin Johnson Hs (Lamidan) | Don Marcelino | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2530000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128881 | Jose Abad Santos Ces | Jose Abad Santos (Trinidad) | 0 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8446000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Occidental | 304281 | Jose Abad Santos Nhs | Jose Abad Santos (Trinidad) | 0 | 1 | 16 | 4STY16CL | BATCH 9 CL | 27022469 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Occidental | 304282 | Jose De Arce Mhs (Sangkokdatal Hs) | Sarangani | 0 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6582000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128984 | Julian M. Turado Elem. School | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2891000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128882 | Kalbay Es | Jose Abad Santos (Trinidad) | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2921000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Occidental | 304283 | Kalbay Nhs | Jose Abad Santos (Trinidad) | 0 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18522269 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Occidental | 304283 | Kalbay Nhs | Jose Abad Santos (Trinidad) | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 15346328 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128993 | Kibalatong Es | Malita | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2148000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128971 | Kidalapong Es | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2853500 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128841 | Kinanga Es | Don Marcelino | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2859500 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128994 | Kinangan Es | Malita | 0 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8356000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128973 | Kitana Ps | Malita | 0 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1120000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental |  | L. Payan Es | Santa Maria | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1979000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128997 | Lalon Es | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2936000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128997 | Lalon Es | Malita | 0 |  | 2 | 1STY2CL | BATCH 5 CL | 2028000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Occidental | 304291 | Lawa Nhs | Don Marcelino | 0 | 1 | 12 | 3STY12CL | BATCH 5 CL | 18366269 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Occidental | 304291 | Lawa Nhs | Don Marcelino | 0 |  | 9 | 3STY9CL | BATCH 5 CL | 15256328 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Occidental | 304291 | Lawa Nhs | Don Marcelino | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2522000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128998 | Lenna Es | Malita | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1994000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 205013 | Libudon Es | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2906000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 129117 | Lilan Elementary School | Santa Maria | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2876000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128846 | Linadasan Es | Don Marcelino | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1994000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128999 | Little Baguio Es | Malita | 0 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8416000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128884 | Malalan Es | Jose Abad Santos (Trinidad) | 0 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8464000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 129119 | Malaygan Es | Santa Maria | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2921000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 304287 | Mariano Peralta National High School | Malita | 0 | 1 | 40 | 4STY20CL | BATCH 5 CL | 62389661 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 304287 | Mariano Peralta National High School | Malita | 0 |  | 6 | 3STY6CL | BATCH 5 CL | 10444714 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 304287 | Mariano Peralta National High School | Malita | 0 |  | 12 | 4STY12CL | BATCH 5 CL | 22207508 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 205005 | Molopolo Es | Kiblawan | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6422000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 205005 | Molopolo Es | Kiblawan | 1 |  | 1 | 1STY1CL | BATCH 5 CL | 1120000 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 316001 | Molopolo National High School | Kiblawan | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15220328 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 316001 | Molopolo National High School | Kiblawan | 1 |  | 4 | 2STY4CL | BATCH 9 CL | 5746403.8743 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128979 | Mote Elementary School | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2891000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128980 | Nawan Es | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2891000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 129123 | Pongpong Es | Santa Maria | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1982000 |  |  | Completed | 1 |  |  | 16LF0021 |  |  | 2016-07-27 | 2016-07-27 | 2016-08-01
NC 2016 | K10 | Region XI | Davao Occidental | 128889 | Rolando E. Pardinas Sr. Es | Jose Abad Santos (Trinidad) | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2008000 |  |  | Completed | 1 |  |  | 16LF008 |  | 2016-02-29 | 2016-03-10 | 2016-03-10 | 2016-03-17 | 2016-05-20 | LEGACY CONSTRUCTION
NC 2016 | K10 | Region XI | Davao Occidental | 129125 | San Antonio Es | Santa Maria | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2008000 |  |  | Completed | 1 |  |  | 16LF008 |  | 2016-02-29 | 2016-03-10 | 2016-03-10 | 2016-03-17 | 2016-05-20 | R. SEMILLA CONST. & MARKETING
NC 2016 | K10 | Region XI | Davao Occidental | 129069 | San Isidro Es | Jose Abad Santos (Trinidad) | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2936000 |  |  | Completed | 1 |  |  | 16LF0022 |  |  | 2016-08-01 | 2016-08-01 | 2016-08-10
NC 2016 | K10 | Region XI | Davao Del Sur | 205006 | San Pedro Ps | Kiblawan | 1 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1978000 |  |  | Completed | 1 |  |  | 16LF0020 |  |  | 2016-07-27 | 2016-07-27 | 2016-08-01
NC 2016 | K10 | Region XI | Davao Occidental | 129006 | Santagose Es | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2876000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 129006 | Santagose Es | Malita | 0 |  | 2 | 1STY2CL | BATCH 5 CL | 1988000 |  |  | Completed | 1 |  |  |  | 16LD0012 | 2016-04-21 | 2016-04-28 | 2016-05-12 | 2016-05-27 | 2016-06-27 | Two Degrees Const & Supply
NC 2016 | SHS | Region XI | Davao Occidental | 304296 | Sta. Maria Nhs | Santa Maria | 0 | 1 | 18 | 3STY9CL | BATCH 5 CL | 30386656 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Davao Occidental | 304296 | Sta. Maria Nhs | Santa Maria | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2526000 |  |  | Completed | 1 |  |  |  | 16LD0006 | 2016-02-24 | 2016-02-26 | 2016-03-08 | 2016-03-11 | 2016-05-24 | R.C. Melgazo Builders
NC 2016 | SHS | Region XI | Davao Del Sur | 304297 | Sulop Nhs | Sulop | 1 | 1 | 12 | 3STY6CL | BATCH 1 CL | 21038263.02 |  |  | Completed | 1 |  |  |  | 16LD0008 | 2016-02-24 | 2016-02-26 | 2016-03-08 | 2016-03-11 | 2016-05-24 | R.C. Melgazo Builders
NC 2016 | SHS | Region XI | Davao Del Sur | 304297 | Sulop Nhs | Sulop | 1 |  | 12 | 3STY12CL | BATCH 1 CL | 18390268.79 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Del Sur | 304297 | Sulop Nhs | Sulop | 1 |  | 8 | 2STY4CL | BATCH 1 CL | 12900000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Del Sur | 128920 | Tacul Ps | Kiblawan | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6422000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 205039 | Tfs-Danaw Ps | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2921000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 205039 | Tfs-Danaw Ps | Malita | 0 |  | 2 | 1STY2CL | BATCH 5 CL | 2018000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 205036 | Tfs-Malandeg Ps | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2921000 |  |  | Completed | 1 |  |  |  | 16LG0037 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY
NC 2016 | K10 | Region XI | Davao Occidental | 205041 | Tfs-Tambelang Ps | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2936000 |  |  | Completed | 1 |  |  |  | 16L0032 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY
NC 2016 | K10 | Region XI | Davao Occidental | 205041 | Tfs-Tambelang Ps | Malita | 0 |  | 2 | 1STY2CL | BATCH 5 CL | 2028000 |  |  | Completed | 1 |  |  |  | 16LG0022 | 2016-02-19 | 2016-02-26 | 2016-03-11 | 2016-03-17 | 2016-05-20 | THREE W BUILDERS INC.
NC 2016 | K10 | Region XI | Davao Occidental | 129007 | Tical Es | Malita | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1988000 |  |  | Completed | 1 |  |  |  | 16LG0036 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY
NC 2016 | SHS | Region XI | Davao Occidental | 304293 | Ticulon Nhs | Malita | 0 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15229328 |  |  | Completed | 1 |  |  |  | 16LG0031 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY
NC 2016 | SHS | Region XI | Davao Occidental | 304293 | Ticulon Nhs | Malita | 0 |  | 4 | 2STY4CL | BATCH 5 CL | 6430000 |  |  | Completed | 1 |  |  |  | 16LG0040 | [5 empty] | 0
NC 2016 | SHS | Region XI | Davao Occidental | 304268 | Tubalan Comprehensive Nhs | Santa Maria | 0 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6410000 |  |  | Completed | 1 |  |  |  | 16LG0039 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY
NC 2016 | TECHVOC | Region XI | Davao Occidental | 304268 | Tubalan Comprehensive Nhs | Santa Maria | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2517000 |  |  | Completed | 1 |  |  |  | 16LG0033 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY
NC 2016 | K10 | Region XI | Davao Occidental | 129074 | Ubas Es | Sarangani | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2981000 |  |  | Completed | 1 |  |  |  | 16LG0034 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY
NC 2016 | K10 | Region XI | Davao Occidental | 128844 | William Joyce Sr. Elementary School | Don Marcelino | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1988000 |  |  | Completed | 1 |  |  |  | 16LG0041 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | FJ CONSTRUCTION
NC 2016 | K10 | Region XI | Davao Occidental | 129053 | Balangonan Es | Jose Abad Santos (Trinidad) | 0 | 1 | 12 | 3STY12CL | BATCH 13 CL | 18582269 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128992 | Kablulan Es | Malita | 0 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2921000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128992 | Kablulan Es | Malita | 0 |  | 8 | 1STY4CL | BATCH 13 CL | 8189531.316 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128892 | Manuel Medel Sr. Es | Jose Abad Santos (Trinidad) | 0 | 1 | 8 | 2STY8CL | BATCH 13 CL | 12150076.849 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128892 | Manuel Medel Sr. Es | Jose Abad Santos (Trinidad) | 0 |  | 1 | 1STY1CL | BATCH 13 CL | 1135000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128877 | Maria/Rita Medel Elementary School | Jose Abad Santos (Trinidad) | 0 | 1 | 8 | 2STY8CL | BATCH 13 CL | 12190076.849 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 128877 | Maria/Rita Medel Elementary School | Jose Abad Santos (Trinidad) | 0 |  | 1 | 1STY1CL | BATCH 13 CL | 1140000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 129065 | Molmol Es | Jose Abad Santos (Trinidad) | 0 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2951000 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Occidental | 129065 | Molmol Es | Jose Abad Santos (Trinidad) | 0 |  | 8 | 1STY4CL | BATCH 13 CL | 8149531.316 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Davao Oriental | 304300 | Baganga Nhs | Baganga | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 24352577.982 |  |  | Completed | 1 |  |  |  | 16LG0036 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY
NC 2016 | TECHVOC | Region XI | Davao Oriental | 304309 | Cateel Nat'L. Agri. Hs | Cateel | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2539549.27 |  |  | Completed | 1 |  |  |  | 16LG0035 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY
NC 2016 | K10 | Region XI | Davao Oriental | 304311 | Cateel Voc.Hs | Cateel | 1 | 1 | 16 | 2STY8CL | BATCH 5 CL | 22582794.06 |  |  | Completed | 1 |  |  |  | 16LG0024 | 2016-02-19 | 2016-02-26 | 2016-03-11 | 2016-03-17 | 2016-05-20 | FIVE MASSIVE INFRA & SUPPLY
NC 2016 | K10 | Region XI | Davao Oriental | 304311 | Cateel Voc.Hs | Cateel | 1 |  | 6 | 2STY6CL | BATCH 5 CL | 8128471.77 |  |  | Completed | 1 |  |  |  | 16LG0023 | 2016-02-19 | 2016-02-26 | 2016-03-11 | 2016-03-17 | 2016-05-20 | MARK ANTHONY CONST. & SUPPLY
NC 2016 | TECHVOC | Region XI | Davao Oriental | 304312 | Crispin E. Rojas National High School | Baganga | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2539549.27 |  |  | Completed | 1 | [5 empty] | 2016-08-05 | 2016-08-18
NC 2016 | K10 | Region XI | Davao Oriental | 304315 | E. Moralizon Nvhs | Manay | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.05 |  |  | Completed | 1 | [5 empty] | 2016-08-05 | 2016-08-18
NC 2016 | K10 | Region XI | Davao Oriental | 304324 | Manay Nhs | Manay | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15418925.24 |  |  | Completed | 1 | [5 empty] | 2016-08-05 | 2016-08-18
NC 2016 | TECHVOC | Region XI | Davao Oriental | 304339 | Tarragona National High School | Tarragona | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2539549.27 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Davao Oriental | 304339 | Tarragona National High School | Tarragona | 1 | 1 | 12 | 2STY6CL | BATCH 13 CL | 16429930.1 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Digos City | 316302 | Digos City Nhs - Matti Hs Annex | City Of Digos (Capital) | 1 | 1 | 15 | 3STY15CL | BATCH 7 CL | 21543013.45 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Digos City | 316302 | Digos City Nhs - Matti Hs Annex | City Of Digos (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2439549.27 |  |  | Completed | 1 |  |  |  | 16LD0012 | 2016-04-21 | 2016-04-28 | 2016-05-12 | 2016-05-27 | 2016-06-27 | Two Degrees Const & Supply
NC 2016 | SHS | Region XI | Digos City | 304401 | Kapatagan Nhs | City Of Digos (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 1 CL | 11080942.5917 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Digos City | 304401 | Kapatagan Nhs | City Of Digos (Capital) | 1 |  | 4 | 2STY4CL | BATCH 1 CL | 6436137.6381 |  |  | Completed | 1 |  |  |  | 16LD0006 | 2016-02-24 | 2016-02-26 | 2016-03-08 | 2016-03-11 | 2016-05-24 | R.C. Melgazo Builders
NC 2016 | TECHVOC | Region XI | Digos City | 304401 | Kapatagan Nhs | City Of Digos (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2499549.27 |  |  | Completed | 1 |  |  |  | 16LD0008 | 2016-02-24 | 2016-02-26 | 2016-03-08 | 2016-03-11 | 2016-05-24 | R.C. Melgazo Builders
NC 2016 | TECHVOC | Region XI | Island Garden City Of Samal | 304220 | Balet National High School | Island Garden City Of Samal | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2673214.6215 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Island Garden City Of Samal | 304245 | Mambago-B National High School | Island Garden City Of Samal | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2518227.1197 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Island Garden City Of Samal | 304245 | Mambago-B National High School | Island Garden City Of Samal | 2 | 1 | 10 | 2STY10CL | BATCH 13 CL | 14135065.799 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Island Garden City Of Samal | 323403 | Nieves Villarica National High School | Igacos | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 29560142.5235 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Island Garden City Of Samal | 128736 | Peñaplata Central Elementary School Sped Center | Island Garden City Of Samal | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Island Garden City Of Samal | 128736 | Peñaplata Central Elementary School Sped Center | Island Garden City Of Samal | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Island Garden City Of Samal | 304259 | Tagbitan-Ag National High School | Island Garden City Of Samal | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2697468.3545 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Mati City | 304320 | Bagumbayan Agro-Ind. Hs | Lupon | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2669980.9742 |  |  | Completed | 1 |  |  |  | 16LG0037 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY
NC 2016 | TECHVOC | Region XI | Mati City | 304313 | Dawan Nhs | City Of Mati (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2673368.6897 |  |  | Completed | 1 |  |  |  | 16L0032 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY
NC 2016 | K10 | Region XI | Mati City | 316108 | Lavigan National High School | Governor Generoso | 2 | 1 | 6 | 2STY6CL | BATCH 5 CL | 10025000 |  |  | Completed | 1 |  |  |  | 16LG0022 | 2016-02-19 | 2016-02-26 | 2016-03-11 | 2016-03-17 | 2016-05-20 | THREE W BUILDERS INC.
NC 2016 | K10 | Region XI | Mati City | 304319 | Lupon Vocational High School | Lupon | 2 | 1 | 12 | 2STY12CL | BATCH 13 CL | 16022138.898 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Mati City | 304319 | Lupon Vocational High School | Lupon | 2 |  | 2 | 1STY2CL | BATCH 13 CL | 2132466.644 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Mati City | 304323 | Macangao Agri. Vhs | Lupon | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2670883.4521 |  |  | Completed | 1 |  |  |  | 16LG0036 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY
NC 2016 | SHS | Region XI | Mati City |  | Macangao Agri. Vhs To Tagboa Agri-Vocational Hs | Lupon | 2 | 1 | 12 | 1STY12CL | BATCH 13 CL | 12058076.849 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Mati City | 304301 | Manuel B.Guiñez Sr. Nhs | Banaybanay | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 |  |  |  | 16LG0031 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY
NC 2016 | K10 | Region XI | Mati City | 304301 | Manuel B.Guiñez Sr. Nhs | Banaybanay | 2 | 1 | 16 | 2STY8CL | BATCH 13 CL | 23900153.698 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Mati City | 304317 | Manuel S. Nasser Sr. National High School | San Isidro | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2672099.3549 |  |  | Completed | 1 |  |  |  | 16LG0040 | [5 empty] | 0
NC 2016 | TECHVOC | Region XI | Mati City | 316101 | Marayag Nhs | Lupon | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2767283.2707 |  |  | Completed | 1 |  |  |  | 16LG0039 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY
NC 2016 | TECHVOC | Region XI | Mati City | 304325 | Mati National Comprehensive High School | City Of Mati (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 |  |  |  | 16LG0033 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY
NC 2016 | K10 | Region XI | Mati City | 304325 | Mati National Comprehensive High School | City Of Mati (Capital) | 2 | 1 | 20 | 2STY10CL | BATCH 13 CL | 28066882.198 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Mati City | 304326 | Mati Sat | City Of Mati (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 |  |  |  | 16LG0034 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY
NC 2016 | K10 | Region XI | Mati City | 304327 | Matiao Nhs | City Of Mati (Capital) | 2 | 1 | 12 | 2STY6CL | BATCH 13 CL | 18042923.11 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XI | Mati City | 304332 | San Isidro Nhs | San Isidro | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2669980.9742 |  |  | Completed | 1 |  |  |  | 16LG0041 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | FJ CONSTRUCTION
NC 2016 | TECHVOC | Region XI | Mati City | 304336 | Sigaboy Agri. Voc. Hs | Governor Generoso | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2681272.4838 |  |  | Completed | 1 |  |  |  | 16LG0036 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY
NC 2016 | TECHVOC | Region XI | Mati City | 304338 | Taguibo Agri. Voc. High School | City Of Mati (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2680419.1339 |  |  | Completed | 1 |  |  |  | 16LG0035 | 2016-06-27 | 2016-07-05 | 2016-07-19 | 2016-07-27 |  | MARK ANTHONY CONST. & SUPPLY
NC 2016 | K10 | Region XI | Mati City | 129295 | Matigdao Es | Lupon | 3 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2218728 |  |  | Completed | 1 |  |  |  | 16LG0024 | 2016-02-19 | 2016-02-26 | 2016-03-11 | 2016-03-17 | 2016-05-20 | FIVE MASSIVE INFRA & SUPPLY
NC 2016 | SHS | Region XI | Mati City | 304340 | Tibanban Nhs | Governor Generoso | 3 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2952600 |  |  | Completed | 1 |  |  |  | 16LG0023 | 2016-02-19 | 2016-02-26 | 2016-03-11 | 2016-03-17 | 2016-05-20 | MARK ANTHONY CONST. & SUPPLY
NC 2016 | SHS | Region XI | Panabo City | 304403 | A. O. Floirendo National High School | City Of Panabo | 2 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11950076.849 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Panabo City | 304403 | A. O. Floirendo National High School | City Of Panabo | 2 |  | 4 | 2STY4CL | BATCH 13 CL | 6490110 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Panabo City | 304408 | Panabo National High School | City Of Panabo | 2 | 1 | 24 | 3STY12CL | BATCH 13 CL | 37990800 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Panabo City |  | Shs In Panabo City | City Of Panabo | 2 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31956000 |  |  | Completed | 1 |  |  | P0074937MN-CW1 | 16LC0075 | 2016-08-10 | 2016-08-05 | 2016-08-30 | 2016-09-20 | 2016-09-23 | FFJJ Construction
NC 2016 | SHS | Region XI | Panabo City |  | Shs In Panabo City | City Of Panabo | 2 |  | 12 | 4STY12CL | BATCH 11 CL | 22452343.62 |  |  | Completed | 1 |  |  | P0074938MN-CW1 | 16LC0067 | 2016-08-04 | 2016-08-05 | 2016-08-23 | 2016-09-13 | 2016-09-16 | FFJJ Construction
NC 2016 | SHS | Region XI | Panabo City |  | Shs In Panabo City | City Of Panabo | 2 |  | 8 | 4STY8CL | BATCH 11 CL | 15197518.84 |  |  | Completed | 1 |  |  | P0074936MN-CW1 | 16LC0063 | 2016-07-29 | 2016-08-05 | 2016-08-18 | 2016-09-06 | 2016-09-09 | FFJJ Construction
NC 2016 | SHS | Region XI | Panabo City | 316401 | Southern Davao National High School | City Of Panabo | 2 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11950076.849 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Tagum City | 304238 | La Filipina Nhs | City Of Tagum (Capital) | 1 | 1 | 15 | 3STY15CL | BATCH 13 CL | 21383013.45 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Tagum City | 304226 | Laureta National High School | City Of Tagum (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11517510 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Tagum City | 128771 | Magugpo Pilot Central Elementary School | City Of Tagum (Capital) | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 16618460.712 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Tagum City | 128795 | Mangga Elementary School | City Of Tagum (Capital) | 1 | 1 | 12 | 2STY12CL | BATCH 13 CL | 16022138.898 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Tagum City | 304232 | Pipisan Maug National High School | City Of Tagum (Capital) | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14033441.1023 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Tagum City |  | Pipsan Maug Nhs-Liboganon Extension Campus | City Of Tagum (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9003810 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Tagum City | 304225 | Tagum City National Comprehensive High School | City Of Tagum (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Tagum City |  | Tagum City National Comprehensive Hs-Pandapan Extension Campus | Tagum City | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319337.6381 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Tagum City | 304260 | Tagum City Nhs | City Of Tagum (Capital) | 1 | 1 | 20 | 4STY20CL | BATCH 9 CL | 30537840 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Tagum City | 304260 | Tagum City Nhs | City Of Tagum (Capital) | 1 |  | 12 | 4STY12CL | BATCH 9 CL | 19952109.258 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Tagum City |  | Tagum City Nhs-Canocotan Extension Campus | City Of Tagum (Capital) | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Tagum City | 304261 | Tagum National Trade School | City Of Tagum (Capital) | 1 | 1 | 30 | 3STY15CL | BATCH 9 CL | 45881760 |  |  | Completed | 1
NC 2016 | SHS | Region XI | Tagum City | 304261 | Tagum National Trade School | City Of Tagum (Capital) | 1 |  | 20 | 2STY10CL | BATCH 9 CL | 28066882.2047 |  |  | Completed | 1
NC 2016 | K10 | Region XI | Tagum City | 128798 | Visayan Village Central Elementary School | City Of Tagum (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9003810 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129637 | Bayanihan Elementary | DAVAO CITY | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2750000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129720 | Jose Bastida ES | DAVAO CITY | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2750000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129645 | Maa CES | DAVAO CITY | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4080000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Davao del Norte | 304229 | Dujali NHS | BRAULIO E. DUJALI | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2765106 |  |  | Completed | 1 |  |  | P00170808MN-CW1 | 17LC0273 | 2017-07-12 | 2017-07-19 | 2017-08-03 | 2017-08-18 | 2017-09-07 | A.B Aponesto
NC 2017 | SHS | Region XI | Davao del Norte | 304229 | Dujali NHS | BRAULIO E. DUJALI | 2 |  | 2 | 1STY2CL | BATCH 2 | 2878651 |  |  | Completed | 1 |  |  | P00170809MN-CW1 | 17LC0272 | 2017-07-12 | 2017-07-19 | 2017-08-03 | 2017-08-18 | 2017-09-07 | A.B Aponesto
NC 2017 | K10 | Region XI | Davao del Norte | 128627 | Carmen CES | CARMEN | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2901186 |  |  | Completed | 1 |  |  | P00170810MN-CW1 | 17LC0274 | 2017-07-12 | 2017-07-19 | 2017-08-03 | 2017-08-18 | 2017-09-07 | Five Massive Infra and Supply Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304222 | Carmen NHS | CARMEN | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2786760 |  |  | Completed | 1 |  |  | P00170811MN-CW1 | 17LC0278 | 2017-07-12 | 2017-07-19 | 2017-08-03 | 2017-08-18 | 2017-09-07 | Five Massive Infra and Supply Corp.
NC 2017 | K10 | Region XI | Davao del Norte | 128633 | Mabuhay ES | CARMEN | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2767697 |  |  | Completed | 1 |  |  | P00170812MN-CW1 | 17LC0275 | 2017-07-12 | 2017-07-19 | 2017-08-03 | 2017-08-18 | 2017-09-07 | Mag Corporation
NC 2017 | K10 | Region XI | Davao del Norte | 128642 | Tibulao ES | CARMEN | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2761254 |  |  | Completed | 1 |  |  | P00170813MN-CW1 | 17LC0276 | 2017-07-12 | 2017-07-19 | 2017-08-03 | 2017-08-18 | 2017-09-07 | Mag Corporation
NC 2017 | SHS | Region XI | Davao del Norte | 315901 | Tubod National High School | CARMEN | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2740875 |  |  | Completed | 1 |  |  | P00170814MN-CW1 | 17LC0295 | 2017-07-12 | 2017-07-19 | 2017-08-03 | 2017-08-18 | 2017-09-07 | CJEP Builders and Engineering Services
NC 2017 | K10 | Region XI | Davao del Norte | 128644 | Tuganay ES | CARMEN | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2767697 |  |  | Completed | 1 |  |  | P00170815MN-CW1 | 17LC0277 | 2017-07-12 | 2017-07-19 | 2017-08-03 | 2017-08-18 | 2017-09-07 | RDF Construction and Supply
NC 2017 | K10 | Region XI | Davao del Norte | 128748 | Kimamon ES | SANTO TOMAS | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2845674 |  |  | Completed | 1 |  |  | P00170816MN-CW1 | 17LC0286 | 2017-07-12 | 2017-07-19 | 2017-08-03 | 2017-08-18 | 2017-10-13 | FT Construction and General Merchandise
NC 2017 | K10 | Region XI | Davao del Norte | 128749 | Kinamayan ES | SANTO TOMAS | 2 | 1 | 3 | 1STY3CL | BATCH 2 | 3885518 |  |  | Completed | 1 |  |  | P00170817MN-CW1 | 17LC0289 | 2017-07-12 | 2017-07-19 | 2017-08-03 | 2017-08-18 | 2017-09-07 | FT Construction and General Merchandise
NC 2017 | K10 | Region XI | Davao del Norte | 128751 | Lunga-og ES | SANTO TOMAS | 2 | 1 | 4 | 1STY4CL | BATCH 2 | 5180174 |  |  | Completed | 1 |  |  | P00170818MN-CW1 | 17LC0279 | 2017-07-12 | 2017-07-19 | 2017-08-03 | 2017-08-18 | 2017-09-07 | Mag Corporation
NC 2017 | SHS | Region XI | Davao del Norte | 304246 | Marsman NHS | SANTO TOMAS | 2 | 1 | 3 | 1STY3CL | BATCH 2 | 4016122 |  |  | Completed | 1 |  |  | P00170819MN-CW1 | 17LC0294 | 2017-07-12 | 2017-07-19 | 2017-08-03 | 2017-08-18 | 2017-09-07 | FT Construction and General Merchandise
NC 2017 | K10 | Region XI | Davao del Norte | 128752 | Nafco Central Elementary School | SANTO TOMAS | 2 | 1 | 4 | 1STY4CL | BATCH 2 | 5198771 |  |  | Completed | 1 |  |  | P00170820MN-CW1 | 17LC0288 | 2017-07-12 | 2017-07-19 | 2017-08-03 | 2017-08-18 | 2017-09-07 | Micah Construction and Supply
NC 2017 | K10 | Region XI | Davao del Norte | 128754 | Salvacion ES | SANTO TOMAS | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2845674 |  |  | Completed | 1 |  |  | P00170821MN-CW1 | 17LC0281 | 2017-07-12 | 2017-07-19 | 2017-08-03 | 2017-08-18 | 2017-09-07 | CJEP Builders and Engineering Services
NC 2017 | K10 | Region XI | Davao del Norte | 128767 | Tulalian Elementary | SANTO TOMAS | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2880903 |  |  | Completed | 1 |  |  | P00170822MN-CW1 | 17LC0296 | 2017-07-12 | 2017-07-19 | 2017-08-03 | 2017-08-18 | 2017-09-07 | Five Massive Infra and Supply Corp.
NC 2017 | K10 | Region XI | Davao Oriental | 129167 | Batiano ES | BAGANGA | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 3938639.84 |  |  | Completed | 1 | [8 empty] | 2017-09-10 | JAI BUILDERS
NC 2017 | K10 | Region XI | Davao Oriental | 205508 | Casunugan ES | BAGANGA | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 3911881.91 |  |  | Completed | 1 | [8 empty] | 2017-09-10 | JAI BUILDERS
NC 2017 | K10 | Region XI | Davao Oriental | 129160 | San Isidro ES | BAGANGA | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 3863608.34 |  |  | Completed | 1 | [8 empty] | 2017-09-10 | JAI BUILDERS
NC 2017 | K10 | Region XI | Davao Oriental | 316111 | Caatijan NHS | BOSTON | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 3922486.81 |  |  | Completed | 1 | [8 empty] | 2017-09-10 | TWINA BUILDERS
NC 2017 | K10 | Region XI | Davao Oriental | 316111 | Caatijan NHS | BOSTON | 1 |  | 3 | 1STY3CL | BATCH 2 | 3922486.81 |  |  | Completed | 1 | [8 empty] | 2017-09-10 | TWINA BUILDERS
NC 2017 | K10 | Region XI | Davao Oriental | 129206 | Alvar ES | CARAGA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2852524.4 |  |  | Completed | 1 | [8 empty] | 2017-09-10 | RANGAY CONST. & SUPPLY
NC 2017 | SHS | Region XI | Davao Oriental | 304307 | Caraga National High School | CARAGA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2832051.3 |  |  | Completed | 1 | [8 empty] | 2017-09-10 | FAJR CONST. PARTS & SUPPLY
NC 2017 | K10 | Region XI | Davao Oriental | 129213 | Hanginan Elementary School | CARAGA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 4380950.41 |  |  | Completed | 1 | [8 empty] | 2017-09-10 | RANGAY CONST. & SUPPLY
NC 2017 | SHS | Region XI | Davao Oriental | 304308 | Pantuyan NHS | CARAGA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2756380.34 |  |  | Completed | 1 | [8 empty] | 2018-01-09 | RC TROCIO BUILDERS
NC 2017 | SHS | Region XI | Davao Oriental | 304308 | Pantuyan NHS | CARAGA | 1 |  | 2 | 1STY2CL | BATCH 2 | 2756380.34 |  |  | Completed | 1 | [8 empty] | 2018-01-09 | RC TROCIO BUILDERS
NC 2017 | K10 | Region XI | Davao Oriental | 129246 | Santiago ES | CARAGA | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4024044.11 |  |  | Completed | 1 | [8 empty] | 2017-09-10 | FAJR CONST. PARTS & SUPPLY
NC 2017 | K10 | Region XI | Davao Oriental | 129228 | Sta. Fe ES | CARAGA | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 3990085.29 |  |  | Completed | 1 | [8 empty] | 2017-09-10 | RANGAY CONST. & SUPPLY
NC 2017 | K10 | Region XI | Davao Oriental | 205507 | Aragon Elementary School | CATEEL | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2719023.17 |  |  | Completed | 1 | [8 empty] | 2017-09-10 | TWINA BUILDERS
NC 2017 | K10 | Region XI | Davao Oriental | 205507 | Aragon Elementary School | CATEEL | 1 |  | 3 | 1STY3CL | BATCH 2 | 3807433.78 |  |  | Completed | 1 | [8 empty] | 2017-09-10 | TWINA BUILDERS
NC 2017 | K10 | Region XI | Davao Oriental | 205515 | Maylaya IS | CATEEL | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2759308.2 |  |  | Completed | 1 | [8 empty] | 2017-09-10 | TWINA BUILDERS
NC 2017 | K10 | Region XI | Davao Oriental | 205515 | Maylaya IS | CATEEL | 1 |  | 2 | 1STY2CL | BATCH 2 | 2759308.2 |  |  | Completed | 1 | [8 empty] | 2017-09-10 | TWINA BUILDERS
NC 2017 | SHS | Region XI | Davao Oriental | 304324 | Manay National High School | MANAY | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2721625.96 |  |  | Completed | 1 | [8 empty] | 2017-09-10 | RCBAR BUILDERS
NC 2017 | K10 | Region XI | Davao Oriental | 129363 | Old Macopa ES | MANAY | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3149171.3 |  |  | Completed | 1 | [8 empty] | 2017-09-17 | RCBAR BUILDERS
NC 2017 | K10 | Region XI | Davao Oriental | 129363 | Old Macopa ES | MANAY | 1 |  | 4 | 1STY4CL | BATCH 2 | 5444038.6 |  |  | Completed | 1 | [8 empty] | 2017-09-17 | RCBAR BUILDERS
NC 2017 | K10 | Region XI | Davao Oriental | 129368 | Ronquillo & Dayanghirang ES | MANAY | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4011896.95 |  |  | Completed | 1 | [8 empty] | 2017-09-10 | RCBAR BUILDERS
NC 2017 | K10 | Region XI | Davao Oriental | 129371 | Taocanga ES | MANAY | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4058672.08 |  |  | Completed | 1 | [8 empty] | 2017-09-17 | RCBAR BUILDERS
NC 2017 | K10 | Region XI | Davao Oriental | 129448 | Dadong ES | TARRAGONA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3236193.52 |  |  | Completed | 1 | [8 empty] | 2017-09-17 | R. SEMILLA CONST. & MARKETING
NC 2017 | K10 | Region XI | Davao Oriental | 129448 | Dadong ES | TARRAGONA | 1 |  | 3 | 1STY3CL | BATCH 2 | 4149843.57 |  |  | Completed | 1 | [8 empty] | 2017-09-17 | R. SEMILLA CONST. & MARKETING
NC 2017 | K10 | Region XI | Davao Oriental | 129449 | Jovellar ES | TARRAGONA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2920158.29 |  |  | Completed | 1 | [8 empty] | 2017-09-17 | R. SEMILLA CONST. & MARKETING
NC 2017 | K10 | Region XI | Davao Oriental | 129451 | L. Tamay Primary School | TARRAGONA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2813103.97 |  |  | Completed | 1 | [8 empty] | 2017-09-17 | FJAR CONST.
NC 2017 | K10 | Region XI | Davao Oriental | 129453 | Lucatan ES | TARRAGONA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3049114.59 |  |  | Completed | 1 | [8 empty] | 2017-09-17 | FJAR CONST.
NC 2017 | K10 | Region XI | Davao Oriental | 129453 | Lucatan ES | TARRAGONA | 1 |  | 3 | 1STY3CL | BATCH 2 | 4129948.51 |  |  | Completed | 1 | [8 empty] | 2017-09-17 | FJAR CONST.
NC 2017 | K10 | Region XI | Davao Oriental | 205511 | Nagas ES | TARRAGONA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2822489.07 |  |  | Completed | 1 | [8 empty] | 2017-09-20 | MARK ANTHONY CONST. & SUPPLY
NC 2017 | K10 | Region XI | Davao Oriental | 205511 | Nagas ES | TARRAGONA | 1 |  | 3 | 1STY3CL | BATCH 2 | 3971618.89 |  |  | Completed | 1 | [8 empty] | 2017-09-20 | MARK ANTHONY CONST. & SUPPLY
NC 2017 | K10 | Region XI | Davao Oriental | 316113 | Paulina Gambong Abayon NHS | TARRAGONA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2867167.87 |  |  | Completed | 1 | [8 empty] | 2017-09-20 | MARK ANTHONY CONST. & SUPPLY
NC 2017 | K10 | Region XI | Davao Oriental | 205514 | Talagot ES | TARRAGONA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2867084.46 |  |  | Completed | 1 | [8 empty] | 2017-09-20 | MARK ANTHONY CONST. & SUPPLY
NC 2017 | K10 | Region XI | Davao Oriental | 205514 | Talagot ES | TARRAGONA | 1 |  | 3 | 1STY3CL | BATCH 2 | 4036706.35 |  |  | Completed | 1 | [8 empty] | 2017-09-20 | MARK ANTHONY CONST. & SUPPLY
NC 2017 | K10 | Region XI | Davao Oriental | 129462 | Tarragona CES | TARRAGONA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2980894.1 |  |  | Completed | 1 | [8 empty] | 2017-09-20 | MARK ANTHONY CONST. & SUPPLY
NC 2017 | K10 | Region XI | Davao Oriental | 129462 | Tarragona CES | TARRAGONA | 1 |  | 3 | 1STY3CL | BATCH 2 | 4001481.99 |  |  | Completed | 1 | [8 empty] | 2017-09-20 | MARK ANTHONY CONST. & SUPPLY
NC 2017 | SHS | Region XI | Mati City | 316107 | Leandro G. Japos NHS | BANAYBANAY | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2647215.57 |  |  | Completed | 1 |  |  |  | 17LG0085 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | LLM Unified Builders & Trading Corp.
NC 2017 | SHS | Region XI | Mati City | 325104 | Badas NHS | CITY OF MATI (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2694155.19 |  |  | Completed | 1 |  |  |  | 17LG0078 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | Legacy Construction Corporation
NC 2017 | K10 | Region XI | Mati City | 129392 | Cabubuanan ES | CITY OF MATI (Capital) | 2 | 1 | 3 | 1STY3CL | BATCH 2 | 3769721.94 |  |  | Completed | 1 |  |  |  | 17LG0088 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | Jecel Construction Supply
NC 2017 | SHS | Region XI | Mati City | 316104 | Don Salvador Lopez NHS | CITY OF MATI (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2620511.46 |  |  | Completed | 1 |  |  |  | 17LG0083 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | Jecel Construction Supply
NC 2017 | K10 | Region XI | Mati City | 325101 | Doña Rosa G. Rabat MHS | CITY OF MATI (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2647114.16 |  |  | Completed | 1 |  |  |  | 17LG0083 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | Jecel Construction Supply
NC 2017 | K10 | Region XI | Mati City | 129415 | Lanca ES | CITY OF MATI (Capital) | 2 | 1 | 3 | 1STY3CL | BATCH 2 | 3784826.12 |  |  | Completed | 1 |  |  |  | 17LG0082 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | Legacy Construction Corporation
NC 2017 | SHS | Region XI | Mati City | 325102 | LAWIGAN NATIONAL HIGH SCHOOL | CITY OF MATI (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2640321.9 |  |  | Completed | 1 |  |  |  | 17LG0089 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | Jecel Construction Supply
NC 2017 | SHS | Region XI | Mati City | 304318 | Libudon NHS | CITY OF MATI (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2704247.2 |  |  | Completed | 1 |  |  |  | 17LG0079 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | FFJJ Construction
NC 2017 | SHS | Region XI | Mati City | 304325 | Mati Nat'l. Comp. HS | CITY OF MATI (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2628922.05 |  |  | Completed | 1 |  |  |  | 17LG0090 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | FFJJ Construction
NC 2017 | K10 | Region XI | Mati City | 129421 | Paciano A. Genon EMS | CITY OF MATI (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2707210.26 |  |  | Completed | 1 |  |  |  | 17LG0079 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | FFJJ Construction
NC 2017 | K10 | Region XI | Mati City | 129380 | Rabat-Rocamora Mati Central ES I | CITY OF MATI (Capital) | 2 | 1 | 3 | 1STY3CL | BATCH 2 | 3702877.56 |  |  | Completed | 1 |  |  |  | 17LG0080 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | FFJJ Construction
NC 2017 | K10 | Region XI | Mati City | 205504 | Rabat-Rocamora Mati Central SPED Sch. | CITY OF MATI (Capital) | 2 | 1 | 3 | 1STY3CL | BATCH 2 | 3702877.56 |  |  | Completed | 1 |  |  |  | 17LG0080 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | FFJJ Construction
NC 2017 | K10 | Region XI | Mati City | 129385 | Tagawisan ES | CITY OF MATI (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2612021.28 |  |  | Completed | 1 |  |  |  | 17LG0078 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | Legacy Construction Corporation
NC 2017 | K10 | Region XI | Mati City | 129405 | Taguibo ES | CITY OF MATI (Capital) | 2 | 1 | 5 | 1STY5CL | BATCH 2 | 6388924.51 |  |  | Completed | 1 |  |  |  | 17LG0081 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | Legacy Construction Corporation
NC 2017 | K10 | Region XI | Mati City | 129280 | Bonifacio ES | GOVERNOR GENEROSO | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2645411.54 |  |  | Completed | 1 |  |  |  | 17LG0077 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | FAJR Const. Parts & Supply
NC 2017 | SHS | Region XI | Mati City | 304322 | Luzon National High School | GOVERNOR GENEROSO | 2 | 1 | 3 | 1STY3CL | BATCH 2 | 3734531.9 |  |  | Completed | 1 |  |  |  | 17LG0077 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | FAJR Const. Parts & Supply
NC 2017 | K10 | Region XI | Mati City | 129298 | Pundaguitan Elementary School | GOVERNOR GENEROSO | 2 | 1 | 3 | 1STY3CL | BATCH 2 | 3773220.53 |  |  | Completed | 1 |  |  |  | 17LG0074 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | Legacy Construction Corporation
NC 2017 | K10 | Region XI | Mati City | 129299 | Quezon ES | GOVERNOR GENEROSO | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2678448.15 |  |  | Completed | 1 |  |  |  | 17LG0074 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | Legacy Construction Corporation
NC 2017 | K10 | Region XI | Mati City | 129289 | Serapion Basalo ES | GOVERNOR GENEROSO | 2 | 1 | 4 | 1STY4CL | BATCH 2 | 5040106.11 |  |  | Completed | 1 |  |  |  | 17LG0068 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | FFJJ Construction
NC 2017 | SHS | Region XI | Mati City | 304336 | Sigaboy Agri. Voc. HS | GOVERNOR GENEROSO | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2638633.77 |  |  | Completed | 1 |  |  |  | 17LG0069 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | Legacy Construction Corporation
NC 2017 | SHS | Region XI | Mati City | 304336 | Sigaboy Agri. Voc. HS | GOVERNOR GENEROSO | 2 |  | 2 | 1STY2CL | BATCH 2 | 2638623.96 |  |  | Completed | 1 |  |  |  | 17LG0069 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | Legacy Construction Corporation
NC 2017 | K10 | Region XI | Mati City | 129300 | Tamban ES | GOVERNOR GENEROSO | 2 | 1 | 4 | 1STY4CL | BATCH 2 | 5036588.96 |  |  | Completed | 1 |  |  |  | 17LG0070 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | FFJJ Construction
NC 2017 | K10 | Region XI | Mati City | 129325 | Benito Barol Sr. ES | LUPON | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2645902.43 |  |  | Completed | 1 |  |  |  | 17LG0085 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | LLM Unified Builders & Trading Corp.
NC 2017 | K10 | Region XI | Mati City | 129330 | Comara T. Manuel CES II | LUPON | 2 | 1 | 3 | 1STY3CL | BATCH 2 | 3702877.56 |  |  | Completed | 1 |  |  |  | 17LG0071 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | Legacy Construction Corporation
NC 2017 | K10 | Region XI | Mati City | 129330 | Comara T. Manuel CES II | LUPON | 2 |  | 3 | 1STY3CL | BATCH 2 | 3702877.56 |  |  | Completed | 1 |  |  |  | 17LG0071 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | Legacy Construction Corporation
NC 2017 | K10 | Region XI | Mati City | 129320 | Tiombocan Elementary School | LUPON | 2 | 1 | 3 | 1STY3CL | BATCH 2 | 3927975.05 |  |  | Completed | 1 |  |  |  | 17LG0072 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | FFJJ Construction
NC 2017 | K10 | Region XI | Mati City | 129425 | Batobato CES | SAN ISIDRO | 2 | 1 | 5 | 1STY5CL | BATCH 2 | 6026491.49 |  |  | Completed | 1 |  |  |  | 17LG0073 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | Five Massive Infra & Supply
NC 2017 | K10 | Region XI | Mati City | 129426 | Dugmanon ES | SAN ISIDRO | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2667298.99 |  |  | Completed | 1 |  |  |  | 17LG0086 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | Jecel Construction Supply
NC 2017 | K10 | Region XI | Mati City | 129441 | La Union ES | SAN ISIDRO | 2 | 1 | 5 | 1STY5CL | BATCH 2 | 6043471.86 |  |  | Completed | 1 |  |  |  | 17LG0075 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | FFJJ Construction
NC 2017 | K10 | Region XI | Mati City | 129429 | Lapu-Lapu ES | SAN ISIDRO | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2673712.16 |  |  | Completed | 1 |  |  |  | 17LG0076 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | Legacy Construction Corporation
NC 2017 | K10 | Region XI | Mati City | 129431 | Manikling ES | SAN ISIDRO | 2 | 1 | 3 | 1STY3CL | BATCH 2 | 3734531.895 |  |  | Completed | 1 |  |  |  | 17LG0084 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | FFJJ Construction
NC 2017 | K10 | Region XI | Mati City | 129431 | Manikling ES | SAN ISIDRO | 2 |  | 3 | 1STY3CL | BATCH 2 | 3734531.895 |  |  | Completed | 1 |  |  |  | 17LG0084 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | FFJJ Construction
NC 2017 | SHS | Region XI | Mati City | 304332 | San Isidro NHS | SAN ISIDRO | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2647275.33 |  |  | Completed | 1 |  |  |  | 17LG0076 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | Legacy Construction Corporation
NC 2017 | K10 | Region XI | Mati City | 129442 | Talisay ES | SAN ISIDRO | 2 | 1 | 3 | 1STY3CL | BATCH 2 | 3740862.765 |  |  | Completed | 1 |  |  |  | 17LG0087 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | Legacy Construction Corporation
NC 2017 | K10 | Region XI | Mati City | 129442 | Talisay ES | SAN ISIDRO | 2 |  | 3 | 1STY3CL | BATCH 2 | 3740862.765 |  |  | Completed | 1 |  |  |  | 17LG0087 | 2017-07-25 | 2017-08-02 | 2017-08-15 | 2017-08-29 | 2017-09-26 | Legacy Construction Corporation
NC 2017 | K10 | Region XI | Compostela Valley | 204020 | Corazon C. Aquino ES | COMPOSTELA | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128384 | Lahi ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3083000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128432 | Haguimitan ES | MONKAYO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3103000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128448 | Pilar ES | MONKAYO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3133000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128454 | Totoy ES | MONKAYO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3123000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128459 | Banagbanag ES | MONTEVISTA | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3133000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128520 | Magsaysay ES | NEW BATAAN | 1 | 1 | 5 | 1STY5CL | BATCH 4 | 7154000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129711 | A. Mabini Elementary School | DAVAO CITY | 1 | 1 | 4 | 2STY4CL | BATCH 4 | 8945000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304343 | Baguio National School of Arts and Trades | DAVAO CITY | 3 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 3325000 |  |  | Completed | 1 |  |  |  | 17LH0120 | 2017-09-25 |  | 2017-10-05 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129465 | Bala ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2656600 |  |  | Completed | 1 |  |  |  | 17LH0078 | 2017-07-16 |  | 2017-09-26 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129727 | Balderas ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2738255 |  |  | Completed | 1 |  |  |  | 17LH0090 | 2017-07-20 |  | 2017-09-28 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129731 | Biao ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 3073600 |  |  | Completed | 1 |  |  |  | 17LH0094 | 2017-07-20 |  | 2017-09-28 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129732 | Biao Guianga ES. | DAVAO CITY | 3 | 1 | 4 | 1STY4CL | BATCH 4 | 4966000 |  |  | Completed | 1 |  |  |  | 17LH0155 | 2017-10-19 |  | 2017-10-26 | 2017-12-01 | 2017-12-08
NC 2017 | K10 | Region XI | Davao City | 129732 | Biao Guianga ES. | DAVAO CITY | 3 |  | 4 | 1STY4CL | BATCH 4 | 4966000 |  |  | Completed | 1 |  |  |  | 17LH0158 | 2017-10-19 |  | 2017-10-26 | 2017-12-01 | 2017-12-08
NC 2017 | TVL | Region XI | Davao City | 304347 | Biao NHS | DAVAO CITY | 3 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 4179900 |  |  | Completed | 1 |  |  |  | 17LH0118 | 2017-09-25 |  | 2017-10-05 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129586 | Binaton ES | DAVAO CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2920000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304350 | Binugao NHS | DAVAO CITY | 3 | 1 | 2 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 7246200 |  |  | Completed | 1 |  |  |  | 17LH0129 | 2017-09-25 |  | 2017-10-05 | 2017-11-16 | 2017-11-22
NC 2017 | TVL | Region XI | Davao City | 304353 | Buda NHS | DAVAO CITY | 3 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 4037600 |  |  | Completed | 1 |  |  |  | 17LH0127 | 2017-09-25 |  | 2017-10-05 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129655 | Butay ES | DAVAO CITY | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 4150000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129563 | Cabagtukan ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2738255 |  |  | Completed | 1 |  |  |  | 17LH0092 | 2017-07-20 |  | 2017-09-28 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129466 | Cadalian ES | DAVAO CITY | 3 | 1 | 4 | 1STY4CL | BATCH 4 | 5170800 |  |  | Completed | 1 |  |  |  | 17LH0108 | 2017-07-20 |  | 2017-09-28 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129531 | Calinan Central ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2840800 |  |  | Completed | 1 |  |  |  | 17LH0093 | 2017-07-20 |  | 2017-09-28 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129494 | Catigan ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2745300 |  |  | Completed | 1 |  |  |  | 17LH0080 | 2017-07-16 |  | 2017-09-26 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129494 | Catigan ES | DAVAO CITY | 3 |  | 2 | 1STY2CL | BATCH 4 | 2742300 |  |  | Completed | 1 |  |  |  | 17LH0097 | 2017-07-20 |  | 2017-09-28 | 2017-11-16 | 2017-11-22
NC 2017 | TVL | Region XI | Davao City | 316207 | Crossing Bayabas NHS - Camansi HS Annex | DAVAO CITY | 3 | 1 | 2 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 7837900 |  |  | Completed | 1 |  |  |  | 17LH0151 | 2017-10-19 |  | 2017-10-26 | 2017-12-01 | 2017-12-08
NC 2017 | TVL | Region XI | Davao City | 316206 | Crossing Bayabas NHs - Don Enrique Bustamante NHS | DAVAO CITY | 3 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 3325000 |  |  | Completed | 1 |  |  |  | 17LH0152 | 2017-10-19 |  | 2017-10-26 | 2017-12-01 | 2017-12-08
NC 2017 | TVL | Region XI | Davao City | 304357 | Crossing Bayabas NHS - E. B. Lopez Mem. NHS | DAVAO CITY | 3 | 1 | 2 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 6769200 |  |  | Completed | 1 |  |  |  | 17LH0149 | 2017-10-19 |  | 2017-10-26 | 2017-12-01 | 2017-12-08
NC 2017 | K10 | Region XI | Davao City | 129589 | Crossing Malabog ES | DAVAO CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2920000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304358 | Dacudao NHS | DAVAO CITY | 3 | 1 | 2 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 6927100 |  |  | Completed | 1 |  |  |  | 17LH0131 | 2017-09-25 |  | 2017-10-05 | 2017-11-16 | 2017-11-17
NC 2017 | K10 | Region XI | Davao City | 129604 | Datu Duyan ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2943600 |  |  | Completed | 1 |  |  |  | 17LH0082 | 2017-07-16 |  | 2017-09-26 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129659 | Datu Libayao ES | DAVAO CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2920000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129659 | Datu Libayao ES | DAVAO CITY | 2 |  | 2 | 1STY2CL | BATCH 4 | 2920000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129605 | Datu Lompipi ES | DAVAO CITY | 3 | 1 | 4 | 1STY4CL | BATCH 4 | 5178500 |  |  | Completed | 1 |  |  |  | 17LH0107 | 2017-07-20 |  | 2017-09-28 | 2017-11-10 | 2017-11-17
NC 2017 | TVL | Region XI | Davao City | 304344 | Elias P. Dacudao Gumalang School of Home Industries | DAVAO CITY | 3 | 1 | 2 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 6910900 |  |  | Completed | 1 |  |  |  | 17LH0133 | 2017-08-24 |  | 2017-09-19 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129511 | Fatima ES | DAVAO CITY | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 4150000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304383 | G.Astilla Sr. Cultural Minority HS - Marilog NHS Annex | DAVAO CITY | 3 | 1 | 2 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 7127400 |  |  | Completed | 1 |  |  |  | 17LH0150 | 2017-10-19 |  | 2017-10-26 | 2017-12-01 | 2017-12-08
NC 2017 | K10 | Region XI | Davao City | 129685 | Gasco ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2865500 |  |  | Completed | 1 |  |  |  | 17LH0098 | 2017-07-20 |  | 2017-09-28 | 2017-11-16 | 2017-11-22
NC 2017 | SHS | Region XI | Davao City | 304369 | Gorgonio Tajo, Sr. NHS | DAVAO CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2750000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129568 | Kanacan ES | DAVAO CITY | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 4445700 |  |  | Completed | 1 |  |  |  | 17LH0069 | 2017-07-16 |  | 2017-09-26 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129557 | Kapt. T. Monteverde Sr. CES | DAVAO CITY | 1 | 1 | 4 | 2STY4CL | BATCH 4 | 8995000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129663 | Labo ES | DAVAO CITY | 2 | 1 | 5 | 1STY5CL | BATCH 4 | 6270000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129569 | Lamanan ES | DAVAO CITY | 3 | 1 | 4 | 1STY4CL | BATCH 4 | 5305000 |  |  | Completed | 1 |  |  |  | 17LH0157 | 2017-10-19 |  | 2017-10-26 | 2017-12-01 | 2017-12-08
NC 2017 | K10 | Region XI | Davao City | 129536 | Lampianao ES | DAVAO CITY | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3931403 |  |  | Completed | 1 |  |  |  | 17LH0077 | 2017-07-16 |  | 2017-09-26 | 2017-11-16 | 2017-11-22
NC 2017 | TVL | Region XI | Davao City | 304374 | Lower Tamugan NHS | DAVAO CITY | 3 | 1 | 2 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 6743900 |  |  | Completed | 1 |  |  |  | 17LH0137 | 2017-08-24 |  | 2017-09-19 | 2017-11-16 | 2017-11-22
NC 2017 | TVL | Region XI | Davao City | 304342 | Ma. Cristina P. Belcar Agricultural High School | DAVAO CITY | 3 | 1 | 3 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 9975000 |  |  | Completed | 1 |  |  |  | 17LH0136 | 2017-08-24 |  | 2017-09-19 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129615 | Magsaysay ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2774600 |  |  | Completed | 1 |  |  |  | 17LH0101 | 2017-07-20 |  | 2017-09-28 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129470 | Malalan ES | DAVAO CITY | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3895600 |  |  | Completed | 1 |  |  |  | 17LH0068 | 2017-07-16 |  | 2017-09-26 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129470 | Malalan ES | DAVAO CITY | 3 |  | 4 | 1STY4CL | BATCH 4 | 5136000 |  |  | Completed | 1 |  |  |  | 17LH0106 | 2017-07-20 |  | 2017-09-28 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129617 | Malamba Elementary School | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2762500 |  |  | Completed | 1 |  |  |  | 17LH0100 | 2017-07-20 |  | 2017-09-28 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129618 | Malikongkong ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2969100 |  |  | Completed | 1 |  |  |  | 17LH0087 | 2017-07-16 |  | 2017-09-26 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 206006 | Maluan Elementary School | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2907800 |  |  | Completed | 1 |  |  |  | 17LH0084 | 2017-07-16 |  | 2017-09-26 | 2017-11-16 | 2017-11-22
NC 2017 | SHS | Region XI | Davao City | 304380 | Mandug NHS (Pablo Lorenzo NHS) | DAVAO CITY | 2 | 1 | 4 | 2STY4CL | BATCH 4 | 8945000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129471 | Mangas-As ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2826500 |  |  | Completed | 1 |  |  |  | 17LH0081 | 2017-07-16 |  | 2017-09-26 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129636 | Marahan West ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2774600 |  |  | Completed | 1 |  |  |  | 17LH0099 | 2017-07-20 |  | 2017-09-28 | 2017-11-16 | 2017-11-22
NC 2017 | TVL | Region XI | Davao City | 304381 | Marilog HS Of Agriculture (Tech-Voc School) | DAVAO CITY | 3 | 1 | 2 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 7258700 |  |  | Completed | 1 |  |  |  | 17LH0138 | 2017-08-24 |  | 2017-09-19 | 2017-11-16 | 2018-11-22
NC 2017 | TVL | Region XI | Davao City | 304382 | Marilog National High School | DAVAO CITY | 3 | 1 | 2 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 7130300 |  |  | Completed | 1 |  |  |  | 17LH0139 | 2017-08-24 |  | 2017-09-19 | 2017-11-16 | 2018-11-22
NC 2017 | TVL | Region XI | Davao City | 304384 | Marilog NHS - Marahan NHS | DAVAO CITY | 3 | 1 | 2 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 6887700 |  |  | Completed | 1 |  |  |  | 17LH0140 | 2017-08-24 |  | 2017-09-19 | 2017-11-16 | 2018-11-22
NC 2017 | TVL | Region XI | Davao City | 304385 | Mintal Comprehensive High School | DAVAO CITY | 3 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 3925700 |  |  | Completed | 1 |  |  |  | 17LH0121 | 2017-09-25 |  | 2017-10-05 | 2017-11-16 | 2017-11-22
NC 2017 | TVL | Region XI | Davao City | 304387 | Mintal NCHS - Tugbok National HS | DAVAO CITY | 3 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 3325000 |  |  | Completed | 1 |  |  |  | 17LH0123 | 2017-09-25 |  | 2017-10-05 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129496 | Mt. Apo ES. | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2916500 |  |  | Completed | 1 |  |  |  | 17LH0097 | 2017-07-20 |  | 2017-09-28 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129623 | Nangalid Elementary School | DAVAO CITY | 3 | 1 | 4 | 1STY4CL | BATCH 4 | 5112814.7 |  |  | Completed | 1 |  |  |  | 17LH0073 | 2017-07-16 |  | 2017-09-26 | 2017-11-16 | 2017-11-22
NC 2017 | TVL | Region XI | Davao City | 316203 | Optaciano Hilay NHS - Mulig NHS Annex | DAVAO CITY | 3 | 1 | 3 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 10262200 |  |  | Completed | 1 |  |  |  | 17LH0141 | 2017-08-24 |  | 2017-09-19 | 2017-11-16 | 2018-11-22
NC 2017 | K10 | Region XI | Davao City | 129572 | Pablo Sebuan Elementary School | DAVAO CITY | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3996700 |  |  | Completed | 1 |  |  |  | 17LH0071 | 2017-07-16 |  | 2017-09-26 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 206005 | Pamantawan PS | DAVAO CITY | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 4150000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Davao City | 304390 | Panaga High School-(Paquibato NHS Annex) | DAVAO CITY | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 4150000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129574 | Pangyan PS | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2826500 |  |  | Completed | 1 |  |  |  | 17LH0083 | 2017-07-16 |  | 2017-09-26 | 2017-11-16 | 2017-11-22
NC 2017 | SHS | Region XI | Davao City | 304389 | Paquibato NHS | DAVAO CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 3000000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304389 | Paquibato NHS | DAVAO CITY | 2 |  | 2 | TVL REGULAR WORKSHOP BLDG. | BATCH 4 | 8590000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129673 | Pegdalahan ES | DAVAO CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2920000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129575 | Popo ES | DAVAO CITY | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3931403 |  |  | Completed | 1 |  |  |  | 17LH0088 | 2017-07-16 |  | 2017-09-26 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129690 | San Isidro ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2750400 |  |  | Completed | 1 |  |  |  | 17LH0095 | 2017-07-20 |  | 2017-09-28 | 2017-11-16 | 2017-11-22
NC 2017 | TVL | Region XI | Davao City | 304398 | Sirawan NHS | DAVAO CITY | 3 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 3355300 |  |  | Completed | 1 |  |  |  | 17LH0128 | 2017-09-25 |  | 2017-10-05 | 2017-11-16 | 2017-11-22
NC 2017 | TVL | Region XI | Davao City | 304386 | Sto. Niño National High School | DAVAO CITY | 3 | 1 | 2 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 8312200 |  |  | Completed | 1 |  |  |  | 17LH0142 | 2017-08-24 |  | 2017-09-19 | 2017-11-16 | 2018-11-22
NC 2017 | TVL | Region XI | Davao City | 316208 | Suawan High School- Annex of Lower Tamugan National High School | DAVAO CITY | 3 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 3784100 |  |  | Completed | 1 |  |  |  | 17LH0148 | 2017-10-19 |  | 2017-10-26 | 2017-12-01 | 2017-12-08
NC 2017 | TVL | Region XI | Davao City | 316208 | Suawan High School- Annex of Lower Tamugan National High School | DAVAO CITY | 3 |  | 1 | TVL REGULAR WORKSHOP BLDG. | BATCH 4 | 4075548 |  |  | Completed | 1 |  |  |  | 17LH0154 | 2017-10-19 |  | 2017-10-26 | 2017-12-01 | 2017-12-08
NC 2017 | K10 | Region XI | Davao City | 129675 | Surayan ES | DAVAO CITY | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 4150000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129580 | Tagbaw Elementary | DAVAO CITY | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 4324543 |  |  | Completed | 1 |  |  |  | 17LH0089 | 2017-07-20 |  | 2017-09-28 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129677 | Tapak ES | DAVAO CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2920000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304397 | Telesforo S. Singson NHS | DAVAO CITY | 3 | 1 | 1 | TVL REGULAR WORKSHOP BLDG. | BATCH 4 | 5444070 |  |  | Completed | 1 |  |  |  | 17LH0153 | 2017-10-19 |  | 2017-10-26 | 2017-12-01 | 2017-12-08
NC 2017 | K10 | Region XI | Davao City | 129513 | Teofilo Fernandez ES | DAVAO CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2750000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129581 | Titogop Elementary School | DAVAO CITY | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3834565.34 |  |  | Completed | 1 |  |  |  | 17LH0072 | 2017-07-16 |  | 2017-09-26 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129743 | Tugbok Central ES SPED Center | DAVAO CITY | 3 | 1 | 4 | 1STY4CL | BATCH 4 | 4902200 |  |  | Completed | 1 |  |  |  | 17LH0070 | 2017-07-16 |  | 2017-09-26 | 2017-11-16 | 2017-11-22
NC 2017 | K10 | Region XI | Davao City | 129635 | Upper Masawang ES | DAVAO CITY | 3 | 1 | 4 | 1STY4CL | BATCH 4 | 4849950 |  |  | Completed | 1 |  |  |  | 17LH0156 | 2017-10-19 |  | 2017-10-26 | 2017-12-01 | 2017-12-08
NC 2017 | K10 | Region XI | Davao City | 129635 | Upper Masawang ES | DAVAO CITY | 3 |  | 4 | 1STY4CL | BATCH 4 | 4849950 |  |  | Completed | 1 |  |  |  | 17LH0159 | 2017-10-19 |  | 2017-10-26 | 2017-12-01 | 2017-12-08
NC 2017 | TVL | Region XI | Davao City | 304355 | Wangan National High School-Calinan NHS Annex | DAVAO CITY | 3 | 1 | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 3653300 |  |  | Completed | 1 |  |  |  | 17LH0125 | 2017-07-16 |  | 2017-09-26 | 2017-11-16 | 2017-11-22
NC 2017 | TVL | Region XI | Davao del Norte | 304217 | Asuncion National High School | ASUNCION (SAUG) | 1 | 1 | 2 | TVL REGULAR WORKSHOP BLDG. | BATCH 4 | 5953418.97 |  |  | Completed | 1 |  |  | P00174036MN-CW1 | 17LC0237 | 2017-07-12 | 2017-07-19 | 2017-09-22 | 2017-10-10 | 2017-10-27 | Micah Const. & Supply
NC 2017 | TVL | Region XI | Davao del Norte | 304221 | Antonio V. Fruto Sr. NHS | BRAULIO E. DUJALI | 2 | 1 | 3 | TVL REGULAR WORKSHOP BLDG. | BATCH 4 | 8864235 |  |  | Completed | 1 |  |  | P00182250MN-CW1 | 17LC0430 | 2017-11-06 | 2017-11-23 | 2017-12-14 | 2017-12-22 | 2017-11-03 | CJEP Builders and Engineering Services
NC 2017 | TVL | Region XI | Davao del Norte | 304229 | Dujali National High School | BRAULIO E. DUJALI | 2 | 1 | 3 | TVL REGULAR WORKSHOP BLDG. | BATCH 4 | 8592125 |  |  | Completed | 1 |  |  | P00174040MN-CW1 | 17LC0241 | 2017-07-12 | 2017-07-19 | 2017-09-22 | 2017-10-20 | 2017-11-03 | Micah Const. & Supply
NC 2017 | TVL | Region XI | Davao del Norte | 304229 | Dujali National High School | BRAULIO E. DUJALI | 2 |  | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 3475061.14 |  |  | Completed | 1 |  |  | P00174041MN-CW1 | 17LC0242 | 2017-07-12 | 2017-07-19 | 2017-09-22 | 2017-10-20 | 2017-11-03 | Micah Const. & Supply
NC 2017 | TVL | Region XI | Davao del Norte | 304222 | Carmen NHS | CARMEN | 2 | 1 | 5 | TVL REGULAR WORKSHOP BLDG. | BATCH 4 | 15185284.56 |  |  | Completed | 1 |  |  | P00174042MN-CW1 | 17LC0243 | 2017-07-12 | 2017-07-19 | 2017-09-26 | 2017-10-12 | 2017-10-27 | LLM Unified Builders and Trading Corp.
NC 2017 | TVL | Region XI | Davao del Norte | 315901 | Tubod National High School | CARMEN | 2 | 1 | 4 | TVL REGULAR WORKSHOP BLDG. | BATCH 4 | 10905054 |  |  | Completed | 1 |  |  | P00174043MN-CW1 | 17LC0244 | 2017-07-12 | 2017-07-19 | 2017-09-22 | 2017-10-10 | 2017-10-27 | RCBAR Builders
NC 2017 | TVL | Region XI | Davao del Norte | 315901 | Tubod National High School | CARMEN | 2 |  | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 3349781.59 |  |  | Completed | 1 |  |  | P00174044MN-CW1 | 17LC0245 | 2017-07-12 | 2017-07-19 | 2017-09-22 | 2017-10-10 | 2017-11-03 | RCBAR Builders
NC 2017 | K10 | Region XI | Davao del Norte | 128709 | Limbaan ES | NEW CORELLA | 1 | 1 | 4 | 1STY4CL | BATCH 4 | 5223493 |  |  | Completed | 1 |  |  | P00174037MN-CW1 | 17LC0309 | 2017-07-12 | 2017-07-19 | 2017-09-26 | 2017-10-12 | 2017-10-30 | Mark Anthony Const. & Supply
NC 2017 | K10 | Region XI | Davao del Norte | 128595 | Sawata Ernandcor CES | SAN ISIDRO | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 4059843 |  |  | Completed | 1 |  |  | P00174038MN-CW1 | 17LC0316 | 2017-07-12 | 2017-07-19 | 2017-09-26 | 2017-10-12 | 2017-10-30 | CJEP Builders and Engineering Services
NC 2017 | TVL | Region XI | Davao del Norte | 304237 | Kimamon National High School | SANTO TOMAS | 2 | 1 | 1 | TVL REGULAR WORKSHOP BLDG. | BATCH 4 | 2858997.19 |  |  | Completed | 1 |  |  | P00174045MN-CW1 | 17LC0240 | 2017-07-12 | 2017-07-19 | 2017-09-22 | 2017-10-10 | 2017-10-27 | Micah Construction & Supply
NC 2017 | TVL | Region XI | Davao del Norte | 304256 | Salvacion NHS | SANTO TOMAS | 2 | 1 | 1 | TVL REGULAR WORKSHOP BLDG. | BATCH 4 | 2920655 |  |  | Completed | 1 |  |  | P00174048MN-CW1 | 17LC0255 | 2017-07-12 | 2017-07-19 | 2017-09-22 | 2017-10-10 |  | Micah Construction and Supply
NC 2017 | TVL | Region XI | Davao del Norte | 304254 | Sto Tomas NHS | SANTO TOMAS | 2 | 1 | 4 | TVL REGULAR WORKSHOP BLDG. | BATCH 4 | 12245618 |  |  | Completed | 1 |  |  | P00174046MN-CW1 | 17LC0256 | 2017-07-12 | 2017-07-19 | 2017-09-26 | 2017-10-12 | 2017-10-30 | Micah Construction & Supply
NC 2017 | TVL | Region XI | Davao del Norte | 304254 | Sto Tomas NHS | SANTO TOMAS | 2 |  | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 3455351.44 |  |  | Completed | 1 |  |  | P00174047MN-CW1 | 17LC0257 | 2017-07-12 | 2017-07-19 | 2017-09-22 | 2017-10-10 | 2017-11-03 | Micah Construction & Supply
NC 2017 | TVL | Region XI | Davao del Norte | 315902 | Tulalian NHS | SANTO TOMAS | 2 | 1 | 3 | TVL REGULAR WORKSHOP BLDG. | BATCH 4 | 8303356.43 |  |  | Completed | 1 |  |  | P00174049MN-CW1 | 17LC0258 | 2017-07-12 | 2017-07-19 | 2017-09-26 | 2017-10-12 | 2017-10-27 | Micah Construction and Supply
NC 2017 | TVL | Region XI | Davao del Norte | 315902 | Tulalian NHS | SANTO TOMAS | 2 |  | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 4 | 3335596.88 |  |  | Completed | 1 |  |  | P00174050MN-CW1 | 17LC0259 | 2017-07-12 | 2017-07-19 | 2017-09-26 | 2017-10-12 | 2017-11-03 | Mark Anthony Construction and Supply
NC 2017 | K10 | Region XI | Davao del Sur |  | Libertad NHS | BANSALAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2648186 |  |  | Completed | 1 |  |  |  |  | 2017-09-12 |  | 2017-09-25 |  | 2017-10-26 | LTB Builders and Construction
NC 2017 | K10 | Region XI | Davao del Sur |  | Libertad NHS | BANSALAN | 1 |  | 2 | 1STY2CL | BATCH 4 | 2648186 |  |  | Completed | 1 |  |  |  |  | 2017-09-12 |  | 2017-09-25 |  | 2017-10-26 | LTB Builders and Construction
NC 2017 | K10 | Region XI | Davao del Sur | 128860 | Lapulabao ES | HAGONOY | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2640966 |  |  | Completed | 1 |  |  |  |  | 2017-09-12 |  | 2017-09-25 |  | 2017-10-26 | Digos Constrak Corporation
NC 2017 | K10 | Region XI | Davao del Sur | 128875 | Tologan ES | HAGONOY | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2645946 |  |  | Completed | 1 |  |  |  |  | 2017-09-12 |  | 2017-09-25 |  | 2017-10-26 | Leamor Construction and Supply
NC 2017 | K10 | Region XI | Davao del Sur |  | Kimlawis NHS | KIBLAWAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2806786 |  |  | Completed | 1 |  |  |  |  | 2017-10-04 |  | 2017-10-19 |  | 2017-11-03 | Lite Heavey Equipment & Trading services
NC 2017 | K10 | Region XI | Davao del Sur |  | Kimlawis NHS | KIBLAWAN | 1 |  | 2 | 1STY2CL | BATCH 4 | 2806786 |  |  | Completed | 1 |  |  |  |  | 2017-10-04 |  | 2017-10-19 |  | 2017-11-03 | Lite Heavey Equipment & Trading services
NC 2017 | K10 | Region XI | Davao del Sur | 128916 | SAN ISIDRO ELEMENTARY SCHOOL | KIBLAWAN | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3842585.1 |  |  | Completed | 1 |  |  |  |  | 2017-09-12 |  | 2017-09-25 |  | 2017-10-26 | Dingo Builders & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 128918 | Sto. Niño ES | KIBLAWAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2727506 |  |  | Completed | 1 |  |  |  |  | 2017-09-12 |  | 2017-09-25 |  | 2017-10-26 | Prindi Construction
NC 2017 | K10 | Region XI | Davao del Sur | 128923 | Barayong CES | MAGSAYSAY | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3770140.1 |  |  | Completed | 1 |  |  |  |  | 2017-09-12 |  | 2017-09-26 |  | 2017-10-26 | NLC Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 316009 | Kasuga National High School | MAGSAYSAY | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2639883.92 |  |  | Completed | 1 |  |  |  |  | 2017-09-12 |  | 2017-09-25 |  | 2017-10-26 | NLC Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 128942 | San Miguel ES | MAGSAYSAY | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2667151 |  |  | Completed | 1 |  |  |  |  | 2017-09-12 |  | 2017-09-25 |  | 2017-10-26 | Leamor Construction and Supply
NC 2017 | K10 | Region XI | Davao del Sur | 128948 | Bulacan ES | MALALAG | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2681016 |  |  | Completed | 1 |  |  |  |  | 2017-09-12 |  | 2017-09-25 |  | 2017-10-26 | Mark Anthony Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 129029 | Asinan ES | MATANAO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2740896 |  |  | Completed | 1 |  |  |  |  | 2017-09-12 |  | 2017-09-25 |  | 2017-10-26 | NLC Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 129014 | Camanchiles ES | MATANAO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2694576 |  |  | Completed | 1 |  |  |  |  | 2017-09-12 |  | 2017-09-25 |  | 2017-10-26 | Mark Anthony Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 129036 | Glot Towak ES | MATANAO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2690221 |  |  | Completed | 1 |  |  |  |  | 2017-09-12 |  | 2017-09-25 |  | 2017-10-26 | NLC Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 129017 | Matanao CES | MATANAO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2617226 |  |  | Completed | 1 |  |  |  |  | 2017-09-12 |  | 2017-09-25 |  | 2017-10-26 | RC Melgazo Builders
NC 2017 | K10 | Region XI | Davao del Sur |  | New Katipunan HS | MATANAO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2686641 |  |  | Completed | 1 |  |  |  |  | 2017-09-12 |  | 2017-09-25 |  | 2017-10-26 | Ecomixed Construction Development Corporation
NC 2017 | K10 | Region XI | Davao del Sur | 129019 | New Murcia ES | MATANAO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2648326 |  |  | Completed | 1 |  |  |  |  | 2017-09-12 |  | 2017-09-25 |  | 2017-10-26 | Davao Sanitary builders Corporation
NC 2017 | K10 | Region XI | Davao del Sur | 129024 | San Vicente ES | MATANAO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2648326 |  |  | Completed | 1 |  |  |  |  | 2017-09-12 |  | 2017-09-25 |  | 2017-10-26 | Mark Anthony Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 129026 | Sinawilan ES | MATANAO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2650506 |  |  | Completed | 1 |  |  |  |  | 2017-09-12 |  | 2017-09-25 |  | 2017-10-26 | LTB Builders
NC 2017 | K10 | Region XI | Davao del Sur |  | Malinao Agricultural HS | PADADA | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2639816 |  |  | Completed | 1 |  |  |  |  | 2017-09-12 |  | 2017-09-25 |  | 2017-10-26 | Mark Anthony Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur |  | Malinao Agricultural HS | PADADA | 1 |  | 2 | 1STY2CL | BATCH 4 | 2639816 |  |  | Completed | 1 |  |  |  |  | 2017-09-12 |  | 2017-09-25 |  | 2017-10-26 | Leamor Construction & supply
NC 2017 | K10 | Region XI | Davao del Sur | 129051 | Piape ES | PADADA | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3729200 |  |  | Completed | 1 |  |  |  |  | 2017-09-12 |  | 2017-09-25 |  | 2017-10-26 | LTB Builders & Construction
NC 2017 | K10 | Region XI | Davao del Sur |  | Perfecto Sagarino Sr. NHS | SULOP | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2648436 |  |  | Completed | 1 |  |  |  |  | 2017-09-12 |  | 2017-09-25 |  | 2017-10-26 | Mark Anthony Construction & Supply
NC 2017 | K10 | Region XI | Davao Occidental | 128891 | Aldo Pagagao Elementary School | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2869618 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128886 | Andres Yacon Sr. ES | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2869618 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128893 | ELEUTERIA S. CASTRO ES | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 3820117 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 129056 | Ignacia Guillermo ES (Butulan ES) | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2869618 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 205027 | Kidaman ES | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2999731 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 205027 | Kidaman ES | JOSE ABAD SANTOS (TRINIDAD) | 0 |  | 2 | 1STY2CL | BATCH 4 | 2999731 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128888 | Patulang ES | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2869618 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 129068 | Quiapo Elementary School | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2869618 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 129069 | San Isidro ES | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2869618 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 205050 | Tunggal Capitan ES | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2869618 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Davao Occidental | 304269 | B'Laan NHS | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2814922 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128967 | Felis Elementary School | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2728992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128968 | Fishing Village ES | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2728992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128984 | Julian M. Turado Elementary School | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2814922 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 205025 | Kangko ES | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2814922 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128972 | Kilalag Elementary School | MALITA | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 3820117 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 205026 | Kisawel Elementary School | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2814992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128973 | Kitana Elem. School | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2728992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128975 | Lafeud PS | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2728992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128996 | Lagumit ES | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2728992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 129000 | Macol ES | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2728992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 205056 | Malandog PS | MALITA | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 3820117 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 129001 | Malaway ES | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2728992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128977 | Malita Central Elementary School | MALITA | 0 | 1 | 4 | 1STY4CL | BATCH 4 | 4971628 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128977 | Malita Central Elementary School | MALITA | 0 |  | 2 | 1STY2CL | BATCH 4 | 2728992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 129003 | Manuel Peralta ES | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2814992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 129005 | New Argao ES | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2728992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 205053 | New Mabuhay ES | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2814992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128983 | Sarawagon PS | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2728992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128985 | Talogoy Elementary School | MALITA | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 3820117 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128982 | Teodorico Lopez ES (Sangay ES) | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2728992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 205042 | TFS-Kalamagan | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2814922 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 205038 | TFS-Tabunan PS | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2814922 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Davao Occidental | 304293 | Ticulon NHS | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2728992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 129103 | Basiawan CES | SANTA MARIA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2728992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 129106 | Cadaatan ES | SANTA MARIA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2728992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 129126 | De Guzman- Zapanta ES | SANTA MARIA | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 3820117 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 129112 | Kidadan ES | SANTA MARIA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2728992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 129120 | Mamacao ES | SANTA MARIA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2728992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 129121 | Migsulang Primary School | SANTA MARIA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2869618 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 129124 | San Agustin ES | SANTA MARIA | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 2728992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 129054 | Angel F. Olarte Sr. ES | SARANGANI | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3103679 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 129063 | Mabila CES | SARANGANI | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3103679 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 129066 | Patuko ES | SARANGANI | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3103679 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Oriental | 304307 | Caraga National High School | CARAGA | 1 | 1 | 10 | 4STY WORKSHOP BLDG (7X18) | BATCH 4 | 45401515.23 |  |  | Completed | 1 | [8 empty] | 2017-11-22 | RELY CONSTRUCTION
NC 2017 | TVL | Region XI | Davao Oriental | 304339 | Tarragona National High School | TARRAGONA | 1 | 1 | 6 | 3STY WORKSHOP BLDG (7X18) | BATCH 4 | 31412095.71 |  |  | Completed | 1 | [8 empty] | 2017-12-05 | FFJJ CONSTRUCTION
NC 2017 | K10 | Region XI | Digos City |  | Balabag NHS | CITY OF DIGOS (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2673466 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Digos City | 129774 | Binaton ES | CITY OF DIGOS (Capital) | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2990648 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Digos City | 129750 | Digos City CES | CITY OF DIGOS (Capital) | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2853308 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Digos City | 316304 | Digos City NHS - Soong HS Annex | CITY OF DIGOS (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3806119.02 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Digos City | 129753 | Federico Alferez ES (Goma) | CITY OF DIGOS (Capital) | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2921179 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Digos City |  | Igpit NHS | CITY OF DIGOS (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2669046 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Digos City | 129772 | San Miguel ES | CITY OF DIGOS (Capital) | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 4133207 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Digos City |  | Soong NHS | CITY OF DIGOS (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2875199 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Mati City | 316105 | Paniquian NHS | BANAYBANAY | 2 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 4 | 3328450.32 |  |  | Completed | 1 |  |  |  | 17LG0098 | 2017-10-03 | 2017-10-11 | 2017-10-24 | 2017-11-08 | 2017-11-27 | LLM Unified Builders & Trading Corp.
NC 2017 | TVL | Region XI | Mati City | 316105 | Paniquian NHS | BANAYBANAY | 2 |  | 1 | WORKSHOP BLDG. (7X18) | BATCH 4 | 2695757.02 |  |  | Completed | 1 |  |  |  | 17LG0098 | 2017-10-03 | 2017-10-11 | 2017-10-24 | 2017-11-08 | 2017-11-27 | LLM Unified Builders & Trading Corp.
NC 2017 | TVL | Region XI | Mati City | 304326 | Mati SAT | City of Mati (Capital) | 2 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 4 | 3312619.4533 |  |  | Completed | 1 |  |  |  | 17LG0099 | 2017-10-03 | 2017-10-11 | 2017-10-24 | 2017-11-08 | 2017-11-27 | FFJJ Construction
NC 2017 | TVL | Region XI | Mati City | 304326 | Mati SAT | City of Mati (Capital) | 2 |  | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 4 | 3312619.4533 |  |  | Completed | 1 |  |  |  | 17LG0099 | 2017-10-03 | 2017-10-11 | 2017-10-24 | 2017-11-08 | 2017-11-27 | FFJJ Construction
NC 2017 | TVL | Region XI | Mati City | 304326 | Mati SAT | City of Mati (Capital) | 2 |  | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 4 | 3312619.4533 |  |  | Completed | 1 |  |  |  | 17LG0099 | 2017-10-03 | 2017-10-11 | 2017-10-24 | 2017-11-08 | 2017-11-27 | FFJJ Construction
NC 2017 | TVL | Region XI | Mati City | 304338 | Taguibo Agri. Voc. High School | City of Mati (Capital) | 2 | 1 | 1 | WORKSHOP BLDG. (7X18) | BATCH 4 | 2700002.11 |  |  | Completed | 1 |  |  |  | 17LG0100 | 2017-10-03 | 2017-10-11 | 2017-10-24 | 2017-11-08 | 2017-11-27 | Jecel Construction Supply
NC 2017 | K10 | Region XI | Mati City | 129292 | Lavigan ES | GOVERNOR GENEROSO | 2 | 1 | 7 | 1STY3CL & 1STY4CL | BATCH 4 | 8852365.98 |  |  | Completed | 1 |  |  |  | 17LG0101 | 2017-10-03 | 2017-10-11 | 2017-10-24 | 2017-11-08 | 2017-11-27 | FFJJ Construction
NC 2017 | TVL | Region XI | Mati City | 304336 | Sigaboy Agri. Voc. HS | GOVERNOR GENEROSO | 2 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 4 | 3338019.528 |  |  | Completed | 1 |  |  |  | 17LG0102 | 2017-10-03 | 2017-10-11 | 2017-10-24 | 2017-11-08 | 2017-11-27 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 304336 | Sigaboy Agri. Voc. HS | GOVERNOR GENEROSO | 2 |  | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 4 | 3338019.528 |  |  | Completed | 1 |  |  |  | 17LG0102 | 2017-10-03 | 2017-10-11 | 2017-10-24 | 2017-11-08 | 2017-11-27 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 304336 | Sigaboy Agri. Voc. HS | GOVERNOR GENEROSO | 2 |  | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 4 | 3338019.528 |  |  | Completed | 1 |  |  |  | 17LG0102 | 2017-10-03 | 2017-10-11 | 2017-10-24 | 2017-11-08 | 2017-11-27 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 304336 | Sigaboy Agri. Voc. HS | GOVERNOR GENEROSO | 2 |  | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 4 | 3338019.528 |  |  | Completed | 1 |  |  |  | 17LG0102 | 2017-10-03 | 2017-10-11 | 2017-10-24 | 2017-11-08 | 2017-11-27 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 304336 | Sigaboy Agri. Voc. HS | GOVERNOR GENEROSO | 2 |  | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 4 | 3338019.528 |  |  | Completed | 1 |  |  |  | 17LG0102 | 2017-10-03 | 2017-10-11 | 2017-10-24 | 2017-11-08 | 2017-11-27 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 304320 | Bagumbayan Agro-Ind. HS | LUPON | 2 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 4 | 3350719.57 |  |  | Completed | 1 |  |  |  | 17LG0103 | 2017-10-03 | 2017-10-11 | 2017-10-24 | 2017-11-08 | 2017-11-27 | Melrobe Builders & Const. Supplies
NC 2017 | TVL | Region XI | Mati City | 304320 | Bagumbayan Agro-Ind. HS | LUPON | 2 |  | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 4 | 3350719.57 |  |  | Completed | 1 |  |  |  | 17LG0103 | 2017-10-03 | 2017-10-11 | 2017-10-24 | 2017-11-08 | 2017-11-27 | Melrobe Builders & Const. Supplies
NC 2017 | TVL | Region XI | Mati City | 304319 | Lupon Voc. HS | LUPON | 2 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 4 | 3312619.46 |  |  | Completed | 1 |  |  |  | 17LG0103 | 2017-10-03 | 2017-10-11 | 2017-10-24 | 2017-11-08 | 2017-11-27 | Melrobe Builders & Const. Supplies
NC 2017 | TVL | Region XI | Mati City | 304317 | Manuel S. Nasser, Sr. NHS | SAN ISIDRO | 2 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 4 | 3350719.57 |  |  | Completed | 1 |  |  |  | 17LG0104 | 2017-10-03 | 2017-10-11 | 2017-10-24 | 2017-11-08 | 2017-11-27 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 304332 | San Isidro NHS | SAN ISIDRO | 2 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 4 | 3338019.54 |  |  | Completed | 1 |  |  |  | 17LG0104 | 2017-10-03 | 2017-10-11 | 2017-10-24 | 2017-11-08 | 2017-11-27 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Panabo City | 304403 | A. O. Floirendo National High School | CITY OF PANABO | 2 | 1 | 4 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 12374724.19 |  |  | Completed | 1 |  |  |  | 17LG0135 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Agong Builders & Const. Supply, Inc.
NC 2017 | TVL | Region XI | Panabo City | 304403 | A. O. Floirendo National High School | CITY OF PANABO | 2 |  | 7 | WORKSHOP BLDG (7X18) | BATCH 4 | 19006683 |  |  | Completed | 1 | [9 empty] | CJEP Builders & Engineering Services
NC 2017 | TVL | Region XI | Panabo City | 304405 | Don Manuel A. Javellana Memorial National High School | CITY OF PANABO | 2 | 1 | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 6137706.16 |  |  | Completed | 1 | [9 empty] | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Panabo City | 316403 | Kauswagan National High School | CITY OF PANABO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3351886.45 |  |  | Completed | 1 | [9 empty] | Mark Anthony Construction & Supply
NC 2017 | TVL | Region XI | Panabo City | 316403 | Kauswagan National High School | CITY OF PANABO | 2 |  | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 2890655.9 |  |  | Completed | 1 | [9 empty] | MAG Corporation
NC 2017 | TVL | Region XI | Panabo City | 304409 | Little Panay National High School | CITY OF PANABO | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 6612235.4 |  |  | Completed | 1 | [9 empty] | CJEP Builders & Engineering Services
NC 2017 | TVL | Region XI | Panabo City | 304409 | Little Panay National High School | CITY OF PANABO | 2 |  | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 2837555.78 |  |  | Completed | 1 | [9 empty] | CJEP Builders & Engineering Services
NC 2017 | TVL | Region XI | Panabo City | 304407 | Manay National High School | CITY OF PANABO | 2 | 1 | 3 | WORKSHOP BLDG (7X18) | BATCH 4 | 8143414.61 |  |  | Completed | 1 | [9 empty] | CJEP Builders & Engineering Services
NC 2017 | TVL | Region XI | Panabo City | 316405 | Quezon High School - Panabo NHS Annex | CITY OF PANABO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3686956.42 |  |  | Completed | 1 | [9 empty] | Micah Construction & Supply
NC 2017 | TVL | Region XI | Panabo City | 316405 | Quezon High School - Panabo NHS Annex | CITY OF PANABO | 2 |  | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3215252.37 |  |  | Completed | 1 | [9 empty] | CJEP Builders & Engineering Services
NC 2017 | TVL | Region XI | Panabo City | 316402 | San Vicente National High School | CITY OF PANABO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3495819.27 |  |  | Completed | 1 | [9 empty] | Micah Construction & Supply
NC 2017 | TVL | Region XI | Panabo City | 316402 | San Vicente National High School | CITY OF PANABO | 2 |  | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3059071.82 |  |  | Completed | 1 | [9 empty] | Golden BuildAxis Corp.
NC 2017 | TVL | Region XI | Panabo City | 316401 | Southern Davao National High School | CITY OF PANABO | 2 | 1 | 4 | WORKSHOP BLDG (7X18) | BATCH 4 | 10798093.36 |  |  | Completed | 1 | [9 empty] | Five Massive Infra & Supply Corp.
NC 2017 | K10 | Region XI | Davao del Norte | 128807 | Sto. Niño CES | TALAINGOD | 1 | 1 | 4 | 1STY4CL | BATCH 5 | 4923982 |  |  | Completed | 1 |  |  | P00174544MN-CW1 | 17LC0264 | 2017-07-12 | 2017-07-19 | 2017-09-26 | 2017-10-22 | 2017-10-30 | Two Degrees Construction & Supply
NC 2017 | SHS | Region XI | Compostela Valley | 304182 | Mangayon NHS | COMPOSTELA | 1 | 1 | 8 | 2STY8CL | BATCH 7 | 19301000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 304182 | Mangayon NHS | COMPOSTELA | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4181000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128269 | Maparat ES | COMPOSTELA | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4309000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128274 | San Jose ES | COMPOSTELA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3033000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 304183 | San Miguel NHS | COMPOSTELA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4181000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128276 | Siocon Elementary School | COMPOSTELA | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 6066000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304189 | Laak NHS | LAAK | 2 | 1 | 16 | 4STY16CL | BATCH 7 | 35535000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128283 | Banbanon ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128290 | Candiis ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128293 | Datu Ampunan ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3333000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128294 | Datu Davao Elementary School | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3533000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128295 | Doña Josefa ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3133000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128296 | El Katipunan ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128297 | Hinagtungan ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128298 | Ilpapa ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3108000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128303 | Kibaguio ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3133000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 204022 | Limot ES | LAAK (SAN VICENTE) | 2 | 1 | 4 | 1STY4CL | BATCH 7 | 5648000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128315 | Malinao ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3108000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128316 | Mangloy ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128320 | Panamoren ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3108000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128329 | Cabuyoan ES | MABINI (DOÑA ALICIA) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128338 | Masicareg ES | MABINI (DOÑA ALICIA) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3283000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128348 | Gayab ES | MACO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128366 | Kaburakanan ES | MACO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3083000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128354 | Magangit ES | MACO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128357 | New Visayas ES | MACO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3108000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128361 | Singanan PS | MACO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3108000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128362 | Taglawig ES | MACO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3054000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304207 | Paloc NHS | MARAGUSAN | 1 | 1 | 12 | 3STY12CL | BATCH 7 | 33513000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128378 | Bagong Silang ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4309000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 315813 | Langgawisan National High School | MARAGUSAN (SAN MARIANO) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4881000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128392 | New Katipunan ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128395 | New Panay ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3033000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 304207 | Paloc NHS | MARAGUSAN (SAN MARIANO) | 1 |  | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 8696000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128408 | Guisok PS | MAWAB | 2 | 1 | 4 | 1STY4CL | BATCH 7 | 5548000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128420 | Tabontabon ES | MAWAB | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3083000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128422 | Tuboran ES | MAWAB | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3033000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 304176 | Babag NHS | MONKAYO | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4181000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304176 | Babag NHS | MONKAYO | 1 |  | 12 | 3STY12CL | BATCH 7 | 27907000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128429 | Boay ES | MONKAYO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3234000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 315801 | Monkayo NHS - Casoon HS Annex | MONKAYO | 1 |  | 12 | 3STY12CL | BATCH 7 | 28057000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 315801 | Monkayo NHS- Casoon HS Annex | MONKAYO | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4231000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 304201 | Pasian NHS | MONKAYO | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4181000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304201 | Pasian NHS | MONKAYO | 1 |  | 12 | 3STY12CL | BATCH 7 | 27867000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128449 | Rizal Memorial ES | MONKAYO | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4309000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128451 | San Isidro ES | MONKAYO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3234000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128452 | San Jose ES | MONKAYO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3033000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 304203 | Montevista NHS - Annex (DNAS Campus) | MONTEVISTA | 1 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 7996000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304203 | Montevista NHS - Annex (DNAS Campus) | MONTEVISTA | 1 |  | 12 | 3STY12CL | BATCH 7 | 28515000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128478 | San Vicente ES | MONTEVISTA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3033000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 304177 | Bantacan NHS | NEW BATAAN | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4181000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304177 | Bantacan NHS | NEW BATAAN | 1 |  | 16 | 2UNITS 2STY8CL | BATCH 7 | 37453000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 304180 | Camanlangan NHS | NEW BATAAN | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4181000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304180 | Camanlangan NHS | NEW BATAAN | 1 |  | 16 | 2UNITS 2STY8CL | BATCH 7 | 37151000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 304206 | New Bataan NHS | NEW BATAAN | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4181000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304206 | New Bataan NHS | NEW BATAAN | 1 |  | 16 | 4STY16CL | BATCH 7 | 34204000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128527 | San Isidro ES | NEW BATAAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128534 | Ayan ES | PANTUKAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128540 | Boringot ES | PANTUKAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3733000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128541 | Diat ES | PANTUKAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 5009000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128557 | Pulang Lupa PS | PANTUKAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3533000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128558 | Sarog ES | PANTUKAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4709000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128559 | Sta. Teresa ES | PANTUKAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4309000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City |  | Davao City NHS (Annex) | DAVAO CITY | 1 | 1 | 12 | 4STY12CL | BATCH 7 | 34281773 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City |  | Davao City NHS (Annex) | DAVAO CITY | 1 |  | 9 | 3STY9CL (L-TYPE) | BATCH 7 | 26425492 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Davao City | 304367 | Dr. Santiago Dakudao Sr. National High School | DAVAO CITY | 2 | 1 | 12 | 4STY12CL | BATCH 7 | 34181773 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129695 | Elpidio Quirino ES | DAVAO CITY | 1 | 1 | 12 | 4STY12CL | BATCH 7 | 34281773 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129566 | General Roxas CES | DAVAO CITY | 3 | 1 | 12 | 3STY12CL | BATCH 7 | 30859300 |  |  | Completed | 1 |  |  |  | 17LH0160 | 2017-10-26 |  | 2017-11-14 | 2018-01-03 | 2018-01-15
NC 2017 | TVL | Region XI | Davao City | 304375 | MAA NATIONAL HIGH SCHOOL | DAVAO CITY | 1 | 1 | 4 | 4STY LABORATORY WORKSHOP BLDG. | BATCH 7 | 18892336 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129649 | Matina Pangi ES | DAVAO CITY | 1 | 1 | 12 | 4STY12CL | BATCH 7 | 34281773 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129516 | Pilar P. Rodriguez ES | DAVAO CITY | 2 | 1 | 9 | 3STY9CL | BATCH 7 | 26425492 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129723 | San Lorenzo ES | DAVAO CITY | 1 | 1 | 9 | 3STY9CL | BATCH 7 | 26525492 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Davao City | 304396 | Talomo National High School | DAVAO CITY | 1 | 1 | 20 | 4STY20CL | BATCH 7 | 44821083 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304396 | Talomo National High School | DAVAO CITY | 1 |  | 4 | 4STY LABORATORY WORKSHOP BLDG. | BATCH 7 | 18832336 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Davao del Norte | 304234 | Capungangan HS-Annex | KAPALONG | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 5829837 |  |  | Completed | 1 |  |  | P00177181MN-CW1 | 17LC0305 | 2017-07-12 | 2017-07-19 | 2017-12-21 | 2017-12-22 | 2017-12-28 | Micah Construction & Supply
NC 2017 | TVL | Region XI | Davao del Norte | 304224 | Datu Balong NHS | KAPALONG | 1 | 1 | 1 | REGULAR WORKSHOP BLDG. | BATCH 7 | 2914861 |  |  | Completed | 1 |  |  | P00177178MN-CW1 | 17LC0238 | 2017-07-12 | 2017-07-19 | 2017-12-05 | 2017-12-22 | 2017-12-18 | LLM Unified Builders and Trading Corp
NC 2017 | TVL | Region XI | Davao del Norte | 304228 | Doña Carmen Soriano National High School | KAPALONG | 1 | 1 | 2 | REGULAR WORKSHOP BLDG. | BATCH 7 | 5728415 |  |  | Completed | 1 |  |  | P00177179MN-CW1 | 17LC0246 | 2017-07-12 | 2017-07-19 | 2017-12-21 | 2017-12-22 | 2017-12-28 | Micah Construction & Supply
NC 2017 | TVL | Region XI | Davao del Norte | 304228 | Doña Carmen Soriano National High School | KAPALONG | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3326043.59 |  |  | Completed | 1 |  |  | P00177180MN-CW1 | 17LC0247 | 2017-07-12 | 2017-07-19 | 2017-12-21 | 2017-12-22 | 2017-12-28 | Micah Construction & Supply
NC 2017 | K10 | Region XI | Davao del Norte | 128653 | Gupitan Elementary School | KAPALONG | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 4945833 |  |  | Completed | 1 |  |  | P00177175MN-CW1 | 17LC0271 | 2017-07-12 | 2017-07-19 | 2017-12-05 | 2017-12-22 | 2017-12-18 | LLM Unified Builders and Trading Corp
NC 2017 | K10 | Region XI | Davao del Norte | 128655 | Langan ES | KAPALONG | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2928631 |  |  | Completed | 1 |  |  | P00177176MN-CW1 | 17LC0284 | 2017-07-12 | 2017-07-19 | 2017-12-05 | 2017-12-12 | 2017-12-18 | Five Massive Infra & Supply Corp.
NC 2017 | TVL | Region XI | Davao del Norte | 304241 | Luna National High School | KAPALONG | 1 | 1 | 1 | REGULAR WORKSHOP BLDG. | BATCH 7 | 2950942 |  |  | Completed | 1 |  |  | P00177182MN-CW1 | 17LC0249 | 2017-07-12 | 2017-07-19 | 2017-11-23 | 2017-12-08 | 2017-12-18 | LLM Unified Builders and Trading Corp
NC 2017 | K10 | Region XI | Davao del Norte | 204528 | Pipisan Elementary School | KAPALONG | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 4933347 |  |  | Completed | 1 |  |  | P00177177MN-CW1 | 17LC0308 | 2017-07-12 | 2017-07-19 | 2017-12-05 | 2017-12-12 | 2017-12-18 | LLM Unified Builders and Trading Corp
NC 2017 | TVL | Region XI | Davao del Norte | 304243 | Semong National High School | KAPALONG | 1 | 1 | 1 | REGULAR WORKSHOP BLDG. | BATCH 7 | 2889345 |  |  | Completed | 1 |  |  | P00177183MN-CW1 | 17LC0248 | 2017-07-12 | 2017-07-19 | 2017-11-23 | 2017-12-08 | 2017-12-18 | LLM Unified Builders and Trading Corp
NC 2017 | TVL | Region XI | Davao del Norte | 304239 | Limbaan NHS | NEW CORELLA | 1 | 1 | 1 | REGULAR WORKSHOP BLDG. | BATCH 7 | 3019004.16 |  |  | Completed | 1 |  |  | P00177184MN-CW1 | 17LC0251 | 2017-07-12 | 2017-07-19 | 2017-11-23 | 2017-12-08 | 2017-12-18 | Exact Construction
NC 2017 | TVL | Region XI | Davao del Norte | 304248 | New Corella National High School | NEW CORELLA | 1 | 1 | 4 | REGULAR WORKSHOP BLDG. | BATCH 7 | 12221551 |  |  | Completed | 1 |  |  | P00177185MN-CW1 | 17LC0252 | 2017-07-12 | 2017-07-19 | 2017-12-21 | 2017-12-22 | 2017-12-28 | R.R Seismundo Construction & Supply
NC 2017 | TVL | Region XI | Davao del Norte | 304248 | New Corella National High School | NEW CORELLA | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3482587.94 |  |  | Completed | 1 |  |  | P00177186MN-CW1 | 17LC0253 | 2017-07-12 | 2017-07-19 | 2017-11-23 | 2017-12-08 | 2017-12-18 | Exact Construction
NC 2017 | TVL | Region XI | Davao del Norte | 304251 | Sawata NHS | SAN ISIDRO | 1 | 1 | 4 | REGULAR WORKSHOP BLDG. | BATCH 7 | 10858579.78 |  |  | Completed | 1 |  |  | P00177187MN-CW1 | 17LC0254 | 2017-07-12 | 2017-07-19 | 2017-11-23 | 2017-12-08 | 2017-12-18 | LLM Unified Builders and Trading Corp
NC 2017 | K10 | Region XI | Davao del Norte | 204510 | Banaog Elementary School | TALAINGOD | 1 | 1 | 5 | 1STY5CL | BATCH 7 | 6204400 |  |  | Completed | 1 |  |  | P00177191MN-CW1 | 17LC0321 | 2017-07-12 | 2017-07-19 | 2017-12-21 | 2017-12-22 | 2017-12-28 | CJEP Builders & Engineering Services
NC 2017 | K10 | Region XI | Davao del Norte | 204510 | Banaog Elementary School | TALAINGOD | 1 |  | 5 | 1STY5CL | BATCH 7 | 6204400 |  |  | Completed | 1 |  |  | P00177192MN-CW1 | 17LC0564 | 2017-12-08 | 2017-12-15 | 2017-12-28 | 2017-12-29 | 2018-01-08 | LLM Unified Builders and Trading Corp
NC 2017 | K10 | Region XI | Davao del Norte | 204508 | BAROBO ELEMENTARY SCOOL | TALAINGOD | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 4996170 |  |  | Completed | 1 |  |  | P00177190MN-CW1 | 17LC0282 | 2017-07-12 | 2017-07-19 | 2017-12-05 | 2017-12-22 | 2017-12-18 | Five Massive Infra & Supply Corp.
NC 2017 | K10 | Region XI | Davao del Norte | 204512 | Basak Elementary School | TALAINGOD | 1 | 1 | 5 | 1STY5CL | BATCH 7 | 6291409 |  |  | Completed | 1 |  |  | P00177193MN-CW1 | 17LC0267 | 2017-07-12 | 2017-07-19 | 2017-12-21 | 2017-12-22 | 2017-12-28 | LLM Unified Builders and Trading Corp
NC 2017 | K10 | Region XI | Davao del Norte | 204517 | Central Baugan Primary School | TALAINGOD | 1 | 1 | 5 | 1STY5CL | BATCH 7 | 6273479 |  |  | Completed | 1 |  |  | P00177194MN-CW1 | 17LC0323 | 2017-07-12 | 2017-07-19 | 2017-12-21 | 2017-12-22 | 2017-12-28 | Mag Corporation
NC 2017 | K10 | Region XI | Davao del Norte | 315905 | Dagohoy National High School | TALAINGOD | 1 | 1 | 5 | 1STY5CL | BATCH 7 | 6284477 |  |  | Completed | 1 |  |  | P00177201MN-CW1 | 17LC0300 | 2017-07-12 | 2017-07-19 | 2017-12-21 | 2017-12-22 | 2017-12-28 | Micah Construction & Supply
NC 2017 | TVL | Region XI | Davao del Norte | 304258 | Datu Jose A. Libayao Memorial NHS | TALAINGOD | 1 | 1 | 3 | REGULAR WORKSHOP BLDG. | BATCH 7 | 8361456 |  |  | Completed | 1 |  |  | P00177200MN-CW1 | 17LC0250 | 2017-07-12 | 2017-07-19 | 2017-12-21 | 2017-12-08 | 2017-12-18 | Mag Corporation
NC 2017 | K10 | Region XI | Davao del Norte | 204518 | Kuyas Elementary School | TALAINGOD | 1 | 1 | 5 | 1STY5CL | BATCH 7 | 6273042 |  |  | Completed | 1 |  |  | P00177195MN-CW1 | 17LC0292 | 2017-07-12 | 2017-07-19 | 2017-12-21 | 2017-12-22 | 2017-12-28 | Five Massive Infra & Supply Corp.
NC 2017 | K10 | Region XI | Davao del Norte | 204519 | Milyong Elementary School | TALAINGOD | 1 | 1 | 5 | 1STY5CL | BATCH 7 | 6274600 |  |  | Completed | 1 |  |  | P00177196MN-CW1 | 17LC0325 | 2017-07-12 | 2017-07-19 | 2017-12-21 | 2017-12-22 | 2017-12-28 | R.R Seismundo Construction & Supply
NC 2017 | K10 | Region XI | Davao del Norte | 204534 | Napisulan Elementary School | TALAINGOD | 1 | 1 | 5 | 1STY5CL | BATCH 7 | 6284477 |  |  | Completed | 1 |  |  | P00177197MN-CW1 | 17LC0283 | 2017-07-12 | 2017-07-19 | 2017-12-21 | 2017-12-22 | 2017-12-28 | Five Massive Infra & Supply Corp.
NC 2017 | K10 | Region XI | Davao del Norte | 204536 | Napunong Elementary School | TALAINGOD | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 4918438 |  |  | Completed | 1 |  |  | P00177198MN-CW1 | 17LC0327 | 2017-07-12 | 2017-07-19 | 2017-12-21 | 2017-12-22 | 2017-12-28 | Mag Corporation
NC 2017 | K10 | Region XI | Davao del Norte | 500448 | Nasilaban Integrated School | TALAINGOD | 1 | 1 | 5 | 1STY5CL | BATCH 7 | 6283900 |  |  | Completed | 1 |  |  | P00177202MN-CW1 | 17LC0261 | 2017-07-12 | 2017-07-19 | 2017-12-21 | 2017-12-22 | 2017-12-28 | LLM Unified Builders & Trading Corp
NC 2017 | K10 | Region XI | Davao del Norte | 128805 | Paiton ES | TALAINGOD | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2820079 |  |  | Completed | 1 |  |  | P00177188MN-CW1 | 17LC0263 | 2017-07-12 | 2017-07-19 | 2017-12-21 | 2017-12-22 | 2017-12-28 | LLM Unified Builders and Trading Corp
NC 2017 | SHS | Region XI | Davao del Norte | 304257 | Sto. Nino NHS | TALAINGOD | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 4916208 |  |  | Completed | 1 |  |  | P00177199MN-CW1 | 17LC0302 | 2017-07-12 | 2017-07-19 | 2017-12-21 | 2017-12-22 | 2017-12-28 | CJEP Builders & Engineering Services
NC 2017 | K10 | Region XI | Davao del Norte | 128808 | Tibi-Tibi ES | TALAINGOD | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 4945127 |  |  | Completed | 1 |  |  | P00171946MN-CW1 | 17LC0360 | 2017-11-03 | 2017-11-10 | 2017-12-08 | 2017-12-08 | 2017-12-18 | RC BAR Builders
NC 2017 | K10 | Region XI | Davao del Sur | 128812 | Bansalan CES | BANSALAN | 1 | 1 | 9 | 3STY9CL | BATCH 7 | 26673040 |  |  | Completed | 1 |  |  |  |  | 2017-10-12 |  | 2017-10-25 |  | 2017-11-27 | LLM Unified Builders & Trading Corp.
NC 2017 | K10 | Region XI | Davao del Sur | 128826 | Bitaug ES | BANSALAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2659896 |  |  | Completed | 1 |  |  |  |  | 2017-10-12 |  | 2017-10-25 |  | 2017-11-27 | JLACE Builders Corporation
NC 2017 | K10 | Region XI | Davao del Sur |  | Mabuhay HS | BANSALAN | 1 | 1 | 6 | 2STY6CL | BATCH 7 | 12447055 |  |  | Completed | 1 |  |  |  |  | 2017-10-12 |  | 2017-10-25 |  | 2017-11-27 | LTB Builders & Construction
NC 2017 | SHS | Region XI | Davao del Sur | 304286 | Marber NHS | BANSALAN | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3802200 |  |  | Completed | 1 |  |  |  |  | 2017-10-12 |  | 2017-10-25 |  | 2017-11-27 | St. Mathew G-C & Development Corp.
NC 2017 | K10 | Region XI | Davao del Sur |  | San Isidro HS | MAGSAYSAY | 1 | 1 | 6 | 2STY6CL | BATCH 7 | 12489885 |  |  | Completed | 1 |  |  |  |  | 2017-10-12 |  | 2017-10-25 |  | 2017-11-27 | Leamor Construction & supply
NC 2017 | K10 | Region XI | Davao del Sur | 129027 | Savoy ES | MATANAO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2866941 |  |  | Completed | 1 |  |  |  |  | 2017-10-12 |  | 2017-10-25 |  | 2017-11-27 | LTB Builders & Construction
NC 2017 | K10 | Region XI | Davao del Sur | 129027 | Savoy ES | MATANAO | 1 |  | 2 | 1STY2CL | BATCH 7 | 2686216 |  |  | Completed | 1 |  |  |  |  | 2017-10-12 |  | 2017-10-25 |  | 2017-11-27 | LTB Builders & Construction
NC 2017 | SHS | Region XI | Davao del Sur | 304278 | Inawayan NHS | SANTA CRUZ | 1 | 1 | 6 | 3STY6CL | BATCH 7 | 15156515.1 |  |  | Completed | 1 |  |  |  |  | 2017-10-12 |  | 2017-10-25 |  | 2017-11-27 | LTB Builders & Construction
NC 2017 | K10 | Region XI | Davao del Sur | 129099 | SANTA CRUZ CES | SANTA CRUZ | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3802200 |  |  | Completed | 1 |  |  |  |  | 2017-10-12 |  | 2017-10-25 |  | 2017-11-27 | L.A. Arizola Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 129099 | SANTA CRUZ CES | SANTA CRUZ | 1 |  | 4 | 2STY4CL | BATCH 7 | 9669900 |  |  | Completed | 1 |  |  |  |  | 2017-10-12 |  | 2017-10-25 |  | 2017-11-27 | Mark Anthony Construction & Supply
NC 2017 | SHS | Region XI | Davao del Sur | 304294 | STA. CRUZ NATIONAL HIGH SCHOOL | SANTA CRUZ | 1 | 1 | 8 | 2UNITS 2STY4CL | BATCH 7 | 18850080 |  |  | Completed | 1 |  |  |  |  | 2017-10-12 |  | 2017-10-25 |  | 2017-11-27 | Mark Anthony Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 129130 | Balasinon ES | SULOP | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2816907.92 |  |  | Completed | 1 |  |  |  |  | 2017-10-12 |  | 2017-10-25 |  | 2017-11-27 | Leamor Construction & supply
NC 2017 | K10 | Region XI | Davao del Sur | 129151 | Waterfall ES | SULOP | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2650106 |  |  | Completed | 1 |  |  |  |  | 2017-10-12 |  | 2017-10-25 |  | 2017-11-27 | NLC Construction & Supply
NC 2017 | K10 | Region XI | Davao Occidental | 128840 | Don Marcelino Maruya ES | DON MARCELINO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2728992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128850 | Jose Villanueva ES | DON MARCELINO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2783636 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128845 | Lawa CES | DON MARCELINO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2728992 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Davao Occidental | 304291 | Lawa NHS | DON MARCELINO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2728992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 316012 | Luisa Joyce Mallari National High School | DON MARCELINO | 0 | 1 | 8 | 2STY8CL | BATCH 7 | 17420691 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128848 | Maltusan ES | DON MARCELINO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2783636 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128851 | Palamid ES | DON MARCELINO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2783636 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128854 | Thomas Jhonson ES | DON MARCELINO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2783636 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128880 | David Lachica Sr. Elementary school | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2869618 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 316008 | Emeliano S. Fontanares Sr. NHS | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | 6 | 2STY6CL | BATCH 7 | 11905796 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Davao Occidental | 304281 | Jose Abad Santos NHS | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | 6 | 2STY6CL | BATCH 7 | 11724416.5 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Davao Occidental | 304281 | Jose Abad Santos NHS | JOSE ABAD SANTOS (TRINIDAD) | 0 |  | 6 | 2STY6CL | BATCH 7 | 11724416.5 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128884 | Malalan ES | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2869618 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128876 | Monroe M. Joyce ES | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2869618 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Davao Occidental | 316007 | Benjamin Velasco Bautista Sr. National High School | MALITA | 0 | 1 | 6 | 2STY6CL | BATCH 7 | 11600380.5 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Davao Occidental | 316007 | Benjamin Velasco Bautista Sr. National High School | MALITA | 0 |  | 6 | 2STY6CL | BATCH 7 | 11600380.5 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 316018 | Pedro Mariscal National High School | SANTA MARIA | 0 | 1 | 6 | 2STY6CL | BATCH 7 | 11733539 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Oriental | 129232 | Binaton ES | CARAGA | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3925459.07 |  |  | Completed | 1 | [8 empty] | 2017-12-06 | RC TROCIO BUILDERS
NC 2017 | K10 | Region XI | Davao Oriental | 129215 | Lahi PS | CARAGA | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3878670.2 |  |  | Completed | 1 | [8 empty] | 2017-12-06 | RANGAY CONSTRUCTION
NC 2017 | K10 | Region XI | Davao Oriental | 129222 | Panlaisan ES | CARAGA | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4510320.03 |  |  | Completed | 1 | [8 empty] | 2017-12-06 | RANGAY CONSTRUCTION
NC 2017 | K10 | Region XI | Davao Oriental | 129242 | Pantuyan ES | CARAGA | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 5002734.55 |  |  | Completed | 1 | [8 empty] | 2017-12-06 | RANGAY CONSTRUCTION
NC 2017 | K10 | Region XI | Davao Oriental | 129226 | San Pedro ES | CARAGA | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3837729.93 |  |  | Completed | 1 | [8 empty] | 2017-12-06 | RANGAY CONSTRUCTION
NC 2017 | K10 | Region XI | Davao Oriental | 129250 | Baybay PS | CATEEL | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3837729.93 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Digos City |  | Aplaya NHS | CITY OF DIGOS (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 7 | 12446880 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Digos City |  | Dawis NHS | CITY OF DIGOS (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 7 | 12388113.02 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Digos City | 304400 | Digos City NHS (Davao Del Sur NHS) | CITY OF DIGOS (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 7 | 39700158.96 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Digos City | 304401 | Kapatagan NHS | CITY OF DIGOS (Capital) | 1 | 1 | 4 | 2STY4CL (2 LABORATORIES) | BATCH 7 | 10108868.99 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Digos City | 304401 | Kapatagan NHS | CITY OF DIGOS (Capital) | 1 |  | 4 | 2STY4CL (2 LABORATORIES) | BATCH 7 | 10108868.99 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Digos City | 304401 | Kapatagan NHS | CITY OF DIGOS (Capital) | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2899995.26 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Digos City | 316302 | Matti NHS | CITY OF DIGOS (Capital) | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2815551.38 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Digos City | 316302 | Matti NHS | CITY OF DIGOS (Capital) | 1 |  | 4 | 2STY4CL (2 LABORATORIES) | BATCH 7 | 9795762.43 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Digos City | 316302 | Matti NHS | CITY OF DIGOS (Capital) | 1 |  | 4 | 2STY4CL (2 LABORATORIES) | BATCH 7 | 9795762.43 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Digos City | 129756 | Remedios N. Saplala ES (Matti ES) | CITY OF DIGOS (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 7 | 9542414.49 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Digos City | 304402 | Ruparan NHS | CITY OF DIGOS (Capital) | 1 | 1 | 8 | 2STY8CL (4 LABORATORIES) | BATCH 7 | 18574790.26 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Digos City | 341513 | SHS in Digos City | CITY OF DIGOS (Capital) | 1 | 1 | 10 | 2STY10CL | BATCH 7 | 21581033.77 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Digos City | 341513 | SHS in Digos City | CITY OF DIGOS (Capital) | 1 |  | 10 | 2STY10CL | BATCH 7 | 21581033.77 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Digos City | 341513 | SHS in Digos City | CITY OF DIGOS (Capital) | 1 | 1 | 4 | 2STY4CL (2 LABORATORIES) | BATCH 7 | 9837095.76 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Island Garden City of Samal | 128682 | Adecor ES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2794667 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Island Garden City of Samal | 304216 | Anonang National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2891419 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Island Garden City of Samal | 128726 | Aumbay ES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2800824 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Island Garden City of Samal | 128601 | Camudmud Elementary School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2887307 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Island Garden City of Samal | 128686 | Cogon ES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2889914 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Island Garden City of Samal | 128689 | Guadalupe ES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2867017 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Island Garden City of Samal | 128733 | Limao ES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2854816 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Island Garden City of Samal | 128695 | San Isidro ES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2904358 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Island Garden City of Samal | 128609 | San Isidro Integrated School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2800222 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Island Garden City of Samal | 128737 | San Jose Elementary School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2894572 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Island Garden City of Samal | 128739 | Tagbitan-ag ES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3968426 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Island Garden City of Samal | 128740 | Tagdaliao Elementary School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2884154 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Island Garden City of Samal | 323410 | Tagpopongan National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 5 | 1STY5CL | BATCH 7 | 6369610 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Mati City | 304301 | Manuel B. Guiñez Sr. NHS | BANAYBANAY | 2 | 1 | 3 | 3STY WORKSHOP BLDG. (7X18) | BATCH 7 | 14825400.49 |  |  | Completed | 1 |  |  |  | 17LG0107 | 2017-11-07 | 2017-11-16 | 2017-12-05 | 2017-12-14 | 2017-12-29 | Three W Builders, Inc.
NC 2017 | TVL | Region XI | Mati City | 316104 | Don Salvador Lopez NHS | CITY OF MATI (Capital) | 2 | 1 | 3 | 3STY WORKSHOP BLDG. (7X18) | BATCH 7 | 14913802.41 |  |  | Completed | 1 |  |  |  | 17LG0109 | 2017-11-07 | 2017-11-16 | 2017-12-05 | 2017-12-14 | 2017-12-29 | Rhodwill Parts & Hardware & Const. Service
NC 2017 | K10 | Region XI | Mati City | 257001 | Jose C. Martinez Jr. Elementary School | CITY OF MATI (Capital) | 2 | 1 | 8 | 2STY8CL | BATCH 7 | 17610793.29 |  |  | Completed | 1 |  |  |  | 17LG0108 | 2017-11-07 | 2017-11-16 | 2017-12-05 | 2017-12-14 | 2017-12-29 | FFJJ Construction
NC 2017 | TVL | Region XI | Mati City | 325102 | Lawigan National HS | CITY OF MATI (Capital) | 2 | 1 | 3 | 3STY WORKSHOP BLDG. (7X18) | BATCH 7 | 14956622.09 |  |  | Completed | 1 |  |  |  | 17LG0110 | 2017-11-07 | 2017-11-16 | 2017-12-05 | 2017-12-14 | 2017-12-29 | FFJJ Construction
NC 2017 | TVL | Region XI | Mati City | 325106 | Mayo NHS | City of Mati (Capital) | 2 | 1 | 3 | 3STY WORKSHOP BLDG. (7X18) | BATCH 7 | 14913802.41 |  |  | Completed | 1 |  |  |  | 17LG0111 | 2017-11-07 | 2017-11-16 | 2017-12-05 | 2017-12-14 | 2017-12-29 | RC Trocio Builders
NC 2017 | SHS | Region XI | Mati City | 304322 | Luzon NHS | GOVERNOR GENEROSO | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 9601333.52 |  |  | Completed | 1 |  |  |  | 17LG0112 | 2017-11-07 | 2017-11-16 | 2017-12-05 | 2017-12-14 | 2017-12-29 | RC Trocio Builders
NC 2017 | TVL | Region XI | Mati City | 304322 | Luzon NHS | GOVERNOR GENEROSO | 2 |  | 6 | 3STY WORKSHOP BLDG. (7X18) | BATCH 7 | 29827604.81 |  |  | Completed | 1 |  |  |  | 17LG0113 | 2017-11-07 | 2017-11-16 | 2017-12-05 | 2017-12-14 | 2017-12-29 | FFJJ Construction
NC 2017 | SHS | Region XI | Mati City | 304329 | Nangan NHS | GOVERNOR GENEROSO | 2 | 1 | 6 | 2STY6CL | BATCH 7 | 12683827.01 |  |  | Completed | 1 |  |  |  | 17LG0114 | 2017-11-07 | 2017-11-16 | 2017-12-05 | 2017-12-14 | 2017-12-29 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 304336 | Sigaboy Agri. Voc. HS | GOVERNOR GENEROSO | 2 | 1 | 9 | 3STY WORKSHOP BLDG. (7X18) | BATCH 7 | 44675105.76 |  |  | Completed | 1 |  |  |  | 17LG0115 | 2017-11-07 | 2017-11-16 | 2017-12-05 | 2017-12-14 | 2017-12-29 | Three W Builders, Inc. / ACQ Solomonic Builders Devt. Corp.
NC 2017 | TVL | Region XI | Mati City | 304319 | Lupon Voc. HS | LUPON | 2 | 1 | 9 | 3STY WORKSHOP BLDG. (7X18) | BATCH 7 | 44476201.44 |  |  | Completed | 1 |  |  |  | 17LG0116 | 2017-11-07 | 2017-11-16 | 2017-12-05 | 2017-12-14 | 2017-12-29 | Melrobe Builders & Cosnt. Supplies
NC 2017 | TVL | Region XI | Mati City | 304302 | Bitaogan NHS | SAN ISIDRO | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 7 | 9594288.99 |  |  | Completed | 1 |  |  |  | 17LG0117 | 2017-11-07 | 2017-11-16 | 2017-12-05 | 2017-12-14 | 2017-12-29 | FFJJ Construction
NC 2017 | TVL | Region XI | Mati City | 304302 | Bitaogan NHS | SAN ISIDRO | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 7 | 9534816.19 |  |  | Completed | 1 |  |  |  | 17LG0118 | 2017-11-07 | 2017-11-16 | 2017-12-05 | 2017-12-14 | 2017-12-29 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 304317 | Manuel S. Nasser, Sr. NHS | SAN ISIDRO | 2 | 1 | 3 | 3STY WORKSHOP BLDG (7X18) | BATCH 7 | 14913802.41 |  |  | Completed | 1 |  |  |  | 17LG0119 | 2017-11-07 | 2017-11-16 | 2017-12-05 | 2017-12-14 | 2017-12-29 | RC Trocio Builders
NC 2017 | TVL | Region XI | Mati City | 304317 | Manuel S. Nasser, Sr. NHS | SAN ISIDRO | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 7 | 9622271.93 |  |  | Completed | 1 |  |  |  | 17LG0120 | 2017-11-07 | 2017-11-16 | 2017-12-05 | 2017-12-14 | 2017-12-29 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 304332 | San Isidro NHS | SAN ISIDRO | 2 | 1 | 8 | 2STY WORKSHOP BLDG. (7X18) | BATCH 7 | 38361133.1 |  |  | Completed | 1 |  |  |  | 17LG0121 | 2017-11-07 | 2017-11-16 | 2017-12-05 | 2017-12-14 | 2017-12-29 | Rely Construction & Supply
NC 2017 | TVL | Region XI | Mati City | 304332 | San Isidro NHS | SAN ISIDRO | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 7 | 9587382.59 |  |  | Completed | 1 |  |  |  | 17LG0122 | 2017-11-07 | 2017-11-16 | 2017-12-05 | 2017-12-14 | 2017-12-29 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 304332 | San Isidro NHS | SAN ISIDRO | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 7 | 9528251.09 |  |  | Completed | 1 |  |  |  | 17LG0123 | 2017-11-07 | 2017-11-16 | 2017-12-05 | 2017-12-14 | 2017-12-29 | Legacy Construction Corp.
NC 2017 | SHS | Region XI | Tagum City | 322401 | Canocotan National High School | CITY OF TAGUM (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 4005804.03 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Tagum City | 304231 | Jose Tuason Jr. Memorial National High School | CITY OF TAGUM (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 3099571.59 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Tagum City | 304238 | La Filipina NHS | CITY OF TAGUM (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 3483243.12 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Tagum City | 304226 | Laureta National High School | CITY OF TAGUM (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 3193862.84 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Tagum City | 500425 | Liboganon Integrated School | CITY OF TAGUM (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 3501873.13 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Tagum City | 500426 | Pandapan Integrated School | CITY OF TAGUM (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 3553000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Tagum City | 304232 | Pipisan Maug National High School | CITY OF TAGUM (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 6387725.68 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Tagum City | 304225 | Tagum City National Comprehensive High School | CITY OF TAGUM (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 3491024.47 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Tagum City | 304261 | TAGUM NATIONAL TRADE SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 6341465.1 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 315819 | Bango NHS | COMPOSTELA | 1 | 1 | 16 | 2UNITS 2STY8CL | BATCH 10 | 39282000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128262 | Bongkilaton ES | COMPOSTELA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3133000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128263 | Compostela CES | COMPOSTELA | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 13937000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304181 | Compostela NHS | COMPOSTELA | 1 | 1 | 36 | 3UNITS 3STY12CL | BATCH 10 | 82240000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304184 | Consuelo M. Valderama NHS | COMPOSTELA | 1 | 1 | 8 | 2STY8CL | BATCH 10 | 20043000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304187 | Gabi NHS | COMPOSTELA | 1 | 1 | 12 | 3STY12CL | BATCH 10 | 27756000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304187 | Gabi NHS | COMPOSTELA | 1 |  | 4 | 2STY4CL | BATCH 10 | 10793000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 204008 | Lower Panansalan es | COMPOSTELA | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 4893000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304196 | Maparat NHS | COMPOSTELA | 1 | 1 | 16 | 2UNITS 2STY8CL | BATCH 10 | 37383000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128273 | Panansalan ES | COMPOSTELA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3083000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304183 | San Miguel NHS | COMPOSTELA | 1 | 1 | 12 | 2UNITS 2STY6CL | BATCH 10 | 27764000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304210 | Siocon NHS | COMPOSTELA | 1 | 1 | 8 | 2STY8CL | BATCH 10 | 19021000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128277 | T.H. Valderrama ES | COMPOSTELA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304185 | Don Vicente Romualdez NHS | LAAK | 2 | 1 | 16 | 2UNITS 2STY8CL | BATCH 10 | 37151000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304188 | Kapatagan NHS | LAAK | 2 | 1 | 12 | 3STY12CL | BATCH 10 | 28379000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304190 | Kidawa NHS | LAAK | 2 | 1 | 8 | 2STY8CL | BATCH 10 | 19363000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304189 | Laak NHS | LAAK | 2 | 1 | 12 | 3STY12CL | BATCH 10 | 29263000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 315804 | Melale NHS | LAAK | 2 | 1 | 12 | 3STY12CL | BATCH 10 | 28436000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 315804 | Melale NHS | LAAK | 2 |  | 8 | 2STY8CL | BATCH 10 | 19138000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 315812 | San Antonio NHS | LAAK | 2 | 1 | 8 | 2STY8CL | BATCH 10 | 18860000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128279 | Amorcruz ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128280 | Andap Elementary School | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128281 | Anitap ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128282 | Bagong Silang ES | LAAK (SAN VICENTE) | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4788000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128284 | Barubo ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3133000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128285 | Bayanihan ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128286 | Belmonte ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3108000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128287 | Binasbas ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3108000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128288 | Buhi ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128289 | Bullokan ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128291 | Ceboleda ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3108000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128292 | Concepcion ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 204016 | Dalimdim ES | LAAK (SAN VICENTE) | 2 | 1 | 4 | 1STY4CL | BATCH 10 | 5748000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 304185 | Don Vicente Romualdez NHS | LAAK (SAN VICENTE) | 2 |  | 1 | UNIQUE TECHVOC | BATCH 10 | 4181000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128299 | Imelda ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3083000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128300 | Inakayan ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3083000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128301 | Kaligutan ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128302 | Kapatagan ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 304188 | Kapatagan National High School | LAAK (SAN VICENTE) | 2 |  | 1 | UNIQUE TECHVOC | BATCH 10 | 4181000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128304 | Kidawa ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3083000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128305 | Kilagdeng ES | LAAK (SAN VICENTE) | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4773000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128306 | Kiokmay ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128307 | L.S. Sarmiento ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3332000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128308 | Laak CES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 304189 | LAAK NATIONAL HIGH SCHOOL | LAAK (SAN VICENTE) | 2 |  | 2 | UNIQUE TECHVOC | BATCH 10 | 8196000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128309 | Langtud ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3108000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128310 | Libuton ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128311 | Longanapan ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3108000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128312 | Lower Ampawid ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3133000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128313 | Mabuhay ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128314 | Makopa ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128317 | Melale ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3108000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 315804 | Melale NHS | LAAK (SAN VICENTE) | 2 |  | 1 | UNIQUE TECHVOC | BATCH 10 | 4256000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128318 | Naga ES | LAAK (SAN VICENTE) | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4794000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128319 | New Bethlehem ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3108000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128321 | Sabud ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3133000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128322 | San Antonio ES | LAAK (SAN VICENTE) | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4741000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128323 | Sisimon ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128324 | Sta. Emilia ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128325 | Tigasa ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3133000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128326 | Tuk-an Elementary School | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 315822 | Golden Valley NHS | MABINI | 2 | 1 | 10 | 2STY10CL | BATCH 10 | 21189000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 204013 | Kapoc ES | MABINI | 2 | 1 | 6 | 2STY6CL | BATCH 10 | 13947000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 315805 | Pindasan NHS | MABINI | 2 | 1 | 16 | 2UNITS 2STY8CL | BATCH 10 | 37096000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128328 | Anitapan ES | MABINI (DOÑA ALICIA) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3183000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 304174 | Anitapan NHS | MABINI (DOÑA ALICIA) | 2 | 1 | 1 | UNIQUE TECHVOC | BATCH 10 | 4331000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128330 | Cadunan ES | MABINI (DOÑA ALICIA) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128332 | Del Pilar ES | MABINI (DOÑA ALICIA) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128333 | Don William Gemperle ES | MABINI (DOÑA ALICIA) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3233000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128333 | Don William Gemperle ES | MABINI (DOÑA ALICIA) | 2 |  | 4 | 1STY4CL | BATCH 10 | 5498000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128334 | Libudon ES | MABINI (DOÑA ALICIA) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3083000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128335 | Mabini CES | MABINI (DOÑA ALICIA) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128336 | Mambatang ES | MABINI (DOÑA ALICIA) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3133000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128337 | Manasa Elementary School | MABINI (DOÑA ALICIA) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3283000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128340 | Pindasan ES | MABINI (DOÑA ALICIA) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 315805 | Pindasan NHS | MABINI (DOÑA ALICIA) | 2 |  | 1 | UNIQUE TECHVOC | BATCH 10 | 4181000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128341 | San Antonio ES | MABINI (DOÑA ALICIA) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128343 | Tagbalabao ES | MABINI (DOÑA ALICIA) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3334000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128344 | Anibongan ES | MACO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304173 | Anibongan NHS | MACO | 2 | 1 | 8 | 2UNITS 2STY4CL | BATCH 10 | 21923000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128363 | Anislagan ES | MACO | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4712000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304193 | Atty. Orlando S. R. NHS | MACO | 2 | 1 | 20 | 4STY20CL | BATCH 10 | 43402000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304193 | Atty. Orlando S. R. NHS | MACO | 2 |  | 16 | 4STY16CL | BATCH 10 | 35322000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128364 | Calabcab PS | MACO | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4778000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128346 | Concepcion ES | MACO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128347 | Elizalde ES | MACO | 2 | 1 | 8 | 2STY8CL | BATCH 10 | 18862000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304186 | Elizalde NHS | MACO | 2 | 1 | 16 | 2UNITS 2STY8CL | BATCH 10 | 37862000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 304186 | Elizalde NHS | MACO | 2 |  | 1 | UNIQUE TECHVOC | BATCH 10 | 4256000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128350 | HIJO ELEMENTARY SCHOOL | MACO | 2 | 1 | 4 | 1STY4CL | BATCH 10 | 5548000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 204003 | Langgam ES | MACO | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4878000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128352 | Lapulapu ES | MACO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3296000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 204017 | Libaoc ES | MACO | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 11643000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 204006 | Lumatab ES | MACO | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 11712000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128353 | Maco CES | MACO | 2 | 1 | 12 | 3STY12CL | BATCH 10 | 28182000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128369 | Maco Heights CES | MACO | 2 | 1 | 4 | 1STY4CL | BATCH 10 | 5548000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128369 | Maco Heights CES | MACO | 2 |  | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128369 | Maco Heights CES | MACO | 2 |  | 6 | 2STY6CL | BATCH 10 | 13947000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128370 | Manipongol ES | MACO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3183000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128355 | New Asturias ES | MACO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3083000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 315811 | New Leyte NHS | MACO | 2 | 1 | 1 | UNIQUE TECHVOC | BATCH 10 | 4256000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 315811 | New Leyte NHS | MACO | 2 |  | 6 | 2STY6CL | BATCH 10 | 14220000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128358 | Pangi ES | MACO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128359 | Panibasan ES | MACO | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 11090000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128375 | Panoraon Elementary School | MACO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3083000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128360 | Sangab ES | MACO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3183000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128377 | Teresa ES | MACO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3234000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128389 | Maragusan CES | MARAGUSAN | 1 | 1 | 16 | 2UNITS 2STY8CL | BATCH 10 | 37063000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304198 | Maragusan NHS | MARAGUSAN | 1 | 1 | 12 | 3STY12CL | BATCH 10 | 28523000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304198 | Maragusan NHS | MARAGUSAN | 1 |  | 16 | 2UNITS 2STY8CL | BATCH 10 | 39946000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 315815 | New Albay NHS | MARAGUSAN | 1 | 1 | 12 | 3STY12CL | BATCH 10 | 28528000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128397 | Pamintaran ES | MARAGUSAN | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 13947000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304213 | Tupaz NHS | MARAGUSAN | 1 | 1 | 12 | 3STY12CL | BATCH 10 | 28475000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128405 | Andili ES | MAWAB | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 10857000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304172 | Andili NHS | MAWAB | 2 | 1 | 16 | 2UNITS 2STY8CL | BATCH 10 | 37624000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 304172 | Andili NHS | MAWAB | 2 |  | 2 | UNIQUE TECHVOC | BATCH 10 | 7996000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128406 | Bawani ES | MAWAB | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128407 | Concepcion ES | MAWAB | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3083000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128409 | Katipunan ES | MAWAB | 2 | 1 | 4 | 1STY4CL | BATCH 10 | 5598000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 304191 | Lorenzo S. Sarmiento Sr. NHS | MAWAB | 2 | 1 | 1 | UNIQUE TECHVOC | BATCH 10 | 4181000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128411 | Mahayag PS | MAWAB | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4736000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128412 | Malinawon ES | MAWAB | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128413 | Mawab CES | MAWAB | 2 | 1 | 6 | 2STY6CL | BATCH 10 | 13872000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128414 | Nueva Visayas ES | MAWAB | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4736000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128415 | Nuevo Iloco ES | MAWAB | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 315802 | Nuevo Iloco NHS | MAWAB | 2 | 1 | 12 | 3STY12CL | BATCH 10 | 29263000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128416 | Salvacion ES | MAWAB | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3214000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128418 | Saosao ES | MAWAB | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4793000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128419 | Sawangan ES | MAWAB | 2 | 1 | 4 | 1STY4CL | BATCH 10 | 5548000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128421 | Tan-Awan ES | MAWAB | 2 | 1 | 4 | 1STY4CL | BATCH 10 | 5623000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 315803 | Tuboran NHS | MAWAB | 2 | 1 | 12 | 3STY12CL | BATCH 10 | 28443000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128424 | Awao ES | MONKAYO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3183000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304200 | Awao NHS | MONKAYO | 1 | 1 | 12 | 3STY12CL | BATCH 10 | 28194000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128425 | Babag ES | MONKAYO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3157000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 204010 | Depot ES | MONKAYO | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 10988000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128436 | Macopa ES | MONKAYO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128438 | Matangad ES | MONKAYO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3183000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128438 | Matangad ES | MONKAYO | 1 |  | 6 | 2STY6CL | BATCH 10 | 14098000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304199 | Monkayo NHS | MONKAYO | 1 | 1 | 32 | 2UNITS 4STY16CL | BATCH 10 | 66726000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128444 | Naboc ES | MONKAYO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128450 | Samuag ES | MONKAYO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304212 | Tubo-Tubo NHS | MONKAYO | 1 | 1 | 16 | 2UNITS 2STY8CL | BATCH 10 | 37628000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128456 | Tuburan ES | MONKAYO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 315808 | Ulip NHS | MONKAYO | 1 | 1 | 12 | 3STY12CL | BATCH 10 | 28057000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304214 | Union NHS | MONKAYO | 1 | 1 | 8 | 2STY8CL | BATCH 10 | 18598000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128464 | Canidkid ES | MONTEVISTA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128468 | Magtaya ES | MONTEVISTA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3376000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304204 | Mayaon NHS | MONTEVISTA | 1 | 1 | 8 | 2STY8CL | BATCH 10 | 18800000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304202 | Montevista NHS | MONTEVISTA | 1 | 1 | 12 | 3STY12CL | BATCH 10 | 28359000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304202 | Montevista NHS | MONTEVISTA | 1 |  | 8 | 2STY8CL | BATCH 10 | 19061000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128475 | Prosperidad ES | MONTEVISTA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128481 | Antequera ES | NABUNTURAN | 2 | 1 | 8 | 2STY8CL | BATCH 10 | 18704000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128501 | Bayabas ES | NABUNTURAN | 2 | 1 | 6 | 2STY6CL | BATCH 10 | 13980000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304178 | Bayabas NHS | NABUNTURAN | 2 | 1 | 8 | 2UNITS 2STY4CL | BATCH 10 | 22070000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128486 | Cabidianan ES | NABUNTURAN | 2 | 1 | 10 | 2STY10CL | BATCH 10 | 21545000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 315806 | Kao NHS | NABUNTURAN | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 12106000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 315806 | Kao NHS | NABUNTURAN | 2 |  | 12 | 3STY12CL | BATCH 10 | 29062000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128488 | Katipunan ES | NABUNTURAN | 2 | 1 | 8 | 2STY8CL | BATCH 10 | 18451000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128502 | Linda ES | NABUNTURAN | 2 | 1 | 10 | 2STY10CL | BATCH 10 | 21440000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128503 | Magsaysay ES | NABUNTURAN | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 10988000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128503 | Magsaysay ES | NABUNTURAN | 2 |  | 6 | 2STY6CL | BATCH 10 | 13947000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128491 | Mainit ES | NABUNTURAN | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 10888000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304194 | Mainit NHS | NABUNTURAN | 2 | 1 | 16 | 4STY16CL | BATCH 10 | 34329000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304195 | Manat NHS | NABUNTURAN | 2 | 1 | 12 | 3STY12CL | BATCH 10 | 28027000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304195 | Manat NHS | NABUNTURAN | 2 |  | 8 | 2STY8CL | BATCH 10 | 18723000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128494 | Matilo ES | NABUNTURAN | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 10993000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128504 | Mipangi ES | NABUNTURAN | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 10988000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128505 | Nabunturan CES | NABUNTURAN | 2 | 1 | 12 | 2UNITS 2STY6CL | BATCH 10 | 27550000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304205 | Nabunturan NCHS | NABUNTURAN | 2 | 1 | 24 | 2UNITS 3STY12CL | BATCH 10 | 55460000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 315818 | Nabunturan NCHS - New Sibonga HS Annex | NABUNTURAN | 2 | 1 | 12 | 2UNITS 2STY6CL | BATCH 10 | 27550000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128495 | New Dauis ES | NABUNTURAN | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 10872000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128506 | New Sibonga ES | NABUNTURAN | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 10988000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128496 | Ogao ES | NABUNTURAN | 2 | 1 | 10 | 2STY10CL | BATCH 10 | 21440000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128497 | Pangutosan ES | NABUNTURAN | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 11007000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128508 | San Isidro ES | NABUNTURAN | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 11044000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128498 | San Vicente ES | NABUNTURAN | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 10988000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 204002 | Tagaytay ES | NABUNTURAN | 2 | 1 | 6 | 2STY6CL | BATCH 10 | 13947000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128480 | Anislagan ES | NABUNTURAN (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128482 | Basak ES | NABUNTURAN (Capital) | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4309000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128484 | Bukal ES | NABUNTURAN (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128507 | C.M. Recto ES | NABUNTURAN (Capital) | 2 | 1 | 4 | 1STY4CL | BATCH 10 | 5548000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128485 | Cabacungan ES | NABUNTURAN (Capital) | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4778000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128487 | Kao ES | NABUNTURAN (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128489 | Libasan ES | NABUNTURAN (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128490 | Magading ES | NABUNTURAN (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128492 | Manat CES | NABUNTURAN (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 304195 | Manat NHS | NABUNTURAN (Capital) | 2 |  | 3 | UNIQUE TECHVOC | BATCH 10 | 12543000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 304205 | Nabunturan NCHS | NABUNTURAN (Capital) | 2 |  | 2 | UNIQUE TECHVOC | BATCH 10 | 7996000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128483 | San Juan ES | NABUNTURAN (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3083000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128509 | San Roque ES | NABUNTURAN (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 204005 | Sasa ES | NABUNTURAN (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128499 | Sta. Maria ES | NABUNTURAN (Capital) | 2 | 1 | 4 | 1STY4CL | BATCH 10 | 5548000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128500 | Tagnocon ES | NABUNTURAN (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 10 | 13625000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128500 | Tagnocon ES | NABUNTURAN (Capital) | 2 |  | 2 | 1STY2CL | BATCH 10 | 3214000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128510 | Andap Elementary School | NEW BATAAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128511 | Bantacan ES | NEW BATAAN | 1 | 1 | 5 | 1STY5CL | BATCH 10 | 6785000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128514 | Cabinuangan CES | NEW BATAAN | 1 | 1 | 10 | 2STY10CL | BATCH 10 | 21540000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128515 | Camanlangan ES | NEW BATAAN | 1 | 1 | 8 | 2STY8CL | BATCH 10 | 19014000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128529 | Simsimen ES | NEW BATAAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3397000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128532 | Araibo ES | PANTUKAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3043000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304175 | Araibo NHS | PANTUKAN | 2 | 1 | 12 | 3STY12CL | BATCH 10 | 28016000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128537 | Binogsayan ES | PANTUKAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3344000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128538 | Bongabong ES | PANTUKAN | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 10970000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128539 | Bongabong ES | PANTUKAN | 2 | 1 | 8 | 2STY8CL | BATCH 10 | 18451000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304179 | Bongabong NHS | PANTUKAN | 2 | 1 | 16 | 2UNITS 2STY8CL | BATCH 10 | 38974000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 304179 | Bongabong NHS | PANTUKAN | 2 |  | 1 | UNIQUE TECHVOC | BATCH 10 | 4181000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128535 | Bon-Temple ES | PANTUKAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3214000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128533 | Eduardo H. Maquidato, Sr. ES | PANTUKAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3083000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128544 | Kingking ES | PANTUKAN | 2 | 1 | 6 | 2STY6CL | BATCH 10 | 13947000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128545 | Lahi ES | PANTUKAN | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4878000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128546 | Las Arenas ES | PANTUKAN | 2 | 1 | 6 | 2STY6CL | BATCH 10 | 14048000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128547 | Liniputan ES | PANTUKAN | 2 | 1 | 4 | 1STY4CL | BATCH 10 | 6365000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128548 | Magnaga ES | PANTUKAN | 2 | 1 | 15 | 3STY15CL | BATCH 10 | 32679000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 315807 | Magnaga NHS | PANTUKAN | 2 | 1 | 16 | 2UNITS 2STY8CL | BATCH 10 | 37151000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 315807 | Magnaga NHS | PANTUKAN | 2 |  | 1 | UNIQUE TECHVOC | BATCH 10 | 4181000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128549 | Matiao ES | PANTUKAN | 2 | 1 | 8 | 2STY8CL | BATCH 10 | 18451000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128550 | Maubog ES | PANTUKAN | 2 | 1 | 8 | 2STY8CL | BATCH 10 | 18451000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128551 | Nagas ES | PANTUKAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3309000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128552 | Napnapan ES | PANTUKAN | 2 | 1 | 4 | 1STY4CL | BATCH 10 | 5661000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 315816 | Napnapan NHS | PANTUKAN | 2 | 1 | 16 | 2UNITS 2STY8CL | BATCH 10 | 38364000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128553 | P. Fuentes Sr. ES | PANTUKAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3133000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128555 | Pantukan ES | PANTUKAN | 2 | 1 | 6 | 2STY6CL | BATCH 10 | 14022000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 304208 | Pantukan National High School | PANTUKAN | 2 | 1 | 1 | UNIQUE TECHVOC | BATCH 10 | 4181000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304208 | Pantukan NHS | PANTUKAN | 2 |  | 16 | 2UNITS 2STY8CL | BATCH 10 | 31872000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304208 | Pantukan NHS | PANTUKAN | 2 |  | 12 | 3STY12CL | BATCH 10 | 38116000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128560 | Tagdangua ES | PANTUKAN | 2 | 1 | 6 | 2STY6CL | BATCH 10 | 13947000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128561 | Tagugpo ES | PANTUKAN | 2 | 1 | 8 | 2STY8CL | BATCH 10 | 18451000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128561 | Tagugpo ES | PANTUKAN | 2 |  | 6 | 2STY6CL | BATCH 10 | 14027000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304209 | Tagugpo NHS | PANTUKAN | 2 | 1 | 8 | 2STY8CL | BATCH 10 | 18880000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Compostela Valley | 304211 | Tambongon NHS | PANTUKAN | 2 | 1 | 12 | 3STY12CL | BATCH 10 | 27806000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Compostela Valley | 304211 | Tambongon NHS | PANTUKAN | 2 |  | 1 | UNIQUE TECHVOC | BATCH 10 | 4181000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128562 | Tapis ES | PANTUKAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3194000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128563 | Tibagon ES | PANTUKAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128564 | Tugop ES | PANTUKAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3194000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 204015 | Upper Camili ES | PANTUKAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3194000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129679 | A. Loyola ES | DAVAO CITY | 3 | 1 | 28 | 4STY12CL & 4STY16CL | BATCH 10 | 67418500 |  |  | Completed | 1 |  |  |  | 17LH0210 | 2017-11-14 |  | 2017-12-12 | 2018-02-15 | 2019-02-09
NC 2017 | TVL | Region XI | Davao City | 304341 | ALEJANDRA L. NAVARRO NHS | DAVAO CITY | 2 | 1 | 4 | 4STY WORKSHOP BLDG. (7X18) | BATCH 10 | 18912336 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304341 | ALEJANDRA L. NAVARRO NHS | DAVAO CITY | 2 |  | 8 | 4STY WORKSHOP BLDG. (7X18) | BATCH 10 | 40323597 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129477 | Armed Forces of the Philippines Logistics Command Elementary School | DAVAO CITY | 2 | 1 | 9 | 3STY9CL | BATCH 10 | 26485492 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304343 | Baguio National School of Arts and Trades | DAVAO CITY | 3 | 1 | 11 | 4STY7CL STANDARD CL REGULAR WORKSHOP, 2 REGULAR CL & 4STY4CL SCIENCE AND ICT LABORATORY | BATCH 10 | 48657000 |  |  | Completed | 1 |  |  |  | 17LH0219 | 2017-11-21 |  | 2017-12-29 | 2018-01-18 | 2018-02-05
NC 2017 | SHS | Region XI | Davao City | 304343 | Baguio National School of Arts and Trades | DAVAO CITY | 3 |  | 6 | 3STY6CL | BATCH 10 | 13785000 |  |  | Completed | 1 |  |  |  | 17LH0183 | 2017-11-06 |  | 2017-12-05 | 2018-01-18 | 2018-02-01
NC 2017 | SHS | Region XI | Davao City | 304343 | Baguio National School of Arts and Trades | DAVAO CITY | 3 |  | 9 | 3STY9CL | BATCH 10 | 24468100 |  |  | Completed | 1 |  |  |  | 17LH0195 | 2017-11-08 |  | 2017-12-07 | 2018-01-18 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 206003 | Balah Licosan PS | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 9545900 |  |  | Completed | 1 |  |  |  | 17LH0163 | 2017-11-08 |  | 2017-11-23 | 2018-01-01 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129682 | Bankas Heights ES | DAVAO CITY | 3 | 1 | 6 | 3STY6CL | BATCH 10 | 14189600 |  |  | Completed | 1 |  |  |  | 17LH0188 | 2017-11-06 |  | 2017-12-05 | 2018-01-18 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129730 | Bartolome ES | DAVAO CITY | 3 | 1 | 9 | 3STY9CL | BATCH 10 | 25368100 |  |  | Completed | 1 |  |  |  | 17LH0197 | 2017-11-08 |  | 2017-12-07 | 2018-01-18 | 2018-02-05
NC 2017 | K10 | Region XI | Davao City | 129491 | Bayabas ES | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 8945900 |  |  | Completed | 1 |  |  |  | 17LH0167 | 2017-11-08 |  | 2017-11-23 | 2018-01-01 | 2018-02-01
NC 2017 | SHS | Region XI | Davao City | 316201 | Bernardino B. Bosque NHS | DAVAO CITY | 2 | 1 | 12 | 3STY12CL | BATCH 10 | 31708009 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 316201 | Bernardino B. Bosque NHS | DAVAO CITY | 2 |  | 4 | 4STY LABORATORY WORKSHOP BLDG. | BATCH 10 | 18912336 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304350 | Binugao NHS | DAVAO CITY | 3 | 1 | 13 | 4STY7CL STANDARD CL REGULAR WORKSHOP, 4 STANDARD CLASSROOM SCIENCE AND ICT LABORATORY AND 2 REGULAR CLASSROOM | BATCH 10 | 48874167.08 |  |  | Completed | 1 |  |  |  | 17LH0220 | 2017-11-21 |  | 2017-12-19 | 2018-01-18 | 2018-02-01
NC 2017 | SHS | Region XI | Davao City | 304350 | Binugao NHS | DAVAO CITY | 3 |  | 16 | 4STY16CL | BATCH 10 | 37069500 |  |  | Completed | 1 |  |  |  | 17LH0206 | 2017-11-14 |  | 2017-12-19 |  | 2018-02-15
NC 2017 | K10 | Region XI | Davao City | 129506 | Buhangin CES SPED CENTER | DAVAO CITY | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 34361773 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129506 | Buhangin CES SPED CENTER | DAVAO CITY | 2 |  | 24 | 4STY24CL | BATCH 10 | 52374596 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129493 | C.B. Bangoy Sr. ES | DAVAO CITY | 3 | 1 | 6 | 3STY6CL | BATCH 10 | 13798900 |  |  | Completed | 1 |  |  |  | 17LH0178 | 2017-11-06 |  | 2017-12-05 | 2018-01-18 | 2018-02-05
NC 2017 | K10 | Region XI | Davao City | 129562 | Cabagbahangan ES | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 9545900 |  |  | Completed | 1 |  |  |  | 17LH0169 | 2017-11-08 |  | 2017-11-23 | 2018-01-01 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129531 | Calinan Central ES | DAVAO CITY | 3 | 1 | 12 | 4STY12CL | BATCH 10 | 31672300 |  |  | Completed | 1 |  |  |  | 17LH0202 | 2017-11-08 |  | 2017-12-07 | 2018-01-18 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129715 | Catalunan Grande ES | DAVAO CITY | 1 | 1 | 15 | 3STY15CL | BATCH 10 | 36509495 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129555 | Cesareo VillaAbrille Elementary School | DAVAO CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34431773 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129658 | Damilag PS | DAVAO CITY | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2920000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129660 | Datu Manlangan ES | DAVAO CITY | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2920000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 129606 | Datu Salumay ES | DAVAO CITY | 3 | 1 | 10 | 2STY6CL & 2STY4CL | BATCH 10 | 21952100 |  |  | Completed | 1 |  |  |  | 17LH0193 | 2017-11-08 |  | 2017-12-07 | 2018-01-18 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129565 | Dominga ES | DAVAO CITY | 3 | 1 | 6 | 3STY6CL | BATCH 10 | 14189600 |  |  | Completed | 1 |  |  |  | 17LH0187 | 2017-11-06 |  | 2017-12-05 | 2018-01-18 | 2018-02-05
NC 2017 | K10 | Region XI | Davao City | 129718 | Dona Soledad Dolor ES | DAVAO CITY | 1 | 1 | 6 | 3STY6CL | BATCH 10 | 14918676 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Davao City | 304395 | Emilio J. Estipona- Guinga NHS | DAVAO CITY | 3 | 1 | 6 | 3STY6CL | BATCH 10 | 14639600 |  |  | Completed | 1 |  |  |  | 17LH0184 | 2017-11-06 |  | 2017-12-05 | 2018-01-18 | 2018-02-01
NC 2017 | TVL | Region XI | Davao City | 304366 | F. Bangoy NHS | DAVAO CITY | 2 | 1 | 4 | 4STY LABORATORY WORKSHOP BLDG. | BATCH 10 | 18872336 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Davao City | 304366 | F. Bangoy NHS | DAVAO CITY | 2 |  | 20 | 4STY20CL | BATCH 10 | 45243583 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129481 | F. Bustamante ES | DAVAO CITY | 2 | 1 | 20 | 4STY20CL | BATCH 10 | 44821083 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304369 | Gorgonio Tajo, Sr. NHS | DAVAO CITY | 2 | 1 | 18 | 3STY WORKSHOP BLDG. (7X18) | BATCH 10 | 41211113 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129467 | Gumalang ES | DAVAO CITY | 3 | 1 | 6 | 2STY6CL | BATCH 10 | 11756100 |  |  | Completed | 1 |  |  |  | 17LH0175 | 2017-11-08 |  | 2017-11-23 | 2018-01-18 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129734 | Imelda ES | DAVAO CITY | 3 | 1 | 8 | 2STY8CL | BATCH 10 | 17037600 |  |  | Completed | 1 |  |  |  | 17LH0191 | 2017-11-08 |  | 2017-12-07 | 2018-01-18 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129567 | Inayangan ES | DAVAO CITY | 3 | 1 | 6 | 3STY6CL | BATCH 10 | 13807500 |  |  | Completed | 1 |  |  |  | 17LH0180 | 2017-11-06 |  | 2017-12-05 | 2018-01-18 | 2018-02-05
NC 2017 | TVL | Region XI | Davao City | 316210 | Inayangan HS (Telesforo Annex) | DAVAO CITY | 3 | 1 | 10 | 2STY4CL & 3STY6CL | BATCH 10 | 23885500 |  |  | Completed | 1 |  |  |  | 17LH0213 | 2017-11-14 |  | 2017-12-19 |  | 2018-02-15
NC 2017 | K10 | Region XI | Davao City | 129549 | Jose Vicente Ferriols ES | DAVAO CITY | 3 | 1 | 9 | 3STY9CL | BATCH 10 | 24616300 |  |  | Completed | 1 |  |  |  | 17LH0200 | 2017-11-08 |  | 2017-11-08 | 2018-01-18 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129643 | Kabacan ES | DAVAO CITY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 18632336 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129535 | Lacson ES | DAVAO CITY | 3 | 1 | 9 | 3STY9CL | BATCH 10 | 25668100 |  |  | Completed | 1 |  |  |  | 17LH0194 | 2017-11-08 |  | 2017-11-08 | 2018-01-18 | 2018-02-01
NC 2017 | TVL | Region XI | Davao City | 304371 | Lamanan National High School | DAVAO CITY | 3 | 1 | 11 | 3STY5STANDARD REGULAR WORKSHOP, 2 REGULAR CL & 4STY4CL ICT AND SCIENCE LABORATORY | BATCH 10 | 40637900 |  |  | Completed | 1 |  |  |  | 17LH0221 | 2017-11-21 |  | 2017-12-19 | 2018-01-18 | 2018-02-05
NC 2017 | SHS | Region XI | Davao City | 304371 | Lamanan National High School | DAVAO CITY | 3 |  | 4 | 2STY4CL | BATCH 10 | 8984800 |  |  | Completed | 1 |  |  |  | 17LH0164 | 2017-11-08 |  | 2017-11-23 | 2018-01-01 | 2018-02-05
NC 2017 | K10 | Region XI | Davao City | 129538 | Lt. C. Villafuerte, Sr. ES | DAVAO CITY | 3 | 1 | 20 | 4STY20CL | BATCH 10 | 44408400 |  |  | Completed | 1 |  |  |  | 17LH0211 | 2017-11-14 |  | 2017-12-12 |  | 2018-02-15
NC 2017 | K10 | Region XI | Davao City | 129645 | Maa CES | DAVAO CITY | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 39943597 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129558 | Magallanes Elementary School | DAVAO CITY | 1 | 1 | 15 | 3STY15CL | BATCH 10 | 36649495 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129558 | Magallanes Elementary School | DAVAO CITY | 1 |  | 20 | 4STY20CL | BATCH 10 | 45321083 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129615 | Magsaysay ES | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 8962750 |  |  | Completed | 1 |  |  |  | 17LH0177 | 2017-11-08 |  | 2017-11-23 | 2018-01-18 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129615 | Magsaysay ES | DAVAO CITY | 3 |  | 4 | 2STY4CL | BATCH 10 | 8962750 |  |  | Completed | 1 |  |  |  | 17LH0189 | 2017-11-08 |  | 2017-12-07 | 2018-01-18 | 2018-02-01
NC 2017 | TVL | Region XI | Davao City | 316213 | MAHAYAG NATIONAL HIGH SCHOOL | DAVAO CITY | 2 | 1 | 4 | 4STY4CL | BATCH 10 | 18832336 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 316213 | MAHAYAG NATIONAL HIGH SCHOOL | DAVAO CITY | 2 |  | 6 | 3STY LABORATORY WORKSHOP BLDG. | BATCH 10 | 31933009 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129469 | Malagos ES | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 8951700 |  |  | Completed | 1 |  |  |  | 17LH0174 | 2017-11-08 |  | 2017-11-23 | 2018-01-18 | 2018-02-01
NC 2017 | SHS | Region XI | Davao City | 304380 | Mandug NHS (Pablo Lorenzo NHS) | DAVAO CITY | 2 | 1 | 9 | 3STY9CL | BATCH 10 | 26485492 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304380 | Mandug NHS (Pablo Lorenzo NHS) | DAVAO CITY | 2 |  | 3 | 3STY WORKSHOP BLDG. (7X18) | BATCH 10 | 14992676 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304380 | Mandug NHS (Pablo Lorenzo NHS) | DAVAO CITY | 2 |  | 6 | 3STY WORKSHOP BLDG. (7X18) | BATCH 10 | 31933009 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304382 | Marilog National High School | DAVAO CITY | 3 | 1 | 10 | 3STY6CLSTANDARD CL REGULAR WORKSHOP & 4STY4CL ICT AND SCIENCE LABORATORY | BATCH 10 | 42421028.62 |  |  | Completed | 1 |  |  |  | 17LH0222 | 2017-11-21 |  | 2017-12-19 | 2018-01-18 | 2018-02-01
NC 2017 | SHS | Region XI | Davao City | 304382 | Marilog National High School | DAVAO CITY | 3 |  | 8 | 2STY8CL | BATCH 10 | 16992700 |  |  | Completed | 1 |  |  |  | 17LH0192 | 2017-11-08 |  | 2017-12-07 | 2018-01-18 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129621 | Masawang ES | DAVAO CITY | 3 | 1 | 6 | 2STY6CL | BATCH 10 | 12556200 |  |  | Completed | 1 |  |  |  | 17LH0190 | 2017-11-08 |  | 2017-12-07 | 2018-01-18 | 2018-02-01
NC 2017 | TVL | Region XI | Davao City | 304385 | Mintal Comprehensive High School | DAVAO CITY | 3 | 1 | 4 | 4STY2STANDARD CL REGULAR WORKHOP AND 2 STANDARD CL FOR ICT AND SCIENCE LABORATORY | BATCH 10 | 23010900 |  |  | Completed | 1 |  |  |  | 17LH0223 | 2017-11-21 |  | 2017-12-19 | 2018-01-18 | 2018-02-01
NC 2017 | SHS | Region XI | Davao City | 304385 | Mintal Comprehensive High School | DAVAO CITY | 3 |  | 12 | 4STY12CL | BATCH 10 | 31761900 |  |  | Completed | 1 |  |  |  | 17LH0207 | 2017-11-14 |  | 2017-12-12 |  | 2018-02-15
NC 2017 | SHS | Region XI | Davao City | 304385 | Mintal Comprehensive High School | DAVAO CITY | 3 |  | 20 | 4STY20CL | BATCH 10 | 40988800 |  |  | Completed | 1 |  |  |  | 17LH0208 | 2017-11-14 |  | 2017-12-12 |  | 2018-02-15
NC 2017 | SHS | Region XI | Davao City | 304385 | Mintal Comprehensive High School | DAVAO CITY | 3 |  | 20 | 4STY20CL | BATCH 10 | 40988800 |  |  | Completed | 1 |  |  |  | 17LH0209 | 2017-11-14 |  | 2017-12-12 |  | 2018-02-15
NC 2017 | K10 | Region XI | Davao City | 129738 | Mintal ES | DAVAO CITY | 3 | 1 | 6 | 3STY6CL | BATCH 10 | 13762100 |  |  | Completed | 1 |  |  |  | 17LH0182 | 2017-11-06 |  | 2017-12-05 | 2018-01-18 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129738 | Mintal ES | DAVAO CITY | 3 |  | 15 | 3STY15CL | BATCH 10 | 33724300 |  |  | Completed | 1 |  |  |  | 17LH0181 | 2017-11-14 |  | 2017-12-12 |  | 2018-02-15
NC 2017 | K10 | Region XI | Davao City | 129573 | Pagan Grande ES | DAVAO CITY | 3 | 1 | 6 | 3STY6CL | BATCH 10 | 14039600 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129629 | Salaysay ES | DAVAO CITY | 3 | 1 | 6 | 2STY6CL | BATCH 10 | 12556200 |  |  | Completed | 1 |  |  |  | 17LH0168 | 2017-11-08 |  | 2017-11-23 | 2018-01-01 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129691 | San Miguel ES | DAVAO CITY | 3 | 1 | 12 | 3STY12CL | BATCH 10 | 30859300 |  |  | Completed | 1 |  |  |  | 17LH0201 | 2017-11-08 |  | 2017-12-07 | 2018-01-18 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129551 | Sta. Clara ES | DAVAO CITY | 3 | 1 | 6 | 3STY6CL | BATCH 10 | 13739600 |  |  | Completed | 1 |  |  |  | 17LH0179 | 2017-11-06 |  | 2017-12-05 | 2018-01-18 | 2018-02-01
NC 2017 | TVL | Region XI | Davao City | 316208 | Suawan High School | DAVAO CITY | 3 | 1 | 4 | 4STY4STANDARD CL SCIENCE AND ICT LABORATORY | BATCH 10 | 17482047.61 |  |  | Completed | 1 |  |  |  | 17LH02255 | 2017-11-21 |  | 2017-12-19 | 2018-01-18 | 2018-02-01
NC 2017 | SHS | Region XI | Davao City | 316208 | Suawan High School | DAVAO CITY | 3 |  | 4 | 2STY4CL | BATCH 10 | 9069200 |  |  | Completed | 1 |  |  |  | 17LH0165 | 2017-11-08 |  | 2017-11-23 | 2018-01-01 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129740 | Tacunan Elementary | DAVAO CITY | 3 | 1 | 17 | 1STY2CL & 3STY15CL | BATCH 10 | 36468600 |  |  | Completed | 1 |  |  |  | 17LH0205 | 2017-11-14 |  | 2017-12-12 |  | 2018-02-15
NC 2017 | K10 | Region XI | Davao City | 129741 | Tagakpan ES | DAVAO CITY | 3 | 1 | 6 | 2STY6CL | BATCH 10 | 11722500 |  |  | Completed | 1 |  |  |  | 17LH0176 | 2017-11-08 |  | 2017-11-23 | 2018-01-18 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129742 | Talandang ES | DAVAO CITY | 3 | 1 | 9 | 3STY9CL | BATCH 10 | 25668100 |  |  | Completed | 1 |  |  |  | 17LH0196 | 2017-11-06 |  | 2017-12-05 | 2018-01-18 | 2018-02-05
NC 2017 | K10 | Region XI | Davao City | 129724 | Talomo CES | DAVAO CITY | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 44941083 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129544 | Tamayong ES | DAVAO CITY | 3 | 1 | 6 | 1STY2CL & 2STY4CL | BATCH 10 | 11649400 |  |  | Completed | 1 |  |  |  | 17LH0185 | 2017-11-06 |  | 2017-12-05 | 2018-01-18 | 2018-02-05
NC 2017 | TVL | Region XI | Davao City | 316205 | Tambobong National High School | DAVAO CITY | 3 | 1 | 2 | 2STY4STANDARD SCIENCE AND ICT BLDG. | BATCH 10 | 17037600 |  |  | Completed | 1 |  |  |  | 17LH0224 | 2017-11-21 |  | 2017-12-19 | 2018-01-18 | 2018-02-01
NC 2017 | SHS | Region XI | Davao City | 316205 | Tambobong National High School | DAVAO CITY | 3 |  | 6 | 3STY6CL | BATCH 10 | 14043500 |  |  | Completed | 1 |  |  |  | 17LH0186 | 2017-11-06 |  | 2017-12-05 | 2018-01-18 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129474 | Tawantawan ES | DAVAO CITY | 3 | 1 | 6 | 2STY6CL | BATCH 10 | 11689900 |  |  | Completed | 1 |  |  |  | 17LH0173 | 2017-11-08 |  | 2017-11-23 | 2018-01-01 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129503 | Tibuloy ES | DAVAO CITY | 3 | 1 | 6 | 2STY6CL | BATCH 10 | 11806200 |  |  | Completed | 1 |  |  |  | 17LH0171 | 2017-11-08 |  | 2017-11-23 | 2018-01-01 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129743 | Tugbok Central ES SPED Center | DAVAO CITY | 3 | 1 | 12 | 3STY12CL | BATCH 10 | 29399300 |  |  | Completed | 1 |  |  |  | 17LH0203 | 2017-11-08 |  | 2017-12-07 | 2018-01-18 | 2018-02-05
NC 2017 | K10 | Region XI | Davao City | 129693 | Tungkalan ES | DAVAO CITY | 3 | 1 | 9 | 3STY9CL | BATCH 10 | 25368100 |  |  | Completed | 1 |  |  |  | 17LH0198 | 2017-11-08 |  | 2017-12-07 | 2018-01-18 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129552 | V.S. Bangoy ES | DAVAO CITY | 3 | 1 | 9 | 3STY9CL | BATCH 10 | 24918100 |  |  | Completed | 1 |  |  |  | 17LH0199 | 2017-11-08 |  | 2017-12-07 | 2018-01-18 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129745 | Vinzons ES | DAVAO CITY | 3 | 1 | 6 | 2STY6CL | BATCH 10 | 12106200 |  |  | Completed | 1 |  |  |  | 17LH0166 | 2017-11-08 |  | 2017-11-23 | 2018-01-01 | 2018-02-01
NC 2017 | TVL | Region XI | Davao City | 304399 | Waan National High School | DAVAO CITY | 2 | 1 | 4 | 4STY LABORATORY WORKSHOP BLDG. | BATCH 10 | 18912336 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129547 | Wangan ES | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 8975100 |  |  | Completed | 1 |  |  |  | 17LH0170 | 2017-11-08 |  | 2017-11-23 | 2018-01-01 | 2018-02-05
NC 2017 | K10 | Region XI | Davao City | 129475 | Wines ES | DAVAO CITY | 3 | 1 | 6 | 2STY6CL | BATCH 10 | 11678700 |  |  | Completed | 1 |  |  |  | 17LH0172 | 2017-11-08 |  | 2017-11-23 | 2018-01-01 | 2018-02-01
NC 2017 | K10 | Region XI | Davao del Norte | 128566 | Buclad ES | ASUNCION (SAUG) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2885770 |  |  | Completed | 1 |  |  | P00180690MN-CW1 | 17LC0266 | 2017-07-12 | 2017-07-19 | 2017-12-27 | 2017-12-28 | 2018-01-08 | Micah Construction & Supply
NC 2017 | K10 | Region XI | Davao del Norte | 128567 | Cabaywa ES | ASUNCION (SAUG) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2762753 |  |  | Completed | 1 |  |  | P00180691MN-CW1 | 17LC0270 | 2017-07-12 | 2017-07-19 | 2017-12-27 | 2017-12-28 | 2018-01-08 | Micah Construction & Supply
NC 2017 | K10 | Region XI | Davao del Norte | 128570 | Cambanogoy CES | ASUNCION (SAUG) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2844627 |  |  | Completed | 1 |  |  | P00171911MN-CW1 | 17LC0362 | 2017-10-26 | 2017-11-03 | 2017-11-16 | 2017-12-05 | 2017-12-15 | LLM Unified Builders & Trading Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304234 | Capungangan HS-Annex | KAPALONG | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9069399 |  |  | Completed | 1 |  |  | P00180702MN-CW1 | 17LC0405 | 2017-12-08 | 2017-12-15 | 2017-12-27 | 2017-12-28 | 2018-01-08 | Micah Construction and Supply
NC 2017 | SHS | Region XI | Davao del Norte | 304234 | Capungangan HS-Annex | KAPALONG | 1 |  | 4 | 2STY4CL | BATCH 10 | 9069399 |  |  | Completed | 1 |  |  | P00180703MN-CW1 | 17LC0406 | 2017-12-08 | 2017-12-15 | 2017-12-27 | 2017-12-28 | 2018-01-08 | Micah Construction and Supply
NC 2017 | SHS | Region XI | Davao del Norte | 304234 | Capungangan HS-Annex | KAPALONG | 1 |  | 2 | 1STY2CL | BATCH 10 | 2718274 |  |  | Completed | 1 |  |  | P00180704MN-CW1 | 17LC0268 | 2017-07-12 | 2017-07-19 | 2017-12-27 | 2017-12-28 | 2018-01-08 | Micah Construction and Supply
NC 2017 | K10 | Region XI | Davao del Norte | 128662 | Maniki CES SPED Center | KAPALONG | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3899949 |  |  | Completed | 1 |  |  | P00180695MN-CW1 | 17LC0297 | 2017-07-12 | 2017-07-19 | 2017-12-27 | 2017-12-28 | 2018-01-08 | Micah Construction and Supply
NC 2017 | K10 | Region XI | Davao del Norte | 128666 | Patel Elementary School | KAPALONG | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2774560 |  |  | Completed | 1 |  |  | P00180696MN-CW1 | 17LC0306 | 2017-07-12 | 2017-07-19 | 2017-12-27 | 2017-12-28 | 2018-01-08 | LLM Unified Builders and Trading Corp.
NC 2017 | K10 | Region XI | Davao del Norte | 128700 | Cabidianan ES | NEW CORELLA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2844627 |  |  | Completed | 1 |  |  | P00180698MN-CW1 | 17LC0313 | 2017-07-12 | 2017-07-19 | 2017-12-27 | 2017-12-28 | 2018-01-08 | E.P Manantan Construction and Development Corp.
NC 2017 | K10 | Region XI | Davao del Norte | 128703 | Del Pilar ES | NEW CORELLA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2844627 |  |  | Completed | 1 |  |  | P00180699MN-CW1 | 17LC0312 | 2017-07-12 | 2017-07-19 | 2017-12-27 | 2017-12-28 | 2018-01-08 | Mag Corporation
NC 2017 | SHS | Region XI | Davao del Norte | 304249 | Mesaoy NHS | NEW CORELLA | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9279249 |  |  | Completed | 1 |  |  | P00180711MN-CW1 | 17LC0424 | 2017-12-08 | 2017-12-15 | 2017-12-27 | 2017-12-28 | 2018-01-08 | R.R Seiemundo Contruction & Supply
NC 2017 | SHS | Region XI | Davao del Norte | 304249 | Mesaoy NHS | NEW CORELLA | 1 |  | 4 | 2STY4CL | BATCH 10 | 9279249 |  |  | Completed | 1 |  |  | P00180712MN-CW1 | 17LC0425 | 2017-12-08 | 2017-12-15 | 2017-12-27 | 2017-12-28 | 2018-01-08 | R.R Seiemundo Contruction & Supply
NC 2017 | SHS | Region XI | Davao del Norte | 304249 | Mesaoy NHS | NEW CORELLA | 1 |  | 2 | 1STY2CL | BATCH 10 | 2775449 |  |  | Completed | 1 |  |  | P00180713MN-CW1 | 17LC0314 | 2017-07-12 | 2017-07-19 | 2017-12-27 | 2017-12-28 | 2018-01-08 | E.P Manantan Construction & Development Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304248 | New Corella National High School | NEW CORELLA | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9661348 |  |  | Completed | 1 |  |  | P00180708MN-CW1 | 17LC0427 | 2017-12-08 | 2017-12-15 | 2017-12-27 | 2017-12-28 | 2017-01-08 | R.R Seiemundo Contruction & Supply
NC 2017 | SHS | Region XI | Davao del Norte | 304248 | New Corella National High School | NEW CORELLA | 1 |  | 4 | 2STY4CL | BATCH 10 | 9661348 |  |  | Completed | 1 |  |  | P00180709MN-CW1 | 17LC0426 | 2017-12-08 | 2017-12-15 | 2017-12-27 | 2017-12-28 | 2017-01-08 | R.R Seiemundo Contruction & Supply
NC 2017 | SHS | Region XI | Davao del Norte | 304248 | New Corella National High School | NEW CORELLA | 1 |  | 2 | 1STY2CL | BATCH 10 | 2844627 |  |  | Completed | 1 |  |  | P00180710MN-CW1 | 17LC0310 | 2017-07-12 | 2017-07-09 | 2017-12-27 | 2017-12-28 | 2018-01-08 | Micah Construction & Supply
NC 2017 | K10 | Region XI | Davao del Norte | 128715 | New Cortez ES | NEW CORELLA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2844627 |  |  | Completed | 1 |  |  | P00171936MN-CW1 | 17LC0365 | 2017-10-26 | 2017-11-03 | 2017-11-16 | 2017-10-18 | 2017-12-15 | Tagum Builders Contractors Corporation
NC 2017 | K10 | Region XI | Davao del Norte | 128652 | Gov. Dujali ES | SAN ISIDRO | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 4072839 |  |  | Completed | 1 |  |  | P00171923MN-CW1 | 17LC0348 | 2017-11-03 | 2017-11-10 | 2017-12-08 | 2017-12-08 | 2017-12-18 | Five Massive Infra and Supply Corp.
NC 2017 | K10 | Region XI | Davao del Norte | 128576 | Kipalili ES | SAN ISIDRO | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3970935 |  |  | Completed | 1 |  |  | P00171912MN-CW1 | 17LC0363 | 2017-10-26 | 2017-11-03 | 2017-11-16 | 2017-12-05 | 2017-12-18 | Five Massive Infra and Supply Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304240 | Linao National High School | SAN ISIDRO | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9098419 |  |  | Completed | 1 |  |  | P00180705MN-CW1 | 17LC0567 | 2017-12-08 | 2017-12-15 | 2017-12-27 | 2017-12-28 | 2018-01-08 | LLM Unified Builders & Trading Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304240 | Linao National High School | SAN ISIDRO | 1 |  | 4 | 2STY4CL | BATCH 10 | 9098419 |  |  | Completed | 1 |  |  | P00180706MN-CW1 | 17LC0568 | 2017-12-08 | 2017-12-15 | 2017-12-27 | 2017-12-28 | 2018-01-08 | LLM Unified Builders & Trading Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304240 | Linao National High School | SAN ISIDRO | 1 |  | 2 | 1STY2CL | BATCH 10 | 2718274 |  |  | Completed | 1 |  |  | P00180707MN-CW1 | 17LC0269 | 2017-07-12 | 2017-07-19 | 2017-12-27 | 2017-12-28 | 2018-01-08 | Five Massive Infra & Supply Corp.
NC 2017 | K10 | Region XI | Davao del Norte | 128667 | Pinamuno ES | SAN ISIDRO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2928631 |  |  | Completed | 1 |  |  | P00171929MN-CW1 | 17LC0353 | 2017-11-03 | 2017-11-10 | 2017-12-08 | 2017-12-28 | 2017-12-18 | LLM Unified Builders and Trading Corp.
NC 2017 | K10 | Region XI | Davao del Norte | 128804 | NASECO ES | TALAINGOD | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2769001 |  |  | Completed | 1 |  |  | P00180701MN-CW1 | 17LC0566 | 2017-12-08 | 2017-12-15 | 2017-12-27 | 2017-12-28 | 2018-01-08 | LLM Unified Builders & Trading Corp.
NC 2017 | K10 | Region XI | Davao del Sur | 128811 | Balutakay ES | BANSALAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2680157.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-21 |  | 2017-12-04 |  | 2017-12-20 | RC Melgazo Builders
NC 2017 | K10 | Region XI | Davao del Sur | 128815 | Mabuhay ES | BANSALAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2639883.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | Prindi Construction
NC 2017 | K10 | Region XI | Davao del Sur | 128833 | Malupo ES | BANSALAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2738745.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | Prindi Construction
NC 2017 | K10 | Region XI | Davao del Sur | 128817 | Managa ES | BANSALAN | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 4093390 |  |  | Completed | 1 |  |  |  |  | 2017-11-21 |  | 2017-12-04 |  | 2017-12-20 | Davao Santhony Builders Corporation
NC 2017 | SHS | Region XI | Davao del Sur | 304286 | Marber NHS | BANSALAN | 1 | 1 | 6 | 3STY6CL | BATCH 10 | 15149880 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | L.A. Arizola Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 128818 | New Clarin ES | BANSALAN | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9500715 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | North Star Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 316006 | New Clarin National High School | BANSALAN | 1 | 1 | 9 | 3STY9CL | BATCH 10 | 26711890 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | St. Timothy Construction Supply
NC 2017 | SHS | Region XI | Davao del Sur | 304285 | Pedro A. Arches NHS | BANSALAN | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 18688870 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | LTB Builders & Construction
NC 2017 | SHS | Region XI | Davao del Sur | 304285 | Pedro A. Arches NHS | BANSALAN | 1 |  | 9 | 3STY9CL | BATCH 10 | 26822440 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | LTB Builders & Construction
NC 2017 | K10 | Region XI | Davao del Sur | 128857 | Apolonio R. Fuentes Sr. ES | HAGONOY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2639883.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | Mark Anthony Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 128859 | Cerino L. Lamosa Elementary School | HAGONOY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2639883.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | Mark Anthony Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 128855 | Hagonoy Central Elementary School | HAGONOY | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 12376050 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | A.V. Mesonia
NC 2017 | K10 | Region XI | Davao del Sur | 128862 | Leoncio S. Peliño ES(Malabang West) | HAGONOY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2687675 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | Mark Anthony Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 128863 | Maliit Digos ES | HAGONOY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2669900 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | Mark Anthony Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 128865 | Sacub ES | HAGONOY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2640745.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | RC Melgazo Builders
NC 2017 | SHS | Region XI | Davao del Sur | 316004 | SACUB National High School | HAGONOY | 1 | 1 | 6 | 3STY6CL | BATCH 10 | 15154250 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | A.V. Mesonia
NC 2017 | K10 | Region XI | Davao del Sur | 128866 | San Guillermo ES | HAGONOY | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3848551 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | JLACE Builders Corp.
NC 2017 | SHS | Region XI | Davao del Sur | 304274 | Gov. N. Llanos NHS | KIBLAWAN | 1 | 1 | 6 | 3STY6CL | BATCH 10 | 15130180 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | Mark Anthony Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 128903 | Ihan ES | KIBLAWAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2639882.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | LLM Unified Builders
NC 2017 | K10 | Region XI | Davao del Sur | 128903 | Ihan ES | KIBLAWAN | 1 |  | 2 | 1STY2CL | BATCH 10 | 2639882.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | LLM Unified Builders
NC 2017 | K10 | Region XI | Davao del Sur | 128913 | Jose T. Arranguez SR. ES | KIBLAWAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2639883.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | Mark Anthony Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 128905 | Kiblawan CES | KIBLAWAN | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9518590 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | Ecomixed Construction & Development Corporation
NC 2017 | SHS | Region XI | Davao del Sur | 316001 | Molopolo National High School | KIBLAWAN | 1 | 1 | 6 | 3STY6CL | BATCH 10 | 15171600 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | Rely construction& Supply
NC 2017 | K10 | Region XI | Davao del Sur | 128919 | Tacub PS | KIBLAWAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2859841 |  |  | Completed | 1 |  |  |  |  | 2017-11-21 |  | 2017-12-04 |  | 2017-12-20 | Mark Anthony Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 128920 | TACUL ELEMENTARY SCHOOL | KIBLAWAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2666745.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | NLC Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 205046 | Asbang-Elok ES | MAGSAYSAY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2853213.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-21 |  | 2017-12-04 |  | 2017-12-20 | NLC Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 128922 | Bala Elementary School | MAGSAYSAY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2700760 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | Davao Santhony Builders
NC 2017 | SHS | Region XI | Davao del Sur | 304265 | Barayong National High School | MAGSAYSAY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 18636200 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | Three W Builders
NC 2017 | K10 | Region XI | Davao del Sur | 316009 | Kasuga National High School | MAGSAYSAY | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 12483735 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | LTB Builders & Construction
NC 2017 | K10 | Region XI | Davao del Sur | 205057 | Lower Asbang Elok ES | MAGSAYSAY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2917580.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-21 |  | 2017-12-04 |  | 2017-12-20 | NLC Construction & Supply
NC 2017 | SHS | Region XI | Davao del Sur | 304284 | Lower Bala NHS | MAGSAYSAY | 1 | 1 | 8 | 2STY8CL | BATCH 10 | 18620960 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | Leamor Construction & supply
NC 2017 | K10 | Region XI | Davao del Sur | 128938 | Malawanit ES | MAGSAYSAY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2640745.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | Mark Anthony Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 128929 | New Opon Elementary School | MAGSAYSAY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2708870 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | Mark Anthony Construction & Supply
NC 2017 | TVL | Region XI | Davao del Sur | 304298 | Tacul Agricultural High School | MAGSAYSAY | 1 | 1 | 12 | 12UNITS UNIQUE WORKSHOP | BATCH 10 | 40180000 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | St. Timothy Constructio & Supply
NC 2017 | SHS | Region XI | Davao del Sur | 304298 | Tacul Agricultural High School | MAGSAYSAY | 1 |  | 10 | 2STY10CL | BATCH 10 | 21190210 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | Rely Construction & supply
NC 2017 | SHS | Region XI | Davao del Sur | 304298 | Tacul Agricultural High School | MAGSAYSAY | 1 |  | 4 | 2STY4CL | BATCH 10 | 9684080 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | NLC Constructio & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 128943 | Tacul ES | MAGSAYSAY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2640745.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | NLC Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 128955 | Benito J. Quibod Elementary School | MALALAG | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | Two Degrees Construction & Supply
NC 2017 | SHS | Region XI | Davao del Sur | 304270 | Davao Del Sur SOF | MALALAG | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 12756168.02 |  |  | Completed | 1 |  |  |  |  | 2017-11-21 |  | 2017-12-04 |  | 2017-12-20 | LTB Builders & Construction
NC 2017 | TVL | Region XI | Davao del Sur | 304270 | Davao Del Sur SOF | MALALAG | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3430000 |  |  | Completed | 1 |  |  |  |  | 2017-11-21 |  | 2017-12-04 |  | 2017-12-20 | L.A. Arizola Construction Suppl
NC 2017 | TVL | Region XI | Davao del Sur | 304270 | Davao Del Sur SOF | MALALAG | 1 |  | 2 | 2UNITS UNIQUE WORKSHOP | BATCH 10 | 6558000 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | LLM Unified Builders
NC 2017 | K10 | Region XI | Davao del Sur | 128957 | Jose F.Lanoza ES | MALALAG | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2824810 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | Two Degrees Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 128954 | Malalag CES | MALALAG | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9605885.66 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | Leamor Construction & supply
NC 2017 | K10 | Region XI | Davao del Sur | 128960 | Tagansule ES | MALALAG | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2640745.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | Leamor Construction & supply
NC 2017 | K10 | Region XI | Davao del Sur | 129028 | Asbang ES | MATANAO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2855535.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | Two Degrees Construction & Supply
NC 2017 | K10 | Region XI | Davao del Sur | 129031 | Buri ES | MATANAO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2639883.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | Amplex Construction
NC 2017 | K10 | Region XI | Davao del Sur | 129035 | Dongan Pekong ES | MATANAO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2866960.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | Davao Santhony Builders Corporation
NC 2017 | K10 | Region XI | Davao del Sur | 205007 | Kapoc ES | MATANAO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2871147.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | Kofejok Construction
NC 2017 | K10 | Region XI | Davao del Sur | 129041 | Manga CES | MATANAO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2640745.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | NLC Construction & Supply
NC 2017 | SHS | Region XI | Davao del Sur | 304288 | Matanao National High School | MATANAO | 1 | 1 | 12 | 3STY12CL | BATCH 10 | 31859267.25 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | FGM Builders
NC 2017 | K10 | Region XI | Davao del Sur | 316017 | New Katipunan National High School | MATANAO | 1 | 1 | 8 | 2UNITS 2STY4CL | BATCH 10 | 19213050 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | LTB Builders & Construction
NC 2017 | K10 | Region XI | Davao del Sur | 129020 | New Visayas ES | MATANAO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2640745.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | Leamor Construction
NC 2017 | SHS | Region XI | Davao del Sur | 316003 | SALUD CAGAS TECH.& VOC. H.S | MATANAO | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 18604820 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | LTB Builders & Construction
NC 2017 | SHS | Region XI | Davao del Sur | 304290 | Sinawilan NHS | MATANAO | 1 | 1 | 6 | 3STY6CL | BATCH 10 | 15098515.1 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | LTB Builders & Construction
NC 2017 | K10 | Region XI | Davao del Sur | 129034 | Tribal Filipino School of Datalfitak | MATANAO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3047928.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | BDF Construction
NC 2017 | K10 | Region XI | Davao del Sur | 129045 | GAUDIOSO ORBITA ES | PADADA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2639883.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | Kofejok Construction
NC 2017 | K10 | Region XI | Davao del Sur | 129046 | German Lanticse ES | PADADA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2639883.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | LTB Builders & Construction
NC 2017 | K10 | Region XI | Davao del Sur | 129090 | Apolinar Franco, Sr. ES | SANTA CRUZ | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2874357.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | MAG Corporation
NC 2017 | K10 | Region XI | Davao del Sur | 129076 | Astorga CES | SANTA CRUZ | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2639883.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | MAG Corporation
NC 2017 | SHS | Region XI | Davao del Sur | 304295 | Bato NHS | SANTA CRUZ | 1 | 1 | 6 | 3STY6CL | BATCH 10 | 15448540 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | St. Timothy Construction supply
NC 2017 | TVL | Region XI | Davao del Sur | 304263 | Federico Yap National High School | SANTA CRUZ | 1 | 1 | 2 | 2UNITS UNIQUE WORKSHOP | BATCH 10 | 6465000 |  |  | Completed | 1 |  |  |  |  | 2017-11-21 |  | 2017-12-04 |  | 2017-12-20 | L.A. Arizola Construction Supply
NC 2017 | K10 | Region XI | Davao del Sur | 129081 | Inawayan ES | SANTA CRUZ | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9621317.34 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | LLM Unified Builders
NC 2017 | SHS | Region XI | Davao del Sur | 304278 | Inawayan National High School | SANTA CRUZ | 1 | 1 | 8 | 2STY8CL | BATCH 10 | 18599790.26 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | Decktop Builders Corporation
NC 2017 | TVL | Region XI | Davao del Sur | 304278 | Inawayan National High School | SANTA CRUZ | 1 |  | 2 | 2UNITS UNIQUE WORKSHOP | BATCH 10 | 6503000 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | L.A. Arizola Construction Supply
NC 2017 | K10 | Region XI | Davao del Sur | 129083 | Langan Elementary School | SANTA CRUZ | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2874826.92 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | St. Mathew G-C & Development Corporation
NC 2017 | K10 | Region XI | Davao del Sur | 129084 | Pogpog ES | SANTA CRUZ | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9840135 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | Leamor Construction
NC 2017 | SHS | Region XI | Davao del Sur | 304279 | Sibulan National High School | SANTA CRUZ | 1 | 1 | 6 | 3STY6CL | BATCH 10 | 15374805 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | Arcinue commercial
NC 2017 | SHS | Region XI | Davao del Sur | 304280 | Tudaya National High School | SANTA CRUZ | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 10251824.5 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | A.V. Mesiona
NC 2017 | SHS | Region XI | Davao del Sur | 316005 | Felipe-Inocencia Deluao NHS | SULOP | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9809325 |  |  | Completed | 1 |  |  |  |  | 2017-11-12 |  | 2017-11-27 |  | 2017-12-20 | Seven Five Five construction
NC 2017 | TVL | Region XI | Davao Occidental | 304272 | Don Marcelino NHS | DON MARCELINO | 0 | 1 | 6 | 2STY6CL WORKSHOP BLDG (7X18) | BATCH 10 | 35033853 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304292 | John Martin Johnson HS (Lamidan) | DON MARCELINO | 0 | 1 | 1 | 2STY4CL WORKSHOP BLDG (7X18) | BATCH 10 | 8653054 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304291 | Lawa NHS | DON MARCELINO | 0 | 1 | 6 | 2STY6CL WORKSHOP BLDG (7X18) | BATCH 10 | 11797144 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304291 | Lawa NHS | DON MARCELINO | 0 |  | 1 | 2STY4CL WORKSHOP BLDG (7X18) | BATCH 10 | 8653054 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304273 | Edna Guillermo Memorial National High School | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | 6 | 2STY6CL WORKSHOP BLDG (7X18) | BATCH 10 | 11905796 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304273 | Edna Guillermo Memorial National High School | JOSE ABAD SANTOS (TRINIDAD) | 0 |  | 1 | 2STY4CL WORKSHOP BLDG (7X18) | BATCH 10 | 8810237 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304281 | Jose Abad Santos NHS | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | 2 | 2STY4CL WORKSHOP BLDG (7X18) | BATCH 10 | 17387525 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304283 | Kalbay NHS | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | 6 | 2STY6CL WORKSHOP BLDG (7X18) | BATCH 10 | 11905796 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304271 | Demolok Valley National High School | MALITA | 0 | 1 | 4 | 2STY8CL WORKSHOP BLDG (7X18) | BATCH 10 | 17121686 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304271 | Demolok Valley National High School | MALITA | 0 |  | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 2600000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304271 | Demolok Valley National High School | MALITA | 0 |  | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 2600000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304271 | Demolok Valley National High School | MALITA | 0 |  | 1 | 2STY4CL WORKSHOP BLDG (7X18) | BATCH 10 | 8653054 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304287 | Mariano Peralta National High School | MALITA | 0 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 2600000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304287 | Mariano Peralta National High School | MALITA | 0 |  | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 2600000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304287 | Mariano Peralta National High School | MALITA | 0 |  | 2 | 2STY4CL WORKSHOP BLDG (7X18) | BATCH 10 | 17043581 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304293 | Ticulon NHS | MALITA | 0 | 1 | 1 | 2STY4CL WORKSHOP BLDG (7X18) | BATCH 10 | 8603605 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304266 | Basiawan NHS | SANTA MARIA | 0 | 1 | 6 | 2STY6CL WORKSHOP BLDG (7X18) | BATCH 10 | 11733539 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304266 | Basiawan NHS | SANTA MARIA | 0 |  | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 2600000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304266 | Basiawan NHS | SANTA MARIA | 0 |  | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 2600000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304266 | Basiawan NHS | SANTA MARIA | 0 |  | 1 | 2STY4CL WORKSHOP BLDG (7X18) | BATCH 10 | 8603605 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304276 | Heracleo Casco MNHS | SANTA MARIA | 0 | 1 | 6 | 2STY6CL WORKSHOP BLDG (7X18) | BATCH 10 | 11733539 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304296 | Sta. Maria NHS | SANTA MARIA | 0 | 1 | 2 | 2STY4CL WORKSHOP BLDG (7X18) | BATCH 10 | 17043581 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304268 | Tubalan Comprehensive NHS | SANTA MARIA | 0 | 1 | 6 | 2STY6CL WORKSHOP BLDG (7X18) | BATCH 10 | 11733539 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304268 | Tubalan Comprehensive NHS | SANTA MARIA | 0 |  | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 2600000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304262 | Alberto Olarte, Sr. NHS | SARANGANI | 0 | 1 | 6 | 2STY6CL WORKSHOP BLDG (7X18) | BATCH 10 | 11905796 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304282 | Jose De Arce MHS (Sangkokdatal HS) | SARANGANI | 0 | 1 | 1 | 2STY4CL WORKSHOP BLDG (7X18) | BATCH 10 | 8810237 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Oriental | 304299 | Baculin NHS | BAGANGA | 1 | 1 | 3 | 3STY WORKSHOP BLDG (7X18) | BATCH 10 | 14942753.91 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Oriental | 304299 | Baculin NHS | BAGANGA | 1 |  | 4 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 18340189.77 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Oriental | 304300 | Baganga NHS | BAGANGA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2984166.47 |  |  | Completed | 1 | [8 empty] | 2018-01-11 | MRDG CONSTRUCTION SERVICES
NC 2017 | TVL | Region XI | Davao Oriental | 304300 | Baganga NHS | BAGANGA | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2984166.47 |  |  | Completed | 1 | [8 empty] | 2018-01-11 | MRDG CONSTRUCTION SERVICES
NC 2017 | TVL | Region XI | Davao Oriental | 304300 | Baganga NHS | BAGANGA | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2984166.47 |  |  | Completed | 1 | [8 empty] | 2018-01-11 | MRDG CONSTRUCTION SERVICES
NC 2017 | TVL | Region XI | Davao Oriental | 304300 | Baganga NHS | BAGANGA | 1 |  | 4 | 2STY REGULAR WORKSHOP (7X18) | BATCH 10 | 18031537.52 |  |  | Completed | 1 | [8 empty] | 2018-01-09 | MICAH CONSTRUCTION
NC 2017 | TVL | Region XI | Davao Oriental | 304300 | Baganga NHS | BAGANGA | 1 |  | 6 | 3STY REGULAR WORKSHOP (7X18) | BATCH 10 | 30754175.12 |  |  | Completed | 1 | [8 empty] | 2017-12-20 | RELY CONSTRUCTION
NC 2017 | TVL | Region XI | Davao Oriental | 304300 | Baganga NHS | BAGANGA | 1 |  | 4 | 2STY REGULAR WORKSHOP (7X18) | BATCH 10 | 18327512.13 |  |  | Completed | 1 | [8 empty] | 2018-01-09 | RR SIESMUNDO CONST
NC 2017 | TVL | Region XI | Davao Oriental | 304312 | Crispin E. Rojas National High School | BAGANGA | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2984166.47 |  |  | Completed | 1 | [8 empty] | 2018-01-11 | RANGAY CONSTRUCTION
NC 2017 | TVL | Region XI | Davao Oriental | 304312 | Crispin E. Rojas National High School | BAGANGA | 1 |  | 6 | 3STY REGULAR WORKSHOP (7X18) | BATCH 10 | 31026077.76 |  |  | Completed | 1 | [8 empty] | 2017-12-20 | OG SANTOS CONSTRUCTION
NC 2017 | TVL | Region XI | Davao Oriental | 304312 | Crispin E. Rojas National High School | BAGANGA | 1 |  | 4 | 2STY REGULAR WORKSHOP (7X18) | BATCH 10 | 18586433.84 |  |  | Completed | 1 | [8 empty] | 2018-01-09 | RC TROCIO BUILDERS
NC 2017 | TVL | Region XI | Davao Oriental | 304316 | DR. BEATO C. MACAYRA NATIONAL HIGH SCHOOL | BAGANGA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3606505.41 |  |  | Completed | 1 | [8 empty] | 2018-01-11 | JAI BUILDERS AND SUPPLY
NC 2017 | TVL | Region XI | Davao Oriental | 304316 | DR. BEATO C. MACAYRA NATIONAL HIGH SCHOOL | BAGANGA | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3606505.41 |  |  | Completed | 1 | [8 empty] | 2018-01-11 | JAI BUILDERS AND SUPPLY
NC 2017 | TVL | Region XI | Davao Oriental | 304316 | DR. BEATO C. MACAYRA NATIONAL HIGH SCHOOL | BAGANGA | 1 |  | 6 | 3STY REGULAR WORKSHOP (7X18) | BATCH 10 | 31377343.31 |  |  | Completed | 1 | [8 empty] | 2018-12-19 | RELY CONSTRUCTION
NC 2017 | TVL | Region XI | Davao Oriental | 304304 | Boston NHS | BOSTON | 1 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9828226.31 |  |  | Completed | 1 | [8 empty] | 2018-01-11 | RANGAY CONST. & SUPPLY
NC 2017 | TVL | Region XI | Davao Oriental | 304304 | Boston NHS | BOSTON | 1 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9812661.35 |  |  | Completed | 1 | [8 empty] | 2018-01-09 | R. SEMILLA CONST. & SUPPLY
NC 2017 | TVL | Region XI | Davao Oriental | 304308 | Pantuyan NHS | CARAGA | 1 | 1 | 4 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 18645916.09 |  |  | Completed | 1 | [8 empty] | 2018-01-09 | RC TROCIO BUILDERS
NC 2017 | TVL | Region XI | Davao Oriental | 304333 | San Luis NHS | CARAGA | 1 | 1 | 4 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 18489684.77 |  |  | Completed | 1 | [8 empty] | 2018-01-09 | RC TROCIO BUILDERS
NC 2017 | TVL | Region XI | Davao Oriental | 304334 | Sangab National High School | CARAGA | 1 | 1 | 4 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 20904598.6 |  |  | Completed | 1 | [8 empty] | 2018-01-11 | MARK ANTHONY CONST & SUPPLY
NC 2017 | TVL | Region XI | Davao Oriental | 304335 | Santiago National High School | CARAGA | 1 | 1 | 4 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 18392669.02 |  |  | Completed | 1 | [8 empty] | 2018-06-07 | RC TROCIO BUILDERS
NC 2017 | TVL | Region XI | Davao Oriental | 304309 | Cateel Nat'l. Agri. HS | CATEEL | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3012357.36 |  |  | Completed | 1 | [8 empty] | 2017-01-11 | RC TROCIO BUILDERS
NC 2017 | TVL | Region XI | Davao Oriental | 304309 | Cateel Nat'l. Agri. HS | CATEEL | 1 |  | 4 | 2STY REGULAR WORKSHOP (7X18) | BATCH 10 | 18656981.51 |  |  | Completed | 1 | [8 empty] | 2017-12-27 | RC TROCIO BUILDERS
NC 2017 | TVL | Region XI | Davao Oriental | 304311 | Cateel Vocational High School | CATEEL | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3012357.36 |  |  | Completed | 1 | [8 empty] | 2018-01-11 | RR SIESMUNDO CONST. & SUPPLY
NC 2017 | TVL | Region XI | Davao Oriental | 304311 | Cateel Vocational High School | CATEEL | 1 |  | 4 | 2STY REGULAR WORKSHOP (7X18) | BATCH 10 | 18402596.24 |  |  | Completed | 1 | [8 empty] | 2018-01-09 | MARK ANTHONY CONST. & SUPPLY
NC 2017 | TVL | Region XI | Davao Oriental | 304311 | Cateel Vocational High School | CATEEL | 1 |  | 4 | 2STY REGULAR WORKSHOP (7X18) | BATCH 10 | 18656981.51 |  |  | Completed | 1 | [8 empty] | 2018-01-09 | RC TROCIO BUILDERS
NC 2017 | TVL | Region XI | Davao Oriental | 304310 | San Antonio NHS | CATEEL | 1 | 1 | 4 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 18399651.94 |  |  | Completed | 1 | [8 empty] | 2018-01-20 | RR SIESMUNDO CONST. & SUPPLY
NC 2017 | TVL | Region XI | Davao Oriental | 316102 | Del Pilar NHS | MANAY | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3167785.15 |  |  | Completed | 1 | [8 empty] | 2018-11-11 | MRDG CONSTRUCTION SERVICES
NC 2017 | TVL | Region XI | Davao Oriental | 316102 | Del Pilar NHS | MANAY | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3167785.15 |  |  | Completed | 1 | [8 empty] | 2018-11-11 | MRDG CONSTRUCTION SERVICES
NC 2017 | TVL | Region XI | Davao Oriental | 316102 | Del Pilar NHS | MANAY | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3357241.85 |  |  | Completed | 1 | [8 empty] | 2018-11-11 | MRDG CONSTRUCTION SERVICES
NC 2017 | TVL | Region XI | Davao Oriental | 316102 | Del Pilar NHS | MANAY | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3357241.85 |  |  | Completed | 1 | [8 empty] | 2018-11-11 | MRDG CONSTRUCTION SERVICES
NC 2017 | TVL | Region XI | Davao Oriental | 304315 | Evaristo Moralizon National Vocational High School | MANAY | 1 | 1 | 4 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 18435179.21 |  |  | Completed | 1 | [8 empty] | 2018-01-09 | RC TROCIO BUILDERS
NC 2017 | TVL | Region XI | Davao Oriental | 304315 | Evaristo Moralizon National Vocational High School | MANAY | 1 |  | 4 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 18340189.77 |  |  | Completed | 1 | [8 empty] | 2018-01-09 | RC TROCIO BUILDERS
NC 2017 | K10 | Region XI | Davao Oriental | 129369 | Jose Antop, Sr. ES | MANAY | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 12738595.77 |  |  | Completed | 1 | [8 empty] | 2018-01-09 | MRDG CONSTRUCTION SERVICES
NC 2017 | TVL | Region XI | Davao Oriental | 304324 | Manay National High School | MANAY | 1 | 1 | 4 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 18340189.77 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Digos City | 341513 | SHS in Digos City | CITY OF DIGOS (Capital) | 1 | 1 | 12 | 3STY12CL (6 REGULAR WORKSHOP BLDG.) | BATCH 10 | 32159267.25 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Island Garden City of Samal | 128598 | Angel Villarica Central Elementary School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 5 | 1STY5CL | BATCH 10 | 6508242 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Island Garden City of Samal | 128683 | Anonang ES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3965160 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304216 | Anonang National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 2STY4CL SCIENCE LAB. | BATCH 10 | 9599375.19 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304216 | Anonang National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 10 | 9599375.19 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304216 | Anonang National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 2 | REGULAR WORKSHOP BLDG. | BATCH 10 | 5638882.17 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 323411 | Anonang National High School-San Jose Extension | ISLAND GARDEN CITY OF SAMAL | 2 |  | 2 | 2STY4CL SCIENCE LAB. | BATCH 10 | 9686746.68 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 323411 | Anonang National High School-San Jose Extension | ISLAND GARDEN CITY OF SAMAL | 2 |  | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 10 | 9686746.68 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 323411 | Anonang National High School-San Jose Extension | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 3 | REGULAR WORKSHOP BLDG. | BATCH 10 | 8828038.51 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304220 | Balet National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 2STY4CL SCIENCE LAB. | BATCH 10 | 9688058.17 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304220 | Balet National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 10 | 9688058.17 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304220 | Balet National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3341250 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304220 | Balet National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 1 | REGULAR WORKSHOP BLDG. | BATCH 10 | 2985489.95 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Island Garden City of Samal | 323407 | Bandera National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 10 | 2STY10CL | BATCH 10 | 21069536.81 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Island Garden City of Samal | 323407 | Bandera National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 6 | 2STY6CL | BATCH 10 | 12818175.78 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 323407 | Bandera National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 2 | 2STY4CL SCIENCE LAB. | BATCH 10 | 9631538.01 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 323407 | Bandera National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 10 | 9631538.01 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 323407 | Bandera National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 4 | REGULAR WORKSHOP BLDG. | BATCH 10 | 12380418.26 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304223 | Cogon National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 3 | REGULAR WORKSHOP BLDG. | BATCH 10 | 8489807.68 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 323402 | Del Monte National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 2STY4CL SCIENCE LAB. | BATCH 10 | 9565603.37 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 323402 | Del Monte National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 10 | 9565603.37 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 323402 | Del Monte National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 3 | REGULAR WORKSHOP BLDG. | BATCH 10 | 8388546.82 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 323406 | Diosdado Alorro Sr. National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 2STY4CL SCIENCE LAB. | BATCH 10 | 9654825.91 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 323406 | Diosdado Alorro Sr. National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 10 | 9654825.91 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Island Garden City of Samal | 323406 | Diosdado Alorro Sr. National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 4 | 2STY4CL | BATCH 10 | 9654825.91 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 323406 | Diosdado Alorro Sr. National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 2 | REGULAR WORKSHOP BLDG. | BATCH 10 | 5724084.75 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304227 | Don Esteban Dasalla National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 2STY4CL SCIENCE LAB. | BATCH 10 | 9736584.57 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304227 | Don Esteban Dasalla National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 10 | 9678858.42 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304227 | Don Esteban Dasalla National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 2 | REGULAR WORKSHOP BLDG. | BATCH 10 | 5227950 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304236 | Kaputian National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 2STY4CL SCIENCE LAB. | BATCH 10 | 9609061.89 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304236 | Kaputian National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 10 | 9609061.89 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304236 | Kaputian National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 3 | REGULAR WORKSHOP BLDG. | BATCH 10 | 8512935.37 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 323409 | Libertad National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 2STY4CL SCIENCE LAB. | BATCH 10 | 9739704.3 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 323409 | Libertad National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 10 | 9744137.22 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 323409 | Libertad National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 3 | REGULAR WORKSHOP BLDG. | BATCH 10 | 9173339.98 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304247 | Matanos National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 2STY4CL SCIENCE LAB. | BATCH 10 | 9660828.54 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304247 | Matanos National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 10 | 9749762.34 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304247 | Matanos National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 4 | REGULAR WORKSHOP BLDG. | BATCH 10 | 11381503.92 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 323403 | Nieves Villarica National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 2STY4CL SCIENCE LAB. | BATCH 10 | 9503139.75 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 323403 | Nieves Villarica National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 10 | 9503139.75 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 323403 | Nieves Villarica National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 7 | REGULAR WORKSHOP BLDG. | BATCH 10 | 19657352.23 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Island Garden City of Samal | 341526 | SHS w/in Penaplata Central ES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 6 | 2STY6CL | BATCH 10 | 12635909.09 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 341526 | SHS w/in Penaplata Central ES | ISLAND GARDEN CITY OF SAMAL | 2 |  | 2 | 2STY4CL SCIENCE LAB. | BATCH 10 | 9598178.45 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 341526 | SHS w/in Penaplata Central ES | ISLAND GARDEN CITY OF SAMAL | 2 |  | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 10 | 9598178.45 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 341526 | SHS w/in Penaplata Central ES | ISLAND GARDEN CITY OF SAMAL | 2 |  | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 9944710.31 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 341526 | SHS w/in Penaplata Central ES | ISLAND GARDEN CITY OF SAMAL | 2 |  | 4 | REGULAR WORKSHOP BLDG. | BATCH 10 | 11209631.7 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Island Garden City of Samal | 304253 | Sta. Cruz National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 9877081.82 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304253 | Sta. Cruz National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 2 | 2STY4CL SCIENCE LAB. | BATCH 10 | 9877081.82 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304253 | Sta. Cruz National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 10 | 9877081.82 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304253 | Sta. Cruz National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 3 | REGULAR WORKSHOP BLDG. | BATCH 10 | 8736823.14 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304259 | Tagbitan-Ag National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 2STY4CL SCIENCE LAB. | BATCH 10 | 9633047.5 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304259 | Tagbitan-Ag National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 10 | 9633047.5 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304259 | Tagbitan-Ag National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 1 | REGULAR WORKSHOP BLDG. | BATCH 10 | 2984558.77 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Mati City | 129177 | Banaybanay Central Elementary School | BANAYBANAY | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 9545228.19 |  |  | Completed | 1 |  |  |  | 17LG0124 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | LLM Unified Builders & Trading Corp.
NC 2017 | TVL | Region XI | Mati City | 316107 | Leandro G. Japos NHS | BANAYBANAY | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9587382.6 |  |  | Completed | 1 |  |  |  | 17LG0186 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Rely Construction & Supply
NC 2017 | TVL | Region XI | Mati City | 316107 | Leandro G. Japos NHS | BANAYBANAY | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9528251.09 |  |  | Completed | 1 |  |  | s | 17LG0187 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Rely Construction & Supply
NC 2017 | TVL | Region XI | Mati City | 304301 | Manuel B. Guiñez Sr. NHS | BANAYBANAY | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9681309.64 |  |  | Completed | 1 |  |  |  | 17LG0133 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | LLM Unified Builders & Trading Corp.
NC 2017 | TVL | Region XI | Mati City | 304301 | Manuel B. Guiñez Sr. NHS | BANAYBANAY | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9622178.13 |  |  | Completed | 1 |  |  |  | 17LG0134 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | LLM Unified Builders & Trading Corp.
NC 2017 | TVL | Region XI | Mati City | 316105 | Paniquian NHS | BANAYBANAY | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9587382.6 |  |  | Completed | 1 |  |  |  | 17LG0184 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Rely Construction & Supply
NC 2017 | TVL | Region XI | Mati City | 316105 | Paniquian NHS | BANAYBANAY | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9528251.09 |  |  | Completed | 1 |  |  |  | 17LG0185 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Rely Construction & Supply
NC 2017 | TVL | Region XI | Mati City | 304331 | Puntalinao NHS | BANAYBANAY | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9601195.39 |  |  | Completed | 1 |  |  |  | 17LG0173 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | R. Semilla Const. & Marketing
NC 2017 | TVL | Region XI | Mati City | 304331 | Puntalinao NHS | BANAYBANAY | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9542063.89 |  |  | Completed | 1 |  |  |  | 17LG0174 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Agong Builders & Const. Supply, Inc.
NC 2017 | TVL | Region XI | Mati City | 325104 | Badas NHS | CITY OF MATI (Capital) | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9587382.59 |  |  | Completed | 1 |  |  |  | 17LG0190 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 325104 | Badas NHS | CITY OF MATI (Capital) | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9528251.09 |  |  | Completed | 1 |  |  |  | 17LG0191 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 304303 | Bobon NHS | CITY OF MATI (Capital) | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9601195.39 |  |  | Completed | 1 |  |  |  | 17LG0136 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 304303 | Bobon NHS | CITY OF MATI (Capital) | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9542063.89 |  |  | Completed | 1 |  |  |  | 17LG0137 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 304305 | Buso National HS | CITY OF MATI (Capital) | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9601195.39 |  |  | Completed | 1 |  |  |  | 17LG0138 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 304305 | Buso National HS | CITY OF MATI (Capital) | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9542063.89 |  |  | Completed | 1 |  |  |  | 17LG0139 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 304328 | Davao Oriental Regional Science High School | CITY OF MATI (Capital) | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9587382.59 |  |  | Completed | 1 |  |  |  | 17LG0166 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | FFJJ Construction
NC 2017 | TVL | Region XI | Mati City | 304328 | Davao Oriental Regional Science High School | CITY OF MATI (Capital) | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9528251.09 |  |  | Completed | 1 |  |  |  | 17LG0167 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | FFJJ Construction
NC 2017 | TVL | Region XI | Mati City | 304314 | Don Enrique Lopez NHS | CITY OF MATI (Capital) | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9601195.39 |  |  | Completed | 1 |  |  |  | 17LG0142 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | FFJJ Construction
NC 2017 | TVL | Region XI | Mati City | 304314 | Don Enrique Lopez NHS | CITY OF MATI (Capital) | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9542063.89 |  |  | Completed | 1 |  |  |  | 17LG0143 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | FFJJ Construction
NC 2017 | K10 | Region XI | Mati City | 129396 | Don Salvador Lopez ES | CITY OF MATI (Capital) | 2 | 1 | 8 | 2STY8CL | BATCH 10 | 17643924.56 |  |  | Completed | 1 |  |  |  | 17LG0130 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | FFJJ Construction
NC 2017 | TVL | Region XI | Mati City | 316104 | Don Salvador Lopez NHS | CITY OF MATI (Capital) | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9601195.39 |  |  | Completed | 1 |  |  |  | 17LG0182 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Rhodwill Parts & Hardware & Construction Services
NC 2017 | TVL | Region XI | Mati City | 316104 | Don Salvador Lopez NHS | CITY OF MATI (Capital) | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9542063.89 |  |  | Completed | 1 |  |  |  | 17LG0183 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Rhodwill Parts & Hardware & Construction Services
NC 2017 | TVL | Region XI | Mati City | 325102 | Lawigan National HS | CITY OF MATI (Capital) | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9631583.56 |  |  | Completed | 1 |  |  |  | 17LG0188 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Jecel Construction Supply
NC 2017 | TVL | Region XI | Mati City | 325102 | Lawigan National HS | CITY OF MATI (Capital) | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9572452.05 |  |  | Completed | 1 |  |  |  | 17LG0189 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Jecel Construction Supply
NC 2017 | TVL | Region XI | Mati City | 304318 | Libudon NHS | CITY OF MATI (Capital) | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9631583.56 |  |  | Completed | 1 |  |  |  | 17LG0144 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 304318 | Libudon NHS | CITY OF MATI (Capital) | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9572452.05 |  |  | Completed | 1 |  |  |  | 17LG0145 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Legacy Construction Corp.
NC 2017 | K10 | Region XI | Mati City | 129379 | Licop ES | CITY OF MATI (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 10 | 12738537.93 |  |  | Completed | 1 |  |  |  | 17LG0127 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 304325 | Mati Nat'l. Comp. HS | CITY OF MATI (Capital) | 2 | 1 | 8 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 37919123.49 |  |  | Completed | 1 |  |  |  | 17LG0158 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Lotrim Construction, Inc.
NC 2017 | TVL | Region XI | Mati City | 304325 | Mati Nat'l. Comp. HS | CITY OF MATI (Capital) | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9681309.64 |  |  | Completed | 1 |  |  |  | 17LG0159 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 304325 | Mati Nat'l. Comp. HS | CITY OF MATI (Capital) | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9622178.13 |  |  | Completed | 1 |  |  |  | 17LG0160 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 304326 | Mati SAT | City of Mati (Capital) | 2 | 1 | 8 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 37919123.49 |  |  | Completed | 1 |  |  |  | 17LG0161 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Lotrim Construction, Inc.
NC 2017 | TVL | Region XI | Mati City | 304326 | Mati SAT | City of Mati (Capital) | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9681309.64 |  |  | Completed | 1 |  |  |  | 17LG0162 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Rely Construction & Supply
NC 2017 | TVL | Region XI | Mati City | 304326 | Mati SAT | City of Mati (Capital) | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9622178.13 |  |  | Completed | 1 |  |  |  | 17LG0163 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Rely Construction & Supply
NC 2017 | K10 | Region XI | Mati City | 129400 | Matiao Central ES | CITY OF MATI (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 10 | 12683827.01 |  |  | Completed | 1 |  |  |  | 17LG0131 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 304327 | Matiao NHS | City of Mati (Capital) | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9681309.64 |  |  | Completed | 1 |  |  |  | 17LG0164 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Rely Construction & Supply
NC 2017 | TVL | Region XI | Mati City | 304327 | Matiao NHS | City of Mati (Capital) | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9622178.13 |  |  | Completed | 1 |  |  |  | 17LG0165 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Rely Construction & Supply
NC 2017 | TVL | Region XI | Mati City | 325106 | Mayo NHS | City of Mati (Capital) | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9555876.69 |  |  | Completed | 1 |  |  |  | 17LG0192 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Legacy Construction Corp.
NC 2017 | K10 | Region XI | Mati City | 129382 | Mayor Luisito G. Rabat MS | CITY OF MATI (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 10 | 12572694.48 |  |  | Completed | 1 |  |  |  | 17LG0128 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-15 | 2017-12-29 | RC Trocio Builders
NC 2017 | K10 | Region XI | Mati City | 129382 | Mayor Luisito G. Rabat MS | CITY OF MATI (Capital) | 2 |  | 8 | 2STY8CL | BATCH 10 | 17527897.04 |  |  | Completed | 1 |  |  |  | 17LG0129 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-15 | 2017-12-29 | RC Trocio Builders
NC 2017 | TVL | Region XI | Mati City | 304338 | Taguibo Agri. Voc. High School | City of Mati (Capital) | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9615008.2 |  |  | Completed | 1 |  |  |  | 17LG0180 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 304338 | Taguibo Agri. Voc. High School | City of Mati (Capital) | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9555876.69 |  |  | Completed | 1 |  |  |  | 17LG0181 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Legacy Construction Corp.
NC 2017 | K10 | Region XI | Mati City | 129409 | Vicente Almario Sr. MS | CITY OF MATI (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 9586018.4 |  |  | Completed | 1 |  |  |  | 17LG0132 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | FFJJ Construction
NC 2017 | K10 | Region XI | Mati City | 129293 | Luzon CES | GOVERNOR GENEROSO | 2 | 1 | 8 | 2STY8CL | BATCH 10 | 17649449.68 |  |  | Completed | 1 |  |  |  | 17LG0125 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | FFJJ Construction
NC 2017 | TVL | Region XI | Mati City | 304322 | Luzon NHS | GOVERNOR GENEROSO | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9615008.2 |  |  | Completed | 1 |  |  |  | 17LG0153 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | FFJJ Construction
NC 2017 | TVL | Region XI | Mati City | 304322 | Luzon NHS | GOVERNOR GENEROSO | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9555876.69 |  |  | Completed | 1 |  |  |  | 17LG0154 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | FFJJ Construction
NC 2017 | TVL | Region XI | Mati City | 304329 | Nangan NHS | GOVERNOR GENEROSO | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9642633.8 |  |  | Completed | 1 |  |  |  | 17LG0168 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Rtiztok Constrcution & Supply
NC 2017 | TVL | Region XI | Mati City | 304329 | Nangan NHS | GOVERNOR GENEROSO | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9583502.29 |  |  | Completed | 1 |  |  |  | 17LG0169 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Rtiztok Constrcution & Supply
NC 2017 | TVL | Region XI | Mati City | 304330 | Pundaguitan NHS | GOVERNOR GENEROSO | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9587520.72 |  |  | Completed | 1 |  |  |  | 17LG0170 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Rely Construction & Supply
NC 2017 | TVL | Region XI | Mati City | 304330 | Pundaguitan NHS | GOVERNOR GENEROSO | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9667496.84 |  |  | Completed | 1 |  |  |  | 17LG0171 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Rely Construction & Supply
NC 2017 | TVL | Region XI | Mati City | 304330 | Pundaguitan NHS | GOVERNOR GENEROSO | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9608365.33 |  |  | Completed | 1 |  |  |  | 17LG0172 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Rely Construction & Supply
NC 2017 | TVL | Region XI | Mati City | 304336 | Sigaboy Agri. Voc. HS | GOVERNOR GENEROSO | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9587382.59 |  |  | Completed | 1 |  |  |  | 17LG0175 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | R. Semilla Const. & Marketing
NC 2017 | TVL | Region XI | Mati City | 304336 | Sigaboy Agri. Voc. HS | GOVERNOR GENEROSO | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9528251.09 |  |  | Completed | 1 |  |  |  | 17LG0176 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Agong Builders & Const. Supply, Inc.
NC 2017 | TVL | Region XI | Mati City | 304320 | Bagumbayan Agro-Ind. HS | LUPON | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9521219.28 |  |  | Completed | 1 |  |  |  | 17LG0148 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Rely Construction & Supply
NC 2017 | TVL | Region XI | Mati City | 304320 | Bagumbayan Agro-Ind. HS | LUPON | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9601195.39 |  |  | Completed | 1 |  |  |  | 17LG0149 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Rely Construction & Supply
NC 2017 | TVL | Region XI | Mati City | 304320 | Bagumbayan Agro-Ind. HS | LUPON | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9542063.89 |  |  | Completed | 1 |  |  |  | 17LG0150 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Two Degrees Construction and Supply
NC 2017 | TVL | Region XI | Mati City | 304306 | Calapagan NHS | LUPON | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9601195.39 |  |  | Completed | 1 |  |  |  | 17LG0140 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | FFJJ Construction
NC 2017 | TVL | Region XI | Mati City | 304306 | Calapagan NHS | LUPON | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9542063.89 |  |  | Completed | 1 |  |  |  | 17LG0141 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | FFJJ Construction
NC 2017 | K10 | Region XI | Mati City | 129329 | Comara T. Manuel CES I | LUPON | 2 | 1 | 10 | 2STY10CL | BATCH 10 | 20224365.02 |  |  | Completed | 1 |  |  |  | 17LG0126 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | FFJJ Construction
NC 2017 | TVL | Region XI | Mati City | 304321 | Lupon NCHS | LUPON | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9587382.59 |  |  | Completed | 1 |  |  |  | 17LG0151 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Legacy Construction Corp.
NC 2017 | TVL | Region XI | Mati City | 304321 | Lupon NCHS | LUPON | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9528251.09 |  |  | Completed | 1 |  |  |  | 17LG0152 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Jecel Construction Supply
NC 2017 | TVL | Region XI | Mati City | 304319 | Lupon Voc. HS | LUPON | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9681309.64 |  |  | Completed | 1 |  |  |  | 17LG0146 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Agong Builders & Const. Supply, Inc.
NC 2017 | TVL | Region XI | Mati City | 304319 | Lupon Voc. HS | LUPON | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9622178.13 |  |  | Completed | 1 |  |  |  | 17LG0147 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | R. Semilla Const. & Marketing
NC 2017 | TVL | Region XI | Mati City | 304323 | Macangao Agri. VHS | LUPON | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9514312.88 |  |  | Completed | 1 |  |  |  | 17LG0155 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Newcon Builders Construction & Supply, Inc.
NC 2017 | TVL | Region XI | Mati City | 304323 | Macangao Agri. VHS | LUPON | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9594288.99 |  |  | Completed | 1 |  |  |  | 17LG0156 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Newcon Builders Construction & Supply, Inc.
NC 2017 | TVL | Region XI | Mati City | 304323 | Macangao Agri. VHS | LUPON | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9535157.49 |  |  | Completed | 1 |  |  |  | 17LG0157 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Newcon Builders Construction & Supply, Inc.
NC 2017 | TVL | Region XI | Mati City | 304337 | Tagugpo NHS | LUPON | 2 | 1 | 4 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 19125315.35 |  |  | Completed | 1 |  |  |  | 17LG0177 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | FFJJ Construction
NC 2017 | TVL | Region XI | Mati City | 304337 | Tagugpo NHS | LUPON | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9601195.39 |  |  | Completed | 1 |  |  |  | 17LG0178 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | FFJJ Construction
NC 2017 | TVL | Region XI | Mati City | 304337 | Tagugpo NHS | LUPON | 2 |  | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9542063.89 |  |  | Completed | 1 |  |  |  | 17LG0179 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | FFJJ Construction
NC 2017 | TVL | Region XI | Mati City | 304302 | Bitaogan NHS | SAN ISIDRO | 2 | 1 | 2 | 2STY WORKSHOP BLDG. (7X18) | BATCH 10 | 9514312.88 |  |  | Completed | 1 |  |  |  | 17LG0135 | 2017-11-17 | 2017-11-24 | 2017-12-07 | 2017-12-22 | 2017-12-29 | Agong Builders & Const. Supply, Inc.
NC 2017 | TVL | Region XI | Davao City | 304345 | Bernardo D. Carpio National High School | DAVAO CITY | 2 | 1 | 1 | 1STY1CL | BATCH 12 | 4020000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304373 | Los Amigos NHS | DAVAO CITY | 3 | 1 | 2 | TVL UNIQUE WORKSHOP BLDG. | BATCH 12 | 6650000 |  |  | Completed | 1 |  |  |  | 17LH0214 | 2017-11-14 |  | 2017-12-12 |  | 2018-02-15
NC 2017 | TVL | Region XI | Davao City | 304379 | Malabog Nationa High School | DAVAO CITY | 2 | 1 | 2 | 2STY2CL | BATCH 12 | 18197200 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Davao del Norte | 304221 | Antonio V. Fruto Sr. NHS | BRAULIO E. DUJALI | 2 | 1 | 4 | 2STY4CL | BATCH 12 | 9074071 |  |  | Completed | 1 |  |  | P00182250MN-CW1 | 17LC0430 |  | 2017-11-23 | 2017-12-14 | 2017-12-22 | 2017-12-28 | D.B Ravelo Construction and Supply
NC 2017 | SHS | Region XI | Davao del Norte | 304221 | Antonio V. Fruto Sr. NHS | BRAULIO E. DUJALI | 2 |  | 4 | 2STY4CL | BATCH 12 | 9074071 |  |  | Completed | 1 |  |  | P00182251MN-CW1 | 17LC0431 | 2017-11-16 | 2017-11-23 | 2017-12-14 | 2017-12-22 | 2017-12-28 | D.B Ravelo Construction and Supply
NC 2017 | SHS | Region XI | Davao del Norte | 304229 | Dujali National High School | BRAULIO E. DUJALI | 2 | 1 | 4 | 2STY4CL | BATCH 12 | 9020901.76 |  |  | Completed | 1 |  |  | P00182255MN-CW1 | 17LC0381 | 2017-11-16 | 2017-11-23 | 2017-12-14 | 2017-12-22 | 2017-12-27 | Micah Construction & Supply
NC 2017 | SHS | Region XI | Davao del Norte | 304229 | Dujali National High School | BRAULIO E. DUJALI | 2 |  | 4 | 2STY4CL | BATCH 12 | 9020901.76 |  |  | Completed | 1 |  |  | P00182254MN-CW1 | 17LC0382 | 2017-11-16 | 2017-11-23 | 2017-12-14 | 2017-12-20 | 2017-12-27 | Micah Construction & Supply
NC 2017 | SHS | Region XI | Davao del Norte | 304230 | Tanglaw NHS | BRAULIO E. DUJALI | 2 | 1 | 4 | 2STY4CL | BATCH 12 | 9188479 |  |  | Completed | 1 |  |  | P00182256MN-CW1 | 17LC0417 | 2017-11-16 | 2017-11-23 | 2017-12-14 | 2017-12-22 | 2017-12-28 | LLM Unified Builders and Trading Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304230 | Tanglaw NHS | BRAULIO E. DUJALI | 2 |  | 4 | 2STY4CL | BATCH 12 | 9188479 |  |  | Completed | 1 |  |  | P00182257MN-CW1 | 17LC0418 | 2017-11-16 | 2017-11-23 | 2017-12-14 | 2017-12-22 | 2017-12-28 | Five Massive Infra & Supply Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304222 | Carmen NHS | CARMEN | 2 | 1 | 4 | 2STY4CL | BATCH 12 | 9628622 |  |  | Completed | 1 |  |  | P00182252MN-CW1 | 17LC0438 | 2017-11-16 | 2017-11-23 | 2017-12-11 | 2017-12-15 | 2017-12-18 | LLM Unified Builders and Trading Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304222 | Carmen NHS | CARMEN | 2 |  | 4 | 2STY4CL | BATCH 12 | 9805402 |  |  | Completed | 1 |  |  | P00182253MN-CW1 | 17LC0439 | 2017-11-16 | 2017-11-23 | 2017-12-14 | 2017-12-21 | 2017-12-14 | LLM Unified Builders and Trading Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304244 | MABUHAY NATIONAL HIGH SCHOOL | CARMEN | 2 | 1 | 4 | 2STY4CL | BATCH 12 | 9141301.68 |  |  | Completed | 1 |  |  | P00182258MN-CW1 | 17LC0450 | 2017-11-16 | 2017-11-23 | 2017-12-11 | 2017-12-15 | 2017-12-18 | LLM Unified Builders and Trading Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304244 | MABUHAY NATIONAL HIGH SCHOOL | CARMEN | 2 |  | 4 | 2STY4CL | BATCH 12 | 9278890 |  |  | Completed | 1 |  |  | P00182259MN-CW1 | 17LC0436 | 2017-11-16 | 2017-11-23 | 2017-12-11 | 2017-12-15 | 2017-12-18 | Mag Corporation
NC 2017 | SHS | Region XI | Davao del Norte | 304244 | MABUHAY NATIONAL HIGH SCHOOL | CARMEN | 2 |  | 4 | 2STY4CL | BATCH 12 | 9125461 |  |  | Completed | 1 |  |  | P00182260MN-CW1 | 17LC0437 | 2017-11-16 | 2017-11-23 | 2017-12-14 | 2017-12-21 | 2017-12-27 | Mag Corporation
NC 2017 | SHS | Region XI | Davao del Norte | 315901 | Tubod National High School | CARMEN | 2 | 1 | 4 | 2STY4CL | BATCH 12 | 9143089 |  |  | Completed | 1 |  |  | P00182261MN-CW1 | 17LC0441 | 2017-11-16 | 2017-11-23 | 2017-12-14 | 2017-12-21 | 2017-12-27 | Mag Corporation
NC 2017 | K10 | Region XI | Davao Occidental | 205028 | Kibatang ES | DON MARCELINO | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2989618 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Panabo City | 341574 | Panabo City Senior High School | CITY OF PANABO | 2 | 1 | 8 | 2STY8CL | BATCH 12 | 18934950 |  |  | Completed | 1 |  |  | P00182266MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27
NC 2017 | SHS | Region XI | Panabo City | 341574 | Panabo City Senior High School | CITY OF PANABO | 2 |  | 6 | 2STY6CL | BATCH 12 | 12013661.97 |  |  | Completed | 1 |  |  | P00182267MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27
NC 2017 | SHS | Region XI | Panabo City | 304408 | Panabo National High School | CITY OF PANABO | 2 | 1 | 32 | 2UNITS 4STY16CL | BATCH 12 | 80076449 |  |  | Completed | 1 |  |  | P00182264MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | Micah Construction & Supply
NC 2017 | SHS | Region XI | Panabo City | 304408 | Panabo National High School | CITY OF PANABO | 2 |  | 4 | 2STY4CL | BATCH 12 | 9211370.14 |  |  | Completed | 1 |  |  | P00182265MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | R. Semilla Construction & Marketing
NC 2017 | K10 | Region XI | Panabo City | 129785 | Rizal ES | CITY OF PANABO | 2 | 1 | 9 | 3STY9CL | BATCH 12 | 26886214.84 |  |  | Completed | 1 |  |  | P00182263MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | R.R. Seismundo Construction & Supply
NC 2017 | K10 | Region XI | Tagum City | 128768 | APOKON ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 12 | 3STY12CL | BATCH 12 | 32131208.23 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Tagum City | 128775 | COL. ROSALIO C. SALUDARES ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 12 | 15798399.5 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Tagum City | 128769 | LAURETA ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 12 | 15872179 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Tagum City | 128770 | MAGUGPO PILOT IMELDA ELEMENTARTY SCHOOL - SPED CENTER | CITY OF TAGUM (Capital) | 1 | 1 | 12 | 3STY12CL | BATCH 12 | 32283908.94 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Tagum City | 128784 | SUAYBAGUIO-RIÑA ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 12 | 16212810.25 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128266 | Mambusao ES | COMPOSTELA | 1 | 1 | 2 | 1STY2CL | BATCH 13 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128331 | Candinuyan ES | MABINI (DOÑA ALICIA) | 2 | 1 | 2 | 1STY2CL | BATCH 13 | 3283000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128339 | Panamin ES | MABINI (DOÑA ALICIA) | 2 | 1 | 2 | 1STY2CL | BATCH 13 | 3133000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128345 | Bucana ES | MACO | 2 | 1 | 2 | 1STY2CL | BATCH 13 | 3202000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128365 | Dumlan ES | MACO | 2 | 1 | 2 | 1STY2CL | BATCH 13 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128349 | Gubatan ES | MACO | 2 | 1 | 2 | 1STY2CL | BATCH 13 | 3108000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128351 | Kinuban ES | MACO | 2 | 1 | 2 | 1STY2CL | BATCH 13 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128371 | Mapaang ES | MACO | 2 | 1 | 2 | 1STY2CL | BATCH 13 | 3435000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128356 | New Barili ES | MACO | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 12005000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128401 | Tandik ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 2 | 1STY2CL | BATCH 13 | 3341500 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128410 | Lonolono ES | MAWAB | 2 | 1 | 4 | 1STY4CL | BATCH 13 | 6365000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128423 | Anagase Elementary School | MONKAYO | 1 | 1 | 2 | 1STY2CL | BATCH 13 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley |  | Depot NHS | MONKAYO | 1 | 1 | 6 | 2STY6CL | BATCH 13 | 13935500 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 315823 | New Kapatagan NHS | MONKAYO | 1 | 1 | 6 | 2STY6CL | BATCH 13 | 14035500 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128457 | Ulip ES | MONKAYO | 1 | 1 | 3 | 1STY3CL | BATCH 13 | 4309000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128458 | Alimadmad ES | MONTEVISTA | 1 | 1 | 2 | 1STY2CL | BATCH 13 | 3033000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128512 | Barabat ES | NEW BATAAN | 1 | 1 | 2 | 1STY2CL | BATCH 13 | 3433000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128524 | Pagsilaan ES | NEW BATAAN | 1 | 1 | 3 | 1STY3CL | BATCH 13 | 4999000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Compostela Valley | 128542 | Doroteo De Castro ES | PANTUKAN | 2 | 1 | 3 | 1STY3CL | BATCH 13 | 5000000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129476 | A. Pichon Jr. ES | DAVAO CITY | 2 | 1 | 9 | 3STY9CL | BATCH 13 | 26525492 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129504 | Acacia ES | DAVAO CITY | 2 | 1 | 9 | 3STY9CL | BATCH 13 | 26465492 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129712 | BAGO ELEMENTARY SCHOOL | DAVAO CITY | 1 | 1 | 9 | 3STY9CL | BATCH 13 | 26525492 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129684 | Batolusa ES | DAVAO CITY | 3 | 1 | 8 | 4STY8CL | BATCH 13 | 17209600 |  |  | Completed | 1 |  |  |  | 17LH0256 | 2017-11-21 |  | 2017-12-21 | 2018-01-18 | 2018-02-01
NC 2017 | SHS | Region XI | Davao City | 304345 | Bernardo D. Carpio National High School | DAVAO CITY | 2 | 1 | 24 | 4STY24CL (U-TYPE) | BATCH 13 | 53394596 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304345 | Bernardo D. Carpio National High School | DAVAO CITY | 2 |  | 5 | 4STY5CL | BATCH 13 | 18832336 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304345 | Bernardo D. Carpio National High School | DAVAO CITY | 2 |  | 4 | 4STY4CL | BATCH 13 | 18872336 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304347 | Biao NHS | DAVAO CITY | 3 | 1 | 9 | 3STY5CL STANDARD REGULAR WORKSHOP AND 4 STANDARD CL ICT AND SCIENCE LABORATORY | BATCH 13 | 35697856.63 |  |  | Completed | 1 |  |  |  | 17LH0228 | 2017-11-21 |  | 2017-12-19 | 2018-01-18 | 2018-02-01
NC 2017 | TVL | Region XI | Davao City | 304348 | Biao NHS - Talandang HS Annex | DAVAO CITY | 3 | 1 | 10 | 3STY6CL STANDARD REGULAR WORKSHOP & 4STY4CL ICT AND SCIENCE LABORATORY BLDG. | BATCH 13 | 40183100 |  |  | Completed | 1 |  |  |  | 17LH0229 | 2017-11-21 |  | 2017-12-19 | 2018-01-18 | 2018-02-01
NC 2017 | SHS | Region XI | Davao City | 304351 | Binugao NHS - Baracatan NHS | DAVAO CITY | 3 | 1 | 13 | 4STY7STANDARD CL REGULAR WORKSHOP AND 2REGULAR CL & 4STY4CL SCIENCE AND ICT LABORATORY | BATCH 13 | 49213738 |  |  | Completed | 1 |  |  |  | 17LH0230 | 2017-11-21 |  | 2017-12-19 | 2018-01-18 | 2018-02-01
NC 2017 | TVL | Region XI | Davao City | 304353 | Buda NHS | DAVAO CITY | 3 | 1 | 4 | 4STY4CL SCIENCE AND ICT LABORATORY | BATCH 13 | 33172727.05 |  |  | Completed | 1 |  |  |  | 17LH0231 | 2017-11-21 |  | 2017-12-19 | 2018-01-18 | 2018-02-01
NC 2017 | TVL | Region XI | Davao City | 304346 | Cabantian NHS | DAVAO CITY | 2 | 1 | 4 | 4STY4CL | BATCH 13 | 18832336 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Davao City | 304346 | Cabantian NHS | DAVAO CITY | 2 |  | 12 | 4STY12CL | BATCH 13 | 40063597 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304354 | Calinan NHS | DAVAO CITY | 3 | 1 | 8 | 4STY4CL REGULAR WORKSHOP & 4STY4CL FOR SCIENCE AND ICT LABORATORY | BATCH 13 | 32476775.79 |  |  | Completed | 1 |  |  |  | 17LH0232 | 2017-11-21 |  | 2017-12-19 | 2018-01-18 | 2018-02-01
NC 2017 | SHS | Region XI | Davao City | 316207 | Camansi National High School | DAVAO CITY | 3 | 1 | 13 | 4STY7CL REGULAR WORKSHOP AND 2 REGULAR CL & 4STY4CL SCIENCE AND ICT LABORATORY BLDG. | BATCH 13 | 53160136.58 |  |  | Completed | 1 |  |  |  | 17LH0254 | 2017-11-21 |  | 2017-12-21 | 2018-01-18 | 2018-02-01
NC 2017 | SHS | Region XI | Davao City | 316202 | Catalunan Pequeno National High School | DAVAO CITY | 1 | 1 | 15 | 4STY15CL | BATCH 13 | 54155299 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129478 | Cornelio C. Reta, Sr. ES | DAVAO CITY | 2 | 1 | 12 | 4STY12CL | BATCH 13 | 34561773 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304356 | CROSSING BAYABAS NHS | DAVAO CITY | 3 | 1 | 8 | 4STY4CL STANDARD REGULAR WORKSHOP AND 4STY4CL SCIENCE AND ICT LABORATORY | BATCH 13 | 48703703.16 |  |  | Completed | 1 |  |  |  | 17LH0252 | 2017-11-21 |  | 2017-12-20 | 2018-01-18 | 2018-02-05
NC 2017 | SHS | Region XI | Davao City | 304358 | Dacudao National High School | DAVAO CITY | 3 | 1 | 14 | 4STY6CL REGULAR WORKSHOP AND 4 REGULAR CL & 4STY4CL FOR SCIENCE AND ICT LABORATORY | BATCH 13 | 50405640 |  |  | Completed | 1 |  |  |  | 17LH0235 | 2017-11-21 |  | 2017-12-20 | 2018-01-18 | 2018-02-01
NC 2017 | TVL | Region XI | Davao City | 316206 | Don Enrique Bustamante NHS | DAVAO CITY | 3 | 1 | 10 | 3STY6CL REGULAR WORKSHOP & 4STY4CL ICT AND SCIENCE LABORATORY | BATCH 13 | 40585320 |  |  | Completed | 1 |  |  |  | 17LH0250 | 2017-11-21 |  | 2017-12-20 | 2018-01-18 | 2018-02-05
NC 2017 | SHS | Region XI | Davao City | 304361 | Dona Carmen Denia NHS | DAVAO CITY | 3 | 1 | 9 | 4STY3CL REGULAR WORKSHOP, 2 REGULAR CLASSROOM AND 4CL ICT AND SCIENCE LABORATORY | BATCH 13 | 32987000 |  |  | Completed | 1 |  |  |  | 17LH0236 | 2017-11-21 |  | 2017-12-20 | 2018-01-18 | 2018-02-05
NC 2017 | SHS | Region XI | Davao City | 304362 | Dona Carmen Denia NHS - J. V. Ferriols HS | DAVAO CITY | 3 |  | 20 | 4STY8STANDARD REGULAR WORKSHOP, 4STY4STANDARD CL FOR ICT AND SCIENCE LABORATORY AND 8 REGULAR CL | BATCH 13 | 66016065.65 |  |  | Completed | 1 |  |  |  | 17LH0237 | 2017-11-21 |  | 2017-12-20 | 2018-01-18 | 2018-02-05
NC 2017 | K10 | Region XI | Davao City |  | Dona Soledad Duterte HS | DAVAO CITY | 1 | 1 | 12 | 3STY12CL | BATCH 13 | 32708009 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304357 | E. B. Lopez Mem. NHS | DAVAO CITY | 3 | 1 | 10 | 3STY6STANDARD CL REGULAR WORKSHOP & 4STY4CL FOR SCIENCE AND ICT LABORATORY | BATCH 13 | 39752155.05 |  |  | Completed | 1 |  |  |  | 17LH0234 | 2017-11-21 |  | 2017-12-20 | 2018-01-18 | 2018-02-01
NC 2017 | TVL | Region XI | Davao City | 304344 | Elias P. Dacudao Gumalang School of Home Industries | DAVAO CITY | 3 | 1 | 4 | 4STY4CL ICT AND SCIENCE LABORATORY | BATCH 13 | 33734730.15 |  |  | Completed | 1 |  |  |  | 17LH0227 | 2017-11-21 |  | 2017-12-19 | 2018-01-18 | 2018-02-01
NC 2017 | TVL | Region XI | Davao City | 304383 | G.Astilla Sr. Cultural Minority HS - Marilog NHS Annex | DAVAO CITY | 3 | 1 | 4 | 4STY4CL ICT AND SCIENCE LABORATORY | BATCH 13 | 23688100 |  |  | Completed | 1 |  |  |  | 17LH0242 | 2017-11-21 |  | 2017-12-20 | 2018-01-18 | 2018-02-05
NC 2017 | TVL | Region XI | Davao City | 316212 | JOSE T. QUIBOLOY SR. NATIONAL HIGH SCHOOL | DAVAO CITY | 3 | 1 | 2 | 2UNITS 2STY2STANDARD SCIENCE AND ICT LABORATORY BLDG. | BATCH 13 | 17925500 |  |  | Completed | 1 |  |  |  | 17LH0253 | 2017-11-21 |  | 2017-12-19 | 2018-01-18 | 2018-02-05
NC 2017 | K10 | Region XI | Davao City | 129699 | Lapu Lapu ES | DAVAO CITY | 1 | 1 | 16 | 4STY16CL | BATCH 13 | 36955000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304373 | Los Amigos NHS | DAVAO CITY | 3 |  | 14 | 4STY6STANDARD CL REGULAR WORKSHOP, 4 STANDARD CL SCIENCE AND ICT LABORATORY AND 4 REGULAR CL | BATCH 13 | 82090050 |  |  | Completed | 1 |  |  |  | 17LH0239 | 2017-11-21 |  | 2017-12-20 | 2018-01-18 | 2018-02-01
NC 2017 | TVL | Region XI | Davao City | 304374 | Lower Tamugan NHS | DAVAO CITY | 3 | 1 | 13 | 3UNITS 3STY3STANDARD CL REGULAR WORKSHOP & 4STY4CL ICT AND SCIENCE LABORATORY | BATCH 13 | 53389133.56 |  |  | Completed | 1 |  |  |  | 17LH0240 | 2017-11-21 |  | 2017-12-19 | 2018-01-18 | 2018-02-05
NC 2017 | K10 | Region XI | Davao City | 129707 | M. Roxas ES | DAVAO CITY | 1 | 1 | 24 | 4STY24CL | BATCH 13 | 52374596 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304342 | Ma. Cristina P. Belcar Agricultural High School | DAVAO CITY | 3 | 1 | 8 | 4STY4STANDARD CL FOR REGULAR WORKSHOP & 4STY4CL FOR ICT AND SCIENCE LABORATORY | BATCH 13 | 26998000 |  |  | Completed | 1 |  |  |  | 17LH0226 | 2017-11-21 |  | 2017-12-19 | 2018-01-18 | 2018-02-05
NC 2017 | TVL | Region XI | Davao City | 304381 | Marilog High School of Agriculture (Tech-Voc School) | DAVAO CITY | 3 | 1 | 4 | 4STY4CL FOR THE SCIENCE AND ICT LABORATORY | BATCH 13 | 32922144.77 |  |  | Completed | 1 |  |  |  | 17LH0241 | 2017-11-21 |  | 2017-12-20 | 2018-01-18 | 2018-02-01
NC 2017 | TVL | Region XI | Davao City | 304384 | Marilog NHS - Marahan NHS | DAVAO CITY | 3 | 1 | 4 | 4STY4STANDARD CL FOR ICT AND SCIENCE LABORATORY | BATCH 13 | 21290628.31 |  |  | Completed | 1 |  |  |  | 17LH0243 | 2017-11-21 |  | 2017-12-20 | 2018-01-18 | 2018-02-01
NC 2017 | TVL | Region XI | Davao City | 304387 | Mintal NCHS - Tugbok National HS | DAVAO CITY | 3 | 1 | 10 | 4STY8STANDARD REGULAR WORKSHOP, 4CL FOR ICT AND SCIENCE LABORATORY | BATCH 13 | 48449800 |  |  | Completed | 1 |  |  |  | 17LH0245 | 2017-11-21 |  | 2017-12-20 | 2018-01-18 | 2018-02-05
NC 2017 | SHS | Region XI | Davao City | 304388 | Optaciano Hilay NHS | DAVAO CITY | 3 | 1 | 11 | 3STY5CL STANDARD REGULAR WORKSHOP AND 2 REGULAR CL & 4STY4CL FOR ICT AND SCIENCE LABORATORY | BATCH 13 | 40205706.29 |  |  | Completed | 1 |  |  |  | 17LH0246 | 2017-11-21 |  | 2017-12-20 | 2018-01-18 | 2018-02-01
NC 2017 | TVL | Region XI | Davao City | 316203 | Optaciano Hilay NHS - Mulig NHS Annex | DAVAO CITY | 3 | 1 | 10 | 2STY6STANDARD CL REGULAR WORKSHOP & 4STY4CL SCIENCE AND ICT LABORATORY | BATCH 13 | 40096921.67 |  |  | Completed | 1 |  |  |  | 17LH0249 | 2017-11-21 |  | 2017-12-20 | 2018-01-18 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129670 | Pandaitan ES | DAVAO CITY | 2 | 1 | 6 | 2STY6CL | BATCH 13 | 11866000 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304389 | Paquibato NHS | DAVAO CITY | 2 | 1 | 2 | 2STY2CL | BATCH 13 | 27340000 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Davao City | 304389 | Paquibato NHS | DAVAO CITY | 2 |  | 4 | 2STY4CL | BATCH 13 | 34150000 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129672 | Paradise Embac ES | DAVAO CITY | 2 | 1 | 9 | 3STY9CL | BATCH 13 | 26585492 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City | 129688 | Piedad Central ES | DAVAO CITY | 3 | 1 | 20 | 4STY20CL | BATCH 13 | 40785900 |  |  | Completed | 1 |  |  |  | 17LH0259 | 2017-11-21 |  | 2017-12-21 | 2018-01-18 | 2018-02-05
NC 2017 | K10 | Region XI | Davao City | 129688 | Piedad Central ES | DAVAO CITY | 3 |  | 20 | 4STY20CL | BATCH 13 | 40785900 |  |  | Completed | 1 |  |  |  | 17LH0260 | 2017-11-21 |  | 2017-12-21 | 2018-01-18 | 2018-02-05
NC 2017 | K10 | Region XI | Davao City | 129688 | Piedad Central ES | DAVAO CITY | 3 |  | 20 | 4STY20CL | BATCH 13 | 40785900 |  |  | Completed | 1 |  |  |  | 17LH0261 | 2017-11-21 |  | 2017-12-21 | 2018-01-18 | 2018-02-05
NC 2017 | K10 | Region XI | Davao City | 129722 | R.C. Quimpo ES | DAVAO CITY | 1 | 1 | 6 | 3STY6CL | BATCH 13 | 14888676 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304372 | Saloy National High School | DAVAO CITY | 3 | 1 | 4 | 4STY4CL SCIENCE AND ICT LABORATORY | BATCH 13 | 14161451.64 |  |  | Completed | 1 |  |  |  | 17LH0238 | 2017-11-21 |  | 2017-12-20 | 2018-01-18 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129578 | Siao ES | DAVAO CITY | 3 | 1 | 6 | 3STY6CL | BATCH 13 | 14339600 |  |  | Completed | 1 |  |  |  | 17LH0257 | 2017-11-21 |  | 2017-12-21 | 2018-01-18 | 2018-02-01
NC 2017 | TVL | Region XI | Davao City | 304398 | Sirawan NHS | DAVAO CITY | 3 | 1 | 4 | 4STY4CL SCIENCE AND ICT LABORATORY | BATCH 13 | 27134537.57 |  |  | Completed | 1 |  |  |  | 17LH0248 | 2017-11-21 |  | 2017-12-20 | 2018-01-18 | 2018-02-01
NC 2017 | SHS | Region XI | Davao City | 304392 | Sirib NHS | DAVAO CITY | 3 | 1 | 6 | 3STY6CL | BATCH 13 | 13927300 |  |  | Completed | 1 |  |  |  | 17LH0258 | 2017-11-21 |  | 2017-12-21 | 2018-01-18 | 2018-02-01
NC 2017 | TVL | Region XI | Davao City | 304392 | Sirib NHS | DAVAO CITY | 3 |  | 4 | 4STY4CL SCIENCE AND ICT LABORATORY | BATCH 13 | 14586131.13 |  |  | Completed | 1 |  |  |  | 17LH0247 | 2017-11-21 |  | 2017-12-20 | 2018-01-18 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129485 | Sixto Babao ES | DAVAO CITY | 2 | 1 | 20 | 4STY20CL (L-TYPE) | BATCH 13 | 44941083 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao City | 304386 | Sto. Niño National High School | DAVAO CITY | 3 | 1 | 10 | 3STY6STANDARD CL REGULAR WORKSHOP & 4STY4CL FOR SCIENCE AND ICT LABORATORY | BATCH 13 | 45446406.66 |  |  | Completed | 1 |  |  |  | 17LH0244 | 2017-11-21 |  | 2017-12-20 | 2018-01-18 | 2018-02-05
NC 2017 | K10 | Region XI | Davao City | 129519 | T. Awad Echevarria ES | DAVAO CITY | 2 | 1 | 20 | 4STY20CL | BATCH 13 | 44921083 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao City |  | Tacunan High School - Mintal Comprehensive High School Annex | DAVAO CITY | 3 | 1 | 16 | 4STY16CL | BATCH 13 | 37360800 |  |  | Completed | 1 |  |  |  | 17LH0212 | 2017-11-14 |  | 2017-12-19 |  | 2018-02-15
NC 2017 | TVL | Region XI | Davao City | 304394 | Tagakpan NHS | DAVAO CITY | 3 | 1 | 2 | 4STY4STANDARD REGULAR WORKSHOP AND 4STY4STANDARD SCIENCE AND ICT LABORATORY BLDG. | BATCH 13 | 33483089 |  |  | Completed | 1 |  |  |  | 17LH0255 | 2017-11-21 |  | 2017-12-21 | 2018-01-18 | 2018-02-01
NC 2017 | TVL | Region XI | Davao City |  | Tamugan NHS | DAVAO CITY | 3 | 1 | 8 | 4STY4STANDARD CL REGULAR WORKSHOP & 4STY4CL SCIENCE AND ICT LABORATORY | BATCH 13 | 20498571.25 |  |  | Completed | 1 |  |  |  | 17LH0251 | 2017-11-21 |  | 2017-12-20 | 2018-01-18 | 2018-02-01
NC 2017 | TVL | Region XI | Davao City | 304370 | Teofilo V. Fernandez NHS (Indangan NHS) | DAVAO CITY | 2 | 1 | 12 | 4STY12CL (L-TYPE) | BATCH 13 | 54235299 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Davao City | 304370 | Teofilo V. Fernandez NHS (Indangan NHS) | DAVAO CITY | 2 |  | 15 | 4STY15CL | BATCH 13 | 45108583 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Davao City | 304355 | Wangan National High School-Calinan NHS Annex | DAVAO CITY | 3 | 1 | 11 | 3STY5CL REGULAR WOKSHOP AND 2 REGULAR CL & 4STY4CL SCIENCE AND ICT LABORATORY | BATCH 13 | 40000760.4 |  |  | Completed | 1 |  |  |  | 17LH0233 | 2017-11-21 |  | 2017-12-19 | 2018-01-18 | 2018-02-01
NC 2017 | K10 | Region XI | Davao City | 129709 | Zonta ES | DAVAO CITY | 1 | 1 | 12 | 4STY12CL | BATCH 13 | 34381773 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Davao del Norte | 304217 | Asuncion National High School | ASUNCION (SAUG) | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 8945901.75 |  |  | Completed | 1 |  |  | P00183398MN-CW1 | 17LC0368 | 2017-11-16 | 2017-11-23 | 2017-12-14 | 2017-12-20 | 2017-12-27 | Micah Construction & Supply
NC 2017 | SHS | Region XI | Davao del Norte | 304217 | Asuncion National High School | ASUNCION (SAUG) | 1 |  | 4 | 2STY4CL | BATCH 13 | 8970901.76 |  |  | Completed | 1 |  |  | P00183399MN-CW1 | 17LC0369 | 2017-11-16 | 2017-11-23 | 2017-12-14 | 2017-12-20 | 2017-12-27 | Micah Construction & Supply
NC 2017 | SHS | Region XI | Davao del Norte | 304221 | Antonio V. Fruto Sr. NHS | BRAULIO E. DUJALI | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9164870.95 |  |  | Completed | 1 |  |  | P00183425MN-CW1 | 17LC0448 | 2017-11-16 | 2017-11-23 | 2017-12-11 | 2017-12-15 | 2017-12-18 | CJEP Builders & Engineering Services
NC 2017 | SHS | Region XI | Davao del Norte | 304230 | Tanglaw NHS | BRAULIO E. DUJALI | 2 | 1 | 6 | 2STY6CL | BATCH 13 | 12748467.26 |  |  | Completed | 1 |  |  | P00183426MN-CW1 | 17LC0449 | 2017-11-16 | 2017-11-23 | 2017-12-11 | 2017-12-15 | 2017-12-18 | Kanaway Builders Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304215 | Alejal National High School | CARMEN | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 8980205 |  |  | Completed | 1 |  |  | P00183424MN-CW1 | 17LC0433 | 2017-11-16 | 2017-11-23 | 2017-12-11 | 2017-12-15 | 2017-12-18 | LLM Unified Builders and Trading Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304215 | Alejal National High School | CARMEN | 2 |  | 4 | 2STY4CL | BATCH 13 | 8980205 |  |  | Completed | 1 |  |  | P00183423MN-CW1 | 17LC0432 | 2017-11-16 | 2017-11-23 | 2017-12-11 | 2017-12-15 | 2017-12-18 | LLM Unified Builders and Trading Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 315903 | Anibongan NHS | CARMEN | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9389308 |  |  | Completed | 1 |  |  | P00183437MN-CW1 | 17LC0434 | 2017-11-16 | 2017-11-23 | 2017-12-11 | 2017-12-15 | 2017-12-18 | Mag Corporation
NC 2017 | SHS | Region XI | Davao del Norte | 315903 | Anibongan NHS | CARMEN | 2 |  | 4 | 2STY4CL | BATCH 13 | 9389308 |  |  | Completed | 1 |  |  | P00183438MN-CW1 | 17LC0435 | 2017-11-16 | 2017-11-23 | 2017-12-11 | 2017-12-15 | 2017-12-18 | Mag Corporation
NC 2017 | SHS | Region XI | Davao del Norte | 315901 | Tubod National High School | CARMEN | 2 |  | 4 | 2STY4CL | BATCH 13 | 9143089 |  |  | Completed | 1 |  |  | P00183433MN-CW1 | 17LC0440 | 2017-11-16 | 2017-11-23 | 2017-12-11 | 2017-12-21 | 2017-12-27 | Mag Corporation
NC 2017 | SHS | Region XI | Davao del Norte | 341449 | Davao del Norte Regional Sports Academy | CITY OF TAGUM (Capital) | 2 | 1 | 10 | 2STY10CL | BATCH 13 | 20165477 |  |  | Completed | 1 |  |  | P00183439MN-CW1 | 17LC0446 | 2017-11-16 | 2017-11-23 | 2017-12-14 | 2017-12-21 | 2017-12-27 | Micah Construction & Supply
NC 2017 | SHS | Region XI | Davao del Norte | 304224 | Datu Balong NHS | KAPALONG | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9194861 |  |  | Completed | 1 |  |  | P00183400MN-CW1 | 17LC0404 | 2017-11-16 | 2017-11-23 | 2017-12-15 | 2017-12-21 | 2017-12-27 | South Iron Rock Corporation
NC 2017 | SHS | Region XI | Davao del Norte | 304224 | Datu Balong NHS | KAPALONG | 1 |  | 4 | 2STY4CL | BATCH 13 | 9194861 |  |  | Completed | 1 |  |  | P00183401MN-CW1 | 17LC0401 | 2017-11-16 | 2017-11-23 | 2017-12-15 | 2017-12-21 | 2017-12-27 | Five Massive Infra & Supply Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304228 | Doña Carmen Soriano National High School | KAPALONG | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9015901.76 |  |  | Completed | 1 |  |  | P00183402MN-CW1 | 17LC0407 | 2017-11-16 | 2017-11-23 | 2017-12-20 | 2017-12-22 | 2017-12-28 | CJEP Builders & Engineering Services
NC 2017 | SHS | Region XI | Davao del Norte | 304228 | Doña Carmen Soriano National High School | KAPALONG | 1 |  | 4 | 2STY4CL | BATCH 13 | 9015901.76 |  |  | Completed | 1 |  |  | P00183403MN-CW1 | 17LC0408 | 2017-11-16 | 2017-11-23 | 2017-12-20 | 2017-12-22 | 2017-12-28 | LLM Unified Builders and Trading Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304233 | Kapalong National High School | KAPALONG | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9161251 |  |  | Completed | 1 |  |  | P00183404MN-CW1 | 17LC0409 | 2017-11-16 | 2017-11-23 | 2017-12-20 | 2017-12-22 | 2017-12-28 | Micah Construction & Supply
NC 2017 | SHS | Region XI | Davao del Norte | 304233 | Kapalong National High School | KAPALONG | 1 |  | 4 | 2STY4CL | BATCH 13 | 9161251 |  |  | Completed | 1 |  |  | P00183405MN-CW1 | 17LC0410 | 2017-11-16 | 2017-11-23 | 2017-12-20 | 2017-12-22 | 2017-12-28 | Micah Construction & Supply
NC 2017 | SHS | Region XI | Davao del Norte | 304241 | Luna National High School | KAPALONG | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9020901.76 |  |  | Completed | 1 |  |  | P00183410MN-CW1 | 17LC0370 | 2017-11-16 | 2017-11-23 | 2017-12-14 | 2017-12-20 | 2017-12-27 | LLM Unified Builders and Trading Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304241 | Luna National High School | KAPALONG | 1 |  | 4 | 2STY4CL | BATCH 13 | 9020901.76 |  |  | Completed | 1 |  |  | P00183411MN-CW1 | 17LC0372 | 2017-11-16 | 2017-11-23 | 2017-12-14 | 2017-12-20 | 2017-12-27 | LLM Unified Builders and Trading Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304242 | Mabantao National High School | KAPALONG | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9207125 |  |  | Completed | 1 |  |  | P00183412MN-CW1 | 17LC0403 | 2017-11-16 | 2017-11-23 | 2017-12-15 | 2017-12-21 | 2017-12-27 | LLM Unified Builders and Trading Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304242 | Mabantao National High School | KAPALONG | 1 |  | 4 | 2STY4CL | BATCH 13 | 9227309 |  |  | Completed | 1 |  |  | P00183413MN-CW1 | 17LC0404 | 2017-11-16 | 2017-11-23 | 2017-12-15 | 2017-12-21 | 2017-12-27 | CJEP Builders & Engineering Services
NC 2017 | SHS | Region XI | Davao del Norte | 304243 | Semong National High School | KAPALONG | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 8996800 |  |  | Completed | 1 |  |  | P00183414MN-CW1 | 17LC0385 | 2017-11-16 | 2017-11-23 | 2017-12-14 | 2017-12-20 | 2017-12-27 | CJEP Builders & Engineering Services
NC 2017 | SHS | Region XI | Davao del Norte | 304243 | Semong National High School | KAPALONG | 1 |  | 4 | 2STY4CL | BATCH 13 | 8996800 |  |  | Completed | 1 |  |  | P00183415MN-CW1 | 17LC0386 | 2017-11-16 | 2017-11-23 | 2017-12-14 | 2017-12-20 | 2017-12-27 | CJEP Builders & Engineering Services
NC 2017 | SHS | Region XI | Davao del Norte | 304235 | Sua-on National High School | KAPALONG | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9415131 |  |  | Completed | 1 |  |  | P00183406MN-CW1 | 17LC0419 | 2017-11-16 | 2017-11-23 | 2017-12-20 | 2017-12-22 | 2017-12-28 | LLM Unified Builders and Trading Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304235 | Sua-on National High School | KAPALONG | 1 |  | 4 | 2STY4CL | BATCH 13 | 9415131 |  |  | Completed | 1 |  |  | P00183407MN-CW1 | 17LC0420 | 2017-11-16 | 2017-11-23 | 2017-12-20 | 2017-12-22 | 2017-12-28 | LLM Unified Builders and Trading Corp.
NC 2017 | K10 | Region XI | Davao del Norte | 128709 | Limbaan ES | NEW CORELLA | 1 | 1 | 10 | 2STY10CL | BATCH 13 | 21531729.75 |  |  | Completed | 1 |  |  | P00183393MN-CW1 | 17LC0454 | 2017-11-16 | 2017-11-23 | 2017-12-15 | 2017-12-22 | 2017-12-27 | FFJJ Construction
NC 2017 | SHS | Region XI | Davao del Norte | 304239 | Limbaan NHS | NEW CORELLA | 1 |  | 4 | 2STY4CL | BATCH 13 | 9609970 |  |  | Completed | 1 |  |  | P00183409MN-CW1 | 17LC0423 | 2017-11-16 | 2017-11-23 | 2017-12-20 | 2017-12-22 | 2017-12-28 | Mag Corporation
NC 2017 | SHS | Region XI | Davao del Norte | 304239 | Limbaan NHS | NEW CORELLA | 1 |  | 4 | 2STY4CL | BATCH 13 | 9232400 |  |  | Completed | 1 |  |  | P00183408MN-CW1 | 17LC0387 | 2017-11-16 | 2017-11-23 | 2017-12-20 | 2017-12-21 | 2017-12-28 | Legacy Construction Corporation
NC 2017 | K10 | Region XI | Davao del Norte | 128710 | Macgum ES | NEW CORELLA | 1 | 1 | 6 | 2STY6CL | BATCH 13 | 11796800 |  |  | Completed | 1 |  |  | P00183394MN-CW1 | 17LC0451 | 2017-11-16 | 2017-11-23 | 2017-12-15 | 2017-12-21 | 2017-12-27 | LLM Unified Builders and Trading Corp.
NC 2017 | K10 | Region XI | Davao del Norte | 128713 | New Bohol ES | NEW CORELLA | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9117985 |  |  | Completed | 1 |  |  | P00183395MN-CW1 | 17LC0453 | 2017-11-16 | 2017-11-23 | 2017-12-15 | 2017-12-21 | 2017-12-27 | Legacy Construction Corporation
NC 2017 | K10 | Region XI | Davao del Norte | 128714 | New Corella CES | NEW CORELLA | 1 | 1 | 12 | 3STY12CL | BATCH 13 | 32203645 |  |  | Completed | 1 |  |  | P00183396MN-CW1 | 17LC0388 | 2017-11-16 | 2017-11-23 | 2017-12-15 | 2017-12-21 | 2017-12-27 | FFJJ Construction
NC 2017 | K10 | Region XI | Davao del Norte | 128595 | Sawata Ernandcor CES | SAN ISIDRO | 1 | 1 | 12 | 3STY12CL | BATCH 13 | 32610972 |  |  | Completed | 1 |  |  | P00183392MN-CW1 | 17LC0452 | 2017-11-16 | 2017-11-23 | 2017-12-15 | 2017-12-21 | 2017-12-27 | LLM Unified Builders and Trading Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304251 | Sawata NHS | SAN ISIDRO | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9207125 |  |  | Completed | 1 |  |  | P00183416MN-CW1 | 17LC0413 | 2017-11-16 | 2017-11-23 | 2017-12-14 | 2017-12-22 | 2017-12-27 | CJEP Builders & Engineering Services
NC 2017 | SHS | Region XI | Davao del Norte | 304251 | Sawata NHS | SAN ISIDRO | 1 |  | 4 | 2STY4CL | BATCH 13 | 9207125 |  |  | Completed | 1 |  |  | P00183417MN-CW1 | 17LC0414 | 2017-11-16 | 2017-11-23 | 2017-12-14 | 2017-12-22 | 2017-12-27 | CJEP Builders & Engineering Services
NC 2017 | SHS | Region XI | Davao del Norte | 304237 | Kimamon National High School | SANTO TOMAS | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 8945901.76 |  |  | Completed | 1 |  |  | P00183427MN-CW1 | 17LC0421 | 2017-11-16 | 2017-11-23 | 2017-12-20 | 2017-12-22 | 2017-12-27 | Dingo Builders and Supply
NC 2017 | SHS | Region XI | Davao del Norte | 304237 | Kimamon National High School | SANTO TOMAS | 2 |  | 4 | 2STY4CL | BATCH 13 | 8945901.76 |  |  | Completed | 1 |  |  | P00183428MN-CW1 | 17LC0422 | 2017-11-16 | 2017-11-23 | 2017-12-20 | 2017-12-22 | 2017-12-28 | CJEP Builders & Engineering Services
NC 2017 | SHS | Region XI | Davao del Norte | 304256 | Salvacion NHS | SANTO TOMAS | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9836630 |  |  | Completed | 1 |  |  | P00183431MN-CW1 | 17LC0442 | 2017-11-16 | 2017-11-23 | 2017-12-11 | 2017-12-21 | 2017-12-27 | LLM Unified Builders and Trading Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304256 | Salvacion NHS | SANTO TOMAS | 2 |  | 4 | 2STY4CL | BATCH 13 | 9836630 |  |  | Completed | 1 |  |  | P00183432MN-CW1 | 17LC0443 | 2017-11-16 | 2017-11-23 | 2017-12-11 | 2017-12-21 | 2017-12-27 | LLM Unified Builders and Trading Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304254 | Sto Tomas NHS | SANTO TOMAS | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9019259 |  |  | Completed | 1 |  |  | P00183429MN-CW1 | 17LC0444 | 2017-11-16 | 2017-11-23 | 2017-12-11 | 2017-12-21 | 2017-12-27 | LLM Unified Builders and Trading Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304254 | Sto Tomas NHS | SANTO TOMAS | 2 |  | 4 | 2STY4CL | BATCH 13 | 9019259 |  |  | Completed | 1 |  |  | P00183430MN-CW1 | 17LC0445 | 2017-11-16 | 2017-11-23 | 2017-12-11 | 2017-12-21 | 2017-12-27 | LLM Unified Builders and Trading Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 315902 | Tulalian NHS | SANTO TOMAS | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9300200 |  |  | Completed | 1 |  |  | P00183434MN-CW1 | 17LC0447 | 2017-11-16 | 2017-11-23 | 2017-12-20 | 2017-12-21 | 2017-12-27 | LLM Unified Builders and Trading Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 315902 | Tulalian NHS | SANTO TOMAS | 2 |  | 4 | 2STY4CL | BATCH 13 | 8945901.75 |  |  | Completed | 1 |  |  | P00183435MN-CW1 | 17LC0384 | 2017-11-16 | 2017-11-23 | 2017-12-14 | 2017-12-20 | 2017-12-27 | Micah Construction & Supply
NC 2017 | SHS | Region XI | Davao del Norte | 315902 | Tulalian NHS | SANTO TOMAS | 2 |  | 4 | 2STY4CL | BATCH 13 | 8945901.75 |  |  | Completed | 1 |  |  | P00183436MN-CW1 | 17LC0383 | 2017-11-16 | 2017-11-23 | 2017-12-14 | 2017-12-20 | 2017-12-27 | Micah Construction & Supply
NC 2017 | SHS | Region XI | Davao del Norte | 304258 | Datu Jose A. Libayao Memorial NHS | TALAINGOD | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9197205 |  |  | Completed | 1 |  |  | P00183420MN-CW1 | 17LC0415 | 2017-11-16 | 2017-11-23 | 2017-12-20 | 2017-12-22 | 2017-12-28 | LLM Unified Builders and Trading Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304258 | Datu Jose A. Libayao Memorial NHS | TALAINGOD | 1 |  | 4 | 2STY4CL | BATCH 13 | 9197205 |  |  | Completed | 1 |  |  | P00183421MN-CW1 | 17LC0416 | 2017-11-16 | 2017-11-23 | 2017-12-20 | 2017-12-22 | 2017-12-28 | Five Massive Infra & Supply Corp.
NC 2017 | K10 | Region XI | Davao del Norte |  | Napunong Elementary School - Sto. Niño CES Annex | TALAINGOD | 1 | 1 | 8 | 2STY8CL | BATCH 13 | 17530707 |  |  | Completed | 1 |  |  | P00183422MN-CW1 | 17LC0455 | 2017-11-16 | 2017-11-23 | 2017-12-15 | 2017-12-21 | 2017-12-27 | Legacy Construction Corporation
NC 2017 | K10 | Region XI | Davao del Norte | 128807 | Sto. Niño CES | TALAINGOD | 1 | 1 | 12 | 3STY12CL | BATCH 13 | 32309054 |  |  | Completed | 1 |  |  | P00183397MN-CW1 | 17LC0389 | 2017-11-16 | 2017-11-23 | 2017-12-15 | 2017-12-21 | 2017-12-27 | Legacy Construction Corporation
NC 2017 | SHS | Region XI | Davao del Norte | 304257 | Sto. Nino NHS | TALAINGOD | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9069924 |  |  | Completed | 1 |  |  | P00183418MN-CW1 | 17LC0411 | 2017-11-16 | 2017-11-23 | 2017-12-14 | 2017-12-22 | 2017-12-28 | LLM Unified Builders and Trading Corp.
NC 2017 | SHS | Region XI | Davao del Norte | 304257 | Sto. Nino NHS | TALAINGOD | 1 |  | 4 | 2STY4CL | BATCH 13 | 9069924 |  |  | Completed | 1 |  |  | P00183419MN-CW1 | 17LC0412 | 2017-11-16 | 2017-11-23 | 2017-12-20 | 2017-12-22 | 2017-12-28 | LLM Unified Builders and Trading Corp.
NC 2017 | SHS | Region XI | Davao del Sur | 304297 | Sulop NHS | SULOP | 1 | 1 | 6 | 3STY6CL | BATCH 13 | 17422065 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | LLM Unified Builders
NC 2017 | SHS | Region XI | Davao del Sur | 304297 | Sulop NHS | SULOP | 1 |  | 6 | 3STY6CL | BATCH 13 | 16766478.66 |  |  | Completed | 1 |  |  |  |  | 2017-11-26 |  | 2017-12-11 |  | 2017-12-22 | LLM Unified Builders
NC 2017 | K10 | Region XI | Davao Occidental | 205048 | Kiyaga Elementary School | DON MARCELINO | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2989618 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128846 | Linadasan ES | DON MARCELINO | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2853636 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128853 | Tador & Masaglang ES | DON MARCELINO | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2989618 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Davao Occidental | 304264 | Balangonan NHS | JOSE ABAD SANTOS (TRINIDAD) | 0 |  | 1 | 2STY4CL WORKSHOP BLDG (7X18) | BATCH 13 | 11905796 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128885 | Mangili ES | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2783636 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128885 | Mangili ES | JOSE ABAD SANTOS (TRINIDAD) | 0 |  | 2 | 1STY2CL | BATCH 13 | 2783636 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128995 | Kipaliko ES | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2814922 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 205054 | Kisoy Elementary School | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2814992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 128976 | Lorenzo Manuel Primary School | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2814992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 205029 | Sitio Guisok BEAM Primary School | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2814992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 205037 | TFS of Bilibak | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2814922 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 205040 | TFS-Kamugna ES | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2814922 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 205032 | TFS-Makalong ES | MALITA | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2814922 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 129122 | Pedro Mariscal ES | SANTA MARIA | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 2728992 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 129124 | San Agustin ES | SANTA MARIA | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 3820117 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Occidental | 205015 | Camalig ES | SARANGANI | 0 | 1 | 2 | 1STY2CL | BATCH 13 | 3103679 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Davao Oriental | 129218 | Lucatan ES | CARAGA | 1 |  | 2 | 1STY2CL | BATCH 13 | 2877245.82 |  |  | Completed | 1 | [8 empty] | 2017-09-17 | FJAR CONST.
NC 2017 | K10 | Region XI | Davao Oriental | 316113 | Paulina Gambong Abayon NHS | TARRAGONA | 1 | 1 | 6 | 2STY6CL | BATCH 13 | 12795055.92 |  |  | Completed | 1 | [8 empty] | 2018-01-09 | FAJR CONST. PARTS & SUPPLY
NC 2017 | K10 | Region XI | Island Garden City of Samal | 128684 | Bandera Elementary School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9670953.39 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Island Garden City of Samal |  | Bandera NHS - Kaputian | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9761572.27 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Island Garden City of Samal |  | Libertad NHS - Kaputian | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9739704.3 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Island Garden City of Samal | 128692 | Linosotan Elementary School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 10 | 2STY10CL | BATCH 13 | 20714822.56 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Island Garden City of Samal |  | Mambago B - Limao Ext. Babak | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 6 | 2STY6CL | BATCH 13 | 12570321.87 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304245 | Mambago-B National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | 2STY4CL SCIENCE LAB. | BATCH 13 | 9522416.44 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Island Garden City of Samal | 304245 | Mambago-B National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 13 | 9651102.33 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Island Garden City of Samal | 128607 | San Agustin ES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9841475.39 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Island Garden City of Samal |  | Sta. Cruz Gamban Dadatan Ext. | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9877081.82 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Island Garden City of Samal | 128699 | Tagbaobo Elementary School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 6 | 2STY6CL | BATCH 13 | 12682468.36 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Panabo City | 304403 | A. O. Floirendo National High School | CITY OF PANABO | 2 | 1 | 2 | 2STY4CL SCIENCE LAB. | BATCH 13 | 9662277 |  |  | Completed | 1 |  |  | P00183476MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | Tagum Builders Contractors Corporation
NC 2017 | TVL | Region XI | Panabo City | 304403 | A. O. Floirendo National High School | CITY OF PANABO | 2 |  | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 13 | 9662277 |  |  | Completed | 1 |  |  | P00183477MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | Tagum Builders Contractors Corporation
NC 2017 | K10 | Region XI | Panabo City | 129781 | Cabili ES | CITY OF PANABO | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9652582.75 |  |  | Completed | 1 |  |  | P00183470MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | Micah Construction & Supply
NC 2017 | TVL | Region XI | Panabo City | 304405 | Don Manuel A. Javellana Memorial National High School | CITY OF PANABO | 2 | 1 | 2 | 2STY4CL SCIENCE LAB. | BATCH 13 | 9811955 |  |  | Completed | 1 |  |  | P00183478MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | Five Massinve Infra & Supply
NC 2017 | TVL | Region XI | Panabo City | 304405 | Don Manuel A. Javellana Memorial National High School | CITY OF PANABO | 2 |  | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 13 | 9811955 |  |  | Completed | 1 |  |  | P00183479MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | Micah Construction & Supply
NC 2017 | K10 | Region XI | Panabo City | 129804 | Glecerio L. Dondoy CES | CITY OF PANABO | 2 | 1 | 6 | 2STY6CL | BATCH 13 | 12108737.82 |  |  | Completed | 1 |  |  | P00183475MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | Five Massinve Infra & Supply
NC 2017 | K10 | Region XI | Panabo City | 129783 | Gredu ES | CITY OF PANABO | 2 | 1 | 6 | 2STY6CL | BATCH 13 | 12002907 |  |  | Completed | 1 |  |  | P00183471MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | Agong Builders & Construction Supply Inc.
NC 2017 | TVL | Region XI | Panabo City | 316403 | Kauswagan National High School | CITY OF PANABO | 2 | 1 | 2 | 2STY4CL SCIENCE LAB. | BATCH 13 | 8990901.76 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Panabo City | 316403 | Kauswagan National High School | CITY OF PANABO | 2 |  | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 13 | 8990901.76 |  |  | Completed | 1 |  |  | P00183488MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | LLM Unified Builders & Trading Corp.
NC 2017 | TVL | Region XI | Panabo City | 304409 | Little Panay National High School | CITY OF PANABO | 2 | 1 | 2 | 2STY4CL SCIENCE LAB. | BATCH 13 | 8945901.76 |  |  | Completed | 1 |  |  | P00183482MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | South Ironrock Corporation
NC 2017 | TVL | Region XI | Panabo City | 304409 | Little Panay National High School | CITY OF PANABO | 2 |  | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 13 | 9093877 |  |  | Completed | 1 |  |  | P00183483MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | CJEP Builders & Engineering Service
NC 2017 | TVL | Region XI | Panabo City | 304407 | Manay National High School | CITY OF PANABO | 2 | 1 | 2 | 2STY4CL SCIENCE LAB. | BATCH 13 | 8995901.76 |  |  | Completed | 1 |  |  | P00183480MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | LLM Unified Builders & Trading Corp.
NC 2017 | TVL | Region XI | Panabo City | 304407 | Manay National High School | CITY OF PANABO | 2 |  | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 13 | 9662277 |  |  | Completed | 1 |  |  | P00183481MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | Micah Construction & Supply
NC 2017 | K10 | Region XI | Panabo City | 129784 | Panabo Central Elementary School SPED Center | CITY OF PANABO | 2 | 1 | 8 | 2STY8CL | BATCH 13 | 18983738 |  |  | Completed | 1 |  |  | P00183472MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | O.G. Santos Corporation
NC 2017 | TVL | Region XI | Panabo City | 341574 | Panabo City Senior High School | CITY OF PANABO | 2 | 1 | 2 | 2STY4CL SCIENCE LAB. | BATCH 13 | 9840831 |  |  | Completed | 1 |  |  | P00183491MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | LLM Unified Builders & Corp.
NC 2017 | TVL | Region XI | Panabo City | 341574 | Panabo City Senior High School | CITY OF PANABO | 2 |  | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 13 | 9840831 |  |  | Completed | 1
NC 2017 | TVL | Region XI | Panabo City | 316405 | Quezon High School - Panabo NHS Annex | CITY OF PANABO | 2 | 1 | 2 | 2STY4CL SCIENCE LAB. | BATCH 13 | 9662277 |  |  | Completed | 1 |  |  | P00183489MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | Kawanay Builders
NC 2017 | TVL | Region XI | Panabo City | 316405 | Quezon High School - Panabo NHS Annex | CITY OF PANABO | 2 |  | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 13 | 9694223 |  |  | Completed | 1 |  |  | P00183490MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | MAG Corporation
NC 2017 | K10 | Region XI | Panabo City | 129785 | Rizal ES | CITY OF PANABO | 2 |  | 6 | 3STY6CL | BATCH 13 | 15978262.23 |  |  | Completed | 1 |  |  | P00183473MN-CW1 |  |  |  | 2017-12-12 |  |  | Danimerh Construction & Supply
NC 2017 | K10 | Region XI | Panabo City | 129788 | San Vicente ES | CITY OF PANABO | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9240018.9 |  |  | Reverted | 0
NC 2017 | SHS | Region XI | Panabo City | 316402 | San Vicente National High School | CITY OF PANABO | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9286666.66 |  |  | Completed | 1 |  |  | P00183474MN-CW1 | [6 empty] | Micah Construction & Supply
NC 2017 | TVL | Region XI | Panabo City | 316402 | San Vicente National High School | CITY OF PANABO | 2 |  | 2 | 2STY4CL SCIENCE LAB. | BATCH 13 | 9694223 |  |  | Completed | 1 |  |  | P00183484MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | LLM Unified Builders & Corp.
NC 2017 | TVL | Region XI | Panabo City | 316401 | Southern Davao National High School | CITY OF PANABO | 2 | 1 | 2 | 2STY4CL COMP. (ICT) LAB. | BATCH 13 | 8945901.76 |  |  | Completed | 1 |  |  | P00183485MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | EP Manatan Construction & Development Corp.
NC 2017 | TVL | Region XI | Panabo City | 316401 | Southern Davao National High School | CITY OF PANABO | 2 |  | 2 | 2STY4CL SCIENCE LAB. | BATCH 13 | 9487333 |  |  | Completed | 1 |  |  | P00183486MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | EP Manatan Construction & Development Corp.
NC 2017 | K10 | Region XI | Panabo City |  | Southern Davao National High School - Nanyo Ext. Classes | CITY OF PANABO | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9217090.82 |  |  | Completed | 1 |  |  | P00183495MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | VCG Construction & Supply
NC 2017 | K10 | Region XI | Panabo City |  | Southern Davao National High School - New Malitbog Ext. Classes | CITY OF PANABO | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 9223225.84 |  |  | Completed | 1 |  |  | P00183495MN-CW1 |  | 2017-11-16 |  | 2017-12-12 | 2017-12-21 | 2017-12-27 | Micah Construction & Supply
NC 2017 | SHS | Region XI | Tagum City | 500424 | Busaon Integrated School | CITY OF TAGUM (Capital) | 1 | 1 | 9 | 3STY9CL | BATCH 13 | 27412116.25 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Tagum City | 500424 | Busaon Integrated School | CITY OF TAGUM (Capital) | 1 |  | 6 | 3STY6CL | BATCH 13 | 16075611.97 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Tagum City | 128789 | CABUGAN ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 13 | 12677115.11 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Tagum City | 322401 | Canocotan National High School | CITY OF TAGUM (Capital) | 1 | 1 | 9 | 3STY9CL | BATCH 13 | 23689026.06 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Tagum City | 128776 | DR BRIZ CENTRAL ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 9 | 3STY9CL | BATCH 13 | 27091382.43 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Tagum City | 304231 | Jose Tuason Jr. Memorial National High School | CITY OF TAGUM (Capital) | 1 | 1 | 12 | 2STY12CL | BATCH 13 | 23391940.39 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Tagum City | 128777 | LA FILIPINA ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 13 | 15311587 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Tagum City | 304238 | La Filipina NHS | CITY OF TAGUM (Capital) | 1 | 1 | 30 | 3STY30CL | BATCH 13 | 64081857 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Tagum City | 128792 | LIBOGANON ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 13 | 12776172.26 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Tagum City | 500425 | Liboganon Integrated School | CITY OF TAGUM (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 13 | 19480028 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Tagum City | 128795 | MANGGA ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 13 | 11796800 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Tagum City | 128781 | PAGSABANGAN ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9909897.83 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Tagum City | 500426 | Pandapan Integrated School | CITY OF TAGUM (Capital) | 1 | 1 | 12 | 3STY12CL | BATCH 13 | 32218472 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Tagum City | 128797 | SAN ISIDRO ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 8945901.76 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Tagum City | 304225 | Tagum City National Comprehensive High School | CITY OF TAGUM (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 13 | 41583285 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Tagum City | 304260 | Tagum City National High School | CITY OF TAGUM (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 13 | 20743797 |  |  | Completed | 1
NC 2017 | SHS | Region XI | Tagum City | 304261 | TAGUM NATIONAL TRADE SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 30 | 2UNITS 3STY15CL | BATCH 13 | 72038081 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Tagum City | 128785 | UNION ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 13 | 11656168.02 |  |  | Completed | 1
NC 2017 | K10 | Region XI | Tagum City | 128798 | VISAYAN VILLAGE CENTRAL ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 13 | 19075031 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Compostela Valley | 128379 | Bahi ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 4551000 |  |  | Completed | 1 | [8 empty] | 2018-11-23 | VGG CONSTRUCTION AND SUPPLY
NC 2018 | K10 | Region XI | Compostela Valley | 128429 | Boay ES | MONKAYO | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3931000 |  |  | Completed | 1 | [8 empty] | 2018-07-11 | A.B. APONESTO CONST. PARTS AND SUPPLY
NC 2018 | K10 | Region XI | Compostela Valley | 128430 | Cabangkalan ES | MONKAYO | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3931000 |  |  | Completed | 1 | [8 empty] | 2018-08-30 | AGONG BUILDERS AND CONSTRUCTION
NC 2018 | K10 | Region XI | Compostela Valley | 128461 | Bankerohan ES | MONTEVISTA | 1 | 1 | 3 | 1STY3CL | BATCH 1 | 5776000 |  |  | Completed | 1 | [8 empty] | 2018-06-11 | A.B. APONESTO CONST. PARTS AND SUPPLY
NC 2018 | K10 | Region XI | Compostela Valley | 128472 | New Calape ES | MONTEVISTA | 1 | 1 | 4 | 1STY4CL | BATCH 1 | 8036000 |  |  | Completed | 1 | [8 empty] | 2018-11-09 | KANAWAY BUILDERS CORPORATION
NC 2018 | K10 | Region XI | Compostela Valley | 128475 | Prosperidad ES | MONTEVISTA | 1 | 1 | 4 | 1STY4CL | BATCH 1 | 8036000 |  |  | Completed | 1 | [8 empty] | 2018-08-30 | CJEP BUILDERS & ENGINEERING SERVICES
NC 2018 | K10 | Region XI | Compostela Valley | 128478 | San Vicente ES | MONTEVISTA | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3631000 |  |  | Completed | 1 | [8 empty] | 2018-08-11 | A.B. APONESTO CONST. PARTS AND SUPPLY
NC 2018 | SHS | Region XI | Compostela Valley | 304203 | Montevista NHS - Annex (DNAS Campus) | MONTEVISTA | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3033000 |  |  | Completed | 1 | [8 empty] | 2018-08-18 | KANAWAY BUILDERS CORPORATION
NC 2018 | TVL | Region XI | Compostela Valley | 315815 | New Albay NHS | MARAGUSAN (SAN MARIANO) | 1 | 1 | 1 | UNIQUE TECHVOC | BATCH 1 | 4275000 |  |  | Completed | 1 | [8 empty] | 2018-08-30 | KANAWAY BUILDERS CORPORATION
NC 2018 | K10 | Region XI | Compostela Valley | 128368 | Limbo ES | MACO | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 3033000 |  |  | Completed | 1 | [8 empty] | 2018-11-23 | H-ROYAL CONSTRUCTION
NC 2018 | K10 | Region XI | Compostela Valley | 128263 | Compostela Central Elementary School SPED Center | COMPOSTELA | 1 | 1 | 10 | 2STY10CL | Batch 3 | 35115907.53 |  |  | Completed | 1 | [8 empty] | 2018-12-12 | RELY CONSTRUCTION & SUPPLY AND LISCAL CONSTRUCTION SERVICES
NC 2018 | K10 | Region XI | Compostela Valley | 128381 | Caragan ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 8 | 2STY8CL | Batch 3 | 30374921.4 |  |  | Completed | 1 | [8 empty] | 2018-10-12 | VGG CONSTRUCTION AND SUPPLY
NC 2018 | K10 | Region XI | Compostela Valley | 128397 | Pamintaran ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4665075.15 |  |  | Completed | 1 | [8 empty] | 2018-12-12 | MARK ANTHONY CONSTRUCTION
NC 2018 | K10 | Region XI | Compostela Valley | 128402 | Tigbao ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 3 | 1STY3CL W/ TOILET ATTACHED | Batch 3 | 7799649.13 |  |  | Completed | 1 | [8 empty] | 2018-12-12 | TWO DEGREES CONSTRUCTION AND SUPPLY
NC 2018 | K10 | Region XI | Compostela Valley | 128439 | Moncayo CES | MONKAYO | 1 | 1 | 10 | 2STY10CL | Batch 3 | 35282505.68 |  |  | Completed | 1 | [8 empty] | 2018-10-12 | RELY CONSTRUCTION & SUPPLY AND LISCAL CONSTRUCTION SERVICES
NC 2018 | K10 | Region XI | Compostela Valley | 128443 | Muñoz ES | MONKAYO | 1 | 1 | 4 | 1STY4CL W/ TOILET ATTACHED | Batch 3 | 8979169.48 |  |  | Completed | 1 | [8 empty] | 2018-12-12 | KANAWAY BUILDERS CORPORATION
NC 2018 | K10 | Region XI | Compostela Valley | 128466 | Linoan ES | MONTEVISTA | 1 | 1 | 4 | 2STY4CL | Batch 3 | 14457586.22 |  |  | Completed | 1 | [8 empty] | 2018-10-12 | EGCG BUILDERS & SUPPLY
NC 2018 | K10 | Region XI | Compostela Valley | 128471 | Montevista CES | MONTEVISTA | 1 | 1 | 15 | 3STY15CL | Batch 3 | 50694928.58 |  |  | Completed | 1 | [8 empty] | 2018-12-12 | FFJJ CONSTRUCTION
NC 2018 | K10 | Region XI | Compostela Valley | 128523 | Pagsabangan ES | NEW BATAAN | 1 | 1 | 4 | 2UNITS 1STY2CL | Batch 3 | 10678856.76 |  |  | Completed | 1 | [8 empty] | 2018-10-12 | CJEP BUILDERS & ENGINEERING SERVICES
NC 2018 | K10 | Region XI | Compostela Valley | 128528 | San Roque ES | NEW BATAAN | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4665075.15 |  |  | Completed | 1 | [8 empty] | 2018-10-12 | KANAWAY BUILDERS CORPORATION
NC 2018 | K10 | Region XI | Compostela Valley | 204010 | Depot ES | MONKAYO | 1 | 1 | 4 | 2STY4CL | Batch 3 | 13495655.18 |  |  | Completed | 1 | [8 empty] | 2018-12-12 | KANAWAY BUILDERS CORPORATION
NC 2018 | K10 | Region XI | Compostela Valley | 300927 | Diosdado Macapagal NHS | COMPOSTELA | 1 | 1 | 10 | 2STY10CL | Batch 3 | 35327505.68 |  |  | Completed | 1 | [8 empty] | 2018-12-12 | DAVAO CONCRETE PRODUCTS
NC 2018 | K10 | Region XI | Compostela Valley | 500455 | Olaycon Integrated School | MONKAYO | 1 | 1 | 9 | 3STY9CL | Batch 3 | 31851334.17 |  |  | Completed | 1 | [8 empty] | 2018-10-12 | DAVAO CONCRETE PRODUCTS
NC 2018 | K10 | Region XI | Compostela Valley |  | Anagase IS | MONKAYO | 1 | 1 | 6 | 2STY6CL | Batch 3 | 21246444.98 |  |  | Completed | 1 | [8 empty] | 2018-12-12 | H-ROYAL CONSTRUCTION
NC 2018 | K10 | Region XI | Compostela Valley |  | Cagan ES | NEW BATAAN | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 5059575.15 |  |  | Completed | 1 | [8 empty] | 2018-10-12 | MARK ANTHONY CONSTRUCTION
NC 2018 | K10 | Region XI | Compostela Valley | 128364 | Calabcab ES | MACO | 2 | 1 | 4 | 2STY4CL | Batch 3 | 13625405.18 |  |  | Completed | 1 | [8 empty] | 2018-10-12 | AGONG BUILDERS AND CONSTRUCTION
NC 2018 | K10 | Region XI | Compostela Valley | 300607 | Cabidianan NHS | NABUNTURAN (Capital) | 2 | 1 | 6 | 2STY6CL | Batch 3 | 20627044.98 |  |  | Completed | 1 | [8 empty] | 2018-10-12 | TWO DEGREES CONSTRUCTION AND SUPPLY
NC 2018 | K10 | Region XI | Compostela Valley | 301052 | Lawaan NHS | PANTUKAN | 2 | 1 | 6 | 2STY6CL | Batch 3 | 21127044.98 |  |  | Completed | 1 | [8 empty] | 2018-12-12 | ARCINUE COMMERCIAL CORP.
NC 2018 | SHS | Region XI | Compostela Valley | 301294 | Libaylibay NHS | MACO | 2 | 1 | 6 | 2STY6CL | Batch 3 | 20627044.98 |  |  | Completed | 1 | [8 empty] | 2018-12-12 | TWO DEGREES CONSTRUCTION AND SUPPLY
NC 2018 | SHS | Region XI | Compostela Valley | 304192 | Mabini NHS | MABINI (DOÑA ALICIA) | 2 | 1 | 40 | 2UNITS 4STY20CL | Batch 3 | 133670476.22 |  |  | Completed | 1 | [8 empty] | 2018-12-12 | RELY CONSTRUCTION & SUPPLY AND LISCAL CONSTRUCTION SERVICES
NC 2018 | SHS | Region XI | Compostela Valley | 304205 | Nabunturan NCHS | NABUNTURAN (Capital) | 2 | 1 | 20 | 4STY20CL | Batch 3 | 66759378.11 |  |  | Completed | 1 | [8 empty] | 2018-12-12 | THREE W BUILDERS
NC 2018 | K10 | Region XI | Compostela Valley | 128539 | Bongbong ES | PANTUKAN | 2 | 1 | 8 | 2UNITS 2STY4CL | Batch 5 | 28915172.44 |  |  | Completed | 1 | [8 empty] | 2018-12-28 | TRIPLE S BUILDERS INC.
NC 2018 | K10 | Region XI | Davao City | 129642 | Josefa Llanes Escoda Elem. School | DAVAO CITY | 1 | 1 | 12 | 4STY12CL | BATCH 1 | 34301773 |  |  | Completed | 1 |  |  |  |  | 2018-05-02 |  | 2018-05-22 | 2018-06-11 | 2018-07-10
NC 2018 | K10 | Region XI | Davao City | 129648 | Matina CES | DAVAO CITY | 1 | 1 | 16 | 4STY16CL | BATCH 1 | 40143597 |  |  | Completed | 1 |  |  |  |  | 2018-05-02 |  | 2018-05-22 | 2018-06-08 | 2018-06-13
NC 2018 | SHS | Region XI | Davao City | 304377 | JESUS J. SORIANO NATIONAL HIGH SCHOOL | DAVAO CITY | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 32033009 |  |  | Completed | 1 |  |  | P00272561MN-CW1 |  | 2018-05-02 |  | 2018-05-22 | 2018-06-06 | 2018-06-13
NC 2018 | SHS | Region XI | Davao City | 304377 | JESUS J. SORIANO NATIONAL HIGH SCHOOL | DAVAO CITY | 1 |  | 9 | 3STY9CL | BATCH 1 | 41331113 |  |  | Completed | 1 |  |  | P00272562MN-CW1 |  | 2018-05-02 |  | 2018-05-22 | 2018-06-07 | 2018-06-13
NC 2018 | SHS | Region XI | Davao City | 304378 | GOV. VICENTE DUTERTE NATIONAL HIGH SCHOOL | DAVAO CITY | 1 | 1 | 9 | 3STY9CL | BATCH 1 | 42061113 |  |  | Completed | 1 |  |  | P00272563MN-CW1 |  | 2018-05-02 |  | 2018-05-22 | 2018-06-11 | 2018-07-10
NC 2018 | K10 | Region XI | Davao City | 129486 | V. Corcuera ES | DAVAO CITY | 2 | 1 | 24 | 4STY24CL | BATCH 1 | 52374596 |  |  | completed | 1 |  |  |  |  | 2018-05-02 |  | 2018-05-22 | 2018-08-08 | 2018-08-13
NC 2018 | K10 | Region XI | Davao City | 129530 | Sto. Nino Elementary School | DAVAO CITY | 2 | 1 | 9 | 3STY9CL | BATCH 1 | 26575492 |  |  | Completed | 1 |  |  |  |  | 2018-05-02 |  | 2018-05-22 | 2018-06-08 | 2018-06-13
NC 2018 | SHS | Region XI | Davao City | 304367 | Dr. Santiago Dakudao Sr. National High School | DAVAO CITY | 2 | 1 | 16 | 4STY16CL | BATCH 1 | 54008398 |  |  | Completed | 1 |  |  | P00272566MN-CW1 | 18BL0237 | 2018-05-02 |  | 2018-05-22 | 2018-08-08 | 2018-08-13
NC 2018 | SHS | Region XI | Davao City | 304367 | Dr. Santiago Dakudao Sr. National High School | DAVAO CITY | 2 |  | 12 | 4STY12CL | BATCH 1 | 34241773 |  |  | Completed | 1 |  |  | P00272567MN-CW1 | 18LB0238 | 2018-05-02 |  | 2018-05-22 | 2018-06-11 | 2018-08-01
NC 2018 | TVL | Region XI | Davao City | 316211 | Paradise Embac National High School | DAVAO CITY | 2 | 1 | 4 | 2UNITS 2STY2CL (18MX7M) LABORATORY SCHOOL BLDG. | BATCH 1 | 18197200 |  |  | Completed | 1 |  |  | P00272568MN-CW1 | 18LB0234 | 2018-05-02 |  | 2018-05-22 | 2018-06-06 | 2018-06-13
NC 2018 | K10 | Region XI | Davao City | 129713 | Baliok ES | DAVAO CITY | 1 | 1 | 9 | 3STY9CL | Batch 3 | 29293534 |  |  | Completed | 1 |  |  |  |  | 2018-11-10 |  | 2018-12-04 | 2018-12-20 | 2018-12-21
NC 2018 | SHS | Region XI | Davao City | 301717 | Magtuod National High School | DAVAO CITY | 1 | 1 | 8 | 2STY8CL | Batch 3 | 22226365 |  |  | Completed | 1 |  |  |  |  | 2018-11-16 |  | 2018-12-06 | 2018-12-20 | 2018-12-21
NC 2018 | K10 | Region XI | Davao City |  | Dona Soledad Duterte HS | DAVAO CITY | 1 | 1 | 12 | 3STY12CL | Batch 3 | 37700368 |  |  | Completed | 1 |  |  |  |  | 2018-11-10 |  | 2018-12-04 | 2018-12-20 | 2018-12-21
NC 2018 | K10 | Region XI | Davao City | 129507 | Cabantian ES | DAVAO CITY | 2 | 1 | 12 | 3STY12CL | Batch 3 | 40012390 |  |  | Completed | 1 |  |  |  |  | 2018-11-10 |  | 2018-12-04 | 2018-12-19 | 2018-12-21
NC 2018 | K10 | Region XI | Davao City | 129515 | Pedro S. Carriedo ES | DAVAO CITY | 2 | 1 | 15 | 3STY15CL (U-TYPE) | Batch 3 | 43520238 |  |  | Completed | 1 |  |  |  |  | 2018-11-16 |  | 2018-12-04 | 2018-12-19 | 2018-12-21
NC 2018 | SHS | Region XI | Davao City | 304346 | Cabantian NHS | DAVAO CITY | 2 | 1 | 6 | 3STY6CL | Batch 3 | 17193199 |  |  | Completed | 1 |  |  |  |  | 2018-11-10 |  | 2018-12-04 | 2018-12-20 | 2018-12-21
NC 2018 | TVL | Region XI | Davao City | 316213 | MAHAYAG NATIONAL HIGH SCHOOL | DAVAO CITY | 2 | 1 | 2 | 2UNITS 1STY1CL (7MX22M) UNIQUE WORKSHOP | Batch 3 | 8040000 |  |  | Completed | 1 |  |  |  |  | 2018-11-10 |  | 2018-12-04 | 2018-12-20 | 2018-12-21
NC 2018 | K10 | Region XI | Davao City | 129464 | Baguio Central Elementary School | DAVAO CITY | 3 | 1 | 24 | 4STY24CL | Batch 3 | 53979110.81 |  |  | Completed | 1 |  |  |  | 18LH0084 | 2018-10-29 | 2018-11-05 | 2018-11-22 |  | 2019-01-18
NC 2018 | K10 | Region XI | Davao City | 129579 | Suawan ES | DAVAO CITY | 3 | 1 | 12 | 3STY12CL | Batch 3 | 29698400 |  |  | Completed | 1 |  |  |  | 18LH0080 | 2018-10-29 | 2018-11-05 | 2018-11-22 |  | 2019-01-18
NC 2018 | K10 | Region XI | Davao City | 129614 | Mabuhay Elementary School | DAVAO CITY | 3 | 1 | 6 | 2UNITS 1STY3CL | Batch 3 | 14321782.91 |  |  | Completed | 1 |  |  |  | 18LH0081 | 2018-10-29 | 2018-11-05 | 2018-11-22 |  | 2019-01-18
NC 2018 | K10 | Region XI | Davao City | 129735 | Los Amigos Elementary School | DAVAO CITY | 3 | 1 | 24 | 4STY24CL | Batch 3 | 54072776.77 |  |  | Completed | 1 |  |  |  | 18LH0082 | 2018-10-29 | 2018-11-05 | 2018-11-22 |  | 2019-01-18
NC 2018 | K10 | Region XI | Davao City | 206007 | Kidali ES | DAVAO CITY | 3 | 1 | 5 | 1STY2CL & 1STY3CL | Batch 3 | 11840949.85 |  |  | Completed | 1 |  |  |  | 18LH0083 | 2018-10-29 | 2018-11-05 | 2018-11-22 |  | 2019-01-18
NC 2018 | SHS | Region XI | Davao City | 304343 | Baguio National School of Arts and Trades | DAVAO CITY | 3 | 1 | 6 | 3STY6CL | Batch 3 | 20830678.19 |  |  | Completed | 1 |  |  |  | 18LH0086 | 2018-10-29 | 2018-11-05 | 2018-11-22 |  | 2019-01-18
NC 2018 | SHS | Region XI | Davao City | 304355 | Wangan National High School-Calinan NHS Annex | DAVAO CITY | 3 | 1 | 4 | 2STY4CL | Batch 3 | 17779146.33 |  |  | Completed | 1 |  |  |  | 18LH0085 | 2018-10-29 | 2018-11-05 | 2018-11-22 |  | 2019-01-18
NC 2018 | SHS | Region XI | Davao City | 300557 | Vicenta C. Nograles National High School | DAVAO CITY | 1 | 1 | 16 | 2UNITS 4STY8CL | Batch 5 | 48017298 |  |  | Completed | 1 |  |  |  |  | 2018-11-16 |  | 2018-12-18 | 2018-12-27 | 2019-01-17
NC 2018 | K10 | Region XI | Davao del Norte | 128579 | Magbaad ES | ASUNCION (SAUG) | 1 | 1 | 5 | 1STY5CL W/ TOILET ATTACHED | Batch 3 | 9597700 |  |  | Completed | 1 |  |  |  | 18CL0184 | 2018-10-18 |  | 2018-11-07 |  | 2018-12-22
NC 2018 | K10 | Region XI | Davao del Norte | 128581 | Mamangan ES | SAN ISIDRO | 1 | 1 | 3 | 1STY3CL W/ TOILET ATTACHED | Batch 3 | 5802500 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Norte | 128583 | New Bantayan ES | ASUNCION (SAUG) | 1 | 1 | 5 | 1STY5CL W/ TOILET ATTACHED | Batch 3 | 9715500 |  |  | Completed | 1 |  |  |  | 18LC0185 | 2018-10-18 |  | 2018-11-07 |  | 2018-12-22
NC 2018 | K10 | Region XI | Davao del Norte | 128588 | Pamacaun ES | ASUNCION (SAUG) | 1 | 1 | 3 | 1STY3CL W/ TOILET ATTACHED | Batch 3 | 5827500 |  |  | Completed | 1 |  |  |  | 18CL0186 | 2018-10-18 |  | 2018-11-07 |  | 2018-12-07
NC 2018 | K10 | Region XI | Davao del Norte | 128594 | Sawata Adecor ES | SAN ISIDRO | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4075000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Norte | 128657 | Linao ES | SAN ISIDRO | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4004500 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Norte | 128663 | Marcos P. Estoque ES | KAPALONG | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3980230 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Norte | 128674 | Gabuyan CES | KAPALONG | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4118050 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Norte | 128711 | Mambing ES | NEW CORELLA | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4039000 |  |  | Completed | 1 |  |  |  | 18CL0190
NC 2018 | K10 | Region XI | Davao del Norte | 128720 | Saug Elementary School | NEW CORELLA | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4007520 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Norte | 128801 | Dagohoy Elementary School | TALAINGOD | 1 | 1 | 3 | 1STY3CL W/ TOILET ATTACHED | Batch 3 | 5737500 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Norte | 204509 | Gatong ES | TALAINGOD | 1 | 1 | 3 | 1STY3CL W/ TOILET ATTACHED | Batch 3 | 5737500 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Norte | 204523 | Upper & Lower Mabini Elementary School | KAPALONG | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3978800 |  |  | Completed | 1 |  |  |  | 18CL0188 | 2018-10-18 |  | 2018-11-07 |  | 2018-12-07
NC 2018 | K10 | Region XI | Davao del Norte | 204530 | Lower Tagasan Primary School | KAPALONG | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3978800 |  |  | Completed | 1 |  |  |  | 18CL0189 | 2018-10-18 |  | 2018-11-07 |  | 2018-12-07
NC 2018 | TVL | Region XI | Davao del Norte | 304218 | Sagayen NHS | ASUNCION (SAUG) | 1 | 1 | 2 | 1UNIT TVL UNIQUE WORKSHOP BUILDING | Batch 3 | 4566024.82 |  |  | Completed | 1
NC 2018 | SHS | Region XI | Davao del Norte | 304218 | Sagayen NHS | ASUNCION (SAUG) | 1 |  | 8 | 2STY8CL | Batch 3 | 23775298.12 |  |  | Completed | 1
NC 2018 | SHS | Region XI | Davao del Norte | 304252 | Sonlon NHS | ASUNCION (SAUG) | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3933000 |  |  | Completed | 1 |  |  |  | 18CL0187 | 2018-10-18 |  | 2018-11-07 |  | 2018-12-07
NC 2018 | SHS | Region XI | Davao del Norte | 315907 | Sta. Fe National High School | NEW CORELLA | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 4027816 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Norte | 500848 | Lumabag Integrated School | TALAINGOD | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 3900000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Norte | 128746 | Esperanza ES | SANTO TOMAS | 2 | 1 | 10 | 2STY10CL | Batch 3 | 28619196.95 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Norte | 128753 | Pantaron ES | SANTO TOMAS | 2 | 1 | 6 | 2STY6CL | Batch 3 | 15844629.74 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Norte | 128756 | Talomo ES | SANTO TOMAS | 2 | 1 | 4 | 1STY4CL W/ TOILET ATTACHED | Batch 3 | 7710000 |  |  | Completed | 1
NC 2018 | SHS | Region XI | Davao del Norte | 304219 | Balagunan National High School | SANTO TOMAS | 2 | 1 | 6 | 2STY6CL | Batch 3 | 15797231.91 |  |  | Completed | 1
NC 2018 | SHS | Region XI | Davao del Norte | 315904 | La Paz National High School | CARMEN | 2 | 1 | 6 | 2STY6CL | Batch 3 | 15651254.21 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Norte | 500450 | Kinamayan IS | SANTO TOMAS | 2 | 1 | 6 | 2STY6CL | Batch 3 | 15699244.51 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Sur | 128832 | Linawan ES | BANSALAN | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4621362.85 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Sur | 129041 | Manga CES | MATANAO | 1 | 1 | 4 | 2STY4CL | Batch 3 | 16090863.98 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Sur | 129051 | Piape ES | PADADA | 1 | 1 | 4 | 2STY4CL | Batch 3 | 16074495.07 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Sur | 129052 | Tulogan ES | PADADA | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4666105.75 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Sur | 129080 | Idong ES | SANTA CRUZ | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4833638.23 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Sur | 129094 | Matutungan ES | SANTA CRUZ | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4885455.71 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Sur | 129142 | Osmeña Elementary School | SULOP | 1 | 1 | 3 | 1STY3CL | Batch 3 | 6976312.03 |  |  | Completed | 1
NC 2018 | SHS | Region XI | Davao del Sur | 304275 | Hagonoy National High School | HAGONOY | 1 | 1 | 8 | 2UNITS 2STY4CL | Batch 3 | 32166772.54 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Sur | 316006 | New Clarin National High School | BANSALAN | 1 | 1 | 4 | 2STY4CL | Batch 3 | 16559735.56 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Sur | 316009 | Kasuga National High School | MAGSAYSAY | 1 | 1 | 4 | 2STY4CL | Batch 3 | 16497815.76 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Sur | 316011 | Libertad National High School | BANSALAN | 1 | 1 | 2 | 1STY2CL | Batch 3 | 5371949.89 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Sur | 316014 | Malinao National High School of Arts and Trade | PADADA | 1 | 1 | 4 | 2STY4CL | Batch 3 | 16811597.29 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Sur | 316015 | Manuel Francisco C. Ramos Sr. National High School | SANTA CRUZ | 1 |  | 4 | 2STY4CL | Batch 3 | 16529401.97 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Sur | 316016 | Maria Cleta R. Delos Cientos National High School | PADADA | 1 |  | 4 | 2STY4CL | Batch 3 | 16601739.7 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao del Sur | 316020 | San Isidro National High School | MAGSAYSAY | 1 | 1 | 4 | 2STY4CL | Batch 3 | 16572408.46 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental | 128842 | Fred Johnson ES | DON MARCELINO | 0 | 1 | 4 | 2UNITS 1STY2CL | Batch 3 | 5502000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental | 128851 | Palamid ES | DON MARCELINO | 0 | 1 | 2 | 1STY2CL | Batch 3 | 2975000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental | 128891 | Aldo Pagagao Elementary School | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | 2 | 1STY2CL | Batch 3 | 3074000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental | 128965 | BUHANGIN ELEMENTARY SCHOOL | MALITA | 0 | 1 | 8 | 2STY8CL | Batch 3 | 19364000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental | 128974 | Lacaron ES | MALITA | 0 | 1 | 2 | 1STY2CL | Batch 3 | 2882000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental | 129067 | Pulabato ES | SARANGANI | 0 | 1 | 4 | 1STY4CL | Batch 3 | 5935000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental | 129103 | Basiawan CES | SANTA MARIA | 0 | 1 | 6 | 2STY6CL | Batch 3 | 13456000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental | 129104 | Buca ES | SANTA MARIA | 0 | 1 | 4 | 1STY4CL | Batch 3 | 5441000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental | 129106 | Cadaatan ES | SANTA MARIA | 0 | 1 | 2 | 1STY2CL | Batch 3 | 3043000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental | 129107 | COLAGSING ES | SANTA MARIA | 0 | 1 | 2 | 1STY2CL | Batch 3 | 3075000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental | 129111 | Jose Timbol Sr. CES | SANTA MARIA | 0 | 1 | 4 | 2STY4CL | Batch 3 | 10329000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental | 129112 | Kidadan ES | SANTA MARIA | 0 | 1 | 2 | 1STY2CL | Batch 3 | 3056000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental | 129114 | Hilario K. Cernal ES | SANTA MARIA | 0 | 1 | 3 | 1STY3CL | Batch 3 | 4431000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental | 129118 | Malalag Tubig ES | SANTA MARIA | 0 | 1 | 4 | 2STY4CL | Batch 3 | 10378000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental | 129120 | Mamacao ES | SANTA MARIA | 0 | 1 | 3 | 1STY3CL | Batch 3 | 4368000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental | 129121 | Migsulang Primary School | SANTA MARIA | 0 | 1 | 2 | 1STY2CL | Batch 3 | 3114000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental | 129123 | Pongpong ES | SANTA MARIA | 0 | 1 | 8 | 2STY8CL | Batch 3 | 19774000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental | 129125 | San Antonio ES | SANTA MARIA | 0 | 1 | 6 | 2UNITS 1STY3CL | Batch 3 | 8430000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental | 129126 | De Guzman- Zapanta ES | SANTA MARIA | 0 | 1 | 3 | 1STY3CL | Batch 3 | 4387000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental | 129127 | San Pedro ES (Ext. School) | SANTA MARIA | 0 | 1 | 4 | 1STY4CL | Batch 3 | 5560000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental | 129129 | Tanglad ES | SANTA MARIA | 0 | 1 | 3 | 1STY3CL | Batch 3 | 4431000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental |  | Heracleo Casco MNHS (Colagsing Ext.) | SANTA MARIA | 0 | 1 | 4 | 2STY4CL | Batch 3 | 10457000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Occidental |  | Kisulad Babac PS | SANTA MARIA | 0 | 1 | 4 | 1STY4CL | Batch 3 | 5537000 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Oriental | 129196 | Buko-Buko ES | BOSTON | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | BATCH 1 | 4089056.55 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Oriental | 129244 | San Jose Central ES | CARAGA | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | BATCH 1 | 3211409.2 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Oriental | 129273 | San Rafael ES | CATEEL | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | BATCH 1 | 3211409.2 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Oriental | 129455 | Maitum ES | TARRAGONA | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | BATCH 1 | 3267041.77 |  |  | Completed | 1
NC 2018 | TVL | Region XI | Davao Oriental | 304334 | Sangab National High School | CARAGA | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | BATCH 1 | 3775104.82 |  |  | Completed | 1
NC 2018 | TVL | Region XI | Davao Oriental | 316102 | Del Pilar NHS | MANAY | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | BATCH 1 | 3851698.33 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Oriental | 316113 | Paulina Gambong Abayon NHS | TARRAGONA | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | BATCH 1 | 3879500.34 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Oriental | 129276 | Taytayan ES | CATEEL | 1 | 1 | 9 | 3STY9CL | Batch 3 | 29690269.77 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Oriental | 129336 | R. Sumambot ES | MANAY | 1 | 1 | 4 | 1STY4CL W/ TOILET ATTACHED | Batch 3 | 9465340.68 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Oriental | 129357 | Gregorio Moralizon ES 2 | MANAY | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 5214938.22 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Oriental | 129357 | Gregorio Moralizon ES 2 | MANAY | 1 |  | 4 | 1STY4CL W/ TOILET ATTACHED | Batch 3 | 9451965.73 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Oriental | 129445 | Cabagayan ES | TARRAGONA | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 5020184.32 |  |  | Completed | 1
NC 2018 | SHS | Region XI | Davao Oriental | 304304 | Boston NHS | BOSTON | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 5014821.52 |  |  | Completed | 1
NC 2018 | SHS | Region XI | Davao Oriental | 304309 | Cateel Nat'l. Agri. HS | CATEEL | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 5278341.83 |  |  | Completed | 1
NC 2018 | SHS | Region XI | Davao Oriental | 304324 | Manay National High School | MANAY | 1 | 1 | 6 | 2STY6CL | Batch 3 | 18028167.36 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Oriental | 305514 | Tubaon NHS | TARRAGONA | 1 | 1 | 3 | 1STY3CL W/ TOILET ATTACHED BLDG. 1 | Batch 3 | 7714774.13 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Davao Oriental | 305514 | Tubaon NHS | TARRAGONA | 1 |  | 3 | 1STY3CL W/ TOILET ATTACHED BLDG. 2 | Batch 3 | 7692686.41 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Digos City | 129754 | Lungag ES | CITY OF DIGOS (Capital) | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 5291428.03 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Digos City | 129756 | Remedios N. Saplala ES (Matti ES) | CITY OF DIGOS (Capital) | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 3 | 5083320.52 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Digos City | 129762 | Aplaya ES | CITY OF DIGOS (Capital) | 1 | 1 | 15 | 3STY15CL | Batch 3 | 39503143.84 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Digos City | 301906 | Goma National High School | CITY OF DIGOS (Capital) | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4684541.14 |  |  | Completed | 1
NC 2018 | TVL | Region XI | Digos City | 341513 | SHS in Digos City | CITY OF DIGOS (Capital) | 1 | 1 | 1 | UNIQUE WORKSHOP | Batch 3 | 5944823.41 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Island Garden City of Samal | 128736 | Peñaplata Central Elementary School SPED Center | ISLAND GARDEN CITY OF SAMAL | 2 |  | 6 | 2STY6CL | Batch 3 | 16466336.35 |  |  | Completed | 1
NC 2018 | TVL | Region XI | Island Garden City of Samal | 304223 | Cogon National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 4 | 2STY4CL (COMPUTER ICT LAB.) | Batch 3 | 13030509 |  |  | Completed | 1
NC 2018 | TVL | Region XI | Island Garden City of Samal | 304223 | Cogon National High School | ISLAND GARDEN CITY OF SAMAL | 2 |  | 4 | 2STY4CL (SCIENCE LAB.) | Batch 3 | 12970509 |  |  | Completed | 1
NC 2018 | SHS | Region XI | Island Garden City of Samal | 304236 | Kaputian National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 8 | 2STY8CL | Batch 3 | 24623298 |  |  | Completed | 1
NC 2018 | SHS | Region XI | Island Garden City of Samal | 341526 | SHS in Penaplata | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 10 | 2STY10CL | Batch 6 Realignment | 28297729.99 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Mati City | 129183 | Mahayag ES | BANAYBANAY | 2 | 1 | 6 | 2STY6CL | Batch 3 | 16831416.01 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Mati City | 129286 | Sigaboy CES | GOVERNOR GENEROSO | 2 | 1 | 6 | 2STY6CL | Batch 3 | 16762160.01 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Mati City | 129300 | Tamban ES | GOVERNOR GENEROSO | 2 | 1 | 4 | 2STY4CL | Batch 3 | 13707344.09 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Mati City | 129318 | Pangyan Elementary School | LUPON | 2 | 1 | 8 | 2UNITS 1STY4CL | Batch 3 | 19077845.97 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Mati City | 129319 | Tagboa ES | LUPON | 2 | 1 | 4 | 2STY4CL | Batch 3 | 13582794.15 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Mati City | 129320 | Tiombocan Elementary School | LUPON | 2 | 1 | 5 | 1STY2CL & 1STY3CL | Batch 3 | 11509306.13 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Mati City | 129381 | Rabat-Rocamora Mati CES II | CITY OF MATI (Capital) | 2 | 1 | 8 | 2STY8CL | Batch 3 | 22074070.65 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Mati City | 129409 | Vicente Almario Sr. MS | CITY OF MATI (Capital) | 2 | 1 | 2 | 1STY2CL | Batch 3 | 4237971.76 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Mati City | 129409 | Vicente Almario Sr. MS | CITY OF MATI (Capital) | 2 |  | 8 | 2UNITS 1STY4CL | Batch 3 | 17951062.68 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Mati City | 129410 | Brigido Rodriguez Sr. ES | CITY OF MATI (Capital) | 2 | 1 | 4 | 2STY4CL | Batch 3 | 13951337.55 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Mati City | 257001 | Jose C. Martinez Jr. Elementary School | CITY OF MATI (Capital) | 2 | 1 | 4 | 2STY4CL | Batch 3 | 13597916.89 |  |  | Completed | 1
NC 2018 | SHS | Region XI | Mati City | 304305 | Buso National High School | CITY OF MATI (Capital) | 2 | 1 | 4 | 2STY4CL | Batch 3 | 13610651.09 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Panabo City | 129784 | Panabo Central Elementary School SPED Center | CITY OF PANABO | 2 | 1 | 6 | 2STY6CL | Batch 3 | 15651452.33 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Panabo City | 129788 | San Vicente ES | CITY OF PANABO | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12370509.55 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Panabo City | 129795 | Nanyo Central ES | CITY OF PANABO | 2 | 1 | 6 | 2STY6CL | Batch 3 | 15651452.33 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Panabo City | 129817 | New Visayas Elementary School | CITY OF PANABO | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12573526.89 |  |  | Completed | 1
NC 2018 | SHS | Region XI | Panabo City | 304405 | Don Manuel A. Javellana Memorial National High School | CITY OF PANABO | 2 | 1 | 6 | 2STY6CL | Batch 3 | 16305053.05 |  |  | Completed | 1
NC 2018 | TVL | Region XI | Panabo City | 304408 | Panabo National High School | CITY OF PANABO | 2 | 1 | 4 | 2UNITS REGULAR TVL WORKSHOP BLDG. | Batch 3 | 8216248.7 |  |  | Completed | 1
NC 2018 | SHS | Region XI | Panabo City | 304409 | Little Panay National High School | CITY OF PANABO | 2 | 1 | 6 | 2STY6CL | Batch 3 | 15651452.33 |  |  | Completed | 1
NC 2018 | TVL | Region XI | Panabo City | 316402 | San Vicente National High School | CITY OF PANABO | 2 | 1 | 2 | 1UNIT UNIQUE TVL WORKSHOP BLDG. | Batch 3 | 4534074.68 |  |  | Completed | 1
NC 2018 | TVL | Region XI | Panabo City | 316402 | San Vicente National High School | CITY OF PANABO | 2 |  | 4 | 2STY4CL COMP (ICT) LAB. | Batch 3 | 12711551 |  |  | Completed | 1
NC 2018 | SHS | Region XI | Panabo City | 316403 | Kauswagan National High School | CITY OF PANABO | 2 | 1 | 6 | 2STY6CL | Batch 3 | 16011936.35 |  |  | Completed | 1
NC 2018 | SHS | Region XI | Panabo City | 316405 | Quezon High School - Panabo NHS Annex | CITY OF PANABO | 2 | 1 | 6 | 2STY6CL | Batch 3 | 16305053.05 |  |  | Completed | 1
NC 2018 | K10 | Region XI | Tagum City | 128795 | MANGGA ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 30 | 3STY30CL | Batch 3 | 85527000 |  |  | Completed | 1
NC 2018 | SHS | Region XI | Tagum City | 304225 | Tagum City National Comprehensive High School | CITY OF TAGUM (Capital) | 1 | 1 | 20 | 4STY20CL | Batch 3 | 59120000 |  |  | Completed | 1
NC 2019 | K10 | Region XI | Compostela Valley | 128460 | Banglasan ES | MONTEVISTA | 1 | 1 | 3 | 1STY3CL W/ TOILET ATTACHED |  | 6866122.5 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Compostela Valley | 204019 | Cabanggatan ES | MONTEVISTA | 1 | 1 | 4 | 1STY4CL W/ TOILET ATTACHED |  | 9477434.5 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Compostela Valley | 128433 | Inambatan ES | MONKAYO | 1 | 1 | 3 | 1STY3CL W/ TOILET ATTACHED |  | 7030532.5 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Compostela Valley | 128526 | Pongpong ES | NEW BATAAN | 1 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED |  | 5745828.75 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Compostela Valley | 128295 | Doña Josefa ES | LAAK (SAN VICENTE) | 2 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED |  | 5481670 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Compostela Valley | 128408 | Guisok ES | MAWAB | 2 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED |  | 4743328.75 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Compostela Valley | 128543 | Gumayan ES | PANTUKAN | 2 | 1 | 3 | 1STY3CL W/ TOILET ATTACHED |  | 7557897.625 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Compostela Valley | 128302 | Kapatagan ES | LAAK (SAN VICENTE) | 2 | 1 | 10 | 2STY10CL |  | 35203697.2988 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Compostela Valley | 128370 | Manipongol ES | MACO | 2 | 1 | 3 | 1STY3CL W/ TOILET ATTACHED |  | 6625238.8927 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Compostela Valley | 128373 | New Leyte ES | MACO | 2 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED |  | 4743328.75 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Compostela Valley | 128555 | Pantukan ES | PANTUKAN | 2 | 1 | 12 | 2STY12CL |  | 42243345 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region XI | Compostela Valley | 304208 | Pantukan NHS | PANTUKAN | 2 | 1 | 12 | 2STY12CL |  | 42243345 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Compostela Valley | 128417 | San Vicente PS | MAWAB | 2 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED |  | 5244578.75 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Davao City | 129703 | Agdao Elementary School | DAVAO CITY | 1 | 1 | 8 | 4STY8CL |  | 25580055.6625 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region XI | Davao City | 304365 | Erico T. Nograles NHS | DAVAO CITY | 1 | 1 | 24 | 4STY24CL |  | 79423837.4325 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Davao City | 129662 | Kiman-Anao ES | DAVAO CITY | 2 | 1 | 3 | 1STY3CL |  | 8021061.6475 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Davao City | 129678 | Tibungol ES | DAVAO CITY | 2 | 1 | 3 | 1STY3CL |  | 8001011.6475 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Davao City | 8888 | Cabagaayan ES | DAVAO CITY | 3 | 1 | 6 | 2UNITS 1STY3CL |  | 14337537.3572 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Davao City | 129571 | Masicampo ES | DAVAO CITY | 3 | 1 | 6 | 2STY6CL |  | 21808019.288 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Davao del Norte | 204501 | Camansa Lower Elementary School | ASUNCION (SAUG) | 1 | 1 | 2 | 1STY2CL W/TOILET |  | 4292705 |  | REVERTED | 0 | [11 empty] | 1
NC 2019 | K10 | Region XI | Davao del Norte | 204533 | Dr. Vislumino Y. Tamondong Elementary School | KAPALONG | 1 | 1 | 3 | 1STY3CL W/ TOILET |  | 6427027.5 |  | completed | 1 |  |  |  |  | 8/2/2019 | [6 empty] | 0
NC 2019 | SHS | Region XI | Davao del Norte | 315906 | Pinamuno National High School | SAN ISIDRO | 1 | 1 | 4 | 2STY4CL |  | 13784295.8025 |  | completed | 1 |  |  |  |  | 8/2/2019 | [6 empty] | 0
NC 2019 | K10 | Region XI | Davao del Norte | 128643 | Tubod ES | CARMEN | 2 | 1 | 5 | 1STY5CL W/ TOILET ATTACHED |  | 10251615.125 |  | completed | 1 |  |  |  |  | 8/2/2019 | [6 empty] | 0
NC 2019 | K10 | Region XI | Davao del Sur | 316015 | Manuel Francisco C. Ramos Sr., National High School | SANTA CRUZ | 1 | 1 | 4 | 2STY4CL |  | 16853626.2832 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Davao del Sur | 316016 | Maria Cleta R. Delos Cientos National High School | PADADA | 1 | 1 | 3 | 1STY3CL W/ TOILET ATTACHED |  | 7819148.2528 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Davao Occidental | 129002 | Mana CES | MALITA | 0 | 1 | 4 | 2STY4CL |  | 13019847.4475 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Davao Occidental | 129129 | Tanglad ES | SANTA MARIA | 0 | 1 | 2 | 1STY2CL |  | 4936198.7225 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Davao Oriental | 129198 | Cabasagan ES | BOSTON | 1 | 1 | 8 | 2STY8CL |  | 26063498.6961 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Digos City | 302004 | Dawis National High School | CITY OF DIGOS (Capital) | 1 | 1 | 2 | 1STY2CL |  | 5105488.2409 |  | completed | 1 |  |  |  | 19LD0128 |  | 2019-07-26 | 2019-08-08 |  |  |  |  | 0
NC 2019 | K10 | Region XI | Island Garden City of Samal | 500443 | San Isidro Integrated School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 4 | 2STY4CL |  | 12786796.2725 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Mati City | 129413 | Dawan Central ES | CITY OF MATI (Capital) | 2 | 1 | 4 | 2STY4CL |  | 17164351.2886 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region XI | Mati City | 304313 | Dawan NHS | CITY OF MATI (Capital) | 2 | 1 | 4 | 2STY4CL |  | 17239860.571 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Panabo City | 129790 | P. Changco ES | CITY OF PANABO | 2 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED |  | 4192672.5425 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XI | Tagum City | 128783 | SAN AGUSTIN ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 9 | 3STY9CL |  | 29716706.5 |  | completed | 1 | [11 empty] | 0
NC 2020 | K10 | Region XI | Compostela Valley | 128477 | Sambayon ES | MONTEVISTA | 1 | 1 | 2 | 1STY2CL |  | 5012500 |  |  | completed | 1
NC 2020 | SHS | Region XI | Compostela Valley | 304214 | Union NHS | MONKAYO | 1 | 1 | 8 | 2STY8CL |  | 29336078.7 |  |  | completed | 1
NC 2020 | K10 | Region XI | Compostela Valley | 501055 | Canidkid Integrated School | MONTEVISTA | 1 | 1 | 2 | 1STY2CL |  | 5012500 |  |  | completed | 1
NC 2020 | K10 | Region XI | Compostela Valley | 128535 | Bon-Temple ES | PANTUKAN | 2 | 1 | 4 | 2STY4CL |  | 18145250 |  |  | completed | 1
NC 2020 | K10 | Region XI | Compostela Valley | 128542 | Doroteo De Castro ES | PANTUKAN | 2 | 1 | 4 | 1STY4CL |  | 10025000 |  |  | completed | 1
NC 2020 | K10 | Region XI | Compostela Valley | 128544 | Kingking CES | PANTUKAN | 2 | 1 | 16 | 2UNITS 2STY8CL |  | 66616125 |  |  | completed | 1
NC 2020 | K10 | Region XI | Compostela Valley | 128551 | Nagas ES | PANTUKAN | 2 | 1 | 4 | 2STY4CL |  | 17994875 |  |  | completed | 1
NC 2020 | K10 | Region XI | Compostela Valley | 128555 | Pantukan ES | PANTUKAN | 2 | 1 | 8 | 2STY8CL |  | 33508562.5 |  |  | completed | 1
NC 2020 | SHS | Region XI | Compostela Valley | 301358 | Mabuhay NHS | LAAK (SAN VICENTE) | 2 | 1 | 8 | 2STY8CL |  | 30075000 |  |  | completed | 1
NC 2020 | SHS | Region XI | Compostela Valley | 304211 | Tambongon NHS | PANTUKAN | 2 | 1 | 9 | 3STY9CL |  | 34586250 |  |  | completed | 1
NC 2020 | K10 | Region XI | Compostela Valley |  | Mansinaon ES | LAAK (SAN VICENTE) | 2 | 1 | 4 | 2UNITS 1STY2CL |  | 12090150 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao City | 129561 | Wireless ES | DAVAO CITY | 1 | 1 | 20 | 4STY20CL (L-TYPE) |  | 52988069.83 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao City | 129695 | Elpidio Quirino ES | DAVAO CITY | 1 | 1 | 21 | 3STY21CL |  | 56836768.58 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao City | 129713 | Baliok ES | DAVAO CITY | 1 | 1 | 9 | 3STY9CL |  | 29683529.77 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao City | 129715 | Catalunan Grande ES | DAVAO CITY | 1 | 1 | 15 | 3STY15CL |  | 42026930.31 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao City | 129715 | Catalunan Grande ES | DAVAO CITY | 1 |  | 12 | 3STY12CL |  | 35236376.26 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao City | 129715 | Catalunan Grande ES | DAVAO CITY | 1 |  | 6 | 3STY6CL |  | 16468777.27 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao City | 129717 | Davao City Special School | DAVAO CITY | 1 | 1 | 15 | 3STY15CL |  | 42828930.31 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao City | 129717 | Davao City Special School | DAVAO CITY | 1 |  | 15 | 3STY15CL |  | 42302617.81 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao City | 129506 | Buhangin CES SPED CENTER | DAVAO CITY | 2 | 1 | 12 | 3STY12CL |  | 37593750 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao City | 129469 | Malagos ES SPED Center | DAVAO CITY | 3 | 1 | 4 | 2STY4CL |  | 12795913.82 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao City | 129474 | Tawantawan ES | DAVAO CITY | 3 | 1 | 4 | 2STY4CL |  | 12795913.82 |  |  | completed | 1
NC 2020 | K10 | Region XI | Davao City | 129502 | Tagurano ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL |  | 5133287.08 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao City | 129503 | Tibuloy ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL |  | 5133287.08 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao City | 129533 | Dalagdag ES | DAVAO CITY | 3 | 1 | 4 | 2STY4CL |  | 12795913.82 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao City | 129535 | Lacson ES | DAVAO CITY | 3 | 1 | 4 | 2STY4CL |  | 12795913.82 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao City | 129564 | Darila ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL |  | 5133287.08 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao City | 129569 | Lamanan ES | DAVAO CITY | 3 | 1 | 2 | 1STY2CL |  | 5133287.08 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao City | 129629 | SALAYSAY ELEMENTARY SCHOOL | DAVAO CITY | 3 | 1 | 4 | 2STY4CL |  | 12795913.82 |  |  | Completed | 1
NC 2020 | SHS | Region XI | Davao City | 301748 | Catigan National High School | Davao City | 3 | 1 | 12 | 4STY12CL |  | 33570058.01 |  |  | Completed | 1
NC 2020 | SHS | Region XI | Davao City | 304355 | Wangan National High School | DAVAO CITY | 3 | 1 | 4 | 2STY4CL |  | 12795913.82 |  |  | completed | 1
NC 2020 | K10 | Region XI | Davao City | 501072 | Baracayo Integrated School | DAVAO CITY | 3 | 1 | 4 | 2STY4CL |  | 12795913.82 |  |  | Completed | 1
NC 2020 | SHS | Region XI | Davao City | 304387 | Angalan NHS | DAVAO CITY | 3 | 1 | 4 | 2STY4CL |  | 12795913.82 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao del Norte | 128646 | Agman ES | SAN ISIDRO | 1 | 1 | 3 | 1STY3CL WITH TOILET ATTACHED |  | 7518750 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao del Norte | 204502 | Mangguangan ES | NEW CORELLA | 1 | 1 | 3 | 1STY3CL WITH TOILET ATTACHED |  | 7518750 |  |  | Completed | 1
NC 2020 | SHS | Region XI | Davao del Norte | 500789 | Sampao IS | KAPALONG | 1 | 1 | 3 | 1STY3CL WITH TOILET ATTACHED |  | 7518750 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao del Norte | 128618 | Dujali Central Elementary School | BRAULIO E. DUJALI | 2 | 1 | 8 | 2STY8CL |  | 27568750 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao del Norte | 204537 | Maguintalunan Elementary School | SANTO TOMAS | 2 | 1 | 3 | 1STY3CL |  | 7017500 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao del Sur | 305509 | Lapulabao National High School | HAGONOY | 0 | 1 | 10 | 2STY10CL |  | 25137241.39 |  |  | completed | 1
NC 2020 | K10 | Region XI | Davao Occidental | 128991 | Ismael Yahya ES | MALITA | 0 | 1 | 2 | 1STY2CL |  | 4936198.72 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao Occidental | 129108 | Cumasi ES | SANTA MARIA | 0 | 1 | 4 | 2STY4CL |  | 13784296.06 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Davao Occidental |  | Jose Abad Santos NHS (Mangili Extension) | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | 2 | 1STY2CL WITH TOILET ATTACHED |  | 5182120.44 |  |  | completed | 1
NC 2020 | K10 | Region XI | Davao Oriental | 129241 | Mercedes Elementary School | CARAGA | 1 | 1 | 4 | 1STY4CL WITH TOILET ATTACHED |  | 9912552.69 |  |  | completed | 1
NC 2020 | K10 | Region XI | Davao Oriental | 129444 | Baisan ES | TARRAGONA | 1 | 1 | 2 | 1STY2CL WITH TOILET ATTACHED |  | 5678322.34 |  |  | completed | 1
NC 2020 | K10 | Region XI | Davao Oriental | 205512 | Nursery ES | BAGANGA | 1 | 1 | 2 | 1STY2CL WITH TOILET ATTACHED |  | 5566255.93 |  |  | completed | 1
NC 2020 | K10 | Region XI | Davao Oriental | 205512 | Nursery ES | BAGANGA | 1 |  | 3 | 1STY3CL WITH TOILET ATTACHED |  | 7898959.66 |  |  | completed | 1
NC 2020 | SHS | Region XI | Davao Oriental | 304333 | San Luis NHS | CARAGA | 1 | 1 | 10 | 2STY10CL |  | 29474552.99 |  |  | Completed | 1
NC 2020 | SHS | Region XI | Davao Oriental | 500457 | Maylaya IS | CATEEL | 1 | 1 | 2 | 1STY2CL WITH TOILET ATTACHED |  | 5543218.04 |  |  | completed | 1
NC 2020 | SHS | Region XI | Davao Oriental | 500457 | Maylaya IS | CATEEL | 1 |  | 2 | 1STY2CL WITH TOILET ATTACHED |  | 5553224.89 |  |  | completed | 1
NC 2020 | K10 | Region XI | Digos City | 129773 | Apolandia ES | CITY OF DIGOS (Capital) | 1 | 1 | 4 | 2STY4CL |  | 17143196.11 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Mati City | 129407 | Tamisan Elementary School | CITY OF MATI (Capital) | 2 | 1 | 6 | 2STY6CL |  | 22625383 |  |  | completed | 1
NC 2020 | K10 | Region XI | Panabo City | 129802 | Consolacion ES | CITY OF PANABO | 2 | 1 | 6 | 2STY6CL |  | 18350821.65 |  |  | Completed | 1
NC 2020 | K10 | Region XI | Panabo City | 129805 | J.P. Laurel ES | City of Panabo | 2 | 1 | 4 | 2STY4CL |  | 12604969.84 |  |  | completed | 1
NC 2020 | SHS | Region XI | Tagum City | 305519 | Magdum National High School | CITY OF TAGUM (Capital) | 1 | 1 | 6 | 3STY6CL |  | 20551250 |  |  | completed | 1
NC 2021 | K10 | Region XI | Compostela Valley | 128346 | Concepcion ES | MACO | 2 | 1 | 4 | Construction/Completion (2STY6CL) |  | 25831763.9039 | 25767345.54 |  | Completed | 1
NC 2021 | K10 | Region XI | Compostela Valley | 128370 | Manipongol ES | MACO | 2 | 1 | 3 | Construction/Completion (1STY3CL W/ TOILET ATTACHED) |  | 616537.5 | 615000 |  | Completed | 1
NC 2021 | K10 | Region XI | Compostela Valley | 128373 | New Leyte ES | MACO | 2 | 1 | 2 | Construction/Completion (1STY2CL W/ TOILET ATTACHED) |  | 170425 | 170000 |  | Completed | 1
NC 2021 | K10 | Region XI | Compostela Valley | 128408 | Guisok ES | MAWAB | 2 | 1 | 2 | Construction/Completion (1STY2CL W/ TOILET ATTACHED) |  | 170425 | 170000 |  | Completed | 1
NC 2021 | K10 | Region XI | Compostela Valley | 128539 | Bongbong ES | PANTUKAN | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 19348250 | 19300000 |  | Completed | 1 | 2022-11-30
NC 2021 | SHS | Region XI | Compostela Valley | 304211 | Tambongon NHS | PANTUKAN | 2 | 1 | 8 | Construction/Completion (2STY8CL) |  | 27836763.9239 | 27767345.56 |  | Completed | 1
NC 2021 | K10 | Region XI | Davao City | 129561 | Wireless ES | DAVAO CITY | 1 | 1 | 20 | Construction/Completion (4STY20CL (L-TYPE)) |  | 6215500 | 6200000 |  | COMPLETED | 1 | 2022-09-30
NC 2021 | SHS | Region XI | Davao City |  | Dona Soledad Duterte HS | DAVAO CITY | 1 | 1 | 12 | Construction/Completion (3STY12CL) |  | 1133838.5275 | 1131011 |  | Completed | 1
NC 2021 | K10 | Region XI | Davao del Norte | 500448 | Nasilaban Integrated School | TALAINGOD | 1 | 1 | 9 | Construction/Completion (3STY9CL) |  | 39755879.845 | 39656738 |  | COMPLETED | 1 | 2022-12-31 | [9 empty] | Funds intended for two (2) contracts (21LC0238 and 21LC0239) was allocated in this contract (21LC0245) due to request for realignment as per letter dated July 8, 2021 of Joselito B. Caballero, DE, this Office to Dr. Dee D. Silva, DPA, CESO IV, Schoold Division Superintendent, DepEd since the proposed school building is situated in a highly landslide susceptible area based on the Geohazard Certificate issued on June 16 ,2021 by the Mines and Geosciences Bureau, Regional Office XI, Davao City.
NC 2021 | K10 | Region XI | Davao del Norte | 500448 | Nasilaban Integrated School | TALAINGOD | 1 |  | 3 | Construction/Completion (1STY3CL) |  | 5254078.449 | 5240976 |  | COMPLETED | 1 | 2022-12-31 | [9 empty] | Funds intended for two (2) contracts (21LC0238 and 21LC0239) was allocated in this contract (21LC0245) due to request for realignment as per letter dated July 8, 2021 of Joselito B. Caballero, DE, this Office to Dr. Dee D. Silva, DPA, CESO IV, Schoold Division Superintendent, DepEd since the proposed school building is situated in a highly landslide susceptible area based on the Geohazard Certificate issued on June 16 ,2021 by the Mines and Geosciences Bureau, Regional Office XI, Davao City.
NC 2021 | K10 | Region XI | Davao del Norte | 128634 | Magsaysay ES | CARMEN | 2 | 1 | 1 | Construction/Completion of School Buildings |  | 2506250.004 | 2500000 |  | Completed | 1
NC 2021 | K10 | Region XI | Davao Oriental | 129198 | Cabasagan ES | BOSTON | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 2041588.944 | 2036497.7 |  | Completed | 1
NC 2021 | K10 | Region XI | Digos City | 129773 | Apolandia ES | CITY OF DIGOS (Capital) | 1 | 1 | 1 | Construction/Completion (1STY1CL) |  | 1503750.004 | 1500000 |  | Completed | 1 | 2021-11-22 | 2021-11-15 | P00575069MN | 21LD0101 |  | 2021-07-22 | 2021-05-08 | 2021-09-15 | 2021-09-23 | R.C. Melgazo Builders
NC 2021 | K10 | Region XI | Tagum City | 128783 | SAN AGUSTIN ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 9 | Construction/Completion (3STY9CL) |  | 9340407.289 | 9317114.5 |  | Completed | 1
NC 2021 | SHS | Region XI | Tagum City | 305519 | Magdum National High School | CITY OF TAGUM (Capital) | 1 | 1 | 6 | Construction/Completion (3STY6CL) |  | 8556785.619 | 8535447 |  | Completed | 1
NC 2022 | K10 | Region XI | Davao City | 129243 | Congressman Manuel M. Garcia Elementary School | DAVAO CITY | 2 | 1 | 12 | Replacement of burned schoolbuilding 3sty12cl | 2 |  | 47117500 |  | Completed | 1 | 2023-09-13
NC 2022 | K10 | Region XI | Davao del Norte | 128667 | Pinamuno ES - Mamaon Ext. | SAN ISIDRO | 1 | 1 | 2 | 1STY2CL | 2 |  | 10025000 |  | Completed | 1
NC 2022 | K10 | Region XI | Mati City | 129398 | Gov. Leopoldo Lopez Sr. MS | CITY OF MATI (Capital) | 2 | 1 | 2 | 1STY2CL, ICT & SL | 2 |  | 5172900 |  | Completed | 1 | 2023-05-29
NC 2022 | K10 | Region XI | Mati City | 129398 | Gov. Leopoldo Lopez Sr. MS | CITY OF MATI (Capital) | 2 |  | 2 | 1STY2CL Pre-School | 2 |  | 4932300 |  | Completed | 1 | 2023-05-20
NC 2022 | K10 | Region XI | Mati City | 129403 | Tagabakid ES | CITY OF MATI (Capital) | 2 | 1 | 6 | 2STY6CL with ICT & SL | 2 |  | 19037475 |  | Completed | 1 | 2023-07-17
NC 2022 | K10 | Region XI | Mati City | 129403 | Tagabakid ES | CITY OF MATI (Capital) | 2 |  | 3 | 1STY3CL, Regular Classroom w/ Attached Toilet | 2 |  | 6025025 |  | Completed | 1 | 2023-06-08
NC 2022 | SHS | Region XI | Mati City | 304318 | Libudon NHS (Sanghay Campus) | CITY OF MATI (Capital) | 2 | 1 | 8 | 2STY8CL WITH ICT & SL | 2 |  | 25704100 |  | Completed | 1 | 2023-07-24
NC 2022 | SHS | Region XI | Mati City | 325105 | Macambol NHS | CITY OF MATI (Capital) | 2 | 1 | 8 | 2STY8CL WITH ICT & SL | 2 |  | 25443450 |  | Completed | 1 | 2023-08-02
NC 2023 | SHS | Region XI | Davao City | 304360 | Davao City NHS | DAVAO CITY |  | 1 |  |  | Batch 1 | 20643355.45 | 20464292.89 | 19843911.3 | Completed | 1 | 2024-02-04 | 2024-08-12 | 23LB0151 | 23LB0151 | 2023-06-09 |  | 2023-07-11 | 2023-07-14 | 2023-08-09 | BROSCO CONSTRUCTION AND DEVELOPMENT
NC 2023 | SHS | Region XI | Davao City | 304349 | Binowang National High School | DAVAO CITY |  | 1 |  | 6 | Batch 1 | 30262500 | 30000000 | 29249880.3 | Completed | 1 | 2024-02-04 | 2024-06-03 | 23LH0132 |  | 2023-06-09 |  | 2023-07-11 | 2023-07-14 | 2023-08-09 | SIXGLAM BUILDERS AND SUPPLY
NC 2023 | K10 | Region XI | Davao City | 305890 | Norberto G. Bacaro Sr. National High School | DAVAO CITY |  | 1 |  | 8 | Batch 1 | 30262500 | 30000000 | 29439937.36 | ongoing | 0.75 | 2024-08-01 | 2024-12-09 | 23LH0113 |  | 2023-11-27 |  | 2023-12-04 | 2023-12-19 | 2024-01-05 | EDCL CONSTRUCTION AND SUPPLY
NC 2023 | K10 | Region XI | Davao De Oro | 128277 | T.H. Valderrama ES | COMPOSTELA |  | 1 |  | 4 | Batch 1 | 17965837.5 | 17810000 | 17809943.62 | completed | 1 | 2024-03-05 | 2024-03-05 | 23LI-0123 | 23LI-0123 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-31 | 2023-08-09 | MBANGLO ARKIKONS ARCHITECTURAL CONST.& SUPPLY
NC 2023 | K10 | Region XI | Davao De Oro | 128383 | Katipunan Elementary School | MARAGUSAN |  | 1 |  | 4 | Batch 1 | 18557973.75 | 18397000 | 18376917.65 | Completed | 1 | 2024-06-23 | 2024-03-05 | 23LI-0130 | 23LI-0130 | 2023-10-20 | 2023-10-27 | 2023-11-09 | 2023-12-18 | 2023-12-27 | TWO DEGREES CONSTRUCTION & SUPPLY
NC 2023 | K10 | Region XI | Davao De Oro | 128426 | Bagong Taas ES | MONKAYO |  | 1 |  | 4 | Batch 1 | 17874646.5 | 17719600 | 17719036.57 | Completed | 1 | 2024-06-05 | 2024-03-05 | 23LI-0126 | 23LI-0126 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-31 | 2023-08-09 | PMMGS CONST CORP
NC 2023 | K10 | Region XI | Davao De Oro | 204011 | Paco ES | MONKAYO |  | 1 |  | 6 | Batch 1 | 25214715 | 24996000 | 24620311.86 | completed | 1 | 2024-02-24 | 2024-03-05 | 23LI-0127 | 23LI-0127 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-31 | 2023-08-09 | PMMGS CONST CORP
NC 2023 | SHS | Region XI | Davao De Oro | 300640 | Camansi National High School | MONTEVISTA |  | 1 |  | 6 | Batch 1 | 25169926.5 | 24951600 | 24697853.98 | completed | 1 | 2024-03-10 | 2024-03-10 | 23LI-0129 | 23LI-0129 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-31 | 2023-08-09 | MITCH CONST. CORP
NC 2023 | K10 | Region XI | Davao De Oro | 128468 | Magtaya ES | MONTEVISTA |  | 1 |  | 4 | Batch 1 | 18318900 | 18160000 | 18139681.11 | completed | 1 | 2024-02-04 | 2024-02-04 | 23LI-0124 | 23LI-0124 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-31 | 2023-08-09 | ROSBILL CONST.&SUPPLY
NC 2023 | K10 | Region XI | Davao De Oro | 128519 | Magangit Elementary School | NEW BATAAN |  | 1 |  | 4 | Batch 1 | 18012240 | 17856000 | 17845993.15 | Completed | 1 | 2024-06-08 | 2024-06-08 | 23LI-0128 | 23LI-0128 | 2023-10-20 | 2023-10-27 | 2023-11-09 | 2023-12-18 | 2023-12-27 | ROSBILL CONST.&SUPPLY
NC 2023 | K10 | Region XI | Davao De Oro | 501366 | Pongpong Integrated School | NEW BATAAN |  | 1 |  | 2 | Batch 1 | 6543256.88 | 6486500 | 6486533.29 | completed | 1 | 2024-02-21 | 2024-02-21 | 23LI-0125 | 23LI-0125 | 2023-06-30 | 2023-07-07 | 2023-07-25 | 2023-08-08 | 2023-09-25 | TAGUM CONSTRAK CORP
NC 2023 | K10 | Region XI | Davao De Oro | 128338 | Masicareg ES | MABINI (DOÑA ALICIA) |  | 1 |  | 2 | Batch 1 | 6127147.5 | 6074000 | 6023380 | completed | 1 | 2023-11-03 | 2023-11-03 | 23LA-0113 | 23LA-0113 | 2023-07-03 | 2023-07-04 | 2023-07-10 | 2023-08-01 | 2023-08-11 | DOUBLE J CONSTRUCTION & SUPPLY
NC 2023 | K10 | Region XI | Davao De Oro | 128364 | Calabcab ES | MACO |  | 1 |  | 2 | Batch 1 | 5781650.63 | 5731500 | 5701420 | completed | 1 | 2024-01-02 | 2024-02-26 | 23LA-0112 | 23LA-0112 | 2023-07-03 | 2023-07-04 | 2023-07-10 | 2023-08-01 | 2023-08-11 | AGONG BUIDERS & SUPPLY CORP
NC 2023 | K10 | Region XI | Davao De Oro | 305772 | New Visayas National High School | MACO |  | 1 |  | 2 | Batch 1 | 6286025.63 | 6231500 | 6221340 | completed | 1 | 2024-01-02 | 2024-02-16 | 23LA-0111 | 23LA-0111 | 2023-06-29 | 2023-07-04 | 2023-07-10 | 2023-08-01 | 2023-08-11 | MARK ANTHONY CONST & SUPPLY
NC 2023 | K10 | Region XI | Davao De Oro | 300588 | Boringot National High School | PANTUKAN |  | 1 |  | 4 | Batch 1 | 12067676.25 | 11963000 | 11909260 | Completed | 1 | 2024-06-10 | 2023-11-28 | 23LA-0124 | 23LA-0124 | 2023-10-22 | 2023-11-28 | 2023-12-05 | 2023-12-21 | 2023-12-29 | TAGUM BUILDERS CONTRACTORS CORP
NC 2023 | K10 | Region XI | Davao del Norte | 500846 | Rizal Integrated School | ASUNCION (SAUG) |  | 1 |  | 6 | Batch 1 | 30262500 | 30000000 | 30000000 | Ongoing | 0.98 | 2024-05-21 |  | P00775016MN | 23LC0083 | 2023-12-07 | 2023-07-19 | 2023-08-22 | 2023-08-31 | 2023-08-09 | EGCGM Builders and Marketing Corp.
NC 2023 | K10 | Region XI | Davao del Norte | 128648 | Dacudao ES | SAN ISIDRO |  | 1 |  | 2 | Batch 1 | 6959769.75 | 6899400 | 6899000 | completed | 1 | 2023-12-15 | 2023-11-19 | P00775018MN | 23LC0082 | 2023-06-23 | 2023-06-30 | 2023-07-13 | 2023-02-08 | 2023-08-17 | Golden Buildaxis Corporation
NC 2023 | K10 | Region XI | Davao del Norte | 128590 | Sabangan ES | SAN ISIDRO |  | 1 |  | 2 | Batch 1 | 6708187.5 | 6650000 | 6583630 | completed | 1 | 2023-12-31 | 2023-11-18 | P00775017MN | 23LC0081 | 2023-06-23 | 2023-06-30 | 2023-07-13 | 2023-02-08 | 2023-08-17 | Andrich Construction
NC 2023 | SHS | Region XI | Davao del Norte | 304222 | Carmen NHS | CARMEN |  | 1 |  | 6 | Batch 1 | 18422473.98 | 18262675.57 | 19823900.06 | Ongoing | 0.85 | 2024-07-31 |  | P00775019MN | 23LO0217 | 2023-08-30 | 2023-06-09 | 2023-09-19 | 2023-12-15 | 2024-01-15 | Vibranium Builders Corporation
NC 2023 | SHS | Region XI | Davao del Norte | 304254 | Sto Tomas NHS | SANTO TOMAS |  | 1 |  | 4 | Batch 1 | 11451808.4 | 11352474.25 | 9469071.31 | completed | 1 | 2024-04-05 | 2024-02-07 | P00775020MN | 23LO0218 | 2023-08-30 | 2023-06-09 | 2023-09-19 | 2023-12-15 | 2024-02-01 | Rangay Construction and Supply
NC 2023 | K10 | Region XI | Davao del Sur | 128827 | Darapuay Elementary School | BANSALAN |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4979421.98 | Completed | 1 | 2023-11-01 | 2023-11-13 | 23LD0104 | 23LD0104 | 2023-06-23 | 2023-07-04 | 2023-07-18 | 2023-07-27 | 2023-08-07 | NLC CONSTRUCTION AND SUPPLIES
NC 2023 | K10 | Region XI | Davao del Sur | 128829 | Eman Elementary School | BANSALAN |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4911677.61 | Completed | 1 | 2023-11-01 | 2023-11-03 | 23LD0105 | 23LD0105 | 2023-06-23 | 2023-07-04 | 2023-07-18 | 2023-07-27 | 2023-08-07 | JLACE BUILDERS CORPORATION
NC 2023 | K10 | Region XI | Davao del Sur | 128830 | Kinuskusan Elementary School | BANSALAN |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4850057.62 | Completed | 1 | 2023-11-01 | 2023-11-15 | 23LD0106 | 23LD0106 | 2023-06-23 | 2023-07-04 | 2023-07-18 | 2023-07-27 | 2023-08-07 | H-ROYAL CONSTRUCTION
NC 2023 | K10 | Region XI | Davao del Sur | 305883 | Manual National High School | KIBLAWAN |  | 1 |  | 6 | Batch 1 | 30262500 | 30000000 | 29511988.64 | Completed | 1 | 2024-01-31 | 2024-02-21 | 23LD0110 | 23LD0110 | 2023-07-06 | 2023-07-13 | 2023-08-22 | 2023-08-31 | 2023-09-12 | ZJN DEVELOPMENT CONSTRUCTION AND SUPPLY CORPORATION
NC 2023 | K10 | Region XI | Davao del Sur | 205046 | Asbang-Elok Elementary School | MAGSAYSAY |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4849840.61 | Completed | 1 | 2023-11-10 | 2023-11-10 | 23LD0107 | 23LD0107 | 2023-06-23 | 2023-07-04 | 2023-07-18 | 2023-08-07 | 2023-08-17 | DQMB CONSTRUCTION & SUPPLY CORP.
NC 2023 | K10 | Region XI | Davao del Sur | 128946 | Baybay Elementary School | MALALAG |  | 1 |  | 10 | Batch 1 | 50437500 | 50000000 | 49499353.68 | ongoing | 0.95 | 2024-03-06 |  | 23LD0111 | 23LD0111 | 2023-07-06 | 2023-07-13 | 2023-08-22 | 2023-08-31 | 2023-09-12 | AGONG BUILDERS AND CONSTRUCTION SUPPLY,INC.
NC 2023 | K10 | Region XI | Davao del Sur | 129038 | La Suerte Elementary School | MATANAO |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4849798.73 | Completed | 1 | 2023-11-10 | 2023-11-10 | 23LD0108 | 23LD0108 | 2023-06-23 | 2023-07-04 | 2023-07-18 | 2023-08-07 | 2023-08-17 | GLU2R CONSTRUCTION CORP.
NC 2023 | SHS | Region XI | Davao del Sur | 304288 | Matanao National High School | MATANAO |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4698421.98 | Completed | 1 | 2023-11-10 | 2024-02-21 | 23LD0109 | 23LD0109 | 2023-06-23 | 2023-07-04 | 2023-07-18 | 2023-08-07 | 2023-08-17 | MJTP CONSTRUCTION
NC 2023 | K10 | Region XI | Davao Occidental | 109395 | Datu Tawang Elementary School | JOSE ABAD SANTOS (TRINIDAD) |  | 1 |  | 2 | Batch 1 | 5245500 | 5200000 | 5194963.87 | Completed | 1 | 2023-09-30 | 2023-09-30 | P00775029MN | 23LE0075 | 2023-05-31 | 2023-06-07 | 2023-06-20 | 2023-06-23 | 2023-07-12 | Wolfram Trade Builder's
NC 2023 | K10 | Region XI | Davao Occidental | 128892 | Manuel Medel Sr. Elementary School | JOSE ABAD SANTOS (TRINIDAD) |  | 1 |  | 3 | Batch 2 | 10161610.88 | 9817981.53 |  | ongoing | 0.75 | 2024-04-26 |  | P00775620MN | 23LE0086 | 2023-05-31 | 2023-06-07 | 2023-06-20 | 2023-06-23 | 2023-07-12
NC 2023 | K10 | Region XI | Davao Occidental | 129068 | Quiapo Elementary School | JOSE ABAD SANTOS (TRINIDAD) |  | 1 |  | 2 | Batch 1 | 5245500 | 5200000 | 5195016.38 | completed | 1 | 2023-09-30 | 2023-09-30 | P00775030MN | 23LE0076 | 2023-05-31 | 2023-06-07 | 2023-06-20 | 2023-06-23 | 2023-07-12 | Wolfram Trade Builder's
NC 2023 | SHS | Region XI | Davao Occidental | 305674 | Buhangin National High School | MALITA |  | 1 |  | 2 | Batch 1 | 4791562.5 | 4750000 | 4744963.53 | Completed | 1 | 2023-09-30 | 2023-09-30 | P00775033MN | 23LE0078 | 2023-05-31 | 2023-06-07 | 2023-06-20 | 2023-06-23 | 2023-07-12 | Wolfram Trade Builder's
NC 2023 | K10 | Region XI | Davao Occidental | 128977 | Malita Central Elementary School | MALITA |  | 1 |  | 2 | Batch 1 | 4791562.5 | 4750000 | 4745098.11 | completed | 1 | 2023-09-30 | 2023-09-30 | P00775031MN | 23LE0077 | 2023-05-31 | 2023-06-07 | 2023-06-20 | 2023-06-23 | 2023-07-12 | Wolfram Trade Builder's
NC 2023 | SHS | Region XI | Davao Occidental | 304287 | Mariano Peralta National High School | MALITA |  | 1 |  | 2 | Batch 1 | 4791562.5 | 4750000 | 4745098.11 | completed | 1 | 2023-10-13 | 2023-10-13 | P00775032MN | 23LE0084 | 2023-06-07 | 2023-06-20 | 2023-07-04 | 2023-07-17 | 2023-07-25 | Wolfram Trade Builder's
NC 2023 | K10 | Region XI | Davao Occidental | 129102 | Babak PS | SANTA MARIA |  | 1 |  | 5 | Batch 1 | 10732989.77 | 10639890.72 | 10634851.3 | Completed | 1 | 2024-01-21 | 2024-01-21 | P00775035MN | 23LE0080 | 2023-06-15 | 2023-06-20 | 2023-07-04 | 2023-07-17 | 2023-07-25 | Disem Construction & Supply
NC 2023 | K10 | Region XI | Davao Occidental | 501911 | Buca Integrated School | SANTA MARIA |  | 1 |  | 5 | Batch 1 | 10732989.77 | 10639890.72 | 10634518.01 | Completed | 1 | 2023-01-21 | 2023-01-21 | P00775037MN | 23LE0082 | 2023-06-15 | 2023-06-20 | 2023-07-04 | 2023-07-17 | 2023-07-25 | Disem Construction & Supply
NC 2023 | K10 | Region XI | Davao Occidental | 129110 | Doña Regina ES | SANTA MARIA |  | 1 |  | 2 | Batch 1 | 4788571.5 | 4747034.94 | 4742030.6 | completed | 1 | 2023-11-02 | 2023-11-02 | P00775036MN | 23LE0081 | 2023-06-07 | 2023-06-20 | 2023-07-04 | 2023-07-17 | 2023-07-25 | Wolfram Trade Builder's
NC 2023 | K10 | Region XI | Davao Occidental | 109429 | Leonila Limboran Elementary School | SANTA MARIA |  | 1 |  | 2 | Batch 1 | 4788571.5 | 4747034.94 | 4742083.1 | ongoing | 0.43 | 2023-09-30 |  | P00775034MN | 23LE0079 | 2023-05-31 | 2023-06-07 | 2023-06-20 | 2023-06-23 | 2023-07-12 | Wolfram Trade Builder's
NC 2023 | K10 | Region XI | Davao Occidental | 129063 | Mabila CES | SARANGANI |  | 1 |  | 2 | Batch 1 | 5396812.5 | 5350000 | 5344966.11 | Completed | 1 | 2023-11-02 | 2023-11-02 | P00775038MN | 23LE0083 | 2023-06-07 | 2023-06-20 | 2023-07-04 | 2023-07-17 | 2023-07-25 | Wolfram Trade Builder's
NC 2023 | K10 | Region XI | Davao Oriental | 136928 | Francisco D. Minghi Elementary School | BAGANGA |  | 1 |  | 2 | Batch 1 | 6610678.43 | 6553336.73 | 6487279.77 | completed | 1 | 2023-10-11 | 2024-04-18 | P00775045MN | 23LF0147 |  | 2023-06-01 | 2023-06-13 | 2023-07-06 | 2023-07-20 | FZI
NC 2023 | K10 | Region XI | Davao Oriental | 136958 | Limot Elementary School | BAGANGA |  | 1 |  | 2 | Batch 1 | 6531619.67 | 6474963.74 | 6465115.1 | completed | 1 | 2023-10-11 | 2023-10-11 | P00775044MN | 23LF0146 |  | 2023-06-01 | 2023-06-13 | 2023-07-06 | 2023-07-20 | LORDS IVAN
NC 2023 | K10 | Region XI | Davao Oriental | 136960 | Mantapay Elementary School | BAGANGA |  | 1 |  | 2 | Batch 2 | 7968386.42 | 7698924.08 | 7584895.47 | Completed | 1 | 2023-06-11 | 2024-10-03 | P00775619MN | 23LF0156 |  | 2023-09-20 | 2023-10-02 | 2023-10-19 | 2023-11-10 | LORDS IVAN
NC 2023 | K10 | Region XI | Davao Oriental | 129342 | Capasnan ES | MANAY |  | 1 |  | 2 | Batch 1 | 6531619.67 | 6474963.74 | 5448267.14 | Completed | 1 | 2023-11-11 | 2024-08-01 | P00775043MN | 23LF0145 |  | 2023-06-01 | 2023-06-13 | 2023-07-06 | 2023-07-20 | ECBJ
NC 2023 | K10 | Region XI | Davao Oriental | 502246 | Francisco E. Lahora Sr. Integrated School | MANAY |  | 1 |  | 2 | Batch 1 | 6393741.05 | 6338281.09 | 6211474.89 | completed | 1 | 2023-10-27 | 2024-03-01 | P00775039MN | 23LF0141 |  | 2023-05-22 | 2023-06-16 | 2023-06-26 | 2023-07-07 | MELCHIZEDEK
NC 2023 | K10 | Region XI | Davao Oriental | 501962 | Jose Bitac Integrated School | MANAY |  | 1 |  | 2 | Batch 1 | 6776580.77 | 6717800.02 | 6712445.55 | completed | 1 | 2023-10-27 | 2023-11-10 | P00775040MN | 23LF0142 |  | 2023-05-22 | 2023-06-16 | 2023-06-26 | 2023-07-07 | MYMS
NC 2023 | K10 | Region XI | Davao Oriental | 137186 | Mandabon Elementary School | MANAY |  | 1 |  | 2 | Batch 1 | 6531619.67 | 6474963.74 | 6469662.31 | completed | 1 | 2023-10-27 | 2023-11-10 | P00775041MN | 23LF0143 |  | 2023-05-22 | 2023-06-16 | 2023-06-26 | 2023-07-07 | MYMS
NC 2023 | K10 | Region XI | Davao Oriental | 129358 | Pedro Masanguid ES | MANAY |  | 1 |  | 2 | Batch 1 | 6776580.77 | 6717800.02 | 6616930.19 | ongoing | 0.6 | 2023-10-11 |  | P00775042MN | 23LF0144 |  | 2023-06-01 | 2023-06-13 | 2023-07-06 | 2023-07-20 | MELCHIZEDEK | suspended
NC 2023 | K10 | Region XI | Davao Oriental | 305515 | Magdug National High School | GOVERNOR GENEROSO |  | 1 |  | 2 | Batch 1 | 5018531.25 | 4975000 | 4924707.46 | ongoing | 0.95 | 2023-11-13 |  | P00775046MN | 23LG0106 | 2023-05-25 | 2023-06-06 | 2023-06-20 | 2023-06-29 | 2023-07-17 | RANGAY
NC 2023 | K10 | Region XI | Davao Oriental | 305963 | Tamban National High School | GOVERNOR GENEROSO |  | 1 |  | 2 | Batch 1 | 5018531.25 | 4975000 | 4924396.32 | Completed | 1 | 2023-11-13 |  | P00775047MN | 23LG0107 | 2023-05-25 | 2023-06-06 | 2023-06-20 | 2023-06-29 | 2023-07-17 | RANGAY
NC 2023 | K10 | Region XI | Davao Oriental | 129441 | La Union ES | SAN ISIDRO |  | 1 |  | 2 | Batch 1 | 5164800 | 5120000 | 5067471.4 | Completed | 1 | 2023-11-13 | 2023-11-25 | P00775048MN | 23LG0108 | 2023-05-25 | 2023-06-06 | 2023-06-20 | 2023-06-29 | 2023-07-17 | RANGAY
NC 2023 | K10 | Region XI | Davao Oriental | 305517 | Talisay National High School | SAN ISIDRO |  | 1 |  | 2 | Batch 1 | 5018531.25 | 4975000 | 4922165.07 | ongoing | 0.95 | 2023-11-13 |  | P00775049MN | 23LG0109 | 2023-05-25 | 2023-06-06 | 2023-06-20 | 2023-06-29 | 2023-07-17 | RANGAY
NC 2023 | K10 | Region XI | Mati City | 501085 | Cabuaya Integrated School | CITY OF MATI (Capital) |  | 1 |  | 16 | Batch 1 | 69462525 | 32115000 | 31601013.01 and 36,665,000.00 | ongoing | 0.76 |  |  | P00775062MN-CW1 and P00775063MN-CW1 | 23LG0122 and 23LG0123 | 2023-05-25 | 2023-06-06 | 2023-06-20 | 2023-06-29 | 2023-07-17 | H2 Landmark Builders, Inc./MBMI Builders and Supply (JV) and MATT Glass/Aluminum/Construction Supply and Allied Services/ FAJR Construction Parts and Supply (JV)
NC 2023 | K10 | Region XI | Mati City | 129393 | Cangusan ES | CITY OF MATI (Capital) |  | 1 |  | 4 | Batch 1 | 10672575 | 10580000 | 10410719.85 | completed | 1 | 2023-12-23 | 2023-12-23 | P00775051MN-CW1 | 23lg0111 | 2023-05-25 | 2023-06-06 | 2023-06-20 | 2023-06-29 | 2023-07-17 | MBMI Builders & Supply
NC 2023 | K10 | Region XI | Mati City | 501424 | Culian Integrated School | CITY OF MATI (Capital) |  | 1 |  | 10 | Batch 1 | 34297500 | 34000000 | 33455994.73 | ongoing | 0.93 | 2024-03-27 | 2024-03-27 | P00775066MN-CW1 | 23LG0126 | 2023-05-25 | 2023-06-06 | 2023-06-20 | 2023-06-29 | 2023-07-17 | H2 LANDMARK BUILDERS, INC./MBMI BUILDERS AND SUPPLY (JOINT VENTURE)
NC 2023 | K10 | Region XI | Mati City | 129408 | Fausta Salazar Como MS | CITY OF MATI (Capital) |  | 1 |  | 10 | Batch 1 | 32542275 | 27260000 | 27,139,884.42 and 49,381,82.87 | completed | 1 |  |  | P00775056MN-CW1 and P00775057MN-CW1 | 23lg0116 and 23lg0117 | 2023-05-25 | 2023-06-06 | 2023-06-20 | 2023-06-29 | 2023-07-17 | MJCB Builders Inc.
NC 2023 | K10 | Region XI | Mati City | 129414 | Francisco Hinayon ES | CITY OF MATI (Capital) |  | 1 |  | 10 | Batch 1 | 32219475 | 31940000 | 31934999.91 | completed | 1 | 2024-03-22 | 2024-03-22 | P00775058MN-CW1 | 23LG0118 | 2023-05-25 | 2023-06-06 | 2023-06-20 | 2023-06-29 | 2023-07-17 | Legacy Construction Corp.
NC 2023 | K10 | Region XI | Mati City | 500454 | Licop Integrated School | CITY OF MATI (Capital) |  | 1 |  | 10 | Batch 1 | 32728893.75 | 32445000 | 31959063.54 | completed | 1 | 2024-03-27 | 2024-03-27 | P00775061MN-CW1 | 23LG0121 | 2023-05-25 | 2023-06-06 | 2023-06-20 | 2023-06-29 | 2023-07-17 | Matt Glass/Aluminum/Construction Supply and Allied Services
NC 2023 | K10 | Region XI | Mati City | 501087 | Luban Integrated School | CITY OF MATI (Capital) |  | 1 |  | 14 | Batch 1 | 56636268.75 | 31970000 | 31490316.48 and 23,690,710.28 | ongoing | 0.81 |  |  | P00775064MN-CW1 and P00775065MN-CW1 | 23LG0124 and 23LG0125 | 2023-05-25 | 2023-06-06 | 2023-06-20 | 2023-06-29 | 2023-07-17 | Rhodwill Parts & Hardware & Construction Services
NC 2023 | SHS | Region XI | Mati City | 325105 | Macambol NHS | CITY OF MATI (Capital) |  | 1 |  | 10 | Batch 1 | 33122306.25 | 32835000 | 32511069.35 | completed | 1 | 2024-04-26 | 2024-04-26 | P00775060MN-CW1 | 23LG0120 | 2023-05-25 | 2023-06-06 | 2023-06-20 | 2023-06-29 | 2023-07-17 | LLM Unified Builders & Trading Corp.
NC 2023 | K10 | Region XI | Mati City | 129394 | Serafin Vizconde Sr. Elementary School | CITY OF MATI (Capital) |  | 1 |  | 12 | Batch 1 | 38347631.25 | 27435000 | 27,133,057.44 and 10,420,295.55 | ongoing | 0.78 |  |  | P00775052MN-CW1 and P00775053MN-CW1 | 23lg0112 and 23lg0113 | 2023-05-25 | 2023-06-06 | 2023-06-20 | 2023-06-29 | 2023-07-17 | R. Baudon Construction & Supply Co.
NC 2023 | K10 | Region XI | Mati City | 129404 | Tagbinonga ES | CITY OF MATI (Capital) |  | 1 |  | 10 | Batch 1 | 32219475 | 21360000 | 21,124,923.47 and 10,368,216.79 | ongoing | 0.78 |  |  | P00775054MN-CW1 and P00775055MN-CW1 | 23lg0114 and 23lg0115 | 2023-05-25 | 2023-06-06 | 2023-06-20 | 2023-06-29 | 2023-07-17 | R. Baudon Construction & Supply Co.
NC 2023 | SHS | Region XI | Mati City | 304338 | Taguibo Agri. Voc. High School | CITY OF MATI (Capital) |  | 1 |  | 10 | Batch 1 | 31624312.5 | 31350000 | 30881251.34 | completed | 1 | 2024-03-22 | 2024-03-22 | P00775059MN-CW1 | 23LG0119 | 2023-05-25 | 2023-06-06 | 2023-06-20 | 2023-06-29 | 2023-07-17 | Matt Glass/Aluminum/Construction Supply and Allied Services
NC 2023 | K10 | Region XI | Mati City | 102164 | Talucanga Elementary School | CITY OF MATI (Capital) |  | 1 |  | 8 | Batch 1 | 23705625 | 23500000 | 23123958.56 | ongoing | 0.74 | 2024-03-22 | 2024-03-22 | P00775050MN-CW1 | 23lg0110 | 2023-05-25 | 2023-06-06 | 2023-06-20 | 2023-06-29 | 2023-07-17 | ER SALAC BUILDERS CORPORATION
NC 2024 |  | Region XI | Davao City | 129698 | J.P. Laurel ES | DAVAO CITY |  | 1 | 9 | 3STY9CL | GAA 17B | 40000000 |  | 39450442.65 | Ongoing | 0.45 | 2025-09-06 |  | P00875145MN | 24LB0126 | 2024-10-15 | 2024-11-04 | 2024-11-04 | 2024-11-19 | 2024-12-05 | Rosbill Const. and Supply | on-going
NC 2024 |  | Region XI | Davao City | 129705 | Jose Rizal ES | DAVAO CITY |  | 1 | 6 | 3STY6CL | GAA 17B | 20000000 |  | 19660793.23 | Ongoing | 0.25 | 2025-05-14 |  | 24LB0127 | 24LB0127 | 2024-08-23 |  |  |  | 2024-10-17 | Six Glam Builders and Corporation | ONGOING
NC 2024 |  | Region XI | Davao City | 305499 | Buhisan National High School | DAVAO CITY |  | 1 | 9 | 3STY9CL | GAA 17B | 40000000 |  | 39001331.35 | Ongoing | 0.75 | 2025-06-01 |  | 24LB0117 |  | 2024-07-17 | 2024-08-05 | 2024-08-05 | 2024-08-20 |  | Mark Anthony Const. and Supply | ONGOING
NC 2024 |  | Region XI | Davao City | 304368 | F. Bustamante NHS | DAVAO CITY |  | 1 | 20 | 4STY20CL | BATCH 1 | 86400000 |  | 82553554.95 | Ongoing | 0.6 | 2025-05-06 |  | 24LB0118 |  | 2024-04-19 | 2024-05-10 | 2024-05-10 | 2024-05-27 | 2024-06-11 | Rosbill Const. and Supply/Paragon St | ONGOING
NC 2024 |  | Region XI | Davao City | 305885 | Bago Oshiro National High School | DAVAO CITY |  | 1 | 24 | 4STY24CL | BATCH 2 | 96000000 |  | 94564174.64 | Ongoing | 0.2 | 2025-06-01 |  | 24LH0110 |  | 2024-10-31 | 2024-11-21 | 2024-11-21 | 2024-12-20 | 2024-12-27 | Rely Construction & Supply, Inc. | On-going
NC 2024 |  | Region XI | Davao City | 129728 | Balingaeng ES | DAVAO CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5500000 |  | 5417370.62 | Completed | 1 | 2024-12-21 | 2024-12-21 | 24LH0100 |  | 2024-06-25 | 2024-07-16 | 2024-07-16 | 2024-08-27 | 2024-03-09 | Lotrim Construction, Inc. | Completed
NC 2024 |  | Region XI | Davao City | 129731 | Biao Elementary School | DAVAO CITY |  | 1 | 4 | 2STY4CL | GAA 17B | 11500000 |  | 11324721.03 | Ongoing | 0.65 | 2025-03-31 |  | 24LH0098 |  | 2024-06-25 | 2024-07-16 | 2024-07-16 | 2024-08-27 | 2024-03-09 | Altapil Construction & Supply | ONGOING
NC 2024 |  | Region XI | Davao City | 129492 | Binugao CES | DAVAO CITY |  | 1 | 4 | 2STY4CL | GAA 17B | 11500000 |  | 11270855.32 | Ongoing | 0.65 | 2025-03-31 |  | 24LH0102 |  | 2024-06-25 | 2024-07-16 | 2024-07-16 | 2024-08-27 | 2024-03-09 | Six GLAM Builders & Supply Corp. | ONGOING
NC 2024 |  | Region XI | Davao City | 305644 | Dominga National High School | DAVAO CITY |  | 1 | 6 | 3STY6CL | BATCH 1 | 26000000 |  | 25611098.85 | Ongoing | 0.65 | 2025-02-23 |  | 24LH0095 |  | 2024-07-11 | 2024-07-11 | 2024-07-11 | 2024-08-15 | 2024-08-28 | BQPC Corporation | ONGOING
NC 2024 |  | Region XI | Davao City | 304395 | Emilio J. Estipona High School | DAVAO CITY |  | 1 | 12 | 3STY12CL | BATCH 2 | 48000000 |  | 47242548.61 | Ongoing | 0.3 | 2025-09-22 |  | 24LH0108 |  | 2024-10-31 | 2024-11-21 | 2024-11-21 | 2024-12-20 | 2024-12-27 | JLACE Bldrs Corp. | ONGOING
NC 2024 |  | Region XI | Davao City | 129566 | General Roxas CES | DAVAO CITY |  | 1 | 4 | 2STY4CL | GAA 17B | 11500000 |  | 25611098.85 | Completed | 1 | 2025-02-23 | 2025-02-23 | 24LH0097 |  | 2024-07-11 | 2024-07-11 | 2024-07-11 | 2024-08-15 | 2024-08-28 | BQPC Corporation | Completed
NC 2024 |  | Region XI | Davao City | 305658 | Gumitan National High School | DAVAO CITY |  | 1 | 4 | 2UNITS 1STY2CL School Building (with Toilet) with Provision of Rainwater Collector, School Furniture and Water System | BATCH 1 | 19500000 |  | 19013536.87 | Ongoing | 0.9 | 2025-02-23 |  | 24LH0096 |  | 2024-07-11 | 2024-07-11 | 2024-07-11 | 2024-08-15 | 2024-08-28 | R.C. Melcazo | ONGOING
NC 2024 |  | Region XI | Davao City | 129536 | Lampianao ES | DAVAO CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4900322.85 | Completed | 1 | 2024-12-21 | 2024-12-21 | 24LH0104 |  | 2024-06-25 | 2024-07-16 | 2024-07-16 | 2024-08-27 | 2024-03-09 | Mark Anthony Construction & Supply | Completed
NC 2024 |  | Region XI | Davao City | 129469 | Malagos ES SPED Center | DAVAO CITY |  | 1 | 4 | 2STY4CL | GAA 17B | 11500000 |  | 11327250.2 | Completed | 1 | 2025-03-31 | 2025-03-31 | 24LH0101 |  | 2024-06-25 | 2024-07-16 | 2024-07-16 | 2024-08-27 | 2024-03-09 | MBMI Builders & Supply | Completed
NC 2024 |  | Region XI | Davao City | 129686 | Manambulan ES | DAVAO CITY |  | 1 | 8 | 2STY8CL | BATCH 2 | 32000000 |  | 31202653.49 | Ongoing | 0.45 | 2025-07-24 |  | 24LH0107 |  | 2024-10-31 | 2024-11-21 | 2024-11-21 | 2024-12-20 | 2024-12-27 | R.C. Melcazo | ONGOING
NC 2024 |  | Region XI | Davao City |  | Presco Diolosa ES | DAVAO CITY |  | 1 | 4 | 2STY4CL | GAA 17B | 11500000 |  | 11213540.33 | Completed | 1 | 2025-03-31 | 2025-03-31 | 24LH0099 |  | 2024-06-25 | 2024-07-16 | 2024-07-16 | 2024-08-27 | 2024-03-09 | Mindalifi Construction and Supply | Completed
NC 2024 |  | Region XI | Davao City | 129540 | Quirino ES | DAVAO CITY |  | 1 | 3 | 1STY3CL | GAA 17B | 7000000 |  | 6894653.5 | Ongoing | 1 | 2025-01-20 | 2025-01-20 | 24LH0105 |  | 2024-06-25 | 2024-07-16 | 2024-07-16 | 2024-08-27 | 2024-03-09 | BQPC Corporation | ONGOING
NC 2024 |  | Region XI | Davao City | 129501 | Sirawan ES | DAVAO CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4945098.95 | Completed | 1 | 2025-01-20 | 2024-12-21 | 24LH0103 |  | 2024-06-25 | 2024-07-16 | 2024-07-16 | 2024-08-27 | 2024-03-09 | ZJN Development Const. & Supply Corp. | Completed
NC 2024 |  | Region XI | Davao City | 129745 | Vinzons ELem. School | DAVAO CITY |  | 1 | 12 | 3STY12CL | BATCH 2 | 48000000 |  | 47600263.84 | Ongoing | 0.25 | 2025-09-22 |  | 24LH0109 |  | 2024-10-31 | 2024-11-21 | 2024-11-21 | 2024-12-20 | 2024-12-27 | Arcinue Commercial Corp./Jameetrix Const, Inc. -JV | ONGOING
NC 2024 |  | Region XI | Davao De Oro | 315820 | Corazon C. Aquino NHS | COMPOSTELA |  | 1 | 2 | 1STY2CL | GAA 17B | 5860000 |  | 9939650 | Ongoing | 0.97 | 2024-09-20 | 2024-09-20 | 24LA0077 | 24LA0077 | 2024-04-05 | 2024-04-12 | 2024-04-25 | 2025-05-24 | 2025-05-24 | AGONG BUILDERS & CONSTRUCTION SUPPLY INC. | on going
NC 2024 |  | Region XI | Davao De Oro | 501774 | Coronobe Integrated School | MARAGUSAN (SAN MARIANO) |  | 1 | 4 | 2STY4CL | GAA 17B | 18418000 |  | 9850250 | Completed | 1 | 2024-09-20 | 2024-09-20 | 24LA0079 | 24LA0079 | 2024-04-05 | 2024-04-12 | 2024-04-25 | 2025-05-24 | 2025-05-24 | DOUBLE J CONSTRUCTION & SUPPLY | completed
NC 2024 |  | Region XI | Davao De Oro | 128439 | Monkayo CES | MONKAYO |  | 1 | 20 | 2UNITS 2STY10CL | GAA 17B | 75722000 |  | 9900000 | Ongoing | 0.2 | 2024-09-20 |  | 24LA0077 | 24LA0077 | 2024-10-04 | 2024-10-11 | 2024-10-24 | 2025-05-24 | 2025-05-24 | ADAN BUILDERS CO | on going
NC 2024 |  | Region XI | Davao De Oro | 501368 | Belmonte Integrated School | LAAK (SAN VICENTE) |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9938410 | Completed | 1 | 2024-09-20 | 2024-09-20 | 24LA0078 | 24LA0078 | 2024-04-16 | 2024-04-23 | 2024-05-07 | 2025-05-24 | 2025-05-24 | AGONG BUILDERS & CONSTRUCTION SUPPLY INC. | Completed
NC 2024 |  | Region XI | Davao De Oro | 128344 | Anibongan ES | MACO |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 40340000 | Completed | 1 | 2025-12-02 | 2025-02-12 | 24LA0108 | 24LA0108 | 2024-04-16 | 2024-04-23 | 2024-05-07 | 2024-06-14 | 2024-06-14 | GIZA BUILDERS CORRPORATION | Completed
NC 2024 |  | Region XI | Davao De Oro | 128549 | Matiao ES | PANTUKAN |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9900000 | Not Yet Started | 0.01 | [10 empty] | Change recipient to Matiao CES
NC 2024 |  | Region XI | Davao De Oro | 128406 | Bawani ES | MAWAB |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9938410 | Completed | 1 | 2024-09-20 | 2024-09-20 | 24LA0078 | 24LA0078 | 2024-04-16 | 2024-04-23 | 2024-05-07 | 2025-05-24 | 2025-05-24 | AGONG BUILDERS & CONSTRUCTION SUPPLY INC. | Completed
NC 2024 |  | Region XI | Davao De Oro | 128491 | Mainit ES | NABUNTURAN (Capital) |  | 1 | 10 | 2STY10CL | BATCH 1 | 40793656.48 |  | 40340000 | Ongoing | 0.58 | 2025-02-12 |  | 24LA0108 | 24LA0108 | 2024-05-09 | 2024-05-16 | 2024-05-28 | 2024-06-14 | 2024-06-14 | GIZA BUILDERS CORRPORATION | with liquidated damages in effcet May 14, 2025
NC 2024 |  | Region XI | Davao del Norte | 501766 | New Casay Integrated School | BRAULIO E. DUJALI |  | 1 | 4 | 1STY4CL | GAA 17B | 12000000 |  | 11820270 | Ongoing | 1 | 2025-05-02 |  | P00875161MN-CW1/24L00302 | P00875161MN-CW1/24L00302 | [5 empty] | Hero Builders
NC 2024 |  | Region XI | Davao del Norte | 128634 | Magsaysay ES | CARMEN |  | 1 | 4 | 2STY4CL | GAA 17B | 14000000 |  | 13875000 | Ongoing | 0.3 | 2025-10-02 |  | P00875160MN-CW1/24L00300 | P00875160MN-CW1/24L00300 | [5 empty] | Two Degrees Construction & Supply
NC 2024 |  | Region XI | Davao del Sur | 128811 | Balutakay Elementary School | BANSALAN |  | 1 | 4 | 2STY4CL | BATCH 1 | 16540226 |  | 16128161.07 | Completed | 1 | 2024-06-11 |  | P00875424MN | 24LD0188 | 2024-04-25 | 2024-05-02 | 2024-05-16 | 2024-06-26 | 2024-06-26 | R.C. MELGAZO BUILDERS | DPWH IMPLEMENTED PROJECTS; May - 95%
NC 2024 |  | Region XI | Davao del Sur | 128835 | Vicente Duterte Elementary School | BANSALAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4825750 | Completed | 1 | 2024-11-22 |  | P00875168MN | 24LD0208 | 2024-06-24 | 2024-07-02 | 2024-07-23 | 2024-08-14 | 2024-08-27 | 85 AQUARIUS BUILDERS CORPORATION | DPWH IMPLEMENTED PROJECTS; May - 95%
NC 2024 |  | Region XI | Davao del Sur | 128857 | Apolonio R. Fuentes Sr. ES | HAGONOY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4678349.54 | Completed | 1 | 2024-11-21 | 2025-01-21 | P00875170MN | 24LD0210 | 2024-06-24 | 2024-07-02 | 2024-07-23 | 2024-08-14 | 2024-08-27 | MN URBAN CONSRUCTION | DPWH IMPLEMENTED PROJECTS
NC 2024 |  | Region XI | Davao del Sur | 128870 | Guihing Central Elementary School | HAGONOY |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9750945.98 | Ongoing | 1 | 2024-10-18 | 2024-10-18 | P00875171MN | 24LD0199 | 2024-05-23 | 2024-05-30 | 2024-06-20 | 2024-03-07 | 2024-12-07 | H-ROYAL CONSTRUCTION | DPWH IMPLEMENTED PROJECTS
NC 2024 |  | Region XI | Davao del Sur | 304275 | Hagonoy National High School | HAGONOY |  | 1 | 4 | 2STY4CL | BATCH 1 | 15506050 |  | 15026760.52 | Ongoing | 1 | 2024-11-06 | 2024-11-06 | P00875425MN | 24LD0189 | 2024-04-25 | 2024-05-02 | 2024-06-20 | 2024-03-07 | 2024-12-07 | AGONG BUILDERS AND CONSTRUCTION SUPPLY INC. | DPWH IMPLEMENTED PROJECTS
NC 2024 |  | Region XI | Davao del Sur | 128923 | Barayong Central Elementary School | MAGSAYSAY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4850624.7 | Completed | 1 | 2024-11-21 | 2025-01-27 | P00875165MN | 24LD0205 | 2024-06-24 | 2024-07-02 | 2024-06-20 | 2024-03-07 | 2024-12-07 | LEAMOR CONSTRUCTION AND SUPPLY | DPWH IMPLEMENTED PROJECTS
NC 2024 |  | Region XI | Davao del Sur | 316003 | Salud Cagas Technical and Vocational High School | MAGSAYSAY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4825750 | Completed | 1 | 2024-11-21 | 2024-11-21 | P00875163MN | 24LD0203 | 2024-06-24 | 2024-07-02 | 2024-07-23 | 2024-08-14 | 2024-08-27 | MAGNUM BUILDERS CORPORATION | DPWH IMPLEMENTED PROJECTS
NC 2024 |  | Region XI | Davao del Sur | 129041 | Manga Central Elementary School | MATANAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [10 empty] | Dpwh listing is Manga Annex
NC 2024 |  | Region XI | Davao del Sur | 129037 | Sulatorio Elementary School | MATANAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4954998.96 | Completed | 1 | 2024-11-21 | 2024-11-21 | P00875164MN | 24LD0204 | 2024-06-24 | 2024-07-02 | 2024-07-02 | 2024-08-14 | 2024-08-27 | ADAN BUILDERS CO. | DPWH IMPLEMENTED PROJECTS
NC 2024 |  | Region XI | Davao del Sur | 129085 | Sibulan Elementary School | SANTA CRUZ |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969972.54 | Ongoing | 0.85 | 2024-09-16 | 2024-11-21 | P00875166MN | 24LD0206 | 2024-06-24 | 2024-07-02 | 2024-07-02 | 2024-08-14 | 2024-08-27 | ALTAPIL CONSTRUCTION & SUPPLY | DPWH IMPLEMENTED PROJECTS
NC 2024 |  | Region XI | Davao del Sur | 129100 | Tagabuli Elementary School | SANTA CRUZ |  | 1 | 2 | 1STY2CL with Attached 2 Seater Toilets | BATCH 1 | 6234200 |  | 6140955.58 | Ongoing | 0.95 | 2025-02-14 | 2024-09-16 | P00875426MN | 24LD0190 | 2024-04-25 | 2024-05-02 | 2024-05-02 | 2024-06-26 | 2024-06-26 | ZJN DEVELOPMENT CONSTRUCTION AND SUPPLY CORPORATION | DPWH IMPLEMENTED PROJECTS
NC 2024 |  | Region XI | Davao Occidental | 305511 | Calian National High School | Don Marcelino |  | 1 | 6 | 2STY6CL | BATCH 1 | 15134880.88 |  | 15054187.51 | Ongoing | 0.55 | 2025-01-13 |  | P00875427MN-CW1 | 24LE0074 | 2024-05-30 | 2024-06-06 | 2024-06-20 | 2024-08-13 | 2024-08-22 | Disem Construction & Supply | on-going
NC 2024 |  | Region XI | Davao Occidental | 305675 | Ernesto Balindan Sumbo National High School | DON MARCELINO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4971996.88 | Ongoing | 0.85 | 2024-11-19 |  | P00875178MN-CW1 | 24LE0083 | 2024-11-07 | 2024-07-18 | 2024-07-30 | 2024-08-13 | 2024-08-22 | RDF CONSTRUCTION | on-going
NC 2024 |  | Region XI | Davao Occidental | 304264 | Balangonan NHS | JOSE ABAD SANTOS (TRINIDAD) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4972999.03 | Ongoing | 0.75 | 2024-12-04 |  | P00875182MN-CW1 | 24LE0069 | 2024-09-05 | 2024-05-16 | 2024-05-31 | 2024-08-13 | 2024-08-22 | RDF CONSTRUCTION | on-going
NC 2024 |  | Region XI | Davao Occidental | 128988 | Bisang ES | MALITA |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  | 9947990.69 | Completed | 1 | 2024-12-09 | 2024-09-12 | P00875174MN-CW1 | 24LE0066 | 2024-09-05 | 2024-05-16 | 2024-05-31 | 2024-08-13 | 2024-08-22 | ADAN BUILDERS CO | Completed
NC 2024 |  | Region XI | Davao Occidental | 304271 | Demolok Valley National High School | MALITA |  | 1 | 6 | 2STY6CL | GAA 17B | 15000000 |  | 14921999.46 | Ongoing | 0.62 | 2025-01-13 |  | P00875172MN-CW1 | 24LE0064 | 2024-09-05 | 2024-05-16 | 2024-05-31 | 2024-08-13 | 2024-08-22 | Disem Construction & Supply | on-going
NC 2024 |  | Region XI | Davao Occidental | 305672 | Ernesto Lopez National High School | MALITA |  | 1 | 6 | 2STY6CL | GAA 17B | 15000000 |  | 14921902.71 | Ongoing | 0.5 | 2025-01-13 |  | P00875173MN-CW1 | 24LE0065 | 2024-09-05 | 2024-05-16 | 2024-05-31 | 2024-08-13 | 2024-08-22 | Disem Construction & Supply | on-going
NC 2024 |  | Region XI | Davao Occidental | 128998 | Lenna Elementary School | MALITA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4971999.2 | Ongoing | 0.95 | 2024-12-13 |  | P00875175MN-CW1 | 24LE0080 | 2024-11-07 | 2024-07-18 | 2024-07-30 | 2024-08-13 | 2024-08-22 | ADAN BUILDERS CO | on-going
NC 2024 |  | Region XI | Davao Occidental | 128999 | Little Baguio Elementary School | MALITA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4971997.79 | Ongoing | 0.75 | 2024-11-19 |  | P00875176MN-CW1 | 24LE0081 | 2024-11-07 | 2024-07-18 | 2024-07-30 | 2024-08-13 | 2024-08-22 | Disem Construction & Supply | on-going
NC 2024 |  | Region XI | Davao Occidental | 302772 | Tomas Lim Alcordo Sr. National High School | MALITA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4971999.4 | Ongoing | 0.93 | 2024-11-19 |  | P00875177MN-CW1 | 24LE0082 | 2024-11-07 | 2024-07-18 | 2024-07-30 | 2024-08-13 | 2024-08-22 | ADAN BUILDERS CO | on-going
NC 2024 |  | Region XI | Davao Occidental | 129106 | Cadaatan ES | SANTA MARIA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4972999.15 | Completed | 1 | 2024-11-19 | 2024-11-19 | P00875180MN-CW1 | 24LE0068 | 2024-09-05 | 2024-05-16 | 2024-05-31 | 2024-08-13 | 2024-08-22 | RDF CONSTRUCTION | Completed
NC 2024 |  | Region XI | Davao Occidental | 129117 | LILAN ELEMENTARY SCHOOL | SANTA MARIA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4971998.94 | Ongoing | 0.4 | 2024-11-19 |  | P00875181MN-CW1 | 24LE0084 | 2024-11-07 | 2024-07-18 | 2024-07-30 | 2024-08-13 | 2024-08-22 | ADAN BUILDERS CO | on-going
NC 2024 |  | Region XI | Davao Occidental | 501079 | Patuko Integrated School | SARANGANI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4972997.87 | Ongoing | 0 | 2024-11-19 |  | P00875179MN-CW1 | 24LE0067 | 2024-09-05 | 2024-05-16 | 2024-05-31 | 2024-08-13 | 2024-08-22 | ADAN BUILDERS CO | on-going
NC 2024 |  | Region XI | Davao Oriental | 500478 | Binondo Integrated School | BAGANGA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4964796.59 | Completed | 1 | 2024-08-03 | 2024-07-15 | P00875185MN | 24LF0149 |  | 2024-03-22 | 2024-04-04 | 2024-04-25 | 2024-05-03 | Lourds Ivan Const. Services
NC 2024 |  | Region XI | Davao Oriental | 304299 | Our Lady of Guadalupe National High School | BAGANGA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4949949.5 | Completed | 1 | 2024-08-03 | 2024-08-03 | P00875186MN | 24LF0150 |  | 2024-03-22 | 2024-04-04 | 2024-04-25 | 2024-05-03 | JAI Builders Corp.
NC 2024 |  | Region XI | Davao Oriental | 129198 | Cabasagan Elementary School | BOSTON |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4959881.01 | Completed | 1 | 2024-08-03 | 2024-08-03 | P00875187MN | 24LF0152 |  | 2024-03-22 | 2024-04-04 | 2024-04-25 | 2024-05-03 | MBMI Builders & Supply
NC 2024 |  | Region XI | Davao Oriental | 502247 | Simulao Integrated School | BOSTON |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4959883.62 | Completed | 1 | 2024-08-03 | 2024-08-03 | P00875188MN | 24LF0152 |  | 2024-03-22 | 2024-04-04 | 2024-04-25 | 2024-05-03 | MBMI Builders & Supply
NC 2024 |  | Region XI | Davao Oriental | 501966 | Potenciano A. Mabanding Integrated School | CARAGA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4924696.11 | Ongoing | 0.95 | 2024-08-03 | 2024-11-01 | P00875183MN | 24LF0147 |  | 2024-03-22 | 2024-04-04 | 2024-04-25 | 2024-05-03 | Connex 2016 Realty Dev., Inc.
NC 2024 |  | Region XI | Davao Oriental | 501608 | Modesto T. Veroy, Sr. Integrated School | CATEEL |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4949949.5 | Completed | 1 | 2024-08-03 | 2024-08-03 | P00875189MN | 24LF0153 |  | 2024-03-22 | 2024-04-04 | 2024-04-25 | 2024-05-03 | JAI Builders Corp.
NC 2024 |  | Region XI | Davao Oriental | 304324 | Manay National High School | MANAY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4962487.74 | Completed | 1 | 2024-08-03 | 2024-08-03 | P00875184MN | 24LF0148 |  | 2024-03-22 | 2024-04-04 | 2024-04-25 | 2024-05-03 | Rangay Const. & Supply
NC 2024 |  | Region XI | Davao Oriental | 129443 | A.S. Manjoorsa Elementary School | TARRAGONA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4935000.74 | Ongoing | 0.1 | 2024-08-24 |  | P00875190MN | 24LF0156 |  | 2024-04-11 | 2024-04-23 | 2024-05-14 | 2024-05-24 | J4 GROUP OF COMPANIES INCORPORATED
NC 2024 |  | Region XI | Davao Oriental |  | Maputi National High School | BANAYBANAY |  | 1 | 3 | 1STY3CL | GAA 17B | 9800000 |  | 9653453.45 | Ongoing | 0.95 | 2024-10-08 |  | NO DATA | 24LG0066 | 2024-04-04 | 2024-04-12 | 2024-04-27 | 2024-05-07 | 2024-05-29 | R. BAUDON
NC 2024 |  | Region XI | Davao Oriental |  | Surop National High School | GOVERNOR GENEROSO |  | 1 | 3 | 1STY3CL | GAA 17B | 10300000 |  | 10094753.81 | Ongoing | 0.4 | 2024-10-16 |  | NO DATA | 24LG0066 | 2024-04-04 | 2024-04-12 | 2024-04-27 | 2024-05-07 | 2024-05-29 | RAKKI CORP
NC 2024 |  | Region XI | Davao Oriental |  | Tiblawan National High School | GOVERNOR GENEROSO |  | 1 | 3 | 1STY3CL | GAA 17B | 10100000 |  | 9898735.41 | Ongoing | 0.85 | 2024-10-16 |  | NO DATA | 24LG0066 | 2024-04-04 | 2024-04-12 | 2024-04-27 | 2024-05-07 | 2024-05-29 | RAKKI CORP
NC 2024 |  | Region XI | Davao Oriental | 129431 | Manikling Elementary School | SAN ISIDRO |  | 1 | 3 | 1STY3CL | GAA 17B | 9800000 |  | 9634395.79 | Completed | 1 | 2024-10-08 | 2025-03-20 | NO DATA | 24LG0066 | 2024-04-04 | 2024-04-12 | 2024-04-27 | 2024-05-07 | 2024-05-29 | DBR CONST CORP
NC 2024 |  | Region XI | Digos City | 301906 | Goma National High School | CITY OF DIGOS (Capital) |  | 1 | 8 | 2STY8CL | BATCH 1 | 28820000 |  | 28388873.66 | Ongoing | 0.7 |  |  | 24LD0191 | 24LD0191 | 2024-07-05 | 2024-05-14 | 2024-05-28 | 2024-10-06 | 2024-06-24 | ZJN DEVELOPMENT CONSTRUCTION AND SUPPLY CORPORATION
NC 2024 |  | Region XI | Digos City | 129772 | San Miguel ES | CITY OF DIGOS (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4825861.55 | Completed | 1 |  | 2024-04-15 | 24LD0207 | 24LD0207 | 2024-06-25 | 2024-02-07 | 2024-07-23 | 2024-08-14 | 2024-08-29 | LTB BUILDERS AND CONSTRUCTION
NC 2024 |  | Region XI | Island Garden City of Samal | 128608 | San Antonio Elementary School | ISLAND GARDEN CITY OF SAMAL |  | 1 | 12 | 2STY12CL | BATCH 1 | 46714640 |  | 46015424.98 | Ongoing | 0.4 | 2025-08-05 |  | P00875429MN-CW1 | 24LO0312 | 2024-05-24 | 2024-06-12 | 2024-07-04 | 2024-07-29 | 2024-08-19 | RUFINO SEISMUNDO CONSTRUCTION CORP | Revised Target Completion Date
NC 2024 |  | Region XI | Panabo City | 129807 | Katipunan ES | CITY OF PANABO |  | 1 | 4 | 2STY4CL | BATCH 1 | 15141600 |  | 14914840 | Ongoing | 0.35 | 2025-03-17 |  | P00875430MN | CW1/24L00313 | [5 empty] | Tyer One Construction Corp. | Project is already delayed
NC 2024 |  | Region XI | Panabo City | 129813 | Mabunao ES | CITY OF PANABO |  | 1 | 4 | 2STY4CL | GAA 17B | 14000000 |  | 13965000 | Ongoing | 0.91 | 2025-03-20 |  | P00875162MN | CW1/24L00301 | [5 empty] | LLM Construction & Supply | Project is already delayed
NC 2024 |  | Region XI | Tagum City | 128786 | BABANGANAN ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9950000 | Completed | 1 |  |  | P00875157MN | 24LC0089 | 2024-05-04 | 2024-12-04 | 2024-04-25 | 2024-05-15 | 2024-05-24 | GP & H Construction Incorporated
NC 2024 |  | Region XI | Tagum City | 128779 | NEW BALAMBAN ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) |  | 1 | 4 | 2STY4CL | GAA 17B | 20000000 |  | 19900000 | Ongoing | 0.9 | 2024-11-17 | 2024-06-16 | P00875158MN | 24LC0090 | 2024-03-05 | 2024-10-05 | 2024-05-23 | 2024-06-25 | 2024-05-07 | Rangay Construction and Supply
NC 2024 |  | Region XI | Tagum City | 128772 | RIZAL I ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) |  | 1 | 5 | 1STY5CL WITH TOILET ATTACHED | GAA 17B | 10000000 |  | 9950000 | Completed | 1 | 2024-11-17 | 2024-11-17 | P00875159MN | 24LC0091 | 2024-03-05 | 2024-10-05 | 2024-05-23 | 2024-06-25 | 2024-05-07 | Rangay Construction and Supply

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.