## Sheet1
CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
QRF 2023 | Region XII | North Cotabato | 130297 | Pigcawayan CES | PIGKAWAYAN | 1st | 1 | 6 | 1STY6CL | 16500000 | 2- NC | 13497000 | Completed | 1 | 2024-09-19 |  |  | 122-2023 | 2023-11-09 | 2023-11-15 | 2023-12-01 | 2024-01-25 | 2024-02-19 | CABS CONSTRUCTION | Completed subject for final inspection
QRF 2024 | Region XII | General Santos City | 131278 | Labangal Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 4 | 1STY4CL | 11239295.18 | 1- NC | 11239295.18 | Ongoing | 0.2 | 150CD |  | 003-2025 |  | 2025-01-08 | 2025-01-08 | 2025-01-21 | 2025-02-04 | 2025-02-24 | LEIGHCHEEN CONSTRUCTION CORPORATION | On-Going Construction
QRF 2024 | Region XII | General Santos City | 131314 | Pedro Acharon Sr. Central Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 1 | Repair of Classrooms | 348546.5 | 1- R | 348546.5 | Ongoing | 0.75 | 50CD |  | 004-2025- Lot 1 |  | 2025-01-08 | 2025-01-08 | 2025-01-21 | 2025-02-04 | 2025-03-26 | BEBCON BUILDERS AND SUPPLY | On-Going Construction
QRF 2024 | Region XII | General Santos City | 304637 | Datu Andiam Manza National High School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 20 | Repair of Classrooms | 190230.76 | 1- R | 190230.76 | Ongoing | 0.85 | 45CD |  | 004-2025- Lot 2 |  | 2025-01-08 | 2025-01-08 | 2025-01-21 | 2025-02-04 | 2025-03-26 | BEBCON BUILDERS AND SUPPLY | On-Going Construction
QRF 2024 | Region XII | North Cotabato | 130197 | DILANGALEN CENTRAL ELEMENTARY SCHOOL | MIDSAYAP | 1st | 1 | 3 | 1STY3CL | 11342818.56 | 1- NC |  | Ongoing | 0.55 | [9 empty] | CLA Construction Incorporated
QRF 2024 | Region XII | Sarangani | 130443 | Baliton Elementary School | GLAN | Lone | 1 | 2 | 1STY2CL | 4892845.52 | 1- NC |  | Not Yet Started | 0 |  |  |  |  | 2024-12-13 |  | January 28,2025 |  |  |  | FOR AWARD
QRF 2024 | Region XII | Sarangani | 130450 | Calatungan ES | GLAN | Lone | 1 | 5 | Repair of Classrooms | 6875408.92 | 1- R | 5735236.09 | Ongoing | 0.0108 | 2025-06-22 |  |  | 2025I-03-005 | 2024-12-13 |  | January 28,2025 | 2025-03-19 | 2025-03-24 | E & R ENTERPRISES AND CONSTRUCTION | CONSTRUCTION ON GOING
QRF 2024 | Region XII | Sarangani | 130467 | Macatimbol ES | GLAN | Lone | 1 | 2 | Repair of Classrooms | 1015687.2 | 1- R |  | Not Yet Started | 0 |  |  |  |  | 2025-02-05 |  | February 25,2025 |  |  |  | FOR AWARD
QRF 2024 | Region XII | Sarangani | 130474 | Pangyan Central ES | GLAN | Lone | 1 | 5 | Repair of Classrooms | 5671478.61 | 1- R | 3762023.97 | Not Yet Started | 0.0226 | 2025-06-15 |  |  | 2025I-03-001 | 2024-12-13 |  | January 28,2025 | 2025-03-11 | 2025-03-17 | UPSCALE BUILDERS AND SUPPLY CORPORATION | FOR AWARD
QRF 2024 | Region XII | Sarangani | 130487 | Bocay- Il ES | KIAMBA | Lone | 1 | 2 | 1STY2CL | 4916342.86 | 1- NC |  | Under Procurement | 0 | [10 empty] | Rebid
QRF 2024 | Region XII | Sarangani | 130560 | Lun Padidu Central Elementary School | MALAPATAN | Lone | 1 | 6 | 2-UNITS 1STY3CL | 15224946.67 | 1- NC |  | Not Yet Started | 0 |  |  |  |  | 2024-12-13 |  | January 28,2025 |  |  |  | FOR AWARD
QRF 2024 | Region XII | Sarangani | 130563 | Mama Nawa Elementary School | MALAPATAN | Lone | 1 | 10 | Repair of Classrooms | 13605574.34 | 1- R |  | Not Yet Started | 0 |  |  |  |  | 2024-12-13 |  | January 28,2025 |  |  |  | FOR AWARD
QRF 2024 | Region XII | Sarangani | 130582 | Talus ES | MALUNGON | Lone | 1 | 9 | Repair of Classrooms | 14907576.67 | 1- R |  | Not Yet Started | 0 |  |  |  |  | 2024-12-13 |  | January 28,2025 |  |  |  | FOR AWARD
QRF 2024 | Region XII | Sarangani | 304541 | Pangyan National High School | GLAN | Lone | 1 | 2 | Repair of Classrooms | 1188056.38 | 1- R |  | Not Yet Started | 0 |  |  |  |  | 2025-02-05 |  | February 25,2025 |  |  |  | FOR AWARD
QRF 2024 | Region XII | Sarangani | 316604 | Amado M. Quirit Sr National High School | MALAPATAN | Lone | 1 | 7 | Repair of Classrooms | 1475383.74 | 1- R |  | Under Procurement | 0 |  |  |  |  | 2025-04-15 | [5 empty] | BID EVALUATION
QRF 2024 | Region XII | Sarangani | 500260 | Lumigo Integrated School | GLAN | Lone | 1 | 9 | 3-UNITS 1STY3CL | 27304958.65 | 1- NC | 27283547.41 | Ongoing | 0.0203 | 2025-12-16 |  |  | 2025I-03-003 | 2024-12-13 |  | January 28,2025 | 2025-03-11 | 2025-03-21 | MANUELA CONSTRUCTION SERVICES | CONSTRUCTION ON GOING
QRF 2024 | Region XII | Sarangani | 500261 | Roque Adarna Integrated School | GLAN | Lone | 1 | 6 | 2-UNITS 1STY3CL | 15224946.67 | 1- NC |  | Not Yet Started | 0 |  |  |  |  | 2024-12-13 |  | January 28,2025 |  |  |  | FOR AWARD
QRF 2024 | Region XII | Sarangani | 500267 | Mangelen IS | MAASIM | Lone | 1 | 4 | Repair of Classrooms | 5121274.06 | 1- R |  | Under Procurement | 0 | [6 empty] | 2025-04-08 |  |  |  | BID EVALUATION
QRF 2024 | Region XII | Sarangani | 500285 | Tagaytay Integrated School | ALABEL (Capital) | Lone | 1 | 2 | Repair of Classrooms | 621384.02 | 1- R |  | Under Procurement | 0 | [6 empty] | 2025-04-15 |  |  |  | BID EVALUATION
QRF 2024 | Region XII | Sarangani | 500288 | Kinabalan Integrated School | MALUNGON | Lone | 1 | 2 | Repair of Classrooms | 684829.83 | 1- R |  | Under Procurement | 0 | [6 empty] | 2025-04-15 |  |  |  | BID EVALUATION
QRF 2024 | Region XII | Sarangani | 500707 | Tonga Lim Siao Sr. Integrated School | GLAN | Lone | 1 | 6 | Repair of Classrooms | 6696299.07 | 1- R | 3744129.63 | Ongoing | 0.0227 | 2025-06-15 |  |  | 2025I-03-002 | 2024-12-13 |  | January 28,2025 | 2025-03-11 | 2025-03-17 | UPSCALE BUILDERS AND SUPPLY CORPORATION | CONSTRUCTION ON GOING
QRF 2024 | Region XII | Sarangani | 500829 | Panambalan Integrated School | GLAN | Lone | 1 | 7 | Repair of Classrooms | 13029145.87 | 1- R |  | Under Procurement | 0 | [6 empty] | 2025-04-08 |  |  |  | BID EVALUATION
QRF 2024 | Region XII | Sarangani | 501281 | Prudencio Mariano Sr. Integrated School | GLAN | Lone | 1 | 5 | 1STY3CL 1STY2CL | 12309649.43 | 1- NC | 12288654.75 | Ongoing | 0.2182 | 2025-09-17 |  |  | 2025I-03-004 | 2024-12-13 |  | January 28,2025 | 2025-03-11 | 2025-03-21 | MANUELA CONSTRUCTION SERVICES | CONSTRUCTION ON GOING
QRF 2024 | Region XII | Sarangani | 502228 | CALONKAMBING INTEGRATED SCHOOL | GLAN | Lone | 1 | 2 | Repair of Classrooms | 1010642.25 | 1- R |  | Not Yet Started | 0 |  |  |  |  | 2025-02-05 |  | February 25,2025 |  |  |  | FOR AWARD
QRF 2024 | Region XII | Sarangani | 304537 | Malapatan NHS | MALAPATAN | Lone | 1 | 16 | Repair of Classrooms | 437548.03 | 1- R |  | Under Procurement | 0 | [6 empty] | 2025-04-15 |  |  |  | BID EVALUATION
QRF 2024 | Region XII | South Cotabato | 130693 | Ubo Elementary School | LAKE SEBU | 2nd | 1 | 4 | 2-UNITS 1STY2CL | 11873019.44 | 1- NC | 9669539.93 | Ongoing | 0
QRF 2024 | Region XII | South Cotabato | 130860 | Lampitak Elementary School | TAMPAKAN | 1st | 1 | 4 | Repair of Classrooms | 2964223.54 | 1- R | 2103002.51 | Ongoing | 0
QRF 2024 | Region XII | South Cotabato | 130869 | Eleonor D. Belotindos Elementary School | TANTANGAN | 2nd | 1 | 2 | 1STY2CL | 5805259.72 | 1- NC | 4884842.52 | Ongoing | 0.08
QRF 2024 | Region XII | South Cotabato | 304560 | Polomolok National High School | POLOMOLOK | 1st | 1 | 9 | 1STY3CL AND 2STY6CL | 26103951.7 | 1- NC | 23232517 | Ongoing | 0.06
QRF 2024 | Region XII | South Cotabato | 501991 | Dumadalig Integrated School | TANTANGAN | 2nd | 1 | 2 | 1STY2CL | 5805259.72 | 1- NC | 5114680.91 | Ongoing | 0.02
QRF 2024 | Region XII | South Cotabato | 502376 | Cinco Integrated School | BANGA | 2nd | 1 | 2 | 1STY2CL | 5805259.72 | 1- NC | 4329799.25 | Ongoing | 0.05
QRF 2024 | Region XII | Sultan Kudarat | 304605 | Lebak Legislated National High School | LEBAK | 2nd | 1 | 24 | Repair of Classrooms | 1794219.49 | 1- R | 1739342.82 | Completed | 1 | 2025-04-14 | 2025-03-24 | 24-11-028 | 24-11-028 | 2024-11-12 | 2024-11-20 | 2024-12-02 | 2024-12-10 | 2024-12-27 | JV Constech

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%