## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
QRF 2019 | CAR | Abra | 134982 | Patucannay ES | BANGUED (Capital) | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 3305988.58 | 1 | 3216783.844 | Completed | 1 | 2019-11-26 |  | CAR-ABRA-2019-005 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | Baje Construction
QRF 2019 | CAR | Abra | 135038 | Nagaparan ES | DANGLAS | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 2405724.24 | 1 | 2323709.3407 | Completed | 1 | 2019-11-26 |  | CAR-ABRA-2019-005 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | Baje Construction
QRF 2019 | CAR | Abra | 135029 | Canan ES | LA PAZ | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 2205051.57 | 1 | 2095607.877 | Completed | 1 | 2019-11-26 |  | CAR-ABRA-2019-005 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | Baje Construction
QRF 2019 | CAR | Abra | 135064 | Lacub CS | LACUB | 0 | 1 | 12 | REPAIR OF CLASSROOMS | 6159129.62 | 1 | 5966611.555 | Completed | 1 | 2020-03-20 |  | CAR-ABRA-2019-007 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | HGW=3 Engineering & Construction
QRF 2019 | CAR | Abra | 135079 | Sap-al Elementary School | LACUB | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 2567862.69 | 1 | 2468916.4653 | Completed | 1 | 2020-03-20 |  | CAR-ABRA-2019-007 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | HGW=3 Engineering & Construction
QRF 2019 | CAR | Abra | 135065 | Lagangilang Central School | LAGANGILANG | 0 | 1 | 12 | REPAIR OF CLASSROOMS | 5885980.58 | 1 | 5719780.1917 | Completed | 1 | 2019-12-21 |  | CAR-ABRA-2019-006 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | LONNIE Construction
QRF 2019 | CAR | Abra | 135136 | Langiden CS | LANGIDEN | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 3620813.95 | 1 | 3517312.7835 | Completed | 1 | 2019-11-26 |  | CAR-ABRA-2019-005 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | Baje Construction
QRF 2019 | CAR | Abra | 135104 | Lul-luno ES | LUBA | 0 | 1 | 3 | 1STY3CL | 11354965.53 | 1 | 11066634.1827 | Completed | 1 | 2019-12-21 |  | CAR-ABRA-2019-008 / CAR-ABRA-2019-009 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | TRAMS Construction/HOPE EFG Builders | Just Started due to inaccessible roads
QRF 2019 | CAR | Abra | 135112 | Tabangao ES | LUBA | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 2964322.57 | 1 | 2468916.4653 | Completed | 1 | 2019-12-21 |  | CAR-ABRA-2019-008 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | TRAMS Construction
QRF 2019 | CAR | Abra | 135117 | Tukipa PS | LUBA | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 4434581.32 | 1 | 4337718.4494 | Completed | 1 | 2019-12-21 |  | CAR-ABRA-2019-008 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | TRAMS Construction | Just Started due to inaccessible roads
QRF 2019 | CAR | Abra | 305090 | Mataragan NAS | MALIBCONG | 0 | 1 | 10 | REPAIR OF CLASSROOMS | 5605683.18 | 1 | 5413133.3243 | Completed | 1 | 2020-03-20 |  | CAR-ABRA-2019-007 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | HGW=3 Engineering & Construction | Not Yet Started Due to Inaccessible Roads
QRF 2019 | CAR | Abra | 134998 | Madago Primary School | MANABO | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 1268583.76 | 1 | 1217727.357 | Completed | 1 | 2019-12-21 |  | CAR-ABRA-2019-009 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | HOPE EFG Builders
QRF 2019 | CAR | Abra | 135005 | San Jose ES | MANABO | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 3878256.12 | 1 | 3742500.6402 | Completed | 1 | 2019-12-21 |  | CAR-ABRA-2019-006 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | LONNIE Construction
QRF 2019 | CAR | Abra | 135122 | Malamsit Elementary School | PEÑARRUBIA | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 3235671.95 | 1 | 3095453.7457 | Completed | 1 | 2019-12-21 |  | CAR-ABRA-2019-006 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | LONNIE Construction
QRF 2019 | CAR | Abra | 135189 | Maguyepyep Elementary School | SALLAPADAN | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 1066946.84 | 1 | 1045961.9676 | Completed | 1 | 2019-12-21 |  | CAR-ABRA-2019-006 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | LONNIE Construction
QRF 2019 | CAR | Abra | 135126 | Olo ES | SAN ISIDRO | 0 | 1 | 1 | REPAIR OF CLASSROOMS | 632182.64 | 1 | 608544.5499 | Completed | 1 | 2019-12-21 |  | CAR-ABRA-2019-006 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | LONNIE Construction
QRF 2019 | CAR | Abra | 305099 | San Quintin NHS | SAN QUINTIN | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 4179298.38 | 1 | 4058432.9764 | Completed | 1 | 2019-11-26 |  | CAR-ABRA-2019-005 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | Baje Construction
QRF 2019 | CAR | Abra | 135087 | Alangtin Elementary School | TUBO | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 3023693.15 | 1 | 2953738.7947 | Completed | 1 | 2019-12-21 |  | CAR-ABRA-2019-009 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | HOPE EFG Builders
QRF 2019 | CAR | Abra | 135116 | Tubtuba ES | TUBO | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 4351440.58 | 1 | 4269195.8872 | Completed | 1 | 2019-12-21 |  | CAR-ABRA-2019-009 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | HOPE EFG Builders
QRF 2019 | CAR | Apayao | 305106 | Apayao National Industrial Agricultural High School | CALANASAN (BAYAG) | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 5241349.15 | 1 | 5088969.95 | Completed | 1 | NOVEMBER 28,2019 |  |  |  | JUNE 11, 2019 | JUNE 20, 2019 | JULY 2, 2019 | JULY 11, 2019 | JULY 23, 2019 | EBJR CONSTRUCTION
QRF 2019 | CAR | Apayao | 135286 | Bagutong ES | FLORA | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 3017754.7 | 1 | 2969516.03 | Completed | 1 | NOVEMBER 28,2019 |  |  |  | JUNE 11, 2019 | JUNE 20, 2019 | JULY 2, 2019 | JULY 11, 2019 | JULY 23, 2019 | EBJR CONSTRUCTION
QRF 2019 | CAR | Apayao | 219010 | Tamalunog Elementary School | FLORA | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 651052.28 | 1 | 620254.8 | Completed | 1 | NOVEMBER 28,2019 |  |  |  | JUNE 11, 2019 | JUNE 20, 2019 | JULY 2, 2019 | JULY 11, 2019 | JULY 23, 2019 | EBJR CONSTRUCTION
QRF 2019 | CAR | Apayao | 135298 | Baliwanan ES | KABUGAO (Capital) | 0 | 1 | 3 | 1STY3CL | 7034015.36 | 1 |  | Completed | 1 | [10 empty] | 2 failed biddings, 1 failed negotiated procurement, request for re-program
QRF 2019 | CAR | Apayao | 305115 | Kabugao Agro-Ind'l. HS | KABUGAO (Capital) | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 10374144.99 | 1 | 10132642.75 | Completed | 1 | NOVEMBER 28,2019 |  |  |  | JUNE 11, 2019 | JUNE 20, 2019 | JULY 2, 2019 | JULY 11, 2019 | JULY 23, 2019 | EBJR CONSTRUCTION
QRF 2019 | CAR | Apayao | 135343 | San Isidro ES | LUNA | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1315890.14 | 1 | 1295778.16 | Completed | 1 | NOVEMBER 28,2019 |  |  |  | JUNE 11, 2019 | JUNE 20, 2019 | JULY 2, 2019 | JULY 11, 2019 | JULY 23, 2019 | J.G. YACAS CONSTRUCTION, SUPPLY AND EQUIPMENT RENTALS
QRF 2019 | CAR | Apayao | 318801 | Tumog National Agricultural and trade High School | LUNA | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 5083849.15 | 1 | 4977120.33 | Completed | 1 | NOVEMBER 28,2019 |  |  |  | JUNE 11, 2019 | JUNE 20, 2019 | JULY 2, 2019 | JULY 11, 2019 | JULY 23, 2019 | EBJR CONSTRUCTION
QRF 2019 | CAR | Apayao | 305123 | Pudtol NHS | PUDTOL | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 1169283.9 | 1 | 1152244.16 | Completed | 1 | NOVEMBER 28,2019 |  |  |  | JUNE 11, 2019 | JUNE 20, 2019 | JULY 2, 2019 | JULY 11, 2019 | JULY 23, 2019 | J.G. YACAS CONSTRUCTION, SUPPLY AND EQUIPMENT RENTALS
QRF 2019 | CAR | Apayao | 319009 | TAWIT NHS (MATAGUISI COMP. NHS - CACALAGAN ANNEX) | PUDTOL | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 3285437.2 | 1 | 8133846.45 | Completed | 1 | NOVEMBER 28,2019 |  |  |  | JUNE 11, 2019 | JUNE 20, 2019 | JULY 2, 2019 | JULY 11, 2019 | JULY 23, 2019 | EBJR CONSTRUCTION
QRF 2019 | CAR | Baguio City | 136384 | Dontogan Elementary School | BAGUIO CITY | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 2932636.95 | 1 | 1965559.09 | Completed | 1 | 2020-05-02 |  | 001,s.2020 | 001,s.2020 | 2019-11-20 | 2019-11-29 | 2020-12-11 | 2019-12-20 | 2020-02-17 | JJJ-A Construction and Supplier
QRF 2019 | CAR | Ifugao | 305167 | Asipulo National High School | ASIPULO | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 4088343.48 | 1 | 4077601.49 | Completed | 1 | January 12, 2020
QRF 2019 | CAR | Ifugao | 135808 | Amganad ES | BANAUE | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 3464415.42 | 1 | 3422131.02 | Completed | 1 | January 8, 2020
QRF 2019 | CAR | Ifugao | 135808 | Amganad ES | BANAUE | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 3653335.74 | 1 | 3618631.11 | Completed | 1 | January 8, 2020
QRF 2019 | CAR | Ifugao | 135810 | Anaba ES | BANAUE | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 2222779.43 | 1 | 2220521.78 | Completed | 1 | January 8, 2020
QRF 2019 | CAR | Kalinga | 135987 | Ag-agama Elementary School | LUBUAGAN | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 2590760.04 | 1 |  | Completed | 1
QRF 2019 | CAR | Kalinga | 135994 | Mabongtot Elementary School | LUBUAGAN | 0 | 1 | 1 | REPAIR OF CLASSROOMS | 478198.61 | 1 |  | COMPLETED | 1
QRF 2019 | CAR | Kalinga | 135996 | Manangol Elementary School | LUBUAGAN | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 2407902.64 | 1 |  | Completed | 1
QRF 2019 | CAR | Kalinga | 135996 | Manangol Elementary School | LUBUAGAN | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 1251715.24 | 1 |  | Completed | 1
QRF 2019 | CAR | Kalinga | 135998 | Tanglag Elementary School | LUBUAGAN | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 2222429.66 | 1 |  | completed | 1
QRF 2019 | CAR | Kalinga | 136014 | Bagtayan Elementary School | PASIL | 0 | 1 | 2 | 1STY2CL | 6742528.28 | 1 |  | completed | 1
QRF 2019 | CAR | Kalinga | NOT-IN-NSBI | PUGONG ES | PASIL | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 3492885.15 | 1 |  | completed | 1
QRF 2019 | CAR | Kalinga | 319107 | Camalog National High School | PINUKPUK | 0 | 1 | 2 | 1STY2CL | 5337283.8 | 1 |  | Completed | 1
QRF 2019 | CAR | Kalinga | 136049 | Malaap Elementary School | PINUKPUK | 0 | 1 | 2 | 1STY2CL | 6770303.2 | 1 |  | completed | 1
QRF 2019 | CAR | Kalinga | NOT-IN-NSBI | Malagnat NHS | PINUKPUK | 0 | 1 | 4 | 2 UNITS OF 1STY2CL | 11145876.01 | 1 |  | completed | 1
QRF 2019 | CAR | Kalinga | NOT-IN-NSBI | Bagbag Elementary School Bulbul Annex | RIZAL (LIWAN) | 0 | 1 | 4 | 1STY2CL | 5114707.54 | 1 |  | completed | 1
QRF 2019 | CAR | Kalinga | 136071 | Kinama Elementary School | RIZAL (LIWAN) | 0 | 1 | 3 | 1STY3CL | 6964369.27 | 1 |  | completed | 1
QRF 2019 | CAR | Kalinga | 136076 | Rizal Central School | RIZAL (LIWAN) | 0 | 1 | 3 | 1STY3CL | 6825619.52 | 1 |  | Completed | 1
QRF 2019 | CAR | Kalinga | NOT-IN-NSBI | Rizal Central School Cadao Annex | RIZAL (LIWAN) | 0 | 1 | 3 | 1STY3CL | 6727105.08 | 1 |  | completed | 1
QRF 2019 | CAR | Kalinga | NOT-IN-NSBI | Santor NHS | RIZAL (LIWAN) | 0 | 1 | 4 | 2 UNITS OF 1STY2CL | 10024112.37 | 1 |  | completed | 1
QRF 2019 | CAR | Kalinga | 136123 | Dacalan Elementary School | TANUDAN | 0 | 1 | 2 | 1STY2CL | 5666889.58 | 1 |  | Completed | 1 | [10 empty] | Contractor's Fault,
QRF 2019 | CAR | Kalinga | 136123 | Dacalan Elementary School | TANUDAN | 0 | 1 | 3 | 1STY3CL | 8662582.66 | 1 |  | Completed | 1 | [10 empty] | Contractor's Fault,
QRF 2019 | CAR | Kalinga | 136126 | Lubo Elementary School | TANUDAN | 0 | 1 | 5 | 1STY3CL | 8575272.97 | 1 |  | Completed | 1
QRF 2019 | CAR | Kalinga | 136126 | Lubo Elementary School | TANUDAN | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 18074197.42 | 1 |  | Completed | 1
QRF 2019 | CAR | Kalinga | 136143 | Ambato-Legleg Elementary School | TINGLAYAN | 0 | 1 | 4 | 2 UNITS OF 1STY2CL | 35594457.99 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 305235 | Barlig National High School | BARLIG | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 3438008.24 | 1 |  | Reverted | 0 | [10 empty] | Procurement Issues
QRF 2019 | CAR | Mt. Province | 305242 | Eastern Bontoc NAVHS | BARLIG | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 2498721.73 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 136187 | KALEO ELEMENTARY SCHOOL | BARLIG | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 811075.4 | 1 |  | Reverted | 0 | [10 empty] | for award;BAC problem
QRF 2019 | CAR | Mt. Province | 136196 | Ambacbac Elementary School | BAUKO | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 765719.6 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 136216 | Mayag Elementary School | BAUKO | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 1129781.98 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 136221 | Otucan Elementary School | Bauko | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 1113998.38 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 136223 | Pangao Elementary School | BAUKO | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 655852.79 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 136226 | Sadsadan Trail Elementary School | BAUKO | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 1146140.98 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 136238 | Catengan Elementary School | BESAO | 0 | 1 | 3 | 1STY3CL | 6702902.62 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 136239 | Dandanac Elementary School | BESAO | 0 | 1 | 3 | 1STY3CL | 8647684.57 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 305260 | Panabungen School of Arts, Trades & Home Industries | BESAO | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 998369.9376 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 136248 | Tambuan Elementary School | BESAO | 0 | 1 | 4 | 2 UNITS OF 1STY2CL | 8584999.57 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 136267 | Apapawan Elementary School | NATONIN | 0 | 1 | 2 | 1STY2CL | 5193717.59 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 319216 | Banawel National High School | NATONIN | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 829001.86 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 305258 | Natonin National High School | NATONIN | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 2433068.68 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 136274 | Pangtor Primary School | NATONIN | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 1633100.42 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 319203 | Saliok National High School | NATONIN | 0 | 1 | 4 | 2 UNITS OF 1STY2CL | 8490919.57 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 136280 | Tonglayan Elementary School | NATONIN | 0 | 1 | 1 | REPAIR OF CLASSROOMS | 1237382.8 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 136283 | Anonat Elementary School | PARACELIS | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 705200.46 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 319220 | Anonat National Agricultural and Vocational High School | PARACELIS | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 2476665.11 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 136289 | Butigue Elementary School | PARACELIS | 0 | 1 | 3 | 1STY3CL | 6275562.94 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 136306 | Marallag Elementary School | PARACELIS | 0 | 1 | 2 | 1STY2CL | 5193556.21 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 136307 | Mulliang Elementary School | PARACELIS | 0 | 1 | 3 | 1STY3CL | 7218770.11 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 136316 | Capinitan Elementary School | SABANGAN | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 5170561.44 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 221007 | Libo Elementary School | SABANGAN | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 421640.46 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 136325 | Napua Elementary School | SABANGAN | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 521056 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 305262 | Pingad National High School | SABANGAN | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 2704798.65 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 136338 | Sacasacan Elementary School | SADANGA | 0 | 1 | 2 | 1STY2CL | 4389142.81 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 305264 | Sadanga National High School | SADANGA | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 1742434.32 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 136342 | Ambasing Elementary School | SAGADA | 0 | 1 | 2 | 1STY2CL | 5011790.39 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 305229 | Antadao National High School | SAGADA | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 3310364.17 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 136350 | Payag-eo Elementary School | SAGADA | 0 | 1 | 2 | 1STY2CL | 4972915.19 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 319221 | Balaoa National High School | TADIAN | 0 | 1 | 3 | 1STY3CL | 8944905.8 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 319223 | Lubon NHS - Mabalite Extension | TADIAN | 0 | 1 | 1 | REPAIR OF CLASSROOMS | 1179006.55 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 136372 | Masla Elementary School | TADIAN | 0 | 1 | 3 | 1STY3CL | 6477188.46 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 305251 | Masla National High School | TADIAN | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 1136501.98 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 221012 | New LubonElementary School | TADIAN | 0 | 1 | 3 | 1STY3CL | 6966736.19 | 1 |  | Completed | 1
QRF 2019 | CAR | Mt. Province | 136374 | Sayapot Elementary School | TADIAN | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 2700392.38 | 1 |  | Completed | 1
QRF 2019 | CAR | Tabuk City | 136153 | Addang Primary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | 4761026.25 | 1 |  | Completed | 1
QRF 2019 | CAR | Tabuk City | 220531 | Bulanao East Annex - Greenhills PS | CITY OF TABUK (Capital) | 0 | 1 | 5 | 1STY5CL | 9609694.2 | 1 |  | Completed | 1
QRF 2019 | CAR | Tabuk City | 136093 | Calaccad Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 3 | 1STY3CL | 6353531.85 | 1 |  | Completed | 1
QRF 2019 | CAR | Tabuk City | 305200 | Calaccad National High School | CITY OF TABUK (Capital) | 0 | 1 | 5 | 1STY5CL | 9737009.61 | 1 |  | Completed | 1
QRF 2019 | CAR | Tabuk City | 136096 | Cudal Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 9131452.57 | 1 |  | Completed | 1
QRF 2019 | CAR | Tabuk City | 305203 | Cudal National High School | CITY OF TABUK (Capital) | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 11290496.48 | 1 |  | Completed | 1
QRF 2019 | CAR | Tabuk City | 500531 | Dilag Integrated School | CITY OF TABUK (Capital) | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 8571782.04 | 1 |  | Completed | 1
QRF 2019 | CAR | Tabuk City | 136171 | Lucog Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 1 | REPAIR OF CLASSROOMS | 702687.98 | 1 |  | Completed | 1
QRF 2019 | CAR | Tabuk City | 319117 | Naneng NHS - Mosimos Extension | CITY OF TABUK (Capital) | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 7691889.69 | 1 |  | Completed | 1
QRF 2019 | CAR | Tabuk City | 220529 | San Pablo Primary School | CITY OF TABUK (Capital) | 0 | 1 | 3 | 1STY3CL | 6351404.45 | 1 |  | Completed | 1
QRF 2019 | CAR | Tabuk City | 136012 | Tabuk City Central School | CITY OF TABUK (Capital) | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 1101792.64 | 1 |  | Completed | 1
QRF 2019 | CAR | Tabuk City | 305221 | Tabuk City National High School | CITY OF TABUK (Capital) | 0 | 1 | 44 | REPAIR OF CLASSROOMS | 12386627.0261 | 1 |  | Completed | 1
QRF 2019 | CAR | Tabuk City | NOT-IN-NSBI | Tabuk City National High School - BANTAY EXT. | CITY OF TABUK (Capital) | 0 | 1 | 5 | 1STY5CL | 9579509.61 | 1 |  | completed | 1
QRF 2019 | CAR | Tabuk City | 136183 | Western Tabuk CS | CITY OF TABUK (Capital) | 0 | 1 | 5 | 1STY5CL | 9632009.61 | 1 |  | Completed | 1
QRF 2020 | CAR | Abra | 135049 | Bangilo ES | MALIBCONG | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 15842605.76 | 1 |  | Completed | 1
QRF 2020 | CAR | Apayao | 318811 | STA. FILOMENA SCHOOL OF ARTS AND TRADE | CALANASAN (BAYAG) | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 8779024.41 | 1 |  | Completed | 1
QRF 2020 | CAR | Apayao | 318808 | ALLIG NATIONAL AGRICULTURAL AND TRADE HIGH SCHOOL | FLORA | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 2721248.86 | 1 |  | Completed | 1
QRF 2020 | CAR | Apayao | 305113 | FLORA NATIONAL HIGH SCHOOL | FLORA | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 11590542.18 | 1 |  | Completed | 1
QRF 2020 | CAR | Apayao | 305107 | APAYAO SCIENCE HIGH SCHOOL | LUNA | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 10629542.67 | 1 |  | Completed | 1
QRF 2020 | CAR | Apayao | 135348 | TUMOG ELEMENTARY SCHOOL | LUNA | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 11609930.75 | 1 |  | Completed | 1
QRF 2020 | CAR | Apayao | 305109 | STA. MARCELA NATIONAL HIGHSCHOOL | STA. MARCELA | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 7034850.63 | 1 |  | Completed | 1
QRF 2020 | CAR | Benguet | 135644 | Bedbed Elementary School | MANKAYAN | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 1386934.6 | 1 |  | Completed | 1
QRF 2020 | CAR | Ifugao | 305172 | Gohang NHS | BANAUE | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 3678931.08 | 1 | 3122966.93 | Completed | 1 | [10 empty] | Suspended
QRF 2020 | CAR | Kalinga | 135975 | Kabugao ES | BALBALAN | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 6161678.6 | 1 |  | Completed | 1
QRF 2020 | CAR | Kalinga | 135983 | Sesec-An ES | BALBALAN | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 6161678.6 | 1 |  | Completed | 1
QRF 2020 | CAR | Kalinga | 136133 | Bangad Centro- Elementary School | TINGLAYAN | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 6161678.6 | 1 |  | Completed | 1
QRF 2020 | CAR | Mt. Province | 136196 | Ambacbac Elementary School | BAUKO | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 2602877.52 | 1 | 4476989.71 | Completed | 1 | [8 empty] | 2020-11-24 | BOYET CONSTRUCTION
QRF 2021 | CAR | Ifugao | 220001 | Cawayan PS - Annex (Alehwagon) | ASIPULO | 0 | 1 | 1 |  | 671652.1903 | 1 | 653896.26 | completed | 1 | 2021-12-05
QRF 2021 | CAR | Ifugao | 135840 | Namulditan ES | HINGYON | 0 | 1 | 13 |  | 6595350.19 | 1 | 6505905.81 | completed | 1 | 2022-04-27
QRF 2021 | CAR | Mt. Province | 136194 | Ogo-og Elementary School | BARLIG | 0 | 1 | 1 | TY ULYSSES | 778141.6583 | 1 | 763168.63 | completed | 1 | 2021-10-16 | 2021-10-15 |  | INF-2021 R-013 | 2021-06-04 | 2021-06-10 | 2021-06-25 | 2021-07-22 | 2021-08-17 | Precious Gold Builders | With Time extension
QRF 2021 | CAR | Mt. Province | 319214 | Abatan National High School | BAUKO | 0 | 1 | 4 | TY ULYSSES | 2684754.87 | 1 | 2236169.62 | completed | 1 | 2021-12-28 | 2022-02-15 |  |  | 2021-06-04 | 2021-06-10 | 2021-06-25 | 2021-07-22 | 2021-09-29 | JBA Construction & Builders
QRF 2021 | CAR | Mt. Province | 305252 | Mt. Data National High School | BAUKO | 0 | 1 | 3 | TY ULYSSES | 3743563.8722 | 1 | 3484672.67 | completed | 1 | 2021-12-28 | 2022-02-23 |  |  | 2021-06-04 | 2021-06-10 | 2021-06-23 | 2021-07-22 | 2021-09-29 | Litangfan Const'n Services
QRF 2021 | CAR | Mt. Province | 136227 | Salin Elementary School | BAUKO | 0 | 1 | 2 | TY ULYSSES | 2778027.4376 | 1 | 2591147.54 | completed | 1 | 2021-12-28 | 2022-01-31 |  |  | 2021-06-04 | 2021-06-10 | 2021-06-25 | 2021-07-22 | 2021-09-29 | MNJD Const'n | Contract Perfection
QRF 2021 | CAR | Mt. Province | 136227 | Salin Elementary School | BAUKO | 0 |  | 2 | TY ULYSSES | 6215361.4961 | 1 | 6020119.44 | completed | 1 | 2022-01-03 | 2022-01-31 |  | INF-2021 QNC-022 | 2021-06-04 | 2021-06-10 | 2021-06-23 | 2021-07-22 | 2021-08-06 | MNJD Const'n | Contract Perfection
QRF 2021 | CAR | Mt. Province | 305245 | Tapapan National High School | BAUKO | 0 | 1 | 2 | TY ULYSSES | 7945852.9869 | 1 | 7385512 | completed | 1 | 2022-01-10 | 2022-02-28 |  | INF-2021 QNC-023 | 2021-06-04 | 2021-06-10 | 2021-06-23 | 2021-07-22 | 2021-08-13 | Litangfan Const'n Services
QRF 2021 | CAR | Mt. Province | 319215 | Banguitan National High School | BESAO | 0 | 1 | 2 | TY ULYSSES | 1957051.643 | 1 | 1595448.46 | completed | 1 | 2021-12-28 | 2022-05-24 |  |  | 2021-06-04 | 2021-06-10 | 2021-06-25 | 2021-07-22 | 2021-09-29 | Teging Const'n | for rebid
QRF 2021 | CAR | Mt. Province | 136280 | Tonglayan Elementary School | NATONIN | 0 | 1 | 2 | TY ULYSSES | 1975225.7516 | 1 | 1864198.86 | Completed | 1 | 2021-10-27 | 2021-10-20 |  | INF-2021 R-021 | 2021-06-04 | 2021-06-10 | 2021-06-25 | 2021-07-22 | 2021-08-13 | Sembri Const'n
QRF 2021 | CAR | Mt. Province | 136345 | Balugan Elementary School | SAGADA | 0 | 1 | 8 | TY ULYSSES | 9463865.3361 | 1 | 6600466.96 | completed | 1 | 2022-04-25 |  |  |  | 2021-06-04 | 2021-06-10 | 2021-06-25 | 2021-07-22 | 2021-11-26 | Boy-cos Const'n | for rebid
QRF 2021 | CAR | Mt. Province | 136363 | Dacudac Elementary School | TADIAN | 0 | 1 | 3 | TY ULYSSES | 11415841.9303 | 1 | 8159781.5 | completed | 1 | 2022-09-30 |  |  |  | 2021-06-04 | 2021-06-10 | 2021-06-25 | 2021-07-22 | 2021-11-29 | LCDC Const'n | for rebid
QRF 2021 | CAR | Mt. Province | 136374 | Sayapot Elementary School | TADIAN | 0 | 1 | 3 | TY ULYSSES | 2746768.1146 | 1 | 2235121.15 | Completed | 1 | 2022-02-27 | 2022-03-25 |  |  | 2021-06-04 | 2021-06-10 | 2021-06-25 | 2021-07-22 | 2021-11-29 | LCDC Const'n
QRF 2021 | CAR | Mt. Province | 305267 | Tadian School of Arts and Trades | TADIAN | 0 | 1 | 38 | TY ULYSSES | 9181784.9073 | 1 | 8892002.04 | completed | 1 | 2022-01-15 | 2022-04-20 |  | INF-2021 R-021 | 2021-06-04 | 2021-06-10 | 2021-06-25 | 2021-07-22 | 2021-08-18 | JMMAS Const'n & Gen. Merchandise
QRF 2022 | CAR | Abra | 135174 | Boliney CS | BOLINEY | 0 | 1 |  | Others | 7019074.5549 | 1 |  | completed | 1
QRF 2022 | CAR | Kalinga | 136029 | Pasil CS (Malucsad Annex) | PASIL | 0 | 1 |  |  | 3314706.433 | 1 |  | Completed | 1
QRF 2022 | CAR | Mt. Province | 319225 | Agawa National High School | BESAO | 0 | 1 | 4 | NEW CONSTRUCTION | 17274099.21 | 1 |  | completed | 1 | 2023-05-04 | 2023-06-18 | INF-2021 QNC-001 |  | 2022-05-05 | 2022-05-13 | 2022-05-25 | 2022-06-07 | 2022-08-11 | Batakagan Construction | with 19 days time extension, 45 days LD
QRF 2022 | CAR | Tabuk City | 136086 | Bulanao Central School | CITY OF TABUK (Capital) | 0 | 1 | 4 | REPAIR/ REHABILITATION | 4639596.2249 | 1 |  | Completed | 1
QRF 2022 | CAR | Tabuk City | 319101 | Bulo National High School | CITY OF TABUK (Capital) | 0 | 1 | 9 | REPAIR/ REHABILITATION | 8126421.2928 | 1 |  | Completed | 1
QRF 2022 | CAR | Tabuk City | 136102 | Magabbangon Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 1 | REPAIR/ REHABILITATION | 1547589 | 1 |  | Completed | 1
QRF 2022 | CAR | Tabuk City | 136012 | Tabuk City Central School | CITY OF TABUK (Capital) | 0 | 1 |  | Others | 2114165.3102 | 1 |  | Completed | 1
QRF 2022 | CAR | Tabuk City | 136112 | Tannubong Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 4 | REPAIR/ REHABILITATION | 4639596.2249 | 1 |  | Completed | 1
QRF 2022 REPLENISHMENT | CAR | Abra | 134968 | Bangued East Central School | BANGUED (Capital) | Lone | 1 | 13 | REPAIR OF CLASSROOMS | 3628003.8798 | 1 |  | Completed | 1 | 2023-07-14 |  |  |  | 2023-02-28 |  |  |  |  | SEMBRI CONSTRUCTION
QRF 2022 REPLENISHMENT | CAR | Abra | 500743 | La Paz Integrated School | LA PAZ | Lone | 1 | 5 | REPAIR OF CLASSROOMS | 1260341.25 | 1 |  | Completed | 1 | 2023-07-14 |  |  |  | 2023-02-28 |  |  |  |  | SEMBRI CONSTRUCTION
QRF 2022 REPLENISHMENT | CAR | Abra | 305098 | Manabo NHS (San Jose Catacdegan NHS) | MANABO | Lone | 1 | 6 | Replacement | 21534025.5 | 1 |  | completed | 1 | 2023-08-12 |  |  |  | 2023-02-28 |  |  |  |  | SEMBRI CONSTRUCTION
QRF 2022 REPLENISHMENT | CAR | Abra | 305098 | Manabo NHS (San Jose Catacdegan NHS) | MANABO | Lone | 1 | 15 | REPAIR OF CLASSROOMS | 10178009.05 | 1 |  | Completed | 1 | 2023-11-10 |  |  |  | 2023-02-28 |  |  |  |  | SEMBRI CONSTRUCTION
QRF 2022 REPLENISHMENT | CAR | Abra | 305091 | Northern Abra NHS | SAN JUAN | Lone | 1 | 4 | Replacement | 33343514.75 | 1 |  | Completed | 1 | 2023-11-10 |  |  |  | 2023-02-28 |  |  |  |  | AD MARRERO CONSTRUCTION
QRF 2022 REPLENISHMENT | CAR | Abra | 135024 | Tayum Central School | TAYUM | Lone | 1 | 19 | REPAIR OF CLASSROOMS | 4659065.19 | 1 |  | Completed | 1 | 2023-08-12 |  |  |  | 2023-02-28 |  |  |  |  | SEMBRI CONSTRUCTION
QRF 2022 REPLENISHMENT | CAR | Apayao | 305123 | Pudtol Vocational High School | PUDTOL | Lone | 1 | 0 | REPAIR OF CLASSROOMS | 4805407.18 | 1 | ₱ 4,801,706.48 | Completed | 1 | 2023-11-07 | 2023-11-23 | QRF-2022-001 |  | 2023-05-15 | JUNE 20, 2019 | 2023-06-05 | 2023-06-19 | 2023-06-30 | Aquila Construction Co.
QRF 2022 REPLENISHMENT | CAR | Baguio City | 136388 | Elpidio R. Quirino Elementary School | BAGUIO CITY | Lone | 1 | 2 | REPAIR OF CLASSROOMS | 999883.15 | 1 | 846915.49 | completed | 1 | 2023-11-05 | [7 empty] | 2023-08-07 | EZRAH Construction Services
QRF 2022 REPLENISHMENT | CAR | Baguio City | 305280 | Irisan National High School | BAGUIO CITY | Lone | 1 | 4 | REPAIR OF CLASSROOMS | 1960625.84 | 1 | 821468.67 | completed | 1 | 2024-01-04 | [7 empty] | 2023-08-07 | JEKISU Construction
QRF 2022 REPLENISHMENT | CAR | Baguio City | 305277 | Roxas National High School | BAGUIO CITY | Lone | 1 | 2 | REPAIR OF CLASSROOMS | 976825.81 | 1 | 1548386.54 | completed | 1 | 2023-12-05 | [7 empty] | 2023-08-07 | EZRAH Construction Services
QRF 2022 REPLENISHMENT | CAR | Benguet | 305138 | Loo National High School | BUGUIAS | Lone | 1 | 8 | REPAIR OF CLASSROOMS | 5200000 | 1 | 4668156.03 | Completed | 1 | 2024-02-13 | 2024-02-13 | QRF-2022-01 |  | 2023-03-10 |  | 2023-04-11 | 2023-06-13 | 2023-07-18 | MBW Construction
QRF 2022 REPLENISHMENT | CAR | Benguet | 135524 | Itogon Central School | ITOGON | Lone | 1 | 0 | REPAIR OF CLASSROOMS | 2500000 | 1 | 2247286.99 | Completed | 1 | 2023-12-08 | 2024-02-04 | QRF-2022-02 |  | 2023-03-10 |  | 2023-04-11 | 2023-06-08 | 2023-07-11 | JB BANGIT
QRF 2022 REPLENISHMENT | CAR | Benguet | 135617 | Balili ES | LA TRINIDAD (Capital) | Lone | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 1 | 1874733.11 | Completed | 1 | 2023-12-07 | 2024-01-19 | QRF-2022-03 |  | 2023-03-10 |  | 2023-04-11 | 2023-06-08 | 2023-07-10 | PRECIOUS GOLD CONSTRUCTION
QRF 2022 REPLENISHMENT | CAR | Benguet | 135624 | La Trinidad CS | LA TRINIDAD (Capital) | Lone | 1 | 15 | REPAIR OF CLASSROOMS | 9750000 | 1 | 8703674.46 | Completed | 1 | 2024-03-06 | 2024-05-16 | QRF-2022-04 |  | 2023-03-10 |  | 2023-04-11 | 2023-06-08 | 2023-07-10 | HAIGHT'S CONSTRUCTION
QRF 2022 REPLENISHMENT | CAR | Benguet | 135631 | Puguis Elementary School | LA TRINIDAD (Capital) | Lone | 1 | 5 | Replacement | 12500000 | 1 | 10394095.06 | COMPLETED | 1 | 2024-03-06 |  | QRF-2022-08 |  | 2023-03-10 |  | 2023-04-11 | 2023-06-09 | 2023-07-10 | ZYMX CONSTRUCTION
QRF 2022 REPLENISHMENT | CAR | Benguet | 305151 | Lepanto NHS | MANKAYAN | Lone | 1 | 6 | REPAIR OF CLASSROOMS | 3900000 | 1 | 3783533.19 | COMPLETED | 1 | 2024-01-09 | 2024-05-15 | QRF-2022-06 |  | 2023-03-10 |  | 2023-04-11 | 2023-06-09 | 2023-07-13 | GEGA ENGINEERING
QRF 2022 REPLENISHMENT | CAR | Benguet | 135658 | Mankayan Central School | MANKAYAN | Lone | 1 | 18 | REPAIR OF CLASSROOMS | 11700000 | 1 | 9434950.12 | Completed | 1 | 2024-04-23 |  | QRF-2022-05 |  | 2023-03-10 |  | 2023-04-11 | 2023-06-09 | 2023-07-18 | CAIXIA CONSTRUCTION
QRF 2022 REPLENISHMENT | CAR | Benguet | 135716 | Tuba Central School | TUBA | Lone | 1 | 11 | REPAIR OF CLASSROOMS | 7150000 | 1 | 6344950.94 | completed | 1 | 2024-03-06 | 2024-05-30 | QRF-2022-07 |  | 2023-03-10 |  | 2023-04-11 | 2023-06-08 | 2023-07-10 | HAIGHT'S CONSTRUCTION
QRF 2022 REPLENISHMENT | CAR | Kalinga | 136076 | Rizal Central School | RIZAL (LIWAN) | Lone | 1 | 4 | Replacement | 4998077.29 | 1 |  | Completed | 1
QRF 2022 REPLENISHMENT | CAR | Mt. Province | 136186 | Kadaclan Elementary School | BARLIG | Lone | 1 | 8 | Replacement | 47763623.8471 | 1 | ₱ 43,528,472.23 | Completed | 1 | 2024-02-05 |  | Lot 7 QRF 2022 | INF-2023 R-006 | 2023-02-25 | 2023-03-03 | 2023-03-21 | 2023-11-04 | 2023-05-04 | HGW=3 Eng'g & Const'n
QRF 2022 REPLENISHMENT | CAR | Mt. Province | 136235 | Besao Central School | Besao | Lone | 1 | 1 | REPAIR OF CLASSROOM | 3979616.1247 | 1 | ₱ 3,946,200.79 | Completed | 1 | 2023-07-11 |  | Lot 2 QRF 2022 | INF-2023 R-001 | 2023-02-25 | 2023-03-03 | 2023-03-20 | 2023-11-04 | 2023-05-05 | Archie Prince Construction
QRF 2022 REPLENISHMENT | CAR | Mt. Province | 305255 | Mountain Province General Comprehensive High School | BONTOC (Capital) | Lone | 1 | 14 | REPAIR OF CLASSROOMS | 14697323.2501 | 1 | ₱ 13,966,159.08 | Completed | 1 | 2023-11-08 |  | Lot 4 QRF 2022 | INF-2023 R-003 | 2023-02-25 | 2023-03-03 | 2023-03-20 | 2023-11-04 | 2023-05-05 | WWW.Const'n
QRF 2022 REPLENISHMENT | CAR | Mt. Province | 136310 | Paracelis Central School | PARACELIS | Lone | 1 | 4 | Replacement | 13264675.6061 | 1 | ₱ 13,219,562.44 | completed | 1 | 2023-11-06 |  | Lot 6 QRF 2022 | INF-2023 R-005 | 2023-02-25 | 2023-03-03 | 2023-03-21 | 2023-11-04 | 2023-05-03 | MBW Construction
QRF 2022 REPLENISHMENT | CAR | Mt. Province | 136328 | Sabangan Central School | Sabangan | Lone | 1 | 8 | Replacement | 51127254.3521 | 1 |  | Completed | 1 | 2024-10-26 |  | Lot 1 QRF 2022 | INF-2023-R-008 | 2023-04-14 | 03/03/2023, 04/24/2023 | 3-20-23 / 5-10-23/july 17, 2023 | September 11, 2023 | 2023-09-25 | GACOSCOS CONSTRUCTION | ongoing w/ T.Ext'n
QRF 2022 REPLENISHMENT | CAR | Mt. Province | 136351 | Sagada Central School | Sagada | Lone | 1 | 10 | REPAIR OF CLASSROOMS | 9078760.939 | 1 | ₱ 9,042,909.29 | Completed | 1 | 2023-10-09 |  | Lot 5 QRF 2022 | INF-2023 R-004 | 2023-02-25 | 2023-03-03 | 2023-03-21 | 2023-11-04 | 2023-05-05 | FELA Builders
QRF 2022 REPLENISHMENT | CAR | Mt. Province | 136376 | Tadian Central School | TADIAN | Lone | 1 | 2 | Replacement | 6466962.0915 | 1 | ₱ 6,435,000.00 | Completed | 1 | 2023-09-09 |  | Lot 3 QRF 2022 | INF-2023 R-002 | 2023-02-25 | 2023-03-03 | 2023-03-20 | 2023-11-04 | 2023-05-05 | JM-MAS Const'n & Gen. Merchandise
QRF 2023 | CAR | Baguio City | 305280 | Irisan National High School | Baguio City | Lone | 1 | 6 | REPAIR OF CLASSROOMS | 1200000 | 2-R |  | completed | 1
QRF 2023 | CAR | Baguio City | 221501 | Kias Elementary School | Baguio City | Lone | 1 | 4 | REPAIR OF CLASSROOMS | 1000000 | 2-R |  | completed | 1
QRF 2023 | CAR | Ifugao | 135955 | Tinoc CS | TINOC | Lone | 1 | 4 | REPAIR OF CLASSROOMS | 4070250.08 | 2-R |  | completed | 1
QRF 2023 | CAR | Mt. Province | 305249 | Bansa National High School | BAUKO | Lone | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 8128437.39 | 2-S |  | completed | 1 | [10 empty] | contracts awarded
QRF 2023 | CAR | Mt. Province | 305258 | Natonin National High School | NATONIN | Lone | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 12015695 | 2-S |  | completed | 1 | [10 empty] | contracts awarded
QRF 2023 | CAR | Mt. Province | 319224 | Bunga National High School | TADIAN | Lone | 1 | 14 | REPAIR OF CLASSROOMS | 14169367.62 | 2-R |  | completed | 1 | [10 empty] | contracts awarded
QRF 2023 | CAR | Mt. Province | 136364 | Duagan Elementary School | TADIAN | Lone | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 11132912.72 | 2-S |  | completed | 1 | [10 empty] | contracts awarded
QRF 2024 | CAR | Abra | 130933 | Talaytay Primary School | SAN QUINTIN | Lone | 1 | 1 | Repair of Classrooms | 1812258.92 | 1- R |  | Ongoing | 0.8
QRF 2024 | CAR | Abra | 134974 | Sappaac ES | BANGUED (Capital) | Lone | 1 | 3 | Repair of Classrooms | 2314415.38 | 1- R |  | Ongoing | 0.8
QRF 2024 | CAR | Abra | 134977 | Bañacao ES | BANGUED (Capital) | Lone | 1 | 3 | Repair of Classrooms | 2234552.56 | 1- R |  | Ongoing | 0.8
QRF 2024 | CAR | Abra | 134982 | Patucannay ES | BANGUED (Capital) | Lone | 1 | 1 | Repair of Classrooms | 1303489 | 1- R |  | Completed | 1
QRF 2024 | CAR | Abra | 134988 | Bangcagan PS | BUCAY | Lone | 1 | 1 | Repair of Classrooms | 885896.4 | 1- R |  | Ongoing | 0.8
QRF 2024 | CAR | Abra | 135001 | Pagala East PS | BUCAY | Lone | 1 | 2 | Repair of Classrooms | 3070581.61 | 1- R |  | Completed | 1
QRF 2024 | CAR | Abra | 135019 | Don Rosalio Eduarte ES | DOLORES | Lone | 1 | 1 | Repair of Classrooms | 1266246.45 | 1- R |  | Ongoing | 0.8
QRF 2024 | CAR | Abra | 135028 | Bulbulala ES | LA PAZ | Lone | 1 | 13 | Repair of Classrooms | 8335019.94 | 1- R |  | Ongoing | 0.85
QRF 2024 | CAR | Abra | 135036 | Manganip ES | DANGLAS | Lone | 1 | 1 | Repair of Classrooms | 865024.79 | 1- R |  | Ongoing | 0.85
QRF 2024 | CAR | Abra | 305075 | Abra HS | BANGUED (Capital) | Lone | 1 | 4 | Repair of Classrooms | 2013234.97 | 1- R |  | Completed | 1 | [10 empty] | toon es realigned to abra hs, bangued west and velazco es
QRF 2024 | CAR | Abra | 134979 | Bangued West CS | BANGUED (Capital) | Lone | 1 | 3 | Repair of Classrooms | 2924888.53 | 1- R |  | Completed | 1 | [10 empty] | toon es realigned to abra hs, bangued west and velazco es
QRF 2024 | CAR | Abra | 135025 | Velasco ES | TAYUM | Lone | 1 | 3 | Repair of Classrooms | 2658989.57 | 1- R |  | Completed | 1 | [10 empty] | toon es realigned to abra hs, bangued west and velazco es
QRF 2024 | CAR | Abra | 135057 | Caridad Azares ES | LAGANGILANG | Lone | 1 | 2 | Repair of Classrooms | 1747040.5 | 1- R |  | Ongoing | 0.86
QRF 2024 | CAR | Abra | 135113 | Tiempo ES | TUBO | Lone | 1 | 1 | Repair of Classrooms | 937054.79 | 1- R |  | Ongoing | 0.85
QRF 2024 | CAR | Abra | 135121 | Lusuac ES | PEÑARRUBIA | Lone | 1 | 1 | Repair of Classrooms | 1234154.53 | 1- R |  | Ongoing | 0.8
QRF 2024 | CAR | Abra | 135128 | San Isidro CS | SAN ISIDRO | Lone | 1 | 3 | Repair of Classrooms | 2180649.37 | 1- R |  | Completed | 1
QRF 2024 | CAR | Abra | 135134 | Casilagan ES | PIDIGAN | Lone | 1 | 2 | Repair of Classrooms | 2204410.31 | 1- R |  | Ongoing | 0.8
QRF 2024 | CAR | Abra | 135139 | Nagdaingan ES | PIDIGAN | Lone | 1 | 2 | Repair of Classrooms | 1451566.94 | 1- R |  | Ongoing | 0.8
QRF 2024 | CAR | Abra | 135146 | Suyo Pilot ES | PIDIGAN | Lone | 1 | 3 | Repair of Classrooms | 2054760.88 | 1- R |  | Completed | 1
QRF 2024 | CAR | Abra | 135149 | Bolbolo ES | PILAR | Lone | 1 | 3 | Repair of Classrooms | 2207723.45 | 1- R |  | Completed | 1
QRF 2024 | CAR | Abra | 135175 | Bucloc CS | BUCLOC | Lone | 1 | 1 | Repair of Classrooms | 1682247.92 | 1- R |  | Ongoing | 0.77
QRF 2024 | CAR | Abra | 135183 | Dumagas ES | BOLINEY | Lone | 1 | 2 | Repair of Classrooms | 3818698.03 | 1- R |  | Completed | 1
QRF 2024 | CAR | Abra | 135218 | Nangobongan PS | SAN JUAN | Lone | 1 | 1 | Repair of Classrooms | 1079165.92 | 1- R |  | Completed | 1
QRF 2024 | CAR | Abra | 305085 | Dugong National High School | BUCAY | Lone | 1 | 2 | Repair of Classrooms | 1234154.53 | 1- R |  | Completed | 1
QRF 2024 | CAR | Abra | 305086 | Gaddani NHS | TAYUM | Lone | 1 | 2 | Repair of Classrooms | 1787642.05 | 1- R |  | Completed | 1
QRF 2024 | CAR | Abra | 305088 | Lul-luno NHS | LUBA | Lone | 1 | 1 | Repair of Classrooms | 852509.45 | 1- R |  | Ongoing | 0.86
QRF 2024 | CAR | Abra | 501343 | Maguyepyep Integrated School | SALLAPADAN | Lone | 1 | 2 | Repair of Classrooms | 3812923.03 | 1- R |  | Completed | 1

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%