## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | NO. OF CL | SCOPE OF WORK | PROJECT ALLOCATION | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
LMS 2020 | Region I | Pangasinan I, Lingayen | 500372 | Siapar Integrated | ANDA | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM & STEEL GATES | 18456468.1348 | 18371467.59 | completed | 1 | May 4, 2022 | 00:00:00 | 2021-07-003-INFRA | 0 | 00:00:00 | 00:00:00 | August 11, 2021 | August 25, 2021 | September 6, 2021 | ABC East Multi Builders and Traders | 0
LMS 2021 | Region I | Ilocos Norte | 100018 | Casilian ES | BACARRA | 1 | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 16963583.65 | 0 | Ongoing | 0.25 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0
LMS 2021 | Region I | Ilocos Norte | 100034 | Morong ES | BADOC | 2 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 18686642.15 | 0 | Ongoing | 0.25 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0
LMS 2021 | Region I | Ilocos Sur | 100577 | Matue PS | GREGORIO DEL PILAR (CONCEPCION) | 2 | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15489664.3886 | 13617950.39 | Abandoned | 0.45 | 2023-12-30 | 00:00:00 | PB-07-07-2021-0001 | 08 - 2021 | 2021-07-13 | 2021-07-21 | 2021-08-02 | ############### | 2021-10-06 | FFJJ Construction | 0
LMS 2021 | Region I | La Union | 101119 | Daeng ES | TUBAO | 2 | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, , SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 14037218.56 | 0 | Abandoned | 0.1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CENTRAL OFFICE IMPLEMENTED
LMS 2021 | Region I | Pangasinan I, Lingayen | 101520 | Dalupang ES | MABINI | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17662294.1851 | 17662294.1851 | Abandoned | 0.6 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | no movement/accomplishment as of February 2023
LMS 2023 | Region I | Ilocos Norte | 100001 | Apaleng-Libtong ES | BACARRA | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17170000 | 16983806.6 | Completed | 1 | 2024-06-16 | 2024-10-15 | PB-05-2023 | PB-05-2023 | 2023-07-03 | 2023-07-10 | 2023-07-24 | 2023-08-14 | 2023-08-25 | ELOCIN CONSTRUCTION | 0
LMS 2023 | Region I | Ilocos Sur | 100477 | Lamagan PS | CERVANTES | 2 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17170000 | 13462349.99 | Completed | 1 | 2024-01-31 | 2024-04-24 | 2023-07-007-PB-Works |  | 2023-07-25 | 2023-08-01 | 2023-08-14 | 2023-08-23 | 2023-09-04 | WWW.Construction | 0
LMS 2023 | Region I | La Union | 151005 | Lacong ES-Annex | SAN GABRIEL | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17170000 | 16946057.06 | Completed | 1 | 2024-01-06 | 2024-01-08 | 2023LMSRO1-01 | SDOLU-LMS 2023-1 | 2023-05-27 | 2023-06-05 | 2023-06-19 | 2023-07-10 | 2023-07-08 | HG LOPEZ CONSTRUCTION | DIVISION IMPLEMENTED COMPLETED
LMS 2023 | Region I | La Union | 101119 | Daeng ES | TUBAO | 2nd | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17158043.98 | 16937084.62 | COMPLETED | 1 | 2024-11-28 | 2024-11-28 | 2023LMSRO1-02 | SDOLU-LMS 2023-2 | 2023-11-20 | 2023-11-29 | 2023-12-13 | 2023-12-26 | 2024-01-05 | LAV CONSTRUCTION AND SUPPLY | Completed DIVISION IMPLEMENTED
LMS 2024 | Region I | La Union | 101087 | Sasaba PS | SANTOL | 1st | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17022941.1 | 16772636.16 | Completed | 1 | 2024-12-20 | 2024-12-10 | 2024LMS RO1-01 | SDOLU-2024 LMS-01 | 2024-08-04 | 2024-03-26 | 2024-04-11 | 2024-04-18 | 2024-06-24 | DPV BUILDERS AND CONSTRUCTION SUPPLY | Completed
LMS 2024 | Region I | La Union | 100821 | Bitag Elementary School | ARINGAY | 2nd | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17910473.72 | 17679318.86 | Completed | 1 | 2025-04-28 | 2025-05-06 | 2024LMS RO1-02 | SDOLU-2024 LMS-02 | 2024-08-04 | 2024-03-26 | 2024-04-11 | 2024-04-18 | 2024-06-24 | LAV CONSTRUCTION AND SUPPLY | Completed
LMS 2024 | Region I | Pangasinan I, Lingayen | 500371 | Awag Integrated School | ANDA | 1st | 1 | 3 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 17171717.17 | 11559999.13 | Ongoing | 0.95 | 2025-05-05 | 2025-05-02 | 2024-06-003-INFRA |  | 2024-06-27 | 2024-07-05 | 2024-07-17 | 2024-08-15 | 2024-10-08 | JFM Altitude Construction Corporation | for final inspection

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.