## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
QRF 2019 | Region I | La Union | 101069 | Naguituban ES | San Juan | 1 | 1 | 2 | 1STY 2CL | 3607027.98 | 1 | 3583247.64 | Completed | 1 | 2019-10-20 | 2019-09-10 |  |  | 2019-06-06 | 2019-06-13 | 2019-06-28 | 2019-07-15 | 2019-07-22 | JA OLIVAR ENGINEERING DESIGN, CONSTRUCTION & SUPPLY
QRF 2022 | Region I | Candon City | 235501 | Candon South Central School SPED Center | CITY OF CANDON | 2 | 1 | 2 | REPAIR/ REHABILITATION | 901319.11 | 1 |  | Completed | 1 | [10 empty] | NTP issued
QRF 2022 | Region I | La Union | 100846 | Bacnotan Central School | BACNOTAN | 1 | 1 | 3 | REPAIR/ REHABILITATION | 1819327.09 | 1 | 1811418.37 | Completed | 1 | 2022-12-22 | 2022-12-20 | QRF2022-RO1-LU-01 |  | 2022-08-01 | 2022-08-10 | 2022-08-24 | 2022-09-01 | 2022-09-23 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND SUPPLIES
QRF 2022 | Region I | La Union | 100875 | Balaoan CES | BALAOAN | 1 | 1 | 11 | REPAIR/ REHABILITATION | 6693187.73 | 1 | 6527091.32 | Completed | 1 | 2022-12-22 | 2022-12-21 | QRF2022-RO1-LU-02 |  | 2022-08-01 | 2022-08-10 | 2022-08-24 | 2022-09-01 | 2022-09-23 | J.M.B.M. CONSTRUCTION
QRF 2022 | Region I | La Union | 100911 | Bauang North CS | BAUANG | 2 | 1 | 3 | REPAIR/ REHABILITATION | 1801364.18 | 1 | 1791987.88 | Completed | 1 | 2022-12-22 | 2022-12-20 | QRF2022-RO1-LU-03 |  | 2022-08-01 | 2022-08-10 | 2022-08-24 | 2022-09-01 | 2022-09-23 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND SUPPLIES
QRF 2022 | Region I | Laoag City | 153001 | Sto. Nino Elementary School | LAOAG CITY (Capital) | 1 | 1 | 3 | REPAIR/ REHABILITATION | 571180.68 | 1 |  | Completed | 1 | [10 empty] | NTP Issued
QRF 2022 REPLENISHMENT | Region I | Alaminos City | 101166 | Alaminos Central School | CITY OF ALAMINOS | 1st | 1 | 17 | REPAIR OF CLASSROOMS | 28000000 | 1 | Php27,723,177.18 | completed | 1 | 2023-12-30 | 2023-12-19 |  |  | March 14,2023-April 3, 2023 | 2023-03-22 | 2023-04-04 | 2023-04-17 | 2023-04-25 | Manimeld's construction and Iron Works | with additive VO- 276,822.82, revised contract amount 28,000,000, revised Completion date DEcember 30, 2023. Revised contract amount 28,000,000.00
QRF 2022 REPLENISHMENT | Region I | Alaminos City | 300155 | Alaminos City National High School | CITY OF ALAMINOS | 1st | 1 | 12 | Replacement | 54000000 | 1 | Php27,723,177.18 | Completed | 1 | 2024-05-17 |  | 2023-07-12 | 2023-08-29 | 2023-07-06 | 2023-07-13 | 2023-07-25 |  | 2023-09-01 | Aylan Construction & Trading | with time extension
QRF 2022 REPLENISHMENT | Region I | Alaminos City | 300260 | Telbang National High School | CITY OF ALAMINOS | 1st | 1 | 12 | Replacement | 49200000 | 1 |  | Completed | 1 | 2024-03-25 |  | 2023-07-12 | 2023-08-28 | 2023-07-06 | 2023-07-13 | 2023-07-25 |  | 2023-08-29 | T.G. Ocampo Construction and Surveying Services | April 2025: For punchlisitng Previous remarks: with time extension
QRF 2022 REPLENISHMENT | Region I | Batac City | 320804 | City of Batac NHS Poblacion | CITY OF BATAC | 2nd | 1 | 10 | REPAIR OF CLASSROOMS | 3272296.8 | 1 | 2727538.84 | completed | 1 |  | 2023-12-17 | [6 empty] | 2023-07-17 | ELOCIN CONSTRUCTION
QRF 2022 REPLENISHMENT | Region I | Candon City | 300044 | Candon National High School | CITY OF CANDON | 2nd | 1 | 40 | Replacement | 140000000 | 1 | 50451627.8 | Completed | 1 | 2024-05-17 |  | 2023-07-12 | 2023-08-31 | 2023-07-06 | 2023-07-13 | 2023-07-25 |  | 2023-09-01 | ASS Construction/ MA Tejada Construction (Joint Venture) | with time extension
QRF 2022 REPLENISHMENT | Region I | Candon City | 300044 | Candon National High School | CITY OF CANDON | 2nd | 1 | 10 | REPAIR OF CLASSROOMS | 1188260.78 | 1 | ₱1,178,082.17 | completed | 1 |  | 2023-08-05 |  |  | March 26, 2023 -April 18, 2023 |  | 2023-04-18 |  |  | M.A. Tejada Construction
QRF 2022 REPLENISHMENT | Region I | Candon City | 100435 | Candon North Central School | CITY OF CANDON | 2nd | 1 | 4 | Replacement | 12000000 | 1 | 9928466.6536 | Ongoing | 0.8538 | 2024-05-17 |  | 2023-07-12 | 2023-08-30 | 2023-07-06 | 2023-07-13 | 2023-07-25 |  | 2023-09-01 | ASS Construction | Project Revised Cost to 9,956,925.74
QRF 2022 REPLENISHMENT | Region I | Dagupan City | 102165 | Bonuan Buquig ES | DAGUPAN CITY | 4th | 1 | 8 | REPAIR OF CLASSROOMS | 4000000 | 1 | 3990008.65 | completed | 1 | 2023-12-13 | 2023-12-13 |  |  | 2023-08-11 | 2023-08-25 | 2023-09-07 | 2023-09-12 | 2023-09-15 | VIKING III BUILDERS
QRF 2022 REPLENISHMENT | Region I | Dagupan City | 300367 | Bonuan Buquig NHS | DAGUPAN CITY | 4th | 1 | 20 | REPAIR OF CLASSROOMS | 6000000 | 1 | 5908391.57 | completed | 1 | 2023-12-13 | 2023-12-13 |  |  | 2023-08-11 | 2023-08-25 | 2023-09-07 | 2023-09-12 | 2023-09-15 | ZOTA TRADING AND CONSTRUCTION
QRF 2022 REPLENISHMENT | Region I | Dagupan City | 300368 | Dagupan City NHS | DAGUPAN CITY | 4th | 1 | 24 | REPAIR OF CLASSROOMS | 6000000 | 1 | 4913922.28 | completed | 1 | 2023-12-13 | 2023-12-13 |  |  | 2023-08-11 | 2023-08-25 | 2023-09-07 | 2023-09-12 | 2023-09-15 | ELMUEL JAY TRADING AND CONSTRUCTION
QRF 2022 REPLENISHMENT | Region I | Dagupan City | 500054 | Federico N. Ceralde IS | DAGUPAN CITY | 4th | 1 | 18 | REPAIR OF CLASSROOMS | 7000000 | 1 | 6943753.13 | completed | 1 | 2023-12-13 | 2023-12-13 |  |  | 2023-08-11 | 2023-08-25 | 2023-09-07 | 2023-09-12 | 2023-09-15 | A.S.S. CONSTRUCTION
QRF 2022 REPLENISHMENT | Region I | Dagupan City | 102170 | North Central Elementary School | DAGUPAN CITY | 4th | 1 | 3 | REPAIR OF CLASSROOMS | 2100000 | 1 | 2086111.66 | completed | 1 | 2023-12-13 | 2023-12-13 |  |  | 2023-08-11 | 2023-08-25 | 2023-09-07 | 2023-09-12 | 2023-09-15 | ELMUEL JAY TRADING AND CONSTRUCTION
QRF 2022 REPLENISHMENT | Region I | Dagupan City | 500055 | Pugaro IS | DAGUPAN CITY | 4th | 1 | 5 | REPAIR OF CLASSROOMS | 3000000 | 1 | 2971417.4 | completed | 1 | 2023-12-13 | 2023-12-13 |  |  | 2023-08-11 | 2023-08-25 | 2023-09-07 | 2023-09-12 | 2023-09-15 | ELGRAM TRADING AND CONSTRUCTION
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1st | 1 | 3 | Replacement | 9000000 | 1 |  | Completed | 1 | 2024-05-17 |  |  |  |  | 2023-07-16 | 7/25-26/2023 |  |  | Elocin Construction | With Time Suspension/Extension
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1st |  | 3 | Replacement | 9000000 | 1 | 7586101.37 | completed | 1 | 2024-05-17 |  | 2023-07-12 | 2023-08-34 | 2023-07-06 | 2023-07-13 | 2023-07-25 |  | 2023-09-01 | Elocin Construction | With Time Suspension/Extension
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1st |  | 4 | Replacement | 12000000 | 1 |  | Completed | 1 | 2024-05-17 |  |  |  |  | 2023-07-16 | 7/25-26/2023 |  |  | Elocin Construction | With Time Suspension/Extension
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1st |  | 4 | Replacement | 12000000 | 1 | 8990670.2806 | completed | 1 | 2024-05-17 |  | 2023-07-12 | 2023-08-33 | 2023-07-06 | 2023-07-13 | 2023-07-25 |  | 2023-09-01 | Elocin Construction | With Time Suspension/Extension
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1st |  | 10 | Replacement | 30000000 | 1 | 24413054.65 | Ongoing | 0.8 | 2024-05-17 |  | 2023-07-12 | 2023-08-33 | 2023-07-06 | 2023-07-13 | 2023-07-25 |  | 2023-09-01 | Elocin Construction | With Time Suspension/Extension
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 100120 | Dingras Central ES | DINGRAS | 2nd | 1 | 6 | REPAIR OF CLASSROOMS | 2764628.2477 | 1 | 2262662.78 | Completed | 1 | 2023-10-25 |  | PB-03-2023-1 |  | 2023-03-07 | 2023-03-13 | 2023-03-27 | 2023-03-30 | 2023-04-27 | Elocin Construction
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 100152 | Marcos Central School | MARCOS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1842214.5794 | 1 | ₱1,668,320.78 | Completed | 1 | 2023-07-26 | 2023-08-05 | PB-03-2023-2 |  | 2023-03-07 | 2023-03-13 | 2023-03-27 | 2023-03-30 | 2023-04-27 | Elocin Construction
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 320815 | Bingao National High School | SAN NICOLAS | 2nd | 1 | 6 | REPAIR OF CLASSROOMS | 3858132.46 | 1 | 3011166.41 | Completed | 1 | 2023-11-22 |  | PB-03-2023-4 |  | 2023-03-07 | 2023-03-13 | 2023-03-27 | 2023-03-30 | 2023-04-27 | Elocin Construction
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 100260 | San Nicolas ES | SAN NICOLAS | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2433485.53 | 1 | 1859917.48 | Completed | 1 | 2023-12-01 |  | PB-03A-2023-3 |  | 2023-04-13 | 2023-04-19 | 2023-05-02 | 2023-05-08 | 2023-05-29 | Elocin Construction
QRF 2022 REPLENISHMENT | Region I | Ilocos Sur | 100501 | Magsingal North Central School | MAGSINGAL | 1st | 1 | 12 | Replacement | 31559226.85 | 1 | 31529226.85 | Ongoing | 0.75 | 2024-09-28 |  | 2023-07-12 | 2023-08-35 | 2023-07-06 | 2023-07-13 | 2023-08-07 |  | 2023-08-31 | Manimeld’s Construction and Iron Works | Revised ABC to 31,559,226.85
QRF 2022 REPLENISHMENT | Region I | Ilocos Sur | 300056 | Lussoc National High School | SANTO DOMINGO | 1st | 1 | 8 | REPAIR OF CLASSROOMS | 1410280.53 | 1 | ₱1,409,123.18 | Completed | 1 | 2023-08-19 | 2023-08-18 | 2023-04002-PB-Works |  | 2023-04-24 | 2023-05-02 | 2023-05-23 | 2023-05-31 | 2023-06-21 | M.A. Tejada Construction
QRF 2022 REPLENISHMENT | Region I | Ilocos Sur | 300072 | Teodoro Hernaez NHS | SANTA LUCIA | 2nd | 1 | 12 | REPAIR OF CLASSROOMS | 1880259.3 | 1 | ₱1,454,728.12 | Completed | 1 | 2023-08-19 | 2023-08-18 | 2023-04002-PB-Works |  | 2023-04-24 | 2023-05-02 | 2023-05-23 | 2023-05-31 | 2023-06-21 | M.A. Tejada Construction
QRF 2022 REPLENISHMENT | Region I | La Union | 300095 | Bacnotan National High School | BACNOTAN | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1690747.91 | 1 | ₱1,688,435.11 | Completed | 1 | 2023-07-18 | 2023-07-12 | QRF2022-RO1-LU-01 |  | 2023-03-14 | 2023-03-21 | 2023-04-04 | 2023-04-17 | 2023-04-27 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND SUPPLIES
QRF 2022 REPLENISHMENT | Region I | La Union | 300114 | Dona Francisca Lacsamana de Ortega Memorial National High School | BANGAR | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 3295309.0192 | 1 | ₱2,570,259.41 | Completed | 1 | 2023-08-06 | 2023-08-02 | QRF2022-RO1-LU-06 |  | 2023-03-14 | 2023-03-21 | 2023-04-04 | 2023-04-17 | 2023-04-27 | DPV BUILDERS AND CONSTRUCTION SUPPLY
QRF 2022 REPLENISHMENT | Region I | La Union | 300114 | Dona Francisca Lacsamana de Ortega Memorial National High School | BANGAR | 1st |  | 12 | REPAIR OF CLASSROOMS | 6453979 | 1 | ₱4,975,440.38 | Completed | 1 | 2023-09-05 | 2023-09-01 | QRF2022-RO1-LU-07 |  | 2023-03-14 | 2023-03-21 | 2023-04-04 | 2023-04-17 | 2023-04-27 | DPV BUILDERS AND CONSTRUCTION SUPPLY
QRF 2022 REPLENISHMENT | Region I | La Union | 100860 | Bagulin CES | BAGULIN | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1319380.58 | 1 | ₱1,296,139.72 | Completed | 1 | 2023-07-17 | 2023-07-12 | QRF2022-RO1-LU-05 |  | 2023-03-14 | 2023-03-21 | 2023-04-04 | 2023-04-17 | 2023-04-27 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND SUPPLIES
QRF 2022 REPLENISHMENT | Region I | La Union | 101001 | Pugo Central School | PUGO | 2nd | 1 | 7 | REPAIR OF CLASSROOMS | 3610020.2541 | 1 | ₱3,599,857.82 | Completed | 1 | 2023-08-06 | 2023-08-02 | QRF2022-RO1-LU-08 |  | 2023-03-14 | 2023-03-21 | 2023-04-04 | 2023-04-17 | 2023-04-27 | EE MADAYAG CONSTRUCTION
QRF 2022 REPLENISHMENT | Region I | La Union | 101096 | Damortis ES | SANTO TOMAS | 2nd | 1 | 7 | REPAIR OF CLASSROOMS | 3245119.9514 | 1 | ₱3,204,773.82 | Completed | 1 | 2023-08-06 | 2023-06-02 | QRF2022-RO1-LU-09 |  | 2023-03-14 | 2023-03-21 | 2023-04-04 | 2023-04-17 | 2023-04-27 | EE MADAYAG CONSTRUCTION
QRF 2022 REPLENISHMENT | Region I | Laoag City | 300374 | Ilocos Norte National High School | LAOAG CITY (Capital) | 1st | 1 | 12 | REPAIR OF CLASSROOMS | 1965217.36 | 1 |  | Completed | 1
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 101132 | AGNO CENTRAL SCHOOL | AGNO | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 927125.7 | 1 | 921100 | Completed | 1 | 2023-10-26 | 2023-10-25 | 2023-05-12-INFRA |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-06-26 | 2023-06-29 | CLP Builders
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 500441 | Dasol Integrated School | DASOL | 1st | 1 | 8 | Replacement | 21412474.28 | 1 |  | Completed | 1 | 2024-03-27 |  | 2023-07-12 | 2023-08-37 | 2023-07-06 | 2023-07-13 | 2023-07-26 |  | 2023-08-31 | MCB Construction & Supply
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 500441 | Dasol Integrated School | DASOL | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 2781377.1 | 1 | 2769811.29 | Completed | 1 | 2023-10-26 | 2023-10-11 | 2023-05-12-INFRA |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-06-26 | 2023-06-29 | Angelina T. Dizon Construction And Supply
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 500614 | Infanta Integrated School | INFANTA | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 1854251.4 | 1 | 1847200 | Completed | 1 | 2023-10-26 | 2023-10-25 | 2023-05-12-INFRA |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-06-26 | 2023-06-29 | CLP Builders
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 500618 | Pangascasan IS | SUAL | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1390688.55 | 1 | 1370306.45 | Completed | 1 | 2023-10-26 | 2023-10-25 | 2023-05-12-INFRA |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-06-26 | 2023-06-29 | Chestinan Construction Corporation
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300200 | Dumpay National High School | BASISTA | 2nd | 1 | 8 | Replacement | 24934327.79 | 1 |  | Completed | 1 | 2024-02-26 |  | 2023-07-12 | 2023-08-36 | 2023-07-06 | 2023-07-13 | 2023-08-07 |  | 2023-08-31 | Manimeld’s Construction and Iron Works
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300200 | Dumpay National High School | BASISTA | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 1854251.4 | 1 | 1824572.29 | Completed | 1 | 2023-10-26 | 2023-10-25 | 2023-05-12-INFRA |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-06-26 | 2023-06-29 | Aldana Construction
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300235 | Parayao National High School | BINMALEY | 2nd | 1 | 12 | Replacement | 32948933.15 | 1 |  | Ongoing | 0.4936 | 2024-09-16 |  | 2023-07-12 |  | 2023-07-06 | 2023-07-13 |  |  | 2023-12-22 | MCB Construction & Supply
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300235 | Parayao National High School | BINMALEY | 2nd | 1 | 15 | REPAIR OF CLASSROOMS | 6953442.75 | 1 | 6943245.24 | Completed | 1 | 2023-11-08 | 2023-10-18 | 2023-05-12-INFRA |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-10 | 2023-07-12 | DPV Builders and Construction Supply
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300267 | Irene Rayos Ombac NHS | BUGALLON | 2nd | 1 | 12 | REPAIR OF CLASSROOMS | 5562754.2 | 1 | 5525014.04 | Completed | 1 | 2023-11-22 | 2023-11-21 | 2023-05-12-INFRA |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-24 | 2023-07-26 | WM Salayog constructiona nd SUpply
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300234 | Pangasinan School of Arts and Trades | LINGAYEN (Capital) | 2nd | 1 | 16 | Replacement | 40963538.51 | 1 |  | Ongoing | 0.5077 | 2024-09-16 |  | 2023-07-12 |  | 2023-07-06 | 2023-07-13 |  |  | 2023-12-22 | MCB Construction & Supply
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300234 | Pangasinan School of Arts and Trades | LINGAYEN (Capital) | 2nd | 1 | 20 | REPAIR OF CLASSROOMS | 9271257 | 1 | 9210922.62 | Completed | 1 | 2023-10-26 | 2023-10-24 | 2023-05-12-INFRA |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-06-26 | 2023-06-29 | ABC East Multi Builders And Traders
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 101585 | Mangatarem I CS | MANGATAREM | 2nd | 1 | 12 | REPAIR OF CLASSROOMS | 5562754.2 | 1 | 5530867.38 | Completed | 1 | 2023-10-26 | 2023-10-24 | 2023-05-12-INFRA |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-06-26 | 2023-06-29 | Manimeld'S Construction And Iron Works
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300236 | Urbiztondo National High School | URBIZTONDO | 2nd | 1 | 15 | REPAIR OF CLASSROOMS | 6953442.75 | 1 | 6933376.41 | Completed | 1 | 2023-10-26 | 2023-10-25 | 2023-05-12-INFRA |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-06-26 | 2023-06-29 | Elmuel Jay Trading And Construction
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300183 | Calasiao Comprehensive NHS | CALASIAO | 3rd | 1 | 20 | REPAIR OF CLASSROOMS | 9271257 | 1 | 9231257 | Completed | 1 | 2023-10-26 | 2023-10-26 | 2023-05-12-INFRA |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-06-26 | 2023-06-29 | Jeusmack Builders and Construction Supply
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300198 | Doyong-Malabago NHS | CALASIAO | 3rd | 1 | 15 | REPAIR OF CLASSROOMS | 6953442.75 | 1 | 6913442.43 | Completed | 1 | 2023-10-26 | 2023-10-26 | 2023-05-12-INFRA |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-06-26 | 2023-06-29 | Jeusmack Builders and Construction Supply
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 101546 | Malasiqui I CS | MALASIQUI | 3rd | 1 | 3 | REPAIR OF CLASSROOMS | 1390688.55 | 1 | 1384628.86 | Completed | 1 | 2023-10-26 | 2023-10-25 | 2023-05-12-INFRA |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-06-26 | 2023-06-29 | Q&M Construction And Supply
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300220 | Malasiqui NHS | MALASIQUI | 3rd | 1 | 14 | REPAIR OF CLASSROOMS | 6489879.9 | 1 | 6461994.34 | Completed | 1 | 2023-10-26 | 2023-10-25 | 2023-05-12-INFRA |  | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-06-26 | 2023-06-29 | Elgram Trading And Construction
QRF 2022 REPLENISHMENT | Region I | San Carlos City | 500059 | Agdao Integrated School | SAN CARLOS CITY | 3rd | 1 | 2 | REPAIR OF CLASSROOMS | 973850.07 | 1 | 917888.95 | completed | 1 | 2023-06-03 | 2023-06-03 |  |  |  |  | APRIL 4,2023 |  | 2023-04-26 | RGP SUCCESS VENTURES INC
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 101021 | Bangbangolan ES | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 4 | Replacement | 10000000 | 1 | 9983672.11 | Completed | 1 | 2024-05-17 |  |  |  |  | 2023-07-16 | 7/25-26/2023 |  |  | HG Lopez Construction
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 101039 | Catbangen ES | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 9 | Replacement | 22500000 | 1 | 22440043.66 | Ongoing | 0.8 | 2024-05-17 |  |  |  |  | 2023-07-16 | 7/25-26/2023 |  |  | HG Lopez Construction
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 300118 | La Union NHS | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 12 | Replacement | 30000000 | 1 | 29857906 | completed | 1 | 2024-05-17 |  |  |  |  | 2023-07-16 | 7/25-26/2023 |  |  | HG Lopez Construction
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 500482 | Lingsat Integrated School | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 12 | Replacement | 30000000 | 1 | 29932498 | Ongoing | 0.8 | 2024-05-17 |  |  |  |  | 2023-07-16 | 7/25-26/2023 |  |  | HG Lopez Construction
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 500482 | Lingsat Integrated School | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 12 | REPAIR OF CLASSROOMS | 1060966.05 | 1 | 1059997.66 | completed | 1 | 2023-08-31 | 2023-08-31 | INFRA-002-2023 | INFRA-002-2023 | 2023-03-23 | 2023-03-30 | 2023-04-12 | 2023-04-20 | 2023-04-28 | JD MADRID CONSTRUCTION
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 101030 | San Fernando North CS (North CES) | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 4 | Replacement | 10000000 | 1 | 9950511.25 | Completed | 1 | 2024-05-17 |  |  |  |  | 2023-07-16 | 7/25-26/2023 |  |  | Manimelds Construction and Iron Works
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 101030 | San Fernando North CS (North CES) | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 7 | REPAIR OF CLASSROOMS | 1048973.66 | 1 | 1048967.97 | completed | 1 | 2023-08-31 | 2023-08-31 | INFRA-002-2023 | INFRA-002-2023 | 2023-03-23 | 2023-03-30 | 2023-04-12 | 2023-04-20 | 2023-04-28 | JD MADRID CONSTRUCTION
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 500602 | San Fernando South Central Integrated School (South CIS) | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 12 | Replacement | 30000000 | 1 | 29932840.74 | Completed | 1 | 2024-05-17 |  |  |  |  | 2023-07-16 | 7/25-26/2023 |  |  | Manimelds Construction and Iron Works
QRF 2022 REPLENISHMENT | Region I | Urdaneta City | 102269 | Badipa Elementary School | CITY OF URDANETA | 5th | 1 | 9 | REPAIR OF CLASSROOMS | 2016858.14 | 1 | ₱2,011,483.38 | completed | 1 | 2023-08-30 | 2023-08-24 | QRF REPAIR 2022-R1-URDANETA CITY-001 | 202303015 | 2023-03-08 | 2023-04-20 | 2023-05-03 | 2023-05-11 | 2023-05-30 | ELMUELJAY TARDING AND CONSTRUCTION
QRF 2022 REPLENISHMENT | Region I | Urdaneta City | 102294 | Don Amadeo Perez, Sr. Memorial Elementary Central School - East | CITY OF URDANETA | 5th | 1 | 4 | Replacement | 15313741.51 | 1 | 15263741.51 | completed | 1 | 2024-02-26 |  | 2023-07-12 | 2023-08-36 | 2023-07-06 | 2023-07-13 | 2023-08-07 |  | 2023-08-31 | Manimeld’s Construction and Iron Works
QRF 2022 REPLENISHMENT | Region I | Vigan City | 300052 | Ilocos Sur National High School | CITY OF VIGAN (Capital) | 1st | 1 |  | Replacement | 125000000 | 1 | 123384851.8 | Completed | 1 | 2024-05-17 |  | 2023-07-12 | 2023-08-41 | 2023-07-06 | 2023-07-13 | 2023-07-26 |  | 2023-09-01 | ASS Construction
QRF 2023 | Region I | Ilocos Norte | 300002 | Bacarra NCHS | BACARRA | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 2-R | 1834811.6 | Completed | 1 | 2024-09-28 | 2024-08-07 | PB-19-2023-1 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-01 | Abeian Construction
QRF 2023 | Region I | Ilocos Norte | 100013 | Bangsirit ES | BACARRA | 1st | 1 | 8 | REPAIR OF CLASSROOMS | 4925877 | 2-R | 4401231.88 | completed | 1 | 2024-09-28 | 2024-07-11 | PB-19-2023-2 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-01 | DPV Builders and Construction Supply
QRF 2023 | Region I | Ilocos Norte | 100018 | Casilian ES | BACARRA | 1st | 1 | 1 | REPAIR OF CLASSROOM | 639120.75 | 2-R | 634587.67 | completed | 1 | 2024-09-28 | 2024-05-03 | PB-19-2023-2 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-01 | DPV Builders and Construction Supply
QRF 2023 | Region I | Ilocos Norte | 100007 | Pasiocan ES | BACARRA | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1784970.3 | completed | 1 | 2024-09-28 | 2024-08-07 | PB-19-2023-1 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-01 | Abeian Construction
QRF 2023 | Region I | Ilocos Norte | 100009 | Sabas-Sagisi Memorial Elem. School | BACARRA | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1784635.64 | completed | 1 | 2024-09-28 | 2024-08-07 | PB-19-2023-1 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-01 | Abeian Construction
QRF 2023 | Region I | Ilocos Norte | 320801 | BANBAN NHS | BANGUI | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 1595900 | 2-R | 1365141.42 | Completed | 1 | 2024-10-01 | 2024-09-20 | PB-19B-2023-7 |  | 2024-03-04 | 2024-03-08 | 2024-03-25 |  | 2024-05-29 | LAV Construction
QRF 2023 | Region I | Ilocos Norte | 320802 | LANAO NATIONAL HIGH SCHOOL | BANGUI | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1050000 | 2-R | 895425.54 | Completed | 1 | 2024-10-01 | 2024-09-20 | PB-19B-2023-7 |  | 2024-03-04 | 2024-03-08 | 2024-03-25 |  | 2024-05-29 | LAV Construction
QRF 2023 | Region I | Ilocos Norte | 100107 | Paayas ES | BURGOS | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3020855 | 2-R | 2572715.41 | Completed | 1 | 2024-10-01 | 2024-09-30 | PB-19B-2023-6 |  | 2024-03-04 | 2024-03-08 | 2024-03-25 |  | 2024-05-29 | LAV Construction
QRF 2023 | Region I | Ilocos Norte | 100167 | Dampig ES | PAGUDPUD | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1895646.18 | completed | 1 | 2024-08-29 | 2024-08-07 | PB-19-2023-8 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-01 | Abeian Construction
QRF 2023 | Region I | Ilocos Norte | 300026 | Pasaleng National High School | PAGUDPUD | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3020855 | 2-R | 3016937.09 | Completed | 1 | 2024-08-29 | 2024-08-07 | PB-19-2023-8 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-01 | Abeian Construction
QRF 2023 | Region I | Ilocos Norte | 100199 | Davila ES | PASUQUIN | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3020855 | 2-R | 2506581.45 | Completed | 1 | 2024-11-04 | 2024-05-08 | PB-19B-2023-15 |  | 2024-03-04 | 2024-03-08 | 2024-03-25 |  | 2024-05-08 | DPV Builders and Construction Supply
QRF 2023 | Region I | Ilocos Norte | 300014 | Davila National High School | PASUQUIN | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 2788000 | 2-R | 2314877.57 | Completed | 1 | 2024-11-04 | 2024-05-08 | PB-19B-2023-15 |  | 2024-03-04 | 2024-03-08 | 2024-03-25 |  | 2024-05-08 | DPV Builders and Construction Supply
QRF 2023 | Region I | Ilocos Norte | 100206 | Nagsanga ES | PASUQUIN | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1622920.46 | Completed | 1 | 2024-10-01 | 2024-08-11 | PB-19B-2023-16 |  | 2024-03-04 | 2024-03-08 | 2024-03-25 |  | 2024-05-29 | LAV Construction
QRF 2023 | Region I | Ilocos Norte | 100208 | Pasuquin Central Elementary School | PASUQUIN | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 3750206 | 2-R | 3742897.43 | Completed | 1 | 2024-08-29 | 2024-07-18 | PB-19-2023-17 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-01 | DPV Builders and Construction Supply
QRF 2023 | Region I | Ilocos Norte | 100209 | Puyupuyan ES | PASUQUIN | 1st | 1 | 1 | REPAIR OF CLASSROOM | 639120.75 | 2-R | 636101.98 | completed | 1 | 2024-08-29 | 2024-07-18 | PB-19-2023-17 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-01 | DPV Builders and Construction Supply
QRF 2023 | Region I | Ilocos Norte | 100213 | Surong PS | PASUQUIN | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1187200 | 2-R | 1012229.86 | Completed | 1 | 2024-10-01 | 2024-08-11 | PB-19B-2023-16 |  | 2024-03-04 | 2024-03-08 | 2024-03-25 |  | 2024-05-29 | LAV Construction
QRF 2023 | Region I | Ilocos Norte | 100218 | Boyboy ES | PIDDIG | 1st | 1 | 1 | REPAIR OF CLASSROOM | 348290 | 2-R | 343985.21 | Completed | 1 | 2024-11-24 | 2024-11-20 | PB-19-2023-18 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-04 | Elocin Construction
QRF 2023 | Region I | Ilocos Norte | 100271 | Sarrat Central School | SARRAT | 1st | 1 | 1 | REPAIR OF CLASSROOM | 348290 | 2-R | 345057.91 | Completed | 1 | 2024-11-24 | 2024-11-20 | PB-19-2023-18 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-04 | Elocin Construction
QRF 2023 | Region I | Ilocos Norte | 300029 | Sarrat National High School | SARRAT | 1st | 1 | 1 | REPAIR OF CLASSROOM | 639120.75 | 2-R | 632610.25 | Completed | 1 | 2024-11-24 | 2024-11-20 | PB-19-2023-18 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-04 | Elocin Construction
QRF 2023 | Region I | Ilocos Norte | 100311 | Dasar ES | VINTAR | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1794270.16 | completed | 1 | 2024-08-29 | 2024-08-27 | PB-19A-2023-19 |  | 2023-12-20 | 2023-12-27 | 2024-01-08 |  | 2024-04-01 | LAV Construction
QRF 2023 | Region I | Ilocos Norte | 320821 | ISIC-ISIC NATIONAL HIGH SCHOOL | VINTAR | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 633380 | 2-R | 454449.33 | Completed | 1 | 2024-08-29 | 2024-08-29 | PB-19A-2023-19 |  | 2023-12-20 | 2023-12-27 | 2024-01-08 |  | 2024-04-01 | LAV Construction
QRF 2023 | Region I | Ilocos Norte | 500343 | Pallas Integrated School | VINTAR | 1st | 1 | 8 | REPAIR OF CLASSROOMS | 3304000 | 2-R | 3296745.93 | Completed | 1 | 2024-11-24 | 2024-11-20 | PB-19-2023-18 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-04 | Elocin Construction | under suspension
QRF 2023 | Region I | Ilocos Norte | 100324 | Tungel ES | VINTAR | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1480782.92 | completed | 1 | 2024-08-29 | 2024-08-27 | PB-19A-2023-19 |  | 2023-12-20 | 2023-12-27 | 2024-01-08 |  | 2024-04-01 | LAV Construction
QRF 2023 | Region I | Ilocos Norte | 300031 | VINTAR NHS | VINTAR | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 3750206 | 2-R | 2814383.65 | Completed | 1 | 2024-12-09 | 2024-12-27 | PB-19-2023-20 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-04 | Elocin Construction
QRF 2023 | Region I | Ilocos Norte | 100041 | Turod ES | BADOC | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1187200 | 2-R | 831704.72 | Completed | 1 | 2024-12-28 | 2024-11-30 | PB-19-2023-3 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-01 | Elocin Construction
QRF 2023 | Region I | Ilocos Norte | 100060 | Barbarangay ES | BANNA (ESPIRITU) | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 2-R | 1628202.96 | Completed | 1 | 2024-11-30 | 2024-08-11 | PB-19B-2023-9 |  | 2024-03-04 | 2024-03-08 | 2024-03-25 |  | 2024-05-29 | LAV Construction
QRF 2023 | Region I | Ilocos Norte | 100063 | Caestebanan ES | BANNA (ESPIRITU) | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 3020855 | 2-R | 2520165.06 | Completed | 1 | 2024-11-30 | 2024-11-19 | PB-19B-2023-9 |  | 2024-03-04 | 2024-03-08 | 2024-03-25 |  | 2024-05-29 | LAV Construction
QRF 2023 | Region I | Ilocos Norte | 100117 | Pias-Gaang ES | CURRIMAO | 2nd | 1 | 7 | REPAIR OF CLASSROOMS | 4187330 | 2-R | 2857524.12 | Completed | 1 | 2024-12-28 | 2024-11-30 | PB-19-2023-3 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-01 | Elocin Construction
QRF 2023 | Region I | Ilocos Norte | 320808 | Bamasesamar National High School | DINGRAS | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 1298980 | 2-R | 1160009.34 | completed | 1 | 2024-09-13 | 2024-05-25 | PB-19-2023-12 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-01 | Elocin Construction
QRF 2023 | Region I | Ilocos Norte | 300015 | Dingras NHS | DINGRAS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1000219 | 2-R | 920129.09 | Completed | 1 | 2024-10-01 | 2024-06-27 | PB-19-2023-11 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-04 | Elocin Construction
QRF 2023 | Region I | Ilocos Norte | 100130 | Dingras West CES | DINGRAS | 2nd | 1 | 6 | REPAIR OF CLASSROOMS | 3900000 | 2-R | 3334927.64 | Completed | 1 | 2024-10-31 | 2024-10-05 | PB-01-2024 |  | 2024-03-04 | 2024-03-08 | 2024-03-25 |  |  | LAV Construction
QRF 2023 | Region I | Ilocos Norte | 100134 | Peralta ES | DINGRAS | 2nd | 1 | 3 | 1STY3CL | 8630843.3 | 2- NC | 8600094.07 | Completed | 1 | 2024-09-14 | 2024-08-24 | PB-15-2023-1 |  | 2023-11-09 | 2023-11-14 | 2023-11-28 |  | 2024-02-26 | Elocin Construction
QRF 2023 | Region I | Ilocos Norte | 100124 | Saludares-Cali ES | DINGRAS | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2498555 | 2-R | 2487632.44 | Completed | 1 | 2024-10-01 | 2024-06-27 | PB-19-2023-11 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-04 | Elocin Construction
QRF 2023 | Region I | Ilocos Norte | 100135 | San Esteban ES | DINGRAS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 2-R | 1828801.76 | completed | 1 | 2024-09-13 | 2024-05-25 | PB-19-2023-12 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-01 | Elocin Construction
QRF 2023 | Region I | Ilocos Norte | 100138 | Suyo ES | DINGRAS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1815871.21 | completed | 1 | 2024-10-01 | 2024-06-27 | PB-19-2023-11 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-04 | Elocin Construction
QRF 2023 | Region I | Ilocos Norte | 100151 | Mabuti ES | MARCOS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1584474 | Ongoing | 0 |  |  | PB-19B-2023-9 |  | 2024-03-04 | 2024-03-08 | 2024-03-25 |  | 2024-05-29 | LAV Construction | April 2025: Terminated Previous Remarks: under suspension
QRF 2023 | Region I | Ilocos Norte | 100154 | Nueva Era Central Elementary School | NUEVA ERA | 2nd | 1 | 2 | 1STY2CL | 6288548.8 | 2- NC | 6265349.89 | Completed | 1 | 2024-11-06 | 2024-12-27 | PB-15-2023-2 |  | 2023-11-09 | 2023-11-14 | 2023-11-28 |  | 2024-02-26 | Abeian Construction
QRF 2023 | Region I | Ilocos Norte | 500345 | Malaguip Integrated School | PAOAY | 2nd | 1 | 1 | REPAIR OF CLASSROOM | 639120.75 | 2-R | 481818.73 | Completed | 1 | 2024-12-09 | 2024-12-27 | PB-19-2023-13 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-04 | Elocin Construction
QRF 2023 | Region I | Ilocos Norte | 100185 | Nagbacalan ES | PAOAY | 2nd | 1 | 8 | REPAIR OF CLASSROOMS | 4565891 | 2-R | 3621685.56 | Completed | 1 | 2024-12-09 | 2024-12-27 | PB-19-2023-13 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-04 | Elocin Construction
QRF 2023 | Region I | Ilocos Norte | 300025 | Paoay Lake NHS | PAOAY | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 3211861 | 2-R | 2576846.3 | Completed | 1 | 2024-12-09 | 2024-12-27 | PB-19-2023-14 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-01 | Elocin Construction
QRF 2023 | Region I | Ilocos Norte | 320814 | Paoay National High School | PAOAY | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 1595900 | 2-R | 1114477.47 | Completed | 1 | 2024-12-09 | 2024-12-27 | PB-19-2023-14 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-01 | Elocin Construction | under suspension
QRF 2023 | Region I | Ilocos Norte | 100234 | Badio ES | PINILI | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 3211861 | 2-R | 2743455.85 | Completed | 1 | 2024-10-31 | 2024-10-10 | PB-19B-2023-4 |  | 2024-03-04 | 2024-03-08 | 2024-03-25 |  | 2024-05-29 | LAV Construction
QRF 2023 | Region I | Ilocos Norte | 100236 | Bicbica PS | PINILI | 2nd | 1 | 3 | 1STY3CL | 8630843.3 | 2- NC | 8598431.5 | Completed | 1 | 2024-10-31 | 2024-11-20 | PB-15-2023-3 |  | 2023-11-09 | 2023-11-14 | 2023-11-28 |  | 2024-02-26 | KRB Construction
QRF 2023 | Region I | Ilocos Norte | 500593 | Sacritan Integrated School | PINILI | 2nd | 1 | 1 | REPAIR OF CLASSROOM | 639120.75 | 2-R | 545285.46 | Completed | 1 | 2024-10-31 | 2024-08-11 | PB-19B-2023-4 |  | 2024-03-04 | 2024-03-08 | 2024-03-25 |  | 2024-05-29 | LAV Construction
QRF 2023 | Region I | Ilocos Norte | 100256 | Eladio V. Barangan Mem. ES | SAN NICOLAS | 2nd | 1 | 2 | 1STY2CL | 6288548.8 | 2- NC | 6258355.82 | Completed | 1 | 2024-09-08 | 2024-10-05 | PB-15-2023-4 |  | 2023-11-09 | 2023-11-14 | 2023-11-28 |  | 2024-02-26 | Elocin Construction
QRF 2023 | Region I | Ilocos Norte | 100256 | Eladio V. Barangan Mem. ES | SAN NICOLAS | 2nd |  | 3 | REPAIR OF CLASSROOMS | 2449998.96 | 2-R | 2440022.86 | Completed | 1 | 2024-10-10 | 2024-11-30 | PB-19-2023-5 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-04 | Elocin Construction
QRF 2023 | Region I | Ilocos Norte | 100260 | San Nicolas ES | SAN NICOLAS | 2nd | 1 | 1 | REPAIR OF CLASSROOM | 348290 | 2-R | 341366.87 | Completed | 1 | 2024-10-10 | 2024-11-30 | PB-19-2023-5 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-04 | Elocin Construction
QRF 2023 | Region I | Ilocos Norte | 100276 | Barcelona ES | SOLSONA | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 2-R | 1946864.79 | completed | 1 | 2024-11-24 | 2024-07-08 | PB-19-2023-10 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-01 | Elocin Construction
QRF 2023 | Region I | Ilocos Norte | 100284 | Santiago ES | SOLSONA | 2nd | 1 | 1 | REPAIR OF CLASSROOM | 950000 | 2-R | 948168.99 | completed | 1 | 2024-11-24 | 2024-07-08 | PB-19-2023-10 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-01 | Elocin Construction
QRF 2023 | Region I | Ilocos Norte | 300030 | Solsona National High School | SOLSONA | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1050000 | 2-R | 1045358.69 | Completed | 1 | 2024-11-24 | 2024-11-22 | PB-19-2023-10 |  | 2023-11-20 | 2023-11-29 | 2023-12-11 |  | 2024-04-01 | Elocin Construction | under suspension
QRF 2024 | Region I | Batac City | 100079 | Magnuang ES | CITY OF BATAC | 2nd | 1 | 3 | Repair of Classrooms | 565554.92 | 1- R |  | completed | 1 | 2025-04-10 | 2025-02-18 | 2024-006 | 24014 | Nov. 28, 2024 | Dec. 06, 2024 | Dec. 18, 2024 | Dec. 23, 2024 | Dec. 26, 2024 | Martin Development Corporation
QRF 2024 | Region I | Batac City | 100081 | Naguirangan-Capacuan ES | CITY OF BATAC | 2nd | 1 | 2 | 1STY2CL | 6288548.8 | 1- NC |  | Ongoing | 0.75 | 2025-06-19 |  | 2024-002 | 24010 | August 30, 2024 | Sept. 12, 2024 | Sept. 24, 2024 | Oct. 14, 2024 | Oct. 28, 2024 | VCD Construction
QRF 2024 | Region I | Batac City | 100085 | Quiling Elementary School | CITY OF BATAC | 2nd | 1 | 2 | 1STY2CL | 6288548.8 | 1- NC |  | Ongoing | 0.75 | 2025-06-19 |  | 2024-002 | 24009 | August 30, 2024 | Sept. 12, 2024 | Sept. 24, 2024 | Oct. 14, 2024 | Oct. 28, 2024 | VCD Construction
QRF 2024 | Region I | Batac City | 100086 | Sumader ES | CITY OF BATAC | 2nd | 1 | 1 | Repair of Classrooms | 261960.82 | 1- R |  | Completed | 1 | 2025-04-10 | 2025-01-28 | 2024-006 | 24015 | Nov. 28, 2024 | Dec. 06, 2024 | Dec. 18, 2024 | Dec. 23, 2024 | Dec. 26, 2024 | ADG Builders, Inc.
QRF 2024 | Region I | Batac City | 100087 | Tabug ES | CITY OF BATAC | 2nd | 1 | 2 | 1STY2CL | 6288548.8 | 1- NC |  | Ongoing | 0.75 | 2025-06-19 |  | 2024-002 | 24008 | August 30, 2024 | Sept. 12, 2024 | Sept. 24, 2024 | Oct. 14, 2024 | Oct. 28, 2024 | VCD Construction
QRF 2024 | Region I | Batac City | 100089 | Baay ES | CITY OF BATAC | 2nd | 1 | 3 | 1STY3CL | 8630843.3 | 1- NC |  | Ongoing | 0.4 | 2025-08-18 |  | 2024-003 | 24013 | Oct. 07, 2024 | Oct. 16, 2024 | Oct. 28, 2024 | Dec. 18, 2024 | Dec. 26, 2024 | VCD Construction
QRF 2024 | Region I | Batac City | 100091 | Baoa ES | CITY OF BATAC | 2nd | 1 | 1 | Repair of Classrooms | 220610.27 | 1- R | 4315381.41 | Completed | 1 | 2025-04-10 | 2025-01-28 | 2024-006 | 24015 | Nov. 28, 2024 | Dec. 06, 2024 | Dec. 18, 2024 | Dec. 23, 2024 | Dec. 26, 2024 | ADG Builders, Inc.
QRF 2024 | Region I | Batac City | 100093 | Biningan ES | CITY OF BATAC | 2nd | 1 | 3 | Repair of Classrooms | 800478.7 | 1- R | 4315381.41 | Completed | 1 | 2025-04-10 | 2025-03-18 | 2024-006 | 24015 | Nov. 28, 2024 | Dec. 06, 2024 | Dec. 18, 2024 | Dec. 23, 2024 | Dec. 26, 2024 | ADG Builders, Inc.
QRF 2024 | Region I | Batac City | 300005 | Batac National High School | CITY OF BATAC | 2nd | 1 | 2 | Repair of Classrooms | 362703.34 | 1- R |  | Completed | 1 | 2025-04-10 |  | 2024-006 | 24014 | Nov. 28, 2024 | Dec. 06, 2024 | Dec. 18, 2024 | Dec. 23, 2024 | Dec. 26, 2024 | Martin Development Corporation
QRF 2024 | Region I | Batac City | 320804 | City of Batac NHS Poblacion | CITY OF BATAC | 2nd | 1 | 2 | Repair of Classrooms | 674429.08 | 1- R | 4315381.41 | Completed | 1 | 2025-04-10 |  | 2024-006 | 24014 | Nov. 28, 2024 | Dec. 06, 2024 | Dec. 18, 2024 | Dec. 23, 2024 | Dec. 26, 2024 | Martin Development Corporation
QRF 2024 | Region I | Ilocos Norte | 100053 | Nagbalagan ES | BANGUI | 1st | 1 | 4 | 2-UNITS 1STY2CL | 11671993.99 | 1- NC |  | Ongoing | 0.65 | 2025-07-16 |  | PB-07-2024-Lot 1 | PB-07-2024-Lot 1 | 2024-09-04 | 2024-09-10 | 2024-09-23 | 2024-10-28 | 2024-11-18 | Caixia Construction
QRF 2024 | Region I | Ilocos Norte | 100062 | Bugasi ES | BANNA (ESPIRITU) | 2nd | 1 | 3 | 1STY3CL | 8575310.14 | 1- NC |  | Ongoing | 0.8 | 2025-04-17 |  | PB-07-2024-Lot 2 | PB-07-2024-Lot 2 | 2024-09-04 | 2024-09-10 | 2024-09-23 | 2024-10-28 | 2024-11-18 | LAV Construction
QRF 2024 | Region I | Ilocos Norte | 100066 | Crispina ES | BANNA (ESPIRITU) | 2nd | 1 | 2 | Repair of Classrooms | 485255.7 | 1- R |  | reverted | 0 |  |  | PB-14-2024-1 | PB-14-2024-1 | 2024-11-29 | 2024-12-05 | 2024-12-18 | 2025-01-20 | 2025-01-29 | LAV Construction
QRF 2024 | Region I | Ilocos Norte | 100074 | VALDEZ ELEMENTARY SCHOOL | BANNA (ESPIRITU) | 2nd | 1 | 3 | 1STY3CL | 8575310.14 | 1- NC |  | Ongoing | 0.7 | 2025-04-17 |  | PB-07-2024-Lot 3 | PB-07-2024-Lot 3 | 2024-09-04 | 2024-09-10 | 2024-09-23 | 2024-10-28 | 2024-11-18 | Caixia Construction
QRF 2024 | Region I | Ilocos Norte | 100114 | Maglaoi ES | CURRIMAO | 2nd | 1 | 1 | Repair of Classrooms | 443145.15 | 1- R |  | completed | 1 |  |  | PB-14-2024-2 | PB-14-2024-2 | 2024-11-29 | 2024-12-05 | 2024-12-18 | 2025-01-20 | 2025-01-29 | LAV Construction
QRF 2024 | Region I | Ilocos Norte | 100241 | Don Mariano Marcos Mem. Sch. | PINILI | 2nd | 1 | 2 | Repair of Classrooms | 637304.27 | 1- R |  | completed | 1 |  |  | PB-14-2024-2 | PB-14-2024-2 | 2024-11-29 | 2024-12-05 | 2024-12-18 | 2025-01-20 | 2025-01-29 | LAV Construction
QRF 2024 | Region I | Ilocos Norte | 300003 | Bangui NHS | BANGUI | 1st | 1 | 5 | Repair of Classrooms | 859025.56 | 1- R |  | Ongoing | 0.8 |  |  | PB-14-2024-3 | PB-14-2024-3 | 2024-11-29 | 2024-12-05 | 2024-12-18 | 2025-01-20 | 2025-01-29 | LAV Construction
QRF 2024 | Region I | Ilocos Norte | 320812 | Marcos NHS (Santiago Campus) | MARCOS | 2nd | 1 | 4 | Repair of Classrooms | 632738.78 | 1- R |  | Completed | 1 |  |  | PB-14-2024-1 | PB-14-2024-1 | 2024-11-29 | 2024-12-05 | 2024-12-18 | 2025-01-20 | 2025-01-29 | LAV Construction
QRF 2024 | Region I | Ilocos Norte | 500343 | Pallas Integrated School | VINTAR | 1st | 1 | 4 | Repair of Classrooms | 839105.83 | 1- R |  | Not Yet Started | 0 | [10 empty] | Deffered due to the issuance of Notice of Prohibited Use by the LGU
QRF 2024 | Region I | Laoag City | 500742 | San Mateo Integrated School | LAOAG CITY (Capital) | 1st | 1 | 6 | Repair of Classrooms | 1234766.65 | 1- R |  | Completed | 1 | MAr.03,2025 | April 15,2025 | 2024-PB1-002 |  | Oct.04,2024 | Oct.11,2024 | Oct.28,2024 | Nov.25,2025 | Dec.03,2024 | Elocin Construction | Punchlisting
QRF 2024 | Region I | Ilocos Norte | 100002 | Bacarra CES | BACARRA | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1947230.7705 | Ongoing | 0.7 | 2025-09-30 |  |  | 2025-02-22 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100006 | Nambaran ES | BACARRA | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2600000 | 3-R | 2597811.0833 | Ongoing | 0 | 2025-09-30 |  |  | 2025-02-22 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ASS Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100009 | Sabas-Sagisi Memorial Elem. School | BACARRA | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 647983.8 | Ongoing | 0 | 2025-09-30 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100010 | SPECIAL EDUCATION CENTER | BACARRA | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 3900000 | 3-R | 3845845.18 | Ongoing | 0.5 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100011 | Santo Cristo Elementary School | BACARRA | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 649206.51 | Ongoing | 0 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100016 | Cadaratan ES | BACARRA | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1946780.3321 | Completed | 1 | 2025-09-30 |  |  | 2025-02-22 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100019 | Paninaan Elementary School | BACARRA | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2600000 | 3-R | 2598258.0533 | Completed | 1 | 2025-09-30 |  |  | 2025-02-22 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100022 | San Agustin ES | BACARRA | 1st | 1 | 9 | REPAIR OF CLASSROOMS | 5850000 | 3-R | 5832130.29 | Ongoing | 0.6 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100038 | Pasuc-Parang ES | BADOC | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2600000 | 3-R | 2594696.51 | Ongoing | 0 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100066 | Crispina ES | BANNA (ESPIRITU) | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 639079.29 | Ongoing | 0 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100072 | Sinamar ES | BANNA (ESPIRITU) | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1948623.74 | Ongoing | 0.4 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100106 | Nagsurot Elementary School | BURGOS | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1945868.8232 | Ongoing | 0.7 | 2025-09-30 |  |  | 2025-02-22 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ASS Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100113 | Langayan ES | CURRIMAO | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Ongoing | 0.7 | 2025-08-31 |  |  | 2025-02-23 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | Manimeld's Construction & Iron Works | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100114 | Maglaoi ES | CURRIMAO | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 646034.7477 | Ongoing | 0.35 | 2025-09-30 |  |  | 2025-02-22 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ASS Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100117 | Pias-Gaang ES | CURRIMAO | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1945863.08 | Ongoing | 0.6 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100122 | Francisco ES | DINGRAS | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1285260.05 | Ongoing | 0.4 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100128 | Bacsil ES | DINGRAS | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3244750 | Ongoing | 0.5 | 2025-09-30 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | Manimeld's Construction & Iron Works | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100156 | Santiago ES | MARCOS | 2nd | 1 | 7 | REPAIR OF CLASSROOMS | 4550000 | 3-R | 4547749.7278 | Ongoing | 0.6 | 2025-09-30 |  |  | 2025-02-22 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ASS Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100164 | Burayoc ES | PAGUDPUD | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 645894.62 | Ongoing | 0 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100165 | Caparispisan ES | PAGUDPUD | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 646009.29 | Ongoing | 0 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100177 | Subec ES | PAGUDPUD | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 645471.975 | Ongoing | 0.1 | 2025-09-30 |  |  | 2025-02-22 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ASS Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100179 | Tarrag PS | PAGUDPUD | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1294750 | Completed | 1 | 2025-08-31 |  |  | 2025-02-23 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | Manimeld's Construction & Iron Works | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100180 | Bacsil ES | PAOAY | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 649461.85 | Ongoing | 0 | 2025-08-31 |  |  | 2025-02-23 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100184 | Mumulaan ES | PAOAY | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3247141.1267 | Completed | 1 | 2025-09-30 |  |  | 2025-02-22 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ASS Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100188 | Paoay CES | PAOAY | 2nd | 1 | 10 | REPAIR OF CLASSROOMS | 6500000 | 3-R | 6494750 | Ongoing | 0.8 | 2025-08-31 |  |  | 2025-02-23 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | Manimeld's Construction & Iron Works | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100189 | Paoay East Central ES | PAOAY | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Completed | 1 | 2025-08-31 |  |  | 2025-02-23 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | Manimeld's Construction & Iron Works | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100190 | Pasil ES | PAOAY | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 636301.85 | Ongoing | 0.2 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100194 | Binsang ES | PASUQUIN | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Completed | 1 | 2025-08-31 |  |  | 2025-02-23 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | Manimeld's Construction & Iron Works | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100197 | Carusikis ES | PASUQUIN | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2600000 | 3-R | 2596663.7275 | Ongoing | 0.8 | 2025-09-30 |  |  | 2025-02-22 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 |  | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100198 | Dadaeman Elementary School | PASUQUIN | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3244750 | Ongoing | 0.1 | 2025-08-31 |  |  | 2025-02-23 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | Manimeld's Construction & Iron Works | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100200 | Dilanis ES | PASUQUIN | 1st | 1 | 3 | 1STY3CL | 9000000 | 3- NC | 8994759.45 | Ongoing | 0.35 | 2025-08-31 |  |  | 2025-02-23 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | Manimeld's Construction & Iron Works | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100200 | Dilanis ES | PASUQUIN | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1293700 | Ongoing | 0.6 | 2025-09-30 |  |  | 2025-02-23 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | Manimeld's Construction & Iron Works | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100203 | Madalayap Elementary School | PASUQUIN | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2600000 | 3-R | 2587210.91 | Ongoing | 0.6 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100205 | Naglicuan ES | PASUQUIN | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1291108.21 | Ongoing | 0.5 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100206 | Nagsanga ES | PASUQUIN | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Ongoing | 0 | 2025-08-31 |  |  | 2025-02-23 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | Manimeld's Construction & Iron Works | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100207 | Pangil ES | PASUQUIN | 1st | 1 | 4 | 2STY4CL | 12000000 | 3- NC | 11997232.6771 | Ongoing | 0.25 | 2025-09-30 |  |  | 2025-02-22 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ASS Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100208 | Pasuquin Central Elementary School | PASUQUIN | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 646523.89 | Ongoing | 0 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100209 | Puyupuyan ES | PASUQUIN | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 626526.64 | Ongoing | 0 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100211 | Sta. Catalina ES | PASUQUIN | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 3235817.47 | Ongoing | 0.6 | 2025-09-30 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100214 | Tabungao ES | PASUQUIN | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1295629.0509 | Ongoing | 0.7 | 2025-09-30 |  |  | 2025-02-22 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ASS Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100226 | Maruaya PS | PIDDIG | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Ongoing | 0.7 | 2025-08-31 |  |  | 2025-02-23 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | Manimeld's Construction & Iron Works | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100234 | Badio ES | PINILI | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3235817.47 | Ongoing | 0 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100240 | Darat ES | PINILI | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Ongoing | 0 | 2025-08-31 |  |  | 2025-02-23 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | Manimeld's Construction & Iron Works | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100241 | Don Mariano Marcos Mem. Sch. | PINILI | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1947230.7747 | Ongoing | 0.8 | 2025-09-30 |  |  | 2025-02-22 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ASS Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100242 | Gulpeng PS | PINILI | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 643005.08 | Ongoing | 0 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100244 | Nagtrigoan ES | PINILI | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1261742.73 | Ongoing | 0 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100245 | Pugaoan-Bungro ES | PINILI | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1296958.7649 | Ongoing | 0.8 | 2025-09-30 |  |  | 2025-02-22 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ASS Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100247 | Puzol Elementary School | PINILI | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2600000 | 3-R | 2595871.43 | Ongoing | 0 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100252 | Barabar ES | SAN NICOLAS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Ongoing | 0 | 2025-08-31 |  |  | 2025-02-23 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | Manimeld's Construction & Iron Works | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100254 | Bugnay ES | SAN NICOLAS | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 647084.8606 | Completed | 1 | 2025-09-30 |  |  | 2025-02-22 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ASS Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100256 | Eladio V. Barangan Mem. ES | SAN NICOLAS | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 1400000 | 3-R | 1397903.9769 | Completed | 1 | 2025-09-30 |  |  | 2025-02-22 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ASS Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100257 | Filipinas East ES | SAN NICOLAS | 2nd | 1 | 6 | REPAIR OF CLASSROOMS | 3900000 | 3-R | 3894750.31 | Ongoing | 0 | 2025-08-31 |  |  | 2025-02-23 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | Manimeld's Construction & Iron Works | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100260 | San Nicolas ES | SAN NICOLAS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1948932.75 | Ongoing | 0 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100262 | Cabuloan Elementary School | SARRAT | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 644722.89 | Ongoing | 0.6 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100267 | Ruiz ES | SARRAT | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Ongoing | 0.7 | 2025-08-31 |  |  | 2025-02-23 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | Manimeld's Construction & Iron Works | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100271 | Sarrat Central School | SARRAT | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1294750.01 | Ongoing | 0.6 | 2025-08-31 |  |  | 2025-02-23 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | Manimeld's Construction & Iron Works | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100282 | Nagpatpatan ES | SOLSONA | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Ongoing | 0.1 | 2025-08-31 |  |  | 2025-02-23 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | Manimeld's Construction & Iron Works | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100287 | Talugtog ES | SOLSONA | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Ongoing | 0.1 | 2025-08-31 |  |  | 2025-02-23 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | Manimeld's Construction & Iron Works | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100288 | Alsem ES | VINTAR | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1932612.08 | Ongoing | 0.6 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100296 | Esperanza ES | VINTAR | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1283338.55 | Ongoing | 0 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100306 | Visaya Elementary School | VINTAR | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1294750 | Completed | 1 | 2025-08-31 |  |  | 2025-02-23 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | Manimeld's Construction & Iron Works | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 100314 | Lipay ES | VINTAR | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3247441.145 | Ongoing | 0.15 | 2025-09-30 |  |  | 2025-02-22 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ASS Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 150003 | Nagbacalan West ES | PAOAY | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1947773.07 | Completed | 1 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 150008 | San Isidro PS | PASUQUIN | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1288248.77 | Ongoing | 0.3 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 150023 | Casilian Primary School - Taguipuro Annex | BACARRA | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1296398.116 | Ongoing | 0.7 | 2025-09-30 |  |  | 2025-02-22 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ASS Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 300014 | Davila National High School | PASUQUIN | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3244750 | Ongoing | 0 | 2025-08-31 |  |  | 2025-02-23 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | Manimeld's Construction & Iron Works | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 300015 | Dingras NHS | DINGRAS | 2nd | 1 | 6 | REPAIR OF CLASSROOMS | 3900000 | 3-R | 3895135.72 | Completed | 1 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 300017 | Dumalneg NHS | DUMALNEG | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3244750 | Ongoing | 0.1 | 2025-08-31 |  |  | 2025-02-23 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | Manimeld's Construction & Iron Works | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 300023 | Pagsanahan NHS | BADOC | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1291769.55 | Ongoing | 0 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 500344 | SALPAD INTEGRATED SCHOOL | VINTAR | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 644793.38 | Ongoing | 0 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 500592 | Pandan Integrated School | SARRAT | 1st | 1 | 7 | REPAIR OF CLASSROOMS | 4550000 | 3-R | 4522791.9231 | Ongoing | 0 | 2025-09-30 |  |  | 2025-02-22 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ASS Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 500593 | Sacritan Integrated School | PINILI | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2600000 | 3-R | 2597889.5554 | Ongoing | 0 | 2025-09-30 |  |  | 2025-02-22 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ASS Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 502581 | Balaoi Integrated School | PAGUDPUD | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 647045.2657 | Ongoing | 0.1 | 2025-09-30 |  |  | 2025-02-22 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ASS Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 502711 | Tubburan Integrated School | BACARRA | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3228809.88 | Ongoing | 0.5 | 2025-08-31 |  |  | 2025-02-21 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ELOCIN Construction | REGIONAL IMPLEMENTED
QRF 2024 | Region I | Ilocos Norte | 502750 | Sto. Tomas Integrated School | PINILI | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1295964.1322 | Ongoing | 0 | 2025-09-30 |  |  | 2025-02-22 | 2025-03-07 | 2025-03-15 | 2025-03-27 | 2025-03-12 | 2025-03-04 | ASS Construction | REGIONAL IMPLEMENTED

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%