## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No of Sites | SCOPE OF WORK | Batch | Project Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | WITH TRANSFOPMER (Y/N) | CATEGORY 2 | Status as of July 11, 2025
ELECTRIFICATION 2017 | Region II | Cagayan | 102460 | Bulala Sur ES | APARRI | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 551885.05 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region II | Cagayan | 102472 | Plaza PS | APARRI | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 474509.84 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region II | Cagayan | 102565 | Mala Este PS | BUGUEY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 360773.24 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region II | Isabela | 103759 | Malaya ES (Maldam ES) | SAN MARIANO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 219362.91 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region II | Isabela | 103763 | Panninan ES | SAN MARIANO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 129288.3 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 104205 | Mandunot ES | ALFONSO CASTAÑEDA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1076701.55 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 156020 | Pelaway ES Annex | ALFONSO CASTAÑEDA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 412734.71 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 156012 | Lihlit PS | AMBAGUIO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1154735.28 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 156019 | Pogonsino Annex Primary School | BAGABAG | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 660613.2 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 103990 | Kakilingan ES | BAYOMBONG (Capital) | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1201001.02 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 104000 | Villa Adriano PS | BAYOMBONG (Capital) | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 785827.01 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 104102 | Pudi PS | KASIBU | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 784569.52 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 104122 | Dayap PS | KAYAPA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 975474 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 104131 | Macdu ES | KAYAPA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1527697.58 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 104137 | Oliweg E/S | KAYAPA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1419459.81 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 156001 | Tidang Village PS | KAYAPA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 473808.36 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 104197 | Cauco ES | SANTA FE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1260159.66 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region II | Quirino | 156513 | Diodol PS Annex | AGLIPAY | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 199320.9 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region II | Quirino | 104311 | Pamungyen PS | DIFFUN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 181750.86 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region II | Quirino | 104359 | Macabo ES | NAGTIPUNAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 286571.16 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2018 | Region II | Batanes | 300415 | Ivana NHS | IVANA | 0 | 1 | UPGRADING | 1 | 1126860.32 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Batanes | 300416 | Mahatao NHS | MAHATAO | 0 | 1 | UPGRADING | 1 | 1095087.83 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Batanes | 300417 | Sabtang National School of Fisheries | SABTANG | 0 | 1 | UPGRADING | 1 | 1095087.83 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300420 | Afusing NHS | ALCALA | 1 | 1 | UPGRADING | 1 | 495971.47 |  | terminated | 0.2994 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300421 | Alcala Rural School | ALCALA | 1 | 1 | UPGRADING | 1 | 518889.44 |  | terminated | 0.95 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300471 | Aparri East National High School | APARRI | 1 | 1 | UPGRADING | 1 | 699410.46 |  | terminated | 0.95 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300470 | Aparri West National High School | APARRI | 1 | 1 | UPGRADING | 1 | 567838.55 |  | terminated | 0.95 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300437 | Bukig National Agr'l. and Tech. School | APARRI | 1 | 1 | UPGRADING | 1 | 730017.81 |  | terminated | 0.48 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 306020 | AGAMAN NATIONAL HIGH SCHOOL | BAGGAO | 1 | 1 | UPGRADING | 1 | 634259.39 |  | terminated | 0.67 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300429 | Baggao NAS | BAGGAO | 1 | 1 | UPGRADING | 1 | 643414.67 |  | terminated | 0.1097 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300430 | Baggao National School of Arts & Trades | BAGGAO | 1 | 1 | UPGRADING | 1 | 589120.28 |  | terminated | 0.1097 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 155053 | Cagurungan Primary School | BAGGAO | 1 | 1 | SOLAR PANEL | 1 | 559889.96 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | Region II | Cagayan | 300432 | Hacienda Intal NHS | BAGGAO | 1 | 1 | UPGRADING | 1 | 571264.33 |  | terminated | 0.1097 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300433 | Imurung NHS | BAGGAO | 1 | 1 | UPGRADING | 1 | 2011343.55 |  | terminated | 0.67 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 102498 | San Antonio ES | BAGGAO | 1 | 1 | SOLAR PANEL | 1 | 1753452.5 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | Region II | Cagayan | 102503 | Tabugan ES | BAGGAO | 1 | 1 | SOLAR PANEL | 1 | 559889.96 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | Region II | Cagayan | 306426 | Camalaniugan National High School- Catotoran Annex | CAMALANIUGAN | 1 | 1 | UPGRADING | 1 | 588020.29 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300440 | Calaoagan Dackel NHS | GATTARAN | 1 | 1 | UPGRADING | 1 | 637964.57 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300483 | Gonzaga National High School | GONZAGA | 1 | 1 | UPGRADING | 1 | 617102.21 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300465 | Ipil National High School | GONZAGA | 1 | 1 | UPGRADING | 1 | 2263197.02 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 155051 | Laoc Primary School | GONZAGA | 1 | 1 | SOLAR PANEL | 1 | 1846756.72 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | Region II | Cagayan | 300482 | Rebecca NHS | GONZAGA | 1 | 1 | UPGRADING | 1 | 628809.3 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300469 | LAL-LO NATIONAL HIGH SCHOOL | LAL-LO | 1 | 1 | UPGRADING | 1 | 709465.42 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 306004 | Magapit NHS | LAL-LO | 1 | 1 | UPGRADING | 1 | 515742.71 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300488 | Sta. Ana Fishery National High School | SANTA ANA | 1 | 1 | UPGRADING | 1 | 841324.37 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300490 | Sta. Teresita NHS | SANTA TERESITA | 1 | 1 | UPGRADING | 1 | 602505.52 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300473 | Libertad NHS | ABULUG | 2 | 1 | UPGRADING | 1 | 1233921.78 |  | terminated | 0.6085 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300424 | Allacapan VHS | ALLACAPAN | 2 | 1 | UPGRADING | 1 | 740050.2 |  | terminated | 0.6994 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 500065 | Mapurao Integ. Learning School | ALLACAPAN | 2 | 1 | UPGRADING | 1 | 671431.74 |  | terminated | 0.6994 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300434 | Ballesteros NHS | BALLESTEROS | 2 | 1 | UPGRADING | 1 | 740050.2 |  | terminated | 0.6085 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 155040 | Bibigsan PS | CALAYAN | 2 | 1 | SOLAR PANEL | 1 | 663729.76 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | Region II | Cagayan | 300441 | Calayan HS | CALAYAN | 2 | 1 | SOLAR PANEL | 1 | 1478886.29 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | Region II | Cagayan | 102586 | Caniwalan ES | CALAYAN | 2 | 1 | SOLAR PANEL | 1 | 1586151.2 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | Region II | Cagayan | 102587 | Dadao ES | CALAYAN | 2 | 1 | UPGRADING | 1 | 1688631.96 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 102593 | Morol ES | CALAYAN | 2 | 1 | SOLAR PANEL | 1 | 930135.8 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | Region II | Cagayan | 300450 | Claveria RVS | CLAVERIA | 2 | 1 | UPGRADING | 1 | 501909.48 |  | terminated | 0.6994 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300451 | Claveria SAT | CLAVERIA | 2 | 1 | UPGRADING | 1 | 501909.48 |  | terminated | 0.6994 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300438 | Cabatacan National High School | LASAM | 2 | 1 | UPGRADING | 1 | 2131509.18 |  | terminated | 0.9 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300439 | Nabannagan National High School | LASAM | 2 | 1 | UPGRADING | 1 | 1915584.2 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300497 | Western Cagayan SAT | LASAM | 2 | 1 | UPGRADING | 1 | 1118621.25 |  | terminated | 0.5013 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300481 | Piat National HS | PIAT | 2 | 1 | UPGRADING | 1 | 964556.11 |  | terminated | 0.1452 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 102854 | Kittag ES | SANCHEZ-MIRA | 2 | 1 | SOLAR PANEL | 1 | 527749.68 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | Region II | Cagayan | 155046 | Pureg Elementary School | SANCHEZ-MIRA | 2 | 1 | SOLAR PANEL | 1 | 506644.68 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | Region II | Cagayan | 300486 | Sanchez Mira SAT | SANCHEZ-MIRA | 2 | 1 | UPGRADING | 1 | 740050.2 |  | terminated | 0.6994 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 102862 | Santiago Elementary School | SANCHEZ-MIRA | 2 | 1 | SOLAR PANEL | 1 | 734565.68 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | Region II | Cagayan | 300489 | Sta. Praxedes HS | SANTA PRAXEDES | 2 | 1 | UPGRADING | 1 | 570762.04 |  | terminated | 0.6994 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 306017 | Amulung NHS - Dadda Ext. | AMULUNG | 3 | 1 | UPGRADING | 1 | 1146918.75 |  | terminated | 0.3408 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300458 | Enrile Vocational High School | ENRILE | 3 | 1 | UPGRADING | 1 | 668475.19 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300472 | Lemu NHS | ENRILE | 3 | 1 | UPGRADING | 1 | 579730.22 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300459 | Western Enrile Vocational High School | ENRILE | 3 | 1 | UPGRADING | 1 | 824448.52 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 306421 | CARIDAD B. TRINIDAD NHS | IGUIG | 3 | 1 | UPGRADING | 1 | 612469.14 |  | terminated | 0.3408 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300446 | Cabbo NHS | PEÑABLANCA | 3 | 1 | UPGRADING | 1 | 599373.57 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300457 | Penablanca East NHS | PEÑABLANCA | 3 | 1 | UPGRADING | 1 | 730602.29 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300445 | Penablanca National High School | PEÑABLANCA | 3 | 1 | UPGRADING | 1 | 620842.75 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300467 | Itawes National High School | TUAO | 3 | 1 | UPGRADING | 1 | 730602.29 |  | terminated | 0.1452 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300468 | Itawes Nat'l.l Agr'l. & Tech'l. School - Bagumbayan Annex | TUAO | 3 | 1 | UPGRADING | 1 | 538676.19 |  | terminated | 0.1452 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300492 | Tuao Voc'l. and Tech'l. School | TUAO | 3 | 1 | UPGRADING | 1 | 750245.64 |  | terminated | 0.0591 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 300493 | Tuao Voc'l. and Tech'l. School - Culung Annex | TUAO | 3 | 1 | UPGRADING | 1 | 532184.83 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cagayan | 306019 | Tuao Voc'l. and Tech'l. School - Malummin Annex | TUAO | 3 | 1 | UPGRADING | 1 | 505444.28 |  | terminated | 0.0591 | [10 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2018 | Region II | Cauayan City | 323901 | Cauayan City NHS - Research Annex | CITY OF CAUAYAN | 3 | 1 | UPGRADING | 1 | 569092.68 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cauayan City | 103215 | Faustino ES | CITY OF CAUAYAN | 3 | 1 | UPGRADING | 1 | 1416994.55 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cauayan City | 103241 | Sillawit ES | CITY OF CAUAYAN | 3 | 1 | UPGRADING | 1 | 2061137.84 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cauayan City | 323903 | Villa Concepcion HS - Rogus Ext. | CITY OF CAUAYAN | 3 | 1 | UPGRADING | 1 | 348325.74 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cauayan City | 300614 | Villaluna NHS | CITY OF CAUAYAN | 3 | 1 | UPGRADING | 1 | 618992.18 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Cauayan City | 306107 | WEST TABACAL REGION NATIONAL HIGH SCHOOL | CITY OF CAUAYAN | 3 | 1 | UPGRADING | 1 | 2160530.55 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | City of Ilagan | 300542 | Isabela NHS - Main | ILAGAN (Capital) | 1 | 1 | UPGRADING | 1 | 1452300.94 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | City of Ilagan | 306105 | ISAT-Main | ILAGAN (Capital) | 1 | 1 | UPGRADING | 1 | 3689427.49 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | City of Ilagan | 300583 | San Antonio Nat'l. Agro-Ind'l. & Voc'l. HS | ILAGAN (Capital) | 1 | 1 | UPGRADING | 1 | 679654.89 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300521 | Alfreda Albano NHS - Magassi, Cabagan | CABAGAN | 1 | 1 | UPGRADING | 1 | 1800665.03 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300522 | Delfin Albano HS - San Juan Annex | CABAGAN | 1 | 1 | UPGRADING | 1 | 1406343.79 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300520 | Delfin Albano HS-Main | CABAGAN | 1 | 1 | UPGRADING | 1 | 1897430.9 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 103145 | Cabagan Science Elementary School | CABANGAN | 1 | 1 | UPGRADING | 3 | 868239.54 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 306133 | Aneg National High School | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | UPGRADING | 3 | 995822.45 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 306162 | Bayabo Integrated School | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | UPGRADING | 3 | 1046855.62 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 103269 | Delfin Albano Central School | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | UPGRADING | 3 | 3325977.82 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300587 | Ragan Sur National High School | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | UPGRADING | 3 | 2637011.33 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300585 | San Antonio NHS | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | UPGRADING | 1 | 2827752.29 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 103554 | Divilacan Central School | DIVILACAN | 1 | 1 | UPGRADING | 3 | 2574707.64 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300554 | Isabela SF | PALANAN | 1 | 1 | SOLAR PANEL | 1 | 2206445.44 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | Region II | Isabela | 300601 | St. Paul Voc'l. & Ind'l. HS-Main | SAN PABLO | 1 | 1 | UPGRADING | 1 | 1323322.14 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300605 | Buenaventura G. Masigan National High School | SANTA MARIA | 1 | 1 | UPGRADING | 3 | 1382139.14 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300603 | Santa Maria High School | SANTA MARIA | 1 | 1 | UPGRADING | 1 | 1646981.65 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 103854 | Sta. Maria Central School | SANTA MARIA | 1 | 1 | UPGRADING | 3 | 1992023.28 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300606 | Sto Tomas NHS | SANTO TOMAS | 1 | 1 | UPGRADING | 1 | 1649011.33 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 103871 | Sto. Tomas Central School | SANTO TOMAS | 1 | 1 | UPGRADING | 3 | 1190764.76 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300547 | Antagan National High School | TUMAUINI | 1 | 1 | UPGRADING | 3 | 2155606.72 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 306153 | Cumabao IS | TUMAUINI | 1 | 1 | UPGRADING | 1 | 1451220.68 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 306109 | Fermeldy National High School | TUMAUINI | 1 | 1 | UPGRADING | 3 | 2709258.71 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300556 | Lalauanan National High School | TUMAUINI | 1 | 1 | UPGRADING | 3 | 2201117.74 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300551 | Lanna National High School | TUMAUINI | 1 | 1 | UPGRADING | 3 | 2321207.03 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300609 | Tumauini NHS | TUMAUINI | 1 | 1 | UPGRADING | 1 | 1628465.08 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 103884 | Tumauini North Central School | TUMAUINI | 1 | 1 | UPGRADING | 3 | 1896448.69 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 103903 | Tumauini South Central School | TUMAUINI | 1 | 1 | UPGRADING | 3 | 2222813.05 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 103904 | Tumauini West Central School | TUMAUINI | 1 | 1 | UPGRADING | 3 | 1898495.2 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 103072 | Aurora Central School | AURORA | 2 | 1 | UPGRADING | 3 | 1176056.83 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 103102 | Benito Soliven Central School | BENITO SOLIVEN | 2 | 1 | UPGRADING | 3 | 1012396.63 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300503 | Benito Soliven NHS | BENITO SOLIVEN | 2 | 1 | UPGRADING | 1 | 1176226.66 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 500079 | Maluno Integrated School - Main | BENITO SOLIVEN | 2 | 1 | UPGRADING | 3 | 1468714.47 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 500072 | Villaluz Integrated School | BENITO SOLIVEN | 2 | 1 | UPGRADING | 3 | 896259.08 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 500019 | Yeban Integrated School | BENITO SOLIVEN | 2 | 1 | UPGRADING | 3 | 1414672.6 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 103128 | Burgos Central School | BURGOS | 2 | 1 | UPGRADING | 3 | 1153599.18 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300509 | BURGOS NHS (formerly Caliguian NHS-Main) | BURGOS | 2 | 1 | UPGRADING | 1 | 1414778.54 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300511 | San Antonino NHS | BURGOS | 2 | 1 | UPGRADING | 1 | 1273274.55 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 103343 | Gamu Central School | GAMU | 2 | 1 | UPGRADING | 3 | 1113294.27 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300559 | Mabini National High School | GAMU | 2 | 1 | UPGRADING | 3 | 1639894.93 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 500077 | Bimonton Integrated School | MALLIG | 2 | 1 | UPGRADING | 2 | 1218106.74 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 103496 | Mallig Central School - Main | MALLIG | 2 | 1 | UPGRADING | 3 | 1628332.69 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300561 | Mallig NHS (formerly Mallig NHS - Main) | MALLIG | 2 | 1 | UPGRADING | 1 | 1148985.74 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 306110 | San Jose NHS (formerly Mallig HS -San Jose Norte Annex) | MALLIG | 2 | 1 | UPGRADING | 1 | 1190682.84 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 103520 | Naguilian Central School | NAGUILIAN | 2 | 1 | UPGRADING | 3 | 2080920.05 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 306112 | Barucboc National High School | QUEZON | 2 | 1 | UPGRADING | 3 | 1222637.7 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 103571 | Quezon CS | QUEZON | 2 | 1 | UPGRADING | 3 | 2092542.49 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300568 | Quezon HS - Main | QUEZON | 2 | 1 | UPGRADING | 1 | 1181729.01 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 500071 | San Juan Integrated School | QUEZON | 2 | 1 | UPGRADING | 3 | 872096.39 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 103580 | Quirino Central School | QUIRINO | 2 | 1 | UPGRADING | 3 | 1860295.48 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 500068 | Villa Cacho Integrated School | QUIRINO | 2 | 1 | UPGRADING | 3 | 1736088.03 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 306111 | Monico Rarama NHS (Munoz HS -San Pedro Extension) | ROXAS | 2 | 1 | UPGRADING | 1 | 1252371.25 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300562 | Munoz HS | ROXAS | 2 | 1 | UPGRADING | 1 | 1173740.73 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300579 | Roxas NHS-Main | ROXAS | 2 | 1 | UPGRADING | 1 | 1999770.49 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 500094 | Simimbaan Integrated School | ROXAS | 2 | 1 | UPGRADING | 1 | 1218106.74 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300512 | Callang NHS - Main | SAN MANUEL | 2 | 1 | UPGRADING | 1 | 1744759.24 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300514 | Sandiat NHS | SAN MANUEL | 2 | 1 | UPGRADING | 1 | 1547898.63 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300593 | Alibadabad National High School | SAN MARIANO | 2 | 1 | UPGRADING | 3 | 430415.85 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 500086 | Dicamay Integrated School | SAN MARIANO | 2 | 1 | UPGRADING | 3 | 964475.61 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300500 | Alicia National High School | ALICIA | 3 | 1 | UPGRADING | 2 | 1648463.28 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300565 | Palayan Region HS | ALICIA | 3 | 1 | UPGRADING | 1 | 1186861.71 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300576 | Rizal Region NHS , Alicia, Isabela | ALICIA | 3 | 1 | UPGRADING | 1 | 1075486.31 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300506 | Cadaloria HS | ANGADANAN | 3 | 1 | UPGRADING | 1 | 1049158.75 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 500020 | Lomboy Integrated School | ANGADANAN | 3 | 1 | UPGRADING | 3 | 876175.06 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300504 | Cabatuan National High School | CABATUAN | 3 | 1 | UPGRADING | 1 | 1929966.85 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300558 | Luna NHS | LUNA | 3 | 1 | UPGRADING | 1 | 1195227.54 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 103624 | Reina Mercedes Central School | REINA MERCEDES | 3 | 1 | UPGRADING | 3 | 974739.09 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300575 | Reina Mercedes Vocational and Industrial School | REINA MERCEDES | 3 | 1 | UPGRADING | 1 | 1432514.77 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 306116 | Reina Mercedes Vocational High School | REINA MERCEDES | 3 | 1 | UPGRADING | 1 | 1116614.51 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300590 | San Guillermo Voc'l & Ind'l High Sch. | SAN GUILLERMO | 3 | 1 | UPGRADING | 1 | 1074656.19 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300581 | Salinungan NHS | SAN MATEO | 3 | 1 | UPGRADING | 1 | 1245397.84 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 306143 | Cagasat HS-Magsasay Annex | CORDON | 4 | 1 | UPGRADING | 1 | 813316.04 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300508 | CAGASAT NHS | CORDON | 4 | 1 | UPGRADING | 1 | 790744.56 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300523 | Diadi Region HS | CORDON | 4 | 1 | UPGRADING | 1 | 885270.95 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300532 | Dona Josefa E. Marcos HS | CORDON | 4 | 1 | UPGRADING | 1 | 834063 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300526 | Dinapigue NHS | DINAPIGUE | 4 | 1 | UPGRADING | 1 | 889647.51 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300529 | Don Mariano Marcos NHS | ECHAGUE | 4 | 1 | UPGRADING | 1 | 784636.12 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300612 | Echague National High School | ECHAGUE | 4 | 1 | UPGRADING | 2 | 825152.88 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300539 | Highway Region NHS | ECHAGUE | 4 | 1 | UPGRADING | 1 | 820545.41 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300566 | Pangal Sur HS | ECHAGUE | 4 | 1 | UPGRADING | 1 | 831472.93 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300611 | Ugad HS | ECHAGUE | 4 | 1 | UPGRADING | 1 | 1062208.47 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300555 | Jones Rural School - Main | JONES | 4 | 1 | UPGRADING | 1 | 1480331.65 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 103600 | Gen. Aguinaldo ES - Villa Verde PS Annex | RAMON | 4 | 1 | UPGRADING | 3 | 939585.17 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300572 | Gen. Emilio Aguinaldo NHS | RAMON | 4 | 1 | UPGRADING | 1 | 817580.17 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300571 | Ramon National High School | RAMON | 4 | 1 | UPGRADING | 2 | 967178.24 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300574 | Raniag HS | RAMON | 4 | 1 | UPGRADING | 1 | 1184147.04 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 500092 | San Miguel Integrated School-Main | RAMON | 4 | 1 | UPGRADING | 2 | 1127436.31 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 306142 | San Sebastian Integrated School | RAMON | 4 | 1 | UPGRADING | 1 | 1149327.62 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300518 | Dabubu High School Main & Annex | SAN AGUSTIN | 4 | 1 | UPGRADING | 1 | 1145258.17 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Isabela | 300591 | San Isidro NHS | SAN ISIDRO | 4 | 1 | UPGRADING | 1 | 903294.53 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 300617 | Ambaguio High School | AMBAGUIO | 0 | 1 | UPGRADING | 1 | 2380840.46 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 300620 | Bambang NHS | BAMBANG | 0 | 1 | UPGRADING | 1 | 4643660.5 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 300635 | Dupax del Norte NHS | DUPAX DEL NORTE | 0 | 1 | UPGRADING | 1 | 5168669.82 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 300628 | Dupax del Sur NHS | DUPAX DEL SUR | 0 | 1 | UPGRADING | 1 | 1453392.33 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 104098 | Papalungan ES | KASIBU | 0 | 1 | SOLAR PANEL | 1 | 3440083.05 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 104114 | Ban-et PS | KAYAPA | 0 | 1 | SOLAR PANEL | 1 | 1377860.4 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 300633 | Martinez Cuyangan NHS | KAYAPA | 0 | 1 | UPGRADING | 1 | 2511723.29 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 306204 | Runruno National High School | QUEZON | 0 | 1 | UPGRADING | 1 | 2299961.96 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region II | Quirino | 300652 | Aglipay NHS | AGLIPAY | 0 | 1 | UPGRADING | 1 | 470878.68 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Quirino | 300663 | Pinaripad NHS | AGLIPAY | 0 | 1 | UPGRADING | 1 | 722573.4 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Quirino | 300653 | Victoria HS | AGLIPAY | 0 | 1 | UPGRADING | 1 | 605581.61 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Quirino | 300656 | Cabarroguis NSAT | CABARROGUIS (Capital) | 0 | 1 | UPGRADING | 1 | 938805.89 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Quirino | 300664 | Quirino General HS | CABARROGUIS (Capital) | 0 | 1 | UPGRADING | 1 | 995383.23 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Quirino | 300666 | Tucod HS | CABARROGUIS (Capital) | 0 | 1 | UPGRADING | 1 | 618440.27 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Quirino | 300657 | Diffun HS | DIFFUN | 0 | 1 | UPGRADING | 1 | 865201.89 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Quirino | 300661 | Magsaysay National High School | DIFFUN | 0 | 1 | UPGRADING | 1 | 561006.88 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Quirino | 300654 | Balligui HS | MADDELA | 0 | 1 | UPGRADING | 1 | 506369.85 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Quirino | 306317 | Dumabato Integrated School | MADDELA | 0 | 1 | UPGRADING | 1 | 742761.6 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Quirino | 300660 | Maddela CHS | MADDELA | 0 | 1 | UPGRADING | 1 | 1181950.74 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Quirino | 306309 | San Martin IS | MADDELA | 0 | 1 | UPGRADING | 1 | 222063.52 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Quirino | 306310 | GIAYAN INTEGRATED SCHOOL | NAGTIPUNAN | 0 | 1 | SOLAR PANEL | 1 | 2653311.76 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | Region II | Quirino | 300662 | Nagtipunan NHS | NAGTIPUNAN | 0 | 1 | UPGRADING | 1 | 687122.84 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Quirino | 306303 | Sangbay IS | NAGTIPUNAN | 0 | 1 | UPGRADING | 1 | 350034.81 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Quirino | 306316 | Scala Integrated School | NAGTIPUNAN | 0 | 1 | UPGRADING | 1 | 759093.07 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Quirino | 300665 | Saguday NHS | SAGUDAY | 0 | 1 | UPGRADING | 1 | 716743.19 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Santiago City | 300578 | Rizal National High School | CITY OF SANTIAGO | 4 | 1 | UPGRADING | 1 | 1974024.18 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Santiago City | 325201 | Santiago City National High School - Sinsayon | CITY OF SANTIAGO | 4 | 1 | UPGRADING | 1 | 372407.59 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Tuguegarao City | 300668 | CAGAYAN NHS - SENIOR HIGH SCHOOL | Tuguegarao City | 0 | 1 | UPGRADING | 1 | 762912.06 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Tuguegarao City | 300669 | CATAGGAMAN NHS-SENIOR HIGH SCHOOL | Tuguegarao City | 0 | 1 | UPGRADING | 1 | 447205.36 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Tuguegarao City | 300670 | LINAO NHS - SENIOR HIGH SCHOOL | Tuguegarao City | 0 | 1 | UPGRADING | 1 | 369305.78 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Tuguegarao City | 306401 | TUGUEGARAO CITY SENIOR HIGH SCHOOL | Tuguegarao City | 0 | 1 | UPGRADING | 1 | 751115.65 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region II | Tuguegarao City |  | GOSI NHS - SENIOR HIGH SCHOOL | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | 2 | 440825.28 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | Region II | Batanes | 102316 | Itbayat Central School | ITBAYAT | 0 | 1 | UPGRADING | Batch 3 | 1380118.87 |  | TERMINATED | 0.85 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | Region II | Batanes | 102317 | Mayan Elementary School | ITBAYAT | 0 | 1 | UPGRADING | Batch 1 | 1350673.21 |  | TERMINATED | 0.85 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | Region II | Batanes | 500062 | Itbud Integrated School | UYUGAN | 0 | 1 | UPGRADING | Batch 1 | 1499384.73 |  | REVERTED | 0 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | Region II | Cagayan | 300431 | Baggao NHS | BAGGAO | 1 | 1 | UPGRADING | Batch 3 | 841345.4 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Cagayan | 306011 | Licerio Antiporda Sr. NHS - Dalaya Ext. | BUGUEY | 1 | 1 | UPGRADING |  | 518902.41 |  | TERMINATED | 0.85 | [10 empty] | Contract Termination is on Process | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Cagayan | 306423 | Cabiraoan National High School | GONZAGA | 1 | 1 | UPGRADING |  | 571278.61 |  | TERMINATED | 0.4 | [10 empty] | Contract Termination is on Process | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Cagayan | 306013 | Luga National High School | SANTA TERESITA | 1 | 1 | UPGRADING | Batch 3 | 546120.81 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Cagayan | 300478 | Mauanan NHS | RIZAL | 2 | 1 | UPGRADING |  | 570776.31 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Cagayan | 306014 | LUBO NATIONAL HIGH SCHOOL | SANTO NIÑO (FAIRE) | 2 | 1 | UPGRADING | Batch 3 | 570776.31 |  | TERMINATED | 0.4 | [10 empty] | Contract Termination is on Process | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Cagayan | 300491 | Sto. Nino NHS | SANTO NIÑO (FAIRE) | 2 | 1 | UPGRADING |  | 570776.31 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Cagayan | 300425 | AMULUNG NATIONAL HIGH SCHOOL | AMULUNG | 3 | 1 | UPGRADING |  | 766345.96 |  | TERMINATED | 0.4 | [10 empty] | Contract Termination is on Process | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Cagayan | 300453 | Bayabat NHS | AMULUNG | 3 | 1 | UPGRADING | Batch 3 | 660427.53 |  | TERMINATED | 0.6 | [10 empty] | Contract Termination is on Process | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Cagayan | 300452 | Cordova National High Sschool | AMULUNG | 3 | 1 | UPGRADING |  | 870957.81 |  | TERMINATED | 0.55 | [10 empty] | Contract Termination is on Process | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Cagayan | 306010 | PACAC GRANDE NAT'L. HIGH SCHOOL | AMULUNG | 3 | 1 | UPGRADING |  | 696444.35 |  | TERMINATED | 0.45 | [10 empty] | Contract Termination is on Process | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Cagayan | 300427 | Dassun NHS | SOLANA | 3 | 1 | UPGRADING | Batch 3 | 660427.53 |  | COMPLETED | 1 | [10 empty] | Contract Termination is on Process | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Cauayan City | 103227 | Alinam ES | CITY OF CAUAYAN | 3 | 1 | UPGRADING | Batch 1 | 1131302.69 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | Region II | City of Ilagan | 300548 | Dappat Integrated School | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING |  | 1188658.04 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | City of Ilagan | 500087 | Gayong-Gayong Sur Integrated School | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1285590.7 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | City of Ilagan | 500992 | Ilagan East Integrated SPED Center | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 1 | 1105333.93 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | City of Ilagan | 103402 | Ilagan South CS | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING |  | 4454556.78 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | City of Ilagan | 300540 | Ilagan West NHS | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING |  | 1051958.94 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | City of Ilagan | 306149 | ISAT-Cabannungan Annex | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1210672.67 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | City of Ilagan | 500080 | Lupigue Integrated School (formerly Lupigue ES) | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1441858.38 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | City of Ilagan | 500078 | Manaring IS (Bangag-Manaring-Capo ES) | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING |  | 1441858.38 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | City of Ilagan | 103428 | Naguilian Baculud Elementary School | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1333997.26 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | City of Ilagan | 300543 | Rang-ayan NHS (Isabela NHS - Rang-ayan Annex) | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1179541.85 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | City of Ilagan | 103375 | San Juan Rugao ES | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING |  | 2704783.67 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | City of Ilagan | 500018 | San Lorenzo Integrated School (San Lorenzo ES) | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1314275.46 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | City of Ilagan | 500074 | San Pedro Integrated School | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING |  | 1951396.03 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | City of Ilagan | 300584 | San Rafael Nat'l & Voc'l HS (San Antonio NAIVHS-San Rafael Annex) | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING |  | 2788608.14 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | City of Ilagan | 500731 | Sindun Bayabo ES | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1506073.01 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | City of Ilagan | 300602 | Sta. Isabel National High School | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1640651.63 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 500072 | Villaluz Integrated School | BENITO SOLIVEN | 2 | 1 | UPGRADING | Batch 1 | 896259.08 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 500067 | Dolores Integrated School | QUIRINO | 2 | 1 | UPGRADING | Batch 1 | 1583860.26 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 500082 | Sto. Domingo Integrated School | QUIRINO | 2 | 1 | UPGRADING | Batch 1 | 2207057.35 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 306135 | Matusalem National High School | ROXAS | 2 | 1 | UPGRADING | Batch 1 | 1547472.38 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 103636 | Roxas Central School | ROXAS | 2 | 1 | UPGRADING | Batch 1 | 2006254.68 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 103643 | Roxas West Central School | ROXAS | 2 | 1 | UPGRADING | Batch 1 | 1834801.64 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 103719 | San Manuel Central School | SAN MANUEL | 2 | 1 | UPGRADING | Batch 1 | 1841706.18 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 103722 | Sandiat Elementary School | SAN MANUEL | 2 | 1 | UPGRADING | Batch 1 | 1950705.23 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 500014 | Del Pilar Integrated School | SAN MARIANO | 2 | 1 | UPGRADING | Batch 1 | 1323664.13 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 103742 | San Mariano Central School SPED Center | SAN MARIANO | 2 | 1 | UPGRADING | Batch 1 | 1284553.85 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 500095 | San Mariano II Central Integrated School | SAN MARIANO | 2 | 1 | UPGRADING | Batch 1 | 1042522.66 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 300592 | San Mariano National High School - Main | SAN MARIANO | 2 | 1 | UPGRADING | Batch 1 | 1752890.9 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 500069 | Sta. Filomena Integrated School | SAN MARIANO | 2 | 1 | UPGRADING | Batch 1 | 1272500.97 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 103005 | Alicia Central School | ALICIA | 3 | 1 | UPGRADING | Batch 1 | 1973948.91 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 102995 | Alicia East Central School | ALICIA | 3 | 1 | UPGRADING | Batch 1 | 1442381.83 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 102988 | Alicia North Central School | ALICIA | 3 | 1 | UPGRADING | Batch 1 | 1225691.53 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 103006 | Alicia West Central School | ALICIA | 3 | 1 | UPGRADING | Batch 1 | 1538337.93 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 103052 | Angadanan Central School | ANGADANAN | 3 | 1 | UPGRADING | Batch 1 | 1640341.52 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 103022 | Angadanan East Central School | ANGADANAN | 3 | 1 | UPGRADING | Batch 1 | 1602022.89 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 500017 | Fugaru Integrated School | ANGADANAN | 3 | 1 | UPGRADING | Batch 1 | 1428785.71 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 500023 | Sto. Niño Integrated School | ANGADANAN | 3 | 1 | UPGRADING | Batch 1 | 1747331.22 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 103165 | Cabatuan East Central School | CABATUAN | 3 | 1 | UPGRADING | Batch 1 | 1808491.84 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 103166 | Cabatuan West Central School | CABATUAN | 3 | 1 | UPGRADING | Batch 1 | 1743926.56 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 103487 | Luna Central School | LUNA | 3 | 1 | UPGRADING | Batch 1 | 1909573.04 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 306150 | Luna General Comprehensive High School | LUNA | 3 | 1 | UPGRADING | Batch 1 | 1491548.28 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 103690 | San Guillermo Central School | SAN GUILLERMO | 3 | 1 | UPGRADING | Batch 1 | 1705607.93 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 103788 | San Mateo East Central School | SAN MATEO | 3 | 1 | UPGRADING | Batch 1 | 1183725.21 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 103779 | San Mateo North Central School | SAN MATEO | 3 | 1 | UPGRADING | Batch 1 | 1358662.22 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 103789 | San Mateo West Central School | SAN MATEO | 3 | 1 | UPGRADING | Batch 1 | 1550060.96 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 103258 | Cordon North Central School | CORDON | 4 | 1 | UPGRADING | Batch 1 | 1592559.18 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 103247 | Cordon South Central School-Main | CORDON | 4 | 1 | UPGRADING | Batch 1 | 1674242.6 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 500073 | Wigan Integrated School | CORDON | 4 | 1 | UPGRADING | Batch 1 | 1290802.76 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 300533 | Dona Magdalena H. Gaffud HIgh School | ECHAGUE | 4 | 1 | UPGRADING | Batch 1 | 1649125.78 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 103290 | Echague East Central School | ECHAGUE | 4 | 1 | UPGRADING | Batch 1 | 1646429.09 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 103311 | Echague South Central School | ECHAGUE | 4 | 1 | UPGRADING | Batch 1 | 1231232.35 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 300541 | Imelda R. Marcos High School | ECHAGUE | 4 | 1 | UPGRADING | Batch 1 | 1135675.58 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 300498 | Addalam Region HS - Main | JONES | 4 | 1 | UPGRADING | Batch 1 | 1598089.72 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 300524 | Dibuluan National High School | JONES | 4 | 1 | UPGRADING | Batch 1 | 1551051.62 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 103469 | Jones West Central School Campus 1 | JONES | 4 | 1 | UPGRADING | Batch 1 | 1613921.68 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 300600 | Sgt. Prospero Bello HS - Main | JONES | 4 | 1 | UPGRADING | Batch 1 | 1695215.78 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 300582 | San Agustin National High School | SAN AGUSTIN | 4 | 1 | UPGRADING | Batch 1 | 1695215.78 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 500091 | Cebu Integrated Sschool | SAN ISIDRO | 4 | 1 | UPGRADING | Batch 1 | 1592559.18 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Isabela | 306123 | Manuel L. Quezon National High School | SAN ISIDRO | 4 | 1 | UPGRADING | Batch 1 | 1283365.73 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Nueva Vizcaya | 300618 | Aritao National High School | ARITAO | 0 | 1 | UPGRADING | Batch 1 | 4500080.72 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Nueva Vizcaya | 300637 | Munguia NHS | DUPAX DEL NORTE | 0 | 1 | UPGRADING | Batch 1 | 2443832.95 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Nueva Vizcaya | 300631 | Kasibu National Agricultural School | KASIBU | 0 | 1 | UPGRADING | Batch 1 | 4982144.12 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Nueva Vizcaya | 300649 | Santa Fe National High School | SANTA FE | 0 | 1 | UPGRADING | Batch 1 | 5149791.12 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Nueva Vizcaya | 300646 | Solano High School | SOLANO | 0 | 1 | UPGRADING | Batch 3 | 12204160.22 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Quirino | 104238 | Aglipay East CS (Progreso ES) | AGLIPAY | 0 | 1 | UPGRADING |  | 929420.6 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Quirino | 104248 | Victoria Elementary School Annex | AGLIPAY | 0 | 1 | UPGRADING |  | 555784.13 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Quirino | 104247 | Victoria ES | AGLIPAY | 0 | 1 | UPGRADING |  | 637574.37 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Quirino | 104254 | Burgos Elementary School | CABARROGUIS (Capital) | 0 | 1 | UPGRADING |  | 757282.52 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Quirino | 104264 | Mangandingay ES | CABARROGUIS (Capital) | 0 | 1 | UPGRADING |  | 961848.18 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Quirino | 104280 | Diffun CS - Integrated SPED Center | DIFFUN | 0 | 1 | UPGRADING |  | 1038369.32 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Quirino | 104283 | Isidro Paredes ES | DIFFUN | 0 | 1 | UPGRADING |  | 598065.74 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Quirino | 104306 | Liwayway ES | DIFFUN | 0 | 1 | UPGRADING |  | 651551.48 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Quirino | 300659 | Dipintin HS | MADDELA | 0 | 1 | UPGRADING |  | 724435.1 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Quirino | 104330 | Maddela North CS | MADDELA | 0 | 1 | UPGRADING |  | 1059099.99 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Quirino | 104323 | Maddela South CS | MADDELA | 0 | 1 | UPGRADING |  | 928669.98 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Quirino | 104334 | San Bernabe ES | MADDELA | 0 | 1 | UPGRADING |  | 699298.47 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Quirino | 104363 | Nagtipunan CS | NAGTIPUNAN | 0 | 1 | UPGRADING |  | 1384996.29 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Quirino | 104375 | La Paz ES | SAGUDAY | 0 | 1 | UPGRADING |  | 744922.1 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Quirino | 104377 | SAGUDAY CENTRAL SCHOOL | SAGUDAY | 0 | 1 | UPGRADING |  | 926247.23 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Quirino | 104378 | Salvacion ES | SAGUDAY | 0 | 1 | UPGRADING |  | 564434.82 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Santiago City | 103812 | Batal ES | CITY OF SANTIAGO | 4 | 1 | UPGRADING |  | 638253.49 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | Region II | Santiago City | 325204 | Divisoria High School - Naggasican Extension | CITY OF SANTIAGO | 4 | 1 | UPGRADING |  | 408217.95 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | Region II | Santiago City | 103814 | Luna ES | CITY OF SANTIAGO | 4 | 1 | UPGRADING |  | 300024.21 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | Region II | Santiago City | 103815 | Mabini ES | CITY OF SANTIAGO | 4 | 1 | UPGRADING |  | 499829.4 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104393 | Annafunan ES | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 1 | 523307.76 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104402 | Cataggamman ES | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 3 | 1306164.63 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104391 | Tagga-Dadda ES | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 1 | 396711.95 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104392 | Tuguegarao East CS | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 1 | 925595.11 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104400 | Tuguegarao North CS | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 1 | 1249377.84 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104382 | Tuguegarao Northeast CS | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 1 | 902002.59 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104406 | Tuguegarao West CS | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 3 | 1332603.4 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104407 | Ugac Elementary School | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 1 | 403936.85 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2020 | Region II | Batanes | 102311 | Basco Central School | BASCO (Capital) | 0 | 1 | UPGRADING |  | 4914160.07 |  | TERMINATED | 0.35 |  |  | ELEC-2020-RII-BATANES-006 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Batanes | 300411 | Batanes Nat"l Science High School | BASCO (Capital) | 0 | 1 | UPGRADING |  | 1660529.16 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-BATANES-007 | [7 empty] | Implementation not yet started due to the imposition of ecq and to the typhoon kiko and contractor is still in mainland and send letter in the division for the catch up plan in implementing the prjects |  | UPGRADING
ELECTRIFICATION 2020 | Region II | Batanes | 102313 | Diptan Elementary School | BASCO (Capital) | 0 | 1 | UPGRADING |  | 2693654.15 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-BATANES-005 | [7 empty] | Implementation not yet started due to the imposition of ecq and to the typhoon kiko and contractor is still in mainland and send letter in the division for the catch up plan in implementing the prjects |  | UPGRADING
ELECTRIFICATION 2020 | Region II | Batanes | 102328 | Sabtang Central School | SABTANG | 0 | 1 | UPGRADING |  | 1633822.52 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-BATANES-004 | [7 empty] | Implementation not yet started due to the imposition of ecq and to the typhoon kiko and contractor is still in mainland and send letter in the division for the catch up plan in implementing the prjects |  | UPGRADING
ELECTRIFICATION 2020 | Region II | Cagayan | 300437 | Bukig National Agricultural and Technical School | APARRI | 1 | 1 | UPGRADING |  | 723016.85 |  | TERMINATED | 0 |  |  | ELEC-2020-RII-CAGAYAN-001 | [7 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2020 | Region II | Cagayan | 300478 | Mauanan NHS | RIZAL | 2 | 1 | UPGRADING |  | 615683.6 |  | TERMINATED | 0 |  |  | ELEC-2020-RII-CAGAYAN-007 | [7 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2020 | Region II | Cagayan | 300486 | Sanchez Mira SAT | SANCHEZ-MIRA | 2 | 1 | UPGRADING |  | 1019916.77 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-CAGAYAN-002 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Cagayan | 300491 | Sto. Nino NHS | STO. NINO | 2 | 1 | UPGRADING |  | 689117.88 |  | TERMINATED | 0 |  |  | ELEC-2020-RII-CAGAYAN-009 | [7 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2020 | Region II | Cagayan | 306424 | Gadu NHS- Nangalisan Extension | SOLANA | 3 | 1 | UPGRADING |  | 1222194.87 |  | TERMINATED | 0 |  |  | ELEC-2020-RII-CAGAYAN-003 | [7 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2020 | Region II | Cagayan | 300466 | Itawes Nat'l. Agr'l. & Tech'l. School | TUAO | 3 | 1 | UPGRADING |  | 807603.58 |  | TERMINATED | 0 |  |  | ELEC-2020-RII-CAGAYAN-010 | [7 empty] | Contract Termination is on Process |  | UPGRADING
ELECTRIFICATION 2020 | Region II | Cauayan City | 103211 | Cauayan North CS | CITY OF CAUAYAN | 3 | 1 | UPGRADING |  | 1080843.25 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-CAUAYAN CITY-002 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Cauayan City | 103228 | Cauayan South CS | CITY OF CAUAYAN | 3 | 1 | UPGRADING |  | 1238184.17 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-CAUAYAN CITY-001 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Cauayan City | 103233 | Cauayan West CS | CITY OF CAUAYAN | 3 | 1 | UPGRADING |  | 1204885.19 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-CAUAYAN CITY-003 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | City of Ilagan | 103354 | Alinguigan 1st Elementary School | City of Ilagan | 1 | 1 | UPGRADING |  | 698964.52 |  | COMPLETED | 1 |  |  | Elec2020-R2-City of Ilagan-002 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | City of Ilagan | 103355 | Alinguigan 2nd ES | City of Ilagan | 1 | 1 | UPGRADING |  | 698964.52 |  | COMPLETED | 1 | Jan. 2021 |  | Elec2020-R2-City of Ilagan-003 |  | Nov. 12, 2019 | Nov. 19, 2019 | Dec. 09, 2019 | Jan. 07, 2020 | Sept. 21, 2020 | SMT CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2020 | Region II | City of Ilagan | 103361 | Capellan ES | City of Ilagan | 1 | 1 | UPGRADING |  | 727197.59 |  | COMPLETED | 1 | Jan. 2021 |  | Elec2020-R2-City of Ilagan-005 |  | Nov. 12, 2019 | Nov. 19, 2019 | Dec. 09, 2019 | Jan. 07, 2020 | Sept. 21, 2020 | SMT CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2020 | Region II | City of Ilagan | 103382 | Tangcul-San Isidro ES | City of Ilagan | 1 | 1 | UPGRADING |  | 677944.35 |  | COMPLETED | 1 | Jan. 2021 |  | Elec2020-R2-City of Ilagan-001 |  | Nov. 12, 2019 | Nov. 19, 2019 | Dec. 09, 2019 | Jan. 07, 2020 | Sept. 21, 2020 | SMT CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2020 | Region II | Isabela | 300521 | Alfreda Albano National High School - Magassi, Cabagan | CABANGAN | 1 | 1 | UPGRADING |  | 828610.6 |  | COMPLETED | 1 |  |  | ELEC2020-RII-ISABELA-014 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Isabela | 300520 | Delfin Albano High School-Main | CABANGAN | 1 | 1 | UPGRADING |  | 976761.31 |  | COMPLETED | 1 |  |  | ELEC2020-RII-ISABELA-015 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Isabela | 300597 | San Pablo National High School | SAN PABLO | 1 | 1 | UPGRADING |  | 262626.38 |  | COMPLETED | 1 |  |  | ELEC2020-RII-ISABELA-013 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Isabela | 306132 | Simanu National High School | SAN PABLO | 1 | 1 | UPGRADING |  | 961515.07 |  | COMPLETED | 1 |  |  | ELEC2020-RII-ISABELA-006 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Isabela | 300551 | Lanna National High School | TUMAUINI | 1 | 1 | UPGRADING |  | 503768.82 |  | COMPLETED | 1 |  |  | ELEC2020-RII-ISABELA-012 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Isabela | 300609 | Tumauini National High School | TUMAUINI | 1 | 1 | UPGRADING |  | 593838.49 |  | COMPLETED | 1 |  |  | ELEC2020-RII-ISABELA-017 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Isabela | 500073 | Wigan Integrated School | CORDON | 4 | 1 | UPGRADING |  | 921481.88 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-ISABELA-003 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Isabela | 103331 | Echague West Central School | ECHAGUE | 6 | 1 | UPGRADING |  | 937346.67 |  | COMPLETED | 1 |  |  | ELEC2020-RII-ISABELA-008 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Isabela | 103706 | San Isidro East Central School | SAN ISIDRO | 6 | 1 | UPGRADING |  | 937346.67 |  | COMPLETED | 1 |  |  | ELEC2020-RII-ISABELA-005 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Isabela | 103707 | San Isidro West Central School | SAN ISIDRO | 6 | 1 | UPGRADING |  | 937346.67 |  | COMPLETED | 1 |  |  | ELEC2020-RII-ISABELA-004 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Nueva Vizcaya | 300619 | Bagabag NHS | BAGBAG | 0 | 1 | UPGRADING |  | 5019524.37 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-NUEVA VIZCAYA-002 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Nueva Vizcaya | 300627 | Diadi NHS | DIADI | 0 | 1 | UPGRADING |  | 12887267.59 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-NUEVA VIZCAYA-003 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Nueva Vizcaya | 300635 | LAMO NATIONAL HIGH SCHOOL | DUPAX DEL NORTE | 0 | 1 | UPGRADING |  | 5504683.46 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-NUEVA VIZCAYA-001 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Quirino | 104249 | Villa Pagaduan Elementary School | Aglipay | 0 | 1 | UPGRADING |  | 535526.76 |  | COMPLETED | 1 |  |  | ELEC2020-RII-QUIRINO-004 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Quirino | 104266 | San Marcos ES | Cabarroguis | 0 | 1 | UPGRADING |  | 680903.14 |  | COMPLETED | 1 |  |  | ELEC2020-RII-QUIRINO-001 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Quirino | 104281 | Gulac ES | Diffun | 0 | 1 | UPGRADING |  | 556535.75 |  | COMPLETED | 1 |  |  | ELEC2020-RII-QUIRINO-007 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Santiago City | 103837 | Calaocan ES | Santiago City | 1 | 1 | UPGRADING |  | 877681.63 |  | COMPLETED | 1 |  |  | Elec 2020-R II-Santiago City-001 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Santiago City | 306124 | Patul National High School | Santiago City | 1 | 1 | UPGRADING |  | 810365.58 |  | COMPLETED | 1 |  |  | Elec 2020-R II-Santiago City-004 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Santiago City | 325202 | Sagana National High School | Santiago City | 1 | 1 | UPGRADING |  | 864847.86 |  | COMPLETED | 1 |  |  | Elec 2020-R II-Santiago City-005 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Santiago City | 103841 | Sta. Rosa ES | Santiago City | 1 | 1 | UPGRADING |  | 661763.68 |  | COMPLETED | 1 |  |  | Elec 2020-R II-Santiago City-008 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Tuguegarao City | 104384 | Balzain East ES | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING |  | 438364.85 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-TUGUEGARAO CITY-001 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Tuguegarao City | 157002 | Cataggaman Nuevo ES | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING |  | 218174.54 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-TUGUEGARAO CITY-005 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Tuguegarao City | 104403 | Pallua ES | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING |  | 445321.08 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-TUGUEGARAO CITY-004 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region II | Tuguegarao City | 306402 | Tuguegarao City West High School | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING |  | 311749.84 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-TUGUEGARAO CITY-006 | [9 empty] | UPGRADING
ELECTRIFICATION 2023 | Region II | Batanes | 102329 | Savidug Elementary School | SABTANG | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1030909.75 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2023 | Region II | Batanes | 102330 | Sumnanga Elementary School | SABTANG | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 821127.21 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2023 | Region II | Cagayan | 300464 | Illuru National High School | RIZAL | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1429293.86 | 1406356.97 | COMPLETED | 1 | November 3, 2023 | 1900-03-25 | ELEC 2023-RII-Cagayan o1 | INFRA 2023-046 | May 8, 2023 | May 15, 2023 | May 29, 2023 |  | June 08, 2023 | WWW. Constrution |  |  | UPGRADING
ELECTRIFICATION 2023 | Region II | Nueva Vizcaya | 137029 | Hiket Elementary School | AMBAGUIO | Lone | 1 | Provision of Solar-Powered Energy System | 1 | 2620439.1 |  | COMPLETED | 1 | January 23, 2024 | March 12, 2024 | PB06-004-SDONV-CY2023-BEFF-ELEC-LOT2-HIKET ES |  | June 22, 2023 |  | July 14, 2023 | August 18, 2023 | September 25, 2023 | Mighty Construction & Supply |  |  | SOLAR
ELECTRIFICATION 2023 | Region II | Nueva Vizcaya | 137027 | Pihipi Elementary School | AMBAGUIO | Lone | 1 | Provision of Solar-Powered Energy System | 1 | 2620965.54 |  | COMPLETED | 1 | January 16, 2024 | March 12, 2024 | PB06-004-SDONV-CY2023-BEFF-ELEC-LOT1-PIHIPI ES |  | June 22, 2023 |  | July 14, 2023 | August 18, 2023 | September 25, 2023 | Mighty Construction & Supply |  |  | SOLAR
ELECTRIFICATION 2024 | Region II | Batanes | 102311 | Basco Central School | BASCO (Capital) | Lone | 1 | Energization of Electrical System (Underground System) | 1 | 1943508.93 |  | not yet started | 0 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2024 | Region II | Cagayan | 300488 | Sta. Ana Fishery National High School | SANTA ANA | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3077073.36 | 2336832.19 | COMPLETED | 1 | SEPTEMBER 25, 2024 |  | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | INFRA 2023-124-LOT 1 | nov 13, 2023 | november 20, 2024 | december 4, 2023 | MAY 13, 20224 | MAY 29, 2024 | CONSTUIRE CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2024 | Region II | Cagayan | 102331 | Abulug Central Elementary School | ABULUG | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1429293.86 | 1115481.12 | COMPLETED | 1 | SEPTEMBER 25, 2024 |  | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | INFRA 2023-124-LOT 1 | nov 13, 2023 | november 20, 2024 | december 4, 2023 | MAY 13, 20224 | MAY 29, 2024 | CONSTUIRE CONSTRUCTION |  |  | ENERGIZATION
ELECTRIFICATION 2024 | Region II | Cagayan | 300456 | Don Severino Pagalilauan National High School | PEÑABLANCA | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 689117.88 | 688117.88 | ONGOING | 0.95 |  |  | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | INFRA 2024-075 | JULY 9, 2024 | JULY 15, 2024 | JULY 15, 2024 | JULY 16, 2024 |  | GCPK Construction & Supply | for final inspection |  | ENERGIZATION
ELECTRIFICATION 2024 | Region II | Cauayan City | 300516 | Cauayan City NHS | CITY OF CAUAYAN | 6th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3077073.36 |  | ONGOING | 0.3 |  |  | UPGRADING OF ELECTRICAL SYSTEM (OVERHEAD SYSTEM) OF CAUAYAN CITY NATIONAL HIGH SCHOOL | CW-003 S. 2025 | 2024-06-29 | 2024-07-08 | 2024-07-22 | 2024-08-06 |  |  | already downloaded subaro |  | ENERGIZATION
ELECTRIFICATION 2024 | Region II | City of Ilagan | 103384 | Aggassian Elementary School | ILAGAN CITY (CAPITAL) | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3077073.36 | 3071337.63 | Completed | 1 | 2024-10-03 |  | 10398574 | INF-2024-01 | 2023-12-04 | 2023-12-13 | 2023-12-27 | 2024-12-29 | 2024-06-24 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  |  | ENERGIZATION
ELECTRIFICATION 2024 | Region II | Isabela | 501434 | CUBAG INTEGRATED SCHOOL | CABAGAN | 1st | 1 | Upgrading Electrical System On Grid Schools | 1 | 1670752.61 | 1649364.22 | Completed | 1 | 2024-08-20 |  |  | 2024-0505 | November 11,2023 | November 20,2023 | 2023-12-05 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  |  | UPGRADING
ELECTRIFICATION 2024 | Region II | Isabela | 103536 | BISAG ELEMENTARY SCHOOL | PALANAN | 2nd | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 2338294.94 | 2335479.45 | Completed | 1 | 2024-08-20 |  |  | 2024-0505 | November 11,2023 | November 20,2023 | 2023-12-05 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  |  | SOLAR
ELECTRIFICATION 2024 | Region II | Isabela | 306115 | LFG DIAMANTINA NATIONAL HIGH SCHOOL | CABATUAN | 3rd | 1 | Upgrading Electrical System On Grid Schools | 1 | 1563047.81 | 1535336.98 | Completed | 1 | 2024-08-20 |  |  | 2024-0505 | November 11,2023 | November 20,2023 | 2023-12-05 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  |  | UPGRADING
ELECTRIFICATION 2024 | Region II | Isabela | 501316 | Taliktik Integrated School | CORDON | 4th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2383413.13 | 2368626.76 | Completed | 1 | 2024-08-20 |  |  | 2024-0505 | November 11,2023 | November 20,2023 | 2023-12-05 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  |  | ENERGIZATION
ELECTRIFICATION 2024 | Region II | Isabela | 500084 | MACANIAO INTEGRATED SCHOOL | ANGADANAN | 5th | 1 | Upgrading Electrical System On Grid Schools | 1 | 1273865.41 | 1253721.61 | Completed | 1 | 2024-08-20 |  |  | 2024-0505 | November 11,2023 | November 20,2023 | 2023-12-05 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  |  | UPGRADING
ELECTRIFICATION 2024 | Region II | Isabela | 500022 | RIZAL INTEGRATED SCHOOL | SAN GUILLERMO | 6th | 1 | Upgrading Electrical System On Grid Schools | 1 | 1690299.17 | 1679845.08 | Completed | 1 | 2024-08-20 |  |  | 2024-0505 | November 11,2023 | November 20,2023 | 2023-12-05 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  |  | UPGRADING
ELECTRIFICATION 2024 | Region II | Nueva Vizcaya | 104205 | Mandunot ES | ALFONSO CASTANEDA | Lone | 1 | Provision of Solar-Powered Energy System to Schools Off-Grid | 1 | 4053012.33 | 4048810.29 | COMPLETED | 1 | November 10, 2024 |  | PB03-002-SDONV-CY2024EP |  | March 19, 2024 | March 18, 2024 | April 15, 2024 | April 26, 2024 | June 13, 2024 | Mighty Construction | - |  | SOLAR
ELECTRIFICATION 2024 | Region II | Quirino | 300655 | Burgos NHS | CABARROGUIS (Capital) | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3077073.36 | 2547939.16 | COMPLETED | 1 | 2024-08-06 |  | ELEC-2024-REGION II - QUIRINO - 002 | 09-02-16-2024 | 2024-02-16 | 2024-02-23 | 2024-03-06 | 2024-03-15 | 2024-06-07 | GCPK Construction & Supply | with Time Extension / awaiting for the installation of Transformer from the Local Cooperative |  | ENERGIZATION
ELECTRIFICATION 2024 | Region II | Santiago City | 103835 | Baluarte ES | CITY OF SANTIAGO | 4th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3077073.36 |  | not yet started | 0 | [10 empty] | alredy submitted RTA to CO; Awaiting downloading of subaro |  | ENERGIZATION
ELECTRIFICATION 2024 | Region II | Tuguegarao City | 300668 | Cagayan National High School - Junior HS | TUGUEGARAO CITY(Capital) | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3077073.36 |  | Under Procurement | 0 | [10 empty] | no subaro yet; for request of realignment |  | ENERGIZATION

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%