## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Program-Year | Status as of July 11, 2025
K10 (2014) | REGION II | Quirino | 306321 | Alicia Integrated School | AGLIPAY | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-14 | 2015-09-30 | 020514S00017 | 15BK0035 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-31 | 2015-08-14 | KMD BUILDERS AND CONST. SUPPLY |  | NC 2014
SHS | REGION II | Cagayan | 300471 | Aparri East National High School | Aparri | 1 | 1 | 10 | 2STY10CL | BATCH 3 CL | 13150000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300471 | Aparri East National High School | Aparri | 1 |  | 6 | 2STY6CL | BATCH 3 CL | 8350000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300428 | Aparri Sat | Aparri | 1 | 1 | 27 | 3STY9CL | BATCH 3 CL | 45450000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300428 | Aparri Sat | Aparri | 1 |  | 4 | 2STY4CL | BATCH 3 CL | 6469337 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION II | Cagayan | 300428 | Aparri Sat | Aparri | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2490000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300429 | Baggao Nas | Baggao | 1 | 1 | 20 | 2STY10CL | BATCH 3 CL | 26300000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION II | Cagayan | 300429 | Baggao Nas | Baggao | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 4980000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300431 | Baggao Nhs | Baggao | 1 | 1 | 10 | 2STY10CL | BATCH 3 CL | 13150000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300431 | Baggao Nhs | Baggao | 1 |  | 6 | 2STY6CL | BATCH 3 CL | 8350000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300431 | Baggao Nhs | Baggao | 1 |  | 4 | 2STY4CL | BATCH 3 CL | 6469337 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300444 | Camalaniugan Nhs | Camalaniugan | 1 | 1 | 20 | 2STY10CL | BATCH 3 CL | 26300000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300444 | Camalaniugan Nhs | Camalaniugan | 1 |  | 6 | 2STY6CL | BATCH 3 CL | 8350000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION II | Cagayan | 300444 | Camalaniugan Nhs | Camalaniugan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2490000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Cagayan | 300462 | Gattaran National Trade School | Gattaran | 1 | 1 | 24 | 2STY8CL | BATCH 3 CL | 33635000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION II | Cagayan | 300462 | Gattaran National Trade School | Gattaran | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2527000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Cagayan | 102695 | Gonzaga North Cs | Gonzaga | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.05 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300469 | Lal-Lo National High School | Lal-Lo | 1 | 1 | 20 | 2STY10CL | BATCH 3 CL | 26300000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300469 | Lal-Lo National High School | Lal-Lo | 1 |  | 8 | 2STY8CL | BATCH 3 CL | 11150000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION II | Cagayan | 300469 | Lal-Lo National High School | Lal-Lo | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2490000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300488 | Sta. Ana Fishery National High School | Santa Ana | 1 | 1 | 16 | 2STY8CL | BATCH 3 CL | 22300000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION II | Cagayan | 300488 | Sta. Ana Fishery National High School | Santa Ana | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 4980000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300424 | Allacapan Vhs | Allacapan | 2 | 1 | 30 | 2STY10CL | BATCH 9 CL | 40050000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300424 | Allacapan Vhs | Allacapan | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 6550000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300424 | Allacapan Vhs | Allacapan | 2 |  | 3 | 1STY3CL | BATCH 9 CL | 2904910.9364 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION II | Cagayan | 300424 | Allacapan Vhs | Allacapan | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4350600 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300434 | Ballesteros Nhs | Ballesteros | 2 | 1 | 18 | 3STY9CL | BATCH 9 CL | 30260000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300434 | Ballesteros Nhs | Ballesteros | 2 |  | 8 | 2STY8CL | BATCH 9 CL | 11930000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300434 | Ballesteros Nhs | Ballesteros | 2 |  | 3 | 1STY3CL | BATCH 9 CL | 2904910.9364 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION II | Cagayan | 300434 | Ballesteros Nhs | Ballesteros | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2490000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300486 | Sanchez Mira Sat | Sanchez-Mira | 2 | 1 | 30 | 2STY10CL | BATCH 3 CL | 40050000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300486 | Sanchez Mira Sat | Sanchez-Mira | 2 |  | 4 | 2STY4CL | BATCH 3 CL | 6550000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION II | Cagayan | 300486 | Sanchez Mira Sat | Sanchez-Mira | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2490000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300426 | Andarayan Nhs | Solana | 3 | 1 | 15 | 3STY15CL | BATCH 3 CL | 20650000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300458 | Enrile Vocational High School | Enrile | 3 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11250000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300458 | Enrile Vocational High School | Enrile | 3 |  | 12 | 3STY12CL | BATCH 3 CL | 16750000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION II | Cagayan | 300458 | Enrile Vocational High School | Enrile | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2850000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION II | Cagayan | 300467 | Itawes National High School | Tuao | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2850000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300467 | Itawes National High School | Tuao | 3 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8450000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Cagayan | 300467 | Itawes National High School | Tuao | 3 |  | 16 | 2STY8CL | BATCH 3 CL | 26950000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | City Of Ilagan | 103384 | Aggassian Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 103412 | Alibagu Elementary School | Ilagan (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2693142.91 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 103385 | Ballacong Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 155505 | Bangag Ps | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 155505 | Bangag Ps | Ilagan (Capital) | 1 |  | 1 | 1STY1CL | BATCH 7 CL | 1032098.36 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 103359 | Batong Labang Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY1CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 103417 | Bliss Es | Ilagan (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6607815.88 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-08 | 2016-06-21 | 2016-07-04 | 2016-07-15 | SMT CONSTRUCTION |  | NC 2016
K10 | REGION II | City Of Ilagan | 103418 | Cabannungan 1St Es | Ilagan (Capital) | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1032098.36 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 103389 | Cabeceria 23 E/S | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 103386 | Cadu Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 155506 | Calindayagan Elementary School | Ilagan (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2693142.91 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 103361 | Capellan Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 103396 | Capugotan Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | 4A'S CONSTRUCTION |  | NC 2016
K10 | REGION II | City Of Ilagan | 103398 | Dappat Integrated School | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 300548 | Dappat Integrated School | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 103401 | Gayong-Gayong Sur Integrated School | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 103401 | Gayong-Gayong Sur Integrated School | Ilagan (Capital) | 1 |  | 1 | 1STY1CL | BATCH 7 CL | 1032098.36 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-06-28 | 2016-07-11 | SMT CONSTRUCTION |  | NC 2016
K10 | REGION II | City Of Ilagan | 500087 | Gayong-Gayong Sur Is | Ilagan (Capital) | 1 |  | 6 | 2STY6CL | BATCH 7 CL | 8592082.81 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | SMT CONSTRUCTION |  | NC 2016
K10 | REGION II | City Of Ilagan | 500087 | Gayong-Gayong Sur Is | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-05-27 | 2016-06-03 | 2016-06-17 | 2016-06-29 | 2016-07-11 | JMU CONSTRUCTION |  | NC 2016
K10 | REGION II | City Of Ilagan | 300542 | Isabela Nhs - Main | Ilagan (Capital) | 1 | 1 | 36 | 4STY12CL | BATCH 9 CL | 73054690.29 |  |  | Completed | 1 |  |  |  |  | 2016-05-27 | 2016-06-03 | 2016-06-17 | 2016-06-29 | 2016-07-11 | EGB CONSTRUCTION |  | NC 2016
K10 | REGION II | City Of Ilagan | 300542 | Isabela Nhs - Main | Ilagan (Capital) | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 | 2016-06-16 | 2016-06-28 | 2016-07-08 | 2016-07-22 | JMU CONSTRUCTION |  | NC 2016
SHS | REGION II | City Of Ilagan |  | Isabela Sports Senior High School | Ilagan (Capital) | 1 | 1 | 20 | 2STY10CL | BATCH 5 CL | 28026882.22 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-05-03 | 2016-06-24 | 2016-07-07 | EGB CONSTRUCTION |  | NC 2016
K10 | REGION II | City Of Ilagan | 306149 | Isat-Cabannungan Annex | Ilagan (Capital) | 1 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15821387.21 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-05-03 | 2016-06-24 | 2016-07-07 | EGB CONSTRUCTION |  | NC 2016
TECHVOC | REGION II | City Of Ilagan | 306149 | Isat-Cabannungan Annex | Ilagan (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 |  |  |  |  | 2016-03-29 | 2016-04-05 | 2016-04-18 | 2016-05-20 | 2016-05-31 | E.S. PUA CONSTRUCTION |  | NC 2016
SHS | REGION II | City Of Ilagan | 306141 | Lupigue Integrated School | Ilagan (Capital) | 1 | 1 | 12 | 2STY12CL | BATCH 7 CL | 15253927.38 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 | 2016-06-16 | 2016-06-28 | 2016-07-08 | 2016-07-22 | EGB CONSTRUCTION |  | NC 2016
TECHVOC | REGION II | City Of Ilagan | 306141 | Lupigue Integrated School | Ilagan (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 |  |  |  |  | 2016-03-29 | 2016-04-05 | 2016-04-18 | 2016-05-20 | 2016-05-31 | SMT CONSTRUCTION |  | NC 2016
K10 | REGION II | City Of Ilagan | 103369 | Minabang Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 103370 | Morado Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 103371 | Nanaguan Primary School | Ilagan (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2743142.91 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | FOREF CONSTRUCTION |  | NC 2016
K10 | REGION II | City Of Ilagan | 103372 | Pasa Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 103430 | Pilar Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 103373 | Rang-Ayan Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 300543 | Rang-Ayan Nhs (Isabela Nhs - Rang-Ayan Annex) | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
SHS | REGION II | City Of Ilagan | 300544 | San Lorenzo Integrated School | Ilagan (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2693142.91 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 103376 | San Lorenzo Integrated School (San Lorenzo Es) | Ilagan (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2693142.91 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 103394 | San Manuel Cabeceria 4 Es | Ilagan (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2693142.91 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | 4A'S CONSTRUCTION |  | NC 2016
K10 | REGION II | City Of Ilagan | 155519 | San Pablo-Quimalabasa Ps | Ilagan (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2693142.91 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 103407 | San Pedro Integrated School | Ilagan (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2693142.91 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 306129 | San Pedro Integrated School | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 306129 | San Pedro Integrated School | Ilagan (Capital) | 1 |  | 1 | 1STY1CL | BATCH 7 CL | 1032098.36 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 103410 | Sindun Bayabo Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 103411 | Sindun Maride Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 103378 | Sipay Elementary School | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
K10 | REGION II | City Of Ilagan | 103379 | Sta. Catalina Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
SHS | REGION II | City Of Ilagan | 300602 | Sta. Isabel Nhs | Ilagan (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 5 CL | 29357716.36 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-05-03 | 2016-06-24 | 2016-07-07 | C.T. LEONCIO CONSTRUCTION AND TRADING / DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
SHS | REGION II | City Of Ilagan | 300602 | Sta. Isabel Nhs | Ilagan (Capital) | 1 |  | 10 | 2STY10CL | BATCH 5 CL | 14033441.11 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-05-03 | 2016-06-24 | 2016-07-07 | EGB CONSTRUCTION |  | NC 2016
K10 | REGION II | City Of Ilagan | 103437 | Sto. Tomas Es | Ilagan (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6607815.88 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-08 | 2016-06-21 | 2016-07-04 | 2016-07-15 | FOREF CONSTRUCTION |  | NC 2016
K10 | REGION II | City Of Ilagan | 103383 | Villa Imelda Ps | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES |  | NC 2016
SHS | REGION II | Isabela | 300521 | Alfreda Albano Nhs - Magassi, Cabagan | Cabagan | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 11378953.13 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-06-08 | 2016-06-24 | 2016-07-07 | EGB CONSTRUCTION |  | NC 2016
SHS | REGION II | Isabela | 300521 | Alfreda Albano Nhs - Magassi, Cabagan | Cabagan | 1 |  | 6 | 2STY6CL | BATCH 7 CL | 8592082.81 |  |  | Completed | 1 |  |  |  |  | 2016-05-27 | 2016-06-03 | 2016-06-17 | 2016-06-29 | 2016-07-11 | 4A'S CONSTRUCTION |  | NC 2016
TECHVOC | REGION II | Isabela | 300521 | Alfreda Albano Nhs - Magassi, Cabagan | Cabagan | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4860000 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-05-24 | 2016-06-02 | FRAGERR CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 306167 | Alfreda Albano Nhs-Masipi Annex | Cabagan | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6607815.88 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-08 | 2016-06-21 | 2016-07-04 | 2016-07-15 | FRAGERR CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 103265 | Aneg Elementary School | Delfin Albano (Magsaysay) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | M.C. TAGUBA CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 306133 | Aneg National High School | Delfin Albano (Magsaysay) | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2693142.91 |  |  | Completed | 1 |  |  |  |  | 2016-05-03 | 2016-05-10 | 2016-05-23 | 2016-06-24 | 2016-07-11 | M.C. TAGUBA CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 306162 | Bayabo Integrated School | Delfin Albano (Magsaysay) | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2693142.91 |  |  | Completed | 1 |  |  |  |  | 2016-05-03 | 2016-05-10 | 2016-05-23 | 2016-06-24 | 2016-07-11 | ATLANTIC CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 300605 | Buenaventura G. Masigan National High School | Santa Maria | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8592082.81 |  |  | Completed | 1 |  |  |  |  | 2016-05-27 | 2016-06-03 | 2016-06-17 | 2016-06-29 | 2016-07-11 | EDISON CONSTRUCTION AND DEVELOPMENT |  | NC 2016
TECHVOC | REGION II | Isabela | 300605 | Buenaventura G. Masigan National High School | Santa Maria | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 |  |  |  |  | 2016-03-29 | 2016-04-05 | 2016-04-18 | 2016-05-20 | 2016-05-31 | ATLANTIC CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 103844 | Buenavista Elementary School | Santa Maria | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2693142.91 |  |  | Completed | 1 |  |  |  |  | 2016-05-03 | 2016-05-10 | 2016-05-23 | 2016-06-24 | 2016-07-11 | EDISON CONSTRUCTION AND DEVELOPMENT |  | NC 2016
K10 | REGION II | Isabela | 306101 | Calanigan National High School | Santo Tomas | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8592082.81 |  |  | Completed | 1 |  |  |  |  | 2016-05-27 | 2016-06-03 | 2016-06-17 | 2016-06-29 | 2016-07-11 | RSKC CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 103267 | Capitol Elementary School | Delfin Albano (Magsaysay) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-05-03 | 2016-05-10 | 2016-05-23 | 2016-06-24 | 2016-07-11 | ATLANTIC CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 103268 | Carmencita Elementary School | Delfin Albano (Magsaysay) | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1032098.36 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-06-28 | 2016-07-11 | V.R.D.J. CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 306153 | Cumabao Integrated School | Tumauini | 1 | 1 | 16 | 2STY8CL | BATCH 7 CL | 22757906.26 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-06-08 | 2016-06-24 | 2016-07-07 | EGB CONSTRUCTION |  | NC 2016
TECHVOC | REGION II | Isabela | 306153 | Cumabao Integrated School | Tumauini | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 8442082.81 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-08 | 2016-06-21 | 2016-07-04 | 2016-07-15 | RSKC CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 155533 | Dalayya Elementary School | Tumauini | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1032098.36 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-06-28 | 2016-07-11 | SMT CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 300522 | Delfin Albano High School - San Juan Annex | Cabagan | 1 | 1 | 16 | 2STY8CL | BATCH 7 CL | 22757906.26 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-06-08 | 2016-06-24 | 2016-07-07 | EGB CONSTRUCTION |  | NC 2016
TECHVOC | REGION II | Isabela | 300522 | Delfin Albano High School - San Juan Annex | Cabagan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 |  |  |  |  | 2016-03-29 | 2016-04-05 | 2016-04-18 | 2016-05-20 | 2016-05-31 | V.R.D.J. CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 300520 | Delfin Albano High School-Main | Cabagan | 1 | 1 | 30 | 3STY15CL | BATCH 5 CL | 47012629.58 |  |  | Completed | 1 |  |  |  |  | 2016-05-27 | 2016-06-03 | 2016-06-17 | 2016-06-29 | 2016-07-11 | EGB CONSTRUCTION |  | NC 2016
TECHVOC | REGION II | Isabela | 300520 | Delfin Albano High School-Main | Cabagan | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 4860000 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-05-24 | 2016-06-02 | FRAGERR CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 306109 | Fermeldy National High School | Tumauini | 1 | 1 | 16 | 2STY8CL | BATCH 7 CL | 22757906.26 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-06-08 | 2016-06-24 | 2016-07-07 | EGB CONSTRUCTION |  | NC 2016
TECHVOC | REGION II | Isabela | 306109 | Fermeldy National High School | Tumauini | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 |  |  |  |  | 2016-03-29 | 2016-04-05 | 2016-04-18 | 2016-05-20 | 2016-05-31 | V.R.D.J. CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 103270 | Jimenez Multigrade School | Delfin Albano (Magsaysay) | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1032098.36 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-06-28 | 2016-07-11 | V.R.D.J. CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 300556 | Lalauanan National High School | Tumauini | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8592082.81 |  |  | Completed | 1 |  |  |  |  | 2016-05-27 | 2016-06-03 | 2016-06-17 | 2016-06-29 | 2016-07-11 | JMU CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 300551 | Lanna National High School | Tumauini | 1 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10897222.57 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 | 2016-06-16 | 2016-06-28 | 2016-07-08 | 2016-07-22 | E.S. PUA CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 155536 | Pallacot Elementary School | Tumauini | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1032098.36 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-06-28 | 2016-07-11 | SMT CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 300587 | Ragan Sur National High School | Delfin Albano (Magsaysay) | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8592082.81 |  |  | Completed | 1 |  |  |  |  | 2016-05-27 | 2016-06-03 | 2016-06-17 | 2016-06-29 | 2016-07-11 | EGB CONSTRUCTION |  | NC 2016
SHS | REGION II | Isabela | 300610 | Regional Science High School For Region Ii | Tumauini | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6607815.88 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-08 | 2016-06-21 | 2016-07-04 | 2016-07-15 | SMT CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 103273 | San Andres Elementary School | Delfin Albano (Magsaysay) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-05-03 | 2016-05-10 | 2016-05-23 | 2016-06-24 | 2016-07-11 | 969 CONSTRUCTION AND SUPPLIES |  | NC 2016
SHS | REGION II | Isabela | 300585 | San Antonio National High School | Delfin Albano (Magsaysay) | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 11378953.13 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-06-08 | 2016-06-24 | 2016-07-07 | F.A. ASPRER CONSTRUCTION |  | NC 2016
SHS | REGION II | Isabela | 300585 | San Antonio National High School | Delfin Albano (Magsaysay) | 1 |  | 6 | 2STY6CL | BATCH 7 CL | 8592082.81 |  |  | Completed | 1 |  |  |  |  | 2016-05-27 | 2016-06-03 | 2016-06-17 | 2016-06-29 | 2016-07-11 | ATLANTIC CONSTRUCTION |  | NC 2016
TECHVOC | REGION II | Isabela | 300585 | San Antonio National High School | Delfin Albano (Magsaysay) | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4860000 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-05-24 | 2016-06-02 | V.R.D.J. CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 103277 | San Macario Multigrade | Delfin Albano (Magsaysay) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-05-03 | 2016-05-10 | 2016-05-23 | 2016-06-24 | 2016-07-11 | 969 CONSTRUCTION AND SUPPLIES |  | NC 2016
SHS | REGION II | Isabela | 300597 | San Pablo National High School | San Pablo | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6607815.88 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-08 | 2016-06-21 | 2016-07-04 | 2016-07-15 | M.C. TAGUBA CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 103279 | San Ramon Elementary School | Delfin Albano (Magsaysay) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | ATLANTIC CONSTRUCTION |  | NC 2016
SHS | REGION II | Isabela | 300603 | Santa Maria High School | Santa Maria | 1 | 1 | 16 | 4STY16CL | BATCH 7 CL | 27944062.9 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-06-08 | 2016-06-24 | 2016-07-07 | EGB CONSTRUCTION |  | NC 2016
TECHVOC | REGION II | Isabela | 300603 | Santa Maria High School | Santa Maria | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 |  |  |  |  | 2016-03-29 | 2016-04-05 | 2016-04-18 | 2016-05-20 | 2016-05-31 | FRAGERR CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 103280 | Santor Primary School | Delfin Albano (Magsaysay) | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1032098.36 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-06-28 | 2016-07-11 | ATLANTIC CONSTRUCTION |  | NC 2016
SHS | REGION II | Isabela | 306132 | Simanu National High School | San Pablo | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6607815.88 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-08 | 2016-06-21 | 2016-07-04 | 2016-07-15 | FRAGERR CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 103810 | Simanu Sur Elementary School | San Pablo | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2693142.91 |  |  | Completed | 1 |  |  |  |  | 2016-05-03 | 2016-05-10 | 2016-05-23 | 2016-06-24 | 2016-07-11 | FRAGERR CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 300601 | St. Paul Vocational & Industrial High School | San Pablo | 1 | 1 | 18 | 3STY9CL | BATCH 7 CL | 31642774.42 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-06-08 | 2016-06-24 | 2016-07-07 | EGB CONSTRUCTION |  | NC 2016
TECHVOC | REGION II | Isabela | 300601 | St. Paul Vocational & Industrial High School | San Pablo | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4860000 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-05-24 | 2016-06-02 | ATLANTIC CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 300606 | Sto Tomas National High School | Santo Tomas | 1 | 1 | 18 | 3STY9CL | BATCH 7 CL | 31642774.42 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-06-08 | 2016-06-24 | 2016-07-07 | RSKC CONSTRUCTION/EDMARI CONSTRUCTION AND TRADING |  | NC 2016
TECHVOC | REGION II | Isabela | 300606 | Sto Tomas National High School | Santo Tomas | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 |  |  |  |  | 2016-03-29 | 2016-04-05 | 2016-04-18 | 2016-05-20 | 2016-05-31 | V.R.D.J. CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 300609 | Tumauini National High School | Tumauini | 1 | 1 | 24 | 3STY12CL | BATCH 5 CL | 39058990 |  |  | Completed | 1 |  |  |  |  | 2016-06-10 | 2016-06-17 | 2016-06-29 | 2016-07-13 | 2016-08-15 | EGB CONSTRUCTION |  | NC 2016
TECHVOC | REGION II | Isabela | 300609 | Tumauini National High School | Tumauini | 1 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 7290000 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-05-03 | 2016-05-20 | 2016-05-31 | FRAGERR CONSTRUCTION |  | NC 2016
K10 | REGION II | Isabela | 300593 | Alibadbad National High School | San Mariano | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10877342.59 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 103099 | Andabuen Elementary School - Annex | Benito Soliven | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1824740.17 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 300546 | Andabuen National High School | Benito Soliven | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6359337.64 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 103101 | Balliao Elementary School | Benito Soliven | 2 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2680828.12 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 306112 | Barucboc National High School | Quezon | 5 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 306112 | Barucboc National High School | Quezon | 5 |  | 8 | 2STY8CL | BATCH 7 CL | 10877342.59 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 300503 | Benito Soliven National High School | Benito Soliven | 2 |  | 4 | 1STY2CL | BATCH 3 CL | 3629480.34 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 300503 | Benito Soliven National High School | Benito Soliven | 2 | 1 | 10 | 2STY10CL | BATCH 3 CL | 12771310.09 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 306138 | Bimonton Integrated School | Mallig | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 155517 | Binogtungan Elementary School | Benito Soliven | 2 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1032049.65 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 306157 | Cabaruan Integrated School | Naguilian | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.06 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 300509 | Caliguian National High School-Main | Burgos | 5 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10877342.59 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 300512 | Callang National High School - Main | San Manuel | 5 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.06 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 155524 | Camarunggayan Es - Saranay Ps | Aurora | 5 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1012049.65 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 300519 | Del Pilar Integrated School | San Mariano | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27 |  |  |  |  | NC 2016
TECHVOC | REGION II | Isabela |  | Dona Aurora Senior High School | Aurora | 5 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 4756000 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
SHS | REGION II | Isabela |  | Dona Aurora Senior High School | Aurora | 5 | 1 | 45 | 3STY15CL | BATCH 5 CL | 64149040.35 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 306161 | Eden Integrated School | San Manuel | 5 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27 |  |  |  |  | NC 2016
TECHVOC | REGION II | Isabela | 300537 | Gamu Rural School-Main | Gamu | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 4756000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Isabela | 300537 | Gamu Rural School-Main | Gamu | 2 | 1 | 8 | 2STY8CL | BATCH 3 CL | 10877342.59 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Isabela | 300537 | Gamu Rural School-Main | Gamu | 2 |  | 10 | 2STY10CL | BATCH 3 CL | 12771310.09 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 103106 | Gomez Elementary School | Benito Soliven | 2 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2680828.12 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 103631 | Imbiao Elementary School | Roxas | 5 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2640828.12 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 300559 | Mabini National High School | Gamu | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.06 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 300513 | Malalinta National High School | San Manuel | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 300561 | Mallig National High School | Mallig | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 306166 | Mallig Nhs-Centro I Annex | Mallig | 5 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10877342.59 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 306166 | Mallig Nhs-Centro I Annex | Mallig | 5 |  | 1 | 1STY1CL | BATCH 7 CL | 1012049.65 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 306135 | Matusalem National High School | Roxas | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 306155 | Minagbag High School | Quezon | 5 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 306111 | Monico Rarama National High School | Roxas | 5 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.06 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 306111 | Monico Rarama National High School | Roxas | 5 |  | 1 | 1STY1CL | BATCH 7 CL | 1012049.65 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 300562 | Munoz High School | Roxas | 5 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.06 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 103113 | Nacalma Elementary School | Benito Soliven | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1864740.17 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 300563 | Naguillian National High School | Naguilian | 2 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12771310.09 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Isabela | 300563 | Naguillian National High School | Naguilian | 2 |  | 6 | 2STY6CL | BATCH 7 CL | 8214965.06 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 103116 | Punit Es | Benito Soliven | 2 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2640828.12 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 300568 | Quezon National High School | Quezon | 5 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12771310.09 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 300569 | Quirino National High School | Quirino | 5 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12771310.09 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 103134 | Raniag Elementary School | Burgos | 5 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1012049.65 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 155515 | Rizal Primary School | Gamu | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 300579 | Roxas National High School | Roxas | 5 | 1 | 32 | 4STY16CL | BATCH 3 CL | 53744938.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 300511 | San Antonino National High School | Burgos | 5 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12771310.09 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 300511 | San Antonino National High School | Burgos | 5 |  | 1 | 1STY1CL | BATCH 7 CL | 1012049.65 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 103118 | San Francisco Elementary School | Benito Soliven | 2 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1042049.65 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 306110 | San Jose National High School | Mallig | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 306165 | San Mariano Ii Central Integrated School | San Mariano | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 300592 | San Mariano National High School - Main | San Mariano | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11077342.59 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 300592 | San Mariano National High School - Main | San Mariano | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 300592 | San Mariano National High School - Main | San Mariano | 2 |  | 2 | 1STY2CL | BATCH 9 CL | 1814740.17 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 300514 | Sandiat National High School | San Manuel | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 103120 | Sevillana Elementary School | Benito Soliven | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 306163 | Simimbaan Integrated School | Roxas | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 306144 | Sto. Domingo Integrated School | Quirino | 5 | 1 | 4 | 1STY4CL | BATCH 7 CL | 3464886.58 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 103532 | Tomines Elementary School | Naguilian | 2 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1012049.65 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 103507 | Trinidad Elementary School | Mallig | 5 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1012049.65 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 155511 | Udiao Elementary School | San Mariano | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 306103 | Villa Cacho Integrated School | Quirino | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 103593 | Villa Miguel Primary School | Quirino | 5 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1012049.65 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 103767 | Villa Miranda Elementary School | San Mariano | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1874740.17 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 300500 | Alicia National High School | Alicia | 3 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31102890.27 |  |  | Completed | 1 | [5 empty] | 2016-06-15 | 2016-06-27 |  | 2016-06-29 | July 7,2016 |  | NC 2016
SHS | REGION II | Isabela | 300500 | Alicia National High School | Alicia | 3 |  | 6 | 2STY6CL | BATCH 3 CL | 8214965.05 |  |  | Completed | 1 | [5 empty] | 2016-03-16 | 2016-03-28 |  | 2016-05-10 | May 13,2016 |  | NC 2016
SHS | REGION II | Isabela | 300499 | Alicia Vocational School | Alicia | 3 | 1 | 15 | 3STY15CL | BATCH 7 CL | 21383013.45 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 300501 | Angadanan National High School | Angadanan | 3 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18222268.79 |  |  | Completed | 1 | [5 empty] | 2016-06-16 | 2016-06-28 |  | 2016-06-29 | July 7,2016 |  | NC 2016
K10 | REGION II | Isabela | 103769 | Bagong Sikat Es - Annex 1 | San Mateo | 3 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.174 |  |  | Completed | 1 | [5 empty] | 2016-03-16 | 2016-03-28 |  | 2016-05-10 | May 13,2016 |  | NC 2016
K10 | REGION II | Isabela | 103012 | Bonifacio Elementary School | Alicia | 3 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.174 |  |  | Completed | 1 | [5 empty] | 2016-03-16 | 2016-03-28 |  | 2016-05-10 | May 13,2016 |  | NC 2016
K10 | REGION II | Isabela | 103675 | Burgos West Elementary School | San Guillermo | 6 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1072049.6543 |  |  | Completed | 1 | [5 empty] | 2016-08-11 | 2016-08-23 |  | 2016-08-26 | August 29,2016 |  | NC 2016
K10 | REGION II | Isabela | 300504 | Cabatuan National High School | Cabatuan | 3 | 1 | 12 | 4STY12CL | BATCH 3 CL | 22152343.62 |  |  | Completed | 1 | [5 empty] | 2016-06-15 | 2016-07-15 |  | 2016-07-20 | July 27,2016 |  | NC 2016
K10 | REGION II | Isabela | 300504 | Cabatuan National High School | Cabatuan | 3 |  | 8 | 4STY8CL | BATCH 3 CL | 14897518.84 |  |  | Completed | 1 | [5 empty] | 2016-06-16 | 2016-06-29 |  | 2016-06-30 | July 8,2016 |  | NC 2016
TECHVOC | REGION II | Isabela | 300504 | Cabatuan National High School | Cabatuan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 300506 | Cadaloria High School | Angadanan | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 103029 | Calaocan Elementary School | Angadanan | 3 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1889740.174 |  |  | Completed | 1 | [5 empty] | 2016-03-16 | 2016-03-28 |  | 2016-05-10 | May 13,2016 |  | NC 2016
K10 | REGION II | Isabela | 103679 | Dingading Integrated School | San Guillermo | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1889740.174 |  |  | Completed | 1 | [5 empty] | 2016-03-16 | 2016-03-28 |  | 2016-05-10 | May 13,2016 |  | NC 2016
K10 | REGION II | Isabela | 306154 | Ingud-Ramona Integrated School | Angadanan | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 | [5 empty] | 2016-06-15 | 2016-06-27 |  | 2016-06-29 | July 7,2016 |  | NC 2016
SHS | REGION II | Isabela | 306114 | La Paz National High School | Cabatuan | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 306150 | Luna General Comprehensive High School | Luna | 5 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10877342.5917 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Isabela | 300558 | Luna National High School | Luna | 5 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [5 empty] | 2016-06-15 | 2016-06-27 |  | 2016-06-29 | July 7,2016 |  | NC 2016
SHS | REGION II | Isabela | 300558 | Luna National High School | Luna | 5 |  | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [5 empty] | 2016-06-15 | 2016-06-27 |  | 2016-06-29 | July 7,2016 |  | NC 2016
TECHVOC | REGION II | Isabela | 300558 | Luna National High School | Luna | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2418000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 102993 | Mataas Na Kahoy Elementary School | Alicia | 3 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1012049.6543 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 300565 | Palayan Region High School | Alicia | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Isabela | 300575 | Reina Mercedes Vocational And Industrial School | Reina Mercedes | 3 | 1 | 32 | 4STY32CL | BATCH 5 CL | 44532220.04 |  |  | Completed | 1 | [5 empty] | 2016-06-16 | 2016-06-29 |  | 2016-06-30 | July 8,2016 |  | NC 2016
TECHVOC | REGION II | Isabela | 300575 | Reina Mercedes Vocational And Industrial School | Reina Mercedes | 3 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 4756000 |  |  | Completed | 1 | [5 empty] | 2016-03-16 | 2016-03-28 |  | 2016-05-10 | May 13,2016 |  | NC 2016
SHS | REGION II | Isabela | 306116 | Reina Mercedes Vocational High School | Reina Mercedes | 3 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10877342.5917 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION II | Isabela | 306116 | Reina Mercedes Vocational High School | Reina Mercedes | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2418000 |  |  | Completed | 1 | [5 empty] | 2016-06-15 | 2016-06-27 |  | 2016-06-29 | July 7,2016 |  | NC 2016
SHS | REGION II | Isabela | 300577 | Rizal Integrated School, San Guillermo | San Guillermo | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6469337.6381 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 300576 | Rizal Region National High School | Alicia | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 300581 | Salinungan National High School | San Mateo | 3 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 300590 | San Guillermo Vocational & Industrial High School | San Guillermo | 6 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22252343.62 |  |  | Completed | 1 | [5 empty] | 2016-06-15 | 2016-06-27 |  | 2016-06-29 | July 7,2016 |  | NC 2016
TECHVOC | REGION II | Isabela | 300590 | San Guillermo Vocational & Industrial High School | San Guillermo | 6 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4896000 |  |  | Completed | 1 | [5 empty] | 2016-03-16 | 2016-03-28 |  | 2016-05-10 | May 13,2016 |  | NC 2016
K10 | REGION II | Isabela | 103002 | San Juan Elementary School | Alicia | 3 | 1 | 4 | 1STY4CL | BATCH 7 CL | 3464886.575 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 300596 | San Mateo Vocational And Industrial High School | San Mateo | 3 | 1 | 28 | 4STY28CL | BATCH 9 CL | 40067946.14 |  |  | Completed | 1 | [5 empty] | 2016-06-16 | 2016-06-29 |  | 2016-06-30 | July 8,2016 |  | NC 2016
K10 | REGION II | Isabela | 300596 | San Mateo Vocational And Industrial High School | San Mateo | 3 |  | 8 | 2STY8CL | BATCH 9 CL | 10877342.59 |  |  | Completed | 1 | [5 empty] | 2016-06-15 | 2016-06-27 |  | 2016-06-29 | July 7,2016 |  | NC 2016
TECHVOC | REGION II | Isabela | 300596 | San Mateo Vocational And Industrial High School | San Mateo | 3 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4350600 |  |  | Completed | 1 | [5 empty] | 2016-06-15 | 2016-06-27 |  | 2016-06-29 | July 7,2016 |  | NC 2016
SHS | REGION II | Isabela | 300607 | Sto. Niño Integrated School | Angadanan | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.051 |  |  | Completed | 1 | [5 empty] | 2016-03-16 | 2016-03-28 |  | 2016-05-10 | May 13,2016 |  | NC 2016
K10 | REGION II | Isabela | 103695 | Villa Remedios Primary School | San Guillermo | 6 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1062049.6543 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Isabela | 103283 | Aromin Elementary School | Echague | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.174 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 103441 | Bantay Primary School | Jones | 4 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1012049.6543 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 306143 | Cagasat Hs-Magsasay Annex | Cordon | 4 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.051 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-09 | 2016-06-23 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 300518 | Dabubu High School - Main | San Agustin | 4 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.174 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 306168 | Dabubu Hs-Annex | San Agustin | 4 | 1 | 4 | 1STY4CL | BATCH 7 CL | 3614886.575 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 300523 | Diadi Region High School | Cordon | 4 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.051 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-09 | 2016-06-23 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 300524 | Dibuluan National High School | Jones | 4 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 300529 | Don Mariano Marcos National High School | Echague | 6 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.051 |  |  | Completed | 1 |  |  |  |  | 2016-06-14 | 2016-06-22 | 2016-07-05 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 300532 | Dona Josefa E. Marcos High School | Cordon | 4 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.051 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-09 | 2016-06-23 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 300533 | Dona Magdalena H. Gaffud High School | Echague | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 300612 | Echague National High School | Echague | 6 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.051 |  |  | Completed | 1 |  |  |  |  | 2016-07-20 | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 300572 | Gen. Emilio Aguinaldo National High School | Ramon | 4 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 300539 | Highway Region National High School | Echague | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 300541 | Imelda R. Marcos High School | Echague | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 300555 | Jones Rural School - Main | Jones | 4 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10877342.5917 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-09 | 2016-06-23 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 300555 | Jones Rural School - Main | Jones | 4 |  | 6 | 2STY6CL | BATCH 7 CL | 8214965.051 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-09 | 2016-06-23 |  |  |  |  | NC 2016
TECHVOC | REGION II | Isabela | 300555 | Jones Rural School - Main | Jones | 4 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4836000 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-09 | 2016-06-23 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 103448 | Linomot Elementary School | Jones | 4 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1864740.174 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 103660 | Palacian Elementary School | San Agustin | 4 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1864740.174 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 300566 | Pangal Sur High School | Echague | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 300571 | Ramon National High School | Ramon | 4 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.051 |  |  | Completed | 1 |  |  |  |  | 2016-07-20 | 2016-07-28 | [5 empty] | NC 2016
K10 | REGION II | Isabela | 300574 | Raniag High School | Ramon | 4 |  | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-09 | 2016-06-23 |  |  |  |  | NC 2016
TECHVOC | REGION II | Isabela | 300574 | Raniag High School | Ramon | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2418000 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-09 | 2016-06-23 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 300574 | Raniag High School | Ramon | 4 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-09 | 2016-06-23 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 103299 | Salvacion Elementary School | Echague | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.174 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 300582 | San Agustin National High School | San Agustin | 4 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-09 | 2016-06-23 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 103319 | San Felipe Elementary School | Echague | 6 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2640828.124 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14 |  |  |  |  | NC 2016
TECHVOC | REGION II | Isabela | 300591 | San Isidro National High School | San Isidro | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2175300 |  |  | Completed | 1 |  |  |  |  | 2016-07-20 | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 300591 | San Isidro National High School | San Isidro | 6 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21383013.45 |  |  | Completed | 1 |  |  |  |  | 2016-07-20 | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 300591 | San Isidro National High School | San Isidro | 6 |  | 8 | 2STY8CL | BATCH 9 CL | 10877342.59 |  |  | Completed | 1 |  |  |  |  | 2016-07-20 | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 306159 | San Miguel Integrated School | Ramon | 4 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-07-20 | 2016-07-28 | 2016-08-09 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 306142 | San Sebastian Integrated School | Ramon | 4 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 300600 | Sgt. Prospero Bello Hs - Main | Jones | 4 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 103456 | Sto. Domingo Es - Annex (Lsb) | Jones | 4 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1112049.6543 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14 |  |  |  |  | NC 2016
K10 | REGION II | Isabela | 300611 | Ugad High School | Echague | 6 | 1 | 18 | 3STY9CL | BATCH 9 CL | 30322655.84 |  |  | Completed | 1 |  |  |  |  | 2016-07-27 | 2016-08-05 | 2016-08-18 |  |  |  |  | NC 2016
TECHVOC | REGION II | Isabela | 300611 | Ugad High School | Echague | 6 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 7094000 |  |  | Completed | 1 |  |  |  |  | 2016-07-27 | 2016-08-05 | 2016-08-18 |  |  |  |  | NC 2016
SHS | REGION II | Isabela | 306128 | Wigan Integrated School | Cordon | 4 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.051 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-09 | 2016-06-23 |  |  |  |  | NC 2016
K10 | REGION II | Nueva Vizcaya | 300618 | Aritao Nhs | Aritao | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16768460.712 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Nueva Vizcaya | 300618 | Aritao Nhs | Aritao | 0 |  | 6 | 3STY6CL | BATCH 9 CL | 11543844.661 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Nueva Vizcaya | 300620 | Bambang Nhs | Bambang | 0 | 1 | 32 | 4STY16CL | BATCH 9 CL | 58715432.724 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Nueva Vizcaya | 300621 | Bascaran Nhs | Solano | 0 | 1 | 8 | 4STY8CL | BATCH 7 CL | 16074268.83 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Nueva Vizcaya | 300623 | Bintawan Nhs | Villaverde | 0 | 1 | 12 | 4STY12CL | BATCH 7 CL | 21201319.95 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Nueva Vizcaya | 306202 | Bonfal National High School | Bayombong (Capital) | 0 | 1 | 8 | 4STY8CL | BATCH 7 CL | 16074268.83 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Nueva Vizcaya | 300626 | Casat Nhs | Bayombong (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1872266.47 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Nueva Vizcaya | 306203 | Dippog National High School | Quezon | 0 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6619337.64 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Nueva Vizcaya | 300640 | Napo-Tuyak Integrated School | Kayapa | 0 | 1 | 4 | 2STY4CL | BATCH 7 CL | 5975000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Nueva Vizcaya | 300641 | Nueva Vizcaya Gen. Chs | Bayombong (Capital) | 0 | 1 | 36 | 4STY12CL | BATCH 9 CL | 73057733.946 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Nueva Vizcaya | 300645 | Salinas High School | Bambang | 0 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6529337.64 |  |  | Reverted | 0 | [11 empty] | NC 2016
SHS | REGION II | Nueva Vizcaya | 300647 | Sta. Clara Hs | Aritao | 0 | 1 | 8 | 2STY8CL | BATCH 7 CL | 11083000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Nueva Vizcaya | 300651 | Uddiawan Nhs | Solano | 0 | 1 | 8 | 2STY4CL | BATCH 7 CL | 13038675.28 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Nueva Vizcaya | 300646 | Solano High School | Solano | 2 | 1 | 16 | 4STY8CL | BATCH 9 CL | 29795037.68 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Quirino | 300657 | Diffun Hs | Diffun | 0 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1 | [8 empty] | 2016-09-06 | PHESCO INCORPORATED |  | NC 2016
SHS | REGION II | Quirino | 300657 | Diffun Hs | Diffun | 0 |  | 8 | 4STY8CL | BATCH 9 CL | 16372270.724 |  |  | Completed | 1 | [9 empty] | NTL BUILDERS & DEVELOPERS |  | NC 2016
SHS | REGION II | Quirino | 300657 | Diffun Hs | Diffun | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 16618460.712 |  |  | Completed | 1 | [8 empty] | 2016-08-09 | NTL BUILDERS & DEVELOPERS |  | NC 2016
TECHVOC | REGION II | Quirino | 300657 | Diffun Hs | Diffun | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1 | [8 empty] | 2016-08-01 | NC CONSTRUCTION |  | NC 2016
SHS | REGION II | Quirino | 300660 | Maddela Chs | Maddela | 0 | 1 | 15 | 3STY15CL | BATCH 9 CL | 23506314.795 |  |  | Completed | 1 | [8 empty] | 2016-09-06 | PHESCO INCORPORATED |  | NC 2016
SHS | REGION II | Quirino | 300660 | Maddela Chs | Maddela | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 16618460.712 |  |  | Completed | 1 | [8 empty] | 2016-08-01 | NTL BUILDERS & DEVELOPERS |  | NC 2016
TECHVOC | REGION II | Quirino | 300660 | Maddela Chs | Maddela | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4350600 |  |  | Completed | 1 | [8 empty] | 2016-08-04 | JMD-68 BUILDERS |  | NC 2016
SHS | REGION II | Quirino | 300664 | Quirino General Hs | Cabarroguis (Capital) | 0 | 1 | 15 | 3STY15CL | BATCH 9 CL | 23506314.795 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Quirino | 300664 | Quirino General Hs | Cabarroguis (Capital) | 0 |  | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION II | Quirino | 300664 | Quirino General Hs | Cabarroguis (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1 | [8 empty] | 2016-08-04 | JMD-68 BUILDERS |  | NC 2016
SHS | REGION II | Quirino | 300665 | Saguday Nhs | Saguday | 0 | 1 | 16 | 4STY16CL | BATCH 9 CL | 29357716.362 |  |  | Completed | 1 | [8 empty] | 2016-08-01 | PHESCO INCORPORATED |  | NC 2016
SHS | REGION II | Quirino | 300665 | Saguday Nhs | Saguday | 0 |  | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 | [8 empty] | 2016-08-04 | JMD-68 BUILDERS |  | NC 2016
SHS | REGION II | Santiago City | 300599 | Santiago City National High School | City Of Santiago | 4 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Santiago City | 300599 | Santiago City National High School | City Of Santiago | 4 |  | 15 | 3STY15CL | BATCH 9 CL | 23037143.68 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Tuguegarao City | 300668 | Cagayan National High Sschool | Tuguegarao City(Capital) | 3 | 1 | 48 | 4STY16CL | BATCH 9 CL | 80850000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Tuguegarao City | 300668 | Cagayan National High Sschool | Tuguegarao City(Capital) | 3 |  | 8 | 4STY8CL | BATCH 9 CL | 13550000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Tuguegarao City | 300671 | Gosi National High School | Tuguegarao City(Capital) | 3 | 1 | 18 | 3STY9CL | BATCH 7 CL | 32844720 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | Tuguegarao City | 306401 | Tuguegarao City Science High School | Tuguegarao City(Capital) | 3 | 1 | 10 | 2STY10CL | BATCH 7 CL | 13225000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Tuguegarao City | 104400 | Tuguegarao North Cs | Tuguegarao City(Capital) | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6411500 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION II | Tuguegarao City | 104406 | Tuguegarao West Cs | Tuguegarao City(Capital) | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6411500 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION II | CAGAYAN | 300482 | Rebecca NHS | GONZAGA | 1 |  | 6 | 2 UNITS OF 1STY3CL | BATCH 14 | 9000000 |  |  | Completed | 1 | [11 empty] | NC 2017
SHS | REGION II | CAGAYAN | 306002 | Baggao NAS - Sta. Margarita Annex | BAGGAO | 1 |  | 6 | 2 UNITS OF 1STY3CL | BATCH 14 | 9000000 |  |  | Completed | 1 | [11 empty] | NC 2017

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.