## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
SCHOOL HEALTH FACILITIES 2024 | Region III | Balanga City | 502343 | Tanato Integrated School | CITY OF BALANGA (Capital) | 2nd | 1 |  | Construction of School Clinic | 3371042.12 |  | 2612069.69 | completed | 1 | December 25, 2024 | October 11, 2024 | CB-EPA-2023-003 | CB-EPA-2023-004 | November 29, 2023 | December 7, 2023 | December 19, 2023 | July 18, 2024 | August 12, 2024 | R.Z. TIGAS CONSTRUCTION AND SUPPLY | Completed
SCHOOL HEALTH FACILITIES 2024 | Region III | Bataan | 104534 | Kabukiran ES | ABUCAY | 1st | 1 |  | Construction of School Clinic | 3417948.14 |  | 2426684.86 | completed | 1 | August 28, 2024 | August 28, 2024 | School Clinic 2024-Region III-Bataan-003 | CON24-001 | October 25, 2023 to November 21, 2023 | November 7, 2023 | November 21, 2023 | December 13, 2023 | May 29, 2024 | Rodmac Construction & Trading | completed
SCHOOL HEALTH FACILITIES 2024 | Region III | Bataan | 104534 | Kabukiran ES | ABUCAY | 1st |  |  | Construction of Group Handwashing | 483964.6 |  | 365876.45 | completed | 1 | July 29, 2024 | July 29, 2024 | WINS 2024-Region III-Bataan-004 | CON24-002 | October 25, 2023 to November 21, 2023 | November 7, 2023 | November 21, 2023 | December 13, 2023 | May 29, 2024 | AR-ESBI Construction | completed
SCHOOL HEALTH FACILITIES 2024 | Region III | Bataan | 104534 | Kabukiran ES | ABUCAY | 1st |  |  | Construction of Toilets | 813890.87 |  | 614266.62 | completed | 1 | July 29, 2024 | July 29, 2024 | WATSAN 2024-Region III-Bataan-001 | CON24-003 | October 25, 2023 to November 21, 2023 | November 7, 2023 | November 21, 2023 | December 13, 2023 | May 29, 2024 | AR-ESBI Construction | completed
SCHOOL HEALTH FACILITIES 2024 | Region III | Bulacan | 104836 | Hagonoy Cs | HAGONOY | 1st | 1 |  | Construction of School Clinic | 2746771.01 |  | 2167776.11 | completed | 1 | October 10, 2024 | October 10, 2024 | PB-24-005 | PB-24-05-010 | December 5, 2023 | 12/14/2023 | 12/27/2023 | January 8, 2024 | June 5, 2024 | JFM ALTITUDE CONSTRUCTION CORP.
SCHOOL HEALTH FACILITIES 2024 | Region III | Gapan City | 105314 | Bagong Silang ES | CITY OF GAPAN | 4th | 1 |  | Construction of handwashing facilities | 325467.63 |  | 320478.6 | Completed | 1 | June 19, 2024 | June 13, 2024 | RFQ2024-009 | RFQ2024-009 | August 6, 2024 |  | April 12, 2024 | April 12, 2024 | May 29, 2024 | JOYNIELTIN CONSTRUCTION AND TRADING | completed
SCHOOL HEALTH FACILITIES 2024 | Region III | Mabalacat City | 106066 | Mabalacat ES | MABALACAT CITY | 1st | 1 |  | Construction of School Clinic | 3598832.44 |  | 3577749.05 | Completed | 1 | August 15, 2024 | August 15, 2024 | PB-2023-12-005 | SBC-2024-04-005 | December 4, 2023 | 12/14/2023 | December 26, 2023 | December 29, 2023 | May 17, 2024 | T.G Ocampo Construction and Surveying Services
SCHOOL HEALTH FACILITIES 2024 | Region III | Meycauayan City | 500439 | Bancal Integrated School | CITY OF MEYCAUAYAN | 4th | 1 |  | 2 units - Handwashing facility Option 1:Variant B | 600000 |  | 488546.2 | completed | 1 | October 10, 2024 | October 7, 2024 | 2023-001-INFRA | 2023-001-INFRA | November 21, 2023 | November 29, 2023 | December 12, 2023 | May 5, 2024 | May 10, 2024 | Emica Builders and Supply
SCHOOL HEALTH FACILITIES 2024 | Region III | Meycauayan City | 500439 | Bancal Integrated School | CITY OF MEYCAUAYAN | 4th |  |  | 2 units - Four seater toilet detached | 1600000 |  | 1348896.3 | completed | 1 | October 10, 2024 | October 7, 2024 | 2023-001-INFRA | 2023-001-INFRA | November 21, 2023 | November 29, 2023 | December 12, 2023 | May 5, 2024 | May 10, 2024 | Emica Builders and Supply
SCHOOL HEALTH FACILITIES 2024 | Region III | Olongapo City | 107126 | Gordon Heights I Elementary School | OLONGAPO CITY | 1st | 1 |  | Construction of School Clinic | 3442212.05 |  | 3436165.64 | completed | 1 | April 25, 2025 | April 16, 2025 | 2024-06-207 | 2024-06-207 | July 3, 2024 | July 10, 2024 | July 22, 2024 | August 1, 2024 | December 26, 2024 | JFM Altitude | completed
SCHOOL HEALTH FACILITIES 2024 | Region III | Olongapo City | 107139 | Kalalake ES | OLONGAPO CITY | 1st | 1 |  | Construction of School Clinic | 3500000 |  | 3422255.63 | completed | 1 | April 25, 2025 | April 21, 2025 | 2024-06-207 | 2024-06-207 | July 3, 2024 | July 10, 2024 | July 22, 2024 | August 1, 2024 | December 26, 2024 | J.I. Viacrusis Construction | completed
SCHOOL HEALTH FACILITIES 2024 | Region III | Pampanga | 106298 | Moras Dela Paz ES | SANTO TOMAS | 4th | 1 |  | Construction of School Clinic | 3534027.65 |  | 3517524.14 | completed | 1 | August 28, 2024 | August 28, 2024 | I-2024-001 | I-2024-001 | November 16, 2023 | November 24, 2023 | December 6, 2023 | May 8, 2024 | May 13, 2024 | BFF CONSTRUCTION
SCHOOL HEALTH FACILITIES 2024 | Region III | San Fernando City | 301064 | Pampanga High School | CITY OF SAN FERNANDO (Capital) | 3rd | 1 |  | Construction of School Clinic | 3534027.65 |  | 3527033.97 | COMPLETED | 1 | September 3, 2024 | September 2, 2024 |  | Infrastructure 2024-001 | December 1, 2023 | December 11, 2023 | December 27, 2023 | January 15, 2024 | May 22, 2024 | BFF CONSTRUCTION
SCHOOL HEALTH FACILITIES 2024 | Region III | Tarlac City | 106705 | San Manuel ES | CITY OF TARLAC (Capital) | 2nd | 1 |  | Construction of School Clinic | 3371042.12 |  | 2619888.88 | COMPLETED | 1 | September 25, 2024 | September 25, 2024 | TCSD-IP-01-2024 | TCSD-IP-01-L1 | November 21, 2023 | November 28, 2023 | December 11, 2023 | December 13, 2023 | May 27, 2024 | JFM ALTITUDE CONSTRUCTION CORP. | NONE
SCHOOL HEALTH FACILITIES 2024 | Region III | Tarlac City | 106705 | San Manuel ES | CITY OF TARLAC (Capital) | 2nd |  |  | Construction of 2 - unit Group Hand Washing Facility - 10 faucets - for Elementary | 568209.5 |  | 469888.88 | Completed | 1 | June 26, 2024 | June 26, 2024 | TCSD-IP-01-2024 | TCSD-IP-01-L2 | November 21, 2023 | November 28, 2023 | December 11, 2023 | December 13, 2023 | May 27, 2024 | JFM ALTITUDE CONSTRUCTION CORP. | NONE
SCHOOL HEALTH FACILITIES 2024 | Region III | Zambales | 305574 | Bamban National High School | MASINLOC | 2nd | 1 |  | Construction of School Clinic | 3664744.58 |  | 3153468.2 | completed | 1 | September 16, 2024 | September 16, 2024 | Infra-2024-001 | Infra-2024-003 | November 23, 2023 | November 29, 2023 | December 11, 2023 | December 18, 2023 | June 7, 2024 | KAEE Construction Services
SCHOOL HEALTH FACILITIES 2022 | Region III | Nueva Ecija | 105566 | Alzate Village ES | NAMPICUAN | 1 | 1 | 1 | PROPOSED REPAIR OF COMFORT ROOM WITH HAND WASHING | 201576.41 | BATCH 1 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region III | Nueva Ecija | 105568 | Maeling Elementary School | NAMPICUAN | 1 | 1 | 1 | PROPOSED REPAIR OF COMFORT ROOM WITH HAND WASHING | 201576.41 | BATCH 1 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region III | Nueva Ecija | 105572 | Nampicuan Central School | NAMPICUAN | 1 | 1 | 1 | PROPOSED REPAIR OF COMFORT ROOM WITH HAND WASHING | 201576.41 | BATCH 1 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region III | Nueva Ecija | 105573 | Recuerdo ES | NAMPICUAN | 1 | 1 | 1 | PROPOSED REPAIR OF COMFORT ROOM WITH HAND WASHING | 201576.41 | BATCH 1 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region III | Mabalacat City | 106061 | Atlu Bola ES | MABALACAT CITY | 2 | 1 | 4 | REPAIR OF COMFORT ROOMS | 310000 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region III | Mabalacat City | 106087 | Sapang Biabas ES | MABALACAT CITY | 2 | 1 | 6 | REPAIR OF COMFORT ROOMS | 395000 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region III | Mabalacat City | 159535 | Northville 16 ES | MABALACAT CITY | 2 | 1 | 10 | REPAIR OF COMFORT ROOMS | 970000 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region III | Mabalacat City | 306916 | Mabalacat Comm. HS | MABALACAT CITY | 2 | 1 | 10 | REPAIR OF COMFORT ROOMS | 733000 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region III | Mabalacat City | 306941 | Dr. Adelaido C. Bernardo HS | MABALACAT CITY | 2 | 1 | 2 | REPAIR OF 2 CR PLUS 1 UNIT SEPTIC VAULT | 265000 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region III | Mabalacat City | 500631 | Dona Asuncion Lee IS | MABALACAT CITY | 2 | 1 | 8 | REPAIR OF 8 COMFORT ROOMS OF THE 4STY BUILDING | 685900 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region III | Tarlac | 106305 | Dolores Ongsiako CES | ANAO | 2 | 1 | 1 | Construction of group handwashingfacility-for elementary(option 1A with roofing,with counter with tile finish) | 240000 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region III | Tarlac | 106306 | Bantog ES | ANAO | 2 | 1 | 1 | Construction of group handwashingfacility-for elementary(option 1A with roofing,with counter with tile finish) | 240000 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region III | Tarlac | 106608 | Guiteb ES | RAMOS | 2 | 1 | 1 | Construction of group handwashingfacility-for elementary(option 1A with roofing,with counter with tile finish) | 240000 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region III | Tarlac | 106612 | San Raymundo ES | RAMOS | 2 | 1 | 1 | Construction of group handwashingfacility-for elementary(option 1A with roofing,with counter with tile finish) | 240000 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region III | Tarlac | 106614 | Toledo ES | RAMOS | 2 | 1 | 1 | Construction of group handwashingfacility-for elementary(option 1A with roofing,with counter with tile finish) | 240000 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region III | Tarlac | 106620 | Doclong 2nd Elementary School | SAN CLEMENTE | 2 | 1 | 1 | Construction of group handwashingfacility-for elementary(option 1A with roofing,with counter with tile finish) | 240000 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region III | Tarlac | 106624 | Pit-Ao ES | SAN CLEMENTE | 2 | 1 | 1 | Construction of group handwashingfacility-for elementary(option 1A with roofing,with counter with tile finish) | 240000 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region III | Tarlac | 160006 | Don Cesar Abad Gualberto MGS | SAN CLEMENTE | 2 | 1 | 1 | Construction of group handwashingfacility-for elementary(option 1A with roofing,with counter with tile finish) | 240000 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region III | Tarlac | 501609 | San Clemente Integrated School | SAN CLEMENTE | 2 | 1 | 1 | Construction of group handwashingfacility-for elementary(option 1A with roofing,with counter with tile finish) | 240000 | BATCH 2 |  | COMPLETED | 1

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%