## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | NO. OF CL | SCOPE OF WORK | PROJECT ALLOCATION | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
LMS 2020 | Region IV-A | Quezon | 108792 | Miyunod ES | INFANTA | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18842695.7125 | 18830000 | completed | 1 | 2021-11-25 | 00:00:00 | 0 | 2021-60 | July 2-21, 2021 | 2021-07-09 | 2021-07-21 | 2021-07-23 | 2021-07-28 | BOTEY CONSTRUCTION | 0
LMS 2020 | Region IV-A | Quezon | 109039 | Pag-itan E/S | PANUKULAN | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM (for 4CL), AND WATER SYSTEM (for 4CL) | 21194223.6405 | 21163075.84 | completed | 1 | 2021-11-25 | 00:00:00 | 0 | 2021-61 | July 2-21, 2021 | 2021-07-09 | 2021-07-21 | 2021-07-23 | 2021-07-28 | N.T SOTELO CONSTRUCTION & SUPPLY CORPORATION | 0
LMS 2020 | Region IV-A | Quezon | 109039 | Pag-itan E/S | PANUKULAN | 1 |  | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE |  | 21163075.84 | completed | 1 | 2021-11-25 | 00:00:00 | 0 | 2021-61 | July 2-21, 2021 | 2021-07-09 | 2021-07-21 | 2021-07-23 | 2021-07-28 | N.T SOTELO CONSTRUCTION & SUPPLY CORPORATION | 0
LMS 2020 | Region IV-A | Quezon | 109088 | Alibahaban ES (Alibihaban ES) | SAN ANDRES | 3 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15610253.566 | 15590167 | completed | 1 | 2021-11-25 | 00:00:00 | 0 | 2021-62 | July 2-21, 2021 | 2021-07-09 | 2021-07-21 | 2021-07-23 | 2021-07-28 | M.G VILLAMIN CONSTRUCTION | 0
LMS 2020 | Region IV-A | Quezon | 108830 | Villaminda ES | LOPEZ | 4 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15080003.5679 | 15059979 | completed | 1 | 2021-11-25 | 00:00:00 | 0 | 2021-63 | July 2-21, 2021 | 2021-07-09 | 2021-07-21 | 2021-07-23 | 2021-07-28 | M.G VILLAMIN CONSTRUCTION | 0
LMS 2020 | Region IV-A | Rizal | 109468 | San Rafael ES - Inigan ES | RODRIGUEZ (MONTALBAN) | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15419235.0738 | 15110797.65 | completed | 1 | 00:00:00 | 00:00:00 | INFRA-2021-002 | INFRA-2021-002 | July 19, 2021 | July 27, 2021 | August 9, 2021 | Setpember 1, 2021 | Setpember 14, 2021 | A. Suelila Constructiomn | 0
LMS 2021 | Region IV-A | Laguna | 108465 | Pulong Mindanao ES | SANTA MARIA | 4 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CL SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 15744764.7134 |  | Terminated | 0 | [10 empty] | Contract Terminated
LMS 2021 | Region IV-A | Quezon | 108739 | Ligpit Bantayan ES | GUINAYANGAN | 4 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17714094.3688 | 0 | Ongoing | 0.34 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | based on the spot checking report made last November by LMS team (Audit); pls see narrative reports
LMS 2021 | Region IV-A | Rizal | 109518 | Rawang ES | TANAY | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM (for 4CL), AND WATER SYSTEM (for 4CL) | 15006078.5261 | 0 | Terminated | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | Contract Terminated
LMS 2021 | Region IV-A | Rizal | 109518 | Rawang ES | TANAY | 2 |  | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE | 6267959.3241 | 0 | Terminated | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | Contract Terminated
LMS 2021 | Region IV-A | Tayabas City | 109241 | Pandakake ES | CITY OF TAYABAS | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18110071.5632 | 0 | Completed | 1 | 00:00:00 | December 7 2023 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | WERR | 0
LMS 2022 | Region IV-A | Batangas | 107208 | Coral na Munti ES | Agoncillo | 3 | 1 | 4 | CONSTRUCTION OF TWO UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 23885332.0158 | 23500000 | COMPLETED | 1 | 2023-04-11 | 2023-06-16 | AGONCILLO LMS 2022 - RIVA - BATANGAS - 01 | CY 2022 BEFF | 2022-06-22 | 2022-06-29 | 2022-07-11 | 2022-08-02 | 2022-10-04 | Botey Construction | Certificate of Time Extension was granted to the contractor for 30days, with Liquidated damages
LMS 2023 | Region IV-A | Batangas | 107816 | San Pedro Elementary School | TINGLOY | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17638031.48 | 17402609.51 | Completed | 1 | 2024-04-23 | 2024-08-30 | LMS 2022 - IVA - BATANGAS - 001 | LMS 2023 - IVA - BATANGAS - 001 | 2023-10-20 | 2023-10-26 | 2023-11-06 | 2023-12-20 | 2023-12-29 | Marakesh Enterprise | Certificate of Time Extension was granted to the contractor
LMS 2023 | Region IV-A | Batangas | 107663 | Hipit Elementary School | SAN NICOLAS | 3 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16047281.48 | 15802341.11 | Completed | 1 | 2024-04-23 | 2024-08-30 | LMS 2023 - IVA - BATANGAS - 002 | LMS 2023 - IVA - BATANGAS - 002 | 2023-10-20 | 2023-10-26 | 2023-11-06 | 2023-12-20 | 2023-12-29 | Marakesh Enterprise | Certificate of Time Extension was granted to the contractor
LMS 2023 | Region IV-A | Quezon | 501326 | Luod Integrated School | PATNANUNGAN | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 25802288.87 | 25530000 | Completed | 1 | 2024-02-04 | 2024-05-04 | 2023-048-INFRA | 2023-048-INFRA | 2023-07-19 | 2023-06-02 | 2023-06-14 | 2023-06-22 | 2023-07-12 | C.G. Cabana Construction and Supply | 0
LMS 2023 | Region IV-A | Quezon | 109052 | Del Pilar Elementary School | QUEZON | 4 | 1 | 2 | CONSTRUCTION OF ONE (1) UNIT - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16555387.23 | 16375912.86 | Completed | 1 | 2024-02-04 | 2024-02-28 | 2023-048-INFRA | 2023-048-INFRA | 2023-07-19 | 2023-06-02 | 2023-06-14 | 2023-06-22 | 2023-07-12 | Quezon Achievers | 0
LMS 2023 | Region IV-A | Quezon | 109059 | Sabang ES | QUEZON | 4 | 1 | 2 | CONSTRUCTION OF ONE (1) UNIT - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL | 18146137.23 | 17930000 | Completed | 1 | 2024-02-04 | 2023-11-13 | 2023-048-INFRA | 2023-048-INFRA | 2023-07-19 | 2023-06-02 | 2023-06-14 | 2023-06-22 | 2023-07-12 | Botey Construction | 0
LMS 2023 | Region IV-A | Tanauan City | 107764 | Mahabang Buhangin ES | CITY OF TANAUAN | 3 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF, SCHOOL FURNITURE, PERIMETER FENCE 150.0m FRONTAGE (1 BAY = 3.0m), RAIN WATER COLLECTOR TWO (1) SETS AND PROVISION OF SOLAR PANEL | 17360252.16 | 17138185.47 | Ongoing | 0.65 | 2025-06-17 |  | LMS 2024 TANAUAN-001 | LMS 2024 TANAUAN-001 | 2024-08-30 | 2024-09-09 | 2024-09-23 | 2024-10-08 | 2024-10-21 | MARAKESH ENTERPRISES | delayed due to request for modification
LMS 2024 | Region IV-A | Batangas | 107828 | Gumapac Barangay School | TUY | 1st | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18412863.76 | 17900000 | Ongoing | 0.35 | 2025-08-04 |  | LMS 2024 - IVA - BATANGAS - 001 | LMS 2024 - IVA - BATANGAS - 001 | June 11,2024 | 2024-06-18 | 2024-07-01 | 2024-07-17 | 2025-01-30 | Botey Construction | 0
LMS 2024 | Region IV-A | Batangas | 107583 | Tulos Elementary School | ROSARIO | 4th | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18151995.7 | 18150000 | Ongoing | 0.35 | 2025-08-04 |  | LMS 2024 - IVA - BATANGAS - 002 | LMS 2024 - IVA - BATANGAS - 002 | June 11,2024 | 2024-06-18 | 2024-07-01 | 2024-07-17 | 2025-01-30 | Botey Construction | 0
LMS 2024 | Region IV-A | Cavite | 108119 | Guitasin Primary School | SILANG | 5th | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 25252525.25 | 24907973.66 | Ongoing | 0.5 | 2025-07-13 | 00:00:00 | RIVACaviteBACInfra 005-2024 | RIVACaviteBACInfra 005-2024 | 2024-08-01 | 2024-08-08 | 2024-08-27 | Jan. 6. 2025 | Jan. 14, 2025 | R.A. Del Rosario Construction | On-going masonry works and preparation of roofing works
LMS 2024 | Region IV-A | Laguna | 164519 | Sitio Pulot/Bay ES | KALAYAAN | 4th | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16454451.88 |  | Under Procurement | 0 | [10 empty] | For reversion due to the issue on School Site with NPC (under negotiation) / awaiting letter from SDO.
LMS 2024 | Region IV-A | Quezon | 108570 | SAN RAFAEL ELEMENTARY SCHOOL | BURDEOS | 1st | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19200611.34 | 18954730.71 | Completed | 1 | 2025-03-05 | 2025-03-04 | 2023-05-INFRAEPA | 2023-05-INFRAEPA | 2023-11-24 | 2023-12-01 | 2023-12-15 | 2023-12-29 | 2024-05-20 | N.T. Sotelo Contruction & Supply Corporation | Completed
LMS 2024 | Region IV-A | Quezon | 109096 | Segaras ES | SAN ANDRES | 3rd | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16402689.46 | 13000000 | Completed | 1 | 2024-11-15 | 2024-10-18 | 2023-05-INFRAEPA | 2023-05-INFRAEPA | 2023-11-24 | 2023-12-01 | 2023-12-15 | 2023-12-29 | 2024-05-20 | Botey Construction | Completed
LMS 2024 | Region IV-A | Quezon | 108735 | DUNGAWAN PAALYUNAN ES | GUINAYANGAN | 4th | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16402689.46 | 14411651.63 | Completed | 1 | 2024-11-15 | 2025-01-30 | 2023-05-INFRAEPA | 2023-05-INFRAEPA | 2023-11-24 | 2023-12-01 | 2023-12-15 | 2023-12-29 | 2024-05-20 | M.G. Villamin Construction | Completed
LMS 2024 | Region IV-A | Tayabas City | 109249 | Eugenio Francia Elementary School | CITY OF TAYABAS | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 23636363.64 |  | Under Procurement | 0 | [10 empty] | Preparation of Plans / POW/DUPA Modified Design

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.