## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Program-Year | Status as of July 11, 2025
SHS | REGION IV-B | Calapan City | 301798 | Canubing National High School | City Of Calapan (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6777351.59 |  |  | Completed | 1 |  |  | P00073264LZ | 16ED0065 | 2016-06-08 | 2016-06-16 | 2016-08-04 | 2016-08-17 | 2016-08-31 | DK CONSTRUCTION |  | NC 2016
SHS | REGION IV-B | Calapan City | 301797 | Community Vocational High School | City Of Calapan (Capital) | 1 | 1 | 16 | 2STY8CL | BATCH 9 CL | 22079735.1834 |  |  | Completed | 1 |  |  | P00073265LZ | 16ED0069 | 2016-07-29 | 2016-08-08 |  | 2016-09-02 | 2016-09-14 | MONOLITHIC CONST. & CONC. PRODUCTS, INC. |  | NC 2016
TECHVOC | REGION IV-B | Calapan City | 301797 | Community Vocational High School | City Of Calapan (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1 |  |  | P00074446LZ | 16ED0044 | 2016-05-31 | 2016-06-09 | 2016-06-28 | 2016-07-04 | 2016-07-13 | KARANGYAN BLDRS. & TRADERS |  | NC 2016
SHS | REGION IV-B | Calapan City | 301805 | Managpi National High School | City Of Calapan (Capital) | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 13280440 |  |  | Completed | 1 |  |  | P00073266LZ | 16ED0066 | 2016-07-29 | 2016-08-08 |  | 2016-09-02 | 2016-09-14 | I. A. BOSGUE CONST. CORP. |  | NC 2016
TECHVOC | REGION IV-B | Calapan City | 301805 | Managpi National High School | City Of Calapan (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2752716.3457 |  |  | Completed | 1 |  |  | P00074447LZ | 16ED0043 | 2016-05-31 | 2016-06-09 | 2016-06-28 | 2016-07-04 | 2016-07-13 | MARC JILL CONST. |  | NC 2016
SHS | REGION IV-B | Calapan City | 301802 | Nag-Iba National High School | City Of Calapan (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6469337.64 |  |  | Completed | 1 |  |  | P00070478LZ | 16ED0059 | -395769 | 2016-06-16 | 2016-08-04 | 2016-08-15 | 2016-08-31 | DEL ROL ENT. |  | NC 2016
SHS | REGION IV-B | Calapan City | 301800 | Oriental Mindoro National High School | City Of Calapan (Capital) | 1 | 1 | 24 | 2STY12CL | BATCH 3 CL | 30322440 |  |  | Completed | 1 |  |  | P00070479LZ | 16ED0060 | -395769 | 2016-06-16 | 2016-07-28 | 2016-08-22 | 2016-09-12 | ETVR TRADING & CONST. |  | NC 2016
SHS | REGION IV-B | Calapan City | 301800 | Oriental Mindoro National High School | City Of Calapan (Capital) | 1 |  | 8 | 2STY8CL | BATCH 3 CL | 11310050 |  |  | Completed | 1 |  |  | P00070480LZ | 16ED0061 | -395769 | 2016-06-16 | 2016-07-28 | 2016-08-09 | 2016-08-17 | ETVR TRADING & CONST. |  | NC 2016
SHS | REGION IV-B | Marinduque | 301530 | Balanacan Nhs | Mogpog | 0 | 1 | 9 | 3STY9CL | BATCH 5 CL | 16763095.25 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Marinduque | 301532 | Bognuyan Nhs | Gasan | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6485626.319 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Marinduque | 301532 | Bognuyan Nhs | Gasan | 0 |  | 6 | 2STY6CL | BATCH 9 CL | 9150921.402 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Marinduque | 301533 | Bonliw Nhs | Torrijos | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7059509.662 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Marinduque | 301534 | Botilao Nhs | Santa Cruz | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7059509.662 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Marinduque | 301536 | Buenavista Nhs - Bagacay Annex | Buenavista | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6802407.63 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Marinduque | 301542 | Dolores Nhs | Santa Cruz | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6485626.319 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION IV-B | Marinduque | 301543 | Hupi National High School | Santa Cruz | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7059509.662 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Marinduque | 301544 | Ilaya Nhs | Boac (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 5 CL | 9085667.05 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Marinduque | 301547 | Kilo-Kilo Nhs | Santa Cruz | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9046166.455 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Marinduque | 301548 | Landy National High School | Santa Cruz | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6485626.319 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Marinduque | 301549 | Makapuyat Nhs | Santa Cruz | 0 | 1 | 12 | 2STY6CL | BATCH 1 CL | 21239674.52 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Marinduque | 301550 | Makapuyat Nhs - Masaguisi Annex | Santa Cruz | 0 | 1 | 6 | 2STY6CL | BATCH 1 CL | 10619837.26 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION IV-B | Marinduque | 301557 | Mogpog National Comprehensive High School | Mogpog | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6485626.319 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION IV-B | Marinduque | 301557 | Mogpog National Comprehensive High School | Mogpog | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 16708695.494 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Marinduque | 301558 | Mongpong Nhs | Santa Cruz | 0 | 1 | 4 | 2STY4CL | BATCH 1 CL | 10455499.5981 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Marinduque | 308804 | Paciano A. Sena Mem. Hs (Tabionan Nhs) | Gasan | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7059509.662 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Marinduque | 301560 | Punong Nhs | Santa Cruz | 0 | 1 | 4 | 2STY4CL | BATCH 1 CL | 7525669.4581 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Marinduque | 301565 | Tapuyan Nhs | Gasan | 0 | 1 | 10 | 2STY10CL | BATCH 5 CL | 14733227.22 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Marinduque |  | Tigwi Nhs To Tigwi Shs | Torrijos | 0 | 1 | 12 | 2STY6CL | BATCH 1 CL | 22625402.48 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Marinduque | 301568 | Yook Nhs | Buenavista | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6485626.319 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Occidental Mindoro | 301600 | Central Nhs | San Jose | 0 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10867131.51 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Occidental Mindoro | 301588 | Magsaysay Nhs | Magsaysay | 0 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8594965.051 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Occidental Mindoro | 301593 | Occidental Mindoro Nhs | Mamburao (Capital) | 0 | 1 | 15 | 3STY15CL | BATCH 11 CL | 21383013.45 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Occidental Mindoro | 301594 | Paluan Nhs | Paluan | 0 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15571327.92 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION IV-B | Occidental Mindoro | 301592 | Pedro T. Mendiola Sr. Memorial National High School | San Jose | 0 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.5917 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Occidental Mindoro | 301595 | Rizal National High School | Rizal | 0 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8564965.051 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION IV-B | Occidental Mindoro | 301596 | Sablayan Nchs | Sablayan | 0 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION IV-B | Occidental Mindoro | 308901 | San Jose National Agricultural And Industrial High School | San Jose | 0 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8464965.051 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Occidental Mindoro | 301599 | San Jose Nhs | San Jose | 0 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8514965.051 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Occidental Mindoro | 301601 | San Vicente Nhs | Sablayan | 0 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8564965.051 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION IV-B | Occidental Mindoro | 301604 | Santa Cruz Nhs - Pinagturilan Annex | Santa Cruz | 0 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8564965.051 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION IV-B | Oriental Mindoro | 309008 | Anastacio Dela Chica High School | Baco | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1 |  |  | P00073274LZ | [5 empty] | 2016-11-16 | King,s Builders & Dev't. Corp./CMSDEL Const. & Developer JV |  | NC 2016
TECHVOC | REGION IV-B | Oriental Mindoro | 309008 | Anastacio Dela Chica High School | Baco | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2500000 |  |  | Completed | 1 |  |  | P00074449LZ | 16ED0045 |  |  |  |  | 2016-07-19 | B5 Builders |  | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301611 | Apitong Nhs | Naujan | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 |  |  | P00072283LZ | 16ED0058 |  |  |  |  | 2016-07-25 | Anjet Const. Supplies & Labor Services |  | NC 2016
K10 | REGION IV-B | Oriental Mindoro | 301628 | Arceli B. Pantilanan - Bacawan High School | Pola | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2904910.93 |  |  | Completed | 1 |  |  | P00072288LZ | [5 empty] | 2016-10-06 | LTDL Builders |  | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301613 | Aurelio Arago Mnhs | Victoria | 1 | 1 | 16 | 4STY16CL | BATCH 3 CL | 26852469.42 |  |  | Completed | 1 |  |  | P00070477LZ | [5 empty] | 2017-01-15 | St. Gerald Const. |  | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301614 | Aurora Nhs | Naujan | 1 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12771310.09 |  |  | Completed | 1 |  |  | P00072284LZ | 16ED0062 |  |  |  |  | 2016-08-29 | 811 Trading & Const. |  | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301616 | Baco Nhs | Baco | 1 | 1 | 16 | 4STY16CL | BATCH 3 CL | 26702469.42 |  |  | Completed | 1 |  |  | P00070474LZ | [8 empty] | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301619 | Bayuin Nhs | Socorro | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 |  |  | P00072291LZ | 16ED0057 |  |  |  |  | 2016-07-19 | Anjet Const. Supplies & Labor Services |  | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301627 | Domingo Yu Chu Nhs | Pola | 1 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1 |  |  | P00073289LZ | [8 empty] | NC 2016
K10 | REGION IV-B | Oriental Mindoro | 301630 | Doroteo S. Mendoza Sr. Mnhs | Naujan | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10877342.59 |  |  | Completed | 1 |  |  | P00072285LZ | 16ED0063 |  |  |  |  | 2016-08-22 | 811 Trading & Const. |  | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 309001 | Inarawan Nhs | Naujan | 1 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18764436.85 |  |  | Completed | 1 |  |  | P00072286LZ | [5 empty] | 2016-11-17 | King's Builders & Dev't Corp./ CMSDEL Const. & Developer |  | NC 2016
K10 | REGION IV-B | Oriental Mindoro | 309025 | Leandro Panganiban, Sr. - Tagumpay High School | Pola | 1 | 1 | 5 | 1STY5CL | BATCH 7 CL | 4700731.46 |  |  | Completed | 1 |  |  | P00072289LZ | 16ED0089 | [7 empty] | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301634 | Leuteboro Nhs | Socorro | 1 | 1 | 20 | 4STY20CL | BATCH 1 CL | 33110063.69 |  |  | Completed | 1 |  |  | P00070089LZ | [5 empty] | 2017-01-16 | Jasmig Const. Supply |  | NC 2016
K10 | REGION IV-B | Oriental Mindoro | 301612 | Macatoc Nhs | Victoria | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 |  |  | P00072292LZ | 16ED0064 |  |  |  |  | 2016-09-06 | B5 Builders & Supplies/ FS Sugay JV |  | NC 2016
K10 | REGION IV-B | Oriental Mindoro | 301629 | Matulatula High School | Pola | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8456914 |  |  | Completed | 1 |  |  | P00073290LZ | 16ED0068 |  |  |  |  | 2016-09-06 | Greatlakes Ent. |  | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301642 | Melgar Nhs | Naujan | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10877342.59 |  |  | Completed | 1 |  |  | P00073286LZ | 16ED0067 |  |  |  |  | 2016-09-06 | ETVR Trading & Const. |  | NC 2016
K10 | REGION IV-B | Oriental Mindoro | 301645 | Naujan Municipal High School | Naujan | 1 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1 |  |  | P00072287LZ | [5 empty] | 2016-11-17 | CMSEL Const. & Developer |  | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301648 | Porfirio Comia Mnhs | Naujan | 1 | 1 | 12 | 4STY12CL | BATCH 3 CL | 22422484.24 |  |  | Completed | 1 |  |  | P00070475LZ | [5 empty] | 2016-12-08 | Zoe Builders & Supplies Const./ Sanlahi Group JV. |  | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 309004 | Puerto Galera Nhs | Puerto Galera | 1 | 1 | 9 | 3STY9CL | BATCH 3 CL | 16659208.67 |  |  | Completed | 1 |  |  | P00070476LZ | [5 empty] | 2016-11-16 | FEAJ Const. & Gen. Services |  | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 309035 | Puerto Galera Nhs - San Isidro Ext. | Puerto Galera | 1 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  | P00072290LZ | [5 empty] | 2016-12-13 | L.N. Salvador Const. |  | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301651 | San Agustin Nhs | Naujan | 1 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21383013.45 |  |  | Completed | 1 |  |  | P00073287Z | [5 empty] | 2016-11-17 | RREncabo Contructors, Inc./ Marc Jill Const. JV |  | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301653 | San Teodoro Nhs | San Teodoro | 1 | 1 | 12 | 3STY6CL | BATCH 9 CL | 20834263.02 |  |  | Completed | 1 |  |  | P00073292LZ | [5 empty] | 2016-11-16 | RR Encabo Constructors, Inc./ Marc Jill Const. JV |  | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301610 | Alcadesma Nhs | Bansud | 2 | 1 | 15 | 3STY15CL | BATCH 9 CL | 23463848.7681 |  |  | Completed | 1 |  |  | P00073275LZ | [8 empty] | NC 2016
TECHVOC | REGION IV-B | Oriental Mindoro | 301610 | Alcadesma Nhs | Bansud | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2539544.27 |  |  | Completed | 1 |  |  | P00074450LZ | [5 empty] | 2016-08-04 | Alberto Uy Const. & Dev't |  | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301617 | Balugo Nhs | Mansalay | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 11291397.03 |  |  | Completed | 1 |  |  | P00072305LZ | [8 empty] | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301618 | Bansud Nhs - Regional Science High School | Bansud | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6381031.01 |  |  | Completed | 1 |  |  | P00072293LZ | [7 empty] | With Approved Buffer Fund (2018 Batch 2) | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301623 | Bulbugan Nhs | Gloria | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6381031.01 |  |  | Completed | 1 |  |  | P00072303LZ | [7 empty] | With Approved Buffer Fund (2018 Batch 2) | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 309006 | Carmundo Nhs | Bongabong | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6381031.01 |  |  | Completed | 1 |  |  | P00072297LZ | [8 empty] | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301624 | Cawayan Nhs | Bongabong | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8295614.7 |  |  | Completed | 1 |  |  | P00073276LZ | [8 empty] | NC 2016
TECHVOC | REGION IV-B | Oriental Mindoro | 301624 | Cawayan Nhs | Bongabong | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2539544.27 |  |  | Completed | 1 |  |  | P00074451LZ | [5 empty] | 2016-08-04 | ADL Constrak |  | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301625 | Dayhagan Nhs | Bongabong | 2 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11423310.398 |  |  | Completed | 1 |  |  | P00073277LZ | [8 empty] | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 309027 | Felimon M. Salcedo Sr. Mnhs | Bansud | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6381031.01 |  |  | Completed | 1 |  |  | P00072294LZ | [8 empty] | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301633 | Kaligtasan Nhs | Bongabong | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6381031.01 |  |  | Completed | 1 |  |  | P00072298LZ | [8 empty] | NC 2016
K10 | REGION IV-B | Oriental Mindoro | 309005 | Labasan Nhs | Bongabong | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8295614.7 |  |  | Completed | 1 |  |  | P00072299LZ | [8 empty] | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301636 | Malamig Nhs | Gloria | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6381031.01 |  |  | Completed | 1 |  |  | P00072304LZ | [8 empty] | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301638 | Manaul Nhs | Mansalay | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6381031.01 |  |  | Completed | 1 |  |  | P00072306LZ | [8 empty] | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301641 | Masaguisi Nhs | Bongabong | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8295614.7 |  |  | Completed | 1 |  |  | P00072299LZ | [8 empty] | NC 2016
TECHVOC | REGION IV-B | Oriental Mindoro | 301621 | Maujao Nhs | Bulalacao (San Pedro) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2539544.27 |  |  | Completed | 1 |  |  | P00074453LZ | [5 empty] | 2016-08-04 | Lumel Glenn Construction |  | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301621 | Maujao Nhs | Bulalacao (San Pedro) | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8295614.7 |  |  | Completed | 1 |  |  | P00073279LZ | [8 empty] | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301643 | Morente Nhs | Bongabong | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 11291397.03 |  |  | Completed | 1 |  |  | P00072301LZ | [8 empty] | NC 2016
TECHVOC | REGION IV-B | Oriental Mindoro | 309019 | Pag-Asa Nhs | Bansud | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2539544.27 |  |  | Completed | 1 | [8 empty] | 2016-09-13 | D.M. Maliwanag |  | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 309019 | Pag-Asa Nhs | Bansud | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8295614.7 |  |  | Completed | 1 |  |  | P00072295LZ | [8 empty] | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301646 | Pambisan Nhs | Pinamalayan | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 11291397.03 |  |  | Completed | 1 |  |  | P00072307LZ | [7 empty] | With Approved Buffer Fund (2018 Batch 2) | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301647 | Pili Nhs | Pinamalayan | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6381031.01 |  |  | Completed | 1 |  |  | P00072308LZ | [8 empty] | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301649 | Quinabigan Nhs | Pinamalayan | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 16342775.6863 |  |  | Completed | 1 |  |  | P00073288LZ | [7 empty] | With Approved Buffer Fund (2019) | NC 2016
TECHVOC | REGION IV-B | Oriental Mindoro | 301652 | San Mariano Nhs | Roxas | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2539544.27 |  |  | Completed | 1 |  |  | P00074448LZ | [5 empty] | 2016-08-04 | Green Island Enterprises |  | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301652 | San Mariano Nhs | Roxas | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20000467.74 |  |  | Completed | 1 |  |  | P00073291LZ | [8 empty] | NC 2016
TECHVOC | REGION IV-B | Oriental Mindoro | 301622 | San Roque Nhs | Bulalacao (San Pedro) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2539544.27 |  |  | Completed | 1 | [8 empty] | 2016-11-20 | SOSEP Builders |  | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301622 | San Roque Nhs | Bulalacao (San Pedro) | 2 | 1 | 12 | 3STY12CL | BATCH 7 CL | 20000467.74 |  |  | Completed | 1 |  |  | P00072302LZ | [8 empty] | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301654 | Vicente B. Ylagan Nhs | Bongabong | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8295614.7 |  |  | Completed | 1 |  |  | P00073278LZ | [8 empty] | NC 2016
TECHVOC | REGION IV-B | Oriental Mindoro | 301654 | Vicente B. Ylagan Nhs | Bongabong | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2539544.27 |  |  | Completed | 1 |  |  | P00074452LZ | [5 empty] | 2016-08-04 | Lumel Glenn Construction |  | NC 2016
TECHVOC | REGION IV-B | Oriental Mindoro | 301655 | Villapagasa Nhs | Bansud | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 5079088.54 |  |  | Completed | 1 | [8 empty] | 2016-09-11 | Martinez Enterprises |  | NC 2016
SHS | REGION IV-B | Oriental Mindoro | 301655 | Villapagasa Nhs | Bansud | 2 | 1 | 10 | 2STY10CL | BATCH 7 CL | 13183972.54 |  |  | Completed | 1 |  |  | P00072296LZ | [8 empty] | NC 2016
SHS | REGION IV-B | Palawan | 301659 | Aborlan Nhs | Aborlan | 2 | 1 | 30 | 3STY15CL | BATCH 9 CL | 47521109.59 |  |  | Completed | 1 |  |  | 16EG0046 | P00073294 LZ CW1 |  |  | 00:00:00 |  | 2016-07-22 | A.R. Lustre Jr.Construction |  | NC 2016
SHS | REGION IV-B | Palawan | 301660 | Alimanguan Nhs | San Vicente | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6821377.944 |  |  | Completed | 1 |  |  |  | P00072332LZ 16EE0028 |  |  | 00:00:00 |  | 2016-07-18 | KIM HAROLD TRADING & CONST. |  | NC 2016
K10 | REGION IV-B | Palawan | 110715 | Apoc-Apoc Es | Aborlan | 3 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8666522 |  |  | Completed | 1 |  |  |  | 0 |  |  | 2016-06-09 |  | 2016-06-29 | E.V. Villaos Trdg. & Construction |  | NC 2016
K10 | REGION IV-B | Palawan | 309109 | Bacao Nhs (Dumaran Nhs - Bacao Nhs) | Dumaran | 1 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1167553.792 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
SHS | REGION IV-B | Palawan | 301661 | Apurawan Nhs | Aborlan | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12129626.8509 |  |  | Completed | 1 |  |  | 16EG0049 | P00073294LZ CW1 |  |  | 00:00:00 |  | 2016-07-22 | PTK Group Inc. & Ivy Michelle T&C (Joint Venture) |  | NC 2016
SHS | REGION IV-B | Palawan | 301662 | Araceli Nhs | Araceli | 1 | 1 | 18 | 3STY9CL | BATCH 7 CL | 32455759.32 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301667 | Barotuan Nhs | El Nido (Bacuit) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2804658.648 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 309138 | Araceli Plainview Nhs | Araceli | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 7053201.888 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
SHS | REGION IV-B | Palawan | 301663 | Aramaywan Nhs | Narra | 2 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21565910 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
SHS | REGION IV-B | Palawan | 301663 | Aramaywan Nhs | Narra | 2 |  | 9 | 3STY9CL | BATCH 9 CL | 15317811 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301663 | Aramaywan Nhs | Narra | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1 |  |  | 16EF0069 | P00074461LZ |  |  | 00:00:00 |  | 00:00:00 | CRISHELLE CONSTRUCTION |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 309109 | Bacao Nhs (Dumaran Nhs - Bacao Nhs) | Dumaran | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2819272.06 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301666 | Balabac Nhs | Balabac | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2924570 |  |  | Completed | 1 |  |  | 16EF0096 | P00075085LZ |  |  | 00:00:00 |  | 2016-10-07 | SYNDITE CONSTRUCTION |  | NC 2016
K10 | REGION IV-B | Palawan | 309113 | Bancalaan National High School | Balabac | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 19781260 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301681 | Caruray Nhs | San Vicente | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2788601.442 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 309113 | Bancalaan National High School | Balabac | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 7233509.4 |  |  | Completed | 1 |  |  | 16EF0112 | P00073298LZ |  |  | 00:00:00 |  | 2016-10-04 | SYNDITE CONSTRUCTION |  | NC 2016
SHS | REGION IV-B | Palawan | 301667 | Barotuan Nhs | El Nido (Bacuit) | 1 | 1 | 24 | 3STY12CL | BATCH 7 CL | 37706473.6 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301668 | Bataraza National High School | Bataraza | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2791635 |  |  | Completed | 1 |  |  | 16EF0073 | P00074456LZ |  |  | 00:00:00 |  | 2016-08-14 | JIBER CONSTRUCTION |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 309120 | Concepcion National High School | Agutaya | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2924570 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 301668 | Bataraza National High School | Bataraza | 2 | 1 | 15 | 3STY15CL | BATCH 9 CL | 22444664.1225 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 301668 | Bataraza National High School | Bataraza | 2 |  | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
SHS | REGION IV-B | Palawan | 301669 | Bato Nhs | Taytay | 1 | 1 | 24 | 3STY12CL | BATCH 7 CL | 37492314.4 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301669 | Bato Nhs | Taytay | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 5577202.884 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 111088 | Berong Es | Quezon | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8961499.2 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION IV-B | Palawan | 301674 | Bugsuk Nhs - Mangsee Annex | Balabac | 2 |  | 8 | 1STY4CL | BATCH 9 CL | 8385025.5115 |  |  | Completed | 1 |  |  | 16EF0129 | 0 |  |  | 00:00:00 |  | 2016-10-07 | SYNDITE CONSTRUCTION |  | NC 2016
K10 | REGION IV-B | Palawan | 301674 | Bugsuk Nhs - Mangsee Annex | Balabac | 2 | 1 | 10 | 1STY5CL | BATCH 9 CL | 9401462.9386 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 111214 | Bulalo Es | Taytay | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6898652.592 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 309139 | Cabigaan Nhs | Aborlan | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6248582 |  |  | Completed | 1 |  |  |  | 0 |  |  | 2016-06-24 |  | 2016-07-12 | Samurai Construction |  | NC 2016
K10 | REGION IV-B | Palawan | 110751 | Cabugawan Es To Bacao Es | Dumaran | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1154484.16 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
SHS | REGION IV-B | Palawan | 301678 | Calandagan Nhs | Araceli | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 12729237.892 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 110758 | Calasag Es | Dumaran | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1154484.16 |  |  | Completed | 1 |  |  |  | P00072339LZ 16EE0025 |  |  | 00:00:00 |  | 2016-06-27 | 12-30 Construction |  | NC 2016
K10 | REGION IV-B | Palawan | 309155 | Calasaguen Nhs | Brooke'S Point | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9129337.28 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION IV-B | Palawan | 301680 | Candawaga National High School | Rizal (Marcos) | 2 | 1 | 12 | 3STY12CL | BATCH 13 CL | 20993211.619 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Palawan | 309160 | Canipaan Nhs | Rizal (Marcos) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7233509 |  |  | Completed | 1 |  |  | 16EF0110 | P00073321LZ |  |  | 00:00:00 |  | 2016-10-03 | SYNDITE CONSTRUCTION |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 309160 | Canipaan Nhs | Rizal (Marcos) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2792510 |  |  | Completed | 1 |  |  | 16EF0076 | P00074466LZ |  |  | 00:00:00 |  | 2016-08-14 | CRISHELLE TRADING & CONSTRUCTION |  | NC 2016
SHS | REGION IV-B | Palawan | 301681 | Caruray Nhs | San Vicente | 1 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18746157.2 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 | With approved additional funds | NC 2016
SHS | REGION IV-B | Palawan | 111143 | Casian Nhs To Caramay Es | Taytay | 1 | 1 | 12 | 2STY12CL | BATCH 9 CL | 16922093.1778 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301682 | Casian Nhs | Taytay | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2787157.648 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 309103 | Central Taytay Nhs | Taytay | 1 | 1 | 40 | 4STY20CL | BATCH 7 CL | 65758442.7717 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 309107 | Pancol Brgy. Nhs | Taytay | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2787157.648 |  |  | Completed | 1 |  |  |  | P00073348LZ 16EE0054 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 309107 | Pancol Brgy. Nhs | Taytay | 1 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1141414.528 |  |  | Completed | 1 |  |  |  | P00073348LZ 16EE0054 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 309103 | Central Taytay Nhs | Taytay | 1 |  | 4 | 2STY4CL | BATCH 7 CL | 6860015.268 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 309134 | Cheey National High School | Busuanga | 1 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10484355.735 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 301684 | Coron Sof | Coron | 1 | 1 | 10 | 2STY10CL | BATCH 13 CL | 15421785.2089 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION IV-B | Palawan | 110829 | Culandanum Es | Bataraza | 2 | 1 | 8 | 2STY8CL | BATCH 13 CL | 12566775.41 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION IV-B | Palawan | 170506 | San Felipe Es | Araceli | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1167553.792 |  |  | Completed | 1 |  |  |  | P00072337lz 16EE0026 |  |  | 00:00:00 |  | 2016-06-27 | Yurich Builders & Construction |  | NC 2016
K10 | REGION IV-B | Palawan | 301686 | Culandanum Nhs | Aborlan | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12129626.8509 |  |  | Completed | 1 |  |  | 16EG0050 | P00073295LZ CW1 |  |  | 00:00:00 |  | 2016-07-22 | Ivy Michelle Trading & Const. |  | NC 2016
K10 | REGION IV-B | Palawan | 111002 | Cuyo Miller School | Cuyo | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9378961.5 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION IV-B | Palawan | 301688 | Cuyo National High School | Cuyo | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 170566 | Trinidad Cario Ps | Roxas | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1121810.08 |  |  | Completed | 1 |  |  |  | P0007234LZ 16EE0027 |  |  | 00:00:00 |  | 2016-07-18 | 12-30 CONST. |  | NC 2016
K10 | REGION IV-B | Palawan | 301688 | Cuyo National High School | Cuyo | 1 | 1 | 10 | 2STY10CL | BATCH 13 CL | 14473441 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION IV-B | Palawan | 110983 | Decalachao Es | Coron | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9908607.7105 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Palawan | 301692 | Dumaran Mainland Nhs | Dumaran | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14718750.5423 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 301691 | Dumaran Nhs | Dumaran | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 9045418.24 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
SHS | REGION IV-B | Palawan | 301693 | El Nido Nhs | El Nido (Bacuit) | 1 | 1 | 40 | 4STY20CL | BATCH 9 CL | 66135362.7877 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301661 | Apurawan Nhs | Aborlan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2698863 |  |  | Completed | 1 |  |  | 16EG0045 | P00074454LZ CW1 |  |  | 00:00:00 |  | 2016-07-13 | 12-30 CONSTRUCTION & SUPPLY |  | NC 2016
SHS | REGION IV-B | Palawan | 301693 | El Nido Nhs | El Nido (Bacuit) | 1 |  | 10 | 2STY10CL | BATCH 9 CL | 14718750.5423 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301693 | El Nido Nhs | El Nido (Bacuit) | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5574315.296 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 301694 | Francisco F. Ponce De Leon Es To F. Lagan Sr. Mem. Nhs | Roxas | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 12172223.668 |  |  | Reverted | 0 |  |  |  | P00072344LZ 16EE0034 |  |  | 00:00:00 |  | 2016-06-27 | A.P. CONSEBIDO CONST. |  | NC 2016
K10 | REGION IV-B | Palawan | 110723 | Gogognan Es | Aborlan | 3 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1043078 |  |  | Completed | 1 |  |  |  | 0 |  |  | 2016-06-09 |  | 2016-06-29 | Panaad Construction |  | NC 2016
K10 | REGION IV-B | Palawan | 301699 | Gov. Alfredo Abueg Sr. National Technology & Vocational Memorial High School | Brooke'S Point | 2 | 1 | 12 | 2STY12CL | BATCH 9 CL | 16914468.8978 |  |  | Completed | 1 |  |  | 16EF0106 | P0073308LZ |  |  | 00:00:00 |  | 2016-10-02 | UGM CONSTRUCTION |  | NC 2016
K10 | REGION IV-B | Palawan | 301699 | Gov. Alfredo Abueg Sr. National Technology & Vocational Memorial High School | Brooke'S Point | 2 |  | 12 | 3STY12CL | BATCH 9 CL | 18888930 |  |  | Completed | 1 |  |  | 16EF0144 | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 309113 | Bancalaan National High School | Balabac | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2924570 |  |  | Completed | 1 |  |  | 16EF0075 | P00074455LZ |  |  | 00:00:00 |  | 2016-08-14 | SYNDITE CONSTRUCTION |  | NC 2016
K10 | REGION IV-B | Palawan | 309135 | Ilian Nhs | Dumaran | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6975927.24 |  |  | Completed | 1 |  |  |  | P00072340LZ 16EE0048 |  |  | 00:00:00 |  | 2016-07-14 | 12-30 CONSTRUCTION |  | NC 2016
K10 | REGION IV-B | Palawan | 309136 | Inil U. Taha Nhs | Brooke'S Point | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9129337.28 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION IV-B | Palawan | 111148 | Iraan Es | Roxas | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8793661.12 |  |  | Completed | 1 |  |  |  | P00072345LZ 16EE0033 |  |  | 00:00:00 |  | 2016-06-27 | A.P. CONSEBIDO CONST. |  | NC 2016
K10 | REGION IV-B | Palawan | 301701 | Isaub National High School | Aborlan | 3 | 1 | 12 | 2STY6CL | BATCH 7 CL | 17333044 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301671 | Brooke'S Point Nhs - Pangobilian Nhs | Brooke'S Point | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2791635 |  |  | Completed | 1 |  |  | 16EF0095 | P00075084LZ |  |  | 00:00:00 |  | 2016-10-07 | E.V.VILLAOS TARING & CONSTRUCTION |  | NC 2016
K10 | REGION IV-B | Palawan | 301671 | Brooke'S Point Nhs - Pangobilian Nhs | Brooke'S Point | 2 | 1 | 40 | 4STY20CL | BATCH 13 CL | 71537358.734 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION IV-B | Palawan | 301702 | J. P. Rizal Nhs | Rizal (Marcos) | 2 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14747305.1023 |  |  | Completed | 1 |  |  | 16EF0109 | P00073322LZ |  |  | 00:00:00 |  | 2016-10-03 | E.V.VILLAOS TRADING & CONSTRUCTION |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301702 | J. P. Rizal Nhs | Rizal (Marcos) | 2 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 8377530 |  |  | Completed | 1 |  |  | 16EF0064 | P00074468LZ |  |  | 00:00:00 |  | 2016-08-14 | KIM HAROLD TRADING & CONSTRUCTION | Abandoned | NC 2016
SHS | REGION IV-B | Palawan | 111136 | Liminangcong Nhs To Andres Soriano Mem. Es | Taytay | 1 | 1 | 12 | 3STY12CL | BATCH 9 CL | 19089737.6919 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
SHS | REGION IV-B | Palawan | 301703 | Liminangcong Nhs | Taytay | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301703 | Liminangcong Nhs | Taytay | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2786317.6 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 301704 | Maasin Nhs (Bernas Nhs) | Brooke'S Point | 2 | 1 | 12 | 2STY12CL | BATCH 9 CL | 16854979.8978 |  |  | Completed | 1 |  |  | 16EF0107 | P00073310LZ |  |  | 00:00:00 |  | 2016-10-03 | IVY MICHELLE TRADING & CONSTRUCTION |  | NC 2016
K10 | REGION IV-B | Palawan | 301705 | Magara School For Philippine Crafstmen | Roxas | 1 | 1 | 15 | 3STY15CL | BATCH 7 CL | 22079891.84 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 301705 | Magara School For Philippine Crafstmen | Roxas | 1 |  | 4 | 2STY4CL | BATCH 7 CL | 6744103.296 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 110721 | Daan Elementary School | Aborlan | 2 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1032060 |  |  | Completed | 1 |  |  | 16EG0038 | P00072311LZ CW1 |  |  | 00:00:00 |  | 2016-06-29 | Panaad Construction |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301690 | Dumangeña Nhs | Narra | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 |  |  | 16EF0098 | P00075082LZ |  |  | 00:00:00 |  | 2016-09-27 | HARDROCK CONSTRUCTION |  | NC 2016
K10 | REGION IV-B | Palawan | 170582 | Malague Es | Dumaran | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 9095769.664 |  |  | Completed | 1 |  |  |  | P00072341LZ 16EE0031 |  |  | 00:00:00 |  | 2016-06-27 | 12-30 CONSTRUCTION |  | NC 2016
K10 | REGION IV-B | Palawan | 110776 | Nagpadalan Es | Dumaran | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1154484.16 |  |  | Completed | 1 |  |  |  | P00072342LZ 16EE0024 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301699 | Gov. Alfredo Abueg Sr. National Technology & Vocational Memorial High School | Brooke'S Point | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2792510.05 |  |  | Completed | 1 |  |  | 16EF0070 | P00074459LZ |  |  | 00:00:00 |  | 2016-08-14 | CRISHELLE CONSTRUCTION |  | NC 2016
K10 | REGION IV-B | Palawan | 110949 | Nangalao Es | Linapacan | 1 | 1 | 12 | 3STY12CL | BATCH 13 CL | 20983711.459 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Palawan | 301710 | Narra Nhs | Narra | 2 | 1 | 45 | 3STY15CL | BATCH 9 CL | 64697730 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 111176 | New Canipo Nhs (Alimanguan Nhs - New Canipo Nhs) To Tinitian Es | San Vicente | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 12241850.446 |  |  | Completed | 1 |  |  |  | P00072334LZ 16EE0035 |  |  | 00:00:00 |  | 00:00:00 | KUDZ TRADING & CONSTRUCTION SUPPLY |  | NC 2016
SHS | REGION IV-B | Palawan | 301713 | New Ibajay Nhs | El Nido (Bacuit) | 1 | 1 | 9 | 3STY9CL | BATCH 7 CL | 16045865.928 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301704 | Maasin Nhs (Bernas Nhs) | Brooke'S Point | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2792510.05 |  |  | Completed | 1 |  |  | 16EF0071 | P00074460LZ |  |  | 00:00:00 |  | 2016-08-14 | JB & SONS TRADING & CONSTRUCTION |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301713 | New Ibajay Nhs | El Nido (Bacuit) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2804658.648 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
SHS | REGION IV-B | Palawan | 301710 | Narra Nhs | Narra | 2 |  | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 |  |  | 16EF0114 | P00073314LZ |  |  | 00:00:00 |  | 2016-10-04 | JB & SONS TRADING & CONSTRUCTION |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301710 | Narra Nhs | Narra | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1 |  |  | 16EF0067 | P00074462LZ |  |  | 00:00:00 |  | 2016-08-14 | JB & SONS TRADING & CONSTRUCTION |  | NC 2016
SHS | REGION IV-B | Palawan | 301718 | Panacan Nhs | Narra | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 |  |  | 16EF0115 | P00073316LZ |  |  | 00:00:00 |  | 2016-08-04 | SYNDITE CONSTRUCTION |  | NC 2016
K10 | REGION IV-B | Palawan | 309145 | Pamantolon Nhs | Taytay | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8995066.816 |  |  | Completed | 1 |  |  |  | P00072349LZ 16EE0029 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
SHS | REGION IV-B | Palawan | 309146 | Panalingaan Nhs | Rizal (Marcos) | 2 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16076201 |  |  | Completed | 1 |  |  | 16EF0123 | P00073323LZ |  |  | 00:00:00 |  | 00:00:00 | IVY MICHELLE TRADING & CONSTRUCTION |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 309146 | Panalingaan Nhs | Rizal (Marcos) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2792510 |  |  | Completed | 1 |  |  | 16EF0077 | P00074468LZ |  |  | 00:00:00 |  | 2016-08-14 | KIM HAROLD TRADING & CONSTRUCTION |  | NC 2016
K10 | REGION IV-B | Palawan | 301719 | Panitian National High School | Sofronio Española | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12102596.89 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 110955 | Panlaitan Es | Busuanga | 1 | 1 | 10 | 2STY10CL | BATCH 13 CL | 15421785.2089 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION IV-B | Palawan | 170583 | Paratungon East Es | Brooke'S Point | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8877580.16 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION IV-B | Palawan | 301724 | Princess Urduja Nhs | Narra | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 2016-08-14 | JB & SONS TRADING & CONSTRUCTION |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301725 | Pulot National High School | Sofronio Española | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2738461 |  |  | Completed | 1 |  |  | 16EF0099 | P00075083LZ |  |  | 00:00:00 |  | 2016-09-28 | HARDROCK CONSTRUCTION |  | NC 2016
SHS | REGION IV-B | Palawan | 301722 | Plaridel Nhs | Aborlan | 3 | 1 | 48 | 4STY24CL | BATCH 7 CL | 77291040 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301726 | Quezon Nhs | Quezon | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5585020.1 |  |  | Completed | 1 |  |  | 16EF0066 | P00074465LZ |  |  | 00:00:00 |  | 2016-08-04 | SYNDITE CONSTRUCTION |  | NC 2016
SHS | REGION IV-B | Palawan | 301723 | Port Barton Nhs | San Vicente | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11392255.0361 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
SHS | REGION IV-B | Palawan | 301723 | Port Barton Nhs | San Vicente | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 8214965.051 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
SHS | REGION IV-B | Palawan | 301724 | Princess Urduja Nhs | Narra | 2 | 1 | 30 | 3STY15CL | BATCH 9 CL | 43131820 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
SHS | REGION IV-B | Palawan | 301730 | Rio Tuba Nhs | Bataraza | 2 | 1 | 30 | 3STY15CL | BATCH 9 CL | 45273411 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
SHS | REGION IV-B | Palawan | 301724 | Princess Urduja Nhs | Narra | 2 |  | 8 | 2STY8CL | BATCH 9 CL | 11754463 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 2016-10-10 | SYNDITE CONSTRUCTION |  | NC 2016
SHS | REGION IV-B | Palawan | 301726 | Quezon Nhs | Quezon | 2 | 1 | 48 | 4STY24CL | BATCH 9 CL | 70258644 |  |  | Completed | 1 |  |  | 16EF0128 | P00073320LZ |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 170548 | Ransang South Es | Rizal (Marcos) | 2 | 1 | 2 | 1STY1CL | BATCH 13 CL | 2305812.98 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION IV-B | Palawan | 301739 | Sandoval National High School | Narra | 2 |  | 9 | 3STY9CL | BATCH 9 CL | 15317811 |  |  | Completed | 1 |  |  | 16EF0124 | P00073319LZ |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 170548 | Ransang South Es | Rizal (Marcos) | 2 |  | 4 | 1STY4CL | BATCH 13 CL | 4195351.87 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Palawan | 309129 | Southern Bataraza Nhs | Bataraza | 2 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3110757.6364 |  |  | Completed | 1 |  |  | 16EF0113 | P00073305LZ |  |  | 00:00:00 |  | 2016-10-04 | BETA-J CONSTRUCTION. |  | NC 2016
K10 | REGION IV-B | Palawan | 110736 | Sto. Niño Elementary School | Aborlan | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6411877.7026 |  |  | Completed | 1 |  |  | 16EG0043 | P00073296LZ |  |  | 00:00:00 |  | 2016-07-13 | Samurai Construction |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301730 | Rio Tuba Nhs | Bataraza | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2792510.05 |  |  | Completed | 1 |  |  | 16EF0072 | P00074457LZ |  |  | 00:00:00 |  | 2016-08-14 | JB & SONS TRADING & CONSTRUCTION |  | NC 2016
K10 | REGION IV-B | Palawan | 301731 | Roxas National Comprehensive High School | Roxas | 1 | 1 | 40 | 4STY20CL | BATCH 7 CL | 64627682.7238 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
SHS | REGION IV-B | Palawan | 301734 | Salvacion Nhs | Busuanga | 1 | 1 | 10 | 2STY10CL | BATCH 13 CL | 15421785.2089 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION IV-B | Palawan | 309153 | Samariñana Nhs | Brooke'S Point | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8961499.2 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Palawan | 301732 | San Jose (Roxas) Nhs | Roxas | 1 | 1 | 16 | 2STY8CL | BATCH 7 CL | 24205193.78 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
SHS | REGION IV-B | Palawan | 301738 | San Vicente Nhs | San Vicente | 1 | 1 | 30 | 3STY15CL | BATCH 7 CL | 44416774.6 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 309126 | Tarusan National High School | Bataraza | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2844809 |  |  | Completed | 1 |  |  | 16EF0097 | P00075086LZ |  |  | 00:00:00 |  | 2016-09-28 | L.B.LEONCIO TRADING & CONSTRUCTION |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301738 | San Vicente Nhs | San Vicente | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2756487.03 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301739 | Sandoval National High School | Narra | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5317400 |  |  | Completed | 1 |  |  | 16EF0065 | P00074464LZ |  |  | 00:00:00 |  | 2016-08-14 | CRISHELLE CONSTRUCTION |  | NC 2016
K10 | REGION IV-B | Palawan | 301739 | Sandoval National High School | Narra | 2 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21565910 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
SHS | REGION IV-B | Palawan | 301740 | Santa Teresita Nhs | Dumaran | 1 | 1 | 24 | 3STY12CL | BATCH 7 CL | 37706473.6 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301701 | Isaub National High School | Aborlan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2704275 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301740 | Santa Teresita Nhs | Dumaran | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2804658.648 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301722 | Plaridel Nhs | Aborlan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2704275 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
SHS | REGION IV-B | Palawan | 309127 | Sibaring Nhs | Balabac | 2 | 1 | 6 | 1STY3CL | BATCH 9 CL | 6390804.0601 |  |  | Completed | 1 |  |  | 16EF0126 | P00073301LZ |  |  | 00:00:00 |  | 2016-10-12 | SYNDITE CONSTRUCTION |  | NC 2016
K10 | REGION IV-B | Palawan | 309152 | Sta Maria Nhs | Dumaran | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6937289.916 |  |  | Completed | 1 |  |  |  | P00072343lz 16EE0052 |  |  | 00:00:00 |  | 2016-07-14 | 12-30 CONSTRUCTION |  | NC 2016
SHS | REGION IV-B | Palawan | 309115 | Sumbiling Nhs | Bataraza | 2 | 1 | 12 | 2STY12CL | BATCH 9 CL | 17188116.2978 |  |  | Completed | 1 |  |  | 16EF0108 | P00073306LZ |  |  | 00:00:00 |  | 2016-10-03 | IVY MICHELLE TRADING & CONSTRUCTION |  | NC 2016
SHS | REGION IV-B | Palawan | 309115 | Sumbiling Nhs | Bataraza | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 7040322.78 |  |  | Completed | 1 |  |  | 16EF0111 | P00073307LZ |  |  | 00:00:00 |  | 2016-10-03 | L.B.LEONCIO CONSTRUCTION |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 309115 | Sumbiling Nhs | Bataraza | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2846034.07 |  |  | Completed | 1 |  |  | 16EF0074 | P00074458LZ |  |  | 00:00:00 |  | 2016-08-14 | SYNDITE CONSTRUCTION | Abandoned | NC 2016
SHS | REGION IV-B | Palawan | 309149 | Taburi Nhs | Rizal (Marcos) | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12334686 |  |  | Completed | 1 |  |  | 16EF0121 | P00073324LZ |  |  | 00:00:00 |  | 2016-10-10 | L.B.LEONCIO CONSTRUCTION |  | NC 2016
K10 | REGION IV-B | Palawan | 110858 | Tagolango Es | Bataraza | 2 | 1 | 4 | 1STY4CL | BATCH 13 CL | 4085837.5025 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION IV-B | Palawan | 301705 | Magara School For Philippine Crafstmen | Roxas | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2740429.824 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 301742 | Tagumpay Nhs | Roxas | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8844012.544 |  |  | Completed | 1 |  |  |  | P00072346LZ 16EE0032 |  |  | 00:00:00 |  | 2016-07-18 | E.V.VILLAOS CONST. |  | NC 2016
K10 | REGION IV-B | Palawan | 301731 | Roxas National Comprehensive High School | Roxas | 1 |  | 8 | 2STY8CL | BATCH 7 CL | 12032970.112 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
TECHVOC | REGION IV-B | Palawan | 301731 | Roxas National Comprehensive High School | Roxas | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 5480859.648 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 110860 | Tarusan Es | Bataraza | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9129337.28 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Palawan | 301745 | Tumarbong Nhs | Roxas | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2064157.4714 |  |  | Completed | 1 |  |  |  | 0 |  |  | 00:00:00 |  | 00:00:00 | 0 |  | NC 2016
K10 | REGION IV-B | Palawan | 111252 | Tumbod Es | Taytay | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8995066.816 |  |  | Completed | 1 |  |  |  | P00072350LZ 16EE0030 |  |  | 00:00:00 |  | 2016-07-18 | E.V. VILLAOS |  | NC 2016
K10 | REGION IV-B | Palawan | 309125 | Turda National High School | Coron | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 13130084.5339 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Puerto Princesa City | 309301 | Palawan National School | Puerto Princesa City (Capital) | 2 | 1 | 32 | 4STY16CL | BATCH 7 CL | 55020000 |  |  | Completed | 1 |  |  | P00072322LZ_CW1 | 16EG0041 | 2016-06-02 | 2016-06-10 | 2016-06-24 |  | 2016-07-13 | E.V. VILLAOS TRADING & CONST. |  | NC 2016
SHS | REGION IV-B | Puerto Princesa City | 309301 | Palawan National School | Puerto Princesa City (Capital) | 2 |  | 20 | 4STY20CL | BATCH 7 CL | 32982000 |  |  | Completed | 1 |  |  | P00072323LZ_CW1 | 16EG0040 | 2016-06-02 | 2016-06-10 | 2016-06-24 |  | 2016-07-13 | A.R. LUSTRE JR. CONSTRUCTION |  | NC 2016
TECHVOC | REGION IV-B | Puerto Princesa City | 301796 | Sicsican Nhs | Puerto Princesa City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2677500 |  |  | Completed | 1 |  |  | P00072620LZ_CW1 | 16EG0029 | 2016-04-15 | 2016-04-22 | 2016-04-01 |  | 2016-05-27 | E.C. Timbancaya Enterprises |  | NC 2016
SHS | REGION IV-B | Puerto Princesa City | 301796 | Sicsican Nhs | Puerto Princesa City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 7 CL | 27510000 |  |  | Completed | 1 |  |  | P00072324LZ_CW1 | 16EG0037 | 2016-05-13 | 2016-05-23 | 2016-06-03 |  | 2016-06-22 | E.V. Villaos Trading & Const. |  | NC 2016
SHS | REGION IV-B | Puerto Princesa City | 301796 | Sicsican Nhs | Puerto Princesa City (Capital) | 2 |  | 20 | 4STY20CL | BATCH 7 CL | 32982000 |  |  | Completed | 1 |  |  | P00072325LZ_CW1 | 16EG0044 | 2016-06-02 | 2016-06-10 | 2016-06-24 |  | 2016-07-13 | E.V. VILLAOS TRADING & CONST. |  | NC 2016
SHS | REGION IV-B | Puerto Princesa City | 301787 | Babuyan Nhs | Puerto Princesa City (Capital) | 3 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14177081.1023 |  |  | Completed | 1 |  |  | P00073329LZ_CW1 | 16EG0058 | 2016-07-19 | 2016-07-28 | 2016-08-09 |  | 2016-08-25 | Ivy Michelle Trading & Construction |  | NC 2016
SHS | REGION IV-B | Puerto Princesa City | 301779 | Bacungan Nhs | Puerto Princesa City (Capital) | 3 | 1 | 12 | 2STY12CL | BATCH 9 CL | 16189718.8978 |  |  | Completed | 1 |  |  | P00073330LZ_CW1 | 16EG0062 | 2016-08-01 | 2016-08-10 | 2016-08-22 |  | 2016-09-09 | A.R. Lustre Jr. Construction |  | NC 2016
SHS | REGION IV-B | Puerto Princesa City | 301780 | Bahile Nhs | Puerto Princesa City (Capital) | 3 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12069776.8509 |  |  | Completed | 1 |  |  | P00073331LZ_CW1 | 16EG0051 | 2016-06-10 | 2016-06-17 | 2016-06-30 |  | 2016-07-22 | Ivy Michelle Trading & Const. |  | NC 2016
SHS | REGION IV-B | Puerto Princesa City | 301781 | Cabayugan Nhs | Puerto Princesa City (Capital) | 3 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12069776.8509 |  |  | Completed | 1 |  |  | P00073332LZ_CW1 | 16EG0052 | 2016-06-10 | 2016-06-17 | 2016-06-30 |  | 2016-07-22 | Syndtite Construction Corporation |  | NC 2016
K10 | REGION IV-B | Puerto Princesa City | 301784 | Langogan National High School | Puerto Princesa City (Capital) | 3 | 1 | 12 | 2STY12CL | BATCH 9 CL | 16189718.8978 |  |  | Completed | 1 |  |  | P00073333LZ_CW1 | 16EG0063 | 2016-08-01 | 2016-08-10 | 2016-08-22 |  | 2016-09-09 | E.V. Villaos Trading & Construction |  | NC 2016
K10 | REGION IV-B | Puerto Princesa City | 301788 | Luzviminda National High School | Puerto Princesa City (Capital) | 3 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14177081.1023 |  |  | Completed | 1 |  |  | P00073334LZ_CW1 | 16EG0057 | 2016-07-19 | 2016-07-28 | 2016-08-09 |  | 2016-08-25 | Ivy Michelle Trading & Construction |  | NC 2016
SHS | REGION IV-B | Puerto Princesa City | 301785 | Macarascas Nhs | Puerto Princesa City (Capital) | 3 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14177081.1023 |  |  | Completed | 1 |  |  | P00073335LZ_CW1 | 16EG0056 | 2016-07-19 | 2016-07-28 | 2016-08-09 |  | 2016-08-25 | E.V. Villaos Trading & Construction |  | NC 2016
SHS | REGION IV-B | Puerto Princesa City | 301789 | Mangingisda Nhs | Puerto Princesa City (Capital) | 3 | 1 | 12 | 2STY12CL | BATCH 9 CL | 16189718.8978 |  |  | Completed | 1 |  |  | P00073336LZ_CW1 | 16EG0064 | 2016-08-01 | 2016-08-10 | 2016-08-22 |  | 2016-09-09 | JV - PTK Group Inc./Ivy Michelle Trading |  | NC 2016
SHS | REGION IV-B | Puerto Princesa City | 301786 | Napsan National High School | Puerto Princesa City (Capital) | 3 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12069776.8509 |  |  | Completed | 1 |  |  | P00073337LZ_CW1 | 16EG0053 | 2016-06-10 | 2016-06-17 | 2016-06-30 |  | 2016-07-22 | E.V. Villaos Trading & Construction |  | NC 2016
SHS | REGION IV-B | Puerto Princesa City | 301791 | Pto. Princesa City Nat. Sci. Hs | Puerto Princesa City (Capital) | 3 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1 |  |  | P00073338LZ_CW1 | 16EG0048 | 2016-06-10 | 2016-06-17 | 2016-06-30 |  | 2016-07-22 | E.V. Villaos Trading & Construction |  | NC 2016
SHS | REGION IV-B | Puerto Princesa City | 301795 | San Rafael National High School | Puerto Princesa City (Capital) | 3 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14177081.1023 |  |  | Completed | 1 |  |  | P00073339LZ_CW1 | 16EG0055 | 2016-07-19 | 2016-07-28 | 2016-08-09 |  | 2016-08-25 | Kudz Trading & Construction Supply |  | NC 2016
SHS | REGION IV-B | Puerto Princesa City |  | Shs In Puerto Princesa City | Puerto Princesa City | 3 | 1 | 12 | 2STY12CL | BATCH 9 CL | 16022138.8978 |  |  | Completed | 1 |  |  | P00073328LZ_CW1 | 16EG0080 | 2016-10-18 | 2016-10-28 | 2016-11-08 |  | 2016-11-25 | Ivy Michelle Trading & Construction |  | NC 2016
SHS | REGION IV-B | Puerto Princesa City | 309302 | Simpucan Nhs (Napsan Nhs - Simpucan Annex) | Puerto Princesa City (Capital) | 3 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20234695.669 |  |  | Completed | 1 |  |  | P00073340LZ_CW1 | 16EG0047 | 2016-06-10 | 2016-06-17 | 2016-06-30 |  | 2016-07-22 | Ivy Michelle Trading & Construction |  | NC 2016
TECHVOC | REGION IV-B | Romblon | 301750 | Banton Nhs | Banton | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Romblon | 301750 | Banton Nhs | Banton | 0 | 1 | 6 | 3STY6CL | BATCH 13 CL | 12573229.1271 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION IV-B | Romblon | 301752 | Cajidiocan National High School | Cajidiocan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION IV-B | Romblon | 309201 | Calatrava National High School | Calatrava | 0 | 1 | 12 | 4STY12CL | BATCH 13 CL | 25800577.982 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION IV-B | Romblon | 301756 | Concepcion Nhs (Main) | Concepcion | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Romblon | 301759 | Don Carlos M. Mejias Memorial Nhs | San Fernando | 0 | 1 | 12 | 2STY12CL | BATCH 13 CL | 17609352.7878 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION IV-B | Romblon | 301761 | Ferrol National High School | Ferrol | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Romblon | 301764 | Libertad National High School | Odiongan | 0 | 1 | 6 | 3STY6CL | BATCH 11 CL | 12371844.661 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION IV-B | Romblon | 301765 | Looc National High School | Looc | 0 | 1 | 15 | 3STY15CL | BATCH 11 CL | 21443013.45 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION IV-B | Romblon | 301765 | Looc National High School | Looc | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION IV-B | Romblon | 301753 | Lumbang East National High School | Cajidiocan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Romblon | 301768 | Magdiwang Nhs | Magdiwang | 0 | 1 | 12 | 3STY12CL | BATCH 11 CL | 20029495.669 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION IV-B | Romblon | 301768 | Magdiwang Nhs | Magdiwang | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION IV-B | Romblon | 301769 | Odiongan National High School | Odiongan | 0 | 1 | 8 | 4STY8CL | BATCH 11 CL | 16602270.724 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION IV-B | Romblon | 301769 | Odiongan National High School | Odiongan | 0 |  | 12 | 3STY12CL | BATCH 11 CL | 18452268.79 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION IV-B | Romblon | 301769 | Odiongan National High School | Odiongan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Romblon | 301772 | San Jose Agricultural Hs | San Jose | 0 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9908607.7105 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION IV-B | Romblon | 301763 | Sta. Fe Nhs | Santa Fe | 0 | 1 | 12 | 3STY12CL | BATCH 13 CL | 22017445.2359 |  |  | Completed | 1 | [11 empty] | NC 2016

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.