## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | NO. OF CL | SCOPE OF WORK | PROJECT ALLOCATION | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
LMS 2020 | Region IX | Isabela City | 305549 | Lampinigan National High School | CITY OF ISABELA (Capital) | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19525553.3757 | 19417116.63 | COMPLETED | 1 | 2021-12-30 | 2022-06-23 | INFRA2021-01 | INFRA2021-01 | July 4-11, 2021 | July 12, 2021 | July 26, 2021 | July 29, 2021 | August 3, 2021 | 2M CONSTRUCTION AND ENTERPRISES
LMS 2020 | Region IX | Zamboanga City | 126155 | Camp Socorro | ZAMBOANGA CITY | 2 | 1 | 4 | PROPOSED CONSTRUCTION ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 22006289 | 21998288.85 | COMPLETED | 1 | 2021-12-04 | 2022-05-04 | 06-0030-21 | 06-0030-21 | 2021-07-02 | 2021-07-09 | 2021-07-21 | 2021-08-11 | 2021-08-21 | Zamboanga 3VC CONSTRUCTION INCORPORATED
LMS 2020 | Region IX | Zamboanga del Norte | 303702 | Sitog NHS Ext - Dabiak | Katipunan | 2 | 1 | 2 | CONSTRUCTION OFONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20686643.261 | 10204006.09 | COMPLETED | 1 | 2021-12-31 | 2021-12-31 | CB 2021-023 | CB 2021-023 | July 1, 2021 | July 9, 2021 | July 22, 2021 | July 27, 2021 | Aug. 4, 2021 | YSL BUILDERS
LMS 2020 | Region IX | Zamboanga del Norte | 303702 | Sitog NHS Ext - Dabiak | Katipunan | 2 |  | 2 | CONSTRUCTION OFONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM |  | 10204006.09 | COMPLETED | 1 | 2021-12-31 | 2021-12-31 | CB 2021-023 | CB 2021-023 | July 1, 2021 | July 9, 2021 | July 22, 2021 | July 27, 2021 | Aug. 4, 2021 | YSL BUILDERS
LMS 2020 | Region IX | Zamboanga del Sur | 124885 | Bag-Ong Mandaue IPS | AURORA | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18695810.1265 | 18684761.34 | COMPLETED | 1 | 2021-12-31 | 2022-03-02 | ZDS- 20- LMS-01 | ZDS- 20- LMS-01 | 2021-07-08 | 2021-07-16 | 2021-07-28 | 2021-08-05 | 2021-08-11 | GENETIAN BUILDERS AND ENTERPRISES INC
LMS 2020 | Region IX | Zamboanga Sibugay | 125746 | San Jose PS | OLUTANGA | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19309086.9083 | 19290632.4 | COMPLETED | 1 | On-going Suspension Order since March 02, 2022 | - | ZSY-2020LMS-01 | ZSY-2020LMS-01 | June 29, 2021 | July 17, 2021 | July 19, 2021 | 2021-07-30 | 2021-08-26 | CPAN Engineering & Enterprises | Change Order (Water Pump Solar Panel) for C.O. approval
LMS 2021 | Region IX | Isabela City | 133031 | Caro ES | CITY OF ISABELA (Capital) | 0 | 1 | 2 | PROPOSED CONSTRUCTION OF (1) ONE STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 10045807.572 | 0 | Ongoing | 0.18 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | PRISMOIDAL CONSRUCTION CORPORATION | CENTRAL OFFICE MANAGED
LMS 2021 | Region IX | Zamboanga City | 126129 | Sapa Dulian ES | ZAMBOANGA CITY | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND OF DRILLING FOR DEEPWELL WATER SYSTEM & SOLAR PUMP | 21293479.9976 | 0 | Ongoing | 0.34 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | PRISMOIDAL CONSRUCTION CORPORATION | CENTRAL OFFICE MANAGED
LMS 2021 | Region IX | Zamboanga City | 126129 | Sapa Dulian ES | ZAMBOANGA CITY | 2 |  | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND OF DRILLING FOR DEEPWELL WATER SYSTEM & SOLAR PUMP | 6520 | 0 | Ongoing | 0.34 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | PRISMOIDAL CONSRUCTION CORPORATION | CENTRAL OFFICE MANAGED
LMS 2021 | Region IX | Zamboanga del Norte | 195529 | Basak ES | SIAYAN | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 10394988.9397 | 0 | Ongoing | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | PRISMOIDAL CONSRUCTION CORPORATION | CENTRAL OFFICE MANAGED
LMS 2021 | Region IX | Zamboanga del Sur | 300000 | Digon National High School | MARGOSATUBIG | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18679356.24 | 0 | ABANDONED | 0.25 | 2022-08-29 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 2022-05-31 | PRISMOIDAL CONSRUCTION CORPORATION | CENTRAL OFFICE MANAGED
LMS 2021 | Region IX | Zamboanga Sibugay | 125639 | Datagan ES | Kabasalan | 2 | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16697503.52 | 0 | Ongoing | 0.38 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | PRISMOIDAL CONSRUCTION CORPORATION | CENTRAL OFFICE MANAGED
LMS 2022 | Region IX | Zamboanga del Norte | 124538 | Head Tipan ES | MUTIA | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 15387438.1528 | 15899497.92 | Completed | 1 | 2023-04-10 | 2023-04-10 | 2022-055-CBZN | CB-2022-039 | 2022-10-28 | 2022-11-07 | 2022-11-18 | 2022-12-01 | 2022-12-07 | YSL BUILDERS | none
LMS 2022 | Region IX | Zamboanga del Norte | 124609 | Nilabo ES | RIZAL | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF 2 UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 21731277.2877 | 22131576 | COMPLETED | 1 | 2022-12-31 | 2023-02-20 | LMS2020-RIX-ZAMBOANGA DEL NORTE | LMS 2022-RIX-ZDN-01 | 2022-04-04 | 2022-04-13 | 2022-04-25 | 2022-05-04 | 2022-06-30 | YSL Builders | none
LMS 2022 | Region IX | Zamboanga del Sur | 125086 | INIGO G. MERCADO PS | JOSEFINA | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18280842.6521 | 17133688.9 | COMPLETED | 1 | 2022-12-26 | 2022-12-19 | ZDS-22-LMS-01 | ZDS-22-LMS-01 | 2023-04-05 | 2023-04-14 | 2023-04-27 | 2023-05-30 | 2023-06-07 | GENETIAN BUILDERS AND ENTERPRISES INC
LMS 2022 | Region IX | Zamboanga Sibugay | 125845 | Bualan ES | TALUSAN | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) UNIT - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 7551146.3957 | 25295175.54 | COMPLETED | 1 | 2024-10-25 | 2025-01-10 | 2023-024-CBZN | CB2023-023 | Nov. 14, 2023 | Nov. 24, 2023 | Dec. 07, 2023 | Dec. 18, 2023 | Dec. 28, 2023 | YSL BUILDERS | 0
LMS 2022 | Region IX | Zamboanga Sibugay | 303871 | Kasigpitan NHS | TALUSAN | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) UNIT - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 7571189.8457 | 18787999.57 | Completed | 1 | 2024-10-25 | 2025-01-10 | ZDS-23-LMS-01 | ZDS-23-LMS-01 | 2023-04-13 | 2023-04-26 | 2023-05-08 | 2023-05-22 | 2023-05-31 | Genetian Builders & Enterprises Inc.
LMS 2022 | Region IX | Zamboanga Sibugay | 314308 | Laparay NHS | TALUSAN | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 11431953.6095 | 18086919.56 | Completed | 1 | 2023-11-04 | 2024-05-03 | ZDS-23-LMS-02 | ZDS-23-LMS-02 | 2023-04-13 | 2023-04-26 | 2023-05-08 | 2023-05-22 | 2023-05-31 | Genetian Builders & Enterprises Inc.
LMS 2022 | Region IX | Zamboanga Sibugay | 125850 | Mahayahay ES | TALUSAN | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) UNIT - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 7540541.3957 | 11154681.24 | Completed | 1 | 2024-10-25 | 2025-01-10 | ZS-2023-LMS-01 | ZS-2023-LMS-01 | 2023-04-04 | 2023-04-17 | 2023-04-28 | 2023-06-23 | 2023-07-07 | Shameem Construction | -
LMS 2023 | Region IX | Zamboanga del Norte | 303714 | Mutia NHS Annex - Tubak | MUTIA | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER SOLAR LIGHT AND SOLAR PV ENERGY SYSTEM | 17166895.91 | 16993668.9 | COMPLETED | 1 | 2023-11-15 | 2023-12-30 | 2023-8-CBZN | CB-2023-008 | 2023-04-05 | 2023-04-14 | 2023-04-27 | 2023-05-30 | 2023-06-07 | YSL BUILDERS
LMS 2023 | Region IX | Zamboanga del Norte | 124547 | Adante ES | PIÑAN (NEW PIÑAN) | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF 2 UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER SOLAR LIGHT, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 25577846.13 | 25295175.54 | COMPLETED | 1 | 2024-06-30 | 2024-11-25 | 2023-024-CBZN | CB2023-023 | Nov. 14, 2023 | Nov. 24, 2023 | Dec. 07, 2023 | Dec. 18, 2023 | Dec. 28, 2023 | YSL BUILDERS
LMS 2023 | Region IX | Zamboanga del Sur | 125307 | Bag-ong Opon Elementary School | RAMON MAGSAYSAY (LIARGO) | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19077138.92 | 18787999.57 | COMPLETED | 1 | 2023-11-04 | 2023-12-14 | ZDS-23-LMS-01 | ZDS-23-LMS-01 | 2023-04-13 | 2023-04-26 | 2023-05-08 | 2023-05-22 | 2023-05-31 | GENETIAN BUILDERS AND ENTERPRISES INC
LMS 2023 | Region IX | Zamboanga del Sur | 124940 | Buburay ES | DIMATALING | 2 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18381376.01 | 18086919.56 | COMPLETED | 1 | 2023-11-04 | 2023-11-30 | ZDS-23-LMS-02 | ZDS-23-LMS-02 | 2023-04-13 | 2023-04-26 | 2023-05-08 | 2023-05-22 | 2023-05-31 | GENETIAN BUILDERS AND ENTERPRISES INC
LMS 2023 | Region IX | Zamboanga Sibugay | 125854 | Talusan CES | TALUSAN | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 13320323.48 | 11154681.24 | COMPLETED | 1 | 2023-11-04 | - | ZS-2023-LMS-01 | ZS-2023-LMS-01 | 2023-04-04 | 2023-04-17 | 2023-04-28 | 2023-06-23 | 2023-07-07 | Shameem Construction
LMS 2024 | Region IX | Dapitan City | 125928 | Daro Elementary School | DAPITAN CITY | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF 2 UNITs ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER SOLAR LIGHT, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 22816847.47 | 22512075.6 | Ongoing | 0.7 | November 14, 2024 | - | SDODAP-INFRA-2023-004 | SDODAP-INFRA-2023-004 | November 14, 2023 | November 21, 2023 | December 07, 2023 | May 06, 2024 | May 17, 2024 | MORTE CONSTRUCTION | -
LMS 2024 | Region IX | Isabela City | 502129 | Badjao Floating Integrated School | CITY OF ISABELA (Capital) | Lone | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19205159.17 | 17785991.82 | Ongoing | 0.58 | 2025-06-27 | - | INFRAEPA2024-01 | - | - | 2024-11-15 | 2023-12-04 | 2024-05-16 | 2024-09-02 | 2M CONSTRUCTION AND ENTERPRISES | NONE
LMS 2024 | Region IX | Pagadian City | 198503 | Bentud Pinukis Penintulan Nu Piksalabukan Subanen | PAGADIAN CITY (Capital) | 1st | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 22198056.48 | 21927158.04 | COMPLETED | 1 | December 04, 2024 | December 04, 2024 | LMS-2024-RIX-PAG-01 | LMS-2024-RIX-PAG-01 | November 13, 2023 | November 21, 2023 | December 04, 2023 | December 11, 2023 | June 03, 2024 | GENETIAN BUILDERS & ENTERPRISES | NONE
LMS 2024 | Region IX | Zamboanga City | 126168 | Pasilmanta ES | ZAMBOANGA CITY | 2nd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 25252525.25 | 24974606.93 | Completed | 1 | November 30, 2024 | 2025-02-13 | LMS 2024 -RIX- ZAMBO CITY - 02 | LMS 2024 -RIX- ZAMBO CITY - 02 | October 30,2023 | November 7, 2023 | November 20,2023 | May 13,2024 | June 03, 2024 | ZAMBOANGA 3VC CONSTRUCTION INC, | With Approved Time Extension
LMS 2024 | Region IX | Zamboanga City | 126133 | Simanta ES | ZAMBOANGA CITY | 2nd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 25252525.25 | 24988205.79 | Completed | 1 | November 30, 2024 | 2025-02-10 | LMS 2024 -RIX- ZAMBO CITY - 01 | LMS 2024 -RIX- ZAMBO CITY - 01 | October 30,2023 | November 7, 2023 | November 20,2023 | May 13,2024 | June 03, 2024 | ZAMBOANGA 3VC CONSTRUCTION INC, | With Approved Time Extension
LMS 2024 | Region IX | Zamboanga City | 126167 | Panganak ES | ZAMBOANGA CITY | 2nd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 25252525.25 | 24980749.43 | Completed | 1 | November 30, 2024 | 2025-05-28 | LMS 2024 -RIX- ZAMBO CITY - 03 | LMS 2024 -RIX- ZAMBO CITY - 03 | October 30,2023 | November 7, 2023 | November 20,2023 | May 13,2024 | June 03, 2024 | ZAMBOANGA 3VC CONSTRUCTION INC, | With Approved Time Extension
LMS 2024 | Region IX | Zamboanga del Norte | 124673 | Tinago ES | SERGIO OSMEÑA SR. | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF 2 UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER SOLAR LIGHT, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 24985083.83 | 25698497.43 | COMPLETED | 1 | November 20, 2024 | 2024-10-30 | 2024-005-CBZN | CB-2024-018 | November 21, 2023 | November 24, 2023 | December 07, 2023 | December 22, 2023 | May 20, 2024 | YSL BUILDERS
LMS 2024 | Region IX | Zamboanga del Norte | 303702 | SITOG NHS - SEROAN EXT. | KATIPUNAN | 2nd | 1 | 4 | PROPOSED CONSTRUCTION OF 2 UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER SOLAR LIGHT, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 24985434.88 | 24704050.49 | COMPLETED | 1 | November 20, 2024 | 2024-10-30 | 2024-006-CBZN | CB-2024-019 | November 21, 2023 | November 24, 2023 | December 07, 2023 | December 22, 2023 | May 20, 2024 | YSL BUILDERS
LMS 2024 | Region IX | Zamboanga del Sur | 125481 | Sto. Rosario Elementary School | TUKURAN | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 23519080.9 | 21703822.5 | COMPLETED | 1 | 2024-12-28 | 2025-03-06 | ZDS-24-LMS-01 | ZDS-24-LMS-01 | 2023-11-13 | 2023-11-21 | 2023-12-04 | 2024-01-03 | 2024-05-22 | R.R. GANDINGAN CONSTRUCTION
LMS 2024 | Region IX | Zamboanga del Sur | 125350 | TAPIAN ES | SAN MIGUEL | 2nd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 22127905.86 | 20576515 | COMPLETED | 1 | 2024-11-18 | 2024-11-15 | ZDS-24-LMS-02 | ZDS-24-LMS-02 | 2023-11-13 | 2023-11-21 | 2023-12-04 | 2024-01-03 | 2024-05-22 | R.R. GANDINGAN CONSTRUCTION
LMS 2024 | Region IX | Zamboanga Sibugay | 303858 | Bulawan NHS | Payao | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 13539348.82 | 12340386.36 | Completed | 1 | October 23, 2024 | March 19, 2025 | ZSY-2024LMS-01 | ZSY-2024LMS-01 | November 22, 2023 | November 29, 2023 | December 15, 2023 | February 28, 2024 | June 26, 2024 | Long Island Builders and Construction | With Approved Time Extension
LMS 2024 | Region IX | Zamboanga Sibugay | 125833 | Paruk ES | Siay | 2nd | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 9316708.43 | 8213612.07 | Completed | 1 | September 24, 2024 | March 19, 2025 | ZSY-2024LMS-02 | ZSY-2024LMS-02 | November 22, 2023 | November 29, 2023 | December 15, 2023 | February 28, 2024 | June 26, 2024 | Long Island Builders and Construction | With Approved Time Extension due to manhauling of construction materials from barangay road to site area

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.