## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
SCHOOL HEALTH FACILITIES 2024 | Region V | Camarines Norte | 112109 | Camacho Aler Elementary School | CAPALONGA | 1st | 1 |  | Construction of Water and Sanitation Facilities - 4-Seater, Rain Water Collector and 10 Faucets Handwashing Facility with Roofing, Counter Tile Finish 2 Units | 1862376 |  | 1844368.38 | COMPLETED | 1 | August 4, 2024 | July 30, 2024 | INFRA07-11-2023CN | INFRA07-11-2023CN | November 7, 2023 | November 15, 2023 | December 5, 2023 | January 16, 2024 | June 5, 2024 | Meltri Construction Services | COMPLETED
SCHOOL HEALTH FACILITIES 2024 | Region V | Iriga City | 114445 | Iriga South CS | IRIGA CITY | 5th | 1 |  | Construction of Group Handwashing Facility - For Elementary 1 Unit (Option 1A - with Roofing, with Counter, with Tile Finish) and 1 Unit (OPTION 3A - One-Sided, without Roofing, with Counter, with Tile Finish) | 586727.75 |  | 586210.48 | COMPLETED | 1 | August 29, 2024 | August 23, 2024 | 2024-01-29-PR-011 | INFRA-24-06-06-001 | February 16, 2024 | February 26, 2024 | March 12, 2024 | March 18, 2024 | June 28, 2024 | Tripartite Eng'g and Construction | completed
SCHOOL HEALTH FACILITIES 2024 | Region V | Ligao City | 111844 | Ligao West CES (Binatagan) | CITY OF LIGAO | 3rd | 1 |  | Construction of School Clinic | 2911074.79 |  | 2906241.32 | COMPLETED | 1 | September 15, 2024 |  | 2023-INFRA-01 | 2023-INFRA-01 | November 20, 2024 | December 4, 2024 | December 18, 2023 | May 15, 2024 | June 3, 2024 | La Abel Construction & Supply
SCHOOL HEALTH FACILITIES 2024 | Region V | Masbate | 113770 | Monreal Central School | MONREAL | 1st | 1 |  | Construction of School Clinic | 3192342.78 |  | 3189548.77 | ongoing | 0.8 | May 27, 2025 |  | INFRA 2024-08-001 | 2024-024 | August 12, 2024 | August 20, 2024 | September 2, 2024 | September 20, 2024 | December 28, 2024 | JOHNCB CONSTRUCTION
SCHOOL HEALTH FACILITIES 2024 | Region V | Masbate | 113876 | San Fernando CS | SAN FERNANDO | 1st | 1 |  | Construction of School Clinic | 3201465.5 |  | 3198180.97 | ongoing | 0.9 | May 27, 2025 |  | INFRA 2024-08-001 | 2024-025 | August 12, 2024 | August 20, 2024 | September 2, 2024 | September 20, 2024 | December 28, 2024 | JOHNCB CONSTRUCTION
SCHOOL HEALTH FACILITIES 2024 | Region V | Masbate | 113900 | San Jacinto CS | SAN JACINTO | 1st | 1 |  | Construction of School Clinic | 3201465.5 |  | 3181448.42 | Completed | 1 | May 27, 2025 |  | INFRA 2024-08-001 | 2024-023 | August 12, 2024 | August 20, 2024 | September 2, 2024 | September 20, 2024 | December 28, 2024 | JOHNCB CONSTRUCTION
SCHOOL HEALTH FACILITIES 2024 | Region V | Sorsogon | 114183 | Vinisitahan ES | DONSOL | 1st | 1 |  | Construction of School Clinic | 2779451.4 |  | 2583307.17 | Completed | 1 | April 24, 2025 | April 24, 2025 | 24-06-002 | 24-06-002 | June 29, 2024 | July 23, 2024 | August 5, 2024 | August 27, 2024 | October 16, 2024 | Golden Tiller Construction and Supply
SCHOOL HEALTH FACILITIES 2022 | Region V | Camarines Norte | 112274 | San Ramon ES | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 6 | Construction Of Handwashing Facilities | 793742 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Camarines Norte | 112264 | L. Opeda Elementary School | SAN VICENTE | 2 | 1 | 4 | Construction Of Handwashing Facilities | 556309 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Camarines Sur | 112759 | Bombon Central School | BOMBON | 2 | 1 | 1 | New Handwashing Facilities | 216359.09 | BATCH 2 |  | Completed | 1 | 2023-10-17 |  | 45085 | 2023-07-030 | 2023-06-14 | 2023-06-21 | 2023-07-03 | 2023-07-07 | 2023-08-18 | Riders Corners Building and Reality Development Corporation
SCHOOL HEALTH FACILITIES 2022 | Region V | Camarines Sur | 112771 | Sto. Domingo Elementary School | BOMBON | 2 | 1 | 1 | New Handwashing Facilities | 216359.09 | BATCH 2 |  | Completed | 1 | 2023-10-17 |  | 45085 | 2023-07-030 | 2023-06-14 | 2023-06-21 | 2023-07-03 | 2023-07-07 | 2023-08-18 | Riders Corners Building and Reality Development Corporation
SCHOOL HEALTH FACILITIES 2022 | Region V | Camarines Sur | 309707 | Siembre High School | BOMBON | 2 | 1 | 1 | New Handwashing Facilities | 216359.09 | BATCH 2 |  | Completed | 1 | 2023-10-17 |  | 45085 | 2023-07-030 | 2023-06-14 | 2023-06-21 | 2023-07-03 | 2023-07-07 | 2023-08-18 | Riders Corners Building and Reality Development Corporation
SCHOOL HEALTH FACILITIES 2022 | Region V | Camarines Sur | 302051 | Sta. Lutgarda HS (Junior High) | Cabusao | 2 | 1 | 1 | Repair of Health Facilities | 569311.19 | BATCH 2 |  | Completed | 1 | 2023-10-17 |  | 45085 | 2023-07-030 | 2023-06-14 | 2023-06-21 | 2023-07-03 | 2023-07-07 | 2023-08-18 | Riders Corners Building and Reality Development Corporation
SCHOOL HEALTH FACILITIES 2022 | Region V | Camarines Sur | 112498 | Camaligan Central School | CAMALIGAN | 2 | 1 | 2 | New Handwashing Facilities | 427582 | BATCH 2 |  | Completed | 1 | 2023-10-17 |  | 45085 | 2023-07-030 | 2023-06-14 | 2023-06-21 | 2023-07-03 | 2023-07-07 | 2023-08-18 | Riders Corners Building and Reality Development Corporation
SCHOOL HEALTH FACILITIES 2022 | Region V | Camarines Sur | 112499 | Dugcal ES | CAMALIGAN | 2 | 1 | 1 | New Handwashing Facilities | 216359.09 | BATCH 2 |  | Completed | 1 | 2023-10-17 |  | 45085 | 2023-07-030 | 2023-06-14 | 2023-06-21 | 2023-07-03 | 2023-07-07 | 2023-08-18 | Riders Corners Building and Reality Development Corporation
SCHOOL HEALTH FACILITIES 2022 | Region V | Camarines Sur | 302052 | Camaligan National High School | CAMALIGAN | 2 | 1 | 2 | New Handwashing Facilities | 427582 | BATCH 2 |  | Completed | 1 | 2023-10-17 |  | 45085 | 2023-07-030 | 2023-06-14 | 2023-06-21 | 2023-07-03 | 2023-07-07 | 2023-08-18 | Riders Corners Building and Reality Development Corporation
SCHOOL HEALTH FACILITIES 2022 | Region V | Camarines Sur | 112779 | Gainza CS - Gainza | GAINZA | 2 | 1 |  | Repair of Health Facilities | 573205.47 | BATCH 2 |  | Completed | 1 | 2023-10-17 |  | 45085 | 2023-07-030 | 2023-06-14 | 2023-06-21 | 2023-07-03 | 2023-07-07 | 2023-08-18 | Riders Corners Building and Reality Development Corporation
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113154 | Bugao Central ES | BAGAMANOC | 2 | 1 | 3 | Construction Of Handwashing Facilities | 371248.36 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113155 | Cahan Bo. Sch. | BAGAMANOC | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113161 | Bagamanoc CES | BAGAMANOC | 2 | 1 | 3 | Construction Of Handwashing Facilities | 371248.36 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113164 | Salvacion ES | BAGAMANOC | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113165 | Suchan Elementary School | BAGAMANOC | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 302072 | Bagamanoc Rural DHS | BAGAMANOC | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113166 | Agban Central Elementary School | BARAS | 2 | 1 | 3 | Construction Of Handwashing Facilities | 371248.36 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113172 | Abihao ES | BARAS | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113173 | Baras CES | BARAS | 2 | 1 | 3 | Construction Of Handwashing Facilities | 371248.36 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113175 | Macutal Elementary School | BARAS | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113176 | Moning Elementary School | BARAS | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 302070 | Agban NHS | BARAS | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 302073 | Baras Rural DHS | BARAS | 2 | 1 | 3 | Construction Of Handwashing Facilities | 371248.36 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113182 | Bato Central Elementary School | BATO | 2 | 1 | 3 | Construction Of Handwashing Facilities | 371248.36 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113192 | Guinobatan Elementay School | BATO | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113195 | Sipi Elementary School | BATO | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 302074 | Bato Rural Development High School | BATO | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 500032 | Cabugao IS | BATO | 2 | 1 | 3 | Construction Of Handwashing Facilities | 371248.36 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 500412 | Bote IS | BATO | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113220 | Gigmoto CES | GIGMOTO | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113221 | San Pedro ES | GIGMOTO | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 302088 | Gigmoto Rural DHS | GIGMOTO | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 500033 | Sicmil Integrated School | GIGMOTO | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113244 | Alinawan ES | PANGANIBAN (PAYO) | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113251 | Maculiw Comm. Sch. | PANGANIBAN (PAYO) | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113252 | Panay Comm. Sch. | PANGANIBAN (PAYO) | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113253 | Panganiban Central Elementary School | PANGANIBAN (PAYO) | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 302095 | Panganiban National High School | PANGANIBAN (PAYO) | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 309801 | Panganiban NHS (CAIC Compound) | PANGANIBAN (PAYO) | 2 | 1 | 3 | Construction Of Handwashing Facilities | 371248.36 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113285 | Alma Elementary School | SAN MIGUEL | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113287 | Caglatawan Elementary School | SAN MIGUEL | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113292 | Pagsangahan Elementary School | SAN MIGUEL | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113298 | J.M.A.-Tucao ES | SAN MIGUEL | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113305 | San Miguel CES | SAN MIGUEL | 2 | 1 | 3 | Construction Of Handwashing Facilities | 371248.36 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 302098 | San Miguel Rural DHS | SAN MIGUEL | 2 | 1 | 3 | Construction Of Handwashing Facilities | 371248.36 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 302099 | Mabato NHS (SMRDHS Annex) | SAN MIGUEL | 2 | 1 | 3 | Construction Of Handwashing Facilities | 371248.36 | BATCH 2 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region V | Masbate | 113484 | Matabao ES | BATUAN | 2 | 1 | 1 | REPAIR OF HEALTH FACILITIES | 725356 | BATCH 2 |  | Completed | 1 | 2024-01-15 |  | INFRA 2023-09-003 | 2023-03-042 | 2023-09-28 | 2023-10-06 | 2023-10-18 | 2023-11-03 | 2023-11-17 | CAMSUR BICOL TRADING INC.
SCHOOL HEALTH FACILITIES 2022 | Region V | Masbate | 500165 | Antonio Lee Llacer Sr. Integrated School | BATUAN | 2 | 1 | 1 | REPAIR OF HEALTH FACILITIES | 610169 | BATCH 2 |  | Completed | 1 | 2024-01-15 |  | INFRA 2023-09-003 | 2023-03-042 | 2023-09-28 | 2023-10-06 | 2023-10-18 | 2023-11-03 | 2023-11-17 | CAMSUR BICOL TRADING INC.
SCHOOL HEALTH FACILITIES 2022 | Region V | Masbate | 113620 | Baras ES | Esperanza | 2 | 1 | 1 | Repair of Health Facilities | 440032 | BATCH 2 |  | Completed | 1 | 2024-01-01 |  | INFRA 2023-09-003 | 2023-11-045 | 2023-09-28 | 2023-10-06 | 2023-10-18 | 2023-11-03 | 2023-11-17 | 3R3M CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region V | Masbate | 113627 | Masbaranon ES | Esperanza | 2 | 1 | 1 | Repair of Health Facilities | 440031 | BATCH 2 |  | Completed | 1 | 2024-01-01 |  | INFRA 2023-09-003 | 2023-11-045 | 2023-09-28 | 2023-10-06 | 2023-10-18 | 2023-11-03 | 2023-11-17 | 3R3M CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region V | Masbate | 113634 | Tawad ES | Esperanza | 2 | 1 | 1 | Repair of Health Facilities | 440031 | BATCH 2 |  | Completed | 1 | 2024-01-01 |  | INFRA 2023-09-003 | 2023-11-045 | 2023-09-28 | 2023-10-06 | 2023-10-18 | 2023-11-03 | 2023-11-17 | 3R3M CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region V | Masbate | 113636 | Villa ES | Esperanza | 2 | 1 | 1 | Repair of Health Facilities | 440031 | BATCH 2 |  | Completed | 1 | 2024-01-01 |  | INFRA 2023-09-003 | 2023-11-046 | 2023-09-28 | 2023-10-06 | 2023-10-18 | 2023-11-03 | 2023-11-17 | JRMG CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region V | Masbate | 302171 | Santos E. Conag National High School | Esperanza | 2 | 1 | 1 | Repair of Health Facilities | 440032 | BATCH 2 |  | Completed | 1 | 2024-01-01 |  | INFRA 2023-09-003 | 2023-11-046 | 2023-09-28 | 2023-10-06 | 2023-10-18 | 2023-11-03 | 2023-11-17 | JRMG CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region V | Masbate | 113863 | Buyo ES | SAN FERNANDO | 2 | 1 | 1 | REPAIR OF HEALTH FACILITIES | 717068 | BATCH 2 |  | Completed | 1 | 2024-01-15 | 2024-01-08 | INFRA 2023-09-003 | 2023-11-043 | 2023-09-28 | 2023-10-06 | 2023-10-18 | 2023-11-03 | 2023-11-16 | CAMSUR BICOL TRADING INC.
SCHOOL HEALTH FACILITIES 2022 | Region V | Masbate | 113872 | P. Basas ES | SAN FERNANDO | 2 | 1 | 1 | REPAIR OF HEALTH FACILITIES | 780368 | BATCH 2 |  | Completed | 1 | 2024-01-15 |  | INFRA 2023-09-003 | 2023-11-043 | 2023-09-28 | 2023-10-06 | 2023-10-18 | 2023-11-03 | 2023-11-16 | CAMSUR BICOL TRADING INC.
SCHOOL HEALTH FACILITIES 2022 | Region V | Masbate | 113873 | Progreso ES | SAN FERNANDO | 2 | 1 | 1 | REPAIR OF HEALTH FACILITIES | 758724 | BATCH 2 |  | Completed | 1 | 2024-01-15 | 2024-01-08 | INFRA 2023-09-003 | 2023-11-044 | 2023-09-28 | 2023-10-06 | 2023-10-18 | 2023-11-03 | 2023-11-16 | CAMSUR BICOL TRADING INC.
SCHOOL HEALTH FACILITIES 2022 | Region V | Masbate | 113881 | Valparaiso ES | SAN FERNANDO | 2 | 1 | 1 | REPAIR OF HEALTH FACILITIES | 710556 | BATCH 2 |  | Completed | 1 | 2024-01-15 |  | INFRA 2023-09-003 | 2023-11-044 | 2023-09-28 | 2023-10-06 | 2023-10-18 | 2023-11-03 | 2023-11-16 | CAMSUR BICOL TRADING INC.
SCHOOL HEALTH FACILITIES 2022 | Region V | Sorsogon | 113987 | Macabari Elementary School | BARCELONA | 2 | 1 | 1 | New Handwashing Facilities | 620000 | BATCH 2 | 409181.1 | COMPLETED | 1 | 2023-06-09 | 2023-10-11 | 23-01-001 | 23-01-001-01 | 2023-01-04 | 2023-01-12 | 2023-01-24 | 2023-01-30 | 2023-02-10 | NJNY Construction and Supply
SCHOOL HEALTH FACILITIES 2022 | Region V | Sorsogon | 302184 | Barcelona National Comprehensive High School | BARCELONA | 2 | 1 | 1 | New Handwashing Facilities | 600000 | BATCH 2 | 395982.07 | Completed | 1 | 2023-06-09 | 2023-08-22 | 23-01-001 | 23-01-001-01 | 2023-01-04 | 2023-01-12 | 2023-01-24 | 2023-01-30 | 2023-02-10 | NJNY Construction and Supply
SCHOOL HEALTH FACILITIES 2022 | Region V | Sorsogon | 302218 | Celso F. Falcotelo National High School | BARCELONA | 2 | 1 | 1 | New Handwashing Facilities | 650000 | BATCH 2 | 428986.32 | Completed | 1 | 2023-06-09 | 2023-08-22 | 23-01-001 | 23-01-001-01 | 2023-01-04 | 2023-01-12 | 2023-01-24 | 2023-01-30 | 2023-02-10 | NJNY Construction and Supply
SCHOOL HEALTH FACILITIES 2022 | Region V | Sorsogon | 114391 | Calao ES | PRIETO DIAZ | 2 | 1 | 1 | New Handwashing Facilities | 650000 | BATCH 2 | 428922.22 | Completed | 1 | 2023-06-17 | 2023-08-04 | 23-01-001 | 23-01-001-02 | 2023-01-04 | 2023-01-12 | 2023-01-24 | 2023-01-30 | 2023-02-10 | NJNY Construction and Supply
SCHOOL HEALTH FACILITIES 2022 | Region V | Sorsogon | 302223 | Manlabong National High School | PRIETO DIAZ | 2 | 1 | 1 | New Handwashing Facilities | 653305.03 | BATCH 2 | 431102.51 | Completed | 1 | 2023-06-17 | 2023-08-04 | 23-01-001 | 23-01-001-02 | 2023-01-04 | 2023-01-12 | 2023-01-24 | 2023-01-30 | 2023-02-10 | NJNY Construction and Supply
SCHOOL HEALTH FACILITIES 2022 | Region V | Sorsogon | 114411 | Salvacion ES | SANTA MAGDALENA | 2 | 1 | 1 | New Handwashing Facilities | 650000 | BATCH 2 | 429065.08 | Completed | 1 | 2023-06-19 | 2023-12-19 | 23-01-001 | 23-01-001-03 | 2023-01-04 | 2023-01-12 | 2023-01-24 | 2023-01-30 | 2023-02-10 | NJNY Construction and Supply
SCHOOL HEALTH FACILITIES 2022 | Region V | Sorsogon | 114416 | Talaonga ES | SANTA MAGDALENA | 2 | 1 | 1 | New Handwashing Facilities | 580000 | BATCH 2 | 382655.47 | Completed | 1 | 2023-06-19 | 2023-12-19 | 23-01-001 | 23-01-001-03 | 2023-01-04 | 2023-01-12 | 2023-01-24 | 2023-01-30 | 2023-02-10 | NJNY Construction and Supply
SCHOOL HEALTH FACILITIES 2022 | Region V | Sorsogon | 302245 | Sta. Magdalena National High School | SANTA MAGDALENA | 2 | 1 | 1 | New Handwashing Facilities | 650000 | BATCH 2 | 429065.46 | Completed | 1 | 2023-06-19 | 2023-12-19 | 23-01-001 | 23-01-001-03 | 2023-01-04 | 2023-01-12 | 2023-01-24 | 2023-01-30 | 2023-02-10 | NJNY Construction and Supply

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%