## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | NO. OF CL | SCOPE OF WORK | PROJECT ALLOCATION | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
LMS 2020 | Region VII | Bohol | 300519 | Mahanay High School | TALIBON | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY -TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 9750782.823 | 7050000 | Completed | 1 | 2022-03-17 | 2022-08-05 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | Inabanga Drilling Conts Steel Fab and Gen Mdse | Request Extension due to destruction of port due to Typhoon Odette(not ganted by the BAC)
LMS 2021 | Region VII | Bogo City | 119105 | Anonang Norte ES | CITY OF BOGO | 4 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 SEATER), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17588188.9435 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0
LMS 2021 | Region VII | Bohol | 117974 | Cansibuan PS | ANTEQUERA | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE | 8051837.57 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | inaugurated (August)
LMS 2021 | Region VII | Bohol | 118473 | Biasong ES | LOON | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE | 9532846.1644 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | inaugurated (August)
LMS 2021 | Region VII | Bohol | 118780 | Carmen Mellijor PS | TUBIGON | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE | 6286948.88 | 0 | Ongoing | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | Site issues
LMS 2021 | Region VII | Bohol | 118349 | Biabas ES | GUINDULMAN | 3 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE | 9289481.37 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0
LMS 2021 | Region VII | Carcar City | 119157 | Cara-atan Elementary School | CITY OF CARCAR | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17400878.67 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0
LMS 2021 | Region VII | Cebu | 118926 | Catang PS | ARGAO | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE | 9541017.1149 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | inaugurated (August)
LMS 2021 | Region VII | Cebu | 118975 | Kaluangan I PS | ASTURIAS | 3 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 10414217.32 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | inaugurated (August)
LMS 2021 | Region VII | Cebu | 119466 | Maharuhay ES | MEDELLIN | 4 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, AND SCHOOL FURNITURE | 6563376.1669 | 0 | Ongoing | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0
LMS 2021 | Region VII | Cebu | 119448 | Palaypay PS | MALABUYOC | 7 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 8618124.5 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | inaugurated (August)
LMS 2021 | Region VII | Danao City | 119352 | Melecio B. Tito ES | DANAO CITY | 5 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET), WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE AND WATER SYSTEM | 9616220.8261 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | inaugurated (August)
LMS 2021 | Region VII | Negros Oriental | 120038 | Canlukduhan ES | AYUNGON | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17295671.81 | 17268197.24 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0
LMS 2021 | Region VII | Negros Oriental | 120303 | Mongpong Primary School | JIMALALUD | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16599217.8707 | 16572079.83 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0
LMS 2021 | Region VII | Negros Oriental | 120482 | Agan-an Elementary School | SIBULAN | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16382034.5205 | 16354914.9 | completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0
LMS 2021 | Region VII | Negros Oriental | 120443 | Antulang Elementary School | SIATON | 3 | 1 | 4 | CONSTRUCTION OF ONE (1) UNIT ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16529232.17 | 16502080.2 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0
LMS 2021 | Region VII | Talisay City | 233505 | Campinsa Elementary School | CITY OF TALISAY | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 10909009.1202 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | inaugurated (August)
LMS 2022 | Region VII | Negros Oriental | 189514 | Guilongsoran Primary School | SAN JOSE | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16249807.0207 | 16152092.89 | Completed | 1 | 2023-07-19 | 2023-07-19 | ITB 2022-10-136 | LMS202211017 | 2022-10-18 | ############# | ############# | ############# | 2022-12-09 | TRINITYCAD CORPORATION | With approved Time Extension & Variation order - extra work.
LMS 2023 | Region VII | Bohol | 117998 | Boyog ES | BALILIHAN | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY-FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMON TOILET) WITH PROVISION OF SCHOOL FURNITURE | 10766058.66 | 10644375.55 | Completed | 1 | 05/15/2024 | 2024-06-11 | PBI 2023-27 | PBI 2023-27 | 2023-07-10 | 2023-07-18 | 2023-08-03 | 2023-10-09 | 2023-11-16 | C. JANSENN CONSTRUCTION AND GENERAL MERCHANDISE | 0
LMS 2023 | Region VII | Bohol | 103611 | Cantumogcad ES | BUENAVISTA | 2 | 1 | 4 | CONSTRUCTION OF 2 UNITS ONE (1) STOREY-TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE | 12125725.66 | 11981920.24 | Completed | 1 | 05/15/2024 | 2024-05-13 | PBI 2023-28 | PBI 2023-28 | 2023-07-10 | 2023-07-18 | 2023-08-03 | 2023-10-09 | 2023-11-16 | C. JANSENN CONSTRUCTION AND GENERAL MERCHANDISE | 0
LMS 2023 | Region VII | Bohol | 117965 | Tanod ES | ANDA | 3 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY-TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE | 6161022.46 | 6032357.5 | Completed | 1 | 4/16/2024 | 2024-06-25 | PBI 2023-29 | PBI 2023-29 | 2023-07-10 | 2023-07-18 | 2023-08-03 | 2023-10-09 | 2023-11-17 | DMAM CONSTRUCTION SERVICES | 0
LMS 2023 | Region VII | Bohol | 118859 | Pangian ES | VALENCIA | 3 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY-TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMON TOILET)WITH PROVISION OF SCHOOL FURNITURE | 6014632.02 | 4452592.82 | Completed | 1 | 4/26/2024 | 2024-06-28 | PBI 2023-30 | PBI 2023-30 | 2023-07-10 | 2023-07-18 | 2023-08-03 | 2023-10-09 | 2023-11-28 | LTS BUILDERS AND CONSTRUCTION SUPPLY | 0
LMS 2023 | Region VII | Cebu | 119061 | Balintawak ES | BANTAYAN | 4 | 1 | 4 | CONSTRUCTION OF 1STY-4CL SCHOOL BUILDING WITH COMMON TOILET WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 11727969.19 | 11561367.39 | Completed | 1 | 2024-09-01 | 2024-09-01 | CY 2023 LMS-R7-CEBU | CY 2023 LMS-R7-CEBU-03 | 2023-07-19 | 2023-07-26 | 2023-08-07 | 2023-08-17 | 31/08/2023 | ROVILLA CONSTRUCTION | 0
LMS 2023 | Region VII | Cebu | 119063 | Guiwanon Elementary School | BANTAYAN | 4 | 1 | 3 | CONSTRUCTION OF 1STY-3CL SCHOOL BUILDING WITH COMMON TOILET WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 9943843.08 | 9794772.39 | Completed | 1 | 25/12/2023 | 25/12/2023 | CY 2023 LMS-R7-CEBU | CY 2023 LMS-R7-CEBU-01 | 2023-07-19 | 2023-07-26 | 2023-08-07 | 2023-08-17 | 31/08/2023 | ROVILLA CONSTRUCTION | 0
LMS 2023 | Region VII | Cebu | 119071 | Vito ES | BANTAYAN | 4 | 1 | 3 | CONSTRUCTION OF 1STY-3CL SCHOOL BUILDING WITH COMMON TOILET WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 9896120.58 | 9745999.34 | Completed | 1 | 25/12/2023 | 25/12/2023 | CY 2023 LMS-R7-CEBU | CY 2023 LMS-R7-CEBU-02 | 2023-07-19 | 2023-07-26 | 2023-08-07 | 2023-08-17 | 31/08/2023 | ROVILLA CONSTRUCTION | 0
LMS 2023 | Region VII | Cebu | 119192 | Francisco S. Villamor Sr.Elementary School | CARMEN | 5 | 1 | 3 | CONSTRUCTION OF 1STY-3CL SCHOOL BUILDING WITH COMMON TOILET WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 9745045.06 | 9618165.28 | Completed | 1 | 2024-03-01 | 2024-01-03 | CY 2023 LMS-R7-CEBU | CY 2023 LMS-R7-CEBU-04 | 2023-07-19 | 2023-07-26 | 2023-08-07 | 2023-08-17 | 2023-12-09 | TRI-BAIRN CONSTRUCTION | 0
LMS 2023 | Region VII | Cebu | 119230 | Magay ES | COMPOSTELA | 5 | 1 | 4 | PROPOSED CONSTRUCTION OF 1STY-4CL SCHOOL BUILDING WITH COMMON TOILET WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 11139089.16 | 10978920.9 | Completed | 1 | 2024-09-01 | 25/12/2023 | CY 2023 LMS-R7-CEBU | CY 2023 LMS-R7-CEBU-06 | 2023-07-19 | 2023-07-26 | 2023-08-07 | 2023-08-17 | 31/08/2023 | BARR STEEL CONSTRUCTION | 0
LMS 2023 | Region VII | Cebu | 501350 | Tag-ubi Integrated School | COMPOSTELA | 5 | 1 | 3 | CONSTRUCTION OF 1STY-3CL SCHOOL BUILDING WITH COMMON TOILET WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 9399879.76 | 7288932.45 | Completed | 1 | 25/12/2023 | 25/12/2023 | CY 2023 LMS-R7-CEBU | CY 2023 LMS-R7-CEBU-05 | 2023-07-19 | 2023-07-26 | 2023-08-07 | 2023-08-17 | 31/08/2023 | ANIELTHON CONSTRUCTION AND SUPPLY | 0
LMS 2024 | Region VII | Cebu | 119637 | TUBOD ES | SAN FERNANDO | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF TWO (2) UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND WATER SYSTEM (DEEP WELL) | 14679322.67 | 10400000 | Ongoing | 0.8 | 28/04/2025 | 00:00:00 | CY 2024 BEFF LMS-DepED-R7-Cebu-01 | CY 2024 BEFF LMS-DepED-R7-Cebu-01 | 2024-11-06 | 18/06/2024 | 2024-02-07 | 16/08/2024 | 22/10/2024 | TRI-BAIRN CONSTRUCTION | 0
LMS 2024 | Region VII | Cebu | 119699 | LIPTONG ES | SANTANDER | 2nd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND WATER SYSTEM (DEEP WELL) | 11508290.01 | 11393207.11 | COMPLETED | 1 | 28/04/2025 | 28/04/2025 | CY 2024 BEFF LMS-DepED-R7-Cebu-02 | CY 2024 BEFF LMS-DepED-R7-Cebu-02 | 2024-11-06 | 18/06/2024 | 2024-02-07 | 16/08/2024 | 22/10/2024 | RT CONSTRUCTION & ENTERPRISES | 0
LMS 2024 | Region VII | Cebu | 118976 | KALUANGAN II | ASTURIAS | 3rd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND WATER SYSTEM (DEEP WELL) | 11508290.01 | 11328208.14 | COMPLETED | 1 | 28/04/2025 | 28/04/2025 | CY 2024 BEFF LMS-DepED-R7-Cebu-03 | CY 2024 BEFF LMS-DepED-R7-Cebu-03 | 2024-11-06 | 18/06/2024 | 2024-02-07 | 16/08/2024 | 22/10/2024 | ANIELTHON CONSTRUCTION & SUPPLY | 0
LMS 2024 | Region VII | Cebu | 119435 | TARONG ES | MADRIDEJOS | 4th | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND WATER SYSTEM (DEEP WELL) | 8027122.46 | 7907423.97 | Ongoing | 0.8 | 29/03/2025 | 00:00:00 | CY 2024 BEFF LMS-DepED-R7-Cebu-04 | CY 2024 BEFF LMS-DepED-R7-Cebu-04 | 2024-11-06 | 18/06/2024 | 2024-02-07 | 16/08/2024 | 22/10/2024 | ROVILLA CONSTRUCTION | 0
LMS 2024 | Region VII | Cebu | 119214 | CAN-IBUANG PS | CATMON | 5th | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND WATER SYSTEM (DEEP WELL) | 8027122.46 | 7900000 | COMPLETED | 1 | 29/03/2025 | 29/03/2025 | CY 2024 BEFF LMS-DepED-R7-Cebu-05 | CY 2024 BEFF LMS-DepED-R7-Cebu-05 | 2024-11-06 | 18/06/2024 | 2024-02-07 | 16/08/2024 | 22/10/2024 | TRI-BAIRN CONSTRUCTION | 0
LMS 2024 | Region VII | Negros Oriental | 120293 | Buto Primary School | JIMALALUD | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 21640739.3 | 18676898.11 | Ongoing | 0.8 | 2025-07-29 | 00:00:00 | ITB 2023-11-145 | LMS202405023 | 2023-11-09 | 2023-11-16 | 2023-11-28 | 2023-12-04 | 2024-05-22 | TrinityCAD Corporation | With approved time extension due to access road issue during rainy days, unworkable weather condition, with change order to cover other essential items(refer to Variation order). Double hauling
LMS 2024 | Region VII | Negros Oriental | 120027 | PANUSUAN ELEMENTARY SCHOOL | AMLAN | 2nd | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15703660.79 | 12964000.46 | COMPLETED | 1 | 2025-02-14 | 2025-02-14 | ITB 2023-11-146 | LMS202405024 | 2023-11-09 | 2023-11-16 | 2023-11-28 | 2023-12-04 | 2024-05-22 | TrinityCAD Corporation | With time extension due to variation orders, cutting of trees permit and unworkable weather condition
LMS 2024 | Region VII | Negros Oriental | 120618 | Nasuji Elementary School | VALENCIA (LUZURRIAGA) | 3rd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 22517074.36 | 19373377.44 | COMPLETED | 1 | 2025-05-15 | 2025-05-13 | ITB 2023-11-147 | LMS202405025 | 2023-11-09 | 2023-11-16 | 2023-11-28 | 2023-12-04 | 2024-05-22 | TrinityCAD Corporation | With time extension
LMS 2024 | Region VII | Siquijor | 120662 | New Corregidor Elementary School | LARENA | Lone | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE | 8295101.98 | 7573374.84 | Ongoing | 0.95 | 2024-11-11 | 2025-05-30 | 10336667 | 2023-89 | 2023-11-22 | 2023-11-29 | 2023-12-11 | 2023-12-12 | 2024-05-16 | Nale Construction | with Time Extension. Revised completion date December 31, 2024
LMS 2024 | Region VII | Talisay City | 119804 | Tapul Elementary School | Talisay City | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 21184978.14 | 20952888 | COMPLETED | 1 | 2025-01-31 | 2025-01-31 | 2024-001 | 45436 | 2024-03-28 | 2024-04-04 | 2024-04-16 | 2024-04-18 | 2024-06-06 | Quirante Construction Corporation | 0
LMS 2024 | Region VII | Toledo City | 120736 | NEW BUCAO ELEMENTARY SCHOOL | TOLEDO | 3rd | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 9772031.96 | 10376058.62 | Ongoing | 0.2 | 2025-07-27 | 00:00:00 | LMS 2023-R VII-TOLEDO CITY-001 | 2024-015 | Mar. 21, 2024 | Mar. 27, 2024 | Apr. 8, 2024 | Apr. 19, 2024 | Feb. 27, 2025 | Tribairn Construction | Late issuance of NTP due to road not passable

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.