## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Program-Year | Status as of July 11, 2025
SHS | REGION VII | Bais City | 303212 | Bais City National High School | Bais City | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 29605866.712 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Bais City | 303212 | Bais City National High School | Bais City | 2 |  | 12 | 4STY12CL | BATCH 11 CL | 22306281.62 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Bais City | 303212 | Bais City National High School | Bais City | 2 |  | 16 | 4STY8CL | BATCH 11 CL | 29841708.82 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bais City | 303215 | Lonoy National High School | Bais City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2685555.5556 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bais City | 323007 | Mansangaban National Hs | Bais City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2685555.5556 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Bais City | 323012 | Mayor Praxedes P. Villanueva Ii Memorial High School | Bais City | 2 | 1 | 2 | 1STY2CL | BATCH 11 CL | 1846080.17 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Bais City | 120103 | Mayor Praxedes P. Villanueva Ii Memorial High School To Sab-Ahan Es | Bais City | 2 |  | 3 | 1STY3CL | BATCH 11 CL | 2802592.44 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bayawan City | 321911 | Abundio Agarpao, Sr. Memorial High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2770365.4 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bayawan City | 303218 | Actin National High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10550902.144 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bayawan City | 321908 | Antonio M. Lacson Sr. Memorial High School | Bayawan City | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6640355.0552 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bayawan City | 321908 | Antonio M. Lacson Sr. Memorial High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2471055.836 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bayawan City | 232001 | Baican Elementary School | Bayawan City | 3 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Bayawan City | 303219 | Bal-Os National High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10794673.288 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bayawan City | 321901 | Banaybanay National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2834174.2 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bayawan City | 303221 | Bayawan National High School | Bayawan City | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bayawan City | 303221 | Bayawan National High School | Bayawan City | 3 |  | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bayawan City | 303238 | Bugay National High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11322844.1 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bayawan City | 303238 | Bugay National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bayawan City | 120146 | Canabuan Elementary School | Bayawan City | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6710417.7692 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Bayawan City | 321912 | Cansumalig High School | Bayawan City | 3 | 1 | 9 | 3STY9CL | BATCH 9 CL | 14492541.4582 |  |  | Reverted | 0 | [10 empty] | Reverted: The project is included in the CY 2018 BEFF | NC 2016
TECHVOC | REGION VII | Bayawan City | 321912 | Cansumalig High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2616153.08 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bayawan City | 303227 | Dawis National High School | Bayawan City | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 33888650.3943 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bayawan City | 303227 | Dawis National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2914753.96 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bayawan City | 120153 | Hag-Um Primary School | Bayawan City | 3 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2147202.5861 |  |  | Reverted | 0 | [10 empty] | Reverted due to Failure of Bidding for the 5th Times | NC 2016
K10 | REGION VII | Bayawan City | 303239 | Kalamtukan National High School | Bayawan City | 3 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9031942.4637 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bayawan City | 303239 | Kalamtukan National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2627533.256 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bayawan City | 303237 | Kalumboyan National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2775682.8 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bayawan City | 120158 | Kangkawit Elementary School | Bayawan City | 3 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2160525.0915 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Bayawan City | 321905 | Lapay High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11221272.79 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bayawan City | 321905 | Lapay High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bayawan City | 321909 | Malabugas High School | Bayawan City | 3 | 1 | 8 | 4STY8CL | BATCH 9 CL | 15236894.0284 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bayawan City | 321909 | Malabugas High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2687150.44 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bayawan City | 303240 | Manduaw National High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11322844.1 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bayawan City | 303240 | Manduaw National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bayawan City | 321903 | Minaba National High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10672787.716 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bayawan City | 321903 | Minaba National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2519421.584 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bayawan City | 303254 | Narra National High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10957187.384 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bayawan City | 303254 | Narra National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2599082.816 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bayawan City | 303256 | Omod National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2775682.8 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bayawan City | 321910 | Pagatban High School | Bayawan City | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6621247.0422 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bayawan City | 321910 | Pagatban High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2462520.704 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bayawan City | 321906 | San Jose High School | Bayawan City | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7156271.404 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bayawan City | 321906 | San Jose High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bayawan City | 303241 | Tabuan Provincial Community High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10916558.86 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bayawan City | 303241 | Tabuan Provincial Community High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2587702.64 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bayawan City | 303242 | Tayawan National High School | Bayawan City | 3 | 1 | 12 | 4STY12CL | BATCH 9 CL | 23296465.4882 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bayawan City | 303242 | Tayawan National High School | Bayawan City | 3 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5613284.576 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bayawan City | 321904 | Villasol High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2892665.6 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Dumaguete City | 303168 | Dumaguete City Hs | Dumaguete City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Dumaguete City | 303168 | Dumaguete City Hs | Dumaguete City (Capital) | 2 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.59 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Dumaguete City | 303169 | Rtpm - Dumaguete Science Hs | Dumaguete City (Capital) | 2 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15095721.2 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Dumaguete City | 303171 | Taclobo Nhs | Dumaguete City (Capital) | 2 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15095721.2 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 303271 | Ajong Nhs | Sibulan | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20057722.149 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 189530 | Alagasihan Primary School | Mabinay | 2 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2722110.255 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 303207 | Amlan National High School | Amlan (Ayuquitan) | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12034916.2399 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 303207 | Amlan National High School | Amlan (Ayuquitan) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 312957 | Amlan Nhs - Jugno Campus | Amlan (Ayuquitan) | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6529337.64 |  |  | Completed | 1 | [10 empty] | For punchlisting on November 25. | NC 2016
TECHVOC | REGION VII | Negros Oriental | 312909 | Apo Island Hs | Dauin | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | REVERTED | 0 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 303224 | Apolinar B. Macias Mhs (Casile Nhs) | Dauin | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120169 | Atotes Es | Bindoy | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2096214.1914 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 303206 | Avocado Chs | Santa Catalina (North District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 303210 | Ayungon Nhs | Ayungon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4560000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Negros Oriental | 303210 | Ayungon Nhs | Ayungon | 1 |  | 4 | 2STY4CL | BATCH 7 CL | 6350000 |  |  | REVERTED | 0 | [11 empty] | NC 2016
SHS | REGION VII | Negros Oriental | 303210 | Ayungon Nhs | Ayungon | 1 | 1 | 15 | 3STY15CL | BATCH 7 CL | 20926500 |  |  | Terminated | 0 | [10 empty] | TERMINATED | NC 2016
K10 | REGION VII | Negros Oriental | 312962 | Ayungon Nhs-(Carol-An Ext.) | Ayungon | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9236461.5561 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 312962 | Ayungon Nhs-(Carol-An Ext.) | Ayungon | 1 |  | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 312949 | Ayungon Sci-Hi | Ayungon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4560000 |  |  | REVERTED | 0 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 312949 | Ayungon Sci-Hi | Ayungon | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6460600 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 312908 | Balugo Nhs | Valencia | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120579 | Banga Es | Tayasan | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2954910.9364 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 303245 | Barras Annex National High School | Mabinay | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6509337.99 |  |  | COMPLETED | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 303222 | Budlasan Hs | Canlaon | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8565000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 312918 | Buntod Hs | Bacong | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2650000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120294 | Cabang Es | Jimalalud | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6470000 |  |  | REVERTED | 0 | [11 empty] | NC 2016
SHS | REGION VII | Negros Oriental | 312917 | Cabcaban Chs | Bindoy | 1 | 1 | 8 | 2STY4CL | BATCH 9 CL | 14072542.8037 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 312917 | Cabcaban Chs | Bindoy | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Terminated | 1 | [10 empty] | Requested for COA inventory dated October 8, 2019, June 8, 2020, December 1, 2020, January 26, 2021 and submitted required documents for inspection dated April 26, 2021 | NC 2016
SHS | REGION VII | Negros Oriental | 312927 | Cambaloctot Hs | San Jose | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6973023.7319 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 312927 | Cambaloctot Hs | San Jose | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 312924 | Campanun-An Provincial Community High School | Mabinay | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12150156.98 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120350 | Campo-Aling Elementary School | Mabinay | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1824740.17 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 312913 | Candugay Hs (Siaton Nhs Annex) | Siaton (East District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 312970 | Caticugan High School | Siaton (West District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Negros Oriental | 312929 | Cawitan Hs | Santa Catalina (North District) | 3 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Negros Oriental | 312929 | Cawitan Hs | Santa Catalina (North District) | 3 |  | 6 | 3STY6CL | BATCH 13 CL | 11443844.661 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Negros Oriental | 303246 | Dahile Pchs | Mabinay | 2 | 1 | 6 | 1STY6CL | BATCH 9 CL | 4787475.839 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120357 | Danawan Elementary School | Mabinay | 2 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2722110.255 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 303225 | Dauin Nhs | Dauin | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Negros Oriental | 303228 | Demetrio L. Alviola Nhs | Bindoy | 1 | 1 | 24 | 3STY12CL | BATCH 7 CL | 37824000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Negros Oriental | 303228 | Demetrio L. Alviola Nhs | Bindoy | 1 |  | 4 | 2STY4CL | BATCH 7 CL | 6350000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 303229 | Demetrio L. Alviola Nhs-(Nalundan Annex) | Bindoy | 1 | 1 | 6 | 1STY3CL | BATCH 9 CL | 5859821.8728 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 303229 | Demetrio L. Alviola Nhs-(Nalundan Annex) | Bindoy | 1 |  | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Negros Oriental | 312907 | Enrique Villanueva Hs | Sibulan | 2 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13018676 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120459 | Felipe Tayko Mes | Siaton (East District) | 3 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11950076.849 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 312921 | Froilan A. Alanano Mhs | Dauin | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 312941 | Giligaon Hs | Siaton (West District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 312904 | Guba Hs | Vallehermoso | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8600000 |  |  | REVERTED | 0 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 312904 | Guba Hs | Vallehermoso | 1 |  | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | REVERTED | 0 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 312904 | Guba Hs | Vallehermoso | 1 |  | 3 | 1STY3CL | BATCH 9 CL | 2904910.9364 |  |  | REVERTED | 0 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120360 | Himocdungon Elementary School | Mabinay | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 303234 | Inapoy High School | Mabinay | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9169325.9361 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 303234 | Inapoy High School | Mabinay | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4834000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 303208 | Jantianon National High School | Amlan (Ayuquitan) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6985386.5109 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Negros Oriental | 303235 | Jimalalud Nhs | Jimalalud | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 16618460.712 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Negros Oriental | 303235 | Jimalalud Nhs | Jimalalud | 1 |  | 4 | 2STY4CL | BATCH 13 CL | 7086271.404 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 312922 | Jimalalud Nhs- (Tamao Ext.) | Jimalalud | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8500000 |  |  | REVERTED | 0 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120032 | Jose B. Cardenas Mhs (Main) To Awa-An Es | Canlaon | 1 | 1 | 2 | 1STY2CL |  | 1996214.19 |  |  | REVERTED | 0 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120199 | Jose B. Cardenas Mhs (Main) To Binalbagan Es | Canlaon | 1 | 1 | 6 | 1STY3CL | BATCH 9 CL | 5909821.87 |  |  | Completed | 1 |  |  | 16GK0106 | 16GK0106 |  | 2016-08-25 | 2016-09-02 | 2016-09-15 |  |  |  | NC 2016
K10 | REGION VII | Negros Oriental | 120580 | Jose B. Cardenas Mhs (Main) To Cambaye Es | Canlaon | 1 | 1 | 9 | 1STY3CL |  | 8864732.82 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 312965 | Jose B. Cardenas Mhs (Main) To Jbcmhs-Pula Ext. | Canlaon | 1 | 1 | 4 | 2STY4CL |  | 6470000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120389 | Jose B. Cardenas Mhs (Main) To Lamogong Es | Canlaon | 1 | 1 | 3 | 1STY3CL |  | 2954910.94 |  |  | REVERTED | 0 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120210 | Jose B. Cardenas Mhs (Main) To Manggapa Ps | Canlaon | 1 | 1 | 4 | 2STY4CL |  | 6470000 |  |  | REVERTED | 0 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 312966 | Jose B. Cardenas Mhs (Main) To Manjuyod Nhs- Panciao Ext. | Canlaon | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4 |  |  | REVERTED | 0 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120184 | Jose B. Cardenas Mhs (Main) To Manseje Es | Canlaon | 1 | 1 | 1 | 1STY2CL |  | 1996214.19 |  |  | REVERTED | 0 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120591 | Jose B. Cardenas Mhs (Main) To Matuog Es | Canlaon | 1 | 1 | 4 | 2STY4CL |  | 6350000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120303 | Jose B. Cardenas Mhs (Main) To Mongpong Es | Canlaon | 1 | 1 | 1 | 1STY2CL |  | 1990000 |  |  | REVERTED | 0 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120052 | Jose B. Cardenas Mhs (Main) To Nabhang Es | Canlaon | 1 | 1 | 2 | 1STY2CL |  | 2096214.19 |  |  | REVERTED | 0 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120189 | Jose B. Cardenas Mhs (Main) To Pagsalayon Es | Canlaon | 1 | 1 | 1 | 1STY3CL |  | 2990000 |  |  | REVERTED | 0 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120398 | Jose B. Cardenas Mhs (Main) To Sacsac Es | Canlaon | 1 | 1 | 4 | 2STY4CL |  | 6470000 |  |  | Terminated | 1 | [10 empty] | TERMINATED | NC 2016
K10 | REGION VII | Negros Oriental | 120334 | Jose B. Cardenas Mhs (Main) To Solonggon Es | Canlaon | 1 | 1 | 4 | 1STY2CL |  | 3935000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120599 | Jose B. Cardenas Mhs (Main) To Suquib Es | Canlaon | 1 | 1 | 4 | 1STY2CL |  | 1990000 |  |  | REVERTED | 0 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120308 | Jose B. Cardenas Mhs (Main) To Tamao Es | Canlaon | 1 | 1 | 1 | 1STY3CL |  | 2995428.31 |  |  | REVERTED | 0 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120404 | Jose B. Cardenas Mhs (Main) To Tanglad Es | Canlaon | 1 | 1 | 1 | 1STY3CL |  | 2954910.94 |  |  | REVERTED | 0 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120059 | Jose B. Cardenas Mhs (Main) To Tiguib Es | Canlaon | 1 | 1 | 1 | 2STY10CL |  | 3935000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120218 | Jose B. Cardenas Mhs (Main) To Upper Lumapao Es | Canlaon | 1 | 1 | 6 | 2STY6CL |  | 8565000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 312963 | Jose B. Cardenas Mhs-(Tabalogo Ext.) | Canlaon | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8600000 |  |  | REVERTED | 0 |  |  | 16GK0071 | 16GK0071 | 2391819 | 2016-06-06 | 2016-06-24 | 2016-07-07 | 2016-07-13 | 42580 |  | NC 2016
K10 | REGION VII | Negros Oriental | 312916 | Jose B. Cardenas Mhs-(Uptown Annex) | Canlaon | 1 | 1 | 6 | 1STY3CL | BATCH 9 CL | 5909821.8728 |  |  | Completed | 1 |  |  | 16GK0073 | 16GK0073 | 2037829 | 2016-06-06 | 2016-06-24 | 2016-07-07 | 2016-07-13 | 42580 |  | NC 2016
K10 | REGION VII | Negros Oriental | 312916 | Jose B. Cardenas Mhs-(Uptown Annex) | Canlaon | 1 |  | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 |  |  | 16GK0080 | 16GK0080 |  | 2016-07-08 | 2016-07-15 | 2016-07-29 |  |  |  | NC 2016
TECHVOC | REGION VII | Negros Oriental | 312916 | Jose B. Cardenas Mhs-(Uptown Annex) | Canlaon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 |  |  | 16GK0074 | 16GK0074 | 2037830 | 2016-06-06 | 2016-06-24 | 2016-07-07 | 2016-07-13 | 42580 |  | NC 2016
TECHVOC | REGION VII | Negros Oriental | 312933 | Kakha Hs | Santa Catalina (North District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 312903 | Kausawagan Hs | Manjuyod | 1 | 1 | 9 | 3STY9CL | BATCH 7 CL | 14300000 |  |  | Completed | 1 |  |  | 16GK0126 | 16GK0126 |  |  | 2016-10-20 | 2016-11-03 |  |  |  | NC 2016
K10 | REGION VII | Negros Oriental | 303243 | La Liberta Tech-Voc School | La Libertad | 1 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26845224.6319 |  |  | Completed | 1 |  |  | 16GK0070 | 16GK0070 |  | 2016-06-06 |  |  | 2016-07-13 | 42580 | SOME PUNCHLISTED ITEMS NOT YET RECTIFIED; With letter to DPWH 1st for an updates/ follow-up | NC 2016
K10 | REGION VII | Negros Oriental | 189523 | Lanot Elementary School | Mabinay | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 303277 | Mabato Pchs | Ayungon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 |  |  | 16GK0107 | 16GK0107 |  | 2016-08-26 | 2016-09-07 |  |  |  |  | NC 2016
SHS | REGION VII | Negros Oriental | 303244 | Mabinay National High School | Mabinay | 2 | 1 | 24 | 4STY12CL | BATCH 1 CL | 45397981.68 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Negros Oriental | 312951 | Mabinay Science High School | Mabinay | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6509338 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Negros Oriental | 312954 | Malaiba Hs | Canlaon | 1 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15121327.92 |  |  | Completed | 1 |  |  | 16GK0118 | 16GK0118 |  |  | 2016-10-06 | 2016-10-18 |  |  |  | NC 2016
TECHVOC | REGION VII | Negros Oriental | 303253 | Maloh Pchs | Siaton (West District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 312919 | Malongcay Dacu Hs | Dauin | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120367 | Mampalasan Elementary School | Mabinay | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1829740.17 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Negros Oriental | 312901 | Maningcao Nhs | Sibulan | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9063478.3861 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Negros Oriental | 303251 | Manjuyod Nhs | Manjuyod | 1 | 1 | 24 | 3STY12CL | BATCH 9 CL | 37737000 |  |  | Completed | 1 |  |  | 16GK0086 | 16GK0086 | 2391399 | 2016-07-14 | 2016-07-21 | 2016-08-04 | 2016-08-10 | 42608 |  | NC 2016
SHS | REGION VII | Negros Oriental | 303251 | Manjuyod Nhs | Manjuyod | 1 |  | 4 | 2STY4CL | BATCH 9 CL | 6350000 |  |  | Completed | 1 |  |  | 16GK0102 | 16GK0102 |  | 2016-08-18 | 2016-08-25 | 2016-09-08 |  |  |  | NC 2016
K10 | REGION VII | Negros Oriental | 120185 | Mantahaw Es | Bindoy | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2096214.1914 |  |  | Terminated | 0 |  |  | 16GK0105 | 16GK0105 | [6 empty] | TERMINATED | NC 2016
K10 | REGION VII | Negros Oriental | 120185 | Mantahaw Es | Bindoy | 1 |  | 1 | 1STY1CL | BATCH 9 CL | 1100000 |  |  | Terminated | 0 |  |  | 16GK0088 | 16GK0088 |  | 2016-08-02 |  |  |  |  | TERMINATED | NC 2016
TECHVOC | REGION VII | Negros Oriental | 303252 | Maria Macahig Nhs | Siaton (West District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 |  |  |  | 16GK0117 |  | 2016-09-23 | 2016-10-07 |  |  |  |  | NC 2016
SHS | REGION VII | Negros Oriental | 312955 | Masulog Hs | Canlaon | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8264965.051 |  |  | Completed | 1 |  |  | 16GK0099 | 16GK0099 |  | 2016-08-18 | 2016-08-25 | 2016-09-08 |  |  |  | NC 2016
K10 | REGION VII | Negros Oriental | 312959 | Mayaposi Community High School | Mabinay | 2 | 1 | 16 | 2STY8CL | BATCH 9 CL | 24190839.3617 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 312959 | Mayaposi Community High School | Mabinay | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 312932 | Milagrosa Hs | Santa Catalina (South District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Negros Oriental | 303255 | Negros Oriental Nhs | Dumaguete City | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 28732387.793 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Negros Oriental | 303255 | Negros Oriental Nhs | Dumaguete City | 2 |  | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 303264 | Obat Hs | Santa Catalina (North District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 303257 | Owacan Pchs | Jimalalud | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9171461.555 |  |  | Completed | 1 |  |  | 16GK0100 | 16GK0100 |  | 2016-08-18 | 2016-08-25 | 2016-09-08 |  |  |  | NC 2016
K10 | REGION VII | Negros Oriental | 120305 | Pacuan Es | Jimalalud | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6450000 |  |  | REVERTED | 0 | [11 empty] | NC 2016
SHS | REGION VII | Negros Oriental | 303258 | Pacuan Nhs | La Libertad | 1 | 1 | 12 | 3STY12CL | BATCH 13 CL | 20279495.669 |  |  | REVERTED | 0 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 303247 | Paniabonan High School | Mabinay | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 5702403.8743 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 303247 | Paniabonan High School | Mabinay | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12150156.9809 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 312912 | Pedro R. Abul Mhs | Santa Catalina (South District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | REVERTED | 0 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 303261 | Pinalubngan Nhs | Tayasan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4560000 |  |  | Completed | 1 |  |  | 16GK0078 | 16GK0078 |  | 2016-06-06 | 2016-06-24 | 2016-07-07 | 2016-07-13 | 42580 |  | NC 2016
SHS | REGION VII | Negros Oriental | 303261 | Pinalubngan Nhs | Tayasan | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6600000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 312960 | Pinocauan Hs | Vallehermoso | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4560000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 312960 | Pinocauan Hs | Vallehermoso | 1 | 1 | 12 | 2STY6CL | BATCH 7 CL | 16900000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120596 | Pinocawan Es | Tayasan | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6450000 |  |  | Terminated | 0 | [10 empty] | TERMINATED | NC 2016
K10 | REGION VII | Negros Oriental | 120375 | Samac Elementary School | Mabinay | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 312902 | Sampiniton Pchs | Manjuyod | 1 |  | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 312902 | Sampiniton Pchs | Manjuyod | 1 | 1 | 8 | 2STY4CL | BATCH 9 CL | 12900000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Negros Oriental | 303272 | San Antonio National High School | Sibulan | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6536047.22 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120435 | San Jose Provincial High School To Alicia Calumpang (Naiba Es) | San Jose | 2 | 1 | 3 | 1STY3CL |  | 3946432.02 |  |  | REVERTED | 0 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120435 | San Jose Provincial High School To Alicia Calumpang (Naiba Es) | San Jose | 2 |  | 2 | 1STY2CL |  | 2758293.02 |  |  | REVERTED | 0 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120432 | San Jose Provincial High School To Cancawas Ps | San Jose | 2 | 1 | 3 | 1STY3CL |  | 3946432.02 |  |  | REVERTED | 0 | [11 empty] | NC 2016
SHS | REGION VII | Negros Oriental | 189514 | San Jose Provincial High School To Guilongsoran Ps | San Jose | 2 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3946432.02 |  |  | REVERTED | 0 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 312934 | San Miguel Hs | Santa Catalina (North District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 303266 | San Miguel Nhs | Bacong | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Negros Oriental | 312928 | Siapo Hs | San Jose | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9063478.3861 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 303268 | Siaton Nhs | Siaton (East District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Negros Oriental | 312945 | Sibulan Nhs - Balugo Ext. | Sibulan | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6973023.7319 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 312944 | Sibulan Science High School | Sibulan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2507271.0901 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 312935 | Sta. Catalina Science Hs | Santa Catalina (North District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 312942 | Sumaliring Hs [Inalad Hs] | Siaton (East District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 303275 | Tagbino Nhs | Vallehermoso | 1 | 1 | 12 | 3STY12CL | BATCH 11 CL | 18222268.79 |  |  | Completed | 1 |  |  |  | 16GK0110 |  | 2016-09-23 | 2016-10-05 |  |  |  |  | NC 2016
SHS | REGION VII | Negros Oriental | 303276 | Tambo Nhs | Ayungon | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8500000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 312930 | Tamlang Hs | Santa Catalina (North District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 303278 | Tampi National High School | San Jose | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 7408468.5459 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 303278 | Tampi National High School | San Jose | 2 |  | 8 | 2STY8CL | BATCH 9 CL | 9804608.3325 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120438 | Tapon Norte Elementary School To Siapo Es | Mabinay | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | REVERTED | 0 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120378 | Tara Elementary School | Mabinay | 2 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2722110.255 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 303248 | Tara Provincial Community High School | Mabinay | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 303290 | Tayasan Nhs- (Bago Campus) | Tayasan | 1 |  | 3 | 1STY3CL | BATCH 9 CL | 2640828.124 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 303290 | Tayasan Nhs- (Bago Campus) | Tayasan | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8550000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 312950 | Tayasan Science Hs | Tayasan | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 14200000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120485 | Tubigon High School To Calabnugan Es | Sibulan | 2 | 1 | 2 | 1STY2CL |  | 2704325.77 |  |  | REVERTED | 0 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 120490 | Tubigon High School To Looc Es | Sibulan | 2 | 1 | 6 | 1STY3CL | BATCH 7 CL | 7862805.74 |  |  | REVERTED | 0 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 303291 | Valencia Nhs (Valencia Tech. Sch.) | Valencia | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Negros Oriental | 303292 | Vallehermoso Pchs | Vallehermoso | 1 | 1 | 36 | 3STY12CL | BATCH 7 CL | 56392400 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Negros Oriental | 303292 | Vallehermoso Pchs | Vallehermoso | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 9120000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Tanjay City | 322303 | Nagsala Hs | City Of Tanjay | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2716157.6507 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Tanjay City | 322303 | Nagsala Hs | City Of Tanjay | 2 | 1 | 8 | 2STY8CL | BATCH 11 CL | 10877342.5917 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bogo City | 119115 | Anonang Sur Es | City Of Bogo | 4 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bogo City | 302933 | Don Potenciano | City Of Bogo | 4 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bogo City | 302934 | Jovencio N. Masong Nhs | City Of Bogo | 4 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10417131.51 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Bogo City | 302936 | Libertad Nhs | City Of Bogo | 4 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.05 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bohol | 302883 | Calape National High School | Calape | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9111461.555 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Bohol | 302872 | Lourdes Nhs | Panglao | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.59 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bohol | 302830 | Cangawa Nhs | Buenavista | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Bohol | 302830 | Cangawa Nhs | Buenavista | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bohol | 302892 | Inabanga Hs- Nabuad | Inabanga | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bohol |  | Lonoy Ps | Inabanga | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bohol | 302873 | Mahayag National High School | San Miguel | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bohol | 302893 | San Jose Nhs | Talibon | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Bohol | 302893 | San Jose Nhs | Talibon | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Bohol | 302897 | San Miguel Technical Vocational School | San Miguel | 2 | 1 | 12 | 2STY6CL | BATCH 13 CL | 18042923.11 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Bohol | 118409 | Tungod Ps | Inabanga | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bohol | 302809 | Alicia Technical-Voc'L Hs | Alicia | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Bohol | 302884 | Pilar Technical-Vocational Hs | Pilar | 3 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Bohol | 302901 | San Roque National High School | Mabini | 3 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Bohol | 302905 | Sierra Bullones Technical Vocational High School | Sierra Bullones | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2656428.32 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Bohol | 302916 | Valencia Tech-Voc Hs | Valencia | 3 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Carcar City | 302970 | Can-Asujan Nhs | City Of Carcar | 1 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Carcar City | 119179 | Maximina V. Barangan Es (Mercado) | City Of Carcar | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 303093 | Sangat Nhs | San Fernando | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu | 302985 | Argao National High School | Argao | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 302985 | Argao National High School | Argao | 2 | 1 | 20 | 4STY20CL | BATCH 13 CL | 34198179.297 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 302921 | Badian Nhs | Badian | 2 | 1 | 12 | 4STY12CL | BATCH 13 CL | 24352577.982 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 302925 | Bala Nhs | Moalboal | 2 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10717131.51 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu | 302940 | Bitoon Nvhs | Dumanjug | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 302940 | Bitoon Nvhs | Dumanjug | 2 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Cebu | 303124 | Calagasan National High School | Argao | 2 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6520624.0402 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu | 303124 | Calagasan National High School | Argao | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2505000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Cebu | 118947 | Colawin Es | Argao | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6650000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Cebu | 302997 | Dalaguete National High School | Dalaguete | 2 | 1 | 20 | 4STY20CL | BATCH 13 CL | 34198179.297 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu | 302941 | Dumanjug Nhs | Dumanjug | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu | 303000 | Mantalongon Nhs | Dalaguete | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2445000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Cebu | 303000 | Mantalongon Nhs | Dalaguete | 2 | 1 | 12 | 2STY12CL | BATCH 13 CL | 16172138.898 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Cebu | 303000 | Mantalongon Nhs | Dalaguete | 2 |  | 10 | 2STY10CL | BATCH 13 CL | 12836310.09 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 303098 | Santander Nhs | Santander | 2 | 1 | 12 | 3STY12CL | BATCH 11 CL | 18559207.2002 |  |  | Completed | 1 | [10 empty] | Slow Progress | NC 2016
SHS | REGION VII | Cebu | 302919 | Aloguinsan Nhs | Aloguinsan | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 302919 | Aloguinsan Nhs | Aloguinsan | 3 |  | 6 | 3STY6CL | BATCH 9 CL | 10417131.51 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 303069 | Bartolome & Manuela Pañares Mnhs | Barili | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 303069 | Bartolome & Manuela Pañares Mnhs | Barili | 3 |  | 18 | 3STY9CL | BATCH 9 CL | 30242655.84 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 303069 | Bartolome & Manuela Pañares Mnhs | Barili | 3 |  | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 302945 | Buanoy Nhs | Balamban | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31152890.27 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 302945 | Buanoy Nhs | Balamban | 3 |  | 12 | 4STY12CL | BATCH 9 CL | 22182343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 302947 | Gaas Nhs | Balamban | 3 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10567131.51 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu | 312404 | Jose Chona Jo Memorial National High School | Balamban | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Cebu | 312404 | Jose Chona Jo Memorial National High School | Balamban | 3 | 1 | 12 | 4STY12CL | BATCH 13 CL | 24352577.982 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu | 312453 | Kalangahan Nhs | Tuburan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2758700 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu | 303029 | Lamac Nhs | Pinamungahan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2808700 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu | 303044 | Looc Norte Nhs | Asturias | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2470000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 303078 | Lut-Od Nhs | Pinamungahan | 3 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22352343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Cebu | 302949 | Nangka National High School | Balamban | 3 | 1 | 24 | 4STY12CL | BATCH 9 CL | 44304687.24 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 303075 | Pinamungajan Nhs | Pinamungahan | 3 | 1 | 36 | 4STY12CL | BATCH 9 CL | 67820975.64 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu | 303075 | Pinamungajan Nhs | Pinamungahan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 312412 | Pinamungajan Nhs - Night | Pinamungahan | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10417131.51 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 303097 | Santa Lucia Nhs | Asturias | 3 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu | 312414 | Sta. Rita Nhs | Asturias | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2530000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 302938 | Bantayan Nhs | Bantayan | 4 | 1 | 20 | 4STY20CL | BATCH 9 CL | 32902890.27 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 302938 | Bantayan Nhs | Bantayan | 4 |  | 16 | 4STY16CL | BATCH 9 CL | 28202469.42 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 302938 | Bantayan Nhs | Bantayan | 4 |  | 8 | 4STY8CL | BATCH 9 CL | 15747518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu | 302938 | Bantayan Nhs | Bantayan | 4 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5084000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 302995 | Daanbantayan Nhs | Daanbantayan | 4 | 1 | 20 | 4STY20CL | BATCH 5 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 302995 | Daanbantayan Nhs | Daanbantayan | 4 |  | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 303047 | Madridejos Nhs | Madridejos | 4 | 1 | 40 | 4STY20CL | BATCH 5 CL | 65905780.54 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 312409 | Patao Nhs | Bantayan | 4 | 1 | 20 | 4STY20CL | BATCH 5 CL | 32902890.27 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 312409 | Patao Nhs | Bantayan | 4 |  | 9 | 3STY9CL | BATCH 5 CL | 16011327.92 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu | 312409 | Patao Nhs | Bantayan | 4 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 5110000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Cebu | 303087 | San Remigio Nhs | San Remigio | 4 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Cebu | 303087 | San Remigio Nhs | San Remigio | 4 |  | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu | 303087 | San Remigio Nhs | San Remigio | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 303094 | Santa Fe Nhs | Santa Fe | 4 | 1 | 16 | 4STY8CL | BATCH 5 CL | 31495037.68 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu | 303094 | Santa Fe Nhs | Santa Fe | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2550000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 312476 | Sulangan Is | Bantayan | 4 | 1 | 8 | 4STY8CL | BATCH 5 CL | 15747518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu | 303091 | Arcelo Mnhs | Liloan | 5 | 1 | 40 | 4STY20CL | BATCH 9 CL | 62305780.54 |  |  | Completed | 1 |  |  |  | 16HI0038 | [5 empty] | ARN BUILDERS |  | NC 2016
SHS | REGION VII | Cebu | 303091 | Arcelo Mnhs | Liloan | 5 |  | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16HI0039 | [5 empty] | ARN BUILDERS |  | NC 2016
SHS | REGION VII | Cebu | 302967 | Camotes National High School | San Francisco | 5 | 1 | 6 | 3STY6CL | BATCH 13 CL | 10417131.51 |  |  | Completed | 1 |  |  |  | 16HI0069 | [5 empty] | C. LARA CONSTRUCTION |  | NC 2016
SHS | REGION VII | Cebu | 119196 | Carmen Nhs-Day To Luyang Es | Carmen | 5 | 1 | 40 | 4STY20CL | BATCH 5 CL | 62285780.54 |  |  | Completed | 1 |  |  |  | 17HI0043 | [5 empty] | PRAGMATIC DEV'T. CONST. CORP |  | NC 2016
SHS | REGION VII | Cebu | 302978 | Catmon Nhs | Catmon | 5 | 1 | 6 | 2STY6CL | BATCH 11 CL | 8214965.05 |  |  | Completed | 1 |  |  |  | 16HI0070 | [5 empty] | YES CONSTRUCTION |  | NC 2016
K10 | REGION VII | Cebu | 119226 | Compostela National High School(Day Class) To Compostela Cs | Compostela | 5 | 1 | 40 | 4STY20CL | BATCH 9 CL | 62205780.54 |  |  | Completed | 1 |  |  |  | 17HI0042 | [5 empty] | EDISON DEVELOPMENT CORP |  | NC 2016
TECHVOC | REGION VII | Cebu | 119226 | Compostela National High School(Day Class) To Compostela Cs | Compostela | 5 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4860000 |  |  | Completed | 1 |  |  |  | 17HI0053 | [5 empty] | BT CONSTRUCTION |  | NC 2016
SHS | REGION VII | Cebu | 303109 | Liki Nhs | Sogod | 5 | 1 | 8 | 4STY8CL | BATCH 5 CL | 14977518.84 |  |  | Completed | 1 |  |  |  | 16HI0049 | [5 empty] | JO BUILDERS | Slow Progress | NC 2016
TECHVOC | REGION VII | Cebu | 303109 | Liki Nhs | Sogod | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2460000 |  |  | Completed | 1 |  |  |  | 16HI0031 | [5 empty] | FIRST GRANDUER BUILDERS |  | NC 2016
SHS | REGION VII | Cebu | 119419 | Liloan Nhs To Suba Es | Liloan | 5 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16HI0067 | [5 empty] | DUROS DEVELOPMENT CORP. |  | NC 2016
SHS | REGION VII | Cebu | 303114 | Tayud Nhs | Consolacion | 6 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31102890.27 |  |  | Completed | 1 | [10 empty] | Slow Progress | NC 2016
SHS | REGION VII | Cebu | 302993 | Tugbongan Nhs | Consolacion | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 15147518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Cebu City | 119926 | Agsungot Es | Cebu City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu City | 312502 | Babag Hs | Cebu City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 | [10 empty] | incomplete (DPWH request additional fund due to site development problem occurred during construction phase) | NC 2016
SHS | REGION VII | Cebu City | 303152 | Barrio Luz Nhs (Day & Night) | Cebu City (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 9 CL | 29357716.362 |  |  | COMPLETED | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu City | 303134 | Bonbon Nhs | Cebu City (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9121461.5561 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu City | 303134 | Bonbon Nhs | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu City | 303143 | Bulacao Community Hs (Day & Night) | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Cebu City | 303143 | Bulacao Community Hs(Day & Night) | Cebu City (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Cebu City | 119891 | Busay Elementary School | Cebu City (Capital) | 1 | 1 | 12 | 3STY12CL | BATCH 13 CL | 20029495.669 |  |  | Completed | 1 | [10 empty] | subject for termination (for re bid) due to MGB report of sinkholes | NC 2016
K10 | REGION VII | Cebu City | 303138 | Camp Lapu-Lapu Nhs(Day & Night) | Cebu City (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Cebu City | 303153 | City Central Nhs(Day & Night) | Cebu City (Capital) | 1 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1 | [10 empty] | Works has been resume by DPWH started on June 3, 2019 | NC 2016
K10 | REGION VII | Cebu City | 303153 | City Central Nhs(Day & Night) | Cebu City (Capital) | 1 |  | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1 | [10 empty] | Schedule for turnover after rectification works be completed | NC 2016
K10 | REGION VII | Cebu City | 303142 | Don Carlos A. Gothong Memorial Nhs | Cebu City (Capital) | 2 | 1 | 24 | 4STY12CL | BATCH 9 CL | 45900000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu City | 303142 | Don Carlos A. Gothong Memorial Nhs | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu City | 303150 | Don Sergio Osme¤A, Sr. Memorial Hs (Day & Night) | Cebu City (Capital) | 2 | 1 | 32 | 4STY16CL | BATCH 9 CL | 58715432.724 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu City | 303150 | Don Sergio Osme¤A, Sr. Memorial Hs (Day & Night) | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu City | 303133 | Don Vicente Rama Mem. Nhs (Basak Nhs) | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [10 empty] | Incomplete (only complete based on POW) | NC 2016
K10 | REGION VII | Cebu City | 303133 | Don Vicente Rama Mem. Nhs(Basak Nhs) | Cebu City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 29357716.362 |  |  | Completed | 1 | [10 empty] | DPWH follow up/pressure the contractor and gave the contractor an ultimatum or face legal action | NC 2016
K10 | REGION VII | Cebu City | 303133 | Don Vicente Rama Mem. Nhs(Basak Nhs) | Cebu City (Capital) | 2 |  | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [10 empty] | DPWH follow up/pressure the contractor and gave the contractor an ultimatum or face legal action | NC 2016
K10 | REGION VII | Cebu City | 119886 | Labangon Elementary School | Cebu City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1 | [10 empty] | Schedule for turnover after rectification works be completed | NC 2016
K10 | REGION VII | Cebu City | 303139 | Lahug Nhs(Night) | Cebu City (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 9 CL | 29357716.362 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu City | 303132 | Lusaran Nhs | Cebu City (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 5 CL | 10350000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu City | 303158 | Mabini Integrated School | Cebu City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu City | 303151 | Mabolo National High School | Cebu City (Capital) | 1 | 1 | 32 | 4STY16CL | BATCH 9 CL | 58715432.724 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu City | 303151 | Mabolo National High School | Cebu City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Cebu City | 303162 | Oprra Nhs(Day & Night) | Cebu City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Cebu City | 312507 | Pamutan Integrated School | Cebu City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 | [10 empty] | incomplete (DPWH request additional fund due to site development problem occurred during construction phase) | NC 2016
K10 | REGION VII | Cebu City | 119910 | Pardo Extension Elementary School | Cebu City (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22950000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu City | 303159 | Pardo Nhs (Day & Night) | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | REVERTED | 0 | [11 empty] | NC 2016
SHS | REGION VII | Cebu City | 303159 | Pardo Nhs (Day & Night) | Cebu City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 27350000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu City | 303137 | Paril Nhs | Cebu City (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Cebu City | 303160 | Pit-Os National High School | Cebu City (Capital) | 1 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34198179.297 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu City | 303160 | Pit-Os National High School | Cebu City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Cebu City |  | Shs In Bonbon, Cebu City | Cebu City (Capital) | 2 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11593844.661 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu City | 303163 | Sinsin Nhs | Cebu City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu City | 303163 | Sinsin Nhs | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2517000 |  |  | REVERTED | 0 | [10 empty] | Subject for reversion | NC 2016
SHS | REGION VII | Cebu City | 312501 | Sirao Integrated School | Cebu City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu City | 303164 | Sudlon Nhs | Cebu City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [10 empty] | Incomplete works despite buffer fund has been downloaded last Dec. 2017 | NC 2016
SHS | REGION VII | Cebu City | 312505 | Tabunan Integrated School | Cebu City (Capital) | 2 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11443844.661 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu City | 303140 | Talamban Nhs (Day & Night) | Cebu City (Capital) | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 20550000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Cebu City | 303140 | Talamban Nhs (Day & Night) | Cebu City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Cebu City | 500227 | Taptap Is | Cebu City (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11443844.661 |  |  | Completed | 1 | [10 empty] | Incomplete works despite buffer fund has been downloaded last Dec. 2017 | NC 2016
K10 | REGION VII | Cebu City | 303155 | Tejero Nhs(Day & Night) | Cebu City (Capital) | 1 | 1 | 12 | 4STY12CL | BATCH 9 CL | 19952109.258 |  |  | Completed | 1 | [10 empty] | Works has been resume by DPWH started on June 3, 2019 | NC 2016
K10 | REGION VII | Cebu City | 312506 | Tisa High School ( Day & Night) | Cebu City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Cebu City | 312506 | Tisa High School ( Day & Night) | Cebu City (Capital) | 2 |  | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Danao City | 302956 | Estefa O. Monte Memorial National High School | Danao | 5 | 1 | 6 | 3STY6CL | BATCH 3 CL | 10437131.51 |  |  | Completed | 1 |  |  |  | 16HI0050 | [5 empty] | JO BUILDERS |  | NC 2016
SHS | REGION VII | Danao City | 303037 | Maslog National High School |  | 5 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10417131.51 |  |  | Completed | 1 |  |  |  | 16HI0047 | [5 empty] | JO BUILDERS |  | NC 2016
K10 | REGION VII | Danao City | 322003 | Ramon M. Durano Sr. Foundation - Science & Technology Center | Danao | 5 | 1 | 20 | 4STY20CL | BATCH 9 CL | 28007601.243 |  |  | Completed | 1 |  |  |  | 16HI0030 | [5 empty] | SAN NARCISO BUILDERS |  | NC 2016
K10 | REGION VII | Danao City | 303039 | Ramon M. Durano Sr. Memorial National High School | Danao | 5 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15237982.3363 |  |  | Completed | 1 |  |  |  | 16HI0048 | [5 empty] | JO BUILDERS |  | NC 2016
K10 | REGION VII | Lapu-Lapu City | 119985 | Babag I Es | Lapu-Lapu City (Opon) | 6 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Lapu-Lapu City | 303172 | Babag National High School | Lapu-Lapu City (Opon) | 6 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Lapu-Lapu City | 303172 | Babag National High School | Lapu-Lapu City (Opon) | 6 |  | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Lapu-Lapu City | 119974 | Bagong Silang Es | Lapu-Lapu City (Opon) | 6 | 1 | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Lapu-Lapu City | 119963 | Bankal Es | Lapu-Lapu City (Opon) | 6 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31102890.27 |  |  | COMPLETED | 1 | [10 empty] | PUNCHLIST HAVE NOT YET BEEN COMPLIED | NC 2016
SHS | REGION VII | Lapu-Lapu City | 303174 | Bankal National High School | Lapu-Lapu City (Opon) | 6 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Lapu-Lapu City | 119975 | Basak Es | Lapu-Lapu City (Opon) | 6 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Lapu-Lapu City | 119964 | Buaya Elementary School | Lapu-Lapu City (Opon) | 6 | 1 | 12 | 4STY12CL | BATCH 9 CL | 19952109.258 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Lapu-Lapu City | 119987 | Canjulao Es | Lapu-Lapu City (Opon) | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Lapu-Lapu City | 119977 | Gun-Ob Es | Lapu-Lapu City (Opon) | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Lapu-Lapu City | 303177 | Lo-Ok National High School | Lapu-Lapu City (Opon) | 6 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Lapu-Lapu City | 119966 | Mactan Air Base Es | Lapu-Lapu City (Opon) | 6 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.59 |  |  | Reverted | 0 | [11 empty] | NC 2016
K10 | REGION VII | Lapu-Lapu City | 303178 | Mactan Nhs | Lapu-Lapu City (Opon) | 6 | 1 | 24 | 4STY12CL | BATCH 9 CL | 39904218.516 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Lapu-Lapu City | 303178 | Mactan Nhs | Lapu-Lapu City (Opon) | 6 |  | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Lapu-Lapu City | 119979 | Marigondon Elementary School | Lapu-Lapu City (Opon) | 6 | 1 | 20 | 4STY20CL | BATCH 9 CL | 28007601.243 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Lapu-Lapu City | 303180 | Marigondon Nhs | Lapu-Lapu City (Opon) | 6 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Lapu-Lapu City | 303181 | Marigondon Nhs - Basak Night Hs Ext. | Lapu-Lapu City (Opon) | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Lapu-Lapu City | 303193 | Nemesio-Epifania Taneo Mhs (Tingo Hs (De, January 15, 1995) | Lapu-Lapu City (Opon) | 6 | 1 | 12 | 4STY12CL | BATCH 9 CL | 20352109.258 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Lapu-Lapu City | 303184 | Pajo National High School | Lapu-Lapu City (Opon) | 6 | 1 | 12 | 4STY12CL | BATCH 9 CL | 19952109.258 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Lapu-Lapu City | 303184 | Pajo National High School | Lapu-Lapu City (Opon) | 6 |  | 16 | 4STY8CL | BATCH 9 CL | 26845533.912 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Lapu-Lapu City | 119969 | Punta Engano Es | Lapu-Lapu City (Opon) | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Lapu-Lapu City | 303187 | Pusok Nhs | Lapu-Lapu City (Opon) | 6 | 1 | 20 | 4STY20CL | BATCH 9 CL | 28007601.243 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Lapu-Lapu City | 303189 | Sta. Rosa Nhs | Lapu-Lapu City (Opon) | 6 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10817131.51 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Lapu-Lapu City | 119984 | Sudtonggan Es | Lapu-Lapu City (Opon) | 6 | 1 | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Lapu-Lapu City | 119962 | Tungasan Es | Lapu-Lapu City (Opon) | 6 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22552343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Mandaue City | 312811 | Banilad Nhs (Cabancalan Nhs Ext.) | Mandaue City | 6 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10882042.74 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Mandaue City | 120005 | Cabancalan Ii Es | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Mandaue City | 303194 | Cabancalan Nhs | Mandaue City | 6 | 1 | 16 | 4STY8CL | BATCH 9 CL | 29795037.68 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Mandaue City | 120010 | Canduman Es | Mandaue City | 6 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Mandaue City | 303195 | Canduman Nhs | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15395522.34 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Mandaue City | 120011 | Casili Night Hs To Casili Es | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16328864.74 |  |  | Completed | 1 |  |  | P00075842VS | 17HN0075 | [5 empty] | SERCHER DEV'T. CORP. |  | NC 2016
SHS | REGION VII | Mandaue City | 303198 | Jagobiao Nhs | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Mandaue City | 312807 | Maguikay Nhs | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Mandaue City | 303200 | Mandaue City Cnhs - Labogon Nhs Ext. | Mandaue City | 6 | 1 | 12 | 4STY12CL | BATCH 9 CL | 23012343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Mandaue City | 303199 | Mandaue City Comprehensive Nhs | Mandaue City | 6 | 1 | 20 | 4STY20CL | BATCH 13 CL | 32212890.87 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Mandaue City | 119997 | Mandaue City Cs | Mandaue City | 6 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Mandaue City | 119997 | Mandaue City Cs | Mandaue City | 6 |  | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Mandaue City | 189001 | Mandaue City Cs Sped Center | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 9 CL | 15395522.34 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Mandaue City | 312809 | Mandaue Sped Center Hs | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15905522.34 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Mandaue City | 120006 | Subangdaku Es | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Mandaue City | 303202 | Subangdaku Tech-Voc Hs (Mandaue City Cnhs - Subangdaku Nhs Ext.) | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15905522.34 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Mandaue City | 120017 | Tabok Es Ii | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Mandaue City | 120007 | Tipolo Es | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Mandaue City | 120003 | Umapad Es | Mandaue City | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Siquijor | 303302 | Banban National High School | Siquijor (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8214965.05 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Siquijor | 120657 | Banban National High School To Cabulihan Is |  | 0 | 1 | 4 | 2STY4CL |  | 6319337.64 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Siquijor | 303305 | Banban National High School To Catulayan Nhs |  | 0 | 1 | 4 | 2STY4CL |  | 6319337.64 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Siquijor | 303299 | Banban National High School To Ponong Hs |  | 0 | 1 | 4 | 1STY4CL |  | 3484886.58 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Siquijor | 303302 | Banban National High School | Siquijor (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2432393.98 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Siquijor | 303303 | Basac National High School | Larena | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Siquijor | 303303 | Basac National High School | Larena | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2419429.87 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Siquijor | 303293 | Campalanas National High School | Lazi | 0 | 1 | 16 | 2STY4CL | BATCH 9 CL | 25277350.56 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Siquijor | 303293 | Campalanas National High School | Lazi | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2432515.4 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Siquijor | 303304 | Candaping National High School | Maria | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10877342.59 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Siquijor | 303304 | Candaping National High School | Maria | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2419583.56 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Siquijor | 303296 | Cang-Alwang National High School | Siquijor (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6321810.79 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Siquijor | 303305 | Catulayan National High School | San Juan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2432556.18 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Siquijor | 303306 | Deped-Lazi National Agricultural School | Lazi | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2432648.13 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Siquijor | 303297 | Enrique Villanueva National High School | Enrique Villanueva | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8214965.05 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Siquijor | 303297 | Enrique Villanueva National High School | Enrique Villanueva | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4836556.18 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Siquijor | 303295 | Leon Parami High School | Lazi | 0 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Siquijor | 303295 | Leon Parami High School | Lazi | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2432648.13 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Siquijor | 120665 | Roxas Elementary School | Enrique Villanueva | 0 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1014438.63 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Siquijor | 303298 | San Antonio National High School | Siquijor (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2432684.35 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Siquijor | 303301 | Siquijor Provincial Science High School | Siquijor (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1817323.74 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Siquijor | 303300 | Tambisan National High School | San Juan | 0 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION VII | Siquijor | 303300 | Tambisan National High School | San Juan | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4862851.85 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Talisay City | 233503 | Biasong Elementary School | City Of Talisay | 1 | 1 | 6 | 3STY6CL | BATCH 13 CL | 11443844.661 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Talisay City | 119785 | Borromeo Bros. Elementary School | City Of Talisay | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15221327.92 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Talisay City | 322204 | Bulacao National High School | City Of Talisay | 1 | 1 | 8 | 4STY8CL | BATCH 9 CL | 15097518 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Talisay City | 302971 | Cansojong National High School | City Of Talisay | 1 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15221327 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Talisay City | 303019 | Jaclupan National High School | City Of Talisay | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15421327.92 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Talisay City | 119800 | Lagtang Elementary School | City Of Talisay | 1 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Talisay City | 322206 | Lagtang Night High School | City Of Talisay | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10417131 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Talisay City | 303040 | Lawaan National High School | City Of Talisay | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Talisay City | 322201 | Maghaway National High School | City Of Talisay | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10517131 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Talisay City | 322201 | Maghaway National High School | City Of Talisay | 1 |  | 4 | 2STY4CL | BATCH 9 CL | 6452000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Talisay City | 303056 | Mohon Nhs (Mohon Divino Amore Nhs) | City Of Talisay | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Talisay City | 119790 | San Roque Elementary School | City Of Talisay | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15121327 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Talisay City | 303088 | San Roque Nhs (Laray Nhs - Jaclupan Nhs Ext.) | City Of Talisay | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15221327 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Talisay City | 303113 | Talisay City National High School | City Of Talisay | 1 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26996317.0922 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Talisay City | 303113 | Talisay City National High School | City Of Talisay | 1 |  | 8 | 4STY8CL | BATCH 11 CL | 14897518 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Toledo City | 303308 | Bato National High School | Toledo City | 3 | 1 | 24 | 4STY8CL | BATCH 9 CL | 40268300.868 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Toledo City | 120715 | Cantabaco Elementary School | Toledo City | 3 | 1 | 12 | 2STY12CL | BATCH 13 CL | 14579217.18 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Toledo City | 303318 | Don Sndres Soriano Nat. High School | Toledo City | 3 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31202890.27 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Toledo City | 303311 | General Climaco National High School | Toledo City | 3 |  | 12 | 4STY12CL | BATCH 9 CL | 19952109.258 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Toledo City | 303311 | General Climaco National High School | Toledo City | 3 | 1 | 8 | 4STY8CL | BATCH 9 CL | 13622766.956 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Toledo City | 303310 | Luray Ii National High School (Day & Night) | Toledo City | 3 |  | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Toledo City | 303310 | Luray Ii National High School (Day & Night) | Toledo City | 3 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION VII | Toledo City | 120756 | Sam-Ang Elementary School | Toledo City | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 5802403.8743 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Toledo City | 303316 | Toledo National Vocational School | Toledo City | 3 | 1 | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION VII | Toledo City | 303316 | Toledo National Vocational School | Toledo City | 3 |  | 28 | 4STY28CL | BATCH 9 CL | 36076151.526 |  |  | Completed | 1 | [11 empty] | NC 2016

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.