## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of Sites Terminated | No. of CL Terminated | Status as of July 11, 2025
REPAIR 2020 | Region VII | Bais City | 120094 | Lowason ES | BAIS CITY | 2 | 1 | 7 | Repair of Classrooms | 2503300 | 1 |  | COMPLETED | 1 | [9 empty] | PAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region VII | Bais City | 120100 | Palaypay ES | BAIS CITY | 2 | 1 | 12 | Repair of Classrooms | 3944563 | 1 |  | COMPLETED | 1 |  |  |  |  | 2019-12-03 | 2019-12-11 | 2019-12-23 | 2020-01-15 | 2020-09-10 | PAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region VII | Bayawan City | 120116 | Maglinao Elementary School | BASAY | 3 | 1 | 13 | Repair of Classrooms | 5188394 | 1 |  | COMPLETED | 1 |  |  |  |  | 2019-12-03 | 2019-12-11 | 2019-12-23 | 2020-01-15 | 2020-09-10 | RISM BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | Region VII | Bayawan City | 120156 | Kalumboyan ES | CITY OF BAYAWAN (TULONG) | 3 | 1 | 27 | Repair of Classrooms | 9371995 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 27 | 0 | 0
REPAIR 2020 | Region VII | Bayawan City | 120137 | San Jose Elementary School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 8 | Repair of Classrooms | 1787212 | 1 |  | COMPLETED | 1 |  |  |  |  | 2019-12-03 | 2019-12-11 | 2019-12-23 | 2020-01-15 | 2020-09-10 | RISM BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VII | Bogo City | 119110 | Marangog ES | CITY OF BOGO | 4 | 1 | 8 | Repair of Classrooms | 1931819 | 1 | 2964721.57 | COMPLETED | 1 |  |  |  |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-02-13 | Septptember 25, 2020 | Inabanga Drilling |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 117987 | Laya ES | BACLAYON | 1 | 1 | 10 | Repair of Classrooms | 2964722 | 1 | 4518423.55 | COMPLETED | 1 |  |  |  |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-02-13 | October 18, 2020 | C Jansen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118101 | Pangangan ES | CALAPE | 1 | 1 | 19 | Repair of Classrooms | 4518424 | 1 | 2953032.13 | COMPLETED | 1 |  |  |  |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-02-13 | October 18, 2020 | C Jansen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118728 | Sto. Niño ES | TALIBON | 2 | 1 | 16 | Repair of Classrooms | 2953033 | 1 | 2269568.23 | COMPLETED | 1 |  |  |  |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-02-13 | October 18, 2020 | C Jansen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118767 | Tagum Sur ES | TRINIDAD | 2 | 1 | 12 | Repair of Classrooms | 2269569 | 1 | 1747575.57 | COMPLETED | 1 |  |  |  |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-02-13 | September 25, 2020 | Inabanga Drilling |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118806 | Bood Elementary School | UBAY | 2 | 1 | 13 | Repair of Classrooms | 1747576 | 1 | 3004320.21 | COMPLETED | 1 |  |  |  |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-02-13 | October 18, 2020 | C Jansen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118041 | Bilar Central ES | BILAR | 3 | 1 | 12 | Repair of Classrooms | 3004321 | 1 | 6183313.36 | COMPLETED | 1 |  |  |  |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-02-13 | September 21, 2020 | LTS Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118411 | Balili ES | JAGNA | 3 | 1 | 9 | Repair of Classrooms | 2382324 | 1 | 2094612.22 | COMPLETED | 1 |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 4, 2020 | C Jansen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118412 | Boctol ES | JAGNA | 3 | 1 | 9 | Repair of Classrooms | 2796022 | 1 | 1022109.47 | COMPLETED | 1 |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 7, 2020 | LTS Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118414 | Bunga Mar ES | JAGNA | 3 | 1 | 15 | Repair of Classrooms | 5707971 | 1 | 953437.6 | COMPLETED | 1 |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 4, 2020 | MABB Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118413 | Bunga Ylaya ES | JAGNA | 3 | 1 | 5 | Repair of Classrooms | 1243259 | 1 | 4078883.97 | COMPLETED | 1 |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 4, 2020 | JF Estapia construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118415 | Buyog ES | JAGNA | 3 | 1 | 4 | Repair of Classrooms | 1231828 | 1 | 1597582.98 | COMPLETED | 1 |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 7, 2020 | LM Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118416 | Cabungaan ES | JAGNA | 3 | 1 | 9 | Repair of Classrooms | 2261795 | 1 | 1489323.25 | COMPLETED | 1 |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 7, 2020 | Sombrio Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118417 | Calabacita ES | JAGNA | 3 | 1 | 8 | Repair of Classrooms | 2097273 | 1 | 1444881.41 | COMPLETED | 1 |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 7, 2020 | LTS Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118418 | Cambugason ES | JAGNA | 3 | 1 | 9 | Repair of Classrooms | 1678898 | 1 | 1131798.98 | COMPLETED | 1 |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 10, 2020 | Algamon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118419 | Can-ipol ES | JAGNA | 3 | 1 | 4 | Repair of Classrooms | 1374469 | 1 | 2052105.72 | COMPLETED | 1 |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 4, 2020 | MABB Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118420 | Canjulao ES | JAGNA | 3 | 1 | 8 | Repair of Classrooms | 2784402 | 1 | 1165667.99 | COMPLETED | 1 |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 4, 2020 | MABB Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118421 | Cantagay ES | JAGNA | 3 | 1 | 5 | Repair of Classrooms | 1581749 | 1 | 1425644.73 | COMPLETED | 1 |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 7, 2020 | A.D. Daniel construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118422 | Cantuyoc ES | JAGNA | 3 | 1 | 6 | Repair of Classrooms | 1427826 | 1 | 2664613.1 | COMPLETED | 1 |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 7, 2020 | LM Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118423 | Can-uba ES | JAGNA | 3 | 1 | 10 | Repair of Classrooms | 3798578 | 1 | 596892.48 | COMPLETED | 1 |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 10, 2020 | Algamon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118424 | Jagna Central ES | JAGNA | 3 | 1 | 27 | Repair of Classrooms | 6183314 | 1 | 5738027.78 | COMPLETED | 1 |  |  |  |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-02-13 | September 23, 2020 | Clavite Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 27 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118425 | Kinagbaan ES | JAGNA | 3 | 1 | 2 | Repair of Classrooms | 727415 | 1 | 1572397.99 | COMPLETED | 1 |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 7, 2020 | LM Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118426 | Larapan ES | JAGNA | 3 | 1 | 8 | Repair of Classrooms | 2240723 | 1 | 1724597.4 | COMPLETED | 1 |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 4, 2020 | C Jansen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118427 | Lonoy ES | JAGNA | 3 | 1 | 8 | Repair of Classrooms | 2301511 | 1 | 2071243.72 | COMPLETED | 1 |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 4, 2020 | 3N Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118428 | Malbog ES | JAGNA | 3 | 1 | 8 | Repair of Classrooms | 2920486 | 1 | 1190280.86 | COMPLETED | 1 |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 7, 2020 | LM Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118431 | Odiong ES | JAGNA | 3 | 1 | 4 | Repair of Classrooms | 1678249 | 1 | 1329453.55 | COMPLETED | 1 |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 4, 2020 | C Jansen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 500208 | Tubod ES | JAGNA | 3 | 1 | 6 | Repair of Classrooms | 1774442 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VII | Bohol | 118864 | Valencia Central Elementary School | VALENCIA | 3 | 1 | 24 | Repair of Classrooms | 5738028 | 1 | 1652345.79 | COMPLETED | 1 |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 7, 2020 | Sombrio Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0
REPAIR 2020 | Region VII | Carcar City | 119180 | Napo Elementary School | CITY OF CARCAR | 1 | 1 | 4 | Repair of Classrooms | 1648918 | 1 |  | COMPLETED | 1 | 2021-02-05 | 2020-12-11 |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VII | Cebu | 119633 | Tañañas Elementary School | SAN FERNANDO | 1 | 1 | 2 | Repair of Classrooms | 445693 | 1 |  | COMPLETED | 1 | 2021-02-05 |  |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VII | Cebu | 119722 | Sibonga Central ES | SIBONGA | 1 | 1 | 16 | Repair of Classrooms | 5377393 | 1 |  | COMPLETED | 1 | 2021-02-05 | 2020-12-28 |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2020 | Region VII | Cebu | 118872 | Alcoy Central ES | ALCOY | 2 | 1 | 17 | Repair of Classrooms | 4467735 | 1 |  | COMPLETED | 1 | 2021-01-06 | 2020-12-28 |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0
REPAIR 2020 | Region VII | Cebu | 119298 | Dalaguete Central ES | DALAGUETE | 2 | 1 | 9 | Repair of Classrooms | 3014494 | 1 |  | COMPLETED | 1 | 2021-01-06 | 2020-10-30 |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VII | Cebu | 119327 | Panaguikan ES | DALAGUETE | 2 | 1 | 11 | Repair of Classrooms | 3808351 | 1 |  | COMPLETED | 1 | 2021-01-06 | 2020-12-28 |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2020 | Region VII | Cebu | 119329 | Sacsac ES | DALAGUETE | 2 | 1 | 10 | Repair of Classrooms | 2544596 | 1 |  | COMPLETED | 1 | 2021-03-07 |  |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region VII | Cebu | 119187 | Carmen Central ES | CARMEN | 5 | 1 | 33 | Repair of Classrooms | 10084805 | 1 |  | COMPLETED | 1 | 2021-01-06 | 2020-12-28 |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 33 | 0 | 0
REPAIR 2020 | Region VII | Cebu | 119190 | Dawis Sur ES | CARMEN | 5 | 1 | 10 | Repair of Classrooms | 3100579 | 1 |  | COMPLETED | 1 | 2021-01-06 | 2020-10-19 |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region VII | Cebu | 119198 | Puente ES | CARMEN | 5 | 1 | 9 | Repair of Classrooms | 4092882 | 1 |  | COMPLETED | 1 | 2021-02-05 |  |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VII | Cebu | 119742 | Sogod Central ES | SOGOD | 5 | 1 | 22 | Repair of Classrooms | 5389977 | 1 |  | COMPLETED | 1 | 2021-01-06 |  |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 0 | 0
REPAIR 2020 | Region VII | Cebu | 119250 | Tugbongan ES | CONSOLACION | 6 | 1 | 11 | Repair of Classroom | 3442625 | 1 |  | COMPLETED | 1 | 2021-01-06 |  |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2020 | Region VII | Cebu | 119251 | Alegria ES | CORDOVA | 6 | 1 | 7 | Repair of Classrooms | 2531381 | 1 |  | COMPLETED | 1 | 2021-02-05 | 2020-10-19 |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region VII | Cebu | 119255 | Cordova Central ES | CORDOVA | 6 | 1 | 19 | Repair of Classrooms | 7913474 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 0 | 0
REPAIR 2020 | Region VII | Cebu City | 303138 | Camp Lapu-Lapu NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 9 | Repair of Classrooms | 1941128.16 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VII | Cebu City | 119919 | Carreta ES (Bagong Buhay ES) | CEBU CITY (Capital) | 1 | 1 | 37 | Repair of Classrooms | 2839457.83 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 37 | 0 | 0
REPAIR 2020 | Region VII | Cebu City | 303132 | Lusaran NHS | CEBU CITY (Capital) | 1 | 1 | 6 | Repair of Classrooms | 1195235 | 1 |  | COMPLETED | 1 | [10 empty] | FOR ISSUANCE OF NTP | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VII | Cebu City | 303154 | Regino Mercado NHS (Night) | CEBU CITY (Capital) | 1 | 1 | 9 | Repair of Classrooms | 1179167 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VII | Cebu City | 119903 | San Jose Elementary School | CEBU CITY (Capital) | 1 | 1 | 8 | Repair of Classrooms | 1339994 | 1 |  | COMPLETED | 1 | [10 empty] | FOR ISSUANCE OF NTP | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VII | Cebu City | 303156 | Zapatera NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 32 | Repair of Classrooms | 2936384.81 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0
REPAIR 2020 | Region VII | Cebu City | 119905 | Bulacao Community ES | CEBU CITY (Capital) | 2 | 1 | 7 | Repair of Classrooms | 1581930.28 | 1 |  | COMPLETED | 1 | [10 empty] | Suspended due to fire evacuees in-house in school | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region VII | Cebu City | 119866 | Don Vicente Rama MES (Basak ES) | CEBU CITY (Capital) | 2 | 1 | 18 | Repair of Classrooms | 3422466.68 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0
REPAIR 2020 | Region VII | Cebu City | 119910 | PARDO EXTENSION ELEMENTARY SCHOOL | CEBU CITY (Capital) | 2 | 1 | 3 | Repair of Classrooms | 553319 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VII | Cebu City | 303161 | Ramon Duterte Memorial NHS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | 6 | Repair of Classrooms | 1176673 | 1 | 2542106.2 | COMPLETED | 1 |  |  | cityofnaga 2019-004 |  | 2019-11-19 | 2019-11-26 | 2019-12-12 | Dec.23, 2019 |  | TRI BAIRN CONSTRUCTION | FOR ISSUANCE OF NTP | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VII | City of Naga, Cebu | 325304 | Cogon National High School | CITY OF NAGA | 1 | 1 | 4 | Repair of Classrooms | 564747 | 1 | 543284.65 | COMPLETED | 1 |  |  | cityofnaga 2019-004 |  | 2019-11-19 | 2019-11-26 | 2019-12-12 | Dec.23, 2019 |  | TRI BAIRN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VII | City of Naga, Cebu | 325308 | Tagjaguimit National High School | CITY OF NAGA | 1 | 1 | 2 | Repair of Classrooms | 543285 | 1 | 1000000 | COMPLETED | 1 |  |  |  |  | January 7, 2020 | January 13, 2020 | January 27, 2020 | January 29, 2020 | September 23, 2020 | F E & A Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VII | City of Naga, Cebu | 303120 | Tuyan National High School | CITY OF NAGA | 1 | 1 | 8 | Repair of Classrooms | 2542107 | 1 | 564746.27 | COMPLETED | 1 |  |  | cityofnaga 2019-004 |  | 2019-11-19 | 2019-11-26 | 2019-12-12 | Dec.23, 2019 |  | TRI BAIRN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VII | Danao City | 119355 | Portland ES | DANAO CITY | 5 | 1 | 4 | Repair of Classrooms | 1000000 | 1 | 1405616.36 | COMPLETED | 1 | 2021-04-27 |  |  |  |  | 2019-11-20 | 2019-12-09 | 2019-12-19 | 2020-12-21 | PAR Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VII | Dumaguete City | 119945 | Cantil-e ES | DUMAGUETE CITY (Capital) | 2 | 1 | 8 | Repair of Classrooms | 1181000 | 1 | 2729546.51 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | SUNSHINE SAPHIRE CONSTRUCTION & SUPPLY | with variation order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VII | Dumaguete City | 119940 | West City Exceptional Child Learning Center | DUMAGUETE CITY (Capital) | 2 | 1 | 8 | Repair of Classrooms | 1405617 | 1 | 1181000 | COMPLETED | 1 | 2021-04-28 |  |  |  | 2020-01-22 | 2020-01-29 | 2020-02-10 | 2020-02-26 | 2020-12-22 | RISM Builders and Construction Services, Inc. | with variation order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VII | Guihulngan City | 120260 | Agulang PS | CITY OF GUIHULNGAN | 1 | 1 | 2 | Repair of Classrooms | 691810 | 1 | 990614 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | SUNSHINE SAPHIRE CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VII | Guihulngan City | 120241 | Calabaclabacan ES | CITY OF GUIHULNGAN | 1 | 1 | 8 | Repair of Classrooms | 2729547 | 1 | 1100736.86 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | SUNSHINE SAPHIRE CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VII | Guihulngan City | 120250 | Lip-o ES | CITY OF GUIHULNGAN | 1 | 1 | 3 | Repair of Classrooms | 1400423 | 1 | 1131560 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | PAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VII | Guihulngan City | 120252 | Magkanaway PS | CITY OF GUIHULNGAN | 1 | 1 | 3 | Repair of Classrooms | 1131560 | 1 | 1922984 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | PAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VII | Guihulngan City | 120278 | Nagsaha ES | CITY OF GUIHULNGAN | 1 | 1 | 3 | Repair of Classrooms | 990614 | 1 | 1574195.47 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | SUNSHINE SAPHIRE CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VII | Guihulngan City | 120281 | Plagatasanon ES | CITY OF GUIHULNGAN | 1 | 1 | 5 | Repair of Classrooms | 1574196 | 1 |  | COMPLETED | 1 |  |  |  |  | Nov. 25, 2019 | Dec. 03, 2019 | Dec. 16, 2019 | Jan. 13, 2020 |  | FROY J BUILDERS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VII | Guihulngan City | 120286 | Tominhao PS | CITY OF GUIHULNGAN | 1 | 1 | 3 | Repair of Classrooms | 1100737 | 1 | 1400423 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | PAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VII | Guihulngan City | 120641 | Ulay Elementary School | VALLEHERMOSO | 1 | 1 | 7 | Repair of Classrooms | 1922984 | 1 | 691810 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | SUNSHINE SAPHIRE CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region VII | Lapu-Lapu City | 119977 | Gun-ob ES | LAPU-LAPU CITY (OPON) | 0 | 1 | 4 | Repair of Classrooms | 1848839.29 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VII | Lapu-Lapu City | 119972 | Abuno ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 6 | Repair of Classrooms | 2307557 | 1 |  | COMPLETED | 1 |  |  |  |  | Nov. 25, 2019 | Dec. 03, 2019 | Dec. 16, 2019 | Jan. 13, 2020 |  | TRI BAIRN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VII | Lapu-Lapu City | 303183 | Marigondon NHS - Science Tech. Educ. Center (STEC) Ext. | LAPU-LAPU CITY (OPON) | 6 | 1 | 13 | Repair of Classrooms | 2128918 | 1 | 2984674.27 | COMPLETED | 1 |  |  | RE2020-001 | 2020-09-046 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-01-06 |  | Tri Bairn Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | Region VII | Lapu-Lapu City | 119958 | Sta. Rosa ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 12 | Repair of Classrooms | 4899367 | 1 |  | COMPLETED | 1 |  |  |  |  | Nov. 25, 2019 | Dec. 03, 2019 | Dec. 16, 2019 | Jan. 13, 2020 |  | GOLDEN HAMMER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region VII | Mandaue City | 120008 | Bakilid ES | MANDAUE CITY | 6 | 1 | 9 | Repair of Classrooms | 2984675 | 1 | 717399.7 | COMPLETED | 1 |  |  | RE2020-002 | 2020-09 -047 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-01-06 |  | Golden Hammer Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VII | Mandaue City | 312801 | Canduman NHS - Tabok NHS | MANDAUE CITY | 6 | 1 | 2 | Repair of Classroom | 672833 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VII | Mandaue City | 303198 | Jagobiao NHS | MANDAUE CITY | 6 | 1 | 2 | Repair of Classrooms | 717400 | 1 | 672832.91 | COMPLETED | 1 |  |  | RE2020-003 | 2020-0 9 -048 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-01-06 |  | Jelay Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VII | Negros Oriental | 120043 | Iniban Elementary School | AYUNGON | 1 | 1 | 9 | Repair of Classrooms | 1921000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VII | Negros Oriental | 120206 | Linothangan Elementary School | CANLAON CITY | 1 | 1 | 8 | Repair of Classrooms | 3292082 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VII | Negros Oriental | 120208 | Malaiba Elementary School | CANLAON CITY | 1 | 1 | 3 | Repair of Classrooms | 843690 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VII | Negros Oriental | 120211 | Masulog ES | CANLAON CITY | 1 | 1 | 20 | Repair of Classrooms | 8310000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0
REPAIR 2020 | Region VII | Negros Oriental | 120213 | Panubigan Elementary School | CANLAON CITY | 1 | 1 | 16 | Repair of Classrooms | 6951280 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2020 | Region VII | Negros Oriental | 120216 | Tabalogo ES | CANLAON CITY | 1 | 1 | 8 | Repair of Classrooms | 3435981 | 1 |  | COMPLETED | 1 |  |  | 2019 - 48 |  | Nov. 21 to Dec. 9, 2019 | Nov. 27, 2019 | Dec. 9, 2019 | Dec. 16, 2019 |  | ALOJA BUILDERS AND REALTY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VII | Negros Oriental | 120384 | Campuyo Elementary School | MANJUYOD | 1 | 1 | 9 | Repair of Classrooms | 4400000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VII | Negros Oriental | 303207 | Amlan National High School | AMLAN (AYUQUITAN) | 2 | 1 | 17 | Repair of Classrooms | 6183000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0
REPAIR 2020 | Region VII | Negros Oriental | 120025 | Aurelio Ibero MES (Jugno ES) | AMLAN (AYUQUITAN) | 2 | 1 | 7 | Repair of Classroom | 1941000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region VII | Negros Oriental | 120364 | Lumbangan Elementary School | MABINAY | 2 | 1 | 26 | Repair of Classrooms | 6532000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 26 | 0 | 0
REPAIR 2020 | Region VII | Negros Oriental | 120488 | Escaguit Elementary School | SIBULAN | 2 | 1 | 4 | Repair of Classrooms | 1443000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VII | Negros Oriental | 120445 | Bantolinao Elementary School | SIATON | 3 | 1 | 6 | Repair of Classrooms | 1720574 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VII | Negros Oriental | 120462 | Lico-Lico Elementary School | SIATON | 3 | 1 | 9 | Repair of Classrooms | 2693714 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region VII | Negros Oriental | 120474 | Palayuhan ES | SIATON | 3 | 1 | 8 | Repair of Classrooms | 1836000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VII | Negros Oriental | 120647 | Kaladias ES | ZAMBOANGUITA | 3 | 1 | 14 | Repair of Classrooms | 3411000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2020 | Region VII | Siquijor | 120670 | Cangomantong Elementary School | LAZI | 0 | 1 | 8 | Repair of Classrooms | 2908041 | 1 |  | COMPLETED | 1 |  |  | 2019 - 49 |  | Nov. 21 to Dec. 9, 2019 | Nov. 27, 2019 | Dec. 9, 2019 | Dec. 16, 2019 |  | E.D. Angas Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region VII | Siquijor | 120682 | Minalulan Elementary School | MARIA | 0 | 1 | 10 | Repair of Classrooms | 2207997 | 1 |  | COMPLETED | 1 |  |  | 2019 - 50 |  | Nov. 21 to Dec. 9, 2019 | Nov. 27, 2019 | Dec. 9, 2019 | Dec. 16, 2019 |  | VVER Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region VII | Siquijor | 120709 | Tambisan Elementary School | SAN JUAN | 0 | 1 | 7 | Repair of Classrooms | 2317963 | 1 |  | COMPLETED | 1 |  |  | 2019 - 51 |  | Nov. 21 to Dec. 9, 2019 | Nov. 27, 2019 | Dec. 9, 2019 | Dec. 16, 2019 |  | E.D. Angas Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region VII | Siquijor | 120696 | Cang-atuyom Elementary School | SIQUIJOR (Capital) | 0 | 1 | 4 | Repair of Classrooms | 645206 | 1 |  | COMPLETED | 1 |  |  | 2019 - 51 |  | Nov. 21 to Dec. 9, 2019 | Nov. 27, 2019 | Dec. 9, 2019 | Dec. 16, 2019 |  | E.D. Angas Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region VII | Siquijor | 120704 | San Antonio Elementary School | SIQUIJOR (Capital) | 0 | 1 | 5 | Repair of Classrooms | 1388364 | 1 | 5613375.27 | COMPLETED | 1 |  |  |  | 2020-001-Infra |  |  | December 18, 2019 | December 26, 2019 | September 28, 2020 | ESP Design, Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VII | Tagbilaran City | 322102 | San Isidro National High School | TAGBILARAN CITY (Capital) | 1 | 1 | 6 | Repair of Classrooms | 1829395 | 1 |  | COMPLETED | 1 |  |  | talisaycity2020-001 |  | 2020-01-07 | 2020-01-13 | 2020-01-27 | 2020-01-30 | waiting for SARO | SB & T Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VII | Tagbilaran City | 118715 | Tiptip Elementary School | TAGBILARAN CITY (Capital) | 1 | 1 | 16 | Repair of Classrooms | 5613376 | 1 | 1829394.44 | COMPLETED | 1 |  |  |  | 2020-002-Infra |  |  | December 18, 2019 | December 26, 2019 | September 28, 2020 | ESP Design, Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2020 | Region VII | Talisay City | 119798 | Iba Elementary School | CITY OF TALISAY | 1 | 1 | 3 | Repair of Classrooms | 1181811 | 1 |  | COMPLETED | 1 |  |  | talisaycity2020-002 |  | 2020-01-07 | 2020-01-13 | 2020-01-27 | 2020-01-30 | waiting for SARO | JY Bontilao Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VII | Talisay City | 303019 | Jaclupan National High School | CITY OF TALISAY | 1 | 1 | 6 | Repair of Classrooms | 2247523 | 1 |  | COMPLETED | 1 | [9 empty] | RISM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VII | Talisay City | 119787 | Lawaan Elementary School | CITY OF TALISAY | 1 | 1 | 6 | Repair of Classrooms | 2379951 | 1 |  | COMPLETED | 1 |  |  | talisaycity2020-003 |  | 2020-01-07 | 2020-01-13 | 2020-01-27 | 2020-01-30 | waiting for SARO | QCC Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region VII | Tanjay City | 120546 | Canghatap Elementary School | CITY OF TANJAY | 2 | 1 | 5 | Repair of Classrooms | 2178500 | 1 |  | COMPLETED | 1 | [9 empty] | RISM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VII | Tanjay City | 120555 | Lamwas Elementary School | CITY OF TANJAY | 2 | 1 | 3 | Repair of Classrooms |  | 1 |  | COMPLETED | 1 | [9 empty] | RISM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VII | Tanjay City | 120561 | Ponglo Elementary School | CITY OF TANJAY | 2 | 1 | 3 | Repair of Classrooms |  | 1 |  | COMPLETED | 1 | [9 empty] | RISM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VII | Tanjay City | 234002 | Rosario V. Moras Memorial School | CITY OF TANJAY | 2 | 1 | 2 | Repair of Classrooms |  | 1 |  | COMPLETED | 1 | [9 empty] | VVER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region VII | Tanjay City | 120411 | Caningay Elementary School | PAMPLONA | 2 | 1 | 3 | Repair of Classrooms | 1968302 | 1 |  | COMPLETED | 1 | [9 empty] | VVER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region VII | Tanjay City | 120428 | Tigbao Elementary School | PAMPLONA | 2 | 1 | 5 | Repair of Classrooms |  | 1 | 3803586.63 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region VII | Toledo City | 120715 | Cantabaco ES | TOLEDO CITY | 3 | 1 | 16 | Repair of Classrooms | 3803587 | 1 | 3803586.63 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2021 | Region VII | Bais City | 120088 | Cambagahan ES | BAIS CITY | 2 | 1 | 1 | Repair of Classroom | 550447.95 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region VII | Bais City | 323005 | Manuel L. Teves Memorial HS | BAIS CITY | 2 | 1 | 1 | Repair of Classroom | 505199.54 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region VII | Bais City | 120101 | Panalaan ES | BAIS CITY | 2 | 1 | 4 | Repair of Classrooms | 2031532.51 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region VII | Bayawan City | 120114 | Don Pablo Carmen Blanco Utzurrum Memorial Elementary School | BASAY | 3 | 1 | 8 | Repair of Classrooms | 4820489.9 | 1 | 3424000 | COMPLETED | 1 |  |  |  | 2021-BEFF-001 | 6/18/2021 | 6/28/2021 | 2021-07-12 | 7/16/2021 | 6/27/2021 | RISM BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region VII | Bogo City | 119118 | Bogo II Central ES | CITY OF BOGO | 4 | 1 | 4 | Repair of Classrooms | 2472943.1 | 1 |  | COMPLETED | 1 | Nov. 14, 2021 | [5 empty] | July 12, 2021 | July 14, 2021 | Aug. 16, 2021 | SB & T CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region VII | Bogo City | 119119 | Bung-aw Elementary School | CITY OF BOGO | 4 | 1 | 2 | Repair of Classrooms | 1022507.69 | 1 |  | COMPLETED | 1 | Nov. 10, 2021 | [5 empty] | July 12, 2021 | July 14, 2021 | Aug. 12, 2021 | TRI BAIRN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VII | Bohol | 117935 | Toril ES | ALBURQUERQUE | 1 | 1 | 9 | Repair of Classrooms | 2894130.84 | 1 | 1950492.7 | COMPLETED | 1 | 2022-10-30 |  |  |  | 2021-05-31 | 2021-06-08 | 2021-06-22 | 2021-08-18 | Sept 28, 2021 | JF Estafia | For Punchlisting | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2021 | Region VII | Bohol | 118564 | Tawala ES | PANGLAO | 1 | 1 | 11 | Repair of Classrooms | 3584468.21 | 1 | 2407509.72 | COMPLETED | 1 | 2022-09-30 |  |  |  | 2021-05-31 | 2021-06-08 | 2021-06-22 | 2021-08-18 | Sept 28, 2021 | JF Estafia | For Punchlisting | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2021 | Region VII | Bohol | 118407 | Sto. Rosario Elementary School | INABANGA | 2 | 1 | 8 | Repair of Classrooms | 2726461.35 | 1 | 2028570.53 | COMPLETED | 1 |  |  |  |  | 2021-05-31 | 2021-06-08 | 2021-06-22 | 2021-08-18 | Sept 28, 2021 | Inabanga Drilling |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region VII | Bohol | 118589 | Bogo ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 8 | Repair of Classrooms | 2037504.14 | 1 | 1333892.23 | COMPLETED | 1 | 2022-11-30 |  |  |  | 2021-05-31 | 2021-06-08 | 2021-06-22 | 2021-08-18 | Sept 28, 2021 | LM Construction | For Punchlisting | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region VII | Bohol | 118613 | Kabasacan ES | SAGBAYAN (BORJA) | 2 | 1 | 4 | Repair of Classrooms | 1180348.83 | 1 | 884810.81 | COMPLETED | 1 |  |  |  |  | 2021-05-31 | 2021-06-08 | 2021-06-22 | 2021-08-18 | Sept 28, 2021 | Inabanga Drilling |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region VII | Bohol | 117940 | Cayacay ES | ALICIA | 3 | 1 | 11 | Repair of Classrooms | 3372561.8 | 1 | 2343280.96 | COMPLETED | 1 | 2022-09-30 |  |  |  | 2021-05-31 | 2021-06-08 | 2021-06-22 | 2021-08-18 | Sept 28, 2021 | EFB Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2021 | Region VII | Bohol | 118012 | Batuan Central ES | BATUAN | 3 | 1 | 3 | Repair of Classrooms | 1088648.66 | 1 | 848900.62 | COMPLETED | 1 |  |  |  |  | 2021-05-31 | 2021-06-08 | 2021-06-22 | 2021-08-18 | Sept 28, 2021 | C Jansen construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region VII | Bohol | 118863 | Ticum ES | VALENCIA | 3 | 1 | 7 | Repair of Classrooms | 2348214.64 | 1 | 1585072.11 | COMPLETED | 1 |  |  |  |  | 2021-05-31 | 2021-06-08 | 2021-06-22 | 2021-08-18 | Sept 28, 2021 | JF Estafia |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region VII | Carcar City | 119154 | Buenavista Elementary School | CITY OF CARCAR | 1 | 1 | 3 | Repair of Classrooms | 2221764.39 | 1 |  | COMPLETED | 1 | [6 empty] | July 7, 2021 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region VII | Carcar City | 119178 | MAINIT ELEMENTARY SCHOOL | CITY OF CARCAR | 1 | 1 | 1 | Repair of Classroom | 779719.39 | 1 | 697452.29 | COMPLETED | 1 |  |  |  | Repair2019-01carcar |  |  | July 7, 2021 |  |  | PJA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region VII | Cebu | 119618 | Balungag ES | SAN FERNANDO | 1 | 1 | 6 | Repair of Classrooms | 2245599.16 | 1 | 2196844.85 | COMPLETED | 1 |  |  |  | CY 2021 BEFF REPAIR-DEPED-R7-01 | JUNE 24, 2021 | JULY 05, 2021 | JULY 19, 2021 | AUGUST 16, 2021 | SEPTEMBER 20, 2021 | SB & T CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region VII | Cebu | 118875 | Guiwang ES | ALCOY | 2 | 1 | 6 | Repair of Classrooms | 1905019.22 | 1 | 1886306.1 | COMPLETED | 1 |  |  |  | CY 2021 BEFF REPAIR-DEPED-R7-02 | JUNE 24, 2021 | JULY 05, 2021 | JULY 19, 2021 | AUGUST 16, 2021 | SEPTEMBER 20, 2021 | LA PRUEBA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region VII | Cebu | 118933 | Tabayag ES | ARGAO | 2 | 1 | 6 | Repair of Classrooms | 2006667.47 | 1 | 1991113.58 | COMPLETED | 1 |  |  |  | CY 2021 BEFF REPAIR-DEPED-R7-03 | JUNE 24, 2021 | JULY 05, 2021 | JULY 19, 2021 | AUGUST 16, 2021 | SEPTEMBER 20, 2021 | MARLJAVIS CONSTRUCTION, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region VII | Cebu | 119324 | Manangal ES | DALAGUETE | 2 | 1 | 4 | Repair of Classrooms | 1227850.89 | 1 | 1215822.71 | COMPLETED | 1 |  |  |  | CY 2021 BEFF REPAIR-DEPED-R7-04 | JUNE 24, 2021 | JULY 05, 2021 | JULY 19, 2021 | AUGUST 16, 2021 | SEPTEMBER 20, 2021 | JY BONTILAO & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region VII | Cebu | 118913 | Sto. Rosario ES | ALOGUINSAN | 3 | 1 | 3 | Repair of Classrooms | 1274310.97 | 1 | 1008724.53 | COMPLETED | 1 |  |  |  | CY 2021 BEFF REPAIR-DEPED-R7-05 | JUNE 24, 2021 | JULY 05, 2021 | JULY 19, 2021 | AUGUST 16, 2021 | SEPTEMBER 20, 2021 | ANIELTHON CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region VII | Cebu | 119570 | Sambagon ES | PINAMUNGAHAN | 3 | 1 | 8 | Repair of Classrooms | 2622329 | 1 | 2607273.15 | COMPLETED | 1 |  |  |  | CY 2021 BEFF REPAIR-DEPED-R7-06 | JUNE 24, 2021 | JULY 05, 2021 | JULY 19, 2021 | AUGUST 16, 2021 | SEPTEMBER 20, 2021 | TRI BAIRN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region VII | Cebu | 119821 | Sandayong ES | TUBURAN | 3 | 1 | 6 | Repair of Classrooms | 2082851.88 | 1 | 1857235.25 | COMPLETED | 1 |  |  |  | CY 2021 BEFF REPAIR-DEPED-R7-07 | JUNE 24, 2021 | JULY 05, 2021 | JULY 19, 2021 | AUGUST 16, 2021 | SEPTEMBER 20, 2021 | GELA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region VII | Cebu | 119216 | Catmondaan ES | CATMON | 5 | 1 | 7 | Repair of Classrooms | 2986666.58 | 1 | 2958650.33 | COMPLETED | 1 |  |  |  | CY 2021 BEFF REPAIR-DEPED-R7-08 | JUNE 24, 2021 | JULY 05, 2021 | JULY 19, 2021 | AUGUST 16, 2021 | SEPTEMBER 20, 2021 | BARR STEEL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region VII | Cebu | 119218 | Ginabukan ES | CATMON | 5 | 1 | 1 | Repair of Classroom | 426692.23 | 1 | 424334.83 | COMPLETED | 1 |  |  |  | CY 2021 BEFF REPAIR-DEPED-R7-08 | JUNE 24, 2021 | JULY 05, 2021 | JULY 19, 2021 | AUGUST 16, 2021 | SEPTEMBER 20, 2021 | BARR STEEL | SUSPENDED (ROAD NOT PASSABLE DUE TO ROAD CONCRETING) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region VII | Cebu | 119221 | Tabili Elem. | CATMON | 5 | 1 | 7 | Repair of Classrooms | 2613056.54 | 1 | 2592621.31 | COMPLETED | 1 |  |  |  | CY 2021 BEFF REPAIR-DEPED-R7-09 | JUNE 24, 2021 | JULY 05, 2021 | JULY 19, 2021 | AUGUST 16, 2021 | SEPTEMBER 20, 2021 | Golden Hammer Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region VII | Cebu | 119254 | Cogon ES | CORDOVA | 6 | 1 | 6 | Repair of Classrooms | 2518645.47 | 1 | 2498421.71 | COMPLETED | 1 |  |  |  | CY 2021 BEFF REPAIR-DEPED-R7-10 | JUNE 24, 2021 | JULY 05, 2021 | JULY 19, 2021 | AUGUST 16, 2021 | SEPTEMBER 20, 2021 | JY BONTILAO & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region VII | Cebu City | 119886 | Labangon Elementary School | CEBU CITY (Capital) | 2 | 1 | 18 | Repair of Classrooms | 3752209.21 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0
REPAIR 2021 | Region VII | City of Naga, Cebu | 119514 | Bairan Elementary School | CITY OF NAGA | 1 | 1 | 1 | Repair of Classroom | 524662.6 | 1 | 522369.86 | COMPLETED | 1 | 2021-11-15 | 2021-08-31 | cityofnaga2021-001 |  | 2021-07-08 | 2021-07-15 | 2021-07-27 | 2021-08-03 | 2021-08-09 | TRI BAIRN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region VII | City of Naga, Cebu | 119506 | Inayagan Elementary School | CITY OF NAGA | 1 | 1 | 3 | Repair of Classrooms | 1649255.52 | 1 | 1643039.14 | COMPLETED | 1 | 2021-11-15 | 2021-09-20 | cityofnaga2021-001 |  | 2021-07-08 | 2021-07-15 | 2021-07-27 | 2021-08-03 | 2021-08-09 | TRI BAIRN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region VII | Danao City | 119349 | Guinsay ES | DANAO CITY | 5 | 1 | 2 | Repair of Classrooms | 1602429.37 | 1 | 1265800.85 | COMPLETED | 1 | [9 empty] | TRI BAIRN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VII | Danao City | 322002 | Guinsay National High School | DANAO CITY | 5 | 1 | 2 | Repair of Classrooms | 1397522.32 | 1 | 1002959.84 | COMPLETED | 1 | [9 empty] | HERO Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VII | Dumaguete City | 303166 | Camanjac National High School | Dumaguete City | 2 | 1 | 13 | Repair of Classrooms | 2999999.73 | 1 | 2979000 | COMPLETED | 1 | 2022-01-02 | [5 empty] | 2021-06-15 |  | 2021-07-29 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2021 | Region VII | Guihulngan City | 120264 | Banwague ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | Repair of Classrooms | 756256.04 | 1 | 622167.9 | COMPLETED | 1 | 2021-11-29 |  |  | ITB 2021-05 | 2021-08-04 | 2021-08-12 | 2021-08-24 | 2021-09-07 | 2021-09-21 | Triple Jo Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VII | Guihulngan City | 120251 | Maculos ES | CITY OF GUIHULNGAN | 1 | 1 | 3 | Repair of Classrooms | 1773747.19 | 1 | 1230581.49 | COMPLETED | 1 | 2021-12-29 |  |  | ITB 2021-06 | 2021-08-04 | 2021-08-12 | 2021-08-24 | 2021-09-07 | 2021-09-21 | Triple Jo Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region VII | Guihulngan City | 120283 | Taloto ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | Repair of Classrooms | 1081239.33 | 1 | 775994.89 | COMPLETED | 1 | 2021-11-29 |  |  | ITB 2021-05 | 2021-08-04 | 2021-08-12 | 2021-08-24 | 2021-09-07 | 2021-09-21 | Triple Jo Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VII | Lapu-Lapu City | 303187 | Pusok NHS | LAPU-LAPU CITY (OPON) | 0 | 1 | 22 | Repair of Classrooms | 1556726.92 | 1 | 1523197.92 | COMPLETED | 1 | December 10, 2021 | Sept. 20, 2021 |  |  | June 03, 2021 | June 10, 2021 | June 22, 2021 | July 08, 2021 | August 12, 2021 | ANIELTHON CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 0 | 0
REPAIR 2021 | Region VII | Lapu-Lapu City | 119984 | Sudtonggan ES | LAPU-LAPU CITY (OPON) | 0 | 1 | 5 | Repair of Classrooms | 2413014.34 | 1 | 1785629.05 | COMPLETED | 1 | December 10, 2021 | November 10, 2021 |  |  | June 03, 2021 | June 10, 2021 | June 22, 2021 | July 08, 2021 | August 12, 2021 | TRAIBARN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region VII | Mandaue City | 119994 | Cesar M. Cabahug ES (Looc) | MANDAUE CITY | 6 | 1 | 13 | Repair of Classrooms | 2999986.07 | 1 | 2942434.03 | COMPLETED | 1 | 11-15-21 |  | RE2021-01 | 2021 - 07 | 2021-03-06 | 2021-09-06 | 06/21/21 | 06/30/21 | 07/21/21 | Golden Hammer Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2021 | Region VII | Negros Oriental | 120053 | So-ok Elementary School | AYUNGON | 1 | 1 | 8 | Repair of Classrooms | 3721317.42 | 1 | 3003000 | COMPLETED | 1 | 2021-12-04 | 2021-12-03 |  |  | 2021-06-09 | 2021-06-14 | 2021-06-28 | 2021-07-15 | 2021-11-28 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region VII | Negros Oriental | 120199 | Binalbagan Elementary School | CANLAON CITY | 1 | 1 | 10 | Repair of Classrooms | 4706070.84 | 1 | 3522000 | COMPLETED | 1 | 2021-12-04 | 2022-07-11 |  |  | 2021-06-09 | 2021-06-14 | 2021-06-28 | 2021-07-15 | 2021-11-28 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region VII | Negros Oriental | 120217 | Tigbahi ES | CANLAON CITY | 1 | 1 | 6 | Repair of Classrooms | 4246688.66 | 1 | 3177000 | COMPLETED | 1 | 2021-12-04 | 2022-07-11 |  |  | 2021-06-09 | 2021-06-14 | 2021-06-28 | 2021-07-15 | 2021-11-28 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region VII | Negros Oriental | 120219 | Villa Iowa ES | CANLAON CITY | 1 | 1 | 8 | Repair of Classrooms | 5165453.02 | 1 | 3874000 | COMPLETED | 1 | 2021-12-02 | 2022-03-08 |  |  | 2021-06-09 | 2021-06-14 | 2021-06-28 | 2021-07-15 | 2021-11-27 | PAR BUILDERS ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region VII | Negros Oriental | 120374 | Pedro Gobuyan, Sr. MES (Mayaposi ES) | MABINAY | 2 | 1 | 6 | Repair of Classrooms | 1965466.89 | 1 | 1475000 | COMPLETED | 1 | 2021-12-02 | 2021-11-19 |  |  | 2021-06-09 | 2021-06-14 | 2021-06-28 | 2021-07-15 | 2021-11-27 | PAR BUILDERS ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region VII | Negros Oriental | 120437 | San Roque Primary School | SAN JOSE | 2 | 1 | 4 | Repair of Classrooms | 1966423.02 | 1 | 1624000 | COMPLETED | 1 | 2021-12-04 | 2021-11-26 |  |  | 2021-06-09 | 2021-06-14 | 2021-06-28 | 2021-07-15 | 2021-11-28 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region VII | Negros Oriental | 303249 | Santiago Delmo MHS (Maluay HS) | ZAMBOANGUITA | 3 | 1 | 20 | Repair of Classrooms | 8901004.3 | 1 | 6664000 | COMPLETED | 1 | 2022-03-04 |  |  |  | 2021-06-09 | 2021-06-14 | 2021-06-28 | 2021-07-15 | 2021-11-28 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | processing of fire safety inspection certificate | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0
REPAIR 2021 | Region VII | Siquijor | 120675 | Kimba Elementary School | Lazi | 1 | 1 | 5 | Repair of Classrooms | 2999578.32 | 1 | 2458560.33 | COMPLETED | 1 | 2021-11-15 |  |  |  | 2021-05-25 | 2021-06-02 | 2021-06-23 | 2021-06-30 | 2021-07-16 | NALE Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region VII | Tagbilaran City | 118716 | Ubujan Elementary School | Tagbilaran City | 1 | 1 | 14 | Repair of Classrooms | 6594981.05 | 1 | 5011996.46 | COMPLETED | 1 | February 4, 2022 | September 8, 2021 |  | 2021-01-Infra | June 14, 2021 | June 23, 2021 | July 5, 2021 | July 7, 2021 | August 2, 2021 | C. Jansen Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2021 | Region VII | Talisay City | 233504 | Hawanay Elementary School | CITY OF TALISAY | 1 | 1 | 2 | Repair of Classrooms | 1502153 | 1 |  | COMPLETED | 1 | 2019-11-22 | August 23,2019 |  |  | 2019-01-08 | 2019-01-15 | 2019-01-28 | 2019-04-08 | 2019-08-22 | Maqueserg Construction & Gen. Mdse. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VII | Talisay City | 119801 | Manguilamon Elementary School | CITY OF TALISAY | 1 | 1 | 2 | Repair of Classrooms | 1497351.18 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VII | Tanjay City | 234006 | Canggabi Elementary School | CITY OF TANJAY | 2 | 1 | 1 | Repair of Classroom | 484821.83 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region VII | Tanjay City | 234001 | George Pilas MS (Aseotes PS) | CITY OF TANJAY | 2 | 1 | 1 | Repair of Classroom | 338983.18 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region VII | Tanjay City | 120542 | Pelagio Jabel MS (Bahian ES) | CITY OF TANJAY | 2 | 1 | 2 | Repair of Classrooms | 1086834.18 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region VII | Tanjay City | 120426 | Simborio ES | PAMPLONA | 2 | 1 | 3 | Repair of Classrooms | 1185395.62 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region VII | Toledo City | 303307 | AWIHAO NATIONAL HIGH SCHOOL | TOLEDO CITY | 3 | 1 | 5 | Repair of Classrooms | 2842658.2 | 1 |  | COMPLETED | 1 | [9 empty] | ANIELTHON CONSTRUCTION AND SUPPLY | 2814944.5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region VII | Bohol | 117930 | Bahi Primary School | ALBURQUERQUE | 1 | 1 | 3 | Repair of Classrooms | 1692566.73 | 1 | 1337047.43 | COMPLETED | 1 | Jan 29.2023 |  |  | 12022-03-01-1 | 3.30.2022 | 4.7.2022 | 4.19.2022 | 6.15.2022 | 9.30.2022 | ROMERO CONST | ATP Jan 17, 2022 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region VII | Bohol | 118205 | Tanday ES | CORELLA | 1 | 1 | 4 | Repair of Classrooms | 1685475.3 | 1 | 1331041.93 | COMPLETED | 1 | 2023-02-13 |  |  | 12022-03-01-2 | 3.30.2022 | 4.7.2022 | 4.19.2022 | 6.15.2022 | 9.30.2022 | ROMERO CONST | ATP Jan 17, 2022 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2022 | Region VII | Bohol | 118207 | Dela Paz ES | CORTES | 1 | 1 | 6 | Repair of Classrooms | 2084958.22 | 1 | 1647277.79 | COMPLETED | 1 | Jan 29.2023 |  |  | 12022-03-01-1 | 3.30.2022 | 4.7.2022 | 4.19.2022 | 6.15.2022 | 9.30.2022 | ROMERO CONST | ATP Jan 17, 2022 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2022 | Region VII | Bohol | 118699 | Cambuac Sur ES | SIKATUNA | 1 | 1 | 11 | Repair of Classrooms | 2480931.92 | 1 | 1959942.27 | COMPLETED | 1 | 2023-02-13 |  |  | 12022-03-01-2 | 3.30.2022 | 4.7.2022 | 4.19.2022 | 6.15.2022 | 9.30.2022 | ROMERO CONST | ATP Jan 17, 2022 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2022 | Region VII | Bohol | 118197 | Nahawan ES | CLARIN | 2 | 1 | 9 | Repair of Classrooms | 2651332.26 | 1 | 2634918.21 | COMPLETED | 1 | 2023-02-28 |  |  | 12022-03-01-3 | 3.30.2022 | 4.7.2022 | 4.19.2022 | 6.15.2022 | 9.30.2022 | INABANGA DRILLING | ATP Jan 17, 2022 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2022 | Region VII | Bohol | 118228 | Malitbog Elementary School | DAGOHOY | 2 | 1 | 9 | Repair of Classrooms | 2121016.52 | 1 | 1844676.76 | COMPLETED | 1 | Mach 5, 2023 |  |  | 12022-03-01-4 | 3.30.2022 | 4.7.2022 | 4.19.2022 | 6.15.2022 | 10.6.2022 | ELMUEL JAY TRADING & CONST | ATP Jan 17, 2022 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2022 | Region VII | Bohol | 118641 | San Isidro Central ES | SAN ISIDRO | 2 | 1 | 7 | Repair of Classrooms | 1590612.12 | 1 | 1383177.89 | COMPLETED | 1 | 2023-03-05 |  |  | 12022-03-01-4 | 3.30.2022 | 4.7.2022 | 4.19.2022 | 6.15.2022 | 10.6.2022 | ELMUEL JAY TRADING & CONST | ATP Jan 17, 2022 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2022 | Region VII | Bohol | 117955 | Badiang ES | ANDA | 3 | 1 | 9 | Repair of Classrooms | 3181801.14 | 1 | 2532521.16 | COMPLETED | 1 | 2023-02-28 |  |  | 12022-03-01-5 | 3.30.2022 | 4.7.2022 | 4.19.2022 | 6.15.2022 | 9.30.2022 | ALAGAMON CONST | ATP Jan 17, 2022 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2022 | Region VII | Bohol | 118024 | Rizal ES | BATUAN | 3 | 1 | 7 | Repair of Classrooms | 2372684.01 | 1 | 1866762.38 | COMPLETED | 1 | 2023-02-28 |  |  | 12022-03-01-6 | 3.30.2022 | 4.7.2022 | 4.19.2022 | 6.15.2022 | 9.30.2022 | ROMERO CONST | ATP Jan 17, 2022 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2022 | Region VII | Bohol | 118669 | Licolico ES | SEVILLA | 3 | 1 | 7 | Repair of Classrooms | 2011819.45 | 1 | 1577505.46 | COMPLETED | 1 | 2023-02-28 |  |  | 12022-03-01-6 | 3.30.2022 | 4.7.2022 | 4.19.2022 | 6.15.2022 | 9.30.2022 | ROMERO CONST | ATP Jan 17, 2022 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2022 | Region VII | Cebu | 119134 | Pondohan ES | BOLJOON | 2 | 1 | 6 | Repair of Classrooms | 3067481.98 | 2 | 3051317.85 | COMPLETED | 1 |  |  | CY 2022 REPAIR BATCH 2-DEPED-R7-CEBU-01 | CY 2022 REPAIR BATCH 2-DEPED-R7-CEBU-01 | August 3, 2022 | August 10, 2022 | August 22, 2022 | August 30, 2022 | November 21, 2022 | La Prueba Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2022 | Region VII | Cebu | 119447 | Montañeza ES | MALABUYOC | 2 | 1 | 13 | Repair of Classrooms | 8124237.16 | 1 | 8074200.13 | COMPLETED | 1 | 2022-11-01 |  | CY 2022 BEFF REPAIR-DEPED-R7-CEBU | CY 2022 BEFF REPAIR-DEPED-R7-CEBU-01 | 2022-03-15 | 2022-03-22 | 2022-04-04 | 2022-04-18 | 2022-06-27 | TRI BAIRN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2022 | Region VII | Cebu | 119607 | Dalahikan ES | SAMBOAN | 2 | 1 | 4 | Repair of Classrooms | 2390068.3 | 2 | 2355012.05 | COMPLETED | 1 |  |  | CY 2022 REPAIR BATCH 2-DEPED-R7-CEBU-02 | CY 2022 REPAIR BATCH 2-DEPED-R7-CEBU-02 | August 3, 2022 | August 10, 2022 | August 22, 2022 | August 30, 2022 | November 21, 2022 | GCATZ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2022 | Region VII | Cebu | 303073 | Pilar NHS | PILAR | 5 | 1 | 12 | Repair of Classrooms | 6283149.47 | 1 | 6264532.5 | COMPLETED | 1 | 2022-10-02 |  | CY 2022 BEFF REPAIR-DEPED-R7-CEBU | CY 2022 BEFF REPAIR-DEPED-R7-CEBU-02 | 2023-03-15 | 2023-03-22 | 2023-04-04 | 2023-04-18 | 2022-06-27 | BARR STEEL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2022 | Region VII | Negros Oriental | 120311 | Aniniaw ES | LA LIBERTAD | 1 | 1 | 5 | Repair of Classrooms & Toilet | 2511000 | 2 | 2490201.33 | COMPLETED | 1 | 2023-04-10 | 2023-03-28 | ITB no. 2022-06-061 | BEFF 202209008 | 2022-07-04 | 2022-07-12 | 2022-07-25 | 2022-07-28 | 2022-09-20 | Tribata Construction and Development | with approved time extension. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region VII | Negros Oriental | 120433 | Janayjanay Elementary School | SAN JOSE | 2 | 1 | 5 | Repair of Classrooms | 2801981.26 | 1 | 2207000 | COMPLETED | 1 | 2022-10-14 | 2022-12-06 | ITB no. 2022-02-007 | ITB no. 2022-02-007 | 2022-02-14 | 2023-02-23 | 2022-03-07 | 2022-03-24 | 2022-06-03 | RISM Builders & Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region VII | Siquijor | 120660 | Libo Elementary School | ENRIQUE VILLANUEVA | 0 | 1 | 3 | Repair of Classrooms | 1766789.71 | 1 | 1429945.54 | COMPLETED | 1 | 2022-09-17 | 2022-09-26 |  |  | 2022-02-08 | 2022-02-16 | 2022-02-28 | 2022-03-22 |  | NALE Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region VII | Siquijor | 500232 | Cabulihan Integrated School | LARENA | 0 | 1 | 1 | Repair of Classroom | 636955.25 | 1 | 535080.38 | COMPLETED | 1 | 2022-08-17 | 2022-09-26 |  |  | 2022-02-08 | 2022-02-16 | 2022-02-28 | 2022-03-22 |  | E.D. Angas Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2022 | Region VII | Siquijor | 303304 | Candaping National High School | MARIA | 0 | 1 | 3 | Repair of Classrooms | 1614561.19 | 1 | 1307112.06 | COMPLETED | 1 | 2022-10-17 |  |  |  | 2022-02-08 | 2022-02-16 | 2022-02-28 | 2022-03-22 |  | NALE Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region VII | Siquijor | 303300 | Tambisan National High School | SAN JUAN | 0 | 1 | 4 | Repair of Classrooms | 3064866.16 | 1 | 2513189.24 | COMPLETED | 1 | 2022-10-17 |  |  |  | 2022-02-08 | 2022-02-16 | 2022-02-28 | 2022-03-22 |  | E.D. Angas Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VII | Bais City | 120071 | Amalao Elementary School | BAIS CITY | 2nd | 1 | 3 | Repair of Classrooms | 4280000 | DPWH (Batch 1) | 4086043.23 | COMPLETED | 1 | 2023-12-21 | 2024-03-03 |  | 23HK0157 | 2023-07-06 | 2023-07-14 | 2023-07-26 | 2023-09-20 | 2023-10-04 | NALE Construction | to schedule punchlist | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Bais City | 120073 | Cambanjao ES | BAIS CITY | 2nd | 1 | 6 | Repair of Classrooms | 4110000 | DPWH (Batch 1) | 3960050 | COMPLETED | 1 | 2023-12-16 |  |  | 23HK0138 | 2023-06-30 | 2023-07-08 | 2023-07-20 | 2023-09-20 | 2023-10-02 | Ashleyka Const. & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VII | Bais City | 120076 | Dansulan ES | BAIS CITY | 2nd | 1 | 5 | Repair of Classrooms | 3710000 | DPWH (Batch 1) | 3566960.5 | COMPLETED | 1 | 2023-12-11 |  |  | 23HK0137 | 2023-06-30 | 2023-07-08 | 2023-07-20 | 2023-09-20 | 2023-10-02 | Dumduma Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VII | Bais City | 120104 | San Vicente Elementary School | BAIS CITY | 2nd | 1 | 3 | Repair of Classrooms | 3340000 | DPWH (Batch 1) | - | COMPLETED | 1 |  | 2024-03-12 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Bayawan City | 120146 | Canabuan Elementary School | CITY OF BAYAWAN (TULONG) | 3rd | 1 | 4 | Repair of Classrooms | 665000 | DEPED (Batch 1) | 641500 | COMPLETED | 1 | [6 empty] | 9/14/2023 | 2023-10-05 | 2023-10-06 | HIT Contractors |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VII | Bayawan City | 120128 | Dawis Elementary School | CITY OF BAYAWAN (TULONG) | 3rd | 1 | 3 | Repair of Classrooms | 2035000 | DPWH (Batch 1) | 1959000 | COMPLETED | 1 | 2023-12-31 | 2024-03-15 | 23HL0107 | 23HL0107 | 2023-08-24 | 2023-09-07 | 2023-09-19 | 2023-09-26 | 2023-12-10 | Tribata Construction and Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Bayawan City | 120165 | Tayawan Elementary School | CITY OF BAYAWAN (TULONG) | 3rd | 1 | 3 | Repair of Classrooms | 1745000 | DPWH (Batch 1) | 1681912.41 | COMPLETED | 1 | 2023-12-31 | 2024-03-15 | 23HL0108 | 23HL0108 | 2023-08-24 | 2023-09-07 | 2023-09-19 | 2023-09-26 | 2023-12-10 | RR Gadingan Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Bayawan City | 120141 | Villareal Elementary School | CITY OF BAYAWAN (TULONG) | 3rd | 1 | 5 | Repair of Classrooms | 3945000 | DPWH (Batch 1) | 3796987.33 | COMPLETED | 1 | 2023-12-31 | 2024-03-15 | 23HL0106 | 23HL0106 | 2023-08-24 | 2023-09-07 | 2023-09-19 | 2023-09-26 | 2023-12-10 | NRS Builders and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 186502 | Can-omay PS | ANTEQUERA | 1st | 1 | 1 | Repair of Classrooms | 258248.58 | DEPED (Batch 1) | 0 | COMPLETED | 1 | [10 empty] | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 302811 | Baclayon NHS | BACLAYON | 1st | 1 | 8 | Repair of Classrooms | 2716310.54 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118096 | Kinabag-an ES | CALAPE | 1st | 1 | 5 | Repair of Classrooms | 5345683.59 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118097 | Labu-on ES | CALAPE | 1st | 1 | 9 | Repair of Classrooms | 3672844.13 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118100 | Mantatao ES | CALAPE | 1st | 1 | 6 | Repair of Classrooms | 2074196.6 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 312319 | Hagbuaya High School | CATIGBIAN | 1st | 1 | 6 | Repair of Classrooms | 1207513.07 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 312320 | Haguilanan High School | CATIGBIAN | 1st | 1 | 4 | Repair of Classrooms | 1672678.94 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118209 | Loreto ES | CORTES | 1st | 1 | 7 | Repair of Classrooms | 2987668.17 | DPWH (Batch 2) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118216 | San Roque Elementary School | CORTES | 1st | 1 | 8 | Repair of Classrooms | 2906428.22 | DPWH (Batch 2) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118534 | Bayacabac ES | MARIBOJOC | 1st | 1 | 2 | Repair of Classrooms | 692229.67 | DEPED (Batch 1) | 619354.91 | COMPLETED | 1 | 2024-09-05 |  | NONE | 2024-02-001 | 2024-01-05 | 2024-01-12 | 2024-01-26 | 2024-03-28 | 2024-04-01 | NORTH STAR CONST. & TRADING | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118555 | Bolod Elementary School | PANGLAO | 1st | 1 | 8 | Repair of Classrooms | 3217773.27 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118700 | Sikatuna Central ES | SIKATUNA | 1st | 1 | 10 | Repair of Classrooms | 4489855.12 | DPWH (Batch 2) | 0 | Ongoing | 0.45 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 312332 | Bagongbanwa High School | TUBIGON | 1st | 1 | 4 | Repair of Classrooms | 851985.27 | DEPED (Batch 1) | 0 | COMPLETED | 1 | [10 empty] | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118785 | Jose Boja ES | TUBIGON | 1st | 1 | 7 | Repair of Classrooms | 2171819.18 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118791 | Pangapasan ES | TUBIGON | 1st | 1 | 3 | Repair of Classrooms | 2183161.95 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 302822 | Tubigon West NHS | TUBIGON | 1st | 1 | 12 | Repair of Classrooms | 3750140.08 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118030 | Hingotanan ES | BIEN UNIDO | 2nd | 1 | 23 | Repair of Classrooms | 35000000 | DPWH (Batch 2) | 0 | Ongoing | 0.15 | [10 empty] | Bid-out february 20, 2024 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 302857 | Hingotanan NHS | BIEN UNIDO | 2nd | 1 | 21 | Repair of Classrooms | 10000000 | DPWH (Batch 2) | 0 | Ongoing | 0.25 | [10 empty] | Bid-out february 20, 2024 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118078 | Lubang Elementary School | BUENAVISTA | 2nd | 1 | 10 | Repair of Classrooms | 12000000 | DPWH (Batch 2) | 0 | Ongoing | 0.75 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 312312 | Panghagban HS | BUENAVISTA | 2nd | 1 | 18 | Repair of Classrooms | 9000000 | DPWH (Batch 2) | 0 | Ongoing | 0.15 | [10 empty] | Bid-out february 20, 2024 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118186 | Bonbon Elementary School | CLARIN | 2nd | 1 | 3 | Repair of Classrooms | 1519267.88 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118218 | Babag ES | DAGOHOY | 2nd | 1 | 5 | Repair of Classrooms | 1610604.28 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [10 empty] | BIDDING 10/25/23 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118222 | Can-oling ES | DAGOHOY | 2nd | 1 | 9 | Repair of Classrooms | 4792341.93 | DPWH (Batch 2) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118230 | San Vicente ES | DAGOHOY | 2nd | 1 | 14 | Repair of Classrooms | 7269351.88 | DPWH (Batch 2) | 0 | Ongoing | 0.7 | [10 empty] | bidding march 18, 2024 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 302842 | Cantubod NHS | DANAO | 2nd | 1 | 24 | Repair of Classrooms | 9600000 | DPWH (Batch 2) | 0 | Ongoing | 0.93 | [10 empty] | bidding April 18, 2024 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 302841 | Danao NHS | DANAO | 2nd | 1 | 39 | Repair of Classrooms | 16000000 | DPWH (Batch 2) | 0 | Ongoing | 0.95 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118337 | Nasingin ES | GETAFE | 2nd | 1 | 11 | Repair of Classrooms | 4500000 | DPWH (Batch 2) | 0 | Ongoing | 0.5 | [10 empty] | bidding January 16, 2024 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118380 | Liloan Norte ES | INABANGA | 2nd | 1 | 10 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 312303 | Mayor Inocencio B. Mendez HS | PRES. CARLOS P. GARCIA (PITOGO) | 2nd | 1 | 24 | Repair of Classrooms | 9600000 | DPWH (Batch 2) | 0 | Ongoing | 0.37 | [10 empty] | bid out february 20, 2024 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118599 | Popoo ES | PRES. CARLOS P. GARCIA (PITOGO) | 2nd | 1 | 9 | Repair of Classrooms | 3600000 | DPWH (Batch 2) | 0 | Ongoing | 0.18 | [10 empty] | bidding march 18, 2024 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 501128 | Sto. Rosario Integrated School | PRES. CARLOS P. GARCIA (PITOGO) | 2nd | 1 | 4 | Repair of Classrooms | 12000000 | DPWH (Batch 2) | 0 | Ongoing | 0.2 | [10 empty] | bid out february 6, 2024 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118631 | Baryong Daan PS | SAN ISIDRO | 2nd | 1 | 2 | Repair of Classrooms | 1383898.75 | DPWH (Batch 2) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118635 | Cambansag Elementary | SAN ISIDRO | 2nd | 1 | 3 | Repair of Classrooms | 2294836.8 | DPWH (Batch 2) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118636 | Candungao ES | SAN ISIDRO | 2nd | 1 | 5 | Repair of Classrooms | 3012786.89 | DPWH (Batch 2) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 312327 | Candungao High School | SAN ISIDRO | 2nd | 1 | 2 | Repair of Classrooms | 1301487.58 | DPWH (Batch 2) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118734 | Busalian ES | TALIBON | 2nd | 1 | 16 | Repair of Classrooms | 7200000 | DPWH (Batch 2) | 0 | Ongoing | 0.6 | [10 empty] | bid out January 16, 2024 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118735 | Calituban ES | TALIBON | 2nd | 1 | 13 | Repair of Classrooms | 6500000 | DPWH (Batch 2) | 0 | Ongoing | 0.5 | [10 empty] | bid out february 20, 2024 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 312313 | Mayor Catalino Y. Casoyla MHS | TALIBON | 2nd | 1 | 22 | Repair of Classrooms | 7700000 | DPWH (Batch 2) | 0 | Ongoing | 0.3 | [10 empty] | bid out february 13, 2024 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118732 | P/Lt. Eugenio B. Artiaga ES | TALIBON | 2nd | 1 | 15 | Repair of Classrooms | 6750000 | DPWH (Batch 2) | 0 | Ongoing | 0.3 | [10 empty] | bid out february 20, 2024 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118749 | Guinobatan ES | TRINIDAD | 2nd | 1 | 3 | Repair of Classrooms | 1559243.56 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [10 empty] | BID OUT 10/19/23 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 302910 | Tagum Sur NHS | TRINIDAD | 2nd | 1 | 20 | Repair of Classrooms | 6000000 | DPWH (Batch 2) | 0 | Ongoing | 0.15 | [10 empty] | bidding march 19, 2024 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118802 | Bay-ang ES | UBAY | 2nd | 1 | 8 | Repair of Classrooms | 3235520.01 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [10 empty] | bid OUT - 10/16/23 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 312334 | Bulilis High School | UBAY | 2nd | 1 | 19 | Repair of Classrooms | 6969386.4 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118812 | Camambugan ES | UBAY | 2nd | 1 | 16 | Repair of Classrooms | 6956511.08 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [10 empty] | bid OUT - 10/16/23 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 302825 | Camambugan NHS | UBAY | 2nd | 1 | 26 | Repair of Classrooms | 8437707.14 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [10 empty] | bid OUT - 11/08/23 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 26 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118813 | Casate ES | UBAY | 2nd | 1 | 16 | Repair of Classrooms | 13700000 | DPWH (Batch 2) | 0 | Ongoing | 0.3 | [10 empty] | bidding march 18, 2024 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 303130 | Erico B. Aumentado High School | UBAY | 2nd | 1 | 9 | Repair of Classrooms | 3449802.31 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118825 | Lomangog ES | UBAY | 2nd | 1 | 16 | Repair of Classrooms | 7600000 | DPWH (Batch 2) | 0 | Ongoing | 0.25 | [10 empty] | bidding April 18, 2024 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 117943 | Katipunan Elementary School Annex | ALICIA | 3rd | 1 | 6 | Repair of Classrooms | 4366263 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 302863 | La Hacienda NHS | ALICIA | 3rd | 1 | 17 | Repair of Classrooms | 5946502 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 117950 | Untaga ES | ALICIA | 3rd | 1 | 13 | Repair of Classrooms | 5732633 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 302829 | CANDABONG NATIONAL HIGH SCHOOL | ANDA | 3rd | 1 | 11 | REPAIR OF CLASSROOMS | 9367164 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 117961 | LONDAG ES | ANDA | 3rd | 1 | 8 | REPAIR OF CLASSROOMS | 7801309 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118018 | Cantigdas Elementary School | BATUAN | 3rd | 1 | 5 | Repair of Classrooms | 3883411 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118026 | STA. CRUZ ES | BATUAN | 3rd | 1 | 3 | REPAIR OF CLASSROOMS | 3930471 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118111 | Cadapdapan ES | CANDIJAY | 3rd | 1 | 13 | Repair of Classrooms | 7096749 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118121 | Pagahat ES | CANDIJAY | 3rd | 1 | 2 | Repair of Classrooms | 1700751 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118126 | Tambongan ES | CANDIJAY | 3rd | 1 | 8 | Repair of Classrooms | 5079535 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 302855 | Guinsularan High School | DUERO | 3rd | 1 | 9 | Repair of Classrooms | 5408646 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118301 | San Pedro ES | DUERO | 3rd | 1 | 5 | Repair of Classrooms | 2402553 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 312336 | Lungsodaan High School | MABINI | 3rd | 1 | 6 | Repair of Classrooms | 1982188 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118665 | CAMBAGUI ES | SEVILLA | 3rd | 1 | 3 | REPAIR OF CLASSROOMS | 3911090 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 302903 | SEVILLA NATIONAL HIGH SCHOOL | SEVILLA | 3rd | 1 | 5 | REPAIR OF CLASSROOMS | 4573882 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 312362 | Nan-od High School | SIERRA BULLONES | 3rd | 1 | 4 | Repair of Classrooms | 1536710 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VII | Bohol | 118858 | Omjon ES | VALENCIA | 3rd | 1 | 13 | Repair of Classrooms | 8230580 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2023 | Region VII | Carcar City | 119159 | Liburon Elementary School | CITY OF CARCAR | 1st | 1 | 15 | Repair of Classrooms | 12335684.24 | DPWH (Batch 1) | 11902888 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2023 | Region VII | Carcar City | 119181 | OCANA CENTRAL ES | CITY OF CARCAR | 1st | 1 | 12 | Repair of Classrooms | 8639234.46 | DPWH (Batch 2) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2023 | Region VII | Carcar City | 119161 | PERRELOS ELEMENTARY SCHOOL | CITY OF CARCAR | 1st | 1 | 13 | Repair of Classrooms | 10161300.46 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119705 | Bahay-Bagacay ES | SIBONGA | 1st | 1 | 5 | Repair of Classrooms | 2809227.56 | DPWH (Batch 1) | 2700404.6 | COMPLETED | 1 | 2024-06-08 | 2024-01-24 | 23HE0182 | [5 empty] | 2023-10-25 | Ten twenty Allied Developers |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 118873 | Bulalacao ES | ALCOY | 2nd | 1 | 6 | Repair of Classrooms | 3038795.55 | DPWH (Batch 1) | - | Ongoing | 0.7 | 2024-04-08 |  | P00775256NP | 23HG0082 | 2023-04-10 | 2023-11-10 | 24/10/2023 | 20/11/2023 | 2023-11-12 | 647 Construction and development Corp. | (CLUSTER 3 ) 4,857,971.36 (to verify amount per site) | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 118877 | Nug-as ES | ALCOY | 2nd | 1 | 6 | Repair of Classrooms | 2047185.13 | DPWH (Batch 1) | - | Ongoing | 0.7 | 2024-04-08 |  | P00775257NP | 23HG0082 | 2023-04-10 | 2023-11-10 | 24/10/2023 | 20/11/2023 | 2023-11-12 | 647 Construction and development Corp. | (CLUSTER 3 ) 4,857,971.36 (to verify amount per site) | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119604 | Basak Elementary School | SAMBOAN | 2nd | 1 | 5 | Repair of Classrooms | 2710845.95 | DPWH (Batch 1) |  | Ongoing | 0.75 | 2024-07-06 |  | P00775260NP P00775258NP P00775261NP | 2HG0081 | 2023-04-10 | 2023-11-10 | 24/10/2023 | 20/11/2023 | 2023-11-12 | APRIL ROSE ENT. & BUILDERS | (CLUSTER 2 ) 5,434,867.65 (to verify amount per site) | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 500662 | Bulangsuran Integrated School | SAMBOAN | 2nd | 1 | 5 | Repair of Classrooms | 2535928.75 | DPWH (Batch 1) |  | Ongoing | 0.7 | 2024-11-05 |  | P00775264NP P00775262NP P00775259NP | 23HG0076 | 28/09/2023 | 2023-05-10 | 17/10/2023 | 23/10/2023 | 2023-08-11 | APRIL ROSE ENT. & BUILDERS | (CLUSTER 1 ) 6,633,547.64 (to verify amount per site) | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 187027 | Cambigong ES | SAMBOAN | 2nd | 1 | 4 | Repair of Classrooms | 2049809.28 | DPWH (Batch 1) |  | Ongoing | 0.6 | 2024-11-05 |  | P00775264NP P00775262NP P00775259NP | 23HG0076 | 28/09/2023 | 2023-05-10 | 17/10/2023 | 23/10/2023 | 2023-08-11 | APRIL ROSE ENT. & BUILDERS | (CLUSTER 1 ) 6,633,547.64 (to verify amount per site) | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119606 | Cañorong ES | SAMBOAN | 2nd | 1 | 4 | Repair of Classrooms | 2501006.95 | DPWH (Batch 1) |  | Ongoing | 0.8 | 2024-11-05 |  | P00775264NP P00775262NP P00775259NP | 2HG0076 | 28/09/2023 | 2023-05-10 | 17/10/2023 | 23/10/2023 | 2023-08-11 | APRIL ROSE ENT. & BUILDERS | (CLUSTER 1 ) 6,633,547.64 (to verify amount per site) | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119612 | Monteverde ES | SAMBOAN | 2nd | 1 | 3 | Repair of Classrooms | 1549154.16 | DPWH (Batch 1) |  | Ongoing | 0.6 | 2024-07-06 |  | P00775260NP P00775258NP P00775261NP | 23HG0081 | 2023-04-10 | 2023-11-10 | 24/10/2023 | 20/11/2023 | 2023-11-12 | APRIL ROSE ENT. & BUILDERS | (CLUSTER 2 ) 5,434,867.65 (to verify amount per site) | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119613 | Samboan Central ES | SAMBOAN | 2nd | 1 | 3 | Repair of Classrooms | 1546172.27 | DPWH (Batch 1) |  | Ongoing | 0.6 | 2024-07-06 |  | P00775260NP P00775258NP P00775261NP | 23HG0081 | 2023-04-10 | 2023-11-10 | 24/10/2023 | 20/11/2023 | 2023-11-12 | APRIL ROSE ENT. & BUILDERS | (CLUSTER 2) 5,434,867.65 (to verify amount per site) poor workmanship | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 303089 | San Sebastian NHS | SAMBOAN | 2nd | 1 | 17 | Repair of Classrooms | 8280717.16 | DPWH (Batch 1) | 7751165.3 | Ongoing | 0.9 | 2024-12-03 |  | P00775263NP | 23HG0075 | 28/09/2023 | 2023-05-10 | 17/10/2023 | 23/10/2023 | 2023-08-11 | APRIL ROSE ENT. & BUILDERS |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119075 | Budbud ES | BARILI | 3rd | 1 | 7 | Repair of Classrooms | 3782401.92 | DPWH (Batch 1) | 3620017.25 | COMPLETED | 1 | 2024-08-01 | 24/04/2024 | P00775265NP-CW1 | 23HF00100 | 29/09/2023 | 2023-05-10 | 17/10/2023 | 23/10/2023 | 26/10/2023 | JAY-BR ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119078 | Gunting Elementary School | BARILI | 3rd | 1 | 8 | Repair of Classrooms | 4614236.54 | DPWH (Batch 1) | 4422738.26 | COMPLETED | 1 | 23/03/2024 | 24/04/2024 | P00775266NP-CW1 | 23HF00105 | 29/09/2023 | 2023-05-10 | 17/10/2023 | 23/10/2023 | 26/10/2023 | JAY-BR ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119553 | Anapog ES | PINAMUNGAHAN | 3rd | 1 | 19 | Repair of Classrooms | 8176833.34 | DPWH (Batch 1) | 7800598.53 | COMPLETED | 1 | 24/01/2024 | 2024-07-03 | P00775267NP-CW1 | 23HF0093 | 29/09/2023 | 2023-05-10 | 17/10/2023 | 23/10/2023 | 26/10/2023 | DMDG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 303076 | Anopog NHS | PINAMUNGAHAN | 3rd | 1 | 15 | Repair of Classrooms | 5125707.77 | DPWH (Batch 1) | 4920913.07 | COMPLETED | 1 | 2024-05-02 | 24/04/2024 | P00775267NP-CW1 | 23HF0092 | 2023-06-10 | 2023-12-10 | 24/10/2023 | 2023-03-11 | 2023-08-11 | BL PANGAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119557 | Camugao ES | PINAMUNGAHAN | 3rd | 1 | 10 | Repair of Classrooms | 5090040.12 | DPWH (Batch 1) | 4890757.81 | COMPLETED | 1 | 2024-05-02 | 24/04/2024 | P00775268NP-CW1 | 23HF0090 | 2023-06-10 | 2023-12-10 | 24/10/2023 | 2023-03-11 | 2023-08-11 | BL PANGAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119562 | Lut-od ES | PINAMUNGAHAN | 3rd | 1 | 14 | Repair of Classrooms | 7243921.95 | DPWH (Batch 1) | 6950000 | COMPLETED | 1 | 23/01/2024 | 2024-06-03 | P00775269NP-CW1 | 23HF0091 | 29/09/2023 | 2023-05-10 | 17/10/2023 | 23/10/2023 | 26/10/2023 | DMDG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119567 | Punod ES | PINAMUNGAHAN | 3rd | 1 | 7 | Repair of Classrooms | 2977030.39 | DPWH (Batch 1) | 2868797.74 | COMPLETED | 1 | 2024-09-01 | 2024-06-03 | P00775270NP-CW1 | 23HF0103 | 29/09/2023 | 2023-05-10 | 17/10/2023 | 23/10/2023 | 26/10/2023 | DMDG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119571 | Sibago ES | PINAMUNGAHAN | 3rd | 1 | 7 | Repair of Classrooms | 3933029.84 | DPWH (Batch 1) | 3790517.21 | COMPLETED | 1 | 2024-09-01 | 2024-06-03 | P00775271NP-CW1 | 23HF0104 | 29/09/2023 | 2023-05-10 | 17/10/2023 | 23/10/2023 | 26/10/2023 | DMDG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 501916 | Catarman Integrated School | LILOAN | 5th | 1 | 6 | Repair of Classrooms | 2189318.39 | DPWH (Batch 1) |  | Ongoing | 0.95 | [10 empty] | FOR PUNCHLISTING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119546 | Moabog ES | PILAR | 5th | 1 | 3 | Repair of Classrooms | 1934898.8 | DPWH (Batch 2) |  | Ongoing | 0.95 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119854 | Buenavista ES | TUDELA | 5th | 1 | 6 | Repair of Classrooms | 2842630.53 | DPWH (Batch 2) |  | Ongoing | 0.9 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119856 | Daan Secante ES | TUDELA | 5th | 1 | 3 | Repair of Classrooms | 1553637.41 | DPWH (Batch 2) | 1496542.62 | Ongoing | 0.3 | 27/07/2024 | [8 empty] | CYJE FIRST BUILDERS CONSTRUCTION CORP. |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119248 | Tayud ES | CONSOLACION | 6th | 1 | 36 | Repair of Classrooms | 396436.04 | DEPED (Batch 1) | 5233500 | Ongoing | 0.95 |  |  | CY 2023 BEFF Repair | CY 2023 BEFF Repair-DepED-R7-Cebu | 2024-04-06 |  | 2024-11-06 | 18/06/2024 | 2024-09-07 | BARR STEEL CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119252 | Bangbang ES | CORDOVA | 6th | 1 | 12 | Repair of Classrooms | 4178938.39 | DPWH (Batch 1) | 3914891.02 | Ongoing | 0.95 | 15/02/2024 |  | P00775274NP | 223HN0156 | 2023-09-22 | 2023-09-29 | 2024-10-12 | 2023-10-18 | 2023-10-27 | Green world construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 187025 | Catarman Elementary School | CORDOVA | 6th | 1 | 2 | Repair of Classrooms | 1028357.29 | DPWH (Batch 1) | 992364.78 | Ongoing | 0.95 | 15/02/2024 |  | P00775276NP | 223HN0156 | 2023-09-22 | 2023-09-29 | 2024-10-12 | 2023-10-18 | 2023-10-27 | Green world construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119259 | Ibabao ES | CORDOVA | 6th | 1 | 11 | Repair of Classrooms | 3906152.75 | DPWH (Batch 1) | 3623398.99 | Ongoing | 0.95 | 15/02/2024 |  | P00775275NP | 223HN0156 | 2023-09-22 | 2023-09-29 | 2024-10-12 | 2023-10-18 | 2023-10-27 | Green world construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 118887 | Compostela ES | ALEGRIA | 7th | 1 | 10 | Repair of Classrooms | 5464765.99 | DPWH (Batch 1) | 5233500 | Ongoing | 0.95 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119398 | Anao ES | GINATILAN | 7th | 1 | 3 | Repair of Classrooms | 1770932.8 | DPWH (Batch 1) | 1620000 | Ongoing | 0.95 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119405 | Kagsing ES | GINATILAN | 7th | 1 | 5 | Repair of Classrooms | 2794373.38 | DPWH (Batch 1) | 2600000 | Ongoing | 0.95 | [9 empty] | FIRST GRANDEUR BUILDERS |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119442 | Lombo ES | MALABUYOC | 7th | 1 | 4 | Repair of Classrooms | 3075098.68 | DPWH (Batch 1) | 2887973.7 | COMPLETED | 1 |  | 2024-08-07 |  | 23HO0333 | [5 empty] | BT CONSTRUCTION & GENERAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 502119 | Looc IS | MALABUYOC | 7th | 1 | 10 | Repair of Classrooms | 5768971.99 | DPWH (Batch 1) | 5483508.03 | Ongoing | 0.95 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 312462 | Mahanlud NHS | MALABUYOC | 7th | 1 | 5 | Repair of Classrooms | 1959991.53 | DPWH (Batch 1) | 1800000 | Ongoing | 0.95 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119594 | Butong ES | RONDA | 7th | 1 | 4 | Repair of Classrooms | 1611587.61 | DPWH (Batch 1) | 1532133.41 | COMPLETED | 1 | 2024-10-02 | 24/04/2024 | P00775283NP | 23HO0334 | 2023-01-12 | 2023-11-12 | 21/12/2023 | 29/12/2023 | 2024-11-01 | LA PRUEBA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119601 | Ronda Central ES | RONDA | 7th | 1 | 16 | Repair of Classrooms | 8186738.78 | DPWH (Batch 1) | 7850202.92 | COMPLETED | 1 | 24/05/2024 | 24/05/2024 | P00775284NP | 23HO0330 | 2023-01-12 | 2023-11-12 | 21/12/2023 | 29/12/2023 | 2024-11-01 | Ten twenty Allied Developers |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2023 | Region VII | Cebu | 119602 | Sta. Cruz ES | RONDA | 7th | 1 | 14 | Repair of Classrooms | 5431268.01 | DPWH (Batch 1) | 5184452.32 | COMPLETED | 1 | 2024-10-03 | 21/10/2024 | P00775285NP | 23HO0332 | 2023-01-12 | 2023-11-12 | 21/12/2023 | 29/12/2023 | 2024-11-01 | BANTAY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2023 | Region VII | Cebu City | 303151 | MABOLO NATIONAL HIGH SCHOOL | CEBU CITY (Capital) | 1st | 1 | 46 | Repair of Classrooms | 5564000 | DPWH (Batch 1) | 5359000 | COMPLETED | 1 |  |  |  | 23HH0135 |  |  | Sept. 20, 2023 |  | Oct. 16, 2023 | Planac Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 46 | 0 | 0
REPAIR 2023 | Region VII | Cebu City | 303133 | Don Vicente Rama Mem. NHS (Basak NHS) | CEBU CITY (Capital) | 2nd | 1 | 104 | Repair of Classrooms | 9000000 | DPWH (Batch 1) | 8663198.33 | COMPLETED | 1 |  |  |  | 23HH0137 |  |  | Sept. 20, 2023 |  | Oct. 19, 2023 | EV Caballero |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 104 | 0 | 0
REPAIR 2023 | Region VII | Cebu City | 119880 | Guadalupe ES | CEBU CITY (Capital) | 2nd | 1 | 38 | Repair of Classrooms | 6350000 | DPWH (Batch 1) | 6062760 | COMPLETED | 1 |  |  |  | 23HH0136 |  |  | Sept. 20, 2023 |  | Oct. 17, 2023 | Matroson Builders & Eng'g Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 38 | 0 | 0
REPAIR 2023 | Region VII | Cebu City | 119907 | Inayawan ES | CEBU CITY (Capital) | 2nd | 1 | 46 | Repair of Classrooms | 9351000 | DPWH (Batch 1) | 9101676.4 | COMPLETED | 1 |  |  |  | 23HH0138 |  |  | Sept. 20, 2023 |  | Oct. 19, 2023 | Corro Const. Devt & Trade Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 46 | 0 | 0
REPAIR 2023 | Region VII | Cebu City | 187501 | Quiot ES | CEBU CITY (Capital) | 2nd | 1 | 32 | Repair of Classrooms | 5300000 | DPWH (Batch 1) | 5108546.19 | COMPLETED | 1 |  |  |  | 23HH0134 |  |  | Sept. 20, 2023 |  | Oct. 17, 2023 | JAJ & L Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0
REPAIR 2023 | Region VII | City of Naga, Cebu | 119514 | Bairan Elementary School | CITY OF NAGA | 1st | 1 | 4 | Repair of Classrooms | 2102141.53 | DPWH (Batch 1) | 2017154.63 | COMPLETED | 1 | March 22, 2024 |  | P00775292NP | 23HE0167 | SEPTEMBER 12, 2023 | SEPTEMBER 19, 2023 | OCTOBER 02, 2023 | OCTOBER 17, 2023 | OCTOBER 24, 2023 | BT CONSTRUCTION & GENERAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VII | City of Naga, Cebu | 302929 | Balirong National High School | CITY OF NAGA | 1st | 1 | 4 | Repair of Classrooms | 1939995.27 | DPWH (Batch 1) | 1860000 | COMPLETED | 1 | March 22, 2024 |  | P00775294NP | 23HE0169 | SEPTEMBER 12, 2023 | SEPTEMBER 19, 2023 | OCTOBER 02, 2023 | OCTOBER 17, 2023 | OCTOBER 24, 2023 | LRTY CONSTRUCTION & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VII | City of Naga, Cebu | 303002 | Don Emilio Canonigo Memorial National High School | CITY OF NAGA | 1st | 1 | 5 | Repair of Classrooms | 2784658.45 | DPWH (Batch 1) | 2680000 | COMPLETED | 1 | February 21, 2024 |  | P00775295NP | 23HE0181 | SEPTEMBER 15, 2023 | SEPTEMBER 22, 2023 | OCTOBER 04, 2023 | OCTOBER 18, 2023 | OCTOBER 24, 2023 | PLANAC CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VII | City of Naga, Cebu | 312433 | Lanas National High School | CITY OF NAGA | 1st | 1 | 3 | Repair of Classrooms | 1656748.55 | DPWH (Batch 1) | 1586757.8 | COMPLETED | 1 | February 21, 2024 |  | P00775297NP | 23HE0180 | SEPTEMBER 15, 2023 | SEPTEMBER 22, 2023 | OCTOBER 04, 2023 | OCTOBER 18, 2023 | OCTOBER 24, 2023 | A.T. DUMLAO CONSTRUCTION, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | City of Naga, Cebu | 119518 | Langtad Elementary School | CITY OF NAGA | 1st | 1 | 2 | Repair of Classrooms | 999836.36 | DEPED (Batch 1) | 950096.3 | COMPLETED | 1 | March 05, 2024 | December 16, 2023 | cityofnaga 2023-02 | cityofnaga 2023-02 | November 01, 2023 |  | November 08, 2023 | November 17, 2023 | November 21, 2023 | TRI BAIRN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VII | City of Naga, Cebu | 119519 | Lutac Elementary School | CITY OF NAGA | 1st | 1 | 5 | Repair of Classrooms | 2525761.63 | DPWH (Batch 1) | 2427359.77 | COMPLETED | 1 | March 22, 2024 |  | P00775293NP | 23HE0173 | SEPTEMBER 12, 2023 | SEPTEMBER 19, 2023 | OCTOBER 02, 2023 | OCTOBER 17, 2023 | OCTOBER 24, 2023 | EMINENT BUILDERS INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VII | City of Naga, Cebu | 119508 | Naalad Elementary School | CITY OF NAGA | 1st | 1 | 7 | Repair of Classrooms | 3498240.91 | DPWH (Batch 1) | 3365302.48 | COMPLETED | 1 | March 22, 2024 | February 2, 2024 | P00775291NP | 23HE0172 | SEPTEMBER 12, 2023 | SEPTEMBER 19, 2023 | OCTOBER 02, 2023 | OCTOBER 17, 2023 | OCTOBER 24, 2023 | TEN TWENTY ALLIED DEVELOPERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | Region VII | City of Naga, Cebu | 502093 | Npc-Colon Integrated School | CITY OF NAGA | 1st | 1 | 4 | Repair of Classrooms | 1999816.33 | DPWH (Batch 1) | 1922000 | COMPLETED | 1 | March 24, 2024 |  | P00775298NP | 23HE0168 | SEPTEMBER 12, 2023 | SEPTEMBER 22, 2023 | OCTOBER 02, 2023 | OCTOBER 18, 2023 | OCTOBER 24, 2023 | PLANAC CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VII | City of Naga, Cebu | 303035 | Placido L. Señor National High School | CITY OF NAGA | 1st | 1 | 9 | Repair of Classrooms | 4499136.71 | DPWH (Batch 1) | 4331666.53 | COMPLETED | 1 | February 21, 2024 |  | P00775296NP | 23HE0170 | SEPTEMBER 12, 2023 | SEPTEMBER 19, 2023 | OCTOBER 02, 2023 | OCTOBER 17, 2023 | OCTOBER 24, 2023 | EMINENT BUILDERS INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2023 | Region VII | Danao City | 500447 | BINALIW INTEGRATED SCHOOL | DANAO CITY | 5th | 1 | 3 | Repair of Classrooms | 1500000 | DPWH (Batch 1) | 1493454.93 | COMPLETED | 1 | 2023-12-02 |  | P00775300NP | 23HI0130 | 2023-09-06 | 2023-09-27 |  | 2023-10-03 | 2023-10-13 | WQC Design and Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Danao City | 500745 | Cogon Cruz Integrated School | DANAO CITY | 5th | 1 | 3 | Repair of Classrooms | 1200000 | DPWH (Batch 1) | 1192198.92 | COMPLETED | 1 | 2023-11-25 | 2023-11-25 | P00775301NP | 23HI0131 | 2023-09-06 | 2023-09-27 |  | 2023-09-29 | 2023-10-06 | WQC Design and Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Danao City | 302959 | Elpidio H. Perez Memorial Technical-Vocational High School | DANAO CITY | 5th | 1 | 3 | Repair of Classrooms | 1500000 | DPWH (Batch 1) | 1441633.79 | COMPLETED | 1 | 2023-12-02 |  | P00775299NP | 23HI0132 | 2023-09-06 | 2023-09-27 |  | 2023-10-03 | 2023-10-13 | WQC Design and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Danao City | 500783 | Guinacot Integrated School | DANAO CITY | 5th | 1 | 3 | Repair of Classrooms | 1200000 | DPWH (Batch 1) | 1192949.76 | COMPLETED | 1 | 2023-12-02 | 2023-12-02 | P00775302NP | 23HI0133 | 2023-09-06 | 2023-09-27 |  | 2023-10-03 | 2023-10-13 | WQC Design and Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Guihulngan City | 120263 | BALOGO ELEMENTARY SCHOOL | CITY OF GUIHULNGAN | 1st | 1 | 1 | Repair of Classrooms | 2800000 | DPWH (Batch 1) | 2800000 | COMPLETED | 1 | 2023-12-29 | 2023-12-29 | P00775305NP | 23HJ0136 | 2023-08-24 | 2023-08-31 | 2023-09-13 | 2023-09-26 | 2023-10-02 | MAI CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region VII | Guihulngan City | 120235 | Binobohan ES | CITY OF GUIHULNGAN | 1st | 1 | 3 | Repair of Classrooms | 4200000 | DPWH (Batch 1) | 4200000 | Ongoing | 0.6 | 2024-01-06 |  | P00775303NP | 23HJ0117 | 2023-08-22 | 2023-08-29 | 2023-09-11 | 2023-09-19 | 2023-09-28 | KAWAII BUILDERS & SUPPLIES |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region VII | Guihulngan City | 120244 | Don Pelagio Villegas Memorial E/S | CITY OF GUIHULNGAN | 1st | 1 | 2 | Repair of Classrooms | 4600000 | DPWH (Batch 1) | 4600000 | COMPLETED | 1 | 2023-12-22 | 2023-12-22 | P00775304NP | 23HJ0107 | 2023-08-17 | 2023-08-24 | 2023-09-05 | 2023-09-13 | 2023-09-25 | K.M. GOLONG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VII | Guihulngan City | 120267 | Guihulngan South CS | CITY OF GUIHULNGAN | 1st | 1 | 3 | Repair of Classrooms | 4200000 | DPWH (Batch 1) | 4200000 | COMPLETED | 1 | 2024-01-06 | 2024-01-06 | P00775306NP | 23HJ0120 | 2023-08-22 | 2023-08-29 | 2023-09-11 | 2023-09-19 | 2023-09-28 | K.M. GOLONG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Guihulngan City | 120272 | Linantuyan ES | CITY OF GUIHULNGAN | 1st | 1 | 2 | Repair of Classrooms | 3900000 | DPWH (Batch 1) | 3900000 | COMPLETED | 1 | 2023-12-29 | 2023-12-29 | P00775307NP | 23HJ0135 | 2023-08-24 | 2023-08-31 | 2023-09-13 | 2023-09-26 | 2023-10-02 | MAI CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VII | Guihulngan City | 324802 | P. Zamora National High School | CITY OF GUIHULNGAN | 1st | 1 | 4 | Repair of Classrooms | 5400000 | DPWH (Batch 1) | 5400000 | COMPLETED | 1 | 2024-01-18 | 2024-01-18 | P00775308NP | 23HJ0125 | 2023-08-24 | 2023-08-31 | 2023-09-13 | 2023-09-26 | 2023-10-02 | K.M. GOLONG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VII | Guihulngan City | 120638 | Tabon Elementary School | VALLEHERMOSO | 1st | 1 | 3 | Repair of Classrooms | 4400000 | DPWH (Batch 1) | 4400000 | COMPLETED | 1 | 2024-04-15 | 2024-01-08 | P00775309NP | 23HJ0127 | 2023-08-24 | 2023-08-31 | 2023-09-13 | 2023-09-26 | 2023-10-02 | K.M. GOLONG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Lapu-Lapu City | 119977 | Gun-ob Elementary School | LAPU-LAPU CITY (OPON) | 6th | 1 | 10 | Repair of Classrooms | 3500000 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2023 | Region VII | Lapu-Lapu City | 312704 | Marigondon NHS-Sudtonggan Night High School | LAPU-LAPU CITY (OPON) | 6th | 1 | 4 | Repair of Classrooms | 2000000 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VII | Lapu-Lapu City | 119955 | Pangan-an Elementary School | LAPU-LAPU CITY (OPON) | 6th | 1 | 7 | Repair of Classrooms | 2800000 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | Region VII | Lapu-Lapu City | 119956 | Poo Elementary School | LAPU-LAPU CITY (OPON) | 6th | 1 | 10 | Repair of Classrooms | 5000000 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2023 | Region VII | Lapu-Lapu City | 303188 | Pusok NHS - Pusok Night HS | LAPU-LAPU CITY (OPON) | 6th | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VII | Lapu-Lapu City | 303191 | Sta. Rosa NHS - Pangan-an High School | LAPU-LAPU CITY (OPON) | 6th | 1 | 5 | Repair of Classrooms | 2500000 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VII | Mandaue City | 119998 | Basak ES | MANDAUE CITY | 6th | 1 | 9 | Repair of Classrooms | 1379578 | DPWH (Batch 1) | 1330123.48 | COMPLETED | 1 | 2024-01-01 | 2023-12-28 | P00775316NP | 23HN0159 | 2023-09-22 | 2023-09-29 | 2023-10-12 | 2023-10-18 | 2023-10-27 | Bantay Construction | CLUSTERED PROJECT | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2023 | Region VII | Mandaue City | 303194 | Cabancalan NHS | MANDAUE CITY | 6th | 1 | 9 | Repair of Classrooms | 2805450 | DPWH (Batch 1) | 2682155.83 | COMPLETED | 1 | 2024-01-01 | 2024-04-15 | P00775319NP | 23HN0158 | 2023-09-22 | 2023-09-29 | 2023-10-12 | 2023-10-18 | 2023-10-27 | GTM Builders and Supply | CLUSTERED PROJECT | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2023 | Region VII | Mandaue City | 120018 | Don Calixto C. Yongco, Sr. ES (Tawason ES) | MANDAUE CITY | 6th | 1 | 3 | Repair of Classrooms | 1023122 | DPWH (Batch 1) | 985489.62 | COMPLETED | 1 | 2024-01-01 | 2023-12-28 | P00775318NP | 23HN0159 | 2023-09-22 | 2023-09-29 | 2023-10-12 | 2023-10-18 | 2023-10-27 | Bantay Construction | CLUSTERED PROJECT | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Mandaue City | 303197 | Don Gerardo LLOMNHS | MANDAUE CITY | 6th | 1 | 6 | Repair of Classrooms | 1650000 | DPWH (Batch 1) | 1589835.3 | COMPLETED | 1 | 2024-01-01 | 2024-04-15 | P00775320NP | 23HN0158 | 2023-09-22 | 2023-09-29 | 2023-10-12 | 2023-10-18 | 2023-10-27 | GTM Builders and Supply | CLUSTERED PROJECT | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VII | Mandaue City | 119996 | Ibabao-Estancia ES | MANDAUE CITY | 6th | 1 | 4 | Repair of Classrooms | 857402 | DEPED (Batch 1) | 761022.91 | COMPLETED | 1 | 2024-04-20 | March 18, 2024 | REP2023-01 | 23-11-036 | September 1, 2023 | September 8, 2023 | September 20, 2023 | September 26, 2023 | 2023-11-20 | HERO Construction & Development Corporation | Clustered Project | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VII | Mandaue City | 119999 | Labogon ES | MANDAUE CITY | 6th | 1 | 2 | Repair of Classrooms | 942214 | DEPED (Batch 1) | 836354.84 | COMPLETED | 1 | 2024-04-20 | March 18, 2024 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VII | Mandaue City | 120000 | Leonard Wood ES | MANDAUE CITY | 6th | 1 | 2 | Repair of Classrooms | 825130 | DEPED (Batch 1) | 732309.85 | COMPLETED | 1 | 2024-04-20 | March 18, 2024 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VII | Mandaue City | 303201 | Mandaue City Science HS | MANDAUE CITY | 6th | 1 | 11 | Repair of Classrooms | 1691500 | DPWH (Batch 1) | 1629685.67 | COMPLETED | 1 | 2024-01-01 |  | P00775321NP | 23HN0158 | 2023-09-22 | 2023-09-29 | 2023-10-12 | 2023-10-18 | 2023-10-27 | GTM Builders and Supply | CLUSTERED PROJECT | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2023 | Region VII | Mandaue City | 120017 | Tabok ES II | MANDAUE CITY | 6th | 1 | 14 | Repair of Classrooms | 2500000 | DPWH (Batch 1) | 2410423.83 | COMPLETED | 1 | 2024-01-01 |  | P00775317NP | 23HN0159 | 2023-09-22 | 2023-09-29 | 2023-10-12 | 2023-10-18 | 2023-10-27 | Bantay Construction | CLUSTERED PROJECT | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120039 | Carol-an Elementary School | AYUNGON | 1st | 1 | 7 | Repair of Classrooms | 6900000 | DPWH (Batch 1) | 6608793.79 | COMPLETED | 1 | 02/20/2024 |  | P00775322NP | 23HJ0119 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | EJJ Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120040 | Duli-Duli Elementary School | AYUNGON | 1st | 1 | 2 | Repair of Classrooms | 4600000 | DPWH (Batch 1) | 4385649.39 | COMPLETED | 1 | 12/22/23 |  | P00775323NP | 23HJ0108 | 8/17/23 | 8/24/23 | 2023-05-09 | 9/13/23 | 9/25/23 | E.F.V. Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 303277 | Mabato Provincial Community HS | AYUNGON | 1st | 1 | 6 | Repair of Classrooms | 6100000 | DPWH (Batch 1) | 5835766.89 | COMPLETED | 1 | 2024-10-02 |  | P00775326NP | 23HJ0122 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | EJJ Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120057 | Tampocon I Elementary School | AYUNGON | 1st | 1 | 6 | Repair of Classrooms | 5200000 | DPWH (Batch 1) | 4968985.83 | COMPLETED | 1 | 2024-06-01 |  | P00775324NP | 23HJ0134 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | Gram Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120058 | Tibyawan Elementary School | AYUNGON | 1st | 1 | 3 | Repair of Classrooms | 5400000 | DPWH (Batch 1) | 5166301.97 | COMPLETED | 1 | 2024-08-01 |  | P00775325NP | 23HJ0129 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | EJJ Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120170 | Batangan Elementary School | BINDOY (PAYABON) | 1st | 1 | 8 | Repair of Classrooms | 7600000 | DPWH (Batch 1) | 7285000 | COMPLETED | 1 | 3/17/24 |  | P00775327NP | 23HJ0131 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | Gram Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 312917 | Cabcaban CHS | BINDOY (PAYABON) | 1st | 1 | 12 | Repair of Classrooms | 8400000 | DPWH (Batch 1) | 8040003.5 | COMPLETED | 1 | 3/16/24 |  | P00775329NP | 23HJ0106 | 8/17/23 | 8/24/23 | 2023-05-09 | 9/15/23 | 9/25/23 | EJJ Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 189519 | Naula-an Elementary School | BINDOY (PAYABON) | 1st | 1 | 2 | Repair of Classrooms | 5500000 | DPWH (Batch 1) | 5248804.6 | COMPLETED | 1 | 12/22/23 |  | P00775328NP | 23HJ0110 | 8/17/23 | 8/24/23 | 2023-05-09 | 9/13/23 | 9/25/23 | E.F.V. Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120291 | Bangcal Elementary School | JIMALALUD | 1st | 1 | 3 | Repair of Classrooms | 5400000 | DPWH (Batch 1) | 5164904.61 | COMPLETED | 1 | 2024-06-01 |  | P00775330NP | 23HJ0115 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | Gram Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120293 | Buto Primary School | JIMALALUD | 1st | 1 | 2 | Repair of Classrooms | 5400000 | DPWH (Batch 1) | 5191029.12 | COMPLETED | 1 | 2024-01-02 |  | P00775331NP | 23HJ0105 | 9/14/2023 | 9/21/23 | 2023-03-10 | 10/18/23 | 2023-03-11 | Higel Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120297 | Irene Elementary School | JIMALALUD | 1st | 1 | 1 | Repair of Classrooms | 2270000 | DPWH (Batch 1) | 2180230.39 | Ongoing | 0.99 | 2024-01-02 |  | P00775329NP | 23HJ0109 | 9/14/2023 | 9/21/23 | 2023-03-10 | 10/18/23 | 2023-03-11 | Kawaii Builders and Supplies |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120304 | Owacan ES | JIMALALUD | 1st | 1 | 6 | Repair of Classrooms | 4900000 | DPWH (Batch 1) | 4708620.97 | COMPLETED | 1 | 2024-10-02 |  | P00775333NP | 23HJ0124 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | Higel Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120308 | Tamao Elementary School | JIMALALUD | 1st | 1 | 3 | Repair of Classrooms | 5400000 | DPWH (Batch 1) | 5205977.97 | COMPLETED | 1 | 2024-08-01 |  | P00775334NP | 23HJ0128 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | Fakujo Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120314 | Biga-a ES | LA LIBERTAD | 1st | 1 | 3 | Repair of Classrooms | 2900000 | DPWH (Batch 1) | 2779994.93 | COMPLETED | 1 | 2024-06-01 |  | P00775335NP | 23HJ0116 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | Gram Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120315 | Busilac ES | LA LIBERTAD | 1st | 1 | 6 | Repair of Classrooms | 6500000 | DPWH (Batch 1) | 6202500 | COMPLETED | 1 | 3/17/24 |  | P00775336NP | 23HJ0118 | 9/14/23 | 9/21/23 | 2023-03-10 | 10/18/2023 | 2023-03-11 | H.I.T. Contractors |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120326 | Mapalasan ES | LA LIBERTAD | 1st | 1 | 2 | Repair of Classrooms | 3370000 | DPWH (Batch 1) | 3219891.04 | COMPLETED | 1 | 12/22/23 |  | P00775337NP | 23HJ0111 | 8/17/23 | 8/24/23 | 2023-05-09 | 9/13/23 | 9/25/23 | Gram Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120328 | Nasunggan ES | LA LIBERTAD | 1st | 1 | 2 | Repair of Classrooms | 4600000 | DPWH (Batch 1) | 4399882.18 | Ongoing | 0.98 | 12/22/23 |  | P00775338NP | 23HJ0112 | 8/17/23 | 8/24/23 | 2023-05-09 | 9/13/23 | 9/25/23 | Gram Construction and Supply |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120330 | Pangca ES | LA LIBERTAD | 1st | 1 | 2 | Repair of Classrooms | 7000000 | DPWH (Batch 1) | 6724010.14 | COMPLETED | 1 | 12/29/23 |  | P00775339NP | 23HJ0126 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | Higel Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120380 | Bagtic ES | MANJUYOD | 1st | 1 | 6 | Repair of Classrooms | 7600000 | DPWH (Batch 1) | 7305783.65 | COMPLETED | 1 | 2024-10-02 |  | P00775340NP | 23HJ0113 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | Kouken Construction | on going rectification of punchlist items | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120391 | LOCAY E/S | MANJUYOD | 1st | 1 | 3 | Repair of Classrooms | 4700000 | DPWH (Batch 1) | 4510326.42 | COMPLETED | 1 | 2024-06-01 |  | P00775341NP | 23HJ0121 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | Kouken Construction | on going rectification of punchlist items | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120397 | Palay ES | MANJUYOD | 1st | 1 | 2 | Repair of Classrooms | 5560000 | DPWH (Batch 1) | 5306555.02 | COMPLETED | 1 | 12/27/23 |  | P00775342NP | 23HJ0104 | 8/17/23 | 8/24/23 | 2023-05-09 | 9/19/23 | 9/28/23 | E.F.V. Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120399 | Sagrada ES | MANJUYOD | 1st | 1 | 3 | Repair of Classrooms | 5400000 | DPWH (Batch 1) | 5168401.97 | COMPLETED | 1 | 2024-08-01 |  | P00775343NP | 23HJ0132 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | EJJ Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120402 | San Isidro ES | MANJUYOD | 1st | 1 | 5 | Repair of Classrooms | 6700000 | DPWH (Batch 1) | 6416000 | COMPLETED | 1 | 2024-02-01 |  | P00775344NP | 23HJ0133 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | MAI Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120405 | Tubod ES | MANJUYOD | 1st | 1 | 3 | Repair of Classrooms | 5400000 | DPWH (Batch 1) | 5164201.97 | COMPLETED | 1 | 2024-08-01 |  | P00775345NP | 23HJ0130 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | EJJ Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120579 | Banga Elementary School | TAYASAN | 1st | 1 | 7 | Repair of Classrooms | 8000000 | DPWH (Batch 1) | 7670000 | COMPLETED | 1 | 02/20/2024 |  | P00775346NP | 23HJ0114 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | Gram Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120591 | Matuog Elementary School | TAYASAN | 1st | 1 | 7 | Repair of Classrooms | 6700000 | DPWH (Batch 1) | 6414976.03 | COMPLETED | 1 | 02/20/2024 |  | P00775347NP | 23HJ0123 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | EJJ Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120027 | Panusuan Elementary School | AMLAN (AYUQUITAN) | 2nd | 1 | 2 | Repair of Classrooms | 2550000 | DPWH (Batch 2) | 0 | COMPLETED | 1 | 2024-05-10 |  |  |  | September 26, 2023 | October 04, 2023 | October 18, 2023 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 303209 | Silab Community High School Annex | AMLAN (AYUQUITAN) | 2nd | 1 | 8 | Repair of Classrooms | 3660000 | DPWH (Batch 1) | 3513835 | COMPLETED | 1 | 2023-12-10 |  |  | 23KH0133 | July 04, 2023 | July 12, 2023 | July 24, 2023 | September 19, 2023 | September 28, 2023 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120029 | Tandayag Elementary School | AMLAN (AYUQUITAN) | 2nd | 1 | 7 | Repair of Classrooms | 8500000 | DPWH (Batch 2) | 0 | COMPLETED | 1 | 2024-06-08 |  |  |  | September 26, 2023 | October 04, 2023 | October 18, 2023 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 189530 | Alagasihan Elementary School | MABINAY | 2nd | 1 | 3 | Repair of Classrooms | 2140000 | DPWH (Batch 1) | 2059300 | COMPLETED | 1 | 2023-11-15 |  |  | 23KH0153 | July 06, 2023 | July 14, 2023 | July 26, 2023 | September 21, 2023 | October 04, 2023 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120338 | Arebasore Elementary School | MABINAY | 2nd | 1 | 3 | Repair of Classrooms | 3360000 | DPWH (Batch 1) | 3236735.97 | COMPLETED | 1 | 2023-12-11 |  |  | 23KH0154 | July 06, 2023 | July 14, 2023 | July 26, 2023 | September 15, 2023 | October 04, 2023 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120340 | Baliw Elementary School | MABINAY | 2nd | 1 | 3 | Repair of Classrooms | 3730000 | DPWH (Batch 1) | 3595000 | COMPLETED | 1 | 2023-12-14 |  |  | 23KH0144 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 20, 2023 | October 03, 2023 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120344 | Basakan Elementary School | MABINAY | 2nd | 1 | 2 | Repair of Classrooms | 2320000 | DPWH (Batch 1) | 2216406.05 | Ongoing | 0.99 | 2023-11-17 |  |  | 23KH0149 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 20, 2023 | October 03, 2023 |  | ongoing rectification of punchlisted items | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 312924 | Campanun-an Senior High School | MABINAY | 2nd | 1 | 2 | Repair of Classrooms | 2340000 | DPWH (Batch 1) | 2235488.03 | Ongoing | 0.98 | 2023-11-17 |  |  | 23KH0150 | July 06, 2023 | July 14, 2023 | July 26, 2023 | September 21, 2023 | October 03, 2023 |  | ongoing rectification of punchlisted items | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120350 | Campo-aling Elementary School | MABINAY | 2nd | 1 | 2 | Repair of Classrooms | 2670000 | DPWH (Batch 1) | 2570218 | COMPLETED | 1 | 2023-12-03 |  |  | 23KH0151 | July 06, 2023 | July 14, 2023 | July 26, 2023 | September 21, 2023 | October 05, 2023 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120352 | Cansal-ing Elementary School | MABINAY | 2nd | 1 | 2 | Repair of Classrooms | 2220000 | DPWH (Batch 1) | 2123745.83 | Ongoing | 0.99 | 2023-11-16 |  |  | 23KH0152 | July 06, 2023 | July 14, 2023 | July 26, 2023 | September 21, 2023 | October 04, 2023 |  | ongoing rectification of punchlisted items | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120358 | Don Cristito C. Tirambulo MES | MABINAY | 2nd | 1 | 6 | Repair of Classrooms | 4830000 | DPWH (Batch 1) | 4650095 | COMPLETED | 1 | 2023-12-28 |  |  | 23KH0141 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 20, 2023 | October 03, 2023 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120360 | Himocdungon Elementary School | MABINAY | 2nd | 1 | 4 | Repair of Classrooms | 3940000 | DPWH (Batch 1) | 3793255 | Ongoing | 0.99 | 2023-12-17 |  |  | 23KH0156 | July 06, 2023 | July 14, 2023 | July 26, 2023 | September 21, 2023 | October 04, 2023 |  | ongoing rectification of punchlisted items | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 189510 | Lower Capanun-an Elementary School | MABINAY | 2nd | 1 | 4 | Repair of Classrooms | 4530000 | DPWH (Batch 1) | 4361349 | COMPLETED | 1 | 2023-12-24 | 2025-02-10 |  | 23KH0143 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 19, 2023 | October 03, 2023 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 312967 | Manlingay High School | MABINAY | 2nd | 1 | 3 | Repair of Classrooms | 2710000 | DPWH (Batch 1) | 2587158.27 | Ongoing | 0.99 | 2023-12-02 |  |  | 23KH0147 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 20, 2023 | October 03, 2023 |  | ongoing rectification of punchlisted items | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120376 | Tadlong Elementary School | MABINAY | 2nd | 1 | 5 | Repair of Classrooms | 3050000 | DPWH (Batch 1) | 2928830 | COMPLETED | 1 | 2023-12-06 |  |  | 23KH0155 | July 06, 2023 | July 14, 2023 | July 26, 2023 | September 21, 2023 | October 04, 2023 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120378 | Tara Elementary School | MABINAY | 2nd | 1 | 3 | Repair of Classrooms | 3620000 | DPWH (Batch 1) | 3453184 | COMPLETED | 1 | 2023-12-13 | 2024-06-24 |  | 23KH0148 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 14, 2023 | October 03, 2023 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 303248 | Tara Provincial Community High School | MABINAY | 2nd | 1 | 3 | Repair of Classrooms | 3410000 | DPWH (Batch 1) | 3285000 | COMPLETED | 1 | 2023-12-11 |  |  | 23KH0146 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 20, 2023 | October 03, 2023 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120379 | Tingtingon ES | MABINAY | 2nd | 1 | 1 | Repair of Classrooms | 1830000 | DPWH (Batch 1) | 1747241.23 | Ongoing | 0.99 | 2023-11-11 |  |  | 23KH0142 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 20, 2023 | October 03, 2023 |  | ongoing rectification of punchlisted items | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120439 | Sra. Ascion Elementary School | SAN JOSE | 2nd | 1 | 9 | Repair of Classrooms | 8120000 | DPWH (Batch 1) | 7831080 | COMPLETED | 1 | 2024-02-21 |  |  | 23KH0132 | July 04, 2023 | July 12, 2023 | July 24, 2023 | September 19, 2023 | September 28, 2023 | Ashleyka Construction & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120504 | Buenavista Elementary School | SANTA CATALINA | 3rd | 1 | 7 | Repair of Classrooms | 5920000 | DPWH (Batch 1) | 5706383.04 | COMPLETED | 1 | 2023-10-04 |  |  | 23HL0089 | June 23, 2023 | June 30, 2023 | August 30, 2023 | September 7, 2023 | September 22, 2023 | NRS BUILDERS & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120508 | Danao Elementary School | SANTA CATALINA | 3rd | 1 | 2 | Repair of Classrooms | 1550000 | DPWH (Batch 1) | 1493258.11 | COMPLETED | 1 | 2023-10-05 |  |  | 23HL0090 | June 23, 2023 | June 30, 2023 | August 30, 2023 | September 7, 2023 | September 22, 2023 | ALEXANDRIA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120516 | Omol Elementary School | SANTA CATALINA | 3rd | 1 | 2 | Repair of Classrooms | 1780000 | DPWH (Batch 1) | 1715774.88 | COMPLETED | 1 | 2023-10-05 |  |  | 23HL0091 | June 23, 2023 | June 30, 2023 | August 30, 2023 | September 7, 2023 | September 22, 2023 | ALEXANDRIA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120471 | Nawacat Elementary School | SIATON | 3rd | 1 | 3 | Repair of Classrooms | 2310000 | DPWH (Batch 1) | 2223687.34 | COMPLETED | 1 | 2023-10-04 |  |  | 23HL0092 | June 23, 2023 | June 30, 2023 | August 30, 2023 | September 7, 2023 | September 22, 2023 | NRS BUILDERS & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 189507 | Ulayan Elementary School | SIATON | 3rd | 1 | 3 | Repair of Classrooms | 2145000 | DPWH (Batch 1) | 2067761.72 | COMPLETED | 1 | 2023-10-15 |  |  | 23HL0103 | August 29, 2023 | September 7, 2023 | September 19, 2023 | September 26, 2023 | Octoberber 12, 2023 | NRS BUILDERS & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Negros Oriental | 120612 | Dobdob ES | VALENCIA (LUZURRIAGA) | 3rd | 1 | 2 | Repair of Classrooms | 1480000 | DPWH (Batch 1) | 1425205.4 | COMPLETED | 1 | 2023-10-17 |  |  | 23HL0104 | August 29, 2023 | September 7, 2023 | September 19, 2023 | September 26, 2023 | Octoberber 12, 2023 | ALEXANDRIA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VII | Siquijor | 500232 | Cabulihan IS | LARENA | Lone | 1 | 6 | Repair of Classrooms | 3725844.65 | DPWH (Batch 1) | 3582195.42 | COMPLETED | 1 | January 13, 2024 |  |  | 23HM0126 | September 4, 2023 | September 13, 2023 | September 26, 2023 | October 2, 2023 | October 11, 2023 | VNCO Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VII | Siquijor | 501429 | Maria Integrated School | MARIA | Lone | 1 | 6 | Repair of Classrooms | 3929375.04 | DPWH (Batch 1) | 3776406.34 | COMPLETED | 1 | January 13, 2024 |  |  | 23HM0128 | September 4, 2023 | September 13, 2023 | September 26, 2023 | October 2, 2023 | October 11, 2023 | Tesar Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VII | Siquijor | 120697 | Cansayang ES | SAN JUAN | Lone | 1 | 6 | Repair of Classrooms | 3877378.6 | DPWH (Batch 1) | 3726306.32 | COMPLETED | 1 | January 13, 2024 |  |  | 23HM0127 | September 4, 2023 | September 13, 2023 | September 26, 2023 | October 2, 2023 | October 11, 2023 | Quicksilver Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VII | Tagbilaran City | 118704 | Cabawan Elementary School | TAGBILARAN CITY (Capital) | 1st | 1 | 5 | Repair of Classrooms | 1435691.97 | DPWH (Batch 1) | 1380442.75 | COMPLETED | 1 | 2024-01-08 |  |  | 23HA0125 - Repair of 5 Classrooms, Cabawan Elementary School, Tagbilaran City, Bohol | 29/09/2023 | 2023-06-10 | 18/10/2023 | 24/10/2023 | 2023-10-11 | One orchard Construction and Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VII | Tagbilaran City | 118705 | City East Elementary School | TAGBILARAN CITY (Capital) | 1st | 1 | 6 | Repair of Classrooms | 1781974.38 | DPWH (Batch 1) | 0 | COMPLETED | 1 |  |  |  | 23HA0139 - Repair of 6 Classrooms, City East Elementary School, Tagbilaran City, Bohol | 2023-06-10 | 13/10/2023 | 2023-08-11 | 20/11/2023 | 2023-04-12 | One orchard Construction and Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VII | Tagbilaran City | 302846 | Dr. Cecilio Putong NHS (Bohol NHS) | TAGBILARAN CITY (Capital) | 1st | 1 | 30 | Repair of Classrooms | 9873441.61 | DPWH (Batch 1) | 0 | COMPLETED | 1 |  |  |  | 23HA0135 - Repair of 30 Classrooms, Dr. Cecilio Putong NHS (Bohol NHS), Tagbilaran City, Bohol | 2023-06-10 | 13/10/2023 | 26/10/2023 | 13/11/2023 | 2023-04-12 | HANZGRACE Construction and Trading Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 30 | 0 | 0
REPAIR 2023 | Region VII | Tagbilaran City | 118711 | Mansasa Elementary School | TAGBILARAN CITY (Capital) | 1st | 1 | 5 | Repair of Classrooms | 2220493.85 | DPWH (Batch 1) | 0 | COMPLETED | 1 |  |  |  | 23HA0134 - Repair of 5 Classrooms, Mansasa Elementary School, Tagbilaran City, Bohol | 2023-05-10 | 2023-12-10 | 24/10/2023 | 27/10/2023 | 13/11/2023 | C Jansen Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VII | Tagbilaran City | 118712 | San Isidro Elementary School | TAGBILARAN CITY (Capital) | 1st | 1 | 3 | Repair of Classrooms | 1650000 | DPWH (Batch 1) | 0 | COMPLETED | 1 |  |  |  | 23HA0132 - Repair of 3 Classrooms, San Isidro Elementary School, Tagbilaran City, Bohol | 2023-05-10 | 2023-12-10 | 2023-08-11 | 20/11/2023 | 2023-04-12 | One orchard Construction and Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Tagbilaran City | 118714 | Taloto Elementary School | TAGBILARAN CITY (Capital) | 1st | 1 | 3 | Repair of Classrooms | 1950296.72 | DPWH (Batch 1) | 0 | COMPLETED | 1 | 2024-02-16 |  |  | 23HA0137 - Repair of 3 classrooms, Taloto Elementary School, Tagbilaran City, Bohol | 2023-06-10 | 13/10/2023 | 2023-08-11 | 20/11/2023 | 2023-04-12 | One orchard Construction and Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Talisay City | 119797 | Candulawan Elementary School | CITY OF TALISAY | 1st | 1 | 9 | Repair of Classrooms | 1412421.99 | DPWH (Batch 1) | 0 | COMPLETED | 1 | 2025-09-03 |  |  | 2024-02-Infra | 23/06/2024 | 24/06/2024 | 2024-05-07 | 2024-10-07 | 2024-03-10 | CJANSEN Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2023 | Region VII | Talisay City | 233504 | Hawanay Elementary School | CITY OF TALISAY | 1st | 1 | 1 | Repair of Classrooms | 544552.33 | DEPED (Batch 1) | 0 | COMPLETED | 1 | [10 empty] | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region VII | Talisay City | 233502 | Lawaan III Elementary School | CITY OF TALISAY | 1st | 1 | 6 | Repair of Classrooms | 1786120.53 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [10 empty] | COMPLETD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VII | Talisay City | 322201 | Maghaway National High School | CITY OF TALISAY | 1st | 1 | 21 | Repair of Classrooms | 4326779.93 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [10 empty] | COMPLETD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0
REPAIR 2023 | Region VII | Talisay City | 119796 | Manipis Elementary School | CITY OF TALISAY | 1st | 1 | 5 | Repair of Classrooms | 2371613.04 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [10 empty] | COMPLETD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VII | Talisay City | 303056 | Mohon (Divino Amore) National High School | CITY OF TALISAY | 1st | 1 | 12 | Repair of Classrooms | 1023961.81 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [10 empty] | COMPLETD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2023 | Region VII | Talisay City | 119790 | San Roque ES | CITY OF TALISAY | 1st | 1 | 27 | Repair of Classrooms | 3331406.01 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [10 empty] | COMPLETD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 27 | 0 | 0
REPAIR 2023 | Region VII | Talisay City | 303113 | Talisay City National High School | CITY OF TALISAY | 1st | 1 | 24 | Repair of Classrooms | 5805518.35 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [10 empty] | COMPLETD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0
REPAIR 2023 | Region VII | Talisay City | 119792 | Tanke Elementary School | CITY OF TALISAY | 1st | 1 | 10 | Repair of Classrooms | 3163304.37 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [10 empty] | COMPLETD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2023 | Region VII | Talisay City | 322208 | Tapul National High School | CITY OF TALISAY | 1st | 1 | 13 | Repair of Classrooms | 1843175.49 | DPWH (Batch 1) | 0 | COMPLETED | 1 | [10 empty] | COMPLETD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2023 | Region VII | Talisay City | 119793 | Vicenta A. Manreal ES | CITY OF TALISAY | 1st | 1 | 12 | Repair of Classrooms | 725295.09 | DEPED (Batch 1) | 0 | COMPLETED | 1 | [10 empty] | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2023 | Region VII | Tanjay City | 120549 | Don Placido Mapa Memorial School | CITY OF TANJAY | 2nd | 1 | 3 | Repair of Classrooms | 3270000 | DPWH (Batch 1) | 3117045.62 | COMPLETED | 1 | 2023-12-08 |  | P00775389NP-CWS | 23HK0139 | 2023-07-01 | 2023-07-09 | 2023-07-21 | 2023-09-20 | 2023-10-03 | NALE Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region VII | Tanjay City | 120553 | Fabiana G. Banogon MES (Camansi ES) | CITY OF TANJAY | 2nd | 1 | 5 | Repair of Classrooms | 3880000 | DPWH (Batch 1) | 3707378.74 | COMPLETED | 1 | 2023-12-15 |  | P00775390NP-CWS | 23HK0140 | 2023-07-01 | 2023-07-09 | 2023-07-21 | 2023-09-20 | 2023-10-03 | NALE Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VII | Tanjay City | 120408 | Balayong Elem School | PAMPLONA | 2nd | 1 | 6 | Repair of Classrooms | 6480000 | DPWH (Batch 1) | 6248144.77 | COMPLETED | 1 | 2024-01-25 | 2024-01-25 |  | 23HK0134 | 2023-06-30 | 2023-07-08 | 2023-07-20 | 2023-09-20 | 2023-10-02 | Ashleyka Const. and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VII | Tanjay City | 120425 | San Isidro Elementary School | PAMPLONA | 2nd | 1 | 2 | Repair of Classrooms | 3170000 | DPWH (Batch 1) | 3055741.71 | COMPLETED | 1 | 2023-12-08 | 2024-01-03 |  | 23HK0136 | 2023-06-30 | 2023-07-08 | 2023-07-20 | 2023-09-20 | 2023-10-05 | Bigfoot Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VII | Tanjay City | 120427 | Sta. Agueda ES | PAMPLONA | 2nd | 1 | 9 | Repair of Classrooms | 8870000 | DPWH (Batch 1) | 8549504 | COMPLETED | 1 | 2024-03-03 | 2024-03-03 |  | 23HK0135 | 2023-06-30 | 2023-07-08 | 2023-07-20 | 2023-09-20 | 2023-10-02 | PER Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2023 | Region VII | Toledo City | 120711 | Apid ES | TOLEDO CITY | 3rd | 1 | 5 | Repair of Classrooms | 2684230.31 | DPWH (Batch 1) | 2538029.64 | COMPLETED | 1 | [9 empty] | YBK CONSTRUCTION | DPWH IMPLEMENTED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VII | Toledo City | 120713 | Biga ES | TOLEDO CITY | 3rd | 1 | 4 | Repair of Classrooms | 2185173.46 | DPWH (Batch 1) | 2103000 | COMPLETED | 1 | [9 empty] | TEN TWENTY ALLIED DEVELOPERS | DPWH IMPLEMENTED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VII | Toledo City | 120714 | BUNGA ELEMENTARY SCHOOL | TOLEDO CITY | 3rd | 1 | 7 | Repair of Classrooms | 3077072.35 | DPWH (Batch 1) | 2965000 | COMPLETED | 1 | [9 empty] | ANZEN CONSTRUCTION & SUPPLY | DPWH IMPLEMENTED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | Region VII | Toledo City | 120728 | Carmen ES | TOLEDO CITY | 3rd | 1 | 2 | Repair of Classrooms | 1073677.95 | DPWH (Batch 1) | 1031089 | COMPLETED | 1 | [9 empty] | ANZEN CONSTRUCTION & SUPPLY | DPWH IMPLEMENTED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region VII | Toledo City | 303310 | Don Andres Soriano NHS | TOLEDO CITY | 3rd | 1 | 10 | Repair of Classrooms | 3058483.89 | DPWH (Batch 1) | 2900809.83 | COMPLETED | 1 | [9 empty] | YBK CONSTRUCTION | DPWH IMPLEMENTED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2023 | Region VII | Toledo City | 120717 | Gen. P. Del Rosario ES | TOLEDO CITY | 3rd | 1 | 6 | Repair of Classrooms | 3142137.85 | DPWH (Batch 1) | 3001256.23 | COMPLETED | 1 | [9 empty] | BL PANGAN CONSTRUCTION | DPWH IMPLEMENTED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region VII | Toledo City | 120750 | Jacinta Larosa ES (Ilihan ES) | TOLEDO CITY | 3rd | 1 | 4 | Repair of Classrooms | 2147753.82 | DPWH (Batch 1) | 2070582 | COMPLETED | 1 | [9 empty] | JAY-BR ENTERPRISES | DPWH IMPLEMENTED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region VII | Toledo City | 120718 | Loay Elementary School | TOLEDO CITY | 3rd | 1 | 5 | Repair of Classrooms | 2756620.27 | DPWH (Batch 1) | 2658150.69 | COMPLETED | 1 | [9 empty] | YBK CONSTRUCTION | DPWH IMPLEMENTED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region VII | Toledo City | 303318 | LURAY II NATIONAL HIGH SCHOOL (DAY & NIGHT)) | TOLEDO CITY | 3rd | 1 | 7 | Repair of Classrooms | 3222929.08 | DPWH (Batch 1) | 3105000 | COMPLETED | 1 | [9 empty] | ANZEN CONSTRUCTION & SUPPLY | DPWH IMPLEMENTED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2024 | Region VII | Bais City | 303212 | Bais City National High School | BAIS CITY | 2nd | 1 | 6 | Repair of Classrooms | 1919274.94 | 1 | 1880000 | COMPLETED | 1 | 2025-02-15 | 2025-01-07 | BCD-2024-075 | [6 empty] | RISM | complete | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | Region VII | Bais City | 323013 | Tangculogan High School | BAIS CITY | 2nd | 1 | 2 | Repair of Classrooms | 1442191.82 | 1 | 1118578.74 | COMPLETED | 1 | 2025-02-15 | 2025-01-09 | BCD-2024-075 | BCD-2024-075 | [5 empty] | Triple Jo const. | complete | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2024 | Region VII | Bayawan City | 120138 | Senator Lorenzo G. Teves Memorial Elementary School | CITY OF BAYAWAN (TULONG) | 3rd | 1 | 8 | Repair of Classrooms | 4498259.02 | 1 | 4438000 | COMPLETED | 1 | 2025-01-05 |  | 2024-BEFF-002 | 2024-BEFF-002 | 2024-07-27 | 2024-07-03 | 2024-07-15 | 2024-07-30 | 2024-09-30 | RISM Buidlers and Construction Services inc. | On-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2024 | Region VII | Bogo City | 312405 | Bartolome C.Pianar MNHS | CITY OF BOGO | 4th | 1 | 6 | Repair of Classrooms | 3555056.74 | 1 | 3505721.29 | COMPLETED | 1 | 2025-03-02 |  | ITB202406-001 | ITB202406-001 | 2024-07-03 | 2024-07-08 | 2024-07-22 | 2024-07-24 | 2024-10-18 | 3R Builders and Supply OPC | On-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 305742 | Candijay Municipal High School | CANDIJAY | 1st | 1 | 4 | Repair of Classrooms | 2808549.27 | 1 | 2754515.71 | COMPLETED | 1 | 2025-03-20 | 2025-04-15 | PBI 2024-08 | PBI 2024-08 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-21 | Anielthon Const and Supply | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118060 | Bago ES | BUENAVISTA | 2nd | 1 | 9 | Repair of Classrooms | 3521608.78 | 1 | 2638990.9 | COMPLETED | 1 | 2025-03-21 | 2025-03-17 | PBI 2024-01 | PBI 2024-01 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-22 | Inabanga Drilling Conts Steel Fab and Gen Mdse | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118108 | Abihilan ES | CANDIJAY | 3rd | 1 | 8 | Repair of Classrooms | 3863767.14 | 1 | 3806607.53 | COMPLETED | 1 | 2025-03-21 | 2025-03-20 | PBI 2024-10 | PBI 2024-10 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-22 | LJPM Builders and Sconst Supply | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118109 | Anoling ES | CANDIJAY | 3rd | 1 | 8 | Repair of Classrooms | 3502198.08 | 1 | 3458345.23 | COMPLETED | 1 | 2025-05-15 | ongoing | PBI 2024-26 | PBI 2024-26 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 |  |  | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 302912 | Anoling National High School | CANDIJAY | 3rd | 1 | 10 | Repair of Classrooms | 4509706.7 | 1 | 3441535.89 | COMPLETED | 1 | 2025-03-21 | ongoing | PBI 2024-25 | PBI 2024-25 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-22 | Zion Const | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118110 | Boyoan ES | CANDIJAY | 3rd | 1 | 10 | Repair of Classrooms | 5455888.68 | 1 | 4798710.18 | COMPLETED | 1 | 2025-03-21 | ongoing | PBI 2024-12 | PBI 2024-12 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-22 | Zion Const | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118112 | Cambane ES | CANDIJAY | 3rd | 1 | 3 | Repair of Classrooms | 2027073.09 | 1 | 1966202.52 | COMPLETED | 1 | 2025-02-18 | 2025-01-24 | PBI 2024-13 | PBI 2024-13 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-21 | Husain Const and Supply Corp. | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118113 | Canawa ES | CANDIJAY | 3rd | 1 | 8 | Repair of Classrooms | 3971975.96 | 1 |  | COMPLETED | 1 |  |  |  |  | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 |  |  | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118114 | Candijay Central ES | CANDIJAY | 3rd | 1 | 8 | Repair of Classrooms | 3612679.56 | 1 | 3556539.8 | COMPLETED | 1 | 2025-03-21 | 2025-03-06 | PBI 2024-15 | PBI 2024-15 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-22 | C Jansen Const and Gen Mdse | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 302865 | Candijay National High School | CANDIJAY | 3rd | 1 | 21 | Repair of Classrooms | 6629141.18 | 1 | 6540192.12 | COMPLETED | 1 | 2025-04-20 | 2025-03-20 | PBI 2024-29 | PBI 2024-29 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-22 | C Jansen Const and Gen Mdse | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118115 | Can-olin ES | CANDIJAY | 3rd | 1 | 9 | Repair of Classrooms | 4108888.58 | 1 | 4047761.84 | COMPLETED | 1 | 2025-03-21 | completed | PBI 2024-21 | PBI 2024-21 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-22 | C Jansen Const and Gen Mdse | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118116 | Cogtong ES | CANDIJAY | 3rd | 1 | 15 | Repair of Classrooms | 5808126.73 | 1 | 4008758.5 | COMPLETED | 1 | 2025-05-15 | ongoing | PBI 2024-27 | PBI 2024-27 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 |  |  | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 302866 | Cogtong NHS | CANDIJAY | 3rd | 1 | 17 | Repair of Classrooms | 6257354.97 | 1 | 6174050.8 | COMPLETED | 1 | 2025-04-20 | completed | PBI 2024-24 | PBI 2024-24 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-22 | C Jansen Const and Gen Mdse | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118117 | La Union Elementary School | CANDIJAY | 3rd | 1 | 15 | Repair of Classrooms | 5922916.73 | 1 | 4221855.58 | COMPLETED | 1 | 2025-03-27 | ongoing | PBI 2024-18 | PBI 2024-18 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 |  | Quicksilver Const Services | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 302864 | La Union NHS | CANDIJAY | 3rd | 1 | 16 | Repair of Classrooms | 5567480.19 | 1 | 3858829.45 | COMPLETED | 1 | 2025-03-27 | ongoing | PBI 2024-17 | PBI 2024-17 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 |  | Quicksilver Const Services | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118119 | Lungsodaan ES | CANDIJAY | 3rd | 1 | 11 | Repair of Classrooms | 3858133.83 | 1 | 3804993.77 | COMPLETED | 1 | 2025-05-15 | ongoing | PBI 2024-16 | PBI 2024-16 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 |  |  | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118120 | Mahangin Elementary School | CANDIJAY | 3rd | 1 | 6 | Repair of Classrooms | 3166032.56 | 1 | 2494615.88 | COMPLETED | 1 | 2025-03-23 | completed | PBI 2024-20 | PBI 2024-20 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 |  | VVER Const Devt Corp | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118122 | Panadtaran ES | CANDIJAY | 3rd | 1 | 10 | Repair of Classrooms | 5332022.34 | 1 | 5257776.35 | COMPLETED | 1 | 2025-03-21 | 2025-03-18 | PBI 2024-14 | PBI 2024-14 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-22 | C Jansen Const and Gen Mdse | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118123 | Panas ES | CANDIJAY | 3rd | 1 | 7 | Repair of Classrooms | 2801779.92 | 1 | 2759784.51 | COMPLETED | 1 | 2025-02-18 | completed | PBI 2024-22 | PBI 2024-22 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-21 | DMAM Const Services | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118124 | Pangpang ES | CANDIJAY | 3rd | 1 | 6 | Repair of Classrooms | 1159714.77 | 1 | 910070.31 | COMPLETED | 1 | 2025-01-23 | completed | PBI 2024-19 | PBI 2024-19 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 |  | VVER Const Devt Corp | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118125 | San Isidro ES | CANDIJAY | 3rd | 1 | 8 | Repair of Classrooms | 2919392.92 | 1 | 2077213.76 | COMPLETED | 1 | 2025-02-18 | 2025-01-14 | PBI 2024-28 | PBI 2024-28 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-21 | Job D Merchant and Builders | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 302911 | Tambongan NHS | CANDIJAY | 3rd | 1 | 24 | Repair of Classrooms | 6403436.16 | 1 | 6282572.77 | COMPLETED | 1 | 2025-04-19 | 2025-02-14 | PBI 2024-07 | PBI 2024-07 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-21 | Anielthon Const and Supply | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118127 | Tawid Elementary School | CANDIJAY | 3rd | 1 | 8 | Repair of Classrooms | 3607549.19 | 1 | 3557198.78 | COMPLETED | 1 | 2025-03-21 | 2025-03-28 | PBI 2024-09 | PBI 2024-09 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-22 | LJPM Builders and Sconst Supply | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118128 | Tubod ES | CANDIJAY | 3rd | 1 | 7 | Repair of Classrooms | 3775256.29 | 1 | 2832666.64 | COMPLETED | 1 | 2025-03-21 | 2025-03-18 | PBI 2024-30 | PBI 2024-30 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-22 | C Jansen Const and Gen Mdse | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118129 | Tugas ES | CANDIJAY | 3rd | 1 | 10 | Repair of Classrooms | 3922375.89 | 1 | 3826582.94 | COMPLETED | 1 | 2025-03-20 | 2025-02-21 | PBI 2024-11 | PBI 2024-11 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-21 | Anielthon Const and Supply | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118433 | Bonkokan ES | LILA | 3rd | 1 | 12 | Repair of Classrooms | 5583978.5958 | 1 | 4148488.97 | COMPLETED | 1 | 2025-03-20 | ongoing | PBI 2024-02 | PBI 2024-02 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-21 | Sombrio Const and Supply | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118439 | Malinao ES | LILA | 3rd | 1 | 2 | Repair of Classrooms | 1858585.86 | 1 | 2864595.32 | COMPLETED | 1 | 2025-03-19 | completed | PBI 2024-03 | PBI 2024-03 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-21 | Sombrio Const and Supply | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118441 | Taug PS | LILA | 3rd | 1 | 2 | Repair of Classrooms | 404040.4 | 1 | 1914787.95 | COMPLETED | 1 | 2024-12-05 | completed | PBI 2024-06 | PBI 2024-06 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-21 | Sombrio Const and Supply | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118442 | Tiguis ES | LILA | 3rd | 1 | 5 | Repair of Classrooms | 2020202.02 | 1 | cluster with taug | COMPLETED | 1 | 2025-02-03 | completed | PBI 2024-03 | PBI 2024-03 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-21 | Sombrio Const and Supply | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2024 | Region VII | Bohol | 118453 | Tocdog ES | LOAY | 3rd | 1 | 4 | Repair of Classrooms | 2012059.07 | 1 | cluster with malinao | COMPLETED | 1 | 2025-02-18 | completed | PBI 2024-04 | PBI 2024-04 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-21 | Sombrio Const and Supply | mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2024 | Region VII | Canlaon City | 120215 | Pula ES | CANLAON CITY | 1st | 1 | 5 | Repair of Classrooms | 4140248.27 | 1 | 4098845.79 | COMPLETED | 1 | 2025-02-15 |  | ITB2024-003 | 2024-003 | 2024-06-26 | 2024-07-03 | 2024-07-16 | 2024-07-25 | 2024-09-11 | R.R. Gadingan Construction | SARO received | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2024 | Region VII | Cebu | 501574 | Bugho Integrated School | SAN FERNANDO | 1st | 1 | 11 | Repair of Classrooms | 3434696.73 | 1 | 3376320.13 | COMPLETED | 1 | 18/04/2025 |  | CY2024 BEFF REPAIR-DEPED-R7-CEBU |  | 16/10/2024 | 23/10/2024 | 2024-04-11 | 2024-11-11 | 29/11/2024 | MP Sorela Construction and supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2024 | Region VII | Cebu | 118902 | Bogo ES | ALOGUINSAN | 3rd | 1 | 2 | Repair of Classrooms | 1230936.32 | 1 | 1198335.13 | COMPLETED | 1 | 19/03/2025 |  | CY2024 BEFF REPAIR-DEPED-R7-CEBU |  | 16/10/2024 | 23/10/2024 | 2024-04-11 | 2024-11-11 | 29/11/2024 | Gela Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2024 | Region VII | Cebu | 302995 | Daanbantayan National High School | DAANBANTAYAN | 4th | 1 | 36 | Repair of Classrooms | 1609753.76 | 1 | 1586701.96 | COMPLETED | 1 | 19/03/2025 | 2025-09-03 | CY2024 BEFF REPAIR-DEPED-R7-CEBU |  | 16/10/2024 | 23/10/2024 | 2024-04-11 | 2024-11-11 | 29/11/2024 | RT Construction and enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36 | 0 | 0
REPAIR 2024 | Region VII | Cebu | 303092 | Liloan NHS | LILOAN | 5th | 1 | 25 | Repair of Classrooms | 3257234.88 | 1 | 3214877.65 | COMPLETED | 1 | 18/04/2025 |  | CY2024 BEFF REPAIR-DEPED-R7-CEBU |  | 16/10/2024 | 23/10/2024 | 2024-04-11 | 2024-11-11 | 29/11/2024 | Rovilla construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 25 | 0 | 0
REPAIR 2024 | Region VII | Cebu | 303114 | Tayud National High School | CONSOLACION | 6th | 1 | 20 | Repair of Classrooms | 1531044.87 | 1 | 1512140.42 | COMPLETED | 1 | 18/04/2025 |  | CY2024 BEFF REPAIR-DEPED-R7-CEBU |  | 16/10/2024 | 23/10/2024 | 2024-04-11 | 2024-11-11 | 29/11/2024 | Rovilla construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0
REPAIR 2024 | Region VII | Cebu City | 119892 | Camp Lapu-Lapu ES | CEBU CITY (Capital) | 1st | 1 | 18 | Repair of Classrooms | 5034542.43 | 1 | 3323822.83 | COMPLETED | 1 | April 14, 2025 |  | 2024-22(Lot 2) | DepEd CCD 2024-30 | September 13, 2024 | September 23, 2024 | October 7, 2024 | November 8, 2024 | December 9, 2024 | Steadfast Builders Construction Corporation | On - Going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0
REPAIR 2024 | Region VII | Cebu City | 119914 | Pasil Elementary School | CEBU CITY (Capital) | 2nd | 1 | 32 | Repair of Classrooms | 8113131.31 | 1 | 6008338.86 | COMPLETED | 1 | April 23, 2025 |  | 2024-22(Lot 1) | DepEd CCD 2024-29 | September 13, 2024 | September 23, 2024 | October 7, 2024 | November 8, 2024 | December 18, 2024 | Hero Construction and Development Corporation | On - Going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0
REPAIR 2024 | Region VII | Dumaguete City | 119932 | Amador Dagudag MES | DUMAGUETE CITY (Capital) | 2nd | 1 | 4 | Repair of Classrooms | 953206.76 | 1 | 676154.66 | COMPLETED | 1 | 2025-04-05 | 2025-03-31 | 2024-005 | 2024-005 | 2024-11-21 | 2024-12-02 | 2024-12-18 | 2025-01-02 | 2025-02-12 | Millenial Mammoth Development Corporation | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2024 | Region VII | Dumaguete City | 119944 | Calindagan ES | DUMAGUETE CITY (Capital) | 2nd | 1 | 2 | Repair of Classrooms | 381282.71 | 1 | 273578.95 | COMPLETED | 1 | 2025-05-20 |  | 2024-004 | 2024-004 | 2024-11-21 | 2024-12-02 | 2024-12-18 | 2025-01-02 | 2025-02-12 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | ongoing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2024 | Region VII | Dumaguete City | 119946 | City Central Elementary School | DUMAGUETE CITY (Capital) | 2nd | 1 | 6 | Repair of Classrooms | 3240902.98 | 1 | 2325421.05 | COMPLETED | 1 | 2025-05-20 |  | 2024-004 | 2024-004 | 2024-11-21 | 2024-12-02 | 2024-12-18 | 2025-01-02 | 2025-02-12 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | ongoing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | Region VII | Guihulngan City | 120248 | Lag-asan ES | CITY OF GUIHULNGAN | 1st | 1 | 6 | Repair of Classrooms | 5126087.05 | 1 | 4389914.25 | COMPLETED | 1 | 2025-04-21 |  | ITB 2024-013 | ITB 2024-013 | 2024-10-16 | 2024-10-24 | November 7, 22024 | 2024-11-25 | 2024-11-28 | G.PO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | Region VII | Lapu-Lapu City | 119973 | Agus Elementary School | LAPU-LAPU CITY (OPON) | Lone | 1 | 12 | Repair of Classrooms | 3039405.44 | 1 | 3000000 | COMPLETED | 1 | 2025-02-14 | 2025-02-14 | 2024-Infra-001 | 2024-Infra-001 | 2024-07-18 | 2024-07-25 | 2024-08-09 | 2024-08-20 | 2024-10-17 | TriBairn Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2024 | Region VII | Lapu-Lapu City | 119963 | Bankal Elementary School | LAPU-LAPU CITY (OPON) | Lone | 1 | 20 | Repair of Classrooms | 3166835.8 | 1 | 3120118.63 | COMPLETED | 1 | 2025-01-15 | 2025-01-11 | 2024-Infra-002 | 2024-Infra-002 | 2024-07-18 | 2024-07-25 | 2024-08-09 | 2024-08-20 | 2024-10-17 | Golden Hammer Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0
REPAIR 2024 | Region VII | Negros Oriental | 120189 | Pagsalayon ES | BINDOY (PAYABON) | 1st | 1 | 6 | Repair of Classrooms | 6454488.69 | 1 | 6329000 | COMPLETED | 1 | 2025-04-04 | 2025-03-26 | ITB 2024-07-116 | BEFF202409031 | 2024-07-09 | 2024-07-17 | 2024-07-30 | 2024-08-12 | 2024-10-07 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | Region VII | Negros Oriental | 120432 | Cancawas Primary School | SAN JOSE | 2nd | 1 | 3 | Repair of Classrooms | 2304321.13 | 1 | 1932000 | COMPLETED | 1 | 2025-01-27 | 2025-01-16 | ITB 2024-07-117 | BEFF202409032 | 2024-07-09 | 2024-07-17 | 2024-07-30 | 2024-08-12 | 2024-10-07 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2024 | Region VII | Siquijor | 303305 | Catulayan National High School | SAN JUAN | Lone | 1 | 9 | Repair of Classrooms | 5830766.12 | 1 | 5756858.55 | COMPLETED | 1 | 2025-06-30 |  | 10889961 | 2024-032 | 2024-05-25 | 2024-05-30 | 2024-06-13 | 2024-06-19 | 2024-10-07 | Nale Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2024 | Region VII | Tagbilaran City | 118710 | Manga Elementary School | TAGBILARAN CITY (Capital) | 1st | 1 | 9 | Repair of Classrooms | 6344702.34 | 1 | 6281255.32 | COMPLETED | 1 | 2025-03-09 | 2025-03-01 | 2024-02-Infra | 2024-02-Infra | 2024-06-23 | 2024-06-24 | 2024-07-05 | 2024-07-10 | 2024-10-03 | CJANSEN Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2024 | Region VII | Talisay City | 322204 | Bulacao National High School | CITY OF TALISAY | 1st | 1 | 16 | Repair of Classrooms | 3980639.21 | 1 | 3938087.39 | COMPLETED | 1 | 2025-03-04 | 2025-03-04 | talisaycity 2024-015 | talisaycityrepair 2024-2015 | 2024-10-09 | 2024-10-10 | 2024-10-22 | 2024-10-25 | 2025-11-04 | Tri Bairn Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2024 | Region VII | Tanjay City | 303285 | Bahi-an High School | CITY OF TANJAY | 2nd | 1 | 1 | Repair of Classrooms | 773357.01 | 1 | 3204000 | COMPLETED | 1 | [5 empty] | 2024-09-06 | 2024-09-18 |  |  | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | SARO received | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2024 | Region VII | Tanjay City | 120558 | Mato-Bato Elementary School | CITY OF TANJAY | 2nd | 1 | 3 | Repair of Classrooms | 2468342.68 | 1 | 3204000 | COMPLETED | 1 | [5 empty] | 2024-09-06 | 2024-09-18 |  |  | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | SARO received | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2024 | Region VII | Toledo City | 303307 | AWIHAO NATIONAL HIGH SCHOOL | TOLEDO CITY | 3rd | 1 | 6 | Repair of Classrooms | 3314226.29 | 1 | 2581368.6 | COMPLETED | 1 | 2025-03-13 | 2025-03-14 |  | Repair 2024-14 | 2024-08-28 | 2024-09-04 | 2024-09-18 | 2024-09-18 | 2024-11-13 | GOLDEN COMPASS BUILDERS INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%