## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | NO. OF CL | SCOPE OF WORK | PROJECT ALLOCATION | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
LMS 2020 | Region X | Bukidnon | 113623 | Lumatong Pangukayan Ta Apu Manohay | MARAMAG | 3 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18157630.9036 | 13617950.39 | Ongoing | 0.89 | 2025-03-30 | 00:00:00 | PB-02-05-2024-005 | 0016-2024 | 2024-05-11 | 2024-05-20 | 2024-06-03 | 2024-06-06 | 2024-06-28 | CQ Haribon Construction | Terminated Contract No. 08-2021 with FFJJ Construction, New Contract No. 0016-2024, Php 4,579,658.48
LMS 2020 | Region X | Gingoog City | 128071 | Mimbuntong Elementary School | GINGOOG CITY | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE,\ SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19025682.2429 | 17827523.07 | completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 2021-08-26 | 2021-08-28 | 2021-08-31 | IMBDC | 0
LMS 2020 | Region X | Lanao del Norte | 127123 | Sta. Cruz ES | MAIGO | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 16818990.1918 | 13774087.91 | completed | 1 | 2021-02-28 | 2021-05-24 | 2020-01(Infra) | 43831 | 2020-08-19 | 2020-08-27 | 2020-09-21 | 2020-10-12 | 2020-11-23 | Lanao Genesis Construction Supply | Completed
LMS 2020 | Region X | Lanao del Norte | 200523 | Pelingkingan PS | TANGCAL | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 19741282.5164 | 0 | Reverted | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | failure of bid (under negotiation); return of funds
LMS 2021 | Region X | Bukidnon | 113721 | Makabugwas Ta San Dionesio | TALAKAG | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16205887.9248 | 0 | ABANDONED | 0.41 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | Letter request for suspension was sent to the Central Office. No Response from CO. This is a CO Implemented project. We cannot fill in the details.
LMS 2021 | Region X | Misamis Occidental | 127367 | Migubay PS | Concepcion | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 13433577.8053 | 0 | Ongoing | 0.14 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | Waiting for approved DAED
LMS 2021 | Region X | Misamis Occidental | 127496 | Deboloc ES | Plaridel | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15202037.935 | 0 | Ongoing | 0.1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | Waiting for approved DAED
LMS 2021 | Region X | Misamis Oriental | 130200 | Aligodon Higaonon Tulogan Nauhanan | CLAVERIA | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19652994.9643 | 0 | Ongoing | 0.33 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | No Movement in Site (Abandoned); Building permit on Process, Contractor requested fot Time extension due to weather condition
LMS 2021 | Region X | Misamis Oriental | 130200 | Aligodon Higaonon Tulogan Nauhanan | CLAVERIA | 2 |  | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 6520 | 0 | Ongoing | 0.33 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | No Movement in Site (Abandoned); Building permit on Process, Contractor requested fot Time extension due to weather condition
LMS 2021 | Region X | Ozamis City | 128190 | Balintawak Elementary School | OZAMIS CITY | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18244962.88 | 0 | Ongoing | 0.13 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | Under Work Suspension
LMS 2022 | Region X | El Salvador | 304768 | Himaya National High School | CITY OF EL SALVADOR | 2 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16459251.5365 | 11765349.85 | Completed | 1 | 2024-01-17 | 2023-08-18 | 2022-10-0228 | 2022-12-0327 | 2023-04-25 | 2023-05-03 | 2023-05-15 | 2023-07-11 | 2023-07-14 | ROVINVAL ENGINEERING AND CONSTRUCTION | Completed
LMS 2022 | Region X | El Salvador | 305683 | Sambulawan National High School | CITY OF EL SALVADOR | 2 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16469856.5365 | 12076295.82 | Completed | 1 | 2023-12-31 | 2023-09-06 | 2022-04-0065 | 2022-09-0205 | 2023-04-25 | 2023-05-03 | 2023-05-15 | 2023-07-07 | 2023-07-27 | LJPM BUILDERS AND CONSTRUCTION SUPPLY | Completed
LMS 2022 | Region X | Lanao del Norte | 127171 | Sigayan Adil PS | PANTAR | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, WATER SYSTEM AND REPAIR & REHABILITATION OF CLASSROOMS. | 17137950.7406 | 12954954.09 | Completed | 1 | 2023-06-09 | 2023-06-10 | 2023-02(Infra) | 44958 | 2022-11-23 | 2022-12-01 | 2022-12-19 | 2023-01-09 | 2023-02-09 | S& J BUILDERS | Completed
LMS 2022 | Region X | Lanao del Norte | 127101 | Durianon Primary School | MAGSAYSAY | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, WATER SYSTEM AND REPAIR & REHABILITATION OF CLASSROOMS. | 15730677.8052 | 0 | COMPLETED | 1 | 2023-06-09 | 2023-05-05 | 2023-01(Infra) | 44927 | 2022-11-23 | 2022-12-01 | 2022-12-19 | 2023-01-09 | 2023-02-09 | AHM BUILDERS | Completed
LMS 2022 | Region X | Lanao del Norte | 501602 | Pelingkingan Integrated School | TANGCAL | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 19938695.3452 | 0 | COMPLETED | 1 | 2023-01-05 | 2023-11-30 | 2022-05(infra) | 44682 | 2022-04-20 | 2022-04-29 | 2022-05-17 | 2022-08-25 | 2022-09-07 | N-ASIACOM | Completed
LMS 2022 | Region X | Misamis Occidental | 127281 | Naburos ES | BALIANGAO | 1 | 1 | 5 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND REPAIR AND REHABILITATION OF ONE STOREY THREE (3) - CLASSROOM SCHOOL BUILDING (BLSB - TYPE 1) - (6.40m x 8.00m) | 16494219.42 | 16279166.49 | Completed | 1 | 2023-08-09 | 2024-11-22 |  | 002-2023 | 2022-10-26 | 2022-11-03 | 2022-11-15 | 2022-12-14 | 2023-01-30 | RRJ Builders | Completed
LMS 2022 | Region X | Misamis Occidental | 127371 | Soso-on Elementary School | CONCEPCION | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17603739.1268 | 17030172.22 | Completed | 1 | 2023-03-06 | 2024-07-04 | LMS 2022-RX-Misamis Occidental-001 | 013-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-09-29 | RRJ Builders | Completed
LMS 2022 | Region X | Misamis Occidental | 501874 | Manla Integrated School | SAPANG DALAGA | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND SOLAR PV ENERGY SYSTEM | 16435255.6737 | 15385260.39 | Completed | 1 | 2023-07-08 | 2023-09-15 | LMS 2022-RX-Misamis Occidental-002 | 001-2023 | 2022-10-26 | 2022-11-03 | 2022-11-15 | 2022-12-13 | 2023-01-27 | 3R's Builders | Completed
LMS 2022 | Region X | Misamis Oriental | 201509 | Dahilig ES | BALINGOAN | 1 | 1 | 4 | CONSTRUCTION OF 2UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 14773677.2926 | 13824219.59 | Completed | 1 | 2023-04-12 | 2023-07-11 | PB-Infra 2022-001 |  | 2022-08-10 | 2022-08-10 | 2022-08-30 | 2022-09-22 | 2022-11-27 | Meterking Inc. | Completed
LMS 2023 | Region X | Lanao del Norte | 127159 | Bowi PS | PANTAR | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 17600258.64 | 14152726.43 | Completed | 1 | 2024-06-04 | 2024-05-30 | 2023 - 01(Infra) | 44927 | 2023-07-28 | 2023-08-07 | 2023-08-22 | 2023-09-01 | 2023-12-07 | SBM Builder's | Completed
LMS 2023 | Region X | Lanao del Norte | 127175 | Bulacon PS | SALVADOR | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 17609276.98 | 17116471.79 | Completed | 1 | 2025-03-20 | 2025-03-20 | 2024 - 09(Infra) | 45536 | 2024-06-06 | 2024-06-14 | 2024-07-05 | 2024-08-05 | 2024-08-26 | Lanao Genesis Construction Supply | 1st contract was terminated; 2nd contract NTP on Aug. 2024, looking for source of water for watersystem
LMS 2023 | Region X | Misamis Occidental | 501873 | Locus Integrated School | SAPANG DALAGA | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 17750076.13 | 17392036.74 | Ongoing | 0.95 | 2024-04-22 | 00:00:00 | LMS 2023 - RX - MISAMIS OCCIDENTAL - 001 - R | 016-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-17 | Genetian Builders & Enterprises, Inc. | Schedule for Final Inspection on June 4, 2025.
LMS 2023 | Region X | Misamis Occidental | 127539 | Camanse ES | SINACABAN | 2 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 17472250.06 | 16780281.43 | Completed | 1 | 2024-05-06 | 2024-06-13 | LMS 2023 - RX - MISAMIS OCCIDENTAL - 002 - R | 017-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-11-08 | Genetian Builders & Enterprises, Inc. | Completed with occupancy permit
LMS 2023 | Region X | Misamis Oriental | 130154 | Kinanao Pamalihi ES | BALINGASAG | 1 | 1 | 4 | CONSTRUCTION OF 2 UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19632409.94 | 17364431.28 | Completed | 1 | 2024-05-04 | 2024-12-15 | PB - Construction-2023-002 | 4673305 | June 3,2023 | June 13,2023 | June 27,2023 | July 27,2023 | 2023-12-29 | Minkonstrak Engineering and Gen Services | Completed
LMS 2024 | Region X | Bukidnon | 113847 | Basbasanan To Goynawa To Balakayo | SAN FERNANDO | 2nd | 1 | 3 | CONSTRUCTION OF BUILDING NO.1- 1 STOREY 3 CLASSROOM BUILDING with TOILET ATTACHED, wITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, WATER SYSTEM, PERIMETER GATE AND FENCE | 11198312.24 | 8493552.5 | Ongoing | 0.95 | Revised to June 10, 2025 | 00:00:00 | PB-02-11-2023-0026 | 012-2024 | 2023-11-26 | 2023-12-04 | 2023-12-18 | 2023-12-27 | 2024-05-20 | Vibranium Builders Corporation | Substantially Completed; with Approved Time extension no.'s 1&2, variation order no.'s 1&2 and due to unfavorable weather conditions. Request a extension awaits the delivery of furniture.
LMS 2024 | Region X | Bukidnon | 113847 | Basbasanan To Goynawa To Balakayo | SAN FERNANDO | 2nd |  | 2 | CONSTRUCTION BUILDING NO. 2- 1 STOREY 2 CLASSROOM BUILDING WITH TOILET ATTACHED WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND PERIMETER SOLAR LIGHTS | 14860395.24 | 8493552.5 | Ongoing | 0.95 | Revised to June 10, 2025 | 00:00:00 | PB-02-11-2023-0026 | 012-2024 | 2023-11-26 | 2023-12-04 | 2023-12-18 | 2023-12-27 | 2024-05-20 | Vibranium Builders Corporation | substantially completed; with Approved Time extension no.'s 1&2, variation order no.'s 1&2 and due to unfavorable weather conditions. Request a extension awaits the delivery of furniture.
LMS 2024 | Region X | El Salvador | 305683 | Sambulawan National High School | CITY OF EL SALVADOR | 2nd | 1 | 3 | CONSTRUCTION OF 1STY3CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 16488351.52 | 12568813.6 | Completed | 1 | 2024-10-15 | 2024-11-12 | 2024-01-0003 | 2024-02-0002 | 2024-01-04 | 2024-01-23 | 2024-02-07 | 2024-05-08 | 2024-05-21 | JDE Construction | Completed
LMS 2024 | Region X | Gingoog City | 111092 | Sagu-Ilaw Ta Kabuka Elementary School | GINGOOG CITY | 1st | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 22120108.86 | 21858003.57 | Ongoing | 0.5 | 2025-05-25 | 00:00:00 | LMS 2023 - RX - GINGOOG CITY - 004 | BMB-F-24-0000862 | 2023-11-03 | 2023-11-10 | 2023-11-21 | 2024-05-21 | 2024-06-03 | Blaff Construction and Supplies | On-going Construction (under time suspension - due to actual site condition)
LMS 2024 | Region X | Iligan City | 128131 | Panoroganan ES | ILIGAN CITY | Lone | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 15851835.73 | 12555775.14 | Completed | 1 | 2025-01-10 | 2025-02-12 | INFRA-2023-11-03 | INFRA-2023-11-03 | 2023-11-28 | 2023-12-06 | 2023-12-20 | 2024-01-26 | 2024-05-31 | Brima Construction and Enterprise | Completed
LMS 2024 | Region X | Malaybalay City | 501853 | Mapayag Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 |  | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 18241095.24 | 14778549.81 | Ongoing | 0.9 | 2025-04-07 | 00:00:00 | 003-INFRA-2023 | 003-INFRA-2023 | 2023-11-29 | 2023-12-07 | 2023-12-19 | 2023-12-19 | 2024-09-09 | Vimbranium Builder's Corporation | Approved Time Extension equivalent to 30 CDs.
LMS 2024 | Region X | Misamis Occidental | 127568 | Gala ES | TUDELA | 2nd | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 16544911.02 | 16369981.76 | Ongoing | 0.95 | 2024-03-19 | 00:00:00 | LMS 2024 - RX - MISAMIS OCCIDENTAL - 002 | 011-2024 | 2024-01-16 | 2024-01-24 | 2024-02-05 | 2024-03-24 | 2024-07-22 | RJLG CONSTRUCTION AND SUPPLIES | For final inspection on June 11, 2025
LMS 2024 | Region X | Misamis Oriental | 201506 | Kalitian ES | KINOGUITAN | 1st | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 17917491.26 | 14458743.76 | Completed | 1 | 2024-11-17 | 2024-12-18 | PB-BAC1-Construction 2024-001 | 4919317 | 2024-01-17 | 2024-01-24 | 2024-02-05 | 2024-02-21 | 2024-06-13 | CLC Construction Services & Supply | Completed (Including Variation Order)
LMS 2024 | Region X | Misamis Oriental | 201503 | Lonsi ES | ALUBIJID | 2nd | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 16902227.11 | 13216388.97 | Completed | 1 | 2024-11-17 | 2025-03-20 | PB-BAC1-Construction 2024-002 | 4919350 | 2024-01-17 | 2024-01-24 | 2024-02-05 | 2024-02-21 | 2024-06-13 | Trench | Completed (Including Variation Order )
LMS 2024 | Region X | Oroquieta City | 238501 | Kanowanan Tribal ES | OROQUIETA CITY (Capital) | 1st | 1 | 2 | CONSTRUCTION OF 1STY2CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND FLOOD MARKER | 15701425.95 | 13445916.11 | Completed | 1 | 2024-10-10 | 2024-12-09 |  |  | 2024-11-23 | 2024-11-30 | 2023-12-14 | 2024-05-03 | 2024-05-10 | RSMA BUILDERS & GEN. MDSE | Processing for Occupancy Permit.
LMS 2024 | Region X | Ozamis City | 128188 | Pershing Tan Queto Sr. ES | OZAMIS CITY | 2nd | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 18361158.83 | 18151162.88 | completed | 1 | 2024-11-29 | 2024-12-29 | 092-CIVIL 2023-003 (EPA) | 092-CIVIL 2023-003 (EPA) | 2023-11-22 | 2023-11-29 | 2023-12-15 | 2024-01-02 | 2024-06-27 | Mitz and Nick Builders | with time extension
LMS 2024 | Region X | Tangub City | 128223 | Capalaran West ES | TANGUB CITY | 2nd | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 19993368.26 | 19397245.16 | Completed | 1 | 2024-12-26 | 2025-02-03 | LMS 2023-Region X-Tangub 001 |  | 2024-11-23 | 2024-11-30 | 2023-12-12 | 2023-12-20 | 2024-07-04 | RIC Construction | Completed
LMS 2024 | Region X | Valencia City | 137043 | MAKAILAW ELEMENTARY SCHOOL | VALENCIA CITY | 4th | 1 | 4 | CONSTRUCTION OF 2 UNITS 1ST-2CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 18656357.05 | 14580621.09 | terminated | 0.24 | 2025-10-10 | 00:00:00 | 45352 | 009 s. 2024 | 2024-06-03 | 2024-02-02 | 2024-02-16 | 2024-03-11 | 2024-05-27 | ALRAF CONSTRUCTION | Contract Terminated/rescinded

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.