## Sheet1
Region | Division | School ID | School Name | Municipality | Leg District | No. of Sites | Scope of Work | Total Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | Municipality Classification
Region III | Aurora | 300690 | Lual NHS | CASIGURAN | Lone | 1 | PROPOSED TWO (2) - STOREY ALTERNATIVE LEARNING SYSTEM (ALS) BUILDING (22.50m x 9.50m) - with Roof Deck( TO be elevated by 1.0m) | 12446387.1 | 10458975.45 | ongoing | 0.7 | June 21, 2025 |  | 2024-04-181 | SGOD-INFRA-32 | July 1, 2024 | July 8, 2024 | July 22, 2024 | August 1, 2024 | August 17, 2024 | MACCO CONSTRUCTION | Request to utilized savings is up to now no response from CO | 0 | 0 | 0 | 1 | 0 | 0.5 | 0.2 |  |  | 2nd