## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | No. of Sites Reverted.1 | No. of Sites Not yet started.1 | No. of Sites Under Procurement.1 | No. of Sites On Going.1 | No. of Sites Completed.1 | CATEGORY 2 | Unnamed: 46
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Antipolo City | 301418 | Antipolo NHS | CITY OF ANTIPOLO | 1st | 1 |  | Repair of Clinic | 815466.71 |  | 813834.07 | Completed | 1 | March 14, 2025 | Feb. 12, 2025 |  | BEFF-ANT-2024-02 | July 10, 2024 | July 18, 2024 | July 30, 2024 | August 7, 2024 | Oct. 15, 2025 | HAWKSTOW CONST. AND DEVELOPMENT |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 3.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Antipolo City | 109327 | Juan Sumulong ES | CITY OF ANTIPOLO | 2nd | 1 |  | Repair of Clinic | 611000 |  | 603643.98 | Completed | 1 | March 14, 2025 | Feb. 12, 2025 |  | BEFF-ANT-2024-02 | July 10, 2024 | July 18, 2024 | July 30, 2024 | August 7, 2024 | Oct. 15, 2025 | HAWKSTOW CONST. AND DEVELOPMENT |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 3.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Antipolo City | 109361 | Sumilang ES | CITY OF ANTIPOLO | 2nd | 1 |  | Construction of Water System | 2500000 |  | 2498521.95 | Completed | 1 | March 14, 2025 | March 5, 2025 |  | BEFF-ANT-2024-02 | July 10, 2024 | July 18, 2024 | July 30, 2024 | August 7, 2024 | Oct. 15, 2025 | HAWKSTOW CONST. AND DEVELOPMENT |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 3.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Batangas | 107248 | Santol ES | Balayan | 1st | 1 |  | Construction of Group Handwashing Facility | 373029.78 |  | 370000 | Completed | 1 | May 6, 2025 | April 25, 2025 | WINS 2024 - IVA - BATANGAS PROVINCE - 001 | WINS 2024 - IVA - BATANGAS PROVINCE - 001 | June 11, 2024 | June 18, 2024 | July 1, 2024 | July 17, 2024 | January 30, 2025 | Botey Construction | NONE | 0 | 0 | 0 | 0 | 1 | [5 empty] | 0.9 | 0.1
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Batangas | 107263 | Bauan East CS | Bauan | 2nd | 1 |  | Construction of Group Handwashing Facility | 373029.78 |  | 370000 | Completed | 1 | May 6, 2025 | April 25, 2025 | WINS 2024 - IVA - BATANGAS PROVINCE - 002 | WINS 2024 - IVA - BATANGAS PROVINCE - 002 | June 11, 2024 | June 18, 2024 | July 1, 2024 | July 17, 2024 | January 30, 2025 | Botey Construction | NONE | 0 | 0 | 0 | 0 | 1 | [5 empty] | 0.3 | 0.7
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Batangas | 107337 | Calumayin School | Cuenca | 3rd | 1 |  | Construction of Group Handwashing Facility | 359254.72 |  | 350000 | Completed | 1 | May 6, 2025 | April 25, 2025 | WINS 2024 - IVA - BATANGAS PROVINCE - 003 | WINS 2024 - IVA - BATANGAS PROVINCE - 003 | June 11, 2024 | June 18, 2024 | July 1, 2024 | July 17, 2024 | January 30, 2025 | Botey Construction | NONE | 0 | 0 | 0 | 0 | 1 | [5 empty] | 0.3 | 0.7
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Batangas | 107530 | Maugat East ES | Padre Garcia | 4th | 1 |  | Construction of Group Handwashing Facility | 366446.94 |  | 350000 | Completed | 1 | May 6, 2025 | April 25, 2025 | WINS 2024 - IVA - BATANGAS PROVINCE - 004 | WINS 2024 - IVA - BATANGAS PROVINCE - 004 | June 11, 2024 | June 18, 2024 | July 1, 2024 | July 17, 2024 | January 30, 2025 | Botey Construction | NONE | 0 | 0 | 0 | 0 | 1 | [5 empty] | 0.3 | 0.7
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 108016 | Aguinaldo Elementary School | KAWIT | 1st | 1 |  | Construction of 4-Seater Toilet | 1778541.58 |  | 1771974.69 | On-going | 0.8 | May 14, 2025 |  |  | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | Already working on the Finishing Works/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0.8 | 0
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 301174 | Binakayan National High School | KAWIT | 1st | 1 |  | Construction of Group Handwashing Facility - For Secondary (Option 3A - One-Sided, with Roofing, with Counter, with Tile Finish) | 1199236.08 |  | 1195104.07 | On-going | 0.18 | May 14, 2025 |  |  | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | Slow Pace of Work/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0.18 | 0
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 108019 | Florante Ilano Memorial Elementary School | KAWIT | 1st | 1 |  | Construction of Group Handwashing Facility - For Elementary (Option 3A - One-Sided, with Roofing, with Counter, with Tile Finish) | 1144861.02 |  | 1140823.76 | On-going | 0.18 | May 14, 2025 |  |  | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | Slow Pace of Work/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0.18 | 0
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 107892 | Bancal Elementary School | CARMONA | 5th | 1 |  | Construction of 4-Seater Toilet | 1778541.58 |  | 1771974.69 | On-going | 0.25 | May 14, 2025 |  |  | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | Slow Pace of Work/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0.25 | 0
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 107893 | Cabilang Baybay Elementary School | CARMONA | 5th | 1 |  | Construction of Group Handwashing Facility - For Elementary (Option 3A - One-Sided, with Roofing, with Counter, with Tile Finish) | 1869086.95 |  | 1862721.32 | Completed | 1 | May 14, 2025 |  |  | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | For completion of necessary documents for the completion of the project on the site/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 301177 | Carmona National High School | CARMONA | 5th | 1 |  | Construction of Group Handwashing Facility - For Secondary (Option 3A - One-Sided, with Roofing, with Counter, with Tile Finish) | 1199236.08 |  | 1195104.07 | On-going | 0.18 | May 14, 2025 |  |  | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | Slow Pace of Work/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0.18 | 0
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 107857 | Amadeo Elementary School | AMADEO | 7th | 1 |  | Construction of 4-Seater Toilet | 1729344.95 |  | 1722983 | On-going | 0.18 | May 14, 2025 |  |  | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | Slow Pace of Work/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0.18 | 0
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 107858 | Dagatan Elementary School | AMADEO | 7th | 1 |  | Construction of Group Handwashing Facility - For Elementary (Option 3A - One-Sided, with Roofing, with Counter, with Tile Finish) | 1821589.36 |  | 1815097.94 | Completed | 1 | May 14, 2025 |  |  | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | For completion of necessary documents for the completion of the project on the site/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 301210 | Pangil National High School | AMADEO | 7th | 1 |  | Construction of Group Handwashing Facility - For Secondary (Option 3A - One-Sided, with Roofing, with Counter, with Tile Finish) | 1467459.85 |  | 1462528.61 | Completed | 1 | May 14, 2025 |  |  | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | For completion of necessary documents for the completion of the project on the site/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 107839 | Alfonso Central School | ALFONSO | 8th | 1 |  | Construction of 4-Seater Toilet | 1778541.58 |  | 1771974.69 | Completed | 1 | May 14, 2025 |  |  | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | For completion of necessary documents for the completion of the project on the site/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 301165 | Alfonso Integrated High School | ALFONSO | 8th | 1 |  | Construction of Group Handwashing Facility - For Secondary (Option 3A - One-Sided, with Roofing, with Counter, with Tile Finish) | 2378202.03 |  | 2369501.2 | On-going | 0.18 | May 14, 2025 |  |  | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | Slow Pace of Work/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0.18 | 0
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 107840 | Amuyong Elementary School | ALFONSO | 8th | 1 |  | Construction of Group Handwashing Facility - For Elementary (Option 3A - One-Sided, with Roofing, with Counter, with Tile Finish) | 1144861.02 |  | 1140823.76 | On-going | 0.18 | May 14, 2025 |  |  | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | Slow Pace of Work/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0.18 | 0
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite City | 109632 | Ladislao Diwa Elementary School | CAVITE CITY | 1st | 1 |  | 8 units of Group Handwashing Facility Option 1B | 4864447.28 |  | 4134506.33 | Completed | 1 | February 17, 2025 | December 15, 2024 | 2024-06-0004 | 2024-06-0004 | June 4, 2024 | June 13, 2024 | June 26, 2024 | July 4, 2024 | September 20, 2024 | L2A Builders and Trading | * | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 1.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | City of Biñan | 108217 | Dela Paz Main ES | CITY OF BIÑAN | Lone | 1 |  | Construction of Group Handwashing Facilities | 555792.24 |  | 547697.65 | Completed | 1 | September 15, 2024 | September 13, 2024 | 10923021 | 10923021 | N/A - RFQ | N/A - RFQ | N/A - RFQ | June 25, 2024 | July 17, 2024 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 11.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | City of Biñan | 108217 | Dela Paz Main ES | CITY OF BIÑAN | Lone |  |  | Repair of Classroom to be Used/Converted to School Clinic | 1071103.22 |  | 930346.44 | Completed | 1 | August 18, 2024 | August 6, 2024 | R4A-BNN-2023-02 | R4A-BNN-2023-02 | December 27, 2023 - January 16, 2024 | January 4, 2024 | January 16, 2024 | February 7, 2024 | May 20, 2024 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 1 | 0 |  | 8.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | City of Biñan | 164526 | Southville 5A ES - Langkiwa | CITY OF BIÑAN | Lone | 1 |  | Construction of Water and Sanitation Facilities | 1115051.25 |  | 957782.88 | Completed | 1 | January 15, 2025 | January 17, 2025 | R4A-BNN-2024-05 | R4A-BNN-2024-05 | July 24 - August 13, 2024 | August 1, 2024 | August 13, 2024 | August 27, 2024 | October 17, 2024 | GS Motar Builders Construction & Trading | Waiting for the release of Sub-ARO | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 2.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | City of Biñan | 307934 | Southville 5A INHS | CITY OF BIÑAN | Lone | 1 |  | Construction of School Clinic | 3612913.97 |  | 3155056.04 | Completed | 1 | September 17, 2024 | December 11, 2024 | R4A-BNN-2023-03 | R4A-BNN-2023-03 | December 27, 2023 - January 16, 2024 | January 4, 2024 | January 16, 2024 | February 7, 2024 | May 20, 2024 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 1.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Gen. Trias City | 107948 | Ipilan Barrio School | CITY OF GENERAL TRIAS | 6th | 1 |  | Conversion of classroom to Health Center | 936863.31 |  | 818653.12 | Completed | 1 | March 27, 2025 | March 27, 2025 | 2024-12-001 | 2024-12-001 | July 8, 2024 | SVP | SVP | July 16, 2024 | December 27, 2024 | JKK Construction Services | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Laguna | 108200 | Bay CS | BAY | 2nd | 1 |  | Construction of Hand Washing Facilities | 208229.39 |  | 208055 | On-going | 0.15 | 9/16/2025 | - | R4a-2024-016 | R4a-2024-016 | 2024-09-27 | 10/7/2024 (Pre-Bid Conference) | Oct. 21, 2024 | 2024-11-08 | 5/21/2025 | ELD Enterprises | Released NTP on May 19, 2025 | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0 | 0.15
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Laguna | 108303 | Bambang ES | LOS BAÑOS | 2nd | 1 |  | Construction of Hand Washing Facilities | 208229.39 |  | 208055 | On-going | 0.15 | 9/16/2025 | - | R4a-2024-016 | R4a-2024-016 | 2024-09-27 | 10/7/2024 (Pre-Bid Conference) | Oct. 21, 2025 | 2024-11-08 | 5/21/2025 | ELD Enterprises | Released NTP on May 19, 2025 | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0 | 0.15
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Laguna | 108188 | Alaminos CS | ALAMINOS | 3rd | 1 |  | Construction of Hand Washing Facilities | 208229.39 |  | 208055 | On-going | 0.15 | 9/16/2025 | - | R4a-2024-016 | R4a-2024-016 | 2024-09-27 | 10/7/2024 (Pre-Bid Conference) | Oct. 21, 2026 | 2024-11-08 | 5/21/2025 | ELD Enterprises | Released NTP on May 19, 2025 | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0 | 0.15
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Laguna | 108253 | Balayhangin ES | CALAUAN | 3rd | 1 |  | Construction of Hand Washing Facilities | 208229.39 |  | 208055 | On-going | 0.15 | 9/16/2025 | - | R4a-2024-016 | R4a-2024-016 | 2024-09-27 | 10/7/2024 (Pre-Bid Conference) | Oct. 21, 2027 | 2024-11-08 | 5/21/2025 | ELD Enterprises | Released NTP on May 19, 2025 | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0 | 0.15
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Laguna | 108272 | Burol ES | CAVINTI | 4th | 1 |  | Construction of Hand Washing Facilities | 208229.39 |  | 208055 | On-going | 0.15 | 9/16/2025 | - | R4a-2024-016 | R4a-2024-016 | 2024-09-27 | 10/7/2024 (Pre-Bid Conference) | Oct. 21, 2028 | 2024-11-08 | 5/21/2025 | ELD Enterprises | Released NTP on May 19, 2025 | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0 | 0.15
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Laguna | 108327 | Longos ES | KALAYAAN | 4th | 1 |  | Construction of Hand Washing Facilities | 208229.39 |  | 208055 | On-going | 0.15 | 9/16/2025 | - | R4a-2024-016 | R4a-2024-016 | 2024-09-27 | 10/7/2024 (Pre-Bid Conference) | Oct. 21, 2029 | 2024-11-08 | 5/21/2025 | ELD Enterprises | Released NTP on May 19, 2025 | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0 | 0.15
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Quezon | 108556 | Aluyon Elementary School | BURDEOS | 1st | 1 |  | Construction of School Clinic | 5252051.98 |  | 108556 | Completed | 1 | November 20, 2024 | November 18, 2024 |  | 2023-06-INFRAEPA | November 24, 2023 | December 1, 2023 | December 15, 2023 | December 29, 2023 | May 20, 2024 | N.T. Sotelo Construction and Supply Corporation |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 12.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Quezon | 108621 | Mangilag Norte ES | CANDELARIA | 2nd | 1 |  | Construction of School Clinic | 4675089.04 |  | 4200000 | Completed | 1 | September 17, 2024 | July 30, 2024 |  | 2023-06-INFRAEPA | November 24, 2023 | December 1, 2023 | December 15, 2023 | December 29, 2023 | May 21, 2024 | Botey Construction |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 8.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Quezon | 108944 | AGDANGAN CENTRAL ES | AGDANGAN | 3rd | 1 |  | Construction of School Clinic | 4704018.14 |  | 3737566.6 | Completed | 1 | September 16, 2024 | September 13, 2024 |  | 2023-06-INFRAEPA | November 24, 2023 | December 1, 2023 | December 15, 2023 | December 29, 2023 | May 20, 2024 | M.G. Villamin Construction |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 11.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Quezon | 108503 | ALABAT CENTRAL ELEMENTARY SCHOOL | ALABAT | 4th | 1 |  | Construction of School Clinic | 4758321.11 |  | 4747000 | Completed | 1 | September 16, 2024 | September 11, 2024 |  | 2023-06-INFRAEPA | November 24, 2023 | December 1, 2023 | December 15, 2023 | December 29, 2023 | May 20, 2024 | Neniko Construction & Supplies |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 11.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Rizal | 301417 | Angono National High School | ANGONO | 1st | 1 |  | Construction of Group Handwashing Facilities | 322353.43 |  | 293502.72 | On-going | 0.6 | May 6, 2025 |  | INFRA-2024-001 | INFRA-2024-001 | July 29, 2024 | August 6, 2024 | August 20, 2024 | August 30, 2024 | February 6, 2025 | RALB Construction | Clustered Contract | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0.4 | 0.2
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Rizal | 109315 | San Vicente ES | ANGONO | 1st | 1 |  | Construction of Group Handwashing Facilities | 320411.31 |  | 293502.72 | On-going | 0.65 | May 6, 2025 |  | INFRA-2024-001 | INFRA-2024-001 | July 29, 2024 | August 6, 2024 | August 20, 2024 | August 30, 2024 | February 6, 2025 | RALB Construction | Clustered Contract | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0.4 | 0.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Rizal | 109486 | Dulongbayan ES | SAN MATEO | 3rd | 1 |  | Construction of Group Handwashing Facilities | 320411.31 |  | 5230782.45 | Completed | 1 | November 20, 2024 | November 18, 2024 |  | 2023-06-INFRAEPA | November 24, 2023 | December 1, 2023 | December 15, 2023 | December 29, 2023 | May 20, 2024 | N.T. Sotelo Construction and Supply Corporation |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 0.4 | 0.6
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Rizal | 165504 | Patiis Elementary School | SAN MATEO | 3rd | 1 |  | Construction of Group Handwashing Facilities | 320411.31 |  | 4200000 | Completed | 1 | September 17, 2024 | July 30, 2024 |  | 2023-06-INFRAEPA | November 24, 2023 | December 1, 2023 | December 15, 2023 | December 29, 2023 | May 21, 2024 | Botey Construction |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 0.2 | 0.8
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Rizal | 342566 | San Jose Litex SHS | RODRIGUEZ (MONTALBAN) | 4th | 1 |  | Construction of Group Handwashing Facilities | 322353.43 |  | 3737566.6 | Completed | 1 | September 16, 2024 | September 13, 2024 |  | 2023-06-INFRAEPA | November 24, 2023 | December 1, 2023 | December 15, 2023 | December 29, 2023 | May 20, 2024 | M.G. Villamin Construction |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 0.5 | 0.5
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Rizal | 109479 | San Rafael ES | RODRIGUEZ (MONTALBAN) | 4th | 1 |  | Construction of Group Handwashing Facilities | 320411.31 |  | 4747000 | Completed | 1 | September 16, 2024 | September 11, 2024 |  | 2023-06-INFRAEPA | November 24, 2023 | December 1, 2023 | December 15, 2023 | December 29, 2023 | May 20, 2024 | Neniko Construction & Supplies |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 0.1 | 0.9
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | San Pablo City | 109768 | Del Remedio Elementary School | SAN PABLO CITY | 3rd | 1 |  | Construction of 3 Units Group Handwashing Facility - For Elementary (Option 3A - One-Sided, with Roofing, with Counter, with Tile Finish) | 360000 |  | 339381.46 | Completed | 1 | August 16, 2024 | August 15, 2024 | BEFF-H-001 | BEFF-H-001 | November 30, 2023 | December 11, 2023 | December 27, 2023 | January 12, 2024 | July 2, 2024 | N.T. Sotelo Construction and Supply Corporation |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | San Pablo City | 109755 | San Miguel Elementary School | SAN PABLO CITY | 3rd | 1 |  | Construction of School Clinic | 2500000 |  | 2350669.64 | Completed | 1 | October 30, 2024 | October 30, 2024 | BEFF-SH-001 | BEFF-SH-001 | November 30, 2023 | December 11, 2023 | December 27, 2023 | January 12, 2024 | July 2, 2024 | N.T. Sotelo Construction and Supply Corporation |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 10.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | San Pedro City | 108426 | Pacita Complex I ES | SAN PEDRO | 1st | 1 |  | Construction of School Clinic | 4680001.53 |  | 3483584.6 | completed | 1 | October 29, 2024 | November 12, 2024 | 2023-PB-055 | 2023-PB-055 | November 17, 2023 | November 24, 2023 | January 11, 2024 | May 9, 2024 | June 1, 2024 | D&D Construction |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 11.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Tayabas City | 109235 | Katigan-Alupay ES | CITY OF TAYABAS | 1st | 1 |  | Construction of Water System (Deep Well Design with Solar - Powered Submersible Water Pump) | 2427369 |  | 2240000 | Completed | 1 | July 16, 2024 | July 12, 2024 | ITB-INFRA-2024-002 | ITB-INFRA-2024-002 | November 9, 2023 | November 17, 2023 | December 1, 2023 | May 3, 2024 | May 10, 2024 | BOTEY CONSTRUCTION | paid | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Tayabas City | 109235 | Katigan-Alupay ES | CITY OF TAYABAS | 1st |  |  | Construction of Water and Sanitation Facilities - Four (4) Seater | 754000 |  | 753000 | Completed | 1 | July 16, 2024 | July 27, 2024 | : ITB-INFRA-2024-001 | : ITB-INFRA-2024-001 | November 9, 2023 | November 17, 2023 | December 1, 2023 | May 3, 2024 | May 10, 2024 | BOTEY CONSTRUCTION | paid | 0 | 0 | 0 | 0 | 0 | [5 empty] | 1 | 0 |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Tayabas City | 109238 | Masin Elementary School | CITY OF TAYABAS | 1st | 1 |  | Construction of Group Hand Washing Facilities | 268500 |  | 267000 | Completed | 1 | June 16, 2024 | June 25, 2024 | : ITB-INFRA-2024-001 | : ITB-INFRA-2024-001 | November 9, 2023 | November 17, 2023 | December 1, 2023 | May 3, 2024 | May 10, 2024 | BOTEY CONSTRUCTION | paid | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 9.24
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 301073 | Balete National High School | BALETE | 2 | 1 | 2 | Construction of Group Handwashing Facility - For Secondary (Option 1B - with Flat Roofing, with Counter with Tile Finish) | 429941.23 | BATCH 1 | Lot 1 - 1,044,849.92 | Completed | 1 | 11/27/2022 | 11/27/2022 | WINS 2022 - RIVA - BATANGAS - 001 | WINS 2022 - RIVA - BATANGAS - 001 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | GS MOTAR BUILDERS CONSTRUCTION AND TRADING | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 107250 | Balete Central School | BALETE | 2 | 1 | 1 | Construction of Group Handwashing Facility - For Elementary (Option 1A - with Flat Roofing, with Counter with Tile Finish) | 216320.41 | BATCH 1 |  | Completed | 1 | 11/27/2022 | 11/27/2022 | WINS 2022 - RIVA - BATANGAS - 001 | WINS 2022 - RIVA - BATANGAS - 001 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | GS MOTAR BUILDERS CONSTRUCTION AND TRADING | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 501264 | Emilia L. Malabanan Integrated School | BALETE | 2 | 1 | 1 | Construction of Group Handwashing Facility - For Elementary (Option 1A - with Flat Roofing, with Counter with Tile Finish) | 216320.41 | BATCH 1 |  | Completed | 1 | 11/27/2022 | 11/27/2022 | WINS 2022 - RIVA - BATANGAS - 001 | WINS 2022 - RIVA - BATANGAS - 001 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | GS MOTAR BUILDERS CONSTRUCTION AND TRADING | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 301158 | Tingloy National High School | TINGLOY | 2 | 1 | 2 | Construction of Group Handwashing Facility - For Secondary (Option 1B - with Flat Roofing, with Counter with Tile Finish) | 429941.23 | BATCH 1 | Lot 2 - 1,067,097.15 | Completed | 1 | 11/27/2022 | 11/25/2022 | WINS 2022 - RIVA - BATANGAS - 002 | WINS 2022 - RIVA - BATANGAS - 002 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | RRE ERECTORS AND TRADING SPECIALIST | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 107820 | Tingloy Central School | TINGLOY | 2 | 1 | 1 | Construction of Group Handwashing Facility - For Elementary (Option 1A - with Flat Roofing, with Counter with Tile Finish) | 216320.41 | BATCH 1 |  | Completed | 1 | 11/27/2022 | 11/25/2022 | WINS 2022 - RIVA - BATANGAS - 002 | WINS 2022 - RIVA - BATANGAS - 002 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | RRE ERECTORS AND TRADING SPECIALIST | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 342199 | Tingloy Senior High School | TINGLOY | 2 | 1 | 2 | Construction of Group Handwashing Facility - For Secondary (Option 1B - with Flat Roofing, with Counter with Tile Finish) | 429941.23 | BATCH 1 |  | Completed | 1 | 11/27/2022 | 11/25/2022 | WINS 2022 - RIVA - BATANGAS - 002 | WINS 2022 - RIVA - BATANGAS - 002 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | RRE ERECTORS AND TRADING SPECIALIST | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 107666 | San Nicolas Central School | SAN NICOLAS | 3 | 1 | 1 | Construction of Group Handwashing Facility - For Elementary (Option 1A - with Flat Roofing, with Counter with Tile Finish) | 216320.41 | BATCH 1 | Lot 3 - 1,053,092.20 | Completed | 1 | 11/27/2022 | 11/25/2022 | WINS 2022 - RIVA - BATANGAS - 003 | WINS 2022 - RIVA - BATANGAS - 003 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | MARAKESH ENTERPRISES | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 307713 | San Nicolas Integrated High School | SAN NICOLAS | 3 | 1 | 1 | Construction of Group Handwashing Facility - For Secondary (Option 1B - with Flat Roofing, with Counter with Tile Finish) | 215767.21 | BATCH 1 |  | Completed | 1 | 11/27/2022 | 11/25/2022 | WINS 2022 - RIVA - BATANGAS - 003 | WINS 2022 - RIVA - BATANGAS - 003 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | MARAKESH ENTERPRISES | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 301149 | Sta. Teresita National High School | SANTA TERESITA | 3 | 1 | 1 | Construction of Group Handwashing Facility - For Secondary (Option 1B - with Flat Roofing, with Counter with Tile Finish) | 215767.21 | BATCH 1 |  | Completed | 1 | 11/27/2022 | 11/25/2022 | WINS 2022 - RIVA - BATANGAS - 003 | WINS 2022 - RIVA - BATANGAS - 003 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | MARAKESH ENTERPRISES | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 107691 | Mohon Elementary School | SANTA TERESITA | 3 | 1 | 1 | Construction of Group Handwashing Facility - For Elementary (Option 1A - with Flat Roofing, with Counter with Tile Finish) | 216320.41 | BATCH 1 | Lot 1 - 1,044,849.92 | Completed | 1 | 11/27/2022 | 11/27/2022 | WINS 2022 - RIVA - BATANGAS - 001 | WINS 2022 - RIVA - BATANGAS - 001 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | GS MOTAR BUILDERS CONSTRUCTION AND TRADING | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 501541 | Sampa-Pacifico Integrated School | SANTA TERESITA | 3 | 1 | 1 | Construction of Group Handwashing Facility - For Elementary (Option 1A - with Flat Roofing, with Counter with Tile Finish) | 216320.41 | BATCH 1 | Lot 3 - 1,053,092.20 | Completed | 1 | 11/27/2022 | 11/25/2022 | WINS 2022 - RIVA - BATANGAS - 003 | WINS 2022 - RIVA - BATANGAS - 003 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | MARAKESH ENTERPRISES | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 107690 | Irukan-Kalayaan Elementary School | SANTA TERESITA | 3 | 1 | 1 | Construction of Group Handwashing Facility - For Elementary (Option 1A - with Flat Roofing, with Counter with Tile Finish) | 216320.41 | BATCH 1 |  | Completed | 1 | 11/27/2022 | 11/25/2022 | WINS 2022 - RIVA - BATANGAS - 003 | WINS 2022 - RIVA - BATANGAS - 003 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | MARAKESH ENTERPRISES | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Cavite | 107930 | Kabulusan Elementary School | GENERAL EMILIO AGUINALDO | 8 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (1 UNIT OPTION 3A - ONE - SIDED, WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 163253.91 | BATCH 1 |  | Completed | 1 | [10 empty] | Didnt proceed on Procurement because the amount didnt exceed 1m, the project proceeded on Small Value Procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Cavite | 107932 | Kaypaaba Elementary School | GENERAL EMILIO AGUINALDO | 8 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (1 UNIT OPTION 3A - ONE - SIDED, WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 163253.91 | BATCH 1 |  | Completed | 1 | [10 empty] | Didnt proceed on Procurement because the amount didnt exceed 1m, the project proceeded on Small Value Procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Cavite | 107927 | Castaños Elementary School | GENERAL EMILIO AGUINALDO | 8 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (1 UNIT OPTION 3A - ONE - SIDED, WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 163253.91 | BATCH 1 |  | Completed | 1 | [10 empty] | Didnt proceed on Procurement because the amount didnt exceed 1m, the project proceeded on Small Value Procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Cavite | 107933 | Lumipa Elementary School | GENERAL EMILIO AGUINALDO | 8 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (1 UNIT OPTION 3A - ONE - SIDED, WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 163253.91 | BATCH 1 |  | Completed | 1 | [10 empty] | Didnt proceed on Procurement because the amount didnt exceed 1m, the project proceeded on Small Value Procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108284 | Famy Elementary School | FAMY | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132568.57 | Completed | 1 | 2022-10-18 | 2022-10-17 | R4A-2022-005 | R4A-2022-005 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | N.T. Sotelo Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 301240 | Famy National Integrated High School | FAMY | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONED SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 133901.99 | BATCH 1 | 132568.57 | Completed | 1 | 2022-10-18 | 2022-10-17 | R4A-2022-005 | R4A-2022-005 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | N.T. Sotelo Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 164504 | San Miguel ES | FAMY | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132568.57 | Completed | 1 | 2022-10-18 | 2022-10-17 | R4A-2022-005 | R4A-2022-005 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | N.T. Sotelo Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108285 | Mabitac ES | MABITAC | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132568.57 | Completed | 1 | 2022-10-18 | 2022-10-17 | R4A-2022-005 | R4A-2022-005 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | N.T. Sotelo Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108289 | Nanguma ES | MABITAC | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132568.57 | Completed | 1 | 2022-10-18 | 2022-10-17 | R4A-2022-005 | R4A-2022-005 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | N.T. Sotelo Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108291 | Paagahan ES | MABITAC | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132568.57 | Completed | 1 | 2022-10-18 | 2022-10-17 | R4A-2022-005 | R4A-2022-005 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | N.T. Sotelo Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 301249 | Mabitac NHS | MABITAC | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 135765.31 | BATCH 1 | 132568.57 | Completed | 1 | 2022-10-18 | 2022-10-17 | R4A-2022-005 | R4A-2022-005 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | N.T. Sotelo Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 301255 | Paagahan Integrated National High School | MABITAC | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 133901.99 | BATCH 1 | 132568.57 | Completed | 1 | 2022-10-18 | 2022-10-17 | R4A-2022-005 | R4A-2022-005 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | N.T. Sotelo Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 307928 | Matalatala Integrated National High School | MABITAC | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 133901.99 | BATCH 1 | 132568.57 | Completed | 1 | 2022-10-18 | 2022-10-17 | R4A-2022-005 | R4A-2022-005 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | N.T. Sotelo Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108390 | Banilan ES | PAKIL | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132992.21 | Completed | 1 | 2022-10-18 | 2022-10-14 | R4A-2022-006 | R4A-2022-006 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | Juncan Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108391 | Matikiw ES | PAKIL | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132992.21 | Completed | 1 | 2022-10-18 | 2022-10-14 | R4A-2022-006 | R4A-2022-006 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | Juncan Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108392 | Casa Real ES | PAKIL | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132992.21 | Completed | 1 | 2022-10-18 | 2022-10-14 | R4A-2022-006 | R4A-2022-006 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | Juncan Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108393 | Casinsin ES | PAKIL | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132992.21 | Completed | 1 | 2022-10-18 | 2022-10-14 | R4A-2022-006 | R4A-2022-006 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | Juncan Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108398 | Kabulusan ES | PAKIL | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132992.21 | Completed | 1 | 2022-10-18 | 2022-10-14 | R4A-2022-006 | R4A-2022-006 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | Juncan Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108400 | Maulawin ES | PAKIL | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132992.21 | Completed | 1 | 2022-10-18 | 2022-10-14 | R4A-2022-006 | R4A-2022-006 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | Juncan Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108401 | Pakil ES | PAKIL | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132992.21 | Completed | 1 | 2022-10-18 | 2022-10-14 | R4A-2022-006 | R4A-2022-006 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | Juncan Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 301243 | Kabulusan Integrated National High School | PAKIL | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 133901.99 | BATCH 1 | 132992.21 | Completed | 1 | 2022-10-18 | 2022-10-14 | R4A-2022-006 | R4A-2022-006 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | Juncan Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108364 | Rizal ES | RIZAL | 3 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 135658.97 | BATCH 1 | 132992.21 | Completed | 1 | 2022-10-18 | 2022-10-14 | R4A-2022-006 | R4A-2022-006 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | Juncan Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 307903 | Cristobal S. Conducto Memorial National High School | RIZAL | 3 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 133901.99 | BATCH 1 | 132992.21 | Completed | 1 | 2022-10-18 | 2022-10-14 | R4A-2022-006 | R4A-2022-006 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | Juncan Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 501326 | Luod Integrated School | PATNANUNGAN | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 250491.84 | BATCH 1 | 249279 | Completed | 1 | 9/28/2022 | 9/17/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | L.A PROFUGO CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109086 | Sampaloc ES I | SAMPALOC | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222197.06 | Completed | 1 | 9/28/2022 | 2022-10-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | L.A PROFUGO CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109087 | Sampaloc ES II (G-Hills) | SAMPALOC | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222197.06 | Completed | 1 | 9/28/2022 | 2022-10-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | L.A PROFUGO CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108944 | Agdangan Central Elementary School | AGDANGAN | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222213.29 | Completed | 1 | 9/28/2022 | 2022-08-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | L.A PROFUGO CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108945 | Binagbag ES | AGDANGAN | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222197.06 | Completed | 1 | 9/28/2022 | 2022-08-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | L.A PROFUGO CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108948 | Dayap ES | AGDANGAN | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222197.06 | Completed | 1 | 9/28/2022 | 2022-08-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | L.A PROFUGO CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108949 | E. Licup ES | AGDANGAN | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222197.06 | Completed | 1 | 9/28/2022 | 2022-08-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | L.A PROFUGO CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108951 | Ilayang Kinagunan ES | AGDANGAN | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222197.06 | Completed | 1 | 9/28/2022 | 2022-08-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | L.A PROFUGO CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108957 | Salvacion ES | AGDANGAN | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222197.06 | Completed | 1 | 9/28/2022 | 2022-08-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | L.A PROFUGO CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108503 | Alabat Central Elementary School | ALABAT | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 243663.27 | BATCH 1 | 243416 | Completed | 1 | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 500866 | CB Encarnado Integrated School | ALABAT | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 243663.27 | BATCH 1 | 243416 | Completed | 1 | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 501220 | RT Camacho Integrated School | ALABAT | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 243663.27 | BATCH 1 | 243416 | Completed | 1 | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108993 | Mainit Norte ES | PEREZ | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 264120.41 | BATCH 1 | 263912 | Completed | 1 | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108995 | PAMBUHAN ES | PEREZ | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 250470.41 | BATCH 1 | 249821 | Completed | 1 | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108996 | Perez CS | PEREZ | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 264120.41 | BATCH 1 | 263912 | Completed | 1 | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108997 | Perez West Elementary School | PEREZ | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 264120.41 | BATCH 1 | 263912 | Completed | 1 | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108998 | Pinagtubigan ES | PEREZ | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 264120.41 | BATCH 1 | 263912 | Completed | 1 | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 501265 | Severo Tejada Integrated School | PEREZ | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 264120.41 | BATCH 1 | 263912 | Completed | 1 | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109015 | Concepcion ES | PLARIDEL | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222920 | Completed | 1 | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109016 | Ilosong ES | PLARIDEL | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222920 | Completed | 1 | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109017 | Plaridel CS | PLARIDEL | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222920 | Completed | 1 | 9/28/2022 | 2022-09-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109018 | Tanauan ES | PLARIDEL | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222920 | Completed | 1 | 9/28/2022 | 2022-09-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109232 | Busal ES | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 177290.34 | BATCH 1 | 175668.2 | Completed | 1 | 2023-03-02 | March 21, 2023 | INFRA-2022-006 | INFRA-2022-006 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109234 | Ilasan ES | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 161906.39 | BATCH 1 | 160284.24 | Completed | 1 | 2023-03-02 | March 21, 2023 | INFRA-2022-006 | INFRA-2022-006 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109237 | Lawigue ES | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 161906.39 | BATCH 1 | 160284.24 | Completed | 1 | 2023-03-02 | March 14, 2023 | INFRA-2022-004 | INFRA-2022-004 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109241 | Pandakake ES | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 172162.36 | BATCH 1 | 170540.21 | Completed | 1 | 2023-03-02 | March 14, 2023 | INFRA-2022-004 | INFRA-2022-004 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109242 | South Palale ES | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 161906.39 | BATCH 1 | 160284.24 | Completed | 1 | 2023-03-02 | March 21, 2023 | INFRA-2022-006 | INFRA-2022-006 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109243 | Tayabas East CS | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 161906.39 | BATCH 1 | 160284.24 | Completed | 1 | 2023-03-02 | March 14, 2023 | INFRA-2022-004 | INFRA-2022-004 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109246 | Valencia ES | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 172162.36 | BATCH 1 | 170540.21 | Completed | 1 | 2023-03-02 | March 21, 2023 | INFRA-2022-006 | INFRA-2022-006 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109247 | Wakas ES | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 161906.39 | BATCH 1 | 160284.24 | Completed | 1 | 2023-03-02 | March 14, 2023 | INFRA-2022-004 | INFRA-2022-004 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109248 | West Palale ES | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH)Construction of Hand Washing Facilities | 161906.39 | BATCH 1 | 160284.24 | Completed | 1 | 2023-03-02 | March 21, 2023 | INFRA-2022-006 | INFRA-2022-006 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109254 | Froilan E. Lopez ES | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 161906.39 | BATCH 1 | 160284.24 | Completed | 1 | 2023-03-02 | 2023-03-14 | INFRA-2022-005 | INFRA-2022-005 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109255 | Kalumpang Elementary School | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 161906.39 | BATCH 1 | 160284.24 | Completed | 1 | 2023-03-02 | 2023-03-14 | INFRA-2022-005 | INFRA-2022-005 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109256 | Lalo ES | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 161906.39 | BATCH 1 | 160284.24 | Completed | 1 | 2023-03-02 | 2023-03-14 | INFRA-2022-005 | INFRA-2022-005 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109257 | Malao-A / Calantas ES | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 161906.39 | BATCH 1 | 160284.24 | Completed | 1 | 2023-03-02 | 2023-03-14 | INFRA-2022-005 | INFRA-2022-005 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109260 | Tayabas West CS II | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 161906.39 | BATCH 1 | 160284.24 | Completed | 1 | 2023-03-02 | March 14, 2023 | INFRA-2022-004 | INFRA-2022-004 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 342576 | Buenaventura Alandy NHS | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (NEW OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 163526.53 | BATCH 1 | 161886.19 | Completed | 1 | 2023-03-02 | 2023-03-14 | INFRA-2022-005 | INFRA-2022-005 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109239 | Mate ES | CITY OF TAYABAS | 1 | 1 | 1 | Construction of 4-Seater Toilet | 586069.72 | BATCH 1 | 580800.58 | Completed | 1 | 2023-03-02 | 2023-05-08 | INFRA-2022-007 | INFRA-2022-007 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108957 | SALVACION ES | AGDANGAN | 2 | 1 | 1 | Construction of School Clinic | 2540985.98 | BATCH 2 | 222197.06 | Completed | 1 | 9/28/2022 | 2022-08-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | L.A PROFUGO CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108979 | APAD ES | JOMALIG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 243416 | Completed | 1 | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108980 | BUKAL ES | JOMALIG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 243416 | Completed | 1 | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108982 | CASUGURAN ES | JOMALIG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 243416 | Completed | 1 | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108983 | GANGO ES | JOMALIG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 263912 | Completed | 1 | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108985 | Jomalig CES | JOMALIG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 257320.41 | BATCH 2 | 249821 | Completed | 1 | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 301333 | JOMALIG NHS | JOMALIG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 263912 | Completed | 1 | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 302394 | APAD JOMALIG NHS | JOMALIG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 263912 | Completed | 1 | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 301283 | MAGSAYSAY NHS (Formerly Ajos Ext.) | MULANAY | 2 | 1 | 1 | Construction of School Clinic | 2660554.56 | BATCH 2 | 263912 | Completed | 1 | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108987 | KILOGAN ELEMENTARY SCHOOL | PATNANUNGAN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 263912 | Completed | 1 | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108989 | PATNANUNGAN CENTRAL SCHOOL | PATNANUNGAN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 222920 | Completed | 1 | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108990 | PATNANUNGAN NORTE ELEMENTARY SCHOOL | PATNANUNGAN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 222920 | Completed | 1 | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108991 | SININTAN ELEMENTARY SCHOOL | PATNANUNGAN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 222920 | Completed | 1 | 9/28/2022 | 2022-09-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108992 | TAPOL ELEMENTARY SCHOOL | PATNANUNGAN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 222920 | Completed | 1 | 9/28/2022 | 2022-09-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 301374 | PATNANUNGAN NHS | PATNANUNGAN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 175668.2 | Completed | 1 | 2023-03-02 | March 21, 2023 | INFRA-2022-006 | INFRA-2022-006 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 305524 | PAARALANG SEKUNDARYA NG PATNANUNGAN NORTE | PATNANUNGAN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 160284.24 | Completed | 1 | 2023-03-02 | March 21, 2023 | INFRA-2022-006 | INFRA-2022-006 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108999 | RIZAL-MAABOT ES | PEREZ | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 236672.71 | BATCH 2 | 160284.24 | Completed | 1 | 2023-03-02 | March 14, 2023 | INFRA-2022-004 | INFRA-2022-004 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 301375 | PEREZ NHS | PEREZ | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 236672.71 | BATCH 2 | 170540.21 | Completed | 1 | 2023-03-02 | March 14, 2023 | INFRA-2022-004 | INFRA-2022-004 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 301316 | CONCEPCION NHS | PLARIDEL | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 215487.88 | BATCH 2 | 160284.24 | Completed | 1 | 2023-03-02 | March 21, 2023 | INFRA-2022-006 | INFRA-2022-006 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109051 | Cometa ES | QUEZON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 236672.71 | BATCH 2 | 160284.24 | Completed | 1 | 2023-03-02 | March 14, 2023 | INFRA-2022-004 | INFRA-2022-004 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109052 | Del Pilar ES | QUEZON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 236672.71 | BATCH 2 | 170540.21 | Completed | 1 | 2023-03-02 | March 21, 2023 | INFRA-2022-006 | INFRA-2022-006 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109053 | Guinhawa ES | QUEZON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 236672.71 | BATCH 2 | 160284.24 | Completed | 1 | 2023-03-02 | March 14, 2023 | INFRA-2022-004 | INFRA-2022-004 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109054 | Gumubat ES | QUEZON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 236672.71 | BATCH 2 | 160284.24 | Completed | 1 | 2023-03-02 | March 21, 2023 | INFRA-2022-006 | INFRA-2022-006 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 301313 | EVARISTO R. MACALINTAL MNHS (Formerly Cometa NHS) | QUEZON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 236672.71 | BATCH 2 | 160284.24 | Completed | 1 | 2023-03-02 | 2023-03-14 | INFRA-2022-005 | INFRA-2022-005 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 301314 | CESAR C. TAN MEM NHS (formerly Cometa Annex) | QUEZON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 236672.71 | BATCH 2 | 160284.24 | Completed | 1 | 2023-03-02 | 2023-03-14 | INFRA-2022-005 | INFRA-2022-005 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109122 | Don Juan Vercelos Elem. School | SAN FRANCISCO | 2 | 1 | 1 | Construction of School Clinic | 2540985.98 | BATCH 2 | 160284.24 | Completed | 1 | 2023-03-02 | 2023-03-14 | INFRA-2022-005 | INFRA-2022-005 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109149 | Rizal Elementary School | SAN NARCISO | 2 | 1 | 1 | Construction of School Clinic | 2540985.98 | BATCH 2 | 160284.24 | Completed | 1 | 2023-03-02 | 2023-03-14 | INFRA-2022-005 | INFRA-2022-005 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Clinic