## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | DUE TO | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | SCOPE | Unnamed: 45
QRF 2020 | Region IV-A | Quezon | 301366 | Nagsinamo NHS | LUCBAN | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 923093.16 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 108668 | Tagbacan Ibaba ES | CATANAUAN | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 750000 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 301303 | Calantas NHS | MACALELON | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1000000 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 108941 | San Pedro ES | MULANAY | 3 | 1 | 1 | REPAIR OF CLASSROOM | 499627.14 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109090 | Camflora ES | SAN ANDRES | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 1800000 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 308024 | Camflora National High School (Annex) | SAN ANDRES | 3 | 1 | 10 | REPAIR OF CLASSROOMS | 2271387.68 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 301306 | Camflora NHS | SAN ANDRES | 3 | 1 | 26 | REPAIR OF CLASSROOMS | 2790218.03 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 26 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109092 | Inanuran ES | SAN ANDRES | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 1773796.62 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109094 | Pansoy ES | SAN ANDRES | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 735596.83 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109114 | Aurora ES | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1708681.96 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109116 | Bayog ES | SAN FRANCISCO (AURORA) | 3 | 1 | 10 | REPAIR OF CLASSROOMS | 2258578.77 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 301309 | Casay National High School | SAN FRANCISCO (AURORA) | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 200000 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 308044 | Huyon-Uyon National High School | SAN FRANCISCO (AURORA) | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 973487.02 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 308039 | LUALHATI D. EDAÑO NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 9 | REPAIR OF CLASSROOMS | 5058311.38 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109126 | Mabuhay ES | SAN FRANCISCO (AURORA) | 3 | 1 | 9 | REPAIR OF CLASSROOMS | 4849958.19 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 302326 | Mabunga National High School | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 2550130.07 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109128 | Madagoldol ES | SAN FRANCISCO (AURORA) | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2095004.72 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 301390 | Marcial B. Villanueva NHS (Formerly San Francisco NHS, San Francisco) | SAN FRANCISCO (AURORA) | 3 | 1 | 12 | REPAIR OF CLASSROOMS | 500000 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109133 | Pugon ES | SAN FRANCISCO (AURORA) | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 1114583.22 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 301379 | Pugon NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 1 | REPAIR OF CLASSROOM | 699319.78 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 301368 | Renato Edano ES | SAN FRANCISCO (AURORA) | 3 | 1 | 15 | REPAIR OF CLASSROOMS | 1239163.34 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109134 | Tayuman Elementary School | SAN FRANCISCO (AURORA) | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1111607.26 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 301411 | Tumbaga NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 1 | REPAIR OF CLASSROOM | 150000 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109146 | Nangka ES | SAN NARCISO | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1392308.34 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109153 | San VIcente ES | SAN NARCISO | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 1760025.17 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109154 | Vigo CES | SAN NARCISO | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 522381.1 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 301284 | Alabat Island National High School | ALABAT | 4 | 1 | 6 | REPAIR OF CLASSROOMS | 816036.65 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109228 | Tabason ES | TAGKAWAYAN | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 900000 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Tanauan City | 321602 | Balele National High School | CITY OF TANAUAN | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2257184.98 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Tanauan City | 301075 | Banjo Laurel NHS | CITY OF TANAUAN | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2312048.49 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Imus City | 301190 | Gen. Emilio Aguinaldo NHS (Imus) | IMUS | 3 | 1 | 16 | TY ULYSSES | 337822.31 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Imus City | 107974 | Imus Pilot Elementary School | IMUS | 3 | 1 | 20 | TY ULYSSES | 143612.61 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Laguna | 108205 | Paciano Rizal ES | BAY | 2 | 1 | 2 | TY ULYSSES | 669527.99 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Laguna | 108311 | Mayondon Elementary School | LOS BAÑOS | 2 | 1 | 8 | TY ULYSSES | 89932.67 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Laguna | 307927 | Dayap National Integrated High School | CALAUAN | 3 | 1 | 12 | TY ULYSSES | 256638.82 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 108702 | Cablao ES | GENERAL NAKAR | 1 | 1 | 2 | TY ROLLY/QUINTA | 1666261.4847 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 302394 | Apad Jomalig National High School (Apad NHS) | JOMALIG | 1 | 1 | 9 | TY ROLLY/QUINTA | 7435608.7135 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 108986 | Katakian ES | PATNANUNGAN | 1 | 1 | 3 | TY ROLLY/QUINTA | 1067248.0882 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 301374 | Patnanungan NHS | PATNANUNGAN | 1 | 1 | 12 | TY ROLLY/QUINTA | 4632762.13 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 108552 | Siain ES | BUENAVISTA | 3 | 1 | 1 | TY ROLLY/QUINTA | 471611.1288 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 108553 | Villa Aurora ES | BUENAVISTA | 3 | 1 | 2 | TY ROLLY/QUINTA | 841649.8068 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 108696 | San Vicente ES | GENERAL LUNA | 3 | 1 | 3 | TY ROLLY/QUINTA | 755476.4023 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 108877 | Macalelon Central Elementary School | MACALELON | 3 | 1 | 3 | TY ROLLY/QUINTA | 1473519.8429 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 108918 | Acaciahan ES | MULANAY | 3 | 1 | 5 | TY ROLLY/QUINTA | 1026885.1208 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 108927 | Canuyep ES | MULANAY | 3 | 1 | 6 | TY ROLLY/QUINTA | 1256908.8576 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 108938 | Patabog ES | MULANAY | 3 | 1 | 6 | TY ROLLY/QUINTA | 4747820.6541 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 301394 | SAN ISIDRO NATIONAL HIGH SCHOOL, PADRE BURGOS | PADRE BURGOS | 3 | 1 | 13 | TY ROLLY/QUINTA | 5395013.4368 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109007 | Pitogo CS I | PITOGO | 3 | 1 | 9 | TY ROLLY/QUINTA | 2155169.6406 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109008 | Pitogo CS II | PITOGO | 3 | 1 | 11 | TY ROLLY/QUINTA | 2298863.312 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109091 | Camflora Elementary School- Annex | SAN ANDRES | 3 | 1 | 4 | TY ROLLY/QUINTA | 2960305.1483 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 308024 | Camflora National High School (Annex) | SAN ANDRES | 3 | 1 | 4 | TY ROLLY/QUINTA | 2098782.202 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109093 | Mangero Elementary School | SAN ANDRES | 3 | 1 | 6 | TY ROLLY/QUINTA | 1958316.844 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109098 | Talisay ES | SAN ANDRES | 3 | 1 | 4 | TY ROLLY/QUINTA | 2214963.773 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109116 | Bayog ES | SAN FRANCISCO (AURORA) | 3 | 1 | 10 | TY ROLLY/QUINTA | 2140731.5801 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 301298 | Dr. Vivencio V. Marquez National High School | SAN FRANCISCO (AURORA) | 3 | 1 | 6 | TY ROLLY/QUINTA | 2950995.667 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 308039 | LUALHATI D. EDAÑO NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 15 | TY ROLLY/QUINTA | 4727285.321 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109126 | Mabuhay ES | SAN FRANCISCO (AURORA) | 3 | 1 | 3 | TY ROLLY/QUINTA | 1712177.4789 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 301369 | Pagsangahan NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 8 | TY ROLLY/QUINTA | 1606393.954 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 301368 | Renato Edaño Vicencio NHS (Formerly Pagsangahan NHS-Don Juan Vercelos Annex) | SAN FRANCISCO (AURORA) | 3 | 1 | 12 | TY ROLLY/QUINTA | 3174436.7974 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 308003 | Sto. Niño National High School (Formerly Pagsangahan NHS Ext. Sto. Niño) | SAN FRANCISCO (AURORA) | 3 | 1 | 10 | TY ROLLY/QUINTA | 2285567.4959 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109134 | Tayuman Elementary School | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | TY ROLLY/QUINTA | 1903232.7235 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109136 | Viva Antipolo ES | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | TY ROLLY/QUINTA | 1969455.334 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109142 | Calwit ES | SAN NARCISO | 3 | 1 | 4 | TY ROLLY/QUINTA | 3248893.3842 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 301322 | Gregorio Reyes NHS | SAN NARCISO | 3 | 1 | 6 | TY ROLLY/QUINTA | 1526895.2989 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109149 | Rizal ES | SAN NARCISO | 3 | 1 | 3 | TY ROLLY/QUINTA | 2577000.2093 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109154 | Vigo CES | SAN NARCISO | 3 | 1 | 11 | TY ROLLY/QUINTA | 2387060.8623 | 1 |  | Completed | 1 | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109302 | Punta Elementary School | UNISAN | 3 | 1 | 5 | TY ROLLY/QUINTA | 3283133.6012 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109306 | Unisan CES | UNISAN | 3 | 1 | 3 | TY ROLLY/QUINTA | 1936317.8628 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 301414 | Unisan Integrated High School (Formerly Unisan NHS) | UNISAN | 3 | 1 | 6 | TY ROLLY/QUINTA | 2969709.897 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 108831 | Alat-alatin ES | LOPEZ | 4 | 1 | 6 | TY ROLLY/QUINTA | 3101919.5873 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 108846 | Jongo ES | LOPEZ | 4 | 1 | 5 | TY ROLLY/QUINTA | 1634469.166 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109214 | Mapulot ES | TAGKAWAYAN | 4 | 1 | 5 | TY ROLLY/QUINTA | 1870352.8615 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 308002 | Mapulot National High School | TAGKAWAYAN | 4 | 1 | 8 | TY ROLLY/QUINTA | 3894221.749 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Tanauan City | 107749 | Balele ES | CITY OF TANAUAN | 3 | 1 | 8 | TY ROLLY | 2156030 | 1 |  | Completed | 1 |  | 2023-09-11 |  |  | 2023-05-10 | 2023-05-19 | 2023-06-08 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Tanauan City | 107751 | Banjo East ES | CITY OF TANAUAN | 3 | 1 | 9 | TY ROLLY | 3599667.97 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Tanauan City | 107762 | Laurel ES | CITY OF TANAUAN | 3 | 1 | 4 | TY ROLLY | 2472980.59 | 1 |  | Completed | 1 | 2023-10-09 | 00:00:00 |  |  | 2023-05-10 | 2023-05-19 | 2023-05-30 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Tanauan City | 107764 | Mahabang Buhangin Elementary School | CITY OF TANAUAN | 3 | 1 | 4 | TY ROLLY | 2799853.68 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Tanauan City | 107767 | Maugat ES | CITY OF TANAUAN | 3 | 1 | 7 | TY ROLLY | 4029242.81 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Tanauan City | 107783 | Tapia ES | CITY OF TANAUAN | 3 | 1 | 6 | TY ROLLY | 1443834.22 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Tanauan City | 107784 | Tinurik ES | CITY OF TANAUAN | 3 | 1 | 9 | TY ROLLY | 6116147.93 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Tayabas City | 301347 | Luis Palad Integrated High School | CITY OF TAYABAS | 1 | 1 | 16 | TY QUINTA/ROLLY/ULYSSES | 1309900.7 | 1 |  | completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2022 | Region IV-A | Tanauan City | 107754 | Bilogbilog Elementary School | CITY OF TANAUAN | 3 | 1 | 9 | REPAIR/ REHABILITATION | 8175554.7148 | 1 |  | completed | 1 |  | 00:00:00 | [8 empty] | with RTA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region IV-A | Batangas | 107225 | Balayan East Central School | BALAYAN | 1st | 1 | 6 | Replacement | 22500000 | 1 | 20082720.48 | COMPLETED | 1 | 2024-01-07 | 2024-09-09 | QRF 2023-BATANGAS-IVA-01 | QRF 2023-BATANGAS-IVA-01 | 2023-07-08 | 8/15/2023 | 8/23/2023 | 9/29/2023 | 10/27/2023 | AB San Lorenzo Construction and Supply Company | Delayed due to contractor's fault | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 3.25 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | Region IV-A | Quezon | 108561 | BURDEOS CENTRAL SCHOOL | BURDEOS | 1st | 1 | 15 | REPAIR OF CLASSROOMS | 10337287.3043 | 1 | 10323137 | COMPLETED | 1 | 2023-11-07 | 8/14/2023 |  | QRF 2023-QUEZON-IVA-01 | 2023-03-02 | 2023-10-02 | 2/22/2023 | 2023-06-03 | 3/14/2023 | L.A. Profugo Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 1 | 0 |  | 9.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 REPLENISHMENT | Region IV-A | Quezon | 301334 | BURDEOS NHS (Formerly JUDITH NHS) | BURDEOS | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 2782893.1751 | 1 | 2778600 | COMPLETED | 1 | 2023-11-07 | 2023-05-07 |  | QRF 2023-QUEZON-IVA-02 | 2023-03-02 | 2023-10-02 | 2/22/2023 | 2023-06-03 | 3/14/2023 | C.G. Cabana Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 9.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 REPLENISHMENT | Region IV-A | Quezon | 301361 | PSHN | GEN. NAKAR | 1st | 1 | 18 | REPAIR OF CLASSROOMS | 11175657.489 | 1 | 11155714.06 | COMPLETED | 1 | 7/17/2023 | 2023-03-07 |  | QRF 2023-QUEZON-IVA-03 | 2023-03-02 | 2023-10-02 | 2/22/2023 | 3/13/2023 | 3/14/2023 | M.G. Villamin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 1 | 0 |  | 9.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 REPLENISHMENT | Region IV-A | Quezon | 109045 | POLILLO CENTRAL ES | POLILLO | 1st | 1 | 15 | REPAIR OF CLASSROOMS | 9054870.0763 | 1 | 9041896 | COMPLETED | 1 | 2023-11-07 | 8/25/2023 | QRF 2023-QUEZON-IVA-04 | QRF 2023-QUEZON-IVA-04 | 2023-03-02 | 2023-10-02 | 2/22/2023 | 2023-06-03 | 3/14/2023 | C.G. Cabana Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 1 | 0 |  | 9.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 REPLENISHMENT | Region IV-A | Quezon | 301377 | POLILLO NHS | POLILLO | 1st | 1 | 43 | REPAIR OF CLASSROOMS | 12907120.9512 | 1 | 12850000 | COMPLETED | 1 | 8/16/2023 | 9/16/2023 | QRF 2023-QUEZON-IVA-05 | QRF 2023-QUEZON-IVA-05 | 2023-03-02 | 2023-10-02 | 2/22/2023 | 3/13/2023 | 3/20/2023 | Botey Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 43 | 1 | 0 |  | 9.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2023 | Region IV-A | Dasmarinas City | 107908 | Paliparan III ES | CITY OF DASMARIÑAS | 4th | 1 | 6 | REPAIR OF CLASSROOMS | 2637865.5 | 2-R | 1822725.3 | Completed | 1 | 9/30/2024 | 2024-10-09 | CY2023 QRF Batch 2 RRC | CY2023 QRF Batch 2 RRC | March 13, 2024- | 3/21/2024 | 2024-03-04 | 2024-03-05 | 2024-03-06 | Open Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 11.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region IV-A | Tanauan City | 107749 | Balele ES | CITY OF TANAUAN | 3 | 1 | 9 | REPAIR OF CLASSROOMS | 1800000 | 1 | 1423774.38 | Completed | 1 | 10/28/2023 | 2023-11-09 |  |  | 2023-10-05 | 5/19/2023 | 2023-08-06 | 2023-07-07 | 7/21/2023 | open builders corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | 9.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 107753 | Bernardo Lirio Memorial Central School | CITY OF TANAUAN | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 800000 | 1 | 790492.18 | Completed | 1 | 10/28/2023 | 8/30/2023 |  |  | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | gs motar builders construction and trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 9.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 301089 | Boot NHS | CITY OF TANAUAN | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 800000 | 1 | 790298.94 | Completed | 1 | 10/28/2023 | 9/14/2023 |  |  | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | gs motar builders construction and trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 9.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 321603 | Janopol Oriental National High School | CITY OF TANAUAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 400000 | 1 | 391219.74 | Completed | 1 | 10/28/2023 | October 19,2023 |  |  | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | gs motar builders construction and trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 9.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 107762 | Laurel ES | CITY OF TANAUAN | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1186282.19 | Completed | 1 | 2023-09-10 | October 19,2023 |  |  | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | MG VILLAMIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 11.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 301113 | Luyos National High School | CITY OF TANAUAN | 3 | 1 | 9 | REPAIR OF CLASSROOMS | 1800000 | 1 | 1782547.48 | Completed | 1 | 2023-09-10 | October 19,2023 |  |  | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | 11.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 107765 | Malaking Pulo ES | CITY OF TANAUAN | 3 | 1 | 8 | REPAIR OF CLASSROOMS | 1600000 | 1 | 1583362.61 | Completed | 1 | 2023-09-10 | October 19,2023 |  |  | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | 11.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 301119 | Malaking Pulo National High School | CITY OF TANAUAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 400000 | 1 | 390711.09 | Completed | 1 | 10/28/2023 | October 19,2023 |  |  | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 9.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 107770 | Pagaspas ES | CITY OF TANAUAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 400000 | 1 | 391587.77 | Completed | 1 | 10/28/2023 | 8/20/2023 |  |  | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | MG VILLAMIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 9.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 301138 | Pres. Jose P. Laurel National High School | CITY OF TANAUAN | 3 | 1 | 7 | REPAIR OF CLASSROOMS | 1400000 | 1 | 1387885.25 | Completed | 1 | 2023-09-10 | October 19,2023 |  |  | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | 11.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 107779 | Suplang Elementary School | CITY OF TANAUAN | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1180052.23 | Completed | 1 | 10/28/2023 | 9/18/2023 |  |  | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 9.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 301159 | Tinurik National High School | CITY OF TANAUAN | 3 | 1 | 8 | REPAIR OF CLASSROOMS | 1600000 | 1 | 1584414.37 | Completed | 1 | 2023-09-10 | October 19,2023 |  |  | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | MG VILLAMIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | 11.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 500867 | Ulango Integrated School | CITY OF TANAUAN | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1189951.19 | Completed | 1 | 2023-09-10 | October 19,2023 |  |  | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | MG VILLAMIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 11.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 107787 | Wawa ES | CITY OF TANAUAN | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1188805.92 | Completed | 1 | 10/28/2023 | 9/20/2023 |  |  | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | gs motar builders construction and trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 9.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 321603 | Janopol Oriental National High School | CITY OF DASMARIÑAS | 3rd | 1 | 6 | REPAIR OF CLASSROOMS | 8500000 | 2-R | 8483174.9 | Completed | 1 | 5/16/2024 | 5/19/2024 |  |  | 2023-10-05 | 11/30/2023 | 12/13/2023 | 2024-05-01 | 1/19/2024 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 12.23 |  |  |  |  | REPAIR | Completed