## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No. of Sites | Elem. Individual Learner Table & Chair Set | JHS Individual Learner Table & Chair Set | SHS Individual Learner Table & Chair Set | Total Individual Learner Table & Chair Set | Teacher's Table & Chair Set | Science Laboratory Table & Stool Set | Working Table & Stool Set | Approved Budget for Contract | Implementing Unit | Legend | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Supplier | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Sets Reverted | No. of Sets Not yet started | No. of Sets Under Procurement | No. of Sets On Going | No. of Sets Completed | No. of Sets Terminated | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed
CY 2023 SF | REGION IV-A | Antipolo City | 301420 | Dalig Nhs To Cupang Nhs | City Of Antipolo | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | REGION IV-A | Bacoor City | 107890 | Talaba Elementary School | BACOOR | 2nd | 1 | 720 | - | - | 720 | 16 | - | - | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 1
CY 2023 SF | REGION IV-A | Laguna | 307940 | Sta. Maria NHS - Calangay Annex | SANTA MARIA | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | REGION IV-A | Tayabas City | 109258 | Potol ES | CITY OF TAYABAS | 1st | 1 | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1