## Sheet1
Region | Division | School ID | School Name | Municipality | Leg District | No. of Sites | Scope of Work | Total Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | Municipality Classification
Region IV-B | Occidental Mindoro | 301596 | Sablayan National Comprehensive High School | SABLAYAN | Lone | 1 | PROPOSED TWO (2) - STOREY ALTERNATIVE LEARNING SYSTEM (ALS) BUILDING (22.50m x 9.50m) - with Roof Deck | 16540705.31 | 16458637.91 | ongoing | 0.9 | April 10, 2025 | April 15,2025 | DepEd-OccMdo-2024-05 |  | May 31, 2024 | June 10 2024 | June 24, 2024 | June 28, 2024 | June 19, 2024 | hawkstow construction and development | actual target completion was adjusted due to contractor request for extension regarding weather condition | 0 | 0 | 0 | 1 | 0 | 0.83 | 0.07 |  |  | 1st