## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | NO. OF CL | SCOPE OF WORK | PROJECT ALLOCATION | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated/ Abandoned | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of CL Terminated/ Abandoned | No. of Sites Reverted.1 | No. of Sites Not yet started.1 | No. of Sites Under Procurement.1 | No. of Sites On Going.1 | No. of Sites Completed.1 | No. of Sites Terminated/ Abandoned.1 | Previous % | Difference | Month Completed | OGP SCHOOLS with DCP Packages | TO BE COMPLETED BY 2023 | TO BE COMPLETED BY 2023.1 | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | BBM ADMINISTRATION | Batch | Municipality Class | Provision of Solar Panel | STATUS.1
LMS 2020 | Region IV-B | Marinduque | 109901 | Tambunan ES | BOAC (Capital) | 0 | 1 | 4 | PROPOSED CONSTRUCTION OF 1STY4CL SCHOOL BLDG (WITH COMMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20455972.2891 | 0 | Completed | 1 | 2022-08-15 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1 | Completed
LMS 2020 | Region IV-B | Oriental Mindoro | 110339 | Mamalao Mangyan School | BACO | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND SOLAR PV ENERGY SYSTEM | 20188286.0327 | 20087944.35 | completed | 1 | April 05, 2022 | March 07, 2022 | LMS 2020 - R IV-B - Oriental Mindoro - 001 | 015-2021 | July 06, 2021 | July 14, 2021 | July 26, 2021 | Aug. 11, 2021 | Aug. 31, 2021 | CMSEL Construction and Developer | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1 | completed
LMS 2020 | Region IV-B | Oriental Mindoro | 170036 | Bailan ES | BULALACAO (SAN PEDRO) | 2 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND SOLAR PV ENERGY SYSTEM | 19229984.4143 | 18180121.46 | Completed | 1 | June 15, 2022 | June 14, 2022 | LMS 2020 - R IV-B - Oriental Mindoro - 002 | 019-2021 | July 06, 2021 | July 14, 2021 | July 26, 2021 | Aug. 11, 2021 | Sept. 03, 2021 | Orient Star Construction Inc. | with contract time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1 | Completed
LMS 2020 | Region IV-B | Puerto Princesa City | 111525 | Nasuduan ES | Puerto Princesa City | 3 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19185222.7994 | 17849626.85 | Completed | 1 | May 19, 2022 Revised: June 18, 2022 | 2022-06-15 | 0 | INFRA 2021-03 | July 27,2021 | August 3,2021 | 2021-08-16 | Sept. 10, 2021 | Sept. 14, 2021 | Maryknoll Builders and Supply | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1 | Completed
LMS 2021 | Region IV-B | CALAPAN CITY | 111547 | Silonay ES | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE | 8578776.11 | 8479929.95 | ON-GOING | 0.9 | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | 2021-AdmS4(006)-BI-CB-013a-C200 | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | 2022-01-25 | WERR COPR. INTL. JV. WITH BANCAL CONST, & SUPPLY | SCHOOL FURNITURE NOT YET DELIVERED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2.25 |  | 0 | 1 | [6 empty] | 0 | completed
LMS 2021 | Region IV-B | CALAPAN CITY | 111547 | Silonay ES | CITY OF CALAPAN (Capital) | 1 |  | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE | 5719184.08 | 8479929.95 | ON-GOING | 0.9 | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | 2021-AdmS4(006)-BI-CB-013a-C200 | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | 2022-01-25 | WERR COPR. INTL. JV. WITH BANCAL CONST, & SUPPLY | SCHOOL FURNITURE NOT YET DELIVERED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 6.23 | [6 empty] | CY 2023 |  |  | 0 | COMPLETED
LMS 2021 | Region IV-B | Marinduque | 109922 | Bacongbacong PS | Gasan | 0 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), AND WATER SYSTEM | 12631518.4833 | 0 | Ongoing | 0.62 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.62 | 0 |  |  | 1 | [7 empty] | 0 | Ongoing
LMS 2021 | Region IV-B | Occidental Mindoro | 110128 | EMOK ES | MAGSAYSAY | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18796598.3373 | 0 | terminated (implemented by C.O) | 0.1582 | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1582 | 0 |  |  | 0 | 1 | [6 empty] | 1 | Terminated
LMS 2021 | Region IV-B | Palawan | 305600 | Tabon National High School | Quezon | 2 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18320194.7555 | 0 | Abandoned (implemented by C.O) | 0.2 | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 |  |  | 0 | 1 | [6 empty] | 1 | Abandoned
LMS 2022 | Region IV-B | Palawan | 110744 | Maracañao Elementary School | AGUTAYA | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20470791.2919 | 20622113.46 | Completed | 1 | 2023-12-26 | 00:00:00 | LMS 2023 - MIMAROPA - ORIENTAL MINDORO - 002 | LMS 05-2023 | 2023-04-19 | 2023-04-27 | 2023-05-10 | 2023-05-19 | 2023-05-26 | CMSEL CONST. AND DEVELOPER | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.24 |  | 1 |  |  |  |  | CY 2024 |  |  | 1 | Completed
LMS 2022 | Region IV-B | Romblon | 111254 | Agbay-Ang ES | ALCANTARA | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND SLOPE PROTECTION | 19037682.2232 | 21050000 | Completed | 1 | 2024-01-25 | 00:00:00 | LMS 2023 - MIMAROPA - ORIENTAL MINDORO - 001 | LMS 04-2023 | 2023-04-19 | 2023-04-27 | 2023-05-10 | 2023-05-18 | 2023-05-26 | A.D.L. CONSTRAK OPC | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 9.24 |  | 1 | [7 empty] | 1 | Completed
LMS 2023 | Region IV-B | Oriental Mindoro | 130206 | Mungos Mangyan Elementary School | BONGABONG | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 20880049.26 | 20622113.46 | Completed | 1 | 2023-12-26 | 2023-12-20 | LMS 2023 - MIMAROPA - ORIENTAL MINDORO - 002 | LMS 05-2023 | 2023-04-19 | 2023-04-27 | 2023-05-10 | 2023-05-19 | 2023-05-26 | CMSEL CONST. AND DEVELOPER | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.24 | - | 1 |  |  |  |  | CY 2024 | 1 |  | 1 | Completed
LMS 2023 | Region IV-B | Oriental Mindoro | 136953 | Naswak Hatubuan Bangon Elementary School | BONGABONG | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 21303170.78 | 21050000 | Completed | 1 | 2024-01-25 | 2024-01-19 | LMS 2023 - MIMAROPA - ORIENTAL MINDORO - 001 | LMS 04-2023 | 2023-04-19 | 2023-04-27 | 2023-05-10 | 2023-05-18 | 2023-05-26 | A.D.L. CONSTRAK OPC | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.24 | - | 1 |  |  |  |  | CY 2024 | 1 |  | 1 | Completed
LMS 2023 | Region IV-B | Oriental Mindoro | 137123 | Cambayang Elementary School | BULALACAO (SAN PEDRO) | 2 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE | 14291013.26 | 14120000 | Completed | 1 | 2023-12-26 | 2024-12-02 | LMS 2023 - MIMAROPA - ORIENTAL MINDORO - 003 | LMS 06-2023 | 2023-04-19 | 2023-04-27 | 2023-05-10 | 2023-05-20 | 2023-05-26 | A.D.L. CONSTRAK OPC | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.24 | - | 1 |  |  |  |  | CY 2024 | 1 |  | 0 | Completed
LMS 2023 | Region IV-B | Puerto Princesa City | 171501 | Manggapin Elementary School | PUERTO PRINCESA CITY (Capital) | 2nd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM AT MANGGAPIN ELEMENTARY SCHOOL | 22354334.98 | 22131576 | Completed | 1 | July 25, 2024 Revised: August 23, 2024 | Aug. 26, 2024 | INFRA 2023-10-03 | INFRA 2023-10-03 | Oct. 25, 2023 | Oct. 31, 2023 | Nov. 13, 2023 | Nov. 16, 2023 | Nov. 21, 2023 | Maryknoll Builders and Supply | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.9 | 0.1 |  |  | 0 | [5 empty] | 2 |  | 1 | ongoing
LMS 2024 | Region IV-B | Oriental Mindoro | 137017 | Magdayaga Elementary School | Bongabong | 2nd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 21109748.66 | 20837923.61 | Completed | 1 | 2025-01-25 | 2023-12-20 | LMS 2024 - MIMAROPA - ORIENTAL MINDORO - 003 | LMS 15-2024 | Nov. 29, 2023 | Dec. 7, 2023 | Dec. 20, 2023 | Jan. 4, 2024 | May 20, 2024 | CMSEL CONST. AND DEVELOPER | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.25 | [8 empty] | 1st | 1 | Completed
LMS 2024 | Region IV-B | Oriental Mindoro | 306032 | Bailan Katutubong Mangyan High School | Bulalcao | 2nd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 21994317.96 | 21725000 | Completed | 1 | 2025-05-27 | 2025-05-23 | LMS 2024 - MIMAROPA - ORIENTAL MINDORO - 002 | LMS 14-2024 | Nov. 29, 2023 | Dec. 7, 2023 | Dec. 20, 2023 | Jan. 4, 2024 | May 20, 2024 | A.D.L. CONSTRAK OPC | With contract time extensions due to frequent rains and armed conflict. Final payment on process. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.86 | 0.14 | [9 empty] | 1st | 1 | ONGOING
LMS 2024 | Region IV-B | Oriental Mindoro | 137102 | EM Fabella-Ansaldo Elementary School | Roxas | 2nd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 20756365.76 | 20230000 | Completed | 1 | 2025-01-25 | 2024-12-03 | LMS 2024 - MIMAROPA - ORIENTAL MINDORO - 001 | LMS 13-2024 | Nov. 29, 2023 | Dec. 7, 2023 | Dec. 20, 2023 | Jan. 4, 2024 | May 20, 2024 | A.D.L. CONSTRAK OPC | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.25 | [8 empty] | 1st | 1 | Completed
LMS 2024 | Region IV-B | Palawan | 111056 | Batang-Batang Beach Elementary School | NARRA | 2nd | 1 | 4 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 17171717.17 | 15827000 | ONGOING | 0.15 | 2025-10-22 | 00:00:00 | 2024-01-001_INFRA | 2025-03-001 | 2024-11-15 | 2024-11-26 | 2024-11-29 | 2025-12-16 | 2025-03-26 | Maryknoll Builders & Ssupply | NEGOTIATED PROCUREMENT | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.15 | 0 | [9 empty] | 1st | 1 | ONGOING
LMS 2024 | Region IV-B | Puerto Princesa City | 111511 | Cabayugan ES - Sugod Extension | PUERTO PRINCESA CITY (Capital) | 3rd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 21248071.44 | 20966655 | ONGOING | 0.5 | May 18, 2025 | 00:00:00 | LMS 2024 - MIMAROPA - PUERTO PRINCESA CITY - 002 | INFRA 2024-07-005 | 2024-06-25 | 2024-07-01 | July 15, 2024 | July 23, 2024 | Sept. 19, 2024 | Maryknoll Builders & Ssupply | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.5 | 0 | [9 empty] | 4th | 1 | ONGOING
LMS 2024 | Region IV-B | Puerto Princesa City | 111520 | Makirawa ES | PUERTO PRINCESA CITY (Capital) | 3rd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 20830359.96 | 20620761 | Completed | 1 | January 15, 2025 | 00:00:00 | LMS 2024 - MIMAROPA - PUERTO PRINCESA CITY - 001 | INFRA 2023-11-04 | Nov. 22, 2023 | Nov. 28, 2023 | Dec. 11, 2023 | Dec. 22, 2023 | May 13, 2024 | Joint Venture of Ian Jason Construction & Supply and RBM2 Construction | For Final Inspection | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | [9 empty] | 1st | 1 | Ongoing
LMS 2024 | Region IV-B | Romblon | 171008 | Palati PS | ODIONGAN | Lone | 1 | 3 | LMSP - PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND SOLAR PV ENERGY SYSTEM | 19645773.82 | 0 | ONGOING | 0.7977 | 00:00:00 | 00:00:00 | INF-LMS-2024-01 | INF-LMS-2024-01 | 2023-11-14 | 2023-11-21 | 2023-12-05 | 2024-01-29 | 2024-05-22 | RMR Construction and Trading | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.65 | 0.1477 | [9 empty] | 1st | 1 | ONGOING
LMS 2024 | Region IV-B | Romblon | 111437 | Layag Cultural Minority School | SAN FERNANDO | Lone | 1 | 2 | LMSP - PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND SOLAR PV ENERGY SYSTEM | 15486264.53 | 0 | ONGOING | 0.4 | 00:00:00 | 00:00:00 | INF-LMS-2024-02 | INF-LMS-2024-02 | 2023-11-14 | 2023-11-21 | 2023-12-05 | 2024-01-29 | 2024-05-22 | RMR Construction and Trading | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.4 | 0 | [9 empty] | 1st | 1 | ONGOING