## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | No. of Classrooms | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of CL Terminated | Previous % | Difference | STOREY | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original)
NEWCON 2016 | REGION VIII | Baybay City | 313316 | Baybay City Nat'L Night Hs | City Of Baybay | 5 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8770000 |  |  | Completed | 1 |  |  | P00073919VS-CW1 | 16IG0074 | Oct. 19-25, 2016 | Oct. 26, 2018 | 2016-11-08 | Nov. 21, 2016 | 42795 | LADY OF ASSUMPTION ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Baybay City | 313316 | Baybay City Nat'L Night Hs | City Of Baybay | 5 |  | 4 | 2STY4CL | BATCH 9 CL | 6730000 |  |  | Completed | 1 |  |  | P00073920VS-CW1 | 16IG0075 | Oct. 19-25, 2016 | Oct. 26, 2018 | 2016-11-08 | Nov. 21, 2016 | 42795 | LADY OF ASSUMPTION ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Baybay City | 303348 | Baybay Nhs | City Of Baybay | 5 | 1 | 8 | 2STY8CL | BATCH 13 CL | 12010076.849 |  |  | Completed | 1 |  |  | P00075855VS-CW1 | 17IG0082 | March 14-20, 2016 | 2016-03-21 | 2017-04-04 | Aug. 4, 2017 | 42956 | PABLO S. LABASBAS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Baybay City | 303348 | Baybay Nhs | City Of Baybay | 5 |  | 3 | 1STY3CL | BATCH 13 CL | 2960000 |  |  | Completed | 1 |  |  | P00075856VS-CW1 | 16IG0087 | Dec. 2-8, 2016 | Dec.9, 2016 | 2016-12-22 | Jan. 24, 2017 | 42769 | R.S. REYNA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VIII | Baybay City | 303349 | Bitanhuan Nhs | City Of Baybay | 5 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1990000 |  |  | Completed | 1 |  |  | P00073921VS-CW1 | 16IG0027 | May 31-June 6, 2016 | 2016-06-07 | 2016-06-21 | 2016-06-04 | 42559 | R.AGULLO CONSTRUCTION & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Baybay City | 303360 | Caridad Nhs | City Of Baybay | 5 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12010076.8509 |  |  | Completed | 1 |  |  | P00073922VS-CW1 | 16IG0080 | Nov. 11-17, 2016 | Nov. 18, 2016 | 2016-12-01 | Decmber 7, 2016 | 42755 | JUCONS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Baybay City | 303360 | Caridad Nhs | City Of Baybay | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2477000 |  |  | Completed | 1 |  |  | P00074572VS-CW1 | 16IG0032 | june 29-july 5, 2016 | 2016-07-06 | 2016-07-21 | 2016-08-08 | 42592 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Baybay City | 313323 | Ciabu Nhs | City Of Baybay | 5 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8770000 |  |  | Completed | 1 |  |  | P00073923VS-CW1 | 16IG0044 | July 21-27, 2016 | 2016-06-28 | 2016-08-18 | 2016-10-25 | 42671 | RJIR ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Baybay City | 313323 | Ciabu Nhs | City Of Baybay | 5 |  | 4 | 2STY4CL | BATCH 9 CL | 6730000 |  |  | Completed | 1 |  |  | P00073924VS-CW1 | 16IG0043 | July 21-27, 2016 | 2016-06-28 | 2016-08-18 | 2016-10-25 | 42751 | JUCONS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Baybay City | 313323 | Ciabu Nhs | City Of Baybay | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2497000 |  |  | Completed | 1 |  |  | P00074573VS-CW1 | 16IG0031 | june 29-july 5, 2016 | 2016-07-06 | 2016-07-21 | Auugust 5, 2016 | 42594 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Baybay City | 121079 | Lintaon Es To Baybay I Cs | City Of Baybay | 5 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2030000 |  |  | Completed | 1 |  |  | P00073925VS-CW1 | 16IG0024 | Sept. 21-27, 2016 | Sept. 28, 2016 | 2016-10-11 | Nov. 11, 2016 | 42697 | KRC CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Baybay City | 121145 | Mahayahay Es To Marcos Es | City Of Baybay | 5 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1040000 |  |  | Completed | 1 |  |  | P00073926VS-CW1 | 16IG0029 | Sept. 21-27, 2016 | Sept. 28, 2016 | 2016-10-11 | Nov. 11, 2016 | 42671 | JUCONS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Baybay City | 313312 | Mailhi Nhs | City Of Baybay | 5 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3870000 |  |  | Completed | 1 |  |  | P00073927VS-CW1 | 16IG0035 | june 29-july 5, 2016 | 2016-07-06 | 2016-07-21 | 2106-08-11 | 42599 | KAUIE BUILDERS AND CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Baybay City | 313312 | Mailhi Nhs | City Of Baybay | 5 |  | 3 | 1STY3CL | BATCH 9 CL | 2960000 |  |  | Completed | 1 |  |  | P00073928VS-CW1 | 16IG0028 | May 31-June 6, 2016 | 2016-06-07 | 2016-06-21 | 2016-06-04 | 42559 | CIRCLE Z VENTURES & DEV. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VIII | Baybay City | 303419 | Plaridel Nhs | City Of Baybay | 5 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13460000 |  |  | Completed | 1 |  |  | P00073929VS-CW1 | 16IG0042 | July 21-27, 2016 | 2016-06-28 | 2016-08-18 | Nov. 21, 2016 | 42893 | LADY OF ASSUMPTION ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Baybay City | 303419 | Plaridel Nhs | City Of Baybay | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2477000 |  |  | Completed | 1 |  |  | P00074574VS-CW1 | 16IG0051 | Aug. 10-16, 2016 | 2016-08-17 | 2016-08-30 | Sept. 14, 2016 | 42634 | JUCONS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Baybay City | 303420 | Pomponan Nhs | City Of Baybay | 5 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2030000 |  |  | Completed | 1 |  |  | P00073930VS-CW1 | 16IG0025 | May 31-June 6, 2016 | 2016-06-07 | 2016-06-21 | 2016-06-04 | 42559 | R.AGULLO CONSTRUCTION & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Baybay City | 303420 | Pomponan Nhs | City Of Baybay | 5 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4974000 |  |  | Completed | 1 |  |  | P00074575VS-CW1 | 16IG0034 | Aug. 2-8, 2016 | Aug. 9, 2016 | 2016-08-23 | Sept. 5, 2016 | 42621 | JA ACHACOSO ENT. & GENERAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Baybay City | 121092 | San Isidro Es | City Of Baybay | 5 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1990000 |  |  | Completed | 1 |  |  | P00073931VS-CW1 | 16IG0026 | May 31-June 6, 2016 | 2016-06-07 | 2016-06-21 | 2016-06-04 | 42559 | R.S. REYNA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Baybay City | PSA328552 | Stand Alone 1 (Baybay Nhs) | City Of Baybay | 5 | 1 | 24 | 2STY12CL | BATCH 9 CL | 32204277.7955 |  |  | Completed | 1 |  |  | P00073932VS-CW1 | 16IG0076 | Oct. 19-25, 2016 | Oct. 26, 2018 | 2016-11-08 | Nov. 24, 2016 | 42824 | HIGH-INNOVATIVE CONST. & DEV. PHILS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VIII | Baybay City | PSA328552 | Stand Alone 1 (Baybay Nhs) | City Of Baybay | 5 |  | 16 | 2STY8CL | BATCH 9 CL | 24020153.7017 |  |  | Completed | 1 |  |  | P00073933VS-CW1 | 16IG0077 | Nov. 4 - Dec. 1 , 2016 | Dec. 2, 2016 | 2016-12-16 | 2017-03-29 | 42831 | RJIR ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VIII | Baybay City | PSA328552 | Stand Alone 1 (Baybay Nhs) | City Of Baybay | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2477000 |  |  | Completed | 1 |  |  | P00074576VS-CW1 | 16IG0033 | june 29-july 5, 2016 | 2016-07-06 | 2016-07-21 | Auugust 5, 2016 | 42592 | VICTORIA DEV. & CONST. SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Biliran | 303319 | Almeria Nhs | Almeria | 0 | 1 | 6 | 2STY6CL | BATCH 11 CL | 8600000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Biliran | 303320 | Biliran Nahs | Biliran | 0 | 1 | 12 | 2STY6CL | BATCH 3 CL | 17500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Biliran | 303320 | Biliran Nahs | Biliran | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 5350000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Biliran | 303322 | Cabucgayan Nsat | Cabucgayan | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12080076.8509 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Biliran | 303322 | Cabucgayan Nsat | Cabucgayan | 0 |  | 6 | 2STY6CL | BATCH 9 CL | 8760000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Biliran | 303322 | Cabucgayan Nsat | Cabucgayan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2517000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Biliran | 303324 | Culaba Nvs | Culaba | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2520000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Biliran | 313203 | Ict High School Of Eastern Biliran | Caibiran | 0 | 1 | 20 | 2STY10CL | BATCH 9 CL | 23168358.1675 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VIII | Biliran | 313203 | Ict High School Of Eastern Biliran | Caibiran | 0 |  | 6 | 2STY6CL | BATCH 9 CL | 8780000 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION VIII | Biliran | 313203 | Ict High School Of Eastern Biliran | Caibiran | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2517000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Biliran | 303328 | Manlabang Nhs | Caibiran | 0 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11596000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Biliran | 303329 | Maripipi Nvs | Maripipi | 0 | 1 | 8 | 2STY8CL | BATCH 13 CL | 12250076.849 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Biliran | 303330 | Naval National High School | Naval (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2507000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Biliran | 303330 | Naval National High School | Naval (Capital) | 0 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11965076.849 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Biliran | 303330 | Naval National High School | Naval (Capital) | 0 |  | 3 | 1STY3CL | BATCH 13 CL | 3087851.684 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VIII | Biliran | 303331 | Naval School Of Fisheries | Naval (Capital) | 0 | 1 | 12 | 2STY12CL | BATCH 9 CL | 16092138.8978 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Biliran | 303331 | Naval School Of Fisheries | Naval (Capital) | 0 |  | 10 | 2STY10CL | BATCH 9 CL | 14088441.1023 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VIII | Biliran | 303331 | Naval School Of Fisheries | Naval (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2462000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Biliran | 303333 | Tucdao Nhs | Kawayan | 0 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2161466.644 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Biliran | 303333 | Tucdao Nhs | Kawayan | 0 |  | 1 | 1STY1CL | BATCH 13 CL | 1223294.659 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Borongan City | 122370 | Balacdas Ps | City Of Borongan (Capital) | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Borongan City | 313504 | Benowangan Nhs (Lalawigan Nhs - Benowangan Annex) | City Of Borongan (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6482000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Borongan City | 122400 | Canyupay Es | City Of Borongan (Capital) | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Borongan City | 303500 | E. Samar Nchs | City Of Borongan (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2512768.1307 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Borongan City | 313515 | E. Samar Nchs - Supt. Fidel E. Anacta, Sr. Mhs Annex | City Of Borongan (Capital) | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11095000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Borongan City | 313515 | E. Samar Nchs - Supt. Fidel E. Anacta, Sr. Mhs Annex | City Of Borongan (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2472000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Borongan City | 122402 | Hebacong Es | City Of Borongan (Capital) | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1170000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Borongan City | 303511 | Lalawigan Nhs | City Of Borongan (Capital) | 0 | 1 | 6 | 3STY6CL | BATCH 9 CL | 9460418.359 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Borongan City | 303511 | Lalawigan Nhs | City Of Borongan (Capital) | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4880666.6667 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Borongan City | 303526 | Maypangdan Nhs | City Of Borongan (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15171327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VIII | Borongan City | 303526 | Maypangdan Nhs | City Of Borongan (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2433666.6667 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Borongan City | 303525 | Sta. Fe Nhs | City Of Borongan (Capital) | 0 | 1 | 6 | 3STY6CL | BATCH 9 CL | 9450418.359 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Borongan City | 303525 | Sta. Fe Nhs | City Of Borongan (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2447000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Borongan City | 122364 | Suhotan Ps To Siha Es | City Of Borongan (Capital) | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1110000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Calbayog City | 124134 | Cag-Olango Elementary School | Calbayog City | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864816.26 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Calbayog City | 313801 | Calbayog City National High School | Calbayog City | 1 | 1 | 40 | 4STY20CL | BATCH 11 CL | 62205780.54 |  |  | Completed | 1 |  |  |  | 17IJ-0092 |  |  |  | 2017-07-11 | 42937 | JVCD JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION VIII | Calbayog City | 313801 | Calbayog City National High School | Calbayog City | 1 |  | 4 | 1STY4CL | BATCH 11 CL | 3667968.78 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION VIII | Calbayog City | 313803 | Calbayog City Night High School | Calbayog City | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10882042.74 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Calbayog City | 124086 | Canjumadac Elementary School | Calbayog City | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2982437.766 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VIII | Calbayog City | 123992 | Cogon Elementary School | Calbayog City | 1 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1224580.0817 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Calbayog City | 123992 | Cogon Elementary School | Calbayog City | 1 |  | 2 | 1STY2CL | BATCH 9 CL | 1744744.436 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Calbayog City | 313808 | Dawo Integrated School | Calbayog City | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2051297.908 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Calbayog City | 124095 | Hibuhatan Elementary School | Calbayog City | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6673289.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Calbayog City | 124015 | Higasaan Primary School | Calbayog City | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2982437.766 |  |  | Completed | 1 |  |  |  | 16IJ-0102 |  |  |  | 2017-11-03 | 43049 | VCD |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VIII | Calbayog City | 124016 | Himalandrog Elementary School | Calbayog City | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2982437.766 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VIII | Calbayog City | 124017 | Looc Elementary School | Calbayog City | 1 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1146385.163 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Calbayog City | 313810 | Malaga Nhs - Caglanipao Sur Annex School | Calbayog City | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864816.28 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Calbayog City | 313811 | Malaga Nhs-Pena I Annex School | Calbayog City | 1 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6373289.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Calbayog City | 124025 | San Antonio Primary School | Calbayog City | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2051297.908 |  |  | Completed | 1 |  |  |  | 16IJ-0121 |  |  |  | 2017-11-03 | 43049 | VCD |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Calbayog City | 303651 | San Policarpo National High School | Calbayog City | 1 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20029495.669 |  |  | Completed | 1 |  |  |  | 16IJ-0065 |  |  |  | 2017-05-16 | 42881 | B. VICENCIO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Calbayog City | 313814 | Seven Hills National High School | Calbayog City | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2051297.908 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Calbayog City | 313807 | Tabawan Integrated School | Calbayog City | 1 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6936271.404 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122746 | A-Et Elementary School | Sulat | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122324 | Aguinaldo Elementary School | Arteche | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1190000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122671 | Alang-Alang Elementary School | Quinapondan | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122672 | Anislag Elementary School | Quinapondan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2153800 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303494 | Arteche National High School | Arteche | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2726593.2584 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122408 | Balagon Elementary School | Can-Avid | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2153800 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303495 | Balangkayan National High School | Balangkayan | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11075000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303495 | Balangkayan National High School | Balangkayan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2462000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122655 | Balingasag Elementary School | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2038000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122608 | Bangon Elementary School | Balangkayan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1998000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122735 | Bangon Elementary School | San Policarpo | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2108000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122656 | Batang Elementary School | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2028000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122657 | Bato Ps | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1939000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122760 | Beto Elementary School | Taft | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1200000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122506 | Biga Elementary School | Giporlos | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1170000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122658 | Binalayan Elementary School | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2018000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122536 | Bobon Elementary School | Mercedes | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2018000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122762 | Bongdo Primary School | Taft | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122428 | Botnga Primary School | Dolores | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122519 | Buenavista Elementary School | Guiuan | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122711 | Butig Elementary School | Salcedo | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122477 | Cacatmonan Primary School | Hernani | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2153800 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122636 | Cagdaja Elementary School To Dalid Es | Quinapondan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122540 | Cagdara-O Primary School | Guiuan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1998000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122411 | Caghalong Primary School | Can-Avid | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122330 | Cagsalay Elementary School | Arteche | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122663 | Cagtoog Elementary School | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2028000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 313520 | Cambilla Elementary School To Carapdapan Nhs | Arteche | 0 |  | 3 | 1STY3CL | BATCH 9 CL | 3031000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 313501 | Can-Avid National High School | Can-Avid | 0 | 1 | 24 | 2STY12CL | BATCH 9 CL | 26332590.9236 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 313501 | Can-Avid National High School | Can-Avid | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4864000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122507 | Cansingkol Elementary School | Giporlos | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2931000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122652 | Cantinio Primary School To Agsam Es | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2018000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122714 | Cantomoja Elementary School | Salcedo | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1200000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122720 | Capanoypoyan Primary School To Taclaon Es | Salcedo | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2008000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 313520 | Carapdapan National High School | Arteche | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8336000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122481 | Carmen Elementary School | Hernani | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2881000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122723 | Caruyagon Elementary School | San Julian | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122541 | Cogon Elementary School | Guiuan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1998000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 313522 | Concepcion National High School | Arteche | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2931000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 192508 | Dacul Primary School | Taft | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122522 | Dalaragan Primary School | Guiuan | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2871000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122771 | Danao Elementary School To Polangi Es | Taft | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1190000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122615 | Del Pilar Elementary School | Maydolong | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1180000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122765 | Del Remedios Elementary School | Taft | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1221000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303499 | Dolores National High School | Dolores | 0 | 1 | 20 | 2STY10CL | BATCH 13 CL | 25856000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303499 | Dolores National High School | Dolores | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2699435.9551 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122574 | Dorillo Elementary School | Jipapad | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1221000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122523 | Gahoy Elementary School | Guiuan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1998000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122766 | Gayam Primary School | Taft | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303501 | Gen. Macarthur National Agricultural School | General Macarthur | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2726593.2584 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303502 | Giporlos National Trade School | Giporlos | 0 | 1 | 24 | 2STY8CL | BATCH 9 CL | 33055000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303502 | Giporlos National Trade School | Giporlos | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4372822.2222 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122715 | Guba Primary School | Salcedo | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1170000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122632 | Guinmaayohan Elementary School To Bagacay Es | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303503 | Guiuan National High School | Guiuan | 0 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12998000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303507 | Hinolaso National High School | Dolores | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6532000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303508 | Homonhon National High School | Guiuan | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11185000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122509 | Huknan Elementary School To Gigoso Es | Giporlos | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122564 | Inapulangan Elementary School | Guiuan | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 192520 | Ipil Elementary School | Dolores | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122419 | Jepaco Elementary School | Can-Avid | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303510 | Jipapad National High School | Jipapad | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11135000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303510 | Jipapad National High School | Jipapad | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2492000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122576 | Jiwaran Primary School | Jipapad | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122619 | Julag Primary School | Balangkayan | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122748 | Kandalakit Elementary School | Sulat | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2038000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122695 | Karapdapan Elementary School | Salcedo | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1160000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122620 | Lapgap Elementary School | Maydolong | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1190000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 313523 | Lapgap National High School | Maydolong | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2038000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303512 | Lawaan National School Of Craftsmanship And Home Industries | Lawaan | 0 | 1 | 20 | 2STY10CL | BATCH 9 CL | 23098358.1675 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303512 | Lawaan National School Of Craftsmanship And Home Industries | Lawaan | 0 |  | 8 | 2STY8CL | BATCH 9 CL | 11065000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303512 | Lawaan National School Of Craftsmanship And Home Industries | Lawaan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2422714.2857 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122343 | Layog Primary School To Beta-Og Es | Lawaan | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1110000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 192516 | Libertad Elementary School | Maslog | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1221000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122487 | Limbujan Primary School | General Macarthur | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1190000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303513 | Llorente National High School | Llorente | 0 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12948000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303513 | Llorente National High School | Llorente | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2507980.0817 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122457 | Luhang Elementary School | Dolores | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 192514 | Lunang Elementary School | Dolores | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1998000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 192507 | Lunang Primary School | San Julian | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1110000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122768 | Lupok Central Elementary School To Malinao Es | Taft | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6422000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122454 | Lupok Central Elementary School To Hinolaso Es | Dolores | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2871000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122577 | Mabuhay Elementary School | Jipapad | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1190000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122488 | Macapagal Primary School | General Macarthur | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122578 | Magsaysay Elementary School | Jipapad | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122621 | Magsaysay Primary School | Balangkayan | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1160000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303514 | Malabag National High School | Giporlos | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2881000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122461 | Malobago Primary School | Maslog | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1221000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 313516 | Manicani National High School | Guiuan | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3031000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303516 | Matarinao School Of Fisheries | Salcedo | 0 | 1 | 6 | 3STY6CL | BATCH 9 CL | 9490418.359 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303516 | Matarinao School Of Fisheries | Salcedo | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2442000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 313514 | Maydolong National High School | Maydolong | 0 | 1 | 12 | 2STY6CL | BATCH 13 CL | 16632000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 313514 | Maydolong National High School | Maydolong | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2512768.1307 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122579 | Maylimon Elementary School | Jipapad | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122626 | Maytigbao Elementary School | Maydolong | 0 | 1 | 2 | 2STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303518 | Mercedes National High School | Mercedes | 0 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6355390.5783 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122667 | Naga Elementary School | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2028000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122490 | Nagaja Elementary School | Hernani | 0 | 1 | 5 | 1STY5CL | BATCH 9 CL | 4629000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122649 | Oras East District Sped Center To Saurong Es | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1998000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303520 | Oras National High School | Oras | 0 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10497131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303529 | Oras West Central Elementary School To Taft Nhs | Taft | 0 |  | 10 | 2STY10CL | BATCH 13 CL | 12948000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303520 | Oras West Central Elementary School To Oras Nhs | Oras | 0 |  | 4 | 2STY4CL | BATCH 13 CL | 6422000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122575 | Oras West Central Elementary School To Jipapad Ces | Jipapad | 0 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2871000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122491 | Osmeña Primary School | General Macarthur | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122682 | Paco Elementary School | Quinapondan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1998000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122761 | Pangabutan Primary School To Binaloan Es | Taft | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303505 | Pedro E. Candido Memorial National High School | Hernani | 0 | 1 | 12 | 2STY6CL | BATCH 13 CL | 16667000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122494 | Quezon Primary School | General Macarthur | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1170000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 192505 | Quiatan Elemenary School | Dolores | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1190000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303522 | Quinapondan National High School To Salcedo National High School | Quinapondan | 0 | 1 | 12 | 2STY6CL | BATCH 13 CL | 20000000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122581 | Roxas Elementary School | Jipapad | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 313509 | Salcedo Vocational High School | Salcedo | 0 | 1 | 12 | 2STY6CL | BATCH 13 CL | 16772000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 313509 | Salcedo Vocational High School | Salcedo | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2557456.5884 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303523 | Samar National Pilot Opportunity School Of Agriculture | San Policarpo | 0 | 1 | 16 | 2STY8CL | BATCH 9 CL | 19669216.6651 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303523 | Samar National Pilot Opportunity School Of Agriculture | San Policarpo | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2437000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 313521 | San Antonio Primary School To Dapdap Ntvhs | Dolores | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2098000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122629 | San Gabriel Elementary School | Maydolong | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1190000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122679 | San Isidro Elementary School To Sta. Cruz Es | General Macarthur | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2038000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122498 | San Isidro Elementary School | Hernani | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1180000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122352 | San Isidro Primary School | Lawaan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2028000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 192503 | San Isidro Ps | Quinapondan | 0 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1939000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 192519 | San Juan Elementary School | Guiuan | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2981000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303524 | San Julian National High School | San Julian | 0 |  | 6 | 2STY6CL | BATCH 9 CL | 7448468.5459 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303524 | San Julian National High School | San Julian | 0 | 1 | 10 | 2STY10CL | BATCH 9 CL | 12938000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122467 | San Roque Elementary School | Maslog | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1221000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122500 | San Roque Primary School | General Macarthur | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1180000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 313502 | Southern Samar National Comprehensive National High School | Balangiga | 0 | 1 | 20 | 2STY10CL | BATCH 9 CL | 23168358.1675 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 313502 | Southern Samar National Comprehensive National High School | Balangiga | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4894000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122468 | Sta. Catalina Primary School | Dolores | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1190000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122501 | Sta. Cruz Elementary School | General Macarthur | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1150000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122502 | Sta. Fe Primary School | General Macarthur | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1190000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122650 | Sta. Monica Integrated School | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2108000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122743 | Sta.Cruz Elementary School | San Policarpo | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122325 | Sulangan Central Elementary School To Arteche Ces | Arteche | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8336000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122758 | Sulat Central Elementary School | Sulat | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2871000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303527 | Sulat National High School | Sulat | 0 | 1 | 20 | 2STY10CL | BATCH 9 CL | 23118358.1675 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303527 | Sulat National High School | Sulat | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4934000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122569 | Sulu-An Integrated School | Guiuan | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6582000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122551 | Sung-An Es | Mercedes | 0 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1939000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122744 | Tabo Elementary School | San Policarpo | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1998000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303529 | Taft National High School | Taft | 0 | 1 | 12 | 2STY6CL | BATCH 13 CL | 16642000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122630 | Tagasli-An Es | Maydolong | 0 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1939000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 192518 | Tagporo Elementary School | Guiuan | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1170000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122469 | Tan-Awan Elementary School | Dolores | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122503 | Tandang Sora Primary School | General Macarthur | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122470 | Tangbo Elementary School | Maslog | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122651 | Tawagan Elementary School | Oras | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1978000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 303504 | Taytay Integrated School | Guiuan | 0 | 1 | 10 | 2STY10CL | BATCH 9 CL | 12948000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122553 | Trinidad Elementary School | Guiuan | 0 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1210000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122554 | Tubabao Elementary School | Guiuan | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Eastern Samar | 122504 | Tugop Elementary School | General Macarthur | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2981000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VIII | Leyte | 303336 | Alang-Alang National High School | Alangalang | 1 | 1 | 24 | 2STY8CL | BATCH 7 CL | 33155000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VIII | Leyte | 303336 | Alang-Alang National High School | Alangalang | 1 |  | 10 | 2STY10CL | BATCH 7 CL | 12898000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VIII | Leyte | 303441 | Gregorio C. Catenza Nhs (Tunga Nhs) | Tunga | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Leyte | 303441 | Gregorio C. Catenza Nhs (Tunga Nhs) | Tunga | 1 |  | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 303441 | Gregorio C. Catenza Nhs (Tunga Nhs) | Tunga | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Leyte | 303343 | Juan S. Tismo National High School (Babatngon National High School | Babatngon | 1 | 1 | 18 | 2STY6CL | BATCH 9 CL | 24888000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION VIII | Leyte | 303415 | Palo National High School | Palo | 1 | 1 | 45 | 3STY15CL | BATCH 7 CL | 64149040.35 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 45 | 0
NEWCON 2016 | REGION VIII | Leyte | 303415 | Palo National High School | Palo | 1 |  | 18 | 3STY9CL | BATCH 7 CL | 30242655.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION VIII | Leyte | 303426 | San Miguel National High School | San Miguel | 1 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VIII | Leyte | 303426 | San Miguel National High School | San Miguel | 1 |  | 8 | 2STY8CL | BATCH 7 CL | 10985000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Leyte | 121928 | San Roque Elementary School | Tanauan | 1 | 1 | 6 | 3STY6CL | BATCH 13 CL | 10498731.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Leyte | 303429 | Sta. Cruz National High School | San Miguel | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.051 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Leyte | 303430 | Sta. Fe National High School | Santa Fe | 1 | 1 | 16 | 2STY8CL | BATCH 9 CL | 21970000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VIII | Leyte | 303430 | Sta. Fe National High School | Santa Fe | 1 |  | 12 | 2STY12CL | BATCH 9 CL | 17963836.31 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 121930 | Sto. Niño Elementary School | Tanauan | 1 | 1 | 12 | 2STY12CL | BATCH 13 CL | 14579217.1798 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 303437 | Tanauan National High School (San Roque Nhs) | Tanauan | 1 | 1 | 15 | 3STY15CL | BATCH 7 CL | 21383013.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION VIII | Leyte | 303388 | Tanauan Sch. Of Craftsmanship & Home Industries (Lit-Tanauan | Tanauan | 1 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 303388 | Tanauan Sch. Of Craftsmanship & Home Industries (Lit-Tanauan | Tanauan | 1 |  | 16 | 4STY16CL | BATCH 9 CL | 29357716.362 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VIII | Leyte | 303440 | Tolosa National High School | Tolosa | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10985000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Leyte | 303440 | Tolosa National High School | Tolosa | 1 |  | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 303342 | Atty. Roque A. Marcos Memorial School (La Paz Nhs) | Lapaz | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18322268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 303342 | Atty. Roque A. Marcos Memorial School (La Paz Nhs) | Lapaz | 2 |  | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Leyte | 313324 | Barugo National High School | Barugo | 2 | 1 | 12 | 2STY6CL | BATCH 7 CL | 16592000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 313324 | Barugo National High School | Barugo | 2 |  | 12 | 3STY12CL | BATCH 7 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 303353 | Burauen Comprehensive National High School | Burauen | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Leyte | 303353 | Burauen Comprehensive National High School | Burauen | 2 |  | 15 | 3STY15CL | BATCH 7 CL | 21383013.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION VIII | Leyte | 303353 | Burauen Comprehensive National High School | Burauen | 2 |  | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VIII | Leyte | 303354 | Burauen National High School | Burauen | 2 | 1 | 15 | 3STY15CL | BATCH 7 CL | 21383013.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION VIII | Leyte | 303369 | Dulag National High School | Dulag | 2 | 1 | 32 | 4STY16CL | BATCH 9 CL | 58715432.724 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0
NEWCON 2016 | REGION VIII | Leyte | 303369 | Dulag National High School | Dulag | 2 |  | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VIII | Leyte | 303371 | Granja-Kalinawan National High School | Jaro | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 303371 | Granja-Kalinawan National High School | Jaro | 2 |  | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 303371 | Granja-Kalinawan National High School | Jaro | 2 |  | 16 | 4STY16CL | BATCH 9 CL | 29357716.362 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VIII | Leyte | 303380 | Juan Villablanca Memorial High School | Pastrana | 2 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 303380 | Juan Villablanca Memorial High School | Pastrana | 2 |  | 6 | 2STY6CL | BATCH 7 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Leyte | 303380 | Juan Villablanca Memorial High School | Pastrana | 2 |  | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Leyte | 313307 | Jugaban National High School | Carigara | 2 | 1 | 18 | 3STY9CL | BATCH 7 CL | 30242655.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION VIII | Leyte | 121527 | Julita Central School | Julita | 2 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VIII | Leyte | 121527 | Julita Central School | Julita | 2 |  | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Leyte | 303397 | Mac Arthur National High School | Mac Arthur | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Leyte | 303397 | Mac Arthur National High School | Mac Arthur | 2 |  | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VIII | Leyte | 303397 | Mac Arthur National High School | Mac Arthur | 2 |  | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 303432 | Sta. Mesa National High School | Dagami | 2 | 1 | 18 | 3STY9CL | BATCH 9 CL | 30242655.84 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION VIII | Leyte | 303432 | Sta. Mesa National High School | Dagami | 2 |  | 8 | 2STY8CL | BATCH 9 CL | 10985000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Leyte | 313322 | Cahigan Nhs | Villaba | 3 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8346000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Leyte | 303358 | Calubian National High School | Calubian | 3 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18273000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 303358 | Calubian National High School | Calubian | 3 |  | 9 | 3STY9CL | BATCH 9 CL | 15122000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VIII | Leyte | 303358 | Calubian National High School | Calubian | 3 |  | 2 | 1STY2CL | BATCH 9 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Leyte | 303387 | Leyte Agro-Industrial School | Leyte | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Leyte | 303403 | Marcelino R. Veloso Nhs | Tabango | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Leyte | 303403 | Marcelino R. Veloso Nhs | Tabango | 3 | 1 | 10 | 2STY10CL | BATCH 13 CL | 14279402.099 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VIII | Leyte | 303423 | San Isidro Nhs | San Isidro | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Leyte | 303423 | San Isidro Nhs | San Isidro | 3 | 1 | 10 | 2STY10CL | BATCH 13 CL | 13380904 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VIII | Leyte | 313345 | Sulpa Nhs | Villaba | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Leyte | 313345 | Sulpa Nhs | Villaba | 3 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9184586.555 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Leyte | 121893 | Tabango North Central School | Tabango | 3 | 1 | 12 | 2STY12CL | BATCH 7 CL | 14774000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 121893 | Tabango North Central School | Tabango | 3 |  | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Leyte | 303442 | Villaba Comprehensive Hs | Villaba | 3 | 1 | 6 | 3STY6CL | BATCH 11 CL | 11443844.661 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Leyte | 303442 | Villaba Comprehensive Hs | Villaba | 3 |  | 15 | 3STY15CL | BATCH 11 CL | 21384000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION VIII | Leyte | 303442 | Villaba Comprehensive Hs | Villaba | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2924570 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Leyte | 303389 | Villaba Nhs (Lncast) | Villaba | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Leyte | 303378 | Isabel Nhs | Isabel | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Leyte | 313302 | Isabel Nhs Comprehensive | Isabel | 4 | 1 | 12 | 2STY12CL | BATCH 13 CL | 16022138.898 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 313302 | Isabel Nhs Comprehensive | Isabel | 4 |  | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Leyte | 303383 | Kananga National High School | Kananga | 4 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15272000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VIII | Leyte | 303383 | Kananga National High School | Kananga | 4 |  | 6 | 2STY6CL | BATCH 11 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Leyte | 303383 | Kananga National High School | Kananga | 4 |  | 24 | 4STY12CL | BATCH 11 CL | 44304687.24 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VIII | Leyte | 303395 | Lim-Ao National High School | Kananga | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Leyte | 303404 | Matag-Ob National High School | Matag-Ob | 4 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18303000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 303404 | Matag-Ob National High School | Matag-Ob | 4 |  | 9 | 3STY9CL | BATCH 7 CL | 15122000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VIII | Leyte | 303406 | Matlang National High School | Isabel | 4 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18273000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 303408 | Merida Vocational School | Merida | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Leyte | 303408 | Merida Vocational School | Merida | 4 | 1 | 24 | 2STY12CL | BATCH 13 CL | 29448000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VIII | Leyte | 313306 | Palompon National High School | Palompon | 4 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15172000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VIII | Leyte | 313306 | Palompon National High School | Palompon | 4 |  | 9 | 3STY9CL | BATCH 9 CL | 15122000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VIII | Leyte | 313306 | Palompon National High School | Palompon | 4 |  | 15 | 3STY15CL | BATCH 9 CL | 21384000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION VIII | Leyte | 313306 | Palompon National High School | Palompon | 4 |  | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Leyte | 313327 | Rizal Nhs | Kananga | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Leyte | 303427 | Seguinon National High School | Albuera | 4 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18273000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 303427 | Seguinon National High School | Albuera | 4 |  | 6 | 2STY6CL | BATCH 7 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Leyte | 303335 | Abuyog National High School | Abuyog | 5 | 1 | 15 | 3STY15CL | BATCH 7 CL | 21383013.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION VIII | Leyte | 303347 | Bato School Of Fisheries | Bato | 5 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 303347 | Bato School Of Fisheries | Bato | 5 |  | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Leyte | 303356 | Cahagnaan National High School | Matalom | 5 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6682000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Leyte | 303374 | Hilongos National High School | Hilongos | 5 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 303374 | Hilongos National High School | Hilongos | 5 |  | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 303374 | Hilongos National High School | Hilongos | 5 |  | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 303379 | Javier National High School | Javier(Bugho) | 5 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VIII | Leyte | 303379 | Javier National High School | Javier(Bugho) | 5 |  | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VIII | Leyte | 303379 | Javier National High School | Javier(Bugho) | 5 |  | 12 | 3STY12CL | BATCH 7 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 303398 | Mahaplag National High School | Mahaplag | 5 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21383013.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION VIII | Leyte | 303398 | Mahaplag National High School | Mahaplag | 5 |  | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VIII | Leyte | 303399 | Mahaplag National High School (Upper Campus Ra 7094) | Mahaplag | 5 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10985000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Leyte | 303399 | Mahaplag National High School (Upper Campus Ra 7094) | Mahaplag | 5 |  | 8 | 2STY8CL | BATCH 7 CL | 10985000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Leyte | 303399 | Mahaplag National High School (Upper Campus Ra 7094) | Mahaplag | 5 |  | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Leyte | 313344 | Manlilisid National High School | Javier | 5 | 1 | 12 | 2STY6CL | BATCH 13 CL | 16592000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Leyte | 313344 | Manlilisid National High School | Javier | 5 |  | 1 | 1STY1CL | BATCH 13 CL | 1098449.69 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Leyte | 303405 | Matalom National High School | Matalom | 5 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VIII | Leyte | 303405 | Matalom National High School | Matalom | 5 |  | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VIII | Leyte | 121648 | Polahongon Elementary School | Mahaplag | 5 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15122327.92 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VIII | Leyte | 121648 | Polahongon Elementary School | Mahaplag | 5 |  | 6 | 2STY6CL | BATCH 13 CL | 8296000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Leyte | 121648 | Polahongon Elementary School | Mahaplag | 5 |  | 1 | 1STY1CL | BATCH 13 CL | 1098449.69 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Leyte | 313314 | Polahongon National High School | Mahaplag | 5 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21383013.45 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0
NEWCON 2016 | REGION VIII | Leyte | 313314 | Polahongon National High School | Mahaplag | 5 |  | 6 | 3STY6CL | BATCH 9 CL | 10417131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303531 | Allen Nhs | Allen | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303531 | Allen Nhs | Allen | 1 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6936271.404 |  |  | Terminated | 0 | [10 empty] | Original Contract Terminated on June 29, 2022. New contract completed on February 18, 2023. | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4
NEWCON 2016 | REGION VIII | Northern Samar | 303531 | Allen Nhs | Allen | 1 |  | 20 | 2STY10CL | BATCH 13 CL | 25542620.18 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303561 | Basilio B. Chan Mem. Agricultural And Industrial Sch. | Lavezares | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11950076.849 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303561 | Basilio B. Chan Mem. Agricultural And Industrial Sch. | Lavezares | 1 |  | 3 | 1STY3CL | BATCH 13 CL | 3082851.684 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303534 | Biri National High School | Biri | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11950076.849 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303535 | Bobon School For Philippine Craftsmen | Bobon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303536 | Buenavista Nhs | Rosario | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2853063.86 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303540 | Capul Agro-Industrial School | Capul | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 122845 | Catarman Ii Cs | Catarman (Capital) | 1 | 1 | 12 | 2STY6CL | BATCH 13 CL | 18042923.11 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303541 | Catarman National High School | Catarman (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6936271.404 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303541 | Catarman National High School | Catarman (Capital) | 1 |  | 8 | 2STY8CL | BATCH 13 CL | 11950076.849 |  |  | Terminated | 0 | [10 empty] | Contract Terminated on September 24, 2019. Under Preliminary Detailed Engineering. | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8
NEWCON 2016 | REGION VIII | Northern Samar | 303541 | Catarman National High School | Catarman (Capital) | 1 |  | 12 | 2STY12CL | BATCH 13 CL | 14579217.18 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 313606 | Cawayan Integrated School | Catarman (Capital) | 1 | 1 | 8 | 2STY4CL | BATCH 13 CL | 12638675.28 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303548 | Eladio T. Balite Memorial School Of Fisheries | Bobon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2429548.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303548 | Eladio T. Balite Memorial School Of Fisheries | Bobon | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11950076.849 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303563 | Lope De Vega Nhs | Lope De Vega | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Northern Samar | PSA328558 | Lope De Vega Nhs (Stand Alone) | Lope De Vega | 1 | 1 | 8 | 2STY8CL | BATCH 11 CL | 11950076.849 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Northern Samar | PSA328558 | Lope De Vega Nhs (Stand Alone) | Lope De Vega | 1 |  | 2 | 1STY2CL | BATCH 11 CL | 2132466.644 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Northern Samar | PSA328558 | Lope De Vega Nhs (Stand Alone) | Lope De Vega | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2551025.68 |  |  | Terminated | 0 | [10 empty] | Contract Terminated on June 29, 2022. Project site for validation by the Department of Education. | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
NEWCON 2016 | REGION VIII | Northern Samar | 313623 | Maravilla National High School | Lavezares | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2551025.68 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303566 | Mondragon Agro-Ind'L Hs | Mondragon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303566 | Mondragon Agro-Ind'L Hs | Mondragon | 1 | 1 | 24 | 2STY12CL | BATCH 13 CL | 32044277.796 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303566 | Mondragon Agro-Ind'L Hs | Mondragon | 1 |  | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303570 | Polangi National High School | Catarman (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11950076.849 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 122814 | Salvacion Es | Bobon | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303577 | San Isidro Agro-Industrial High School | San Isidro | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2623912.13 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303578 | San Isidro Nhs (San Isidro) | San Isidro | 1 | 1 | 24 | 2STY12CL | BATCH 13 CL | 32044277.796 |  |  | Terminated | 0.3 | [10 empty] | Contract Terminated on October 14, 2022. Project site for validation by the Departement of Education. | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24
NEWCON 2016 | REGION VIII | Northern Samar | 303580 | San Jose Technical Hs | San Jose | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 123073 | San Juan Es | Lavezares | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303582 | San Vicente School Of Fisheries | San Vicente | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Terminated | 0 | [10 empty] | Contrac Terminated on October 14, 2022. For advertisement. | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
NEWCON 2016 | REGION VIII | Northern Samar | 123284SHS | Victoria Cs | Victoria | 1 | 1 | 8 | 2STY8CL | BATCH 11 CL | 11950076.849 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 123284 | Victoria Cs | Victoria | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2429548.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 313602 | Anito Nhs | Gamay | 2 | 1 | 8 | 2STY4CL | BATCH 13 CL | 13413775.28 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303533 | Batag Nhs | Laoang | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303544 | Catubig Valley Nhs | Catubig | 2 | 1 | 16 | 2STY8CL | BATCH 13 CL | 23217185.18 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303546 | Don Juan F. Avalon National High School | San Roque | 2 | 1 | 24 | 2STY8CL | BATCH 13 CL | 34675777.77 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303551 | Gala Vocational School | Gamay | 2 | 1 | 12 | 2STY6CL | BATCH 13 CL | 17829630.1 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303556 | Laoang National Technical High School | Laoang | 2 | 1 | 16 | 2STY8CL | BATCH 13 CL | 23317185.18 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303560 | Las Navas National High School | Las Navas | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2429548.27 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303560 | Las Navas National High School | Las Navas | 2 | 1 | 24 | 2STY8CL | BATCH 13 CL | 35125777.77 |  |  | Terminated | 0 | [10 empty] | (1) The project was terminated (wholly) for convenience due to original plan is no longer economically and technically feasible for construction as per result of Geotechnical Investigation. Moreover, no buffer fund was released to cover the proposed revised design which requires an additional allocation amounting to Php 5,244,796.26. (2) Site Validation will be conducted with representative from DepEd. | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24
NEWCON 2016 | REGION VIII | Northern Samar | 303559 | Lorenzo S. Menzon Ais | Lapinig | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2648207.61 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 313624 | Oleras Nhs | Laoang | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8814965.05 |  |  | Terminated | 0 | [10 empty] | (1) The project was terminated (wholly) for convenience due to original plan is no longer economically and technically feasible for construction as per result of Geotechnical Investigation. Moreover, no buffer fund was released to cover the proposed revised design which requires an additional allocation amounting to Php 1,433,488.38. (2) Site Validation will be conducted with representative from DepEd. | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6
NEWCON 2016 | REGION VIII | Northern Samar | 303569 | Pambujan Nhs | Pambujan | 2 | 1 | 18 | 3STY9CL | BATCH 13 CL | 32020767.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 313603 | Rawis National High School | Laoang | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8814965.05 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303583 | Silvino Lubos Vocational High School | Silvino Lobos | 2 | 1 | 16 | 2STY8CL | BATCH 13 CL | 24917185.18 |  |  | Terminated | 0.5 | [10 empty] | (1) One unit of the school building was already completed. However, the second unit cannot be implemented due to the recommendations as per result of soil investigation report. The project was terminated partly for convenience due to the project site of the second unit school building did not conform with the result of Geotechnical investigation. (2) Site Validation will be conducted with representative from DepEd. | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16
NEWCON 2016 | REGION VIII | Northern Samar | 303584 | Sumoroy Agro-Industrial School | Palapag | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2808700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303584 | Sumoroy Agro-Industrial School | Palapag | 2 | 1 | 24 | 3STY12CL | BATCH 13 CL | 40408991.338 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VIII | Northern Samar | 303584 | Sumoroy Agro-Industrial School | Palapag | 2 |  | 9 | 3STY9CL | BATCH 13 CL | 16110383.81 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0
NEWCON 2016 | REGION VIII | Ormoc City | 124200 | Airport Primary School | Ormoc City | 4 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3025000 |  |  | Completed | 1 |  |  | P00074120VS-CW1 | 16IF0065 | 04/27/2016 | 2016-05-05 | 05/17/2016 | 05/20/2016 | 07/21/2016 | RJIR ENT. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VIII | Ormoc City | 124175 | Cagbuhangin Elementary School | Ormoc City | 4 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1920000 |  |  | Completed | 1 |  |  | P00070556VS-CW1 | 16IF0043 | 2016-03-02 | 2016-03-10 | 03/23/2016 | 2016-05-10 | 05/26/2016 | GMP BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Ormoc City | 303654 | Dolores National High School | Ormoc City | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6690000 |  |  | Completed | 1 |  |  | P00070554VS-CW1 | 16IF0040 | 2016-03-02 | 2016-03-10 | 03/23/2016 | 2016-05-10 | 05/26/2016 | A.C. RIVERO DEV. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Ormoc City | 124154 | Hugpa Elementary School | Ormoc City | 4 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1980000 |  |  | Completed | 1 |  |  | P00070557VS-CW1 | 16IF0042 | 2016-03-02 | 2016-03-10 | 03/23/2016 | 2016-05-10 | 05/26/2016 | GMP BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Ormoc City | 303655 | Ipil National High School | Ormoc City | 4 | 1 | 12 | 3STY12CL | BATCH 3 CL | 19140000 |  |  | Completed | 1 |  |  | P00070553VS-CW1 | 16IF0037 | 2016-03-02 | 2016-03-10 | 03/22/2016 | 2016-05-10 | 05/26/2016 | A.C. RIVERO DEV. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Ormoc City | 313901 | Lilo-An Nat. High School | Ormoc City | 4 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6690000 |  |  | Completed | 1 |  |  | P00070553VS-CW2 | 16IF0103 | 09/20/2017 | 2016-10-05 | 12/13/2016 | 12/16/2016 | 42747 | A.C. RIVERO DEV. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Ormoc City | 303656 | Linao National High School | Ormoc City | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6690000 |  |  | Completed | 1 |  |  | P00070555VS-CW1 | 16IF0038 | 2016-03-02 | 2016-03-10 | 03/22/2016 | 2016-05-10 | 05/26/2016 | J.A. ACHACOSO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Ormoc City | 124164 | Mahayag Elementary School | Ormoc City | 4 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2870000 |  |  | Completed | 1 |  |  | P00070558VS-CW1 | 16IF0045 | 2016-03-02 | 2016-03-10 | 03/22/2016 | 2016-05-10 | 05/26/2016 | A.C. RIVERO DEV. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0
NEWCON 2016 | REGION VIII | Ormoc City | 124185 | Matica-A Elementary School | Ormoc City | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6710000 |  |  | Completed | 1 |  |  | P00070559VS-CW1 | 16IF0041 | 2016-03-02 | 2016-03-10 | 03/22/2016 | 2016-05-10 | 06/13/2016 | ARCA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Ormoc City | 303658 | New Ormoc City National High School | Ormoc City | 4 | 1 | 12 | 3STY12CL | BATCH 11 CL | 17127665.62 |  |  | Completed | 1 |  |  | P00070559VS-CW2 | 16IF0091 | 09/20/2017 | 09/15/2016 | 09/28/2016 | 09/30/2016 | 10/13/2016 | ARCA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Ormoc City | 313905 | Ormoc City Night High School | Ormoc City | 4 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8400000 |  |  | Completed | 1 |  |  | P00070560VS-CW1 | 16IF0039 | 2016-03-02 | 2016-03-10 | 03/22/2016 | 2016-05-10 | 05/26/2016 | RJIR ENT. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Ormoc City | 303662 | Valencia Nat. High School | Ormoc City | 4 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8500000 |  |  | Completed | 1 |  |  | P00072437VS-CW1 | 16IF0051 | 2016-03-02 | 2016-03-10 | 03/22/2016 | 05/23/2016 | 06/21/2016 | A.C. RIVERO DEV. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Ormoc City | 303662 | Valencia Nat. High School | Ormoc City | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 1940000 |  |  | Completed | 1 |  |  | P00072633VS-CW1 | 16IF0052 | 2016-03-02 | 2016-03-10 | 03/22/2016 | 06/15/2016 | 06/23/2016 | CIRCLE Z |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Ormoc City | 194502 | Vl Villacencio Elementary School | Ormoc City | 4 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1960000 |  |  | Completed | 1 |  |  | P00070561VS-CW1 | 16IF0044 | 2016-03-02 | 2016-03-10 | 03/22/2016 | 2016-05-10 | 05/26/2016 | CIRCLE Z |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303599 | Clarencio Calagos Mem Sof | Santa Margarita | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303599 | Clarencio Calagos Mem Sof | Santa Margarita | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8570000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303599 | Clarencio Calagos Mem Sof | Santa Margarita | 1 |  | 4 | 2STY4CL | BATCH 13 CL | 6469337 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303612 | Matuguinao National High School | Matuguinao | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303615 | Pagsanghan Nhs | Pagsanghan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303618 | Ramon T. Diaz Mhs | Gandara | 1 | 1 | 12 | 2STY6CL | BATCH 13 CL | 17140000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303618 | Ramon T. Diaz Mhs | Gandara | 1 |  | 4 | 2STY4CL | BATCH 13 CL | 6469337 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 313708 | San Jorge Nhs | San Jorge | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 313708 | San Jorge Nhs | San Jorge | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8570000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303632 | Sto. Nino Nhs | Santo Niño | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2750000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303643 | Zumarraga National School | Zumarraga | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303592 | Basey National High School | Basey | 2 | 1 | 18 | 2STY6CL | BATCH 3 CL | 8870000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303592 | Basey National High School | Basey | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303593 | Burgos Is | Basey | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303596 | Calapi Nhs | Motiong | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2750000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303597 | Calbiga National High School | Calbiga | 2 | 1 | 40 | 4STY20CL | BATCH 11 CL | 64836952.5344 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303606 | Hinabangan Nhs | Hinabangan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303608 | Independencia Nhs | Talalora | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303609 | Jiabong National High School | Jiabong | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2700000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 123786 | Magsaysay Es | Santa Rita | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8570000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303613 | Motiong Nhs | Motiong | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303614 | Osmeña Nhs | Marabut | 2 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12921310.09 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303640 | Quintin Quijano Sr. Agricultural School | Pinabacdao | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303640 | Quintin Quijano Sr. Agricultural School | Pinabacdao | 2 | 1 | 8 | 2STY4CL | BATCH 13 CL | 12938674 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303626 | San Jose De Buan Nhs | San Jose De Buan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303631 | Sta. Rita National High School | Santa Rita | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303639 | Villareal Nhs | Villareal | 2 | 1 | 8 | 2STY4CL | BATCH 13 CL | 13138674 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0
NEWCON 2016 | REGION VIII | Samar (Western Samar) | 303641 | Wright Nhs | Paranas (Wright) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Southern Leyte | 303453 | Don Agustin F. Escaño Nhs | Tomas Oppus | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Southern Leyte | 303460 | Himbangan National High School | Saint Bernard | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Southern Leyte | 303447 | Hinunangan National High School(Canipaan Nhs - Hinunangan Annex) | Hinunangan | 0 | 1 | 12 | 3STY12CL | BATCH 13 CL | 22017445.2359 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Southern Leyte | 313409 | Liloan National Technical Vocational High School | Liloan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Southern Leyte | 313409 | Liloan National Technical Vocational High School | Liloan | 0 | 1 | 36 | 2STY12CL | BATCH 13 CL | 51010121.324 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 36 | 0
NEWCON 2016 | REGION VIII | Southern Leyte | 303477 | Pintuyan National Vocational High School | Pintuyan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Southern Leyte | 303477 | Pintuyan National Vocational High School | Pintuyan | 0 | 1 | 12 | 3STY12CL | BATCH 13 CL | 22017445.2359 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Southern Leyte | 303477 | Pintuyan National Vocational High School | Pintuyan | 0 |  | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Southern Leyte | 303481 | San Juan Nhs | San Juan (Cabalian) | 0 | 1 | 12 | 3STY6CL | BATCH 11 CL | 24035879.932 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Southern Leyte | 303481 | San Juan Nhs | San Juan (Cabalian) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Southern Leyte | 303483 | San Ricardo National High School | San Ricardo | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Southern Leyte | 303487 | Sogod National High School | Sogod | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Southern Leyte | 303487 | Sogod National High School | Sogod | 0 | 1 | 36 | 3STY9CL | BATCH 13 CL | 68804476.198 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 36 | 0
NEWCON 2016 | REGION VIII | Southern Leyte | 303487 | Sogod National High School | Sogod | 0 |  | 12 | 3STY12CL | BATCH 13 CL | 18222268.79 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Southern Leyte | 303489 | Sta. Paz National High School | San Francisco | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Southern Leyte | 303492 | Villa Jacinta National Vocational High School | Macrohon | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
NEWCON 2016 | REGION VIII | Southern Leyte | 303492 | Villa Jacinta National Vocational High School | Macrohon | 0 | 1 | 12 | 3STY12CL | BATCH 13 CL | 21100403.969 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Tacloban City | 314003 | Antonio Balmes National High School | Tacloban City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6432000 |  |  | Reverted | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
NEWCON 2016 | REGION VIII | Tacloban City | 124255 | Cabalawan Es | Tacloban City (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1853000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Tacloban City | 124224 | Caibaan Es | Tacloban City (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8346000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Tacloban City | 303665 | Cirilo Roy Montejo Nhs (Panalaron Nhs) | Tacloban City (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 13 CL | 10467131.51 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0
NEWCON 2016 | REGION VIII | Tacloban City | 124235 | Lucio Vivero Es | Tacloban City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Tacloban City | 195001 | Manlurip Elementary School | Tacloban City (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1833000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NEWCON 2016 | REGION VIII | Tacloban City | 314004 | Northern Tacloban City National High School | Tacloban City (Capital) | 1 | 1 | 20 | 2STY10CL | BATCH 7 CL | 25796000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0
NEWCON 2016 | REGION VIII | Tacloban City | 303666 | Sagkahan National High School | Tacloban City (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VIII | Tacloban City | 303666 | Sagkahan National High School | Tacloban City (Capital) | 1 |  | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0
NEWCON 2016 | REGION VIII | Tacloban City | 303666 | Sagkahan National High School | Tacloban City (Capital) | 1 |  | 16 | 4STY8CL | BATCH 7 CL | 29795037.68 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0
NEWCON 2016 | REGION VIII | Tacloban City | 124248 | Salvacion Es | Tacloban City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6422000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0
NEWCON 2016 | REGION VIII | Tacloban City | PSA328572 | Shs In V&G Subdivision, Tacloban City | Tacloban City (Capital) | 1 | 1 | 24 | 3STY12CL | BATCH 9 CL | 32830083.822 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0
NEWCON 2016 | REGION VIII | Tacloban City | PSA328572 | Shs In V&G Subdivision, Tacloban City | Tacloban City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0