## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No. of Sites | Elem. Individual Learner Table & Chair Set | JHS Individual Learner Table & Chair Set | SHS Individual Learner Table & Chair Set | Total Individual Learner Table & Chair Set | Teacher's Table & Chair Set | Science Laboratory Table & Stool Set | Working Table & Stool Set | Approved Budget for Contract | Implementing Unit | Legend | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Supplier | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Sets Reverted | No. of Sets Not yet started | No. of Sets Under Procurement | No. of Sets On Going | No. of Sets Completed | No. of Sets Terminated | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed
CY 2023 SF | REGION VIII | Baybay City | 121079 | Lintaon Es To Baybay I Cs | City Of Baybay | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | REGION VIII | Baybay City | 121145 | Mahayahay Es To Marcos Es | City Of Baybay | 5th | 1 | 45 | - | - | 45 | 1 | - | - | 129869 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1
CY 2023 SF | REGION VIII | Borongan City | 122364 | Suhotan Ps To Siha Es | City Of Borongan (Capital) | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 129869 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1
CY 2023 SF | REGION VIII | Eastern Samar | 122325 | Sulangan Central Elementary School To Arteche Ces | Arteche | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | REGION VIII | Eastern Samar | 122454 | Lupok Central Elementary School To Hinolaso Es | Dolores | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | REGION VIII | Eastern Samar | 122509 | Huknan Elementary School To Gigoso Es | Giporlos | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 129869 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1
CY 2023 SF | REGION VIII | Eastern Samar | 122575 | Oras West Central Elementary School To Jipapad Ces | Jipapad | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | REGION VIII | Eastern Samar | 122343 | Layog Primary School To Beta-Og Es | Lawaan | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 129869 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1
CY 2023 SF | REGION VIII | Eastern Samar | 122649 | Oras East District Sped Center To Saurong Es | Oras | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | REGION VIII | Eastern Samar | 303522 | Quinapondan National High School To Salcedo National High School | Quinapondan | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 |  | 0
CY 2023 SF | REGION VIII | Eastern Samar | 122720 | Capanoypoyan Primary School To Taclaon Es | Salcedo | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0
CY 2023 SF | REGION VIII | Eastern Samar | 122761 | Pangabutan Primary School To Binaloan Es | Taft | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0
CY 2023 SF | REGION VIII | Eastern Samar | 122768 | Lupok Central Elementary School To Malinao Es | Taft | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0
CY 2023 SF | REGION VIII | Eastern Samar | 122771 | Danao Elementary School To Polangi Es | Taft | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0