## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No. of Sites | Elem. Individual Learner Table & Chair Set | JHS Individual Learner Table & Chair Set | SHS Individual Learner Table & Chair Set | Total Individual Learner Table & Chair Set | Teacher's Table & Chair Set | Science Laboratory Table & Stool Set | Working Table & Stool Set | Approved Budget for Contract | Implementing Unit | Legend | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Supplier | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Sets Reverted | No. of Sets Not yet started | No. of Sets Under Procurement | No. of Sets On Going | No. of Sets Completed | No. of Sets Terminated | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed
CY 2024 SF | Region XII | General Santos City | 131296 | H.N. Cahilsot Central Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | General Santos City | 131297 | Romana C. Acharon Central Elemetary School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | General Santos City | 131321 | NASA Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 585 | - | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | General Santos City | 131323 | Upper Tambler I Central Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 585 | - | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | General Santos City | 210012 | Jose R. Lansang Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | General Santos City | 304636 | Antonino G. Busano, Sr. High School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | - | 450 | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | General Santos City | 304653 | Lagao National High School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | - | 495 | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Kidapawan City | 131326 | Kidapawan City Pilot Elementary School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 495 | - | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Kidapawan City | 131328 | Suerte MES | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Kidapawan City | 131344 | Lanao Central Elementary School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Kidapawan City | 131358 | Paco Central Elementary School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Kidapawan City | 304667 | Onica National High School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Kidapawan City | 500309 | Binoligan Integrated School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Koronadal City | 131391 | Magsaysay ES | CITY OF KORONADAL (Capital) | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Koronadal City | 131395 | Marbel 6 ES | CITY OF KORONADAL (Capital) | 2nd | 1 | 495 | - | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Koronadal City | 304671 | Koronadal NCHS | CITY OF KORONADAL (Capital) | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Koronadal City | 317201 | Bacongco NHS | CITY OF KORONADAL (Capital) | 2nd | 1 | - | 495 | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Koronadal City | 317205 | Esperanza National High School – Annex, San Jose Campus | CITY OF KORONADAL (Capital) | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 129828 | Marabuhay ES | ALAMADA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 129833 | AMATAC ELEMENTARY SCHOOL | ALAMADA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 129852 | Tawas-Abaga Elementary School | ALAMADA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 129853 | Teren-Teren Elementary School | ALAMADA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 304412 | ALAMADA HIGH SCHOOL | ALAMADA | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 129955 | Wadya ES | BANISILAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 304453 | Kibudtungan National High School | CARMEN | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130005 | Kabacan Pilot Central School | KABACAN | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130027 | Kapayawi ES | LIBUNGAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130029 | Kitubod ES | LIBUNGAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130038 | C. V. Cocal Annex Elementary School | LIBUNGAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130192 | VILLARICA ELEMENTARY SCHOOL | MIDSAYAP | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130195 | CENTRAL BULANAN ES | MIDSAYAP | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 207508 | San Pedro Elementary School | MIDSAYAP | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 304432 | Dilangalen National High School | MIDSAYAP | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130267 | Lampaki ES | PIGKAWAYAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130269 | Gallego ES (Malu-ao ES) | PIGKAWAYAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130279 | Rogonan ES | PIGKAWAYAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130286 | Cabpangi ES | PIGKAWAYAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130287 | Capayuran ES | PIGKAWAYAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130330 | Pikit Central Elementary School | PIKIT | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130698 | Maganod Elementary School | PIKIT | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 304509 | Sultan Memorial HS | PIKIT | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130051 | Datu Mantawil ES | MAGPET | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130077 | Inac ES | MAGPET | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130094 | Biangan Elementary School | MAKILALA | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130095 | Buena Vida ES | MAKILALA | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130101 | Luayon ES (Garing) | MAKILALA | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130104 | Rodero ES | MAKILALA | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130108 | Bato Elementary School | MAKILALA | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 304482 | New Caridad NVTHS | TULUNAN | 2nd | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 304515 | Tulunan NHS | TULUNAN | 2nd | 1 | - | 1530 | - | 1530 | 34 | - | - | 5236000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 129938 | Kiaring ES | BANISILAN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 129944 | Pantar ES | BANISILAN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 129950 | Sabang ES | BANISILAN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 129951 | Salama CES | BANISILAN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 129952 | Thailand Elementary School | BANISILAN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130255 | BAGONTAPAY CENTRAL ELEMENTARY SCHOOL | M'LANG | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130405 | F. Cajelo ES | TULUNAN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sarangani | 130479 | Nicomedes Tolentino ES | GLAN | Lone | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sarangani | 130535 | Malalag CES-SPED Center | MAITUM | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sarangani | 304534 | Malalag National High School | MAITUM | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sarangani | 500281 | Wali Integrated School | MAITUM | Lone | 1 | - | - | 280 | 280 | 7 | - | - | 962500 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sarangani | 130611 | Malandag CES Sped Center | MALUNGON | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 130644 | Sancho ES | BANGA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 130646 | Banga Central Elementary School | BANGA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 130651 | Lamkot ES | Banga | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 316718 | San Vicente National High School | BANGA | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 501270 | Lambukay Integrated School | BANGA | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 304550 | Lake Sebu NHS | LAKE SEBU | 2nd | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 130699 | El Kuda ES | NORALA | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 316909 | Fabiola Villa-Gasis NHS - San Miguel NHS Annex | NORALA | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 130767 | Colongulo Elementary School | SURALLAH | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 130771 | Lambusong ES | SURALLAH | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 130782 | Shri- Visaya Elementary School | SURALLAH | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 130783 | Surallah CES | SURALLAH | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 130868 | Bukay Pait Elementary School | TANTANGAN | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 130870 | Dumadalig Integrated School | TANTANGAN | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 130879 | New Iloilo ES | TANTANGAN | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 130884 | Tantangan Central Elementary School | TANTANGAN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 316911 | New Lambunao IS | TANTANGAN | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 130808 | Datal Nabong ES | T'BOLI | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 130813 | Edwards ES | T'BOLI | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 130818 | Laconon IS | T'BOLI | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 130825 | Lamsine ES | T'BOLI | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 130829 | Lugan CES | T'BOLI | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 130844 | Talambong ES | T'BOLI | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 130846 | Talufo IS | T'BOLI | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 130847 | Tboli ES | T'BOLI | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 130968 | Aguil Elementary School | COLUMBIO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 304605 | Lebak Legislated National High School | LEBAK | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 316804 | Mangudadatu National High School - Villamonte Annex | LEBAK | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 304611 | Baluan Senior High School | PALIMBANG | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 304616 | KALIBUHAN NATIONAL HIGH SCHOOL | PALIMBANG | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 304602 | Senator Ninoy Aquino National High School | SEN. NINOY AQUINO | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Tacurong City | 131219 | Amado Fernandez Sr. CES | CITY OF TACURONG | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | General Santos City | 131267 | A. Biscayda Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | General Santos City | 131279 | Lanton Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | General Santos City | 131282 | Arizala Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | General Santos City | 210011 | H.N. Cahilsot Central Elementary School II | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Kidapawan City | 131334 | Manongol CES | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Kidapawan City | 131341 | Lapan Elementary School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Koronadal City | 131407 | Koronadal Central II ES | CITY OF KORONADAL (Capital) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Koronadal City | 304669 | Concepcion NHS | CITY OF KORONADAL (Capital) | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Koronadal City | 304672 | Marbel 7 National High School | CITY OF KORONADAL (Capital) | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 129843 | Mirasol ES | ALAMADA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 129849 | Rangayen ES | ALAMADA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130031 | Nicaan Central Elementary School | LIBUNGAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130175 | Miguel Intes (Katingawan) ES | MIDSAYAP | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130178 | Salunayan ES | MIDSAYAP | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130204 | Sta. Cruz ES | MIDSAYAP | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130058 | Kisandal ES | MAGPET | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 304706 | Inac High School | MAGPET | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 100922 | Braulio G. Dano Elementary School | MAKILALA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130085 | Indangan ES | MAKILALA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130088 | Makilala Central Elementary School | MAKILALA | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130094 | Biangan Elementary School | MAKILALA | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130095 | Buena Vida ES | MAKILALA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130096 | Buhay ES | MAKILALA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130105 | San Isidro ES | MAKILALA | 2nd | 1 | 45 | - | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130116 | Leboce ES | MAKILALA | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130125 | Villaflores ES | MAKILALA | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 207566 | Lower Saguing ES | MAKILALA | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 316539 | Malungon High School | MAKILALA | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 129992 | Tonganon ES | CARMEN | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130391 | Bituan ES | Tulunan | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | North Cotabato | 130394 | Nabundasan ES | TULUNAN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sarangani | 130469 | Margus Elementary School | GLAN | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sarangani | 130507 | Salakit Elementary School | KIAMBA | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sarangani | 130521 | Maasim CES | MAASIM | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sarangani | 304522 | Banate National High School | MALUNGON | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 304560 | Polomolok National High School | POLOMOLOK | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 501198 | Polomolok Creek Integrated School | POLOMOLOK | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 501847 | LR Morandante Integrated School | POLOMOLOK | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 502160 | Silway 7 Integrated School | POLOMOLOK | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 208527 | Tampakan SPED Center | TAMPAKAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 130891 | Lote Elementary School | TUPI | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 304575 | Tupi National High School | TUPI | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 501664 | Lunen Integrated School | TUPI | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 502385 | Juan-Loreto Tamayo Integrated School | TUPI | 1st | 1 | - | - | 160 | 160 | 4 | - | - | 483600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | South Cotabato | 130671 | Lake Sebu CES | LAKE SEBU | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 130970 | Lam-alis Elementary School | COLUMBIO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 209032 | Balnate Elementary School | COLUMBIO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 500761 | Upper Bunawan Integrated School | COLUMBIO | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 304590 | Isulan National High School | ISULAN (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 316801 | Sultan Ali Akbar Sinenggayan National High School | ISULAN (Capital) | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 131085 | Pinguiaman Elementary School | LAMBAYONG (MARIANO MARCOS) | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 500762 | Palumbe Integrated School | LAMBAYONG (MARIANO MARCOS) | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 500434 | Palavilla Integrated School | LUTAYAN | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 500716 | Antong Integrated School | LUTAYAN | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 131206 | Bannawag Elementary School | PRESIDENT QUIRINO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 130920 | Biwang Central School | BAGUMBAYAN | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 131003 | Salabaca Elementary School | ESPERANZA | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 304589 | Esperanza National High School | ESPERANZA | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 131032 | DATU GUIABAR PILOT SCHOOL | KALAMANSIG | 2nd | 1 | 675 | - | - | 675 | 15 | - | - | 2031000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 131044 | Pag-asa Elementary School | KALAMANSIG | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 131046 | Ricardo Cabaluna Memorial Elementary School | KALAMANSIG | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 304591 | Kalamansig National High School | KALAMANSIG | 2nd | 1 | - | 448 | - | 448 | 9 | - | - | 1343300 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region XII | Sultan Kudarat | 131129 | Salangsang Elementary School | LEBAK | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1354000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0
CY 2023 SF | Region XII | COTABATO CITY | 131264 | Don E. Sero Elementary School | COTABATO CITY | 1st | 1 | 180 | 0 | 0 | 180 | 4 |  |  | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Cotabato City | 316903 | CCNHS - ANNEX ( Bubong Site) | COTABATO CITY | 1st | 1 | 0 | 450 | 0 | 450 | 10 |  |  | 1448000 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1317680 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | General Santos City | 210011 | H.N. Cahilsot Central Elementary School II | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 675 | 0 | 0 | 675 | 15 |  |  | 2172000 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1976520 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | General Santos City | 317005 | Dadiangas North High School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 0 | 270 | 0 | 270 | 6 |  |  | 868800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 790608 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Kidapawan City | 304658 | Ginatilan National High School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 0 | 720 | 0 | 720 | 16 |  |  | 2316800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 2108288 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Kidapawan City | 304659 | Manongol National High School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 0 | 540 | 0 | 540 | 12 | 0 | 84 | 2691000 | Regional Office Implementation | 75% Allocation for Regular Supplier | 2490096 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Kidapawan City | 304661 | Kidapawan City National High School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 0 | 1080 | 0 | 1080 | 24 |  |  | 3475200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 3162432 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Kidapawan City | 304665 | Saniel Cruz National High School | CITY OF KIDAPAWAN (Capital) | 2nd |  | 0 | 540 | 0 | 540 | 12 | 0 | 84 | 2691000 | Regional Office Implementation | 75% Allocation for Regular Supplier | 2490096 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Kidapawan City | 304665 | Saniel Cruz National High School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 0 | 180 | 0 | 180 | 4 |  |  | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Kidapawan City | 304666 | Spottswood NHS | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 0 | 180 | 0 | 180 | 4 |  |  | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Kidapawan City | 304668 | Paco NHS | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Kidapawan City | 317101 | Linangkob National High School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 0 | 180 | 0 | 180 | 4 |  |  | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Kidapawan City | 317101 | Linangkob National High School | CITY OF KIDAPAWAN (Capital) | 2nd |  | 0 | 180 | 0 | 180 | 4 |  |  | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Kidapawan City | 317102 | Juan L. Gantuangco School of Arts and Trades | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 0 | 540 | 0 | 540 | 12 | 0 | 84 | 2691000 | Regional Office Implementation | 75% Allocation for Regular Supplier | 2490096 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Kidapawan City | 317102 | Juan L. Gantuangco School of Arts and Trades | CITY OF KIDAPAWAN (Capital) | 2nd |  | 0 | 180 | 0 | 180 | 4 |  |  | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Koronadal City | 131394 | Marbel 1 CES | CITY OF KORONADAL (Capital) | 2nd | 1 | 360 | 0 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Koronadal City | 304671 | Koronadal NCHS | CITY OF KORONADAL (Capital) | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Koronadal City | 317205 | Esperanza National High School – Annex, San Jose Campus | CITY OF KORONADAL (Capital) | 2nd | 1 | 0 | 540 | 0 | 540 | 12 |  |  | 1737600 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1581216 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 303624 | Cesar C. Cabaya Sr. HS | Libungan | 1st | 1 | 0 | 180 | 0 | 180 | 4 |  |  | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 130174 | Midsayap Pilot ES | Midsayap | 1st | 1 | 450 | 0 | 0 | 450 | 10 |  |  | 1448000 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1317680 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304415 | ANTIPAS NHS | ANTIPAS | 2nd | 1 | 0 | 720 | 0 | 720 | 16 |  |  | 2316800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 2108288 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304416 | Antipas NHS - Malire Annex | ANTIPAS | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304470 | Malatab HS | ANTIPAS | 2nd | 1 | 0 | 540 | 0 | 540 | 12 |  |  | 1737600 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1581216 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304436 | Greenfield NHS | ARAKAN | 2nd | 1 | 0 | 540 | 0 | 540 | 12 |  |  | 1737600 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1581216 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304439 | Marciano Dahan HS | ARAKAN | 2nd | 1 | 0 | 180 | 0 | 180 | 4 | 14 | 0 | 745380 | Regional Office Implementation | 75% Allocation for Regular Supplier | 671272 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304440 | Kabalantian HS | ARAKAN | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304442 | F. A. Andolana Mem. NHS | ARAKAN | 2nd | 1 | 0 | 180 | 0 | 180 | 4 |  | 0 | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304460 | Lanao Kuran NVTHS | ARAKAN | 2nd | 1 | 0 | 180 | 0 | 180 | 4 |  | 0 | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304471 | MALIBATUAN HIGH SCHOOL | ARAKAN | 2nd | 1 | 0 | 180 | 0 | 180 | 4 | 14 | 0 | 745380 | Regional Office Implementation | 75% Allocation for Regular Supplier | 671272 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 316534 | Meocan High School | ARAKAN | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304422 | Basak NHS | MAGPET | 2nd | 1 | 0 | 540 | 0 | 540 | 12 |  |  | 1737600 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1581216 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304463 | Magpet National High School | MAGPET | 2nd | 1 | 0 | 540 | 0 | 540 | 12 |  |  | 1737600 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1581216 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304464 | Mahongkog High School | MAGPET | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304465 | Temporan National High School | MAGPET | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304473 | Manobo NHS | MAGPET | 2nd | 1 | 0 | 540 | 0 | 540 | 12 |  |  | 1737600 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1581216 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304490 | Pangao-an NHS | MAGPET | 2nd | 1 | 0 | 720 | 0 | 720 | 16 |  |  | 2316800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 2108288 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 316501 | Manumba National HS | MAGPET | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 500460 | Sallab High School | MAGPET | 2nd | 1 | 0 | 0 | 80 | 80 | 2 |  |  | 258600 | Regional Office Implementation | 75% Allocation for Regular Supplier | 235326 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304423 | Bulakanon High School | MAKILALA | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304457 | Ricardo L. Ipong NHS | MAKILALA | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304466 | Makilala National High School | MAKILALA | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304434 | Don Antonio Jayme Mem. HS | PRESIDENT ROXAS | 2nd | 1 | 0 | 540 | 0 | 540 | 12 |  |  | 1737600 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1581216 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304496 | Pres. Roxas National High School | PRESIDENT ROXAS | 2nd | 1 | 0 | 720 | 0 | 720 | 16 |  |  | 2316800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 2108288 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304498 | Ilustre HS | PRESIDENT ROXAS | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 129948 | Rancho ES | Banisilan | 3rd | 1 | 180 | 0 | 0 | 180 | 4 |  |  | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304431 | Dalapitan HS | MATALAM | 3rd | 1 | 0 | 540 | 0 | 540 | 12 |  |  | 1737600 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1581216 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304477 | New Alimodian HS | MATALAM | 3rd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 316507 | Agustin M. Valdevieso, Sr. High School | MATALAM | 3rd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304462 | Lika NHS | M'LANG | 3rd | 1 | 0 | 540 | 0 | 540 | 12 |  |  | 1737600 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1581216 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304488 | Nueva Vida National High School | M'LANG | 3rd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304510 | New Rizal HS | M'LANG | 3rd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304504 | Sibsib High School | TULUNAN | 3rd | 1 | 0 | 135 | 0 | 360 | 3 | 0 | 21 | 672750 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | Region XII | North Cotabato | 316514 | Minapan High School | TULUNAN | 3rd | 1 | 0 | 270 | 0 | 540 | 6 |  |  | 868800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | Region XII | Sarangani | 304530 | Leonard Young Sr. National High School | GLAN | Lone | 1 | 0 | 135 | 0 | 720 | 3 |  |  | 434400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | Region XII | Sarangani | 500265 | Datu Molod IS | MAASIM | Lone | 1 | 0 | 270 | 0 | 485 | 6 |  |  | 868800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | Region XII | Sarangani | 500711 | Francisco A. Cagang Sr. Integrated School | MALAPATAN | Lone | 1 | 0 | 0 | 200 | 320 | 5 |  |  | 646500 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2023 SF | Region XII | South Cotabato | 130721 | Dole Cannery CES | POLOMOLOK | 1st | 1 | 0 | 135 | 0 | 180 | 3 |  |  | 434400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | Region XII | South Cotabato | 316704 | Lamba NHS - Banga NHS Annex | BANGA | 2nd | 1 | 0 | 270 | 0 | 180 | 6 |  |  | 868800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | Region XII | South Cotabato | 316714 | Malaya NHS - Banga NHS Annex | BANGA | 2nd | 1 | 0 | 135 | 0 | 135 | 3 |  | 21 | 672750 | Regional Office Implementation | 75% Allocation for Regular Supplier | 622524 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | South Cotabato | 316914 | El Nonok IS | BANGA | 2nd | 1 | 270 | 0 | 0 | 180 | 6 |  |  | 868800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | Region XII | South Cotabato | 316914 | El Nonok IS | BANGA | 2nd | 1 | 270 | 0 | 0 | 180 | 6 |  |  | 868800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | Region XII | South Cotabato | 100777 | Datal Ligaw Elementary School | LAKE SEBU | 2nd | 1 | 0 | 180 | 0 | 270 | 4 |  |  | 579200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region XII | South Cotabato | 130658 | Bakdulong Elementary School | LAKE SEBU | 2nd | 1 | 0 | 180 | 0 | 180 | 4 |  |  | 579200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region XII | South Cotabato | 281569 | Datu Kahar Macasayon ES | LAKE SEBU | 2nd | 1 | 0 | 180 | 0 | 270 | 4 |  |  | 579200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region XII | South Cotabato | 130810 | Demamis ES | T'BOLI | 2nd | 1 | 0 | 180 | 0 | 135 | 4 |  |  | 579200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region XII | South Cotabato | 130848 | T'bolok Elementary School | T'BOLI | 2nd | 1 | 0 | 180 | 0 | 135 | 4 |  |  | 579200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region XII | Sultan Kudarat | 304588 | Columbio National High School | COLUMBIO | 1st | 1 | 0 | 180 | 0 | 270 | 4 |  |  | 579200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region XII | Sultan Kudarat | 304625 | Telafas National High School | COLUMBIO | 1st | 1 | 0 | 270 | 0 | 270 | 6 |  |  | 868800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | Region XII | Sultan Kudarat | 304596 | Laguilayan National High School | ISULAN (Capital) | 1st | 1 | 0 | 180 | 0 | 270 | 4 |  |  | 579200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region XII | Sultan Kudarat | 304614 | New Pangasinan National High School | ISULAN (Capital) | 1st | 1 | 0 | 270 | 0 | 135 | 6 |  |  | 868800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | Region XII | Sultan Kudarat | 304595 | Kapingkong National High School | LAMBAYONG (MARIANO MARCOS) | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | Region XII | Sultan Kudarat | 304598 | Pimbalayan National High School - Lambayong Annex | LAMBAYONG (MARIANO MARCOS) | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | Region XII | Sultan Kudarat | 304607 | Madanding National High School | LAMBAYONG (MARIANO MARCOS) | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | Region XII | Sultan Kudarat | 304608 | Maligaya National High School | LAMBAYONG (MARIANO MARCOS) | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 790608 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 304609 | Mamali National High School | LAMBAYONG (MARIANO MARCOS) | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 395304 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 304606 | Lutayan National High Schoool | LUTAYAN | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 790608 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 500716 | Antong Integrated School | Lutayan | 1st | 1 | - | - | 200 | 200 | 5 | - | - | 646500 | Regional Office Implementation | 75% Allocation for Regular Supplier | 588315 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 304594 | Kalanawe II National High School | PRESIDENT QUIRINO | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 395304 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 304617 | President Quirino National High School | PRESIDENT QUIRINO | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 790608 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 304618 | Central Mangilala High School - President Quirino Annex | PRESIDENT QUIRINO | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 395304 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 130910 | Bagumbayan Central Elementary School | BAGUMBAYAN | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 790608 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 131124 | Keytodac Central School | LEBAK | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 790608 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 304619 | Purikay National High School | LEBAK | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 304626 | Tran National High School | LEBAK | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 316804 | Mangudadatu National High School - Villamonte Annex | LEBAK | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 304610 | Milbuk National High School | PALIMBANG | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 304611 | Baluan Senior High School | PALIMBANG | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 304615 | Palimbang National High School | PALIMBANG | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Tacurong City | 304579 | Apolinario S. Bernardo National High School | CITY OF TACURONG | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 790608 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Tacurong City | 304620 | Rajah Muda NHS | CITY OF TACURONG | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1 | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Tacurong City | 304627 | Virginia F. Griño National High School | CITY OF TACURONG | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 790608 | Completed | 1 | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1 | 2025-02-02 | 2025-02-01