## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | NO. OF CL | SCOPE OF WORK | PROJECT ALLOCATION | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated/ Abandoned | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of CL Terminated/ Abandoned | No. of Sites Reverted.1 | No. of Sites Not yet started.1 | No. of Sites Under Procurement.1 | No. of Sites On Going.1 | No. of Sites Completed.1 | No. of Sites Terminated/ Abandoned.1 | Previous % | Difference | Month Completed | OGP SCHOOLS with DCP Packages | TO BE COMPLETED BY 2023 | TO BE COMPLETED BY 2023.1 | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | BBM ADMINISTRATION | Batch | Municipality Class | Provision of Solar Panel
LMS 2020 | CARAGA | Agusan del Norte | 131592 | Tinigbasan ES | TUBAY | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR,SLOPE PROTECTION, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 21247319.3187 | 0 | completed | 1 | 00:00:00 | 00:00:00 | INFRA-2021-015 | 0 | August 3, 2021 | August 11, 2021 | August 23, 2021 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Agusan del Norte | 131592 | Tinigbasan ES | TUBAY | 2 |  | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR,SLOPE PROTECTION, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM |  | 0 | completed | 1 | 00:00:00 | 00:00:00 | INFRA-2021-015 | 0 | August 3, 2021 | August 11, 2021 | August 23, 2021 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Agusan del Sur | 305479 | Kolambugan National High School | SIBAGAT | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 21060050.7338 | 21014420.71 | completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 | 00:00:00 | 00:00:00 | INNOVATI CONSTRUCTION CORP | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Agusan del Sur | 305479 | Kolambugan National High School | SIBAGAT | 2 |  | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM |  | 21014420.71 | completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 | 00:00:00 | 00:00:00 | INNOVATI CONSTRUCTION CORP | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Bayugan City | 131607 | New Salem ES | CITY OF BAYUGAN | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 21432580.1464 | 21382541.73 | Completed | 1 | 00:00:00 | 00:00:00 | 2021-008 | 2021-008 | July 13, 2021 | July 21, 2021 | August 2, 2021 | August 6, 2021 | 00:00:00 | Thearis Builders and Supply | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Bayugan City | 131607 | New Salem ES | CITY OF BAYUGAN | 1 |  | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM |  | 21382541.73 | Completed | 1 | 00:00:00 | 00:00:00 | 2021-008 | 2021-008 | July 13, 2021 | July 21, 2021 | August 2, 2021 | August 6, 2021 | 00:00:00 | Thearis Builders and Supply | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Bislig City | 132626 | Pamaypayan ES | CITY OF BISLIG | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19163303.3063 | 19125272.89 | COMPLETED | 1 | 2022-01-11 | 2022-03-02 | LMS_BISLIG CITY_001 | LMS_BISLIG CITY_001 | 2021-07-13 | 2021-07-21 | 2021-08-03 | 2021-08-10 | 2021-08-23 | MN Bayalas Construction | PCAB Category "B", Lic. No.: 34251 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Dinagat Island | 132391 | A. Ecleo Elementary School | DINAGAT | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19402338.5115 | 14100000 | Completed | 1 | 2021-12-01 | 2022-01-12 | CONSTRUCTION INFRA21-002 | 0 | 2021-07-13 | 2021-07-23 | 2021-08-05 | 2021-09-27 | 2021-10-01 | RJB CONSTRUCTION | COMPLETED\ | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Siargao | 132196 | Pacifico Primary School | SAN ISIDRO | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 21210000 | 19000000 | Completed | 1 | 2021-11-24 | 00:00:00 | BEFF-INFRA2021-004 | 0 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-08-03 | 2021-08-13 | WINDFALL | contract duration extended | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Surigao City | 132276 | Arturo Borja ES | SURIGAO CITY (Capital) | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18560762.8515 | 18532126.31 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-08-10 | FOR ISSUANCE | RJB Construction & Supply | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Surigao del Norte | 214011 | Tiltilan Elementary School | GIGAQUIT | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15998830.9734 | 15971550.75 | completed | 1 | 2021-11-02 | 00:00:00 | 2021-005-BEFF-CARAGA | 005-2021 | 2021-07-07 | 2021-07-14 | 2021-07-26 | 2021-08-02 | 2021-08-04 | RJB CONSTRUCTION AND SUPPLY | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Surigao del Norte | 132429 | Cantugas Cul. Minorities ES | MAINIT | 2 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19223342.8674 | 19150635.95 | completed | 1 | 2021-12-09 | 00:00:00 | 2021-004-BEFF-CARAGA | 004-2021 | 2021-07-07 | 2021-07-14 | 2021-07-26 | 2021-08-09 | 2021-08-11 | CHIVES CONSTRUCTION AND SUPPLY | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Surigao del Sur | 132803 | Napanpanan Elementary School | Lingig | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19892960.4848 | 19859577 | Completed | 1 | December 28, 2021 | December 20, 2021 | LMS 2020 - R XIII - SURIGAO DEL SUR - 001 | 2021 - 15 | July 15, 2021 | July 27, 2021 | August 5, 2021 | August 24, 2021 | September 07, 2021 | RELY CONSTRUCTION AND SUPPLY | Completed on time | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Tandag City | 132958 | Banahao Elementary School | CITY OF TANDAG (Capital) | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15432866.1651 | 0 | Completed | 1 | December 15, 2021 | 00:00:00 | 0 | 0 | July 8, 2021 | July 22, 2021 | August 2, 2021 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2021 | CARAGA | Butuan City | 281539 | Salvacion Indigenous Community Elementary School | BUTUAN CITY (Capital) | 1 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15725955.42 | 0 | Ongoing | 0.48 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.48 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | CARAGA | Cabadbaran City | 131524 | Mahaba Elementary school | CITY OF CABADBARAN | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18753240.13 | 0 | Ongoing | 0.4 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.4 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2022 | CARAGA | Agusan del Norte | 131530 | Balangbalang ES | REMEDIOS T. ROMUALDEZ | 2 | 1 | 4 | CONSTRUCTION OF TWO (2) UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR,SLOPE PROTECTION, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 22633517.1088 | 12091132.49 | Completed | 1 | 2023-11-22 | 2023-11-22 | 2023-001-LMS-CARAGA | 006-2023 | 2023-04-20 | 2023-04-27 | 2023-05-09 | 2023-05-24 | 2023-05-26 | AMALGO CONSTRUCTION | With Time Extension due to Extra Work | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | CARAGA | Dinagat Island | 304823 | Cab-ilan National High School | DINAGAT | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 25399321.6421 | 11736814.2 | Completed | 1 | 2024-05-25 | 2024-06-22 | LMS-001 | 44958 | 18/04/2022 | 29/04/2022 | 13/05/2022 | 2022-06-07 | 2022-07-26 | RJB CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | CARAGA | Dinagat Island | 132316 | Osmeña Elementary School | LIBJO (ALBOR) | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 23245664.4637 | 21098025.14 | COMPLETED | 1 | 2024-11-20 | 2025-05-22 | INFRA2023-004 | INFRA2023-004 | 2023-12-04 | 2023-12-11 | 2024-01-03 | 2024-01-31 | 2024-05-25 | RJB CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 |  | 0 | 1 |  |  |  | CY 2024 |  |  | 1
LMS 2022 | CARAGA | Dinagat Island | 132317 | Plaridel Elementary School | LIBJO (ALBOR) | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 21422137.7841 | 21036508.36 | Completed | 1 | 2022-12-28 | 2023-06-06 | INFRA22-003-02 | PB-05-2023 | 2023-07-03 | 2023-07-10 | 2023-07-24 | 2023-08-14 | 2023-08-25 | ARDRAW | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | CARAGA | Siargao | 132186 | Katipunan Elementary School | PILAR | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20882792.8856 | 17970756.58 | Completed | 1 | 2022-12-28 | 2022-12-05 | BEFF-INFRA2022-008 | BEFF-INFRA2022-008 | 2022-03-31 | 2022-04-07 | 2022-04-21 | 2022-05-10 | 2022-05-19 | RELY CONSTRUCTION AND SUPPLY | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 |  | 1 |  |  |  |  | CY 2024 |  |  | 1
LMS 2022 | CARAGA | Siargao | 132207 | Bailan Elementary School | SANTA MONICA (SAPAO) | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20884952.7605 | 16246968.08 | Completed | 1 | 2022-12-28 | 2023-03-18 | BEFF-INFRA2022-009 | BEFF-INFRA2022-009 | 2022-03-31 | 2022-04-07 | 2022-04-21 | 2022-05-10 | 2022-05-19 | INNOVATI CONSTRUCTION CORP | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 |  | 1 |  |  |  |  | CY 2024 |  |  | 1
LMS 2022 | CARAGA | Surigao del Norte | 132349 | Little Baguio ES | BACUAG | 2 | 1 | 5 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND REPAIR/REHABILITATION OF 1 STY 1 CL DEPED STANDARD BUILDING | 17775494.1415 | 17586011.08 | COMPLETED | 1 | 2024-07-03 | 2023-11-06 | 2023LMSRO1-02 | SDOLU-LMS 2023-2 | 2023-11-20 | 2023-11-29 | 2023-12-13 | 2023-12-26 | 2024-01-05 | LAV CONSTRUCTION AND SUPPLY | DIVISION IMPLEMENTED ( SUSPENDED DUE TO NON PASSABLE SITE) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 |  | 0 | 1 |  |  |  | CY 2024 |  |  | 1
LMS 2022 | CARAGA | Surigao del Norte | 132463 | Sohoton ES | MALIMONO | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) UNIT ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND REPAIR/REHABILITATION OF 1STY 2 CL BLSB TYPE I BUILDING | 17220573.8108 | 10698569.48 | Completed | 1 | 2023-12-26 | 2024-04-29 | LMS 2022-RII-CAGAYAN-001 | INFRA2023 045 LOT 1 | 2023-05-08 | 2023-05-16 | 2023-05-29 | 2023-06-19 | 2023-06-22 | GANIE CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 |  | 0 | 1 |  |  |  | CY 2024 |  |  | 1
LMS 2022 | CARAGA | Surigao del Norte | 132528 | Gacepan ES | SISON | 2 | 1 | 5 | CONSTRUCTION OF ONE (1) UNIT ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND REPAIR/REHABILITATION OF TWO (2) 1STY 3 CL BLSB TYPE I BUILDING | 19503501.2023 | 15072295.7 | Completed | 1 | 2023-11-07 | February 13m 2024 | LMS 2022-RII-CAGAYAN-002 | INFRA2023 045 LOT 2 | 2023-05-08 | 2023-05-16 | 2023-05-29 | 2023-06-19 | 2023-06-22 | YZK CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 |  | 0 | 1 |  |  |  | CY 2024 |  |  | 1
LMS 2022 | CARAGA | Surigao del Norte | 132547 | SALVACION ES | TAGANA-AN | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) UNIT ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND REPAIR/REHABILITATION OF TWO (2) UNITS 1STY 2 CL BLSB TYPE I BUILDING | 17808072.6712 | 14214688.77 | COMPLETED | 1 | 2023-07-18 | 2024-02-02 | 2022-004-LMS-CARAGA | 003-2023 | 2022-12-28 | 2023-01-05 | 2023-01-17 | 2023-02-01 | 2023-02-03 | DANREV CONSTRUCTION AND SUPPLY | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 |  | 0 | 1 |  |  |  | CY 2024 |  |  | 1
LMS 2022 | CARAGA | Surigao del Sur | 214548 | Tabinas Indigenous Community Elementary School | CARMEN | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM, AND FLOOD MARKER | 21084577.8768 | 17818880.19 | Completed | 1 | 2024-05-15 | 2024-08-01 | CY2023 LMS | CY2023 LMS | 2023-06-26 | 2023-07-03 | 2023-07-17 | 2023-08-15 | 2023-09-13 | Rely Construction and Supply | with Time Extensions due to unworkable days due to bad weather condition and delays in the delivery of materials due to unpassable road | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 0 | 1 |  |  |  | CY 2023 |  |  | 1
LMS 2023 | CARAGA | Agusan del Norte | 131531 | Humilog ES | REMEDIOS T. ROMUALDEZ | 2 | 1 | 4 | CONSTRUCTION OF TWO (2) UNITS ONE (1) STOREY TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM COLLECTOR, | 17170000.1 | 14766095.03 | Ongoing | 0.99 | 00:00:00 | 00:00:00 | LMS 2023 - CARAGA - AGUSAN DEL NORTE - 001 | LMS 2023 - CARAGA - AGUSAN DEL NORTE - 001 | 00:00:00 | 00:00:00 | 00:00:00 | 2023-07-26 | 2023-08-07 | Jodels Construction Supplies & Merchandise | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.75 | 0.24 | 6.25 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | CARAGA | Dinagat Island | 132316 | Osmeña Elementary School | LIBJO (ALBOR) | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOM SCHOOL BUILDING (WITH COMMON TOILET), with Provision of WATER SYSTEM-Deep Well Design with electric-powered Submersible water pump, School Furniture, Perimeter Solar Lighting System | 17166772.68 | 13427411.97 | Completed | 1 | 2024-02-15 | 2024-03-25 | INFRA2023-002 | INFRA2023-004 | 2023-05-02 | 2023-05-16 | 2023-05-25 | 2023-06-02 | 2023-07-20 | DANREV | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | CARAGA | Siargao | 132169 | Halian Elementary School | DEL CARMEN | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17169796.75 | 16945355.98 | Completed | 1 | 2024-04-08 | 2024-07-10 | BEFF-INFRA2023-018 | BEFF-INFRA2023-018 | 2024-01-26 | 2024-02-07 | 2024-02-20 | 2024-03-05 | 2024-03-08 | RBEP Construction | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.24 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | CARAGA | Siargao | 132149 | Corazon Elementary School | GENERAL LUNA | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17169796.75 | 16943551 | Completed | 1 | 2024-04-08 | 2024-07-10 | BEFF-INFRA2023-019 | BEFF-INFRA2023-019 | 2024-01-26 | 2024-02-07 | 2024-02-20 | 2024-03-05 | 2024-03-08 | RBEP Construction | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.24 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | CARAGA | Surigao del Norte | 132543 | Laurel ES | TAGANA-AN | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOM SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17165004.86 | 12091132.49 | Completed | 1 | 2023-11-22 | 2023-11-22 | 2023-001-LMS-CARAGA | 006-2023 | 2023-04-20 | 2023-04-27 | 2023-05-09 | 2023-05-24 | 2023-05-26 | AMALGO CONSTRUCTION | With Time Extension due to Extra Work | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | CARAGA | Surigao del Sur | 305747 | Gacub Atad S. Iligan Tribal National High School | CARMEN | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER SOLAR LIGHTING SYSTEM, AND WATER SYSTEM | 14359089.13 | 11736814.2 | Completed | 1 | 2024-05-25 | 2024-06-22 | LMS-001 | 2023 - 002 | 2023-10-02 | 2023-10-16 | 2023-10-25 | 2023-11-02 | 2023-12-20 | RELY CONSTRUCTION AND SUPPLY | With Time Extension due to Extra Work | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.24 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | CARAGA | Tandag City | 136972 | Pag-asa Tribal Community Elementary School | CITY OF TANDAG (Capital) | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 22972431.7 | 22744896.06 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | CYL Construction and Supply | With Time Extension due to Extra Work | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.5013 | 0.4987 | 5.25 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2024 | CARAGA | Agusan del Norte | 131588 | RAM Elementary School | TUBAY | 2nd | 1 | 4 | : CONSTRUCTION OF TWO (2) UNITS ONE (1) STOREY TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 23088243.68 | 0 | Ongoing | 0.7 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.7 | [9 empty] | 5th | 1
LMS 2024 | CARAGA | Agusan del Sur | 212051 | Jose T. Cuyos, Sr. I PS | ROSARIO | 1st | 1 | 4 | CONSTRUCTION OF TWO(2) UNITS - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE and SOLAR PV ENERGY SYSTEM | 20300220.62 | 17777918.71 | Completed | 1 | 2025-01-07 | 2025-01-07 | 2024-06-028 | 2024-04-010 | 2024-05-01 | 2024-05-07 | 2024-05-20 | 2024-06-05 | 2024-08-07 | OBMB BUILDERS | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 4th | 1
LMS 2024 | CARAGA | Bayugan City | 131643 | Taglibas ES | CITY OF BAYUGAN | 1st | 1 | 4 | CONSTRUCTION OF TWO (2) UNITS ONE (1) STOREY TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM COLLECTOR, | 22961884 | 0 | Ongoing | 0.85 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | Mt. Ararat realigned to Taglibas ES | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.85 |  |  |  |  | 1 | 4 | 22961884 |  |  | 4th | 1
LMS 2024 | CARAGA | Butuan City | 132072 | Doña Teodora ES | BUTUAN CITY (Capital) | 1st | 1 | 6 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 27272727.27 | 25950680.71 | Ongoing | 0.95 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | with suballotment already downloaded | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.95 | 0 | [9 empty] | 4th | 1
LMS 2024 | CARAGA | Cabadbaran City | 330101 | Puting Bato National High School | CITY OF CABADBARAN | 2nd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 22850951.92 | 2923591.71 | Ongoing | 0.9 | 2025-01-31 | 00:00:00 | 10312123 | 10312123 | 2023-11-13 | 2023-11-09 | 2023-12-06 | 2024-05-24 | 2024-05-24 | RELY CONSTRUCTION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.9 | 0 | [9 empty] | 5th | 1
LMS 2024 | CARAGA | Dinagat Island | 132558 | Sta Cruz Elementary School | TUBAJON | Lone | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY-FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR, SOLAR PV ENERGY SYSTEM, FURNITURES AND WATER SYSTEM | 22210093.61 | 21098025.14 | COMPLETED | 1 | 2024-11-20 | 2025-05-22 | INFRA2023-004 | INFRA2023-004 | 2023-12-04 | 2023-12-11 | 2024-01-03 | 2024-01-31 | 2024-05-25 | RJB CONSTRUCTION AND SUPPLY | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 5th | 1
LMS 2024 | CARAGA | Siargao | 132223 | N.Sering Comm. Sch.ES | SOCORRO | 1st | 1 | 2 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 16637813.31 | 16378679.01 | Ongoing | 0.18 | 2024-08-27 | 00:00:00 | BEFF-INFRA2024-001 | BEFF-INFRA2024-001 | 2024-01-27 | 2024-02-07 | 2024-04-02 | 2024-04-02 | 2024-05-29 | AN ESCALANTE CONSTRUCTION INC. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.18 | 0 | [9 empty] | 1st | 1
LMS 2024 | CARAGA | Surigao City | 132242 | Alegria ES | SURIGAO CITY (Capital) | 2nd | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 22395355.38 | 18148693.46 | Completed | 1 | 2025-01-21 | 2025-01-20 | 2023-11-577 | FY-2023-INFRA-015 | 2023-12-10 | 2023-12-18 | 2024-01-05 | 2024-07-26 | 2024-08-09 | RELY CONSTRUCTION AND SUPPLY INC. | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 1st | 1
LMS 2024 | CARAGA | Surigao del Norte | 132481 | Sani-Sani PS | PLACER | 2nd | 1 | 2 | CONSTRUCTION OF 1STY2CL (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 18036516.81 | 17823108.98 | COMPLETED | 1 | 2024-10-20 | 2024-12-09 | 2024-001-LMS-CARAGA | INFRA003-2024 | 2023-11-09 | 2023-11-16 | 2023-11-28 | 2024-05-09 | 2024-05-13 | RJB CONSTRUCTION AND SUPPLY | WITH TIME EXTENSION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 4th | 1
LMS 2024 | CARAGA | Surigao del Sur | 500571 | Pakwan Integrated School | LANUZA | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 21869030.83 | 21626168.4137 | Ongoing | 0.9 | 2025-04-12 | 00:00:00 | LMS 2024 - R XIII - SURIGAO DEL SUR - 003 | 008 - 2024 | 2023-11-09 | 2023-11-15 | 2023-11-30 | 2024-02-19 | 2024-10-14 | RELY CONSTRUCTION AND SUPPLY | Contract time extension approved due to impassable roads caused by severe weather | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.9 | 0 | [9 empty] | 4th | 1
LMS 2024 | CARAGA | Tandag City | 132965 | Hitaob Elementary School | CITY OF TANDAG (Capital) | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 22162351.68 | 17311234.52 | Ongoing | 0.4 | 2025-01-07 | 00:00:00 | 2023-11-201 | 0 | 2023-11-29 | 2023-12-07 | 2023-12-27 | 2024-01-10 | 2024-07-09 | Grandstellar Builders Inc. | with time extension and suspension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.4 | 0 | [9 empty] | 4th | 1