## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of Sites Terminated | No. of CL Terminated | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | BBM TERM COMPLETED | Unnamed: 46
REPAIR 2020 | NCR | Caloocan City | 136632 | Amparo ES | KALOOKAN CITY | 1 | 1 | 25 | Repair of Classrooms | 10000000 | 1 | 9991962.22 | COMPLETED | 1 | 2021-08-24 |  |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City |  | Bagong Barrio SHS | KALOOKAN CITY | 1 | 1 | 2 | Repair of Classrooms | 3000000 | 1 | 2997588.67 | COMPLETED | 1 | 2021-08-24 | 2021-08-18 |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 136639 | Bagong Silang ES | KALOOKAN CITY | 1 | 1 | 15 | Repair of Classrooms | 5300000 | 1 | 5295739.98 | COMPLETED | 1 | 2021-08-24 | 2021-08-03 |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 319707 | Caloocan City Business High School | KALOOKAN CITY | 1 | 1 | 4 | Repair of Classrooms | 5000000 | 1 | 4995981.11 | COMPLETED | 1 | 2021-08-24 | 2021-08-18 |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 136633 | Camarin D ES | KALOOKAN CITY | 1 | 1 | 26 | Repair of Classrooms | 11000000 | 1 | 10991158.44 | COMPLETED | 1 | 2021-08-24 | 2021-06-29 |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 319701 | Cielito Zamora Junior High School | KALOOKAN CITY | 1 | 1 | 4 | Repair of classrooms | 4000000 | 1 | 3996784.89 | COMPLETED | 1 | 2021-08-24 |  |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 136636 | Congress ES | KALOOKAN CITY | 1 | 1 | 12 | Repair of Classrooms | 4735000 | 1 | 4731194.11 | COMPLETED | 1 | 2021-08-24 | 2021-08-23 |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City |  | Don Antonio Uy Remington SHS | KALOOKAN CITY | 1 | 1 | 2 | Repair of Classrooms | 2000000 | 1 | 1998392.44 | COMPLETED | 1 | 2021-08-24 | 2021-08-19 |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 223502 | Gabriela Silang ES (Bagong Silang ES - Annex) | KALOOKAN CITY | 1 | 1 | 12 | Repair of Classrooms | 4785000 | 1 | 4781153.92 | COMPLETED | 1 | 2021-08-24 | 2021-06-29 |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 136644 | Manuel L. Quezon ES | KALOOKAN CITY | 1 | 1 | 15 | Repair of Classrooms | 9000000 | 1 | 8992766 | COMPLETED | 1 | 2021-08-24 |  |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 319705 | Maypajo High School | KALOOKAN CITY | 1 | 1 | 12 | Repair of Classrooms | 5937257 | 1 | 5937256.44 | COMPLETED | 1 | 2020-12-07 | 11/16/2020 |  | PCA-2020-INFRA-001 | 1/23/2020 | 11/25/2019 | 2/24/2020 | 2020-06-03 | 2020-09-08 | EV & E CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 136646 | NHC ES | KALOOKAN CITY | 1 | 1 | 10 | Repair of Classrooms | 5000000 | 1 | 4995981.11 | COMPLETED | 1 | 2021-08-24 |  |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 305378 | NHC HS | KALOOKAN CITY | 1 | 1 | 12 | Repair of Classrooms | 4310000 | 1 | 4306535.72 | COMPLETED | 1 | 2021-08-24 | 2021-06-29 |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 136655 | Sampaguita Elementary School | KALOOKAN CITY | 1 | 1 | 15 | Repair of Classrooms | 5900000 | 1 | 5895257.71 | COMPLETED | 1 | 2021-08-24 | 2021-06-29 |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City |  | Vicente Malapitan North SHS | KALOOKAN CITY | 1 | 1 | 6 | Repair of Classrooms | 7000000 | 1 | 6994373.56 | COMPLETED | 1 | 2021-08-24 |  |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 305388 | Caloocan HS | KALOOKAN CITY | 2 | 1 | 40 | Repair of Classrooms | 10000000 | 1 | 9991962.22 | COMPLETED | 1 | 2021-08-24 |  |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 136618 | Gregoria de Jesus ES | KALOOKAN CITY | 2 | 1 | 9 | Repair of Classrooms | 2500000 | 1 | 2497990.56 | COMPLETED | 1 | 2021-08-24 |  |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 305392 | M. B. Asistio Sr. HS Unit 1 | KALOOKAN CITY | 2 | 1 | 2 | Repair of Classrooms | 3000000 | 1 | 2997588.67 | COMPLETED | 1 | 2021-08-24 | 2021-08-18 |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 305391 | M. B. Asistio, Sr. HS | KALOOKAN CITY | 2 | 1 | 2 | Repair of Classrooms | 3000000 | 1 | 2997588.67 | COMPLETED | 1 | 2021-08-24 | 2021-08-18 |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | City of San Juan | 136746 | San Juan ES | CITY OF SAN JUAN | 0 | 1 | 18 | Repair of Classrooms | 5927946 | 1 | 4700481.32 | COMPLETED | 1 | April 23, 2021 |  | REPAIR2020-NCR-SANJUAN-001 | 2020-PB-001 | November 21, 2019 | December 6, 2019 | December 19, 2019 | February 18, 2020 | December 7, 2020 | GOLDEN SHOVEL BUILDERS EARTHMOVING AND DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Las Piñas City | 136782 | Almanza Elementary School | CITY OF LAS PIÑAS | 0 | 1 | 18 | Repair of Classrooms | 2617692 | 1 | 2617691.75 | COMPLETED | 1 | 2021-01-21 | 2020-12-18 | [6 empty] | 2020-09-23 | Image Builders and General Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Las Piñas City | 320304 | Las Pinas City National Science High School | CITY OF LAS PIÑAS | 0 | 1 | 12 | Repair of Classrooms | 2918934 | 1 | 2918993.98 | COMPLETED | 1 | 2021-01-21 | 2021-04-20 | [6 empty] | 2020-09-23 | RM Mangubat Realty and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Las Piñas City | 320301 | Las Pinas East NHS - Equitable Annex | CITY OF LAS PIÑAS | 0 | 1 | 32 | Repair of Classrooms | 3295088 | 1 | 3295087.25 | COMPLETED | 1 | 2021-01-21 | 2020-12-18 | [6 empty] | 2020-09-23 | Image Builders and General Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Las Piñas City | 136786 | Moonwalk ES - Mikesell Annex | CITY OF LAS PIÑAS | 0 | 1 | 13 | Repair of Classrooms | 1312503 | 1 | 1312503 | COMPLETED | 1 | 2021-01-21 | 2021-01-20 | [6 empty] | 2020-09-23 | REDCAR Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 136699 | Bangkal ES Main | CITY OF MAKATI | 1 | 1 | 36 | Repair of Classrooms | 2500000 | 1 | 1910420.43 | COMPLETED | 1 | March 11, 2021 | March 11, 2021 | 2020-007 | 2020-007 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 4, 2020 | Dreamworxs Builders & Trading, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 305409 | Gen. Pio del Pilar NHS | CITY OF MAKATI | 1 | 1 | 17 | Repair of Classrooms | 3926450 | 1 | 2653829.77 | COMPLETED | 1 | March 10, 2021 | March 10, 2021 | 2020-009 | 2020-009 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 3, 2020 | Zaneya Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 136706 | Jose Magsaysay ES | CITY OF MAKATI | 1 | 1 | 30 | Repair of Toilets | 4139315.84 | 1 | 4128981.28 | COMPLETED | 1 | March 11, 2021 | March 11, 2021 | 2020-006 | 2020-006 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 4, 2020 | St. Gabriel Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 136708 | Nicanor C. Garcia, Sr. ES | CITY OF MAKATI | 1 | 1 | 11 | Repair of Classrooms | 1917013 | 1 | 1906020.37 | COMPLETED | 1 | March 11, 2021 | March 11, 2021 | 2020-006 | 2020-006 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 4, 2020 | St. Gabriel Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 136715 | Palanan ES | CITY OF MAKATI | 1 | 1 | 40 | Repair of Classrooms | 4000000 | 1 | 2639426.63 | COMPLETED | 1 | March 11, 2021 | March 11, 2021 | 2020-007 | 2020-007 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 4, 2020 | Dreamworxs Builders & Trading, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 136694 | Fort Bonifacio ES | CITY OF MAKATI | 2 | 1 | 15 | Repair of Classrooms | 1730417 | 1 | 1481252.95 | COMPLETED | 1 | March 11, 2021 | March 11, 2021 | 2020-011 | 2020-011 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 4, 2020 | Sherf Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 305411 | Fort Bonifacio HS | CITY OF MAKATI | 2 | 1 | 52 | Repair of Classrooms | 2152386.5 | 1 | 1600572.72 | COMPLETED | 1 | March 10, 2021 | March 10, 2021 | 2020-009 | 2020-009 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 3, 2020 | Zaneya Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 136710 | Nemesio I. Yabut ES | CITY OF MAKATI | 2 | 1 | 36 | Repair of Classrooms | 3097855 | 1 | 3072264.56 | COMPLETED | 1 | March 11, 2021 | March 11, 2021 | 2020-010 | 2020-010 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 4, 2020 | MCORR Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 320001 | Pitogo HS | CITY OF MAKATI | 2 | 1 | 38 | Repair of Classrooms | 2940794.54 | 1 | 2691571.12 | COMPLETED | 1 | March 11, 2021 | March 11, 2021 | 2020-011 | 2020-011 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 4, 2020 | Sherf Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 136696 | Rizal ES | CITY OF MAKATI | 2 | 1 | 54 | Repair of Classrooms | 2932017 | 1 | 2906048.66 | COMPLETED | 1 | March 11, 2021 | March 11, 2021 | 2020-010 | 2020-010 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 4, 2020 | MCORR Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 136712 | South Cembo ES | CITY OF MAKATI | 2 | 1 | 49 | Repair of Toilets | 6187099.88 | 1 | 6154750.12 | COMPLETED | 1 | March 22, 2021 | March 22, 2021 | 2020-008 | 2020-008 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 15, 2020 | TM Abad Construction | reverted due to previous project cityhall | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 136698 | West Rembo ES | CITY OF MAKATI | 2 | 1 | 12 | Repair of Classrooms | 1406103 | 1 | 1156979.1 | COMPLETED | 1 | March 11, 2021 | March 11, 2021 | 2020-011 | 2020-011 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 4, 2020 | Sherf Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Malabon City | 340567 | SHS within Imelda ES | CITY OF MALABON | 0 | 1 | 9 | Repair of Classrooms | 2182877 | 1 | 2182876.16 | COMPLETED | 1 |  |  |  | 2020-INFRA-09-0006 |  |  | 01/31/2020 (120 CDs) |  | 2020-10-12 | Tapnio & Tan Construction & Development Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Malabon City | 136850 | Tinajeros ES | CITY OF MALABON | 0 | 1 | 6 | Repair of Classrooms | 1677247 | 1 | 1677246.48 | COMPLETED | 1 |  | 2020-12-21 |  | 2020-INFRA-09-0005 |  |  | 01/31/2020 (120 CDs) |  | 2020-10-14 | Martian Builders & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Mandaluyong City | 500051 | Andres Bonifacio Integrated School | CITY OF MANDALUYONG | 0 | 1 | 40 | Repair of Classrooms | 6421055 | 1 | 6421054.08 | COMPLETED | 1 | November 16, 2020 | November 16, 2020 | 2020-Mandaluyong-01 | No.1 | January 27 - February 14, 2020 | February 3, 2020 | February 17, 2020 | February 20, 2020 | September 7, 2020 | B.Valencerina Trading & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Mandaluyong City | 136665 | DONA PILAR ELEMENTARY SCHOOL | CITY OF MANDALUYONG | 0 | 1 | 40 | Repair of Classrooms | 9402013 | 1 | 9402012.41 | COMPLETED | 1 | January 11, 2021 | January 11, 2021 | 2020-Mandaluyong-04 | No.04 | August 10, 2020 - August 28, 2020 | August 18, 2020 | September 1, 2020 | September 4, 2020 | October 15, 2020 | Tracsom Builders, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Mandaluyong City | 500333 | EULOGIO RODRIGUEZ INTEGRATED SCHOOL | CITY OF MANDALUYONG | 0 | 1 | 40 | Repair of Classrooms | 9944054 | 1 | 9844613 | COMPLETED | 1 | January 11, 2021 | January 11, 2021 | 2020-Mandaluyong-04 | No.04 | August 10, 2020 - August 28, 2020 | August 18, 2020 | September 1, 2020 | September 4, 2020 | October 15, 2020 | Tracsom Builders, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Mandaluyong City | 500331 | ISAAC LOPEZ INTEGRATED SCHOOL | CITY OF MANDALUYONG | 0 | 1 | 40 | Repair of Classrooms | 10150751 | 1 | 10049242.84 | COMPLETED | 1 | January 11, 2021 | January 11, 2021 | 2020-Mandaluyong-04 | No.04 | August 10, 2020 - August 28, 2020 | August 18, 2020 | September 1, 2020 | September 4, 2020 | October 15, 2020 | Tracsom Builders, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Mandaluyong City | 107975 | Mandaluyong Addition Hills ES | CITY OF MANDALUYONG | 0 | 1 | 36 | Repair of Classrooms | 8500786 | 1 | 8500785.42 | COMPLETED | 1 | January 11, 2021 | January 11, 2021 | 2020-Mandaluyong-04 | No.04 | August 10, 2020 - August 28, 2020 | August 18, 2020 | September 1, 2020 | September 4, 2020 | October 15, 2020 | Tracsom Builders, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Mandaluyong City | 136660 | MANDALUYONG ELEMENTARY SCHOOL | CITY OF MANDALUYONG | 0 | 1 | 40 | Repair of Classrooms | 9474902 | 1 | 9380152.43 | COMPLETED | 1 | January 11, 2021 | January 11, 2021 | 2020-Mandaluyong-04 | No.04 | August 10, 2020 - August 28, 2020 | August 18, 2020 | September 1, 2020 | September 4, 2020 | October 15, 2020 | Tracsom Builders, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Mandaluyong City | 305393 | Mandaluyong High School | CITY OF MANDALUYONG | 0 | 1 | 40 | Repair of classrooms | 9230097 | 1 | 9,137,795,.22 | COMPLETED | 1 | January 11, 2021 | January 11, 2021 | 2020-Mandaluyong-04 | No.04 | August 10, 2020 - August 28, 2020 | August 18, 2020 | September 1, 2020 | September 4, 2020 | October 15, 2020 | Tracsom Builders, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Mandaluyong City | 136669 | Nueve de Febrero Elementary School | CITY OF MANDALUYONG | 0 | 1 | 24 | Repair of Classrooms | 5180804 | 1 | 5180803.97 | COMPLETED | 1 | November 16, 2020 | November 16, 2020 | 2020-Mandaluyong-01 | No.1 | January 27 - February 14, 2020 | February 3, 2020 | February 17, 2020 | February 20, 2020 | September 7, 2020 | B.Valencerina Trading & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Mandaluyong City | 136670 | Pedro P. Cruz (Mauway) ES | CITY OF MANDALUYONG | 0 | 1 | 30 | Repair of Classrooms | 5470279 | 1 | 5470278.61 | COMPLETED | 1 | November 16, 2020 | November 16, 2020 | 2020-Mandaluyong-01 | No.1 | January 27 - February 14, 2020 | February 3, 2020 | February 17, 2020 | February 20, 2020 | September 7, 2020 | B.Valencerina Trading & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Mandaluyong City |  | Senate President Neptali A. Gonzales IS | CITY OF MANDALUYONG | 0 | 1 | 24 | Refurbishment of Classrooms | 35976579 | 1 | 35640463.12 | COMPLETED | 1 | January 11, 2021 | January 11, 2021 | 2020-Mandaluyong-05 | No.05 | August 10, 2020 - August 28, 2020 | August 18, 2020 | September 1, 2020 | September 4, 2020 | October 15, 2020 | Tracsom Builders, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Manila | 136434 | Gen. Vicente Lim Elementary School | TONDO | 1 | 1 | 21 | Repair of Classrooms | 6023971 | 1 | 6023970.46 | COMPLETED | 1 | April 20, 2021 | April 8, 2021 | [6 empty] | December 7, 2021 | Open Builders Incorporated | Bid-out/Waiting for the SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Manila | 136441 | R. Almario Elementary School | TONDO | 1 | 1 | 42 | Repair of Classrooms | 14700000 | 1 | 14592990.89 | COMPLETED | 1 | August 7, 2021 | [7 empty] | November 26, 2020 | CB Tampengco Construction & Supply | Under procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Manila | 222001 | R. Almario Elementary School - Parola Annex | TONDO | 1 | 1 | 8 | Repair of Classrooms | 5000000 | 1 | 4964096.43 | COMPLETED | 1 | August 7, 2021 | 2021-08-06 | [6 empty] | November 26, 2020 | CB Tampengco Construction & Supply | Under procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Manila | 136419 | Barrio Obrero Elementary School | TONDO | 2 | 1 | 85 | Repair of Classrooms | 20635044 | 1 | 20484829.86 | COMPLETED | 1 | August 7, 2021 | [7 empty] | November 26, 2020 | CB Tampengco Construction & Supply | Under procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 85 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Manila | 136453 | A. Mabini Elementary School | QUIAPO | 3 | 1 | 33 | Repair of Classrooms | 11550000 | 1 | 11465921.42 | COMPLETED | 1 | August 7, 2021 | [7 empty] | November 26, 2020 | CB Tampengco Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Manila | 136463 | Trinidad Tecson Elementary School | SAMPALOC | 4 | 1 | 44 | Repair of Classrooms | 10000000 | 1 | 9927204.69 | COMPLETED | 1 | August 7, 2021 | 2021-06-29 | [6 empty] | November 26, 2020 | CB Tampengco Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Manila | 136478 | H.J. Atienza Elementary School | MALATE | 5 | 1 | 53 | Repair of Classrooms | 15000000 | 1 | 14906250 | COMPLETED | 1 | August 7, 2021 | [7 empty] | November 26, 2020 | Aylan Construction & Trading | Under procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Manila | 136484 | Fernando Ma. Guerrero E.S. | SANTA ANA | 5 | 1 | 89 | Repair of Classrooms | 15000000 | 1 | 14906250 | COMPLETED | 1 | August 7, 2021 | [7 empty] | November 26, 2020 | Aylan Construction & Trading | Work suspended due to overlapping of work with DPWH retrofitting project | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Manila | 305313 | I. Villamor High School | SANTA ANA | 6 | 1 | 70 | Repair of Classrooms | 15678069 | 1 | 15678068.61 | COMPLETED | 1 | June 18, 2021 | 2021-06-02 | [6 empty] | November 26, 2020 | Lourbel Consttuction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Manila | 305316 | Mariano Marcos Memorial High School | SANTA ANA | 6 | 1 | 60 | Repair of Classrooms | 25000000 | 1 | 24842526.77 | COMPLETED | 1 | August 7, 2021 | [7 empty] | November 26, 2020 | Aylan Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Manila | 136485 | Sta. Ana ES | SANTA ANA | 6 | 1 | 71 | Repair of Classrooms | 25000000 | 1 | 24843750.08 | COMPLETED | 1 | August 7, 2021 | [7 empty] | November 26, 2020 | Aylan Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 71 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136671 | Barangka ES | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 318738.72 | COMPLETED | 1 | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136671 | Barangka ES | CITY OF MARIKINA | 1 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 320105 | 1 | 2928816.3 | COMPLETED | 1 | November 25,2020 | November 4,2020 |  |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | METER KING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136671 | Barangka ES | CITY OF MARIKINA | 1 |  | 1 | Repair of Toilets | 2928817 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | NATIONAL BUILDERS & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 319903 | Barangka NHS | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136672 | Industrial Valley ES | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 3421665.38 | COMPLETED | 1 | November 25,2020 | November 4,2020 |  |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | METER KING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136672 | Industrial Valley ES | CITY OF MARIKINA | 1 |  | 1 | Repair of Toilets | 3421666 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 | February 6,2020 | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 319907 | Jesus Dela Peña National High School | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136673 | Kalumpang ES | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 318738.72 | COMPLETED | 1 | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136673 | Kalumpang ES | CITY OF MARIKINA | 1 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 320105 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 319904 | Kalumpang National High School | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136674 | L. Victorino ES | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 995850.04 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136675 | Malanday ES | CITY OF MARIKINA | 1 | 1 | 32 | Provision of Make Shift Shower Rooms | 995851 | 1 | 318738.72 | COMPLETED | 1 | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136675 | Malanday ES | CITY OF MARIKINA | 1 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 320105 | 1 | 7310695.34 | COMPLETED | 1 | November 25,2020 | November 4,2020 |  |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | CRYSTAL DREAMS DEV. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136675 | Malanday ES | CITY OF MARIKINA | 1 |  | 1 | Repair of Toilets | 7310696 | 1 | 997131.04 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305402 | Malanday NHS | CITY OF MARIKINA | 1 | 1 | 32 | Provision of Make Shift Shower Rooms | 995851 | 1 | 995850.04 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305402 | Malanday NHS | CITY OF MARIKINA | 1 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 324347 | 1 | 323270.6 | COMPLETED | 1 | 2021-02-15 | February 4,2021 |  |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136676 | Marikina ES | CITY OF MARIKINA | 1 | 1 | 60 | Repair of classrooms | 7403981 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136676 | Marikina ES | CITY OF MARIKINA | 1 |  | 32 | Provision of Make Shift Shower Rooms | 997132 | 1 | 279466.16 | COMPLETED | 1 | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136676 | Marikina ES | CITY OF MARIKINA | 1 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 280834 | 1 | 3312296.07 | COMPLETED | 1 | November 25,2020 | November 4,2020 |  |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | METER KING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136676 | Marikina ES | CITY OF MARIKINA | 1 |  | 1 | Repair of Toilets | 3312297 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305401 | Marikina Science HS | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | GSMAXX CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136678 | San Roque ES | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 318738.72 | COMPLETED | 1 | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136678 | San Roque ES | CITY OF MARIKINA | 1 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 320105 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | NATIONAL BUILDERS & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 319905 | San Roque National High School | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305405 | Sta. Elena HS | CITY OF MARIKINA | 1 | 1 | 32 | Provision of Make Shift Shower Rooms | 997132 | 1 | 997131.04 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | NATIONAL BUILDERS & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136687 | Sto. Nino ES | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 318738.72 | COMPLETED | 1 | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136687 | Sto. Nino ES | CITY OF MARIKINA | 1 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 320105 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | November 3,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | GSMAXX CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 319906 | Sto. Nino National High School | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | NATIONAL BUILDERS & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305399 | Tañong HS | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 7403980.83 | COMPLETED | 1 | February 25,2021 | October 23,2020 |  |  | December 22,2019 | January 6,2020 | January 20,2020 | January 21,2020 | August 25,2020 | MMEEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305399 | Tañong HS | CITY OF MARIKINA | 1 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 320105 | 1 | 318738.72 | COMPLETED | 1 | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 | 2018-11-12 | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136680 | Concepcion ES | CITY OF MARIKINA | 2 | 1 | 32 | Provision of Make Shift Shower Rooms | 995851 | 1 | 995850.04 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | NATIONAL BUILDERS & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136680 | Concepcion ES | CITY OF MARIKINA | 2 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 320105 | 1 | 318738.72 | COMPLETED | 1 | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136680 | Concepcion ES | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 10786068 | 1 | 10786067.59 | COMPLETED | 1 | November 25,2020 | November 25,2020 |  |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | MMEEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 500052 | Concepcion Integrated School - Elem Level | CITY OF MARIKINA | 2 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 | 2018-11-12 | February 17,2020 | February 21,2020 | September 1,2020 | NATIONAL BUILDERS & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 500052 | Concepcion Integrated School - Elem. Level | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 5914427 | 1 | 5914426.7 | COMPLETED | 1 | November 25,2020 | November 25,2020 |  |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 26,2020 | TRIX =ZION VENTURES CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 500052 | Concepcion Integrated School - Elementary level | CITY OF MARIKINA | 2 |  | 42 | Repair of classrooms | 8570644 | 1 | 8570643.62 | COMPLETED | 1 | February 25,2021 | February 4,2021 |  |  | February 6,2020 | February 12,2020 | February 24,2020 | February 21,2020 | August 25,2020 | TRIX =ZION VENTURES CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 500052 | Concepcion Integrated School - Sec. Level | CITY OF MARIKINA | 2 |  | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 | 2018-11-12 | February 17,2020 | February 21,2020 | September 1,2020 | NATIONAL BUILDERS & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 500052 | Concepcion Integrated School - Sec. Level | CITY OF MARIKINA | 2 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 320105 | 1 | 318738.72 | COMPLETED | 1 | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 | 2018-11-12 | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136681 | Fortune ES | CITY OF MARIKINA | 2 | 1 | 36 | Repair of classrooms | 7041978 | 1 | 7041977.54 | COMPLETED | 1 | March 2,2021 | October 27,2020 |  |  | December 22,2019 | January 6,2020 | January 20,2020 | January 21,2020 | September 2,2020 | SHERF bUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136681 | Fortune ES | CITY OF MARIKINA | 2 |  | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 | January 6,2020 | February 17,2020 | February 21,2020 | September 1,2020 | GSMAXX CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136681 | Fortune ES | CITY OF MARIKINA | 2 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 404781 | 1 | 400821.7 | COMPLETED | 1 | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 | January 6,2020 | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136681 | Fortune ES | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 4308481 | 1 | 4308480.44 | COMPLETED | 1 | November 25,2020 | November 3,2020 |  |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | RUTHLAND TRADING and COSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 319902 | Fortune High School | CITY OF MARIKINA | 2 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | GSMAXX CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 319902 | Fortune High School | CITY OF MARIKINA | 2 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 314329 | 1 | 312243.75 | COMPLETED | 1 | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 319902 | Fortune High School | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 5483788 | 1 | 5483787.55 | COMPLETED | 1 | November 25,2020 | November 3,2020 |  |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | RUTHLAND TRADING and COSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136682 | H. Bautista ES | CITY OF MARIKINA | 2 | 1 | 32 | Provision of Make Shift Shower Rooms | 997132 | 1 | 997131.04 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136682 | H. Bautista ES | CITY OF MARIKINA | 2 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 320105 | 1 | 318738.72 | COMPLETED | 1 | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136682 | H. Bautista ES | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 7650423 | 1 | 7650422.56 | COMPLETED | 1 | November 25,2020 | November 4,2020 |  |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | M-TRI R CONSTRUCTION and TRADING CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136683 | Kapitan Moy ES | CITY OF MARIKINA | 2 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | NATIONAL BUILDERS & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305400 | Marikina Heights NHS | CITY OF MARIKINA | 2 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | November 3,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | GSMAXX CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305398 | Marikina HS | CITY OF MARIKINA | 2 | 1 | 32 | Provision of Make Shift Shower Rooms | 997132 | 1 | 997131.04 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | NATIONAL BUILDERS & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305398 | Marikina HS | CITY OF MARIKINA | 2 |  | 1 | Repair/Upgrading of Water System | 558843 | 1 | 997131.04 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | NATIONAL BUILDERS & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305398 | Marikina HS | CITY OF MARIKINA | 2 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 280667 | 1 | 279466.16 | COMPLETED | 1 | 2021-02-15 | February 4,2021 |  |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305398 | Marikina HS | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 7023649 | 1 | 7023648.16 | COMPLETED | 1 | November 25,2020 | November 25,2020 |  |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 26,2020 | TRIX =ZION VENTURES CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136677 | Nangka ES | CITY OF MARIKINA | 2 | 1 | 32 | Provision of Make Shift Shower Rooms | 997132 | 1 | 997131.04 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | GSMAXX CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136677 | Nangka ES | CITY OF MARIKINA | 2 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 318517 | 1 | 316107.25 | COMPLETED | 1 | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136677 | Nangka ES | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 4438637 | 1 | 4438636.97 | COMPLETED | 1 | November 25,2020 | November 25,2020 |  |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | RUTHLAND TRADING and COSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 319901 | Nangka HS | CITY OF MARIKINA | 2 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | GSMAXX CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 319901 | Nangka HS | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 6521366 | 1 | 6521365.42 | COMPLETED | 1 | November 25,2020 | November 4,2020 |  |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | BIG BOY CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA | 2 | 1 | 32 | Provision of Make Shift Shower Rooms | 997132 | 1 | 997131.04 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA | 2 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 320105 | 1 | 318738.72 | COMPLETED | 1 | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 2383433 | 1 | 2383432.62 | COMPLETED | 1 | November 25,2020 | November 3,2020 |  |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | RUTHLAND TRADING and COSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA | 2 |  | 30 | Repair of Classrooms | 12645660 | 1 | 12645659.02 | COMPLETED | 1 | February 25,2021 | October 28,2020 |  |  | February 6,2020 | February 12,2020 | February 24,2020 | February 26,2020 | August 27,2020 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305404 | Parang HS | CITY OF MARIKINA | 2 | 1 | 32 | Provision of Make Shift Shower Rooms | 997132 | 1 | 997131.04 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305404 | Parang HS | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 4551799 | 1 | 4551798.56 | COMPLETED | 1 | November 25,2020 | November 4,2020 |  |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | CRYSTAL DREAMS DEV. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136685 | SSS Village ES | CITY OF MARIKINA | 2 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | GSMAXX CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136685 | SSS Village ES | CITY OF MARIKINA | 2 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 320105 | 1 | 318738.72 | COMPLETED | 1 | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136685 | SSS Village ES | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 9711211 | 1 | 9711210.4 | COMPLETED | 1 | November 25,2020 | November 25,2020 |  |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | B.C. CUERPO CONSTRUCTION CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305630 | SSS Village NHS | CITY OF MARIKINA | 2 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | GSMAXX CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136686 | St. Mary ES | CITY OF MARIKINA | 2 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 1 | November 2,2020 | Oct. 30,2020 |  |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | GSMAXX CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136686 | St. Mary ES | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 1532844 | 1 | 1532843.09 | COMPLETED | 1 | November 25,2020 | November 11,2020 |  |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 28,2020 | GOLDEN SHOVEL BUILDERS EARTHMOVING and DEVT. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136686 | St. Mary ES | CITY OF MARIKINA | 2 |  | 28 | Repair of Classrooms | 5062768 | 1 | 5062767.88 | COMPLETED | 1 | March 2,2021 | October 27,2020 |  |  | February 6,2020 | February 12,2020 | February 24,2020 | February 26,2020 | September 2,2020 | SHERF bUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Muntinlupa City | 136910 | Bayanan Elementary School Unit I | CITY OF MUNTINLUPA | 0 | 1 | 56 | Repair of classrooms | 8102278 | 1 | 8040863.03 | COMPLETED | 1 | May 4, 2021 | 2021-05-01 |  |  | Oct. 6-27, 2020 | Oct. 15, 2020 | Oct. 28, 2020 | Oct. 29, 2020 | Dec. 23, 2021 | RGDG Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Muntinlupa City | 136912 | Cupang ES | CITY OF MUNTINLUPA | 0 | 1 | 47 | Repair of classrooms | 7910483 | 1 | 11033706.41 | COMPLETED | 1 | May 4, 2021 | 2021-04-30 |  |  | 11/25/19-12/16/19 | Dec. 3, 2019 | Dec. 16, 2019 | Dec. 20, 2019 | Dec. 23, 2021 | GMO Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 47 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Muntinlupa City | 303450 | Cupang Senior High School | CITY OF MUNTINLUPA | 0 | 1 | 60 | Repair of classrooms | 3203233 | 1 |  | COMPLETED | 1 | May 4, 2021 | Feb. 19, 2021 |  |  | Oct. 6-27, 2020 | Oct. 15, 2020 | Oct. 28, 2020 | Oct. 29, 2020 | Dec. 23, 2021 | GMO Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Muntinlupa City | 136900 | F. De Mesa ES | CITY OF MUNTINLUPA | 0 | 1 | 16 | Repair of Classrooms | 4145346 | 1 | 4145345.57 | COMPLETED | 1 | Jan.28, 2021 | Feb. 26, 2021 |  |  | 11/25/19-12/16/19 | Dec. 3, 2019 | Dec. 16, 2019 | Dec. 20, 2019 | Sept. 23, 2020 | RGDG Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Muntinlupa City | 136901 | Itaas Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 44 | Repair of Classrooms | 11708081 | 1 | 11621306.42 | COMPLETED | 1 | May 4, 2021 | 2021-04-17 |  |  | Oct. 6-27, 2020 | Oct. 15, 2020 | Oct. 28, 2020 | Oct. 29, 2020 | Dec. 23, 2021 | RGDG Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Muntinlupa City | 320702 | Muntinlupa Business High School - Sucat Annex | CITY OF MUNTINLUPA | 0 | 1 | 37 | Repair of Classrooms | 5000517 | 1 | 7006974.14 | COMPLETED | 1 | May 4, 2021 | 2021-04-03 |  |  | Oct. 6-27, 2020 | Oct. 15, 2020 | Oct. 28, 2020 | Oct. 29, 2020 | Dec. 23, 2021 | Open Builders Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Muntinlupa City | 305470 | PEDRO E. DIAZ HIGH SCHOOL | CITY OF MUNTINLUPA | 0 | 1 | 47 | Repair of classrooms | 7062357 | 1 | 4904526.76 | COMPLETED | 1 | May 4, 2021/June 18, 2021 |  |  |  | Oct. 6-27, 2020 | Oct. 15, 2020 | Oct. 28, 2020 | Oct. 29, 2020 | Dec. 23, 2021 | Redcar Trading and Const |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 47 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Muntinlupa City | 228501 | Poblacion Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 8 | Repair of Classrooms | 2074091 | 1 | 2074090.26 | COMPLETED | 1 | Jan. 28, 2021 | Jan. 22, 2020 |  |  | 11/25/19-12/16/19 | Dec. 3, 2019 | Dec. 16, 2019 | Dec. 20, 2019 | Sept. 23, 2020 | RGDG Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Muntinlupa City | 136905 | Soldiers' Hills ES | CITY OF MUNTINLUPA | 0 | 1 | 12 | Repair of Classrooms | 2857186 | 1 | 2857185.65 | COMPLETED | 1 | Jan.28, 2021 | 2020-12-19 |  |  | Oct. 6-27, 2020 | Oct. 15, 2020 | Oct. 28, 2020 | Oct. 29, 2020 | Sept. 23, 2020 | RGDG Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Navotas | 136858 | Dagat-Dagatan Elementary School | CITY OF NAVOTAS | 0 | 1 | 9 | Repair of Classrooms | 3550468 | 1 |  | COMPLETED | 1 | January 28, 2021 | January 28, 2021 |  | - |  |  |  | February 12, 2020 | September 11, 2020 | RHR Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Navotas | 305455 | Tanza National High School | CITY OF NAVOTAS | 0 | 1 | 6 | Repair of Classrooms | 2541300 | 1 |  | COMPLETED | 1 | March 2, 2021 | March 2, 2021 |  | - |  |  |  | February 12, 2020 | September 11, 2020 | Tapnio & Tan Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Paranaque City | 136769 | Baclaran ES Unit II | CITY OF PARAÑAQUE | 1 | 1 | 9 | Repair of Classrooms | 4469616 | 1 | 3376689.23 | COMPLETED | 1 | 2021-05-10 | May 7, 2021 |  |  | February 25, 2020 | March 3, 2020 | September 24, 2020 | October 12, 2020 | Dec 11, 2020 | REDCAR TRADING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Paranaque City | 136754 | La Huerta Elementary School | CITY OF PARAÑAQUE | 1 | 1 | 32 | Renovation of School Building | 5989048 | 1 | 5414347.51 | COMPLETED | 1 | 2021-05-10 | May 6, 2021 |  |  | October 9, 2020 | October 16, 2020 | October 28, 2020 | October 29, 2020 | Dec 11, 2020 | Redcar Trading & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Paranaque City | 136756 | Paranaque ES Central | CITY OF PARAÑAQUE | 1 | 1 | 21 | Repair of Classrooms | 6073842 | 1 | 4367703.07 | COMPLETED | 1 | May 14, 2021 | May 26, 2021 |  |  | February 25, 2020 | March 3, 2020 | September 24, 2020 | October 12, 2020 | Dec 15, 2020 | OPEN BUILDERS, INCORPORATED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Paranaque City | 305424 | Paranaque National High School Main | CITY OF PARAÑAQUE | 1 | 1 | 22 | Renovation Of School Building | 5033243 | 1 | 4524088.67 | COMPLETED | 1 | 2021-05-10 | May 10, 2021 |  |  | October 9, 2020 | October 16, 2020 | October 28, 2020 | October 29, 2020 | Dec 11, 2020 | RGDG Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Paranaque City | 305426 | PARANAQUE NHS-BACLARAN | CITY OF PARAÑAQUE | 1 | 1 | 8 | Renovation Of School Building | 2841268 | 1 | 2806060.77 | COMPLETED | 1 | April 24, 2021 | April 24, 2021 |  |  | October 9, 2020 | October 16, 2020 | October 28, 2020 | October 29, 2020 | Nov 25, 2020 | Sherf Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Paranaque City | 136772 | R. GATCHALIAN ES | CITY OF PARAÑAQUE | 1 | 1 | 20 | Renovation Of School Building | 3819670 | 1 | 3429451.2 | COMPLETED | 1 | 2021-05-10 | May 7, 2021 |  |  | October 9, 2020 | October 16, 2020 | October 28, 2020 | October 29, 2020 | Dec 11, 2020 | Redcar Trading & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Paranaque City | 226002 | SAN ISIDRO ELEMENTARY SCHOOL | CITY OF PARAÑAQUE | 1 | 1 | 1 | Renovation Of School Building | 3551273 | 1 | 3516255.47 | COMPLETED | 1 | 2021-05-10 | May 7, 2021 |  |  | February 25, 2020 | March 3, 2020 | September 24, 2020 | October 12, 2020 | Dec 11, 2020 | OPEN BUILDERS, INCORPORATED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Paranaque City | 136766 | Tambo ES | CITY OF PARAÑAQUE | 1 | 1 | 18 | Renovation Of School Building | 5654268 | 1 | 4975169.34 | COMPLETED | 1 | 2021-05-10 | May 10, 2021 |  |  | October 9, 2020 | October 16, 2020 | October 28, 2020 | October 29, 2020 | Dec 11, 2020 | RGDG Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Paranaque City | 136753 | Fourth Estate ES | CITY OF PARAÑAQUE | 2 | 1 | 15 | Repair of Classrooms | 5509082 | 1 | 5723613.23 | COMPLETED | 1 | May 14, 2021 | 2021-06-18 |  |  | February 25, 2020 | March 3, 2020 | September 24, 2020 | October 12, 2020 | Dec 15, 2020 | OPEN BUILDERS, INCORPORATED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Paranaque City | 305429 | Masville NHS | CITY OF PARAÑAQUE | 2 | 1 | 16 | Renovation Of School Building | 5091387 | 1 | 4580642.38 | COMPLETED | 1 | 2021-05-10 | May 10, 2021 |  |  | October 9, 2020 | October 16, 2020 | October 28, 2020 | October 29, 2020 | Dec 11, 2020 | Redcar Trading & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Paranaque City | 136759 | San Antonio ES | CITY OF PARAÑAQUE | 2 | 1 | 12 | Renovation Of School Building | 4788498 | 1 | 4772116.91 | COMPLETED | 1 | 2021-05-10 | May 7, 2021 |  |  | October 9, 2020 | October 16, 2020 | October 28, 2020 | October 29, 2020 | Dec 11, 2020 | RGDG Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Pasay City | 305367 | Pasay City East HS | PASAY CITY | 0 | 1 | 12 | Renovation Of School Building | 3008719 | 1 | 2975654.81 | COMPLETED | 1 | April 6, 2021 | March 26, 2021 |  |  | September 22, 2020 |  | October 15, 2020 | October 22, 2020 | December 1, 2020 | RGDG Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Pasay City | 136596 | Villamor Airbase ES | PASAY CITY | 0 | 1 | 43 | Repair of Classrooms | 13125997 | 1 | 13125996.07 | COMPLETED | 1 | July 17, 2021 | 2021-10-11 |  |  | November 19, 2019 |  | November 27, 2019 | January 8, 2020 | October 20, 2020 | Dreamworx Builder & Trdg. Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Pasig City | 136726 | DR. SIXTO ANTONIO ELEMENTARY SCHOOL | CITY OF PASIG | 0 | 1 | 6 | Repair of Classrooms | 6753578 | 1 | 6484874.15 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Pasig City | 305415 | Kapitolyo HS | CITY OF PASIG | 0 | 1 | 11 | Repair of Classrooms | 6503176 | 1 | 6453165.61 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Pasig City | 136719 | Liberato Damian ES | CITY OF PASIG | 0 | 1 | 9 | Repair of Classrooms | 6165642 | 1 | 6065709.85 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Pasig City | 305413 | Rizal High School | CITY OF PASIG | 0 | 1 | 1 | Repair and Rehabilitation of Auditorium | 46757348 | 1 | 46657798.84 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Pasig City | 136737 | Rosario ES | CITY OF PASIG | 0 | 1 | 79 | Repair of Classrooms | 18433162 | 1 | 18433162 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 79 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Pasig City | 136738 | San Lorenzo Ruiz ES | CITY OF PASIG | 0 | 1 | 38 | Repair of classrooms | 10889486 | 1 | 10383598.81 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Pasig City | 340655 | Ugong Pasig National High School | CITY OF PASIG | 0 | 1 | 17 | Repair of classrooms | 8825129 | 1 | 6888888.88 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Pasig City | 305414 | Sagad HS | CITY OF PASIG | 1 | 1 | 13 | Repair of Classrooms | 8009508 | 1 | 8009508 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 136500 | BUNGAD Elementary School | QUEZON CITY | 1 | 1 | 17 | Repair of Classrooms | 10575472 | 1 | 10575471.73 | COMPLETED | 1 |  |  | SDO-2020-INFRA-006 | 008, s. 2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 |  | 2020-12-22 | JRCF Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 136505 | San Antonio ES | QUEZON CITY | 1 | 1 | 18 | Repair of Classrooms | 12042455 | 1 | 7263320.67 | COMPLETED | 1 |  |  | SDO-2020-INFRA-007 | 009, s.2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | J. SIMEON Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 136498 | San Francisco ES | QUEZON CITY | 1 | 1 | 40 | Repair of Classrooms | 20242021 | 1 | 20242020.15 | COMPLETED | 1 |  |  | SDO-2020-INFRA-007 | 009, s.2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | J. SIMEON Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 305324 | Sergio Osmena, Sr. HS | QUEZON CITY | 1 | 1 | 25 | Repair of Classrooms | 13465807 | 1 | 21642253.53 | COMPLETED | 1 |  |  | SDO-2020-INFRA-007 | 009, s.2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | J. SIMEON Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 136544 | Holy Spirit ES | QUEZON CITY | 2 | 1 | 80 | Repair of Classrooms | 35583393 | 1 | 35583392.99 | COMPLETED | 1 |  |  | SDO-2020-INFRA-007 | 010 s. 2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | IM Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 319501 | Holy Spirit National High School | QUEZON CITY | 2 | 1 | 22 | Repair of Classrooms | 9549411 | 1 | 9549410.49 | COMPLETED | 1 |  |  | SDO-2020-INFRA-007 | 010 s. 2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | IM Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 136545 | Lupang Pangako ES | QUEZON CITY | 2 | 1 | 30 | Repair of Classrooms | 12165753 | 1 | 12165752.44 | COMPLETED | 1 |  |  | SDO-2020-INFRA-007 | 010 s. 2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | IM Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 136560 | Batino Elementary School (SPED Center) | QUEZON CITY | 3 | 1 | 20 | Repair of Classrooms | 16055060 | 1 | 16055059.89 | COMPLETED | 1 |  |  | SDO-2020-INFRA-007 | 009, s.2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | J. SIMEON Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 305346 | Camp Gen. E. Aguinaldo HS | QUEZON CITY | 3 | 1 | 43 | Repair of Classrooms | 18453991 | 1 | 15094086 | COMPLETED | 1 |  |  | SDO-2020-INFRA-007 | 009, s.2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | J. SIMEON Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 136579 | GEN. ROXAS Elementary School | QUEZON CITY | 4 | 1 | 28 | Repair of Classrooms | 13342976 | 1 | 13342975.81 | COMPLETED | 1 |  |  | SDO-2020-INFRA-006 | 008, s. 2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 |  | 2020-12-14 | TM ABAD Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 305356 | Ponciano A. Bernardo HS | QUEZON CITY | 4 | 1 | 31 | Repair of Classrooms | 15481044 | 1 | 21430000.61 | COMPLETED | 1 |  |  | SDO-2020-INFRA-007 | 009, s.2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | J. SIMEON Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 136527 | Dona Rosario Elementary School | QUEZON CITY | 5 | 1 | 31 | Repair of Classrooms | 12377970 | 1 | 17121742.29 | COMPLETED | 1 |  |  | SDO-2020-INFRA-007 | 010 s. 2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | IM Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 305339 | North Fairview HS | QUEZON CITY | 5 | 1 | 35 | Repair of Classrooms | 16581817 | 1 | 16581816.1 | COMPLETED | 1 |  |  | SDO-2020-INFRA-007 | 010 s. 2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | IM Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 340690 | SHS in NOH-Sta Lucia | QUEZON CITY | 5 | 1 | 20 | Repair of Classrooms | 12889402 | 1 | 12798453.27 | COMPLETED | 1 |  |  | SDO-2020-INFRA-009 | 011, s.2020 | 2020-10-09 | 2020-10-16 | 2020-10-29 |  | 2020-12-28 | RHR Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City |  | West Fairview HS Annex | QUEZON CITY | 5 | 1 | 21 | Repair of classrooms | 8040798 | 1 | 8040797.38 | COMPLETED | 1 |  |  | SDO-2020-INFRA-007 | 010 s. 2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | IM Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136892 | Aguho Elementary School | PATEROS | 1 | 1 | 2 | Repair of classrooms | 1132559 | 1 | 1130760.99 | COMPLETED | 1 |  |  | DTP-CY20-INFRA-005 |  | November 29, 2019 | December 2,2019 | December 20, 2019 | January 8, 2020 | October 26, 2020 | DAWING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136896 | Pateros Elementary School | PATEROS | 1 | 1 | 19 | Repair of Classrooms | 8500000 | 1 | 8452895.95 | COMPLETED | 1 |  |  | DTP-CY20-INFRA-007 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | C.B. TAMPENGCO CONSTRUCTION & SUPPY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 305466 | Pateros National High School | PATEROS | 1 | 1 | 12 | Repair of Classrooms | 4006325 | 1 | 4004527.47 | COMPLETED | 1 |  |  | DTP-CY20-INFRA-005 |  | November 29, 2019 | December 2,2019 | December 20, 2019 | January 8, 2020 | October 26, 2020 | DAWING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 305466 | Pateros National High School | PATEROS | 1 |  | 20 | Repair of Classrooms | 4000000 | 1 | 3977865.72 | COMPLETED | 1 |  |  | DTP-CY20-INFRA-007 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | C.B. TAMPENGCO CONSTRUCTION & SUPPY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136895 | Paulina Manalo ES | PATEROS | 1 | 1 | 12 | Repair of Classrooms | 3000000 | 1 | 2983213.88 | COMPLETED | 1 |  |  | DTP-CY20-INFRA-007 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | C.B. TAMPENGCO CONSTRUCTION & SUPPY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136898 | Sto. Rosario Elementary School | PATEROS | 1 | 1 | 8 | Repair of Classrooms | 2000000 | 1 | 1988009.96 | COMPLETED | 1 |  |  | DTP-CY20-INFRA-007 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | C.B. TAMPENGCO CONSTRUCTION & SUPPY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 305459 | Bagumbayan National High School | TAGUIG CITY | 1 | 1 | 24 | Repair of Classrooms | 5000000 | 1 | 4972314.53 | COMPLETED | 1 |  |  | DTP-CY20-INFRA-007 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | C.B. TAMPENGCO CONSTRUCTION & SUPPY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136883 | Cipriano P. Sta. Teresa Elementary School | TAGUIG CITY | 1 | 1 | 24 | Repair of Classrooms | 6500000 | 1 | 6466300.71 | COMPLETED | 1 | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136873 | Eusebio C. Santos Elementary School | TAGUIG CITY | 1 | 1 | 15 | Repair of Classrooms | 4120021 | 1 | 4096678.4 | COMPLETED | 1 |  |  | DTP-CY20-INFRA-007 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | C.B. TAMPENGCO CONSTRUCTION & SUPPY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 305462 | Gen. Ricardo G. Papa, Sr. Memorial HS Annex | TAGUIG CITY | 1 | 1 | 12 | Repair of Classrooms | 2703631 | 1 | 2688403.33 | COMPLETED | 1 |  |  | DTP-CY20-INFRA-005 |  | November 29, 2019 | December 2,2019 | December 20, 2019 | January 8, 2020 | October 26, 2020 | CRESTA MANAGEMENT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136875 | Ricardo P. Cruz, Sr. Elementary School | TAGUIG CITY | 1 | 1 | 21 | Repair of Classrooms | 7000000 | 1 | 6963557.53 | COMPLETED | 1 | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 320604 | Sen. Renato "Compañero" Cayetano Memorial Science & Technology High School | TAGUIG CITY | 1 | 1 | 12 | Repair of Classrooms | 4000000 | 1 | 3979120.35 | COMPLETED | 1 | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 500565 | Taguig Integrated School | TAGUIG CITY | 1 | 1 | 9 | Repair of Classrooms | 3000000 | 1 | 2983085.6 | COMPLETED | 1 |  |  | DTP-CY20-INFRA-007 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | C.B. TAMPENGCO CONSTRUCTION & SUPPY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 305460 | Taguig National High School | TAGUIG CITY | 1 | 1 | 9 | Repair of Classrooms | 2778695 | 1 | 2763713.99 | COMPLETED | 1 |  |  | DTP-CY20-INFRA-005 |  | November 29, 2019 | December 2,2019 | December 20, 2019 | January 8, 2020 | October 26, 2020 | CRESTA MANAGEMENT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136877 | Tipas Elementary School -Main | TAGUIG CITY | 1 | 1 | 6 | Repair of Classrooms | 1500000 | 1 | 1491711.41 | COMPLETED | 1 |  |  | DTP-CY20-INFRA-007 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | C.B. TAMPENGCO CONSTRUCTION & SUPPY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136879 | Ususan Elementary School | TAGUIG CITY | 1 | 1 | 20 | Repair of Classrooms | 5000000 | 1 | 4972244.95 | COMPLETED | 1 |  |  | DTP-CY20-INFRA-007 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | C.B. TAMPENGCO CONSTRUCTION & SUPPY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136885 | Enlisted Men's Signal Village Elementary School | TAGUIG CITY | 2 | 1 | 18 | Repair of Classrooms | 5400000 | 1 | 5371297.14 | COMPLETED | 1 | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 320612 | Gat. Andres Bonifacio High School | TAGUIG CITY | 2 | 1 | 20 | Repair of Classrooms | 6000000 | 1 | 5969292.92 | COMPLETED | 1 | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136886 | Kapitan Jose Cardones Memorial ES | TAGUIG CITY | 2 | 1 | 21 | Repair of Classrooms | 7000000 | 1 | 6964111.49 | COMPLETED | 1 | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136890 | Maharlika Elementary School | TAGUIG CITY | 2 | 1 | 21 | Repair of Classrooms | 6000000 | 1 | 5968583.62 | COMPLETED | 1 | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 500341 | Palar Integrated School | TAGUIG CITY | 2 | 1 | 21 | Repair of Classrooms | 6000000 | 1 | 5968973.68 | COMPLETED | 1 | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 305463 | Signal Village National High School | TAGUIG CITY | 2 | 1 | 18 | Repair of Classrooms | 4500000 | 1 | 4476962.88 | COMPLETED | 1 | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136891 | Tenement Elementary School | TAGUIG CITY | 2 | 1 | 15 | Repair of Classrooms | 4500000 | 1 | 4476555.15 | COMPLETED | 1 | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 320605 | Upper Bicutan National High School | TAGUIG CITY | 2 | 1 | 12 | Repair of Classrooms | 3000000 | 1 | 2984133.45 | COMPLETED | 1 | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Valenzuela City | 136793 | Canumay West ES | CITY OF VALENZUELA | 1 | 1 | 58 | Repair of Classrooms | 14307871 | 1 | 14232465.7 | COMPLETED | 1 | August 5, 2021 |  |  | INFRA-BEFF-2020-11-0003(LI) | Aug 25, 2020 | Sept 3, 2020 | Sept 15, 2020 | Sept 18, 2020 | Dec 8, 2020 | Aylan Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 58 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Valenzuela City | 305439 | Canumay West National High School | CITY OF VALENZUELA | 1 | 1 | 42 | Repair of Classrooms | 6501204 | 1 | 6501204 | COMPLETED | 1 | May 29, 2021 | 2021-03-19 |  | INFRA-EPA-BEFF-2020-09-0001(LI) | Nov 27, 2019 | Dec 5, 2019 | Dec 17, 2019 | Dec 27, 2019 | Oct 1, 2020 | Hawkstow Construction & Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Valenzuela City | 136815 | Lawang Bato Elementary School | CITY OF VALENZUELA | 1 | 1 | 10 | Repair of Classrooms | 2945973 | 1 | 2945973 | COMPLETED | 1 | May 29, 2021 | 2021-11-05 |  | INFRA-EPA-BEFF-2020-09-0001(LI) | Nov 27, 2019 | Dec 5, 2019 | Dec 17, 2019 | Dec 27, 2019 | Oct 1, 2020 | Hawkstow Construction & Development | Used as quarantine/isolation facility of LGU | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Valenzuela City | 305440 | Lawang Bato National High School | CITY OF VALENZUELA | 1 | 1 | 18 | Repair of Classrooms | 5182293 | 1 | 5182293 | COMPLETED | 1 | May 29, 2021 | 2021-09-21 |  | INFRA-EPA-BEFF-2020-09-0001(LI) | Nov 27, 2019 | Dec 5, 2019 | Dec 17, 2019 | Dec 27, 2019 | Oct 1, 2020 | Hawkstow Construction & Development | Used as quarantine/isolation facility of LGU | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Valenzuela City | 136795 | Lingunan ES | CITY OF VALENZUELA | 1 | 1 | 13 | Repair of Classrooms | 4787891 | 1 | 4769546.44 | COMPLETED | 1 | August 5, 2021 | 2021-07-07 |  | INFRA-BEFF-2020-11-0003(LI) | Aug 25, 2020 | Sept 3, 2020 | Sept 15, 2020 | Sept 18, 2020 | Dec 8, 2020 | Aylan Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Valenzuela City | 136816 | Apolonia F. Rafael Elementary School | CITY OF VALENZUELA | 2 | 1 | 44 | Repair of Classrooms | 10505698 | 1 | 10428168.99 | COMPLETED | 1 | August 5, 2021 |  |  | INFRA-BEFF-2020-11-0003(LI) | Aug 25, 2020 | Sept 3, 2020 | Sept 15, 2020 | Sept 18, 2020 | Dec 8, 2020 | Aylan Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Valenzuela City | 136821 | Caruhatan East ES | CITY OF VALENZUELA | 2 | 1 | 6 | Repair of Classrooms | 2390922 | 1 | 2353303.86 | COMPLETED | 1 | August 5, 2021 |  |  | INFRA-BEFF-2020-11-0003(LI) | Aug 25, 2020 | Sept 3, 2020 | Sept 15, 2020 | Sept 18, 2020 | Dec 8, 2020 | Aylan Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Valenzuela City | 136823 | Constantino ES | CITY OF VALENZUELA | 2 | 1 | 20 | Repair of Classrooms | 4765006 | 1 | 4719604.96 | COMPLETED | 1 | August 5, 2021 | 2021-07-07 |  | INFRA-BEFF-2020-11-0003(LI) | Aug 25, 2020 | Sept 3, 2020 | Sept 15, 2020 | Sept 18, 2020 | Dec 8, 2020 | Aylan Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Valenzuela City | 136814 | Gen. T. de Leon ES | CITY OF VALENZUELA | 2 | 1 | 62 | Repair of Classrooms | 15993182 | 1 | 15915164.5 | COMPLETED | 1 | August 5, 2021 |  |  | INFRA-BEFF-2020-11-0003(LI) | Aug 25, 2020 | Sept 3, 2020 | Sept 15, 2020 | Sept 18, 2020 | Dec 8, 2020 | Aylan Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Valenzuela City | 305442 | Parada NHS | CITY OF VALENZUELA | 2 | 1 | 15 | Repair of Classrooms | 5836640 | 1 | 5804677.4 | COMPLETED | 1 | August 5, 2021 |  |  | INFRA-BEFF-2020-11-0003(LI) | Aug 25, 2020 | Sept 3, 2020 | Sept 15, 2020 | Sept 18, 2020 | Dec 8, 2020 | Aylan Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Valenzuela City | 136827 | Serrano ES | CITY OF VALENZUELA | 2 | 1 | 24 | Repair of Classrooms | 5885727 | 1 | 5885727 | COMPLETED | 1 | May 29, 2021 | 2021-01-25 |  | INFRA-EPA-BEFF-2020-09-0001(LI) | Nov 27, 2019 | Dec 5, 2019 | Dec 17, 2019 | Dec 27, 2019 | Oct 1, 2020 | Hawkstow Construction & Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Caloocan City | 136643 | A. Mabini Elementary School | KALOOKAN CITY | 1 | 1 | 1 | Repair of Perimeter Fence | 35000000 | 1 | 34850000 | COMPLETED | 1 | 2022-04-25 |  | 2021-Infra-002 | 2021-Infra-Cal-002 | 2021-06-29 | 2021-07-07 | 2021-07-19 | 2021-08-02 | 2019-09-06 | IM Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Caloocan City | 319707 | Caloocan City Business High School | KALOOKAN CITY | 1 | 1 | 28 | Repair of Classrooms | 14100000 | 1 | 14044594.8 | COMPLETED | 1 | 2022-02-27 | 2021-08-18 | 2021-Infra-002 | 2021-Infra-Cal-003 | 2021-06-29 | 2021-07-07 | 2021-07-19 | 2021-08-02 | 2021-08-31 | Solenko Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Caloocan City | 305374 | Camarin High School | KALOOKAN CITY | 1 | 1 | 36 | Repair of Classrooms | 16200000 | 1 | 16174537.387 | COMPLETED | 1 | 2022-02-27 |  | 2021-Infra-002 | 2021-Infra-Cal-003 | 2021-06-29 | 2021-07-07 | 2021-07-19 | 2021-08-02 | 2021-08-31 | Solenko Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Caloocan City | 136645 | Marcelo H. del Pilar ES (MLQ ES Unit I) | KALOOKAN CITY | 1 | 1 | 9 | Repair of Classrooms | 5032830.79 | 1 | 5000698.61 | COMPLETED | 1 | 2022-02-27 |  | 2021-Infra-002 | 2021-Infra-Cal-003 | 2021-06-29 | 2021-07-07 | 2021-07-19 | 2021-08-02 | 2021-08-31 | Solenko Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Caloocan City | 136629 | Morning Breeze Elementary School | KALOOKAN CITY | 1 | 1 | 33 | Repair of Classrooms | 16000000 | 1 | 15945000 | COMPLETED | 1 | 2022-09-30 |  | 2021-Infra-002 | 2021-Infra-Cal-004 | 2021-06-29 | 2021-07-07 | 2021-07-19 | 2021-08-02 | 2021-08-31 | Aylan Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Caloocan City | 136615 | Andres Bonifacio ES | KALOOKAN CITY | 2 | 1 | 18 | Repair of Classrooms | 10600000 | 1 | 10560000 | COMPLETED | 1 | 2022-05-13 |  | 2021-Infra-002 | 2021-Infra-Cal-004 | 2021-06-29 | 2021-07-07 | 2021-07-19 | 2021-08-02 | 2021-08-31 | Aylan Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Caloocan City | 136617 | Caloocan Central Elementary School | KALOOKAN CITY | 2 | 1 | 18 | Repair of Classrooms | 10600000 | 1 | 10560000 | COMPLETED | 1 | 2022-05-13 |  | 2021-Infra-002 | 2021-Infra-Cal-004 | 2021-06-29 | 2021-07-07 | 2021-07-19 | 2021-08-02 | 2021-08-31 | Aylan Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Caloocan City | 305390 | Maria Clara HS | KALOOKAN CITY | 2 | 1 | 20 | Repair of Classrooms | 9000000 | 1 | 8965000 | COMPLETED | 1 | 2022-05-13 |  | 2021-Infra-002 | 2021-Infra-Cal-004 | 2021-06-29 | 2021-07-07 | 2021-07-19 | 2021-08-02 | 2021-08-31 | Aylan Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | City of San Juan | 136751 | Pinaglabanan ES | CITY OF SAN JUAN | 0 | 1 | 6 | Repair of Classrooms | 3000000 | 1 | 2388888.88 | COMPLETED | 1 | 2021-12-20 |  | REPAIR2021-NCR-SANJUAN-001 | INFRA2021-08-01 | 2021-07-06 | 2021-07-13 | 2021-07-26 | 2021-07-28 | 2021-08-04 | ZEAL POWER CONSTRUCTION AND DEV'T CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Las Piñas City | 320302 | CAA NHS Annex | CITY OF LAS PIÑAS | 0 | 1 | 27 | Repair of Classrooms | 4945261.49 | 1 | 3417765.61 | COMPLETED | 1 | 2021-12-22 | 2021-11-10 | REPAIR2021-NCR-LAS PIÑAS CITY-001 |  | 2021-06-30 | 2021-07-07 | 2021-07-21 | 2021-07-19 | 2021-08-24 | Open Builders Incorporated | Turn-over | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Makati City | 305412 | Benigno "Ninoy" S. Aquino HS | CITY OF MAKATI | 2 | 1 | 59 | Repair of Toilets | 7200222.96 | 1 | 4680401.6 | COMPLETED | 1 | 2022-01-31 |  | SDO-MKT-021-008 | SDO-MKT-021-008 | 2021-08-04 | 2021-08-12 | 2021-08-24 | 2021-09-06 | 2021-09-08 | DREAMWORX BUILDER & TRADING, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Malabon City | 500337 | Catmon IS | CITY OF MALABON | 0 | 1 | 59 | Repair of Classrooms | 4500000 | 1 | 4469655.11 | COMPLETED | 1 |  |  |  | 2021-INFRA-10-0003 |  | SEPT 8, 2021 | 2021-09-28 | 2021-10-07 | 2021-10-14 | MRRM TRADING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Malabon City | 501208 | Dampalit IS | CITY OF MALABON | 0 | 1 | 12 | Repair of Classrooms | 547476.62 | 1 | 542461 | COMPLETED | 1 |  |  |  | 2021-INFRA-10-0006 |  | SEPT 8, 2021 | 2021-09-28 | 2021-10-07 | 2021-10-14 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Malabon City | 136835 | Longos ES | CITY OF MALABON | 0 | 1 | 8 | Repair of Classrooms | 387857.31 | 1 | 386779.49 | COMPLETED | 1 |  |  |  | 2021-INFRA-10-0007 |  | SEPT 8, 2021 | 2021-09-28 | 2021-10-07 | 2021-10-14 | Martian Builders and supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Malabon City | 136830 | Malabon ES | CITY OF MALABON | 0 | 1 | 10 | Repair of Classrooms | 2791834.53 | 1 | 2786822.55 | COMPLETED | 1 |  |  |  | 2021-INFRA-10-0006 |  | SEPT 8, 2021 | 2021-09-28 | 2021-10-07 | 2021-10-14 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Malabon City | 305447 | Malabon National High School | CITY OF MALABON | 0 | 1 | 9 | Repair of Classrooms | 3124712.65 | 1 | 3114428.54 | COMPLETED | 1 |  |  |  | 2021-INFRA-10-0005 |  | SEPT 8, 2021 | 2021-09-28 | 2021-10-07 | 2021-10-14 | DREAMWORX BUILDER & TRADING, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Malabon City | 136836 | Ninoy Aquino ES | CITY OF MALABON | 0 | 1 | 67 | Repair of Classrooms | 4500000 | 1 | 4468956.55 | COMPLETED | 1 |  |  |  | 2021-INFRA-10-004 |  | SEPT 8, 2021 | 2021-09-28 | 2021-10-07 | 2021-10-14 | TAPNIO & TAN CONSTRUCTION & DEVT. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 67 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Malabon City | 136831 | Panghulo ES | CITY OF MALABON | 0 | 1 | 21 | Repair of Classrooms | 861201.95 | 1 | 859671.83 | COMPLETED | 1 |  |  |  | 2021-INFRA-10-0007 |  | SEPT 8, 2021 | 2021-09-28 | 2021-10-07 | 2021-10-14 | Martian Builders and supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Malabon City | 136833 | Santulan ES | CITY OF MALABON | 0 | 1 | 16 | Repair of Classrooms | 500000 | 1 | 498127.47 | COMPLETED | 1 |  |  |  | 2021-INFRA-10-0007 |  | SEPT 8, 2021 | 2021-09-28 | 2021-10-07 | 2021-10-14 | Martian Builders and supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Malabon City | 500339 | Tañong IS | CITY OF MALABON | 0 | 1 | 15 | Repair of Classrooms | 555637.65 | 1 | 554096.37 | COMPLETED | 1 |  |  |  | 2021-INFRA-10-0007 |  | SEPT 8, 2021 | 2021-09-28 | 2021-10-07 | 2021-10-14 | Martian Builders and supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Malabon City | 305448 | Tañong NHS | CITY OF MALABON | 0 | 1 | 1 | Repair of Classroom | 270614.12 | 1 | 269678.35 | COMPLETED | 1 |  |  |  | 2021-INFRA-10-0007 |  | SEPT 8, 2021 | 2021-09-28 | 2021-10-07 | 2021-10-14 | Martian Builders and supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Malabon City | 305452 | Tinajeros NHS | CITY OF MALABON | 0 | 1 | 8 | Repair of Classrooms | 355402.21 | 1 | 350382.11 | COMPLETED | 1 |  |  |  | 2021-INFRA-10-0006 |  | SEPT 8, 2021 | 2021-09-28 | 2021-10-07 | 2021-10-14 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Mandaluyong City | 500500 | Hulo Integrated School | CITY OF MANDALUYONG | 0 | 1 | 64 | Repair of Classrooms | 15791089.99 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Mandaluyong City | 500331 | Isaac Lopez Integrated School (Isaac Lopez ES) | CITY OF MANDALUYONG | 0 | 1 | 40 | Repair of Classrooms | 8303301.94 | 1 | 10049242.84 | COMPLETED | 1 | January 11, 2021 | January 11, 2021 | 2020-Mandaluyong-04 | No.04 | August 10, 2020 - August 28, 2020 | August 18, 2020 | September 1, 2020 | September 4, 2020 | October 15, 2020 | Tracsom Builders, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Mandaluyong City | 305394 | Mataas na Paaralang Neptali A. Gonzales | CITY OF MANDALUYONG | 0 | 1 | 68 | Repair of Classrooms | 11622728.4 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Manila | 305288 | Dr. Juan G. Nolasco High School | TONDO | 1 | 1 | 102 | Repair of Classrooms | 33000000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 102 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Manila | 500567 | F. G. Calderon Elementary School | TONDO | 2 | 1 | 60 | Repair of Classrooms | 23200000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Manila | 136426 | Francisco Benitez Elementary School | TONDO | 2 | 1 | 68 | Repair of Classrooms | 27800000 | 1 |  | COMPLETED | 1 | 2022-09-30 | [9 empty] | Ongoing; Requested for time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Manila | 136428 | Gregoria de Jesus ES | TONDO | 2 | 1 | 46 | Repair of Classrooms | 21900000 | 1 |  | COMPLETED | 1 | [10 empty] | Ongoing; Requested for time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Manila | 136451 | Francisco Balagtas ES | SANTA CRUZ | 3 | 1 | 57 | Repair of Classrooms | 20200000 | 1 |  | COMPLETED | 1 | [10 empty] | Ongoing; Requested for time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 57 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Manila | 305302 | Jose Abad Santos High School | SANTA CRUZ | 3 | 1 | 33 | Repair of Classrooms | 13800000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Manila | 500568 | Antonio A. Maceda Integrated School | SAMPALOC | 4 | 1 | 48 | Repair of Classrooms | 17500000 | 1 |  | COMPLETED | 1 | [10 empty] | Ongoing; Requested for time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Manila | 136462 | Gen. L. Geronimo Elementary School | SAMPALOC | 4 | 1 | 51 | Repair of Classrooms | 17700000 | 1 |  | COMPLETED | 1 | [10 empty] | Ongoing; Requested for time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Manila | 136465 | Juan Luna Elementary School | SAMPALOC | 4 | 1 | 3 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Manila | 305310 | Carlos P. Garcia High School | PACO | 6 | 1 | 76 | Repair of Classrooms | 31700000 | 1 |  | COMPLETED | 1 | [10 empty] | Ongoing; Requested for time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 76 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Manila | 136472 | Pio del Pilar Elementary School | SAMPALOC | 6 | 1 | 69 | Repair of Classrooms | 30800000 | 1 |  | COMPLETED | 1 | [10 empty] | Ongoing; Requested for time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 69 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Manila | 305315 | Victoriano Mapa High School | SAN MIGUEL | 6 | 1 | 34 | Repair of Classrooms | 16150000 | 1 |  | COMPLETED | 1 | 2022-09-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Marikina City | 319903 | Barangka NHS | CITY OF MARIKINA | 1 | 1 | 20 | Repair of Classrooms | 5880043.6 | 1 | 5810762.74 | COMPLETED | 1 | 2021-12-05 | 2021-10-22 | REPAIR-2021-NCR-MARIKINA CITY-005 |  | 2021-06-17 | 2021-06-23 | 2021-07-05 | 2021-07-21 | 2021-08-05 | OPEN BUILDERS INCORPORATED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Marikina City | 136672 | Industrial Valley ES | CITY OF MARIKINA | 1 | 1 | 30 | Repair of Classrooms | 7289241.42 | 1 | 7192530.47 | COMPLETED | 1 | 2021-12-05 | November 4,2020 | REPAIR-2021-NCR-MARIKINA CITY-004 |  | 2021-06-17 | 2021-06-23 | 2021-07-05 | 2021-07-21 | 2021-08-16 | TRIX-ZION VENTURES CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Marikina City | 136687 | Sto. Nino ES | CITY OF MARIKINA | 1 | 1 | 71 | Repair of Classrooms | 26904567.33 | 1 | 26788608.22 | COMPLETED | 1 | 2022-01-05 | 2021-01-15 | REPAIR-2021-NCR-MARIKINA CITY-003 |  | 2021-06-17 | 2021-06-23 | 2021-07-05 | 2021-07-21 | 2021-08-05 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 71 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Marikina City | 136680 | Concepcion ES | CITY OF MARIKINA | 2 | 1 | 83 | Repair of Classrooms | 20342356.74 | 1 | 20231961.91 | COMPLETED | 1 | 2022-01-04 | Oct. 30,2020 | REPAIR-2021-NCR-MARIKINA CITY-006 |  | 2021-06-17 | 2021-06-23 | 2021-07-05 | 2021-07-21 | 2021-08-04 | MT. GUITING-GUITING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 83 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Marikina City | 319902 | Fortune High School | CITY OF MARIKINA | 2 | 1 | 20 | Repair of Classrooms | 3779778.12 | 1 | 3673457.09 | COMPLETED | 1 | 2021-11-05 | 2021-10-22 | REPAIR-2021-NCR-MARIKINA CITY-0001 |  | 2021-06-17 | 2021-06-23 | 2021-07-05 | 2021-07-21 | 2021-08-04 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Marikina City | 305630 | SSS National High School | CITY OF MARIKINA | 2 | 1 | 20 | Repair of Classrooms | 3903308.21 | 1 | 3853308.21 | COMPLETED | 1 | 2021-11-05 | 2021-11-15 | REPAIR-2021-NCR-MARIKINA CITY-002 |  | 2021-06-17 | 2021-06-23 | 2021-07-05 | 2021-07-21 | 2021-08-05 | ST. GABRIEL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 136908 | Alabang ES (Main) | CITY OF MUNTINLUPA | 0 | 1 | 44 | Repair of Classsroom | 7883989.97 | 1 | 7874528.38 | COMPLETED | 1 | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | RGDG CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 136911 | Buli ES | CITY OF MUNTINLUPA | 0 | 1 | 32 | Repair of Classsroom | 2956597.21 | 1 | 2929909.9 | COMPLETED | 1 | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | RGDG CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 228502 | Filinvest Alabang Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 18 | Repair of Classrooms | 2251992.82 | 1 | 2215811.55 | COMPLETED | 1 | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | RGDG CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 136901 | Itaas Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 21 | Repair of Classrooms | 465900.65 | 1 | 423054.55 | COMPLETED | 1 | 2022-02-12 | 2021-04-17 |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | REDCAR TRADING AND CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 500438 | Lakeview Integrated School | CITY OF MUNTINLUPA | 0 | 1 | 32 | Repair of Classsroom | 8161304.02 | 1 | 8092879.8 | COMPLETED | 1 | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | RGDG CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 136903 | Muntinlupa ES | CITY OF MUNTINLUPA | 0 | 1 | 28 | Repair of Classrooms | 9385103.5 | 1 | 9377379.45 | COMPLETED | 1 | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | REDCAR TRADING AND CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 305468 | Muntinlupa NHS | CITY OF MUNTINLUPA | 0 | 1 | 21 | Repair of Classsroom | 2068928.09 | 1 | 2062619.37 | COMPLETED | 1 | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | REDCAR TRADING AND CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 320704 | Muntinlupa NHS -Tunasan Annex | CITY OF MUNTINLUPA | 0 | 1 | 72 | Repair of Classsroom | 11212593.59 | 1 | 11188729.42 | COMPLETED | 1 | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | REDCAR TRADING AND CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 305469 | Muntinlupa Science High School | CITY OF MUNTINLUPA | 0 | 1 | 79 | Repair of Classsroom | 8092765.95 | 1 | 8058590.7 | COMPLETED | 1 | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | RGDG CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 79 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 228501 | Poblacion Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 70 | Repair of Classsroom | 11100443.04 | 1 | 11068283.06 | COMPLETED | 1 | 2022-02-12 | Jan. 22, 2020 |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | REDCAR TRADING AND CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 320701 | Poblacion National High School | CITY OF MUNTINLUPA | 0 | 1 | 44 | Repair of Classrooms | 3518631.25 | 1 | 3476011.78 | COMPLETED | 1 | 2022-02-01 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | REDCAR TRADING AND CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 136904 | Putatan Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 6 | Repair of Classrooms | 1171377.26 | 1 | 1133816.25 | COMPLETED | 1 | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | RGDG CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 136914 | Sucat Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 58 | Repair of Classrooms | 7592098.05 | 1 | 7585902.63 | COMPLETED | 1 | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | RGDG CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 58 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 136906 | Tunasan Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 22 | Repair of Classsroom | 5787317.34 | 1 | 5775710.85 | COMPLETED | 1 | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | RGDG CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 136907 | Victoria Homes ES | CITY OF MUNTINLUPA | 0 | 1 | 43 | Repair of Classsroom | 2745612.97 | 1 | 2679216.17 | COMPLETED | 1 | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | REDCAR TRADING AND CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Navotas | 340628 | Filemon Lizan Senior High School | CITY OF NAVOTAS | 0 | 1 | 16 | Repair of Classrooms | 4146099.62 | 1 | 4091619.52 | COMPLETED | 1 | 2021-11-22 |  | BAC-PB-2021-05 | BAC-PB-2021-05 | 2021-05-27 | 2021-06-07 | 2021-06-21 | 2021-07-05 | 2021-07-19 | St. Gabriel Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Navotas | 136859 | Kapitbahayan Elementary School | CITY OF NAVOTAS | 0 | 1 | 9 | Repair of Classrooms | 3586590.03 | 1 | 3558762.46 | COMPLETED | 1 | 2021-11-19 |  | BAC-PB-2021-03 | BAC-PB-2021-03 | 2021-05-27 | 2021-06-07 | 2021-06-21 | 2021-07-05 | 2021-07-19 | RHR Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Navotas | 136867 | Tangos Elementary School | CITY OF NAVOTAS | 0 | 1 | 15 | Repair of Classrooms | 6281344.86 | 1 | 6246516.52 | COMPLETED | 1 | 2021-11-21 |  | BAC-PB-2021-04 | BAC-PB-2021-04 | 2021-05-27 | 2021-06-07 | 2021-06-21 | 2021-07-05 | 2021-07-19 | MRRM Trading & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 136767 | Baclaran ES Central | CITY OF PARAÑAQUE | 1 | 1 | 27 | Renovation of School Building | 3401859.28 | 1 | ₱2,449,068.77 | COMPLETED | 1 | 2020-01-05 |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-23 | 2019-08-28 | august 8, 2019 | AGH Construction Corp |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 136768 | Baclaran ES Unit I | CITY OF PARAÑAQUE | 1 | 1 | 12 | Renovation of School Building | 4469756.83 | 1 | ₱2,932,759.67 | COMPLETED | 1 |  |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-23 |  |  | Open Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 320205 | Don Bosco High School Parañaque | CITY OF PARAÑAQUE | 1 | 1 | 40 | Renovation of School Building | 6376607.77 | 1 | ₱5,602,990.20 | COMPLETED | 1 |  |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-25 |  |  | RGDG Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 136754 | La Huerta Elementary School | CITY OF PARAÑAQUE | 1 | 1 | 44 | Renovation of School Building | 3828482.48 | 1 | ₱3,367,611.91 | COMPLETED | 1 | 2021-05-10 | May 6, 2021 |  |  | 2021-06-03 | 2021-06-11 | 2021-06-23 | October 29, 2020 | Dec 11, 2020 | RGDG Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 136757 | Paranaque Elementary School Unit II | CITY OF PARAÑAQUE | 1 | 1 | 28 | Renovation of School Building | 6371447.85 | 1 | ₱4,200,155.58 | COMPLETED | 1 |  |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-25 |  |  | Dreamworx Builder & Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 305424 | Paranaque National High School Main | CITY OF PARAÑAQUE | 1 | 1 | 15 | Repair of Classrooms | 3880768.29 | 1 | ₱2,834,346.28 | COMPLETED | 1 |  |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-23 | 2019-08-28 | November 6, 2019 | Open Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 305427 | Paranaque NHS - Don Galo Annex | CITY OF PARAÑAQUE | 1 | 1 | 39 | Renovation of School Building | 3574901.7 | 1 | ₱2,478,753.31 | COMPLETED | 1 |  |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-24 | 2019-08-28 | November 6, 2019 | RGDG Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 320201 | Paranaque Science HS | CITY OF PARAÑAQUE | 1 | 1 | 28 | Renovation of School Building | 4220750.09 | 1 | ₱2,987,924.09 | COMPLETED | 1 |  |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-24 |  |  | RGDG Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 340635 | Sto. Niño Senior High School | CITY OF PARAÑAQUE | 1 | 1 | 12 | Renovation of School Building | 4382325.75 | 1 | ₱2,907,126.06 | COMPLETED | 1 |  |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-24 |  |  | Open Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 136766 | Tambo ES | CITY OF PARAÑAQUE | 1 | 1 | 53 | Renovation of School Building | 3482039.2 | 1 | ₱2,548,301.47 | COMPLETED | 1 |  |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-23 | 2019-08-28 | November 6, 2019 | R2A Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 305428 | Dr. Arcadio Santos NHS - Main | CITY OF PARAÑAQUE | 2 | 1 | 36 | Renovation of School Building | 6374901.7 | 1 | ₱4,074,142.04 | COMPLETED | 1 |  |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-25 |  |  | Trix-Zion Ventures Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City |  | Marcelo Green ES | CITY OF PARAÑAQUE | 2 | 1 | 40 | Renovation of School Building | 6376607.77 | 1 | ₱4,153,528.85 | COMPLETED | 1 |  |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-25 |  |  | Rakmir Trading & Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 136755 | Masville ES | CITY OF PARAÑAQUE | 2 | 1 | 28 | Renovation of School Building | 2751762.77 | 1 | ₱2,739,675.82 | COMPLETED | 1 |  |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-24 |  |  | RGDG Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Pasay City | 136604 | Jose Rizal ES | PASAY CITY | 0 | 1 | 23 | Repair of Classrooms & Gymnasium | 10175124.74 | 1 | 10122201.82 | COMPLETED | 1 | 2022-07-01 |  |  | SDOPC- CA-2021-12-008 | 2021-10-23 |  | 2021-11-12 | 2021-12-01 | 2021-12-06 | Dreamworx Builder & Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Pasay City | 319601 | Kalayaan NHS | PASAY CITY | 0 | 1 | 11 | Repair of Classrooms | 3000000 | 1 | 2898085.88 | COMPLETED | 1 | 1/1/2022 (1/16/2022 revised) |  | SDOPC 2021-07-004 | SDOPC 2021-07-005 |  | 2021-07-22 | 2021-08-03 | 2021-08-19 | 8/26/2021 (9/3/2021 recieved) | RAKMIR TRADING & CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Pasay City | 305367 | Pasay City East HS | PASAY CITY | 0 | 1 | 36 | Repair of classsroom | 13027391.68 | 1 | 12959052.4 | COMPLETED | 1 | 2022-07-15 | March 26, 2021 | SDOPC 2021-07-003 | SDOPC- CA-2021-12-007 | 2021-07-15 | 2021-07-22 | 2021-08-04 | 2021-12-01 | 2021-12-06 | REDCAR TRADING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Pasay City | 136601 | Timoteo Paez ES | PASAY CITY | 0 | 1 | 9 | Repair of Classrooms & Gymnasium | 10478004.8 | 1 | 10408120.51 | COMPLETED | 1 | 2022-07-04 |  |  | SDOPC- CA-2021-12-009 | 2021-10-23 |  | 2021-11-12 | 2021-12-01 | 2021-12-06 | RGDG Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Pasig City | 136736 | Napico Elementary School | CITY OF PASIG | 0 | 1 | 54 | Repair of Classrooms | 10617899 | 1 | 6925414.89 | COMPLETED | 1 |  |  | PB No. 2021-Infra-004 | PCA-2021-Infra-002-a | July 1, 2023 | July 9, 2023 | July 21, 2023 | August 11, 2023 |  | OPEN BUILDERS INCORPORATED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Pasig City | 136720 | Palatiw ES | CITY OF PASIG | 0 | 1 | 12 | Repair of Classrooms | 3966835.32 | 1 | 2776777.56 | COMPLETED | 1 |  |  | PB No. 2021-Infra-005 | PCA-2021-Infra-002-a | July 1, 2024 | July 9, 2024 | July 21, 2024 | August 11, 2024 |  | ZANEYA BUILDERS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Pasig City | 305419 | Santolan HS | CITY OF PASIG | 0 | 1 | 24 | Repair of Classrooms | 9024884.16 | 1 | 6669390 | COMPLETED | 1 |  |  | PB No. 2021-Infra-003 | PCA-2021-Infra-002-a | July 1, 2022 | July 9, 2022 | July 21, 2022 | August 11, 2022 |  | GMO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Pasig City | 305420 | Sta. Lucia HS | CITY OF PASIG | 0 | 1 | 12 | Repair of Classrooms | 3144024.36 | 1 | 2569335.6 | COMPLETED | 1 |  |  | PB No. 2021-Infra-002 | PCA-2021-Infra-002-a | July 1, 2021 | July 9, 2021 | July 21, 2021 | August 11, 2021 |  | OPEN BUILDERS INCORPORATED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Quezon City | 136497 | Masambong Elementary School | QUEZON CITY | 1 | 1 | 41 | Repair of Classrooms | 16400000 | 1 | 16341506.12 | COMPLETED | 1 |  |  |  |  | 2021-08-05 | 2021-08-17 | 2021-08-31 |  |  | AYLAN CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Quezon City | 136506 | Toro Hills ES | QUEZON CITY | 1 | 1 | 10 | Repair of Classrooms | 2995854.13 | 1 | 2995854.13 | COMPLETED | 1 |  |  |  |  | 2021-08-05 | 2021-08-17 | 2021-08-31 |  |  | AYLAN CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Quezon City | 305332 | Bagong Silangan HS | QUEZON CITY | 2 | 1 | 51 | Repair of Classrooms | 20400000 | 1 | 20327239.32 | COMPLETED | 1 |  |  |  |  | 2021-08-05 | 2021-08-17 | 2021-08-31 |  |  | AYLAN CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Quezon City | 136559 | Quirino ES | QUEZON CITY | 3 | 1 | 43 | Repair of Classrooms | 19350000 | 1 | 19280984.36 | COMPLETED | 1 |  |  |  |  | 2021-08-05 | 2021-08-17 | 2021-08-31 |  |  | AYLAN CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Quezon City | 136585 | Diosdado P. Macapagal ES (Tatalon ES) | QUEZON CITY | 4 | 1 | 38 | Repair of Classrooms | 15200000 | 1 | 15145786.16 | COMPLETED | 1 |  |  |  |  | 2021-08-05 | 2021-08-17 | 2021-08-31 |  |  | AYLAN CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Quezon City | 305358 | Ramon Magsaysay (Cubao) HS | QUEZON CITY | 4 | 1 | 55 | Repair of Classrooms | 22000000 | 1 | 21921532.6 | COMPLETED | 1 |  |  |  |  | 2021-08-05 | 2021-08-17 | 2021-08-31 |  |  | AYLAN CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Quezon City | 305336 | Lagro HS | QUEZON CITY | 5 | 1 | 24 | Repair of Classrooms | 9600000 | 1 | 9565759.68 | COMPLETED | 1 |  |  |  |  | 2021-08-05 | 2021-08-17 | 2021-08-31 |  |  | AYLAN CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Quezon City | 136511 | Culiat Elementary School | QUEZON CITY | 6 | 1 | 39 | Repair of Classrooms | 15600000 | 1 | 15544359.48 | COMPLETED | 1 |  |  |  |  | 2021-08-05 | 2021-08-17 | 2021-08-31 |  |  | AYLAN CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Quezon City | 136514 | Pasong Tamo ES | QUEZON CITY | 6 | 1 | 48 | Repair of Classrooms | 19200000 | 1 | 19131519.36 | COMPLETED | 1 |  |  |  |  | 2021-08-05 | 2021-08-17 | 2021-08-31 |  |  | AYLAN CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Taguig | 500342 | Napindan Integrated School | TAGUIG CITY | 1 | 1 | 33 | Repair of Classrooms | 9900000 | 1 |  | COMPLETED | 1 |  |  |  |  | 2021-08-11 | 2021-08-13 | 2021-08-30 |  |  | AYLAN CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Taguig | 136875 | Ricardo P. Cruz, Sr. Elementary School | TAGUIG CITY | 1 | 1 | 18 | Repair of Classrooms | 6300000 | 1 |  | COMPLETED | 1 |  |  |  |  | 2021-08-11 | 2021-08-13 | 2021-08-30 |  |  | AYLAN CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Taguig | 500565 | Taguig Integrated School | TAGUIG CITY | 1 | 1 | 24 | Repair of Classrooms | 7200000 | 1 |  | COMPLETED | 1 |  |  |  |  | 2021-08-11 | 2021-08-13 | 2021-08-30 |  |  | TM ABAD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Taguig | 305460 | Taguig National High School | TAGUIG CITY | 1 | 1 | 41 | Repair of Classrooms | 12300000 | 1 | 2763713.99 | COMPLETED | 1 |  |  | DTP-CY20-INFRA-005 |  | 2021-08-11 | 2021-08-13 | 2021-08-30 | January 8, 2020 | October 26, 2020 | TM ABAD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Taguig | 320601 | Taguig Science High School | TAGUIG CITY | 1 | 1 | 16 | Repair of Classrooms | 4800000 | 1 |  | COMPLETED | 1 |  |  |  |  | 2021-08-11 | 2021-08-13 | 2021-08-30 |  |  | AYLAN CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Taguig | 500340 | Kapitan Eddie T. Reyes Integrated School | TAGUIG CITY | 2 | 1 | 27 | Repair of Classrooms | 8100000 | 1 |  | COMPLETED | 1 | 2022-09-30 |  |  |  | 2021-08-11 | 2021-08-13 | 2021-08-30 |  |  | AYLAN CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Taguig | 500340 | Kapitan Eddie T. Reyes Integrated School | TAGUIG CITY | 2 |  | 6 | Repair of Classrooms | 3000683.71 | 1 |  | COMPLETED | 1 | 2022-09-30 |  |  |  | 2021-08-11 | 2021-08-13 | 2021-08-30 |  |  | AYLAN CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Taguig | 320606 | President Diosdado Macapagal HS - Signal VNHS Annex | TAGUIG CITY | 2 | 1 | 20 | Repair of Classrooms | 7000000 | 1 |  | COMPLETED | 1 |  |  |  |  | 2021-08-11 | 2021-08-13 | 2021-08-30 |  |  | TM ABAD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Taguig | 305463 | Signal Village National High School | TAGUIG CITY | 2 | 1 | 29 | Repair of Classrooms | 10150000 | 1 | 4476962.88 | COMPLETED | 1 | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | 2021-08-11 | 2021-08-13 | 2021-08-30 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Taguig | 136887 | Upper Bicutan ES | TAGUIG CITY | 2 | 1 | 21 | Repair of Classrooms | 6300000 | 1 |  | COMPLETED | 1 |  |  |  |  | 2021-08-11 | 2021-08-13 | 2021-08-30 |  |  | AYLAN CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Taguig | 305465 | Western Bicutan NHS | TAGUIG CITY | 2 | 1 | 23 | Repair of Classrooms | 6900000 | 1 |  | COMPLETED | 1 | 2022-09-30 |  |  |  | 2021-08-11 | 2021-08-13 | 2021-08-30 |  |  | AYLAN CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Valenzuela City | 320406 | Canumay East National High School | CITY OF VALENZUELA | 1 | 1 | 22 | Repair of Classrooms | 7615969.12 | 1 | 7567366.19 | COMPLETED | 1 | 2022-05-28 |  |  | INFRA-BEFF-PB-2021-08-0002(LI) | 2021-06-30 | 2021-07-12 | 2021-07-23 |  | 2021-09-30 | Aylan Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Valenzuela City | 136805 | Paltok ES | CITY OF VALENZUELA | 1 | 1 | 18 | Repair of Classrooms | 7864249.43 | 1 | 7814204.44 | COMPLETED | 1 | 2022-05-28 |  |  | INFRA-BEFF-PB-2021-08-0002(LI) | 2021-06-30 | 2021-07-12 | 2021-07-23 |  | 2021-09-30 | Aylan Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Valenzuela City | 320402 | Vicente Trinidad National High School (Punturin NHS) | CITY OF VALENZUELA | 1 | 1 | 24 | Repair of Classrooms | 10847548.51 | 1 | 10785600.14 | COMPLETED | 1 | 2022-05-28 |  |  | INFRA-BEFF-PB-2021-08-0002(LI) | 2021-06-30 | 2021-07-12 | 2021-07-23 |  | 2021-09-30 | Aylan Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Valenzuela City | 320408 | Bagbaguin National High School | CITY OF VALENZUELA | 2 | 1 | 20 | Repair of Classrooms | 8941874.4 | 1 | 8890203.41 | COMPLETED | 1 | 2022-05-28 |  |  | INFRA-BEFF-PB-2021-08-0002(LI) | 2021-06-30 | 2021-07-12 | 2021-07-23 |  | 2021-09-30 | Aylan Construction & Trading | Other buildings for repair used as isolation by LGU | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Valenzuela City | 305444 | Maysan National High School | CITY OF VALENZUELA | 2 | 1 | 23 | Repair of Classrooms | 10395960.78 | 1 | 10337387.28 | COMPLETED | 1 | 2022-05-28 |  |  | INFRA-BEFF-PB-2021-08-0002(LI) | 2021-06-30 | 2021-07-12 | 2021-07-23 |  | 2021-09-30 | Aylan Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Valenzuela City | 136819 | Silvestre Lazaro Elementary School | CITY OF VALENZUELA | 2 | 1 | 47 | Repair of Classrooms | 14680783.55 | 1 | 14606341.82 | COMPLETED | 1 | 2022-05-28 |  |  | INFRA-BEFF-PB-2021-08-0002(LI) | 2021-06-30 | 2021-07-12 | 2021-07-23 |  | 2021-09-30 | Aylan Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 47 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Valenzuela City | 305441 | Valenzuela NHS | CITY OF VALENZUELA | 2 | 1 | 47 | Repair of Classrooms | 10082592.16 | 1 | 10027879.63 | COMPLETED | 1 | 2022-05-28 |  |  | INFRA-BEFF-PB-2021-08-0002(LI) | 2021-06-30 | 2021-07-12 | 2021-07-23 |  | 2021-09-30 | Aylan Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 47 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2023 | NCR | Caloocan City | 136634 | Camarin Elementary School | KALOOKAN CITY | 1st | 1 | 44 | Repair of Classrooms | 18000000 | DPWH (Batch 2) | 17111059.79 | COMPLETED | 1 | 2024-07-11 | 2024-06-03 | P00775535NP | 23OD0252 | 27/09/2023 | 2023-04-10 | 28/11/2023 | 27/12/2023 | 15/01/2024 | WAWAO BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 1 | 0 |  | 8.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Caloocan City | 305388 | Caloocan HS | KALOOKAN CITY | 2nd | 1 | 102 | Repair of Classrooms | 16991645.34 | DPWH (Batch 2) | 16164581.01 | COMPLETED | 1 | 2024-10-10 |  | P00775536NP | 23OD0254 | 27/09/2023 | 2023-04-10 | 28/11/2023 | 27/12/2023 | 15/01/2024 | AYLAN CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 102 | 0 | 0 | 1 | 0 |  | 1.25 |  |  |  |  | COMPLETED
REPAIR 2023 | NCR | Caloocan City | 136649 | Tala ES | KALOOKAN CITY | 3rd | 1 | 64 | Repair of Classrooms | 18000000 | DPWH (Batch 2) | 17120138.36 | completed | 1 | 2024-10-10 |  | P00775537NP | 23OD0253 | 27/09/2023 | 2023-04-10 | 28/11/2023 | 27/12/2023 | 15/01/2024 | FRAMECON BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 0.85 | 0.15 |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | NCR | Las Piñas City | 136789 | Pilar Village Elementary School | CITY OF LAS PIÑAS | Lone | 1 | 15 | Repair of Classrooms | 8000000 | DPWH (Batch 2) | 7488565.82 | COMPLETED | 1 | 2024-06-14 | 2024-06-14 | P00775578NP | 23OI0115 | 2024-01-05 | 2024-01-12 | 2024-01-25 | 2024-02-07 | 2024-02-23 | Framecon Builders | waiting the installation of the Solar Control Pannel c/o meralco application | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 1 | 0 |  | 1.25 |  |  |  |  | COMPLETED
REPAIR 2023 | NCR | Mandaluyong City | 500334 | Jose Fabella Memorial School | CITY OF MANDALUYONG | Lone | 1 | 32 | Repair of Classrooms | 9746347.14 | DPWH (Batch 2) | 9265002.62 | COMPLETED | 1 | 2024-05-17 | 2024-05-16 | P00775539NP | 23OB0466 | 2023-09-20 | 2023-09-28 | 2023-10-25 | 2024-01-09 | 2024-01-18 | FRANZCOR TRADING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 1 | 0 |  | 9.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Manila | 500566 | T. Paez Integrated School | TONDO | 1st | 1 | 40 | Repair of Classrooms | 7000000 | DPWH (Batch 2) |  | COMPLETED | 1 |  | 2024-05-24 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 1 | 0 |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | NCR | Manila | 136444 | Gen. Maximino Hizon Elementary School | TONDO | 2nd | 1 | 24 | Repair of Classrooms | 23500000 | DPWH (Batch 2) |  | COMPLETED | 1 |  | 2024-08-24 | [8 empty] | Completed 12 classrooms only | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 1 | 0 |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | NCR | Manila | 136458 | Laong Laan ES | SAMPALOC | 4th | 1 | 12 | Repair of Classrooms | 5000000 | DPWH (Batch 2) |  | COMPLETED | 1 |  | 2024-03-24 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | NCR | Manila | 136474 | Dr. Celedonio A. Salvador Elementary School | PACO | 5th | 1 | 43 | Repair of Classrooms | 22262842.81 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 1 | 0 |  | 2.25 |  |  |  |  | Completed
REPAIR 2023 | NCR | Paranaque City | 136763 | F. Serrano Sr. Elementary School | CITY OF PARAÑAQUE | 2nd | 1 | 60 | Repair of Classrooms | 18000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 1 | 0 |  | 8.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Paranaque City | 137127 | Marcelo Green Elementary School | CITY OF PARAÑAQUE | 2nd | 1 | 40 | Repair of Classrooms | 2000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 1 | 0 |  | 8.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Paranaque City | 305975 | Marcelo Green High School Parañaque | CITY OF PARAÑAQUE | 2nd | 1 | 16 | Repair of Classrooms | 4000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 1 | 0 |  | 8.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Paranaque City | 320204 | Sun Valley National High School | CITY OF PARAÑAQUE | 2nd | 1 | 40 | Repair of Classrooms | 6000000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 1 | 0 |  | 8.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Pasig City | 136724 | Bambang Elementary School | CITY OF PASIG | Lone | 1 | 20 | Repair of Classrooms | 10000000 | DPWH (Batch 2) | 9648509.54 | COMPLETED | 1 | 2024-05-17 | 2024-05-17 | P00775548NP | 23OB0462 | 2023-09-20 | 2023-09-28 | 2023-10-25 | 2024-01-09 | 2024-01-19 | Prudent Diamond Square Construction Co. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 1 | 0 |  | 10.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Pasig City | 305418 | Manggahan High School | CITY OF PASIG | Lone | 1 | 4 | Repair of Classrooms | 4500000 | DPWH (Batch 2) | 4342216.28 | COMPLETED | 1 | 2024-03-18 | 2024-02-19 | P00775551NP | 23OB0465 | 2023-09-20 | 2023-09-28 | 2023-10-25 | 2024-01-09 | 2024-01-19 | Prudent Diamond Square Construction Co. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 10.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Pasig City | 136742 | Maybunga Elementary School | CITY OF PASIG | Lone | 1 | 12 | Repair of Classrooms | 4000000 | DPWH (Batch 2) | 3859664.34 | COMPLETED | 1 | 2024-03-18 | 2024-02-19 | P00775549NP | 23OB0463 | 2023-09-20 | 2023-09-28 | 2023-10-25 | 2024-01-09 | 2024-01-19 | 816 Ember Construction Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | 10.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Pasig City | 305413 | Rizal High School | CITY OF PASIG | Lone | 1 | 16 | Repair of Classrooms | 10000000 | DPWH (Batch 2) | 9601704.9 | COMPLETED | 1 | 2024-05-17 | 2024-06-30 | P00775550NP | 23OB0464 | 2023-09-20 | 2023-09-28 | 2023-10-25 | 2024-01-09 | 2024-01-19 | Dahl Construction Corp. | Revised target date of completion: July 1, 2024 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 1 | 0 |  | 10.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Quezon City | 136499 | Bayanihan Elementary School | QUEZON CITY | 1st | 1 | 12 | Repair of Classrooms | 2000000 | DPWH (Batch 2) | 1909971.31 | COMPLETED | 1 | 2024-05-03 | 2024-03-18 |  | 23OF0171 | 2023-09-22 | 2023-09-29 | 2023-10-11 | 2023-12-29 | 2024-01-05 | FRAMECON BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | 5.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Quezon City | 136502 | Paltok ES | QUEZON CITY | 1st | 1 | 10 | Repair of Classrooms | 3500000 | DPWH (Batch 2) | 3343725 | COMPLETED | 1 | 2024-05-03 | 2024-03-18 |  | 23OF0171 | 2023-09-22 | 2023-09-29 | 2023-10-11 | 2023-12-29 | 2024-01-05 | FRAMECON BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 |  | 5.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Valenzuela City | 305445 | Caruhatan National High School | CITY OF VALENZUELA | 2nd | 1 | 32 | Repair of Classrooms | 18000000 | DPWH (Batch 2) | 17039839.13 | COMPLETED | 1 | 2024-08-09 |  | P00775555NP | 23OD0249 | 2024-12-30 | 2024-01-05 | 2023-10-17 | 2024-01-30 | 2024-02-12 | Giltop Civil Engineering Construction | for final inspection of DepEd | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 1 | 0 |  | 1.25 |  |  |  |  | Completed
REPAIR 2023 | NCR | Valenzuela City | 320403 | Mapulang Lupa National High School | CITY OF VALENZUELA | 2nd | 1 | 21 | Repair of Classrooms | 18000000 | DPWH (Batch 2) | 17038731.62 | COMPLETED | 1 | 2024-08-09 |  | P00775556NP | 23OD05251 | 2024-12-30 | 2024-01-05 | 2023-10-17 | 2024-01-30 | 2024-02-12 | Giltop Civil Engineering Construction | for final inspection of DepEd | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 1 | 0 |  | 1.25 |  |  |  |  | completed
REPAIR 2023 | NCR | Valenzuela City | 305446 | Sitero Francisco Memorial National High School | CITY OF VALENZUELA | 2nd | 1 | 21 | Repair of Classrooms | 18000000 | DPWH (Batch 2) | 17034781.35 | COMPLETED | 1 | 2024-08-09 |  | P00775554NP | 23OD0520 | 2024-12-30 | 2024-01-05 | 2023-10-17 | 2024-01-30 | 2024-02-12 | Giltop Civil Engineering Construction | for final inspection of DepEd | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 1 | 0 |  | 1.25 |  |  |  |  | completed
REPAIR 2024 | NCR | Caloocan City | 136625 | Baesa ES | KALOOKAN CITY | 1st | 1 | 16 | Repair of Classrooms | 7575757.58 | 1 | 7449908.85 | Ongoing | 0.45 | 2025-06-01 |  | PB No. 2024-Infra-002 | 2024-Cal-PB-009 | 2024-08-20 | 2024-08-27 | 2024-09-11 | 2024-10-01 | 2024-12-03 | CARRY-ON CONSTRUCTION | Limited implementation of works due to unavailability of temporary classrooms | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0.3 | 0.15 | [6 empty] | Ongoing
REPAIR 2024 | NCR | City of San Juan | 136746 | San Juan ES | CITY OF SAN JUAN | Lone | 1 | 6 | Repair of Classrooms | 2727272.73 | 1 | 2695000 | COMPLETED | 1 | 2025-04-10 | 2025-03-07 | REPAIR2024-NCR-SAN JUAN-001 | INFRA2024-002 | 2024-06-19 | 2024-06-27 | 2024-07-09 | 2024-11-11 | 2024-12-03 | Hawkstow Construction and Development | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | NCR | Las Piñas City | 136788 | Pamplona Elementary School Unit I | CITY OF LAS PIÑAS | Lone | 1 | 8 | Repair of Classrooms | 6060606.06 | 1 | 5991800.23 | COMPLETED | 1 | 2025-02-16 | 2024-12-06 | 2024-06-I-02 | 2024-06-I-02 | 27/06/2024 | 2024-07-05 | 2024-07-18 | 2024-08-01 | 2024-09-19 | Image Builders and General Services | Completed and Turned over | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | NCR | Malabon City | 136834 | Imelda ES | CITY OF MALABON | Lone | 1 | 6 | Repair of Classrooms | 959595.96 | 1 | 945760.95 | COMPLETED | 1 | 2025-01-20 | 2024-12-12 |  | 2024-INFRA-09-0004 |  | 2024-08-08 | 2024-08-20 | 2024-08-30 | 2024-09-30 | SHERF BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | 1.25 |  |  |  |  | completed
REPAIR 2024 | NCR | Malabon City | 136830 | Malabon ES | CITY OF MALABON | Lone | 1 | 9 | Repair of Classrooms | 2525252.53 | 1 | 2466707.98 | completed | 1 | 2025-02-19 |  |  | 2024-INFRA-09-0002 |  | 2024-08-08 | 2024-08-20 | 2024-08-30 | 2024-09-30 | MARTIAN BUILDERS and SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0.8 | 0.2 |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | NCR | Malabon City | 136844 | Muzon ES | CITY OF MALABON | Lone | 1 | 6 | Repair of Classrooms | 959595.96 | 1 | 946300.74 | COMPLETED | 1 | 2025-01-20 | 2024-12-12 |  | 2024-INFRA-09-0003 |  | 2024-08-08 | 2024-08-20 | 2024-08-30 | 2024-09-30 | TAPNIO and TAN CONSTRUCTION and DEVT CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | 1.25 |  |  |  |  | completed
REPAIR 2024 | NCR | Mandaluyong City | 136661 | Plainview Elementary School | CITY OF MANDALUYONG | Lone | 1 | 12 | Repair of Classrooms | 6243580.18 | 1 | 4018358.82 | Ongoing | 0.95 | 2025-03-20 | 2025-04-20 | REPAIR2024-NCR-MANDALUYONG-001 | OSEC-NCR-24-5376 | 2024-10-23 | 2024-11-05 | 2024-11-12 | 2024-11-14 | 2024-11-20 | GUILLAND CONSTRUCTION AND TRADING | For procurement | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0.95 | 0 | [6 empty] | Ongoing
REPAIR 2024 | NCR | Manila | 305308 | Valeriano E. Fugoso Memorial High School | QUIAPO | 4th | 1 | 7 | Repair of Classrooms | 5303030.3 | 1 |  | Ongoing | 0.65 | [9 empty] | JKK CONSTRUCTION SERVICES | Contractor received the Notice to Proceed last March 25, 2025 only | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0.15 | 0.5 | [6 empty] | Ongoing
REPAIR 2024 | NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA | 2nd | 1 | 36 | Repair of Classrooms | 8537771.05 | 1 | 8452393.34 | Completed | 1 | 2025-05-25 |  | BEFF-REPAIR -2024-NCR-MARIKINA CITY-001 | BEFF-REPAIR -2024-NCR-MARIKINA CITY-001 | 2024-11-05 | 2024-11-12 | 2024-11-28 | 2024-12-12 | 2024-12-26 | Marakesh Enterprises | With Approved Extra Work Order of P20,393.34 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0.75 | 0.25 |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | NCR | Muntinlupa City | 136910 | Bayanan ES - Unit I | CITY OF MUNTINLUPA | Lone | 1 | 38 | Repair of Classrooms | 535173.3 | 1 | 454897.23 | COMPLETED | 1 | 2025-03-31 | 2025-03-28 |  | 2024-007 | Sept 20-27, 2024 | Sept. 30, 2024 | 2024-10-14 | 2024-11-13 | 2024-12-02 | Dreamworx Builder and Trading, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 1 | 0 |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | NCR | Muntinlupa City | 136913 | Cupang ES - Annex | CITY OF MUNTINLUPA | Lone | 1 | 12 | Repair of Classrooms | 1450569.22 | 1 | 1232983.84 | COMPLETED | 1 | 2025-03-31 | 2025-03-28 |  | 2024-007 | Sept 20-27, 2024 | Sept. 30, 2024 | 2024-10-14 | 2024-11-13 | 2024-12-02 | Dreamworx Builder and Trading, Inc. | realigned from Cupang ES- Annex to 3 school sites (Cupang ES- Annex, Sucat ES Sitio Pagkakaisa- Annex and Bayanan ES Unit 1) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | 4.25 | 1 | 9 | 6060606.06 |  | Completed
REPAIR 2024 | NCR | Muntinlupa City | 136915 | Sucat ES Sitio Pagkakaisa - Annex | CITY OF MUNTINLUPA | Lone | 1 | 6 | Repair of Classrooms | 4014257.48 | 1 | 3412118.83 | COMPLETED | 1 | 2025-03-31 | 2025-03-28 |  | 2024-007 | Sept 20-27, 2024 | Sept. 30, 2024 | 2024-10-14 | 2024-11-13 | 2024-12-02 | Dreamworx Builder and Trading, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | NCR | Navotas City | 305453 | Navotas National High School | CITY OF NAVOTAS | Lone | 1 | 15 | Repair of Classrooms | 5303030.3 | 1 |  | Ongoing | 0.85 | [10 empty] | for procurement | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0.85 | [6 empty] | Ongoing
REPAIR 2024 | NCR | Paranaque City | 136759 | San Antonio Elementary School | CITY OF PARAÑAQUE | 2nd | 1 | 20 | Repair of Classrooms | 5850738.62 | 1 |  | COMPLETED | 1 | 2025-03-15 |  | Par -11030754 | PB-2024-032-B | 2024-07-10 | 2024-07-18 | 2024-07-30 | 2024-08-05 | 2024-10-16 | RGDG Construction | PROCURED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 1 | 0 |  | 4.25 |  |  |  |  | completed
REPAIR 2024 | NCR | Pasay City | 136595 | Rivera Village Elementary School | PASAY CITY | Lone | 1 | 11 | Repair of Classrooms | 7575757.58 | 1 | 5779796.68 | Ongoing | 0.85 | 2025-09-06 |  | SDOPC- 2025-01-001-PB | SDOPC- 2025-01-001-PB | 2025-01-09 | 2025-02-03 | 2025-02-04 | 2025-02-19 | 2025-02-20 | RHR Construction | On-going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0.25 | 0.6 | [6 empty] | Ongoing
REPAIR 2024 | NCR | Quezon City | 136534 | Lagro ES | QUEZON CITY | 5th | 1 | 12 | Repair of Classrooms | 7070707.07 | 1 |  | UNDER PROCUREMENT | 0 | [10 empty] | BID-OUT (APRIL 21, 2025) | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Ongoing
REPAIR 2024 | NCR | Taguig City and Pateros | 502057 | Bagong Tanyag Integrated School | TAGUIG CITY | 2nd | 1 | 9 | Repair of Classrooms | 5144117.09 | 1 | 5048001.8 | COMPLETED | 1 |  |  | DTP-CY2024-INFRA-001 |  | 2024-07-31 | 2024-08-07 | 2024-08-19 | 2024-08-27 | 2024-10-15 | Ramalla Construction and Trading | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | NCR | VALENZUELA CITY | 136798 | MAYSAN ELEMENTARY SCHOOL | CITY OF VALENZUELA | 2nd | 1 | 12 | Repair of Classrooms | 5454545.45 | 1 | 4742254.36 | Completed | 1 |  |  | SDO-VAL-PB-BEFF-REPAIR-2024-11-0004 | SDO-VAL-PB-BEFF-REPAIR-2024-11-0004 |  | 2024-10-29 | 2024-11-11 |  | Decemeber 2, 2024 | Hawkstow Construction and Development | on going, with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0.75 | 0.25 |  | 5.25 |  |  |  |  | Ongoing