## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No of Sites | SCOPE OF WORK | Batch | Project Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Site Reverted | No. of Site Not yet started | No. of Site Under Procurement | No. of Site On Going | No. of Site Completed | No. of Site Terminated | WITH TRANSFOPMER (Y/N) | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | CATEGORY 2 | Unnamed: 43
ELECTRIFICATION 2017 | Region I | Pangasinan II, Binalonan | 102132 | Bila ES | SISON | 5 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 201940.01 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region I | Pangasinan II, Binalonan | 102024 | Calunetan ES | SISON | 5 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 287690.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region I | Pangasinan II, Binalonan | NOT.IN.BEIS | Bangar ES | San Nicolas | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 190649.72 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region I | Pangasinan II, Binalonan | 101971 | Cristobal Rodrigo ES | SAN NICOLAS | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 125121.99 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region I | Pangasinan II, Binalonan | 101992 | Pastoran ES | SAN NICOLAS | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 169595.41 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region I | Pangasinan II, Binalonan | 101993 | Puyao ES | SAN NICOLAS | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 174550.95 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region I | Pangasinan II, Binalonan | 102099 | Casilan ES | UMINGAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 113224.83 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Alaminos City | 300155 | Alaminos City NHS | CITY OF ALAMINOS | 1 | 1 | UPGRADING | 2 | 2376416.44 | 2364155.76 | COMPLETED | 1 | 2018-07-19 | 2018-07-19 |  |  | 2018-04-13 | 2018-04-19 | 2018-05-03 | 2018-05-10 | 2018-05-21 | ALCEL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Batac City | 300005 | Batac National High School | Batac City | 2 | 1 | UPGRADING | 2 | 1305111.24 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Batac City | 300012 | CRISPINA MARCOS VALDEZ NHS | Batac City | 2 | 1 | UPGRADING | 2 | 1305111.24 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Candon City | 300047 | Candon City High School | CITY OF CANDON | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 711644.09 | 705.320.36 | COMPLETED | 1 | 2018-11-26 | 2019-02-13 | PB-INFRA-02-2018 |  | 2018-07-07 | 2018-07-17 | 2018-07-17 | 2018-08-20 | 2018-08-28 | MRK SQUARE CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Candon City | 300051 | Dr. Ricardo Gacula Memorial National High School | CITY OF CANDON | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 958451.44 | 950712.2 | COMPLETED | 1 | 2018-11-26 | 2019-02-13 | PB-INFRA-02-2018 |  | 2018-07-07 | 2018-07-17 | 2018-07-17 | 2018-08-20 | 2018-08-28 | MRK SQUARE CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Candon City | 300083 | Sto. Tomas National High School | CITY OF CANDON | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 880009.36 | 873967.44 | COMPLETED | 1 | 2018-11-26 | 2019-02-13 | PB-INFRA-02-2018 |  | 2018-07-07 | 2018-07-17 | 2018-07-17 | 2018-08-20 | 2018-08-28 | MRK SQUARE CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Dagupan City | 102157 | East Central IS | DAGUPAN CITY | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1567287.75 | 1554489.25 | COMPLETED | 1 | July 4, 2018 | July 4, 2018 | [6 empty] | April 6, 2018 | ZOTA TRADING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Dagupan City | 500054 | Federico N. Ceralde IS | DAGUPAN CITY | 4 | 1 | UPGRADING | 2 | 1136698.75 | 1127180.5 | COMPLETED | 1 | 2018-09-25 | 2018-09-25 | [5 empty] | 2018-06-28 | 2018-07-06 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Dagupan City | 102178 | Pugaro IS | DAGUPAN CITY | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1069836.08 | 1059523.39 | COMPLETED | 1 | July 4, 2018 | July 4, 2018 | [6 empty] | April 6, 2018 | ZOTA TRADING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300001 | Adams NHS | ADAMS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 825617.42 | 803491.0678 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300006 | Burgos Agro-Industrial School | BURGOS | 1 | 1 | UPGRADING | 2 | 804898.5191 | 787840.2812 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300009 | Carasi NHS | CARASI | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1143193.66 | 1119174.8024 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300017 | Dumalneg NHS | DUMALNEG | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1131237.69 | 1107922.4984 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300019 | Luzong NHS | PAGUDPUD | 1 | 1 | UPGRADING | 2 | 650890.0578 | 634920.9062 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300024 | PAGUDPUD NHS | PAGUDPUD | 1 | 1 | UPGRADING | 2 | 712493.4423 | 695928.5312 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1 | 1 | UPGRADING | 2 | 804898.5191 | 787840.2812 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 500592 | Pandan IS | SARRAT | 1 | 1 | UPGRADING | 2 | 650890.0578 | 634920.9062 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300029 | Sarrat National High School | SARRAT | 1 | 1 | UPGRADING | 2 | 804898.5191 | 787039.6562 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 320816 | STA. ROSA NATIONAL HIGH SCHOOL | SARRAT | 1 | 1 | UPGRADING | 2 | 681691.7501 | 665344.6562 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 320821 | ISIC-ISIC NATIONAL HIGH SCHOOL | VINTAR | 1 | 1 | UPGRADING | 2 | 589286.6733 | 573753.1562 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 500344 | SALPAD INTEGRATED SCHOOL | VINTAR | 1 | 1 | UPGRADING | 2 | 620088.3656 | 603536.4062 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300002 | Bacarra NCHS | BACARRA | 2 | 1 | UPGRADING | 2 | 881902.7497 | 864700.2812 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 500000 | Caraitan Integrated School | BADOC | 2 | 1 | UPGRADING | 2 | 681691.7501 | 665024.4062 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300021 | Nagrebcan NHS | BADOC | 2 | 1 | UPGRADING | 2 | 681691.7501 | 665344.6562 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300003 | Bangui NHS | BANGUI | 2 | 1 | UPGRADING | 2 | 681691.7501 | 665504.7812 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300008 | Caestebanan NHS | BANNA (ESPIRITU) | 2 | 1 | UPGRADING | 2 | 620088.3656 | 604337.0312 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300013 | Currimao NHS | CURRIMAO | 2 | 1 | UPGRADING | 2 | 650890.0578 | 634120.2812 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 320806 | Dingras NHS/Lt. Edgar Foz Mem. NHS (Barong Campus) | DINGRAS | 2 | 1 | UPGRADING | 2 | 589286.6733 | 573593.0312 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 320809 | Dingras NHS/Lt. Edgar Foz Mem. NHS- (Sulquiano Campus) | DINGRAS | 2 | 1 | UPGRADING | 2 | 650890.0578 | 634920.9062 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 320807 | San Marcelino National High School | DINGRAS | 2 | 1 | UPGRADING | 2 | 620088.3656 | 604240.9563 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300020 | Marcos NHS | MARCOS | 2 | 1 | UPGRADING | 2 | 650890.0578 | 634920.9062 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300022 | NUEVA ERA NATIONAL HIGH SCHOOL | NUEVA ERA | 2 | 1 | UPGRADING | 2 | 650890.0578 | 634920.9062 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 320814 | Paoay National High School | PAOAY | 2 | 1 | UPGRADING | 2 | 804898.5191 | 787039.6562 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 500593 | Sacritan IS | PINILI | 2 | 1 | UPGRADING | 2 | 650890.0578 | 634920.9062 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300028 | San Nicolas NHS | SAN NICOLAS | 2 | 1 | UPGRADING | 2 | 727894.2885 | 710980.2812 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300030 | Solsona National High School | SOLSONA | 2 | 1 | UPGRADING | 2 | 774096.8268 | 711620.7812 | COMPLETED | 1 | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Sur | 100370 | Bantay East CS | BANTAY | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 593540.61 | 588675.89 | COMPLETED | 1 | 2018-11-26 | 2018-11-23 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Sur | 300038 | Bantay NHS | BANTAY | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 686696.24 | 648431.79 | COMPLETED | 1 | 2018-11-26 | 2018-12-03 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Sur | 100371 | Bantay West Central School | BANTAY | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 618227.78 | 589207.33 | COMPLETED | 1 | 2018-11-26 | 2018-11-23 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Sur | 100372 | Bulag ES | BANTAY | 1 | 1 | UPGRADING | 1 | 379200.22 | 375489.93 | COMPLETED | 1 | 2018-11-09 | 2018-12-03 |  |  | 2018-08-30 |  | 2018-09-06 | 2018-09-07 | 2018-09-10 | RAMSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Sur | 300045 | Caoayan NHS | CAOAYAN | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 986746.23 | 979288.47 | COMPLETED | 1 | 2018-11-26 | 2019-03-21 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Sur | 300035 | SAN JUAN NHS | SAN JUAN (LAPOG) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1092784.66 | 1085483.84 | COMPLETED | 1 | 2018-11-26 | 2019-03-29 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Sur | 100617 | San Vicente IS | SAN VICENTE | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 808567.21 | 803172.25 | COMPLETED | 1 | 2018-11-26 | 2019-03-21 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Sur | 300080 | Sinait NHS | SINAIT | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 557523.26 | 534791.41 | COMPLETED | 1 | 2018-11-26 | 2019-03-29 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Sur | 300063 | Narvacan Nat'l. Central HS | NARVACAN | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 629893.44 | 624266.05 | COMPLETED | 1 | 2018-11-26 | 2019-03-21 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Sur | 320901 | Mabilbila IS | SANTA | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 947353.53 | 940831.52 | COMPLETED | 1 | 2018-11-26 | 2018-11-23 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Sur | 300077 | Santa Maria NHS | SANTA MARIA | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 887388.59 | 882020.33 | COMPLETED | 1 | 2018-11-26 |  |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | La Union | 300106 | Balaoan NHS-Castor Concepcion MNHS | BALAOAN | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1536816.3 | 1362570.53 | COMPLETED | 1 | [9 empty] | JANPAC ENGINEERING & CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | La Union | 321018 | LUNA NATIONAL VOCATIONAL HIGH SCHOOL | LUNA | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1006982.57 | 891632.77 | COMPLETED | 1 | [9 empty] | JANPAC ENGINEERING & CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | La Union | 300124 | Oanari NHS | LUNA | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 969820.67 | 860218.38 | COMPLETED | 1 | [9 empty] | JANPAC ENGINEERING & CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | La Union | 300097 | Balbalayang NHS | SAN GABRIEL | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1092741.59 | 968373.08 | COMPLETED | 1 | [9 empty] | JANPAC ENGINEERING & CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | La Union |  | SAN JUAN SENIOR HIGH SCHOOL | SAN JUAN | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1011563.33 | 894104.76 | COMPLETED | 1 | [9 empty] | JANPAC ENGINEERING & CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | La Union | 300093 | Aringay NHS | ARINGAY | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1789981.7 | 1780026.31 | COMPLETED | 1 | [9 empty] | NMDC CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | La Union | 300090 | Eulogio Clarence De Guzman Junior Memorial National Vocational High School | BAUANG | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 956985.36 | 904095.35 | COMPLETED | 1 | [9 empty] | JANPAC ENGINEERING & CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | La Union | 300128 | Paringao NHS | BAUANG | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 970724.94 | 917914.02 | COMPLETED | 1 | [9 empty] | JANPAC ENGINEERING & CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | La Union | 300136 | San Gregorio National High School | CABA | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1025780.07 | 1019626.69 | COMPLETED | 1 | [9 empty] | NMDC CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | La Union | 300091 | Amlang-Nagtagaan NHS | ROSARIO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1163070.09 | 1156233.67 | COMPLETED | 1 | [9 empty] | NMDC CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | La Union | 300152 | Tubao National High School | TUBAO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1949479.54 | 1938730.64 | COMPLETED | 1 | [9 empty] | NMDC CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Laoag City | 300374 | ILOCOS NORTE NATIONAL HIGH SCHOOL | LAOAG CITY | 1 | 1 | UPGRADING | 2 | 2213609.278 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300158 | Anda National High School | ANDA | 1 | 1 | UPGRADING | 2 | 940466.25 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 500608 | BANI EAST INTEGRATED SCHOOL | BANI | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1238583.7 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300192 | Dacap Norte NHS | BANI | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 459052.5 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300268 | Zaragosa NHS | BOLINAO | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1709137.99 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 500441 | Dasol IS | DASOL | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1008247.87 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300255 | Sual National High School | SUAL | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1188525.14 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300173 | Bocboc East NHS | AGUILAR | 2 | 1 | UPGRADING | 2 | 1180826.86 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300267 | Irene Rayos Ombac NHS | BUGALLON | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 459052.5 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300233 | Pangasinan NHS | LINGAYEN (Capital) | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1301990.03 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300234 | Pangasinan SAT | LINGAYEN (Capital) | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1200219.41 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300236 | Urbiztondo National High School | URBIZTONDO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 923773.32 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300168 | Bayambang NHS (Bayambang) | BAYAMBANG | 3 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1086061.05 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300188 | Moises B. Rebamontan NHS | BAYAMBANG | 3 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 577242.58 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300259 | Tanolong National High School | BAYAMBANG | 3 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 654297.57 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300224 | Mapandan National High School | MAPANDAN | 3 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1622181.45 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300265 | Torres NHS | MAPANDAN | 3 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 954894.47 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300237 | Payas NHS | SANTA BARBARA | 3 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 641892.95 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300294 | Cabanbanan NHS | MANAOAG | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 815407.48 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 500383 | Mangaldan IS | MANGALDAN | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1560913.55 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300326 | Mangaldan National High School | MANGALDAN | 4 | 1 | UPGRADING | 2 | 2534915.7 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300272 | Ambalangan Dalin NHS | SAN FABIAN | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 693500.18 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300274 | Anonang NHS | SAN FABIAN | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 876203.79 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 500006 | San Fabian IS | SAN FABIAN | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 897261.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300321 | Lobong NHS | SAN JACINTO | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 824735.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300348 | San Jacinto National High School | SAN JACINTO | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 808925.25 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300355 | San Pedro Apartado NHS | ALCALA | 5 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 701069.14 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300287 | Benigno V. Aldana NHS | POZORRUBIO | 5 | 1 | UPGRADING | 2 | 820000 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300290 | Bobonan National High School | POZORRUBIO | 5 | 1 | UPGRADING | 2 | 827525 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 500380 | Dilan Integrated School | POZORRUBIO | 5 | 1 | UPGRADING | 2 | 814693.9 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300329 | San Pedro Apartado NHS | POZZORUBIO | 5 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 904428.35 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300279 | Alejandro F. Oligan HS (Asan Sur NHS) | SISON | 5 | 1 | UPGRADING | 2 | 853000 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 500378 | Don Valentin Torres Integrated School | SISON | 5 | 1 | UPGRADING | 2 | 881072.42 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300284 | Barangobong NHS | VILLASIS | 5 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 682758.6 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 500385 | DUNGON IS | VILLASIS | 5 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 581796.47 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300300 | Carosucan Sur NHS | ASINGAN | 6 | 1 | UPGRADING | 2 | 653572.63 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300281 | Balungao NHS | BALUNGAO | 6 | 1 | UPGRADING | 2 | 874817.26 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300331 | Natividad NHS | NATIVIDAD | 6 | 1 | UPGRADING | 2 | 759129.66 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300311 | Eugenio P. Perez NHS | POZORRUBIO | 6 | 1 | UPGRADING | 2 | 886391.64 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300340 | Robert B. Estrella Memorial NHS | ROSALES | 6 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 655749.22 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300328 | Mataas Na Paaralang Juan C. Laya | SAN MANUEL | 6 | 1 | UPGRADING | 2 | 921000 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300309 | Eastern Pangasinan Agricultural College | SANTA MARIA | 6 | 1 | UPGRADING | 2 | 1598495.33 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | San Carlos City | 500059 | Agdao Integrated School | SAN CARLOS CITY | 3 | 1 | UPGRADING | 3 | 1427586.4 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | San Carlos City | 300379 | Cobol NHS | SAN CARLOS CITY | 3 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 954866.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | San Carlos City | 300380 | COLILING NATIONAL HIGH SCHOOL | SAN CARLOS CITY | 3 | 1 | UPGRADING | 2 | 1004365.1075 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | San Carlos City | 300382 | Libas NHS | SAN CARLOS CITY | 3 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1009366.63 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | San Carlos City | 300384 | Mabalbalino NHS | SAN CARLOS CITY | 3 | 1 | UPGRADING | 3 | 1187919.87 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | San Carlos City | 300385 | Malacanang NHS | SAN CARLOS CITY | 3 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1016668.74 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | San Carlos City | 300389 | Tamayo National High School | SAN CARLOS CITY | 3 | 1 | UPGRADING | 3 | 1252621.19 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | San Carlos City | 300390 | Tandoc NHS | SAN CARLOS CITY | 3 | 1 | UPGRADING | 2 | 1361537.6706 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | San Carlos City | 500057 | Tarece Integrated School | SAN CARLOS CITY | 3 | 1 | UPGRADING | 3 | 1996698.46 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | San Carlos City | 300391 | Turac NHS | SAN CARLOS CITY | 3 | 1 | UPGRADING | 2 | 1464095.4917 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | San Fernando City | 300099 | Bangbangolan NHS | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING | 2 | 1328769.3294 | 1189731.25 | COMPLETED | 1 |  |  |  |  | 2018-04-27 | 2018-05-08 | 2018-05-18 | 2018-05-30 | 2018-06-01 | AE SQUARE ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | San Fernando City | 500983 | San Fernando City SPED Integrated School | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING | 2 | 1097980.9423 | 917243.5 | COMPLETED | 1 |  |  |  |  | 2018-04-27 | 2018-05-08 | 2018-05-18 | 2018-05-30 | 2018-06-01 | AE SQUARE ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | San Fernando City | 101030 | San Fernando North CS (North CES) | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING | 2 | 1051360.8415 | 925785.69 | COMPLETED | 1 |  |  |  |  | 2018-04-27 | 2018-05-08 | 2018-05-18 | 2018-05-30 | 2018-06-01 | AE SQUARE ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | San Fernando City | 500602 | San Fernando South Central Integrated School (South CIS) | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING | 2 | 620849.2327 | 541254.44 | COMPLETED | 1 |  |  |  |  | 2018-04-27 | 2018-05-08 | 2018-05-18 | 2018-05-30 | 2018-06-01 | AE SQUARE ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Urdaneta City | 300395 | Cabaruan NHS | CITY OF URDANETA | 5 | 1 | UPGRADING | 2 | 1068477.85 | 957618.51 | COMPLETED | 1 | 8-16-2018 | 10-15-2018 |  |  | 2018-02-04 | 2018-10-04 | 4-23-2018 | 2018-07-05 | 2018-11-05 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Urdaneta City | 300397 | Camabu NHS | CITY OF URDANETA | 5 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 847104.78 | 783323.06 | COMPLETED | 1 | 8-16-2018 | 10-15-2018 |  |  | 2018-02-04 | 2018-10-04 | 4-23-2018 | 2018-07-05 | 2018-11-05 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Urdaneta City | 500007 | Catablan IS | CITY OF URDANETA | 5 | 1 | UPGRADING | 2 | 913475.77 | 843045.43 | COMPLETED | 1 | 8-16-2018 | 10-15-2018 |  |  | 2018-02-04 | 2018-10-04 | 4-23-2018 | 2018-07-05 | 2018-11-05 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Urdaneta City | 300406 | Nancalobasaan NHS | CITY OF URDANETA | 5 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1006805.78 | 930663.77 | COMPLETED | 1 | 8-16-2018 | 10-15-2018 |  |  | 2018-02-04 | 2018-10-04 | 4-23-2018 | 2018-07-05 | 2018-11-05 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Vigan City | 100786 | Burgos Memorial School West | CITY OF VIGAN (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1258735.11 | 1218637.93 | COMPLETED | 1 |  |  |  |  | 2018-02-12 | 2018-02-26 | 2018-03-12 | 2018-04-17 | 2018-04-23 | ELKAN Engineering Services and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region I | Vigan City | 100798 | San Julian ES | CITY OF VIGAN (Capital) | 1 | 1 | UPGRADING | 1 | 220225.14 | 219081.49 | COMPLETED | 1 |  |  |  |  | 2018-02-12 | 2018-02-26 | 2018-03-12 | 2018-04-17 | 2018-04-23 | ELKAN Engineering Services and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region I | Vigan City | 100800 | Vigan CS | CITY OF VIGAN (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1032751.73 | 1024505.51 | COMPLETED | 1 |  |  |  |  | 2018-02-12 | 2018-02-26 | 2018-03-12 | 2018-04-17 | 2018-04-23 | ELKAN Engineering Services and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2019 | Region I | Alaminos City | 300157 | Alos NHS | CITY OF ALAMINOS | 1 | 1 | UPGRADING |  | 502151.58 | 498392.85 | COMPLETED | 1 | 0CT. 10, 2019 | SEPT. 16, 2019 | INFRA-2018-12-14 | INFRA-2018-12-14 | NOV. 21-28, 2018 | NOv. 27, 2018 | Dec. 12, 2018 | DEC. 18, 2018 | AUG. 12, 2019 | ALCEL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Alaminos City | 300253 | San Vicente NHS | CITY OF ALAMINOS | 1 | 1 | UPGRADING |  | 1560326.86 | 1550655.04 | COMPLETED | 1 | 0CT. 10, 2019 | SEPT. 16, 2019 | INFRA-2018-12-14 | INFRA-2018-12-14 | NOV. 21-28, 2018 | NOv. 27, 2018 | Dec. 12, 2018 | DEC. 18, 2018 | AUG. 12, 2019 | ALCEL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Candon City | 300044 | Candon National High School | CITY OF CANDON | 2 | 1 | UPGRADING |  | 2277028.06 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Candon City | 100435 | Candon North Central School | CITY OF CANDON | 2 | 1 | UPGRADING |  | 279530.97 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Candon City | 100437 | Caterman Elementary School | CITY OF CANDON | 2 | 1 | UPGRADING |  | 543662.36 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Candon City | 100440 | Darapidap Elementary School | CITY OF CANDON | 2 | 1 | UPGRADING |  | 413843.15 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Dagupan City | 300368 | Dagupan City NHS | DAGUPAN CITY | 4 | 1 | UPGRADING | Batch 1 | 14039604.71 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 300026 | Pasaleng National High School | PAGUDPUD | 1 | 1 | UPGRADING |  | 558498.94 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 300004 | Banna National High School | BANNA (ESPIRITU) | 2 | 1 | UPGRADING |  | 650906.33 |  | REVERTED | 0 | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 |  |  | UPGRADING | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 300011 | Catagtaguen National High School | BANNA (ESPIRITU) | 2 | 1 | UPGRADING |  | 681708.79 |  | REVERTED | 0 | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 |  |  | UPGRADING | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 320805 | Currimao NHS (Pias-Gaang Campus) | CURRIMAO | 2 | 1 | UPGRADING |  | 620103.87 |  | REVERTED | 0 | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 |  |  | UPGRADING | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 320808 | Dingras NHS/Lt. Edgar Foz Mem. NHS (San Marcos Campus) | DINGRAS | 2 | 1 | UPGRADING |  | 620103.87 |  | REVERTED | 0 | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 |  |  | UPGRADING | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 320810 | SUYO NATIONAL HIGH SCHOOL | DINGRAS | 2 | 1 | UPGRADING |  | 650906.33 |  | REVERTED | 0 | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 |  |  | UPGRADING | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 320811 | Marcos NHS (Agunit Campus) | MARCOS | 2 | 1 | UPGRADING |  | 650906.33 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 320812 | Marcos NHS (Santiago Campus) | MARCOS | 2 | 1 | UPGRADING |  | 650906.33 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 320820 | Adriano P. Arzadon NHS | NUEVA ERA | 2 | 1 | UPGRADING |  | 589301.41 |  | REVERTED | 0 | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 |  |  | UPGRADING | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 500594 | Uguis Integrated School | NUEVA ERA | 2 | 1 | UPGRADING |  | 681708.79 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 500345 | Malaguip Integrated School | PAOAY | 2 | 1 | UPGRADING |  | 866523.57 |  | REVERTED | 0 | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 |  |  | UPGRADING | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 300025 | Paoay Lake NHS | PAOAY | 2 | 1 | UPGRADING |  | 620103.87 |  | REVERTED | 0 | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 |  |  | UPGRADING | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 300027 | Pinili NHS | PINILI | 2 | 1 | UPGRADING |  | 727912.49 |  | REVERTED | 0 | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 |  |  | UPGRADING | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 320815 | Bingao National High School | SAN NICOLAS | 2 | 1 | UPGRADING |  | 727912.49 |  | REVERTED | 0 | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 |  |  | UPGRADING | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 320817 | Bagbag Solsona National High School | SOLSONA | 2 | 1 | UPGRADING |  | 620103.87 |  | REVERTED | 0 | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 |  |  | UPGRADING | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 320818 | Talugtog Solsona National High School | SOLSONA | 2 | 1 | UPGRADING |  | 712511.26 |  | REVERTED | 0 | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 |  |  | UPGRADING | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Sur | 300043 | Cabugao NHS | CABUGAO | 1 | 1 | UPGRADING |  | 1365318.52 |  | COMPLETED | 1 | 2019-10-14 | 2019-10-15 |  |  | 2018-11-12 | 2018-11-19 | 2018-12-05 | 2018-12-13 | 2019-08-15 | MA TEJADA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Sur | 300057 | Magsingal NHS | MAGSINGAL | 1 | 1 | UPGRADING |  | 1402550.73 |  | COMPLETED | 1 | 2019-10-14 | 2019-10-15 |  |  | 2018-11-12 | 2018-11-19 | 2018-12-05 | 2018-12-13 | 2019-08-15 | MA TEJADA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Sur | 300058 | Manzante NHS | MAGSINGAL | 1 | 1 | UPGRADING |  | 1034183.81 |  | COMPLETED | 1 | 2019-10-20 | 2020-06-28 |  |  | 2018-11-12 | 2018-11-19 | 2018-12-05 | 2018-12-13 | 2019-08-22 | RAMSA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Sur | 300041 | Burgos National High School | BURGOS | 2 | 1 | UPGRADING |  | 1475986.51 |  | COMPLETED | 1 | 2019-10-20 |  |  |  | 2018-11-12 | 2018-11-19 | 2018-12-05 | 2018-12-13 | 2019-08-22 | RAMSA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Sur | 300046 | Cervantes NHS | CERVANTES | 2 | 1 | UPGRADING |  | 1306978.36 |  | COMPLETED | 1 | 2019-10-22 | 2020-01-17 |  |  | 2018-11-12 | 2018-11-19 | 2018-12-05 | 2018-12-13 | 2019-08-24 | WWW. CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Sur | 300072 | Teodoro Hernaez NHS | SANTA LUCIA | 2 | 1 | UPGRADING |  | 1405288.56 |  | COMPLETED | 1 | 2019-10-11 | 2020-01-23 |  |  | 2018-11-12 | 2018-11-19 | 2018-12-05 | 2018-12-13 | 2019-08-13 | ELKAN ENGINEERING SERVICES & GENERAL MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Sur | 300085 | Suyo NHS | SUYO | 2 | 1 | UPGRADING |  | 1399465.28 |  | COMPLETED | 1 | 2019-10-22 | 2020-01-17 |  |  | 2018-11-12 | 2018-11-19 | 2018-12-05 | 2018-12-13 | 2019-08-24 | WWW. CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Sur | 500349 | Ambalayat IS | TAGUDIN | 2 | 1 | UPGRADING |  | 916943.61 |  | COMPLETED | 1 | 2019-10-11 | 2020-01-23 |  |  | 2018-11-12 | 2018-11-19 | 2018-12-05 | 2018-12-13 | 2019-08-13 | ELKAN ENGINEERING SERVICES & GENERAL MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300095 | BACNOTAN NHS | BACNOTAN | 1 | 1 | UPGRADING |  | 1906451.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 500351 | Bitalag Integrated School | BACNOTAN | 1 | 1 | UPGRADING |  | 1544809.71 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300111 | PARAOIR NHS | BALAOAN | 1 | 1 | UPGRADING | Batch 3 | 1098395.68 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300114 | DOÑA FRANCISCA LACSAMANA DE ORTEGA MEMORIAL NATIONAL HIGH SCHOOL | BANGAR | 1 | 1 | UPGRADING |  | 1299958.28 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300132 | Regional Science HS, La Union | BANGAR | 1 | 1 | UPGRADING |  | 1012671.91 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300120 | LUNA NHS | LUNA | 1 | 1 | UPGRADING |  | 1370937.01 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300135 | San Gabriel Vocational High School | SAN GABRIEL | 1 | 1 | UPGRADING |  | 1885466.97 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 340825 | SHS within San Gabriel CS | SAN GABRIEL | 1 | 1 | UPGRADING |  | 850444.61 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300148 | Sudipen Voc'l Sch. | SUDIPEN | 1 | 1 | UPGRADING | Batch 3 | 1026903.38 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300139 | Dr. Manuel T. Cases Sr. National High School | AGOO | 2 | 1 | UPGRADING | Batch 3 | 1005801.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300129 | Pres. Elpidio. Quirino NHS | AGOO | 2 | 1 | UPGRADING |  | 1116662.58 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300094 | BACCUIT NHS | BAUANG | 2 | 1 | UPGRADING |  | 958860.54 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300104 | CABA NHS | CABA | 2 | 1 | UPGRADING | Batch 3 | 1083702.68 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300122 | Naguilian National HS | NAGUILIAN | 2 | 1 | UPGRADING |  | 1175756.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300131 | PUGO CENTRAL NHS | PUGO | 2 | 1 | UPGRADING | Batch 3 | 1047910.2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300110 | ALIPANG NHS | ROSARIO | 2 | 1 | UPGRADING | Batch 3 | 755316.08 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 500002 | Rosario Integrated School | ROSARIO | 2 | 1 | UPGRADING |  | 1993175.59 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300109 | DAMORTIS NHS | SANTO TOMAS | 2 | 1 | UPGRADING | Batch 3 | 1344792.22 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 321010 | Sto. Tomas NHS | SANTO TOMAS | 2 | 1 | UPGRADING | Batch 3 | 1074660.52 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Laoag City | 500056 | Balatong Integrated School | LAOAG CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1733471.06 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Laoag City | 305601 | Caaoacan High School | LAOAG CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1293828.99 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Laoag City | 300373 | Ilocos Norte College of Arts & Trades | LAOAG CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 2941485.57 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Laoag City | 300375 | Ilocos Norte Regional School of Fisheries | LAOAG CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 2662684.25 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 300161 | Balingasay NHS | BOLINAO | 1 | 1 | UPGRADING | Batch 2 | 1167558.13 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 500607 | Bacnit Integrated School | MABINI | 1 | 1 | UPGRADING | Batch 2 | 1212450.07 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 300180 | Cabanaetan NHS | MABINI | 1 | 1 | UPGRADING | Batch 2 | 1184953.07 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 500605 | Aguilar Integrated School | AGUILAR | 2 | 1 | UPGRADING | Batch 2 | 1591348.45 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 300170 | BAYOYONG NHS | BASISTA | 2 | 1 | UPGRADING | Batch 2 | 1305064.18 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 500610 | BUGALLON INTEGRATED SCHOOL | BUGALLON | 2 | 1 | UPGRADING | Batch 2 | 1424138.59 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 300241 | POLONG NATIONAL HIGH SCHOOL | BUGALLON | 2 | 1 | UPGRADING | Batch 2 | 1409579.72 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 300209 | Labrador NHS | LABRADOR | 2 | 1 | UPGRADING | Batch 2 | 1403799.49 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 500367 | Domalandan Center IS | LINGAYEN (Capital) | 2 | 1 | UPGRADING | Batch 2 | 1364601.38 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 300203 | Estanza NHS | LINGAYEN (Capital) | 2 | 1 | UPGRADING | Batch 2 | 1364601.38 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 300181 | Cabayaoasan NHS | MANGATAREM | 2 | 1 | UPGRADING | Batch 2 | 1424138.59 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 300218 | Macarang National High School | MANGATAREM | 2 | 1 | UPGRADING | Batch 2 | 1364601.38 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 300247 | Real National High School | URBIZTONDO | 2 | 1 | UPGRADING | Batch 2 | 1432831.08 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 300193 | Daniel Maramba NHS | SANTA BARBARA | 3 | 1 | UPGRADING | Batch 2 | 1350042.51 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 300225 | Maticmatic NHS | SANTA BARBARA | 3 | 1 | UPGRADING | Batch 2 | 1305064.18 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan II, Binalonan | 300276 | Arboleda NHS | ALCALA | 5 | 1 | UPGRADING | Batch 3 | 1370898.6 | 1358579.39 | COMPLETED | 1 | 2020-02-02 | 1/30/2020 |  |  | 9/23/2019 | 9/30/2019 | 10/14/2020 | 10/30/2019 | 2019-05-11 | ILS POWER ENGINEERING SERVICES & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan II, Binalonan | 300288 | Bersamin Agro-Industrial HS | ALCALA | 5 | 1 | UPGRADING | Batch 3 | 1149498.32 | 1141250.33 | COMPLETED | 1 | 2020-02-02 | 1/30/2020 |  |  | 9/23/2019 | 9/30/2019 | 10/14/2020 | 10/30/2019 | 2019-05-11 | ILS POWER ENGINEERING SERVICES & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan II, Binalonan | 300335 | Pindangan National High School -Alcala | ALCALA | 5 | 1 | UPGRADING | Batch 3 | 1220551.4 | 1078561.27 | COMPLETED | 1 | 2020-02-02 | 1/30/2020 |  |  | 9/23/2019 | 9/30/2019 | 10/14/2020 | 10/30/2019 | 2019-05-11 | ILS POWER ENGINEERING SERVICES & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan II, Binalonan | 300286 | Bautista National High School | BAUTISTA | 5 | 1 | UPGRADING | Batch 3 | 1662857.3 | 1649849.92 | COMPLETED | 1 | 2020-02-02 | 1/30/2020 |  |  | 9/23/2019 | 9/30/2019 | 10/14/2020 | 10/30/2019 | 2019-05-11 | ILS POWER ENGINEERING SERVICES & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan II, Binalonan | 300319 | Laoac NHS | LAOAC | 5 | 1 | UPGRADING | Batch 3 | 1643624.88 | 1623000.07 | COMPLETED | 1 | 2020-02-02 | 1/20/2020 |  |  | 9/23/2019 | 9/30/2019 | 10/14/2020 | 10/30/2019 | 2019-05-11 | ILS POWER ENGINEERING SERVICES & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan II, Binalonan | 300306 | Don Benito Agro-Industrial High School | POZORRUBIO | 5 | 1 | UPGRADING | Batch 3 | 864595.59 | 843721.68 | COMPLETED | 1 | 2020-02-02 | 1/20/2020 |  |  | 9/23/2019 | 9/30/2019 | 10/14/2020 | 10/30/2019 | 2019-05-11 | WWW CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan II, Binalonan | 300332 | Palguyod NHS | POZORRUBIO | 5 | 1 | UPGRADING | Batch 3 | 851898.63 | 739738.11 | COMPLETED | 1 | 2020-02-02 | 1/20/2020 |  |  | 9/23/2019 | 9/30/2019 | 10/14/2020 | 10/30/2019 | 2019-05-11 | ILS POWER ENGINEERING SERVICES & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan II, Binalonan | 300270 | Amagbagan Integrated School | SISON | 5 | 1 | UPGRADING | Batch 3 | 1101410.69 | 1093593.44 | COMPLETED | 1 | 2020-02-02 | 1/20/2020 |  |  | 9/23/2019 | 9/30/2019 | 10/14/2020 | 10/30/2019 | 2019-05-11 | ILS POWER ENGINEERING SERVICES & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan II, Binalonan | 300278 | Artacho NHS | SISON | 5 | 1 | UPGRADING | Batch 3 | 927791.35 | 871721.68 | COMPLETED | 1 | 2020-02-02 | 1/20/2020 |  |  | 9/23/2019 | 9/30/2019 | 10/14/2020 | 10/30/2019 | 2019-05-11 | WWW CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | San Fernando City | 300116 | Dr. Quintin Balcita Sr. NHS | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 807410.7 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | San Fernando City | 300118 | La Union NHS | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 968218.13 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | San Fernando City | 321001 | La Union NHS - Sacyud Annex | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 680650.87 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | San Fernando City | 500530 | Nagyubuyuban IS | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 973082.8 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | San Fernando City | 500480 | Pagudpud IS | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 1251836.69 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | San Fernando City | 300126 | Pao National High School | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 674265.26 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | San Fernando City | 101032 | Parparya ES | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 878446.56 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | San Fernando City | 101033 | Puspus ES | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 880015.55 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | San Fernando City | 500481 | SIBUAN-OTONG INTEGRATED SCHOOL | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 1021285.87 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Urdaneta City | 300405 | Lananpin NHS | CITY OF URDANETA | 5 | 1 | UPGRADING |  | 1289747.82 |  | COMPLETED | 1 | December 26,2019 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Urdaneta City | 300403 | Mariano Q. Umipig NHS | CITY OF URDANETA | 5 | 1 | UPGRADING |  | 1160998.01 |  | COMPLETED | 1 | December 26, 2019 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Vigan City | 300088 | Vigan National High School East | CITY OF VIGAN (Capital) | 1 | 1 | UPGRADING | Batch 1 | 1991860.37 | 1973058.97 | COMPLETED | 1 | November 19, 2019 |  | 2019-003-001 | INFRA-2019-004 | November 5, 2019 | November 12, 2019 | November 26, 2019 |  |  | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region I | Vigan City | 300089 | Vigan West NHS (Vigan NHS West) | CITY OF VIGAN (Capital) | 1 | 1 | UPGRADING | Batch 1 | 1105485.98 | 1051695.11 | COMPLETED | 1 | November 19, 2019 |  | 2019-003-001 | INFRA-2019-004 | November 5, 2019 | November 12, 2019 | November 26, 2019 |  |  | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Alaminos City | 101166 | Alaminos City Central School | CITY OF ALAMINOS | 1 | 1 | UPGRADING |  | 2373427.65 | 2369840.85 | COMPLETED | 1 | AUG. 7, 2021 | 2021-06-23 | Elec2020-RI-Alaminos City-001 |  | APRIL 14-20, 2021 | 2021-04-19 | 2021-04-21 | 2021-04-27 | 2021-05-10 | MANIMELDS CONSTRUCTION & IRON WORKS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Alaminos City | 101178 | Dulacac ES | CITY OF ALAMINOS | 1 | 1 | UPGRADING |  | 1717802.92 | 1668486.7 | COMPLETED | 1 | DEC.26,2020 | DEC. 15, 2020 | Elec2020-RI-Alaminos City-005 |  | nov. 22-29, 2019 | nov. 28, 2019 | dec. 13, 2019 | jan. 20, 2020 | 2020-09-28 | MANIMELDS CONSTRUCTION & IRON WORKS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Alaminos City | 322701 | Ildefonso Quimson Community HS | CITY OF ALAMINOS | 1 | 1 | UPGRADING |  | 2362809.82 | 2220937.34 | COMPLETED | 1 | DEC.28,2020 |  | Elec2020-RI-Alaminos City-006 |  | nov. 22-29, 2019 | nov. 28, 2019 | dec. 13, 2019 | jan. 20, 2020 | 2020-09-28 | ILS POWER ENGINEERING SERVICE & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Alaminos City | 101181 | Lucap ES | CITY OF ALAMINOS | 1 | 1 | UPGRADING |  | 2880676.56 | 2815050.02 | COMPLETED | 1 | DEC.26,2020 | DEC. 15, 2020 | Elec2020-RI-Alaminos City-012 |  | nov. 22-29, 2019 | nov. 28, 2019 | dec. 13, 2019 | jan. 20, 2020 | 2020-09-28 | MANIMELDS CONSTRUCTION & IRON WORKS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Alaminos City | 500564 | Pangapisan IS | CITY OF ALAMINOS | 1 | 1 | UPGRADING |  | 2874221.77 | 2830911.74 | COMPLETED | 1 | DEC.26,2020 | DEC. 15, 2020 | Elec2020-RI-Alaminos City-008 |  | nov. 22-29, 2019 | nov. 28, 2019 | dec. 13, 2019 | jan. 20, 2020 | 2020-09-30 | MANIMELDS CONSTRUCTION & IRON WORKS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Alaminos City | 300260 | Telbang NHS | CITY OF ALAMINOS | 1 | 1 | UPGRADING |  | 1853337.22 | 1757869.11 | COMPLETED | 1 | DEC.28,2020 |  | Elec2020-RI-Alaminos City-011 |  | nov. 22-29, 2019 | nov. 28, 2019 | dec. 13, 2019 | jan. 20, 2020 | 2020-09-30 | ILS POWER ENGINEERING SERVICE & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Batac City | 320803 | City of Batac National high school Payao | CITY OF BATAC | 2 | 1 |  |  | 1608316.11 |  | COMPLETED | 1 |  |  | Elec2020-RI-Batac City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Batac City | 320804 | City of Batac NHS Poblacion | CITY OF BATAC | 2 | 1 |  |  | 2288538.2 |  | COMPLETED | 1 |  |  | Elec2020-RI-Batac City-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Batac City | 340747 | Gen. Artemio Ricarte SHS | CITY OF BATAC | 2 | 1 |  |  | 1071054.4 |  | COMPLETED | 1 |  |  | Elec2020-RI-Batac City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Candon City | 100433 | Calaoa-an Elementary School | CITY OF CANDON | 2 | 1 | UPGRADING |  | 709938.7 | 693017.52 | COMPLETED | 1 |  |  | Elec2020-RI-Candon City-008 | [5 empty] | 2020-10-02 | ELKAN ENG'G SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Candon City | 100434 | Calongbuyan Elementary School | CITY OF CANDON | 2 | 1 | UPGRADING |  | 872816.04 |  | COMPLETED | 1 |  |  | Elec2020-RI-Candon City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Candon City | 100436 | Candon South Central School | CITY OF CANDON | 2 | 1 | UPGRADING |  | 1370324.42 |  | COMPLETED | 1 |  |  | Elec2020-RI-Candon City-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Candon City | 100437 | Caterman Elementary Annnex | CITY OF CANDON | 2 | 1 | UPGRADING |  | 767711.01 |  | COMPLETED | 1 |  |  | Elec2020-RI-Candon City-009 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Candon City | 100445 | Patpata Elementary School | CITY OF CANDON | 2 | 1 | UPGRADING |  | 1006019.04 |  | COMPLETED | 1 |  |  | Elec2020-RI-Candon City-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Dagupan City | 300367 | Bonuan Buquig NHS | DAGUPAN CITY | 4 | 1 | UPGRADING |  | 587052.26 |  | COMPLETED | 1 | April 6, 2021 |  | Elec2020-RI-Dagupan City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Dagupan City | 300369 | Carael National HS | DAGUPAN CITY | 4 | 1 | UPGRADING |  | 622206.26 |  | COMPLETED | 1 | April 6, 2021 |  | Elec2020-RI-Dagupan City-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Dagupan City | 300371 | Judge Jose de Venecia, Sr. Technical-Vocational Secondary School | DAGUPAN CITY | 4 | 1 | UPGRADING |  | 578295.4 |  | COMPLETED | 1 | April 6, 2021 |  | Elec2020-RI-Dagupan City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Norte | 320802 | LANAO NATIONAL HIGH SCHOOL | BANGUI | 1 | 1 | UPGRADING |  | 1003799.34 | 998014.28 | COMPLETED | 1 |  |  | Elec2020-RI-Ilocos Norte-018 |  |  |  | 2021-04-05 |  |  | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Norte | 300014 | Davila National High School | PASUQUIN | 1 | 1 | UPGRADING |  | 1507479.95 | 1505285.32 | COMPLETED | 1 |  |  | Elec2020-RI-Ilocos Norte-006 |  |  |  | 2021-04-05 |  |  | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Norte | 300016 | Piddig National High School | PIDDIG | 1 | 1 | UPGRADING |  | 2630637.25 | 2623501.81 | COMPLETED | 1 |  |  | Elec2020-RI-Ilocos Norte-014 |  |  |  | 2021-04-05 |  |  | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Norte | 500591 | Florentino Camaquin Integrated School | VINTAR | 1 | 1 | UPGRADING |  | 3220991.48 | 3204753.86 | COMPLETED | 1 |  |  | Elec2020-RI-Ilocos Norte-009 |  |  |  | 2021-04-05 |  |  | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Norte | 500343 | Pallas IS | VINTAR | 1 | 1 | UPGRADING |  | 2255397.9 | 2234380.79 | COMPLETED | 1 |  |  | Elec2020-RI-Ilocos Norte-012 |  |  |  | 2021-04-05 |  |  | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Norte | 300010 | Caribquib NHS | BANNA (ESPIRITU) | 2 | 1 | UPGRADING |  | 1251461.73 | 1243660.7 | COMPLETED | 1 |  |  | Elec2020-RI-Ilocos Norte-005 |  | 2019-11-11 | 11/21/2019 | 2019-03-12 | 01/13/2020 | 2020-08-10 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Norte | 300015 | Dingras NHS/Lt. Edgar Foz Mem. NHS | DINGRAS | 2 | 1 | UPGRADING |  | 1752386.54 | 1742020.97 | COMPLETED | 1 |  |  | Elec2020-RI-Ilocos Norte-007 |  | 2019-11-11 | 11/21/2019 | 2019-03-12 | 01/13/2020 | 2020-08-10 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Sur | 300056 | Lussoc National High School | SANTO DOMINGO | 1 | 1 | UPGRADING |  | 1370276.32 | 1214762.12 | COMPLETED | 1 | 2020-12-21 |  | Elec2020-RI-Ilocos Sur-002 |  | 2020-01-20 | 2020-01-27 | 2020-02-07 | 2020-07-13 | 2020-09-23 | JUA Electrical Services & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Sur | 500595 | BINACUD INTEGRATED SCHOOL | SINAIT | 1 | 1 | UPGRADING |  | 885237.08 | 801750.54 | COMPLETED | 1 | 2020-12-21 |  | Elec2020-RI-Ilocos Sur-009 |  | 2020-01-20 | 2020-01-27 | 2020-02-07 | 2020-07-13 | 2020-09-23 | JUA Electrical Services & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Sur | 100653 | SINAIT WEST CS | SINAIT | 1 | 1 | UPGRADING |  | 1070193.08 | 968510.5 | COMPLETED | 1 | 2020-12-21 |  | Elec2020-RI-Ilocos Sur-004 |  | 2020-01-20 | 2020-01-27 | 2020-02-07 | 2020-07-13 | 2020-09-23 | JUA Electrical Services & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Sur | 300033 | Alilem NHS (Alilem Daya HS) | ALILEM | 2 | 1 | UPGRADING |  | 1733147.33 |  | COMPLETED | 1 |  |  | Elec2020-RI-Ilocos Sur-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Sur | 300059 | Nagbukel NHS | NAGBUKEL | 2 | 1 | UPGRADING |  | 1075430.82 | 962407.34 | COMPLETED | 1 | 2020-12-21 |  | Elec2020-RI-Ilocos Sur-015 |  | 2020-01-20 | 2020-01-27 | 2020-02-07 | 2020-07-13 | 2020-09-23 | JUA Electrical Services & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Sur | 500596 | Lungog Integrated School | NARVACAN | 2 | 1 | UPGRADING |  | 1114866.18 | 1024071.12 | COMPLETED | 1 | 2020-12-21 |  | Elec2020-RI-Ilocos Sur-011 |  | 2020-01-20 | 2020-01-27 | 2020-02-07 | 2020-07-13 | 2020-09-23 | JUA Electrical Services & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Sur | 300075 | San Esteban NHS | SAN ESTEBAN | 2 | 1 | UPGRADING |  | 1466231.35 | 1358951.5 | COMPLETED | 1 | 2020-12-21 |  | Elec2020-RI-Ilocos Sur-012 |  | 2020-01-20 | 2020-01-27 | 2020-02-07 | 2020-07-13 | 2020-09-23 | JUA Electrical Services & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Sur | 300078 | Santiago NHS | SANTIAGO | 2 | 1 | UPGRADING |  | 1176447.5 | 1072233.01 | COMPLETED | 1 | 2020-12-21 |  | Elec2020-RI-Ilocos Sur-013 |  | 2020-01-20 | 2020-01-27 | 2020-02-07 | 2020-07-13 | 2020-09-23 | JUA Electrical Services & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 300143 | SINAPANGAN NATIONAL HIGH SCHOOL | BALAOAN | 1 | 1 |  |  | 1017979.19 |  | COMPLETED | 1 |  |  | Elec2020-RI-La Union-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 500354 | Bungro Sococ IS | LUNA | 1 | 1 |  |  | 1030250.42 |  | COMPLETED | 1 |  |  | Elec2020-RI-La Union-026 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 300146 | Sto. Rosario National High School | SAN JUAN | 1 | 1 |  |  | 1027428.11 |  | COMPLETED | 1 |  |  | Elec2020-RI-La Union-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 300140 | Santol Voc'l. HS | SANTOL | 1 | 1 |  |  | 1027428.11 |  | COMPLETED | 1 |  |  | Elec2020-RI-La Union-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 300141 | Santol Voc'l. HS - Liguay Annex | SANTOL | 1 | 1 |  |  | 1004521.35 |  | COMPLETED | 1 |  |  | Elec2020-RI-La Union-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 300125 | Old Sudipen NHS | SUDIPEN | 1 | 1 |  |  | 1027428.11 |  | COMPLETED | 1 |  |  | Elec2020-RI-La Union-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 300134 | San Francisco NHS | SUDIPEN | 1 | 1 |  |  | 1037406.9 |  | COMPLETED | 1 |  |  | Elec2020-RI-La Union-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 300130 | Don Eufemio F. Eriguel MNHS | AGOO | 2 | 1 |  |  | 1037406.9 |  | COMPLETED | 1 |  |  | Elec2020-RI-La Union-010 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 500563 | San Julian IS | AGOO | 2 | 1 |  |  | 1059422.31 |  | COMPLETED | 1 |  |  | Elec2020-RI-La Union-011 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 300149 | Suyo NHS | BAGULIN | 2 | 1 |  |  | 935015.42 |  | COMPLETED | 1 |  |  | Elec2020-RI-La Union-038 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 300102 | Burgos National High School | BURGOS | 2 | 1 |  |  | 1002880.86 |  | COMPLETED | 1 |  |  | Elec2020-RI-La Union-019 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 500361 | Cabaruan IS | SANTO TOMAS | 2 | 1 |  |  | 940338.94 |  | COMPLETED | 1 |  |  | Elec2020-RI-La Union-040 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Laoag City | 102209 | Gabaldon Elementary School | LAOAG CITY (Capital) | 1 | 1 |  |  | 1689350.51 |  | COMPLETED | 1 |  |  | Elec2020-RI-Laoag City-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Laoag City | 300372 | Gabu NHS | LAOAG CITY (Capital) | 1 | 1 | UPGRADING |  | 1647339.36 | 1457191.76 | COMPLETED | 1 | 2021-08-01 |  | Elec2020-RI-Laoag City-001 | [6 empty] | Elocin Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Laoag City | 500742 | San Mateo Integrated School | LAOAG CITY (Capital) | 1 | 1 | UPGRADING |  | 995334.64 | 898971.44 | COMPLETED | 1 | 2021-08-01 |  | Elec2020-RI-Laoag City-003 | [6 empty] | Elocin Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan I, Lingayen | 300250 | SAN JOSE NHS | ANDA | 1 | 1 |  |  | 848388.02 |  | COMPLETED | 1 |  |  | Elec2020-RI-Pangasinan I-017 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan I, Lingayen | 500370 | BOLINAO IS | BOLINAO | 1 | 1 |  |  | 3019424.51 |  | COMPLETED | 1 |  |  | Elec2020-RI-Pangasinan I-019 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan I, Lingayen | 300167 | Basista NHS | BASISTA | 2 | 1 |  |  | 507212.72 |  | COMPLETED | 1 |  |  | Elec2020-RI-Pangasinan I-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan I, Lingayen | 500368 | Urbiztondo IS | URBIZTONDO | 2 | 1 |  |  | 2185427.09 |  | COMPLETED | 1 |  |  | Elec2020-RI-Pangasinan I-009 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan I, Lingayen | 300171 | Beleng NHS | BAYAMBANG | 3 | 1 |  |  | 834713.32 |  | COMPLETED | 1 |  |  | Elec2020-RI-Pangasinan I-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan I, Lingayen | 300178 | Buenlag NHS | CALASIAO | 3 | 1 |  |  | 1262019.34 |  | COMPLETED | 1 |  |  | Elec2020-RI-Pangasinan I-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan I, Lingayen | 300198 | Doyong-Malabago NHS | CALASIAO | 3 | 1 |  |  | 1231259.59 |  | COMPLETED | 1 |  |  | Elec2020-RI-Pangasinan I-013 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan I, Lingayen | 300176 | BOTAO NHS | STA. BARBARA | 3 | 1 |  |  | 437584.21 |  | COMPLETED | 1 |  |  | Elec2020-RI-Pangasinan I-018 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan II, Binalonan | 300301 | Cipriano P. Primicias NHS | ALCALA | 5 | 1 | UPGRADING |  | 1840504.84 | 1763912.4 | COMPLETED | 1 | APRIL, 2021 |  | Elec2020-RI-Pangasinan II-002 |  | SEPTEMBER 10, 2019 | SEPTEMBER 17, 2019 | OCTOBER 1, 2019 | SEPTEMBER 24, 2019 | SEPTEMBER 28, 2019 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan II, Binalonan | 300302 | Coloscaoayan NHS | BAUTISTA | 5 | 1 | UPGRADING |  | 1136466.71 | 1131139.91 | COMPLETED | 1 | APRIL, 2021 |  | Elec2020-RI-Pangasinan II-003 |  | SEPTEMBER 10, 2019 | SEPTEMBER 17, 2019 | OCTOBER 1, 2019 | SEPTEMBER 24, 2019 | SEPTEMBER 28, 2019 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan II, Binalonan | 300275 | Antonio P. Villar National High School | SANTO TOMAS | 5 | 1 | UPGRADING |  | 1840504.84 | 1834900.42 | COMPLETED | 1 | APRIL, 2021 |  | Elec2020-RI-Pangasinan II-001 |  | SEPTEMBER 10, 2019 | SEPTEMBER 17, 2019 | OCTOBER 1, 2019 | SEPTEMBER 24, 2019 | SEPTEMBER 28, 2019 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan II, Binalonan | 500377 | Bantay Insik Integrated School | SISON | 5 | 1 | UPGRADING |  | 1230907.65 | 1225195.32 | COMPLETED | 1 | APRIL, 2021 |  | Elec2020-RI-Pangasinan II-012 |  | SEPTEMBER 10, 2019 | SEPTEMBER 17, 2019 | OCTOBER 1, 2019 | SEPTEMBER 24, 2019 | SEPTEMBER 28, 2019 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan II, Binalonan | 300366 | Unzad NHS | VILLASIS | 5 | 1 | UPGRADING |  | 1181071.98 | 1049662.54 | COMPLETED | 1 | APRIL, 2021 |  | Elec2020-RI-Pangasinan II-017 |  | SEPTEMBER 10, 2019 | SEPTEMBER 17, 2019 | OCTOBER 1, 2019 | DECEMBER 2, 2020 | DECEMBER 7, 2020 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan II, Binalonan | 101721 | Asingan North CS | ASINGAN | 6 | 1 | UPGRADING |  | 1376176.68 | 1376176.68 | COMPLETED | 1 | APRIL, 2021 |  | Elec2020-RI-Pangasinan II-005 |  | SEPTEMBER 10, 2019 | SEPTEMBER 17, 2019 | OCTOBER 1, 2019 | DECEMBER 2, 2020 | DECEMBER 7, 2020 | INTERLINK POWER CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan II, Binalonan | 300314 | Guiling-Coliling NHS | ROSALES | 6 | 1 | UPGRADING |  | 1145326.09 | 1017086.71 | COMPLETED | 1 | APRIL, 2021 |  | Elec2020-RI-Pangasinan II-004 |  | SEPTEMBER 10, 2019 | SEPTEMBER 17, 2019 | OCTOBER 1, 2019 | DECEMBER 2, 2020 | DECEMBER 7, 2020 | INTERLINK POWER CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan II, Binalonan | 300293 | Cabalitian NHS | UMINGAN | 6 | 1 | UPGRADING |  | 871363.59 | 775221.1 | COMPLETED | 1 | APRIL, 2021 |  | Elec2020-RI-Pangasinan II-006 |  | SEPTEMBER 10, 2019 | SEPTEMBER 17, 2019 | OCTOBER 1, 2019 | DECEMBER 2, 2020 | DECEMBER 7, 2020 | INTERLINK POWER CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan II, Binalonan | 300365 | Umingan Central National High School | UMINGAN | 6 | 1 | UPGRADING |  | 3246650.99 |  | COMPLETED | 1 | APRIL, 2021 |  | Elec2020-RI-Pangasinan II-016 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | San Carlos City | 300376 | Abanon NHS | SAN CARLOS CITY | 3 | 1 |  |  | 824544.53 |  | COMPLETED | 1 |  |  | Elec2020-RI-San Carlos City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | San Carlos City | 500058 | Guelew Integrated School | SAN CARLOS CITY | 3 | 1 |  |  | 1226569.27 |  | COMPLETED | 1 |  |  | Elec2020-RI-San Carlos City-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | San Fernando City | 101037 | BUNGRO ELEMENTARY SCHOOL | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 977888.78 | 938549.36 | COMPLETED | 1 | 2020-12-08 | 2020-11-23 | Elec2020-RI-San Fernando-007 | CSFLU-INFRA-002-2020 | 2019-11-19 | 2019-11-26 | 2019-12-09 | 2019-12-16 | 2020-09-09 | AE SQUARE ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | San Fernando City | 101023 | Cadaclan ES | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 1255161.23 | 1179071.69 | COMPLETED | 1 | 2020-12-08 | 2020-11-23 | Elec2020-RI-San Fernando-006 | CSFLU-INFRA-001-2020 | 2019-11-19 | 2019-11-26 | 2019-12-09 | 2019-12-16 | 2020-09-09 | AE SQUARE ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | San Fernando City | 101040 | Masicong ES | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 1471804.45 | 1304865.03 | COMPLETED | 1 | 2020-12-08 | 2020-10-30 | Elec2020-RI-San Fernando-002 | CSFLU-INFRA-003-2020 | 2019-11-19 | 2019-11-26 | 2019-12-09 | 2019-12-16 | 2020-09-09 | RHOB CONSTRUCTION & ENGINEERING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | San Fernando City | 101031 | Pao ES | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 1240642.07 | 1238781.1 | COMPLETED | 1 | 2021-03-29 | 2021-03-11 | Elec2020-RI-San Fernando-003 | CSFLU-INFRA-003-2020 | 2020-12-01 | 2020-12-07 | 2020-12-21 | 2020-12-23 | 2020-12-29 | JC ELECTROFIELDS POWER SYSTEMS, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | San Fernando City | 101042 | Sacyud E/S | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 1024641.48 | 1023583.28 | COMPLETED | 1 | 2020-12-08 | 2020-11-23 | Elec2020-RI-San Fernando-001 | CSFLU-INFRA-004-2020 | 2019-11-19 | 2019-11-26 | 2019-12-09 | 2019-12-16 | 2020-09-09 | AE SQUARE ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Urdaneta City | 102269 | Badipa ES | CITY OF URDANETA | 5 | 1 |  |  | 906936.71 |  | COMPLETED | 1 | April 16, 2021 |  | Elec2020-RI-Urdaneta City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Urdaneta City | 300394 | Badipa NHS | CITY OF URDANETA | 5 | 1 |  |  | 874157.03 |  | COMPLETED | 1 |  |  | Elec2020-RI-Urdaneta City-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Urdaneta City | 300398 | Camantiles NHS | CITY OF URDANETA | 5 | 1 |  |  | 1273032.67 |  | COMPLETED | 1 | April 16, 2021 |  | Elec2020-RI-Urdaneta City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Vigan City | 100783 | Ayusan-Paoa Elementary School | CITY OF VIGAN (Capital) | 1 | 1 | UPGRADING |  | 1062858.04 | 1040441.5 | COMPLETED | 1 |  |  | Elec2020-RI-Vigan City-001 | INFR-202-001 | 2021-03-23 | 2021-03-31 | 2021-04-13 | 2021-04-15 | 2021-04-28 | ELKAN ENGINEERING SERVICES & GENERAL MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Vigan City | 100784 | Bulala-Paratong Elementary School | CITY OF VIGAN (Capital) | 1 | 1 | UPGRADING |  | 910539.26 |  | COMPLETED | 1 |  |  | Elec2020-RI-Vigan City-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region I | Vigan City | 100793 | Nagsangalan ES | CITY OF VIGAN (Capital) | 1 | 1 | UPGRADING |  | 977580.91 |  | COMPLETED | 1 |  |  | Elec2020-RI-Vigan City-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region I | Ilocos Sur | 300036 | Sugpon NHS | SUGPON | 2nd | 1 | Solar PV System (Off-grid or On-grid) | 1 | 3187890.68 | 3124132.87 | COMPLETED | 1 | 2023-12-03 | 2024-04-24 | 2023-07-005-PB-Works |  | 2023-07-25 | 2023-08-01 | 2023-08-14 | 2023-08-25 | 2023-09-04 | WWW.Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 4.24 | SOLAR | COMPLETED
ELECTRIFICATION 2024 | Region I | Alaminos City | 300240 | Polo National High School | CITY OF ALAMINOS | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3000000 | 2987931.48 | COMPLETED | 1 | 2025-04-21 | 2025-04-15 | PB-infra- 2024-12 |  | 2024-07-08 | 2024-07-17 | 2024-07-29 | 2024-08-06 | 2024-12-23 | MANIMELDS CONSTRUCTION & IRON WORKS | for punchlisting | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.9 | 0.1 |  | 5.25 | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region I | Pangasinan I, Lingayen | 300250 | San Jose NHS (Anda) | ANDA | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3000000 | 2814072.69 | COMPLETED | 1 |  |  | 2024-06-002-INFRA |  | 2024-06-27 | 2024-07-05 | 2024-07-17 | 2024-08-15 |  | 3CA Builders Corporation | 180 CD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 1.25 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2024 | Region I | Pangasinan I, Lingayen | 500366 | Tampac IS | AGUILAR | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1500000 | 1490191.68 | ONGOING | 0.95 |  |  | 2024-06-002-INFRA |  | 2024-06-27 | 2024-07-05 | 2024-07-17 | 2024-08-15 |  | Caixia Construction | With SARO, Waiting for NTP | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.95 | 0 |  |  | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region I | Pangasinan I, Lingayen | 101422 | Calasiao Central School | CALASIAO | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1500000 | 1490287.22 | ONGOING | 0.9 |  |  | 2024-06-002-INFRA |  | 2024-06-27 | 2024-07-05 | 2024-07-17 |  |  | ILS Power Engineering Services and Supply |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.8 | 0.1 |  |  | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region I | San Fernando City | 101021 | Bangbangolan ES | CITY OF SAN FERNANDO (Capital) | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1500000 | 1448491.14 | COMPLETED | 1 | 2024-10-18 | 2024-09-20 | CSFLU-INFRA-03-01-2024 | CSFLU-INFRA-03-01-2024 | 2024-04-11 | 2024-04-19 | 2024-05-02 | 2024-05-08 | 2024-06-13 | AE Square Enterprises | With approved modification of school recipient from Apolonia es to Paso De Blas es and Constantino es | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | ENERGIZATION | COMPLETED