## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | TOTAL NO. OF BUILDINGS | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of bldg Reverted | No. of bldg Not yet started | No. of bldg Under Procurement | No. of bldg On Going | No. of bldg Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | Implementing Unit | BBM TERM COMPLETED | AWAITING SUBMISSION OF RTA | batch of suballotment | Unnamed: 45
GABALDON 2020 | Region I | Candon City | 100427 | Ayudante Elementary School | CITY OF CANDON | 2 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 1990377.99 | 1 |  | Completed | 1 | [10 empty] | DEFFERED PROCUREMENT | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region I | Ilocos Norte | 100202 | Gabaldon ES | PASUQUIN | 1 | 1 | 8 | 1 | Rehabilitation of Gabaldon Building | 10410704.18 | 1 | 10251139.45 | Completed | 1 | 2022-02-23 | 2021-12-09 | 2021-05-08 | 2021-06-21 | 2021-05-19 | 2021-05-27 | 2021-06-08 | 2021-06-18 | 2021-07-30 | Elocin Construction | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region I | Ilocos Sur | 100459 | Pandan ES | CAOAYAN | 1 | 1 | 12 | 1 | Rehabilitation of Gabaldon Building | 13610112.44 | 1 | 13563377.97 | Completed | 1 | 2021-04-15 | [7 empty] | 2020-09-17 | MA TEJADA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region I | Ilocos Sur | 100638 | Santiago South Central School | SANTIAGO | 2 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 3537854.71 | 1 | 3514079.29 | Completed | 1 | 2021-01-15 | [7 empty] | 2020-09-17 | MA TEJADA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region I | La Union | 100846 | Bacnotan Central School | BACNOTAN | 1 | 1 | 12 | 1 | Rehabilitation of Gabaldon Building | 17585093.32 | 1 | 17559001.02 | Completed | 1 | 2022-01-03 | 2021-12-20 | 2023-07-006-PB-Works | 2021-06-16 | 2021-05-19 | 2021-05-27 | 2021-06-08 | 2021-06-18 | 2021-07-07 | MANIMELDS IRON WORKS AND CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region I | La Union | 100801 | Agoo East CES | AGOO | 2 | 1 | 6 | 1 | Rehabilitation of Gabaldon Building | 8439581.13 | 1 | 8416617.77 | Completed | 1 | 2022-01-03 | 2021-12-10 | 2023-07-005-PB-Works | 2021-06-17 | 2021-05-19 | 2021-05-27 | 2021-06-08 | 2021-06-18 | 2021-07-07 | MANIMELDS IRON WORKS AND CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region I | Pangasinan II, Binalonan | 101703 | Pindangan West ES | ALCALA | 5 | 1 | 7 | 1 | Rehabilitation of Gabaldon Building | 8491938.58 | 1 | 8475978.91 | Completed | 1 | 2022-02-12 | 2021-12-14 | 2021-05-08 | 2021-06-18 | 2021-05-19 | 2021-05-27 | 2021-06-08 | 2021-06-18 | 2021-07-07 | MANIMELDS IRON WORKS AND CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region I | Pangasinan II, Binalonan | 101784 | Don Rufino Tabayoyong CS | LAOAC | 5 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 5038139.51 | 1 | 5011673.02 | Completed | 1 | 2022-01-05 | 2021-12-06 | 2021-05-08 | 2021-06-19 | 2021-05-19 | 2021-05-27 | 2021-06-08 | 2021-06-18 | 2021-07-07 | MANIMELDS IRON WORKS AND CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2021 | Region I | Laoag City | 300373 | Ilocos Norte College of Arts & Trades | LAOAG CITY (Capital) | 1 | 1 | 9 | 1 | Rehabilitation of Gabaldon Building | 3071403 | 1 | 2911465.28 | COMPLETED | 1 | 2021-10-30 | 2021-10-30 | 2021-05-09 | 2021-06-22 | 2021-05-19 | 2021-05-27 | 2021-06-08 | 2021-06-18 | 2021-07-30 | Elocin Construction | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Regional Office | CY 2022 |  |  | COMPLETED
GABALDON 2021 | Region I | Pangasinan II, Binalonan | 102126 | Villasis I Central School SPED Center | VILLASIS | 5 | 1 | 8 | 1 | Rehabilitation of Gabaldon Building | 10107429 | 1 | 10095606.34 | COMPLETED | 1 | 2022-01-06 | 2021-12-06 | 2021-05-09 | 2021-06-20 | 2021-05-19 | 2021-05-27 | 2021-06-08 | 2021-06-18 | 2021-07-07 | MANIMELDS IRON WORKS AND CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Regional Office | CY 2022 |  |  | COMPLETED
GABALDON 2023 | Region I | Ilocos Sur | 100525 | Narvacan North Central School | NARVACAN | 2 | 1 | 20 | 1 | Restoration & Conservation of Gabaldon Building | 10727623.23 | 1 | 8759254.25 | Completed | 1 | 1/31/2024 | 2024-10-04 | 2023-07-006-PB-Works |  | 7/25/2023 | 2023-01-08 | 8/14/2023 | 8/25/2023 | 2023-04-09 | MA Tejada Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 5.24 | Division Office | cy 2024 |  |  | Completed
GABALDON 2023 | Region I | La Union | 100801 | Agoo East CES | AGOO | 2 | 1 | 4 | 1 | Restoration & Conservation of Gabaldon Building | 2300000 | 1 | 2282755.65 | COMPLETED | 1 | 9/27/2023 | 9/22/2023 | 2023 GAB-RO1-01 |  | 5/27/2023 | 2023-05-06 | 6/19/2023 | 6/26/2023 | 6/29/2023 | MANIMELDS IRON WORKS AND CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 3.24 | Division Office | cy 2024 |  |  | COMPLETED
GABALDON 2024 | Region I | Pangasinan I, Lingayen | 101420 | Bued ES | CALASIAO | 3rd | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 10000000 | 1 |  | Under Procurement | 0 | [10 empty] | waiting for the approved plans for the restoration | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | Division Office |  | 1 | 0 | under procurement
GABALDON 2024 | Region I | San Carlos City | 300388 | Speaker Eugenio Perez National Agricultural School | SAN CARLOS CITY | 3rd | 1 | 17 | 1 | Conservation and Restoration of Gabaldon School Building | 19117181.04 | 1 |  | Under Procurement | 0 | [10 empty] | STIIL COMPLYING THE DOCUMENTS NEEDED BY NCCA. | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | Division Office |  | 1 | 0 | Under Procurement