## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | NO. OF CL | SCOPE OF WORK | PROJECT ALLOCATION | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated/ Abandoned | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of CL Terminated/ Abandoned | No. of Sites Reverted.1 | No. of Sites Not yet started.1 | No. of Sites Under Procurement.1 | No. of Sites On Going.1 | No. of Sites Completed.1 | No. of Sites Terminated/ Abandoned.1 | Previous % | Difference | Month Completed | OGP SCHOOLS with DCP Packages | TO BE COMPLETED BY 2023 | TO BE COMPLETED BY 2023.1 | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | BBM ADMINISTRATION | Batch | Municipality Class | Provision of Solar Panel
LMS 2021 | Region III | Aurora | 157509 | Dianao ES | DILASAG | 0 | 1 | 3 | CONSTRUCTION OF ONE(1) STOREY THREE(3) CLASSROOM SCHOOL BUILDING WITH (COMMON TOILET) WITH PROVISION OF PERIMETER FENCE, SCHOOL FURNITURE, SOLAR PANEL AND WATER SYSTEM | 17990219.996 |  | Ongoing | 0.46 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.46 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region III | Bataan | 104651 | Kanawan Integrated School | MORONG | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18332263.58 |  | Abandoned | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region III | Bataan | 500119 | Biaan Aeta IS | MARIVELES | 2 | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17423919.51 |  | Ongoing | 0.2 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.2 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region III | Bulacan | 158504 | Talamsi I ES (Talamsi PS) | DOÑA REMEDIOS TRINIDAD | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17999033.7429 |  | Abandoned | 0.3 | [9 empty] | WERR Corporation International JV Bancal Construction and Supply | based on the spot checking report made last November by LMS team (Audit); pls see narrative reports | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0.3 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region III | Nueva Ecija | 105274 | E. Abalos PS | CUYAPO | 1 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER) ANDSCHOOL FURNITURE | 4992620.94 |  | Abandoned | 0.4 | [9 empty] | WERR Corporation International JV Bancal Construction and Supply | based on the spot checking report made last November by LMS team (Audit); pls see narrative reports | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0.4 | 0 |  |  | 0 | 1 | [6 empty] | 0
LMS 2021 | Region III | Pampanga | 306913 | Camias High School | PORAC | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE | 5520405.3423 |  | Ongoing | 0.7 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.7 | 0 |  |  | 0 | 1 | [6 empty] | 0
LMS 2021 | Region III | Tarlac | 106672 | Macaguing Primary School | SANTA IGNACIA | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 8884909.37 |  | Abandoned | 0.5 | [9 empty] | WERR Corporation International JV Bancal Construction and Supply | based on the spot checking report made last November by LMS team (Audit); pls see narrative reports | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0.5 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region III | Zambales | 281504 | Belbel Elementary School | BOTOLAN | 2 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18534442.11 |  | Ongoing | 0.3 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.3 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2023 | Region III | Nueva Ecija | 105195 | Ariendo ES | BONGABON | 3 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER), PERIMETER FENCEA, SOLAR PV ENERGY SYSTEM AND SCHOOL FURNITURE | 17165672.76 | 16935358.6 | completed | 1 | 2023-12-06 | 2024-03-07 | DEPED-NE-INFRA-PB-01-2023 | INFRA-NE-01-2022 | 2023-06-19 | 2023-06-26 | 2023-07-10 | 2023-07-14 | 2023-08-08 | REBCOR CONST. AND TRADING CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region III | Tarlac | 106511 | Gayong-Gayong ES | MAYANTOC | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 11801006.92 |  | Completed | 1 |  | 2023-10-20 |  |  | 2023-05-03 | 2023-05-11 | 2023-05-24 | 2023-06-29 | 2023-07-05 | CAIXIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 10.24 | - | 1 | [5 empty] | 1 |  | 0
LMS 2024 | Region III | Bulacan | 158519 | Talamsi II ES | DOÑA REMEDIOS TRINIDAD | 1st | 1 | 2 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 18181818.18 | 17959590.65 | Completed | 1 | 2025-01-08 | 2024-12-20 | PB-24-005 | PB-24-05-011 | 2023-12-05 | 2023-12-14 | 2023-12-27 | 2024-01-08 | 2024-06-05 | EMICA BUILDERS AND SUPPLY | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.24 | [8 empty] | 1st | 1
LMS 2024 | Region III | Nueva Ecija | 105296 | Manuel Tiaoqui Elementary School (Formerly Tagtagumbao PS) | CUYAPO | 1st | 1 | 2 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 14568887.4 | 14370537.84 | completed | 1 | 2025-01-12 | 2025-03-11 | DEPED-NE-INFRA-063-2024 | INFRA-NE-LMS-001-2024 | 2024-03-08 | 2024-03-20 | 2024-04-02 | 2024-05-22 | 2024-08-15 | IJKMAE CONSTRUCTION INC. | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.25 | [8 empty] | 1st | 1
LMS 2024 | Region III | Nueva Ecija | 159020 | Tamale ES (Former Jaime L. Gamilla ES Annex) | BONGABON | 3rd | 1 | 2 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 17167389.49 | 16942768.53 | completed | 1 | 2025-01-12 | 2025-03-11 | DEPED-NE-INFRA-063-2024 | INFRA-NE-LMS-002-2024 | 2024-03-08 | 2024-03-20 | 2024-04-02 | 2024-05-22 | 2024-08-15 | JOYUS CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.25 | [8 empty] | 1st | 1
LMS 2024 | Region III | Nueva Ecija | 105594 | Singgalat ES | PALAYAN CITY (Capital) | 3rd | 1 | 2 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 17167389.49 | 16832451.48 | completed | 1 | 2025-01-05 | 2024-11-28 | DEPED-NE-INFRA-063-2024 | INFRA-NE-LMS-003-2024 | 2024-03-08 | 2024-03-20 | 2024-04-02 | 2024-05-22 | 2024-08-08 | V TRILLANA BUILDERS & TRADING | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.24 | [8 empty] | 2nd | 1
LMS 2024 | Region III | Pampanga | 502153 | Sebitanan Integrated School | SASMUAN (SEXMOAN) | 2nd | 1 | 6 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - SIX (6) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET IN EACH CLASSROOM) WITH PROVISION OF SCHOOL FURNITURE | 17171717.17 | 16961394.45 | Completed | 1 | 2025-01-05 | 2025-01-03 | I-2024-002 | I-2024-002 | 2023-11-16 | 2023-11-24 | 2023-12-06 | 2024-05-24 | 2024-05-31 | V. TRILLANA BUILDERS AND TRADING | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.25 | [8 empty] | 1st | 0
LMS 2024 | Region III | Pampanga | 300939 | Tagulod High School | CANDABA | 4th | 1 | 6 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - SIX (6) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET IN EACH CLASSROOM) WITH PROVISION OF SCHOOL FURNITURE & DETACHED HANDWASHING FACILITY | 17171717.17 | 16964878.39 | Completed | 1 | 2024-12-30 | 2024-12-09 | I-2024-003 | I-2024-003 | 2023-11-16 | 2023-11-24 | 2023-12-06 | 2024-05-24 | 2024-05-31 | TRACCOR BUILDERS | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.24 | [8 empty] | 1st | 0
LMS 2024 | Region III | Tarlac | 106552 | Sapang ES | MONCADA | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 12791493.32 | 8769144.65 | Ongoing | 0.95 | 2025-05-01 | 00:00:00 | 0 | 0 | 00:00:00 | 2024-06-03 | 2024-06-17 | 2024-06-28 | 2024-09-18 | HOR-VERT ENTERPRISES | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.85 | 0.1 | [9 empty] | 4th | 0
LMS 2024 | Region III | Zambales | 106945 | Buhawen Elementary School | SAN MARCELINO | 1st | 1 | 2 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 17171717.17 | 16950000 | completed | 1 | 2025-01-02 | 2025-02-15 | Infra-2024-001 | Infra-2024-002 | 2023-11-23 | 2023-11-29 | 2023-12-11 | 2023-12-18 | 2024-06-06 | V. TRILLANA BUILDERS AND TRADING | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 1st | 1
LMS 2024 | Region III | Zambales | 106915 | Manggahan Elementary School | PALAUIG | 2nd | 1 | 2 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 17171717.17 | 13378953.8 | completed | 1 | 2024-12-04 | 2025-05-06 | Infra-2024-001 | Infra-2024-004 | 2023-11-23 | 2023-11-29 | 2023-12-11 | 2023-12-18 | 2024-06-07 | THREE CM Builders | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 3rd | 1