## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No of Sites | SCOPE OF WORK | Batch | Project Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Site Reverted | No. of Site Not yet started | No. of Site Under Procurement | No. of Site On Going | No. of Site Completed | No. of Site Terminated | WITH TRANSFOPMER (Y/N) | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | CATEGORY 2 | Unnamed: 43
ELECTRIFICATION 2017 | Region V | Albay | 112031 | Hamorawon ES | RAPU-RAPU | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1232937.25 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION | REVERTED
ELECTRIFICATION 2017 | Region V | Albay | 112042 | Nstr. Sra De Guadalupe ES | RAPU-RAPU | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 336798.67 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION | REVERTED
ELECTRIFICATION 2017 | Region V | Camarines Sur | 112576 | Cabasag Comm. Sch | DEL GALLEGO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 519535.41 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Camarines Sur | 173504 | Salvacion ES | DEL GALLEGO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 580689.22 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Camarines Sur | 112585 | San Pablo Comm Sch | DEL GALLEGO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 528799.28 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Camarines Sur | 173514 | Agawan (Sitio of Tabog) | CARAMOAN | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 159624.17 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Camarines Sur | 112532 | Canatuan PS | CARAMOAN | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 440198.32 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Camarines Sur | 112543 | Hanoy PS | CARAMOAN | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 446985.76 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Camarines Sur | 112573 | Terogo PS | CARAMOAN | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 697001.28 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Camarines Sur | 112574 | Toboan PS | CARAMOAN | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 583800.4 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Camarines Sur | 112643 | Mangogon ES | LAGONOY | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 801783.89 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Camarines Sur | 173555 | San Andres ES | SIRUMA | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 586539.68 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113588 | Pasig ES | CLAVERIA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 879014.24 | 871113.92 | COMPLETED | 1 |  |  | INFRA 2017-12-017 | 2018-02-015 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113593 | San Ramon ES | CLAVERIA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 842231.87 | 834308.05 | COMPLETED | 1 |  |  | INFRA 2017-12-017 | 2018-02-016 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113864 | Cabug ES | SAN FERNANDO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 507440.05 | 497291.25 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-006 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113908 | Boca Chica ES | SAN PASCUAL | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 693094.89 | 669727.65 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-005 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 174522 | Gregorio T. Vilar Elementary School | SAN PASCUAL | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 436891.64 | 436011.01 | COMPLETED | 1 |  |  | INFRA 2017-12-017 | 2018-02-013 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Red Diamond Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113917 | Halabangbaybay ES | SAN PASCUAL | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 625621.18 | 617321.82 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-005 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113920 | Laurente ES | SAN PASCUAL | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 716445.44 | 709572.52 | COMPLETED | 1 |  |  | INFRA 2017-12-017 | 2018-02-014 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113921 | Lukban ES | SAN PASCUAL | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 384943.122 | 377244.26 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-006 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113923 | Mabuhay ES | SAN PASCUAL | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 732908.54 | 724986.88 | COMPLETED | 1 |  |  | INFRA 2017-12-017 | 2018-02-016 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113931 | Ramona ES | SAN PASCUAL | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 220922.35 | 213563.9 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-006 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113906 | San Rafael ES (Alimango ES) | SAN PASCUAL | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 744754.94 | 736798.25 | COMPLETED | 1 |  |  | INFRA 2017-12-017 | 2018-02-015 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 174523 | Segundina L. Rivera Primary School | SAN PASCUAL | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 422920.72 | 410233.1 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-006 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113937 | Sulficio Elliot ES | SAN PASCUAL | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 110554.08 | 107428.81 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-005 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113393 | Amoroy ES | AROROY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 562749.64 | 496360.28 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-010 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Ascentia Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 174517 | Isidoro F. Calimotan, Sr. ES | AROROY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 571423.4 | 569904.26 | COMPLETED | 1 |  |  | INFRA 2017-12-017 | 2018-02-012 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Aaron Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113387 | Manamoc ES | AROROY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 515477.22 | 507164.93 | COMPLETED | 1 |  |  | INFRA 2017-12-017 | 2018-02-012 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Aaron Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113436 | Madancalan PS | BALENO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 298127.43 | 258590.57 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-011 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Ascentia Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113451 | Danao ES | BALUD | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 716664.73 | 644272.05 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-010 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Ascentia Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113452 | Guinbanuahan ES | BALUD | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 986746.48 | 875664.78 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-011 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Ascentia Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113644 | Centro E/S | MANDAON | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 285395.97 | 273044.21 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 201-02-011 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-04-10 | Ascentia Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113648 | Guincaiptan ES | MANDAON | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 373294.56 | 330363.49 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 201-02-011 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-04-10 | Ascentia Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113720 | Bonbon ES | MILAGROS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 469697.85 | 405805.55 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-010 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Ascentia Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113726 | Matanglad ES | MILAGROS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 284297.83 | 282591.43 | COMPLETED | 1 |  |  | INFRA 2017-12-017 | 2018-02-013 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Red Diamond Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113731 | Pamangpangon ES | MILAGROS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 304461.49 | 301413.06 | COMPLETED | 1 |  |  | INFRA 2017-12-017 | 2018-02-013 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Red Diamond Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113714 | Tinaclipan ES | MILAGROS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 727933.44 | 720055.57 | COMPLETED | 1 |  |  | INFRA 2017-12-017 | 2018-02-012 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Aaron Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113746 | Mabuhay ES | MOBO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 489767.12 | 482908.48 | COMPLETED | 1 |  |  | INFRA 2017-12-017 | 2018-02-013 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Red Diamond Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 174506 | Agoho Elementary School | CAWAYAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 679668.44 | 677729.17 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-009 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Sansa Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113555 | Pin-as ES | CAWAYAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 436779.92 | 436756.66 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-007 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Zarepath Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113563 | Talisay ES | CAWAYAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 929820.19 | 921218.74 | COMPLETED | 1 |  |  | INFRA 2017-12-017 | 2018-02-013 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113566 | Vienteriales ES | CAWAYAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 361926.77 | 361894.39 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-008 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Zarepath Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113567 | Villaganas Village ES | CAWAYAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 483029.3 | 481716.24 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-007 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Zarepath Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113607 | Divisoria ES | DIMASALANG | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 534411.47 | 532831.07 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-007 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Zarepath Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113614 | Rizal ES | DIMASALANG | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 545468.67 | 541541.5 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-008 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Zarepath Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113615 | San Vicente ES | DIMASALANG | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 323164.42 | 323084.91 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-008 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Zarepath Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113625 | Libertad PS | ESPERANZA | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 227024.48 | 226010.32 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-008 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Zarepath Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113630 | Rizal PS | ESPERANZA | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 195333.11 | 195130.72 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-007 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Zarepath Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113632 | Santiago ES | ESPERANZA | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 439980.67 | 437340.4 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-009 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-04-10 | Sansa Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113837 | Tubod ES | PLACER | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 469965.55 | 467113.81 | COMPLETED | 1 |  |  | INFRA 2017-10-014 | 2018-02-009 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Sansa Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region V | Albay | 309515 | Malilipot NHS | MALILIPOT | 1 | 1 | UPGRADING | 1 | 2106133.08 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Albay | 301871 | San Antonio NHS, Malilipot | MALILIPOT | 1 | 1 | UPGRADING | 1 | 1155364.48 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Albay | 309505 | San Francisco NHS | MALILIPOT | 1 | 1 | UPGRADING | 1 | 1005974.09 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Albay | 111639 | Baligang ES | CAMALIG | 2 | 1 | UPGRADING | 1 | 6161438.9 |  | REVERTED | 0 | [10 empty] | no sub-aro downloaded | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 |  |  | UPGRADING | REVERTED
ELECTRIFICATION 2018 | Region V | Albay | 301813 | Batan National High School | RAPU-RAPU | 2 | 1 | UPGRADING | 1 | 1868547.6 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 12.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Albay | 309509 | Bilbao National High School | RAPU-RAPU | 2 | 1 | UPGRADING | 1 | 1482133.62 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 12.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Albay | 301884 | Mancao National High School | RAPU-RAPU | 2 | 1 | UPGRADING | 1 | 1595786.93 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 12.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Albay | 309519 | Tinopan HS | RAPU-RAPU | 2 | 1 | UPGRADING | 1 | 1570749.69 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 12.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Albay | 301882 | Villahermosa NHS | RAPU-RAPU | 2 | 1 | UPGRADING | 1 | 1709022.71 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 12.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Albay | 111965 | Alabangpuro ES | PIO DURAN | 3 | 1 | UPGRADING | 1 | 1374646.64 |  | REVERTED | 0 | [10 empty] | no downloaded fund | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 |  |  | UPGRADING | REVERTED
ELECTRIFICATION 2018 | Region V | Albay | 309503 | Alabangpuro High School | PIO DURAN | 3 | 1 | UPGRADING | 2 | 1374646.64 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Albay | 301840 | Magpanambo NHS | POLANGUI | 3 | 1 | UPGRADING | 1 | 1496125.18 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Norte | 301898 | Jose Panganiban NHS | JOSE PANGANIBAN | 1 | 1 | UPGRADING | 1 | 3939736.92 | 3913595.4 | COMPLETED | 1 | 2018-07-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Norte | 301893 | Daguit NHS | LABO | 1 | 1 | UPGRADING | 1 | 2492745.53 | 2468080.15 | COMPLETED | 1 | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Norte | 301923 | Talobatib HS | LABO | 1 | 1 | UPGRADING | 1 | 1656810.17 | 3631385.71 | COMPLETED | 1 | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Norte | 301922 | Tulay Na Lupa NHS | LABO | 1 | 1 | UPGRADING | 1 | 3649542.64 | 1642239.75 | COMPLETED | 1 | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Norte | 301890 | Batobalani NHS | PARACALE | 1 | 1 | UPGRADING | 1 | 2626785.92 | 2596870.62 | COMPLETED | 1 | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Norte | 301910 | Paracale NHS | PARACALE | 1 | 1 | UPGRADING | 1 | 2634173.86 | 2608327.86 | COMPLETED | 1 | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Norte | 301889 | Basud NHS | BASUD | 2 | 1 | UPGRADING | 1 | 7013018.85 | 6963077.23 | COMPLETED | 1 | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Norte | 301906 | Moreno Integrated School | DAET (Capital) | 2 | 1 | UPGRADING | 1 | 3642946.55 | 3606232.35 | COMPLETED | 1 | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Norte | 301905 | Mercedes HS | MERCEDES | 2 | 1 | UPGRADING | 1 | 2523429.7 | 2495864 | COMPLETED | 1 | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301988 | Lupi-Iligan HS | LUPI | 1 | 1 | UPGRADING | 1 | 2261423.66 | 1969455.26 | COMPLETED | 1 | 1/17/2019 | 2019-10-01 |  | 2018-10-036 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301929 | Simeon Tycangco MHS | RAGAY | 1 | 1 | UPGRADING | 1 | 2549977.63 | 2251366.66 | COMPLETED | 1 | 1/17/2019 | 2019-10-01 |  | 2018-10-036 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301930 | Sisa Feliciano MHS | RAGAY | 1 | 1 | UPGRADING | 1 | 2083426.75 | 1717914.86 | COMPLETED | 1 | 1/17/2019 | 2019-10-01 |  | 2018-10-036 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309743 | Bolo Norte HS | SIPOCOT | 1 | 1 | UPGRADING | 1 | 2657221.68 | 2323637.87 | COMPLETED | 1 | 1/17/2019 | 2019-10-01 |  | 2018-10-036 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309767 | Manangle High School | SIPOCOT | 1 | 1 | UPGRADING | 1 | 1015428.28 | 961058.46 | COMPLETED | 1 | 1/17/2019 | 2019-10-01 |  | 2018-10-036 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301935 | Bahao HS | LIBMANAN | 2 | 1 | UPGRADING | 1 | 2174993.93 | 1894351.47 | COMPLETED | 1 | 1/19/2019 | 1/14/2019 |  | 2018-10-038 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301994 | Mambulo Nuevo High School | LIBMANAN | 2 | 1 | UPGRADING | 1 | 2474177.75 | 2296519.86 | COMPLETED | 1 | 1/19/2019 | 1/14/2019 |  | 2018-10-038 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309745 | Northern Plain HS | LIBMANAN | 2 | 1 | UPGRADING | 1 | 1247131.89 | 1147671.47 | COMPLETED | 1 | 1/19/2019 | 1/14/2019 |  | 2018-10-038 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309731 | Antipolo HS, Minalabac | MINALABAC | 2 | 1 | UPGRADING | 1 | 1947146.05 | 1936318.45 | COMPLETED | 1 | 1/19/2019 | on-going |  | 2018-10-037 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302025 | Sagrada Familia High School | MINALABAC | 2 | 1 | UPGRADING | 1 | 2033467.72 | 2020150.3 | COMPLETED | 1 | 1/19/2019 | on-going |  | 2018-10-037 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301968 | Don Mariano C. Veneracion NHS | PAMPLONA | 2 | 1 | UPGRADING | 1 | 1852571.57 | 1839633.71 | COMPLETED | 1 | 1/19/2019 | on-going |  | 2018-10-037 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302032 | Maura N. Sibulo National HS | PAMPLONA | 2 | 1 | UPGRADING | 1 | 1852571.57 | 1840158.72 | COMPLETED | 1 | 1/19/2019 | on-going |  | 2018-10-037 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309732 | Dr. Lorenzo P. Ziga MHS | PASACAO | 2 | 1 | UPGRADING | 1 | 1886881.46 | 1870097.06 | COMPLETED | 1 | 1/19/2019 | on-going |  | 2018-10-037 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301965 | Rolando R. Andaya, Sr. MHS | PASACAO | 2 | 1 | UPGRADING | 1 | 1293794.83 | 1284175.86 | COMPLETED | 1 | 1/19/2019 | on-going |  | 2018-10-037 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309707 | Siembre HS | BOMBON | 3 | 1 | UPGRADING | 1 | 1096756.47 | 1089277.69 | COMPLETED | 1 | 1/25/2019 | on-going |  | 2018-10-039 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302053 | Sulpicio A. Roco MHS | BOMBON | 3 | 1 | UPGRADING | 1 | 1585526.55 | 1577100.5 | COMPLETED | 1 | 1/25/2019 | on-going |  | 2018-10-039 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309735 | Northern Canaman HS | CANAMAN | 3 | 1 | UPGRADING | 1 | 1622289.56 | 1610170.5 | COMPLETED | 1 | 1/25/2019 | on-going |  | 2018-10-039 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301957 | Doroteo Federis, Sr. NHS (frmerly: Carangcang HS) | MAGARAO | 3 | 1 | UPGRADING | 1 | 1351201.39 | 1340545.39 | COMPLETED | 1 | 1/25/2019 | on-going |  | 2018-10-039 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302034 | Magarao NHS (formerly: San Isidro NHS) | MAGARAO | 3 | 1 | UPGRADING | 1 | 2031906.68 | 2020570.5 | COMPLETED | 1 | 1/25/2019 | on-going |  | 2018-10-039 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301946 | Binanuaanan NHS | PILI (Capital) | 3 | 1 | UPGRADING | 1 | 2223308.53 | 2200190.5 | COMPLETED | 1 | 1/25/2019 | on-going |  | 2018-10-039 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302017 | Gov.Mariano E. Villafuerte HS | PILI (Capital) | 3 | 1 | UPGRADING | 1 | 1913337.83 | 1901222.5 | COMPLETED | 1 | 1/25/2019 | on-going |  | 2018-10-039 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302054 | Tabgon HS, Goa | GOA | 4 | 1 | UPGRADING | 1 | 1372217.91 | 1363063.5 | COMPLETED | 1 | 1/25/2019 | on-going |  | 2018-10-039 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309768 | Cabotonan High School | LAGONOY | 4 | 1 | UPGRADING | 1 | 688543.69 | 657566.44 | COMPLETED | 1 | 1/19/2019 | 2019-09-01 |  | 2018-10-041 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301963 | Dahat National Vocational HS | LAGONOY | 4 | 1 | UPGRADING | 1 | 1291895.7 | 1141972.43 | COMPLETED | 1 | 1/19/2019 | 2019-09-01 |  | 2018-10-041 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302039 | San Ramon Pilot NHS, Lagonoy (frmerly:Sn.Ramon Pilot HS) | LAGONOY | 4 | 1 | UPGRADING | 1 | 1914501.56 | 1531284.58 | COMPLETED | 1 | 1/19/2019 | 2019-09-01 |  | 2018-10-041 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309708 | Catalotoan HS | SAGÑAY | 4 | 1 | UPGRADING | 1 | 876848.61 | 871188.51 | COMPLETED | 1 | 1/19/2019 |  |  | 2018-10-040 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309714 | Dr. Rodolfo V. Pamor MHS - Sagñay Southeastern Annex HS | SAGÑAY | 4 | 1 | UPGRADING | 1 | 1968881.53 | 1951156.85 | COMPLETED | 1 | 1/19/2019 |  |  | 2018-10-040 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309753 | Salogon HS | SAN JOSE | 4 | 1 | UPGRADING | 1 | 1614124.45 | 1298414.41 | COMPLETED | 1 | 1/19/2019 | 2019-09-01 |  | 2018-10-041 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309771 | Villafuerte-Peña High School | SAN JOSE | 4 | 1 | UPGRADING | 1 | 1176699.96 | 1042098.45 | COMPLETED | 1 | 1/19/2019 | 2019-09-01 |  | 2018-10-041 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301984 | Vivencio Obias - Kinalansan NHS (formerly: Kinalansan NHS) | SAN JOSE | 4 | 1 | UPGRADING | 1 | 3138071.77 | 2994583.84 | COMPLETED | 1 | 1/19/2019 | 2019-09-01 |  | 2018-10-041 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301986 | La Salvacion NHS | TIGAON | 4 | 1 | UPGRADING | 1 | 2413979.33 | 2393533.47 | COMPLETED | 1 | 1/25/2019 |  |  | 2018-10-041 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309766 | San Rafael National High School - Cabalinadan Annex HS | TIGAON | 4 | 1 | UPGRADING | 1 | 1459235.29 | 1448397.7 | COMPLETED | 1 | 1/25/2019 |  |  | 2018-10-041 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302029 | Tinawagan NHS | TIGAON | 4 | 1 | UPGRADING | 1 | 2198602.27 | 2183966.34 | COMPLETED | 1 | 1/25/2019 |  |  | 2018-10-041 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 112317 | Agdangan ES | BAAO | 5 | 1 | UPGRADING | 1 | 1335674.46 | 1326372.24 | COMPLETED | 1 | 1/25/2019 |  |  | 2018-10-042 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301933 | Eusebia Paz Arroyo Mem. NHS | BAAO | 5 | 1 | UPGRADING | 1 | 881608.32 | 875269.53 | COMPLETED | 1 | 1/25/2019 |  |  | 2018-10-042 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302014 | Pararao HS | BALATAN | 5 | 1 | UPGRADING | 1 | 1558409.79 | 1546681.07 | COMPLETED | 1 | 1/25/2019 | 8/31/2019 |  | 2018-10-042 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309759 | Pulang Daga High School | BALATAN | 5 | 1 | UPGRADING | 1 | 1826170.87 | 1810585 | COMPLETED | 1 | 1/25/2019 | 8/31/2019 |  | 2018-10-042 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302059 | Tapayas HS | BALATAN | 5 | 1 | UPGRADING | 1 | 1339454.4 | 1331418.75 | COMPLETED | 1 | 1/25/2019 | 8/31/2019 |  | 2018-10-042 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309746 | Payak HS | BATO | 5 | 1 | UPGRADING | 1 | 1375160.28 | 1366978.29 | COMPLETED | 1 | 1/25/2019 |  |  | 2018-10-042 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302026 | Salvacion HS, Bato | BATO | 5 | 1 | UPGRADING | 1 | 1791228.85 | 1778610.22 | COMPLETED | 1 | 1/25/2019 |  |  | 2018-10-042 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301971 | Fabrica HS | BULA | 5 | 1 | UPGRADING | 1 | 1395935.08 | 1301496.18 | COMPLETED | 1 | 1/19/2019 | 1/17/2018 |  | 2018-10-043 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301982 | Inoyonan HS | BULA | 5 | 1 | UPGRADING | 1 | 1527923.25 | 1312067.77 | COMPLETED | 1 | 1/19/2019 | 1/17/2018 |  | 2018-10-043 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302041 | San Ramon HS | BULA | 5 | 1 | UPGRADING | 1 | 945965.75 | 858981.7 | COMPLETED | 1 | 1/19/2019 | 1/17/2018 |  | 2018-10-043 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301992 | Tandaay Provincial HS | NABUA | 5 | 1 | UPGRADING | 1 | 1219125.3 | 1140672.11 | COMPLETED | 1 | 1/19/2019 | 1/17/2018 |  | 2018-10-043 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Catanduanes | 302101 | Sicmil IS | GIGMOTO | 0 | 1 | UPGRADING | 1 | 1251978.25 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Catanduanes | 309802 | Cobo IS | PANDAN | 0 | 1 | UPGRADING | 1 | 1496144.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Catanduanes | 302091 | Manambrag NHS | SAN ANDRES (CALOLBON) | 0 | 1 | UPGRADING | 1 | 2069243.38 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Catanduanes | 302092 | Mayngaway NHS | SAN ANDRES (CALOLBON) | 0 | 1 | UPGRADING | 1 | 1955914.93 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Catanduanes | 302098 | San Miguel Rural DHS | SAN MIGUEL | 0 | 1 | UPGRADING | 1 | 2230044.6 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Iriga City | 343238 | San Agustin Senior High School | IRIGA CITY | 5 | 1 | UPGRADING | 1 | 1224536.41 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Legaspi City | 302257 | Banquerohan NHS | LEGAZPI CITY (Capital) | 2 | 1 | UPGRADING | 2 | 2771096.04 | 2716466.89 | COMPLETED | 1 | 2018-09-15 |  |  |  | 2018-04-12 | 2018-04-20 | 2018-05-02 | 2018-05-18 | 2018-05-21 | ZAREPATH Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Legaspi City | 302261 | Pag-asa NHS | LEGAZPI CITY (Capital) | 2 | 1 | UPGRADING | 1 | 3313445.5 | 3106673.93 | COMPLETED | 1 | 2018-09-10 |  |  |  | 2018-04-12 | 2018-04-20 | 2018-05-02 | 2018-05-18 | 2018-05-21 | ZAREPATH Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Ligao City | 301837 | Ligao NHS | CITY OF LIGAO | 3 | 1 | UPGRADING | 2 | 2588654.65 | 2250000 | COMPLETED | 1 | 9/24/2018 |  |  | DO LIGAO 04-05-2018 | 2018-04-23 | 2018-05-02 | 2018-05-17 | 2018-06-29 | 2018-07-04 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Masbate | 302129 | Cataingan National High School | CATAINGAN | 3 | 1 | UPGRADING | 2 | 3548375.59 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Masbate | 302121 | Buenavista National High School | USON | 3 | 1 | UPGRADING | 2 | 2529306.31 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Masbate | 302131 | Del Carmen National High School | USON | 3 | 1 | UPGRADING | 2 | 3394197.47 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Masbate | 302110 | Temistocles A. Merioles, Sr. Memorial High School | USON | 3 | 1 | UPGRADING | 2 | 1346259.42 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Masbate City | 302133 | Capitolina O. Legaspi Memorial High School | CITY OF MASBATE (Capital) | 2 | 1 | UPGRADING | 2 | 1228060.54 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Masbate City | 113695 | Jose Zurbito Sr. Elementary School | CITY OF MASBATE (Capital) | 2 | 1 | UPGRADING | 3 | 1472274.9 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Masbate City | 302148 | Masbate National Comprehensive High School | CITY OF MASBATE (Capital) | 2 | 1 | UPGRADING | 2 | 3621816.14 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Masbate City |  | Masbate National Comprehensive High School Annex-Senior High School | CITY OF MASBATE (Capital) | 2 | 1 | UPGRADING | 2 | 1220272.53 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon | 302197 | Casiguran Technical Vocational School | CASIGURAN | 1 | 1 | UPGRADING | 2 | 2652600.35 | 2112236.92 | COMPLETED | 1 | 2018-10-16 | [7 empty] | 2018-06-26 | Riderscorner Construction & General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon | 302201 | Cumadcad NHS | CASTILLA | 1 | 1 | UPGRADING | 2 | 1681856.55 | 1340119.31 | COMPLETED | 1 | 2018-10-16 | [7 empty] | 2018-06-26 | Riderscorner Construction & General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon | 302222 | Magallanes National High School | MAGALLANES | 1 | 1 | UPGRADING | 2 | 1534901.95 | 1340000 | COMPLETED | 1 | 2018-11-19 | [7 empty] | 2018-08-01 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon | 302220 | Magallanes National Vocational HS | MAGALLANES | 1 | 1 | UPGRADING | 2 | 1546296.31 | 1400426.11 | COMPLETED | 1 | 2018-11-19 | [7 empty] | 2018-07-27 | JERA Gen. Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon | 302184 | Barcelona National Comprehensive HS | BARCELONA | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1501127.63 | 1418661.93 | COMPLETED | 1 | Sept. 22, 2018 | [7 empty] | 2018-07-17 | Riderscorner Construction & General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon | 302190 | Bulan NHS | BULAN | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1980291.25 | 1650000 | COMPLETED | 1 | 2018-10-03 | [7 empty] | 2018-07-17 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon | 302214 | Gubat NHS | GUBAT | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1447611.59 | 1152240.71 | COMPLETED | 1 | Sept. 22, 2018 | [7 empty] | 2018-07-17 | Riderscorner Construction & General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon | 302212 | Gallanosa National High School | IROSIN | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1766634.29 | 1410046.01 | COMPLETED | 1 | 2018-10-03 | [7 empty] | 2018-07-17 | Riderscorner Construction & General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon | 302186 | Biriran NHS | JUBAN | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1317882.11 | 1120000 | COMPLETED | 1 | Sept. 22, 2018 | [7 empty] | 2018-07-17 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon | 302187 | Juban National High School | JUBAN | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 881760.7 | 750000 | COMPLETED | 1 | 2018-10-03 | [7 empty] | 2018-07-17 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon | 302245 | Sta. Magdalena National High School | SANTA MAGDALENA | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 967339.2 | 825000 | COMPLETED | 1 | 2018-10-03 | [7 empty] | 2018-07-17 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon City | 302271 | Buenavista National High School | CITY OF SORSOGON (Capital) | 1 | 1 | UPGRADING | 1 | 988154.78 | 934630.94 | COMPLETED | 1 | October 31, 2018 |  |  |  |  | April 25, 2018 | May 7, 2018 |  |  | Riders Corner |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon City | 302280 | Lydia D. Martinez Memorial High School | CITY OF SORSOGON (Capital) | 1 | 1 | UPGRADING | 1 | 656937.92 | 650397.97 | COMPLETED | 1 | October 31, 2018 |  |  |  |  | April 25, 2018 | May 7, 2018 |  |  | Zarepath |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon City | 302272 | MERCEDES B. PERALTA SENIOR HIGH SCHOOL | CITY OF SORSOGON (Capital) | 1 | 1 | UPGRADING | 1 | 1351069.37 | 1337619.24 | terminated | 0.4 | October 31, 2018 |  |  |  |  | April 25, 2018 | May 7, 2018 |  |  | Zarepath | Terminated due to lapse of fund | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 0.4 | 0 |  |  | UPGRADING | terminated
ELECTRIFICATION 2018 | Region V | Sorsogon City | 302275 | Rawis National High School | CITY OF SORSOGON (Capital) | 1 | 1 | UPGRADING | 1 | 1153525.17 | 1097641.39 | COMPLETED | 1 | October 31, 2018 |  |  |  |  | April 25, 2018 | May 7, 2018 |  |  | Riders Corner |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon City | 302278 | Sawanga National High School | CITY OF SORSOGON (Capital) | 1 | 1 | UPGRADING | 2 | 1818648.95 | 1799599.67 | terminated | 0.4 | [9 empty] | Zarepath | Terminated due to lapse of fund | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 0.4 | 0 |  |  | UPGRADING | terminated
ELECTRIFICATION 2018 | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO | 1 | 1 | UPGRADING | 2 | 6729139.42 | 6007162.8 | COMPLETED | 1 | 2018-12-17 | 2018-12-17 |  |  | 2018-05-18 |  | 2018-07-12 |  | Sept. 9, 2018 | Zarepath Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Albay | 301863 | Pili National High School | BACACAY | 1 | 1 | UPGRADING | Batch 3 | 2530593.03 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Albay | 301878 | Sogod National High school | BACACAY | 1 | 1 | UPGRADING | Batch 3 | 2835628.63 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Albay | 301827 | Estancia National High School | MALINAO | 1 | 1 | UPGRADING | Batch 3 | 1251780.25 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Albay | 301815 | Bical High School | SANTO DOMINGO (LIBOG) | 1 | 1 | UPGRADING | Batch 3 | 1031796.91 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Albay | 301872 | San Fernando National High School | SANTO DOMINGO (LIBOG) | 1 | 1 | UPGRADING | Batch 3 | 1247258.11 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Albay | 301830 | Jovellar National High School | JOVELLAR | 3 | 1 | UPGRADING | Batch 3 | 2020559.44 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Albay | 301873 | San Isidro National High School | JOVELLAR | 3 | 1 | UPGRADING | Batch 3 | 1113045.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Norte | 301886 | Bagong Silang I HS | LABO | 1 | 1 | UPGRADING | Batch 3 | 3266647.1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Norte | 301899 | Labo National High School | LABO | 1 | 1 | UPGRADING | Batch 3 | 4043823.52 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Norte | 301917 | Leocadio Alejo Entienza HS | SANTA ELENA | 1 | 1 | UPGRADING |  | 4043823.52 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Norte | 301891 | Camarines Norte National HS | DAET (Capital) | 2 | 1 | UPGRADING | Batch 3 | 3857618.71 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Norte | 301892 | D. Q. Liwag NHS | VINZONS | 2 | 1 | UPGRADING |  | 4510135.44 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Norte | 301925 | Vinzons Pilot High School | VINZONS | 2 | 1 | UPGRADING |  | 14022233.76 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 302046 | Sinuknipan NHS | DEL GALLEGO | 1 | 1 | UPGRADING | Batch 3 | 2089735.91 |  | COMPLETED | 1 | 2020-04-04 |  |  | 2019-10-051 | 2019-07-08 |  | 8/27/2019 |  | 2019-12-06 | PHILIAN CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur |  | Sinuknipan Senior High School | DEL GALLEGO | 1 | 1 | UPGRADING | Batch 3 | 1346316.56 |  | COMPLETED | 1 | 2020-04-04 |  |  | 2019-10-051 | 2019-07-08 |  | 8/27/2019 |  | 2019-12-06 | PHILIAN CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309751 | Ragay Science and Math Oriented High School | RAGAY | 1 | 1 | UPGRADING | Batch 3 | 2310948.95 |  | COMPLETED | 1 | 2020-04-04 |  |  | 2019-10-051 | 2019-07-08 |  | 8/27/2019 |  | 2019-12-06 | PHILIAN CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301927 | Anib National High School | SIPOCOT | 1 | 1 | UPGRADING | Batch 3 | 2458552.08 |  | COMPLETED | 1 | 2020-04-04 |  |  | 2019-10-051 | 2019-07-08 |  | 8/27/2019 |  | 2019-12-06 | PHILIAN CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309755 | Sacred Heart High School | SIPOCOT | 1 | 1 | UPGRADING | Batch 3 | 2318394.14 |  | COMPLETED | 1 | 2020-04-04 |  |  | 2019-10-051 | 2019-07-08 |  | 8/27/2019 |  | 2019-12-06 | PHILIAN CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301973 | Gainza National HS | GAINZA | 2 | 1 | UPGRADING | Batch 3 | 1566614.35 |  | COMPLETED | 1 | April 10, 2020 |  |  | - | 2019-07-08 |  | 9/23/2019 |  | 2019-12-12 | ZKR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301999 | Milaor National High School | MILAOR | 2 | 1 | UPGRADING | Batch 3 | 2319927.77 |  | COMPLETED | 1 | April 10, 2020 |  |  | - | 2019-07-08 |  | 9/23/2019 |  | 2019-12-12 | ZKR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301981 | Hobo National High School | MINALABAC | 2 | 1 | UPGRADING | Batch 3 | 2868966.33 |  | COMPLETED | 1 | April 10, 2020 |  |  | - | 2019-07-08 |  | 9/23/2019 |  | 2019-12-12 | ZKR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309757 | Cagbibi National High School | PAMPLONA | 2 | 1 | UPGRADING | Batch 3 | 1223675.91 |  | COMPLETED | 1 | April 10, 2020 |  |  | - | 2019-07-08 |  | 9/23/2019 |  | 2019-12-12 | ZKR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309723 | Del Rosario National HS | PAMPLONA | 2 | 1 | UPGRADING | Batch 3 | 1797949.17 |  | COMPLETED | 1 | April 10, 2020 |  |  | - | 2019-07-08 |  | 9/23/2019 |  | 2019-12-12 | ZKR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 302021 | Ramon B. Felipe Sr. NHS (frmerly: San Vicente HS) | PAMPLONA | 2 | 1 | UPGRADING | Batch 3 | 2464359.02 |  | COMPLETED | 1 | April 10, 2020 |  |  | - | 2019-07-08 |  | 9/23/2019 |  | 2019-12-12 | ZKR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301983 | Jose De Villa NHS | CALABANGA | 3 | 1 | UPGRADING | Batch 3 | 2336338.97 |  | COMPLETED | 1 | April 4, 2020 |  |  | 2019-10-052 | 2019-07-08 |  | 8/27/2019 |  | 2019-06-12 | JERA CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301998 | Medroso-Mendoza NHS | CALABANGA | 3 | 1 | UPGRADING | Batch 3 | 2831480.62 |  | COMPLETED | 1 | April 4, 2020 |  |  | 2019-10-052 | 2019-07-08 |  | 8/27/2019 |  | 2019-06-12 | JERA CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301954 | Sabang National High School | CALABANGA | 3 | 1 | UPGRADING | Batch 3 | 3003112.73 |  | COMPLETED | 1 | [6 empty] | 8/27/2019 |  | 2019-06-12 | JERA CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 303542 | Severo High School | CALABANGA | 3 | 1 | UPGRADING | Batch 3 | 3953216 |  | COMPLETED | 1 | April 4, 2020 |  |  | 2019-10-052 | 2019-07-08 |  | 8/27/2019 |  | 2019-06-12 | JERA CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 302065 | Union National High School | CALABANGA | 3 | 1 | UPGRADING | Batch 3 | 1782299.84 |  | COMPLETED | 1 | [6 empty] | 8/27/2019 |  | 2019-06-12 | JERA CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301955 | West Coast High School | CALABANGA | 3 | 1 | UPGRADING | Batch 3 | 3953216 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 500157 | Ponong Integrated School | MAGARAO | 3 | 1 | UPGRADING | Batch 3 | 1952525.81 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301962 | Altamarino-Clasio High School (formerly Curry High School) | PILI (Capital) | 3 | 1 | UPGRADING | Batch 2 | 1816543.54 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309749 | BINOBONG HIGH SCHOOL | PILI (Capital) | 3 | 1 | UPGRADING | Batch 3 | 1240932.14 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309719 | Dona Basilia S. Quilon Memorial High School (formerly:Bagong Sirang HS) | PILI (Capital) | 3 | 1 | UPGRADING | Batch 3 | 2134901.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301975 | Goa National High School | GOA | 4 | 1 | UPGRADING | Batch 2 | 3540417.58 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309741 | Juan L. Filipino Memorial High School | GOA | 4 | 1 | UPGRADING | Batch 3 | 3640861.92 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 302040 | Panagan National High School | LAGONOY | 4 | 1 | UPGRADING | Batch 2 | 2049381.87 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309715 | Nato National High School (Main Campus) | SAGÑAY | 4 | 1 | UPGRADING | Batch 2 | 1757233.46 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309715 | Nato National High School (San Isidro) | SAGÑAY | 4 |  | UPGRADING | Batch 2 | 1798703.1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309752 | Tinorongan National High School (Formerly Sagñay Western HS) | SAGÑAY | 4 | 1 | UPGRADING | Batch 2 | 1449333.92 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 302035 | Rangas-Ramos NHS (frmerly:Sn Jose Fish.Sch.) | SAN JOSE | 4 | 1 | UPGRADING | Batch 2 | 1706475.23 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309721 | Huyonhuyon HS | TIGAON | 4 | 1 | UPGRADING | Batch 2 | 2408143.82 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 302015 | Partido Agro-Industrial NHS | TIGAON | 4 | 1 | UPGRADING | Batch 3 | 8309190.67 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 302038 | San Rafael National High School | TIGAON | 4 | 1 | UPGRADING | Batch 3 | 3690189.18 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur |  | San Rafael National High School annex | Tigaon | 4 | 1 | UPGRADING | Batch 3 | 4921431.62 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 302056 | Tamban NHS | TINAMBAC | 4 | 1 | UPGRADING | Batch 3 | 7264217.74 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 112317 | Agdangan ES | BAAO | 5 | 1 | UPGRADING | Batch 3 | 2945467.81 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301960 | Coguit HS | BALATAN | 5 | 1 | UPGRADING | Batch 3 | 4586815.53 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309725 | Laganac High School | BALATAN | 5 | 1 | UPGRADING | Batch 3 | 2867429.08 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301997 | Masoli High School | BATO | 5 | 1 | UPGRADING | Batch 3 | 1885493.94 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 112421 | Tambo ES | BUHI | 5 | 1 | UPGRADING | Batch 3 | 2495578.97 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301938 | Balaogan National High School | BULA | 5 | 1 | UPGRADING | Batch 3 | 1803929.13 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309760 | Fabrica HS - La Victoria Annex HS | BULA | 5 | 1 | UPGRADING | Batch 3 | 3061918.51 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 302007 | Ombao HS | BULA | 5 | 1 | UPGRADING | Batch 3 | 1826009.25 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 302002 | Lourdes PHS | NABUA | 5 | 1 | UPGRADING | Batch 3 | 1255263.79 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301991 | Malawag National High School | NABUA | 5 | 1 | UPGRADING | Batch 3 | 2064135.14 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Catanduanes | 302072 | Bagamanoc Rural DHS | BAGAMANOC | 0 | 1 | UPGRADING | Batch 3 | 1681122.6 |  | COMPLETED | 1 | 2020-04-04 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Catanduanes | 302073 | Baras Rural DHS | BARAS | 0 | 1 | UPGRADING | Batch 3 | 2235281.45 |  | COMPLETED | 1 | 2020-04-04 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Catanduanes | 500412 | Bote IS | BATO | 0 | 1 | UPGRADING | Batch 3 | 2692700.44 |  | COMPLETED | 1 | 2020-04-04 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Catanduanes | 302082 | Caramoran School of Fisheries | CARAMORAN | 0 | 1 | UPGRADING | Batch 3 | 2620441.03 |  | COMPLETED | 1 | 2020-04-04 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Catanduanes | 302102 | Supang-Datag National High School | CARAMORAN | 0 | 1 | UPGRADING | Batch 3 | 1273227.26 |  | COMPLETED | 1 | 2020-04-04 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Catanduanes | 113314 | Tambongon CES | VIGA | 0 | 1 | UPGRADING | Batch 3 | 1494832.13 |  | COMPLETED | 1 | 2020-04-04 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Catanduanes | 500031 | Buyo Integrated School | VIRAC (Capital) | 0 | 1 | UPGRADING | Batch 3 | 3186388.56 |  | COMPLETED | 1 | 2020-04-04 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Catanduanes | 302084 | Calatagan High School | VIRAC (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1505771.78 |  | COMPLETED | 1 | 2020-04-04 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Catanduanes | 302083 | Catanduanes NHS | VIRAC (Capital) | 0 | 1 | UPGRADING |  | 6858553.63 |  | COMPLETED | 1 | 2020-04-04 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Catanduanes | 302093 | Palta NHS | VIRAC (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1296398.92 |  | COMPLETED | 1 | 2020-04-04 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Iriga City | 500167 | Cristo Rey IS | IRIGA CITY | 5 | 1 | UPGRADING | Batch 1 | 1586988.5 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Iriga City | 302249 | Perpetual Help NHS | IRIGA CITY | 5 | 1 | UPGRADING | Batch 1 | 1706777.84 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Iriga City | 302252 | Sagrada NHS | IRIGA CITY | 5 | 1 | UPGRADING | Batch 1 | 2343563.46 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Iriga City | 302256 | Sto. Niño NHS | IRIGA CITY | 5 | 1 | UPGRADING | Batch 3 | 3419385.3 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Legaspi City | 114457 | Albay CS | LEGAZPI CITY (Capital) | 2 | 1 | UPGRADING | Batch 1 | 1408291.48 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Legaspi City | 114470 | Cagbacong Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 545908.57 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Legaspi City | 310206 | Cagbacong High School | LEGAZPI CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1031464.78 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Legaspi City | 302262 | Gogon High School | LEGAZPI CITY (Capital) | 2 | 1 | UPGRADING | Batch 1 | 1085598.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Legaspi City | 302259 | Homapon High School | LEGAZPI CITY (Capital) | 2 | 1 | UPGRADING | Batch 1 | 1325598.42 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Legaspi City | 302258 | Oro Site High School | LEGAZPI CITY (Capital) | 2 | 1 | UPGRADING | Batch 1 | 916949.56 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Legaspi City | 302263 | Pawa High School | LEGAZPI CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1518683.47 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Legaspi City | 500169 | Taysan Resettlement Integrated School | LEGAZPI CITY (Capital) | 2 | 1 | UPGRADING | Batch 1 | 1280207.32 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Masbate | 302143 | Luy-a National High School | AROROY | 2 | 1 | UPGRADING | Batch 3 | 2291424.79 | 2258907.83 | COMPLETED | 1 | 2020-03-05 |  | 2019-08-007 | 2019-09-028 | 2019-07-30 | 2019-08-07 | 2019-08-19 | 2019-11-28 | 2019-12-06 | Sansa Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Masbate | 309932 | Nabongsoran High School | AROROY | 2 | 1 | UPGRADING | Batch 3 | 1832115.23 | 1806924.42 | COMPLETED | 1 |  |  | 2019-08-007 | 2019-09-027 | 2019-07-30 | 2019-08-07 | 2019-08-19 | 2019-11-19 | 2019-11-28 | Marabe Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Masbate | 309907 | San Pablo National High School | MANDAON | 2 | 1 | UPGRADING | Batch 3 | 1535130.08 | 1509666.23 | COMPLETED | 1 | 2020-02-26 |  | 2019-08-007 | 2019-09-029 | 2019-07-30 | 2019-08-07 | 2019-08-19 | 2019-11-19 | 2019-11-28 | Ascentia Const. Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Masbate | 302151 | Mobo National High School | MOBO | 2 | 1 | UPGRADING | Batch 3 | 1897641.09 | 1869869.64 | COMPLETED | 1 | 2020-03-05 |  | 2019-08-007 | 2019-09-030 | 2019-07-30 | 2019-08-07 | 2019-08-19 | 2019-11-19 | 2019-12-06 | Bryne Const. & Suppply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Masbate | 302158 | Pawican National High School | CATAINGAN | 3 | 1 | UPGRADING | Batch 3 | 4648037.22 | 4595455.84 | COMPLETED | 1 | 2020-02-27 |  | 2019-08-007 | 2019-09-033 | 2019-07-30 | 2019-08-07 | 2019-08-19 | 2019-11-19 | 2019-11-29 | 144 Cubits Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Masbate | 302177 | Villahermosa National High School | CAWAYAN | 3 | 1 | UPGRADING | Batch 3 | 1559451.65 | 1530475.91 | COMPLETED | 1 |  |  | 2019-08-007 | 2019-09-032 | 2019-07-30 | 2019-08-07 | 2019-08-19 |  |  | GACT Ent. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Masbate | 302136 | Matagangtang National High School | PLACER | 3 | 1 | UPGRADING | Batch 3 | 2056294.37 | 2019815.85 | COMPLETED | 1 | 2020-03-08 |  | 2019-08-007 | 2019-09-031 | 2019-07-30 | 2019-08-07 | 2019-08-19 | 2019-11-29 | 2019-12-09 | Red Diamond Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Masbate | 302170 | San Ramon National High School | USON | 3 | 1 | UPGRADING | Batch 3 | 1461341.2 | 1435682.8 | COMPLETED | 1 | 2020-02-26 |  | 2019-08-007 | 2019-09-034 | 2019-07-30 | 2019-08-07 | 2019-08-19 | 2019-11-19 | 2019-11-28 | Marabe Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Masbate | 302175 | Uson National High School | USON | 3 | 1 | UPGRADING | Batch 3 | 3979065.52 | 3932239.25 | COMPLETED | 1 | 2020-02-27 |  | 2019-08-007 | 2019-09-035 | 2019-07-30 | 2019-08-07 | 2019-08-19 | 2019-11-19 | 2019-11-29 | 144 Cubits Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Naga City | 302264 | Camarines Sur National High School | NAGA CITY | 3 | 1 | UPGRADING | Batch 3 | 10695533.45 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Naga City | 302265 | Cararayan National High School | NAGA CITY | 3 | 1 | UPGRADING | Batch 1 | 6715416.34 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Sorsogon | 302192 | Bulusan NHS | BULUSAN | 2 | 1 | UPGRADING | Batch 2 | 2841488.36 | 1953845.12 | COMPLETED | 1 | Jan. 26, 2020 | March 24, 2020 |  | 19-07-002-01 |  | July 17, 2019 | July 29, 2019 | August 28, 2019 | Oct. 21, 2019 | SMU Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Sorsogon | 302242 | San Roque NHS | BULUSAN | 2 | 1 | UPGRADING | Batch 3 | 1128354.3 | 885797.77 | COMPLETED | 1 | Feb. 25, 2020 | Feb. 20, 2020 |  | 19-07-002-02 |  | July 17, 2019 | July 29, 2019 | August 19, 2019 | Oct. 21, 2019 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Sorsogon | 302182 | Bagacay NHS | GUBAT | 2 | 1 | UPGRADING | Batch 2 | 1686847.85 | 1342252.59 | COMPLETED | 1 | Feb. 25, 2020 | March 5, 2020 |  |  |  | July 17, 2019 | July 29, 2019 | August 19, 2019 | Oct. 21, 2019 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Sorsogon | 302185 | Bentuco NHS | GUBAT | 2 | 1 | UPGRADING | Batch 3 | 1307787.68 | 1032387.78 | COMPLETED | 1 | Feb. 25, 2020 | March 5, 2020 |  |  |  | July 17, 2019 | July 29, 2019 | August 19, 2019 | Oct. 21, 2019 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region V | Sorsogon | 302189 | Bulacao NHS | GUBAT | 2 | 1 | UPGRADING | Batch 3 | 1502223.77 | 1175612.71 | COMPLETED | 1 | Feb. 25, 2020 | March 5, 2020 |  | 19-07-002-03 |  | July 17, 2019 | July 29, 2019 | August 19, 2019 | Oct. 21, 2019 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Albay | 301810 | Malinao National High School | MALINAO | 1 | 1 |  |  | 5739686.34 |  | COMPLETED | 1 |  |  | Elec2020-RV-Albay-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Albay | 301879 | Sto. Domingo National High School | SANTO DOMINGO (LIBOG) | 1 | 1 |  |  | 4767789.44 |  | COMPLETED | 1 |  |  | Elec2020-RV-Albay-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Albay | 309518 | Kilicao High School | DARAGA | 2 | 1 |  |  | 1994809.2 |  | COMPLETED | 1 |  |  | Elec2020-RV-Albay-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Albay | 500155 | San Agustin Integrated School | LIBON | 3 | 1 |  |  | 2647671.69 |  | COMPLETED | 1 |  |  | Elec2020-RV-Albay-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Norte | 112110 | CAPALONGA CS | CAPALONGA | 1 | 1 | UPGRADING |  | 2122922.96 | PHILIANS ENGINEERING AND CONSTRUCTION SUPPLY | COMPLETED | 1 | 2021-03-18 | 2021-03-18 | ELEC 2020-RV-CAMARINES NORTE -003 |  |  | 2019-11-26 |  | 2019-12-16 | 2020-02-28 | 44098 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Norte | 309614 | Magsaysay National High School | CAPALONGA | 1 | 1 | UPGRADING |  | 1478435.03 | PHILIANS ENGINEERING AND CONSTRUCTION SUPPLY | COMPLETED | 1 | 2021-03-18 | 2021-03-18 | ELEC 2020-RV-CAMARINES NORTE -012 |  |  | 2019-11-26 |  | 2019-12-16 | 2020-02-28 | 44098 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Norte | 309619 | GAWAD KALINGA HS | JOSE PANGANIBAN | 1 | 1 | UPGRADING |  | 1501403.36 | PHILIANS ENGINEERING AND CONSTRUCTION SUPPLY | COMPLETED | 1 | 2021-03-18 | 2021-03-18 | ELEC 2020-RV-CAMARINES NORTE -007 |  |  | 2019-11-26 |  | 2019-12-16 | 2020-02-28 | 44098 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Norte | 112163 | LARAP ES | JOSE PANGANIBAN | 1 | 1 | UPGRADING |  | 1855583.04 | PHILIANS ENGINEERING AND CONSTRUCTION SUPPLY | COMPLETED | 1 | 2021-03-18 | 2021-03-18 | ELEC 2020-RV-CAMARINES NORTE -010 |  |  | 2019-11-26 |  | 2019-12-16 | 2020-02-28 | 44098 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Norte | 301887 | Bagong Silang II NHS | LABO | 1 | 1 | UPGRADING |  | 2241623.93 | PHILIANS ENGINEERING AND CONSTRUCTION SUPPLY | COMPLETED | 1 | 2021-03-18 | 2021-03-18 | ELEC 2020-RV-CAMARINES NORTE -002 |  |  | 2019-11-26 |  | 2019-12-16 | 2020-02-28 | 44098 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Norte | 500156 | Dumagmang IS | LABO | 1 | 1 |  |  | 2822880.47 | RIDERSCORNER CONST AND GEN. MDSE. | COMPLETED | 1 |  |  | ELEC 2020-RV-CAMARINES NORTE -005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Norte | 309611 | Dominador Narido High School | BASUD | 2 | 1 | UPGRADING |  | 1416336.07 | PHILIANS ENGINEERING AND CONSTRUCTION SUPPLY | COMPLETED | 1 | 2021-03-18 | 2021-03-18 | ELEC 2020-RV-CAMARINES NORTE -004 |  |  | 2019-11-26 |  | 2019-12-16 | 2020-02-28 | 44098 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Norte | 301915 | SAN FELIPE NHS | BASUD | 2 | 1 | UPGRADING |  | 2049490.27 | PHILIANS ENGINEERING AND CONSTRUCTION SUPPLY | COMPLETED | 1 | 2021-03-18 | 2021-03-18 | ELEC 2020-RV-CAMARINES NORTE -013 |  |  | 2019-11-26 |  | 2019-12-16 | 2020-02-28 | 44098 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 301942 | Barcelonita Fisheries School | Cabusao | 1 | 1 | CONNECTION TO GRID |  | 2911700.15 | 2910674.68 | COMPLETED | 1 | March 31, 2021 |  | Elec2020-RV-Camarines Sur-015 | 2020-09-023 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | November 27, 2020 | December 1, 2020 | PHILIANS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 301966 | Del Gallego National High School | Del Gallego | 1 | 1 | CONNECTION TO GRID |  | 1592231.34 | 1591647.37 | COMPLETED | 1 | March 31, 2021 |  | Elec2020-RV-Camarines Sur-007 | 2020-09-023 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | November 27, 2020 | December 1, 2020 | PHILIANS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur |  | Del Gallego National High School Annex | Del Gallego | 1 | 1 | CONNECTION TO GRID |  | 1957347.8 | 1955677.95 | COMPLETED | 1 | March 31, 2021 |  | Elec2020-RV-Camarines Sur-008 | 2020-09-023 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | November 27, 2020 | December 1, 2020 | PHILIANS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 302000 | Minalabac NHS | Minalabac | 2 | 1 | CONNECTION TO GRID |  | 3604535.82 | 3602124.45 | COMPLETED | 1 | March 20, 2021 |  | Elec2020-RV-Camarines Sur-016 | 2020-09-024 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | November 27, 2020 | November 20, 2020 | POWER COMPACT |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 302066 | Villamayor HS | Minalabac | 2 | 1 | CONNECTION TO GRID |  | 2503436.38 | 2501044.46 | COMPLETED | 1 | March 20, 2021 |  | Elec2020-RV-Camarines Sur-020 | 2020-09-024 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | November 27, 2020 | November 20, 2020 | POWER COMPACT |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 301952 | Calabanga NHS | Calabanga | 3 | 1 | CONNECTION TO GRID |  | 4114962.51 | 4110870 | COMPLETED | 1 | March 24, 2021 |  | Elec2020-RV-Camarines Sur-032 | 2020-09-025 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | November 27, 2020 | November 24, 2020 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 301953 | Quipayo National High School | Calabanga | 3 | 1 | CONNECTION TO GRID |  | 2447903.07 | 2445470 | COMPLETED | 1 | March 24, 2021 |  | Elec2020-RV-Camarines Sur-028 | 2020-09-025 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | November 27, 2020 | November 24, 2020 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 301995 | Mangayawan High School | Canaman | 3 | 1 | CONNECTION TO GRID |  | 1686327.33 | 1684650 | COMPLETED | 1 | March 24, 2021 |  | Elec2020-RV-Camarines Sur-030 | 2020-09-025 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | November 27, 2020 | November 24, 2020 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 302049 | Sta. Cruz National High School | Canaman | 3 | 1 | CONNECTION TO GRID |  | 1809880.88 | 1808080 | COMPLETED | 1 | March 24, 2021 |  | Elec2020-RV-Camarines Sur-027 | 2020-09-025 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | November 27, 2020 | November 24, 2020 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 112621 | Goa Central School | Goa | 4 | 1 | CONNECTION TO GRID |  | 9179224.88 | 9163937.96 | COMPLETED | 1 | March 20, 2021 |  | Elec2020-RV-Camarines Sur-021 | 2020-09-026 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | November 27, 2020 | November 20, 2020 | 3CA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 112989 | Sagñay CS | SAGÑAY | 4 | 1 |  |  | 6179932.82 |  | COMPLETED | 1 |  |  | Elec2020-RV-Camarines Sur-022 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 113028 | San Jose CS | San Jose | 4 | 1 |  |  | 4907678.18 | 4889355.15 | COMPLETED | 1 | March 20, 2021 |  | Elec2020-RV-Camarines Sur-023 | 2020-09-027 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | November 27, 2020 | November 20, 2020 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 113108 | Tigaon CS | TIGAON | 4 | 1 |  |  | 5426681.526 |  | COMPLETED | 1 |  |  | Elec2020-RV-Camarines Sur-024 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 112318 | Antipolo Elementary School | BAAO | 5 | 1 |  |  | 506762.51 |  | COMPLETED | 1 |  |  | Elec2020-RV-Camarines Sur-034 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 301956 | Caranday HS | BAAO | 5 | 1 |  |  | 1656333.25 |  | COMPLETED | 1 |  |  | Elec2020-RV-Camarines Sur-035 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur |  | Caranday NHS (ANNEX) | Baao | 5 | 1 |  |  | 624105 |  | COMPLETED | 1 |  |  | Elec2020-RV-Camarines Sur-036 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 112344 | Balatan CS | Balatan | 5 | 1 |  |  | 2855369.48 | 2831391.45 | COMPLETED | 1 | 2021-03-20 |  | Elec2020-RV-Camarines Sur-002 | 2020-09-027 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | 2020-11-27 | 2020-11-20 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 302044 | Bato National High School | Bato | 5 | 1 |  |  | 2833256.3 | 2812684.51 | COMPLETED | 1 | 2021-03-20 |  | Elec2020-RV-Camarines Sur-004 | 2020-09-027 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | 2020-11-27 | 2020-11-20 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 112418 | Sta. Justina East ES | Buhi | 5 | 1 |  |  | 1290531.45 | 1263196.55 | COMPLETED | 1 | 2021-03-20 |  | Elec2020-RV-Camarines Sur-033 | 2020-09-027 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | 2020-11-27 | 2020-11-20 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Catanduanes | 309801 | Panganiban NHS (CAIC Compound) | Panganiban | 0 | 1 |  |  | 1267004.79 |  | COMPLETED | 1 |  |  | Elec2020-RV-Catanduanes-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Catanduanes | 302071 | Antipolo NHS | Virac | 0 | 1 |  |  | 1211985.1 |  | COMPLETED | 1 |  |  | Elec2020-RV-Catanduanes-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Iriga City | 302254 | San Antonio NHS | Iriga City | 5 | 1 |  |  | 3028350.73 |  | COMPLETED | 1 |  |  | Elec2020-RV-Iriga City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Legazpi City | 310201 | Arimbay HS | LEGAZPI CITY (Capital) | 2 | 1 |  |  | 898841.35 |  | COMPLETED | 1 |  |  | Electrification2020-RV-Legazpi City-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Legazpi City | 114466 | Bagumbayan CS | LEGAZPI CITY (Capital) | 2 | 1 |  |  | 1161596.4 |  | COMPLETED | 1 |  |  | Electrification2020-RV-Legazpi City-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Legazpi City | 114477 | Cabangan ES | LEGAZPI CITY (Capital) | 2 | 1 |  |  | 858841.35 |  | COMPLETED | 1 |  |  | Electrification2020-RV-Legazpi City-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Legazpi City | 302260 | Cabangan High School | LEGAZPI CITY (Capital) | 2 | 1 |  |  | 898841.35 |  | COMPLETED | 1 |  |  | Electrification2020-RV-Legazpi City-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Legazpi City | 114479 | Ibalon Central School | LEGAZPI CITY (Capital) | 2 | 1 |  |  | 858841.37 |  | COMPLETED | 1 |  |  | Electrification2020-RV-Legazpi City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Ligao City | 301807 | Amtic HS | CITY OF LIGAO | 3 | 1 |  |  | 2155034.09 | 2141863.49 | COMPLETED | 1 | 2021-02-24 |  | Elec2020-RV-Ligao City-005 | 2020-INFRA-07 | 2019-12-03 | 2019-12-11 | 2019-12-23 | 2020-10-12 | 2020-11-20 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Ligao City | 301811 | Barayong HS | CITY OF LIGAO | 3 | 1 |  |  | 2158793.3 | 2147561.84 | COMPLETED | 1 | 2021-02-24 |  | Elec2020-RV-Ligao City-003 | 2020-INFRA-08 | 2019-12-03 | 2019-12-11 | 2019-12-23 | 2020-10-12 | 2020-11-20 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Ligao City | 321701 | Ligao City National Technical Vocational HS | CITY OF LIGAO | 3 | 1 |  |  | 4369183.28 | 4343254.57 | COMPLETED | 1 | 2021-03-13 |  | Elec2020-RV-Ligao City-009 | 2020-INFRA-09 | 2020-02-12 | 2020-02-17 | 2020-03-03 | 2020-11-16 | 2020-12-07 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Ligao City | 321702 | Maonon HS | CITY OF LIGAO | 3 | 1 |  |  | 1426727.79 | 1414844.41 | COMPLETED | 1 | 2021-02-24 |  | Elec2020-RV-Ligao City-002 | 2020-INFRA-06 | 2019-12-03 | 2019-12-11 | 2019-12-23 | 2020-10-12 | 2020-11-20 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Ligao City | 301862 | Paulba NHS | CITY OF LIGAO | 3 | 1 |  |  | 6307451.22 | 6279746.66 | COMPLETED | 1 | 2021-03-13 |  | Elec2020-RV-Ligao City-010 | 2020-INFRA-09 | 2020-02-12 | 2020-02-17 | 2020-03-03 | 2020-11-16 | 2020-12-07 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Masbate | 302111 | Aroroy NHS | AROROY | 2 | 1 |  |  | 3323805.99 |  | COMPLETED | 1 |  |  | Elec2020-RV-Masbate-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Masbate | 309941 | Cristeta Bagano MHS | MOBO | 2 | 1 |  |  | 2061671.6 |  | COMPLETED | 1 |  |  | Elec2020-RV-Masbate-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Masbate | 302112 | Badiang National High School | CATAINGAN | 3 | 1 |  |  | 2928720.02 |  | REVERTED | 0 |  |  | Elec2020-RV-Masbate-001 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | UPGRADING | REVERTED
ELECTRIFICATION 2020 | Region V | Masbate City | 113665 | Amancio Aguilar ES | Masbate City | 2 | 1 |  |  | 1390755.98 |  | COMPLETED | 1 |  |  | Electrification 2020-RV-Masbate City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Masbate City | 321801 | BOLO NATIONAL HIGH SCHOOL | Masbate City | 2 | 1 |  |  | 1486953.42 |  | COMPLETED | 1 |  |  | Electrification 2020-RV-Masbate City-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Masbate City | 113702 | NURSERY ELEMENTARY SCHOOL | Masbate City | 2 | 1 |  |  | 1314418.1 |  | COMPLETED | 1 |  |  | Electrification 2020-RV-Masbate City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Naga City | 310302 | Leon Q. Mercado HS (Formerly CSNHS-Pacol Annex) | NAGA CITY | 3 | 1 |  |  | 2265761.12 |  | TERMINATED | 0.35 |  |  | Elec2020-RV-Naga City-002 | [7 empty] | For termination | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0.35 | 0 |  |  | UPGRADING | TERMINATED
ELECTRIFICATION 2020 | Region V | Naga City | 302269 | Naga City School of Arts and Trades | NAGA CITY | 3 | 1 |  |  | 2002874.73 |  | COMPLETED | 1 |  |  | Elec2020-RV-Naga City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Naga City | 310301 | Tinago National High School | NAGA CITY | 3 | 1 |  |  | 1876681.88 |  | COMPLETED | 1 |  |  | Elec2020-RV-Naga City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Sorsogon | 302198 | Castilla NHS | Castilla | 1 | 1 |  |  | 1901616.96 | 1890066.04 | COMPLETED | 1 | 2021-01-04 |  | Elec2020-RV-Sorsogon-003 | 19-11-008-01 |  |  |  |  | 2020-10-02 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Sorsogon | 302204 | Donsol National Comprehensive HS | Donsol | 1 | 1 |  |  | 3637178.2 | 3625248.47 | COMPLETED | 1 | 2021-01-11 |  | Elec2020-RV-Sorsogon-002 | 19-11-008-01 |  |  |  |  | 2020-10-02 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Sorsogon | 302215 | Irosin North NHS | Irosin | 2 | 1 |  |  | 1754680.59 | 1743618.53 | COMPLETED | 1 | 2021-01-04 |  | Elec2020-RV-Sorsogon-007 | 19-11-008-02 |  |  |  |  | 2020-10-02 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Sorsogon | 302232 | Prieto Diaz National High School | Prieto Diaz | 2 | 1 |  |  | 2955787.8 | 1964635.34 | COMPLETED | 1 | 2025-02-10 | 2025-02-10 | 24-06-003 | 24-06-003 | 2024-06-29 | 2024-07-24 | 2024-08-06 | 2024-08-27 | 2024-11-13 | 3CA Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 4.25 | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Sorsogon City | 114568 | BUENAVISTA ELEMENTARY SCHOOL | SORSOGON WEST | 1 | 1 |  |  | 3266250.7 |  | COMPLETED | 1 |  |  | Elec2020-RV-Sorsogon City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2020 | Region V | Sorsogon City | 310402 | PANLAYAAN TECHNICAL VOCATIONAL SCHOOL | SORSOGON WEST | 1 | 1 |  |  | 5394521.59 |  | COMPLETED | 1 |  |  | Elec2020-RV-Sorsogon City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Tabaco City | 302281 | Bantayan High School | Tabaco City | 1 | 1 |  |  | 2182084.78 | 1818000 | COMPLETED | 1 | 2024-12-23 | 2024-12-23 | Elec2020-RV-Tabaco City-002 |  |  |  | 13/11/2019 |  | 16/12/2020 | RANP Construction Supply and Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 12.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region V | Tabaco City | 302285 | Tabaco National High School | Tabaco City | 1 | 1 |  |  | 1818217.28 | 2182000 | COMPLETED | 1 | 2022-12-23 | 2022-12-23 | Elec2020-RV-Tabaco City-001 |  |  |  | 13/11/2019 |  | 16/12/2020 | RANP Construction Supply and Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 12.22 | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region V | Camarines Norte | 112275 | San Vicente CS | SAN VICENTE | 2 | 1 | Upgrading of Electrical System (Overhead System) | 1 | 6000000 | 3171449.81 | COMPLETED | 1 | October, 2023 | 2023-09-27 | ELEC 2023-RV-CAMARINES NORTE -001 |  | 2023-05-08 | 2023-05-15 | 2023-06-05 | 2023-06-22 | 2023-07-03 | Meltri Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 2023 | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region V | Camarines Sur | 302003 | Victor Bernal Provincial High School | NABUA | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2970850.46 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region V | Catanduanes | 302088 | Gigmoto Rural DHS | GIGMOTO | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2999264.19 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region V | Sorsogon | 302199 | Buenavista National High School, Castilla | CASTILLA | 1st | 1 | Upgrading of Electrical System | 1 | 1851079.02 | 1826821.12 | COMPLETED | 1 | 2024-05-27 | 2024-05-27 | 23-10-001 | 23-10-001 | 2023-10-18 | 2023-10-26 | 2023-11-07 | 2024-01-04 | 2024-01-10 | Araphil Construction and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 5.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region V | Sorsogon | 302202 | Dinapa National High School | CASTILLA | 1st | 1 | Upgrading of Electrical System | 1 | 3132700.94 | 3097564.37 | COMPLETED | 1 | 2024-05-27 | 2024-05-27 | 23-10-001 | 23-10-001 | 2023-10-18 | 2023-10-26 | 2023-11-07 | 2024-01-04 | 2024-01-10 | 144 Cubits Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 5.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region V | Sorsogon | 302219 | Macalaya NHS | CASTILLA | 1st | 1 | Upgrading of Electrical System | 1 | 1802734.29 | 1799378.79 | COMPLETED | 1 | 2024-05-27 | 2024-05-27 | 23-10-001 | 23-10-001 | 2023-10-18 | 2023-10-26 | 2023-11-07 | 2024-01-04 | 2024-01-10 | 144 Cubits Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 5.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region V | Sorsogon | 302226 | Mayon National High School | CASTILLA | 1st | 1 | Upgrading of Electrical System | 1 | 2437103.64 | 2405176.47 | COMPLETED | 1 | 2024-05-27 | 2024-05-27 | 23-10-001 | 23-10-001 | 2023-10-18 | 2023-10-26 | 2023-11-07 | 2024-01-04 | 2024-01-10 | Araphil Construction and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 5.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region V | Sorsogon | 302227 | Milagrosa National High School | CASTILLA | 1st | 1 | Upgrading of Electrical System | 1 | 2246530.38 |  | ONGOING | 0 | [10 empty] | obligated by December 2024; undergone 2 failed biddings | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2023 | Region V | Sorsogon | 302228 | Oras National High School | CASTILLA | 1st | 1 | Upgrading of Electrical System | 1 | 2408030.17 | 2381423.69 | COMPLETED | 1 | 2024-05-27 | 2024-05-27 | 23-10-001 | 23-10-001 | 2023-10-18 | 2023-10-26 | 2023-11-07 | 2024-01-04 | 2024-01-10 | 144 Cubits Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 5.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region V | Sorsogon | 302205 | Banuang Gurang National High School | DONSOL | 1st | 1 | Upgrading of Electrical System | 1 | 2038013.08 |  | ONGOING | 0 | [10 empty] | obligated by December 2024; undergone 2 failed biddings | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2023 | Region V | Sorsogon | 310007 | Biton High School | MAGALLANES | 1st | 1 | Upgrading of Electrical System | 1 | 2785510.24 | 2771906.78 | COMPLETED | 1 | 2024-05-27 | 2024-05-27 | 23-10-001 | 23-10-001 | 2023-10-18 | 2023-10-26 | 2023-11-07 | 2024-01-04 | 2024-01-10 | Araphil Construction and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 5.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region V | Sorsogon | 310006 | Bantayan National High School | PILAR | 1st | 1 | Upgrading of Electrical System | 1 | 1609696.98 | 1585882.05 | COMPLETED | 1 | 2024-05-27 | 2024-05-27 | 23-10-001 | 23-10-001 | 2023-10-18 | 2023-10-26 | 2023-11-07 | 2024-01-04 | 2024-01-10 | Araphil Construction and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 5.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region V | Sorsogon | 302180 | Bayasong National High School | PILAR | 1st | 1 | Upgrading of Electrical System | 1 | 2430063.83 |  | ONGOING | 0 | [10 empty] | obligated by December 2024; undergone 2 failed biddings | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2023 | Region V | Sorsogon | 302230 | Pilar National Comprehensive High School | PILAR | 1st | 1 | Upgrading of Electrical System | 1 | 8331388.84 | 8289992.3 | COMPLETED | 1 | 2024-05-27 | 2024-05-27 | 23-10-001 | 23-10-001 | 2023-10-18 | 2023-10-26 | 2023-11-07 | 2024-01-04 | 2024-01-10 | Araphil Construction and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 5.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region V | Albay | 301816 | Bonga National High School | BACACAY | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 4220515.61 |  | COMPLETED | 1 | [9 empty] | RIDERS CORNER BUILDING AND REALTY DEVELOPMENT CORPORATION | NTP issued & precon was just conducted | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.3241 | 0.6759 |  | 5.25 | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region V | Albay | 301832 | Lacag National High School | DARAGA (LOCSIN) | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 4361764.39 |  | COMPLETED | 1 | [9 empty] | POWER COMPACT ENTERPRISES | NTP issued & precon was just conducted | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.85 | 0.15 |  | 5.25 | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region V | Albay | 111937 | Oas South Central School | OAS | 3rd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 5368731.33 |  | ONGOING | 0.85 | [9 empty] | POWER COMPACT ENTERPRISES | NTP issued & precon was just conducted | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.85 | 0 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region V | Camarines Norte | 301896 | Gonzalo Aler National High School | CAPALONGA | 1st | 1 | Upgrading of Electrical Lines (Overhead System) | 1 | 6222526.26 | 6201814.54 | COMPLETED | 1 | 2024-08-29 | 2024-08-28 | INFRA08-11-2023CN | INFRA08-11-2023CN | 2023-11-07 | 2023-11-15 | 2023-12-06 | 2024-01-16 | 2024-05-31 | Meltri Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region V | Camarines Norte | 301924 | Vicente L. Basit Memorial High School | DAET (Capital) | 2nd | 1 | Upgrading of Electrical Lines (Overhead System) | 1 | 6628846.65 | 6608986.67 | COMPLETED | 1 | 2024-08-29 | 2024-08-29 | INFRA08-11-2023CN | INFRA08-11-2023CN | 2023-11-07 | 2023-11-15 | 2023-12-06 | 2024-01-16 | 2024-05-31 | Meltri Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region V | Camarines Sur | 112458 | Cabusao Central School | CABUSAO | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2836477.79 | 2766050.8708 | COMPLETED | 1 |  |  | 45086 | 2024-05-041 | June 14, 2023-July 3, 2023 | 2023-07-03 | 2023-07-03 | 2024-01-02 | 2024-06-13 | 144 CUBITS BUILDERS AND SUPPLY | ON-GOING | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.9 | 0.1 |  | 5.25 | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region V | Camarines Sur | 309736 | Dr. Nelson A. Mejia HS | LIBMANAN | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3232966.57 | 3173104.1233 | COMPLETED | 1 |  |  | 45086 | 2024-05-041 | June 14, 2023-July 3, 2023 | 2023-07-03 | 2023-07-03 | 2024-01-02 | 2024-06-13 | 144 CUBITS BUILDERS AND SUPPLY | ON-GOING | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.9 | 0.1 |  | 5.25 | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region V | Camarines Sur | 112859 | Ocampo Central School | OCAMPO | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3583352.2 | 3497369.19 | ONGOING | 0.9 |  |  | 45086 | 2024-05-042 | June 14, 2023-July 3, 2023 | 2023-07-03 | 2023-07-03 | 2023-12-29 | 2024-06-11 | 3CA BUILDERS CORPORATION | ON-GOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.9 | 0 |  |  | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region V | Camarines Sur | 301978 | Guijalo National High School | CARAMOAN | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2318362.34 | 2252529.88 | ONGOING | 0.9 |  |  | 45086 | 2024-05-042 | June 14, 2023-July 3, 2023 | 2023-07-03 | 2023-07-03 | 2023-12-29 | 2024-06-11 | 3CA BUILDERS CORPORATION | ON-GOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.9 | 0 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region V | Camarines Sur | 301976 | Pinaglabanan NHS | GOA | 4th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3286760.16 | 3240369.6 | ONGOING | 0.95 |  |  | 45086 | 2024-05-042 | June 14, 2023-July 3, 2023 | 2023-07-03 | 2023-07-03 | 2023-12-29 | 2024-06-11 | 3CA BUILDERS CORPORATION | ENERGIZED, READY FOR FINAL INSPECTION | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.9 | 0.05 |  |  | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region V | Camarines Sur | 112320 | Baao West CS | BAAO | 5th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2844612.64 | 2493603.89 | ONGOING | 0.95 |  |  | 45086 | 45416 | June 14, 2023-July 3, 2023 | 2023-07-03 | 2023-07-03 | 2023-12-29 | 2024-06-11 | 3CA BUILDERS CORPORATION | ENERGIZED, READY FOR FINAL INSPECTION | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.9 | 0.05 |  |  | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region V | Catanduanes | 302074 | Bato Rural Development High School | BATO | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 6758699.45 | 6711962.92 | COMPLETED | 1 | 2024-11-04 | 2024-10-04 | [7 empty] | Hi-Tone Const. & Dev. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region V | Iriga City | 302251 | Rinconada National Technical Vocational School | Rinconada National Technical Vocational School - Main Campus | 5th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 11786820.47 | 10593622.98 | ONGOING | 0.95 | 2024-12-24 |  | 2024-2-8-PR-026 | INFRA-24-06-06-002 | February 20, 2024 - March 12, 2024 | 2024-02-28 | 2024-03-12 | 2024-03-26 | 2024-06-18 | ACF Power Enterprises | On-going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.95 | 0 |  |  | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region V | Legaspi City | 114458 | Bogna Elementary School | LEGAZPI CITY (Capital) | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2496770.75 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 12.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region V | Ligao City | 111821 | Ligao East CS | CITY OF LIGAO | 3rd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 5020227.53 | 5000742.18 | COMPLETED | 1 | 2024-09-30 |  | 2023-INFRA-02 | 2023-INFRA-02 | 2024-11-20 | 2024-12-04 | 2023-12-18 | 2024-05-15 | 2024-06-03 | La Abel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.95 | 0.05 |  | 5.25 | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region V | Masbate | 113763 | Dalakit ES | MONREAL | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3990123.74 | 3976095.9 | COMPLETED | 1 | 2024-10-03 |  | INFRA 2023 - 12 -004 | INFRA - 2024 - 002 | 2023-12-18 | 2023-12-27 | 2024-01-08 | 2024-05-09 | 2024-05-21 | EJ CANTORIA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.93 | 0.07 |  | 5.25 | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region V | Masbate | 113770 | Monreal Central School | MONREAL | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3990123.74 | 3976095.9 | COMPLETED | 1 | 2024-10-03 |  | INFRA 2023 - 12 -004 | INFRA - 2024 - 003 | 2023-12-18 | 2023-12-27 | 2024-01-08 | 2024-05-09 | 2024-05-21 | EJ CANTORIA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.9 | 0.1 |  | 5.25 | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region V | Masbate | 113876 | San Fernando CS | SAN FERNANDO | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2527435.61 | 2509991.4 | COMPLETED | 1 | 2024-10-03 |  | INFRA 2023 - 12 -004 | INFRA - 2024 - 004 | 2023-12-18 | 2023-12-27 | 2024-01-08 | 2024-05-09 | 2024-05-21 | EJ CANTORIA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.94 | 0.06 |  | 5.25 | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region V | Masbate | 113897 | Piña Elementary School | SAN JACINTO | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2060087.73 | 2049343.8 | COMPLETED | 1 | 2024-10-03 |  | INFRA 2023 - 12 -004 | INFRA - 2024 - 005 | 2023-12-18 | 2023-12-27 | 2024-01-08 | 2024-05-09 | 2024-05-21 | EJ CANTORIA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.94 | 0.06 |  | 5.25 | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region V | Masbate | 302167 | San Jacinto National High School | SAN JACINTO | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 8167511.59 | 8135502.9 | ONGOING | 0.9 | 2024-10-03 |  | INFRA 2023 - 12 -004 | INFRA - 2024 - 006 | 2023-12-18 | 2023-12-27 | 2024-01-08 | 2024-05-09 | 2024-05-21 | EJ CANTORIA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.7 | 0.2 |  |  | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region V | Masbate City | 321802 | Usab High School | CITY OF MASBATE (Capital) | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3500000 | 3432938.53 | COMPLETED | 1 | 2024-09-11 |  | 2024-RV-MASBATE CITY-001 | 2024-RV-MASBATE CITY-001 | 2024-02-07 | 2024-02-21 | 2024-03-04 | 2024-03-11 | 2024-06-14 | 144 CUBITS BUILDERS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 11.24 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2024 | Region V | Naga City | 114500 | Naga Central School I | NAGA CITY | 3rd | 1 | Upgrading Electrical System On Grid Schools | 1 | 5983578.39 | 5275924.3 | COMPLETED | 1 |  |  | 2023-11-001 | 2024-05-002 |  |  |  |  | 2024-05-28 | Jurassic Construction and Supply | On-Going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.95 | 0.05 |  | 5.25 | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region V | Sorsogon | 302240 | San Juan National High School | CASIGURAN | 1st | 1 | Upgrading of Electrical System | 1 | 2338851.59 | 1964635.34 | COMPLETED | 1 | 2025-02-10 | 2025-02-10 | 24-06-003 | 24-06-003 | 2024-06-29 | 2024-07-24 | 2024-08-06 | 2024-08-27 | 2024-11-13 | 3CA Builders Corporation | For NOA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.8 | 0.2 |  | 5.25 | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region V | Sorsogon | 302214 | Gubat National High School | GUBAT | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 5881147.23 | 4976747.14 | COMPLETED | 1 | 2025-04-25 | 2025-04-25 | 24-06-003 | 24-06-003 | 2024-06-29 | 2024-07-24 | 2024-08-06 | 2024-08-27 | 2024-12-27 | 144 Cubits Builders and Supply | RTA submitted on September 20, 2024 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 | 1 |  | 5.25 | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region V | Sorsogon City | 302279 | Sorsogon National High School | CITY OF SORSOGON (Capital) | 1st | 1 | Upgrading of Electrical System | 1 | 5445327.45 | 5394797.8 | COMPLETED | 1 | 2024-10-01 | 2024-10-30 | 001-24-INFRA-BEFF ELECTRIFICATION | 008-2024 | 2024-01-10 | 2024-01-18 | 2024-01-30 | 2024-05-18 | 2024-05-27 | Araphil Construction & Development Corporation | Short of Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region V | Tabaco City | 302282 | San Antonio National High School, Tabaco | CITY OF TABACO | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 5776290.29 | 3636154.29 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.9061 | 0.0939 |  | 5.25 | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region V | Tabaco City | 302283 | San Lorenzo National High School | CITY OF TABACO | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 6944292.01 | 4641484 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.9216 | 0.0784 |  | 5.25 | UPGRADING | ONGOING