## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | TOTAL NO. OF BUILDINGS | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of bldg Reverted | No. of bldg Not yet started | No. of bldg Under Procurement | No. of bldg On Going | No. of bldg Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | Implementing Unit | BBM TERM COMPLETED | AWAITING SUBMISSION OF RTA | batch of suballotment | Unnamed: 45
GABALDON 2020 | Region VIII | Baybay City | 121102 | Baybay II Central School | CITY OF BAYBAY | 5 | 1 | 7 | 1 | Rehabilitation of Gabaldon Building | 8001304.06 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VIII | Baybay City | 121125 | Plaridel Central School | CITY OF BAYBAY | 5 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 4824381.51 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VIII | Biliran | 120758 | Almeria CS | ALMERIA | 0 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 4140117.82 | 1 | 4108000 | Completed | 1 | [9 empty] | J. Custorio Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VIII | Biliran | 120758 | Almeria CS (Balwarte Camp) | ALMERIA | 0 |  | 2 | 1 | Rehabilitation of Gabaldon Building | 4128547.93 | 1 | 4108000 | Completed | 1 | [9 empty] | J. Custorio Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VIII | Catbalogan City | 123416 | Catbalogan V CES (Mercedes ES) | CITY OF CATBALOGAN (Capital) | 2 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 1205717.66 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VIII | Leyte | 121154 | Burauen North Central School | BARAUEN | 2 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 8204817.56 | 1 | 8154000 | Completed | 1 | [9 empty] | J. Custorio Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VIII | Leyte | 121685 | Waterloo Elementary School | MATALOM | 5 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 3610927.59 | 1 |  | Completed | 1 | [10 empty] | SUSPENDED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VIII | Maasin | 122174 | San Rafael Elementary School | CITY OF MAASIN (Capital) | 0 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 2101688.56 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VIII | Samar (Western Samar) | 123374 | Literon Elementary School | CALBIGA | 2 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 1037799.8 | 1 |  | Completed | 1 | [10 empty] | FOR AWARD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VIII | Samar (Western Samar) | 303643 | Zumarraga NHS | ZUMARRAGA | 2 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 2751335.62 | 1 |  | Completed | 1 | [10 empty] | FOR AWARD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VIII | Southern Leyte | 122074 | Mahalo Elementary School | Anahawan | 0 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 2714955.1855 | 1 | 2900170.11 | Completed | 1 | [9 empty] | AAVB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VIII | Southern Leyte | 122020 | Sta. Cruz Elementary School | Bontoc | 0 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 2750323.3 | 1 |  | Completed | 1 | [10 empty] | SUSPENDED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VIII | Southern Leyte | 122080 | Libagon Central School | Libagon | 0 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 2314497.8116 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VIII | Southern Leyte | 122185 | Ichon Elementary School | Macrohon | 0 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 2055875.565 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VIII | Southern Leyte | 122213 | San Vicente Elementary School | Malitbog | 0 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 6301644.6507 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VIII | Southern Leyte | 122239 | Pintuyan Central School | Pintuyan | 0 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 2459716.8771 | 1 | 2492209.98 | Completed | 1 | [9 empty] | AAVB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VIII | Southern Leyte | 122252 | San Juan Central ElementarySchool | San Juan (Cabalian) | 0 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 3133535.5186 | 1 | 2900170.11 | Completed | 1 | [9 empty] | AAVB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2021 | Region VIII | Baybay City | 121082 | Gaas Elementary School | CITY OF BAYBAY | 5 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 3661725 | 1 | 3585000 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Regional Office | CY 2022 |  |  | COMPLETED
GABALDON 2021 | Region VIII | Eastern Samar | 122484 | Gen. MacArthur Central Elementary School | GENERAL MACARTHUR | 0 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 4910770 | 1 |  | COMPLETED | 1 | 2022-01-15 | 2022-01-15 | 21-04-262 | 012-2021 | 2021-05-15 | 2021-04-21 | 2021-06-23 | 2021-09-09 | 2021-09-17 | QCC Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Regional Office |  |  |  | COMPLETED
GABALDON 2021 | Region VIII | Eastern Samar | 122758 | Sulat Central Elementary School | SULAT | 0 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 5510971 | 1 |  | COMPLETED | 1 | 2022-01-15 | 2022-01-15 | 21-04-263 | 012-2022 | 2021-05-15 | 2021-04-21 | 2021-06-23 | 2021-09-09 | 2021-09-18 | QCC Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Regional Office |  |  |  | COMPLETED
GABALDON 2023 | Region VIII | Biliran | 120770 | TABUNAN ES | ALMERIA | 0 | 1 | 1 | 1 | Restoration & Conservation of Gabaldon Building | 2809414.04 | 1 | 659450.8 | Completed | 1 | 12/13/2023 | 12/13/2023 | 2024INFRA-Repair-008 | CY 2023 REPAIR/REHAB OF GABALDON BLDG-01 | 2023-02-06 | 6/26/2023 | 6/26/2023 | 7/20/2023 | 2023-09-08 | MB ANG CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 1.24 | Division Office | cy 2024 |  |  | Completed
GABALDON 2023 | Region VIII | Eastern Samar | 122775 | Taft Central Elementary School | TAFT | 0 | 1 | 5 | 1 | Restoration & Conservation of Gabaldon Building | 6520393.33 | 1 |  | completed | 1 | ################ | 9/30/2023 | CY2023-GAB-B1-LOT1 | CY2023-GAB-B1-LOT1 | 3/29/2023 | 2023-03-05 | 2023-03-05 | ########### | 5/26/2023 | Vhits D.G Builders & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 12.23 | Division Office | CY 2023 |  |  | completed
GABALDON 2023 | Region VIII | Samar (Western Samar) | 123655 | Pagsanghan Central Elementary School | PAGSANGHAN | 1 | 1 | 7 | 1 | Restoration & Conservation of Gabaldon Building | 14000000 | 1 | 13951642.86 | completed | 1 | 1/15/2024 | 2/25/2024 | CY2023GABLOT1 | 2023-018 | 2023-06-04 | 4/28/2023 | 4/28/2023 | ########### | 6/23/2023 | MJM BUILDERS | WITH TIME EXTENSIONS AND WITH LIQUIDATED DAMAGES | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 6.24 | Division Office |  |  |  | completed
GABALDON 2023 | Region VIII | Southern Leyte | 122230 | Triana Elementary School | LIMASAWA | 1 | 1 | 5 | 1 | Restoration & Conservation of Gabaldon Building | 6428742.23 | 1 | 6302256.68 | Completed | 1 | 1/25/2024 | 2024-12-01 | CY2023-Gabaldon-L1 | CY2023-Gabaldon-L1 | 4/17/2023 | 2023-09-05 | 2023-09-05 | 7/17/2023 | 2023-03-08 | QCC Construction and Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 3.24 | Division Office | cy 2024 |  |  | Completed
GABALDON 2024 | Region VIII | Borongan City | 122387 | San Saturnino Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 6331343.3 | 1 | 6326335.72 | COMPLETED | 1 | 11/18/2024 | 11/15/2024 | CY 2024 GABALDON | CY 2024 GABALDON | 2024-11-03 | 3/20/2024 | 2024-02-04 | 2024-08-04 | 7/17/2024 | LEXBUILD CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  | 5.25 | Division Office |  |  | 5 | not yet started
GABALDON 2024 | Region VIII | Eastern Samar | 122524 | Guiuan East Central School | GUIUAN | Lone | 1 | 5 | 1 | Conservation and Restoration of Gabaldon School Building | 5974124.58 | 1 | 5946102.72 | Ongoing | 0.7 | 2024-01-11 |  | CY2024-GABALDON-L1 | CY2024-GABALDON-L1 | 2024-03-03 | 2024-11-03 | 3/25/2024 | 2024-10-07 | 7/27/2024 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.7 | 0 |  |  | Division Office |  |  | 4 | Ongoing
GABALDON 2024 | Region VIII | Leyte | 121004 | Tinag-an Elementary School | ALBUERA | 4th | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 5036203.53 | 1 | 3878143.65 | Ongoing | 0.75 | 2025-04-02 |  | CY 2024 BEFF_Conservation and Restoration of Gabaldon School Building Program-(RVIII)-LEYTE-Lot-1 | CY 2024 BEFF_Conservation and Restoration of Gabaldon School Building Program-(RVIII)-LEYTE-Lot-1 | 2024-03-04 | 4/15/2024 | 4/29/2024 | 6/21/2024 | 2024-01-08 | SAINT JOSPEH CONSTRUCTION | with time extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.6 | 0.15 |  |  | Division Office |  |  | 5 | Ongoing
GABALDON 2024 | Region VIII | Leyte | 121446 | Matlang Elementary School | ISABEL | 4th | 1 | 3 | 1 | Conservation and Restoration of Gabaldon School Building | 4010447.89 | 1 | 3958128.42 | COMPLETED | 1 | 12/30/2024 | 12/30/2024 | CY 2024 BEFF_Conservation and Restoration of Gabaldon School Building Program-(RVIII)-LEYTE-Lot-2 | CY 2024 BEFF_Conservation and Restoration of Gabaldon School Building Program-(RVIII)-LEYTE-Lot-2 | 2024-03-04 | 4/15/2024 | 4/29/2024 | 6/21/2024 | 7/26/2024 | FOUR K BUILDERS & CONST. SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0.95 | 0.05 |  | 5.25 | Division Office |  |  | 5 | Ongoing
GABALDON 2024 | Region VIII | Maasin City | 122177 | Tomas Oppus Pilot School (TOPS) | CITY OF MAASIN (Capital) | 1st | 1 | 7 | 1 | Conservation and Restoration of Gabaldon School Building | 8601473.61 | 1 | 5962743.44 | Ongoing | 0.35 | 7/21/2025 |  | INFRA-2024-04 | INFRA-2024-04 | 2024-11-07 | 7/19/2024 | 7/31/2024 | 9/25/2024 | 2025-08-01 | VHITS D.G. BUILDERS & ENTERPRISES | Ongoing | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.15 | 0.2 |  |  | Division Office |  |  | 10 | Ongoing