## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No of Sites | SCOPE OF WORK | Batch | Project Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Site Reverted | No. of Site Not yet started | No. of Site Under Procurement | No. of Site On Going | No. of Site Completed | No. of Site Terminated | WITH TRANSFOPMER (Y/N) | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | CATEGORY 2 | Unnamed: 43
ELECTRIFICATION 2017 | Region X | Bukidnon | 199541 | Don Antonio O. Floirendo Sr. Primary School | QUEZON | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 299968.2 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | NO TAKER | 0 | 0 |  |  | ENERGIZATION | REVERTED
ELECTRIFICATION 2017 | Region X | Camiguin | 315003 | Mahinog National High School II | MAHINOG | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 276066 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region X | Camiguin | 315004 | Bugang Integrated School | SAGAY | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 286844.51 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region X | Lanao del Norte | 127213 | Gadongan PS | TAGOLOAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1189918.94 | 1183082.61 | COMPLETED | 1 | 2018-03-08 | April 18.2018 | [7 empty] | GREEN BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region X | Lanao del Norte | 127215 | Lininding ES | TAGOLOAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2479096.78 | 2473089.45 | COMPLETED | 1 | 2018-03-08 | April 24.2018 | [7 empty] | GREEN BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2017 | Region X | Malaybalay City |  | Senior High within Casisang CES | Malaybalay City | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 692717.13 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region X | Bukidnon | 303968 | Libona NHS | LIBONA | 1 | 1 | UPGRADING | 1 | 421084.28 | 334843.13 | COMPLETED | 1 | 2022-12-29 | 2022-10-13 | 07-2018 | 28-2018 | 2018-08-07 | 2018-08-08 | 2018-08-20 | 2018-08-30 | 2018-09-10 | Digos Constrak Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Bukidnon | 314901 | Dalirig NHS | MANOLO FORTICH | 1 | 1 | UPGRADING | 1 | 591286.35 | 588344.62 | COMPLETED | 1 | 2018-10-28 |  | 07-2018 | 29-2018 | 2018-08-08 | 2018-08-08 | 2018-08-20 | 2018-08-30 | 2018-09-10 | Digos Constrak Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Bukidnon | 314903 | San Vicente NHS | SUMILAO | 1 | 1 | UPGRADING | 1 | 318600.41 | 285324.63 | COMPLETED | 1 | 2018-11-12 |  | 07-2018 | 30-2018 | 2018-08-09 | 2018-08-08 | 2018-08-20 | 2018-08-30 | 2018-09-10 | Digos Constrak Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Bukidnon | 303987 | Talakag NHS | TALAKAG | 1 | 1 | UPGRADING | 1 | 946827.8 | 753354.56 | COMPLETED | 1 | 2018-10-28 |  | 07-2018 | 31-2018 | 2018-08-10 | 2018-08-08 | 2018-08-20 | 2018-08-30 | 2018-09-10 | Digos Constrak Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Bukidnon | 314908 | Cabulohan-Paradise NHS - Townsite Annex | CABANGLASAN | 2 | 1 | UPGRADING | 1 | 624418.88 | 558710.14 | ONGOING | 0.95 | 2024-06-15 |  | 07-2018 | 32-2018 | 2018-08-11 | 2018-08-08 | 2018-08-20 | 2018-08-30 | 2018-09-10 | Digos Constrak Corporation | Waiting for schedule of energization from Electric Coop (BUSECO) | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Y | 0.95 | 0 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2018 | Region X | Bukidnon |  | Lantapan Stand-Alone SHS | LANTAPAN | 2 | 1 | UPGRADING | 1 | 1811677.5 | 1622321.51 | COMPLETED | 1 | 2022-12-29 |  | 07-2018 | 33-2018 | 2018-08-12 | 2018-08-08 | 2018-08-20 | 2018-08-30 | 2018-09-10 | Digos Constrak Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Bukidnon | 314907 | Halapitan NHS - Little Baguio Annex | SAN FERNANDO | 2 | 1 | UPGRADING | 1 | 564410.03 | 504908.55 | ONGOING | 0.9 | 2024-07-15 |  | 07-2018 | 34-2018 | 2018-08-13 | 2018-08-08 | 2018-08-20 | 2018-08-30 | 2018-09-10 | Digos Constrak Corporation | Materials for inspection of electric coop; Work is halted due to financial constraint of contactor | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Y | 0.9 | 0 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2018 | Region X | Bukidnon | 303948 | Bocboc NHS | DON CARLOS | 3 | 1 | UPGRADING | 2 | 1377615.56 | 1233103.87 | ONGOING | 0.9 | 2024-06-15 |  | 08-2018 | 35-2018 | 19 Sep 18 | 2018-08-08 | 2018-08-20 | 2018-08-30 | 2018-09-10 | DIGOS CONSTRAK CORPORATION | Materials for inspection of Electric coop; BOM from Electric Cooperative for revision; Current transformer and KWhr Meter for purchasing of the contractor | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Y | 0.9 | 0 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2018 | Region X | Cagayan de Oro City | 304106 | Bayabas National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING | 2 | 2935952.5 | 2911668.44 | COMPLETED | 1 |  |  |  |  | 2018-07-31 | 2018-08-08 | 2018-08-29 |  |  | BREMA CONSTRUCTON |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Cagayan de Oro City | 304108 | Bulua NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING | 1 | 1012007.31 | 989436.07 | COMPLETED | 1 |  |  |  | 208-011 | 2018-05-04 | 2018-05-16 | 2018-06-03 | 2018-06-07 | 2018-07-03 | BRIMA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Cagayan de Oro City | 315403 | Cagayan de Oro NHS - Balulang Annex | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING | 1 | 3465288.73 | 3379251.62 | COMPLETED | 1 |  |  |  | 208-012 | 2018-05-04 | 2018-05-16 | 2018-06-03 | 2018-06-07 | 2018-07-03 | BRIMA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Cagayan de Oro City | 304112 | Carmen National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING | 2 | 2496894.65 | 2473358.01 | COMPLETED | 1 |  |  |  |  | 2018-07-31 | 2018-08-08 | 2018-08-29 |  |  | BREMA CONSTRUCTON |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Cagayan de Oro City | 304125 | Taglimao National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1534398.56 | 1516689.22 | COMPLETED | 1 |  |  |  |  | 2018-07-31 | 2018-08-08 | 2018-08-29 |  |  | BREMA CONSTRUCTON |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Cagayan de Oro City | 304104 | Agusan National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING | 1 | 4433497.52 | 4323276.69 | COMPLETED | 1 |  |  |  | 208-013 | 2018-05-04 | 2018-05-16 | 2018-06-03 | 2018-06-07 | 2018-07-03 | BRIMA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Cagayan de Oro City | 315401 | Balubal NHS | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING | 1 | 3049898.1 | 2973777.69 | COMPLETED | 1 |  |  |  | 208-014 | 2018-05-04 | 2018-05-16 | 2018-06-03 | 2018-06-07 | 2018-07-03 | BRIMA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Cagayan de Oro City | 304115 | Gusa NHS-Cugman Annex | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING | 1 | 1642134.89 | 1601120.29 | COMPLETED | 1 |  |  |  | 208-011 | 2018-05-04 | 2018-05-16 | 2018-06-03 | 2018-06-07 | 2018-07-03 | BRIMA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Cagayan de Oro City | 304118 | Lapasan National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING | 1 | 1550067.26 | 1511066.11 | COMPLETED | 1 |  |  |  | 208-011 | 2018-05-04 | 2018-05-16 | 2018-06-03 | 2018-06-07 | 2018-07-03 | BRIMA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Camiguin | 303989 | Bonbon NHS | CATARMAN | 0 | 1 | UPGRADING | 1 | 1419115.71 |  | COMPLETED | 1 |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Camiguin | 303990 | Camiguin NHS | CATARMAN | 0 | 1 | UPGRADING | 1 | 8681319.02 |  | COMPLETED | 1 |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Camiguin | 303992 | Lawigan-Bura National High School | CATARMAN | 0 | 1 | UPGRADING | 1 | 2682276.05 |  | COMPLETED | 1 |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Camiguin | 303991 | Guinsiliban National High School | GUINSILIBAN | 0 | 1 | UPGRADING | 1 | 3019910.32 |  | COMPLETED | 1 |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Camiguin | 315001 | Maac National High School | GUINSILIBAN | 0 | 1 | UPGRADING | 1 | 4812666.4 |  | COMPLETED | 1 |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Camiguin | 303993 | SIXTO A. ABAO NHS | MAHINOG | 0 | 1 | UPGRADING | 1 | 6434149.04 |  | COMPLETED | 1 |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Camiguin | 303994 | Mambajao NHS | MAMBAJAO (Capital) | 0 | 1 | UPGRADING | 1 | 13653985.18 |  | COMPLETED | 1 |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Camiguin | 303996 | Tupsan NHS | MAMBAJAO (Capital) | 0 | 1 | UPGRADING | 1 | 2773140.02 |  | COMPLETED | 1 |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Camiguin | 303997 | Yumbing National High School | MAMBAJAO (Capital) | 0 | 1 | UPGRADING | 1 | 5469760.43 |  | COMPLETED | 1 |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Camiguin | 303995 | Eulalio U. Pabillore National High Sschool | SAGAY | 0 | 1 | UPGRADING | 1 | 4193168.3 |  | COMPLETED | 1 |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | El Salvador | 304065 | Cogon NHS | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | 2 | 3640724.85 | 3602767.26 | COMPLETED | 1 | 2018-11-05 |  |  | 2018-04-0087 | 2018-04-28 | 2018-05-15 | 2018-06-05 | 2018-06-20 | 2018-06-28 | Joash AR Engineering |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | El Salvador | 315305 | Molugan NHS | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | 1 | 2639714.7 | 2612299.53 | COMPLETED | 1 | 2018-11-05 |  |  | 2018-04-0087 | 2018-04-28 | 2018-05-15 | 2018-05-05 | 2018-06-20 | 2018-06-28 | JOASH AR ENG'G |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Gingoog City | 304136 | Jacinto D. Malimas Sr. National High School | GINGOOG CITY | 1 | 1 | UPGRADING | 2 | 1235494.03 |  | COMPLETED | 1 | 2018-11-05 |  |  |  |  | 2018-05-28 | 2018-06-03 | 2018-07-27 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Gingoog City | 315502 | Odiongan NHS - Talisay NHS Annex | GINGOOG CITY | 1 | 1 | UPGRADING | 2 | 1335344.6 |  | COMPLETED | 1 | 2018-11-05 |  |  |  |  | 2018-05-28 | 2018-06-03 | 2018-07-27 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Lanao del Norte | 304012 | MATUNGAO NATIONAL HIGH SCHOOL | MATUNGAO | 1 | 1 | UPGRADING | 2 | 1575318.14 | 1550017.52 | COMPLETED | 1 | 2018-12-13 |  |  |  | 2018-06-08 | 2018-06-18 | 2018-07-03 | 2018-07-11 | 2018-07-18 | GREEN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Lanao del Norte | 304018 | Pantao Ragat Agro-Ind. HS | PANTAO RAGAT | 2 | 1 | UPGRADING | 2 | 2290379.34 | 2233156.57 | COMPLETED | 1 | 2018-12-13 |  |  |  | 2018-06-08 | 2018-06-18 | 2018-07-03 | 2018-07-11 | 2018-07-18 | GREEN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Malaybalay City | 325505 | Apo Macote NHS | CITY MALAYBALAY (Capital) | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 395210.89 | 395210.89 | COMPLETED | 1 |  |  |  |  | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | MEGABLUE KONSTRAK CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2018 | Region X | Malaybalay City | 303946 | Bangcud NHS | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING | 1 | 3156028.23 | 3156028.23 | COMPLETED | 1 | 2024-06-01 |  | 02-INFRA-2018 | 02-INFRA-2018 | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | MEGABLUE KONSTRAK CORPORATION | Complete Materials and installation onsite, FOR ENERGIZATION-ready for submission of turn-on application | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 12.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Malaybalay City | 303950 | Bukidnon NHS | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING | 1 | 3467155.4 | 3467155.4 | COMPLETED | 1 | 2024-06-01 |  | 02-INFRA-2018 | 02-INFRA-2018 | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | MEGABLUE KONSTRAK CORPORATION | Complete Materials and installation onsite, FOR ENERGIZATION-ready for submission of turn-on application | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 12.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Malaybalay City | 500245 | Can-ayan IS | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING | 1 | 473176.9 | 473176.9 | COMPLETED | 1 |  |  |  |  | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | MEGABLUE KONSTRAK CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Malaybalay City | 314914 | Casisang NHS | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING | 1 | 469166.48 | 469166.48 | COMPLETED | 1 |  |  |  |  | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | MEGABLUE KONSTRAK CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Malaybalay City | 303973 | Managok NHS | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING | 1 | 3568524.3986 | 3568524.3986 | COMPLETED | 1 | 2022-12-29 |  | 02-INFRA-2018 | 02-INFRA-2018 | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | DIGOS CONSTRAK CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Malaybalay City | 314920 | Managok NHS - Miglamin Annex | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING | 1 | 314861.94 | 314861.94 | COMPLETED | 1 | 2024-06-15 |  | 02-INFRA-2018 | 02-INFRA-2018 | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | DIGOS CONSTRAK CORPORATION | Complete Materials and schedule for coop re-installation of missing transformer onsite by jaunary, FOR ENERGIZATION-ready for submission of turn-on application; For application of ELectrical Permit from the City Engineer's Office, ELectrical Plan for signature of PEE. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 4.25 | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Malaybalay City | 314905 | Silae NHS - Annex St. Peter | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING | 1 | 355302.54 | 355302.54 | COMPLETED | 1 | 2024-06-15 |  | 02-INFRA-2018 | 02-INFRA-2018 | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | DIGOS CONSTRAK CORPORATION | Complete Materials and installation onsite, FOR ENERGIZATION-ready for submission of turn-on application; Documentary requirements for application not yet complied | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Occidental | 304024 | Aloran Trade HS | ALORAN | 1 | 1 | UPGRADING | 2 | 2803883.95 | 2786248.77 | COMPLETED | 1 | 2018-12-05 |  |  | 013-2018 | 2018-04-27 |  | 2018-05-10 | 2018-06-08 | 2018-07-31 | JEFY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Occidental | 304037 | Jimenez NCHS | JIMENEZ | 1 | 1 | UPGRADING | 2 | 1149848.54 | 1140754.84 | COMPLETED | 1 | 2018-12-05 |  |  | 012-2018 | 2018-04-27 |  | 2018-05-10 | 2018-06-08 | 2018-07-31 | JEFY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Occidental | 315207 | Sibugon IS | LOPEZ JAENA | 1 | 1 | UPGRADING | 2 | 3088427.99 | 3059883.65 | COMPLETED | 1 | 2018-12-05 |  |  | 016-2018 | 2018-04-27 |  | 2018-05-10 | 2018-06-08 | 2018-08-03 | MAQUESERQ CONSTRUCTION & GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Oriental | 304077 | Kinoguitan NAHS | KINOGUITAN | 1 | 1 | UPGRADING | 1 | 5246873.25 | 481205.07 | COMPLETED | 1 |  |  |  |  | 2018-07-23 | 2018-07-31 | 2018-08-14 |  | 2018-10-30 | Meter King |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Oriental | 304089 | Medina NCHS | MEDINA | 1 | 1 | UPGRADING | 1 | 5813168.42 | 5007063.86 | COMPLETED | 1 |  |  |  |  | 2018-06-25 | 2018-07-03 | 2018-07-17 |  | 2018-09-10 | Meter King |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Oriental | 304096 | Salay NHS | SALAY | 1 | 1 | UPGRADING | 1 | 5713806 | 5174548.22 | COMPLETED | 1 |  |  |  |  | 2018-07-23 | 2018-07-31 | 2018-08-14 |  | 2018-10-30 | Meter King |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Oriental | 304093 | Talisayan NHS | TALISAYAN | 1 | 1 | UPGRADING | 1 | 5439018.9 | 4726011.85 | COMPLETED | 1 |  |  |  |  | 2018-06-25 | 2018-07-03 | 2018-07-17 |  | 2018-09-10 | Meter King |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Oriental | 304073 | Jasaan NHS | JASAAN | 2 | 1 | UPGRADING | 1 | 5740187.25 | 5314879.97 | COMPLETED | 1 |  |  |  |  | 2018-07-23 | 2018-07-31 | 2018-08-14 |  | 2018-10-30 | Meter King |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Oriental | 315307 | Manticao NHS | MANTICAO | 2 | 1 | UPGRADING | 1 | 2269686.96 | 2014354.88 | COMPLETED | 1 |  |  |  |  | 2018-07-23 | 2018-07-31 | 2018-08-14 |  | 2018-10-30 | Meter King |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Oriental | 315303 | Naawan NHS | NAAWAN | 2 | 1 | UPGRADING | 1 | 2304636.87 | 2035580.88 | COMPLETED | 1 |  |  |  |  | 2018-07-23 | 2018-07-31 | 2018-08-14 |  | 2018-10-30 | Meter King |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Oriental | 341230 | Naawan SHS (Maputi ES Campus) | NAAWAN | 2 | 1 | UPGRADING | 1 | 2219343.3 | 1957650.56 | COMPLETED | 1 |  |  |  |  | 2018-07-23 | 2018-07-31 | 2018-08-14 |  | 2018-10-30 | Meter King |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Oriental | 304102 | Tagoloan NHS | TAGOLOAN | 2 | 1 | UPGRADING | 1 | 4013228.99 | 3571331.04 | COMPLETED | 1 |  |  |  |  | 2018-06-25 | 2018-07-03 | 2018-07-17 |  | 2018-09-06 | Meter King |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Oroquieta City | 304045 | Misamis Occidental NHS | OROQUIETA CITY (Capital) | 1 | 1 | UPGRADING | 1 | 4830487.89 | 4804355.61 | COMPLETED | 1 | 2018-10-18 |  |  |  | 2018-02-28 | 2018-03-08 | 2018-03-20 | 2018-04-12 | 2018-05-21 | J.C DELA VEGA CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Oroquieta City | 304057 | Talairon NHS | OROQUIETA CITY (Capital) | 1 | 1 | UPGRADING | 1 | 2770270.4 | 2754387.96 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-02-28 | 2018-03-08 | 2018-03-20 | 2018-04-12 | 2018-05-21 | J.C DELA VEGA CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Ozamis City | 304169 | Pulot National High School | OZAMIS CITY | 2 | 1 | UPGRADING | 2 | 2548844.06 |  | COMPLETED | 1 |  |  |  | 092-INFRA18-008 | 2018-08-16 | - | 2018-08-22 |  |  | EDTAHA BUILDERS, INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Tangub City | 304041 | Lorenzo Tan NHS | TANGUB CITY | 2 | 1 | UPGRADING | 2 | 2506678.54 |  | COMPLETED | 1 |  |  |  |  | 2018-08-07 | 2018-08-20 | 2018-09-05 | 2018-09-08 | 2018-09-13 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Tangub City | 304171 | Tangub City NHS | TANGUB CITY | 2 | 1 | UPGRADING | 3 | 3504891.44 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2018 | Region X | Valencia City |  | Valencia City NHS | CITY OF VALENCIA | 4 | 1 | UPGRADING | 2 | 4667328.3 | 4638510.61 | COMPLETED | 1 |  |  |  |  | 2018-06-08 | 2018-06-14 | 2018-07-02 | 2018-07-10 | 2018-08-07 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Bukidnon | 303947 | Baungon National High School | BAUNGON | 1 | 1 | UPGRADING | Batch 3 | 804834.05 |  | COMPLETED | 1 |  |  |  |  | 2019-10-05 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Bukidnon | 303955 | Halapitan National High School | SAN FERNANDO | 2 | 1 | UPGRADING | Batch 1 | 775314.25 |  | COMPLETED | 1 | 2021-01-13 | 2021-08-21 |  |  | 2019-10-06 |  |  |  |  | Maxwell EECS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Bukidnon | 314910 | Dangcagan National High School - Miaray Annex | DANGCAGAN | 3 | 1 | UPGRADING | Batch 1 | 588498.6 |  | COMPLETED | 1 | 2020-12-21 | 2021-08-26 |  |  | 2019-10-07 |  |  |  |  | Maxwell EECS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Bukidnon | 303953 | Dangcagan NHS | DANGCAGAN | 3 | 1 | UPGRADING | Batch 1 | 647341.99 |  | COMPLETED | 1 | 2020-12-21 | 2021-08-26 |  |  | 2019-10-08 |  |  |  |  | Maxwell EECS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Bukidnon | 314922 | New Nongnongan NHS - San Nicolas Annex | DON CARLOS | 3 | 1 | UPGRADING | Batch 1 | 538656.57 |  | COMPLETED | 1 | 2021-04-18 | 2021-08-22 |  |  | 2019-10-09 |  |  |  |  | Maxwell EECS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Bukidnon | 303961 | Kiburiao National High School | QUEZON | 3 | 1 | UPGRADING | Batch 3 | 853065.56 |  | COMPLETED | 1 | 2022-12-29 |  |  |  | 2019-10-10 |  |  |  |  | Ariane Construction and supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 127996 | Baikingon Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 697653.39 |  | COMPLETED | 1 | Awaiting schedule of local electric cooperative. |  |  |  | 2019-09-09 | 2019-09-16 | 2019-09-30 | 2019-11-21 | 2019-11-22 | CESCO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 315412 | Bonbon National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING |  | 1000263.21 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 304109 | Canitoan National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING |  | 1255382.9 |  | COMPLETED | 1 | Awaiting schedule of local electric cooperative. |  |  |  | 2018-12-12 | 2018-12-26 | 2018-12-26 | 2019-01-04 | 2019-07-31 | Brima Cons. & Ent. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 128003 | Iponan Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1790256.84 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 304117 | Iponan National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING |  | 1941221.11 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 304119 | Lumbia National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING |  | 2328026.76 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 127999 | Pedro "Oloy" N. Roa, Sr. Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1439467.18 |  | COMPLETED | 1 | Awaiting schedule of local electric cooperative. |  |  |  | 2019-09-09 | 2019-09-16 | 2019-09-30 | 2019-11-21 | 2019-11-22 | CESCO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 127984 | Taglimao Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 947753.04 |  | COMPLETED | 1 | Awaiting schedule of local electric cooperative. |  |  |  | 2019-09-09 | 2019-09-16 | 2019-09-30 | 2019-11-21 | 2019-11-22 | CESCO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 315406 | Taglimao NHS-Tumpagon Annex | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING |  | 881941.44 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 304123 | Tignapoloan NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING |  | 1335878.46 |  | COMPLETED | 1 | Awaiting schedule of local electric cooperative. |  |  |  | 2018-12-12 | 2018-12-26 | 2018-12-26 | 2019-01-04 | 2019-07-31 | Brima Cons. & Ent. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 127994 | Upper Carmen Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1031342.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 304111 | CAGAYAN DE ORO NATIONAL HIGH SCHOOL | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING |  | 2342064.6 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 315404 | Camaman-an National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING |  | 1560623.42 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 127943 | FS Catanico Elementary School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING |  | 547270.26 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 315408 | Gusa NHS - FS Catanico Annex | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 853842.16 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 304114 | Gusa Regional Science High School-X | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING |  | 1423490.89 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 127965 | Indahag Elementary School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1621312.18 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 127950 | Linangohan Elementary School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 856819.97 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 304120 | Macabalan National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING |  | 2185874.99 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 127957 | North City Central School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1504365.26 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 127952 | Puerto Elementary School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1214394.89 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 315402 | Puerto National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING |  | 770450.33 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 127958 | St. John Elementary School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 416813.62 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 304105 | Tablon National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING |  | 1355233.48 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127667 | Amoros ES | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 5878705.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127668 | Bolisong ES | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 4884049.14 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127670 | Cogon ES | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 6356922.23 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127671 | El Salvador City CS | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 8256610.31 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127672 | Himaya ES | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 5889258.72 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127673 | Hinigdaan ES | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 7033670.9 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127674 | Kalabaylabay ES | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 5887148.17 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127675 | Kibonbon ES | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 6356922.23 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127676 | Molugan Central School | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 7770416.82 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127677 | Pedro Sa. Baculio ES (Bolobolo) | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 5346837.73 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127678 | Sambulawan Elementary School | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 5889258.72 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127669 | San Francisco de Asis ES | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 7038947.28 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127679 | Sinaloc Elementary School | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 7017841.75 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127680 | Taytay ES | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 5539849.8 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127681 | Ulaliman ES | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 5362666.88 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Gingoog City | 315505 | Gingoog City CNHS - Anakan NHS Annex | GINGOOG CITY | 1 | 1 | UPGRADING | Batch 1 | 1134057.7 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Gingoog City | 315504 | Gingoog City CNHS - PUNDASAN NHS Annex | GINGOOG CITY | 1 | 1 | UPGRADING | Batch 1 | 1152391.16 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Gingoog City | 304137 | San Luis National High School | GINGOOG CITY | 1 | 1 | UPGRADING | Batch 3 | 1199571 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Iligan City | 304160 | Tubaran NHS - Digkilaan HS Annex | ILIGAN CITY | 0 | 1 | UPGRADING | Batch 1 | 4287768.25 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Lanao del Norte | 303998 | Baloi National High School | BALOI | 1 | 1 | UPGRADING | Batch 3 | 3133952.8 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Lanao del Norte | 304019 | Pantar NHS | PANTAR | 1 | 1 | UPGRADING | Batch 1 | 2730152.36 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Malaybalay City |  | Agalayan ES | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 4753770.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Malaybalay City | 126558 | Bangcud CES | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 5069639.71 |  | COMPLETED | 1 | 2022-10-25 |  | 001-INFRA-2019 | 001-INFRA-2019 |  |  |  |  | 2019-11-17 | Eriane Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Malaybalay City |  | Banglay NHS | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 2925354.21 |  | COMPLETED | 1 | 2022-10-25 |  | 001-INFRA-2019 | 001-INFRA-2019 |  |  |  |  | 2019-11-17 | Eriane Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Malaybalay City | 314904 | Malaybalay City National Science HS | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 5689747.82 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Misamis Occidental | 304040 | LOOC NATIONAL HIGH SCHOOL | PLARIDEL | 1 | 1 | UPGRADING | Batch 1 | 4475570.89 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Misamis Occidental | 304028 | Bonifacio NHS | BONIFACIO | 2 | 1 | UPGRADING | Batch 3 | 2882425.06 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Misamis Oriental | 304061 | Baliwagan NHS | BALINGASAG | 1 | 1 | UPGRADING |  | 5788711.74 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Misamis Oriental | 304066 | Consuelo NHS | MAGSAYSAY (LINUGOS) | 1 | 1 | UPGRADING |  | 3139887.57 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Misamis Oriental | 304059 | Alubijid NCHS | ALUBIJID | 2 | 1 | UPGRADING |  | 5300533.22 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Misamis Oriental | 304072 | Initao NCHS | INITAO | 2 | 1 | UPGRADING |  | 5827967.04 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Misamis Oriental | 304078 | Laguindingan NHS | LAGUINDINGAN | 2 | 1 | UPGRADING |  | 5429912.66 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Misamis Oriental | 304094 | Opol NSTS | OPOL | 2 | 1 | UPGRADING |  | 5469168.94 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Oroquieta City | 304044 | Misamis Occidental Science & Tech. HS | OROQUIETA CITY (Capital) | 1 | 1 | UPGRADING | Batch 2 | 5531661.99 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Oroquieta City | 500401 | Mobod IS | OROQUIETA CITY (Capital) | 1 | 1 | UPGRADING | Batch 2 | 6369752.38 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Ozamis City | 304163 | Labo National High School | OZAMIS CITY | 2 | 1 | UPGRADING | Batch 3 | 2701804.31 | 3656256.89 | COMPLETED | 1 | 2019-11-26 |  | ELEC 2019 - RX - OZAMIZ CITY - 002 | 092-INFRA19-10 | 2019-07-12 | 2019-07-23 | 2019-08-05 | 2019-08-22 | 2019-10-22 | JUNJING CONSTRUCTION & GENERAL MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Ozamis City | 304167 | Ozamiz City National High School | OZAMIS CITY | 2 | 1 | UPGRADING |  | 5190029.02 | 5129078.87 | COMPLETED | 1 | 2019-12-26 |  | ELEC 2019 - RX - OZAMIZ CITY - 003 | 092-INFRA19-11 | 2019-07-12 | 2019-07-23 | 2019-08-05 | 2019-08-22 | 2019-10-22 | JUNJING CONSTRUCTION & GENERAL MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Ozamis City | 304168 | Ozamiz City School of Arts and Trades | OZAMIS CITY | 2 | 1 | UPGRADING | Batch 3 | 5841193.64 | 5129078.87 | COMPLETED | 1 | 2019-12-26 |  | ELEC 2019 - RX - OZAMIZ CITY - 001 | 092-INFRA19-08 | 2018-10-27 | 2018-11-05 | 2018-11-20 | 2019-01-04 | 2019-08-28 | JUNJING CONSTRUCTION & GENERAL MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Ozamis City | 304162 | Tabid National High School | OZAMIS CITY | 2 | 1 | UPGRADING |  | 3684680.29 | 3656256.89 | COMPLETED | 1 | 2019-11-26 |  | ELEC 2019 - RX - OZAMIZ CITY - 004 | 092-INFRA19-09 | 2018-10-27 | 2018-11-05 | 2018-11-20 | 2019-01-04 | 2019-08-28 | JUNJING CONSTRUCTION & GENERAL MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2019 | Region X | Valencia City | 314906 | Lilingayon National High School | CITY OF VALENCIA | 4 | 1 | UPGRADING |  | 2116192.85 |  | ONGOING | 0.7 | 2024-08-01 |  | 43191 |  | 2020-10-24 | Negotiated Procurement | 2018-12-21 | 2019-02-07 | 2019-08-28 | Angel & Sam Construction & General Merchandise | Variation Order and Electrical Layout finished. Resumption of work to be issued | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Y | 0.7 | 0 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2020 | Region X | Bukidnon | 314925 | Baungon NHS - Danatag Annex | BAUNGON | 1 | 1 | UPGRADING |  | 3140634.91 |  | COMPLETED | 1 |  |  | Elec2020-RX-Bukidnon-001 | 05-2020 | 2019-12-14 |  |  | 2020-09-14 | 2020-10-05 | METERKING, INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Bukidnon | 303972 | Malitbog Nat. Agr'I. HS | MALITBOG | 1 | 1 | UPGRADING |  | 4012505.61 |  | ONGOING | 0.9 | 2024-08-01 |  | Elec2020-RX-Bukidnon-002 | 08-2021 | 2021-08-11 | 2021-08-19 | 2021-08-31 | 2021-09-28 | 2021-10-12 | CCO Construction & Supply | Ongoing execution of MOA. Additional materials to be purchased. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.9 | 0 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2020 | Region X | Bukidnon | 314921 | Dologon NHS - Kiharong Annex | MARAMAG | 3 | 1 |  |  | 1134744.87 |  | COMPLETED | 1 | 2021-04-02 |  | Elec2020-RX-Bukidnon-008 | 10-2020 | 2019-12-16 |  |  | 2020-11-25 | 2020-12-11 | AN Escalante Construction, INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Bukidnon | 314912 | Quezon National High School | QUEZON | 3 | 1 | UPGRADING |  | 1805170.52 |  | COMPLETED | 1 |  | 2021-04-29 | Elec2020-RX-Bukidnon-004 | 06-2020 | 2019-12-17 |  |  | 2020-09-14 | 2020-10-05 | AN Escalante Construction, INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Bukidnon | 303979 | Salawagan NHS | QUEZON | 3 | 1 | UPGRADING |  | 4112740.21 |  | COMPLETED | 1 | June 1. 2021 | 2021-08-23 | Elec2020-RX-Bukidnon-006 | 11-2020 | 2019-12-18 |  |  |  |  | AN Escalante Construction, INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Cagayan de Oro City | 127991 | Fr. William F. Masterson, SJ., Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 |  |  | 2416291.82 |  | COMPLETED | 1 |  |  | Elec2020-RX-Cagayan de Oro City-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Cagayan de Oro City | 315409 | Iponan NHS - San Simon Annex | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING |  | 1825787.25 |  | COMPLETED | 1 |  |  | Elec2020-RX-Cagayan de Oro City-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Cagayan de Oro City | 304121 | Mambuaya National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 |  |  | 1910588.72 |  | COMPLETED | 1 |  |  | Elec2020-RX-Cagayan de Oro City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Gingoog City | 111422 | BALAY HA TAGNAUWAN TA BAYUNGON ELEMENTARY SCHOOL | GINGOOG CITY | 1 | 1 |  |  | 588467.67 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2020 | Region X | Gingoog City | 304131 | Gingoog City CNHS - BACKKISMI NHS Annex | GINGOOG CITY | 1 | 1 |  |  | 1972266.91 |  | COMPLETED | 1 |  |  | Elec2020-RX-Gingoog City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Gingoog City | 315507 | Lunao National High School | GINGOOG CITY | 1 | 1 |  |  | 2174179.03 |  | COMPLETED | 1 |  |  | Elec2020-RX-Gingoog City-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Gingoog City | 111804 | PIGNANAW SA BANUGAN ELEMENTARY SCHOOL | GINGOOG CITY | 1 | 1 |  |  | 588467.67 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2020 | Region X | Iligan City | 304143 | Dalipuga National High School | ILIGAN CITY | 0 | 1 |  |  | 4684897.73 |  | COMPLETED | 1 |  |  | Elec2020-RX-Iligan City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Iligan City | 128081 | Tambo Central School | ILIGAN CITY | 0 | 1 |  |  | 4936023.01 |  | REVERTED | 0 |  |  | Elec2020-RX-Iligan City-002 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | UPGRADING | REVERTED
ELECTRIFICATION 2020 | Region X | Lanao del Norte | 304000 | Binuni-Demologan NHS | BACOLOD | 1 | 1 |  |  | 3433612.21 |  | COMPLETED | 1 |  |  | Elec2020-RX-Lanao del Norte-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Lanao del Norte | 304013 | Diego H. Patigayon NHS (Mukas NHS) | KOLAMBUGAN | 1 | 1 |  |  | 2706081.19 |  | COMPLETED | 1 |  |  | Elec2020-RX-Lanao del Norte-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Lanao del Norte | 304010 | Maigo NHS | MAIGO | 1 | 1 | UPGRADING |  | 2443266.05 |  | COMPLETED | 1 |  |  | Elec2020-RX-Lanao del Norte-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Lanao del Norte | 315102 | Lanao del Norte Provincial Science and Technology HS (former Malingao NHS (Annex New Pualas NHS) | TUBOD (Capital) | 1 | 1 |  |  | 3201586.1 |  | COMPLETED | 1 |  |  | Elec2020-RX-Lanao del Norte-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Malaybalay City | 126580 | Dalwangan ES | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING |  | 3489637.43 |  | COMPLETED | 1 |  |  | Elec2020-RX-Malaybalay City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Malaybalay City | 126547 | Managok CS | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING |  | 2838644.05 |  | COMPLETED | 1 |  |  | Elec2020-RX-Malaybalay City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Malaybalay City | 303982 | San Martin Agro-Industrial NHS | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING |  | 2443792.12 |  | COMPLETED | 1 | September 30, 2022 |  | Elec2020-RX-Malaybalay City-005 | [7 empty] | Complete installation onsite, FOR ENERGIZATION, with reinstallation issue due to error of BUSECO contractor, complied unlisted for BOM of BUSECO lacking materials by contractor. ready for submission of turn-on application | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Misamis Occidental | 304031 | Clarin NHS | CLARIN | 2 | 1 | UPGRADING |  | 4458236.13 | 4403098.14 | COMPLETED | 1 | 2022-11-04 |  | Elec2020-RX-Misamis Occidental-002 | [5 empty] | 2020-12-14 | RAKZ Builders | - For energization, lacking building permit, Occupancy permit. School has pending accounts payable to Electric Cooperative which cause delay to energization. informed to settle the account tru LSB 2022 funding. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Misamis Occidental | 304055 | Sinonoc NHS | SINACABAN | 2 | 1 | UPGRADING |  | 4464139.66 | 4375021.2 | COMPLETED | 1 | September 30, 2022 | 2022-10-03 | Elec2020-RX-Misamis Occidental-001 | [5 empty] | 2021-08-11 | ESL Milestone Builders INC. | -Waiting for the schools payment for previous billing. Subject for processing for energization. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.22 | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Misamis Oriental | 304069 | Dr. Gerardo Sabal MNHS | CLAVERIA | 2 | 1 | UPGRADING |  | 5357548.51 | METER KING INC. | COMPLETED | 1 | December 28, 2020 |  | Elec2020-RX-Misamis Oriental-002 |  |  | January 24,2020 | February 3, 2020 | February 17,2020 | March 2, 2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Misamis Oriental | 304079 | Libertad NHS | LIBERTAD | 2 | 1 | UPGRADING |  | 5234970.56 | METER KING INC. | COMPLETED | 1 | December 28, 2020 |  |  |  |  | January 24,2020 | February 3, 2020 | February 17,2020 | March 2, 2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Misamis Oriental | 304099 | Sta. Ana NHS | TAGOLOAN | 2 | 1 | UPGRADING |  | 5026839.59 | METER KING INC. | COMPLETED | 1 | December 28, 2020 |  | Elec2020-RX-Misamis Oriental-004 |  |  | January 24,2020 | February 3, 2020 | February 17,2020 | March 2, 2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Misamis Oriental | 304074 | Kalingagan NHS | VILLANUEVA | 2 | 1 |  |  | 5229319.62 |  | REVERTED | 0 |  |  | Elec2020-RX-Misamis Oriental-008 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | UPGRADING | REVERTED
ELECTRIFICATION 2020 | Region X | Ozamis City | 304166 | Montol National High School | OZAMIS CITY | 2 | 1 | UPGRADING |  | 4233597.89 |  | COMPLETED | 1 |  |  | Elec2020-RX-Ozamis City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Ozamis City | 128164 | Ozamiz City Central School | OZAMIS CITY | 2 | 1 | UPGRADING |  | 4472059.05 | DBB INDUSTRIAL SERVICES | COMPLETED | 1 | 2021-10-14 | - | Elec2020-RX-Ozamis City-002 | ELEC2020-RX-OZAMIZCITY-002 | 092-INFRA2021-001 | 2021-04-20 | 2021-04-28 | 2021-05-11 | 2021-05-21 | 44357 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Ozamis City | 304165 | San Antonio National High School | OZAMIS CITY | 2 | 1 | UPGRADING |  | 3847284.76 |  | COMPLETED | 1 |  |  | Elec2020-RX-Ozamis City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Tangub City | 304054 | Caniangan NHS | TANGUB CITY | 2 | 1 | UPGRADING |  | 3028449.97 | 2574180 | COMPLETED | 1 |  | 2/15/2021 | Elec2019-RX-Tangub City-001 |  | 2020-01-14 | 2020-01-24 | 2020-02-05 | 2020-06-12 | 2020-10-07 | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Tangub City | 500750 | Maloro Integrated School | TANGUB CITY | 2 | 1 | UPGRADING |  | 1891404.49 | 1664430 | COMPLETED | 1 |  | 2/15/2021 | Elec2020-RX-Tangub City-005 |  | 2020-01-14 | 2020-01-24 | 2020-02-05 | 2020-06-12 | 2020-10-07 | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Tangub City | 500752 | Pangabuan Integrated School | TANGUB CITY | 2 | 1 | UPGRADING |  | 3888115.7 |  | COMPLETED | 1 | April 2, 2020 | 2021-03-06 | Elec2020-RX-Tangub City-003 |  |  | 2020-01-14 | 2020-01-24 | 2020-02-05 | 2020-06-12 | 44166 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Tangub City | 304050 | Santa Maria NHS | TANGUB CITY | 2 | 1 | UPGRADING |  | 4006045.9 | Rakz Buikders and Supply | COMPLETED | 1 | December 1, 2020 | 2021-03-06 | Elec2020-RX-Tangub City-004 |  |  | 2020-01-14 | 2020-01-24 | 2020-02-05 | 2020-06-12 | 44111 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Valencia City |  | Bagontaas NHS | CITY OF VALENCIA | 4 | 1 | UPGRADING |  | 2581100.71 | 2045609.11 | COMPLETED | 1 | October 31, 2022 |  | Elec2020-RX-Valencia City-001 |  | April 19, 2021 | April 27, 2021 | May 10, 2021 | May 12, 2021 | 2021-05-14 | CCO Construction & Supply | Contractor partially complied with FIBECO's requirements for energization. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Valencia City | 501120 | Batangan CES | CITY OF VALENCIA | 4 | 1 | UPGRADING |  | 2533608.48 | A N Escalante Construction Inc. | COMPLETED | 1 | April 6, 2021 |  | Elec2020-RX-Valencia City-002 | Elec2020-RX-Valencia City-002 | 02-2020 | 2020-08-19 | 2020-08-25 | 2020-09-11 | 2020-10-21 | 44165 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Valencia City | 314909 | Guinuyoran National High School | CITY OF VALENCIA | 4 | 1 | UPGRADING |  | 3240736.13 | A N Escalante Construction Inc. | COMPLETED | 1 | April 6, 2021 |  | Elec2020-RX-Valencia City-008 | Elec2020-RX-Valencia City-008 | 02-2020 | 2020-08-19 | 2020-08-25 | 2020-09-11 | 2020-10-21 | 44165 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2020 | Region X | Valencia City | 501124 | SUGOD ES | CITY OF VALENCIA | 4 | 1 | UPGRADING |  | 2574141.98 | A N Escalante Construction Inc. | COMPLETED | 1 | April 6, 2021 |  | Elec2020-RX-Valencia City-003 | Elec2020-RX-Valencia City-003 | 02-2020 | 2020-08-19 | 2020-08-25 | 2020-09-11 | 2020-10-21 | 44165 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region X | Camiguin | 126933 | Maac Elementary School | GUINSILIBAN | Lone | 1 | Upgrading of Electrical System (Underground System) | 1 | 2353935.51 | 2232071.69 | COMPLETED | 1 | [9 empty] | Elettro Engineering Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region X | Misamis Occidental | 304051 | Sapang Dalaga National High School | SAPANG DALAGA | 1st | 1 | Energization and Upgrading of Electrical System | 1 | 2196264.4 | 2172379.71 | COMPLETED | 1 | 2024-01-17 |  | ELEC 2023-REGION X-MISAMIS OCCIDENTAL-001 | 009-2023 | 2023-05-20 | 2023-05-29 | 2023-06-13 | 2023-08-08 | 2023-09-12 | ESL Milestone Builders and Supply, Inc. | Turned Over | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 5.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2023 | Region X | Misamis Oriental | 315304 | Lumbo NHS | LAGONGLONG | 1st | 1 | Energization of Electrical System (Overhead System) | 1 | 6000000 | 5991584.84 | COMPLETED | 1 | 2024-05-12 |  | G2PB - Electrification-2023-001 | 4610718 | 2023-11-05 | 2023-11-20 | 2023-12-04 | 2024-01-03 | 2024-01-18 | Meter King Inc. | Punchlisting | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | COMPLETED
ELECTRIFICATION 2024 | Region X | Bukidnon | 303978 | Pangantucan NHS | PANGANTUCAN | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1944415.44 | 1625855.39 | ONGOING | 0.85 | 2024-12-23 | - | PB-02-11-2023-0024-A | 015-2024 | PR 2024-02-040 dated February 27, 2024 | Negotiated Procurement due to 2 failed bidding | 2024-03-15 | 2024-04-12 | 2024-06-26 | AN Escalante Construction, Inc. | Ongoing, Done survey by Electric Coop, waiting for BOM | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.85 | 0 |  |  | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region X | Bukidnon | 303952 | Cabulohan-Paradise NHS | CABANGLASAN | 2nd | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 2513688.52 | 2257543 | ONGOING | 0.95 | 2025-08-30 | - | PB-02-11-2023-0024 | 013-2024 | 2023-11-26 | 2023-12-04 | 2023-12-18 | 2023-12-27 | 2024-05-29 | White Beard Construction | Still consolidating documentary requiremets for Electrical Permit and application for turn-on, need to secure Land disposition and Form V-37 in lieu of the title, | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.9 | 0.05 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region X | Bukidnon | 303976 | Old Damulog NHS | DAMULOG | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1792243.8 | 1789757.96 | ONGOING | 0.92 | 2025-06-30 | - | PB-02-11-2023-0024 | 014-2024 | 2023-11-26 | 2023-12-04 | 2023-12-18 | 2023-12-27 | 2024-05-29 | Meter King Inc. | Scheduled to be energized on June 10, 2025 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.85 | 0.07 |  |  | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region X | Cagayan de Oro City | 127960 | Bonbon Elementary School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3140673.42 | 2830507.8 | COMPLETED | 1 | 2024-09-08 | - | Elec 2024-RX-Cagayan de Oro - 001 | 2024-009 | 2023-11-16 | 2024-11-28 | 2023-12-14 | 2023-12-28 | 2024-06-06 | F.B. Batucan Electrical Services | Awaiting for the approval of RO to convert Customer Own to Commercial Own contract with CEPALCO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | ENERGIZATION | COMPLETED
ELECTRIFICATION 2024 | Region X | Cagayan de Oro City | 127944 | Gusa Elementary School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | Upgrading of Electrical System | 1 | 4314432.5 | 3884668.52 | COMPLETED | 1 | 2024-09-08 | - | Elec 2024-RX-Cagayan de Oro - 002 | 2024-008 | 2023-11-16 | 2024-11-28 | 2023-12-14 | 2023-12-28 | 2024-06-06 | F.B. Batucan Electrical Services | Awaiting for the approval of RO to convert Customer Own to Commercial Own contract with CEPALCO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region X | Camiguin | 500683 | Alangilan Integrated School | SAGAY | Lone | 1 | Upgrading of Electrical System (Underground System) | 1 | 4518164.06 | 4175658.37 | COMPLETED | 1 | 2024-09-26 | 2024-10-20 | Infra-01-02-2024 | Infra-01-02-2024 | 2023-11-24 | 2023-12-01 | 2023-12-14 | 2024-01-24 | 2024-05-29 | Elettro Engineering Enterprises | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region X | El Salvador | 304768 | Himaya National High School | CITY OF EL SALVADOR | 2nd | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 2753266.37 | 2748058.88 | COMPLETED | 1 | 2024-10-15 | 2024-10-24 | 2024-01-0001 | 2024-02-0001 | 2024-01-04 | 2024-01-23 | 2024-02-07 | 2024-05-09 | 2024-05-23 | CCO Engineering and Construction Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region X | Gingoog City | 111852 | Kalandang ta Anahaw ES | GINGOOG CITY | 1st | 1 | Installation of hybrid Solar Power System 8 kw and its electrical fixtures, wiring,switches and outlets | 1 | 1845640.12 | 1797132.63 | COMPLETED | 1 | 2024-11-11 | - | ELEC 2024 - REGION X - GINGOOG CITY - 001 | BEFF-2024-Anahaw ES | 2023-11-03 | 2023-11-10 | 2023-11-21 | 2024-05-21 | 2024-06-07 | Greenergy Development Corp. | On-going (under time suspesion - waiting for advice to use of military chopper for transport of euipment and materials for the project) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 4.25 | SOLAR | COMPLETED
ELECTRIFICATION 2024 | Region X | Iligan City | 304146 | Iligan City East National HS (Sta. Filomena) | ILIGAN CITY | Lone | 1 | Modernization of Electrical System On-grid Schools | 1 | 4590704.23 | 4361177.7 | COMPLETED | 1 | 2024-10-22 | - | INFRA-2023-11-02 | INFRA-2023-11-02 | 2023-11-28 | 2023-12-06 | 2024-02-19 | 2024-03-04 | 2024-05-31 | Brima Construction and Enterprise | On-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 11.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region X | Lanao del Norte | 304001 | Diosdado Yap Sr. National High School | BAROY | 1st | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 2136858.59 | 2135747.42 | COMPLETED | 1 | 2025-01-01 | 2025-05-30 | 2024-03(Infra) | 2024-03(Infra) | 2024-04-30 | 2024-05-10 | 2024-05-24 | 2024-06-10 | 2024-08-15 | HPS Engineering and Electrical Services | Checking of Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.95 | 0.05 |  | 5.25 | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region X | Lanao del Norte | 304009 | Magsaysay NHS | MAGSAYSAY | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1408996.7 | 1408545.54 | ONGOING | 0.95 | 2025-01-01 | - | 2024-03(Infra) | 45353 | 2024-04-30 | 2024-05-10 | 2024-05-24 | 2024-06-10 | 2024-08-15 | HPS Engineering and Electrical Services | Contractor to receive the NTP | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.95 | 0 |  |  | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region X | Malaybalay City | 126561 | Cabangahan ES | CITY MALAYBALAY (Capital) | 2nd | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 2041033.97 | 1769898 | ONGOING | 0.9 | 2025-07-30 | - | 002-INFRA-2023 | 002-INFRA-2023 | 2023-11-29 | 2023-12-07 | 2023-12-19 | 2023-12-27 | 2024-08-01 | WHITE BEARD CONSTRUCTION | Drafting of Final MOA with local electric cooperative | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.85 | 0.05 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region X | Misamis Occidental | 304025 | Baliangao SOF | BALIANGAO | 1st | 1 | Energization and Upgrading of Electrical System | 1 | 4007184.23 | 3962812.64 | ONGOING | 0.95 | 2024-12-06 | - | ELEC 2024 - REGION X - MISAMIS OCCIDENTAL - 002 | 012-2024 | 2023-11-29 | 2023-12-07 | 2023-12-19 | 2024-01-16 | 2024-07-25 | ESL MILESTONE BUILDERS & SUPPLY, INC. | ongoing - lacking transformer & post | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.95 | 0 |  |  | ENERGIZATION | ONGOING
ELECTRIFICATION 2024 | Region X | Misamis Occidental | 304034 | Diwat NHS | Bonifacio | 2nd | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 2601401.55 | 2573283.1 | COMPLETED | 1 | 2024-11-12 | - | ELEC 2024 - REGION X - MISAMIS OCCIDENTAL - 001 | 008-2024 | 2023-11-29 | 2023-12-07 | 2023-12-19 | 2024-01-16 | 2024-07-03 | ELETTRO ENGINEERING ENTERPRISES | Completed and Energized | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 11.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region X | Misamis Oriental | 304101 | Sugbongcogon NHS | SUGBONGCOGON | 1st | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 5185403.57 | 5132617.21 | ONGOING | 0.95 | 2024-11-09 | - | G2PB - Electrification-2024-001 |  | 2024-03-11 | 2024-03-18 | 2024-04-01 | 2024-04-11 | 2024-07-05 | Meter King Inc. | ongoing | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.95 | 0 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region X | Misamis Oriental | 304088 | Mat-i (Naawan) NHS | NAAWAN | 2nd | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 5091534.32 | 5058911.8 | ONGOING | 0.95 | 2024-11-09 | - | G2PB - Electrification-2024-002 |  | 2024-03-11 | 2024-03-18 | 2024-04-01 | 2024-04-11 | 2024-07-05 | Meter King Inc. | ongoing | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.95 | 0 |  |  | UPGRADING | ONGOING
ELECTRIFICATION 2024 | Region X | Oroquieta City | 304052 | Senote NHS | Oroquita City | 1st | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 2330287.76 | 2307037.69 | COMPLETED | 1 | ‎18‎ ‎September‎ ‎2024 | - |  |  | 2023-11-29 | 2023-12-06 | 2024-01-16 | 2024-05-10 | 2024-05-21 | ESL Milestone Builders & Supply INC | for final inspection | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region X | Ozamis City | 304164 | Jose Lim Ho National High School | OZAMIS CITY | 2nd | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 3001645.2 | 2991544.11 | COMPLETED | 1 | 2024-10-25 | - | 092-CIVIL 2023-001 (EPA) | 092-CIVIL 2023-001 (EPA) | 2023-11-22 | 2023-11-29 | 2023-12-15 | 2024-01-04 | 2024-06-27 | Elletro Engineering Enterprises | ongoing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 11.24 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region X | Tangub City | 128217 | Tangub City CS | TANGUB CITY | 2nd | 1 | Modernization or Upgrading of Existing Electrical Distribution System | 1 | 2446851.19 | 2422378.91 | COMPLETED | 1 | 2024-10-26 | - | ELEC 2023-Region X-Tangub 001 |  | 2024-11-23 | 2024-11-30 | 2023-12-12 | 2023-12-20 | 2024-07-04 | ESL Milestone Builders INC | ongoing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 4.25 | UPGRADING | COMPLETED
ELECTRIFICATION 2024 | Region X | Valencia City | 126863 | VALENCIA CITY CS | VALENCIA CITY | 4th | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 5591647.46 | 4725764.09 | ONGOING | 0.9 | 2024-10-21 | - | 45323 | 011 s. 2024 | 2024-02-05 | 2024-02-16 | 2024-02-16 | 2024-02-21 | 2024-02-22 | AN ESCALANTE CONSTRUCTION, INC. | ongoing | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.9 | 0 |  |  | UPGRADING | ONGOING