## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | TOTAL NO. OF BUILDINGS | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of bldg Reverted | No. of bldg Not yet started | No. of bldg Under Procurement | No. of bldg On Going | No. of bldg Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | Implementing Unit | BBM TERM COMPLETED | AWAITING SUBMISSION OF RTA | batch of suballotment | Unnamed: 45
GABALDON 2020 | Region X | Cagayan de Oro City | 127962 | Consolacion Elementary School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 2602587.62 | 1 | 2320989.95 | COMPLETED | 1 | 2021-08-02 | 2021-08-01 | 44044 | 20-12-BAC07 | September 21-25, 2020 | Canvass | 2020-09-28 | 2020-10-07 | 2020-12-11 | JARM Construction Services and Supply | Project completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
GABALDON 2020 | Region X | Camiguin | 126914 | Mambajao CS | MAMBAJAO (Capital) | 0 | 1 | 15 | 1 | Rehabilitation of Gabaldon Building | 9860389.51 | 1 | 8424360.07 | COMPLETED | 1 | 2021-09-25 | 2021-09-25 | 43831 | 20-03-BAC01 | 2020-01-10 | 2020-01-17 | 2020-02-06 | 2020-02-26 | 2020-11-16 | JDE Construction | Project completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
GABALDON 2020 | Region X | Camiguin | 126914 | Mambajao CS | MAMBAJAO (Capital) | 0 |  | 1 | 1 | Rehabilitation of Gabaldon Building (Home Economics) | 2518346.23 | 1 | 2262723.44 | COMPLETED | 1 | 2021-07-27 | 2021-07-27 | 43831 | 20-03-BAC01 | 2020-01-10 | 2020-01-17 | 2020-02-06 | 2020-02-26 | 2020-11-16 | JDE Construction | Project completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
GABALDON 2020 | Region X | Lanao del Norte | 127095 | Linamon Central School | LINAMON | 1 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 3350950.38 | 1 | 2842031.84 | COMPLETED | 1 | 2021-03-18 | 2021-07-30 | 43831 | 20-03-BAC02 | 2020-01-10 | 2020-01-17 | 2020-02-06 | 2020-02-26 | 2020-11-18 | AbrahamBM Construction | Project completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
GABALDON 2020 | Region X | Lanao del Norte | 127099 | Samburon Elementary School | LINAMON | 1 | 1 | 7 | 1 | Rehabilitation of Gabaldon Building | 7722092.81 | 1 | 6787587.22 | COMPLETED | 1 | 2021-07-30 | 2021-07-30 | 43831 | 20-03-BAC02 | 2020-01-10 | 2020-01-17 | 2020-02-06 | 2020-02-26 | 2020-11-18 | AbrahamBM Construction | Project completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
GABALDON 2020 | Region X | Misamis Occidental | 127244 | Aloran Central School | ALORAN | 1 | 1 | 8 | 1 | Rehabilitation of Gabaldon Building | 7057211.69 | 1 | 5596707.61 | COMPLETED | 1 | 2022-09-30 | 2024-07-31 | 44228 | 21-08-BAC05 | 2021-03-11 | 2021-03-18 | 2021-06-21 | 2021-07-21 | Sept. 13, 2021 | JARM Construction Services and Supply | Project completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2023-01-01 | 8.24 |  |  |  |  | COMPLETED
GABALDON 2020 | Region X | Misamis Occidental | 127273 | Baliangao CS | BALIANGAO | 1 | 1 | 6 | 1 | Rehabilitation of Gabaldon Building | 9373297.57 | 1 | 7662360.48 | COMPLETED | 1 | 2022-02-05 | 2022-02-05 | 44228 | 21-09-BAC09 | 2021-07-29 | 2021-08-05 | 2021-08-17 | 2021-08-31 | Sept. 20, 2021 | AFS construction | Project completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
GABALDON 2020 | Region X | Misamis Occidental | 127426 | Mansabay Alto ES | LOPEZ JAENA | 1 | 1 | 5 | 1 | Rehabilitation of Gabaldon Building | 5847866.3 | 1 | 4903966.68 | Completed | 1 | 2022-09-30 | 2022-11-30 | 44228 | 21-08-BAC04 | 2021-03-11 | 2021-03-18 | 2021-06-21 | 2021-07-21 | Sept. 7, 2021 | Parbros Construction Services and Supply | Project completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2021 | Region X | Bukidnon | 126508 | Lantapan CES | ANTAPAN | 2 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 2354739 | 1 | 1999294.989 | Completed | 1 | September 30, 2022 | 2023-04-18 | 44228 | 21-08-BAC08 | 2021-03-11 | 2021-03-18 | 2021-06-21 | 2021-07-21 | Sept. 24, 2021 | Tri-FB Construction | Project completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4.23 | Regional Office | CY 2023 |  |  | Completed
GABALDON 2021 | Region X | Cagayan de Oro City | 127979 | Mambuaya Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 3 | 1 | Reconstruction of Type 4 - Rectangular Type Gabaldon Building | 7606016 | 1 | 6056773.59 | COMPLETED | 1 | September 30, 2022 | 2022-12-06 | 44228 | 21-08-BAC06 | 2021-03-11 | 2021-03-18 | 2021-06-21 | 2021-07-21 | Sept. 9. 2021 | Nonabon Enterprises | Project completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Regional Office | CY 2022 |  |  | COMPLETED
GABALDON 2022 | Region X | El Salvador | 127672 | Himaya ES | CITY OF EL SALVADOR | 2 | 1 | 3 | 1 | Restoration of Gabaldon Building | 8936669.89 | 1 | 6629086.32 | COMPLETED | 1 | 2023-01-04 | 2/29/2024 | 2022-10-0229 | 2022-12-0328 | 10/25/2022 | 2022-03-11 | 11/15/2022 | 11/28/2022 | 12/15/2022 | Hid Construction | Project completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 3.24 | Division Office | cy 2024 |  |  | COMPLETED
GABALDON 2022 | Region X | Misamis Oriental | 127714 | ALICOMOHAN CS | SUGBONGCOGON | 2 | 1 | 4 | 1 | Repair & Rehabilitation of 4-Rectangular Type Gabaldon Building | 7905972.01 | 1 | 7770174.85 | Completed | 1 | 3/20/2023 | 8/20/2023 | PB - Repair 2022-02 | 3916422 | 9/16/2022 | 2022-03-10 | 10/17/2022 | 2022-04-11 | 11/13/2022 | Meter King Inc. | Project completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 3.24 | Division Office | cy 2024 |  |  | Completed
GABALDON 2023 | Region X | Lanao del Norte | 500689 | Lala Proper IS | LALA | 2 | 1 | 10 | 1 | Restoration & Conservation of Gabaldon Building | 18049936.9 | 1 | 13418727.45 | Completed | 1 | 4/30/2024 | 10/16/2024 | 2023-04(Infra)-Rebid | 45047 | 7/26/2023 | 2023-02-08 | 8/14/2023 | 8/28/2023 | 9/25/2023 | Millineum Builders and Construction | Project completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 9.24 | Division Office |  |  |  | Completed
GABALDON 2024 | Region X | Cagayan de Oro City | 127963 | Kauswagan Central School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 12113951.57 | 1 | 9585902.87 | Completed | 1 | 12/31/2024 | 3/15/2025 | GABALDON 2024- RX - CAGAYAN DE ORO CITY - 001 | 2024-012 | 3/20/2024 | 2024-01-04 | 4/17/2024 | 2024-07-05 | 2024-04-07 | JDE Construction | Subject for Punchlist | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 3.25 | Division Office |  |  | 3 | Completed
GABALDON 2024 | Region X | Camiguin | 126908 | Baylao Elementary School | MAMBAJAO (Capital) | Lone | 1 | 3 | 1 | Conservation and Restoration of Gabaldon School Building | 3000000 | 1 |  | Ongoing | 0.5 |  |  | Infra-01-04-2024 |  | 9/23/2024 | 2024-01-10 | 10/14/2024 |  |  | Vinlabz Construction | Ongoing installation of Wall Studs | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.5 | 0 |  |  | Division Office |  |  | 10 | Ongoing
GABALDON 2024 | Region X | Gingoog City | 128055 | Manuel Lugod Central School | GINGOOG CITY | 1st | 1 | 7 | 1 | Conservation and Restoration of Gabaldon School Building | 14000000 | 1 | 13900000 | Ongoing | 0.6 | 3/13/2025 |  | GABALDON 2024- RX - GINGOOG CITY - 001 | GAAAO-2024-MLCS | 6/17/2024 | 6/24/2024 | 2024-03-07 | 7/26/2024 | 2024-04-10 | L & L Construction | Time extension for approval. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.6 | 0 |  |  | Division Office |  |  | 8 | Ongoing
GABALDON 2024 | Region X | Misamis Oriental | 127747 | Lagonglong CS | LAGONGLONG | 1st | 1 | 7 | 1 | Conservation and Restoration of Gabaldon School Building | 16768109.2 | 1 | 14067930.31 | Ongoing | 0.3 | 7/17/2025 |  | PB 2024 009-027 |  | 7/29/2024 | 2024-07-08 | 8/20/2024 | 2024-10-09 | 2025-08-01 | Minkonstrak Engineering and General Services | Ongoing | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.3 | 0 |  |  | Division Office |  |  | 10 | Ongoing