## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | TOTAL NO. OF BUILDINGS | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of bldg Reverted | No. of bldg Not yet started | No. of bldg Under Procurement | No. of bldg On Going | No. of bldg Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | Implementing Unit | BBM TERM COMPLETED | AWAITING SUBMISSION OF RTA | batch of suballotment | Unnamed: 45
GABALDON 2020 | Region XI | Compostela Valley | 128552 | Napnapan ES | PANTUKAN | 2 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 3272205.59 | 1 |  | Completed | 1 | [10 empty] | For Mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region XI | Compostela Valley | 304208 | Pantukan NHS | PANTUKAN | 2 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 1740426.25 | 1 |  | Completed | 1 | [10 empty] | For Mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region XI | Davao City | 129712 | BAGO ELEMENTARY SCHOOL | DAVAO CITY | 1 | 1 | 8 | 1 | Rehabilitation of Gabaldon Building | 6026983.08 | 1 |  | Completed | 1 | [10 empty] | FOR ISSUANCE OF RTA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region XI | Davao City | 129557 | Kapt. T. Monteverde Sr. CES | DAVAO CITY | 1 | 1 | 13 | 1 | Rehabilitation of Gabaldon Building | 8390772.6 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region XI | Davao City | 129513 | Teofilo Fernandez ES | DAVAO CITY | 2 | 1 | 8 | 1 | Rehabilitation of Gabaldon Building | 6250198.88 | 1 |  | Completed | 1 | [10 empty] | FOR ISSUANCE OF RTA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region XI | Davao del Sur | 129049 | Padada CES | PADADA | 0 | 1 | 10 | 1 | Rehabilitation of Gabaldon Building | 9240000 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region XI | Davao Oriental | 129211 | Caraga Central ES | Caraga | 1 | 1 | 6 | 1 | Rehabilitation of Gabaldon Building | 6519391.44 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region XI | Davao Oriental | 129356 | Gregorio Moralizon ES | Manay | 1 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 3709572.11 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2021 | Region XI | Davao City | 129492 | Binugao CES | DAVAO CITY | 3 | 1 | 16 | 1 | Rehabilitation of Gabaldon Building | 2944439 | 1 |  | COMPLETED | 1 | [6 empty] | June 30, 2021 |  | Sept. 27, 2021 | J&S Escuadra Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Division Office |  |  |  | COMPLETED
GABALDON 2021 | Region XI | Mati City | 129380 | Rabat-Rocamora Mati CES I | CITY OF MATI (Capital) | 2 | 1 | 20 | 1 | Rehabilitation of Gabaldon Building | 23181008 | 1 |  | COMPLETED | 1 | 2022-09-30 |  |  |  | 2021-05-13 |  | 2021-06-02 | 2021-06-14 | 2021-06-21 | MATT GLASS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Division Office |  |  |  | COMPLETED
GABALDON 2024 | Region XI | Davao City | 129680 | Alambre ES | DAVAO CITY | 3rd | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 7827466.16 | 1 |  | Ongoing | 0.85 | May 11, 2025 |  | BEFF-004-2024 | Contract #2 s.2025 INF DL-XI | June 28, 2024-July 18,2024 | July 5, 2024 | July 18, 2024 | Sept. 30, 2024 | Jan.10, 2025 | R. FABALE CONST. CORP. | Submitted RTA to Central Office; awaiting subaro release | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.85 | 0 |  |  | Division Office |  |  | 10 | Ongoing
GABALDON 2024 | Region XI | Davao City | 129490 | Baracatan ES | DAVAO CITY | 3rd | 1 | 3 | 1 | Conservation and Restoration of Gabaldon School Building | 6530565.38 | 1 |  | Ongoing | 0.85 | May 11, 2025 |  | BEFF-004-2024 | Contract #2 s.2025 INF DL-XI | June 28, 2024-July 18,2024 | July 5, 2024 | July 18, 2024 | Sept. 30, 2024 | Jan.10, 2025 | R. FABALE CONST. CORP. | Submitted RTA to Central Office; awaiting subaro release | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.85 | 0 |  |  | Division Office |  |  | 10 | Ongoing
GABALDON 2024 | Region XI | Davao City | 129494 | Catigan ES | DAVAO CITY | 3rd | 1 | 3 | 1 | Conservation and Restoration of Gabaldon School Building | 6824294.85 | 1 |  | Ongoing | 0.85 | May 11, 2025 |  | BEFF-004-2024 | Contract #2 s.2025 INF DL-XI | June 28, 2024-July 18,2024 | July 5, 2024 | July 18, 2024 | Sept. 30, 2024 | Jan.10, 2025 | R. FABALE CONST. CORP. | Submitted RTA to Central Office; awaiting subaro release | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.85 | 0 |  |  | Division Office |  |  | 10 | Ongoing
GABALDON 2024 | Region XI | Davao de Oro | 128263 | Compostela Central Elementary School SPED Center | COMPOSTELA | 1st | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 5250000 | 1 | 4987335.03 | Ongoing | 0.85 | 4/24/2024 |  | SDD0-013-2024 | SDD0-013-2024 | August 08, 2024 | August 16, 2024 | August 29,2024 | September 30,2024 | December 23,2024 | DQMB CONST. & SUPPLY CORP. | ON GOING WORKS OF PUNCHLIST | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.73 | 0.12 |  |  | Division Office |  |  | 10 | Ongoing
GABALDON 2024 | Region XI | Davao de Oro | 128335 | Mabini CES | MABINI (DOÑA ALICIA) | 2nd | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 6550000 | 1 | 6222512.37 | Ongoing | 0.85 | 5/24/2024 |  | SDD0-014-2024 | SDD0-014-2024 | August 08, 2024 | August 16, 2024 | August 29,2024 | September 30,2024 | December 23,2024 | DQMB CONST. & SUPPLY CORP. | ON GOING PAINTING WORKS | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.6 | 0.25 |  |  | Division Office |  |  | 10 | Ongoing
GABALDON 2024 | Region XI | Davao del Sur | 128954 | Malalag CES | Malalag | 1st | 1 | 12 | 1 | Conservation and Restoration of Gabaldon School Building | 17321825.17 | 1 |  | Not Yet Started | 0 | October 22, 2025 |  | DS-GABALDON-2024-F |  |  | June 26, 2024 | July 08, 2024 | August 09, 2024 |  | DIGOS CONSTRAK CORPORATION (DCC) | The Contractor refused to accept the contract due to Non-Issuance of Tax Clearance from the BIR. Re-Bid | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | Division Office |  |  | 8 | not yet started
GABALDON 2024 | Region XI | Davao Occidental | 128881 | Jose Abad Santos Central Elementary School | JOSE ABAD SANTOS (TRINIDAD) | Lone | 1 | 13 | 1 | Conservation and Restoration of Gabaldon School Building | 13970092.52 | 1 | 13960510.52 | Completed | 1 | January 13, 2025 | December 19, 2024 | ITB W-01-2024 | contract no. 2024-006 | April 15, 2024- April 29, 2024 | April 23, 2024 | April 29, 2024 | May 27, 2024 | July 17, 2024 | DIGOS CONSTRAK CORPORATION (DCC) | completed ahead of time | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2.25 | Division Office |  |  | 3 | Completed
GABALDON 2024 | Region XI | Davao Oriental | 129177 | BanayBanay CES | Banaybanay | 2nd | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 2224912.53 | 1 | 1656888.85 | Completed | 1 | 12/27/2024 | February 24, 2025 | GS-2024-078. | 2024-.24 | 2024-06-06 | 6/13/2024 | 6/25/2024 | 2024-07-09 | 8/29/2024 | MANIMBO CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 3.25 | Division Office |  |  | 6 | COMPLETED
GABALDON 2024 | Region XI | Davao Oriental | 129329 | Comara T. Manuel Central Elementary School SPED Center | LUPON | 2nd | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 2109850.67 | 1 | 1710636.55 | Completed | 1 | 12/27/2024 | February 24, 2025 | GS-2024-077 | 2024-025 | 2024-06-06 | 6/13/2024 | 6/25/2024 | 2024-07-09 | 8/29/2024 | MANIMBO CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 3.25 | Division Office |  |  | 6 | COMPLETED