## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of Sites Terminated | No. of CL Terminated | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | BBM TERM COMPLETED | Unnamed: 46
REPAIR 2020 | Region XI | Compostela Valley | 128386 | Mahayahay ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 3 | Repair of Classrooms | 1570356 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Compostela Valley | 128395 | New Panay ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 3 | Repair of Classrooms | 1708204 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Compostela Valley | 128399 | Saranga ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 2 | Repair of Classrooms | 1347567 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Compostela Valley | 128437 | Mamonga ES | MONKAYO | 1 | 1 | 5 | Repair of Classrooms | 2615886 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Compostela Valley | 128302 | Kapatagan ES | LAAK (SAN VICENTE) | 2 | 1 | 10 | Repair of Classrooms | 3150185 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Compostela Valley | 128338 | Masicareg ES | MABINI (DOÑA ALICIA) | 2 | 1 | 2 | Repair of Classrooms | 1096959 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Compostela Valley | 128363 | Anislagan ES | MACO | 2 | 1 | 8 | Repair of Classrooms | 3829945 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Compostela Valley | 128348 | Gayab ES | MACO | 2 | 1 | 9 | Repair of Classrooms | 4621970 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Compostela Valley | 128536 | Biasong ES | PANTUKAN | 2 | 1 | 3 | Repair of Classrooms | 963259 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao City | 206005 | Pamantawan PS | DAVAO CITY | 2 | 1 | 10 | Repair of Classrooms | 3457811 | 1 |  | COMPLETED | 1 | [10 empty] | Waiting for Sub-aro | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao City | 129568 | Kanacan ES | DAVAO CITY | 3 | 1 | 9 | Repair of Classrooms | 3526407 | 1 |  | COMPLETED | 1 | [10 empty] | Waiting for Sub-aro | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao City | 129503 | Tibuloy ES | DAVAO CITY | 3 | 1 | 11 | Repair of Classrooms | 3718419 | 1 |  | COMPLETED | 1 | [10 empty] | Waiting for Sub-aro | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Norte | 128651 | Domingo B. Hain Elementary School | KAPALONG | 1 | 1 | 12 | Repair of Classrooms | 6617873 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Norte | 500849 | Macgum Integrated School | NEW CORELLA | 1 | 1 | 6 | Repair of Classrooms | 3083628 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Norte | 128615 | Balisong ES | BRAULIO E. DUJALI | 2 | 1 | 9 | Repair of Classrooms | 4050000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Norte | 128624 | Alejal Elementary School | CARMEN | 2 | 1 | 11 | Repair of Classrooms | 5500000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Norte | 128627 | Carmen CES SPED CENTER | CARMEN | 2 | 1 | 20 | Repair of Classrooms | 14058726.61 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Norte | 315904 | La Paz National High School | CARMEN | 2 | 1 | 9 | Repair of Classrooms | 4950000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Norte | 128640 | Sto Niño ES | CARMEN | 2 | 1 | 5 | Repair of Classrooms | 2900000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Norte | 128750 | La Libertad ES | SANTO TOMAS | 2 | 1 | 6 | Repair of Classrooms | 3015641 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Sur | 128829 | Eman ES | BANSALAN | 0 | 1 | 9 | Repair of Classrooms | 3261000 | 1 |  | reverted | 0 | [10 empty] | The Project was not implement because the buildings to be repair is beyond repair due to a series of earthquake on year 2019 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | reverted
REPAIR 2020 | Region XI | Davao del Sur | 128908 | Latian ES | KIBLAWAN | 0 | 1 | 8 | Repair of Classrooms | 2715310 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Sur | 128909 | Manual ES | KIBLAWAN | 0 | 1 | 10 | Repair of Classrooms | 3722304 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Sur | 128931 | Bacungan ES | MAGSAYSAY | 0 | 1 | 12 | Repair of Classrooms | 5044913 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Sur | 128948 | Bulacan ES | MALALAG | 0 | 1 | 22 | Repair of Classrooms | 6927965 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Sur | 129047 | Malinao ES | PADADA | 0 | 1 | 13 | Repair of Classrooms | 4787067 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao Occidental | 128961 | Aglaungan Elementary School | MALITA | 0 | 1 | 3 | Repair of Classrooms | 1263922 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao Occidental | 128962 | Procopio Mejellano Sr. Elementary School | MALITA | 0 | 1 | 5 | Repair of Classrooms | 2569431 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao Occidental | 128985 | Talogoy Elementary School | MALITA | 0 | 1 | 11 | Repair of Classrooms | 4556287 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao Occidental | 129011 | Upper Ticulon ES | MALITA | 0 | 1 | 8 | Repair of Classrooms | 3756459 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao Oriental | 129242 | Pantuyan ES | CARAGA | 1 | 1 | 19 | Repair of Classrooms | 5743782 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao Oriental | 304309 | Cateel Nat'l. Agri. HS | CATEEL | 1 | 1 | 11 | Repair of Classrooms | 4105851 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao Oriental | 129270 | San Alfonso ES | CATEEL | 1 | 1 | 18 | Repair of Classrooms | 5124985 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao Oriental | 500417 | Jose Antop, Sr. San Isidro Integrated School | MANAY | 1 | 1 | 11 | Repair of Classrooms | 3495256 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Digos City | 206501 | Bagumbuhay ES | CITY OF DIGOS (Capital) | 1 | 1 | 3 | Repair of Classrooms | 765925 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Digos City | 129759 | Ruparan ES | CITY OF DIGOS (Capital) | 1 | 1 | 5 | Repair of Classrooms | 1956676 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Island Garden City of Samal | 128599 | Balet Elementary School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 14 | Repair of Classrooms | 6907504 | 1 |  | COMPLETED | 1 | [10 empty] | Rebid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Island Garden City of Samal | 128688 | Don Esteban Dasalla Elementary School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 7 | Repair of Classrooms | 2274970 | 1 |  | COMPLETED | 1 | [10 empty] | Rebid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Mati City | 304328 | Davao Oriental Regional Science High School | CITY OF MATI (Capital) | 2 | 1 | 13 | Repair of Classrooms | 5704593 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Mati City | 304326 | Mati SAT | CITY OF MATI (Capital) | 2 | 1 | 39 | Repair of Classrooms | 32082132 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Panabo City | 129807 | Katipunan ES | CITY OF PANABO | 2 | 1 | 3 | Repair of Classrooms | 1698435 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Panabo City | 207002 | San Francisco ES | CITY OF PANABO | 2 | 1 | 12 | Repair of Classrooms | 4516674 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Tagum City | 128774 | FLORENTINO CATALAN ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 19 | Repair of Classrooms | 6211673 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Compostela Valley | 128432 | Haguimitan ES | MONKAYO | 1 | 1 | 4 | Repair of Classrooms | 2397445.19 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Compostela Valley | 128358 | Pangi ES | MACO | 2 | 1 | 10 | Repair of Classrooms | 5102251.9 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129711 | A. Mabini Elementary School | DAVAO CITY | 1 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 495768.19 | 1 | 3872051.47 | COMPLETED | 1 | Nov. 26, 2021 |  |  |  | November 29- December 18, 2018 | December 6, 2018 | June 30, 2021 | February 18, 2019 | Sept. 27, 2021 | R. Fabale Construction Corporation | Repair of Classrooms kitchen, handwashing facility and gym | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129707 | M. Roxas ES | DAVAO CITY | 1 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 475510.91 | 1 |  | COMPLETED | 1 | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129645 | Maa CES | DAVAO CITY | 1 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 805542.56 | 1 | 1703807.3 | COMPLETED | 1 | Nov. 26, 2021 |  |  |  | November 29- December 18, 2018 | December 6, 2018 | June 30, 2021 | February 18, 2019 | Sept. 27, 2021 | R. Fabale Construction Corporation | Repair of Classrooms, handwashinf facility and gym | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129558 | Magallanes Elementary School | DAVAO CITY | 1 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 475510.91 | 1 | 2472841.95 | COMPLETED | 1 | Nov. 26, 2021 |  |  |  | November 29- December 18, 2018 | December 6, 2018 | June 30, 2021 | February 18, 2019 | Sept. 27, 2021 | R. Fabale Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129701 | San Roque CES | DAVAO CITY | 1 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 374518.99 | 1 | 5602823.14 | COMPLETED | 1 | Nov. 26, 2021 |  |  |  | November 29- December 18, 2018 | December 6, 2018 | June 30, 2021 | February 18, 2019 | Sept. 27, 2021 | R. Fabale Construction Corporation | Repair of Classroom and Gym | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129652 | Alejandra L. Navarro Central Elementary School | DAVAO CITY | 2 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 738689.89 | 1 |  | COMPLETED | 1 | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129523 | Daniel M. Perez Central Elem. School SPED Center | DAVAO CITY | 2 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 875966.74 | 1 |  | COMPLETED | 1 | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129479 | Dona Asuncion Hizon ES | DAVAO CITY | 2 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 615740.75 | 1 |  | COMPLETED | 1 | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129481 | F. Bustamante CES | DAVAO CITY | 2 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 629174.66 | 1 |  | COMPLETED | 1 | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129592 | Malabog CES | DAVAO CITY | 2 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 933530.71 | 1 |  | COMPLETED | 1 | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129513 | Teofilo Fernandez ES | DAVAO CITY | 2 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 614724.37 | 1 |  | COMPLETED | 1 | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129679 | Artemio Loyola Elementary School | DAVAO CITY | 3 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 490808.78 | 1 |  | COMPLETED | 1 | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129464 | Baguio Central Elementary School | DAVAO CITY | 3 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 499936.64 | 1 |  | COMPLETED | 1 | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129562 | Cabagbahangan Elementary School | DAVAO CITY | 3 | 1 | 6 | Repair of Classrooms | 5942117.4 | 1 |  | COMPLETED | 1 | Dec. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | MAG Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129548 | Don Juan Dela Cruz CES | DAVAO CITY | 3 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 622078.65 | 1 |  | COMPLETED | 1 | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129566 | General Roxas CES | DAVAO CITY | 3 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 995558.09 | 1 |  | COMPLETED | 1 | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129538 | Lt. C. Villafuerte, Sr. ES | DAVAO CITY | 3 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 470893.94 | 1 | 1584162.33 | COMPLETED | 1 | Nov. 26, 2021 |  |  |  | November 29- December 18, 2018 | December 6, 2018 | June 30, 2021 | February 18, 2019 | Sept. 27, 2021 | R. Fabale Construction Corporation | Repair of Classrooms | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129620 | Marilog Central ES | DAVAO CITY | 3 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 624178.98 | 1 |  | COMPLETED | 1 | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129503 | Tibuloy ES | DAVAO CITY | 3 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 615990.67 | 1 |  | COMPLETED | 1 | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation | Waiting for Sub-aro | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129743 | Tugbok Central ES SPED Center | DAVAO CITY | 3 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 339806.72 | 1 | 1735633.46 | COMPLETED | 1 | Nov. 26, 2021 |  |  |  | November 29- December 18, 2018 | December 6, 2018 | June 30, 2021 | February 18, 2019 | Sept. 27, 2021 | R. Fabale Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao del Norte | 128593 | San Vicente ES | ASUNCION (SAUG) | 1 | 1 | 5 | Repair of Classrooms | 3476488.37 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao del Norte | 305508 | Ramon S. Segundo Sr. NHS | KAPALONG | 1 | 1 | 3 | Repair of Classrooms | 2001811.05 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Del Norte | 128616 | Cabayangan ES | BRAULIO E. DUJALI | 2 | 1 | 8 | Repair of Classrooms | 6873708.32 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Del Norte | 128625 | Anibongan Elementary School | CARMEN | 2 | 1 | 11 | Repair of Classrooms | 7908251.72 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao del Norte | 128642 | Tibulao ES | CARMEN | 2 | 1 | 9 | Repair of Classrooms | 6465576.64 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Del Norte | 128748 | Kimamon ES | SANTO TOMAS | 2 | 1 | 12 | Repair of Classrooms | 8145121.93 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao del Sur | 129020 | New Visayas ES | MATANAO | 0 | 1 | 15 | Repair of Classrooms | 6736564 | 1 |  | COMPLETED | 1 | April 03, 2022 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Del Sur | 129048 | Mariano Sarona ES | PADADA | 0 | 1 | 11 | Repair of Classrooms | 4940752 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao del Sur | 129095 | Melilla ES | SANTA CRUZ | 0 | 1 | 6 | Repair of Classrooms | 3027305.38 | 1 |  | COMPLETED | 1 | March 18, 2022 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Occidental | 128989 | Bito ES | MALITA | 0 | 1 | 7 | Repair of Classrooms | 3854247.31 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Occidental | 128996 | Lagumit ES | MALITA | 0 | 1 | 4 | Repair of Classrooms | 2126569.22 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Occidental | 128964 | Mariano Calungsod Regis ES (Bolila ES) | MALITA | 0 | 1 | 6 | Repair of Classrooms | 3001616.31 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Occidental | 129124 | San Agustin ES | SANTA MARIA | 0 | 1 | 3 | Repair of Classrooms | 1174733.57 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Oriental | 129221 | Manorigao ES | CARAGA | 1 | 1 | 4 | Repair of Classrooms | 1993784.29 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Oriental | 129347 | Cudada Elementary School | MANAY | 1 | 1 | 4 | Repair of Classrooms | 2255626.86 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Oriental | 129457 | Ompao ES | TARRAGONA | 1 | 1 | 8 | Repair of Classrooms | 3422416.11 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Oriental | 129193 | T Patricio Elementary School | BANAYBANAY | 2 | 1 | 6 | Repair of Classrooms | 2745688.58 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Oriental | 129282 | Crispin Dela Cruz ES | GOVERNOR GENEROSO | 2 | 1 | 6 | Repair of Classrooms | 2888898.23 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Digos City | 129762 | Aplaya ES | CITY OF DIGOS (Capital) | 1 | 1 | 10 | Repair of Classrooms | 2589770.65 | 1 |  | COMPLETED | 1 | 1/16/2022 |  |  |  | 6/3-23/2021 | 2021-11-06 | 6-23-2021 |  |  | Johnray Developer and supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Digos City | 129773 | Apolandia ES | CITY OF DIGOS (Capital) | 1 | 1 | 4 | Repair of Classrooms | 1497687.25 | 1 |  | COMPLETED | 1 | 1/16/2022 |  |  |  | 6/3-23/2021 | 2021-11-06 | 6-23-2021 |  |  | Johnray Developer and supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Island Garden City of Samal | 128600 | Caliclic Elementary School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | Repair of Classrooms | 1201006.09 | 1 |  | COMPLETED | 1 | 11/14/2021 | [7 empty] | 08/25/2021 | R.Fabale Const. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Island Garden City of Samal | 128740 | Tagdaliao Elementary School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 6 | Repair of Classrooms | 3854976.55 | 1 |  | COMPLETED | 1 | 01/26/2022 | [7 empty] | 08/23/2021 | VGG Const. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Island Garden City of Samal | 128741 | Tagluno Elementary School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 4 | Repair of Classrooms | 3811228.62 | 1 |  | COMPLETED | 1 | 01/28/2022 | [7 empty] | 08/25/2021 | R.Fabale Const. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Island Garden City of Samal | 128742 | Tayapoc Elementary School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | Repair of Classrooms | 1242926.34 | 1 |  | COMPLETED | 1 | 2021-11-12 | [7 empty] | 08/23/2021 | VGG Const. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Mati City | 129392 | Cabubuanan Elementary School | CITY OF MATI (Capital) | 2 | 1 | 5 | Repair of Classrooms | 3143567.79 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Panabo City | 129802 | Consolacion ES | CITY OF PANABO | 2 | 1 | 8 | Repair of Classrooms | 5181337.4 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Panabo City | 304407 | Manay National High School | CITY OF PANABO | 2 | 1 | 10 | Repair of Classrooms | 6191526.15 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Panabo City | 129784 | Panabo Central Elementary School SPED Center | CITY OF PANABO | 2 | 1 | 21 | Repair of Classrooms | 12733272.03 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Panabo City | 129788 | San Vicente ES | CITY OF PANABO | 2 | 1 | 8 | Repair of Classrooms | 4464790.83 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Tagum City | 128789 | CABUGAN ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 8 | Repair of Classrooms | 3648846 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2022 | Region XI | Davao del Norte | 128581 | Mamangan ES | SAN ISIDRO | 1 | 1 | 13 | Repair of Classrooms & H.E. | 10020720 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region XI | Mati City | 129405 | Taguibo ES | CITY OF MATI (Capital) | 2 | 1 | 9 | Repair of Classrooms | 4550909.2 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region XI | Mati City | 129406 | Tamia ES | CITY OF MATI (Capital) | 2 | 1 | 4 | Repair of Classrooms | 2005144.53 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2023 | Region XI | Davao City | 304391 | Leon Garcia, Sr. NHS | DAVAO CITY | 2nd | 1 | 29 | Repair of Classrooms | 40800000 | DPWH (Batch 2) | 38977181.46 | COMPLETED | 1 | July 24, 2024 |  | 23LB0154 |  |  |  | NOV. 26, 2023 |  | Dec. 28, 2023 | MarkAnthony Construction and Supply JV Andrich Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 1 | 0 |  | 8.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Davao del Norte | 128592 | San Miguel ES | SAN ISIDRO | 1st | 1 | 7 | Repair of Classrooms | 6010957.9 | DPWH (Batch 2) | 5713620 | COMPLETED | 1 | May 16, 2024 |  | 23LC0084 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 1 | 0 |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Davao del Sur | 128855 | Hagonoy Central Elementary School | HAGONOY | 1st | 1 | 16 | Repair of Classrooms | 18000000 | DPWH (Batch 2) | 16883555.21 | COMPLETED | 1 |  |  | 23LD0116 |  | October 20, 2023 | November 07, 2023 | November 21, 2023 | December 27, 2023 | January 05, 2024 | ZJN DEVELOPMENT CONSTRUCTION AND SUPPLY CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 1 | 0 |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Davao del Sur | 316020 | San Isidro National High School | MAGSAYSAY | 1st | 1 | 11 | Repair of Classrooms | 10000000 | DPWH (Batch 2) | 9360500 | COMPLETED | 1 |  |  | 23LD0118 |  | October 27, 2023 | November 07, 2023 | November 21, 2023 | December 27, 2023 | January 05, 2024 | K & C BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 1 | 0 |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Davao del Sur | 304298 | Tacul Agricultural High School | MAGSAYSAY | 1st | 1 | 15 | Repair of Classrooms | 10000000 | DPWH (Batch 2) | 9360500 | COMPLETED | 1 |  |  | 23LD0124 |  | November 06, 2023 | November 14, 2023 | December 20, 2023 | December 29, 2023 | January 05, 2024 | K & C BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 1 | 0 |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Davao del Sur | 129030 | Bangkal Elementary School | MATANAO | 1st | 1 | 12 | Repair of Classrooms | 13000000 | DPWH (Batch 2) | 12168337.1 | COMPLETED | 1 |  |  | 23LD0119 |  | October 27, 2023 | November 07, 2023 | November 21, 2023 | December 27, 2023 | January 05, 2024 | UPSCALE BUILDERS AND SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Davao del Sur | 304289 | Bangkal National High School | MATANAO | 1st | 1 | 21 | Repair of Classrooms | 12000000 | DPWH (Batch 2) | 43386512.93 | COMPLETED | 1 |  |  | 23LD0125 |  | November 06, 2023 | November 14, 2023 | December 20, 2023 | December 29, 2023 | January 05, 2024 | MARK ANTHONY CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 1 | 0 |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Davao del Sur | 304288 | Matanao National High School | MATANAO | 1st | 1 | 55 | Repair of Classrooms | 45000000 | DPWH (Batch 2) | 11.206,363.31 | COMPLETED | 1 |  |  | 23LD0115 |  | October 06, 2023 | October 17, 2023 | November 07, 2023 | December 27, 2023 | January 05, 2024 | ZJN DEVELOPMENT CONSTRUCTION AND SUPPLY CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 1 | 0 |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Davao del Sur | 304290 | Sinawilan National High School | MATANAO | 1st | 1 | 18 | Repair of Classrooms | 12000000 | DPWH (Batch 2) | 11232448.14 | COMPLETED | 1 |  |  | 23LD0117 |  | October 20, 2023 | November 07, 2023 | November 21, 2023 | December 27, 2023 | January 05, 2024 | MJTP CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 1 | 0 |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Digos City | 129750 | Digos City CES | CITY OF DIGOS (Capital) | 1st | 1 | 12 | Repair of Classrooms | 3131629.88 | DPWH (Batch 1) | 2931437.84 | COMPLETED | 1 | 2024-01-17 |  | P00775431MN-CW1 | 23LD0112 | 2023-09-04 | 2023-09-12 | 2023-09-26 | 2023-10-10 | 2023-10-20 | PRISM BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 1 | 0 |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Digos City | 129760 | Jolencio R. Alberca ES (San Nicolas PS Annex) | CITY OF DIGOS (Capital) | 1st | 1 | 2 | Repair of Classrooms | 1018010.82 | DPWH (Batch 1) | 952939.83 | COMPLETED | 1 | 2024-01-17 |  | P00775432MN-CW1 | 23LD0112 | 2023-09-04 | 2023-09-12 | 2023-09-26 | 2023-10-10 | 2023-10-20 | PRISM BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Digos City | 316302 | Matti NHS | CITY OF DIGOS (Capital) | 1st | 1 | 8 | Repair of Classrooms | 1661267.66 | DPWH (Batch 1) | 1,586.551.66 | COMPLETED | 1 | 2024-01-17 |  | P00775434MN-CW1 | 23LD0113 | 2023-09-04 | 2023-09-12 | 2023-09-26 | 2023-10-10 | 2023-10-20 | TWO DEGREES CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Digos City | 304402 | Ruparan NHS | CITY OF DIGOS (Capital) | 1st | 1 | 17 | Repair of Classrooms | 5759036.56 | DPWH (Batch 1) | 5501087.21 | COMPLETED | 1 | 2024-01-17 |  | P00775435MN-CW1 | 23LD0112 | 2023-09-04 | 2023-09-12 | 2023-09-26 | 2023-10-10 | 2023-10-20 | PRISM BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 1 | 0 |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Digos City | 341513 | SHS in Digos City | CITY OF DIGOS (Capital) | 1st | 1 | 6 | Repair of Classrooms | 3344592.37 | DPWH (Batch 1) | 3130633.73 | COMPLETED | 1 | 2024-01-17 |  | P00775433MN-CW1 | 23LD0113 | 2023-09-04 | 2023-09-12 | 2023-09-26 | 2023-10-10 | 2023-10-20 | TWO DEGREES CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Mati City | 129410 | Brigido Rodriguez Sr. ES | CITY OF MATI (Capital) | 2nd | 1 | 5 | Repair of Classrooms | 3723083.07 | DPWH (Batch 1) | 3549395.75 | COMPLETED | 1 | 2024-03-24 |  | P00775437NP | 23LG0128 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-19 | 2023-09-27 | R. Baudon Construction & Supply Co. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Mati City | 304314 | Don Enrique Lopez NHS | CITY OF MATI (Capital) | 2nd | 1 | 11 | Repair of Classrooms | 6778613.71 | DPWH (Batch 1) | 6462670.2 | COMPLETED | 1 | 2024-06-03 |  | P00775440NP | 23LG0131 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-19 | 2023-09-27 | R. Baudon Construction & Supply Co. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 1 | 0 |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Mati City | 129414 | Francisco Hinayon ES | CITY OF MATI (Capital) | 2nd | 1 | 6 | Repair of Classrooms | 4936139.54 | DPWH (Batch 1) | 4706074.65 | COMPLETED | 1 | 2024-05-03 |  | P00775438NP | 23LG0129 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-19 | 2023-09-27 | R. Baudon Construction & Supply Co. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Mati City | 129419 | Gelacio G. Ytac ES | CITY OF MATI (Capital) | 2nd | 1 | 4 | Repair of Classrooms | 3337821.18 | DPWH (Batch 1) | 3181902.18 | COMPLETED | 1 | 2024-03-05 |  | P00775439NP | 23LG0130 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-19 | 2023-09-27 | R. Baudon Construction & Supply Co. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Mati City | 129381 | Rabat-Rocamora Mati CES II | CITY OF MATI (Capital) | 2nd | 1 | 15 | Repair of Classrooms | 9427396.36 | DPWH (Batch 1) | 8966747.84 | COMPLETED | 1 | 2024-07-11 |  | P00775436NP | 23LG0127 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-19 | 2023-09-27 | R. Baudon Construction & Supply Co. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 1 | 0 |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2024 | Region XI | Davao City | 129616 | Malakeba Elementary School | DAVAO CITY | 3rd | 1 | 6 | Repair of Classrooms | 10030702.93 | 1 |  | COMPLETED | 1 |  |  | BEFF L003-2024 |  | June 28-July 18, 2024 | July 5, 2024 | July 18, 2024 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region XI | Davao De Oro | 128266 | Mambusao ES | COMPOSTELA | 1st | 1 | 3 | Repair of Classrooms | 2308508.08 | 1 | 1781821.5339 | Completed | 1 | 2025-05-31 |  |  |  |  | 2024-10-01 | 2024-10-15 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0.79 | 0.21 |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region XI | Davao De Oro | 128443 | Muñoz ES | MONKAYO | 1st | 1 | 10 | Repair of Classrooms | 7123091.35 | 1 | 4937022.2021 | Completed | 1 | 2025-05-31 |  | SDD0-019-2024 |  | 9/23/2024 | 2024-10-01 | 2024-10-15 |  |  |  | REALIGNED FROM MANGAYOSN ES AND MONTEVISTA NHS TO MUNOZ ES | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0.89 | 0.11 |  | 5.25 | 2 | 10 | 7051860.44 |  | Ongoing
REPAIR 2024 | Region XI | Davao del Norte | 304224 | Datu Balong NHS | KAPALONG | 1st | 1 | 4 | Repair of Classrooms | 2077091.63 | 1 |  | Ongoing | 0.5 |  |  | # 2025-03-03 | # 2025-03-03 | 2024-11-11 | 2024-11-18 | 2024-12-02 | 2025-03-04 | 2025-03-28 | Matt Glass Aluminum/Const. Supply and Allied Services |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0.35 | 0.15 | [6 empty] | Ongoing
REPAIR 2024 | Region XI | Davao del Norte | 304251 | Sawata NHS | SAN ISIDRO | 1st | 1 | 4 | Repair of Classrooms | 2077091.63 | 1 |  | Ongoing | 0.4 |  |  | # 2025-03-03 | # 2025-03-03 | 2024-11-11 | 2024-11-18 | 2024-12-02 | 2025-03-04 | 2025-03-28 | Matt Glass Aluminum/Const. Supply and Allied Services |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0.35 | 0.05 | [6 empty] | Ongoing
REPAIR 2024 | Region XI | Davao del Norte | 304229 | Dujali National High School | BRAULIO E. DUJALI | 2nd | 1 | 6 | Repair of Classrooms | 3461819.38 | 1 |  | Ongoing | 0.6 |  |  | # 2025-03-03 | # 2025-03-03 | 2024-11-11 | 2024-11-18 | 2024-12-02 | 2025-03-04 | 2025-03-28 | Matt Glass Aluminum/Const. Supply and Allied Services |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0.35 | 0.25 | [6 empty] | Ongoing
REPAIR 2024 | Region XI | Davao del Sur | 128810 | Balagonon Elementary School | BANSALAN | 1st | 1 | 6 | Repair of Classrooms | 5005781.97 | 1 | 3764722.33 | COMPLETED | 1 | April 17, 2025 |  | DS-RRBATCH 1-2024-H-LOT 1 | DS-RRBATCH 1-2024-H-LOT 1 |  | August 12, 2024 | August 27, 2024 |  | November 18, 2024 | R.FABALE CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region XI | Davao del Sur | 128818 | New Clarin Elementary School | BANSALAN | 1st | 1 | 4 | Repair of Classrooms | 3337187.98 | 1 | 2429719.45 | COMPLETED | 1 | April 11, 2025 | April 8, 2025 | DS-RR BATCH 1-2024-H-LOT 2 | DS-RR BATCH 1-2024-H-LOT 2 |  | August 12, 2024 | August 27, 2024 |  | November 12, 2024 | BEBCON BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region XI | Davao del Sur | 128862 | Leoncio S. Peliño Elementary School | HAGONOY | 1st | 1 | 2 | Repair of Classrooms | 1668593.99 | 1 | 1200102.67 | COMPLETED | 1 | March 12, 2025 | Marcch 7, 2025 | DS-RR BATCH 1-2024-H-LOT 3 | DS-RR BATCH 1-2024-H-LOT 3 |  | August 12, 2024 | August 27, 2024 |  | November 12, 2024 | BEBCON BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region XI | Davao Occidental | 128839 | Dalupan Elementary School | DON MARCELINO | Lone | 1 | 3 | Repair of Classrooms | 2844029.61 | 1 | 2814474.66 | Ongoing | 0.9 | 150 CD from receipt of NTP |  | ITB W-07-2024 | no contract yet | July 11, 2024 to July 30, 2024 | July 17, 2024 | July 30, 2024 | Resolution no.19,s. 2024 dated August 09, 2024 |  |  | short of award; for NTP | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0.54 | 0.36 | [6 empty] | Ongoing
REPAIR 2024 | Region XI | Davao Occidental | 128850 | Jose Villanueva ES | DON MARCELINO | Lone | 1 | 4 | Repair of Classrooms | 3498371.17 | 1 | 3498371.17 | Ongoing | 0.9 | 150 CD from receipt of NTP |  | ITB W-08-2024 | no contract yet | July 11, 2024 to July 30, 2024 | July 17, 2024 | July 30, 2024 | Resolution no.20,s. 2024 dated August 09, 2024 |  |  | short of award; for NTP | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0.7 | 0.2 | [6 empty] | Ongoing
REPAIR 2024 | Region XI | Davao Occidental | 501416 | Aldo Pagagao Integrated School | JOSE ABAD SANTOS (TRINIDAD) | Lone | 1 | 8 | Repair of Classrooms | 1899160.34 | 1 | 1899160.34 | COMPLETED | 1 | 90 CD from receipt of NTP |  | ITB W-09-2024 | no contract yet | July 11, 2024 to July 30, 2024 | July 17, 2024 | July 30, 2024 | Resolution no.21,s. 2024 dated August 09, 2024 |  |  | short of award; for NTP | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region XI | Davao Oriental | 129206 | Alvar Elementary School | CARAGA | 1st | 1 | 6 | Repair of Classrooms | 4940110.88 | 1 | 3092025.3035 | COMPLETED | 1 | February 14, 2025 | February 13, 2024 | GS 2024 099 |  | July 9, 2024 | July 18, 2024 | July 30, 2024 | August 5, 2024 |  | PHSMB |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region XI | Davao Oriental | 129284 | Osmeña Elementary School | GOVERNOR GENEROSO | 2nd | 1 | 6 | Repair of Classrooms | 4345374.08 | 1 | 3225747.9097 | COMPLETED | 1 | February 7, 2025 | February 6, 2025 | GS 2024 100 |  | July 9, 2024 | July 18, 2024 | July 30, 2024 | August 5, 2024 |  | FAJR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 1 | 0 |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region XI | Digos City | 316302 | Matti NHS | CITY OF DIGOS (Capital) | 1st | 1 | 8 | Repair of Classrooms | 8080808.08 | 1 |  | COMPLETED | 1 | 2025-08-15 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0.27 | 0.73 |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region XI | Island Garden City of Samal | 301799 | Gamban Dadatan National High School | ISLAND GARDEN CITY OF SAMAL | 2nd | 1 | 2 | Repair of Classrooms | 1685858.59 | 1 | 1386639.61 | COMPLETED | 1 | 2024-12-15 | 2024-06-11 | INFRA002-062024 |  | June 28, 2024 | July 5, 2024 | July 23, 2024 | SEPTEMBER 5, 2024 | 2024-09-16 | KCK Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 |  | 12.24 |  |  |  |  | Completed
REPAIR 2024 | Region XI | Island Garden City of Samal | 304250 | Samal National High School | ISLAND GARDEN CITY OF SAMAL | 2nd | 1 | 5 | Repair of Classrooms | 2020202.02 | 1 | 1540056.56 | COMPLETED | 1 | 2025-05-04 | 2025-04-24 |  |  | 2024-10-15 | 2024-10-21 | 2024-11-04 | 2025-01-15 |  | R.Fabale Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region XI | Mati City | 129377 | Bagong Lipunan Improvement Site and Services Elementary School | CITY OF MATI (Capital) | 2nd | 1 | 11 | Repair of Classrooms | 8663125.15 | 1 | 8404964.1269 | COMPLETED | 1 | 2025-07-02 | 2025-03-03 |  |  | 2024-05-27 | 2024-06-04 | 2024-06-17 |  | 2024-09-25 | FAJR CONSTRUCTION PARTS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 1 | 0 |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region XI | Panabo City | 129781 | Cabili ES | CITY OF PANABO | 2nd | 1 | 4 | Repair of Classrooms | 2626262.63 | 1 |  | COMPLETED | 1 | 01/31/2025 |  |  | 2024-08-358 | AUG. 13, 2024 | AUG. 19, 2024 | SEPT.2, 2024 | AUG. 28, 2024 | 11/18/2024 | Najah Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | Region XI | Tagum City | 128787 | BINCUNGAN ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1st | 1 | 6 | Repair of Classrooms | 5757575.76 | 1 |  | under procurement | 0 | [10 empty] | FOR ADVERTISEMENT | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | under procurement