## Sheet1
INDEX (DO NOT MODIFY) | PROGRAM-YEAR | CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | BATCH | TOTAL PROJECT ALLOCATION | TOTAL PROJECT COST | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | TARGET COMPLETION DATE | ACTUAL DATE OF COMPLETION | PROJECT ID | CONTRACT ID | ISSUANCE OF INVITATION TO BID | PRE-SUBMISSION CONFERENCE | BID OPENING | ISSUANCE OF RESOLUTION TO AWARD | ISSUANCE OF NOTICE TO PROCEED | NAME OF CONTRACTOR | OTHER REMARKS | Status as of July 11, 2025
43058 | NC 2024 |  | BARMM | Isabela City | 303894 | Basilan NHS | CITY OF ISABELA (Capital) |  | 1 |  | 1-UNIT 4STY | GAA 17B | 40000000 |  |  | Not Yet Started | 0
43059 | NC 2024 |  | BARMM | Lamitan City | 304940 | Lo-ok National High School | CITY OF LAMITAN |  | 1 | 16 | 4STY16CL | GAA 17B | 40000000 |  |  | Not Yet Started | 0
43060 | NC 2024 |  | BARMM | Lanao del Sur - I | 133540 |  | BUMBARAN |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  |  | Not Yet Started | 0
43061 | NC 2024 |  | BARMM | Lanao del Sur - I | 133541 | Natangcopan PS | BUMBARAN |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  |  | Not Yet Started | 0
43062 | NC 2024 |  | BARMM | Lanao del Sur - I | 133276 | Sultan Alauya Alonto CES | DITSAAN-RAMAIN |  | 1 | 8 | 2STY8CL | BATCH 2 | 30000000 |  |  | Ongoing | 0
43063 | NC 2024 |  | BARMM | Lanao del Sur - I | 133348 | Loway Inudaran ES | MARANTAO |  | 1 | 8 | 2STY8CL | BATCH 2 | 30000000 |  |  | Ongoing | 0
43064 | NC 2024 |  | BARMM | Lanao del Sur - I | 133425 | Ragayan CES | POONA BAYABAO (GATA) |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  |  | Not Yet Started | 0
43065 | NC 2024 |  | BARMM | Lanao del Sur - I | 304972 | Pagalongan NHS | WAO |  | 1 | 12 | 3STY12CL | BATCH 2 | 42000000 |  |  | Ongoing | 0
43066 | NC 2024 |  | BARMM | Lanao del Sur - I | 133537 | South Park Area ES | WAO |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  |  | Not Yet Started | 0
43067 | NC 2024 |  | BARMM | Lanao del Sur - II | 324712 | Datu Raquib Zainodin National Highschool | MADALUM |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  |  | Not Yet Started | 0
43068 | NC 2024 |  | BARMM | Lanao del Sur - II | 133723 | Liangan Primary School | MADAMBA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
43069 | NC 2024 |  | BARMM | Lanao del Sur - II |  | Pagayonan National High School | MADAMBA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
43070 | NC 2024 |  | BARMM | Lanao del Sur - II | 133753 | Calimodan Vil. ES | MALABANG |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  |  | Not Yet Started | 0
43071 | NC 2024 |  | BARMM | Lanao del Sur - II | 133821 | Baraas Central School | SULTAN GUMANDER (PICONG) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
43072 | NC 2024 |  | BARMM | Lanao del Sur - II | 318233 | Balindong Pacalna National High School | TUGAYA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
43073 | NC 2024 |  | BARMM | Maguindanao del Sur | 305012 | Kauran NHS | AMPATUAN |  | 1 | 4 | 1STY4CL | BATCH 2 | 10000000 |  |  | Ongoing | 0
43074 | NC 2024 |  | BARMM | Maguindanao del Sur | 133933 | Bai Bagongan Paglas ES | BULUAN |  | 1 | 4 | 1STY4CL | BATCH 2 | 10000000 |  |  | Ongoing | 0
43075 | NC 2024 |  | BARMM | Maguindanao del Sur | 305028 | Tunggol NHS | DATU MONTAWAL (PAGAGAWAN) |  | 1 | 4 | 1STY4CL | BATCH 2 | 10000000 |  |  | Ongoing | 0
43076 | NC 2024 |  | BARMM | Maguindanao del Sur | 136971 | Datu Bandala Mamasabulod ES | PAGALUNGAN |  | 1 | 4 | 1STY4CL | BATCH 2 | 10000000 |  |  | Ongoing | 0
43077 | NC 2024 |  | BARMM | Maguindanao del Sur | 305022 | South Upi NHS | SOUTH UPI |  | 1 | 4 | 1STY4CL | BATCH 2 | 10000000 |  |  | Ongoing | 0
43078 | NC 2024 |  | BARMM | Maguindanao I | 133951 | Datu Paglas CS | DATU PAGLAS |  | 1 | 8 | 1STY8CL | GAA 17B | 20000000 |  |  | Not Yet Started | 0
43079 | NC 2024 |  | BARMM | Maguindanao I |  | Tocao - Madidis National High School | DATU PAGLAS |  | 1 | 8 | 1STY8CL | GAA 17B | 20000000 |  |  | Not Yet Started | 0
43080 | NC 2024 |  | BARMM | Maguindanao II |  | Pura ES | DATU BLAH T. SINSUAT |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
43081 | NC 2024 |  | BARMM | Maguindanao II | 216594 | Butilen Elementary School | KABUNTALAN (TUMBAO) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
43082 | NC 2024 |  | BARMM | Maguindanao II | 134033 | Maitong ES | KABUNTALAN (TUMBAO) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
43083 | NC 2024 |  | BARMM | Maguindanao II |  | Bayanga Norte ES | MATANOG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
43084 | NC 2024 |  | BARMM | Maguindanao II | 134158 | Alamada ES | SULTAN KUDARAT (NULING) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
43085 | NC 2024 |  | BARMM | Maguindanao II | 134143 | Ibotigen ES | SULTAN KUDARAT (NULING) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
43086 | NC 2024 |  | BARMM | Maguindanao II |  | Inawan ES | SULTAN KUDARAT (NULING) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
43087 | NC 2024 |  | BARMM | Maguindanao II | 134237 | Ranao Pilayan ES | UPI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
43088 | NC 2024 |  | BARMM | Marawi City | 134934 | Amai Pakpak CES | MARAWI CITY |  | 1 | 12 | 3STY12CL | BATCH 2 | 42000000 |  |  | Ongoing | 0
43089 | NC 2024 |  | BARMM | Sulu | 134444 | Bualoh Lipid ES | MAIMBUNG |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  |  | Not Yet Started | 0
43090 | NC 2024 |  | BARMM | Sulu |  | Sultan Jamalul Kiram Central High School | MAIMBUNG |  | 1 | 10 | 2STY10CL | GAA 17B | 40000000 |  |  | Not Yet Started | 0
43091 | NC 2024 |  | BARMM | Sulu |  | Patikul NHS - Extension | PATIKUL |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  |  | Not Yet Started | 0
43092 | NC 2024 |  | BARMM | Sulu | 134416 | Camp Andres CES | LUUK |  | 1 | 12 | 3STY12CL | GAA 17B | 40000000 |  |  | Not Yet Started | 0
43093 | NC 2024 |  | BARMM | Sulu | 252514 | Sapang PS | LUUK |  | 1 | 3 | 1STY3CL | BATCH 2 | 7329687.55 |  |  | Ongoing | 0
43094 | NC 2024 |  | BARMM | Sulu | 134439 | Tandu Bato ES | LUUK |  | 1 | 3 | 1STY3CL | BATCH 2 | 7329687.55 |  |  | Ongoing | 0
43095 | NC 2024 |  | BARMM | Tawi-Tawi | 134902 | Datu Halun Laboratory School | BONGAO |  | 1 | 2 | 1STY2CL | BATCH 2 | 5670312.45 |  |  | Ongoing | 0
43096 | NC 2024 |  | BARMM | Tawi-Tawi | 134716 | Lamion Walking (Main) ES | BONGAO |  | 1 | 2 | 1STY2CL | BATCH 2 | 5670312.45 |  |  | Ongoing | 0
43097 | NC 2024 |  | BARMM | Tawi-Tawi | 305066 | Tawi Tawi SAT | BONGAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
43098 | NC 2024 |  | BARMM | Tawi-Tawi | 305065 | Tawi-Tawi School of Fisheries | BONGAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
43099 | NC 2024 |  | BARMM | Tawi-Tawi | 134886 | Campo Muslim Primary School | LANGUYAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
43100 | NC 2024 |  | BARMM | Tawi-Tawi |  | Lupah Pula CS | MAPUN (CAGAYAN DE TAWI-TAWI) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
43101 | NC 2024 |  | BARMM | Tawi-Tawi | 305070 | UMMAT NHS | SIMUNUL |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
43102 | NC 2024 |  | BARMM | Tawi-Tawi | 134842 | Datu Halun CES | SITANGKAI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
43103 | NC 2024 |  | BARMM | Tawi-Tawi | 134848 | Tongusong ES | SITANGKAI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
43104 | NC 2024 |  | BARMM | Tawi-Tawi |  | Tabawan Stand Alone Senior High School | SOUTH UBIAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.