## Sheet1
INDEX (DO NOT MODIFY) | CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | TARGET COMPLETION DATE | ACTUAL DATE OF COMPLETION | PROJECT ID | CONTRACT ID | ISSUANCE OF INVITATION TO BID | PRE-SUBMISSION CONFERENCE | BID OPENING | ISSUANCE OF RESOLUTION TO AWARD | ISSUANCE OF NOTICE TO PROCEED | NAME OF CONTRACTOR | OTHER REMARKS | Status as of July 11, 2025
128 | REPAIR 2020 | CARAGA | Agusan del Norte | 131470 | LINGAYAO ES | LAS NIEVES | 1 | 1 | 9 | Repair of Classrooms | 2903241 | 1 | 2903240.3576 | COMPLETED | 1 | [9 empty] | J-R3 CONSTRUCTION
129 | REPAIR 2020 | CARAGA | Agusan del Norte | 131550 | F.S. OMAYANA ES | BUENAVISTA | 2 | 1 | 6 | Repair of Classrooms | 2730700 | 1 | 2730699.31 | COMPLETED | 1 | [9 empty] | BN BUILDERS
130 | REPAIR 2020 | CARAGA | Agusan del Norte | 131432 | CUYAGO ES | JABONGA | 2 | 1 | 11 | Repair of Classroom | 4005211 | 1 | 4005210.65 | COMPLETED | 1 | [9 empty] | J-R3 CONSTRUCTION
131 | REPAIR 2020 | CARAGA | Agusan del Norte | 131491 | Amontay ES | NASIPIT | 2 | 1 | 7 | Repair of Classroom | 2572830 | 1 | 2572829.178 | COMPLETED | 1 | [9 empty] | BN BUILDERS
132 | REPAIR 2020 | CARAGA | Agusan del Norte | 131501 | Punta ES | NASIPIT | 2 | 1 | 14 | Repair of Classrooms | 5392357 | 1 | 5392356.429 | COMPLETED | 1 | [9 empty] | ETP BUILDERS
133 | REPAIR 2020 | CARAGA | Agusan del Norte | 131504 | Talisay ES SPED Center | NASIPIT | 2 | 1 | 19 | Repair of Classrooms | 6812834 | 1 | 6812833.07 | COMPLETED | 1 | [9 empty] | RAMJEQUO CONSTRUCTION & SUPPLY
134 | REPAIR 2020 | CARAGA | Agusan del Sur | 131670 | Bunaguit ES | ESPERANZA | 1 | 1 | 7 | Repair of Classrooms | 4288273 | 1 | 907374.9027 | COMPLETED | 1 |  |  | 2020-03-01 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ABZKO Construction Corp. | with RTA
135 | REPAIR 2020 | CARAGA | Agusan del Sur | 131685 | Jose Calo Agudo ES | ESPERANZA | 1 | 1 | 11 | Repair of Classrooms | 5471524 | 1 | 831400.6127 | COMPLETED | 1 |  |  | 2020-03-01 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ABZKO Construction Corp. | with RTA
136 | REPAIR 2020 | CARAGA | Agusan del Sur | 131680 | Langag ES | ESPERANZA | 1 | 1 | 5 | Repair of Classrooms | 2981536 | 1 | 1295038.5106 | COMPLETED | 1 |  |  | 2020-03-01 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ABZKO Construction Corp. | with RTA
137 | REPAIR 2020 | CARAGA | Agusan del Sur | 131687 | Salug ES | ESPERANZA | 1 | 1 | 7 | Repair of Classrooms | 4100539 | 1 | 462674.3557 | COMPLETED | 1 |  |  | 2020-03-01 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ABZKO Construction Corp. | with RTA
138 | REPAIR 2020 | CARAGA | Agusan del Sur | 131690 | San Vicente PS | ESPERANZA | 1 | 1 | 4 | Repair of Classrooms | 2424897 | 1 | 1001764.8066 | COMPLETED | 1 |  |  | 2020-03-01 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ABZKO Construction Corp. | with RTA
139 | REPAIR 2020 | CARAGA | Agusan del Sur | 131695 | Tagbalili ES | ESPERANZA | 1 | 1 | 2 | Repair of Classroom | 1182367 | 1 | 1182366.719 | COMPLETED | 1 |  |  | 2020-03-02 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | MJS Const. & Supply | with RTA
140 | REPAIR 2020 | CARAGA | Agusan del Sur | 131730 | Loreto CES | LORETO | 1 | 1 | 17 | Repair of Classrooms | 7663991 | 1 | 1178086.9053 | COMPLETED | 1 |  |  | 2020-03-02 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | MJS Const. & Supply | with RTA
141 | REPAIR 2020 | CARAGA | Agusan del Sur | 304720 | Los Arcos NHS | PROSPERIDAD | 1 | 1 | 9 | Repair of Classrooms | 4495402 | 1 | 1456263.3134 | COMPLETED | 1 |  |  | 2020-03-02 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | MJS Const. & Supply | with RTA
142 | REPAIR 2020 | CARAGA | Agusan del Sur | 131775 | East Prosperidad Central Elementary School | PROSPERIDAD (Capital) | 1 | 1 | 19 | Repair of Classrooms | 9432657 | 1 | 3852452.9854 | COMPLETED | 1 |  |  | 2020-03-03 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ALCT Const. & Supply | with RTA
143 | REPAIR 2020 | CARAGA | Agusan del Sur | 131776 | La Caridad ES | PROSPERIDAD (Capital) | 1 | 1 | 5 | Repair of Classrooms | 4060509 | 1 | 3716862.9869 | COMPLETED | 1 |  |  | 2020-03-04 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | LGC Const. & Supply | with RTA
144 | REPAIR 2020 | CARAGA | Agusan del Sur | 131796 | La Purisima Elementary Schhol | PROSPERIDAD (Capital) | 1 | 1 | 3 | Repair of Classrooms | 1970778 | 1 | 5744341.7 | COMPLETED | 1 |  |  | 2020-03-08 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | LGC Const. & Supply | with RTA
145 | REPAIR 2020 | CARAGA | Agusan del Sur | 131803 | New Maug Elementary School | PROSPERIDAD (Capital) | 1 | 1 | 10 | Repair of Classrooms | 5847856 | 1 | 5847855.9534 | COMPLETED | 1 |  |  | 2020-03-09 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ALCT Const. & Supply | with RTA
146 | REPAIR 2020 | CARAGA | Agusan del Sur | 131781 | New Visayas ES | PROSPERIDAD (Capital) | 1 | 1 | 3 | Repair of Classrooms | 1817798 | 1 | 4495401.9091 | COMPLETED | 1 |  |  | 2020-03-05 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | JB Ciano Const. | with RTA
147 | REPAIR 2020 | CARAGA | Agusan del Sur | 131782 | Pakwan ES | PROSPERIDAD (Capital) | 1 | 1 | 6 | Repair of Classrooms | 3673954 | 1 | 5471523.1407 | COMPLETED | 1 |  |  | 2020-03-06 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | JB Ciano Const. | with RTA
148 | REPAIR 2020 | CARAGA | Agusan del Sur | 131786 | SAN RAFAEL ES | PROSPERIDAD (Capital) | 1 | 1 | 8 | Repair of Classrooms | 3852453 | 1 | 5635792.4023 | COMPLETED | 1 |  |  | 2020-03-07 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | LGC Const. & Supply | with RTA
149 | REPAIR 2020 | CARAGA | Agusan del Sur | 131936 | Anislagan ES | SAN LUIS | 1 | 1 | 11 | Repair of Classrooms | 5744342 | 1 | 6181298.8776 | COMPLETED | 1 |  |  | 2020-03-10 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | LGC Const. & Supply | with RTA
150 | REPAIR 2020 | CARAGA | Agusan del Sur | 131940 | Cecilia Elementary School | SAN LUIS | 1 | 1 | 7 | Repair of Classrooms | 3946733 | 1 | 7663990.16 | COMPLETED | 1 |  |  | 2020-03-11 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | DAVE Const. | with RTA
151 | REPAIR 2020 | CARAGA | Agusan del Sur | 131945 | Dimasalang ES | SAN LUIS | 1 | 1 | 6 | Repair of Classrooms | 3716863 | 1 | 8167662.9 | COMPLETED | 1 |  |  | 2020-03-12 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ROCK Diwata Builders Inc. | with RTA
152 | REPAIR 2020 | CARAGA | Agusan del Sur | 131947 | Dona Maxima ES | SAN LUIS | 1 | 1 | 11 | Repair of Classrooms | 6181299 | 1 | 4560096.22 | COMPLETED | 1 |  |  | 2020-03-13 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ALCT Const. & Supply | with RTA
153 | REPAIR 2020 | CARAGA | Agusan del Sur | 131966 | Sta. Ines ES | SAN LUIS | 1 | 1 | 10 | Repair of Classrooms | 5635793 | 1 | 4453513.48 | COMPLETED | 1 |  |  | 2020-03-14 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | JM Lacorte Const. | with RTA
154 | REPAIR 2020 | CARAGA | Agusan del Sur | 131864 | Banag-banag ES | SIBAGAT | 1 | 1 | 6 | Repair of Classrooms | 3552946 | 1 | 4318652.22 | COMPLETED | 1 |  |  | 2020-03-15 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ABM1 Builders and Supply | with RTA
155 | REPAIR 2020 | CARAGA | Agusan del Sur | 131865 | Causwagan ES | SIBAGAT | 1 | 1 | 4 | Repair of Classrooms | 2055354 | 1 | 4288272.53 | COMPLETED | 1 |  |  | 2020-03-16 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | JB Ciano Const. | with RTA
156 | REPAIR 2020 | CARAGA | Agusan del Sur | 131868 | El Rio ES | SIBAGAT | 1 | 1 | 9 | Repair of Classrooms | 4453514 | 1 | 4100538.81 | COMPLETED | 1 |  |  | 2020-03-17 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | LM Const. & Gen. Mrkt | with RTA
157 | REPAIR 2020 | CARAGA | Agusan del Sur | 131872 | Kolambugan ES | SIBAGAT | 1 | 1 | 6 | Repair of Classrooms | 3208468 | 1 | 4060508.52 | COMPLETED | 1 |  |  | 2020-03-18 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | LM Const. & Gen. Mrkt | with RTA
158 | REPAIR 2020 | CARAGA | Agusan del Sur | 131876 | Mahayahay ES | SIBAGAT | 1 | 1 | 3 | Repair of Classrooms | 1725552 | 1 | 3946732.94 | COMPLETED | 1 |  |  | 2020-03-19 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | MJS Const. & Supply | with RTA
159 | REPAIR 2020 | CARAGA | Agusan del Sur | 131879 | Padiay ES | SIBAGAT | 1 | 1 | 6 | Repair of Classrooms | 3487766 | 1 | 3673953.75 | COMPLETED | 1 |  |  | 2020-03-20 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | LM Const. & Gen. Mrkt | with RTA
160 | REPAIR 2020 | CARAGA | Agusan del Sur | 131884 | San Roque ES | SIBAGAT | 1 | 1 | 2 | Repair of Classroom | 1178087 | 1 | 3552945.88 | COMPLETED | 1 |  |  | 2020-03-21 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | MJS Const. & Supply | with RTA
161 | REPAIR 2020 | CARAGA | Agusan del Sur | 131885 | San Vicente ES | SIBAGAT | 1 | 1 | 4 | Repair of Classrooms | 2060098 | 1 | 3487765.53 | COMPLETED | 1 |  |  | 2020-03-22 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ABZKO Construction Corp. | with RTA
162 | REPAIR 2020 | CARAGA | Agusan del Sur | 131886 | Senai ES | SIBAGAT | 1 | 1 | 3 | Repair of Classrooms | 1456264 | 1 | 3208467.21 | COMPLETED | 1 |  |  | 2020-03-23 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | INNOVATI Const. | with RTA
163 | REPAIR 2020 | CARAGA | Agusan del Sur | 304740 | SIBAGAT NATIONAL HIGH SCHOOL OF HOME INDUSTRIES | SIBAGAT | 1 | 1 | 16 | Repair of Classrooms | 8167663 | 1 | 2270701.7098 | COMPLETED | 1 |  |  | 2020-03-24 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | DAVE Const. | with RTA
164 | REPAIR 2020 | CARAGA | Agusan del Sur | 131890 | Tabontabon ES | SIBAGAT | 1 | 1 | 8 | Repair of Classrooms | 4560097 | 1 | 1750631.0447 | COMPLETED | 1 |  |  | 2020-03-24 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | DAVE Const. | with RTA
165 | REPAIR 2020 | CARAGA | Agusan del Sur | 131971 | Causwagan ES | TALACOGON | 1 | 1 | 9 | Repair of Classrooms | 4318653 | 1 | 1817797.7461 | COMPLETED | 1 |  |  | 2020-03-25 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ABZKO Construction Corp. | with RTA
166 | REPAIR 2020 | CARAGA | Agusan del Sur | 131976 | Culi-Ram ES | TALACOGON | 1 | 1 | 4 | Repair of Classroom | 2035852 | 1 | 1970777.2701 | COMPLETED | 1 |  |  | 2020-03-25 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ABZKO Construction Corp. | with RTA
167 | REPAIR 2020 | CARAGA | Agusan del Sur | 131648 | Antioquia ES | BUNAWAN | 2 | 1 | 2 | Repair of Classrooms | 907375 | 1 | 4318652.22 | COMPLETED | 1 |  |  | 2020-03-26 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | INNOVATI Const. | with RTA
168 | REPAIR 2020 | CARAGA | Agusan del Sur | 131657 | Libertad ES | BUNAWAN | 2 | 1 | 19 | Repair of Classrooms | 8861401 | 1 | 1725551.4142 | COMPLETED | 1 |  |  | 2020-03-26 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | INNOVATI Const. | with RTA
169 | REPAIR 2020 | CARAGA | Agusan del Sur | 212013 | Singanan ES | BUNAWAN | 2 | 1 | 3 | Repair of Classrooms | 1815620 | 1 | 2035851.1157 | COMPLETED | 1 |  |  | 2020-03-27 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ABM1 Builders and Supply | with RTA
170 | REPAIR 2020 | CARAGA | Agusan del Sur | 131752 | Halapitan Elementary School | LA PAZ | 2 | 1 | 5 | Repair of Classrooms | 2540328 | 1 | 1815619.0454 | COMPLETED | 1 |  |  | 2020-03-27 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ABM1 Builders and Supply | with RTA
171 | REPAIR 2020 | CARAGA | Agusan del Sur | 212006 | Ferdinand-Sabud ES | LORETO | 2 | 1 | 3 | Repair of Classrooms | 2270702 | 1 | 2060097.3697 | COMPLETED | 1 |  |  | 2020-03-29 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | LM Const. & Gen. Mrkt | with RTA
172 | REPAIR 2020 | CARAGA | Agusan del Sur | 212047 | SIKAT PANLABUAN PS | LORETO | 2 | 1 | 2 | Repair of Classrooms | 831401 | 1 |  | COMPLETED | 1
173 | REPAIR 2020 | CARAGA | Agusan del Sur | 131744 | Sto Nino ES | LORETO | 2 | 1 | 3 | Repair of Classrooms | 1750632 | 1 | 2424896.3867 | COMPLETED | 1 |  |  | 2020-03-29 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | LM Const. & Gen. Mrkt | with RTA
174 | REPAIR 2020 | CARAGA | Agusan del Sur | 304744 | Sta. Cruz NHS | ROSARIO | 2 | 1 | 9 | Repair of Classrooms | 4617364 | 1 |  | COMPLETED | 1 | [10 empty] | FOR FURTHER INVESTIGATION OF DOCUMENTS SUBMITTED DURING BIDDING
175 | REPAIR 2020 | CARAGA | Agusan del Sur | 131850 | BY Tumulak ES | SAN FRANCISCO | 2 | 1 | 1 | Repair of Classroom | 462675 | 1 |  | COMPLETED | 1
176 | REPAIR 2020 | CARAGA | Agusan del Sur | 131853 | Lapinigan CES with SPED Program | SAN FRANCISCO | 2 | 1 | 22 | Repair of Classrooms | 9485939 | 1 |  | COMPLETED | 1 | [10 empty] | with RTA
177 | REPAIR 2020 | CARAGA | Agusan del Sur | 131929 | San Pascual ES | SANTA JOSEFA | 2 | 1 | 14 | Repair of Classrooms | 6598983 | 1 |  | COMPLETED | 1 | [10 empty] | FOR FURTHER INVESTIGATION OF DOCUMENTS SUBMITTED DURING BIDDING
178 | REPAIR 2020 | CARAGA | Agusan del Sur | 132008 | Pulanglupa ES | TRENTO | 2 | 1 | 2 | Repair of Classrooms | 1001765 | 1 |  | COMPLETED | 1
179 | REPAIR 2020 | CARAGA | Agusan del Sur | 132010 | Salvacion ES | TRENTO | 2 | 1 | 10 | Repair of Classrooms | 5466058 | 1 |  | COMPLETED | 1 | [10 empty] | FOR FURTHER INVESTIGATION OF DOCUMENTS SUBMITTED DURING BIDDING
180 | REPAIR 2020 | CARAGA | Agusan del Sur | 317438 | San Roque NHS | TRENTO | 2 | 1 | 2 | Repair of Classroom | 1295039 | 1 |  | COMPLETED | 1
181 | REPAIR 2020 | CARAGA | Agusan del Sur | 304753 | Trento NHS | TRENTO | 2 | 1 | 11 | Repair of Classrooms | 6902023 | 1 |  | COMPLETED | 1 | [10 empty] | FOR FURTHER INVESTIGATION OF DOCUMENTS SUBMITTED DURING BIDDING
182 | REPAIR 2020 | CARAGA | Agusan del Sur | 131922 | Veruela Central Elementary School | VERUELA | 2 | 1 | 14 | Repair of Classrooms | 6211205 | 1 |  | COMPLETED | 1 | [10 empty] | FOR FURTHER INVESTIGATION OF DOCUMENTS SUBMITTED DURING BIDDING
183 | REPAIR 2020 | CARAGA | Bayugan City | 131600 | Katipunan ES | Bayugan City | 1 | 1 | 7 | Repair of Classrooms | 3279775 | 1 |  | COMPLETED | 1 |  |  | 2020-001 | 2020-001 | [5 empty] | ALCT Construction & Supply
184 | REPAIR 2020 | CARAGA | Bayugan City | 131601 | Kiawan ES | Bayugan City | 1 | 1 | 3 | Repair of Classrooms | 1533187 | 1 |  | COMPLETED | 1 |  |  | 2020-002 | 2020-002 | [5 empty] | ALCT Construction & Supply
185 | REPAIR 2020 | CARAGA | Bayugan City | 131636 | New Leyte ES | Bayugan City | 1 | 1 | 5 | Repair of Classrooms | 2208541 | 1 |  | COMPLETED | 1 |  |  | 2020-004 | 2020-004 | [5 empty] | MAIR Construction General Merchandise
186 | REPAIR 2020 | CARAGA | Bayugan City | 131611 | San Isidro ES | Bayugan City | 1 | 1 | 6 | Repair of Classrooms | 3082265 | 1 |  | COMPLETED | 1 |  |  | 2020-003 | 2020-003 | [5 empty] | ETP Builders
187 | REPAIR 2020 | CARAGA | Bislig City | 322503 | Bucto NHS | CITY OF BISLIG | 2 | 1 | 2 | Repair of Classrooms | 803075 | 1 | 803074.81 | COMPLETED | 1 | December 22, 2020 | January 04, 2021 | REPAIR2020_CLUSTER1 | REPAIR2020_CLUSTER1 | Nov. 29, 2019 | Dec. - 06, 2019 | Dec. 18, 2019 | Jan. 06, 2020 | Sept. 17,2020 | MN Bayalas Construction | Waiting for the Sub-ARO to release
188 | REPAIR 2020 | CARAGA | Bislig City | 132613 | Coleto ES | CITY OF BISLIG | 2 | 1 | 3 | Repair of Classrooms | 1142992 | 1 | 1142991.99 | COMPLETED | 1 | December 22, 2020 | January 04, 2021 | REPAIR2020_CLUSTER1 | REPAIR2020_CLUSTER1 | Nov. 29, 2019 | Dec. - 06, 2019 | Dec. 18, 2019 | Jan. 06, 2020 | Sept. 17,2020 | MN Bayalas Construction | Waiting for the Sub-ARO to release
189 | REPAIR 2020 | CARAGA | Bislig City | 132615 | F. C. Pedraverde-Lindo ES | CITY OF BISLIG | 2 | 1 | 3 | Repair of Classrooms | 1138775 | 1 | 1138774.04 | COMPLETED | 1 | December 22, 2020 | January 04, 2021 | REPAIR2020_CLUSTER1 | REPAIR2020_CLUSTER1 | Nov. 29, 2019 | Dec. - 06, 2019 | Dec. 18, 2019 | Jan. 06, 2020 | Sept. 17,2020 | MN Bayalas Construction | Waiting for the Sub-ARO to release
190 | REPAIR 2020 | CARAGA | Bislig City | 132617 | Gerardo D. Verano Jr. E.S | CITY OF BISLIG | 2 | 1 | 3 | Repair of Classrooms | 1212729 | 1 | 1212728.01 | COMPLETED | 1 | December 22, 2020 | January 04, 2021 | REPAIR2020_CLUSTER2 | REPAIR2020_CLUSTER2 | Nov. 29, 2019 | Dec. - 06, 2019 | Dec. 18, 2019 | Jan. 06, 2020 | Sept. 17,2020 | MN Bayalas Construction | Waiting for the Sub-ARO to release
191 | REPAIR 2020 | CARAGA | Bislig City | 132836 | Mangagoy North ES | CITY OF BISLIG | 2 | 1 | 4 | Repair of Classrooms | 1612102 | 1 | 1612101.25 | COMPLETED | 1 | December 22, 2020 | January 04, 2021 | REPAIR2020_CLUSTER2 | REPAIR2020_CLUSTER2 | Nov. 29, 2019 | Dec. - 06, 2019 | Dec. 18, 2019 | Jan. 06, 2020 | Sept. 17,2020 | MN Bayalas Construction | Waiting for the Sub-ARO to release
192 | REPAIR 2020 | CARAGA | Bislig City | 132626 | Pamaypayan ES | CITY OF BISLIG | 2 | 1 | 2 | Repair of Classrooms | 803085 | 1 | 803084.8 | COMPLETED | 1 | December 22, 2020 | January 04, 2021 | REPAIR2020_CLUSTER2 | REPAIR2020_CLUSTER2 | Nov. 29, 2019 | Dec. - 06, 2019 | Dec. 18, 2019 | Jan. 06, 2020 | Sept. 17,2020 | MN Bayalas Construction | Waiting for the Sub-ARO to release
193 | REPAIR 2020 | CARAGA | Butuan City | 132074 | F.R. Sibayan Central Elem. School | BUTUAN CITY (Capital) | 1 | 1 | 12 | Repair of Classrooms | 4634588 | 1 |  | COMPLETED | 1 | 2021-04-01 | [8 empty] | Two J.E. Construction and Supply
194 | REPAIR 2020 | CARAGA | Butuan City | 500317 | La Soledad ES | BUTUAN CITY (Capital) | 1 | 1 | 9 | Repair of Classrooms | 4477443 | 1 |  | COMPLETED | 1 | 2021-04-01 | [8 empty] | Two J.E. Construction and Supply
195 | REPAIR 2020 | CARAGA | Butuan City | 212501 | West Central ES | BUTUAN CITY (Capital) | 1 | 1 | 19 | Repair of Classrooms | 5446943 | 1 |  | COMPLETED | 1 | 2021-04-01 | [8 empty] | Two J.E. Construction and Supply
196 | REPAIR 2020 | CARAGA | Cabadbaran City | 131573 | Bay-ang ES | CITY OF CABADBARAN | 2 | 1 | 8 | Repair of Classrooms | 2253162 | 1 | 2253161.11 | COMPLETED | 1 |  |  |  |  | DECEMBER 10, 2019 | DECEMBER 17,2019 | JANUARY 6, 2020 | FEBRUARY 3, 2020 |  | 3C'SL CONSTRUCTION & SUPPLY
197 | REPAIR 2020 | CARAGA | Cabadbaran City | 131576 | La Union ES | CITY OF CABADBARAN | 2 | 1 | 21 | Repair of Classrooms | 6710617 | 1 | 6710616.93 | COMPLETED | 1 |  |  |  |  | DECEMBER 10, 2019 | DECEMBER 17,2019 | JANUARY 6, 2020 | FEBRUARY 3, 2020 |  | JY BONTILAO CONSTRUCTION & ENTERPRISE
198 | REPAIR 2020 | CARAGA | Dinagat Island | 132502 | Paniog ES | BASILISA (RIZAL) | 0 | 1 | 6 | Repair of Classrooms | 2498907 | 1 | 2498906.76 | COMPLETED | 1
199 | REPAIR 2020 | CARAGA | Dinagat Island | 132508 | Sombrado ES | BASILISA (RIZAL) | 0 | 1 | 2 | Repair of Classrooms | 1161567 | 1 |  | COMPLETED | 1
200 | REPAIR 2020 | CARAGA | Dinagat Island | 132511 | Taliman ES | BASILISA (RIZAL) | 0 | 1 | 2 | Repair of Classrooms | 1214000 | 1 | 1214000 | COMPLETED | 1
201 | REPAIR 2020 | CARAGA | Dinagat Island | 132512 | Villa Ecleo ES | BASILISA (RIZAL) | 0 | 1 | 4 | Repair of Classrooms | 1609125 | 1 | 1609124.16 | COMPLETED | 1
202 | REPAIR 2020 | CARAGA | Dinagat Island | 132552 | Imelda ES | TUBAJON | 0 | 1 | 3 | Repair of Classrooms | 1765000 | 1 | 1765000 | COMPLETED | 1
203 | REPAIR 2020 | CARAGA | Siargao | 132143 | San Miguel Elementary School | Dapa | 1 | 1 | 2 | Repair of Classroom | 970000 | 1 | 970000 | COMPLETED | 1 |  |  | BEFF-INFRA2020-007 | BEFF-INFRA2020-007 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO
204 | REPAIR 2020 | CARAGA | Siargao | 132133 | Sta. Felomina Elementary School | Dapa | 1 | 1 | 2 | Repair of Classroom | 997000 | 1 | 997000 | COMPLETED | 1 |  |  | BEFF-INFRA2020-011 | BEFF-INFRA2020-011 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO
205 | REPAIR 2020 | CARAGA | Siargao | 132164 | Bitoon Elementary School | Del Carmen | 1 | 1 | 5 | Repair of Classroom | 1995000 | 1 | 1995000 | COMPLETED | 1 |  |  | BEFF-INFRA2020-010 | BEFF-INFRA2020-010 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO
206 | REPAIR 2020 | CARAGA | Siargao | 132167 | Dumoyog Elementary School | DEL CARMEN | 1 | 1 | 3 | Repair of Classrooms | 2223000 | 1 | 2223000 | COMPLETED | 1 |  |  | BEFF-INFRA2020-001 | BEFF-INFRA2020-001 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO
207 | REPAIR 2020 | CARAGA | Siargao | 132178 | San Fernando Elementary Schoo | Del Carmen | 1 | 1 | 3 | Repair of Classroom | 1497000 | 1 | 1497000 | COMPLETED | 1 |  |  | BEFF-INFRA2020-006 | BEFF-INFRA2020-006 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO
208 | REPAIR 2020 | CARAGA | Siargao | 132145 | Anajawan Elementary School | GEN. LUNA | 1 | 1 | 3 | Repair of Classrooms | 1694000 | 1 | 1694000 | COMPLETED | 1 |  |  | BEFF-INFRA2020-002 | BEFF-INFRA2020-002 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO
209 | REPAIR 2020 | CARAGA | Siargao | 132158 | Sta. Cruz Elementary School | Gen. Luna | 1 | 1 | 3 | Repair of Classroom | 1596000 | 1 | 1596000 | COMPLETED | 1 |  |  | BEFF-INFRA2020-008 | BEFF-INFRA2020-008 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO
210 | REPAIR 2020 | CARAGA | Siargao | 132226 | Maribojoc Elementary School | San Benito | 1 | 1 | 3 | Repair of Classroom | 1397000 | 1 | 1397000 | COMPLETED | 1 |  |  | BEFF-INFRA2020-013 | BEFF-INFRA2020-013 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO
211 | REPAIR 2020 | CARAGA | Siargao | 132201 | Sta. Paz Elementary School | San Isidro | 1 | 1 | 3 | Repair of Classroom | 1197000 | 1 | 1197000 | COMPLETED | 1 |  |  | BEFF-INFRA2020-014 | BEFF-INFRA2020-014 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO
212 | REPAIR 2020 | CARAGA | Siargao | 132205 | Abad Santos Elementary School | SANTA MONICA (SAPAO) | 1 | 1 | 4 | Repair of Classrooms | 1066000 | 1 | 1066000 | COMPLETED | 1 |  |  | BEFF-INFRA2020-003 | BEFF-INFRA2020-003 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO
213 | REPAIR 2020 | CARAGA | Siargao | 132213 | Sapao Central Elementary School | SANTA MONICA (SAPAO) | 1 | 1 | 6 | Repair of Classroom | 2495000 | 1 | 2495000 | COMPLETED | 1 |  |  | BEFF-INFRA2020-005 | BEFF-INFRA2020-005 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO
214 | REPAIR 2020 | CARAGA | Siargao | 213001 | Atoyay Elementary School | SOCORRO | 1 | 1 | 5 | Repair of Classroom | 2990000 | 1 | 2990000 | COMPLETED | 1 |  |  | BEFF-INFRA2020-009 | BEFF-INFRA2020-009 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO
215 | REPAIR 2020 | CARAGA | Siargao | 132222 | Lanit ag Elementary School | SOCORRO | 1 | 1 | 1 | Repair of Classroom | 509000 | 1 | 509000 | COMPLETED | 1 |  |  | C1-BEFF-INFRA2020-004 | C1-BEFF-INFRA2020-004 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO
216 | REPAIR 2020 | CARAGA | Siargao | 132233 | Lawigan Primary School | SOCORRO | 1 | 1 | 1 | Repair of Classroom | 509000 | 1 | 509000 | COMPLETED | 1 |  |  | C1-BEFF-INFRA2020-004 | C1-BEFF-INFRA2020-004 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO
217 | REPAIR 2020 | CARAGA | Siargao | 132223 | N. Sering Comm. Elementary School | SOCORRO | 1 | 1 | 5 | Repair of Classroom | 1995000 | 1 | 1995000 | COMPLETED | 1 |  |  | BEFF-INFRA2020-012 | BEFF-INFRA2020-012 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO
218 | REPAIR 2020 | CARAGA | Surigao City | 304792 | Juan P. Cedro Sr. Memorial High Schoo | SURIGAO CITY (Capital) | 2 | 1 | 7 | Repair of Classrooms | 2071556 | 1 |  | COMPLETED | 1
219 | REPAIR 2020 | CARAGA | Surigao City | 132259 | San Jose Elementary School | SURIGAO CITY (Capital) | 2 | 1 | 6 | Repair of Classrooms | 1776000 | 1 |  | COMPLETED | 1
220 | REPAIR 2020 | CARAGA | Surigao City | 304807 | San Jose NHS | SURIGAO CITY (Capital) | 2 | 1 | 4 | Repair of Classrooms | 1347653 | 1 |  | COMPLETED | 1
221 | REPAIR 2020 | CARAGA | Surigao del Norte | 304811 | Alegria NHS | Alegria | 2 | 1 | 24 | Repair of Classrooms | 5798611 | 1 | 5798610.29 | COMPLETED | 1 |  |  | 001-BEFF 2020 | 002-2020 | 2020-01-27 | 2020-02-04 | 2020-02-21 | 2020-03-16 |  | Kent Marketing Group of Companies, Inc.
222 | REPAIR 2020 | CARAGA | Surigao del Norte | 132329 | San Pedro ES | Alegria | 2 | 1 | 13 | Repair of Classrooms | 3270493 | 1 | 3270492.73 | COMPLETED | 1 |  |  | 002-BEFF 2020 | 001-2020 | 2020-01-27 | 2020-02-04 | 2020-02-21 | 2020-03-16 |  | Kent Marketing Group of Companies, Inc.
223 | REPAIR 2020 | CARAGA | Surigao del Norte | 132452 | Bunyasan ES | Malimono | 2 | 1 | 7 | Repair of Classrooms | 2019600 | 1 | 2019600 | COMPLETED | 1 |  |  | 003-BEFF 2020 | 003-2020 | 2020-01-27 | 2020-02-04 | 2020-02-21 | 2020-03-16 |  | Windfall Construction
224 | REPAIR 2020 | CARAGA | Surigao del Sur | 132657 | Buntalid Elementary School | Cantilan | 1 | 1 | 5 | Repair of Classrooms | 3000472 | 1 | 2142064.8 | COMPLETED | 1 | 2021-05-13 | 2021-05-07 |  | 2020-008 | [5 empty] | Baicamar Const. and Supplies Inc.
225 | REPAIR 2020 | CARAGA | Surigao del Sur | 132662 | Consuelo Elementary School | Cantilan | 1 | 1 | 7 | Repair of Classrooms | 4710678 | 1 | 3042188.77 | COMPLETED | 1 | 2021-05-10 | 2021-04-20 |  | 2020-009 | [5 empty] | FP Alonto Construction Services
226 | REPAIR 2020 | CARAGA | Surigao del Sur | 132702 | Segunda R. Cuajao Memorial Elementary School | Carrascal | 1 | 1 | 8 | Repair of Classrooms | 5040089 | 1 | 5004887.78 | COMPLETED | 1 | 2021-05-13 | 2021-05-12 |  | 2020-010 | [5 empty] | LPO1 Group of Companies
227 | REPAIR 2020 | CARAGA | Surigao del Sur | 132734 | Hinatuan North Central Elementary School | Hinatuan | 2 | 1 | 19 | Repair of Classrooms | 10342438 | 1 | 7676915.81 | COMPLETED | 1 | 2021-05-10 |  |  | 2020-011 | [5 empty] | J-R3 Construction Supply
228 | REPAIR 2020 | CARAGA | Surigao del Sur | 132807 | Pedro Redondo Elementary School- (Island School Site) | Lingig | 2 | 1 | 5 | Repair of Classrooms | 3415232 | 1 | 2877023.17 | COMPLETED | 1 | 2021-05-10 | 2021-08-12 |  | 2020-012 | [5 empty] | J-R3 Construction Supply
229 | REPAIR 2020 | CARAGA | Surigao del Sur | 132814 | Tagpupuran Elementary School | Lingig | 2 | 1 | 6 | Repair of Classrooms | 3470586 | 1 | 2569826.08 | COMPLETED | 1 | 2021-05-10 | 2021-08-12 |  | 2020-013 | [5 empty] | Jimberns Builders and Construction Supply
230 | REPAIR 2020 | CARAGA | Tandag City | 132961 | Buenavista Elementary School | CITY OF TANDAG (Capital) | 1 | 1 | 8 | Repair of Classrooms | 1638886 | 1 | 1638885.99 | COMPLETED | 1 | January 20, 2020 | [8 empty] | JTA Builders
231 | REPAIR 2020 | CARAGA | Tandag City | 500587 | Carmen IS | CITY OF TANDAG (Capital) | 1 | 1 | 7 | Repair of Classrooms | 1573690 | 1 | 1573689.49 | COMPLETED | 1 | January 20, 2020 | [7 empty] | August 15, 2019 | FP Alonto Construction
232 | REPAIR 2020 | CARAGA | Tandag City | 304892 | Jacinto P. Elpa National High School | CITY OF TANDAG (Capital) | 1 | 1 | 6 | Repair of Classrooms | 1676881 | 1 | 1676880.8 | COMPLETED | 1 | January 20, 2020 | December 18, 2020 | [7 empty] | MRS Construction & Supply
233 | REPAIR 2020 | CARAGA | Tandag City | 132974 | San Agustin Elementary School | CITY OF TANDAG (Capital) | 1 | 1 | 7 | Repair of Classrooms | 1909931 | 1 | 1909930.28 | COMPLETED | 1 | January 20, 2020 | [8 empty] | CV Construction & Supply
234 | REPAIR 2020 | CARAGA | Tandag City | 132977 | San Jose Elementary School | CITY OF TANDAG (Capital) | 1 | 1 | 2 | Repair of Classrooms | 588795 | 1 | 588794.84 | COMPLETED | 1 | January 20, 2020 | December 18, 2020 | [7 empty] | MRS Construction & Supply
2429 | REPAIR 2021 | CARAGA | Agusan del Norte | 131467 | Balungagan ES | LAS NIEVES | 1 | 1 | 2 | Repair of Classrooms | 1437536.8 | 1 |  | COMPLETED | 1
2430 | REPAIR 2021 | CARAGA | Agusan del Norte | 131477 | Sagbuco ES | LAS NIEVES | 1 | 1 | 2 | Repair of Classrooms | 1519571.31 | 1 |  | COMPLETED | 1
2431 | REPAIR 2021 | CARAGA | Agusan del Norte | 131513 | Sacol ES | BUENAVISTA | 2 | 1 | 3 | Repair of Classrooms | 2040652.63 | 1 |  | COMPLETED | 1
2432 | REPAIR 2021 | CARAGA | Agusan del Norte | 131570 | Tanutao ES | BUENAVISTA | 2 | 1 | 3 | Repair of Classrooms | 2040652.63 | 1 |  | COMPLETED | 1
2433 | REPAIR 2021 | CARAGA | Agusan del Norte | 304677 | Carmen NHS | CARMEN | 2 | 1 | 1 | Repair of Classroom | 1024721.06 | 1 |  | COMPLETED | 1
2434 | REPAIR 2021 | CARAGA | Agusan del Norte | 131418 | Cervantina ES | CARMEN | 2 | 1 | 2 | Repair of Classrooms | 1441782.04 | 1 |  | COMPLETED | 1
2435 | REPAIR 2021 | CARAGA | Agusan del Norte | 131436 | Magsaysay ES | JABONGA | 2 | 1 | 3 | Repair of Classrooms | 2102730.8 | 1 |  | COMPLETED | 1
2436 | REPAIR 2021 | CARAGA | Agusan del Norte | 131454 | San Roque Elementary School | KITCHARAO | 2 | 1 | 2 | Repair of Classrooms | 1473669.84 | 1 |  | COMPLETED | 1
2437 | REPAIR 2021 | CARAGA | Agusan del Norte | 131482 | Caloc-an ES | MAGALLANES | 2 | 1 | 2 | Repair of Classrooms | 1472619.84 | 1 |  | COMPLETED | 1
2438 | REPAIR 2021 | CARAGA | Agusan del Norte | 131490 | Aclan Elementary School | NASIPIT | 2 | 1 | 1 | Repair of Classroom | 819021.53 | 1 |  | COMPLETED | 1
2439 | REPAIR 2021 | CARAGA | Agusan del Norte | 131497 | Jaguimitan ES | NASIPIT | 2 | 1 | 1 | Repair of Classroom | 867506.27 | 1 |  | COMPLETED | 1
2440 | REPAIR 2021 | CARAGA | Agusan del Norte | 131531 | Humilog ES | REMEDIOS T. ROMUALDEZ | 2 | 1 | 1 | Repair of Classroom | 919116.77 | 1 |  | COMPLETED | 1
2441 | REPAIR 2021 | CARAGA | Agusan del Norte | 131541 | La Paz ES | SANTIAGO | 2 | 1 | 2 | Repair of Classrooms | 1486092.91 | 1 |  | COMPLETED | 1
2442 | REPAIR 2021 | CARAGA | Agusan del Norte | 131593 | Tubay Central Elementary School | TUBAY | 2 | 1 | 2 | Repair of Classrooms | 1473669.84 | 1 |  | COMPLETED | 1
2443 | REPAIR 2021 | CARAGA | Agusan del Sur | 131688 | San Isidro ES | ESPERANZA | 1 | 1 | 3 | Repair of Classrooms | 1986030.2 | 1 | 1942914.76 | COMPLETED | 1 |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | ABADA CONSTRUCTION & SUPPLY
2444 | REPAIR 2021 | CARAGA | Agusan del Sur | 131713 | Tahina ES | ESPERANZA | 1 | 1 | 4 | Repair of Classrooms | 2562627.1 | 1 | 2517614.52 | COMPLETED | 1 |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | ABADA CONSTRUCTION & SUPPLY
2445 | REPAIR 2021 | CARAGA | Agusan del Sur | 317444 | Aurora Nhs | PROSPERIDAD (Capital) | 1 | 1 | 4 | Repair of Classrooms | 2593266.16 | 1 | 2550087.95 | COMPLETED | 1 |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | JB CIANO CONSTRUCTION
2446 | REPAIR 2021 | CARAGA | Agusan del Sur | 131981 | Kabakahan ES | TALACOGON | 1 | 1 | 5 | Repair of Classrooms | 3114802.86 | 1 | 3072470.23 | COMPLETED | 1 |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | ROCK DIWATA BUILDERS INC.
2447 | REPAIR 2021 | CARAGA | Agusan del Sur | 304752 | Talacogon NHS | TALACOGON | 1 | 1 | 9 | Repair of Classrooms | 5855797.46 | 1 | 5812436.97 | COMPLETED | 1 |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | ROCK DIWATA BUILDERS INC.
2448 | REPAIR 2021 | CARAGA | Agusan del Sur | 131754 | Kimondo ES | LA PAZ | 2 | 1 | 2 | Repair of Classrooms | 1450807.05 | 1 | 1406715.08 | COMPLETED | 1 |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | LM CONSTRUCTION & GENERAL MARKETING
2449 | REPAIR 2021 | CARAGA | Agusan del Sur | 131715 | Binucayan CES | LORETO | 2 | 1 | 9 | Repair of Classrooms | 5079981.07 | 1 | 5035764.92 | COMPLETED | 1 |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | DAVE CONSTRUCTION
2450 | REPAIR 2021 | CARAGA | Agusan del Sur | 131742 | San Miguel ES | LORETO | 2 | 1 | 2 | Repair of Classrooms | 1481702.74 | 1 | 1439329.37 | COMPLETED | 1 |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | DAVE CONSTRUCTION
2451 | REPAIR 2021 | CARAGA | Agusan del Sur | 131924 | Aurora ES | SANTA JOSEFA | 2 | 1 | 10 | Repair of Classrooms | 5598627.97 | 1 | 5553052.81 | COMPLETED | 1 |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | DDS BUILDERS
2452 | REPAIR 2021 | CARAGA | Agusan del Sur | 500798 | Patrocinio Integrated School | SANTA JOSEFA | 2 | 1 | 4 | Repair of Classrooms | 2324851.04 | 1 | 2280159.05 | COMPLETED | 1 |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | MRS BUILDERS & SUPPLY
2453 | REPAIR 2021 | CARAGA | Agusan del Sur | 131932 | Simeon S. Castor ES | SANTA JOSEFA | 2 | 1 | 4 | Repair of Classrooms | 2760647.69 | 1 | 2719383.58 | COMPLETED | 1 |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | LM CONSTRUCTION & GENERAL MARKETING
2454 | REPAIR 2021 | CARAGA | Agusan del Sur | 132000 | Gasa ES | TRENTO | 2 | 1 | 4 | Repair of Classrooms | 2461155.56 | 1 | 2418246.72 | COMPLETED | 1 |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | MRS BUILDERS & SUPPLY
2455 | REPAIR 2021 | CARAGA | Agusan del Sur | 132001 | Isdaon Elementary School | TRENTO | 2 | 1 | 6 | Repair of Classrooms | 3640183.73 | 1 | 3595513.58 | COMPLETED | 1 |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | JB CIANO CONSTRUCTION
2456 | REPAIR 2021 | CARAGA | Agusan del Sur | 317409 | Kapatungan National High School | TRENTO | 2 | 1 | 5 | Repair of Classrooms | 3623329.29 | 1 | 3579842.32 | COMPLETED | 1 |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | MRS BUILDERS & SUPPLY
2457 | REPAIR 2021 | CARAGA | Agusan del Sur | 132013 | San Juan ES | TRENTO | 2 | 1 | 7 | Repair of Classrooms | 4501788.25 | 1 | 4459039.69 | COMPLETED | 1 |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | MRS BUILDERS & SUPPLY
2458 | REPAIR 2021 | CARAGA | Bayugan City | 131599 | Hamogaway ES | CITY OF BAYUGAN | 1 | 1 | 3 | Repair of Classrooms | 1451174.45 | 1 |  | COMPLETED | 1
2459 | REPAIR 2021 | CARAGA | Bayugan City | 131612 | Sinadyap ES | CITY OF BAYUGAN | 1 | 1 | 9 | Repair of Classrooms | 3784290.5 | 1 |  | COMPLETED | 1
2460 | REPAIR 2021 | CARAGA | Bislig City | 132611 | Burboanan ES | CITY OF BISLIG | 2 | 1 | 3 | Repair of Classrooms | 1235124.95 | 1 | 986217.78 | COMPLETED | 1 | November 17, 2021 | November 10, 2021 | BEFF_REPAIR2021_001 | BEFF_REPAIR2021_001 | June 09, 2021 | June 17, 2021 | June 30, 2021 | July 06, 2021 | July 14, 2021 | MN Bayalas Construction
2461 | REPAIR 2021 | CARAGA | Bislig City | 132623 | SER-FEL MONE ES | CITY OF BISLIG | 2 | 1 | 4 | Repair of Classrooms | 1494568.14 | 1 | 1193277.63 | COMPLETED | 1 | November 17, 2021 | November 12, 2021 | BEFF_REPAIR2021_001 | BEFF_REPAIR2021_001 | June 09, 2021 | June 17, 2021 | June 30, 2021 | July 06, 2021 | July 14, 2021 | MN Bayalas Construction
2462 | REPAIR 2021 | CARAGA | Bislig City | 132638 | SIMON EDGAR A. GARAY ES | CITY OF BISLIG | 2 | 1 | 2 | Repair of Classrooms | 742005.43 | 1 | 590580.9 | COMPLETED | 1 | November 17, 2021 | November 10, 2021 | BEFF_REPAIR2021_001 | BEFF_REPAIR2021_001 | June 09, 2021 | June 17, 2021 | June 30, 2021 | July 06, 2021 | July 14, 2021 | MN Bayalas Construction
2463 | REPAIR 2021 | CARAGA | Butuan City | 132073 | Datu Santiago B. Ecleo, Sr. Mem'l. Elem. School | BUTUAN CITY (Capital) | 1 | 1 | 6 | Repair of Classrooms | 5296975.6 | 1 |  | COMPLETED | 1
2464 | REPAIR 2021 | CARAGA | Butuan City | 132035 | Mahayahay ES | BUTUAN CITY (Capital) | 1 | 1 | 5 | Repair of Classrooms | 2670112.62 | 1 |  | COMPLETED | 1
2465 | REPAIR 2021 | CARAGA | Cabadbaran City | 131577 | Alfonso B. Dagani ES | CITY OF CABADBARAN | 2 | 1 | 2 | Repair of Classrooms | 1353061.6 | 1 |  | COMPLETED | 1
2466 | REPAIR 2021 | CARAGA | Cabadbaran City | 131518 | Comagascas Elementary Schools | CITY OF CABADBARAN | 2 | 1 | 2 | Repair of Classrooms | 1608455.34 | 1 |  | COMPLETED | 1
2467 | REPAIR 2021 | CARAGA | Cabadbaran City | 317312 | La Union NHS (Calamba NHS Annex) | CITY OF CABADBARAN | 2 | 1 | 2 | Repair of Classrooms | 986339.22 | 1 |  | COMPLETED | 1
2468 | REPAIR 2021 | CARAGA | Cabadbaran City | 131528 | Puting Bato Elementary School | CITY OF CABADBARAN | 2 | 1 | 1 | Repair of Classroom | 575692.26 | 1 |  | COMPLETED | 1
2469 | REPAIR 2021 | CARAGA | Cabadbaran City | 131578 | Sanghan ES | CITY OF CABADBARAN | 2 | 1 | 3 | Repair of Classrooms | 2395603.08 | 1 |  | COMPLETED | 1
2470 | REPAIR 2021 | CARAGA | Dinagat Island | 132394 | Cab-ilan Elementary School | DINAGAT | 0 | 1 | 5 | Repair of Classrooms | 1931052.9 | 1 | 1929067.29 | COMPLETED | 1 | 2021-11-17
2471 | REPAIR 2021 | CARAGA | Dinagat Island | 132319 | Rosita ES | LIBJO (ALBOR) | 0 | 1 | 3 | Repair of Classrooms | 1938513.44 | 1 | 1929999.98 | COMPLETED | 1 | 2021-11-14
2472 | REPAIR 2021 | CARAGA | Siargao | 132125 | Can-uyan Primary School | DAPA | 1 | 1 | 1 | Repair of Classroom | 497000 | 1 |  | COMPLETED | 1
2473 | REPAIR 2021 | CARAGA | Siargao | 132142 | San Carlos Elementary School | DAPA | 1 | 1 | 2 | Repair of Classrooms | 1010000 | 1 |  | COMPLETED | 1
2474 | REPAIR 2021 | CARAGA | Siargao | 132173 | Lobogon Elementary School | DEL CARMEN | 1 | 1 | 2 | Repair of Classrooms | 943000 | 1 |  | COMPLETED | 1
2475 | REPAIR 2021 | CARAGA | Siargao | 132151 | Dao Primary School | GENERAL LUNA | 1 | 1 | 1 | Repair of Classroom | 486000 | 1 |  | COMPLETED | 1
2476 | REPAIR 2021 | CARAGA | Siargao | 132161 | Tawin-Tawin Elementary School | GENERAL LUNA | 1 | 1 | 1 | Repair of Classroom | 485000 | 1 |  | COMPLETED | 1
2477 | REPAIR 2021 | CARAGA | Siargao | 132185 | Jaboy Elementary School | PILAR | 1 | 1 | 2 | Repair of Classrooms | 958000 | 1 |  | COMPLETED | 1
2478 | REPAIR 2021 | CARAGA | Siargao | 132227 | Nuevo Campo Elementary Schoool | SAN BENITO | 1 | 1 | 2 | Repair of Classrooms | 948000 | 1 |  | COMPLETED | 1
2479 | REPAIR 2021 | CARAGA | Siargao | 132228 | Pitogo Elementary School | SAN BENITO | 1 | 1 | 1 | Repair of Classroom | 517000 | 1 |  | COMPLETED | 1
2480 | REPAIR 2021 | CARAGA | Siargao | 132229 | San Juan Elementary School | SAN BENITO | 1 | 1 | 2 | Repair of Classrooms | 990000 | 1 |  | COMPLETED | 1
2481 | REPAIR 2021 | CARAGA | Siargao | 132195 | Macapagal Primary School | SAN ISIDRO | 1 | 1 | 1 | Repair of Classroom | 489426.04 | 1 |  | COMPLETED | 1
2482 | REPAIR 2021 | CARAGA | Siargao | 132197 | Pelaez Elementary School | SAN ISIDRO | 1 | 1 | 1 | Repair of Classroom | 468000 | 1 |  | COMPLETED | 1
2483 | REPAIR 2021 | CARAGA | Siargao | 132210 | Mabini Elementary School | SANTA MONICA (SAPAO) | 1 | 1 | 2 | Repair of Classrooms | 975000 | 1 |  | COMPLETED | 1
2484 | REPAIR 2021 | CARAGA | Siargao | 132231 | Del Pilar Community School | SOCORRO | 1 | 1 | 2 | Repair of Classrooms | 993000 | 1 |  | COMPLETED | 1
2485 | REPAIR 2021 | CARAGA | Surigao City | 132256 | Orok Elementary School | SURIGAO CITY (Capital) | 2 | 1 | 2 | Repair of Classrooms | 1940038.57 | 1 |  | COMPLETED | 1
2486 | REPAIR 2021 | CARAGA | Surigao City | 132295 | Serna Elementary School | SURIGAO CITY (Capital) | 2 | 1 | 2 | Repair of Classrooms | 1591384.77 | 1 |  | COMPLETED | 1
2487 | REPAIR 2021 | CARAGA | Surigao del Norte | 132474 | Macalaya ES | PLACER | 2 | 1 | 8 | Repair of Classrooms | 5245388.45 | 1 | 5235000 | COMPLETED | 1 | 2021-11-02 |  | 001-BEFF-2021-CARAGA | 001-2021 | 2021-06-09 | 2021-06-16 | 2021-06-28 | 2021-07-01 | 2021-07-04 | Windfall Construction
2488 | REPAIR 2021 | CARAGA | Surigao del Norte | 132476 | Pananay-an ES | PLACER | 2 | 1 | 1 | Repair of Classroom | 414081.85 | 1 | 397585.25 | COMPLETED | 1 | 2021-09-06 |  | 003-BEFF-2021-CARAGA | 003-2021 | 2021-06-09 | 2021-06-16 | 2021-06-28 | 2021-07-01 | 2021-07-04 | R.F. Varquez Construction
2489 | REPAIR 2021 | CARAGA | Surigao del Norte | 132477 | Panhutongan ES | PLACER | 2 | 1 | 3 | Repair of Classrooms | 2133444.29 | 1 | 2123401.73 | COMPLETED | 1 | 2021-10-06 |  | 002-BEFF-2021-CARAGA | 002-2021 | 2021-06-09 | 2021-06-16 | 2021-06-28 | 2021-07-01 | 2021-07-04 | Chives Construction and Supply
2490 | REPAIR 2021 | CARAGA | Surigao del Sur | 500321 | Matho Integrated School | CORTES | 1 | 1 | 4 | Repair of Classrooms | 3208327.87 | 1 | 2045494.59 | COMPLETED | 1 | 2021-12-13 | November 24, 2021 |  |  | 2021-07-12 | 2021-07-21 | 2021-08-04 | 2021-08-24 | 2021-09-07 | LPO1 GROUP OF COMPANIES
2491 | REPAIR 2021 | CARAGA | Surigao del Sur | 132780 | R. Moreno Elementary School | LIANGA | 1 | 1 | 5 | Repair of Classrooms | 4108268.49 | 1 | 2663874.03 | COMPLETED | 1 | 2021-12-13 | November 11, 2021 |  |  | 2021-07-12 | 2021-07-21 | 2021-08-04 | 2021-08-24 | 2021-09-07 | TRIDENT ENGINEERING SERVICES
2492 | REPAIR 2021 | CARAGA | Surigao del Sur | 132947 | Layog Elementary School | TAGO | 1 | 1 | 4 | Repair of Classrooms | 3342302.63 | 1 | 2163079.08 | COMPLETED | 1 | 2021-12-12 |  |  |  | 2021-07-12 | 2021-07-21 | 2021-08-04 | 2021-08-24 | 2021-09-06 | FP ALONTO CONSTRUCTION SERVICES
2493 | REPAIR 2021 | CARAGA | Surigao del Sur | 132948 | Lindoy Elementary School | TAGO | 1 | 1 | 1 | Repair of Classroom | 571915.5 | 1 | 361782.94 | COMPLETED | 1 | 2021-12-12 |  |  |  | 2021-07-12 | 2021-07-21 | 2021-08-04 | 2021-08-24 | 2021-09-06 | FP ALONTO CONSTRUCTION SERVICES
2494 | REPAIR 2021 | CARAGA | Surigao del Sur | 132575 | Campbagang Elementary School | BAROBO | 2 | 1 | 5 | Repair of Classrooms | 4201512.17 | 1 | 2843751.17 | reverted | 0.65 | 2022-11-30 |  |  |  | 2021-07-12 | 2021-07-21 | 2021-08-04 | 2021-08-24 | 2021-09-10 | TWO J.E. CONSTRUCTION AND SUPPLY | terminated; reverted
2495 | REPAIR 2021 | CARAGA | Surigao del Sur | 132724 | Bigaan Elementary School | HINATUAN | 2 | 1 | 2 | Repair of Classrooms | 1563818.75 | 1 | 1110868.58 | COMPLETED | 1 | 2021-12-13 |  |  |  | 2021-07-12 | 2021-07-21 | 2021-08-04 | 2021-08-24 | 2021-09-07 | MAIR CONSTRUCTION AND GENERAL MERCHANDISE
2496 | REPAIR 2021 | CARAGA | Surigao del Sur | 132729 | Cambatong Elementary School | HINATUAN | 2 | 1 | 1 | Repair of Classroom | 963943.23 | 1 | 677562.54 | COMPLETED | 1 | 2021-12-13 |  |  |  | 2021-07-12 | 2021-07-21 | 2021-08-04 | 2021-08-24 | 2021-09-07 | MAIR CONSTRUCTION AND GENERAL MERCHANDISE
2497 | REPAIR 2021 | CARAGA | Surigao del Sur | 132747 | San Juan Elementary School | HINATUAN | 2 | 1 | 1 | Repair of Classroom | 956087.39 | 1 | 674806.95 | COMPLETED | 1 | 2021-12-13 |  |  |  | 2021-07-12 | 2021-07-21 | 2021-08-04 | 2021-08-24 | 2021-09-07 | MAIR CONSTRUCTION AND GENERAL MERCHANDISE
2498 | REPAIR 2021 | CARAGA | Tandag City | 132978 | Tandag Central Elementary School | CITY OF TANDAG (Capital) | 1 | 1 | 2 | Repair of Classrooms | 1048250.65 | 1 | 721850.3 | COMPLETED | 1 | 2019-11-28 | [7 empty] | August 15, 2019 | AMA Construction
2499 | REPAIR 2021 | CARAGA | Tandag City | 132979 | Tandag Pilot Elementary School | CITY OF TANDAG (Capital) | 1 | 1 | 4 | Repair of Classrooms | 2052079.62 | 1 | 1414320.21 | COMPLETED | 1
2500 | REPAIR 2021 | CARAGA | Tandag City | 132980 | Telaje Elementary School | CITY OF TANDAG (Capital) | 1 | 1 | 3 | Repair of Classrooms | 3054188.64 | 1 | 1985098.07 | COMPLETED | 1
3779 | REPAIR 2022 | CARAGA | Agusan del Norte | 131533 | Panaytayon ES | REMEDIOS T. ROMUALDEZ | 2 | 1 | 3 | Repair of Classrooms | 2221709.46 | 1 |  | COMPLETED | 1 |  |  | REPAIR 2022 - R XIII - AGUSAN DEL NORTE - 009 | REPAIR 2022 - R XIII - AGUSAN DEL NORTE - 009 | April 13, 2022 | April 22, 2022 | May 4, 2022 | June 11, 2022 | June 27, 2022 | BN Builders and Construction Supplies
3780 | REPAIR 2022 | CARAGA | Dinagat Island | 132395 | Cayetano Elementary School | DINAGAT | 0 | 1 | 3 | Repair of Classrooms | 2339173.98 | 2 |  | COMPLETED | 1 |  |  |  |  | 2022-08-16
3781 | REPAIR 2022 | CARAGA | Dinagat Island | 132400 | New Mabuhay Elementary School | DINAGAT | 0 | 1 | 2 | Repair of Classrooms | 806296.12 | 2 |  | COMPLETED | 1 |  |  |  |  | 2022-08-16 | [5 empty] | DUE TO BAD WEATHER (ROUGH SEA AND SHEAR LINE)
3782 | REPAIR 2022 | CARAGA | Dinagat Island | 132312 | Llamera Elementary School | LIBJO (ALBOR) | 0 | 1 | 3 | Repair of Classrooms | 2251076.69 | 2 |  | COMPLETED | 1 |  |  |  |  | 2022-08-16
3783 | REPAIR 2022 | CARAGA | Dinagat Island | 132317 | Plaridel Elementary School | LIBJO (ALBOR) | 0 | 1 | 2 | Repair of Classrooms | 1000431.64 | 2 |  | COMPLETED | 1 |  |  |  |  | 2022-08-16 | [5 empty] | DUE TO BAD WEATHER (ROUGH SEA AND SHEAR LINE)
3784 | REPAIR 2022 | CARAGA | Dinagat Island | 132557 | Roxas Elementary School | TUBAJON | 0 | 1 | 2 | Repair of Classrooms | 1574058.26 | 2 |  | COMPLETED | 1 |  |  |  |  | 2022-08-16 | [5 empty] | DUE TO BAD WEATHER (ROUGH SEA AND SHEAR LINE)
3785 | REPAIR 2022 | CARAGA | Siargao | 304773 | Burgos National High School | BURGOS | 1 | 1 | 3 | Repair of Classrooms | 1590953 | 1 |  | COMPLETED | 1
3786 | REPAIR 2022 | CARAGA | Siargao | 132162 | Antipolo Elementary School | DEL CARMEN | 1 | 1 | 5 | Repair of Classrooms | 2668177 | 1 |  | COMPLETED | 1
3787 | REPAIR 2022 | CARAGA | Siargao | 132163 | Bagacay Elementary School | DEL CARMEN | 1 | 1 | 1 | Repair of Classroom | 595000 | 1 |  | COMPLETED | 1
3788 | REPAIR 2022 | CARAGA | Siargao | 132155 | Magsaysay Elementary School | GENERAL LUNA | 1 | 1 | 2 | Repair of Classrooms | 1385177 | 1 |  | COMPLETED | 1
3789 | REPAIR 2022 | CARAGA | Siargao | 132157 | Mam-on Primary school | GENERAL LUNA | 1 | 1 | 1 | Repair of Classroom | 630000 | 1 |  | COMPLETED | 1
3790 | REPAIR 2022 | CARAGA | Siargao | 132161 | Tawin-Tawin Elementary School | GENERAL LUNA | 1 | 1 | 2 | Repair of Classrooms | 1248000 | 1 |  | COMPLETED | 1
3791 | REPAIR 2022 | CARAGA | Siargao | 132186 | Katipunan Elementary School | PILAR | 1 | 1 | 1 | Repair of Classroom | 597000 | 1 |  | COMPLETED | 1
3792 | REPAIR 2022 | CARAGA | Siargao | 132189 | Mabuhay Elementary School | PILAR | 1 | 1 | 1 | Repair of Classroom | 597000 | 1 |  | COMPLETED | 1
3793 | REPAIR 2022 | CARAGA | Siargao | 132191 | Salvacion Elementary School | PILAR | 1 | 1 | 6 | Repair of Classrooms | 1987906 | 1 |  | COMPLETED | 1
3794 | REPAIR 2022 | CARAGA | Siargao | 132225 | Bongdo Elementary School | SAN BENITO | 1 | 1 | 2 | Repair of Classrooms | 1060635 | 1 |  | COMPLETED | 1
3795 | REPAIR 2022 | CARAGA | Siargao | 132200 | San Miguel Primary School | SAN ISIDRO | 1 | 1 | 1 | Repair of Classroom | 597000 | 1 |  | COMPLETED | 1
3796 | REPAIR 2022 | CARAGA | Siargao | 132202 | Sto. Nino Elementary School | SAN ISIDRO | 1 | 1 | 1 | Repair of Classroom | 2677422.17 | 1 |  | COMPLETED | 1
3797 | REPAIR 2022 | CARAGA | Siargao | 132206 | Alegria Elementary School | SANTA MONICA (SAPAO) | 1 | 1 | 5 | Repair of Classrooms | 2586906 | 1 |  | COMPLETED | 1
3798 | REPAIR 2022 | CARAGA | Siargao | 132212 | Rizal Elementary School | SANTA MONICA (SAPAO) | 1 | 1 | 1 | Repair of Classroom | 595000.01 | 1 |  | COMPLETED | 1
3799 | REPAIR 2022 | CARAGA | Surigao del Norte | 132321 | Alegria CES | ALEGRIA | 2 | 1 | 3 | Repair of Classrooms | 2206679.8 | 1 |  | COMPLETED | 1 | 2022-09-30 |  | 001-BEFF 2022-Caraga | 004-2022 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-16 | 2022-05-26 | DRANLIVE CONSTRUCTION
3800 | REPAIR 2022 | CARAGA | Surigao del Norte | 132344 | Cabugao ES | BACUAG | 2 | 1 | 5 | Repair of Classrooms | 3188794.34 | 1 |  | COMPLETED | 1 | 2022-09-23 |  | 002-BEFF 2022-Caraga | 007-2022 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-16 | 2022-05-26 | RADIAN CONSTRUCTION AND SUPPLY
3801 | REPAIR 2022 | CARAGA | Surigao del Norte | 132460 | Malimono Central Elementary School | MALIMONO | 2 | 1 | 6 | Repair of Classrooms | 3801772.6 | 1 |  | COMPLETED | 1 | 2022-10-13 | 2022-07-25 | 003-BEFF 2022-Caraga | 003-2022 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-16 | 2022-05-26 | BAMBOE CONSTRUCTION AND SUPPLY
3802 | REPAIR 2022 | CARAGA | Surigao del Norte | 132339 | Macopa ES | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 2 | Repair of Classrooms | 1063102.26 | 1 |  | COMPLETED | 1 | 2022-08-10 | 2022-06-14 | 004-BEFF 2022-Caraga | 002-2022 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-16 | 2022-05-26 | AMALGO CONSTRUCTION
3803 | REPAIR 2022 | CARAGA | Surigao del Norte | 132527 | DE CASTRO ELEMENTARY SCHOOL | SISON | 2 | 1 | 4 | Repair of Classrooms | 2852624.19 | 1 |  | COMPLETED | 1 | 2022-10-24 |  | 005-BEFF 2022-Caraga | 014-2022 | 2022-04-06 | 2022-04-13 | 2022-04-25 | 2022-05-02 | 2022-06-16 | PAROPA CONSTRUCTION AND SUPPLY
3804 | REPAIR 2022 | CARAGA | Surigao del Norte | 132548 | Tagana-an CES | TAGANA-AN | 2 | 1 | 4 | Repair of Classrooms | 2738357.76 | 1 |  | COMPLETED | 1 | 2022-09-23 |  | 006-BEFF 2022-Caraga | 005-2022 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-16 | 2022-05-26 | RADIAN CONSTRUCTION AND SUPPLY
3805 | REPAIR 2022 | CARAGA | Surigao del Norte | 132568 | Tubod CES | TUBOD | 2 | 1 | 3 | Repair of Classrooms | 2125409.8 | 1 |  | COMPLETED | 1 | 2022-08-24 | 2022-07-25 | 007-BEFF 2022-Caraga | 006-2022 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-16 | 2022-05-26 | WINDFALL CONSTRUCTION
3806 | REPAIR 2022 | CARAGA | Surigao del Sur | 501275 | Panaosawon Integrated School | BAYABAS | 1 | 1 | 3 | Repair of Classrooms | 2562384.81 | 1 |  | COMPLETED | 1 |  |  | Repair 2022 - Surigao del Sur 001 |  | March 03, 2022 | March 11, 2022 | March 23, 2022 | April 18, 2022 |  | Trident Engineering Services | Received Sub ARO last August 08, 2022
4206 | REPAIR 2023 | CARAGA | Agusan del Norte | 131454 | San Roque Elementary School | KITCHARAO | 2nd | 1 | 5 | Repair of Classrooms | 5135688.01 | DPWH (Batch 1) |  | Completed | 1
4207 | REPAIR 2023 | CARAGA | Agusan del Norte | 131532 | Luis B. Azura Sr. Memorial ES | REMEDIOS T. ROMUALDEZ | 2nd | 1 | 3 | Repair of Classrooms | 3613007.04 | DPWH (Batch 1) |  | Completed | 1
4208 | REPAIR 2023 | CARAGA | Agusan del Norte | 211510 | Poblacion Doz ES | REMEDIOS T. ROMUALDEZ | 2nd | 1 | 1 | Repair of Classroom | 1680407.71 | DPWH (Batch 1) |  | Completed | 1
4209 | REPAIR 2023 | CARAGA | Agusan del Norte | 131534 | RT Romualdez CES | REMEDIOS T. ROMUALDEZ | 2nd | 1 | 3 | Repair of Classroom | 3822833.56 | DPWH (Batch 1) |  | Completed | 1
4210 | REPAIR 2023 | CARAGA | Cabadbaran City | 131515 | Bayabas ES | CITY OF CABADBARAN | 2nd | 1 | 4 | Repair of Classrooms | 3426370.76 | DPWH (Batch 1) |  | COMPLETED | 1
4211 | REPAIR 2023 | CARAGA | Cabadbaran City | 131516 | Caasinan ES | CITY OF CABADBARAN | 2nd | 1 | 7 | Repair of Classrooms | 5738052.81 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | Suspended
4212 | REPAIR 2023 | CARAGA | Cabadbaran City | 317312 | La Union National High School | CITY OF CABADBARAN | 2nd | 1 | 2 | Repair of Classrooms | 1744136.59 | DPWH (Batch 1) |  | COMPLETED | 1
4213 | REPAIR 2023 | CARAGA | Cabadbaran City | 501722 | Mahaba Integrated School | CITY OF CABADBARAN | 2nd | 1 | 2 | Repair of Classrooms | 1864350.77 | DPWH (Batch 1) |  | COMPLETED | 1
4214 | REPAIR 2023 | CARAGA | Dinagat Island | 132488 | De La Concepcion Elementary School | BASILISA (RIZAL) | Lone | 1 | 4 | Repair of Classrooms | 3915940.43 | DPWH (Batch 1) |  | COMPLETED | 1 | 2024-03-15
4215 | REPAIR 2023 | CARAGA | Dinagat Island | 132499 | Navarro Elementary School | BASILISA (RIZAL) | Lone | 1 | 5 | Repair of Classrooms | 4956773.29 | DPWH (Batch 1) |  | COMPLETED | 1 | 2024-04-10
4216 | REPAIR 2023 | CARAGA | Dinagat Island | 132502 | Paniog Elementary School | BASILISA (RIZAL) | Lone | 1 | 6 | Repair of Classrooms | 5267468.18 | DPWH (Batch 1) |  | COMPLETED | 1 | 2024-03-15
4217 | REPAIR 2023 | CARAGA | Dinagat Island | 132394 | Cab-ilan Elementary School | DINAGAT | Lone | 1 | 6 | Repair of Classrooms | 6398647.58 | DPWH (Batch 1) |  | COMPLETED | 1 | 2024-03-29
4218 | REPAIR 2023 | CARAGA | Dinagat Island | 132316 | Osmeña Elementary School | LIBJO (ALBOR) | Lone | 1 | 8 | Repair of Classrooms | 7044886.13 | DPWH (Batch 1) |  | COMPLETED | 1 | 2024-04-20
4219 | REPAIR 2023 | CARAGA | Dinagat Island | 132516 | Don Ruben Elementary School | SAN JOSE (Capital) | Lone | 1 | 6 | Repair of Classrooms | 5634902.24 | DPWH (Batch 1) |  | COMPLETED | 1 | 2024-03-15
4220 | REPAIR 2023 | CARAGA | Siargao | 132126 | Consolacion Elementary School | DAPA | 1st | 1 | 6 | Repair of Classrooms | 6000000 | DPWH (Batch 2) |  | COMPLETED | 1
4221 | REPAIR 2023 | CARAGA | Siargao | 304774 | Dapa National High School | DAPA | 1st | 1 | 15 | Repair of Classrooms | 8000000 | DPWH (Batch 2) |  | COMPLETED | 1
4222 | REPAIR 2023 | CARAGA | Siargao | 317604 | Siargao National Science High School | DAPA | 1st | 1 | 25 | Repair of Classrooms | 8020106.85 | DPWH (Batch 1) |  | COMPLETED | 1
4223 | REPAIR 2023 | CARAGA | Siargao | 132167 | Dumoyog Primary School | DEL CARMEN | 1st | 1 | 3 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 1
4224 | REPAIR 2023 | CARAGA | Siargao | 132171 | Katipunan Elementary School | DEL CARMEN | 1st | 1 | 7 | Repair of Classrooms | 7000000 | DPWH (Batch 2) |  | COMPLETED | 1
4225 | REPAIR 2023 | CARAGA | Siargao | 132172 | Lasala Elementary School | DEL CARMEN | 1st | 1 | 4 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 1
4226 | REPAIR 2023 | CARAGA | Siargao | 132149 | Corazon Elementary School | GENERAL LUNA | 1st | 1 | 4 | Repair of Classrooms | 4000000 | DPWH (Batch 2) |  | COMPLETED | 1
4227 | REPAIR 2023 | CARAGA | Siargao | 132151 | Dao Primary School | GENERAL LUNA | 1st | 1 | 1 | Repair of Classroom | 1000000 | DPWH (Batch 2) |  | COMPLETED | 1
4228 | REPAIR 2023 | CARAGA | Siargao | 304777 | Gen Luna National High School | GENERAL LUNA | 1st | 1 | 31 | Repair of Classrooms | 21000000 | DPWH (Batch 2) |  | COMPLETED | 1
4229 | REPAIR 2023 | CARAGA | Siargao | 132158 | Sta. Cruz Elementary School | GENERAL LUNA | 1st | 1 | 9 | Repair of Classrooms | 9000000 | DPWH (Batch 2) |  | COMPLETED | 1
4230 | REPAIR 2023 | CARAGA | Siargao | 132181 | Caridad Elementary School | PILAR | 1st | 1 | 8 | Repair of Classrooms | 7000000 | DPWH (Batch 2) |  | COMPLETED | 1
4231 | REPAIR 2023 | CARAGA | Siargao | 132183 | Datu Elementary School | PILAR | 1st | 1 | 6 | Repair of Classrooms | 5000000 | DPWH (Batch 2) |  | COMPLETED | 1
4232 | REPAIR 2023 | CARAGA | Siargao | 132193 | Buhing Calipay Elementary School | SAN ISIDRO | 1st | 1 | 1 | Repair of Classroom | 1000000 | DPWH (Batch 2) |  | COMPLETED | 1
4233 | REPAIR 2023 | CARAGA | Siargao | 132194 | Del Pilar Elementary School | SAN ISIDRO | 1st | 1 | 4 | Repair of Classrooms | 5000000 | DPWH (Batch 2) |  | COMPLETED | 1
4234 | REPAIR 2023 | CARAGA | Siargao | 132203 | Tambacan Elementary School | SAN ISIDRO | 1st | 1 | 6 | Repair of Classrooms | 5000000 | DPWH (Batch 2) |  | COMPLETED | 1
4235 | REPAIR 2023 | CARAGA | Siargao | 132204 | Tigasao Elementary School | SAN ISIDRO | 1st | 1 | 8 | Repair of Classrooms | 7000000 | DPWH (Batch 2) |  | COMPLETED | 1
4236 | REPAIR 2023 | CARAGA | Siargao | 132205 | Abad Santos Elementary School | SANTA MONICA (SAPAO) | 1st | 1 | 4 | Repair of Classrooms | 4000000 | DPWH (Batch 2) |  | COMPLETED | 1
4237 | REPAIR 2023 | CARAGA | Siargao | 132211 | Magsaysay Elementary School | SANTA MONICA (SAPAO) | 1st | 1 | 4 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 1
4238 | REPAIR 2023 | CARAGA | Siargao | 304785 | Sapao National High School | SANTA MONICA (SAPAO) | 1st | 1 | 28 | Repair of Classrooms | 12042759.68 | DPWH (Batch 1) |  | COMPLETED | 1
4239 | REPAIR 2023 | CARAGA | Siargao | 132233 | Lawigan Primary School | SOCORRO | 1st | 1 | 1 | Repair of Classroom | 1000000 | DPWH (Batch 2) |  | COMPLETED | 1
4240 | REPAIR 2023 | CARAGA | Siargao | 132238 | San Roque Elementary School | SOCORRO | 1st | 1 | 6 | Repair of Classrooms | 5600000 | DPWH (Batch 2) |  | COMPLETED | 1
4241 | REPAIR 2023 | CARAGA | Siargao | 304788 | SOCORRO NATIONAL HIGH SCHOOL | SOCORRO | 1st | 1 | 24 | Repair of Classrooms | 14000000 | DPWH (Batch 2) |  | COMPLETED | 1
4242 | REPAIR 2023 | CARAGA | Siargao | 132240 | Sta. Cruz Community Elementary School | SOCORRO | 1st | 1 | 3 | Repair of Classrooms | 2941515.74 | DPWH (Batch 2) |  | COMPLETED | 1
4243 | REPAIR 2023 | CARAGA | Siargao | 132241 | Sudlon Elementary School | SOCORRO | 1st | 1 | 8 | Repair of Classrooms | 7000000 | DPWH (Batch 2) |  | COMPLETED | 1
4244 | REPAIR 2023 | CARAGA | Surigao City | 132249 | Day-asan ES | SURIGAO CITY (Capital) | 2nd | 1 | 8 | Repair of Classrooms | 4519728.71 | DPWH (Batch 2) |  | COMPLETED | 1
4245 | REPAIR 2023 | CARAGA | Surigao City | 132336 | Lope R. Ruiz Memo. ES (Japson ES) | SURIGAO CITY (Capital) | 2nd | 1 | 3 | Repair of Classrooms | 3478396.02 | DPWH (Batch 2) |  | COMPLETED | 1
4246 | REPAIR 2023 | CARAGA | Surigao City | 132297 | Mabua ES | SURIGAO CITY (Capital) | 2nd | 1 | 5 | Repair of Classrooms | 6494027.1 | DPWH (Batch 2) |  | COMPLETED | 1
4247 | REPAIR 2023 | CARAGA | Surigao City | 317706 | Manjagao National High School | SURIGAO CITY (Capital) | 2nd | 1 | 6 | Repair of Classrooms | 3897705.12 | DPWH (Batch 2) |  | COMPLETED | 1
4248 | REPAIR 2023 | CARAGA | Surigao City | 132254 | Mariano Espina Memorial Central Elementary School | SURIGAO CITY (Capital) | 2nd | 1 | 28 | Repair of Classrooms | 9832305.46 | DPWH (Batch 2) |  | COMPLETED | 1
4249 | REPAIR 2023 | CARAGA | Surigao City | 132266 | Martinez ES | SURIGAO CITY (Capital) | 2nd | 1 | 2 | Repair of Classrooms | 1152448.4 | DPWH (Batch 2) |  | COMPLETED | 1
4250 | REPAIR 2023 | CARAGA | Surigao City | 132268 | Navarro MCES | SURIGAO CITY (Capital) | 2nd | 1 | 16 | Repair of Classrooms | 8535127.86 | DPWH (Batch 2) |  | COMPLETED | 1
4251 | REPAIR 2023 | CARAGA | Surigao City | 132269 | Quezon ES | SURIGAO CITY (Capital) | 2nd | 1 | 10 | Repair of Classrooms | 4795113.82 | DPWH (Batch 2) |  | COMPLETED | 1
4252 | REPAIR 2023 | CARAGA | Surigao City | 304796 | Rizal National High School | SURIGAO CITY (Capital) | 2nd | 1 | 7 | Repair of Classrooms | 5104510.6 | DPWH (Batch 2) |  | COMPLETED | 1
4253 | REPAIR 2023 | CARAGA | Surigao City | 132272 | Surigao City Pilot School | SURIGAO CITY (Capital) | 2nd | 1 | 65 | Repair of Classrooms | 15292195.34 | DPWH (Batch 2) |  | Ongoing | 0.9
4254 | REPAIR 2023 | CARAGA | Surigao City | 132261 | Talisay Elementary School | SURIGAO CITY (Capital) | 2nd | 1 | 7 | Repair of Classrooms | 1114894.39 | DPWH (Batch 2) |  | COMPLETED | 1
4255 | REPAIR 2023 | CARAGA | Surigao City | 132243 | Vicente C. Cabilao Memorial Elementary School | SURIGAO CITY (Capital) | 2nd | 1 | 2 | Repair of Classrooms | 2616059.37 | DPWH (Batch 2) |  | COMPLETED | 1
4256 | REPAIR 2023 | CARAGA | Surigao del Norte | 132323 | Budlingin ES | ALEGRIA | 2nd | 1 | 4 | Repair of Classrooms | 3089549.89 | DPWH (Batch 2) |  | COMPLETED | 1 | [9 empty] | AMALGO CONSTRUCTION
4257 | REPAIR 2023 | CARAGA | Surigao del Norte | 132326 | L. J. Mordeno ES | ALEGRIA | 2nd | 1 | 4 | Repair of Classrooms | 2994417.09 | DPWH (Batch 2) |  | COMPLETED | 1 | [9 empty] | AMALGO CONSTRUCTION
4258 | REPAIR 2023 | CARAGA | Surigao del Norte | 132328 | Pongtud ES | ALEGRIA | 2nd | 1 | 4 | Repair of Classrooms | 2973931.11 | DPWH (Batch 2) |  | COMPLETED | 1 | [9 empty] | AMALGO CONSTRUCTION
4259 | REPAIR 2023 | CARAGA | Surigao del Norte | 132345 | Cambuayon ES | BACUAG | 2nd | 1 | 5 | Repair of Classrooms | 3561393.63 | DPWH (Batch 2) |  | COMPLETED | 1 | [9 empty] | ALGAMON CONSTRUCTION
4260 | REPAIR 2023 | CARAGA | Surigao del Norte | 132351 | Pautao ES | BACUAG | 2nd | 1 | 5 | Repair of Classrooms | 2969741.05 | DPWH (Batch 2) |  | COMPLETED | 1 | [9 empty] | C.V. CONSTRUCTION AND DEVELOPMENT
4261 | REPAIR 2023 | CARAGA | Surigao del Norte | 132454 | Cansayong ES | MALIMONO | 2nd | 1 | 7 | Repair of Classrooms | 4796584.88 | DPWH (Batch 2) |  | COMPLETED | 1 | [9 empty] | P & G CONSTRUCTION AND SUPPLY
4262 | REPAIR 2023 | CARAGA | Surigao del Norte | 132458 | Hanagdong Elementary School | MALIMONO | 2nd | 1 | 5 | Repair of Classrooms | 3595637.83 | DPWH (Batch 2) |  | COMPLETED | 1 | [9 empty] | P & G CONSTRUCTION AND SUPPLY
4263 | REPAIR 2023 | CARAGA | Surigao del Norte | 304833 | Malimono National High School | MALIMONO | 2nd | 1 | 3 | Repair of Classrooms | 1517569.64 | DPWH (Batch 2) |  | COMPLETED | 1 | [9 empty] | P & G CONSTRUCTION AND SUPPLY
4264 | REPAIR 2023 | CARAGA | Surigao del Norte | 132461 | Masgad ES | MALIMONO | 2nd | 1 | 4 | Repair of Classrooms | 2994977.65 | DPWH (Batch 2) |  | COMPLETED | 1 | [9 empty] | C.V. CONSTRUCTION AND DEVELOPMENT
4265 | REPAIR 2023 | CARAGA | Surigao del Norte | 304831 | Masgad National High School | MALIMONO | 2nd | 1 | 2 | Repair of Classrooms | 1583416.01 | DPWH (Batch 2) |  | COMPLETED | 1 | [9 empty] | C.V. CONSTRUCTION AND DEVELOPMENT
4266 | REPAIR 2023 | CARAGA | Surigao del Norte | 132332 | Balite ES | SAN FRANCISCO (ANAO-AON) | 2nd | 1 | 4 | Repair of Classrooms | 2973931.11 | DPWH (Batch 2) |  | COMPLETED | 1 | [9 empty] | AMALGO CONSTRUCTION
4267 | REPAIR 2023 | CARAGA | Surigao del Norte | 304843 | San Francisco National High School | SAN FRANCISCO (ANAO-AON) | 2nd | 1 | 22 | Repair of Classrooms | 13362803.04 | DPWH (Batch 2) |  | COMPLETED | 1 | [9 empty] | ROMZ BUILDERS
4268 | REPAIR 2023 | CARAGA | Surigao del Norte | 132529 | Hinapayaw ES | SISON | 2nd | 1 | 3 | Repair of Classrooms | 2123142.38 | DPWH (Batch 2) |  | COMPLETED | 1 | [9 empty] | C.V. CONSTRUCTION AND DEVELOPMENT
4269 | REPAIR 2023 | CARAGA | Surigao del Norte | 132531 | Mabuhay ES | SISON | 2nd | 1 | 6 | Repair of Classrooms | 4183100.34 | DPWH (Batch 2) |  | COMPLETED | 1 | [9 empty] | AMALGO CONSTRUCTION
4270 | REPAIR 2023 | CARAGA | Surigao del Norte | 304849 | Toledo S. Pantilo Sr. Memorial National High School | SISON | 2nd | 1 | 24 | Repair of Classrooms | 6190616.74 | DPWH (Batch 2) |  | COMPLETED | 1 | [9 empty] | MIGO CONSTRUCTION
4271 | REPAIR 2023 | CARAGA | Surigao del Norte | 304847 | Surigao Del Norte National High School | SURIGAO CITY (Capital) | 2nd | 1 | 44 | Repair of Classrooms | 27946795.68 | DPWH (Batch 2) |  | Ongoing | 0.95 | [9 empty] | 471 LP CONSTRUCTION
4272 | REPAIR 2023 | CARAGA | Surigao del Norte | 132541 | Himama-ug ES | TAGANA-AN | 2nd | 1 | 5 | Repair of Classrooms | 3697672.92 | DPWH (Batch 2) |  | COMPLETED | 1
4273 | REPAIR 2023 | CARAGA | Surigao del Norte | 304812 | Tagana-an National High School (ASA NHS) | TAGANA-AN | 2nd | 1 | 2 | Repair of Classrooms | 1578935.52 | DPWH (Batch 2) |  | COMPLETED | 1 | [9 empty] | AMALGO CONSTRUCTION
4274 | REPAIR 2023 | CARAGA | Surigao del Norte | 132564 | Mahucdam ES | TUBOD | 2nd | 1 | 2 | Repair of Classrooms | 1515050.58 | DPWH (Batch 2) |  | COMPLETED | 1 | [9 empty] | AMALGO CONSTRUCTION
5240 | REPAIR 2024 | CARAGA | Agusan del Norte | 131460 | Dalagangan ES | LAS NIEVES | 1st | 1 | 1 | Repair of Classrooms | 1328281.62 | 1 | 1303320.13 | Completed | 1 | 2025-03-23 |  | REPAIR 2024 - R XIII - AGUSAN DEL NORTE - 001 | REPAIR 2024 - R XIII - AGUSAN DEL NORTE - 001 | 2024-10-17 | 2024-10-25 | 2024-11-08 | 2024-12-12 | 2024-12-16 | Karaga Fast-Track Builders, Inc. | with Time Extension
5241 | REPAIR 2024 | CARAGA | Agusan del Norte | 131468 | Las Nieves CES | LAS NIEVES | 1st | 1 | 2 | Repair of Classrooms | 2249285.53 | 1 | 1655302.02 | Completed | 1 | 2025-04-08 |  | REPAIR 2024 - R XIII - AGUSAN DEL NORTE - 003 | REPAIR 2024 - R XIII - AGUSAN DEL NORTE - 003 |  |  | 2024-11-08 | 2024-12-11 | 2024-12-19 | ZEART Construction Supply Co. | with Time Extension
5242 | REPAIR 2024 | CARAGA | Agusan del Norte | 131416 | Cahayagan ES | CARMEN | 2nd | 1 | 2 | Repair of Classrooms | 874101.31 | 1 | 873248.67 | Ongoing | 0.8 | 2025-06-01 |  | REPAIR 2023 - R XIII - AGUSAN DEL NORTE - 005 | REPAIR 2023 - R XIII - AGUSAN DEL NORTE - 005 |  |  |  | 2025-03-20 | 2025-03-27 | Karaga Fast-Track Builders, Inc. | with approved realignment from Kitcharao NHS to 2 sites (Cahayan ES and Mateo Abao CES)
5243 | REPAIR 2024 | CARAGA | Agusan del Norte | 131498 | Mateo B. Abao CES | NASIPIT | 2nd | 1 | 2 | Repair of Classrooms | 2239137.68 |  |  | under procurement | 0
5244 | REPAIR 2024 | CARAGA | Agusan del Norte | 131536 | TAGBONGABONG ES | REMEDIOS T. ROMUALDEZ | 2nd | 1 | 2 | Repair of Classrooms | 2297957.57 | 1 | 2259393.29 | Completed | 1 | 2025-03-25 |  | REPAIR 2024 - R XIII - AGUSAN DEL NORTE - 002 | REPAIR 2024 - R XIII - AGUSAN DEL NORTE - 002 |  | 2024-10-25 | 2024-11-08 | 2024-12-12 | 2024-12-16 | Karaga Fast-Track Builders, Inc. | with Time Extension
5245 | REPAIR 2024 | CARAGA | Agusan del Sur | 304736 | San Luis NHS | SAN LUIS | 1st | 1 | 5 | Repair of Classrooms | 3439916.35 | 1 | 3372981.56 | Ongoing | 0.95 |  |  | 2024-11-029 (LOT-1) | 2024-11-029 (LOT-1) | 2024-11-18 | 2024-11-26 | 2024-12-09 | 2024-12-23 | 2025-01-09 | JICLAM BUILDERS & ENTERPRISES
5246 | REPAIR 2024 | CARAGA | Agusan del Sur | 131845 | Sta. Ana Elementary School | SAN FRANCISCO | 2nd | 1 | 2 | Repair of Classrooms | 1065150.73 | 1 | 1021188.29 | Ongoing | 0.95 |  |  | 2024-11-029 (LOT-2) | 2024-11-029 (LOT-2) | 2024-11-18 | 2024-11-26 | 2024-12-09 | 2024-12-23 | 2025-01-09 | JICLAM BUILDERS & ENTERPRISES
5247 | REPAIR 2024 | CARAGA | Agusan del Sur | 131900 | Caigangan Elementary School | VERUELA | 2nd | 1 | 4 | Repair of Classrooms | 2751933.08 | 1 | 2710909.74 | Ongoing | 0.95 |  |  | 2024-11-029 (LOT-3) | 2024-11-029 (LOT-3) | 2024-11-18 | 2024-11-26 | 2024-12-09 | 2024-12-23 | 2025-01-09 | DDS BUILDERS
5248 | REPAIR 2024 | CARAGA | Bayugan City | 131645 | Verdu ES | CITY OF BAYUGAN | 1st | 1 | 4 | Repair of Classrooms | 5323074.95 | 1 |  | Ongoing | 0.9
5249 | REPAIR 2024 | CARAGA | Butuan City | 132057 | Jose T. Domingo, Sr. CES | BUTUAN CITY (Capital) | 1st | 1 | 4 | Repair of Classrooms | 2828282.83 | 1 | 1943169.2 | COMPLETED | 1 | 2025-04-12 | February 28, 2025 | 2024-CARAGA-BUTUAN CITY-007 | 2024-CARAGA-BUTUAN CITY-008
5250 | REPAIR 2024 | CARAGA | Butuan City | 132118 | Libertad CES | BUTUAN CITY (Capital) | 1st | 1 | 4 | Repair of Classrooms | 2828282.83 | 1 | 2016301.24 | COMPLETED | 1 | 2025-04-15 | March 15, 2025 | 2024-CARAGA-BUTUAN CITY-006 | 2024-CARAGA-BUTUAN CITY-007
5251 | REPAIR 2024 | CARAGA | Cabadbaran City | 304676 | Calamba National High School | CITY OF CABADBARAN | 2nd | 1 | 10 | Repair of Classrooms | 8402658.12 | 1 | 6020066.94 | Ongoing | 0.9 | 2025-06-27 |  | PB 2024 -001 | [5 empty] | 2024-12-19 | JR-3 Construction and Supply
5252 | REPAIR 2024 | CARAGA | Dinagat Island | 132399 | Magsaysay Elementary School | DINAGAT | Lone | 1 | 5 | Repair of Classrooms | 5369045.39 | 1 | 3652648 | COMPLETED | 1 | 2025-08-15 | 2025-04-25 | INFRA2024-005 | INFRA2024-005 | 2024-10-21 | 2024-10-30 | 2024-11-11 | 2024-11-28 | 2024-12-18 | windfall | realigned from Arellano ES to magsaysay ES
5253 | REPAIR 2024 | CARAGA | Dinagat Island | 324406 | Primitivo J. Ebol Memorial National High School | DINAGAT | Lone | 1 | 4 | Repair of Classrooms | 2693298.1 | 1 | 1866329.36 | COMPLETED | 1 | 2025-02-24 | 2025-02-11 | INFRA2024-003 | INFRA2024-003 | 2024-08-08 | 2024-08-20 | 2024-09-04 | 9/223/2024 | 2024-10-28 | windfall
5254 | REPAIR 2024 | CARAGA | Siargao | 132201 | Sta. Paz Elementary School | SAN ISIDRO | 1st | 1 | 4 | Repair of Classrooms | 2020202.02 | 1 | 1986110.18 | Ongoing | 0.98 | 2025-01-24 |  |  |  | 2024-10-17 | 2024-10-24 | 2024-11-11 | 2024-11-18 | 2024-11-25 | RBEP Construction | rectification of punch listed items of works
5255 | REPAIR 2024 | CARAGA | Siargao | 304789 | Nueva Estrella NHS | SOCORRO | 1st | 1 | 8 | Repair of Classrooms | 7070707.07 | 1 | 6988461.07 | Ongoing | 0.98 | 2025-02-23 |  |  |  | 2024-10-17 | 2024-10-24 | 2024-11-11 | 2024-11-18 | 2024-11-25 | RBEP Construction | rectification of punch listed items of works
5256 | REPAIR 2024 | CARAGA | Surigao City | 132248 | Cantiasay Elementaryn School | SURIGAO CITY (Capital) | 2nd | 1 | 3 | Repair of Classrooms | 1161561.33 | 1 | 740000 | Completed | 1 | 2025-04-09 |  |  | FY-2024-INF-027 | 2024-10-31 | 2024-10-31 | 2024-11-13 | 2024-12-17 | 2025-02-03 | LVRO CONSTRUCTION AND SUPPLY
5257 | REPAIR 2024 | CARAGA | Surigao City | 304803 | Day-asan National High School | SURIGAO CITY (Capital) | 2nd | 1 | 16 | Repair of Classrooms | 6643980.54 | 1 | 4347233.71 | Ongoing | 0.95 | 2025-05-01 |  |  | FY-2024-INF-026 | 2024-10-31 | 2024-10-31 | 2024-11-13 | 2024-12-17 | 2024-12-27 | ARDRAW CONSTRUCTION
5258 | REPAIR 2024 | CARAGA | Surigao del Norte | 132326 | L. J. Mordeno ES | ALEGRIA | 2nd | 1 | 6 | Repair of Classrooms | 3771846.61 | 1 | 2315201.09 | COMPLETED | 1 | 2025-01-14 | 2024-10-25 | BEFF 2024-002 | INFRA010-2024 | 2024-06-27 | 2024-07-04 | 2024-07-16 | 2024-07-24 | 2024-09-16 | WINDFALL CONSTRUCTION
5259 | REPAIR 2024 | CARAGA | Surigao del Norte | 132460 | Malimono Central Elementary School | MALIMONO | 2nd | 1 | 4 | Repair of Classrooms | 2367509.57 | 1 | 1580923.67 | COMPLETED | 1 | 2025-01-14 | 2024-12-09 | BEFF 2024-001 | INFRA009-2024 | 2024-06-27 | 2024-07-04 | 2024-07-16 | 2024-07-24 | 2024-09-16 | WINDFALL CONSTRUCTION
5260 | REPAIR 2024 | CARAGA | Surigao del Sur | 132676 | N.A. Uriarte Memorial Elementary School | CANTILAN | 1st | 1 | 5 | Repair of Classrooms | 4636571.93 | 1 | 938,856.40 2,005,958.69 | COMPLETED | 1 | April 02, 2025 April 17, 2025 | April 01, 2025 | REPAIR 2024 - R XIII - SURIGAO DEL SUR - 001 and 002 | 001 - 2024 002 - 2024 | November 25, 2024 | December 02, 2024 | December 13, 2024 | December 19, 2024 | January 03, 2025 | RENOL Egineering Services & Construction Supply | Cluster 2: Approved Extra Work Order
5261 | REPAIR 2024 | CARAGA | Surigao del Sur | 132751 | Tagasaka Elementary School | HINATUAN | 2nd | 1 | 4 | Repair of Classrooms | 3896180.64 | 1 | 1,232,167.19 1,404,153.07 | COMPLETED | 1 | May 02, 2025 |  | REPAIR 2024 - R XIII - SURIGAO DEL SUR - 003 and 004 | 003 - 2024 004 - 2024 | November 25, 2024 | December 02, 2024 | December 13, 2024 | December 19, 2024 | January 03, 2025 | Trident Engineering Services | With Contract Time Extension
5262 | REPAIR 2024 | CARAGA | Tandag City | 132965 | Hitaob Elementary School | CITY OF TANDAG (Capital) | 1st | 1 | 4 | Repair of Classrooms | 3157118.19 | 1 |  | Ongoing | 0.85 | 2025-03-30 | [7 empty] | 2025-03-25 | CRJ CONSTRUCTION AND SUPPLY
5263 | REPAIR 2024 | CARAGA | Tandag City | 304893 | Vicente L. Pimentel Sr. National High School | CITY OF TANDAG (Capital) | 1st | 1 | 6 | Repair of Classrooms | 4188934.24 | 1 |  | Ongoing | 0.9 | 2025-03-30 | [7 empty] | 2025-03-25 | MELROSHEAN CONSTRUCTION CORPORATION

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%