## Sheet1
INDEX (DO NOT MODIFY) | CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | TOTAL NO. OF BUILDINGS | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | TARGET COMPLETION DATE | ACTUAL DATE OF COMPLETION | PROJECT ID | CONTRACT ID | ISSUANCE OF INVITATION TO BID | PRE-SUBMISSION CONFERENCE | BID OPENING | ISSUANCE OF RESOLUTION TO AWARD | ISSUANCE OF NOTICE TO PROCEED | NAME OF CONTRACTOR | OTHER REMARKS | Status as of July 11, 2025
12 | GABALDON 2020 | NCR | Manila | 136438 | Magat Salamat Elementary School | TONDO | 1 | 1 | 30 | 1 | Rehabilitation of Gabaldon Building | 22518985.22 | 1 | 22438862.19 | Completed | 1 | March 20, 2021 | 2021-07-02 | [6 empty] | June 3, 2020 | Sherf Builders Corporation
218 | GABALDON 2024 | NCR | Manila | 136433 | Emilio Jacinto Elementary School | TONDO | 1st | 1 | 46 | 1 | Conservation and Restoration of Gabaldon School Building | 70290443 | 1 | 64926690.13 | Ongoing | 0.45 | 9/24/2025 |  |  |  | 9/17/2024 | 9/25/2024 | 2024-07-10 | 10/29/2024 | 2025-03-01 | Flordes Construction and Trading | Currently on-going
219 | GABALDON 2024 | NCR | Quezon City | 136524 | Placido del Mundo ES | QUEZON CITY | 6th | 1 | 12 | 1 | Conservation and Restoration of Gabaldon School Building | 12449405.63 | 1 | 11900000 | Not Yet Started | 0 |  |  | SDOQC-2024-INFRA-002 |  | 11/19/2024 | 11/27/2024 | 2024-09-12 | 12/16/2024 |  | Aylan Construction and Trading | To request CO for Architectural Plan, Drafting CMP & awaiting for Sub ARO
220 | GABALDON 2024 | NCR | Taguig City and Pateros | 136896 | Pateros Elementary School | PATEROS | 1st | 1 | 7 | 1 | Conservation and Restoration of Gabaldon School Building | 13343097.49 | 1 | 13243142.21 | Not Yet Started | 0 |  |  |  |  | 2/26/2025 | 2025-04-03 | 3/17/2025 | 3/24/2025 |  |  | For issuance of NOA, Contract and NTP. Awaiting for the lift of election ban

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%