## Sheet1
INDEX (DO NOT MODIFY) | CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | NO. OF CL | SCOPE OF WORK | PROJECT ALLOCATION | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | TARGET COMPLETION DATE | ACTUAL DATE OF COMPLETION | PROJECT ID | CONTRACT ID | ISSUANCE OF INVITATION TO BID | PRE-SUBMISSION CONFERENCE | BID OPENING | ISSUANCE OF RESOLUTION TO AWARD | ISSUANCE OF NOTICE TO PROCEED | NAME OF CONTRACTOR | OTHER REMARKS | Status as of July 11, 2025
155 | LMS 2021 | NIR | Kabankalan City | 117891 | Sagumayon PS | Kabankalan City | 6 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 24548206.13 | 0 | Ongoing | 0.95 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED
156 | LMS 2021 | NIR | Negros Occidental | 302631 | Florentina C. Recto MHS - Caliling Ext | CAUAYAN | 6 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 12162474.45 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED inaugurated (August)
157 | LMS 2021 | NIR | Negros Occidental | 117008 | Patol Elementary School | CAUAYAN | 6 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17312723.74 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED inaugurated (August)
158 | LMS 2021 | NIR | Negros Occidental | 116982 | Talangnan ES | CAUAYAN | 6 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19254393.25 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED inaugurated (August)
170 | LMS 2021 | NIR | Negros Oriental | 120038 | Canlukduhan ES | AYUNGON | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17295671.81 | 17268197.24 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0
171 | LMS 2021 | NIR | Negros Oriental | 120303 | Mongpong Primary School | JIMALALUD | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16599217.8707 | 16572079.83 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0
172 | LMS 2021 | NIR | Negros Oriental | 120482 | Agan-an Elementary School | SIBULAN | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16382034.5205 | 16354914.9 | completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0
173 | LMS 2021 | NIR | Negros Oriental | 120443 | Antulang Elementary School | SIATON | 3 | 1 | 4 | CONSTRUCTION OF ONE (1) UNIT ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16529232.17 | 16502080.2 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0
252 | LMS 2022 | NIR | Negros Oriental | 189514 | Guilongsoran Primary School | SAN JOSE | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16249807.0207 | 16152092.89 | Completed | 1 | 2023-07-19 | 2023-07-19 | ITB 2022-10-136 | LMS202211017 | 2022-10-18 | ############# | ############# | ############# | 2022-12-09 | TRINITYCAD CORPORATION | With approved Time Extension & Variation order - extra work.
474 | LMS 2024 | NIR | Cadiz City | 117533 | Hiyang-Hiyang ES | CADIZ CITY | 2nd | 1 | 5 | CONSTRUCTION OF 1STY 5CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM with hauling cost | 16383838.38 | 15997903.42 | Ongoing | 0.75 | 2025-03-07 | 00:00:00 | 0 | 0 | 2024-06-27 | 2024-07-05 | 2024-07-24 | 2024-08-06 | 2024-02-10 | Keanne construction services | With approved 150CD time extension due to unpassable road (landslide/manual hauling/unpassable road) Project ID and Contract ID to be confirmed from the BAC Secretariat
478 | LMS 2024 | NIR | Himamaylan City | 117066 | Balatogan Elementary School | CITY OF HIMAMAYLAN | 5th | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17171717.17 | 16860289.87 | Ongoing | 0.75 | 2025-06-12 | 00:00:00 | 2024-10-0006 | 2024-10-0006 | 2024-06-29 | 2024-07-11 | 2024-07-23 | 2024-08-20 | 2024-10-08 | JCORD Construction | On going
482 | LMS 2024 | NIR | Negros Occidental | 117026 | Gahit ES | ENRIQUE B. MAGALONA (SARAVIA) | 3rd | 1 | 3 | CONSTRUCTION OF 1STY3CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 11351550.98 | 11139555.27 | Ongoing | 0.85 | 2025-03-03 | 00:00:00 | 23-11-29 | 24-09-005 | 2023-11-20 | 2023-11-27 | 2023-12-11 | 2024-07-26 | 2024-09-17 | KEANNE CONSTRUCTION SERVICES | on-going
483 | LMS 2024 | NIR | Negros Occidental | 117262 | E. Basa ES | MOISES PADILLA (MAGALLON) | 5th | 1 | 3 | CONSTRUCTION OF 1STY3CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 11351550.98 | 9895300.9 | Ongoing | 0.85 | 2025-02-15 | 00:00:00 | 23-11-29 | 24-09-003 | 2023-11-20 | 2023-11-27 | 2023-12-11 | 2024-07-26 | 2024-09-04 | CGGFR Construction and Construction Supply | on-going
484 | LMS 2024 | NIR | Negros Occidental | 180510 | Montelo ES | ILOG | 6th | 1 | 3 | CONSTRUCTION OF 1STY3CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 11351550.98 | 11222892.59 | Ongoing | 0.85 | 2025-03-03 | 00:00:00 | 23-11-004 | 24-09-004 | 2023-11-20 | 2023-11-27 | 2023-12-11 | 2024-07-26 | 2024-09-20 | Par Builders | on-going
490 | LMS 2024 | NIR | Negros Oriental | 120293 | Buto Primary School | JIMALALUD | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 21640739.3 | 18676898.11 | Ongoing | 0.8 | 2025-07-29 | 00:00:00 | ITB 2023-11-145 | LMS202405023 | 2023-11-09 | 2023-11-16 | 2023-11-28 | 2023-12-04 | 2024-05-22 | TrinityCAD Corporation | With approved time extension due to access road issue during rainy days, unworkable weather condition, with change order to cover other essential items(refer to Variation order). Double hauling
491 | LMS 2024 | NIR | Negros Oriental | 120027 | PANUSUAN ELEMENTARY SCHOOL | AMLAN | 2nd | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15703660.79 | 12964000.46 | COMPLETED | 1 | 2025-02-14 | 2025-02-14 | ITB 2023-11-146 | LMS202405024 | 2023-11-09 | 2023-11-16 | 2023-11-28 | 2023-12-04 | 2024-05-22 | TrinityCAD Corporation | With time extension due to variation orders, cutting of trees permit and unworkable weather condition
492 | LMS 2024 | NIR | Negros Oriental | 120618 | Nasuji Elementary School | VALENCIA (LUZURRIAGA) | 3rd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 22517074.36 | 19373377.44 | COMPLETED | 1 | 2025-05-15 | 2025-05-13 | ITB 2023-11-147 | LMS202405025 | 2023-11-09 | 2023-11-16 | 2023-11-28 | 2023-12-04 | 2024-05-22 | TrinityCAD Corporation | With time extension
493 | LMS 2024 | NIR | Siquijor | 120662 | New Corregidor Elementary School | LARENA | Lone | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE | 8295101.98 | 7573374.84 | Ongoing | 0.95 | 2024-11-11 | 2025-05-30 | 10336667 | 2023-89 | 2023-11-22 | 2023-11-29 | 2023-12-11 | 2023-12-12 | 2024-05-16 | Nale Construction | with Time Extension. Revised completion date December 31, 2024

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.