## Sheet1
INDEX (DO NOT MODIFY) | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LEG DISTRICT | NO. OF SITES | SCOPE OF WORK | TOTAL ALLOCATION | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | TARGET COMPLETION DATE | ACTUAL DATE OF COMPLETION | PROJECT ID | CONTRACT ID | ISSUANCE OF INVITATION TO BID | PRE-SUBMISSION CONFERENCE | BID OPENING | ISSUANCE OF RESOLUTION TO AWARD | ISSUANCE OF NOTICE TO PROCEED | NAME OF CONTRACTOR | OTHER REMARKS | Status as of July 11, 2025
2 | Region I | Ilocos Sur | 100684 | Sta. Cruz CS | SANTA CRUZ | 2nd | 1 | PROPOSED TWO (2) - STOREY ALTERNATIVE LEARNING SYSTEM (ALS) BUILDING (22.50m x 9.50m) - with Roof Deck | 12871493.45 | Original: 9,322,239.10 Revised: Php 10,250,272.33 | ongoing | 0.8 | Original: 4/18/2025 Revised: 5/18/2025 |  | PB-015-2024 |  | October 2, 2024 | October 9, 2024 | October 22, 2024 | October 30, 2024 | November 20, 2024 | MA Tejada COnstruction | With additional works amounting to Php 928,033.23 due to revision of plans

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%