## Sheet1
INDEX (DO NOT MODIFY) | CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO OF SITES | SCOPE OF WORK | BATCH | PROJECT ALLOCATION | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | TARGET COMPLETION DATE | ACTUAL DATE OF COMPLETION | PROJECT ID | CONTRACT ID | ISSUANCE OF INVITATION TO BID | PRE-SUBMISSION CONFERENCE | BID OPENING | ISSUANCE OF RESOLUTION TO AWARD | ISSUANCE OF NOTICE TO PROCEED | NAME OF CONTRACTOR | OTHER REMARKS | WITH TRANSFOPMER (Y/N) | CATEGORY 2 | Status as of July 11, 2025
115 | ELECTRIFICATION 2017 | Region II | Cagayan | 102460 | Bulala Sur ES | APARRI | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 551885.05 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
116 | ELECTRIFICATION 2017 | Region II | Cagayan | 102472 | Plaza PS | APARRI | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 474509.84 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
117 | ELECTRIFICATION 2017 | Region II | Cagayan | 102565 | Mala Este PS | BUGUEY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 360773.24 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
118 | ELECTRIFICATION 2017 | Region II | Isabela | 103759 | Malaya ES (Maldam ES) | SAN MARIANO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 219362.91 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
119 | ELECTRIFICATION 2017 | Region II | Isabela | 103763 | Panninan ES | SAN MARIANO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 129288.3 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
120 | ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 104205 | Mandunot ES | ALFONSO CASTAÑEDA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1076701.55 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
121 | ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 156020 | Pelaway ES Annex | ALFONSO CASTAÑEDA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 412734.71 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
122 | ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 156012 | Lihlit PS | AMBAGUIO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1154735.28 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
123 | ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 156019 | Pogonsino Annex Primary School | BAGABAG | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 660613.2 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
124 | ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 103990 | Kakilingan ES | BAYOMBONG (Capital) | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1201001.02 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
125 | ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 104000 | Villa Adriano PS | BAYOMBONG (Capital) | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 785827.01 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
126 | ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 104102 | Pudi PS | KASIBU | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 784569.52 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
127 | ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 104122 | Dayap PS | KAYAPA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 975474 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
128 | ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 104131 | Macdu ES | KAYAPA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1527697.58 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
129 | ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 104137 | Oliweg E/S | KAYAPA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1419459.81 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
130 | ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 156001 | Tidang Village PS | KAYAPA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 473808.36 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
131 | ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 104197 | Cauco ES | SANTA FE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1260159.66 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
132 | ELECTRIFICATION 2017 | Region II | Quirino | 156513 | Diodol PS Annex | AGLIPAY | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 199320.9 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
133 | ELECTRIFICATION 2017 | Region II | Quirino | 104311 | Pamungyen PS | DIFFUN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 181750.86 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
134 | ELECTRIFICATION 2017 | Region II | Quirino | 104359 | Macabo ES | NAGTIPUNAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 286571.16 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
1101 | ELECTRIFICATION 2018 | Region II | Batanes | 300415 | Ivana NHS | IVANA | 0 | 1 | UPGRADING | 1 | 1126860.32 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1102 | ELECTRIFICATION 2018 | Region II | Batanes | 300416 | Mahatao NHS | MAHATAO | 0 | 1 | UPGRADING | 1 | 1095087.83 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1103 | ELECTRIFICATION 2018 | Region II | Batanes | 300417 | Sabtang National School of Fisheries | SABTANG | 0 | 1 | UPGRADING | 1 | 1095087.83 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1104 | ELECTRIFICATION 2018 | Region II | Cagayan | 300420 | Afusing NHS | ALCALA | 1 | 1 | UPGRADING | 1 | 495971.47 |  | terminated | 0.2994 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1105 | ELECTRIFICATION 2018 | Region II | Cagayan | 300421 | Alcala Rural School | ALCALA | 1 | 1 | UPGRADING | 1 | 518889.44 |  | terminated | 0.95 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1106 | ELECTRIFICATION 2018 | Region II | Cagayan | 300471 | Aparri East National High School | APARRI | 1 | 1 | UPGRADING | 1 | 699410.46 |  | terminated | 0.95 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1107 | ELECTRIFICATION 2018 | Region II | Cagayan | 300470 | Aparri West National High School | APARRI | 1 | 1 | UPGRADING | 1 | 567838.55 |  | terminated | 0.95 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1108 | ELECTRIFICATION 2018 | Region II | Cagayan | 300437 | Bukig National Agr'l. and Tech. School | APARRI | 1 | 1 | UPGRADING | 1 | 730017.81 |  | terminated | 0.48 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1109 | ELECTRIFICATION 2018 | Region II | Cagayan | 306020 | AGAMAN NATIONAL HIGH SCHOOL | BAGGAO | 1 | 1 | UPGRADING | 1 | 634259.39 |  | terminated | 0.67 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1110 | ELECTRIFICATION 2018 | Region II | Cagayan | 300429 | Baggao NAS | BAGGAO | 1 | 1 | UPGRADING | 1 | 643414.67 |  | terminated | 0.1097 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1111 | ELECTRIFICATION 2018 | Region II | Cagayan | 300430 | Baggao National School of Arts & Trades | BAGGAO | 1 | 1 | UPGRADING | 1 | 589120.28 |  | terminated | 0.1097 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1112 | ELECTRIFICATION 2018 | Region II | Cagayan | 155053 | Cagurungan Primary School | BAGGAO | 1 | 1 | SOLAR PANEL | 1 | 559889.96 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
1113 | ELECTRIFICATION 2018 | Region II | Cagayan | 300432 | Hacienda Intal NHS | BAGGAO | 1 | 1 | UPGRADING | 1 | 571264.33 |  | terminated | 0.1097 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1114 | ELECTRIFICATION 2018 | Region II | Cagayan | 300433 | Imurung NHS | BAGGAO | 1 | 1 | UPGRADING | 1 | 2011343.55 |  | terminated | 0.67 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1115 | ELECTRIFICATION 2018 | Region II | Cagayan | 102498 | San Antonio ES | BAGGAO | 1 | 1 | SOLAR PANEL | 1 | 1753452.5 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
1116 | ELECTRIFICATION 2018 | Region II | Cagayan | 102503 | Tabugan ES | BAGGAO | 1 | 1 | SOLAR PANEL | 1 | 559889.96 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
1117 | ELECTRIFICATION 2018 | Region II | Cagayan | 306426 | Camalaniugan National High School- Catotoran Annex | CAMALANIUGAN | 1 | 1 | UPGRADING | 1 | 588020.29 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1118 | ELECTRIFICATION 2018 | Region II | Cagayan | 300440 | Calaoagan Dackel NHS | GATTARAN | 1 | 1 | UPGRADING | 1 | 637964.57 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1119 | ELECTRIFICATION 2018 | Region II | Cagayan | 300483 | Gonzaga National High School | GONZAGA | 1 | 1 | UPGRADING | 1 | 617102.21 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1120 | ELECTRIFICATION 2018 | Region II | Cagayan | 300465 | Ipil National High School | GONZAGA | 1 | 1 | UPGRADING | 1 | 2263197.02 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1121 | ELECTRIFICATION 2018 | Region II | Cagayan | 155051 | Laoc Primary School | GONZAGA | 1 | 1 | SOLAR PANEL | 1 | 1846756.72 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
1122 | ELECTRIFICATION 2018 | Region II | Cagayan | 300482 | Rebecca NHS | GONZAGA | 1 | 1 | UPGRADING | 1 | 628809.3 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1123 | ELECTRIFICATION 2018 | Region II | Cagayan | 300469 | LAL-LO NATIONAL HIGH SCHOOL | LAL-LO | 1 | 1 | UPGRADING | 1 | 709465.42 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1124 | ELECTRIFICATION 2018 | Region II | Cagayan | 306004 | Magapit NHS | LAL-LO | 1 | 1 | UPGRADING | 1 | 515742.71 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1125 | ELECTRIFICATION 2018 | Region II | Cagayan | 300488 | Sta. Ana Fishery National High School | SANTA ANA | 1 | 1 | UPGRADING | 1 | 841324.37 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1126 | ELECTRIFICATION 2018 | Region II | Cagayan | 300490 | Sta. Teresita NHS | SANTA TERESITA | 1 | 1 | UPGRADING | 1 | 602505.52 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1127 | ELECTRIFICATION 2018 | Region II | Cagayan | 300473 | Libertad NHS | ABULUG | 2 | 1 | UPGRADING | 1 | 1233921.78 |  | terminated | 0.6085 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1128 | ELECTRIFICATION 2018 | Region II | Cagayan | 300424 | Allacapan VHS | ALLACAPAN | 2 | 1 | UPGRADING | 1 | 740050.2 |  | terminated | 0.6994 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1129 | ELECTRIFICATION 2018 | Region II | Cagayan | 500065 | Mapurao Integ. Learning School | ALLACAPAN | 2 | 1 | UPGRADING | 1 | 671431.74 |  | terminated | 0.6994 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1130 | ELECTRIFICATION 2018 | Region II | Cagayan | 300434 | Ballesteros NHS | BALLESTEROS | 2 | 1 | UPGRADING | 1 | 740050.2 |  | terminated | 0.6085 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1131 | ELECTRIFICATION 2018 | Region II | Cagayan | 155040 | Bibigsan PS | CALAYAN | 2 | 1 | SOLAR PANEL | 1 | 663729.76 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
1132 | ELECTRIFICATION 2018 | Region II | Cagayan | 300441 | Calayan HS | CALAYAN | 2 | 1 | SOLAR PANEL | 1 | 1478886.29 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
1133 | ELECTRIFICATION 2018 | Region II | Cagayan | 102586 | Caniwalan ES | CALAYAN | 2 | 1 | SOLAR PANEL | 1 | 1586151.2 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
1134 | ELECTRIFICATION 2018 | Region II | Cagayan | 102587 | Dadao ES | CALAYAN | 2 | 1 | UPGRADING | 1 | 1688631.96 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1135 | ELECTRIFICATION 2018 | Region II | Cagayan | 102593 | Morol ES | CALAYAN | 2 | 1 | SOLAR PANEL | 1 | 930135.8 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
1136 | ELECTRIFICATION 2018 | Region II | Cagayan | 300450 | Claveria RVS | CLAVERIA | 2 | 1 | UPGRADING | 1 | 501909.48 |  | terminated | 0.6994 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1137 | ELECTRIFICATION 2018 | Region II | Cagayan | 300451 | Claveria SAT | CLAVERIA | 2 | 1 | UPGRADING | 1 | 501909.48 |  | terminated | 0.6994 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1138 | ELECTRIFICATION 2018 | Region II | Cagayan | 300438 | Cabatacan National High School | LASAM | 2 | 1 | UPGRADING | 1 | 2131509.18 |  | terminated | 0.9 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1139 | ELECTRIFICATION 2018 | Region II | Cagayan | 300439 | Nabannagan National High School | LASAM | 2 | 1 | UPGRADING | 1 | 1915584.2 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1140 | ELECTRIFICATION 2018 | Region II | Cagayan | 300497 | Western Cagayan SAT | LASAM | 2 | 1 | UPGRADING | 1 | 1118621.25 |  | terminated | 0.5013 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1141 | ELECTRIFICATION 2018 | Region II | Cagayan | 300481 | Piat National HS | PIAT | 2 | 1 | UPGRADING | 1 | 964556.11 |  | terminated | 0.1452 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1142 | ELECTRIFICATION 2018 | Region II | Cagayan | 102854 | Kittag ES | SANCHEZ-MIRA | 2 | 1 | SOLAR PANEL | 1 | 527749.68 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
1143 | ELECTRIFICATION 2018 | Region II | Cagayan | 155046 | Pureg Elementary School | SANCHEZ-MIRA | 2 | 1 | SOLAR PANEL | 1 | 506644.68 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
1144 | ELECTRIFICATION 2018 | Region II | Cagayan | 300486 | Sanchez Mira SAT | SANCHEZ-MIRA | 2 | 1 | UPGRADING | 1 | 740050.2 |  | terminated | 0.6994 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1145 | ELECTRIFICATION 2018 | Region II | Cagayan | 102862 | Santiago Elementary School | SANCHEZ-MIRA | 2 | 1 | SOLAR PANEL | 1 | 734565.68 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
1146 | ELECTRIFICATION 2018 | Region II | Cagayan | 300489 | Sta. Praxedes HS | SANTA PRAXEDES | 2 | 1 | UPGRADING | 1 | 570762.04 |  | terminated | 0.6994 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1147 | ELECTRIFICATION 2018 | Region II | Cagayan | 306017 | Amulung NHS - Dadda Ext. | AMULUNG | 3 | 1 | UPGRADING | 1 | 1146918.75 |  | terminated | 0.3408 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1148 | ELECTRIFICATION 2018 | Region II | Cagayan | 300458 | Enrile Vocational High School | ENRILE | 3 | 1 | UPGRADING | 1 | 668475.19 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1149 | ELECTRIFICATION 2018 | Region II | Cagayan | 300472 | Lemu NHS | ENRILE | 3 | 1 | UPGRADING | 1 | 579730.22 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1150 | ELECTRIFICATION 2018 | Region II | Cagayan | 300459 | Western Enrile Vocational High School | ENRILE | 3 | 1 | UPGRADING | 1 | 824448.52 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1151 | ELECTRIFICATION 2018 | Region II | Cagayan | 306421 | CARIDAD B. TRINIDAD NHS | IGUIG | 3 | 1 | UPGRADING | 1 | 612469.14 |  | terminated | 0.3408 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1152 | ELECTRIFICATION 2018 | Region II | Cagayan | 300446 | Cabbo NHS | PEÑABLANCA | 3 | 1 | UPGRADING | 1 | 599373.57 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1153 | ELECTRIFICATION 2018 | Region II | Cagayan | 300457 | Penablanca East NHS | PEÑABLANCA | 3 | 1 | UPGRADING | 1 | 730602.29 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1154 | ELECTRIFICATION 2018 | Region II | Cagayan | 300445 | Penablanca National High School | PEÑABLANCA | 3 | 1 | UPGRADING | 1 | 620842.75 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1155 | ELECTRIFICATION 2018 | Region II | Cagayan | 300467 | Itawes National High School | TUAO | 3 | 1 | UPGRADING | 1 | 730602.29 |  | terminated | 0.1452 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1156 | ELECTRIFICATION 2018 | Region II | Cagayan | 300468 | Itawes Nat'l.l Agr'l. & Tech'l. School - Bagumbayan Annex | TUAO | 3 | 1 | UPGRADING | 1 | 538676.19 |  | terminated | 0.1452 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1157 | ELECTRIFICATION 2018 | Region II | Cagayan | 300492 | Tuao Voc'l. and Tech'l. School | TUAO | 3 | 1 | UPGRADING | 1 | 750245.64 |  | terminated | 0.0591 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1158 | ELECTRIFICATION 2018 | Region II | Cagayan | 300493 | Tuao Voc'l. and Tech'l. School - Culung Annex | TUAO | 3 | 1 | UPGRADING | 1 | 532184.83 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1159 | ELECTRIFICATION 2018 | Region II | Cagayan | 306019 | Tuao Voc'l. and Tech'l. School - Malummin Annex | TUAO | 3 | 1 | UPGRADING | 1 | 505444.28 |  | terminated | 0.0591 | [10 empty] | Contract Termination is on Process |  | UPGRADING
1160 | ELECTRIFICATION 2018 | Region II | Cauayan City | 323901 | Cauayan City NHS - Research Annex | CITY OF CAUAYAN | 3 | 1 | UPGRADING | 1 | 569092.68 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1161 | ELECTRIFICATION 2018 | Region II | Cauayan City | 103215 | Faustino ES | CITY OF CAUAYAN | 3 | 1 | UPGRADING | 1 | 1416994.55 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1162 | ELECTRIFICATION 2018 | Region II | Cauayan City | 103241 | Sillawit ES | CITY OF CAUAYAN | 3 | 1 | UPGRADING | 1 | 2061137.84 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1163 | ELECTRIFICATION 2018 | Region II | Cauayan City | 323903 | Villa Concepcion HS - Rogus Ext. | CITY OF CAUAYAN | 3 | 1 | UPGRADING | 1 | 348325.74 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1164 | ELECTRIFICATION 2018 | Region II | Cauayan City | 300614 | Villaluna NHS | CITY OF CAUAYAN | 3 | 1 | UPGRADING | 1 | 618992.18 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1165 | ELECTRIFICATION 2018 | Region II | Cauayan City | 306107 | WEST TABACAL REGION NATIONAL HIGH SCHOOL | CITY OF CAUAYAN | 3 | 1 | UPGRADING | 1 | 2160530.55 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1166 | ELECTRIFICATION 2018 | Region II | City of Ilagan | 300542 | Isabela NHS - Main | ILAGAN (Capital) | 1 | 1 | UPGRADING | 1 | 1452300.94 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1167 | ELECTRIFICATION 2018 | Region II | City of Ilagan | 306105 | ISAT-Main | ILAGAN (Capital) | 1 | 1 | UPGRADING | 1 | 3689427.49 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1168 | ELECTRIFICATION 2018 | Region II | City of Ilagan | 300583 | San Antonio Nat'l. Agro-Ind'l. & Voc'l. HS | ILAGAN (Capital) | 1 | 1 | UPGRADING | 1 | 679654.89 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1169 | ELECTRIFICATION 2018 | Region II | Isabela | 300521 | Alfreda Albano NHS - Magassi, Cabagan | CABAGAN | 1 | 1 | UPGRADING | 1 | 1800665.03 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1170 | ELECTRIFICATION 2018 | Region II | Isabela | 300522 | Delfin Albano HS - San Juan Annex | CABAGAN | 1 | 1 | UPGRADING | 1 | 1406343.79 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1171 | ELECTRIFICATION 2018 | Region II | Isabela | 300520 | Delfin Albano HS-Main | CABAGAN | 1 | 1 | UPGRADING | 1 | 1897430.9 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1172 | ELECTRIFICATION 2018 | Region II | Isabela | 103145 | Cabagan Science Elementary School | CABANGAN | 1 | 1 | UPGRADING | 3 | 868239.54 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1173 | ELECTRIFICATION 2018 | Region II | Isabela | 306133 | Aneg National High School | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | UPGRADING | 3 | 995822.45 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1174 | ELECTRIFICATION 2018 | Region II | Isabela | 306162 | Bayabo Integrated School | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | UPGRADING | 3 | 1046855.62 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1175 | ELECTRIFICATION 2018 | Region II | Isabela | 103269 | Delfin Albano Central School | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | UPGRADING | 3 | 3325977.82 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1176 | ELECTRIFICATION 2018 | Region II | Isabela | 300587 | Ragan Sur National High School | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | UPGRADING | 3 | 2637011.33 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1177 | ELECTRIFICATION 2018 | Region II | Isabela | 300585 | San Antonio NHS | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | UPGRADING | 1 | 2827752.29 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1178 | ELECTRIFICATION 2018 | Region II | Isabela | 103554 | Divilacan Central School | DIVILACAN | 1 | 1 | UPGRADING | 3 | 2574707.64 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1179 | ELECTRIFICATION 2018 | Region II | Isabela | 300554 | Isabela SF | PALANAN | 1 | 1 | SOLAR PANEL | 1 | 2206445.44 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
1180 | ELECTRIFICATION 2018 | Region II | Isabela | 300601 | St. Paul Voc'l. & Ind'l. HS-Main | SAN PABLO | 1 | 1 | UPGRADING | 1 | 1323322.14 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1181 | ELECTRIFICATION 2018 | Region II | Isabela | 300605 | Buenaventura G. Masigan National High School | SANTA MARIA | 1 | 1 | UPGRADING | 3 | 1382139.14 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1182 | ELECTRIFICATION 2018 | Region II | Isabela | 300603 | Santa Maria High School | SANTA MARIA | 1 | 1 | UPGRADING | 1 | 1646981.65 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1183 | ELECTRIFICATION 2018 | Region II | Isabela | 103854 | Sta. Maria Central School | SANTA MARIA | 1 | 1 | UPGRADING | 3 | 1992023.28 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1184 | ELECTRIFICATION 2018 | Region II | Isabela | 300606 | Sto Tomas NHS | SANTO TOMAS | 1 | 1 | UPGRADING | 1 | 1649011.33 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1185 | ELECTRIFICATION 2018 | Region II | Isabela | 103871 | Sto. Tomas Central School | SANTO TOMAS | 1 | 1 | UPGRADING | 3 | 1190764.76 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1186 | ELECTRIFICATION 2018 | Region II | Isabela | 300547 | Antagan National High School | TUMAUINI | 1 | 1 | UPGRADING | 3 | 2155606.72 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1187 | ELECTRIFICATION 2018 | Region II | Isabela | 306153 | Cumabao IS | TUMAUINI | 1 | 1 | UPGRADING | 1 | 1451220.68 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1188 | ELECTRIFICATION 2018 | Region II | Isabela | 306109 | Fermeldy National High School | TUMAUINI | 1 | 1 | UPGRADING | 3 | 2709258.71 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1189 | ELECTRIFICATION 2018 | Region II | Isabela | 300556 | Lalauanan National High School | TUMAUINI | 1 | 1 | UPGRADING | 3 | 2201117.74 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1190 | ELECTRIFICATION 2018 | Region II | Isabela | 300551 | Lanna National High School | TUMAUINI | 1 | 1 | UPGRADING | 3 | 2321207.03 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1191 | ELECTRIFICATION 2018 | Region II | Isabela | 300609 | Tumauini NHS | TUMAUINI | 1 | 1 | UPGRADING | 1 | 1628465.08 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1192 | ELECTRIFICATION 2018 | Region II | Isabela | 103884 | Tumauini North Central School | TUMAUINI | 1 | 1 | UPGRADING | 3 | 1896448.69 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1193 | ELECTRIFICATION 2018 | Region II | Isabela | 103903 | Tumauini South Central School | TUMAUINI | 1 | 1 | UPGRADING | 3 | 2222813.05 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1194 | ELECTRIFICATION 2018 | Region II | Isabela | 103904 | Tumauini West Central School | TUMAUINI | 1 | 1 | UPGRADING | 3 | 1898495.2 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1195 | ELECTRIFICATION 2018 | Region II | Isabela | 103072 | Aurora Central School | AURORA | 2 | 1 | UPGRADING | 3 | 1176056.83 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1196 | ELECTRIFICATION 2018 | Region II | Isabela | 103102 | Benito Soliven Central School | BENITO SOLIVEN | 2 | 1 | UPGRADING | 3 | 1012396.63 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1197 | ELECTRIFICATION 2018 | Region II | Isabela | 300503 | Benito Soliven NHS | BENITO SOLIVEN | 2 | 1 | UPGRADING | 1 | 1176226.66 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1198 | ELECTRIFICATION 2018 | Region II | Isabela | 500079 | Maluno Integrated School - Main | BENITO SOLIVEN | 2 | 1 | UPGRADING | 3 | 1468714.47 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1199 | ELECTRIFICATION 2018 | Region II | Isabela | 500072 | Villaluz Integrated School | BENITO SOLIVEN | 2 | 1 | UPGRADING | 3 | 896259.08 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1200 | ELECTRIFICATION 2018 | Region II | Isabela | 500019 | Yeban Integrated School | BENITO SOLIVEN | 2 | 1 | UPGRADING | 3 | 1414672.6 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1201 | ELECTRIFICATION 2018 | Region II | Isabela | 103128 | Burgos Central School | BURGOS | 2 | 1 | UPGRADING | 3 | 1153599.18 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1202 | ELECTRIFICATION 2018 | Region II | Isabela | 300509 | BURGOS NHS (formerly Caliguian NHS-Main) | BURGOS | 2 | 1 | UPGRADING | 1 | 1414778.54 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1203 | ELECTRIFICATION 2018 | Region II | Isabela | 300511 | San Antonino NHS | BURGOS | 2 | 1 | UPGRADING | 1 | 1273274.55 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1204 | ELECTRIFICATION 2018 | Region II | Isabela | 103343 | Gamu Central School | GAMU | 2 | 1 | UPGRADING | 3 | 1113294.27 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1205 | ELECTRIFICATION 2018 | Region II | Isabela | 300559 | Mabini National High School | GAMU | 2 | 1 | UPGRADING | 3 | 1639894.93 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1206 | ELECTRIFICATION 2018 | Region II | Isabela | 500077 | Bimonton Integrated School | MALLIG | 2 | 1 | UPGRADING | 2 | 1218106.74 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1207 | ELECTRIFICATION 2018 | Region II | Isabela | 103496 | Mallig Central School - Main | MALLIG | 2 | 1 | UPGRADING | 3 | 1628332.69 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1208 | ELECTRIFICATION 2018 | Region II | Isabela | 300561 | Mallig NHS (formerly Mallig NHS - Main) | MALLIG | 2 | 1 | UPGRADING | 1 | 1148985.74 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1209 | ELECTRIFICATION 2018 | Region II | Isabela | 306110 | San Jose NHS (formerly Mallig HS -San Jose Norte Annex) | MALLIG | 2 | 1 | UPGRADING | 1 | 1190682.84 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1210 | ELECTRIFICATION 2018 | Region II | Isabela | 103520 | Naguilian Central School | NAGUILIAN | 2 | 1 | UPGRADING | 3 | 2080920.05 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1211 | ELECTRIFICATION 2018 | Region II | Isabela | 306112 | Barucboc National High School | QUEZON | 2 | 1 | UPGRADING | 3 | 1222637.7 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1212 | ELECTRIFICATION 2018 | Region II | Isabela | 103571 | Quezon CS | QUEZON | 2 | 1 | UPGRADING | 3 | 2092542.49 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1213 | ELECTRIFICATION 2018 | Region II | Isabela | 300568 | Quezon HS - Main | QUEZON | 2 | 1 | UPGRADING | 1 | 1181729.01 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1214 | ELECTRIFICATION 2018 | Region II | Isabela | 500071 | San Juan Integrated School | QUEZON | 2 | 1 | UPGRADING | 3 | 872096.39 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1215 | ELECTRIFICATION 2018 | Region II | Isabela | 103580 | Quirino Central School | QUIRINO | 2 | 1 | UPGRADING | 3 | 1860295.48 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1216 | ELECTRIFICATION 2018 | Region II | Isabela | 500068 | Villa Cacho Integrated School | QUIRINO | 2 | 1 | UPGRADING | 3 | 1736088.03 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1217 | ELECTRIFICATION 2018 | Region II | Isabela | 306111 | Monico Rarama NHS (Munoz HS -San Pedro Extension) | ROXAS | 2 | 1 | UPGRADING | 1 | 1252371.25 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1218 | ELECTRIFICATION 2018 | Region II | Isabela | 300562 | Munoz HS | ROXAS | 2 | 1 | UPGRADING | 1 | 1173740.73 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1219 | ELECTRIFICATION 2018 | Region II | Isabela | 300579 | Roxas NHS-Main | ROXAS | 2 | 1 | UPGRADING | 1 | 1999770.49 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1220 | ELECTRIFICATION 2018 | Region II | Isabela | 500094 | Simimbaan Integrated School | ROXAS | 2 | 1 | UPGRADING | 1 | 1218106.74 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1221 | ELECTRIFICATION 2018 | Region II | Isabela | 300512 | Callang NHS - Main | SAN MANUEL | 2 | 1 | UPGRADING | 1 | 1744759.24 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1222 | ELECTRIFICATION 2018 | Region II | Isabela | 300514 | Sandiat NHS | SAN MANUEL | 2 | 1 | UPGRADING | 1 | 1547898.63 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1223 | ELECTRIFICATION 2018 | Region II | Isabela | 300593 | Alibadabad National High School | SAN MARIANO | 2 | 1 | UPGRADING | 3 | 430415.85 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1224 | ELECTRIFICATION 2018 | Region II | Isabela | 500086 | Dicamay Integrated School | SAN MARIANO | 2 | 1 | UPGRADING | 3 | 964475.61 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1225 | ELECTRIFICATION 2018 | Region II | Isabela | 300500 | Alicia National High School | ALICIA | 3 | 1 | UPGRADING | 2 | 1648463.28 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1226 | ELECTRIFICATION 2018 | Region II | Isabela | 300565 | Palayan Region HS | ALICIA | 3 | 1 | UPGRADING | 1 | 1186861.71 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1227 | ELECTRIFICATION 2018 | Region II | Isabela | 300576 | Rizal Region NHS , Alicia, Isabela | ALICIA | 3 | 1 | UPGRADING | 1 | 1075486.31 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1228 | ELECTRIFICATION 2018 | Region II | Isabela | 300506 | Cadaloria HS | ANGADANAN | 3 | 1 | UPGRADING | 1 | 1049158.75 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1229 | ELECTRIFICATION 2018 | Region II | Isabela | 500020 | Lomboy Integrated School | ANGADANAN | 3 | 1 | UPGRADING | 3 | 876175.06 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1230 | ELECTRIFICATION 2018 | Region II | Isabela | 300504 | Cabatuan National High School | CABATUAN | 3 | 1 | UPGRADING | 1 | 1929966.85 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1231 | ELECTRIFICATION 2018 | Region II | Isabela | 300558 | Luna NHS | LUNA | 3 | 1 | UPGRADING | 1 | 1195227.54 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1232 | ELECTRIFICATION 2018 | Region II | Isabela | 103624 | Reina Mercedes Central School | REINA MERCEDES | 3 | 1 | UPGRADING | 3 | 974739.09 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1233 | ELECTRIFICATION 2018 | Region II | Isabela | 300575 | Reina Mercedes Vocational and Industrial School | REINA MERCEDES | 3 | 1 | UPGRADING | 1 | 1432514.77 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1234 | ELECTRIFICATION 2018 | Region II | Isabela | 306116 | Reina Mercedes Vocational High School | REINA MERCEDES | 3 | 1 | UPGRADING | 1 | 1116614.51 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1235 | ELECTRIFICATION 2018 | Region II | Isabela | 300590 | San Guillermo Voc'l & Ind'l High Sch. | SAN GUILLERMO | 3 | 1 | UPGRADING | 1 | 1074656.19 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1236 | ELECTRIFICATION 2018 | Region II | Isabela | 300581 | Salinungan NHS | SAN MATEO | 3 | 1 | UPGRADING | 1 | 1245397.84 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1237 | ELECTRIFICATION 2018 | Region II | Isabela | 306143 | Cagasat HS-Magsasay Annex | CORDON | 4 | 1 | UPGRADING | 1 | 813316.04 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1238 | ELECTRIFICATION 2018 | Region II | Isabela | 300508 | CAGASAT NHS | CORDON | 4 | 1 | UPGRADING | 1 | 790744.56 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1239 | ELECTRIFICATION 2018 | Region II | Isabela | 300523 | Diadi Region HS | CORDON | 4 | 1 | UPGRADING | 1 | 885270.95 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1240 | ELECTRIFICATION 2018 | Region II | Isabela | 300532 | Dona Josefa E. Marcos HS | CORDON | 4 | 1 | UPGRADING | 1 | 834063 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1241 | ELECTRIFICATION 2018 | Region II | Isabela | 300526 | Dinapigue NHS | DINAPIGUE | 4 | 1 | UPGRADING | 1 | 889647.51 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1242 | ELECTRIFICATION 2018 | Region II | Isabela | 300529 | Don Mariano Marcos NHS | ECHAGUE | 4 | 1 | UPGRADING | 1 | 784636.12 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1243 | ELECTRIFICATION 2018 | Region II | Isabela | 300612 | Echague National High School | ECHAGUE | 4 | 1 | UPGRADING | 2 | 825152.88 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1244 | ELECTRIFICATION 2018 | Region II | Isabela | 300539 | Highway Region NHS | ECHAGUE | 4 | 1 | UPGRADING | 1 | 820545.41 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1245 | ELECTRIFICATION 2018 | Region II | Isabela | 300566 | Pangal Sur HS | ECHAGUE | 4 | 1 | UPGRADING | 1 | 831472.93 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1246 | ELECTRIFICATION 2018 | Region II | Isabela | 300611 | Ugad HS | ECHAGUE | 4 | 1 | UPGRADING | 1 | 1062208.47 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1247 | ELECTRIFICATION 2018 | Region II | Isabela | 300555 | Jones Rural School - Main | JONES | 4 | 1 | UPGRADING | 1 | 1480331.65 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1248 | ELECTRIFICATION 2018 | Region II | Isabela | 103600 | Gen. Aguinaldo ES - Villa Verde PS Annex | RAMON | 4 | 1 | UPGRADING | 3 | 939585.17 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1249 | ELECTRIFICATION 2018 | Region II | Isabela | 300572 | Gen. Emilio Aguinaldo NHS | RAMON | 4 | 1 | UPGRADING | 1 | 817580.17 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1250 | ELECTRIFICATION 2018 | Region II | Isabela | 300571 | Ramon National High School | RAMON | 4 | 1 | UPGRADING | 2 | 967178.24 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1251 | ELECTRIFICATION 2018 | Region II | Isabela | 300574 | Raniag HS | RAMON | 4 | 1 | UPGRADING | 1 | 1184147.04 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1252 | ELECTRIFICATION 2018 | Region II | Isabela | 500092 | San Miguel Integrated School-Main | RAMON | 4 | 1 | UPGRADING | 2 | 1127436.31 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1253 | ELECTRIFICATION 2018 | Region II | Isabela | 306142 | San Sebastian Integrated School | RAMON | 4 | 1 | UPGRADING | 1 | 1149327.62 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1254 | ELECTRIFICATION 2018 | Region II | Isabela | 300518 | Dabubu High School Main & Annex | SAN AGUSTIN | 4 | 1 | UPGRADING | 1 | 1145258.17 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1255 | ELECTRIFICATION 2018 | Region II | Isabela | 300591 | San Isidro NHS | SAN ISIDRO | 4 | 1 | UPGRADING | 1 | 903294.53 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1256 | ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 300617 | Ambaguio High School | AMBAGUIO | 0 | 1 | UPGRADING | 1 | 2380840.46 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
1257 | ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 300620 | Bambang NHS | BAMBANG | 0 | 1 | UPGRADING | 1 | 4643660.5 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
1258 | ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 300635 | Dupax del Norte NHS | DUPAX DEL NORTE | 0 | 1 | UPGRADING | 1 | 5168669.82 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
1259 | ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 300628 | Dupax del Sur NHS | DUPAX DEL SUR | 0 | 1 | UPGRADING | 1 | 1453392.33 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
1260 | ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 104098 | Papalungan ES | KASIBU | 0 | 1 | SOLAR PANEL | 1 | 3440083.05 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
1261 | ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 104114 | Ban-et PS | KAYAPA | 0 | 1 | SOLAR PANEL | 1 | 1377860.4 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
1262 | ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 300633 | Martinez Cuyangan NHS | KAYAPA | 0 | 1 | UPGRADING | 1 | 2511723.29 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
1263 | ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 306204 | Runruno National High School | QUEZON | 0 | 1 | UPGRADING | 1 | 2299961.96 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
1264 | ELECTRIFICATION 2018 | Region II | Quirino | 300652 | Aglipay NHS | AGLIPAY | 0 | 1 | UPGRADING | 1 | 470878.68 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
1265 | ELECTRIFICATION 2018 | Region II | Quirino | 300663 | Pinaripad NHS | AGLIPAY | 0 | 1 | UPGRADING | 1 | 722573.4 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
1266 | ELECTRIFICATION 2018 | Region II | Quirino | 300653 | Victoria HS | AGLIPAY | 0 | 1 | UPGRADING | 1 | 605581.61 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
1267 | ELECTRIFICATION 2018 | Region II | Quirino | 300656 | Cabarroguis NSAT | CABARROGUIS (Capital) | 0 | 1 | UPGRADING | 1 | 938805.89 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
1268 | ELECTRIFICATION 2018 | Region II | Quirino | 300664 | Quirino General HS | CABARROGUIS (Capital) | 0 | 1 | UPGRADING | 1 | 995383.23 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
1269 | ELECTRIFICATION 2018 | Region II | Quirino | 300666 | Tucod HS | CABARROGUIS (Capital) | 0 | 1 | UPGRADING | 1 | 618440.27 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
1270 | ELECTRIFICATION 2018 | Region II | Quirino | 300657 | Diffun HS | DIFFUN | 0 | 1 | UPGRADING | 1 | 865201.89 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
1271 | ELECTRIFICATION 2018 | Region II | Quirino | 300661 | Magsaysay National High School | DIFFUN | 0 | 1 | UPGRADING | 1 | 561006.88 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
1272 | ELECTRIFICATION 2018 | Region II | Quirino | 300654 | Balligui HS | MADDELA | 0 | 1 | UPGRADING | 1 | 506369.85 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
1273 | ELECTRIFICATION 2018 | Region II | Quirino | 306317 | Dumabato Integrated School | MADDELA | 0 | 1 | UPGRADING | 1 | 742761.6 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
1274 | ELECTRIFICATION 2018 | Region II | Quirino | 300660 | Maddela CHS | MADDELA | 0 | 1 | UPGRADING | 1 | 1181950.74 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
1275 | ELECTRIFICATION 2018 | Region II | Quirino | 306309 | San Martin IS | MADDELA | 0 | 1 | UPGRADING | 1 | 222063.52 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
1276 | ELECTRIFICATION 2018 | Region II | Quirino | 306310 | GIAYAN INTEGRATED SCHOOL | NAGTIPUNAN | 0 | 1 | SOLAR PANEL | 1 | 2653311.76 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
1277 | ELECTRIFICATION 2018 | Region II | Quirino | 300662 | Nagtipunan NHS | NAGTIPUNAN | 0 | 1 | UPGRADING | 1 | 687122.84 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
1278 | ELECTRIFICATION 2018 | Region II | Quirino | 306303 | Sangbay IS | NAGTIPUNAN | 0 | 1 | UPGRADING | 1 | 350034.81 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
1279 | ELECTRIFICATION 2018 | Region II | Quirino | 306316 | Scala Integrated School | NAGTIPUNAN | 0 | 1 | UPGRADING | 1 | 759093.07 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
1280 | ELECTRIFICATION 2018 | Region II | Quirino | 300665 | Saguday NHS | SAGUDAY | 0 | 1 | UPGRADING | 1 | 716743.19 |  | COMPLETED | 1 |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 | [5 empty] | UPGRADING
1281 | ELECTRIFICATION 2018 | Region II | Santiago City | 300578 | Rizal National High School | CITY OF SANTIAGO | 4 | 1 | UPGRADING | 1 | 1974024.18 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1282 | ELECTRIFICATION 2018 | Region II | Santiago City | 325201 | Santiago City National High School - Sinsayon | CITY OF SANTIAGO | 4 | 1 | UPGRADING | 1 | 372407.59 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1283 | ELECTRIFICATION 2018 | Region II | Tuguegarao City | 300668 | CAGAYAN NHS - SENIOR HIGH SCHOOL | Tuguegarao City | 0 | 1 | UPGRADING | 1 | 762912.06 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1284 | ELECTRIFICATION 2018 | Region II | Tuguegarao City | 300669 | CATAGGAMAN NHS-SENIOR HIGH SCHOOL | Tuguegarao City | 0 | 1 | UPGRADING | 1 | 447205.36 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1285 | ELECTRIFICATION 2018 | Region II | Tuguegarao City | 300670 | LINAO NHS - SENIOR HIGH SCHOOL | Tuguegarao City | 0 | 1 | UPGRADING | 1 | 369305.78 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1286 | ELECTRIFICATION 2018 | Region II | Tuguegarao City | 306401 | TUGUEGARAO CITY SENIOR HIGH SCHOOL | Tuguegarao City | 0 | 1 | UPGRADING | 1 | 751115.65 |  | COMPLETED | 1 | [12 empty] | UPGRADING
1287 | ELECTRIFICATION 2018 | Region II | Tuguegarao City |  | GOSI NHS - SENIOR HIGH SCHOOL | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | 2 | 440825.28 |  | COMPLETED | 1 | [12 empty] | UPGRADING
3028 | ELECTRIFICATION 2019 | Region II | Batanes | 102316 | Itbayat Central School | ITBAYAT | 0 | 1 | UPGRADING | Batch 3 | 1380118.87 |  | TERMINATED | 0.85 | [12 empty] | UPGRADING
3029 | ELECTRIFICATION 2019 | Region II | Batanes | 102317 | Mayan Elementary School | ITBAYAT | 0 | 1 | UPGRADING | Batch 1 | 1350673.21 |  | TERMINATED | 0.85 | [12 empty] | UPGRADING
3030 | ELECTRIFICATION 2019 | Region II | Batanes | 500062 | Itbud Integrated School | UYUGAN | 0 | 1 | UPGRADING | Batch 1 | 1499384.73 |  | REVERTED | 0 | [12 empty] | UPGRADING
3031 | ELECTRIFICATION 2019 | Region II | Cagayan | 300431 | Baggao NHS | BAGGAO | 1 | 1 | UPGRADING | Batch 3 | 841345.4 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3032 | ELECTRIFICATION 2019 | Region II | Cagayan | 306011 | Licerio Antiporda Sr. NHS - Dalaya Ext. | BUGUEY | 1 | 1 | UPGRADING |  | 518902.41 |  | TERMINATED | 0.85 | [10 empty] | Contract Termination is on Process | Y | UPGRADING
3033 | ELECTRIFICATION 2019 | Region II | Cagayan | 306423 | Cabiraoan National High School | GONZAGA | 1 | 1 | UPGRADING |  | 571278.61 |  | TERMINATED | 0.4 | [10 empty] | Contract Termination is on Process | Y | UPGRADING
3034 | ELECTRIFICATION 2019 | Region II | Cagayan | 306013 | Luga National High School | SANTA TERESITA | 1 | 1 | UPGRADING | Batch 3 | 546120.81 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3035 | ELECTRIFICATION 2019 | Region II | Cagayan | 300478 | Mauanan NHS | RIZAL | 2 | 1 | UPGRADING |  | 570776.31 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3036 | ELECTRIFICATION 2019 | Region II | Cagayan | 306014 | LUBO NATIONAL HIGH SCHOOL | SANTO NIÑO (FAIRE) | 2 | 1 | UPGRADING | Batch 3 | 570776.31 |  | TERMINATED | 0.4 | [10 empty] | Contract Termination is on Process | Y | UPGRADING
3037 | ELECTRIFICATION 2019 | Region II | Cagayan | 300491 | Sto. Nino NHS | SANTO NIÑO (FAIRE) | 2 | 1 | UPGRADING |  | 570776.31 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3038 | ELECTRIFICATION 2019 | Region II | Cagayan | 300425 | AMULUNG NATIONAL HIGH SCHOOL | AMULUNG | 3 | 1 | UPGRADING |  | 766345.96 |  | TERMINATED | 0.4 | [10 empty] | Contract Termination is on Process | Y | UPGRADING
3039 | ELECTRIFICATION 2019 | Region II | Cagayan | 300453 | Bayabat NHS | AMULUNG | 3 | 1 | UPGRADING | Batch 3 | 660427.53 |  | TERMINATED | 0.6 | [10 empty] | Contract Termination is on Process | Y | UPGRADING
3040 | ELECTRIFICATION 2019 | Region II | Cagayan | 300452 | Cordova National High Sschool | AMULUNG | 3 | 1 | UPGRADING |  | 870957.81 |  | TERMINATED | 0.55 | [10 empty] | Contract Termination is on Process | Y | UPGRADING
3041 | ELECTRIFICATION 2019 | Region II | Cagayan | 306010 | PACAC GRANDE NAT'L. HIGH SCHOOL | AMULUNG | 3 | 1 | UPGRADING |  | 696444.35 |  | TERMINATED | 0.45 | [10 empty] | Contract Termination is on Process | Y | UPGRADING
3042 | ELECTRIFICATION 2019 | Region II | Cagayan | 300427 | Dassun NHS | SOLANA | 3 | 1 | UPGRADING | Batch 3 | 660427.53 |  | COMPLETED | 1 | [10 empty] | Contract Termination is on Process | Y | UPGRADING
3043 | ELECTRIFICATION 2019 | Region II | Cauayan City | 103227 | Alinam ES | CITY OF CAUAYAN | 3 | 1 | UPGRADING | Batch 1 | 1131302.69 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
3044 | ELECTRIFICATION 2019 | Region II | City of Ilagan | 300548 | Dappat Integrated School | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING |  | 1188658.04 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3045 | ELECTRIFICATION 2019 | Region II | City of Ilagan | 500087 | Gayong-Gayong Sur Integrated School | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1285590.7 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3046 | ELECTRIFICATION 2019 | Region II | City of Ilagan | 500992 | Ilagan East Integrated SPED Center | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 1 | 1105333.93 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3047 | ELECTRIFICATION 2019 | Region II | City of Ilagan | 103402 | Ilagan South CS | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING |  | 4454556.78 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3048 | ELECTRIFICATION 2019 | Region II | City of Ilagan | 300540 | Ilagan West NHS | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING |  | 1051958.94 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3049 | ELECTRIFICATION 2019 | Region II | City of Ilagan | 306149 | ISAT-Cabannungan Annex | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1210672.67 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3050 | ELECTRIFICATION 2019 | Region II | City of Ilagan | 500080 | Lupigue Integrated School (formerly Lupigue ES) | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1441858.38 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3051 | ELECTRIFICATION 2019 | Region II | City of Ilagan | 500078 | Manaring IS (Bangag-Manaring-Capo ES) | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING |  | 1441858.38 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3052 | ELECTRIFICATION 2019 | Region II | City of Ilagan | 103428 | Naguilian Baculud Elementary School | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1333997.26 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3053 | ELECTRIFICATION 2019 | Region II | City of Ilagan | 300543 | Rang-ayan NHS (Isabela NHS - Rang-ayan Annex) | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1179541.85 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3054 | ELECTRIFICATION 2019 | Region II | City of Ilagan | 103375 | San Juan Rugao ES | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING |  | 2704783.67 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3055 | ELECTRIFICATION 2019 | Region II | City of Ilagan | 500018 | San Lorenzo Integrated School (San Lorenzo ES) | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1314275.46 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3056 | ELECTRIFICATION 2019 | Region II | City of Ilagan | 500074 | San Pedro Integrated School | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING |  | 1951396.03 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3057 | ELECTRIFICATION 2019 | Region II | City of Ilagan | 300584 | San Rafael Nat'l & Voc'l HS (San Antonio NAIVHS-San Rafael Annex) | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING |  | 2788608.14 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3058 | ELECTRIFICATION 2019 | Region II | City of Ilagan | 500731 | Sindun Bayabo ES | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1506073.01 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3059 | ELECTRIFICATION 2019 | Region II | City of Ilagan | 300602 | Sta. Isabel National High School | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1640651.63 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3060 | ELECTRIFICATION 2019 | Region II | Isabela | 500072 | Villaluz Integrated School | BENITO SOLIVEN | 2 | 1 | UPGRADING | Batch 1 | 896259.08 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3061 | ELECTRIFICATION 2019 | Region II | Isabela | 500067 | Dolores Integrated School | QUIRINO | 2 | 1 | UPGRADING | Batch 1 | 1583860.26 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3062 | ELECTRIFICATION 2019 | Region II | Isabela | 500082 | Sto. Domingo Integrated School | QUIRINO | 2 | 1 | UPGRADING | Batch 1 | 2207057.35 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3063 | ELECTRIFICATION 2019 | Region II | Isabela | 306135 | Matusalem National High School | ROXAS | 2 | 1 | UPGRADING | Batch 1 | 1547472.38 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3064 | ELECTRIFICATION 2019 | Region II | Isabela | 103636 | Roxas Central School | ROXAS | 2 | 1 | UPGRADING | Batch 1 | 2006254.68 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3065 | ELECTRIFICATION 2019 | Region II | Isabela | 103643 | Roxas West Central School | ROXAS | 2 | 1 | UPGRADING | Batch 1 | 1834801.64 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3066 | ELECTRIFICATION 2019 | Region II | Isabela | 103719 | San Manuel Central School | SAN MANUEL | 2 | 1 | UPGRADING | Batch 1 | 1841706.18 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3067 | ELECTRIFICATION 2019 | Region II | Isabela | 103722 | Sandiat Elementary School | SAN MANUEL | 2 | 1 | UPGRADING | Batch 1 | 1950705.23 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3068 | ELECTRIFICATION 2019 | Region II | Isabela | 500014 | Del Pilar Integrated School | SAN MARIANO | 2 | 1 | UPGRADING | Batch 1 | 1323664.13 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3069 | ELECTRIFICATION 2019 | Region II | Isabela | 103742 | San Mariano Central School SPED Center | SAN MARIANO | 2 | 1 | UPGRADING | Batch 1 | 1284553.85 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3070 | ELECTRIFICATION 2019 | Region II | Isabela | 500095 | San Mariano II Central Integrated School | SAN MARIANO | 2 | 1 | UPGRADING | Batch 1 | 1042522.66 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3071 | ELECTRIFICATION 2019 | Region II | Isabela | 300592 | San Mariano National High School - Main | SAN MARIANO | 2 | 1 | UPGRADING | Batch 1 | 1752890.9 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3072 | ELECTRIFICATION 2019 | Region II | Isabela | 500069 | Sta. Filomena Integrated School | SAN MARIANO | 2 | 1 | UPGRADING | Batch 1 | 1272500.97 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3073 | ELECTRIFICATION 2019 | Region II | Isabela | 103005 | Alicia Central School | ALICIA | 3 | 1 | UPGRADING | Batch 1 | 1973948.91 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3074 | ELECTRIFICATION 2019 | Region II | Isabela | 102995 | Alicia East Central School | ALICIA | 3 | 1 | UPGRADING | Batch 1 | 1442381.83 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3075 | ELECTRIFICATION 2019 | Region II | Isabela | 102988 | Alicia North Central School | ALICIA | 3 | 1 | UPGRADING | Batch 1 | 1225691.53 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3076 | ELECTRIFICATION 2019 | Region II | Isabela | 103006 | Alicia West Central School | ALICIA | 3 | 1 | UPGRADING | Batch 1 | 1538337.93 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3077 | ELECTRIFICATION 2019 | Region II | Isabela | 103052 | Angadanan Central School | ANGADANAN | 3 | 1 | UPGRADING | Batch 1 | 1640341.52 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3078 | ELECTRIFICATION 2019 | Region II | Isabela | 103022 | Angadanan East Central School | ANGADANAN | 3 | 1 | UPGRADING | Batch 1 | 1602022.89 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3079 | ELECTRIFICATION 2019 | Region II | Isabela | 500017 | Fugaru Integrated School | ANGADANAN | 3 | 1 | UPGRADING | Batch 1 | 1428785.71 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3080 | ELECTRIFICATION 2019 | Region II | Isabela | 500023 | Sto. Niño Integrated School | ANGADANAN | 3 | 1 | UPGRADING | Batch 1 | 1747331.22 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3081 | ELECTRIFICATION 2019 | Region II | Isabela | 103165 | Cabatuan East Central School | CABATUAN | 3 | 1 | UPGRADING | Batch 1 | 1808491.84 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3082 | ELECTRIFICATION 2019 | Region II | Isabela | 103166 | Cabatuan West Central School | CABATUAN | 3 | 1 | UPGRADING | Batch 1 | 1743926.56 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3083 | ELECTRIFICATION 2019 | Region II | Isabela | 103487 | Luna Central School | LUNA | 3 | 1 | UPGRADING | Batch 1 | 1909573.04 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3084 | ELECTRIFICATION 2019 | Region II | Isabela | 306150 | Luna General Comprehensive High School | LUNA | 3 | 1 | UPGRADING | Batch 1 | 1491548.28 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3085 | ELECTRIFICATION 2019 | Region II | Isabela | 103690 | San Guillermo Central School | SAN GUILLERMO | 3 | 1 | UPGRADING | Batch 1 | 1705607.93 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3086 | ELECTRIFICATION 2019 | Region II | Isabela | 103788 | San Mateo East Central School | SAN MATEO | 3 | 1 | UPGRADING | Batch 1 | 1183725.21 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3087 | ELECTRIFICATION 2019 | Region II | Isabela | 103779 | San Mateo North Central School | SAN MATEO | 3 | 1 | UPGRADING | Batch 1 | 1358662.22 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3088 | ELECTRIFICATION 2019 | Region II | Isabela | 103789 | San Mateo West Central School | SAN MATEO | 3 | 1 | UPGRADING | Batch 1 | 1550060.96 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3089 | ELECTRIFICATION 2019 | Region II | Isabela | 103258 | Cordon North Central School | CORDON | 4 | 1 | UPGRADING | Batch 1 | 1592559.18 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3090 | ELECTRIFICATION 2019 | Region II | Isabela | 103247 | Cordon South Central School-Main | CORDON | 4 | 1 | UPGRADING | Batch 1 | 1674242.6 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3091 | ELECTRIFICATION 2019 | Region II | Isabela | 500073 | Wigan Integrated School | CORDON | 4 | 1 | UPGRADING | Batch 1 | 1290802.76 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3092 | ELECTRIFICATION 2019 | Region II | Isabela | 300533 | Dona Magdalena H. Gaffud HIgh School | ECHAGUE | 4 | 1 | UPGRADING | Batch 1 | 1649125.78 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3093 | ELECTRIFICATION 2019 | Region II | Isabela | 103290 | Echague East Central School | ECHAGUE | 4 | 1 | UPGRADING | Batch 1 | 1646429.09 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3094 | ELECTRIFICATION 2019 | Region II | Isabela | 103311 | Echague South Central School | ECHAGUE | 4 | 1 | UPGRADING | Batch 1 | 1231232.35 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3095 | ELECTRIFICATION 2019 | Region II | Isabela | 300541 | Imelda R. Marcos High School | ECHAGUE | 4 | 1 | UPGRADING | Batch 1 | 1135675.58 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3096 | ELECTRIFICATION 2019 | Region II | Isabela | 300498 | Addalam Region HS - Main | JONES | 4 | 1 | UPGRADING | Batch 1 | 1598089.72 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3097 | ELECTRIFICATION 2019 | Region II | Isabela | 300524 | Dibuluan National High School | JONES | 4 | 1 | UPGRADING | Batch 1 | 1551051.62 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3098 | ELECTRIFICATION 2019 | Region II | Isabela | 103469 | Jones West Central School Campus 1 | JONES | 4 | 1 | UPGRADING | Batch 1 | 1613921.68 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3099 | ELECTRIFICATION 2019 | Region II | Isabela | 300600 | Sgt. Prospero Bello HS - Main | JONES | 4 | 1 | UPGRADING | Batch 1 | 1695215.78 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3100 | ELECTRIFICATION 2019 | Region II | Isabela | 300582 | San Agustin National High School | SAN AGUSTIN | 4 | 1 | UPGRADING | Batch 1 | 1695215.78 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3101 | ELECTRIFICATION 2019 | Region II | Isabela | 500091 | Cebu Integrated Sschool | SAN ISIDRO | 4 | 1 | UPGRADING | Batch 1 | 1592559.18 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3102 | ELECTRIFICATION 2019 | Region II | Isabela | 306123 | Manuel L. Quezon National High School | SAN ISIDRO | 4 | 1 | UPGRADING | Batch 1 | 1283365.73 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3103 | ELECTRIFICATION 2019 | Region II | Nueva Vizcaya | 300618 | Aritao National High School | ARITAO | 0 | 1 | UPGRADING | Batch 1 | 4500080.72 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3104 | ELECTRIFICATION 2019 | Region II | Nueva Vizcaya | 300637 | Munguia NHS | DUPAX DEL NORTE | 0 | 1 | UPGRADING | Batch 1 | 2443832.95 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3105 | ELECTRIFICATION 2019 | Region II | Nueva Vizcaya | 300631 | Kasibu National Agricultural School | KASIBU | 0 | 1 | UPGRADING | Batch 1 | 4982144.12 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3106 | ELECTRIFICATION 2019 | Region II | Nueva Vizcaya | 300649 | Santa Fe National High School | SANTA FE | 0 | 1 | UPGRADING | Batch 1 | 5149791.12 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3107 | ELECTRIFICATION 2019 | Region II | Nueva Vizcaya | 300646 | Solano High School | SOLANO | 0 | 1 | UPGRADING | Batch 3 | 12204160.22 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3108 | ELECTRIFICATION 2019 | Region II | Quirino | 104238 | Aglipay East CS (Progreso ES) | AGLIPAY | 0 | 1 | UPGRADING |  | 929420.6 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3109 | ELECTRIFICATION 2019 | Region II | Quirino | 104248 | Victoria Elementary School Annex | AGLIPAY | 0 | 1 | UPGRADING |  | 555784.13 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3110 | ELECTRIFICATION 2019 | Region II | Quirino | 104247 | Victoria ES | AGLIPAY | 0 | 1 | UPGRADING |  | 637574.37 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3111 | ELECTRIFICATION 2019 | Region II | Quirino | 104254 | Burgos Elementary School | CABARROGUIS (Capital) | 0 | 1 | UPGRADING |  | 757282.52 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3112 | ELECTRIFICATION 2019 | Region II | Quirino | 104264 | Mangandingay ES | CABARROGUIS (Capital) | 0 | 1 | UPGRADING |  | 961848.18 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3113 | ELECTRIFICATION 2019 | Region II | Quirino | 104280 | Diffun CS - Integrated SPED Center | DIFFUN | 0 | 1 | UPGRADING |  | 1038369.32 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3114 | ELECTRIFICATION 2019 | Region II | Quirino | 104283 | Isidro Paredes ES | DIFFUN | 0 | 1 | UPGRADING |  | 598065.74 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3115 | ELECTRIFICATION 2019 | Region II | Quirino | 104306 | Liwayway ES | DIFFUN | 0 | 1 | UPGRADING |  | 651551.48 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3116 | ELECTRIFICATION 2019 | Region II | Quirino | 300659 | Dipintin HS | MADDELA | 0 | 1 | UPGRADING |  | 724435.1 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3117 | ELECTRIFICATION 2019 | Region II | Quirino | 104330 | Maddela North CS | MADDELA | 0 | 1 | UPGRADING |  | 1059099.99 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3118 | ELECTRIFICATION 2019 | Region II | Quirino | 104323 | Maddela South CS | MADDELA | 0 | 1 | UPGRADING |  | 928669.98 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3119 | ELECTRIFICATION 2019 | Region II | Quirino | 104334 | San Bernabe ES | MADDELA | 0 | 1 | UPGRADING |  | 699298.47 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3120 | ELECTRIFICATION 2019 | Region II | Quirino | 104363 | Nagtipunan CS | NAGTIPUNAN | 0 | 1 | UPGRADING |  | 1384996.29 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3121 | ELECTRIFICATION 2019 | Region II | Quirino | 104375 | La Paz ES | SAGUDAY | 0 | 1 | UPGRADING |  | 744922.1 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3122 | ELECTRIFICATION 2019 | Region II | Quirino | 104377 | SAGUDAY CENTRAL SCHOOL | SAGUDAY | 0 | 1 | UPGRADING |  | 926247.23 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3123 | ELECTRIFICATION 2019 | Region II | Quirino | 104378 | Salvacion ES | SAGUDAY | 0 | 1 | UPGRADING |  | 564434.82 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3124 | ELECTRIFICATION 2019 | Region II | Santiago City | 103812 | Batal ES | CITY OF SANTIAGO | 4 | 1 | UPGRADING |  | 638253.49 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
3125 | ELECTRIFICATION 2019 | Region II | Santiago City | 325204 | Divisoria High School - Naggasican Extension | CITY OF SANTIAGO | 4 | 1 | UPGRADING |  | 408217.95 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
3126 | ELECTRIFICATION 2019 | Region II | Santiago City | 103814 | Luna ES | CITY OF SANTIAGO | 4 | 1 | UPGRADING |  | 300024.21 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
3127 | ELECTRIFICATION 2019 | Region II | Santiago City | 103815 | Mabini ES | CITY OF SANTIAGO | 4 | 1 | UPGRADING |  | 499829.4 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
3128 | ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104393 | Annafunan ES | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 1 | 523307.76 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3129 | ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104402 | Cataggamman ES | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 3 | 1306164.63 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3130 | ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104391 | Tagga-Dadda ES | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 1 | 396711.95 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3131 | ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104392 | Tuguegarao East CS | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 1 | 925595.11 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3132 | ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104400 | Tuguegarao North CS | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 1 | 1249377.84 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3133 | ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104382 | Tuguegarao Northeast CS | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 1 | 902002.59 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3134 | ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104406 | Tuguegarao West CS | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 3 | 1332603.4 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
3135 | ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104407 | Ugac Elementary School | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 1 | 403936.85 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
4430 | ELECTRIFICATION 2020 | Region II | Batanes | 102311 | Basco Central School | BASCO (Capital) | 0 | 1 | UPGRADING |  | 4914160.07 |  | TERMINATED | 0.35 |  |  | ELEC-2020-RII-BATANES-006 | [9 empty] | UPGRADING
4431 | ELECTRIFICATION 2020 | Region II | Batanes | 300411 | Batanes Nat"l Science High School | BASCO (Capital) | 0 | 1 | UPGRADING |  | 1660529.16 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-BATANES-007 | [7 empty] | Implementation not yet started due to the imposition of ecq and to the typhoon kiko and contractor is still in mainland and send letter in the division for the catch up plan in implementing the prjects |  | UPGRADING
4432 | ELECTRIFICATION 2020 | Region II | Batanes | 102313 | Diptan Elementary School | BASCO (Capital) | 0 | 1 | UPGRADING |  | 2693654.15 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-BATANES-005 | [7 empty] | Implementation not yet started due to the imposition of ecq and to the typhoon kiko and contractor is still in mainland and send letter in the division for the catch up plan in implementing the prjects |  | UPGRADING
4433 | ELECTRIFICATION 2020 | Region II | Batanes | 102328 | Sabtang Central School | SABTANG | 0 | 1 | UPGRADING |  | 1633822.52 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-BATANES-004 | [7 empty] | Implementation not yet started due to the imposition of ecq and to the typhoon kiko and contractor is still in mainland and send letter in the division for the catch up plan in implementing the prjects |  | UPGRADING
4434 | ELECTRIFICATION 2020 | Region II | Cagayan | 300437 | Bukig National Agricultural and Technical School | APARRI | 1 | 1 | UPGRADING |  | 723016.85 |  | TERMINATED | 0 |  |  | ELEC-2020-RII-CAGAYAN-001 | [7 empty] | Contract Termination is on Process |  | UPGRADING
4435 | ELECTRIFICATION 2020 | Region II | Cagayan | 300478 | Mauanan NHS | RIZAL | 2 | 1 | UPGRADING |  | 615683.6 |  | TERMINATED | 0 |  |  | ELEC-2020-RII-CAGAYAN-007 | [7 empty] | Contract Termination is on Process |  | UPGRADING
4436 | ELECTRIFICATION 2020 | Region II | Cagayan | 300486 | Sanchez Mira SAT | SANCHEZ-MIRA | 2 | 1 | UPGRADING |  | 1019916.77 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-CAGAYAN-002 | [9 empty] | UPGRADING
4437 | ELECTRIFICATION 2020 | Region II | Cagayan | 300491 | Sto. Nino NHS | STO. NINO | 2 | 1 | UPGRADING |  | 689117.88 |  | TERMINATED | 0 |  |  | ELEC-2020-RII-CAGAYAN-009 | [7 empty] | Contract Termination is on Process |  | UPGRADING
4438 | ELECTRIFICATION 2020 | Region II | Cagayan | 306424 | Gadu NHS- Nangalisan Extension | SOLANA | 3 | 1 | UPGRADING |  | 1222194.87 |  | TERMINATED | 0 |  |  | ELEC-2020-RII-CAGAYAN-003 | [7 empty] | Contract Termination is on Process |  | UPGRADING
4439 | ELECTRIFICATION 2020 | Region II | Cagayan | 300466 | Itawes Nat'l. Agr'l. & Tech'l. School | TUAO | 3 | 1 | UPGRADING |  | 807603.58 |  | TERMINATED | 0 |  |  | ELEC-2020-RII-CAGAYAN-010 | [7 empty] | Contract Termination is on Process |  | UPGRADING
4440 | ELECTRIFICATION 2020 | Region II | Cauayan City | 103211 | Cauayan North CS | CITY OF CAUAYAN | 3 | 1 | UPGRADING |  | 1080843.25 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-CAUAYAN CITY-002 | [9 empty] | UPGRADING
4441 | ELECTRIFICATION 2020 | Region II | Cauayan City | 103228 | Cauayan South CS | CITY OF CAUAYAN | 3 | 1 | UPGRADING |  | 1238184.17 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-CAUAYAN CITY-001 | [9 empty] | UPGRADING
4442 | ELECTRIFICATION 2020 | Region II | Cauayan City | 103233 | Cauayan West CS | CITY OF CAUAYAN | 3 | 1 | UPGRADING |  | 1204885.19 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-CAUAYAN CITY-003 | [9 empty] | UPGRADING
4443 | ELECTRIFICATION 2020 | Region II | City of Ilagan | 103354 | Alinguigan 1st Elementary School | City of Ilagan | 1 | 1 | UPGRADING |  | 698964.52 |  | COMPLETED | 1 |  |  | Elec2020-R2-City of Ilagan-002 | [9 empty] | UPGRADING
4444 | ELECTRIFICATION 2020 | Region II | City of Ilagan | 103355 | Alinguigan 2nd ES | City of Ilagan | 1 | 1 | UPGRADING |  | 698964.52 |  | COMPLETED | 1 | Jan. 2021 |  | Elec2020-R2-City of Ilagan-003 |  | Nov. 12, 2019 | Nov. 19, 2019 | Dec. 09, 2019 | Jan. 07, 2020 | Sept. 21, 2020 | SMT CONSTRUCTION |  |  | UPGRADING
4445 | ELECTRIFICATION 2020 | Region II | City of Ilagan | 103361 | Capellan ES | City of Ilagan | 1 | 1 | UPGRADING |  | 727197.59 |  | COMPLETED | 1 | Jan. 2021 |  | Elec2020-R2-City of Ilagan-005 |  | Nov. 12, 2019 | Nov. 19, 2019 | Dec. 09, 2019 | Jan. 07, 2020 | Sept. 21, 2020 | SMT CONSTRUCTION |  |  | UPGRADING
4446 | ELECTRIFICATION 2020 | Region II | City of Ilagan | 103382 | Tangcul-San Isidro ES | City of Ilagan | 1 | 1 | UPGRADING |  | 677944.35 |  | COMPLETED | 1 | Jan. 2021 |  | Elec2020-R2-City of Ilagan-001 |  | Nov. 12, 2019 | Nov. 19, 2019 | Dec. 09, 2019 | Jan. 07, 2020 | Sept. 21, 2020 | SMT CONSTRUCTION |  |  | UPGRADING
4447 | ELECTRIFICATION 2020 | Region II | Isabela | 300521 | Alfreda Albano National High School - Magassi, Cabagan | CABANGAN | 1 | 1 | UPGRADING |  | 828610.6 |  | COMPLETED | 1 |  |  | ELEC2020-RII-ISABELA-014 | [9 empty] | UPGRADING
4448 | ELECTRIFICATION 2020 | Region II | Isabela | 300520 | Delfin Albano High School-Main | CABANGAN | 1 | 1 | UPGRADING |  | 976761.31 |  | COMPLETED | 1 |  |  | ELEC2020-RII-ISABELA-015 | [9 empty] | UPGRADING
4449 | ELECTRIFICATION 2020 | Region II | Isabela | 300597 | San Pablo National High School | SAN PABLO | 1 | 1 | UPGRADING |  | 262626.38 |  | COMPLETED | 1 |  |  | ELEC2020-RII-ISABELA-013 | [9 empty] | UPGRADING
4450 | ELECTRIFICATION 2020 | Region II | Isabela | 306132 | Simanu National High School | SAN PABLO | 1 | 1 | UPGRADING |  | 961515.07 |  | COMPLETED | 1 |  |  | ELEC2020-RII-ISABELA-006 | [9 empty] | UPGRADING
4451 | ELECTRIFICATION 2020 | Region II | Isabela | 300551 | Lanna National High School | TUMAUINI | 1 | 1 | UPGRADING |  | 503768.82 |  | COMPLETED | 1 |  |  | ELEC2020-RII-ISABELA-012 | [9 empty] | UPGRADING
4452 | ELECTRIFICATION 2020 | Region II | Isabela | 300609 | Tumauini National High School | TUMAUINI | 1 | 1 | UPGRADING |  | 593838.49 |  | COMPLETED | 1 |  |  | ELEC2020-RII-ISABELA-017 | [9 empty] | UPGRADING
4453 | ELECTRIFICATION 2020 | Region II | Isabela | 500073 | Wigan Integrated School | CORDON | 4 | 1 | UPGRADING |  | 921481.88 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-ISABELA-003 | [9 empty] | UPGRADING
4454 | ELECTRIFICATION 2020 | Region II | Isabela | 103331 | Echague West Central School | ECHAGUE | 6 | 1 | UPGRADING |  | 937346.67 |  | COMPLETED | 1 |  |  | ELEC2020-RII-ISABELA-008 | [9 empty] | UPGRADING
4455 | ELECTRIFICATION 2020 | Region II | Isabela | 103706 | San Isidro East Central School | SAN ISIDRO | 6 | 1 | UPGRADING |  | 937346.67 |  | COMPLETED | 1 |  |  | ELEC2020-RII-ISABELA-005 | [9 empty] | UPGRADING
4456 | ELECTRIFICATION 2020 | Region II | Isabela | 103707 | San Isidro West Central School | SAN ISIDRO | 6 | 1 | UPGRADING |  | 937346.67 |  | COMPLETED | 1 |  |  | ELEC2020-RII-ISABELA-004 | [9 empty] | UPGRADING
4457 | ELECTRIFICATION 2020 | Region II | Nueva Vizcaya | 300619 | Bagabag NHS | BAGBAG | 0 | 1 | UPGRADING |  | 5019524.37 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-NUEVA VIZCAYA-002 | [9 empty] | UPGRADING
4458 | ELECTRIFICATION 2020 | Region II | Nueva Vizcaya | 300627 | Diadi NHS | DIADI | 0 | 1 | UPGRADING |  | 12887267.59 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-NUEVA VIZCAYA-003 | [9 empty] | UPGRADING
4459 | ELECTRIFICATION 2020 | Region II | Nueva Vizcaya | 300635 | LAMO NATIONAL HIGH SCHOOL | DUPAX DEL NORTE | 0 | 1 | UPGRADING |  | 5504683.46 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-NUEVA VIZCAYA-001 | [9 empty] | UPGRADING
4460 | ELECTRIFICATION 2020 | Region II | Quirino | 104249 | Villa Pagaduan Elementary School | Aglipay | 0 | 1 | UPGRADING |  | 535526.76 |  | COMPLETED | 1 |  |  | ELEC2020-RII-QUIRINO-004 | [9 empty] | UPGRADING
4461 | ELECTRIFICATION 2020 | Region II | Quirino | 104266 | San Marcos ES | Cabarroguis | 0 | 1 | UPGRADING |  | 680903.14 |  | COMPLETED | 1 |  |  | ELEC2020-RII-QUIRINO-001 | [9 empty] | UPGRADING
4462 | ELECTRIFICATION 2020 | Region II | Quirino | 104281 | Gulac ES | Diffun | 0 | 1 | UPGRADING |  | 556535.75 |  | COMPLETED | 1 |  |  | ELEC2020-RII-QUIRINO-007 | [9 empty] | UPGRADING
4463 | ELECTRIFICATION 2020 | Region II | Santiago City | 103837 | Calaocan ES | Santiago City | 1 | 1 | UPGRADING |  | 877681.63 |  | COMPLETED | 1 |  |  | Elec 2020-R II-Santiago City-001 | [9 empty] | UPGRADING
4464 | ELECTRIFICATION 2020 | Region II | Santiago City | 306124 | Patul National High School | Santiago City | 1 | 1 | UPGRADING |  | 810365.58 |  | COMPLETED | 1 |  |  | Elec 2020-R II-Santiago City-004 | [9 empty] | UPGRADING
4465 | ELECTRIFICATION 2020 | Region II | Santiago City | 325202 | Sagana National High School | Santiago City | 1 | 1 | UPGRADING |  | 864847.86 |  | COMPLETED | 1 |  |  | Elec 2020-R II-Santiago City-005 | [9 empty] | UPGRADING
4466 | ELECTRIFICATION 2020 | Region II | Santiago City | 103841 | Sta. Rosa ES | Santiago City | 1 | 1 | UPGRADING |  | 661763.68 |  | COMPLETED | 1 |  |  | Elec 2020-R II-Santiago City-008 | [9 empty] | UPGRADING
4467 | ELECTRIFICATION 2020 | Region II | Tuguegarao City | 104384 | Balzain East ES | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING |  | 438364.85 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-TUGUEGARAO CITY-001 | [9 empty] | UPGRADING
4468 | ELECTRIFICATION 2020 | Region II | Tuguegarao City | 157002 | Cataggaman Nuevo ES | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING |  | 218174.54 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-TUGUEGARAO CITY-005 | [9 empty] | UPGRADING
4469 | ELECTRIFICATION 2020 | Region II | Tuguegarao City | 104403 | Pallua ES | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING |  | 445321.08 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-TUGUEGARAO CITY-004 | [9 empty] | UPGRADING
4470 | ELECTRIFICATION 2020 | Region II | Tuguegarao City | 306402 | Tuguegarao City West High School | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING |  | 311749.84 |  | COMPLETED | 1 |  |  | ELEC-2020-RII-TUGUEGARAO CITY-006 | [9 empty] | UPGRADING
5210 | ELECTRIFICATION 2023 | Region II | Batanes | 102329 | Savidug Elementary School | SABTANG | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1030909.75 |  | COMPLETED | 1 | [12 empty] | UPGRADING
5211 | ELECTRIFICATION 2023 | Region II | Batanes | 102330 | Sumnanga Elementary School | SABTANG | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 821127.21 |  | COMPLETED | 1 | [12 empty] | UPGRADING
5212 | ELECTRIFICATION 2023 | Region II | Cagayan | 300464 | Illuru National High School | RIZAL | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1429293.86 | 1406356.97 | COMPLETED | 1 | November 3, 2023 | 1900-03-25 | ELEC 2023-RII-Cagayan o1 | INFRA 2023-046 | May 8, 2023 | May 15, 2023 | May 29, 2023 |  | June 08, 2023 | WWW. Constrution |  |  | UPGRADING
5213 | ELECTRIFICATION 2023 | Region II | Nueva Vizcaya | 137029 | Hiket Elementary School | AMBAGUIO | Lone | 1 | Provision of Solar-Powered Energy System | 1 | 2620439.1 |  | COMPLETED | 1 | January 23, 2024 | March 12, 2024 | PB06-004-SDONV-CY2023-BEFF-ELEC-LOT2-HIKET ES |  | June 22, 2023 |  | July 14, 2023 | August 18, 2023 | September 25, 2023 | Mighty Construction & Supply |  |  | SOLAR
5214 | ELECTRIFICATION 2023 | Region II | Nueva Vizcaya | 137027 | Pihipi Elementary School | AMBAGUIO | Lone | 1 | Provision of Solar-Powered Energy System | 1 | 2620965.54 |  | COMPLETED | 1 | January 16, 2024 | March 12, 2024 | PB06-004-SDONV-CY2023-BEFF-ELEC-LOT1-PIHIPI ES |  | June 22, 2023 |  | July 14, 2023 | August 18, 2023 | September 25, 2023 | Mighty Construction & Supply |  |  | SOLAR
5401 | ELECTRIFICATION 2024 | Region II | Batanes | 102311 | Basco Central School | BASCO (Capital) | Lone | 1 | Energization of Electrical System (Underground System) | 1 | 1943508.93 |  | not yet started | 0 | [12 empty] | ENERGIZATION
5402 | ELECTRIFICATION 2024 | Region II | Cagayan | 300488 | Sta. Ana Fishery National High School | SANTA ANA | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3077073.36 | 2336832.19 | COMPLETED | 1 | SEPTEMBER 25, 2024 |  | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | INFRA 2023-124-LOT 1 | nov 13, 2023 | november 20, 2024 | december 4, 2023 | MAY 13, 20224 | MAY 29, 2024 | CONSTUIRE CONSTRUCTION |  |  | ENERGIZATION
5403 | ELECTRIFICATION 2024 | Region II | Cagayan | 102331 | Abulug Central Elementary School | ABULUG | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1429293.86 | 1115481.12 | COMPLETED | 1 | SEPTEMBER 25, 2024 |  | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | INFRA 2023-124-LOT 1 | nov 13, 2023 | november 20, 2024 | december 4, 2023 | MAY 13, 20224 | MAY 29, 2024 | CONSTUIRE CONSTRUCTION |  |  | ENERGIZATION
5404 | ELECTRIFICATION 2024 | Region II | Cagayan | 300456 | Don Severino Pagalilauan National High School | PEÑABLANCA | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 689117.88 | 688117.88 | ONGOING | 0.95 |  |  | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | INFRA 2024-075 | JULY 9, 2024 | JULY 15, 2024 | JULY 15, 2024 | JULY 16, 2024 |  | GCPK Construction & Supply | for final inspection |  | ENERGIZATION
5405 | ELECTRIFICATION 2024 | Region II | Cauayan City | 300516 | Cauayan City NHS | CITY OF CAUAYAN | 6th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3077073.36 |  | ONGOING | 0.3 |  |  | UPGRADING OF ELECTRICAL SYSTEM (OVERHEAD SYSTEM) OF CAUAYAN CITY NATIONAL HIGH SCHOOL | CW-003 S. 2025 | 2024-06-29 | 2024-07-08 | 2024-07-22 | 2024-08-06 |  |  | already downloaded subaro |  | ENERGIZATION
5406 | ELECTRIFICATION 2024 | Region II | City of Ilagan | 103384 | Aggassian Elementary School | ILAGAN CITY (CAPITAL) | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3077073.36 | 3071337.63 | Completed | 1 | 2024-10-03 |  | 10398574 | INF-2024-01 | 2023-12-04 | 2023-12-13 | 2023-12-27 | 2024-12-29 | 2024-06-24 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  |  | ENERGIZATION
5407 | ELECTRIFICATION 2024 | Region II | Isabela | 501434 | CUBAG INTEGRATED SCHOOL | CABAGAN | 1st | 1 | Upgrading Electrical System On Grid Schools | 1 | 1670752.61 | 1649364.22 | Completed | 1 | 2024-08-20 |  |  | 2024-0505 | November 11,2023 | November 20,2023 | 2023-12-05 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  |  | UPGRADING
5408 | ELECTRIFICATION 2024 | Region II | Isabela | 103536 | BISAG ELEMENTARY SCHOOL | PALANAN | 2nd | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 2338294.94 | 2335479.45 | Completed | 1 | 2024-08-20 |  |  | 2024-0505 | November 11,2023 | November 20,2023 | 2023-12-05 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  |  | SOLAR
5409 | ELECTRIFICATION 2024 | Region II | Isabela | 306115 | LFG DIAMANTINA NATIONAL HIGH SCHOOL | CABATUAN | 3rd | 1 | Upgrading Electrical System On Grid Schools | 1 | 1563047.81 | 1535336.98 | Completed | 1 | 2024-08-20 |  |  | 2024-0505 | November 11,2023 | November 20,2023 | 2023-12-05 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  |  | UPGRADING
5410 | ELECTRIFICATION 2024 | Region II | Isabela | 501316 | Taliktik Integrated School | CORDON | 4th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2383413.13 | 2368626.76 | Completed | 1 | 2024-08-20 |  |  | 2024-0505 | November 11,2023 | November 20,2023 | 2023-12-05 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  |  | ENERGIZATION
5411 | ELECTRIFICATION 2024 | Region II | Isabela | 500084 | MACANIAO INTEGRATED SCHOOL | ANGADANAN | 5th | 1 | Upgrading Electrical System On Grid Schools | 1 | 1273865.41 | 1253721.61 | Completed | 1 | 2024-08-20 |  |  | 2024-0505 | November 11,2023 | November 20,2023 | 2023-12-05 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  |  | UPGRADING
5412 | ELECTRIFICATION 2024 | Region II | Isabela | 500022 | RIZAL INTEGRATED SCHOOL | SAN GUILLERMO | 6th | 1 | Upgrading Electrical System On Grid Schools | 1 | 1690299.17 | 1679845.08 | Completed | 1 | 2024-08-20 |  |  | 2024-0505 | November 11,2023 | November 20,2023 | 2023-12-05 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  |  | UPGRADING
5413 | ELECTRIFICATION 2024 | Region II | Nueva Vizcaya | 104205 | Mandunot ES | ALFONSO CASTANEDA | Lone | 1 | Provision of Solar-Powered Energy System to Schools Off-Grid | 1 | 4053012.33 | 4048810.29 | COMPLETED | 1 | November 10, 2024 |  | PB03-002-SDONV-CY2024EP |  | March 19, 2024 | March 18, 2024 | April 15, 2024 | April 26, 2024 | June 13, 2024 | Mighty Construction | - |  | SOLAR
5414 | ELECTRIFICATION 2024 | Region II | Quirino | 300655 | Burgos NHS | CABARROGUIS (Capital) | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3077073.36 | 2547939.16 | COMPLETED | 1 | 2024-08-06 |  | ELEC-2024-REGION II - QUIRINO - 002 | 09-02-16-2024 | 2024-02-16 | 2024-02-23 | 2024-03-06 | 2024-03-15 | 2024-06-07 | GCPK Construction & Supply | with Time Extension / awaiting for the installation of Transformer from the Local Cooperative |  | ENERGIZATION
5415 | ELECTRIFICATION 2024 | Region II | Santiago City | 103835 | Baluarte ES | CITY OF SANTIAGO | 4th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3077073.36 |  | not yet started | 0 | [10 empty] | alredy submitted RTA to CO; Awaiting downloading of subaro |  | ENERGIZATION
5416 | ELECTRIFICATION 2024 | Region II | Tuguegarao City | 300668 | Cagayan National High School - Junior HS | TUGUEGARAO CITY(Capital) | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3077073.36 |  | Under Procurement | 0 | [10 empty] | no subaro yet; for request of realignment |  | ENERGIZATION

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%