## Sheet1
INDEX (DO NOT MODIFY) | PROGRAM-YEAR | CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | BATCH | TOTAL PROJECT ALLOCATION | TOTAL PROJECT COST | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | TARGET COMPLETION DATE | ACTUAL DATE OF COMPLETION | PROJECT ID | CONTRACT ID | ISSUANCE OF INVITATION TO BID | PRE-SUBMISSION CONFERENCE | BID OPENING | ISSUANCE OF RESOLUTION TO AWARD | ISSUANCE OF NOTICE TO PROCEED | NAME OF CONTRACTOR | OTHER REMARKS | Status as of July 11, 2025
1785 | NC 2014 | SHS (2014) | Region II | Batanes | 300413 | Batanes Gen. Comp. HS | UYUGAN | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-10-13 |  | 020114S00003 | 15BA0012-1 | 2015-07-28 | 2015-08-09 | 2015-09-07 | 2015-09-12 | 2015-10-20 | E. M. PAULE CONSTRUCTION & TRADING
1786 | NC 2014 | SHS (2014) | Region II | Batanes | 300414 | Itbayat National Agricultural HS | ITBAYAT | 0 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | 2016-10-13 |  | 020114S00007 | 15BA0012-5 | 2015-07-28 | 2015-08-09 | 2015-09-07 | 2015-09-12 | 2015-10-20 | E. M. PAULE CONSTRUCTION & TRADING
1787 | NC 2014 | SHS (2014) | Region II | Batanes | 305901 | Itbud Integrated School | UYUGAN | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-10-13 |  | 020114S00008 | 15BA0012-2 | 2015-07-28 | 2015-08-09 | 2015-09-07 | 2015-09-12 | 2015-10-20 | E. M. PAULE CONSTRUCTION & TRADING
1788 | NC 2014 | SHS (2014) | Region II | Batanes | 300415 | Ivana NHS | IVANA | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-10-13 |  | 020114S00009 | 15BA0012-4 | 2015-07-28 | 2015-08-09 | 2015-09-07 | 2015-09-12 | 2015-10-20 | E. M. PAULE CONSTRUCTION & TRADING
1789 | NC 2014 | SHS (2014) | Region II | Batanes | 300416 | Mahatao NHS | MAHATAO | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 020114S00005 | 15BA0023-2 | 2015-07-28 | 2015-08-09 | 2015-09-07 | 2015-09-12 | 2015-10-14
1790 | NC 2014 | K10 (2014) | Region II | Batanes | 305902 | Raele Integrated School | ITBAYAT | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2120417.57 |  |  | COMPLETED | 1
1791 | NC 2014 | SHS (2014) | Region II | Batanes | 305902 | Raele Integrated School | ITBAYAT | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
1792 | NC 2014 | SHS (2014) | Region II | Batanes | 300417 | Sabtang National School of Fisheries | SABTANG | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-10-13 |  | 020114S00004 | 15BA0012-3 | 2015-07-28 | 2015-08-09 | 2015-09-07 | 2015-09-12 | 2015-10-20 | E. M. PAULE CONSTRUCTION & TRADING
1793 | NC 2014 | K10 (2014) | Region II | Cagayan | 102643 | Abra Elementary | GATTARAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-09-29 | 2014-11-15 | 020214S00055 | 14BB0047 | 2014-06-17 | 2014-06-20 | 2014-07-15 | 2014-07-22 | 2014-07-25 | D.J.D. CONSTRUCTION
1794 | NC 2014 | SHS (2014) | Region II | Cagayan | 300420 | Afusing NHS | ALCALA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 020214S00135 | 15BB0084 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | CAVAT CAPITOL MERCHANDISING & CONSTRUCTION
1795 | NC 2014 | K10 (2014) | Region II | Cagayan | 102476 | Agaman Proper ES | BAGGAO | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-07 | 2015-01-31 | 020214S00041 | 14BB0040 | 2014-08-14 | 2014-08-18 | 2014-08-28 | 2014-09-30 | 2014-10-02 | D.J.D. CONSTRUCTION
1796 | NC 2014 | K10 (2014) | Region II | Cagayan | 102477 | Agaman Sur ES | BAGGAO | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2095417.57 |  |  | COMPLETED | 1 | 2014-12-07 | 2015-01-31 | 020214S00042 | 14BB0046 | 2014-08-14 | 2014-08-18 | 2014-08-28 | 2014-09-30 | 2014-10-02 | D.J.D. CONSTRUCTION
1797 | NC 2014 | SHS (2014) | Region II | Cagayan | 300421 | Alcala Rural School | ALCALA | 1 | 1 | 4 | 1STY4CL | 2014 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1 | 2015-11-26 | 2015-12-31 | 020214S00127 | 15BB0054 | 2015-07-16 | 2015-07-06 | 2015-07-16 | 2015-07-21 | 2015-07-23 | JIRK CONSTRUCTION
1798 | NC 2014 | SHS (2014) | Region II | Cagayan | 300422 | Alcala Rural School - Baybayog Annex | ALCALA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 020214S00136 | 15BB0085 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | CAVAT CAPITOL MERCHANDISING & CONSTRUCTION
1799 | NC 2014 | K10 (2014) | Region II | Cagayan | 102480 | Annayatan ES | BAGGAO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-07 | 2015-01-31 | 020214S00043 | 14BB0053 | 2014-08-14 | 2014-08-18 | 2014-08-28 | 2014-09-30 | 2014-10-02 | D.J.D. CONSTRUCTION
1800 | NC 2014 | SHS (2014) | Region II | Cagayan | 300471 | Aparri East National High School | APARRI | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 020214S00134 | 15BB0069 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | PRC CONSTRUCTION
1801 | NC 2014 | SHS (2014) | Region II | Cagayan | 300428 | Aparri SAT | APARRI | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 020214S00133 | 15BB0068 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | JOHN 6:51 BUILDERS
1802 | NC 2014 | SHS (2014) | Region II | Cagayan | 300470 | Aparri West National High School | APARRI | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-31 |  | 020214S00132 | 15BB0097 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | PRIMITIVO P. ESLABON CONSTRUCTION & HARDWARE
1803 | NC 2014 | K10 (2014) | Region II | Cagayan | 102361 | Arana-ar ES | ALCALA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-29 | 2014-11-15 | 020214S00035 | 14BB0036 | 2014-06-17 | 2014-06-20 | 2014-07-15 | 2014-07-22 | 2014-07-25 | D.J.D. CONSTRUCTION
1804 | NC 2014 | SHS (2014) | Region II | Cagayan | 300429 | Baggao NAS | BAGGAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-20 |  | 020214S00131 | 15BB0081 | 2015-08-31 | 2015-09-01 | 2015-09-10 | 2015-09-15 | 2015-09-17 | JV: JTA BUILDERS/DJ DAYAG CONSTRUCTION
1805 | NC 2014 | SHS (2014) | Region II | Cagayan | 306002 | Baggao NAS - Sta. Margarita Annex | BAGGAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-20 |  | 020214S00130 | 15BB0083 | 2015-08-31 | 2015-09-01 | 2015-09-10 | 2015-09-15 | 2015-09-17 | JV: JTA BUILDERS/DJ DAYAG CONSTRUCTION
1806 | NC 2014 | SHS (2014) | Region II | Cagayan | 300431 | Baggao NHS | BAGGAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 020214S00129 | 15BB0082 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | CAVAT CAPITOL MERCHANDISING & CONSTRUCTION
1807 | NC 2014 | SHS (2014) | Region II | Cagayan | 306020 | Baggao NHS - Agaman Annex | BAGGAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 020214S00128 | 15BB0079 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | CAVAT CAPITOL MERCHANDISING & CONSTRUCTION
1808 | NC 2014 | K10 (2014) | Region II | Cagayan | 102647 | Batug Sur ES | GATTARAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2090417.57 |  |  | COMPLETED | 1 | 2014-09-29 | 2014-11-15 | 020214S00058 | 14BB0045 | 2014-06-17 | 2014-06-20 | 2014-07-15 | 2014-07-22 | 2014-07-25 | D.J.D. CONSTRUCTION
1809 | NC 2014 | SHS (2014) | Region II | Cagayan | 300435 | Baua HS | GONZAGA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 020214S00116 | 15BB0076 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | JIRK CONSTRUCTION
1810 | NC 2014 | K10 (2014) | Region II | Cagayan | 306423 | Baua HS- Cabiraoan Annex | GONZAGA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
1811 | NC 2014 | SHS (2014) | Region II | Cagayan | 306423 | Baua HS- Cabiraoan Annex | GONZAGA | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
1812 | NC 2014 | SHS (2014) | Region II | Cagayan | 300437 | Bukig National Agr'l. and Tech. School | APARRI | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 020214S00137 | 15BB0070 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | JOHN 6:51 BUILDERS
1813 | NC 2014 | K10 (2014) | Region II | Cagayan | 102364 | Cabuluan ES | ALCALA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-29 | 2014-11-15 | 020214S00039 | 14BB0037 | 2014-06-17 | 2014-06-20 | 2014-07-15 | 2014-07-22 | 2014-07-25 | D.J.D. CONSTRUCTION
1814 | NC 2014 | K10 (2014) | Region II | Cagayan | 306422 | Calaoagan Dackel National High School-Capissayan Annex | GATTARAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
1815 | NC 2014 | SHS (2014) | Region II | Cagayan | 306422 | Calaoagan Dackel National High School-Capissayan Annex | GATTARAN | 1 | 1 | 4 | 1STY4CL | 2014 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1
1816 | NC 2014 | SHS (2014) | Region II | Cagayan | 300440 | Calaoagan Dackel NHS | GATTARAN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 020214S00123 | 15BB0086 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | PRC CONSTRUCTION
1817 | NC 2014 | K10 (2014) | Region II | Cagayan | 102691 | Calayan ES | GONZAGA | 1 | 1 | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-21 |  | 020214S00172 | 15BB0093 | 2015-08-31 | 2015-09-01 | 2015-09-10 | 2015-09-15 | 2015-09-17 | E. GUADIZ CONSTRUCTION
1818 | NC 2014 | K10 (2014) | Region II | Cagayan | 306426 | Camalaniugan National High School- Catotoran Annex | CAMALANIUGAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-12-08 |  | 020214S00177 | 15BB0063 | 2015-07-28 | 2015-07-17 | 2015-07-28 | 2015-07-31 | 2015-08-04 | WDC CONSTRUCTION
1819 | NC 2014 | SHS (2014) | Region II | Cagayan | 300444 | Camalaniugan NHS | CAMALANIUGAN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 020214S00122 | 15BB0098 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | JOHN 6:51 BUILDERS
1820 | NC 2014 | SHS (2014) | Region II | Cagayan | 300447 | Casambalangan NHS | SANTA ANA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 020214S00121 | 15BB0078 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | JIRK CONSTRUCTION
1821 | NC 2014 | K10 (2014) | Region II | Cagayan | 102487 | Catugay ES | BAGGAO | 1 | 1 | 4 | 1STY 1CL & 1STY 3CL | 2014 K10 BATCH 1 | 3957503.55 |  |  | COMPLETED | 1 | 2014-12-07 | 2015-01-31 | 020214S00044 | 14BB0043 | 2014-08-14 | 2014-08-18 | 2014-08-28 | 2014-09-30 | 2014-10-02 | DJ DAYAG CONSTRUCTION
1822 | NC 2014 | K10 (2014) | Region II | Cagayan | 102743 | Dagupan ES | LAL-LO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-29 | 2014-11-05 | 020214S00056 | 14BB0038 | 2014-06-17 | 2014-06-20 | 2014-07-15 | 2014-07-22 | 2014-07-25 | JIRK CONSTRUCTION
1823 | NC 2014 | SHS (2014) | Region II | Cagayan | 300455 | Don Mariano Marcos NHS | GATTARAN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 020214S00120 | 15BB0087 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | JIRK CONSTRUCTION
1824 | NC 2014 | SHS (2014) | Region II | Cagayan | 300460 | Felipe Tuzon Agr'l. School | CAMALANIUGAN | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-31 |  | 020214S00119 | 15BB0095 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | WDC CONSTRUCTION
1825 | NC 2014 | SHS (2014) | Region II | Cagayan | 300462 | Gattaran NTS | GATTARAN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-20 |  | 020214S00118 | 15BB0088 | 2015-08-31 | 2015-09-01 | 2015-09-10 | 2015-09-15 | 2015-09-17 | HPL GENERAL CONSTRUCTION
1826 | NC 2014 | SHS (2014) | Region II | Cagayan | 300483 | Gonzaga National High School | GONZAGA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-04-22 |  | 020214S00117 | 15BB0074 | 2015-11-10 | 2015-11-05 | 2015-11-11 | 2015-11-13 | 2015-11-18 | MILESTONE 888 CONSTRUCTION INC.
1827 | NC 2014 | SHS (2014) | Region II | Cagayan | 300432 | Hacienda Intal NHS | BAGGAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-20 |  | 020214S00125 | 15BB0080 | 2015-08-31 | 2015-09-01 | 2015-09-10 | 2015-09-15 | 2015-09-17 | JV: JTA BUILDERS/DJ DAYAG CONSTRUCTION
1828 | NC 2014 | SHS (2014) | Region II | Cagayan | 300465 | Ipil National High School | GONZAGA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 020214S00142 | 15BB0089 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | CAVAT CAPITOL MERCHANDISING & CONSTRUCTION
1829 | NC 2014 | SHS (2014) | Region II | Cagayan | 300469 | LAL-LO NATIONAL HIGH SCHOOL | LAL-LO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 020214S00148 | 15BB0090 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | JIRK CONSTRUCTION
1830 | NC 2014 | SHS (2014) | Region II | Cagayan | 306003 | Lal-lo NHS - Cabayabasan Annex | LAL-LO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 020214S00156 | 15BB0091 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | JIRK CONSTRUCTION
1831 | NC 2014 | SHS (2014) | Region II | Cagayan | 300474 | Licerio Antiporda Sr. NHS | BUGUEY | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 020214S00155 | 15BB0071 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | CAVAT CAPITOL MERCHANDISING & CONSTRUCTION
1832 | NC 2014 | SHS (2014) | Region II | Cagayan | 306005 | Licerio Antiporda Sr. NHS - Sta. Isabel Ext. | BUGUEY | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-27 | 2015-11-04 | 020214S00154 | 15BB0049 | 2015-07-16 | 2015-07-06 | 2015-07-16 | 2015-07-21 | 2015-07-23 | AGAFER CONSTRUCTION
1833 | NC 2014 | SHS (2014) | Region II | Cagayan | 300475 | Logac National High School | LAL-LO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 020214S00153 | 15BB0092 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | JIRK CONSTRUCTION
1834 | NC 2014 | SHS (2014) | Region II | Cagayan | 306013 | Luga Nat'l High School | SANTA TERESITA | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-27 | 2015-11-24 | 020214S00152 | 15BB0051 | 2015-07-16 | 2015-07-06 | 2015-07-16 | 2015-07-21 | 2015-07-23 | PRIMITIVO P. ESLABON CONSTRUCTION & HARDWARE
1835 | NC 2014 | K10 (2014) | Region II | Cagayan | 102522 | Mabini ES | BAGGAO | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-12-31 |  | 020214S00173 | 15BB0060 | 2015-08-18 | 2015-08-07 | 2015-08-20 | 2015-08-25 | 2015-08-27 | DJ DAYAG CONSTRUCTION
1836 | NC 2014 | SHS (2014) | Region II | Cagayan | 306004 | Magapit NHS | LAL-LO | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-31 |  | 020214S00151 | 15BB0094 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | F.O.B. PASCUAL CONSTRUCTION
1837 | NC 2014 | K10 (2014) | Region II | Cagayan | 102749 | Malanao ES | LAL-LO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-29 | 2014-11-05 | 020214S00059 | 14BB0039 | 2014-06-17 | 2014-06-20 | 2014-07-15 | 2014-07-22 | 2014-07-25 | JIRK CONSTRUCTION
1838 | NC 2014 | K10 (2014) | Region II | Cagayan | 102493 | Mansarong ES | BAGGAO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1839740.174 |  |  | COMPLETED | 1 | 2015-11-22 |  | 020214S00066 | 15BB0055 | 2015-07-28 | 2015-07-21 | 2015-07-28 | 2015-08-14 | 2015-08-18 | DJ DAYAG CONSTRUCTION
1839 | NC 2014 | K10 (2014) | Region II | Cagayan | 102372 | Masin ES | ALCALA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-09-29 | 2014-11-15 | 020214S00040 | 14BB0050 | 2014-06-17 | 2014-06-20 | 2014-07-15 | 2014-07-22 | 2014-07-25 | D.J.D. CONSTRUCTION
1840 | NC 2014 | K10 (2014) | Region II | Cagayan | 155034 | Masisit PS | BAGGAO | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1
1841 | NC 2014 | K10 (2014) | Region II | Cagayan | 155034 | Masisit PS | BAGGAO | 1 |  | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1
1842 | NC 2014 | K10 (2014) | Region II | Cagayan | 102525 | Nagtupacan ES | BAGGAO | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-12-07 | 2015-01-31 | 020214S00045 | 14BB0041 | 2014-08-14 | 2014-08-18 | 2014-08-28 | 2014-09-30 | 2014-10-02 | DJ DAYAG CONSTRUCTION
1843 | NC 2014 | SHS (2014) | Region II | Cagayan | 300480 | Pattao NHS | BUGUEY | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 020214S00150 | 15BB0073 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | CAVAT CAPITOL MERCHANDISING & CONSTRUCTION
1844 | NC 2014 | SHS (2014) | Region II | Cagayan | 306012 | Pattao NHS - Maddalero Ext. | BUGUEY | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-27 | 2015-11-04 | 020214S00094 | 15BB0050 | 2015-07-16 | 2015-07-06 | 2015-07-16 | 2015-07-21 | 2015-07-23 | AGAFER CONSTRUCTION
1845 | NC 2014 | K10 (2014) | Region II | Cagayan | 102571 | Quinawegan ES | BUGUEY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2090417.57 |  |  | COMPLETED | 1 | 2014-09-29 | 2014-11-30 | 020214S00046 | 14BB0051 | 2014-06-17 | 2014-06-20 | 2014-07-15 | 2014-07-22 | 2014-07-25 | D.J.D. CONSTRUCTION
1846 | NC 2014 | SHS (2014) | Region II | Cagayan | 300482 | Rebecca NHS | GONZAGA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-20 |  | 020214S00157 | 15BB0075 | 2015-08-31 | 2015-09-01 | 2015-09-10 | 2015-09-15 | 2015-09-17 | PRC CONSTRUCTION
1847 | NC 2014 | K10 (2014) | Region II | Cagayan | 102499 | San Isidro ES | BAGGAO | 1 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 4C | 10877342.5917 |  |  | COMPLETED | 1
1848 | NC 2014 | K10 (2014) | Region II | Cagayan | 102499 | San Isidro ES | BAGGAO | 1 |  | 1 | 1STY1CL (Toilet Attached) | 2014 K10 BATCH 4C | 1248449.69 |  |  | COMPLETED | 1
1849 | NC 2014 | SHS (2014) | Region II | Cagayan | 300488 | Sta. Ana Fishery National High School | SANTA ANA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 020214S00147 | 15BB0077 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | JV: E.C.T. CONSTRUCTION/RPF CONSTRUCTION
1850 | NC 2014 | K10 (2014) | Region II | Cagayan | 102706 | Sta. Cruz ES | GONZAGA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-09-29 | 2014-11-15 | 020214S00057 | 14BB0048 | 2014-06-17 | 2014-06-20 | 2014-07-15 | 2014-07-22 | 2014-07-25 | D.J.D. CONSTRUCTION
1851 | NC 2014 | K10 (2014) | Region II | Cagayan | 102576 | Sta. Isabel ES | BUGUEY | 1 | 1 | 4 | 1STY 1CL & 1STY 3CL | 2014 K10 BATCH 1 | 3957503.55 |  |  | COMPLETED | 1 | 2014-09-29 | 2014-11-30 | 020214S00047 | 14BB0042 | 2014-06-17 | 2014-06-20 | 2014-07-15 | 2014-07-22 | 2014-07-25 | PRC CONSTRUCTION
1852 | NC 2014 | K10 (2014) | Region II | Cagayan | 102501 | Sta. Margarita East ES | BAGGAO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1834740.174 |  |  | COMPLETED | 1 | 2015-11-22 | 2015-12-15 | 020214S00069 | 15BB0056 | 2015-07-28 | 2015-07-21 | 2015-07-28 | 2015-08-14 | 2015-08-18 | DJ DAYAG CONSTRUCTION
1853 | NC 2014 | SHS (2014) | Region II | Cagayan | 300490 | Sta. Teresita NHS | SANTA TERESITA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 020214S00146 | 15BB0072 | 2015-08-20 | 2015-08-11 | 2015-08-20 | 2015-08-25 | 2015-08-27 | E. GUADIZ CONSTRUCTION
1854 | NC 2014 | K10 (2014) | Region II | Cagayan | 102579 | Villa Cielo ES | BUGUEY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-09-29 | 2014-11-15 | 020214S00050 | 14BB0052 | 2014-06-17 | 2014-06-20 | 2014-07-15 | 2014-07-22 | 2014-07-25 | D.J.D. CONSTRUCTION
1855 | NC 2014 | K10 (2014) | Region II | Cagayan | 102580 | Villa Gracia ES | BUGUEY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-29 | 2014-11-15 | 020214S00060 | 14BB0035 | 2014-06-17 | 2014-06-20 | 2014-07-15 | 2014-07-22 | 2014-07-25 | PRC CONSTRUCTION
1856 | NC 2014 | SHS (2014) | Region II | Cagayan | 306006 | Abariongan National High School | SANTO NIÑO (FAIRE) | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-11 |  | 020214S00145 | 15BC0053 | 2015-07-10 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-07-30 | E.S. PUA CONSTRUCTION
1857 | NC 2014 | SHS (2014) | Region II | Cagayan | 300418 | Abulug NRVHS | ABULUG | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-24 |  | 020214S00138 | 15BC0055 | 2015-07-31 | 2015-08-03 | 2015-08-14 | 2015-08-19 | 2015-08-28 | NORTH TECH BUILDERS AND CONSTRUCTION SUPPLY
1858 | NC 2014 | SHS (2014) | Region II | Cagayan | 300419 | Abulug SOF | ABULUG | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-09 |  | 020214S00143 | 15BC0056 | 2015-07-31 | 2015-08-03 | 2015-08-14 | 2015-08-19 | 2015-08-28 | NORTH TECH BUILDERS AND CONSTRUCTION SUPPLY
1859 | NC 2014 | SHS (2014) | Region II | Cagayan | 300424 | Allacapan VHS | ALLACAPAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-10 |  | 020214S00158 | 15BC0047 | 2015-07-10 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-07-30 | DANDEX CONSTRUCTION
1860 | NC 2014 | K10 (2014) | Region II | Cagayan | 102780 | Allasitan ES | PAMPLONA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2014 K10 BATCH 4C | 2088606.04 |  |  | COMPLETED | 1
1861 | NC 2014 | K10 (2014) | Region II | Cagayan | 102780 | Allasitan ES | PAMPLONA | 2 |  | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1
1862 | NC 2014 | SHS (2014) | Region II | Cagayan | 300434 | Ballesteros NHS | BALLESTEROS | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
1863 | NC 2014 | K10 (2014) | Region II | Cagayan | 102334 | Banguian ES | ABULUG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-12-10 | 2015-12-10 | 020214S00168 | 15BC0075 | 2015-08-06 | 2015-08-07 | 2015-08-20 | 2015-08-26 | 2015-08-28 | JOHN 6:51 BUILDERS
1864 | NC 2014 | SHS (2014) | Region II | Cagayan | 300436 | Bidduang National High School | PAMPLONA | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-11-26 |  | 020214S00140 | 15BC0058 | 2015-07-10 | 2015-07-10 | 2015-07-24 | 2015-07-29 | 2015-07-30 | OCP CONSTRUCTION
1865 | NC 2014 | K10 (2014) | Region II | Cagayan | 102832 | Bural ES | RIZAL | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-11-09 | 2015-07-25 | 020214S00022 | 14BC0048 | 2014-07-16 | 2014-07-18 | 2014-07-31 | 2014-08-07 | 2014-08-11 | E.C.T. CONSTRUCTION
1866 | NC 2014 | K10 (2014) | Region II | Cagayan | 102382 | Burot Elementary School | ALLACAPAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-23 | 2014-11-21 | 020214S00038 | 14BC0060 | 2014-06-24 | 2014-07-03 | 2014-06-18 | 2014-07-24 | 2014-07-25 | E.C.T. CONSTRUCTION
1867 | NC 2014 | SHS (2014) | Region II | Cagayan | 300438 | Cabatacan NHS | LASAM | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-10 |  | 020214S00139 | 15BC0044 | 2015-07-10 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-07-30 | E.C.T. CONSTRUCTION
1868 | NC 2014 | K10 (2014) | Region II | Cagayan | 102541 | Cabayu ES | BALLESTEROS | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-10-25 | 2015-01-28 | 020214S00012 | 14BC0071 | 2014-06-30 | 2014-07-10 | 2014-07-22 | 2014-07-25 | 2014-07-28 | D.J.D. CONSTRUCTION
1869 | NC 2014 | K10 (2014) | Region II | Cagayan | 102939 | Calapangan Elementary School | SANTO NIÑO (FAIRE) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-26 | 2014-11-15 | 020214S00021 | 14BC0050 | 2014-06-17 | 2014-06-26 | 2014-07-08 | 2014-07-11 | 2014-07-14 | CAMIA CONST. DEVELOPMENT CORPORATION (FORMERLY:CAM
1870 | NC 2014 | SHS (2014) | Region II | Cagayan | 300441 | Calayan HS | CALAYAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-25 |  | 020214S00144 | 15BC0069 | 2015-07-20 | 2015-07-16 | 2015-07-30 | 2015-08-05 | 2015-08-14 | E.C.T. CONSTRUCTION
1871 | NC 2014 | K10 (2014) | Region II | Cagayan | 306427 | Calayan HS- Dilam Extension | CALAYAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2014-12-16 | 2015-07-25 | 020214S00026 | 14BC0075 | 2014-07-29 | 2014-07-31 | 2014-08-12 | 2014-08-15 | 2014-08-18 | E.C.T. CONSTRUCTION
1872 | NC 2014 | K10 (2014) | Region II | Cagayan | 102941 | Campo Elementary School | SANTO NIÑO (FAIRE) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2015-01-21 | 020214S00023 | 14BC0051 | 2014-07-16 | 2014-07-18 | 2014-07-31 | 2014-08-07 | 2014-08-11 | E.C.T. CONSTRUCTION
1873 | NC 2014 | K10 (2014) | Region II | Cagayan | 102917 | Capacuan ES | SANTA PRAXEDES | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-25 | 2014-11-15 | 020214S00034 | 14BC0069 | 2014-06-30 | 2014-07-10 | 2014-07-22 | 2014-07-25 | 2014-07-28 | B.A. LAGAZO BUILDERS
1874 | NC 2014 | SHS (2014) | Region II | Cagayan | 300450 | Claveria RVS | CLAVERIA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-10 |  | 020214S00149 | 15BC0063 | 2015-07-10 | 2015-07-10 | 2015-07-24 | 2015-07-29 | 2015-07-30 | E.C.T. CONSTRUCTION
1875 | NC 2014 | SHS (2014) | Region II | Cagayan | 300451 | Claveria SAT | CLAVERIA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-10 |  | 020214S00095 | 15BC0064 | 2015-07-10 | 2015-07-10 | 2015-07-24 | 2015-07-29 | 2015-07-30 | E.C.T. CONSTRUCTION
1876 | NC 2014 | K10 (2014) | Region II | Cagayan | 102384 | Daan-ili ES | ALLACAPAN | 2 | 1 | 4 | 1STY 1CL & 1STY 3CL | 2014 K10 BATCH 1 | 3957503.55 |  |  | COMPLETED | 1 | 2014-10-22 | 2014-11-21 | 020214S00020 | 14BC0061 | 2014-06-24 | 2014-07-03 | 2014-06-18 | 2014-07-24 | 2014-07-25 | E.C.T. CONSTRUCTION
1877 | NC 2014 | K10 (2014) | Region II | Cagayan | 102853 | Dammang ES | SANCHEZ-MIRA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-22 | 2014-11-21 | 020214S00036 | 14BC0068 | 2014-06-24 | 2014-07-03 | 2014-06-18 | 2014-07-24 | 2014-07-25 | E.C.T. CONSTRUCTION
1878 | NC 2014 | SHS (2014) | Region II | Cagayan | 300454 | David M. Puzon MNHS | PAMPLONA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-10 |  | 020214S00091 | 15BC0059 | 2015-07-10 | 2015-07-10 | 2015-07-24 | 2015-07-29 | 2015-07-30 | E.C.T. CONSTRUCTION
1879 | NC 2014 | K10 (2014) | Region II | Cagayan | 102611 | Dibalio ES | CLAVERIA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-25 | 2014-11-15 | 020214S00016 | 14BC0070 | 2014-06-30 | 2014-07-10 | 2014-07-22 | 2014-07-25 | 2014-07-28 | B.A. LAGAZO BUILDERS
1880 | NC 2014 | K10 (2014) | Region II | Cagayan | 102835 | Duyun ES | RIZAL | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-11-24 |  | 020214S00165 | 15BC0070 | 2015-07-20 | 2015-07-16 | 2015-07-30 | 2015-08-05 | 2015-08-12 | E.S. PUA CONSTRUCTION
1881 | NC 2014 | SHS (2014) | Region II | Cagayan | 300464 | Illuru NHS | RIZAL | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-10 |  | 020214S00090 | 15BC0051 | 2015-07-10 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-07-30 | E.C.T. CONSTRUCTION
1882 | NC 2014 | K10 (2014) | Region II | Cagayan | 102389 | Kapalutan ES | ALLACAPAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-10-23 | 2014-10-16 | 020214S00010 | 14BC0062 | 2014-06-24 | 2014-07-03 | 2014-06-18 | 2014-07-24 | 2014-07-25 | E.C.T. CONSTRUCTION
1883 | NC 2014 | K10 (2014) | Region II | Cagayan | 102391 | Kapanickian Sur ES | ALLACAPAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-23 | 2014-11-21 | 020214S00011 | 14BC0063 | 2014-06-24 | 2014-07-03 | 2014-06-18 | 2014-07-24 | 2014-07-25 | E.C.T. CONSTRUCTION
1884 | NC 2014 | K10 (2014) | Region II | Cagayan | 155052 | LAGUM PRIMARY SCHOOL | SANTO NIÑO (FAIRE) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-26 |  | 020214S00068 | 15BC0078 | 2015-07-20 | 2015-07-16 | 2015-07-30 | 2015-08-05 | 2015-08-14 | E.S. PUA CONSTRUCTION
1885 | NC 2014 | SHS (2014) | Region II | Cagayan | 300473 | Libertad NHS | ABULUG | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-10 |  | 020214S00089 | 15BC0057 | 2015-07-10 | 2015-07-10 | 2015-07-24 | 2015-07-29 | 2015-07-30 | DANDEX CONSTRUCTION
1886 | NC 2014 | K10 (2014) | Region II | Cagayan | 102343 | Macugay ES | ABULUG | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
1887 | NC 2014 | K10 (2014) | Region II | Cagayan | 102591 | Magsidel ES | CALAYAN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2875174.43 |  |  | COMPLETED | 1 | 2014-12-16 | 2015-07-25 | 020214S00015 | 14BC0074 | 2014-07-29 | 2014-07-31 | 2014-08-12 | 2014-08-15 | 2014-08-18 | E.C.T. CONSTRUCTION
1888 | NC 2014 | SHS (2014) | Region II | Cagayan | 300477 | Matucay National High School | ALLACAPAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-10 |  | 020214S00088 | 15BC0049 | 2015-07-10 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-07-30 | E.C.T. CONSTRUCTION
1889 | NC 2014 | SHS (2014) | Region II | Cagayan | 300478 | Mauanan NHS | RIZAL | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | 2015-11-11 | 2015-11-11 | 020214S00087 | 15BC0054 | 2015-07-10 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-07-30 | E.S. PUA CONSTRUCTION
1890 | NC 2014 | K10 (2014) | Region II | Cagayan | 102768 | Minanga Sur ES | LASAM | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-10-23 | 2014-11-15 | 020214S00017 | 14BC0067 | 2014-06-24 | 2014-07-03 | 2014-06-18 | 2014-07-24 | 2014-07-25 | CAMIA CONST. DEVELOPMENT CORPORATION (FORMERLY:CAM
1891 | NC 2014 | SHS (2014) | Region II | Cagayan | 306425 | Namuccayan Integrated School | SANTO NIÑO (FAIRE) | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1
1892 | NC 2014 | K10 (2014) | Region II | Cagayan | 306425 | Namuccayan Integrated School | SANTO NIÑO (FAIRE) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
1893 | NC 2014 | K10 (2014) | Region II | Cagayan | 102843 | Nanungaran ES | RIZAL | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-11-09 | 2015-01-28 | 020214S00019 | 14BC0049 | 2014-07-16 | 2014-07-18 | 2014-07-31 | 2014-08-07 | 2014-08-11 | E.C.T. CONSTRUCTION
1894 | NC 2014 | K10 (2014) | Region II | Cagayan | 102949 | Niug ES | SANTO NIÑO (FAIRE) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-30 | 2015-01-28 | 020214S00024 | 14BC0052 | 2014-08-10 | 2014-08-14 | 2014-08-26 | 2014-08-28 | 2014-09-01 | E.S. PUA CONSTRUCTION
1895 | NC 2014 | SHS (2014) | Region II | Cagayan | 300479 | Pamplona National School of Fisheries | PAMPLONA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-10 | 2015-12-22 | 020214S00085 | 15BC0060 | 2015-07-10 | 2015-07-10 | 2015-07-24 | 2015-07-29 | 2015-07-30 | E.C.T. CONSTRUCTION
1896 | NC 2014 | SHS (2014) | Region II | Cagayan | 300481 | Piat National HS | PIAT | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-10 |  | 020214S00084 | 15BC0052 | 2015-07-10 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-07-30 | JIRK CONSTRUCTION
1897 | NC 2014 | K10 (2014) | Region II | Cagayan | 102549 | San Juan ES | BALLESTEROS | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-25 | 2015-01-28 | 020214S00013 | 14BC0072 | 2014-06-30 | 2014-07-22 | 2014-07-23 | 2014-07-25 | 2014-07-28 | D.J.D. CONSTRUCTION
1898 | NC 2014 | K10 (2014) | Region II | Cagayan | 102347 | San Julian ES | ABULUG | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-10-23 | 2015-01-28 | 020214S00048 | 14BC0065 | 2014-06-24 | 2014-07-03 | 2014-06-18 | 2014-07-24 | 2014-07-25 | E.C.T. CONSTRUCTION
1899 | NC 2014 | SHS (2014) | Region II | Cagayan | 300485 | Sanchez Mira NHS | SANCHEZ-MIRA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-10 |  | 020214S00083 | 15BC0061 | 2015-07-10 | 2015-07-10 | 2015-07-24 | 2015-07-29 | 2015-07-30 | CAVAT CAPITOL MERCHANDISING & CONSTRUCTION
1900 | NC 2014 | SHS (2014) | Region II | Cagayan | 300486 | Sanchez Mira SAT | SANCHEZ-MIRA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-10 |  | 020214S00071 | 15BC0062 | 2015-07-10 | 2015-07-10 | 2015-07-24 | 2015-07-29 | 2015-07-30 | E.C.T. CONSTRUCTION
1901 | NC 2014 | K10 (2014) | Region II | Cagayan | 102350 | Sirit ES | ABULUG | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-23 | 2014-10-16 | 020214S00051 | 14BC0066 | 2014-06-24 | 2014-07-03 | 2014-06-18 | 2014-07-24 | 2014-07-25 | E.C.T. CONSTRUCTION
1902 | NC 2014 | SHS (2014) | Region II | Cagayan | 300489 | Sta. Praxedes HS | SANTA PRAXEDES | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-11 | 2015-12-11 | 020214S00081 | 15BC0065 | 2015-07-10 | 2015-07-10 | 2015-07-24 | 2015-07-29 | 2015-07-30 | E.C.T. CONSTRUCTION
1903 | NC 2014 | SHS (2014) | Region II | Cagayan | 300491 | Sto. Nino NHS | SANTO NIÑO (FAIRE) | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-10 |  | 020214S00092 | 15BC0050 | 2015-07-10 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-07-30 | JIRK CONSTRUCTION
1904 | NC 2014 | K10 (2014) | Region II | Cagayan | 102954 | Tabang ES | Sto. Nino | 2 | 1 | 1 | 1STY1CL (Toilet Attached) | 2014 K10 BATCH 4C | 1248449.69 |  |  | COMPLETED | 1 | 2015-11-24 | 2015-11-24 | 020214S00163 | 15BC0072 | 2015-07-20 | 2015-07-16 | 2015-07-30 | 2015-08-05 | 2015-08-12 | E.S. PUA CONSTRUCTION
1905 | NC 2014 | SHS (2014) | Region II | Cagayan | 300495 | Utan IS | ALLACAPAN | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-11 | 2015-11-11 | 020214S00080 | 15BC0048 | 2015-07-10 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-07-30 | OCP CONSTRUCTION
1906 | NC 2014 | K10 (2014) | Region II | Cagayan | 102847 | Villa Cruz ES | Rizal | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-11-24 |  | 020214S00164 | 15BC0071 | 2015-07-20 | 2015-07-16 | 2015-07-30 | 2015-08-05 | 2015-08-12 | E.S. PUA CONSTRUCTION
1907 | NC 2014 | K10 (2014) | Region II | Cagayan | 102831 | Warat ES | PIAT | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-09 | 020214S00018 | 14BC0047 | 2014-07-16 | 2014-07-18 | 2014-07-31 | 2014-08-07 | 2014-08-11 | E.C.T. CONSTRUCTION
1908 | NC 2014 | K10 (2014) | Region II | Cagayan | 102551 | Wawang ES | BALLESTEROS | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-25 | 2015-01-28 | 020214S00014 | 14BC0073 | 2014-06-30 | 2014-07-10 | 2014-07-22 | 2014-07-25 | 2014-07-28 | D.J.D. CONSTRUCTION
1909 | NC 2014 | SHS (2014) | Region II | Cagayan | 300497 | Western Cagayan SAT | LASAM | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-10 |  | 020214S00079 | 15BC0046 | 2015-07-10 | 2015-07-10 | 2015-07-23 | 2015-07-28 | 2015-07-30 | E.C.T. CONSTRUCTION
1910 | NC 2014 | K10 (2014) | Region II | Cagayan | 102976 | Alabiao ES | TUAO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2014 K10 BATCH 4C | 2088606.04 |  |  | COMPLETED | 1
1911 | NC 2014 | K10 (2014) | Region II | Cagayan | 102976 | Alabiao ES | TUAO | 3 |  | 1 | 1STY1CL (Toilet Attached) | 2014 K10 BATCH 4C | 1248449.69 |  |  | COMPLETED | 1
1912 | NC 2014 | SHS (2014) | Region II | Cagayan | 300425 | Amulung NHS | AMULUNG | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-28 |  | 020214S00078 | 15-BD-0071 | 2015-08-13 | 2015-08-25 | 2015-08-26 | 2015-08-30 | 2015-09-11 | CAVAT CAPITOL MERCHANDISING & CONSTRUCTION
1913 | NC 2014 | SHS (2014) | Region II | Cagayan | 306008 | Amulung NHS - Baculud Ext. | AMULUNG | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-11 | 2015-10-11 | 020214S00077 | 15-BD-0033 | 2015-07-11 | 2015-07-23 | 2015-07-23 | 2015-07-30 | 2015-08-12 | JOHN 6:51 BUILDERS
1914 | NC 2014 | SHS (2014) | Region II | Cagayan | 306017 | Amulung NHS - Dadda Ext. | AMULUNG | 3 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | 2015-10-11 | 2015-09-21 | 020214S00076 | 15-BD-0032 | 2015-07-11 | 2015-07-23 | 2015-07-23 | 2015-07-30 | 2015-08-12 | E. GUADIZ CONSTRUCTION
1915 | NC 2014 | SHS (2014) | Region II | Cagayan | 300426 | Andarayan NHS | SOLANA | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 020214S00075 | 15-BD-0046 | 2015-07-17
1916 | NC 2014 | K10 (2014) | Region II | Cagayan | 102877 | Bantay ES | SOLANA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-06 | 2014-11-05 | 020214S00031 | 14-BD-0025 | 2014-06-25 | 2014-06-26 | 2014-07-09 | 2014-07-17 | 2014-08-07 | E.C.T. CONSTRUCTION
1917 | NC 2014 | SHS (2014) | Region II | Cagayan | 306009 | Bayabat NHS - La Suerte Ext. | AMULUNG | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-11 | 2015-12-10 | 020214S00074 | 15-BD-0034 | 2015-07-11 | 2015-07-23 | 2015-07-23 | 2015-07-30 | 2015-08-12 | CAVAT CAPITOL MERCHANDISING & CONSTRUCTION
1918 | NC 2014 | K10 (2014) | Region II | Cagayan | 102798 | Buyun ES | PEÑABLANCA | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1864740.174 |  |  | COMPLETED | 1 | 2015-11-10 | 2015-11-10 | 020214S00065 | 15-BD-0040 | 2015-07-11 | 2015-07-23 | 2015-07-23 | 2015-07-30 | 2015-08-12 | CAVAT CAPITOL MERCHANDISING & CONSTRUCTION
1919 | NC 2014 | SHS (2014) | Region II | Cagayan | 300446 | Cabbo NHS | PEÑABLANCA | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-09 |  | 020214S00073 | 15-BD-0073 | 2015-08-13 | 2015-08-25 | 2015-08-26 | 2015-08-30 | 2015-09-11 | E.C.T. CONSTRUCTION
1920 | NC 2014 | K10 (2014) | Region II | Cagayan | 102712 | Capitan Elementary School | IGUIG | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-24 | 2015-01-25 | 020214S00029 | 14-BD-0022 | 2014-10-07 | 2014-10-24 | 2014-10-27 | 2014-11-04 | 2014-11-26 | DEKM CONSTRUCTION
1921 | NC 2014 | K10 (2014) | Region II | Cagayan | 102428 | Catarauan ES | AMULUNG | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1834740.174 |  |  | COMPLETED | 1 | 2015-11-10 |  | 020214S00062 | 15-BD-0037 | 2015-07-11 | 2015-07-23 | 2015-07-23 | 2015-07-30 | 2015-08-12 | CAVAT CAPITOL MERCHANDISING & CONSTRUCTION
1922 | NC 2014 | SHS (2014) | Region II | Cagayan | 306010 | Cordova National High School Extension Classes | AMULUNG | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-12 |  | 020214S00072 | 15-BD-0044 | 2015-07-19 | 2015-08-04 | 2015-08-05 | 2015-08-10 | 2015-08-27 | E.C.T. CONSTRUCTION
1923 | NC 2014 | K10 (2014) | Region II | Cagayan | 300427 | Dassun NHS | SOLANA | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-10 | 2015-11-25 | 020214S00064 | 15-BD-0041 | 2015-07-11 | 2015-07-23 | 2015-07-23 | 2015-07-30 | 2015-08-12 | CAVAT CAPITOL MERCHANDISING & CONSTRUCTION
1924 | NC 2014 | SHS (2014) | Region II | Cagayan | 300456 | Don Severino Pagalilauan National High School | PEÑABLANCA | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-24 |  | 020214S00103 | 15-BD-0048 | 2015-07-20 | 2015-08-04 | 2015-08-05 | 2015-08-10 | 2015-08-27 | MEGAY CONSTRUCTION AND SUPPLY
1925 | NC 2014 | SHS (2014) | Region II | Cagayan | 300458 | Enrile Vocational High School | ENRILE | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-19 |  | 020214S00105 | 15-BD-0024 | 2015-07-01 | 2015-07-14 | 2015-07-15 | 2015-07-24 | 2015-09-21 | JOHN 6:51 BUILDERS
1926 | NC 2014 | K10 (2014) | Region II | Cagayan | 102882 | Furagui ES | SOLANA | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1849740.174 |  |  | COMPLETED | 1 | 2015-11-20 | 2015-11-28 | 020214S00063 | 15-BD-0042 | 2015-07-11 | 2015-07-23 | 2015-07-24 | 2015-08-07 | 2015-09-21 | PACIFIC STAR ERECTORS
1927 | NC 2014 | SHS (2014) | Region II | Cagayan | 300461 | Gadu NHS | SOLANA | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-03 |  | 020214S00082 | 15-BD-0027 | 2015-06-25 | 2015-06-26 | 2015-07-08 | 2015-07-22 | 2015-08-06 | JJJARNS CONSTRUCTION
1928 | NC 2014 | K10 (2014) | Region II | Cagayan | 306424 | Gadu NHS- Nangalisan Extension | SOLANA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
1929 | NC 2014 | SHS (2014) | Region II | Cagayan | 306424 | Gadu NHS- Nangalisan Extension | SOLANA | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
1930 | NC 2014 | SHS (2014) | Region II | Cagayan | 306001 | Gammad National High School | IGUIG | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-24 |  | 020214S00113 | 15-BD-0045 | 2015-07-20 | 2015-08-04 | 2015-08-05 | 2015-08-10 | 2015-08-27 | CAVAT CAPITOL MERCHANDISING & CONSTRUCTION
1931 | NC 2014 | SHS (2014) | Region II | Cagayan | 300467 | Itawes National High School | TUAO | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-03 |  | 020214S00112 | 15-BD-0029 | 2015-07-01 | 2015-07-14 | 2015-07-15 | 2015-07-22 | 2015-08-06 | KATHA BUILDERS
1932 | NC 2014 | K10 (2014) | Region II | Cagayan | 102431 | La Suerte ES | AMULUNG | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-20 | 2015-02-09 | 020214S00028 | 14-BD-0024 | 2014-10-07 | 2014-10-24 | 2014-10-27 | 2014-10-31 | 2014-11-21 | E. GUADIZ CONSTRUCTION
1933 | NC 2014 | SHS (2014) | Region II | Cagayan | 300472 | Lemu NHS | ENRILE | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-03 |  | 020214S00111 | 15-BD-0025 | 2015-07-01 | 2015-07-14 | 2015-07-15 | 2015-07-22 | 2015-08-03 | JOHN 6:51 BUILDERS
1934 | NC 2014 | SHS (2014) | Region II | Cagayan | 300476 | Magalalag National High School | ENRILE | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-03 |  | 020214S00110 | 15-BD-0026 | 2015-07-01 | 2015-07-14 | 2015-07-15 | 2015-07-22 | 2015-08-06 | JOHN 6:51 BUILDERS
1935 | NC 2014 | K10 (2014) | Region II | Cagayan | 102414 | Magogod ES | AMULUNG | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-11-05 | 2014-12-05 | 020214S00027 | 14-BD-0023 | 2014-06-25 | 2014-06-26 | 2014-07-09 | 2014-07-17 | 2014-08-07 | M.G. JACINTO CONSTRUCTION
1936 | NC 2014 | K10 (2014) | Region II | Cagayan | 102874 | Masin-San Pablo ES | SOLANA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2090417.57 |  |  | COMPLETED | 1 | 2014-11-03 | 2014-11-03 | 020214S00030 | 14-BD-0021 | 2014-06-25 | 2014-06-26 | 2014-07-09 | 2014-07-17 | 2014-08-07 | M.G. JACINTO CONSTRUCTION
1937 | NC 2014 | K10 (2014) | Region II | Cagayan | 102437 | Nanuccauan ES | AMULUNG | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1849740.174 |  |  | COMPLETED | 1 | 2015-11-10 |  | 020214S00067 | 15-BD-0036 | 2015-07-11 | 2015-07-23 | 2015-07-23 | 2015-07-30 | 2015-08-12 | CAVAT CAPITOL MERCHANDISING & CONSTRUCTION
1938 | NC 2014 | K10 (2014) | Region II | Cagayan | 102816 | Parabba ES | PEÑABLANCA | 3 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-26 |  | 020214S00160 | 15-BD-0054 | 2015-07-20 | 2015-08-07 | 2015-08-11 | 2015-08-21 | 2015-09-29 | PACIFIC STAR ERECTORS
1939 | NC 2014 | SHS (2014) | Region II | Cagayan | 300457 | Penablanca East NHS | PEÑABLANCA | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-08 |  | 020214S00109 | 15-BD-0074 | 2015-08-14 | 2015-08-27 | 2015-08-28 | 2015-09-02 | 2015-09-11 | E. GUADIZ CONSTRUCTION
1940 | NC 2014 | SHS (2014) | Region II | Cagayan | 300445 | Penablanca National High School | PEÑABLANCA | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 020214S00108 | 15-BD-0063 | 2015-07-21 | 2015-08-05 | 2015-08-07 | 2015-08-17 | 2015-09-02 | CAVAT CAPITOL MERCHANDISING & CONSTRUCTION
1941 | NC 2014 | K10 (2014) | Region II | Cagayan | 102720 | Redondo PS | IGUIG | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-10-11 | 2015-10-16 | 020214S00061 | 15-BD-0038 | 2015-07-11 | 2015-07-23 | 2015-07-23 | 2015-07-30 | 2015-08-12 | OML CONSTRUCTION
1942 | NC 2014 | SHS (2014) | Region II | Cagayan | 300484 | Sampaguita NHS | SOLANA | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-24 |  | 020214S00107 | 15-BD-0047 | 2015-07-20 | 2015-08-04 | 2015-08-05 | 2015-08-10 | 2015-08-27 | JJJARNS CONSTRUCTION
1943 | NC 2014 | SHS (2014) | Region II | Cagayan | 300487 | Solana Fresh Water Fishery School | SOLANA | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-03 |  | 020214S00106 | 15-BD-0028 | 2015-07-01 | 2015-07-14 | 2015-07-15 | 2015-07-22 | 2015-08-06 | KATHA BUILDERS
1944 | NC 2014 | K10 (2014) | Region II | Cagayan | 102893 | Solana West CS | SOLANA | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-11-24 | 2014-11-24 | 020214S00032 | 14-BD-0020 | 2014-06-25 | 2014-06-26 | 2014-07-09 | 2014-07-17 | 2014-08-07 | M.G. JACINTO CONSTRUCTION
1945 | NC 2014 | K10 (2014) | Region II | Cagayan | 102722 | Sta. Teresa PS | IGUIG | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-11 | 2015-10-16 | 020214S00070 | 15-BD-0039 | 2015-07-11 | 2015-07-23 | 2015-07-23 | 2015-07-30 | 2015-08-12 | CAVAT CAPITOL MERCHANDISING & CONSTRUCTION
1946 | NC 2014 | SHS (2014) | Region II | Cagayan | 300492 | Tuao Voc'l. and Tech'l. School | TUAO | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-03 |  | 020214S00093 | 15-BD-0030 | 2015-07-01 | 2015-07-14 | 2015-07-15 | 2015-07-22 | 2015-08-06 | KATHA BUILDERS
1947 | NC 2014 | SHS (2014) | Region II | Cagayan | 300493 | Tuao Voc'l. and Tech'l. School - Culung Annex | TUAO | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-03 |  | 020214S00104 | 15-BD-0031 | 2015-07-01 | 2015-07-14 | 2015-07-15 | 2015-07-22 | 2015-08-06 | CAVAT CAPITOL MERCHANDISING & CONSTRUCTION
1948 | NC 2014 | SHS (2014) | Region II | Cagayan | 306019 | Tuao Voc'l. and Tech'l. School - Malummin Annex | TUAO | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-26 |  | 020214S00115 | 15-BD-0049 | 2015-09-14 | 2015-09-22 | 2015-09-23 | 2015-09-30 | 2015-10-14 | M.G. JACINTO CONSTRUCTION
1949 | NC 2014 | SHS (2014) | Region II | Cagayan | 300494 | Tuao Voc'l. and Tech'l. School - Pata Annex | TUAO | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-11 | 2015-09-21 | 020214S00102 | 15-BD-0035 | 2015-07-11 | 2015-07-23 | 2015-07-23 | 2015-07-30 | 2015-08-12 | CAVAT CAPITOL MERCHANDISING & CONSTRUCTION
1950 | NC 2014 | SHS (2014) | Region II | Cagayan | 300463 | Vicente D. Trinidad High School | IGUIG | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-09 |  | 020214S00101 | 15-BD-0072A | 2015-08-14 | 2015-08-27 | 2015-08-28 | 2015-09-02 | 2015-09-11 | JOHN 6:51 BUILDERS
1951 | NC 2014 | SHS (2014) | Region II | Cagayan | 306421 | Vicente D. Trinidad NHS - Sta. Rosa Annex | IGUIG | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-24 |  | 020214S00100 | 15-BD-0056 | 2015-07-20 | 2015-08-04 | 2015-08-05 | 2015-08-10 | 2015-08-27 | E.C.T. CONSTRUCTION
1952 | NC 2014 | SHS (2014) | Region II | Cagayan | 300459 | Western Enrile Vocational High School | ENRILE | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-24 |  | 020214S00099 | 15-BD-0055 | 2015-07-20 | 2015-08-04 | 2015-08-05 | 2015-08-10 | 2015-08-27 | RPF CONSTRUCTION
1953 | NC 2014 | SHS (2014) | Region II | Cauayan City | 323902 | Cauayan City NHS - Cabaruan Ext. | CITY OF CAUAYAN | 3 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2700828.124 |  |  | COMPLETED | 1 | 2015-12-11 | 2015-12-23 | 020314S00163 | 15BG0038 | 2015-07-14 | 2015-07-17 | 2015-07-29 | 2015-08-03 | 2015-08-06 | MEGABUCKS CONSTRUCTION & DEVELOPMENT CORP.
1954 | NC 2014 | SHS (2014) | Region II | Cauayan City | 323901 | Cauayan City NHS - Research Annex | CITY OF CAUAYAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-19 |  | 020314S00141 | 15BG0046 | 2015-07-23 | 2015-07-27 | 2015-08-07 | 2015-08-12 | 2015-08-17 | ASIAN PEARL CONSTRUCTION & DEVT. CORP.
1955 | NC 2014 | K10 (2014) | Region II | Cauayan City | 103186 | Cauayan East CS - Main | CITY OF CAUAYAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-10-18 | 2014-11-04 | 020314S00020 | 14BG0020 | 2014-07-03 | 2014-07-04 | 2014-07-18 | 2014-07-23 | 2014-07-28 | R TWO S BUILDERS AND ENTERPRISE
1956 | NC 2014 | K10 (2014) | Region II | Cauayan City | 323905 | Cauayan National High School- Marabulig Extension | CITY OF CAUAYAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1839740.174 |  |  | COMPLETED | 1 | 2015-10-20 | 2015-09-21 | 020314S00065 | 15BG0030 | 2015-06-24 | 2015-06-25 | 2015-07-08 | 2015-07-13 | 2015-07-16 | MAR-DEB CONSTRUCTION & DEVELOPMENT
1957 | NC 2014 | K10 (2014) | Region II | Cauayan City | 103190 | Disimuray ES | CITY OF CAUAYAN | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-27 | 2014-09-29 | 020314S00019 | 14BG0014 | 2014-06-26 | 2014-06-27 | 2014-07-11 | 2014-07-16 | 2014-07-21 | R TWO S BUILDERS AND ENTERPRISE
1958 | NC 2014 | K10 (2014) | Region II | Cauayan City | 103230 | Don Faustino N. Dy ES | CITY OF CAUAYAN | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-03 | 2014-10-17 | 020314S00018 | 14BG0022 | 2014-07-03 | 2014-07-04 | 2014-07-18 | 2014-07-23 | 2014-07-28 | R TWO S BUILDERS AND ENTERPRISE
1959 | NC 2014 | SHS (2014) | Region II | Cauayan City | 300538 | Gappal HS | CITY OF CAUAYAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 | 2016-01-25 |  | 020314S00135 | 15BG0053 | 2015-08-10 | 2015-08-13 | 2015-08-25 | 2015-08-28 | 2015-09-02 | O.U.A. CONSTRUCTION
1960 | NC 2014 | K10 (2014) | Region II | Cauayan City | 251001 | MALIGAYA ELEMENTARY SCHOOL-ANNEX | CITY OF CAUAYAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1834740.174 |  |  | REVERTED | 0 |  |  | 020314S00066
1961 | NC 2014 | K10 (2014) | Region II | Cauayan City | 103231 | Marabulig I ES | CITY OF CAUAYAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-20 | 2015-10-20 | 020314S00067 | 15BG0032 | 2015-06-24 | 2015-06-25 | 2015-07-08 | 2015-07-13 | 2015-07-16 | DANYSONS CONSTRUCTION
1962 | NC 2014 | SHS (2014) | Region II | Cauayan City | 300567 | Pinoma NHS | CITY OF CAUAYAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 020314S00136 | 15BG0042 | 2015-08-14 | 2015-08-14 | 2015-08-25 | 2015-08-27 | 2015-08-28 | ASIAN PEARL CONSTRUCTION & DEVT. CORP.
1963 | NC 2014 | K10 (2014) | Region II | Cauayan City | 103199 | Rogus ES | CITY OF CAUAYAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1854740.174 |  |  | COMPLETED | 1 | 2015-10-20 | 2015-10-20 | 020314S00068 | 15BG0031 | 2015-06-24 | 2015-06-25 | 2015-07-08 | 2015-07-13 | 2015-07-16 | DANYSONS CONSTRUCTION
1964 | NC 2014 | SHS (2014) | Region II | Cauayan City | 300589 | San Antonio National High School | CITY OF CAUAYAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-19 |  | 020314S00139 | 15BG0049 | 2015-07-23 | 2015-07-27 | 2015-08-07 | 2015-08-12 | 2015-08-17 | MAR-DEB CONSTRUCTION & DEVELOPMENT
1965 | NC 2014 | SHS (2014) | Region II | Cauayan City | 300613 | Villa Concepcion HS | CITY OF CAUAYAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 | 2016-01-26 |  | 020314S00125 | 15BG0070 | 2015-08-11 | 2015-08-14 | 2015-08-26 | 2015-08-28 | 2015-09-03 | EDISON DEVELOPMENT CONSTRUCTION
1966 | NC 2014 | SHS (2014) | Region II | Cauayan City | 323903 | Villa Concepcion HS - Rogus Ext. | CITY OF CAUAYAN | 3 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2790828.124 |  |  | COMPLETED | 1 | 2015-12-08 | 2015-11-25 | 020314S00134 | 15BG0039 | 2015-08-10 | 2015-08-14 | 2015-08-25 | 2015-08-28 | 2015-09-02 | DANYSONS CONSTRUCTION
1967 | NC 2014 | SHS (2014) | Region II | Cauayan City | 300614 | Villaluna NHS | CITY OF CAUAYAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-03 | 2015-12-23 | 020314S00133 | 15BG0044 | 2015-07-23 | 2015-07-27 | 2015-08-07 | 2015-08-12 | 2015-08-17 | APD CONSTRUCTION
1968 | NC 2014 | SHS (2014) | Region II | Cauayan City | 306107 | WEST TABACAL REGION NATIONAL HIGH SCHOOL | CITY OF CAUAYAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 | 2016-01-26 |  | 020314S00132 | 15BG0055 | 2015-08-11 | 2015-08-14 | 2015-08-26 | 2015-08-28 | 2015-09-03 | MAR-DEB CONSTRUCTION & DEVELOPMENT
1969 | NC 2014 | K10 (2014) | Region II | City of Ilagan | 103357 | Balla PS | ILAGAN (Capital) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1
1970 | NC 2014 | K10 (2014) | Region II | City of Ilagan | 103357 | Balla PS | ILAGAN (Capital) | 1 |  | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1
1971 | NC 2014 | K10 (2014) | Region II | City of Ilagan | 103391 | Cabeceria 25 ES | ILAGAN (Capital) | 1 | 1 | 4 | 1sty4cl (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 | 2015-12-25 | 2015-12-15 | 020314S00183 | 15BE0100 | 2015-07-20 | 2015-07-21 | 2015-08-04 | 2015-08-20 | 2015-08-26 | EGB CONSTRUCTION
1972 | NC 2014 | K10 (2014) | Region II | City of Ilagan | 103363 | Fuyo ES | ILAGAN (Capital) | 1 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 4A | 1857308.9832 |  |  | COMPLETED | 1 | 2015-04-12 | 2015-03-31 | 020314S00058 | 14BE0086 | 2014-11-23 | 2014-11-24 | 2014-12-09 | 2014-12-22 | 2015-01-09 | E.S. PUA CONSTRUCTION
1973 | NC 2014 | K10 (2014) | Region II | City of Ilagan | 103400 | Gayong-gayong Norte ES | ILAGAN (Capital) | 1 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 4A | 1857308.9832 |  |  | COMPLETED | 1 | 2015-04-12 | 2015-03-31 | 020314S00056 | 14BE0088 | 2014-11-23 | 2014-11-24 | 2014-12-09 | 2014-12-22 | 2015-01-09 | ATLANTIC CONSTRUCTION
1974 | NC 2014 | SHS (2014) | Region II | City of Ilagan | 306152 | Gayong-Gayong Sur IS | ILAGAN (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-27 | 2015-09-30 | 020314S00131 | 15BE0066 | 2015-06-14 | 2015-06-15 | 2015-06-29 | 2015-07-07 | 2015-07-13 | EGB CONSTRUCTION
1975 | NC 2014 | K10 (2014) | Region II | City of Ilagan | 300545 | Ilagan Sports HS (INHS - Alibagu Annex) | ILAGAN (Capital) | 1 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-10 |  | 020314S00181 | 15BE0113 | 2015-07-26 | 2015-07-27 | 2015-08-10 | 2015-08-26 | 2015-09-08 | 4 As CONSTRUCTION
1976 | NC 2014 | SHS (2014) | Region II | City of Ilagan | 300542 | Isabela NHS - Main | ILAGAN (Capital) | 1 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15221327.92 |  |  | COMPLETED | 1 | 2016-04-21 |  | 020314S00118 | 15BE0119 | 2015-08-25 | 2015-08-26 | 2015-09-09 | 2015-09-17 | 2015-09-23 | EGB CONSTRUCTION
1977 | NC 2014 | SHS (2014) | Region II | City of Ilagan | 306149 | ISAT-Cabannungan Annex | ILAGAN (Capital) | 1 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | 2015-12-13 | 2015-11-27 | 020314S00129 | 15BE0068 | 2015-06-29 | 2015-06-30 | 2015-07-14 | 2015-07-21 | 2015-08-03 | EGB CONSTRUCTION
1978 | NC 2014 | SHS (2014) | Region II | City of Ilagan | 306105 | ISAT-Main | ILAGAN (Capital) | 1 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 | 2016-02-10 |  | 020314S00140 | 15BE0099 | 2015-07-20 | 2015-07-21 | 2015-08-04 | 2015-08-26 | 2015-09-08 | EGB CONSTRUCTION
1979 | NC 2014 | SHS (2014) | Region II | City of Ilagan | 306141 | Lupigue Integrated School | ILAGAN (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-27 | 2015-09-08 | 020314S00127 | 15BE0065 | 2015-06-14 | 2015-06-15 | 2015-06-29 | 2015-07-07 | 2015-07-13 | EGB CONSTRUCTION
1980 | NC 2014 | K10 (2014) | Region II | City of Ilagan | 103431 | Salindingan ES | ILAGAN (Capital) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-12-07 | 2015-11-27 | 020314S00182 | 15BE0082 | 2015-07-13 | 2015-07-14 | 2015-07-27 | 2015-07-31 | 2015-08-07 | EGB CONSTRUCTION
1981 | NC 2014 | K10 (2014) | Region II | City of Ilagan | 103375 | San Juan Rugao ES | ILAGAN (Capital) | 1 | 1 | 5 | 1STY5CL (Toilet Attached) | 2014 K10 BATCH 4C | 4673636.82 |  |  | COMPLETED | 1
1982 | NC 2014 | K10 (2014) | Region II | City of Ilagan | 103375 | San Juan Rugao ES | ILAGAN (Capital) | 1 |  | 5 | 1STY5CL (Toilet Attached) | 2014 K10 BATCH 4C | 4673636.82 |  |  | COMPLETED | 1
1983 | NC 2014 | K10 (2014) | Region II | City of Ilagan | 103410 | Sindun Bayabo ES | ILAGAN (Capital) | 1 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 4A | 1857308.9832 |  |  | COMPLETED | 1 | 2015-04-12 | 2015-03-31 | 020314S00057 | 14BE0087 | 2014-11-23 | 2014-11-24 | 2014-12-09 | 2014-12-22 | 2015-01-09 | ATLANTIC CONSTRUCTION
1984 | NC 2014 | K10 (2014) | Region II | Isabela | 103795 | Annanuman ES | SAN PABLO | 1 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 4A | 1857308.9832 |  |  | COMPLETED | 1 | 2015-04-10 | 2015-03-31 | 020314S00061 | 14BE0089 | 2014-11-23 | 2014-11-24 | 2014-12-09 | 2014-12-22 | 2015-01-09 | RSKC CONSTRUCTION
1985 | NC 2014 | K10 (2014) | Region II | Isabela | 103895 | Bantug ES (Jurimar ES) | TUMAUINI | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 020314S00001 | 14BE0034 | 2014-07-30 | 2014-07-31 | 2014-08-14 | 2014-09-02 | 2014-09-12 | V.R.D.J. CONSTRUCTION
1986 | NC 2014 | K10 (2014) | Region II | Isabela | 103395 | Cabeceria 6 ES | ILAGAN (Capital) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-19 | 020314S00022 | 14BE0040 | 2014-07-30 | 2014-07-31 | 2014-08-14 | 2014-09-02 | 2014-09-12 | ATLANTIC CONSTRUCTION
1987 | NC 2014 | SHS (2014) | Region II | Isabela | 306101 | Calanigan NHS (Sto. Tomas Annex) | SANTO TOMAS | 1 | 1 | 4 | 1STY4CL | 2014 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1 | 2015-12-01 | 2015-10-15 | 020314S00126 | 15BE0069 | 2015-06-29 | 2015-06-30 | 2015-07-14 | 2015-07-21 | 2015-08-03 | RSKC CONSTRUCTION
1988 | NC 2014 | K10 (2014) | Region II | Isabela | 306153 | Cumabao IS | TUMAUINI | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
1989 | NC 2014 | K10 (2014) | Region II | Isabela | 103543 | Dibutarek ES | PALANAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2220417.57 |  |  | COMPLETED | 1 | 2014-12-21 | 2014-12-14 | 020314S00016 | 14BE0037 | 2014-07-30 | 2014-07-31 | 2014-08-14 | 2014-09-02 | 2014-09-12 | 969 CONSTRUCTION & SUPPLIES
1990 | NC 2014 | K10 (2014) | Region II | Isabela | 103548 | Dimasalansan ES | DIVILICAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1222329.12 |  |  | COMPLETED | 1 | 2014-11-15 | 2014-11-14 | 020314S00015 | 14BE0036 | 2014-07-30 | 2014-07-31 | 2014-08-14 | 2014-09-02 | 2014-09-12 | E.S. PUA CONSTRUCTION
1991 | NC 2014 | K10 (2014) | Region II | Isabela | 103553 | Ditambali ES | PALANAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2270417.57 |  |  | COMPLETED | 1 | 2014-12-21 | 2014-12-15 | 020314S00014 | 14BE0038 | 2014-07-30 | 2014-07-31 | 2014-08-14 | 2014-09-02 | 2014-09-12 | 969 CONSTRUCTION & SUPPLIES
1992 | NC 2014 | SHS (2014) | Region II | Isabela | 300549 | Divilacan NHS | DIVILICAN | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6919337.6381 |  |  | COMPLETED | 1 | 2016-01-11 |  | 020314S00144 | 15BE0110 | 2015-07-26 | 2015-07-27 | 2015-08-10 | 2015-08-26 | 2015-09-08 | E.C.T. CONSTRUCTION
1993 | NC 2014 | K10 (2014) | Region II | Isabela | 103846 | Divisoria ES | SANTA MARIA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 928654.4916 |  |  | COMPLETED | 1 | 2015-03-26 | 2015-03-23 | 020314S00063 | 14BE0085 | 2014-11-23 | 2014-11-24 | 2014-12-09 | 2014-12-22 | 2015-01-09 | ATLANTIC CONSTRUCTION
1994 | NC 2014 | K10 (2014) | Region II | Isabela | 306109 | Fermeldy NHS (Tumauini NHS - Ferneldy Annex) | TUMAUINI | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
1995 | NC 2014 | SHS (2014) | Region II | Isabela | 306109 | Fermeldy NHS (Tumauini NHS - Ferneldy Annex) | TUMAUINI | 1 | 1 | 4 | 1STY4CL | 2014 SHS BATCH 1 | 3514886.575 |  |  | COMPLETED | 1
1996 | NC 2014 | SHS (2014) | Region II | Isabela | 300554 | Isabela SF | PALANAN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8874965.051 |  |  | COMPLETED | 1 |  |  | 020314S00130 | 15BE0111 | 2015-11-10 | 2015-11-11
1997 | NC 2014 | SHS (2014) | Region II | Isabela | 300551 | Lanna NHS (Isabela NHS - Lanna Annex) | TUMAUINI | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-11 |  | 020314S00123 | 15BE0072 | 2015-07-01 | 2015-07-02 | 2015-07-15 | 2015-08-26 | 2015-09-08 | SMT CONSTRUCTION
1998 | NC 2014 | SHS (2014) | Region II | Isabela | 300560 | Maconacon NHS | MACONACON | 1 | 1 | 4 | 1STY4CL | 2014 SHS BATCH 1 | 3864886.575 |  |  | COMPLETED | 1 | 2015-12-25 | 2015-12-24 | 020314S00122 | 15BE0109 | 2015-07-21 | 2015-07-23 | 2015-08-06 | 2015-08-20 | 2015-08-26 | E.C.T. CONSTRUCTION
1999 | NC 2014 | K10 (2014) | Region II | Isabela | 103158 | Pilig Abajo ES | CABAGAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-12 | 020314S00010 | 14BE0035 | 2014-07-30 | 2014-07-31 | 2014-08-14 | 2014-09-02 | 2014-09-12 | ATLANTIC CONSTRUCTION
2000 | NC 2014 | SHS (2014) | Region II | Isabela | 300610 | Regional Science High School for Region II | TUMAUINI | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 | 2016-02-10 |  | 020314S00121 | 15BE0071 | 2015-07-26 | 2015-07-27 | 2015-08-10 | 2015-08-26 | 2015-09-08 | EGB CONSTRUCTION
2001 | NC 2014 | SHS (2014) | Region II | Isabela | 300585 | San Antonio NHS | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
2002 | NC 2014 | K10 (2014) | Region II | Isabela | 103559 | San Isidro ES | PALANAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2210417.57 |  |  | COMPLETED | 1 | 2014-12-21 | 2014-12-02 | 020314S00013 | 14BE0039 | 2014-07-30 | 2014-07-31 | 2014-08-14 | 2014-09-02 | 2014-09-12 | E.S. PUA CONSTRUCTION
2003 | NC 2014 | SHS (2014) | Region II | Isabela | 300597 | San Pablo NHS (St. Paul Voc'l. & Ind'l. HS Annex) | SAN PABLO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-10 |  | 020314S00119 | 15BE0081 | 2015-07-06 | 2015-07-07 | 2015-07-20 | 2015-08-26 | 2015-09-08 | 4 As CONSTRUCTION
2004 | NC 2014 | K10 (2014) | Region II | Isabela | 103377 | San Rodrigo PS | ILAGAN (Capital) | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-11-30 | 020314S00017 | 14BE0042 | 2014-07-30 | 2014-07-31 | 2014-08-14 | 2014-09-02 | 2014-09-12 | ATLANTIC CONSTRUCTION
2005 | NC 2014 | K10 (2014) | Region II | Isabela | 103881 | San Vicente ES | TUMAUINI | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 020314S00012 | 14BE0031 | 2014-07-30 | 2014-07-31 | 2014-08-14 | 2014-09-02 | 2014-09-12 | V.R.D.J. CONSTRUCTION
2006 | NC 2014 | K10 (2014) | Region II | Isabela | 103810 | Simanu Sur ES | SAN PABLO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 928654.4916 |  |  | COMPLETED | 1 | 2015-03-26 | 2015-03-15 | 020314S00060 | 14BE0084 | 2014-11-23 | 2014-11-24 | 2014-12-09 | 2014-12-22 | 2015-01-09 | RSKC CONSTRUCTION
2007 | NC 2014 | K10 (2014) | Region II | Isabela | 155527 | Sindun Highway Elementary | ILAGAN (Capital) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-20 | 2014-11-20 | 020314S00002 | 14BE0041 | 2014-07-30 | 2014-07-31 | 2014-08-14 | 2014-09-02 | 2014-09-12 | SMT CONSTRUCTION
2008 | NC 2014 | SHS (2014) | Region II | Isabela | 300601 | St. Paul Voc'l. & Ind'l. HS-Main | SAN PABLO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-12 |  | 020314S00128 | 15BE0073 | 2015-07-01 | 2015-07-02 | 2015-07-15 | 2015-09-10 | 2015-09-15 | 4 As CONSTRUCTION
2009 | NC 2014 | SHS (2014) | Region II | Isabela | 300606 | Sto Tomas NHS | SANTO TOMAS | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 | 2016-02-10 |  | 020314S00145 | 15BE0080 | 2015-07-30 | 2015-07-24 | 2015-08-12 | 2015-08-26 | 2015-09-08 | V.R.D.J. CONSTRUCTION
2010 | NC 2014 | SHS (2014) | Region II | Isabela | 300609 | Tumauini NHS | TUMAUINI | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-26 |  | 020314S00162 | 15BE0079 | 2015-07-30 | 2015-07-31 | 2015-08-12 | 2015-08-26 | 2015-09-08 | EGB CONSTRUCTION
2011 | NC 2014 | K10 (2014) | Region II | Isabela | 103886 | Ugad PS | TUMAUINI | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-14 | 020314S00008 | 14BE0032 | 2014-07-30 | 2014-07-31 | 2014-08-14 | 2014-09-02 | 2014-09-12 | V.R.D.J. CONSTRUCTION
2012 | NC 2014 | K10 (2014) | Region II | Isabela | 103164 | Union PS | CABAGAN | 1 | 1 | 2 | 2UNITS 1STY1CL | 2014 K10 BATCH 4A | 1857308.9832 |  |  | COMPLETED | 1 | 2015-04-07 | 2015-03-31 | 020314S00062 | 14BE0090 | 2014-11-23 | 2014-11-24 | 2014-12-09 | 2014-12-22 | 2015-01-09 | SMT CONSTRUCTION
2013 | NC 2014 | SHS (2014) | Region II | Isabela | 300593 | Alibadbad NHS (San Mariano HS - Alibadabad Annex) | SAN MARIANO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8294965.051 |  | 8031908.46 | COMPLETED | 1 | 2016-03-15 |  | 020314S00164 | 15BF0102 | 2015-08-14 | 2015-08-17 | 2015-09-30 | 2015-10-05 | 2015-10-12 | R R C CONSTRUCTION
2014 | NC 2014 | K10 (2014) | Region II | Isabela | 103099 | Andabuen ES - Annex | BENITO SOLIVEN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  | 1890003.15 | COMPLETED | 1
2015 | NC 2014 | SHS (2014) | Region II | Isabela | 300546 | Andabuen National High School | BENITO SOLIVEN | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6369337.6381 |  | 6253875.24 | COMPLETED | 1 | 2016-02-02 |  | 020314S00153 | 15BF0111 | 2015-08-31 | 2015-09-08 | 2015-09-08 | 2015-09-24 | 2015-09-30 | L.C. TALON CONSTRUCTION
2016 | NC 2014 | K10 (2014) | Region II | Isabela | 103338 | Barcolan ES | GAMU | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2940174.43 |  | 2835375.31 | COMPLETED | 1 | 2015-02-16 | 2015-02-16 | 020314S00037 | 14BF0070 | 2014-10-13 | 2014-10-13 | 2014-10-13 | 2014-10-21 | 2014-10-29 | ATLANTIC CONSTRUCTION
2017 | NC 2014 | SHS (2014) | Region II | Isabela | 306112 | BARUCBOC NATIONAL HIGH SCHOOL | QUEZON | 5 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  | 6194186.18 | COMPLETED | 1 | 2016-02-02 |  | 020314S00160 | 15BF0113 | 2015-08-31 | 2015-09-03 | 2015-09-14 | 2015-09-24 | 2015-09-30 | D.S.T. METALCRAFT AND ENGINEERING WORKS
2018 | NC 2014 | SHS (2014) | Region II | Isabela | 300503 | Benito Soliven NHS | BENITO SOLIVEN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8314965.051 |  | 8086290.15 | COMPLETED | 1 | 2016-02-24 |  | 020314S00159 | 15BF0105 | 2015-08-18 | 2015-08-20 | 2015-09-07 | 2015-09-21 | 2015-09-22 | 4 As CONSTRUCTION
2019 | NC 2014 | SHS (2014) | Region II | Isabela | 306138 | Bimonton Integrated School | MALLIG | 5 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  | 1761929.9 | COMPLETED | 1 | 2015-11-09 | 2015-10-17 | 020314S00158 | 15BF0068 | 2015-06-30 | 2015-06-09 | 2015-06-19 | 2015-07-24 | 2015-08-06 | DANYSONS CONSTRUCTION
2020 | NC 2014 | K10 (2014) | Region II | Isabela | 103574 | Binarzang ES | QUIRINO | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  | 2850101.3 | COMPLETED | 1 | 2016-01-14 |  | 020314S00180 | 15BF0086 | 2015-08-04 | 2015-08-10 | 2015-08-17 | 2015-08-28 | 2015-09-01 | SMT CONSTRUCTION
2021 | NC 2014 | K10 (2014) | Region II | Isabela | 103749 | Binatug ES | SAN MARIANO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  | 1937822.85 | COMPLETED | 1 | 2015-02-27 | 2015-02-27 | 020314S00039 | 14BF0065 | 2014-10-13 | 2014-10-13 | 2014-10-13 | 2014-10-15 | 2014-10-31 | DANYSONS CONSTRUCTION
2022 | NC 2014 | SHS (2014) | Region II | Isabela | 306157 | Cabaruan Integrated School | NAGUILIAN | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  | 1751097.05 | COMPLETED | 1 | 2015-12-11 | 2015-12-10 | 020314S00156 | 15BF0085 | 2015-08-03 | 2015-08-10 | 2015-08-17 | 2015-09-01 | 2015-09-07 | JMU CONSTRUCTION
2023 | NC 2014 | SHS (2014) | Region II | Isabela | 300509 | Caliguian NHS-Main | BURGOS | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  | 7976545.42 | COMPLETED | 1 | 2016-02-13 |  | 020314S00155 | 15BF0097 | 2015-08-07 | 2015-08-18 | 2015-09-01 | 2015-09-10 | 2015-09-11 | W.D. NAVARRO CONSTRUCTION CO.
2024 | NC 2014 | SHS (2014) | Region II | Isabela | 300512 | Callang NHS - Main | SAN MANUEL | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  | 8005134.79 | COMPLETED | 1 | 2016-02-28 |  | 020314S00154 | 15BF0096 | 2015-08-07 | 2015-08-10 | 2015-09-01 | 2015-09-02 | 2015-09-11 | A. DE GUIA CONSTRUCTION
2025 | NC 2014 | K10 (2014) | Region II | Isabela | 103565 | Callangigan ES (Caramoc PS) | QUEZON | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  | 1949139.66 | COMPLETED | 1 | 2015-04-03 | 2015-04-03 | 020314S00041 | 14BF0062 | 2014-10-27 | 2014-11-03 | 2014-11-03 | 2014-11-17 | 2014-12-25 | DANYSONS CONSTRUCTION
2026 | NC 2014 | K10 (2014) | Region II | Isabela | 103104 | Capuseran ES | BENITO SOLIVEN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  | 1074415.75 | COMPLETED | 1 | 2015-05-25 | 2015-05-24 | 020314S00011 | 14BF0046 | 2014-09-04 | 2014-09-16 | 2014-09-17 | 2014-09-21 | 2014-09-25 | D.S.T. METALCRAFT AND ENGINEERING WORKS
2027 | NC 2014 | K10 (2014) | Region II | Isabela | 103750 | Casala ES | SAN MARIANO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  | 1086625.62 | COMPLETED | 1 | 2014-11-30 | 2014-11-30 | 020314S00047 | 14BF0047 | 2014-09-09 | 2014-09-21 | 2014-09-22 | 2014-09-26 | 2014-10-03 | A. DE GUIA CONSTRUCTION
2028 | NC 2014 | K10 (2014) | Region II | Isabela | 306137 | Daragutan East NHS | SAN MARIANO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  | 1052901.91 | COMPLETED | 1
2029 | NC 2014 | SHS (2014) | Region II | Isabela | 306137 | Daragutan East NHS | SAN MARIANO | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6379337.6381 |  | 6254499.51 | COMPLETED | 1
2030 | NC 2014 | K10 (2014) | Region II | Isabela | 103735 | Daragutan West PS | SAN MARIANO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  | 1892396.18 | COMPLETED | 1 | 2015-01-01 | 2015-01-01 | 020314S00054 | 14BF0051 | 2014-09-08 | 2014-09-20 | 2014-09-21 | 2014-09-25 | 2014-10-06 | A. DE GUIA CONSTRUCTION
2031 | NC 2014 | K10 (2014) | Region II | Isabela | 103752 | Del Pilar Integrated School | SAN MARIANO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1844740.174 |  | 2657473.98 | COMPLETED | 1 | 2015-11-03 | 2015-10-31 | 020314S00069 | 15BF0059 | 2015-06-06 | 2015-06-22 | 2015-06-24 | 2015-07-15 | 2015-07-24 | SMT CONSTRUCTION
2032 | NC 2014 | K10 (2014) | Region II | Isabela | 306151 | Dicamay IS | SAN MARIANO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  | 1939460.3 | COMPLETED | 1 | 2015-03-25 | 2015-03-25 | 020314S00052 | 14BF0066 | 2014-10-13 | 2014-10-13 | 2014-10-13 | 2014-10-17 | 2014-10-31 | ATLANTIC CONSTRUCTION
2033 | NC 2014 | K10 (2014) | Region II | Isabela | 103513 | Flores ES | NAGUILIAN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  | 2758646.56 | COMPLETED | 1 | 2015-03-03 | 2015-03-03 | 020314S00036 | 14BF0055 | 2014-09-03 | 2014-09-15 | 2014-09-16 | 2014-09-20 | 2014-10-03 | SMT CONSTRUCTION
2034 | NC 2014 | SHS (2014) | Region II | Isabela | 300537 | Gamu Rural School-Main | GAMU | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8294965.051 |  | 8087183.82 | COMPLETED | 1 | 2016-03-15 |  | 020314S00152 | 15BF0103 | 2015-08-17 | 2015-08-14 | 2015-09-30 | 2015-10-05 | 2015-10-12 | JMU CONSTRUCTION
2035 | NC 2014 | K10 (2014) | Region II | Isabela | 103106 | Gomez ES | BENITO SOLIVEN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  | 1926524.7 | COMPLETED | 1 | 2015-01-04 | 2015-01-04 | 020314S00007 | 14BF0053 | 2014-09-07 | 2014-09-19 | 2014-09-20 | 2014-09-24 | 2014-10-07 | A. DE GUIA CONSTRUCTION
2036 | NC 2014 | K10 (2014) | Region II | Isabela | 103514 | La Union ES | NAGUILIAN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2905174.43 |  | 2794142.67 | COMPLETED | 1 | 2015-03-05 | 2015-03-05 | 020314S00021 | 14BF0056 | 2014-09-04 | 2014-09-16 | 2014-09-17 | 2014-09-21 | 2014-10-07 | SMT CONSTRUCTION
2037 | NC 2014 | K10 (2014) | Region II | Isabela | 103758 | Libertad ES | SAN MARIANO | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2925174.43 |  | 2820332.67 | COMPLETED | 1 | 2015-03-02 | 2015-02-28 | 020314S00048 | 14BF0069 | 2014-10-13 | 2014-10-13 | 2014-10-13 | 2014-10-21 | 2014-10-31 | A. DE GUIA CONSTRUCTION
2038 | NC 2014 | SHS (2014) | Region II | Isabela | 300559 | Mabini NHS | GAMU | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6379337.6381 |  | 6247850.01 | COMPLETED | 1 | 2016-02-02 |  | 020314S00151 | 15BF0110 | 2015-08-31 | 2015-09-07 | 2015-09-14 | 2015-09-21 | 2015-09-30 | ROJUNED CONSTRUCTION
2039 | NC 2014 | K10 (2014) | Region II | Isabela | 103738 | Macayucayu ES | SAN MARIANO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  | 1936564.84 | COMPLETED | 1 | 2015-02-11 | 2015-01-11 | 020314S00046 | 14BF0064 | 2014-10-13 | 2014-10-13 | 2014-10-13 | 2014-10-14 | 2014-10-30 | ATLANTIC CONSTRUCTION
2040 | NC 2014 | SHS (2014) | Region II | Isabela | 300513 | Malalinta NHS | SAN MANUEL | 5 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  | 1751125.33 | COMPLETED | 1 | 2015-12-20 | 2015-12-19 | 020314S00149 | 15BF0073 | 2015-06-02 | 2015-06-19 | 2015-08-17 | 2015-08-20 | 2015-09-01 | DANYSONS CONSTRUCTION
2041 | NC 2014 | K10 (2014) | Region II | Isabela | 103759 | Malaya ES (Maldam ES) | SAN MARIANO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1844740.174 |  | 1835516.47 | COMPLETED | 1 | 2015-11-03 | 2015-10-31 | 020314S00070 | 15BF0060 | 2015-06-08 | 2015-06-23 | 2015-06-24 | 2015-07-15 | 2015-07-24 | JMU CONSTRUCTION
2042 | NC 2014 | SHS (2014) | Region II | Isabela | 300561 | Mallig NHS (formerly Mallig NHS - Main) | MALLIG | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8294965.051 |  | 8066832.26 | COMPLETED | 1 | 2016-02-24 |  | 020314S00147 | 15BF0107 | 2015-08-24 | 2015-08-28 | 2015-09-07 | 2015-09-17 | 2015-09-22 | DANYSONS CONSTRUCTION
2043 | NC 2014 | K10 (2014) | Region II | Isabela | 103720 | Mananao ES | SAN MANUEL | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  | 1894993.61 | COMPLETED | 1 | 2015-01-21 | 2015-01-21 | 020314S00045 | 14BF0050 | 2014-09-08 | 2014-09-20 | 2014-09-21 | 2014-09-25 | 2014-10-06 | A. DE GUIA CONSTRUCTION
2044 | NC 2014 | K10 (2014) | Region II | Isabela | 103569 | Mangga ES | QUEZON | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  | 1940443.91 | COMPLETED | 1 | 2015-03-06 | 2015-03-26 | 020314S00042 | 14BF0063 | 2014-10-13 | 2014-10-13 | 2014-10-13 | 2014-10-15 | 2014-10-29 | DANYSONS CONSTRUCTION
2045 | NC 2014 | K10 (2014) | Region II | Isabela | 103760 | Marannao IS | SAN MARIANO | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2905174.43 |  | 2795048.41 | COMPLETED | 1 | 2015-03-03 | 2015-03-03 | 020314S00049 | 14BF0068 | 2014-10-13 | 2014-10-13 | 2014-10-13 | 2014-10-17 | 2014-10-27 | DANYSONS CONSTRUCTION
2046 | NC 2014 | SHS (2014) | Region II | Isabela | 306135 | Matusalem National High School | ROXAS | 5 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  | 1752654.13 | COMPLETED | 1 | 2015-11-20 | 2015-11-19 | 020314S00146 | 15BF0079 | 2015-07-27 | 2015-07-29 | 2015-08-03 | 2015-08-06 | 2015-08-17 | SMT CONSTRUCTION
2047 | NC 2014 | K10 (2014) | Region II | Isabela | 306155 | Minagbag Integrated School | QUEZON | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  | 1899184.68 | COMPLETED | 1 | 2015-01-30 | 2015-02-28 | 020314S00053 | 14BF0048 | 2014-09-09 | 2014-09-21 | 2014-09-22 | 2014-09-24 | 2014-10-03 | DANYSONS CONSTRUCTION
2048 | NC 2014 | SHS (2014) | Region II | Isabela | 306111 | Monico Rarama NHS (Munoz HS -San Pedro Extension) | ROXAS | 5 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  | 1762093.73 | COMPLETED | 1 | 2015-11-09 | 2015-11-08 | 020314S00150 | 15BF0071 | 2015-06-30 | 2015-06-29 | 2015-06-30 | 2015-07-24 | 2015-08-06 | SMT CONSTRUCTION
2049 | NC 2014 | SHS (2014) | Region II | Isabela | 300562 | Munoz HS | ROXAS | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  | 8006021.41 | COMPLETED | 1 | 2016-02-28 |  | 020314S00143 | 15BF0095 | 2015-08-10 | 2015-08-12 | 2015-09-01 | 2015-09-02 | 2015-09-11 | A. DE GUIA CONSTRUCTION
2050 | NC 2014 | K10 (2014) | Region II | Isabela | 103113 | Nacalma ES | BENITO SOLIVEN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  | 1939964.68 | COMPLETED | 1 | 2015-05-25 | 2015-05-24 | 020314S00006 | 14BF0054 | 2014-09-03 | 2014-09-15 | 2014-09-16 | 2014-09-20 | 2014-09-24 | D.S.T. METALCRAFT AND ENGINEERING WORKS
2051 | NC 2014 | SHS (2014) | Region II | Isabela | 300563 | Naguillian National High School | NAGUILIAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  | 8007669.56 | COMPLETED | 1 | 2016-03-15 |  | 020314S00148 | 15BF0098 | 2015-08-17 | 2015-09-10 | 2015-09-30 | 2015-10-07 | 2015-10-12 | R R C CONSTRUCTION
2052 | NC 2014 | K10 (2014) | Region II | Isabela | 103763 | Panninan ES | SAN MARIANO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  | 1977910.55 | COMPLETED | 1 | 2015-02-27 | 2015-02-27 | 020314S00050 | 14BF0067 | 2014-10-13 | 2014-10-13 | 2014-10-13 | 2014-10-17 | 2014-10-31 | DANYSONS CONSTRUCTION
2053 | NC 2014 | K10 (2014) | Region II | Isabela | 103115 | Placer-Dagupan ES | BENITO SOLIVEN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  | 1939715.86 | COMPLETED | 1 | 2015-03-24 | 2015-03-24 | 020314S00009 | 14BF0061 | 2014-10-27 | 2014-11-03 | 2014-11-03 | 2014-11-17 | 2014-12-25 | SMT CONSTRUCTION
2054 | NC 2014 | SHS (2014) | Region II | Isabela | 300568 | Quezon HS - Main | QUEZON | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8314965.051 |  | 8085463.86 | COMPLETED | 1 | 2016-03-05 |  | 020314S00142 | 15BF0104 | 2015-08-24 | 2015-08-26 | 2015-09-07 | 2015-09-14 | 2015-09-22 | DANYSONS CONSTRUCTION
2055 | NC 2014 | SHS (2014) | Region II | Isabela | 300569 | Quirino NHS - Main | QUIRINO | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8294965.051 |  | 8074925.04 | COMPLETED | 1 | 2016-03-05 |  | 020314S00157 | 15BF0106 | 2015-08-24 | 2015-08-25 | 2015-09-07 | 2015-09-15 | 2015-09-22 | 4 As CONSTRUCTION
2056 | NC 2014 | SHS (2014) | Region II | Isabela | 300579 | Roxas NHS-Main | ROXAS | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  | 8006021.41 | COMPLETED | 1 | 2016-02-28 |  | 020314S00137 | 15BF0094 | 2015-08-10 | 2015-08-12 | 2015-09-01 | 2015-09-08 | 2015-09-11 | A. DE GUIA CONSTRUCTION
2057 | NC 2014 | SHS (2014) | Region II | Isabela | 300511 | San Antonino NHS | BURGOS | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8294965.051 |  | 8074474.44 | COMPLETED | 1 | 2016-03-15 |  | 020314S00098 | 15BF0101 | 2015-08-17 | 2015-08-20 | 2015-09-30 | 2015-10-05 | 2015-10-12 | 4 As CONSTRUCTION
2058 | NC 2014 | SHS (2014) | Region II | Isabela | 306110 | San Jose NHS (formerly Mallig HS -San Jose Norte Annex) | MALLIG | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  | 8032916.23 | COMPLETED | 1 | 2016-02-28 |  | 020314S00093 | 15BF0099 | 2015-08-17 | 2015-08-20 | 2015-08-27 | 2015-08-31 | 2015-09-01 | DANYSONS CONSTRUCTION
2059 | NC 2014 | SHS (2014) | Region II | Isabela | 300592 | San Mariano HS - Main | SAN MARIANO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  | 8085286.94 | COMPLETED | 1 | 2016-03-15 |  | 020314S00095 | 15BF0100 | 2015-08-17 | 2015-08-20 | 2015-09-30 | 2015-10-07 | 2015-10-12 | R R C CONSTRUCTION
2060 | NC 2014 | K10 (2014) | Region II | Isabela | 103639 | San Pedro ES-Villa Cocepcion ES Annex - Doña Concha | ROXAS | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  | 2850137.34 | COMPLETED | 1 | 2015-12-15 |  | 020314S00179 | 15BF0087 | 2015-08-03 | 2015-08-10 | 2015-08-17 | 2015-08-28 | 2015-09-01 | SMT CONSTRUCTION
2061 | NC 2014 | SHS (2014) | Region II | Isabela | 300514 | Sandiat NHS | SAN MANUEL | 5 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  | 6198216.86 | COMPLETED | 1 | 2016-02-13 |  | 020314S00091 | 15BF0112 | 2015-08-31 | 2015-09-10 | 2015-09-14 | 2015-09-24 | 2015-09-30 | A. DE GUIA CONSTRUCTION
2062 | NC 2014 | K10 (2014) | Region II | Isabela | 306163 | Simimbaan Integrated School | ROXAS | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  | 1894993.61 | COMPLETED | 1
2063 | NC 2014 | SHS (2014) | Region II | Isabela | 306163 | Simimbaan Integrated School | ROXAS | 5 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  | 1762093.73 | COMPLETED | 1
2064 | NC 2014 | SHS (2014) | Region II | Isabela | 306144 | Sto. Domingo IS | QUIRINO | 5 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  | 1762090.38 | COMPLETED | 1 | 2015-11-26 | 2015-11-25 | 020314S00089 | 15BF0069 | 2015-06-22 | 2015-06-24 | 2015-06-26 | 2015-07-28 | 2015-08-06 | SMT CONSTRUCTION
2065 | NC 2014 | SHS (2014) | Region II | Isabela | 300595 | Ueg NHS (San Mariano HS - Ueg Extension) | SAN MARIANO | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6379337.6381 |  | 6253617.5 | COMPLETED | 1 | 2016-02-02 |  | 020314S00088 | 15BF0108 | 2015-08-31 | 2015-09-08 | 2015-09-14 | 2015-09-17 | 2015-09-30 | E.S. PUA CONSTRUCTION
2066 | NC 2014 | SHS (2014) | Region II | Isabela | 306103 | Villa Cacho Integrated School | QUIRINO | 5 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  | 1760701.65 | COMPLETED | 1 | 2015-11-09 | 2015-10-30 | 020314S00087 | 15BF0070 | 2015-06-22 | 2015-06-24 | 2015-06-25 | 2015-07-24 | 2015-08-06 | JMU CONSTRUCTION
2067 | NC 2014 | K10 (2014) | Region II | Isabela | 103767 | Villa Miranda ES | SAN MARIANO | 5 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2670828.124 |  | 1835516.47 | COMPLETED | 1 | 2015-12-03 | 2015-10-31 | 020314S00071 | 15BF0061 | 2015-06-08 | 2015-06-23 | 2015-06-24 | 2015-07-15 | 2015-07-24 | SMT CONSTRUCTION
2068 | NC 2014 | SHS (2014) | Region II | Isabela | 300500 | Alicia National High School | ALICIA | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1
2069 | NC 2014 | SHS (2014) | Region II | Isabela | 300499 | Alicia Vocational School | ALICIA | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1 | 2016-01-26 |  | 020314S00086 | 15BG0057 | 2015-08-11 | 2015-08-14 | 2015-08-26 | 2015-08-28 | 2015-09-03 | ASIAN PEARL CONSTRUCTION & DEVT. CORP.
2070 | NC 2014 | SHS (2014) | Region II | Isabela | 300501 | Angadanan HS | ANGADANAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 | 2016-01-26 |  | 020314S00138 | 15BG0059 | 2015-08-11 | 2015-08-14 | 2015-08-26 | 2015-08-28 | 2015-09-03 | ASIAN PEARL CONSTRUCTION & DEVT. CORP.
2071 | NC 2014 | K10 (2014) | Region II | Isabela | 103484 | Bustamante ES | LUNA | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-23 | 2014-10-15 | 020314S00024 | 14BG0023 | 2014-07-03 | 2014-07-04 | 2014-08-20 | 2014-08-25 | 2014-09-18 | META CONSTRUCTION
2072 | NC 2014 | SHS (2014) | Region II | Isabela | 300504 | Cabatuan NHS | CABATUAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-19 |  | 020314S00085 | 15BG0047 | 2015-07-23 | 2015-07-27 | 2015-08-07 | 2015-08-12 | 2015-08-17 | MAR-DEB CONSTRUCTION & DEVELOPMENT
2073 | NC 2014 | SHS (2014) | Region II | Isabela | 300506 | Cadaloria HS | ANGADANAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8394965.051 |  |  | COMPLETED | 1 | 2016-01-15 |  | 020314S00084 | 15BG0067 | 2015-08-11 | 2015-08-14 | 2015-08-26 | 2015-08-28 | 2015-09-02 | A. DE GUIA CONSTRUCTION
2074 | NC 2014 | K10 (2014) | Region II | Isabela | 103680 | Dipacamo ES | SAN GUILLERMO | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-10-12 | 2014-11-10 | 020314S00025 | 14BG0017 | 2014-06-26 | 2014-06-27 | 2014-07-11 | 2014-07-16 | 2014-07-21 | R TWO S BUILDERS AND ENTERPRISE
2075 | NC 2014 | K10 (2014) | Region II | Isabela | 103683 | Guam ES | SAN GUILLERMO | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2014-11-26 | 2014-11-26 | 020314S00026 | 14BG0018 | 2014-06-26 | 2014-06-27 | 2014-07-11 | 2014-07-16 | 2014-07-21 | R TWO S BUILDERS AND ENTERPRISE
2076 | NC 2014 | K10 (2014) | Region II | Isabela | 103061 | Ingud-Ramona Integrated School | ANGADANAN | 3 | 1 | 6 | 2sty6cl | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 020314S00172 | 15BG0045 | 2015-08-14 | 2015-08-14 | 2015-08-25 | 2015-08-27 | 2015-08-28 | META CONSTRUCTION
2077 | NC 2014 | SHS (2014) | Region II | Isabela | 306114 | La Paz NHS (Cabatuan NHS - La Paz Annex) | CABATUAN | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-15 |  | 020314S00074 | 15BG0060 | 2015-08-09 | 2015-08-13 | 2015-08-24 | 2015-08-27 | 2015-09-02 | R TWO S BUILDERS AND ENTERPRISE
2078 | NC 2014 | SHS (2014) | Region II | Isabela | 306115 | Luis-Fe Gomez Diamantina NHS | CABATUAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 | 2016-01-25 |  | 020314S00075 | 15BG0050 | 2015-08-10 | 2015-08-13 | 2015-08-25 | 2015-08-28 | 2015-09-02 | MAR-DEB CONSTRUCTION & DEVELOPMENT
2079 | NC 2014 | SHS (2014) | Region II | Isabela | 306150 | Luna General Comprehensive High School (formerly Luna NHS-Mambabanga Annex) | LUNA | 5 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-15 |  | 020314S00076 | 15BG0061 | 2015-08-03 | 2015-08-13 | 2015-08-24 | 2015-08-27 | 2015-09-02 | MAR-DEB CONSTRUCTION & DEVELOPMENT
2080 | NC 2014 | SHS (2014) | Region II | Isabela | 300558 | Luna NHS | LUNA | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 | 2016-01-25 |  | 020314S00077 | 15BG0052 | 2015-08-10 | 2015-08-13 | 2015-08-25 | 2015-08-28 | 2015-09-02 | MAR-DEB CONSTRUCTION & DEVELOPMENT
2081 | NC 2014 | SHS (2014) | Region II | Isabela | 300565 | Palayan Region HS | ALICIA | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 020314S00078 | 15BG0041 | 2015-08-14 | 2015-08-14 | 2015-08-25 | 2015-08-27 | 2015-08-28 | ASIAN PEARL CONSTRUCTION & DEVT. CORP.
2082 | NC 2014 | K10 (2014) | Region II | Isabela | 103686 | Progreso ES | SAN GUILLERMO | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2060417.57 |  |  | COMPLETED | 1 | 2014-11-26 | 2014-11-26 | 020314S00027 | 14BG0016 | 2014-06-26 | 2014-06-27 | 2014-07-11 | 2014-07-16 | 2014-07-21 | R TWO S BUILDERS AND ENTERPRISE
2083 | NC 2014 | SHS (2014) | Region II | Isabela | 300575 | Reina Mercedes Vocational and Industrial School | REINA MERCEDES | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-19 |  | 020314S00079 | 15BG0043 | 2015-07-23 | 2015-07-27 | 2015-08-07 | 2015-08-12 | 2015-08-17 | META CONSTRUCTION
2084 | NC 2014 | SHS (2014) | Region II | Isabela | 306116 | Reina Mercedes Vocational High School | REINA MERCEDES | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6359337.6381 |  |  | COMPLETED | 1 | 2016-01-15 |  | 020314S00080 | 15BG0063 | 2015-08-09 | 2015-08-13 | 2015-08-24 | 2015-08-27 | 2015-09-02 | META CONSTRUCTION
2085 | NC 2014 | SHS (2014) | Region II | Isabela | 300577 | Rizal Integrated School, San Guillermo | SAN GUILLERMO | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 | 2016-01-25 |  | 020314S00081 | 15BG0062 | 2015-08-09 | 2015-08-13 | 2015-08-24 | 2015-08-27 | 2015-09-02 | D.S.T. METALCRAFT AND ENGINEERING WORKS
2086 | NC 2014 | SHS (2014) | Region II | Isabela | 300576 | Rizal Region NHS , Alicia, Isabela | ALICIA | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 | 2016-01-25 |  | 020314S00083 | 15BG0051 | 2015-08-10 | 2015-08-13 | 2015-08-25 | 2015-08-28 | 2015-09-02 | ASIAN PEARL CONSTRUCTION & DEVT. CORP.
2087 | NC 2014 | SHS (2014) | Region II | Isabela | 300581 | Salinungan NHS | SAN MATEO | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-19 |  | 020314S00082 | 15BG0048 | 2015-07-23 | 2015-07-27 | 2015-08-07 | 2015-08-12 | 2015-08-17 | MAR-DEB CONSTRUCTION & DEVELOPMENT
2088 | NC 2014 | K10 (2014) | Region II | Isabela | 102998 | Salvacion ES | ALICIA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-10-14 | 2014-10-12 | 020314S00029 | 14BG0021 | 2014-07-03 | 2014-07-04 | 2014-07-18 | 2014-07-23 | 2014-07-28 | R TWO S BUILDERS AND ENTERPRISE
2089 | NC 2014 | K10 (2014) | Region II | Isabela | 103000 | San Fernando ES | ALICIA | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1
2090 | NC 2014 | K10 (2014) | Region II | Isabela | 103000 | San Fernando ES | ALICIA | 3 |  | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1
2091 | NC 2014 | SHS (2014) | Region II | Isabela | 300590 | San Guillermo Voc'l & Ind'l High Sch. | SAN GUILLERMO | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1 | 2016-01-25 |  | 020314S00092 | 15BG0068 | 2015-08-11 | 2015-08-14 | 2015-08-26 | 2015-08-28 | 2015-09-02 | O.U.A. CONSTRUCTION
2092 | NC 2014 | SHS (2014) | Region II | Isabela | 300596 | San Mateo Voc'l. & Industrial High School-Main | SAN MATEO | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-19 |  | 020314S00107 | 15BG0045 | 2015-07-23 | 2015-07-27 | 2015-08-07 | 2015-08-12 | 2015-08-17 | META CONSTRUCTION
2093 | NC 2014 | SHS (2014) | Region II | Isabela | 300607 | Sto. Niño Integrated School | ANGADANAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 | 2016-01-26 |  | 020314S00116 | 15BG0058 | 2015-08-11 | 2015-08-14 | 2015-08-26 | 2015-08-28 | 2015-09-03 | EDISON DEVELOPMENT CONSTRUCTION
2094 | NC 2014 | K10 (2014) | Region II | Isabela | 103696 | Villa Rose ES | SAN GUILLERMO | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2060417.57 |  |  | COMPLETED | 1 | 2014-10-27 | 2014-11-26 | 020314S00028 | 14BG0015 | 2014-06-26 | 2014-06-27 | 2014-07-11 | 2014-07-16 | 2014-07-21 | R TWO S BUILDERS AND ENTERPRISE
2095 | NC 2014 | K10 (2014) | Region II | Isabela | 306119 | Addalam Region HS - Divinan Annex | JONES | 4 | 1 | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-05 |  | 020314S00170 | 15bh0061 | 2015-07-30 | 2015-08-04 | 2015-08-18 | 2015-08-27 | 2015-09-03 | SHANLEY CONSTRUCTION
2096 | NC 2014 | K10 (2014) | Region II | Isabela | 300498 | Addalam Region HS - Main | JONES | 4 | 1 | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-05 |  | 020314S00169 | 15bh0060 | 2015-07-30 | 2015-08-04 | 2015-08-18 | 2015-08-27 | 2015-09-03 | H.T.L. CONSTRUCTION
2097 | NC 2014 | K10 (2014) | Region II | Isabela | 103242 | Aguinaldo ES | CORDON | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-01 | 2014-12-31 | 020314S00031 | 14bh0041 | 2014-09-08 | 2014-09-10 | 2014-09-22 | 2014-10-20 | 2014-10-29 | V.B. MANUBAY CONSTRUCTION
2098 | NC 2014 | K10 (2014) | Region II | Isabela | 103249 | Dallao ES | CORDON | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2015-01-01 | 2014-12-31 | 020314S00038 | 14bh0042 | 2014-09-08 | 2014-09-10 | 2014-09-22 | 2014-10-20 | 2014-10-29 | V.B. MANUBAY CONSTRUCTION
2099 | NC 2014 | SHS (2014) | Region II | Isabela | 300523 | Diadi Region HS | CORDON | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6359337.6381 |  |  | COMPLETED | 1 | 2016-02-05 |  | 020314S00115 | 15bh0057 | 2015-07-30 | 2015-08-04 | 2015-08-18 | 2015-08-27 | 2015-09-03 | MAR-DEB CONSTRUCTION & DEVELOPMENT
2100 | NC 2014 | K10 (2014) | Region II | Isabela | 103551 | Dinapigue ES | DINAPIGUE | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2045417.57 |  |  | COMPLETED | 1 | 2015-01-01 | 2015-01-01 | 020314S00032 | 14bh0049 | 2014-09-08 | 2014-09-10 | 2014-09-22 | 2014-10-20 | 2014-10-29 | META CONSTRUCTION
2101 | NC 2014 | SHS (2014) | Region II | Isabela | 300526 | Dinapigue NHS | DINAPIGUE | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 | 2016-02-05 |  | 020314S00114 | 15bh0071 | 2015-07-30 | 2015-08-04 | 2015-08-18 | 2015-08-27 | 2015-09-03 | R.S. SEPIAN CONSTRUCTION & TRUCKING
2102 | NC 2014 | SHS (2014) | Region II | Isabela | 300532 | Dona Josefa E. Marcos HS | CORDON | 4 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-31 | 2015-12-31 | 020314S00113 | 15bh0030 | 2015-07-21 | 2015-07-28 | 2015-08-11 | 2015-08-18 | 2015-08-28 | MAR-DEB CONSTRUCTION & DEVELOPMENT
2103 | NC 2014 | SHS (2014) | Region II | Isabela | 300533 | DOÑA MAGDALENA H. GAFFUD HIGH SCHOOL | ECHAGUE | 6 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-05 |  | 020314S00112 | 15bh0058 | 2015-07-30 | 2015-08-04 | 2015-08-18 | 2015-08-27 | 2015-09-03 | ERIC VAN P. SESBRENO CONSTRUCTION
2104 | NC 2014 | SHS (2014) | Region II | Isabela | 300612 | Echague National High School | ECHAGUE | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-05 |  | 020314S00111 | 15bh0067 | 2015-07-30 | 2015-08-04 | 2015-08-18 | 2015-08-27 | 2015-09-03 | META CONSTRUCTION
2105 | NC 2014 | SHS (2014) | Region II | Isabela | 300572 | Gen. Emilio Aguinaldo NHS | RAMON | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 | 2016-02-05 |  | 020314S00110 | 15bh0070 | 2015-07-30 | 2015-08-04 | 2015-08-18 | 2015-08-27 | 2015-09-03 | ISABELA EBC BUILDERS CONSTRUCTION, INC. (FORMERLY
2106 | NC 2014 | SHS (2014) | Region II | Isabela | 300539 | Highway Region NHS | ECHAGUE | 6 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-31 |  | 020314S00109 | 15bh0032 | 2015-07-21 | 2015-07-28 | 2015-08-11 | 2015-08-18 | 2015-08-28 | META CONSTRUCTION
2107 | NC 2014 | SHS (2014) | Region II | Isabela | 300541 | Imelda Marcos HS | ECHAGUE | 6 | 1 | 4 | 1STY4CL | 2014 SHS BATCH 1 | 3504886.575 |  |  | COMPLETED | 1 | 2015-12-31 | 2015-12-31 | 020314S00105 | 15bh0034 | 2015-07-21 | 2015-07-28 | 2015-08-11 | 2015-08-20 | 2015-09-01 | JMD-68 BUILDERS
2108 | NC 2014 | K10 (2014) | Region II | Isabela | 103602 | Oscariz ES | RAMON | 4 | 1 | 5 | 1STY5CL (Toilet Attached) | 2014 K10 BATCH 4C | 4673636.82 |  |  | COMPLETED | 1 | 2015-12-31 | 2015-11-18 | 020314S00168 | 15bh0041 | 2015-07-21 | 2015-07-28 | 2015-08-11 | 2015-08-18 | 2015-08-28 | MAR-DEB CONSTRUCTION & DEVELOPMENT
2109 | NC 2014 | SHS (2014) | Region II | Isabela | 300566 | Pangal Sur HS | ECHAGUE | 6 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-31 |  | 020314S00096 | 15bh0033 | 2015-07-21 | 2015-07-28 | 2015-08-11 | 2015-08-18 | 2015-08-28 | C.D.J. BUILDERS & CONSTRUCTION SUPPLIES
2110 | NC 2014 | K10 (2014) | Region II | Isabela | 103452 | Papan ES | JONES | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-12-31 |  | 020314S00167 | 15bh0040 | 2015-07-21 | 2015-07-28 | 2015-08-11 | 2015-08-18 | 2015-08-28 | ISABELA EBC BUILDERS CONSTRUCTION, INC. (FORMERLY
2111 | NC 2014 | K10 (2014) | Region II | Isabela | 103605 | Planas ES | RAMON | 4 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 4B | 4455568.2979 |  |  | COMPLETED | 1 | 2016-01-04 |  | 020314S00072 | 15bh0048 | 2015-07-21 | 2015-07-28 | 2015-08-11 | 2015-08-20 | 2015-09-01 | SHANLEY CONSTRUCTION
2112 | NC 2014 | SHS (2014) | Region II | Isabela | 300574 | Raniag HS | RAMON | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8244965.051 |  |  | COMPLETED | 1 | 2016-02-05 |  | 020314S00094 | 15bh0069 | 2015-07-30 | 2015-08-04 | 2015-08-18 | 2015-08-27 | 2015-09-03 | META CONSTRUCTION
2113 | NC 2014 | K10 (2014) | Region II | Isabela | 103299 | Salvacion PS | ECHAGUE | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2045417.57 |  |  | COMPLETED | 1 | 2015-01-24 | 2015-01-21 | 020314S00043 | 14bh0047 | 2014-09-08 | 2014-09-10 | 2014-09-22 | 2014-10-13 | 2014-10-22 | JONATHAN M. GADDI CONSTRUCTION
2114 | NC 2014 | SHS (2014) | Region II | Isabela | 300582 | San Agustin NHS | SAN AGUSTIN | 4 | 1 | 4 | 1STY4CL | 2014 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1 | 2015-12-31 |  | 020314S00106 | 15bh0036 | 2015-07-21 | 2015-07-28 | 2015-08-11 | 2015-08-20 | 2015-08-28 | JMD-68 BUILDERS
2115 | NC 2014 | K10 (2014) | Region II | Isabela | 103317 | San Antonio ES | ECHAGUE | 6 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 928654.4916 |  |  | COMPLETED | 1 | 2015-04-02 | 2015-04-02 | 020314S00059 | 14bh0110 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2014-12-19 | 2015-01-28 | C.D.J. BUILDERS & CONSTRUCTION SUPPLIES
2116 | NC 2014 | K10 (2014) | Region II | Isabela | 103318 | San Carlos ES | ECHAGUE | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-25 | 020314S00030 | 14bh0046a | 2014-09-08 | 2014-09-10 | 2014-09-22 | 2014-10-13 | 2014-10-22 | META CONSTRUCTION
2117 | NC 2014 | SHS (2014) | Region II | Isabela | 300591 | San Isidro NHS | SAN ISIDRO | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-05 |  | 020314S00117 | 15bh0066 | 2015-07-30 | 2015-08-04 | 2015-08-18 | 2015-08-27 | 2015-09-03 | MAR-DEB CONSTRUCTION & DEVELOPMENT
2118 | NC 2014 | K10 (2014) | Region II | Isabela | 103300 | San Miguel ES | ECHAGUE | 6 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-12-31 |  | 020314S00165 | 15bh0039 | 2015-07-21 | 2015-07-28 | 2015-08-11 | 2015-08-18 | 2015-08-28 | SHANLEY CONSTRUCTION
2119 | NC 2014 | K10 (2014) | Region II | Isabela | 306159 | San Miguel Integrated School | RAMON | 4 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
2120 | NC 2014 | SHS (2014) | Region II | Isabela | 306159 | San Miguel Integrated School | RAMON | 4 | 1 | 4 | 1STY4CL | 2014 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1
2121 | NC 2014 | SHS (2014) | Region II | Isabela | 306142 | San Sebastian Integrated School | RAMON | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-05 |  | 020314S00103 | 15bh0059 | 2015-07-30 | 2015-08-04 | 2015-08-18 | 2015-08-27 | 2015-09-03 | META CONSTRUCTION
2122 | NC 2014 | K10 (2014) | Region II | Isabela | 103323 | Sta. Ana ES | ECHAGUE | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-02 | 2014-12-31 | 020314S00023 | 14bh0048 | 2014-09-08 | 2014-09-10 | 2014-09-22 | 2014-10-23 | 2014-11-03 | META CONSTRUCTION
2123 | NC 2014 | SHS (2014) | Region II | Isabela | 300611 | Ugad HS | ECHAGUE | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-05 |  | 020314S00102 | 15bh0068 | 2015-07-30 | 2015-08-04 | 2015-08-18 | 2015-08-27 | 2015-09-03 | META CONSTRUCTION
2124 | NC 2014 | K10 (2014) | Region II | Isabela | 103326 | Villa Fermin ES | Echague South | 6 | 1 | 5 | 1STY5CL (Toilet Attached) | 2014 K10 BATCH 4C | 4673636.82 |  |  | COMPLETED | 1 | 2015-12-31 | 2015-12-31 | 020314S00166 | 15bh0042 | 2015-07-21 | 2015-07-28 | 2015-08-11 | 2015-08-18 | 2015-08-28 | META CONSTRUCTION
2125 | NC 2014 | K10 (2014) | Region II | Isabela | 103614 | Villa Marcos ES | RAMON | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-01 | 2014-12-31 | 020314S00033 | 14bh0044 | 2014-09-08 | 2014-09-10 | 2014-09-22 | 2014-10-20 | 2014-10-29 | MAR-DEB CONSTRUCTION & DEVELOPMENT
2126 | NC 2014 | SHS (2014) | Region II | Isabela | 306128 | Wigan Integrated School | CORDON | 4 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-31 | 2015-12-31 | 020314S00101 | 15bh0031 | 2015-07-21 | 2015-07-28 | 2015-08-11 | 2015-08-18 | 2015-08-28 | META CONSTRUCTION
2127 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104056 | Abaca ES | DUPAX DEL SUR | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2014-11-11 | 2014-11-11 | 020414S00025 | 14BJ0046 | 2014-06-18 | 2014-06-18 | 2014-06-30 | 2014-07-03 | 2014-07-08 | E.M. BAYATAN CONSTRUCTION
2128 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104187 | Abuyo ES | ALFONSO CASTAÑEDA | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-12-24 | 2015-12-24 | 020414S00076 | 15BJ0064 | 2015-07-28 | 2015-07-29 | 2015-08-11 | 2015-08-14 | 2015-08-19 | DENISSE-JOHN CONSTRUCTION AND SUPPLIES
2129 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300615 | Alfonso Castañeda NHS | ALFONSO CASTAÑEDA | 0 | 1 | 6 | 1STY6CL | 2014 SHS BATCH 1 | 5336910.09 |  |  | COMPLETED | 1 | 2015-12-24 | 2015-11-30 | 020414S00052 | 15BJ0031 | 2015-07-28 | 2015-07-29 | 2015-08-11 | 2015-08-14 | 2015-08-19 | DENISSE-JOHN CONSTRUCTION AND SUPPLIES
2130 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300617 | Ambaguio NHS | AMBAGUIO | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1 | 2016-02-12 |  | 020414S00053 | 15BI0051 | 2015-08-18 | 2015-08-06 | 2015-08-18 | 2015-08-24 | 2015-08-27 | E.M. BAYATAN CONSTRUCTION
2131 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 103981 | Ammococan ES | BAYOMBONG (Capital) | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 020414S00013 | 14BI0028 | 2014-07-31 | 2014-07-18 | 2014-07-31 | 2014-08-19 | 2014-08-28 | JJA CONSTRUCTION & SUPPLY
2132 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300618 | Aritao HS | ARITAO | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8864965.051 |  |  | COMPLETED | 1 | 2015-12-28 |  | 020414S00054 | 15BJ0052 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-21 | 2015-07-24 | TRIPLE P CONSTRUCTION
2133 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104190 | Bacneng ES | SANTA FE | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-10-12 | 2014-09-23 | 020414S00002 | 14BJ0044 | 2014-06-18 | 2014-06-18 | 2014-06-30 | 2014-07-03 | 2014-07-08 | TRIPLE AE CONSTRUCTION
2134 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300619 | Bagabag NHS | BAGABAG | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8244965.051 |  |  | COMPLETED | 1 | 2016-02-13 |  | 020414S00055 | 15BI0052 | 2015-08-18 | 2015-08-06 | 2015-08-18 | 2015-08-26 | 2015-08-27 | TRIPLE P CONSTRUCTION
2135 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104176 | Baguingey ES | SOLANO | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-11-21 | 020414S00011 | 14BI0025 | 2014-07-31 | 2014-07-18 | 2014-07-31 | 2014-08-19 | 2014-08-28 | JANN-NORRIS CONSTRUCTION AND SUPPLIES
2136 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 103983 | Balong ES | AMBAGUIO | 0 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3559886.575 |  |  | COMPLETED | 1 | 2016-03-30 |  | 020414S00032 | 15BI0066 | 2015-09-15 | 2015-09-03 | 2015-09-15 | 2015-09-23 | 2015-09-29 | E S DE GUZMAN CONSTRUCTION
2137 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300620 | Bambang NHS | BAMBANG | 0 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10617131.51 |  |  | COMPLETED | 1 | 2016-03-11 |  | 020414S00062 | 15BI0058 | 2015-08-18 | 2015-08-06 | 2015-08-18 | 2015-08-26 | 2015-08-27 | C.D.J. BUILDERS & CONSTRUCTION SUPPLIES
2138 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104165 | Bangar ES | SOLANO | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-12-02 | 2014-11-20 | 020414S00014 | 14BI0024 | 2014-07-31 | 2014-07-18 | 2014-07-31 | 2014-08-19 | 2014-08-28 | JANN-NORRIS CONSTRUCTION AND SUPPLIES
2139 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104148 | Baresbes ES | QUEZON | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 020414S00030 | 14BI0029 | 2014-07-31 | 2014-07-18 | 2014-07-31 | 2014-08-19 | 2014-08-28 | EDWIN ERWIN SISON CONSTRUCTION
2140 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300621 | Bascaran NHS | SOLANO | 0 | 1 | 4 | 1STY4CL | 2014 SHS BATCH 1 | 3494886.575 |  |  | COMPLETED | 1 | 2015-12-28 | 2015-12-28 | 020414S00056 | 15BI0045 | 2015-07-30 | 2015-07-17 | 2015-07-30 | 2015-08-13 | 2015-08-27 | JANN-NORRIS CONSTRUCTION AND SUPPLIES
2141 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 103984 | Bayombong CS | BAYOMBONG (Capital) | 0 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3860805.49 |  |  | COMPLETED | 1 | 2015-01-16 | 2014-12-16 | 020414S00020 | 14BI0035 | 2014-08-12 | 2014-08-01 | 2014-08-12 | 2014-08-22 | 2014-09-02 | EDWIN ERWIN SISON CONSTRUCTION
2142 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 103985 | Bayombong South ES | BAYOMBONG (Capital) | 0 | 1 | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-31 |  | 020414S00073 | 15BI0057 | 2015-08-18 | 2015-08-06 | 2015-08-18 | 2015-08-26 | 2015-08-27 | JOVIC CONSTRUCTION AND SUPPLY
2143 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300622 | Belance HS | DUPAX DEL NORTE | 0 | 1 | 6 | 1STY6CL | 2014 SHS BATCH 1 | 5286910.09 |  |  | COMPLETED | 1 | 2015-11-26 | 2015-11-26 | 020414S00049 | 15BJ0030 | 2015-06-30 | 2015-07-01 | 2015-07-14 | 2015-07-17 | 2015-07-22 | MIGHTY CONSTRUCTION & SUPPLY
2144 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 306201 | Binalian Integrated School | KAYAPA | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-25 |  | 020414S00034 | 15BJ0039 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-21 | 2015-07-24 | E.M. BAYATAN CONSTRUCTION
2145 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104078 | Biyoy ES | KASIBU | 0 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3880805.49 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-11-30 | 020414S00018 | 14BJ0052 | 2014-06-18 | 2014-06-18 | 2014-06-30 | 2014-07-03 | 2014-07-08 | E.M. BAYATAN CONSTRUCTION
2146 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 306202 | Bonfal National High School | BAYOMBONG (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 | 2016-02-13 |  | 020414S00057 | 15BI0053 | 2015-08-18 | 2015-08-06 | 2015-08-18 | 2015-08-26 | 2015-08-27 | TRIPLE P CONSTRUCTION
2147 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104005 | Bonfal West ES | BAYOMBONG (Capital) | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-10-28 | 2014-10-18 | 020414S00028 | 14BI0027 | 2014-07-31 | 2014-07-18 | 2014-07-31 | 2014-08-19 | 2014-08-28 | Q.C.D. CONSTRUCTION AND SUPPLY
2148 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300624 | Bugkalot NHS | DUPAX DEL NORTE | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-28 | 2015-12-28 | 020414S00033 | 15BJ0040 | 2015-07-16 | 2015-07-03 | 2015-07-16 | 2015-07-21 | 2015-07-24 | JOVIC CONSTRUCTION AND SUPPLY
2149 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104018 | Bugnay ES | DIADI | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-07 | 2014-12-02 | 020414S00022 | 14BI0022 | 2014-07-31 | 2014-07-18 | 2014-07-31 | 2014-08-19 | 2014-08-28 | EDWIN ERWIN SISON CONSTRUCTION
2150 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104040 | Bulala ES | DUPAX DEL NORTE | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-11-11 | 2014-11-11 | 020414S00024 | 14BJ0045 | 2014-06-18 | 2014-06-18 | 2014-06-30 | 2014-07-03 | 2014-07-08 | TRIPLE AE CONSTRUCTION
2151 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104059 | Canabay ES | DUPAX DEL SUR | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-10-12 | 2014-10-12 | 020414S00026 | 14BJ0043 | 2014-06-18 | 2014-06-18 | 2014-06-30 | 2014-07-03 | 2014-07-08 | JANN-NORRIS CONSTRUCTION AND SUPPLIES
2152 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104081 | Capisaan E/S | KASIBU | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2090417.57 |  |  | COMPLETED | 1 | 2014-11-11 | 2014-11-11 | 020414S00012 | 14BJ0051 | 2014-06-18 | 2014-06-18 | 2014-06-30 | 2014-07-03 | 2014-07-08 | DENISSE-JOHN CONSTRUCTION AND SUPPLIES
2153 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300625 | Carolotan High School | DUPAX DEL SUR | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-28 | 2015-11-28 | 020414S00039 | 15BJ0038 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-21 | 2015-07-24 | MIGHTY CONSTRUCTION & SUPPLY
2154 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300616 | Casecnan National High School | ALFONSO CASTAÑEDA | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-28 | 2015-11-28 | 020414S00040 | 15BJ0037 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-21 | 2015-07-24 | DENISSE-JOHN CONSTRUCTION AND SUPPLIES
2155 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104061 | Castro ES | DUPAX DEL SUR | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2014-11-11 | 2014-11-11 | 020414S00027 | 14BJ0047 | 2014-06-18 | 2014-06-18 | 2014-06-30 | 2014-07-03 | 2014-07-08 | E.M. BAYATAN CONSTRUCTION
2156 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 103955 | Cawacao Elementary School | BAMBANG | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-12-02 | 2014-12-02 | 020414S00015 | 14BI0026 | 2014-07-31 | 2014-07-18 | 2014-07-31 | 2014-08-19 | 2014-08-28 | JANN-NORRIS CONSTRUCTION AND SUPPLIES
2157 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104083 | Cordon ES | KASIBU | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-10-12 | 2014-10-12 | 020414S00004 | 14BJ0038 | 2014-06-18 | 2014-06-18 | 2014-06-30 | 2014-07-03 | 2014-07-08 | E S DE GUZMAN CONSTRUCTION
2158 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104168 | Curifang ES | SOLANO | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-10-29 | 2015-10-29 | 020414S00031 | 15BI0046 | 2015-07-30 | 2015-07-17 | 2015-07-30 | 2015-08-13 | 2015-08-24 | EDWIN ERWIN SISON CONSTRUCTION
2159 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 306203 | Dagupan Integrated School | QUEZON | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-05 | 2015-11-05 | 020414S00070 | 15BI0011 | 2015-06-30 | 2015-06-18 | 2015-06-30 | 2015-07-14 | 2015-07-23 | ERIC VAN P. SESBRENO CONSTRUCTION
2160 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300627 | Diadi NHS | DIADI | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 | 2016-03-29 |  | 020414S00058 | 15BI0054 | 2015-08-18 | 2015-08-06 | 2015-08-18 | 2015-08-26 | 2015-08-27 | ERIC VAN P. SESBRENO CONSTRUCTION
2161 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104084 | Didipio ES | KASIBU | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2014-10-12 | 2014-10-12 | 020414S00001 | 14BJ0039 | 2014-06-18 | 2014-06-18 | 2014-06-30 | 2014-07-03 | 2014-07-08 | TRIPLE AE CONSTRUCTION
2162 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104085 | Dine ES | KASIBU | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-10-12 | 2014-10-12 | 020414S00005 | 14BJ0036 | 2014-06-18 | 2014-06-18 | 2014-06-30 | 2014-07-03 | 2014-07-08 | E.M. BAYATAN CONSTRUCTION
2163 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104086 | Domang ES | KASIBU | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-10-12 | 2014-10-12 | 020414S00006 | 14BJ0037 | 2014-06-18 | 2014-06-18 | 2014-06-30 | 2014-07-03 | 2014-07-08 | E S DE GUZMAN CONSTRUCTION
2164 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 306206 | DUPAX DEL NORTE NATIONAL HIGH SCHOOL-ANNEX | DUPAX DEL NORTE | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 | 2016-01-02 |  | 020414S00064 | 15BJ0059 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-24 | 2015-07-29 | DENISSE-JOHN CONSTRUCTION AND SUPPLIES
2165 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300635 | Dupax del Norte NHS | DUPAX DEL NORTE | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6544337.6381 |  |  | COMPLETED | 1 | 2016-01-02 |  | 020414S00047 | 15BJ0058 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-24 | 2015-07-29 | Q.C.D. CONSTRUCTION AND SUPPLY
2166 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300628 | Dupax del Sur NHS | DUPAX DEL SUR | 0 | 1 | 4 | 1STY4CL | 2014 SHS BATCH 1 | 3514886.575 |  |  | COMPLETED | 1 | 2015-11-26 | 2015-11-26 | 020414S00068 | 15BJ0036 | 2015-06-30 | 2015-07-01 | 2015-07-14 | 2015-07-17 | 2015-07-22 | TRIPLE P CONSTRUCTION
2167 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 306208 | Eastern Nueva Vizcaya National High School | KASIBU | 0 | 1 | 6 | 1STY6CL | 2014 SHS BATCH 1 | 5386910.09 |  |  | COMPLETED | 1 | 2016-01-27 | 2015-11-30 | 020414S00050 | 15BJ0033 | 2015-09-01 | 2015-09-02 | 2015-09-15 | 2015-09-18 | 2015-09-23 | E S DE GUZMAN CONSTRUCTION
2168 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104063 | Ecameging ES | DUPAX DEL SUR | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-23 |  | 020414S00075 | 15BJ0063 | 2015-07-28 | 2015-07-29 | 2015-08-11 | 2015-08-14 | 2015-08-19 | JOVIC CONSTRUCTION AND SUPPLY
2169 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300629 | Ganao National HS | DUPAX DEL SUR | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-28 | 2015-10-15 | 020414S00041 | 15BJ0044 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-21 | 2015-07-24 | TRIPLE P CONSTRUCTION
2170 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300631 | Kasibu Nat'l. Agr'l. School | KASIBU | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 | 2016-02-24 |  | 020414S00067 | 15BJ0055 | 2015-06-30 | 2015-07-03 | 2015-07-16 | 2015-07-21 | 2015-07-24 | E S DE GUZMAN CONSTRUCTION
2171 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300632 | Kayapa HS | KAYAPA | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8339965.051 |  |  | COMPLETED | 1 | 2015-12-28 | 2015-12-28 | 020414S00066 | 15BJ0054 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-21 | 2015-07-24 | E S DE GUZMAN CONSTRUCTION
2172 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104125 | Kayapa Proper ES | KAYAPA | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2014-11-11 | 2014-11-11 | 020414S00010 | 14BJ0049 | 2014-06-18 | 2014-06-18 | 2014-06-30 | 2014-07-03 | 2014-07-08 | MIGHTY CONSTRUCTION & SUPPLY
2173 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300634 | Kongkong Valley NHS | KASIBU | 0 | 1 | 6 | 1STY6CL | 2014 SHS BATCH 1 | 5336910.09 |  |  | COMPLETED | 1 | 2015-11-26 | 2015-11-26 | 020414S00065 | 15BJ0035 | 2015-06-30 | 2015-07-01 | 2015-07-14 | 2015-07-17 | 2015-07-22 | E S DE GUZMAN CONSTRUCTION
2174 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 103991 | Labang ES | AMBAGUIO | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2014-12-27 | 2014-12-17 | 020414S00016 | 14BI0020 | 2014-07-31 | 2014-07-18 | 2014-07-31 | 2014-08-19 | 2014-08-28 | EDWIN ERWIN SISON CONSTRUCTION
2175 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104091 | Lupa ES | KASIBU | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2014-10-12 | 2014-10-12 | 020414S00007 | 14BJ0041 | 2014-06-18 | 2014-06-18 | 2014-06-30 | 2014-07-03 | 2014-07-08 | MIGHTY CONSTRUCTION & SUPPLY
2176 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104092 | Macalong ES | KASIBU | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2014-10-12 | 2014-10-12 | 020414S00003 | 14BJ0040 | 2014-06-18 | 2014-06-18 | 2014-06-30 | 2014-07-03 | 2014-07-08 | Q.C.D. CONSTRUCTION AND SUPPLY
2177 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 103957 | Magsaysay Hill PS | BAMBANG | 0 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2905174.43 |  |  | COMPLETED | 1 | 2014-12-22 | 2014-12-17 | 020414S00019 | 14BI0034 | 2014-08-12 | 2014-08-01 | 2014-08-12 | 2014-08-22 | 2014-09-02 | EDWIN ERWIN SISON CONSTRUCTION
2178 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300636 | Malabing Valley NHS | KASIBU | 0 | 1 | 4 | 1STY4CL | 2014 SHS BATCH 1 | 3664886.575 |  |  | COMPLETED | 1 | 2015-11-26 | 2015-11-26 | 020414S00059 | 15BJ0032 | 2015-06-30 | 2015-07-01 | 2015-07-14 | 2015-07-17 | 2015-07-22 | DENISSE-JOHN CONSTRUCTION AND SUPPLIES
2179 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300633 | Martinez Cuyangan NHS | KAYAPA | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-28 | 2015-11-28 | 020414S00042 | 15BJ0043 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-21 | 2015-07-24 | G.B. CARLOS CONSTRUCTION
2180 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300637 | Munguia NHS | DUPAX DEL NORTE | 0 | 1 | 4 | 1STY4CL | 2014 SHS BATCH 1 | 3614886.575 |  |  | COMPLETED | 1 | 2015-11-26 | 2015-11-26 | 020414S00063 | 15BJ0034 | 2015-06-30 | 2015-07-01 | 2015-07-14 | 2015-07-17 | 2015-07-22 | MIGHTY CONSTRUCTION & SUPPLY
2181 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300638 | Murong NHS | BAGABAG | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-11 | 2015-11-11 | 020414S00043 | 15BI0009 | 2015-06-30 | 2015-06-18 | 2015-06-30 | 2015-07-14 | 2015-07-23 | EDWIN ERWIN SISON CONSTRUCTION
2182 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300639 | Nansiakan NHS | KAYAPA | 0 | 1 | 6 | 1STY6CL | 2014 SHS BATCH 1 | 5336910.09 |  |  | COMPLETED | 1 | 2016-01-30 |  | 020414S00061 | 15BJ0057 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-24 | 2015-07-29 | TRIPLE P CONSTRUCTION
2183 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300640 | Napo-Tuyak Integrated School | KAYAPA | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-28 | 2016-03-29 | 020414S00044 | 15BJ0041 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-21 | 2015-07-24 | G.B. CARLOS CONSTRUCTION
2184 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300641 | Nueva Vizcaya Gen. CHS | BAYOMBONG (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 | 2016-02-09 |  | 020414S00060 | 15BI0055 | 2015-08-18 | 2015-08-06 | 2015-08-18 | 2015-08-26 | 2015-08-27 | E S DE GUZMAN CONSTRUCTION
2185 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104053 | Oyao ES | DUPAX DEL NORTE | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-12-24 |  | 020414S00074 | 15BJ0062 | 2015-07-28 | 2015-07-29 | 2015-08-11 | 2015-08-14 | 2015-08-19 | JOVIC CONSTRUCTION AND SUPPLY
2186 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300642 | PAIMA NATIONAL HIGH SCHOOL | BAYOMBONG (Capital) | 0 | 1 | 6 | 1STY6CL | 2014 SHS BATCH 1 | 5211910.09 |  |  | COMPLETED | 1 | 2016-01-24 | 2015-12-29 | 020414S00051 | 15BI0050 | 2015-08-18 | 2015-08-06 | 2015-08-18 | 2015-08-24 | 2015-08-27 | JOVIC CONSTRUCTION AND SUPPLY
2187 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300643 | Paniki High School | BAGABAG | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-09 | 2015-10-09 | 020414S00045 | 15BI0008 | 2015-06-30 | 2015-06-18 | 2015-06-30 | 2015-07-14 | 2015-07-23 | JANN-NORRIS CONSTRUCTION AND SUPPLIES
2188 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104097 | Pao Elementary School | KASIBU | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2014-10-12 | 2014-10-12 | 020414S00008 | 14BJ0042 | 2014-06-18 | 2014-06-18 | 2014-06-30 | 2014-07-03 | 2014-07-08 | MIGHTY CONSTRUCTION & SUPPLY
2189 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104100 | Paquet ES | KASIBU | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2014-12-18 | 2014-11-30 | 020414S00009 | 14BJ0050 | 2014-07-09 | 2014-07-10 | 2014-07-24 | 2014-07-29 | 2014-08-04 | E S DE GUZMAN CONSTRUCTION
2190 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300644 | Quezon NHS | QUEZON | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8249965.051 |  |  | COMPLETED | 1 | 2016-01-24 |  | 020414S00072 | 15BI0062 | 2015-08-18 | 2015-08-06 | 2015-08-18 | 2015-08-26 | 2015-08-27 | TRIPLE P CONSTRUCTION
2191 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 306204 | Runruno National High School | QUEZON | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 | 2016-03-01 |  | 020414S00071 | 15BI0061 | 2015-08-18 | 2015-08-06 | 2015-08-18 | 2015-08-26 | 2015-08-27 | E.M. BAYATAN CONSTRUCTION
2192 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300645 | Salinas High School | BAMBANG | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-16 | 2015-10-15 | 020414S00048 | 15BI0010 | 2015-06-30 | 2015-06-18 | 2015-06-30 | 2015-07-14 | 2015-07-23 | JANN-NORRIS CONSTRUCTION AND SUPPLIES
2193 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 103998 | Salingsingan ES | AMBAGUIO | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-12-27 | 2014-12-16 | 020414S00021 | 14BI0021 | 2014-07-31 | 2014-07-18 | 2014-07-31 | 2014-08-19 | 2014-08-28 | EDWIN ERWIN SISON CONSTRUCTION
2194 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104162 | San Juan ES | QUEZON | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1834740.174 |  |  | COMPLETED | 1 | 2015-12-04 | 2015-11-30 | 020414S00069 | 15BI0047 | 2015-07-09 | 2015-07-30 | 2015-07-30 | 2015-08-13 | 2015-08-24 | TRIPLE P CONSTRUCTION
2195 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 104033 | San Pablo ES | DIADI | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-24 | 020414S00023 | 14BI0023 | 2014-07-31 | 2014-07-18 | 2014-07-31 | 2014-08-19 | 2014-08-28 | JANN-NORRIS CONSTRUCTION AND SUPPLIES
2196 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300649 | Santa Fe National High School | SANTA FE | 0 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10537131.51 |  |  | COMPLETED | 1 | 2016-02-01 |  | 020414S00037 | 15BJ0060 | 2015-06-07 | 2015-07-08 | 2015-07-21 | 2015-07-24 | 2015-07-29 | E.M. BAYATAN CONSTRUCTION
2197 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300646 | Solano High School | SOLANO | 0 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10447131.51 |  |  | COMPLETED | 1
2198 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300647 | Sta. Clara HS | ARITAO | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-24 | 2015-09-30 | 020414S00046 | 15BJ0042 | 2015-07-28 | 2015-07-29 | 2015-08-11 | 2015-08-14 | 2015-08-19 | TRIPLE P CONSTRUCTION
2199 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300648 | Sta. Cruz Pingkian HS | KAYAPA | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8389965.051 |  |  | COMPLETED | 1 | 2016-01-23 |  | 020414S00036 | 15BJ0053 | 2015-07-28 | 2015-07-29 | 2015-08-11 | 2015-08-14 | 2015-08-19 | TRIPLE P CONSTRUCTION
2200 | NC 2014 | SHS (2014) | Region II | Nueva Vizcaya | 300651 | Uddiawan NHS | SOLANO | 0 | 1 | 4 | 1STY4CL | 2014 SHS BATCH 1 | 3584886.575 |  |  | COMPLETED | 1 | 2015-12-16 | 2015-11-30 | 020414S00035 | 15BI0024 | 2015-07-21 | 2015-07-21 | 2015-07-21 | 2015-08-04 | 2015-08-12 | Q.C.D. CONSTRUCTION AND SUPPLY
2201 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 103950 | Villaros ES | BAGABAG | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-12-07 | 2014-11-30 | 020414S00017 | 14BI0033 | 2014-08-12 | 2014-08-01 | 2014-08-12 | 2014-08-22 | 2014-09-02 | E S DE GUZMAN CONSTRUCTION
2202 | NC 2014 | K10 (2014) | Region II | Nueva Vizcaya | 103927 | Yaway ES | ARITAO | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2014-11-11 | 2014-11-11 | 020414S00029 | 14BJ0048 | 2014-06-18 | 2014-06-18 | 2014-06-30 | 2014-07-03 | 2014-07-08 | TRIPLE AE CONSTRUCTION
2203 | NC 2014 | SHS (2014) | Region II | Quirino | 300652 | Aglipay NHS | AGLIPAY | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 | 2016-01-17 |  | 020514S00023 | 15BK0036 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-31 | 2015-08-14 | NTL BUILDERS AND DEVELOPER
2204 | NC 2014 | K10 (2014) | Region II | Quirino | 306321 | Alicia Integrated School | AGLIPAY | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-14 | 2015-09-30 | 020514S00017 | 15BK0035 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-07-31 | 2015-08-14 | KMD BUILDERS AND CONST. SUPPLY
2205 | NC 2014 | SHS (2014) | Region II | Quirino | 300656 | Cabarroguis NSAT | CABARROGUIS (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-24 |  | 020514S00022 | 15BK0043 | 2015-07-22 | 2015-07-22 | 2015-08-04 | 2015-08-17 | 2015-08-28 | NTL BUILDERS AND DEVELOPER
2206 | NC 2014 | K10 (2014) | Region II | Quirino | 104296 | Campamento ES | DIFFUN | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-05 | 2014-10-05 | 020514S00007 | 14BK0017 | 2014-06-12 | 2014-06-13 | 2014-06-26 | 2014-07-15 | 2014-07-21 | COLBY CONSTRUCTION
2207 | NC 2014 | SHS (2014) | Region II | Quirino | 300657 | Diffun HS | DIFFUN | 0 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 11027342.5917 |  |  | COMPLETED | 1
2208 | NC 2014 | K10 (2014) | Region II | Quirino | 104229 | Diodol ES | AGLIPAY | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1147329.12 |  |  | COMPLETED | 1 | 2014-09-05 | 2014-09-05 | 020514S00008 | 14BK0016 | 2014-06-12 | 2014-06-13 | 2014-06-26 | 2014-07-15 | 2014-07-21 | COLBY CONSTRUCTION
2209 | NC 2014 | K10 (2014) | Region II | Quirino | 306325 | Dioryong IS | NAGTIPUNAN | 0 | 1 | 4 | 1sty4cl (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 | 2016-04-25 |  | 020514S00027 | 15BK0067 | 2015-09-08 | 2015-09-19 | 2015-09-21 | 2015-12-14 | 2015-12-21 | JMD-68 BUILDERS
2210 | NC 2014 | K10 (2014) | Region II | Quirino | 104301 | Doña Imelda ES | DIFFUN | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-05 | 2014-09-05 | 020514S00009 | 14BK0022 | 2014-06-12 | 2014-06-13 | 2014-06-26 | 2014-07-15 | 2014-07-21 | COLBY CONSTRUCTION
2211 | NC 2014 | K10 (2014) | Region II | Quirino | 306317 | Dumabato Integrated School | MADDELA | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
2212 | NC 2014 | SHS (2014) | Region II | Quirino | 306317 | Dumabato Integrated School | MADDELA | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8289965.051 |  |  | COMPLETED | 1
2213 | NC 2014 | K10 (2014) | Region II | Quirino | 306312 | Dumabel IS | AGLIPAY | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-04-25 |  | 020514S00026 | 15BK0066 | 2015-09-08 | 2015-09-19 | 2015-09-21 | 2015-12-14 | 2015-12-21 | C-BROS CONSTRUCTION
2214 | NC 2014 | K10 (2014) | Region II | Quirino | 104374 | Gamis ES | SAGUDAY | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-05 | 2014-09-25 | 020514S00004 | 14BK0023 | 2014-06-12 | 2014-06-13 | 2014-06-26 | 2014-07-15 | 2014-07-21 | NTL BUILDERS AND DEVELOPER
2215 | NC 2014 | K10 (2014) | Region II | Quirino | 104353 | Giayan IS | NAGTIPUNAN | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1177329.12 |  |  | COMPLETED | 1 | 2014-09-05 | 2014-09-05 | 020514S00005 | 14BK0019 | 2014-06-12 | 2014-06-13 | 2014-06-26 | 2014-07-15 | 2014-07-21 | NTL BUILDERS AND DEVELOPER
2216 | NC 2014 | K10 (2014) | Region II | Quirino | 104281 | Gulac ES | DIFFUN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-10-16 | 2015-09-30 | 020514S00011 | 15BK0032 | 2015-07-08 | 2015-07-09 | 2015-07-21 | 2015-07-31 | 2015-08-11 | JMD-68 BUILDERS
2217 | NC 2014 | SHS (2014) | Region II | Quirino | 300660 | Maddela CHS | MADDELA | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 | 2016-01-21 |  | 020514S00025 | 15BK0041 | 2015-07-16 | 2015-07-17 | 2015-08-03 | 2015-08-14 | 2015-08-24 | APD CONSTRUCTION
2218 | NC 2014 | K10 (2014) | Region II | Quirino | 104309 | Magsaysay ES | DIFFUN | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-05 | 2014-10-05 | 020514S00006 | 14BK0018 | 2014-06-12 | 2014-06-13 | 2014-06-26 | 2014-07-15 | 2014-07-21 | NTL BUILDERS AND DEVELOPER
2219 | NC 2014 | SHS (2014) | Region II | Quirino | 300661 | Magsaysay NHS | DIFFUN | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6499337.6381 |  |  | COMPLETED | 1 | 2015-12-22 | 2015-12-22 | 020514S00020 | 15BK0038 | 2015-07-15 | 2015-07-16 | 2015-07-31 | 2015-08-12 | 2015-08-24 | JMD-68 BUILDERS
2220 | NC 2014 | SHS (2014) | Region II | Quirino | 300662 | Nagtipunan NHS | NAGTIPUNAN | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1
2221 | NC 2014 | SHS (2014) | Region II | Quirino | 300663 | Pinaripad NHS | AGLIPAY | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 | 2016-01-24 |  | 020514S00018 | 15BK0042 | 2015-07-22 | 2015-07-23 | 2015-08-04 | 2015-08-19 | 2015-08-28 | NTL BUILDERS AND DEVELOPER
2222 | NC 2014 | K10 (2014) | Region II | Quirino | 104265 | Potia ES | CABARROGUIS (Capital) | 0 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-05 | 2014-10-05 | 020514S00001 | 14BK0021 | 2014-06-12 | 2014-06-13 | 2014-06-26 | 2014-07-15 | 2014-07-21 | COLBY CONSTRUCTION
2223 | NC 2014 | SHS (2014) | Region II | Quirino | 300664 | Quirino General HS | CABARROGUIS (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-24 |  | 020514S00024 | 15BK0046 | 2015-07-22 | 2015-07-22 | 2015-08-04 | 2015-08-19 | 2015-08-28 | NTL BUILDERS AND DEVELOPER
2224 | NC 2014 | K10 (2014) | Region II | Quirino | 156506 | Rizal ES | DIFFUN | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-05 | 2014-09-05 | 020514S00003 | 14BK0020 | 2014-06-12 | 2014-06-13 | 2014-06-26 | 2014-07-15 | 2014-07-21 | NTL BUILDERS AND DEVELOPER
2225 | NC 2014 | SHS (2014) | Region II | Quirino | 300665 | Saguday NHS | SAGUDAY | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-21 |  | 020514S00012 | 15BK0040 | 2015-07-16 | 2015-07-17 | 2015-08-03 | 2015-08-14 | 2015-08-24 | APD CONSTRUCTION
2226 | NC 2014 | K10 (2014) | Region II | Quirino | 104316 | San Pascual ES | DIFFUN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1042049.6543 |  |  | COMPLETED | 1 | 2015-10-16 | 2015-09-30 | 020514S00032 | 15BK0033 | 2015-07-08 | 2015-07-09 | 2015-07-21 | 2015-07-31 | 2015-08-11 | JMD-68 BUILDERS
2227 | NC 2014 | SHS (2014) | Region II | Quirino | 306316 | Scala Integrated School | NAGTIPUNAN | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8354965.051 |  |  | COMPLETED | 1 | 2016-01-24 |  | 020514S00016 | 15BK0044 | 2015-07-22 | 2015-07-23 | 2015-08-04 | 2015-08-17 | 2015-08-28 | NTL BUILDERS AND DEVELOPER
2228 | NC 2014 | SHS (2014) | Region II | Quirino | 300666 | Tucod HS | CABARROGUIS (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 | 2016-01-24 |  | 020514S00015 | 15BK0045 | 2015-07-22 | 2015-07-23 | 2015-08-04 | 2015-08-17 | 2015-08-28 | NTL BUILDERS AND DEVELOPER
2229 | NC 2014 | SHS (2014) | Region II | Quirino | 300653 | Victoria HS | AGLIPAY | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 | 2016-01-21 |  | 020514S00014 | 15BK0039 | 2015-07-15 | 2015-07-16 | 2015-07-31 | 2015-08-12 | 2015-08-24 | TRIBU DESIGN & CONSTRUCTION
2230 | NC 2014 | K10 (2014) | Region II | Santiago City | 325204 | Divisoria High School - Naggasican Extension | CITY OF SANTIAGO | 4 | 1 | 5 | 1STY5CL | 2014 K10 BATCH 4B | 4303392.2448 |  |  | COMPLETED | 1 | 2016-02-17 |  | 020314S00073 | 15bh0045 | 2015-07-21 | 2015-07-28 | 2015-08-11 | 2015-10-05 | 2015-10-15 | H.T.L. CONSTRUCTION
2231 | NC 2014 | K10 (2014) | Region II | Santiago City | 103817 | Nabbuan ES | CITY OF SANTIAGO | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | REVERTED | 0
2232 | NC 2014 | K10 (2014) | Region II | Santiago City | 103817 | Nabbuan ES | CITY OF SANTIAGO | 4 |  | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | REVERTED | 0
2233 | NC 2014 | K10 (2014) | Region II | Santiago City | 103839 | San Jose ES | CITY OF SANTIAGO | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 020314S00040 | 14bh0043 | 2014-09-08 | 2014-09-10 | 2014-09-22 | 2014-10-13 | 2014-10-22 | SHANLEY CONSTRUCTION
2234 | NC 2014 | K10 (2014) | Region II | Santiago City | 325203 | Santiago City National High School - Rosario Extension | CITY OF SANTIAGO | 4 | 1 | 6 | 2sty6cl | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-05 |  | 020314S00176 | 15bh0065 | 2015-07-30 | 2015-08-04 | 2015-08-18 | 2015-08-27 | 2015-09-03 | MAR-DEB CONSTRUCTION & DEVELOPMENT
2235 | NC 2014 | SHS (2014) | Region II | Tuguegarao City | 300669 | Cataggaman National High School | TUGUEGARAO CITY(Capital) | 3 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-03-10 |  | 020214S00098 | 15-BD-0069 | 2015-08-13 | 2015-08-25 | 2015-08-26 | 2015-08-30 | 2015-09-11 | E.C.T. CONSTRUCTION
2236 | NC 2014 | SHS (2014) | Region II | Tuguegarao City | 300671 | Gosi HS | TUGUEGARAO CITY(Capital) | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-24 |  | 020214S00097 | 15-BD-0050 | 2015-07-20 | 2015-08-04 | 2015-08-05 | 2015-08-10 | 2015-08-27 | MEGAY CONSTRUCTION AND SUPPLY
2237 | NC 2014 | K10 (2014) | Region II | Tuguegarao City | 104388 | Libag ES | TUGUEGARAO CITY(Capital) | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-10-06 | 2014-11-05 | 020214S00037 | 14-BD-0027 | 2014-06-25 | 2014-06-26 | 2014-07-09 | 2014-07-17 | 2014-08-07 | E.C.T. CONSTRUCTION
2238 | NC 2014 | SHS (2014) | Region II | Tuguegarao City | 300670 | Linao NHS | TUGUEGARAO CITY(Capital) | 3 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-03-10 |  | 020214S00096 | 15-BD-0070 | 2015-08-13 | 2015-08-25 | 2015-08-26 | 2015-08-30 | 2015-09-11 | ROGELIO M. DIMAANDAL CONSTRUCTION
2239 | NC 2014 | K10 (2014) | Region II | Tuguegarao City | 104407 | Ugac ES | TUGUEGARAO CITY(Capital) | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2015-01-19 | 2015-01-19 | 020214S00049 | 14-BD-0028 | 2014-10-07 | 2014-10-24 | 2014-10-27 | 2014-10-31 | 2014-11-21 | E. GUADIZ CONSTRUCTION
10083 | NC 2015 | SHS (2015) | Region II | BATANES | 300411 | Batanes Nat"l Science HS | BASCO (Capital) | 0 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 2 | 4417968.78 |  |  | COMPLETED | 1
10084 | NC 2015 | SHS (2015) | Region II | BATANES | 300411 | Batanes Nat"l Science HS | BASCO (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2688606.04 |  |  | COMPLETED | 1
10085 | NC 2015 | SHS (2015) | Region II | Cagayan | 300430 | Baggao National School of Arts & Trades | BAGGAO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 020215S00032 | 15BB0117 | 2015-10-06 | 2015-10-09 | 2015-10-28 | 2015-11-02 | 2015-11-04 | E.C.T. CONSTRUCTION
10086 | NC 2015 | SHS (2015) | Region II | Cagayan | 300423 | Alig Valley NHS | ALLACAPAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2488606 |  |  | COMPLETED | 1 |  |  | 020215S00034 | 15BC0122 | 2015-09-16 | 2015-09-18 | 2015-10-01 | 2015-10-06 | 2015-10-21 | DANDEX CONSTRUCTION
10087 | NC 2015 | K10 (2015) | Region II | Cagayan | 102603 | Alimoan ES | CLAVERIA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 020215S00035 | 15BC0088 | 2015-08-06 | 2015-08-07 | 2015-08-20 | 2015-08-26 | 2015-09-04 | B.A. LAGAZO BUILDERS
10088 | NC 2015 | K10 (2015) | Region II | Cagayan | 300434 | Ballesteros NHS | BALLESTEROS | 2 | 1 | 10 | 2STY10CL | 2015 ADDITIONAL FUND BATCH 9 | 4406345.042 |  |  | COMPLETED | 1
10089 | NC 2015 | SHS (2015) | Region II | Cagayan | 300439 | Nabannagan National High School | LASAM | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1988606.04 |  |  | COMPLETED | 1
10090 | NC 2015 | SHS (2015) | Region II | Cagayan | 300439 | Nabannagan National High School | LASAM | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1988606.04 |  |  | COMPLETED | 1
10091 | NC 2015 | SHS (2015) | Region II | Cagayan | 300452 | Cordova NHS | AMULUNG | 3 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 11027342.5917 |  |  | COMPLETED | 1 |  |  | 020215S00030 | 15-BD-0068 | 2015-08-14 | 2015-08-27 | 2015-08-28 | 2015-09-02 | 2015-09-11 | E.C.T. CONSTRUCTION
10092 | NC 2015 | SHS (2015) | Region II | Cagayan | 300466 | Itawes Nat'l. Agr'l. & Tech'l. School | TUAO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1
10093 | NC 2015 | SHS (2015) | Region II | Cagayan | 300466 | Itawes Nat'l. Agr'l. & Tech'l. School | TUAO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1
10094 | NC 2015 | SHS (2015) | Region II | Cagayan | 300468 | Itawes Nat'l.l Agr'l. & Tech'l. School - Bagumbayan Annex | TUAO | 3 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 5 | 13021310 |  |  | COMPLETED | 1 |  |  | 020215S00033 | 15-BD-0078 | 2015-09-03 | 2015-09-15 | 2015-09-16 | 2015-09-20 | 2015-10-27 | MEGAY CONSTRUCTION AND SUPPLY
10095 | NC 2015 | SHS (2015) | Region II | Cauayan City | 300516 | Cauayan City NHS | CITY OF CAUAYAN | 3 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1
10096 | NC 2015 | SHS (2015) | Region II | Cauayan City | 300516 | Cauayan City NHS | CITY OF CAUAYAN | 3 |  | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1
10097 | NC 2015 | SHS (2015) | Region II | Cauayan City | 300516 | Cauayan City NHS | CITY OF CAUAYAN | 3 |  | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1
10098 | NC 2015 | SHS (2015) | Region II | Cauayan City | 306118 | Sillawit National High School | CITY OF CAUAYAN | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2862592.44 |  |  | COMPLETED | 1
10099 | NC 2015 | SHS (2015) | Region II | Cauayan City | 306118 | Sillawit National High School | CITY OF CAUAYAN | 3 |  | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2862592.44 |  |  | COMPLETED | 1
10100 | NC 2015 | SHS (2015) | Region II | City of Ilagan | 300583 | San Antonio Nat'l. Agro-Ind'l. & Voc'l. HS | ILAGAN (Capital) | 1 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 2 | 12821310.093 |  |  | COMPLETED | 1 |  |  | 020315S00038 | 15BE0096 | 2015-07-20 | 2015-07-21 | 2015-08-04 | 2015-08-26 | 2015-09-08 | EGB CONSTRUCTION
10101 | NC 2015 | SHS (2015) | Region II | City of Ilagan | 300584 | San Rafael Nat'l & Voc'l HS (San Antonio NAIVHS-San Rafael Annex) | ILAGAN (Capital) | 1 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 2 | 12621310.093 |  |  | COMPLETED | 1 |  |  | 020315S00039 | 15BE0097 | 2015-07-20 | 2015-07-21 | 2015-08-04 | 2015-08-26 | 2015-09-08 | EGB CONSTRUCTION
10102 | NC 2015 | SHS (2015) | Region II | City of Ilagan | 300602 | Sta. Isabel NHS | ILAGAN (Capital) | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10927342.5917 |  |  | COMPLETED | 1
10103 | NC 2015 | SHS (2015) | Region II | City of Ilagan | 300602 | Sta. Isabel NHS | ILAGAN (Capital) | 1 |  | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10927342.5917 |  |  | COMPLETED | 1
10104 | NC 2015 | SHS (2015) | Region II | Isabela | 300521 | Alfreda Albano NHS - Magassi, Cabagan | CABAGAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8064965.051 |  |  | COMPLETED | 1 |  |  | 020315S00030 | 15BE0112 | 2015-07-26 | 2015-07-27 | 2015-08-10 | 2015-08-26 | 2015-09-08 | EGB CONSTRUCTION
10105 | NC 2015 | SHS (2015) | Region II | Isabela | 300605 | Buenaventura G. Masigan NHS | SANTA MARIA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
10106 | NC 2015 | SHS (2015) | Region II | Isabela | 300605 | Buenaventura G. Masigan NHS | SANTA MARIA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
10107 | NC 2015 | SHS (2015) | Region II | Isabela | 306153 | Cumabao IS | TUMAUINI | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
10108 | NC 2015 | SHS (2015) | Region II | Isabela | 306153 | Cumabao IS | TUMAUINI | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
10109 | NC 2015 | SHS (2015) | Region II | Isabela | 300522 | Delfin Albano HS - San Juan Annex | CABAGAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
10110 | NC 2015 | SHS (2015) | Region II | Isabela | 300522 | Delfin Albano HS - San Juan Annex | CABAGAN | 1 |  | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
10111 | NC 2015 | SHS (2015) | Region II | Isabela | 300520 | Delfin Albano HS-Main | CABAGAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 020315S00050 | 15BE0085 | 2015-07-13 | 2015-07-14 | 2015-07-27 | 2015-08-26 | 2015-09-08 | EGB CONSTRUCTION
10112 | NC 2015 | SHS (2015) | Region II | Isabela | 300556 | Lalauanan HS | TUMAUINI | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
10113 | NC 2015 | SHS (2015) | Region II | Isabela | 300556 | Lalauanan HS | TUMAUINI | 1 |  | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
10114 | NC 2015 | SHS (2015) | Region II | Isabela | 300564 | Palanan HS | PALANAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 3402592.44 |  |  | COMPLETED | 1
10115 | NC 2015 | SHS (2015) | Region II | Isabela | 300564 | Palanan HS | PALANAN | 1 |  | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
10116 | NC 2015 | SHS (2015) | Region II | Isabela | 300587 | Ragan Sur NHS (San Antonio HS - Ragan Sur Annex) | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
10117 | NC 2015 | SHS (2015) | Region II | Isabela | 300587 | Ragan Sur NHS (San Antonio HS - Ragan Sur Annex) | DELFIN ALBANO (MAGSAYSAY) | 1 |  | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
10118 | NC 2015 | K10 (2015) | Region II | Isabela | 300585 | San Antonio NHS | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | 2 | ADDITONAL 1STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 1814740.174 |  |  | COMPLETED | 1
10119 | NC 2015 | SHS (2015) | Region II | Isabela | 300603 | Santa Maria High School | SANTA MARIA | 1 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 2 | 12771310.093 |  |  | COMPLETED | 1 |  |  | 020315S00031 | 15BE0104 | 2015-07-20 | 2015-07-21 | 2015-08-04 | 2015-08-26 | 2015-09-08 | CHOLO CONSTRUCTION AND TRADING
10120 | NC 2015 | SHS (2015) | Region II | Isabela | 306132 | Simanu National High School | SAN PABLO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1988606.04 |  |  | COMPLETED | 1
10121 | NC 2015 | SHS (2015) | Region II | Isabela | 306132 | Simanu National High School | SAN PABLO | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1988606.04 |  |  | COMPLETED | 1
10122 | NC 2015 | K10 (2015) | Region II | Isabela | 300500 | Alicia National High School | ALICIA | 3 | 1 | 2 | ADDITONAL 1STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 1814740.174 |  |  | COMPLETED | 1
10123 | NC 2015 | K10 (2015) | Region II | Isabela | 103007 | Apanay ES | ALICIA | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1 |  |  | 020315S00057 | 15BG0069 | 2015-08-11 | 2015-08-14 | 2015-08-26 | 2015-08-28 | 2015-09-02 | MAR-DEB CONSTRUCTION & DEVELOPMENT
10124 | NC 2015 | SHS (2015) | Region II | Isabela | 306143 | Cagasat HS-Magsasay Annex | CORDON | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
10125 | NC 2015 | SHS (2015) | Region II | Isabela | 306143 | Cagasat HS-Magsasay Annex | CORDON | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
10126 | NC 2015 | SHS (2015) | Region II | Isabela | 300508 | CAGASAT NHS | CORDON | 4 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10727342.5917 |  |  | COMPLETED | 1 |  |  | 020315S00013 | 15bh0072 | 2015-07-30 | 2015-08-04 | 2015-08-18 | 2015-08-27 | 2015-09-03 | ISABELA EBC BUILDERS CONSTRUCTION, INC. (FORMERLY
10127 | NC 2015 | SHS (2015) | Region II | Isabela | 300518 | Dabubu HS | SAN AGUSTIN | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2852592.44 |  |  | COMPLETED | 1
10128 | NC 2015 | SHS (2015) | Region II | Isabela | 300518 | Dabubu HS | SAN AGUSTIN | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2852592.44 |  |  | COMPLETED | 1
10129 | NC 2015 | SHS (2015) | Region II | Isabela | 300524 | Dibuluan National High School | JONES | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
10130 | NC 2015 | SHS (2015) | Region II | Isabela | 300524 | Dibuluan National High School | JONES | 4 |  | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
10131 | NC 2015 | SHS (2015) | Region II | Isabela | 300529 | Don Mariano Marcos NHS | ECHAGUE | 6 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2822592.44 |  |  | COMPLETED | 1
10132 | NC 2015 | SHS (2015) | Region II | Isabela | 300529 | Don Mariano Marcos NHS | ECHAGUE | 6 |  | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2822592.44 |  |  | COMPLETED | 1
10133 | NC 2015 | SHS (2015) | Region II | Isabela | 300555 | Jones Rural School - Main | JONES | 4 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10727342.5917 |  |  | COMPLETED | 1
10134 | NC 2015 | SHS (2015) | Region II | Isabela | 300555 | Jones Rural School - Main | JONES | 4 |  | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10727342.5917 |  |  | COMPLETED | 1
10135 | NC 2015 | SHS (2015) | Region II | Isabela | 300571 | Ramon NHS | RAMON | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
10136 | NC 2015 | SHS (2015) | Region II | Isabela | 300571 | Ramon NHS | RAMON | 4 |  | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
10137 | NC 2015 | SHS (2015) | Region II | Isabela | 300600 | Sgt. Prospero Bello HS - Main | JONES | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2852592.44 |  |  | COMPLETED | 1
10138 | NC 2015 | SHS (2015) | Region II | Isabela | 300600 | Sgt. Prospero Bello HS - Main | JONES | 4 |  | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
10139 | NC 2015 | SHS (2015) | Region II | Nueva Vizcaya | 306207 | Alfonso Castaneda NHS - Annex (Brgy. Abuyo) | ALFONSO CASTAÑEDA | 0 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 4042212 |  |  | COMPLETED | 1 |  |  | 020415S00004 | 15BJ0067 | 2015-08-13 | 2015-08-20 | 2015-09-03 | 2015-10-26 | 2015-10-29 | PISCES CONSTRUCTION
10140 | NC 2015 | SHS (2015) | Region II | Nueva Vizcaya | 300623 | Bintawan NHS | VILLAVERDE | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 020415S00002 | 15BI0056 | 2015-08-18 | 2015-08-06 | 2015-08-18 | 2015-08-26 | 2015-08-27 | ERIC VAN P. SESBRENO CONSTRUCTION
10141 | NC 2015 | K10 (2015) | Region II | Nueva Vizcaya | 306205 | Canabuan National High School | SANTA FE | 0 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 4002212 |  |  | COMPLETED | 1
10142 | NC 2015 | SHS (2015) | Region II | Nueva Vizcaya | 306205 | Canabuan National High School | SANTA FE | 0 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 4002212 |  |  | COMPLETED | 1
10143 | NC 2015 | SHS (2015) | Region II | Nueva Vizcaya | 300626 | Casat NHS | BAYOMBONG (Capital) | 0 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 3927212 |  |  | COMPLETED | 1 |  |  | 020415S00005 | 15BI0078 | 2015-11-03 | 2015-10-22 | 2015-11-03 | 2015-11-16 | 2015-11-24 | JANN-NORRIS CONSTRUCTION AND SUPPLIES
10144 | NC 2015 | SHS (2015) | Region II | Nueva Vizcaya | 300630 | Kakiduguen NHS | KASIBU | 0 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 3977212 |  |  | COMPLETED | 1 |  |  | 020415S00003 | 15BJ0068 | 2015-08-13 | 2015-08-20 | 2015-09-03 | 2015-10-26 | 2015-10-29 | DENISSE-JOHN CONSTRUCTION AND SUPPLIES
10145 | NC 2015 | K10 (2015) | Region II | Nueva Vizcaya | 300646 | Solano High School | SOLANO | 0 | 1 | 16 | 2UNITS 2STY4CL AND 2STY8CL | 2015 ADDITIONAL FUND BATCH 9 | 12618886.3578 |  |  | COMPLETED | 1
10146 | NC 2015 | SHS (2015) | Region II | Nueva Vizcaya | 300650 | Tuao HS | BAGABAG | 0 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 3897212 |  |  | COMPLETED | 1 |  |  | 020415S00007 | 15BI0067 | 2015-09-15 | 2015-09-03 | 2015-09-22 | 2015-10-20 | 2015-10-27 | G.M. PAJARILLAGA CONSTRUCTION & SUPPLY
10147 | NC 2015 | SHS (2015) | Region II | Quirino | 300654 | Balligui HS | MADDELA | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1
10148 | NC 2015 | SHS (2015) | Region II | Quirino | 300654 | Balligui HS | MADDELA | 0 |  | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
10149 | NC 2015 | K10 (2015) | Region II | Quirino | 300657 | Diffun HS | DIFFUN | 0 | 1 | 3 | ADDITONAL 1STY3CL | 2015 ADDITIONAL FUND BATCH 9 | 2640828.124 |  |  | COMPLETED | 1
10150 | NC 2015 | SHS (2015) | Region II | Quirino | 306310 | GIAYAN INTEGRATED SCHOOL | NAGTIPUNAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2108606 |  |  | COMPLETED | 1 |  |  | 020515S00004 | 15BK0062 | 2015-08-20 | 2015-08-24 | 2015-09-07
10151 | NC 2015 | K10 (2015) | Region II | Quirino | 300662 | Nagtipunan NHS | NAGTIPUNAN | 0 | 1 | 8 | 2STY8CL | 2015 ADDITIONAL FUND BATCH 9 | 2212377.5407 |  |  | COMPLETED | 1
10152 | NC 2015 | SHS (2015) | Region II | Quirino | 306309 | San Martin IS | MADDELA | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2038606 |  |  | COMPLETED | 1 |  |  | 020515S00005 | 15BK0063 | 2015-08-20 | 2015-08-24 | 2015-09-07 | 2015-12-14 | 2015-12-21 | JMD-68 BUILDERS
10153 | NC 2015 | SHS (2015) | Region II | Quirino | 306303 | Sangbay IS | NAGTIPUNAN | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6339338 |  |  | COMPLETED | 1 |  |  | 020515S00003 | 15BK0058 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-10-16 | 2015-10-28 | JMD-68 BUILDERS
10154 | NC 2015 | SHS (2015) | Region II | Santiago City | 300528 | Divisoria High School | CITY OF SANTIAGO | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10492131.51 |  |  | COMPLETED | 1 |  |  | 020315S00024 | 15BH0085 | 2015-08-19 | 2015-08-20 | 2015-09-01 | 2015-09-15 | 2015-09-28 | R.S. SEPIAN CONSTRUCTION & TRUCKING
10155 | NC 2015 | SHS (2015) | Region II | Santiago City | 300578 | Rizal National High School | CITY OF SANTIAGO | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 020315S00027 | 15bh0062 | 2015-07-30 | 2015-08-04 | 2015-08-18 | 2015-08-27 | 2015-09-03 | META CONSTRUCTION
10156 | NC 2015 | SHS (2015) | Region II | Santiago City | 300599 | Santiago City National High School | CITY OF SANTIAGO | 4 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15271327.92 |  |  | COMPLETED | 1 |  |  | 020315S00025 | 15BH0086 | 2015-08-19 | 2015-08-20 | 2015-09-01 | 2015-09-15 | 2015-09-28 | ERIC VAN P. SESBRENO CONSTRUCTION
10157 | NC 2015 | SHS (2015) | Region II | Santiago City | 325202 | Santiago City National High School - Sagana | CITY OF SANTIAGO | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8289965.051 |  |  | COMPLETED | 1 |  |  | 020315S00037 | 15bh0063 | 2015-07-30 | 2015-08-04 | 2015-08-18 | 2015-08-27 | 2015-09-03 | ISABELA EBC BUILDERS CONSTRUCTION, INC. (FORMERLY
10158 | NC 2015 | SHS (2015) | Region II | Santiago City | 325201 | Santiago City National High School - Sinsayon | CITY OF SANTIAGO | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 020315S00026 | 15bh0064 | 2015-11-10 | 2015-11-17 | 2015-11-24 | 2015-12-09 | 2015-12-22 | META CONSTRUCTION
10159 | NC 2015 | SHS (2015) | Region II | Tuguegarao City | 300668 | Cagayan NHS | TUGUEGARAO CITY(Capital) | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26777469.42 |  |  | COMPLETED | 1
10160 | NC 2015 | SHS (2015) | Region II | Tuguegarao City | 300668 | Cagayan NHS | TUGUEGARAO CITY(Capital) | 3 |  | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26777469.42 |  |  | COMPLETED | 1
10161 | NC 2015 | TECHVOC (2015) | Region II | Tuguegarao City | 300668 | Cagayan NHS | TUGUEGARAO CITY(Capital) | 3 | 1 | 5 | Construction of 5 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 11827746.35 |  |  | COMPLETED | 1
10162 | NC 2015 | SHS (2015) | Region II | Tuguegarao City | 306401 | Tuguegarao City Science High School | TUGUEGARAO CITY(Capital) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | REVERTED | 0 |  |  | 020215S00026 | 15-BD-0051 | 2015-08-14 | 2015-08-27 | 2015-08-28 | 2015-09-02 | 2015-09-11 | R.T. DIWA CONSTRUCTION
16623 | NC 2016 | SHS | Region II | Cagayan | 300471 | Aparri East National High School | Aparri | 1 | 1 | 10 | 2STY10CL | BATCH 3 CL | 13150000 |  |  | Completed | 1
16624 | NC 2016 | SHS | Region II | Cagayan | 300471 | Aparri East National High School | Aparri | 1 |  | 6 | 2STY6CL | BATCH 3 CL | 8350000 |  |  | Completed | 1
16625 | NC 2016 | SHS | Region II | Cagayan | 300428 | Aparri Sat | Aparri | 1 | 1 | 27 | 3STY9CL | BATCH 3 CL | 45450000 |  |  | Completed | 1
16626 | NC 2016 | SHS | Region II | Cagayan | 300428 | Aparri Sat | Aparri | 1 |  | 4 | 2STY4CL | BATCH 3 CL | 6469337 |  |  | Completed | 1
16627 | NC 2016 | TECHVOC | Region II | Cagayan | 300428 | Aparri Sat | Aparri | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2490000 |  |  | Completed | 1
16628 | NC 2016 | SHS | Region II | Cagayan | 300429 | Baggao Nas | Baggao | 1 | 1 | 20 | 2STY10CL | BATCH 3 CL | 26300000 |  |  | Completed | 1
16629 | NC 2016 | TECHVOC | Region II | Cagayan | 300429 | Baggao Nas | Baggao | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 4980000 |  |  | Completed | 1
16630 | NC 2016 | SHS | Region II | Cagayan | 300431 | Baggao Nhs | Baggao | 1 | 1 | 10 | 2STY10CL | BATCH 3 CL | 13150000 |  |  | Completed | 1
16631 | NC 2016 | SHS | Region II | Cagayan | 300431 | Baggao Nhs | Baggao | 1 |  | 6 | 2STY6CL | BATCH 3 CL | 8350000 |  |  | Completed | 1
16632 | NC 2016 | SHS | Region II | Cagayan | 300431 | Baggao Nhs | Baggao | 1 |  | 4 | 2STY4CL | BATCH 3 CL | 6469337 |  |  | Completed | 1
16633 | NC 2016 | SHS | Region II | Cagayan | 300444 | Camalaniugan Nhs | Camalaniugan | 1 | 1 | 20 | 2STY10CL | BATCH 3 CL | 26300000 |  |  | Completed | 1
16634 | NC 2016 | SHS | Region II | Cagayan | 300444 | Camalaniugan Nhs | Camalaniugan | 1 |  | 6 | 2STY6CL | BATCH 3 CL | 8350000 |  |  | Completed | 1
16635 | NC 2016 | TECHVOC | Region II | Cagayan | 300444 | Camalaniugan Nhs | Camalaniugan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2490000 |  |  | Completed | 1
16636 | NC 2016 | K10 | Region II | Cagayan | 300462 | Gattaran National Trade School | Gattaran | 1 | 1 | 24 | 2STY8CL | BATCH 3 CL | 33635000 |  |  | Completed | 1
16637 | NC 2016 | TECHVOC | Region II | Cagayan | 300462 | Gattaran National Trade School | Gattaran | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2527000 |  |  | Completed | 1
16638 | NC 2016 | K10 | Region II | Cagayan | 102695 | Gonzaga North Cs | Gonzaga | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.05 |  |  | Completed | 1
16639 | NC 2016 | SHS | Region II | Cagayan | 300469 | Lal-Lo National High School | Lal-Lo | 1 | 1 | 20 | 2STY10CL | BATCH 3 CL | 26300000 |  |  | Completed | 1
16640 | NC 2016 | SHS | Region II | Cagayan | 300469 | Lal-Lo National High School | Lal-Lo | 1 |  | 8 | 2STY8CL | BATCH 3 CL | 11150000 |  |  | Completed | 1
16641 | NC 2016 | TECHVOC | Region II | Cagayan | 300469 | Lal-Lo National High School | Lal-Lo | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2490000 |  |  | Completed | 1
16642 | NC 2016 | SHS | Region II | Cagayan | 300488 | Sta. Ana Fishery National High School | Santa Ana | 1 | 1 | 16 | 2STY8CL | BATCH 3 CL | 22300000 |  |  | Completed | 1
16643 | NC 2016 | TECHVOC | Region II | Cagayan | 300488 | Sta. Ana Fishery National High School | Santa Ana | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 4980000 |  |  | Completed | 1
16644 | NC 2016 | SHS | Region II | Cagayan | 300424 | Allacapan Vhs | Allacapan | 2 | 1 | 30 | 2STY10CL | BATCH 9 CL | 40050000 |  |  | Completed | 1
16645 | NC 2016 | SHS | Region II | Cagayan | 300424 | Allacapan Vhs | Allacapan | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 6550000 |  |  | Completed | 1
16646 | NC 2016 | SHS | Region II | Cagayan | 300424 | Allacapan Vhs | Allacapan | 2 |  | 3 | 1STY3CL | BATCH 9 CL | 2904910.9364 |  |  | Completed | 1
16647 | NC 2016 | TECHVOC | Region II | Cagayan | 300424 | Allacapan Vhs | Allacapan | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4350600 |  |  | Completed | 1
16648 | NC 2016 | SHS | Region II | Cagayan | 300434 | Ballesteros Nhs | Ballesteros | 2 | 1 | 18 | 3STY9CL | BATCH 9 CL | 30260000 |  |  | Completed | 1
16649 | NC 2016 | SHS | Region II | Cagayan | 300434 | Ballesteros Nhs | Ballesteros | 2 |  | 8 | 2STY8CL | BATCH 9 CL | 11930000 |  |  | Completed | 1
16650 | NC 2016 | SHS | Region II | Cagayan | 300434 | Ballesteros Nhs | Ballesteros | 2 |  | 3 | 1STY3CL | BATCH 9 CL | 2904910.9364 |  |  | Completed | 1
16651 | NC 2016 | TECHVOC | Region II | Cagayan | 300434 | Ballesteros Nhs | Ballesteros | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2490000 |  |  | Completed | 1
16652 | NC 2016 | SHS | Region II | Cagayan | 300486 | Sanchez Mira Sat | Sanchez-Mira | 2 | 1 | 30 | 2STY10CL | BATCH 3 CL | 40050000 |  |  | Completed | 1
16653 | NC 2016 | SHS | Region II | Cagayan | 300486 | Sanchez Mira Sat | Sanchez-Mira | 2 |  | 4 | 2STY4CL | BATCH 3 CL | 6550000 |  |  | Completed | 1
16654 | NC 2016 | TECHVOC | Region II | Cagayan | 300486 | Sanchez Mira Sat | Sanchez-Mira | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2490000 |  |  | Completed | 1
16655 | NC 2016 | SHS | Region II | Cagayan | 300426 | Andarayan Nhs | Solana | 3 | 1 | 15 | 3STY15CL | BATCH 3 CL | 20650000 |  |  | Completed | 1
16656 | NC 2016 | SHS | Region II | Cagayan | 300458 | Enrile Vocational High School | Enrile | 3 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11250000 |  |  | Completed | 1
16657 | NC 2016 | SHS | Region II | Cagayan | 300458 | Enrile Vocational High School | Enrile | 3 |  | 12 | 3STY12CL | BATCH 3 CL | 16750000 |  |  | Completed | 1
16658 | NC 2016 | TECHVOC | Region II | Cagayan | 300458 | Enrile Vocational High School | Enrile | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2850000 |  |  | Completed | 1
16659 | NC 2016 | TECHVOC | Region II | Cagayan | 300467 | Itawes National High School | Tuao | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2850000 |  |  | Completed | 1
16660 | NC 2016 | SHS | Region II | Cagayan | 300467 | Itawes National High School | Tuao | 3 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8450000 |  |  | Completed | 1
16661 | NC 2016 | SHS | Region II | Cagayan | 300467 | Itawes National High School | Tuao | 3 |  | 16 | 2STY8CL | BATCH 3 CL | 26950000 |  |  | Completed | 1
16662 | NC 2016 | K10 | Region II | City Of Ilagan | 103384 | Aggassian Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16663 | NC 2016 | K10 | Region II | City Of Ilagan | 103412 | Alibagu Elementary School | Ilagan (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2693142.91 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16664 | NC 2016 | K10 | Region II | City Of Ilagan | 103385 | Ballacong Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16665 | NC 2016 | K10 | Region II | City Of Ilagan | 155505 | Bangag Ps | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16666 | NC 2016 | K10 | Region II | City Of Ilagan | 155505 | Bangag Ps | Ilagan (Capital) | 1 |  | 1 | 1STY1CL | BATCH 7 CL | 1032098.36 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16667 | NC 2016 | K10 | Region II | City Of Ilagan | 103359 | Batong Labang Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY1CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16668 | NC 2016 | K10 | Region II | City Of Ilagan | 103417 | Bliss Es | Ilagan (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6607815.88 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-08 | 2016-06-21 | 2016-07-04 | 2016-07-15 | SMT CONSTRUCTION
16669 | NC 2016 | K10 | Region II | City Of Ilagan | 103418 | Cabannungan 1St Es | Ilagan (Capital) | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1032098.36 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16670 | NC 2016 | K10 | Region II | City Of Ilagan | 103389 | Cabeceria 23 E/S | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16671 | NC 2016 | K10 | Region II | City Of Ilagan | 103386 | Cadu Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16672 | NC 2016 | K10 | Region II | City Of Ilagan | 155506 | Calindayagan Elementary School | Ilagan (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2693142.91 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16673 | NC 2016 | K10 | Region II | City Of Ilagan | 103361 | Capellan Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16674 | NC 2016 | K10 | Region II | City Of Ilagan | 103396 | Capugotan Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | 4A'S CONSTRUCTION
16675 | NC 2016 | K10 | Region II | City Of Ilagan | 103398 | Dappat Integrated School | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16676 | NC 2016 | K10 | Region II | City Of Ilagan | 300548 | Dappat Integrated School | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16677 | NC 2016 | K10 | Region II | City Of Ilagan | 103401 | Gayong-Gayong Sur Integrated School | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16678 | NC 2016 | K10 | Region II | City Of Ilagan | 103401 | Gayong-Gayong Sur Integrated School | Ilagan (Capital) | 1 |  | 1 | 1STY1CL | BATCH 7 CL | 1032098.36 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-06-28 | 2016-07-11 | SMT CONSTRUCTION
16679 | NC 2016 | K10 | Region II | City Of Ilagan | 500087 | Gayong-Gayong Sur Is | Ilagan (Capital) | 1 |  | 6 | 2STY6CL | BATCH 7 CL | 8592082.81 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | SMT CONSTRUCTION
16680 | NC 2016 | K10 | Region II | City Of Ilagan | 500087 | Gayong-Gayong Sur Is | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-05-27 | 2016-06-03 | 2016-06-17 | 2016-06-29 | 2016-07-11 | JMU CONSTRUCTION
16681 | NC 2016 | K10 | Region II | City Of Ilagan | 300542 | Isabela Nhs - Main | Ilagan (Capital) | 1 | 1 | 36 | 4STY12CL | BATCH 9 CL | 73054690.29 |  |  | Completed | 1 |  |  |  |  | 2016-05-27 | 2016-06-03 | 2016-06-17 | 2016-06-29 | 2016-07-11 | EGB CONSTRUCTION
16682 | NC 2016 | K10 | Region II | City Of Ilagan | 300542 | Isabela Nhs - Main | Ilagan (Capital) | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 | 2016-06-16 | 2016-06-28 | 2016-07-08 | 2016-07-22 | JMU CONSTRUCTION
16683 | NC 2016 | SHS | Region II | City Of Ilagan |  | Isabela Sports Senior High School | Ilagan (Capital) | 1 | 1 | 20 | 2STY10CL | BATCH 5 CL | 28026882.22 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-05-03 | 2016-06-24 | 2016-07-07 | EGB CONSTRUCTION
16684 | NC 2016 | K10 | Region II | City Of Ilagan | 306149 | Isat-Cabannungan Annex | Ilagan (Capital) | 1 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15821387.21 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-05-03 | 2016-06-24 | 2016-07-07 | EGB CONSTRUCTION
16685 | NC 2016 | TECHVOC | Region II | City Of Ilagan | 306149 | Isat-Cabannungan Annex | Ilagan (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 |  |  |  |  | 2016-03-29 | 2016-04-05 | 2016-04-18 | 2016-05-20 | 2016-05-31 | E.S. PUA CONSTRUCTION
16686 | NC 2016 | SHS | Region II | City Of Ilagan | 306141 | Lupigue Integrated School | Ilagan (Capital) | 1 | 1 | 12 | 2STY12CL | BATCH 7 CL | 15253927.38 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 | 2016-06-16 | 2016-06-28 | 2016-07-08 | 2016-07-22 | EGB CONSTRUCTION
16687 | NC 2016 | TECHVOC | Region II | City Of Ilagan | 306141 | Lupigue Integrated School | Ilagan (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 |  |  |  |  | 2016-03-29 | 2016-04-05 | 2016-04-18 | 2016-05-20 | 2016-05-31 | SMT CONSTRUCTION
16688 | NC 2016 | K10 | Region II | City Of Ilagan | 103369 | Minabang Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16689 | NC 2016 | K10 | Region II | City Of Ilagan | 103370 | Morado Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16690 | NC 2016 | K10 | Region II | City Of Ilagan | 103371 | Nanaguan Primary School | Ilagan (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2743142.91 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | FOREF CONSTRUCTION
16691 | NC 2016 | K10 | Region II | City Of Ilagan | 103372 | Pasa Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16692 | NC 2016 | K10 | Region II | City Of Ilagan | 103430 | Pilar Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16693 | NC 2016 | K10 | Region II | City Of Ilagan | 103373 | Rang-Ayan Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16694 | NC 2016 | K10 | Region II | City Of Ilagan | 300543 | Rang-Ayan Nhs (Isabela Nhs - Rang-Ayan Annex) | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16695 | NC 2016 | SHS | Region II | City Of Ilagan | 300544 | San Lorenzo Integrated School | Ilagan (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2693142.91 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16696 | NC 2016 | K10 | Region II | City Of Ilagan | 103376 | San Lorenzo Integrated School (San Lorenzo Es) | Ilagan (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2693142.91 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16697 | NC 2016 | K10 | Region II | City Of Ilagan | 103394 | San Manuel Cabeceria 4 Es | Ilagan (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2693142.91 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | 4A'S CONSTRUCTION
16698 | NC 2016 | K10 | Region II | City Of Ilagan | 155519 | San Pablo-Quimalabasa Ps | Ilagan (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2693142.91 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16699 | NC 2016 | K10 | Region II | City Of Ilagan | 103407 | San Pedro Integrated School | Ilagan (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2693142.91 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16700 | NC 2016 | K10 | Region II | City Of Ilagan | 306129 | San Pedro Integrated School | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16701 | NC 2016 | K10 | Region II | City Of Ilagan | 306129 | San Pedro Integrated School | Ilagan (Capital) | 1 |  | 1 | 1STY1CL | BATCH 7 CL | 1032098.36 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16702 | NC 2016 | K10 | Region II | City Of Ilagan | 103410 | Sindun Bayabo Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16703 | NC 2016 | K10 | Region II | City Of Ilagan | 103411 | Sindun Maride Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16704 | NC 2016 | K10 | Region II | City Of Ilagan | 103378 | Sipay Elementary School | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16705 | NC 2016 | K10 | Region II | City Of Ilagan | 103379 | Sta. Catalina Es | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16706 | NC 2016 | SHS | Region II | City Of Ilagan | 300602 | Sta. Isabel Nhs | Ilagan (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 5 CL | 29357716.36 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-05-03 | 2016-06-24 | 2016-07-07 | C.T. LEONCIO CONSTRUCTION AND TRADING / DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16707 | NC 2016 | SHS | Region II | City Of Ilagan | 300602 | Sta. Isabel Nhs | Ilagan (Capital) | 1 |  | 10 | 2STY10CL | BATCH 5 CL | 14033441.11 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-05-03 | 2016-06-24 | 2016-07-07 | EGB CONSTRUCTION
16708 | NC 2016 | K10 | Region II | City Of Ilagan | 103437 | Sto. Tomas Es | Ilagan (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6607815.88 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-08 | 2016-06-21 | 2016-07-04 | 2016-07-15 | FOREF CONSTRUCTION
16709 | NC 2016 | K10 | Region II | City Of Ilagan | 103383 | Villa Imelda Ps | Ilagan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-25 | 2016-05-03 | 2016-05-17 | 2016-06-28 | 2016-07-11 | DRAGON TWELVE BUILDERS AND CONSTRUCTION SUPPLIES
16710 | NC 2016 | SHS | Region II | Isabela | 300521 | Alfreda Albano Nhs - Magassi, Cabagan | Cabagan | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 11378953.13 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-06-08 | 2016-06-24 | 2016-07-07 | EGB CONSTRUCTION
16711 | NC 2016 | SHS | Region II | Isabela | 300521 | Alfreda Albano Nhs - Magassi, Cabagan | Cabagan | 1 |  | 6 | 2STY6CL | BATCH 7 CL | 8592082.81 |  |  | Completed | 1 |  |  |  |  | 2016-05-27 | 2016-06-03 | 2016-06-17 | 2016-06-29 | 2016-07-11 | 4A'S CONSTRUCTION
16712 | NC 2016 | TECHVOC | Region II | Isabela | 300521 | Alfreda Albano Nhs - Magassi, Cabagan | Cabagan | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4860000 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-05-24 | 2016-06-02 | FRAGERR CONSTRUCTION
16713 | NC 2016 | K10 | Region II | Isabela | 306167 | Alfreda Albano Nhs-Masipi Annex | Cabagan | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6607815.88 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-08 | 2016-06-21 | 2016-07-04 | 2016-07-15 | FRAGERR CONSTRUCTION
16714 | NC 2016 | K10 | Region II | Isabela | 103265 | Aneg Elementary School | Delfin Albano (Magsaysay) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | M.C. TAGUBA CONSTRUCTION
16715 | NC 2016 | K10 | Region II | Isabela | 306133 | Aneg National High School | Delfin Albano (Magsaysay) | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2693142.91 |  |  | Completed | 1 |  |  |  |  | 2016-05-03 | 2016-05-10 | 2016-05-23 | 2016-06-24 | 2016-07-11 | M.C. TAGUBA CONSTRUCTION
16716 | NC 2016 | K10 | Region II | Isabela | 306162 | Bayabo Integrated School | Delfin Albano (Magsaysay) | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2693142.91 |  |  | Completed | 1 |  |  |  |  | 2016-05-03 | 2016-05-10 | 2016-05-23 | 2016-06-24 | 2016-07-11 | ATLANTIC CONSTRUCTION
16717 | NC 2016 | K10 | Region II | Isabela | 300605 | Buenaventura G. Masigan National High School | Santa Maria | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8592082.81 |  |  | Completed | 1 |  |  |  |  | 2016-05-27 | 2016-06-03 | 2016-06-17 | 2016-06-29 | 2016-07-11 | EDISON CONSTRUCTION AND DEVELOPMENT
16718 | NC 2016 | TECHVOC | Region II | Isabela | 300605 | Buenaventura G. Masigan National High School | Santa Maria | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 |  |  |  |  | 2016-03-29 | 2016-04-05 | 2016-04-18 | 2016-05-20 | 2016-05-31 | ATLANTIC CONSTRUCTION
16719 | NC 2016 | K10 | Region II | Isabela | 103844 | Buenavista Elementary School | Santa Maria | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2693142.91 |  |  | Completed | 1 |  |  |  |  | 2016-05-03 | 2016-05-10 | 2016-05-23 | 2016-06-24 | 2016-07-11 | EDISON CONSTRUCTION AND DEVELOPMENT
16720 | NC 2016 | K10 | Region II | Isabela | 306101 | Calanigan National High School | Santo Tomas | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8592082.81 |  |  | Completed | 1 |  |  |  |  | 2016-05-27 | 2016-06-03 | 2016-06-17 | 2016-06-29 | 2016-07-11 | RSKC CONSTRUCTION
16721 | NC 2016 | K10 | Region II | Isabela | 103267 | Capitol Elementary School | Delfin Albano (Magsaysay) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-05-03 | 2016-05-10 | 2016-05-23 | 2016-06-24 | 2016-07-11 | ATLANTIC CONSTRUCTION
16722 | NC 2016 | K10 | Region II | Isabela | 103268 | Carmencita Elementary School | Delfin Albano (Magsaysay) | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1032098.36 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-06-28 | 2016-07-11 | V.R.D.J. CONSTRUCTION
16723 | NC 2016 | K10 | Region II | Isabela | 306153 | Cumabao Integrated School | Tumauini | 1 | 1 | 16 | 2STY8CL | BATCH 7 CL | 22757906.26 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-06-08 | 2016-06-24 | 2016-07-07 | EGB CONSTRUCTION
16724 | NC 2016 | TECHVOC | Region II | Isabela | 306153 | Cumabao Integrated School | Tumauini | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 8442082.81 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-08 | 2016-06-21 | 2016-07-04 | 2016-07-15 | RSKC CONSTRUCTION
16725 | NC 2016 | K10 | Region II | Isabela | 155533 | Dalayya Elementary School | Tumauini | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1032098.36 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-06-28 | 2016-07-11 | SMT CONSTRUCTION
16726 | NC 2016 | K10 | Region II | Isabela | 300522 | Delfin Albano High School - San Juan Annex | Cabagan | 1 | 1 | 16 | 2STY8CL | BATCH 7 CL | 22757906.26 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-06-08 | 2016-06-24 | 2016-07-07 | EGB CONSTRUCTION
16727 | NC 2016 | TECHVOC | Region II | Isabela | 300522 | Delfin Albano High School - San Juan Annex | Cabagan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 |  |  |  |  | 2016-03-29 | 2016-04-05 | 2016-04-18 | 2016-05-20 | 2016-05-31 | V.R.D.J. CONSTRUCTION
16728 | NC 2016 | K10 | Region II | Isabela | 300520 | Delfin Albano High School-Main | Cabagan | 1 | 1 | 30 | 3STY15CL | BATCH 5 CL | 47012629.58 |  |  | Completed | 1 |  |  |  |  | 2016-05-27 | 2016-06-03 | 2016-06-17 | 2016-06-29 | 2016-07-11 | EGB CONSTRUCTION
16729 | NC 2016 | TECHVOC | Region II | Isabela | 300520 | Delfin Albano High School-Main | Cabagan | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 4860000 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-05-24 | 2016-06-02 | FRAGERR CONSTRUCTION
16730 | NC 2016 | K10 | Region II | Isabela | 306109 | Fermeldy National High School | Tumauini | 1 | 1 | 16 | 2STY8CL | BATCH 7 CL | 22757906.26 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-06-08 | 2016-06-24 | 2016-07-07 | EGB CONSTRUCTION
16731 | NC 2016 | TECHVOC | Region II | Isabela | 306109 | Fermeldy National High School | Tumauini | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 |  |  |  |  | 2016-03-29 | 2016-04-05 | 2016-04-18 | 2016-05-20 | 2016-05-31 | V.R.D.J. CONSTRUCTION
16732 | NC 2016 | K10 | Region II | Isabela | 103270 | Jimenez Multigrade School | Delfin Albano (Magsaysay) | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1032098.36 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-06-28 | 2016-07-11 | V.R.D.J. CONSTRUCTION
16733 | NC 2016 | K10 | Region II | Isabela | 300556 | Lalauanan National High School | Tumauini | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8592082.81 |  |  | Completed | 1 |  |  |  |  | 2016-05-27 | 2016-06-03 | 2016-06-17 | 2016-06-29 | 2016-07-11 | JMU CONSTRUCTION
16734 | NC 2016 | K10 | Region II | Isabela | 300551 | Lanna National High School | Tumauini | 1 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10897222.57 |  |  | Completed | 1 |  |  |  |  | 2016-06-08 | 2016-06-16 | 2016-06-28 | 2016-07-08 | 2016-07-22 | E.S. PUA CONSTRUCTION
16735 | NC 2016 | K10 | Region II | Isabela | 155536 | Pallacot Elementary School | Tumauini | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1032098.36 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-06-28 | 2016-07-11 | SMT CONSTRUCTION
16736 | NC 2016 | K10 | Region II | Isabela | 300587 | Ragan Sur National High School | Delfin Albano (Magsaysay) | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8592082.81 |  |  | Completed | 1 |  |  |  |  | 2016-05-27 | 2016-06-03 | 2016-06-17 | 2016-06-29 | 2016-07-11 | EGB CONSTRUCTION
16737 | NC 2016 | SHS | Region II | Isabela | 300610 | Regional Science High School For Region Ii | Tumauini | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6607815.88 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-08 | 2016-06-21 | 2016-07-04 | 2016-07-15 | SMT CONSTRUCTION
16738 | NC 2016 | K10 | Region II | Isabela | 103273 | San Andres Elementary School | Delfin Albano (Magsaysay) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-05-03 | 2016-05-10 | 2016-05-23 | 2016-06-24 | 2016-07-11 | 969 CONSTRUCTION AND SUPPLIES
16739 | NC 2016 | SHS | Region II | Isabela | 300585 | San Antonio National High School | Delfin Albano (Magsaysay) | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 11378953.13 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-06-08 | 2016-06-24 | 2016-07-07 | F.A. ASPRER CONSTRUCTION
16740 | NC 2016 | SHS | Region II | Isabela | 300585 | San Antonio National High School | Delfin Albano (Magsaysay) | 1 |  | 6 | 2STY6CL | BATCH 7 CL | 8592082.81 |  |  | Completed | 1 |  |  |  |  | 2016-05-27 | 2016-06-03 | 2016-06-17 | 2016-06-29 | 2016-07-11 | ATLANTIC CONSTRUCTION
16741 | NC 2016 | TECHVOC | Region II | Isabela | 300585 | San Antonio National High School | Delfin Albano (Magsaysay) | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4860000 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-05-24 | 2016-06-02 | V.R.D.J. CONSTRUCTION
16742 | NC 2016 | K10 | Region II | Isabela | 103277 | San Macario Multigrade | Delfin Albano (Magsaysay) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-05-03 | 2016-05-10 | 2016-05-23 | 2016-06-24 | 2016-07-11 | 969 CONSTRUCTION AND SUPPLIES
16743 | NC 2016 | SHS | Region II | Isabela | 300597 | San Pablo National High School | San Pablo | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6607815.88 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-08 | 2016-06-21 | 2016-07-04 | 2016-07-15 | M.C. TAGUBA CONSTRUCTION
16744 | NC 2016 | K10 | Region II | Isabela | 103279 | San Ramon Elementary School | Delfin Albano (Magsaysay) | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1850690.17 |  |  | Completed | 1 |  |  |  |  | 2016-04-27 | 2016-05-05 | 2016-05-19 | 2016-06-28 | 2016-07-11 | ATLANTIC CONSTRUCTION
16745 | NC 2016 | SHS | Region II | Isabela | 300603 | Santa Maria High School | Santa Maria | 1 | 1 | 16 | 4STY16CL | BATCH 7 CL | 27944062.9 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-06-08 | 2016-06-24 | 2016-07-07 | EGB CONSTRUCTION
16746 | NC 2016 | TECHVOC | Region II | Isabela | 300603 | Santa Maria High School | Santa Maria | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 |  |  |  |  | 2016-03-29 | 2016-04-05 | 2016-04-18 | 2016-05-20 | 2016-05-31 | FRAGERR CONSTRUCTION
16747 | NC 2016 | K10 | Region II | Isabela | 103280 | Santor Primary School | Delfin Albano (Magsaysay) | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1032098.36 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-06-28 | 2016-07-11 | ATLANTIC CONSTRUCTION
16748 | NC 2016 | SHS | Region II | Isabela | 306132 | Simanu National High School | San Pablo | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6607815.88 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-08 | 2016-06-21 | 2016-07-04 | 2016-07-15 | FRAGERR CONSTRUCTION
16749 | NC 2016 | K10 | Region II | Isabela | 103810 | Simanu Sur Elementary School | San Pablo | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2693142.91 |  |  | Completed | 1 |  |  |  |  | 2016-05-03 | 2016-05-10 | 2016-05-23 | 2016-06-24 | 2016-07-11 | FRAGERR CONSTRUCTION
16750 | NC 2016 | K10 | Region II | Isabela | 300601 | St. Paul Vocational & Industrial High School | San Pablo | 1 | 1 | 18 | 3STY9CL | BATCH 7 CL | 31642774.42 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-06-08 | 2016-06-24 | 2016-07-07 | EGB CONSTRUCTION
16751 | NC 2016 | TECHVOC | Region II | Isabela | 300601 | St. Paul Vocational & Industrial High School | San Pablo | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4860000 |  |  | Completed | 1 |  |  |  |  | 2016-04-19 | 2016-04-27 | 2016-05-10 | 2016-05-24 | 2016-06-02 | ATLANTIC CONSTRUCTION
16752 | NC 2016 | K10 | Region II | Isabela | 300606 | Sto Tomas National High School | Santo Tomas | 1 | 1 | 18 | 3STY9CL | BATCH 7 CL | 31642774.42 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-06-08 | 2016-06-24 | 2016-07-07 | RSKC CONSTRUCTION/EDMARI CONSTRUCTION AND TRADING
16753 | NC 2016 | TECHVOC | Region II | Isabela | 300606 | Sto Tomas National High School | Santo Tomas | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 |  |  |  |  | 2016-03-29 | 2016-04-05 | 2016-04-18 | 2016-05-20 | 2016-05-31 | V.R.D.J. CONSTRUCTION
16754 | NC 2016 | K10 | Region II | Isabela | 300609 | Tumauini National High School | Tumauini | 1 | 1 | 24 | 3STY12CL | BATCH 5 CL | 39058990 |  |  | Completed | 1 |  |  |  |  | 2016-06-10 | 2016-06-17 | 2016-06-29 | 2016-07-13 | 2016-08-15 | EGB CONSTRUCTION
16755 | NC 2016 | TECHVOC | Region II | Isabela | 300609 | Tumauini National High School | Tumauini | 1 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 7290000 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-21 | 2016-05-03 | 2016-05-20 | 2016-05-31 | FRAGERR CONSTRUCTION
16756 | NC 2016 | K10 | Region II | Isabela | 300593 | Alibadbad National High School | San Mariano | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10877342.59 |  |  | Completed | 1
16757 | NC 2016 | K10 | Region II | Isabela | 103099 | Andabuen Elementary School - Annex | Benito Soliven | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1824740.17 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09
16758 | NC 2016 | SHS | Region II | Isabela | 300546 | Andabuen National High School | Benito Soliven | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6359337.64 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27
16759 | NC 2016 | K10 | Region II | Isabela | 103101 | Balliao Elementary School | Benito Soliven | 2 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2680828.12 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27
16760 | NC 2016 | SHS | Region II | Isabela | 306112 | Barucboc National High School | Quezon | 5 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09
16761 | NC 2016 | SHS | Region II | Isabela | 306112 | Barucboc National High School | Quezon | 5 |  | 8 | 2STY8CL | BATCH 7 CL | 10877342.59 |  |  | Completed | 1
16762 | NC 2016 | K10 | Region II | Isabela | 300503 | Benito Soliven National High School | Benito Soliven | 2 |  | 4 | 1STY2CL | BATCH 3 CL | 3629480.34 |  |  | Completed | 1
16763 | NC 2016 | K10 | Region II | Isabela | 300503 | Benito Soliven National High School | Benito Soliven | 2 | 1 | 10 | 2STY10CL | BATCH 3 CL | 12771310.09 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09
16764 | NC 2016 | SHS | Region II | Isabela | 306138 | Bimonton Integrated School | Mallig | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27
16765 | NC 2016 | K10 | Region II | Isabela | 155517 | Binogtungan Elementary School | Benito Soliven | 2 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1032049.65 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09
16766 | NC 2016 | SHS | Region II | Isabela | 306157 | Cabaruan Integrated School | Naguilian | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.06 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09
16767 | NC 2016 | K10 | Region II | Isabela | 300509 | Caliguian National High School-Main | Burgos | 5 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10877342.59 |  |  | Completed | 1
16768 | NC 2016 | K10 | Region II | Isabela | 300512 | Callang National High School - Main | San Manuel | 5 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.06 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09
16769 | NC 2016 | K10 | Region II | Isabela | 155524 | Camarunggayan Es - Saranay Ps | Aurora | 5 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1012049.65 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09
16770 | NC 2016 | K10 | Region II | Isabela | 300519 | Del Pilar Integrated School | San Mariano | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27
16771 | NC 2016 | TECHVOC | Region II | Isabela |  | Dona Aurora Senior High School | Aurora | 5 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 4756000 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09
16772 | NC 2016 | SHS | Region II | Isabela |  | Dona Aurora Senior High School | Aurora | 5 | 1 | 45 | 3STY15CL | BATCH 5 CL | 64149040.35 |  |  | Completed | 1
16773 | NC 2016 | K10 | Region II | Isabela | 306161 | Eden Integrated School | San Manuel | 5 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27
16774 | NC 2016 | TECHVOC | Region II | Isabela | 300537 | Gamu Rural School-Main | Gamu | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 4756000 |  |  | Completed | 1
16775 | NC 2016 | SHS | Region II | Isabela | 300537 | Gamu Rural School-Main | Gamu | 2 | 1 | 8 | 2STY8CL | BATCH 3 CL | 10877342.59 |  |  | Completed | 1
16776 | NC 2016 | SHS | Region II | Isabela | 300537 | Gamu Rural School-Main | Gamu | 2 |  | 10 | 2STY10CL | BATCH 3 CL | 12771310.09 |  |  | Completed | 1
16777 | NC 2016 | K10 | Region II | Isabela | 103106 | Gomez Elementary School | Benito Soliven | 2 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2680828.12 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27
16778 | NC 2016 | K10 | Region II | Isabela | 103631 | Imbiao Elementary School | Roxas | 5 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2640828.12 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27
16779 | NC 2016 | SHS | Region II | Isabela | 300559 | Mabini National High School | Gamu | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.06 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09
16780 | NC 2016 | K10 | Region II | Isabela | 300513 | Malalinta National High School | San Manuel | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27
16781 | NC 2016 | K10 | Region II | Isabela | 300561 | Mallig National High School | Mallig | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27
16782 | NC 2016 | K10 | Region II | Isabela | 306166 | Mallig Nhs-Centro I Annex | Mallig | 5 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10877342.59 |  |  | Completed | 1
16783 | NC 2016 | K10 | Region II | Isabela | 306166 | Mallig Nhs-Centro I Annex | Mallig | 5 |  | 1 | 1STY1CL | BATCH 7 CL | 1012049.65 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09
16784 | NC 2016 | SHS | Region II | Isabela | 306135 | Matusalem National High School | Roxas | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27
16785 | NC 2016 | K10 | Region II | Isabela | 306155 | Minagbag High School | Quezon | 5 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27
16786 | NC 2016 | K10 | Region II | Isabela | 306111 | Monico Rarama National High School | Roxas | 5 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.06 |  |  | Completed | 1
16787 | NC 2016 | K10 | Region II | Isabela | 306111 | Monico Rarama National High School | Roxas | 5 |  | 1 | 1STY1CL | BATCH 7 CL | 1012049.65 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09
16788 | NC 2016 | K10 | Region II | Isabela | 300562 | Munoz High School | Roxas | 5 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.06 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09
16789 | NC 2016 | K10 | Region II | Isabela | 103113 | Nacalma Elementary School | Benito Soliven | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1864740.17 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09
16790 | NC 2016 | SHS | Region II | Isabela | 300563 | Naguillian National High School | Naguilian | 2 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12771310.09 |  |  | Completed | 1
16791 | NC 2016 | SHS | Region II | Isabela | 300563 | Naguillian National High School | Naguilian | 2 |  | 6 | 2STY6CL | BATCH 7 CL | 8214965.06 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09
16792 | NC 2016 | K10 | Region II | Isabela | 103116 | Punit Es | Benito Soliven | 2 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2640828.12 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27
16793 | NC 2016 | SHS | Region II | Isabela | 300568 | Quezon National High School | Quezon | 5 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12771310.09 |  |  | Completed | 1
16794 | NC 2016 | K10 | Region II | Isabela | 300569 | Quirino National High School | Quirino | 5 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12771310.09 |  |  | Completed | 1
16795 | NC 2016 | K10 | Region II | Isabela | 103134 | Raniag Elementary School | Burgos | 5 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1012049.65 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09
16796 | NC 2016 | K10 | Region II | Isabela | 155515 | Rizal Primary School | Gamu | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27
16797 | NC 2016 | K10 | Region II | Isabela | 300579 | Roxas National High School | Roxas | 5 | 1 | 32 | 4STY16CL | BATCH 3 CL | 53744938.84 |  |  | Completed | 1
16798 | NC 2016 | K10 | Region II | Isabela | 300511 | San Antonino National High School | Burgos | 5 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12771310.09 |  |  | Completed | 1
16799 | NC 2016 | K10 | Region II | Isabela | 300511 | San Antonino National High School | Burgos | 5 |  | 1 | 1STY1CL | BATCH 7 CL | 1012049.65 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09
16800 | NC 2016 | K10 | Region II | Isabela | 103118 | San Francisco Elementary School | Benito Soliven | 2 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1042049.65 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09
16801 | NC 2016 | SHS | Region II | Isabela | 306110 | San Jose National High School | Mallig | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27
16802 | NC 2016 | K10 | Region II | Isabela | 306165 | San Mariano Ii Central Integrated School | San Mariano | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27
16803 | NC 2016 | K10 | Region II | Isabela | 300592 | San Mariano National High School - Main | San Mariano | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11077342.59 |  |  | Completed | 1
16804 | NC 2016 | K10 | Region II | Isabela | 300592 | San Mariano National High School - Main | San Mariano | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1
16805 | NC 2016 | K10 | Region II | Isabela | 300592 | San Mariano National High School - Main | San Mariano | 2 |  | 2 | 1STY2CL | BATCH 9 CL | 1814740.17 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09
16806 | NC 2016 | K10 | Region II | Isabela | 300514 | Sandiat National High School | San Manuel | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27
16807 | NC 2016 | K10 | Region II | Isabela | 103120 | Sevillana Elementary School | Benito Soliven | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27
16808 | NC 2016 | SHS | Region II | Isabela | 306163 | Simimbaan Integrated School | Roxas | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27
16809 | NC 2016 | K10 | Region II | Isabela | 306144 | Sto. Domingo Integrated School | Quirino | 5 | 1 | 4 | 1STY4CL | BATCH 7 CL | 3464886.58 |  |  | Completed | 1
16810 | NC 2016 | K10 | Region II | Isabela | 103532 | Tomines Elementary School | Naguilian | 2 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1012049.65 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09
16811 | NC 2016 | K10 | Region II | Isabela | 103507 | Trinidad Elementary School | Mallig | 5 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1012049.65 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09
16812 | NC 2016 | K10 | Region II | Isabela | 155511 | Udiao Elementary School | San Mariano | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27
16813 | NC 2016 | SHS | Region II | Isabela | 306103 | Villa Cacho Integrated School | Quirino | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27
16814 | NC 2016 | K10 | Region II | Isabela | 103593 | Villa Miguel Primary School | Quirino | 5 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1012049.65 |  |  | Completed | 1 | [5 empty] | 2016-07-28 | 2016-08-09
16815 | NC 2016 | K10 | Region II | Isabela | 103767 | Villa Miranda Elementary School | San Mariano | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1874740.17 |  |  | Completed | 1 | [5 empty] | 2016-07-15 | 2016-07-27
16816 | NC 2016 | SHS | Region II | Isabela | 300500 | Alicia National High School | Alicia | 3 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31102890.27 |  |  | Completed | 1 | [5 empty] | 2016-06-15 | 2016-06-27 |  | 2016-06-29 | July 7,2016
16817 | NC 2016 | SHS | Region II | Isabela | 300500 | Alicia National High School | Alicia | 3 |  | 6 | 2STY6CL | BATCH 3 CL | 8214965.05 |  |  | Completed | 1 | [5 empty] | 2016-03-16 | 2016-03-28 |  | 2016-05-10 | May 13,2016
16818 | NC 2016 | SHS | Region II | Isabela | 300499 | Alicia Vocational School | Alicia | 3 | 1 | 15 | 3STY15CL | BATCH 7 CL | 21383013.45 |  |  | Completed | 1
16819 | NC 2016 | K10 | Region II | Isabela | 300501 | Angadanan National High School | Angadanan | 3 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18222268.79 |  |  | Completed | 1 | [5 empty] | 2016-06-16 | 2016-06-28 |  | 2016-06-29 | July 7,2016
16820 | NC 2016 | K10 | Region II | Isabela | 103769 | Bagong Sikat Es - Annex 1 | San Mateo | 3 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.174 |  |  | Completed | 1 | [5 empty] | 2016-03-16 | 2016-03-28 |  | 2016-05-10 | May 13,2016
16821 | NC 2016 | K10 | Region II | Isabela | 103012 | Bonifacio Elementary School | Alicia | 3 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.174 |  |  | Completed | 1 | [5 empty] | 2016-03-16 | 2016-03-28 |  | 2016-05-10 | May 13,2016
16822 | NC 2016 | K10 | Region II | Isabela | 103675 | Burgos West Elementary School | San Guillermo | 6 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1072049.6543 |  |  | Completed | 1 | [5 empty] | 2016-08-11 | 2016-08-23 |  | 2016-08-26 | August 29,2016
16823 | NC 2016 | K10 | Region II | Isabela | 300504 | Cabatuan National High School | Cabatuan | 3 | 1 | 12 | 4STY12CL | BATCH 3 CL | 22152343.62 |  |  | Completed | 1 | [5 empty] | 2016-06-15 | 2016-07-15 |  | 2016-07-20 | July 27,2016
16824 | NC 2016 | K10 | Region II | Isabela | 300504 | Cabatuan National High School | Cabatuan | 3 |  | 8 | 4STY8CL | BATCH 3 CL | 14897518.84 |  |  | Completed | 1 | [5 empty] | 2016-06-16 | 2016-06-29 |  | 2016-06-30 | July 8,2016
16825 | NC 2016 | TECHVOC | Region II | Isabela | 300504 | Cabatuan National High School | Cabatuan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2500000 |  |  | Completed | 1
16826 | NC 2016 | K10 | Region II | Isabela | 300506 | Cadaloria High School | Angadanan | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1
16827 | NC 2016 | K10 | Region II | Isabela | 103029 | Calaocan Elementary School | Angadanan | 3 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1889740.174 |  |  | Completed | 1 | [5 empty] | 2016-03-16 | 2016-03-28 |  | 2016-05-10 | May 13,2016
16828 | NC 2016 | K10 | Region II | Isabela | 103679 | Dingading Integrated School | San Guillermo | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1889740.174 |  |  | Completed | 1 | [5 empty] | 2016-03-16 | 2016-03-28 |  | 2016-05-10 | May 13,2016
16829 | NC 2016 | K10 | Region II | Isabela | 306154 | Ingud-Ramona Integrated School | Angadanan | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 | [5 empty] | 2016-06-15 | 2016-06-27 |  | 2016-06-29 | July 7,2016
16830 | NC 2016 | SHS | Region II | Isabela | 306114 | La Paz National High School | Cabatuan | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1
16831 | NC 2016 | K10 | Region II | Isabela | 306150 | Luna General Comprehensive High School | Luna | 5 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10877342.5917 |  |  | Completed | 1
16832 | NC 2016 | SHS | Region II | Isabela | 300558 | Luna National High School | Luna | 5 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [5 empty] | 2016-06-15 | 2016-06-27 |  | 2016-06-29 | July 7,2016
16833 | NC 2016 | SHS | Region II | Isabela | 300558 | Luna National High School | Luna | 5 |  | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [5 empty] | 2016-06-15 | 2016-06-27 |  | 2016-06-29 | July 7,2016
16834 | NC 2016 | TECHVOC | Region II | Isabela | 300558 | Luna National High School | Luna | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2418000 |  |  | Completed | 1
16835 | NC 2016 | K10 | Region II | Isabela | 102993 | Mataas Na Kahoy Elementary School | Alicia | 3 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1012049.6543 |  |  | Completed | 1
16836 | NC 2016 | K10 | Region II | Isabela | 300565 | Palayan Region High School | Alicia | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1
16837 | NC 2016 | SHS | Region II | Isabela | 300575 | Reina Mercedes Vocational And Industrial School | Reina Mercedes | 3 | 1 | 32 | 4STY32CL | BATCH 5 CL | 44532220.04 |  |  | Completed | 1 | [5 empty] | 2016-06-16 | 2016-06-29 |  | 2016-06-30 | July 8,2016
16838 | NC 2016 | TECHVOC | Region II | Isabela | 300575 | Reina Mercedes Vocational And Industrial School | Reina Mercedes | 3 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 4756000 |  |  | Completed | 1 | [5 empty] | 2016-03-16 | 2016-03-28 |  | 2016-05-10 | May 13,2016
16839 | NC 2016 | SHS | Region II | Isabela | 306116 | Reina Mercedes Vocational High School | Reina Mercedes | 3 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10877342.5917 |  |  | Completed | 1
16840 | NC 2016 | TECHVOC | Region II | Isabela | 306116 | Reina Mercedes Vocational High School | Reina Mercedes | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2418000 |  |  | Completed | 1 | [5 empty] | 2016-06-15 | 2016-06-27 |  | 2016-06-29 | July 7,2016
16841 | NC 2016 | SHS | Region II | Isabela | 300577 | Rizal Integrated School, San Guillermo | San Guillermo | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6469337.6381 |  |  | Completed | 1
16842 | NC 2016 | K10 | Region II | Isabela | 300576 | Rizal Region National High School | Alicia | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1
16843 | NC 2016 | K10 | Region II | Isabela | 300581 | Salinungan National High School | San Mateo | 3 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1
16844 | NC 2016 | K10 | Region II | Isabela | 300590 | San Guillermo Vocational & Industrial High School | San Guillermo | 6 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22252343.62 |  |  | Completed | 1 | [5 empty] | 2016-06-15 | 2016-06-27 |  | 2016-06-29 | July 7,2016
16845 | NC 2016 | TECHVOC | Region II | Isabela | 300590 | San Guillermo Vocational & Industrial High School | San Guillermo | 6 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4896000 |  |  | Completed | 1 | [5 empty] | 2016-03-16 | 2016-03-28 |  | 2016-05-10 | May 13,2016
16846 | NC 2016 | K10 | Region II | Isabela | 103002 | San Juan Elementary School | Alicia | 3 | 1 | 4 | 1STY4CL | BATCH 7 CL | 3464886.575 |  |  | Completed | 1
16847 | NC 2016 | K10 | Region II | Isabela | 300596 | San Mateo Vocational And Industrial High School | San Mateo | 3 | 1 | 28 | 4STY28CL | BATCH 9 CL | 40067946.14 |  |  | Completed | 1 | [5 empty] | 2016-06-16 | 2016-06-29 |  | 2016-06-30 | July 8,2016
16848 | NC 2016 | K10 | Region II | Isabela | 300596 | San Mateo Vocational And Industrial High School | San Mateo | 3 |  | 8 | 2STY8CL | BATCH 9 CL | 10877342.59 |  |  | Completed | 1 | [5 empty] | 2016-06-15 | 2016-06-27 |  | 2016-06-29 | July 7,2016
16849 | NC 2016 | TECHVOC | Region II | Isabela | 300596 | San Mateo Vocational And Industrial High School | San Mateo | 3 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4350600 |  |  | Completed | 1 | [5 empty] | 2016-06-15 | 2016-06-27 |  | 2016-06-29 | July 7,2016
16850 | NC 2016 | SHS | Region II | Isabela | 300607 | Sto. Niño Integrated School | Angadanan | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.051 |  |  | Completed | 1 | [5 empty] | 2016-03-16 | 2016-03-28 |  | 2016-05-10 | May 13,2016
16851 | NC 2016 | K10 | Region II | Isabela | 103695 | Villa Remedios Primary School | San Guillermo | 6 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1062049.6543 |  |  | Completed | 1
16852 | NC 2016 | K10 | Region II | Isabela | 103283 | Aromin Elementary School | Echague | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.174 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14
16853 | NC 2016 | K10 | Region II | Isabela | 103441 | Bantay Primary School | Jones | 4 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1012049.6543 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14
16854 | NC 2016 | SHS | Region II | Isabela | 306143 | Cagasat Hs-Magsasay Annex | Cordon | 4 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.051 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-09 | 2016-06-23
16855 | NC 2016 | K10 | Region II | Isabela | 300518 | Dabubu High School - Main | San Agustin | 4 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.174 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14
16856 | NC 2016 | K10 | Region II | Isabela | 306168 | Dabubu Hs-Annex | San Agustin | 4 | 1 | 4 | 1STY4CL | BATCH 7 CL | 3614886.575 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14
16857 | NC 2016 | K10 | Region II | Isabela | 300523 | Diadi Region High School | Cordon | 4 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.051 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-09 | 2016-06-23
16858 | NC 2016 | SHS | Region II | Isabela | 300524 | Dibuluan National High School | Jones | 4 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14
16859 | NC 2016 | K10 | Region II | Isabela | 300529 | Don Mariano Marcos National High School | Echague | 6 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.051 |  |  | Completed | 1 |  |  |  |  | 2016-06-14 | 2016-06-22 | 2016-07-05
16860 | NC 2016 | K10 | Region II | Isabela | 300532 | Dona Josefa E. Marcos High School | Cordon | 4 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.051 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-09 | 2016-06-23
16861 | NC 2016 | K10 | Region II | Isabela | 300533 | Dona Magdalena H. Gaffud High School | Echague | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14
16862 | NC 2016 | SHS | Region II | Isabela | 300612 | Echague National High School | Echague | 6 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.051 |  |  | Completed | 1 |  |  |  |  | 2016-07-20 | 2016-07-28 | 2016-08-09
16863 | NC 2016 | K10 | Region II | Isabela | 300572 | Gen. Emilio Aguinaldo National High School | Ramon | 4 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14
16864 | NC 2016 | K10 | Region II | Isabela | 300539 | Highway Region National High School | Echague | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14
16865 | NC 2016 | K10 | Region II | Isabela | 300541 | Imelda R. Marcos High School | Echague | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14
16866 | NC 2016 | SHS | Region II | Isabela | 300555 | Jones Rural School - Main | Jones | 4 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10877342.5917 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-09 | 2016-06-23
16867 | NC 2016 | SHS | Region II | Isabela | 300555 | Jones Rural School - Main | Jones | 4 |  | 6 | 2STY6CL | BATCH 7 CL | 8214965.051 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-09 | 2016-06-23
16868 | NC 2016 | TECHVOC | Region II | Isabela | 300555 | Jones Rural School - Main | Jones | 4 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4836000 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-09 | 2016-06-23
16869 | NC 2016 | K10 | Region II | Isabela | 103448 | Linomot Elementary School | Jones | 4 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1864740.174 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14
16870 | NC 2016 | K10 | Region II | Isabela | 103660 | Palacian Elementary School | San Agustin | 4 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1864740.174 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14
16871 | NC 2016 | K10 | Region II | Isabela | 300566 | Pangal Sur High School | Echague | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14
16872 | NC 2016 | K10 | Region II | Isabela | 300571 | Ramon National High School | Ramon | 4 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.051 |  |  | Completed | 1 |  |  |  |  | 2016-07-20 | 2016-07-28
16873 | NC 2016 | K10 | Region II | Isabela | 300574 | Raniag High School | Ramon | 4 |  | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-09 | 2016-06-23
16874 | NC 2016 | TECHVOC | Region II | Isabela | 300574 | Raniag High School | Ramon | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2418000 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-09 | 2016-06-23
16875 | NC 2016 | K10 | Region II | Isabela | 300574 | Raniag High School | Ramon | 4 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-09 | 2016-06-23
16876 | NC 2016 | K10 | Region II | Isabela | 103299 | Salvacion Elementary School | Echague | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.174 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14
16877 | NC 2016 | SHS | Region II | Isabela | 300582 | San Agustin National High School | San Agustin | 4 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-09 | 2016-06-23
16878 | NC 2016 | K10 | Region II | Isabela | 103319 | San Felipe Elementary School | Echague | 6 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2640828.124 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14
16879 | NC 2016 | TECHVOC | Region II | Isabela | 300591 | San Isidro National High School | San Isidro | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2175300 |  |  | Completed | 1 |  |  |  |  | 2016-07-20 | 2016-07-28 | 2016-08-09
16880 | NC 2016 | SHS | Region II | Isabela | 300591 | San Isidro National High School | San Isidro | 6 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21383013.45 |  |  | Completed | 1 |  |  |  |  | 2016-07-20 | 2016-07-28 | 2016-08-09
16881 | NC 2016 | SHS | Region II | Isabela | 300591 | San Isidro National High School | San Isidro | 6 |  | 8 | 2STY8CL | BATCH 9 CL | 10877342.59 |  |  | Completed | 1 |  |  |  |  | 2016-07-20 | 2016-07-28 | 2016-08-09
16882 | NC 2016 | K10 | Region II | Isabela | 306159 | San Miguel Integrated School | Ramon | 4 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-07-20 | 2016-07-28 | 2016-08-09
16883 | NC 2016 | SHS | Region II | Isabela | 306142 | San Sebastian Integrated School | Ramon | 4 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14
16884 | NC 2016 | SHS | Region II | Isabela | 300600 | Sgt. Prospero Bello Hs - Main | Jones | 4 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14
16885 | NC 2016 | K10 | Region II | Isabela | 103456 | Sto. Domingo Es - Annex (Lsb) | Jones | 4 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1112049.6543 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-06-01 | 2016-06-14
16886 | NC 2016 | K10 | Region II | Isabela | 300611 | Ugad High School | Echague | 6 | 1 | 18 | 3STY9CL | BATCH 9 CL | 30322655.84 |  |  | Completed | 1 |  |  |  |  | 2016-07-27 | 2016-08-05 | 2016-08-18
16887 | NC 2016 | TECHVOC | Region II | Isabela | 300611 | Ugad High School | Echague | 6 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 7094000 |  |  | Completed | 1 |  |  |  |  | 2016-07-27 | 2016-08-05 | 2016-08-18
16888 | NC 2016 | SHS | Region II | Isabela | 306128 | Wigan Integrated School | Cordon | 4 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.051 |  |  | Completed | 1 |  |  |  |  | 2016-06-01 | 2016-06-09 | 2016-06-23
16889 | NC 2016 | K10 | Region II | Nueva Vizcaya | 300618 | Aritao Nhs | Aritao | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16768460.712 |  |  | Completed | 1
16890 | NC 2016 | K10 | Region II | Nueva Vizcaya | 300618 | Aritao Nhs | Aritao | 0 |  | 6 | 3STY6CL | BATCH 9 CL | 11543844.661 |  |  | Completed | 1
16891 | NC 2016 | SHS | Region II | Nueva Vizcaya | 300620 | Bambang Nhs | Bambang | 0 | 1 | 32 | 4STY16CL | BATCH 9 CL | 58715432.724 |  |  | Completed | 1
16892 | NC 2016 | SHS | Region II | Nueva Vizcaya | 300621 | Bascaran Nhs | Solano | 0 | 1 | 8 | 4STY8CL | BATCH 7 CL | 16074268.83 |  |  | Completed | 1
16893 | NC 2016 | SHS | Region II | Nueva Vizcaya | 300623 | Bintawan Nhs | Villaverde | 0 | 1 | 12 | 4STY12CL | BATCH 7 CL | 21201319.95 |  |  | Completed | 1
16894 | NC 2016 | SHS | Region II | Nueva Vizcaya | 306202 | Bonfal National High School | Bayombong (Capital) | 0 | 1 | 8 | 4STY8CL | BATCH 7 CL | 16074268.83 |  |  | Completed | 1
16895 | NC 2016 | SHS | Region II | Nueva Vizcaya | 300626 | Casat Nhs | Bayombong (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1872266.47 |  |  | Completed | 1
16896 | NC 2016 | K10 | Region II | Nueva Vizcaya | 306203 | Dippog National High School | Quezon | 0 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6619337.64 |  |  | Completed | 1
16897 | NC 2016 | SHS | Region II | Nueva Vizcaya | 300640 | Napo-Tuyak Integrated School | Kayapa | 0 | 1 | 4 | 2STY4CL | BATCH 7 CL | 5975000 |  |  | Completed | 1
16898 | NC 2016 | SHS | Region II | Nueva Vizcaya | 300641 | Nueva Vizcaya Gen. Chs | Bayombong (Capital) | 0 | 1 | 36 | 4STY12CL | BATCH 9 CL | 73057733.946 |  |  | Completed | 1
16899 | NC 2016 | SHS | Region II | Nueva Vizcaya | 300645 | Salinas High School | Bambang | 0 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6529337.64 |  |  | Reverted | 0
16900 | NC 2016 | SHS | Region II | Nueva Vizcaya | 300647 | Sta. Clara Hs | Aritao | 0 | 1 | 8 | 2STY8CL | BATCH 7 CL | 11083000 |  |  | Completed | 1
16901 | NC 2016 | SHS | Region II | Nueva Vizcaya | 300651 | Uddiawan Nhs | Solano | 0 | 1 | 8 | 2STY4CL | BATCH 7 CL | 13038675.28 |  |  | Completed | 1
16902 | NC 2016 | SHS | Region II | Nueva Vizcaya | 300646 | Solano High School | Solano | 2 | 1 | 16 | 4STY8CL | BATCH 9 CL | 29795037.68 |  |  | Completed | 1
16903 | NC 2016 | SHS | Region II | Quirino | 300657 | Diffun Hs | Diffun | 0 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1 | [8 empty] | 2016-09-06 | PHESCO INCORPORATED
16904 | NC 2016 | SHS | Region II | Quirino | 300657 | Diffun Hs | Diffun | 0 |  | 8 | 4STY8CL | BATCH 9 CL | 16372270.724 |  |  | Completed | 1 | [9 empty] | NTL BUILDERS & DEVELOPERS
16905 | NC 2016 | SHS | Region II | Quirino | 300657 | Diffun Hs | Diffun | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 16618460.712 |  |  | Completed | 1 | [8 empty] | 2016-08-09 | NTL BUILDERS & DEVELOPERS
16906 | NC 2016 | TECHVOC | Region II | Quirino | 300657 | Diffun Hs | Diffun | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1 | [8 empty] | 2016-08-01 | NC CONSTRUCTION
16907 | NC 2016 | SHS | Region II | Quirino | 300660 | Maddela Chs | Maddela | 0 | 1 | 15 | 3STY15CL | BATCH 9 CL | 23506314.795 |  |  | Completed | 1 | [8 empty] | 2016-09-06 | PHESCO INCORPORATED
16908 | NC 2016 | SHS | Region II | Quirino | 300660 | Maddela Chs | Maddela | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 16618460.712 |  |  | Completed | 1 | [8 empty] | 2016-08-01 | NTL BUILDERS & DEVELOPERS
16909 | NC 2016 | TECHVOC | Region II | Quirino | 300660 | Maddela Chs | Maddela | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4350600 |  |  | Completed | 1 | [8 empty] | 2016-08-04 | JMD-68 BUILDERS
16910 | NC 2016 | SHS | Region II | Quirino | 300664 | Quirino General Hs | Cabarroguis (Capital) | 0 | 1 | 15 | 3STY15CL | BATCH 9 CL | 23506314.795 |  |  | Completed | 1
16911 | NC 2016 | SHS | Region II | Quirino | 300664 | Quirino General Hs | Cabarroguis (Capital) | 0 |  | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1
16912 | NC 2016 | TECHVOC | Region II | Quirino | 300664 | Quirino General Hs | Cabarroguis (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1 | [8 empty] | 2016-08-04 | JMD-68 BUILDERS
16913 | NC 2016 | SHS | Region II | Quirino | 300665 | Saguday Nhs | Saguday | 0 | 1 | 16 | 4STY16CL | BATCH 9 CL | 29357716.362 |  |  | Completed | 1 | [8 empty] | 2016-08-01 | PHESCO INCORPORATED
16914 | NC 2016 | SHS | Region II | Quirino | 300665 | Saguday Nhs | Saguday | 0 |  | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1 | [8 empty] | 2016-08-04 | JMD-68 BUILDERS
16915 | NC 2016 | SHS | Region II | Santiago City | 300599 | Santiago City National High School | City Of Santiago | 4 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1
16916 | NC 2016 | SHS | Region II | Santiago City | 300599 | Santiago City National High School | City Of Santiago | 4 |  | 15 | 3STY15CL | BATCH 9 CL | 23037143.68 |  |  | Completed | 1
16917 | NC 2016 | K10 | Region II | Tuguegarao City | 300668 | Cagayan National High Sschool | Tuguegarao City(Capital) | 3 | 1 | 48 | 4STY16CL | BATCH 9 CL | 80850000 |  |  | Completed | 1
16918 | NC 2016 | K10 | Region II | Tuguegarao City | 300668 | Cagayan National High Sschool | Tuguegarao City(Capital) | 3 |  | 8 | 4STY8CL | BATCH 9 CL | 13550000 |  |  | Completed | 1
16919 | NC 2016 | K10 | Region II | Tuguegarao City | 300671 | Gosi National High School | Tuguegarao City(Capital) | 3 | 1 | 18 | 3STY9CL | BATCH 7 CL | 32844720 |  |  | Completed | 1
16920 | NC 2016 | SHS | Region II | Tuguegarao City | 306401 | Tuguegarao City Science High School | Tuguegarao City(Capital) | 3 | 1 | 10 | 2STY10CL | BATCH 7 CL | 13225000 |  |  | Completed | 1
16921 | NC 2016 | K10 | Region II | Tuguegarao City | 104400 | Tuguegarao North Cs | Tuguegarao City(Capital) | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6411500 |  |  | Completed | 1
16922 | NC 2016 | K10 | Region II | Tuguegarao City | 104406 | Tuguegarao West Cs | Tuguegarao City(Capital) | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6411500 |  |  | Completed | 1
23315 | NC 2017 | K10 | Region II | Tuguegarao City | 104401 | Buntun ES | TUGUEGARAO CITY(Capital) | 3 | 1 | 2 | 1STY2CL | BATCH 2 | 2500000 |  |  | Completed | 1
23316 | NC 2017 | TVL | Region II | Tuguegarao City | 300671 | Gosi National High School | TUGUEGARAO CITY(Capital) | 3 | 1 | 2 | 1STY2CL (UNIQUE WORKSHOP) | BATCH 2 | 6070000 |  |  | Completed | 1
23317 | NC 2017 | TVL | Region II | Tuguegarao City | 300671 | Gosi National High School | TUGUEGARAO CITY(Capital) | 3 |  | 3 | 1STY3CL (UNIQUE WORKSHOP) | BATCH 2 | 9105000 |  |  | Completed | 1
23318 | NC 2017 | K10 | Region II | Tuguegarao City | 306402 | Tuguegarao City West High School | TUGUEGARAO CITY(Capital) | 3 | 1 | 2 | 1STY2CL | BATCH 2 | 2500000 |  |  | REVERTED | 0
23319 | NC 2017 | TVL | Region II | Cagayan | 300420 | Afusing NHS | ALCALA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3204000 |  |  | Completed | 1
23320 | NC 2017 | K10 | Region II | Cagayan | 102356 | Alcala West Central School | ALCALA | 1 | 1 | 5 | 1STY5CL W/ TOILET | BATCH 4 | 6252650.72 |  |  | Completed | 1
23321 | NC 2017 | K10 | Region II | Cagayan | 102356 | Alcala West Central School | ALCALA | 1 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2728745.92 |  |  | Completed | 1
23322 | NC 2017 | K10 | Region II | Cagayan | 102362 | Baculod ES | ALCALA | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3863435.02 |  |  | Completed | 1
23323 | NC 2017 | K10 | Region II | Cagayan | 102362 | Baculod ES | ALCALA | 1 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2690745.92 |  |  | Completed | 1
23324 | NC 2017 | TVL | Region II | Cagayan | 300428 | Aparri School of Arts and Trades | APARRI | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3004000 |  |  | Completed | 1
23325 | NC 2017 | TVL | Region II | Cagayan | 300470 | Aparri West National High School | APARRI | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3004000 |  |  | Completed | 1
23326 | NC 2017 | TVL | Region II | Cagayan | 300470 | Aparri West National High School | APARRI | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3129500 |  |  | Completed | 1
23327 | NC 2017 | TVL | Region II | Cagayan | 300470 | Aparri West National High School | APARRI | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3129500 |  |  | Completed | 1
23328 | NC 2017 | TVL | Region II | Cagayan | 300470 | Aparri West National High School | APARRI | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2929500 |  |  | Completed | 1
23329 | NC 2017 | TVL | Region II | Cagayan | 300470 | Aparri West National High School | APARRI | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2929500 |  |  | Completed | 1
23330 | NC 2017 | TVL | Region II | Cagayan | 300437 | Bukig National Agricultural and Technical School | APARRI | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2907250 |  |  | Completed | 1
23331 | NC 2017 | TVL | Region II | Cagayan | 300437 | Bukig National Agricultural and Technical School | APARRI | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2907250 |  |  | Completed | 1
23332 | NC 2017 | TVL | Region II | Cagayan | 300437 | Bukig National Agricultural and Technical School | APARRI | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2907250 |  |  | Completed | 1
23333 | NC 2017 | TVL | Region II | Cagayan | 300437 | Bukig National Agricultural and Technical School | APARRI | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2907250 |  |  | Completed | 1
23334 | NC 2017 | TVL | Region II | Cagayan | 300429 | Baggao National Agricultural School | BAGGAO | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3002000 |  |  | Completed | 1
23335 | NC 2017 | TVL | Region II | Cagayan | 300429 | Baggao National Agricultural School | BAGGAO | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3002000 |  |  | Completed | 1
23336 | NC 2017 | K10 | Region II | Cagayan | 102484 | Birao Elementary School | BAGGAO | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2813745.92 |  |  | Completed | 1
23337 | NC 2017 | TVL | Region II | Cagayan | 300432 | Hacienda Intal NHS | BAGGAO | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3019000 |  |  | Completed | 1
23338 | NC 2017 | K10 | Region II | Cagayan | 500010 | Valley Cove Integrated School | BAGGAO | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2883745.92 |  |  | Completed | 1
23339 | NC 2017 | TVL | Region II | Cagayan | 306005 | Licerio Antiporda Sr. NHS - Sta. Isabel Ext. | BUGUEY | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3019000 |  |  | Completed | 1
23340 | NC 2017 | K10 | Region II | Cagayan | 102569 | Paddaya Este ES | BUGUEY | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2693745.92 |  |  | Completed | 1
23341 | NC 2017 | TVL | Region II | Cagayan | 300480 | Pattao NHS | BUGUEY | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3229000 |  |  | Completed | 1
23342 | NC 2017 | TVL | Region II | Cagayan | 300444 | Camalaniugan NHS | CAMALANIUGAN | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3204000 |  |  | Completed | 1
23343 | NC 2017 | K10 | Region II | Cagayan | 102923 | Union ES | CLAVERIA | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
23344 | NC 2017 | TVL | Region II | Cagayan | 300440 | Calaoagan Dackel National High School | GATTARAN | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3027000 |  |  | Completed | 1
23345 | NC 2017 | TVL | Region II | Cagayan | 300440 | Calaoagan Dackel National High School | GATTARAN | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3027000 |  |  | Completed | 1
23346 | NC 2017 | SHS | Region II | Cagayan | 300455 | Don Mariano Marcos NHS | GATTARAN | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2705745.92 |  |  | Completed | 1
23347 | NC 2017 | TVL | Region II | Cagayan | 300462 | Gattaran National Trade School | GATTARAN | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3184000 |  |  | Completed | 1
23348 | NC 2017 | K10 | Region II | Cagayan | 102676 | Lapogan ES | GATTARAN | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2688745.92 |  |  | Completed | 1
23349 | NC 2017 | K10 | Region II | Cagayan | 102684 | Amunitan Elementary School | GONZAGA | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2633745.92 |  |  | Completed | 1
23350 | NC 2017 | TVL | Region II | Cagayan | 300435 | Baua HS | GONZAGA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3194000 |  |  | Completed | 1
23351 | NC 2017 | TVL | Region II | Cagayan | 300435 | Baua HS | GONZAGA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3044000 |  |  | Completed | 1
23352 | NC 2017 | K10 | Region II | Cagayan | 102687 | C. dela Cruz ES | GONZAGA | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2723745.92 |  |  | Completed | 1
23353 | NC 2017 | K10 | Region II | Cagayan | 102687 | C. dela Cruz ES | GONZAGA | 1 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2708745.92 |  |  | Completed | 1
23354 | NC 2017 | K10 | Region II | Cagayan | 306428 | Gonzaga NHS- Sta. Clara Annex | GONZAGA | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2681245.92 |  |  | Completed | 1
23355 | NC 2017 | K10 | Region II | Cagayan | 306428 | Gonzaga NHS- Sta. Clara Annex | GONZAGA | 1 |  | 5 | 1STY5CL W/ TOILET | BATCH 4 | 6222650.72 |  |  | Completed | 1
23356 | NC 2017 | K10 | Region II | Cagayan | 102696 | Gonzaga South CS | GONZAGA | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2656745.92 |  |  | Completed | 1
23357 | NC 2017 | K10 | Region II | Cagayan | 155051 | Laoc Elementary School | GONZAGA | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2713745.92 |  |  | Completed | 1
23358 | NC 2017 | TVL | Region II | Cagayan | 300482 | Rebecca NHS | GONZAGA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3027000 |  |  | Completed | 1
23359 | NC 2017 | TVL | Region II | Cagayan | 300482 | Rebecca NHS | GONZAGA | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3027000 |  |  | Completed | 1
23360 | NC 2017 | K10 | Region II | Cagayan | 102709 | Tapel ES | GONZAGA | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2651745.92 |  |  | Completed | 1
23361 | NC 2017 | TVL | Region II | Cagayan | 300469 | LAL-LO NATIONAL HIGH SCHOOL | LAL-LO | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3034000 |  |  | Completed | 1
23362 | NC 2017 | TVL | Region II | Cagayan | 306003 | Lal-lo NHS - Cabayabasan Annex | LAL-LO | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3154000 |  |  | Completed | 1
23363 | NC 2017 | TVL | Region II | Cagayan | 300475 | Logac National High School | LAL-LO | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2852000 |  |  | Completed | 1
23364 | NC 2017 | TVL | Region II | Cagayan | 300475 | Logac National High School | LAL-LO | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2852000 |  |  | Completed | 1
23365 | NC 2017 | TVL | Region II | Cagayan | 306004 | Magapit NHS | LAL-LO | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3154000 |  |  | Completed | 1
23366 | NC 2017 | K10 | Region II | Cagayan | 155030 | San Mariano ES | LAL-LO | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2723745.92 |  |  | Completed | 1
23367 | NC 2017 | K10 | Region II | Cagayan | 102911 | San Vicente ES | SANTA ANA | 1 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 4 | 5018351.15 |  |  | Completed | 1
23368 | NC 2017 | K10 | Region II | Cagayan | 102911 | San Vicente ES | SANTA ANA | 1 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2668745.92 |  |  | Completed | 1
23369 | NC 2017 | TVL | Region II | Cagayan | 300488 | Sta. Ana Fishery National High School | SANTA ANA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3189000 |  |  | Completed | 1
23370 | NC 2017 | TVL | Region II | Cagayan | 300490 | Sta. Teresita NHS | SANTA TERESITA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2984500 |  |  | Completed | 1
23371 | NC 2017 | TVL | Region II | Cagayan | 300490 | Sta. Teresita NHS | SANTA TERESITA | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2984500 |  |  | Completed | 1
23372 | NC 2017 | TVL | Region II | Cagayan | 300490 | Sta. Teresita NHS | SANTA TERESITA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3014000 |  |  | Completed | 1
23373 | NC 2017 | K10 | Region II | City of Ilagan | 103361 | Capellan ES | ILAGAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2616650 |  |  | Completed | 1
23374 | NC 2017 | K10 | Region II | City of Ilagan | 103363 | Fuyo ES | ILAGAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2611250 |  |  | Completed | 1
23375 | NC 2017 | K10 | Region II | City of Ilagan | 103365 | Ilagan North CS | ILAGAN (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3817307.57 |  |  | Completed | 1
23376 | NC 2017 | TVL | Region II | City of Ilagan | 306105 | ISAT-Main | ILAGAN (Capital) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3200024.25 |  |  | Completed | 1
23377 | NC 2017 | TVL | Region II | City of Ilagan | 500080 | Lupigue Integrated School | ILAGAN (Capital) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3265172.6 |  |  | Completed | 1
23378 | NC 2017 | K10 | Region II | City of Ilagan | 103358 | Manaring IS (Bangag-Manaring-Capo ES) | ILAGAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2642150 |  |  | Completed | 1
23379 | NC 2017 | K10 | Region II | City of Ilagan | 103366 | Marana 1st ES | ILAGAN (Capital) | 1 | 1 | 4 | 1STY4CL | BATCH 4 | 4872693.15 |  |  | Completed | 1
23380 | NC 2017 | K10 | Region II | City of Ilagan | 103368 | Marana 3rd ES | ILAGAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2608056.92 |  |  | Completed | 1
23381 | NC 2017 | K10 | Region II | City of Ilagan | 103428 | Naguilian Baculud Elementary School | ILAGAN (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3825450.02 |  |  | Completed | 1
23382 | NC 2017 | SHS | Region II | City of Ilagan | 300543 | Rang-ayan NHS (Isabela NHS - Rang-ayan Annex) | ILAGAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745 |  |  | Completed | 1
23383 | NC 2017 | K10 | Region II | City of Ilagan | 103374 | San Andres ES | ILAGAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2608056.92 |  |  | Completed | 1
23384 | NC 2017 | K10 | Region II | City of Ilagan | 103374 | San Andres ES | ILAGAN (Capital) | 1 |  | 3 | 1STY3CL | BATCH 4 | 3767997.02 |  |  | Completed | 1
23385 | NC 2017 | K10 | Region II | City of Ilagan | 103380 | Sta. Victoria ES | ILAGAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2616650 |  |  | Completed | 1
23386 | NC 2017 | K10 | Region II | City of Ilagan | 103383 | Villa Imelda PS | ILAGAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745 |  |  | Completed | 1
23387 | NC 2017 | K10 | Region II | City of Ilagan | 103383 | Villa Imelda PS | ILAGAN (Capital) | 1 |  | 2 | 1STY2CL | BATCH 4 | 2613745 |  |  | Completed | 1
23388 | NC 2017 | K10 | Region II | Isabela | 103075 | Bagong Tanza ES | AURORA | 5 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3771435.02 |  |  | Completed | 1
23389 | NC 2017 | K10 | Region II | Isabela | 103256 | Taliktik ES | CORDON | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2738254.17 |  |  | Completed | 1
23390 | NC 2017 | K10 | Region II | Isabela | 103265 | Aneg ES | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2574384.94 |  |  | Completed | 1
23391 | NC 2017 | K10 | Region II | Isabela | 306133 | Aneg National High School | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745 |  |  | Completed | 1
23392 | NC 2017 | K10 | Region II | Isabela | 306162 | Bayabo Integrated School | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3836935.02 |  |  | Completed | 1
23393 | NC 2017 | K10 | Region II | Isabela | 103268 | Carmencita ES | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3588538.42 |  |  | Completed | 1
23394 | NC 2017 | TVL | Region II | Isabela | 300587 | Ragan Sur National High School | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3199590.41 |  |  | Completed | 1
23395 | NC 2017 | K10 | Region II | Isabela | 103276 | San Juan ES | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2608056.92 |  |  | Completed | 1
23396 | NC 2017 | K10 | Region II | Isabela | 103281 | Sta. Cruz Multigrade | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3741646.02 |  |  | Completed | 1
23397 | NC 2017 | K10 | Region II | Isabela | 103285 | Carulay ES | ECHAGUE | 6 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3931402.87 |  |  | Completed | 1
23398 | NC 2017 | K10 | Region II | Isabela | 103285 | Carulay ES | ECHAGUE | 6 |  | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3931402.87 |  |  | Completed | 1
23399 | NC 2017 | K10 | Region II | Isabela | 103338 | Barcolan ES | GAMU | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2661745.92 |  |  | Completed | 1
23400 | NC 2017 | K10 | Region II | Isabela | 103342 | Furao ES | GAMU | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3771435.02 |  |  | Completed | 1
23401 | NC 2017 | K10 | Region II | Isabela | 103494 | Holy Friday ES | MALLIG | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2788254.17 |  |  | Completed | 1
23402 | NC 2017 | K10 | Region II | Isabela | 103508 | Victoria ES | MALLIG | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2666745.92 |  |  | Completed | 1
23403 | NC 2017 | K10 | Region II | Isabela | 103514 | La Union Elementary School | NAGUILIAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2646745.92 |  |  | Completed | 1
23404 | NC 2017 | K10 | Region II | Isabela | 103518 | Minallo ES | NAGUILIAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2646745.92 |  |  | Completed | 1
23405 | NC 2017 | K10 | Region II | Isabela | 103571 | Quezon CS | QUEZON | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2616745.92 |  |  | Completed | 1
23406 | NC 2017 | K10 | Region II | Isabela | 103589 | Sta. Catalina Elementary School | QUIRINO | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2635745.92 |  |  | Completed | 1
23407 | NC 2017 | K10 | Region II | Isabela | 103609 | San Antonio ES | RAMON | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2738254.17 |  |  | Completed | 1
23408 | NC 2017 | K10 | Region II | Isabela | 306163 | Simimbaan Integrated School | ROXAS | 5 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3790935.02 |  |  | Completed | 1
23409 | NC 2017 | K10 | Region II | Isabela | 306163 | Simimbaan Integrated School | ROXAS | 5 |  | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3790935.02 |  |  | Completed | 1
23410 | NC 2017 | K10 | Region II | Isabela | 103716 | Mararigue ES | SAN MANUEL | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2616745.92 |  |  | Completed | 1
23411 | NC 2017 | K10 | Region II | Isabela | 103728 | Villanueva Elementary School | SAN MANUEL | 5 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3790935.02 |  |  | Completed | 1
23412 | NC 2017 | K10 | Region II | Isabela | 103728 | Villanueva Elementary School | SAN MANUEL | 5 |  | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3790935.02 |  |  | Completed | 1
23413 | NC 2017 | K10 | Region II | Isabela | 103754 | Dipusu ES | SAN MARIANO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2646745.92 |  |  | Completed | 1
23414 | NC 2017 | K10 | Region II | Isabela | 103757 | Gangalan ES | SAN MARIANO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2646745.92 |  |  | Completed | 1
23415 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104193 | Balintugon ES | ALFONSO CASTAÑEDA | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2943577.39 |  |  | Completed | 1
23416 | NC 2017 | K10 | Region II | Nueva Vizcaya | 103912 | Calitlitan ES | ARITAO | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2746213.3 |  |  | Completed | 1
23417 | NC 2017 | K10 | Region II | Nueva Vizcaya | 103924 | Tabueng Elementary School | ARITAO | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2794806.17 |  |  | Completed | 1
23418 | NC 2017 | K10 | Region II | Nueva Vizcaya | 103929 | Amballo Resettlement ES | BAGABAG | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2815000 |  |  | Completed | 1
23419 | NC 2017 | K10 | Region II | Nueva Vizcaya | 103936 | M. V. Duque ES | BAGABAG | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2815000 |  |  | Completed | 1
23420 | NC 2017 | K10 | Region II | Nueva Vizcaya | 103962 | Salicpan ES | BAMBANG | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3210000 |  |  | Completed | 1
23421 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104036 | Abatan PS | DUPAX DEL NORTE | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2663745.92 |  |  | Completed | 1
23422 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104037 | Belance Elementary School | DUPAX DEL NORTE | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2698795.92 |  |  | Completed | 1
23423 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104038 | Binuangan ES | DUPAX DEL NORTE | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2663745.92 |  |  | Completed | 1
23424 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104040 | Bulala ES | DUPAX DEL NORTE | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2704172.47 |  |  | Completed | 1
23425 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104040 | Bulala ES | DUPAX DEL NORTE | 0 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2704172.47 |  |  | Completed | 1
23426 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104041 | Casecnan PS | DUPAX DEL NORTE | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2946731.57 |  |  | Completed | 1
23427 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104042 | Dupax del Norte CS | DUPAX DEL NORTE | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2663745.92 |  |  | Completed | 1
23428 | NC 2017 | SHS | Region II | Nueva Vizcaya | 306206 | DUPAX DEL NORTE NATIONAL HIGH SCHOOL | DUPAX DEL NORTE | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2953045.17 |  |  | Completed | 1
23429 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104045 | Ineangan ES | DUPAX DEL NORTE | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2705786.75 |  |  | Completed | 1
23430 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104046 | Lamo ES | DUPAX DEL NORTE | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2663745.92 |  |  | Completed | 1
23431 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104047 | MABASA ELEMENTARY SCHOOL | DUPAX DEL NORTE | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2663745.92 |  |  | Completed | 1
23432 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104048 | Macabenga ES | DUPAX DEL NORTE | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2663745.92 |  |  | Completed | 1
23433 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104049 | Mantatta PS | DUPAX DEL NORTE | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2744599.02 |  |  | Completed | 1
23434 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104050 | Munguia Elementary School | DUPAX DEL NORTE | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2828517.49 |  |  | Completed | 1
23435 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104051 | Nagakay ES | DUPAX DEL NORTE | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3052836.41 |  |  | Completed | 1
23436 | NC 2017 | K10 | Region II | Nueva Vizcaya | 156007 | Naruron ES | DUPAX DEL NORTE | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2771595.11 |  |  | Reverted | 0
23437 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104052 | New Gumiad ES | DUPAX DEL NORTE | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2982773.51 |  |  | Completed | 1
23438 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104054 | Parai ES | DUPAX DEL NORTE | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2731168.56 |  |  | Completed | 1
23439 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104074 | Alloy ES | KASIBU | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2886155.81 |  |  | Completed | 1
23440 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104077 | Binogawan ES | KASIBU | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2958877.32 |  |  | Completed | 1
23441 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104077 | Binogawan ES | KASIBU | 0 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2958877.32 |  |  | Completed | 1
23442 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104079 | Bua Elementary School | KASIBU | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2827040.17 |  |  | Completed | 1
23443 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104087 | Kakiduguen Elementary School | KASIBU | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2843725.17 |  |  | Completed | 1
23444 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104094 | Kasibu East CS | KASIBU | 0 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3818435.02 |  |  | Completed | 1
23445 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104089 | Kongkong ES | KASIBU | 0 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3860475.85 |  |  | Completed | 1
23446 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104106 | Wangal ES | KASIBU | 0 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 4297720.15 |  |  | Completed | 1
23447 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104111 | Babadi Elementary School | KAYAPA | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3000319.37 |  |  | Completed | 1
23448 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104113 | Banao ES | KAYAPA | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3235146.81 |  |  | Completed | 1
23449 | NC 2017 | K10 | Region II | Santiago City | 103830 | Santiago North CS SpEd Center | CITY OF SANTIAGO | 4 | 1 | 5 | 1STY5CL | BATCH 4 | 6254879.49 |  |  | Completed | 1
23450 | NC 2017 | K10 | Region II | Santiago City | 103830 | Santiago North CS SpEd Center | CITY OF SANTIAGO | 4 |  | 5 | 1STY5CL | BATCH 4 | 6254879.49 |  |  | Completed | 1
23451 | NC 2017 | K10 | Region II | Santiago City | 103830 | Santiago North CS SpEd Center | CITY OF SANTIAGO | 4 |  | 4 | 1STY4CL | BATCH 4 | 5112814.7 |  |  | Completed | 1
23452 | NC 2017 | K10 | Region II | Santiago City | 103830 | Santiago North CS SpEd Center | CITY OF SANTIAGO | 4 |  | 2 | 1STY2CL | BATCH 4 | 2798254.17 |  |  | Completed | 1
23453 | NC 2017 | K10 | Region II | Cagayan | 102383 | Cataratan Integrated School | ALLACAPAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3854778.37 |  |  | Completed | 1
23454 | NC 2017 | K10 | Region II | Cagayan | 102386 | Dalayap ES | ALLACAPAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2640390.67 |  |  | Completed | 1
23455 | NC 2017 | K10 | Region II | Cagayan | 102386 | Dalayap ES | ALLACAPAN | 2 |  | 2 | 1STY2CL | BATCH 7 | 2640390.67 |  |  | Completed | 1
23456 | NC 2017 | K10 | Region II | Cagayan | 102396 | Nagattatan ES | ALLACAPAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3854778.37 |  |  | Completed | 1
23457 | NC 2017 | K10 | Region II | Cagayan | 102397 | PACAC E/S | ALLACAPAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3810302.12 |  |  | Completed | 1
23458 | NC 2017 | K10 | Region II | Cagayan | 155045 | Silagan Elementary School | ALLACAPAN | 2 | 1 | 4 | 1STY4CL | BATCH 7 | 4942591.22 |  |  | Completed | 1
23459 | NC 2017 | K10 | Region II | Cagayan | 155045 | Silagan Elementary School | ALLACAPAN | 2 |  | 2 | 1STY2CL | BATCH 7 | 2640818.74 |  |  | Completed | 1
23460 | NC 2017 | K10 | Region II | Cagayan | 102399 | Tamboli ES | ALLACAPAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3810302.12 |  |  | Completed | 1
23461 | NC 2017 | TVL | Region II | Cagayan | 300425 | AMULUNG NATIONAL HIGH SCHOOL | AMULUNG | 3 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 5900564 |  |  | Completed | 1
23462 | NC 2017 | K10 | Region II | Cagayan | 102429 | Cordova CS | AMULUNG | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3637197 |  |  | Completed | 1
23463 | NC 2017 | K10 | Region II | Cagayan | 102429 | Cordova CS | AMULUNG | 3 |  | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3637197 |  |  | Completed | 1
23464 | NC 2017 | TVL | Region II | Cagayan | 300452 | Cordova National High Sschool | AMULUNG | 3 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 5900564 |  |  | Completed | 1
23465 | NC 2017 | SHS | Region II | Cagayan | 306010 | PACAC GRANDE NAT'L. HIGH SCHOOL | AMULUNG | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2639660 |  |  | Completed | 1
23466 | NC 2017 | K10 | Region II | Cagayan | 102545 | Nararagan ES | BALLESTEROS | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3768435.02 |  |  | Completed | 1
23467 | NC 2017 | K10 | Region II | Cagayan | 102550 | Sta. Cruz ES | BALLESTEROS | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
23468 | NC 2017 | K10 | Region II | Cagayan | 102552 | Zitanga ES | BALLESTEROS | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
23469 | NC 2017 | K10 | Region II | Cagayan | 102552 | Zitanga ES | BALLESTEROS | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4021773.91 |  |  | Completed | 1
23470 | NC 2017 | K10 | Region II | Cagayan | 102608 | Claveria CS | CLAVERIA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
23471 | NC 2017 | K10 | Region II | Cagayan | 102616 | Mapulapula Elementary School | CLAVERIA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
23472 | NC 2017 | K10 | Region II | Cagayan | 102616 | Mapulapula Elementary School | CLAVERIA | 2 |  | 3 | 1STY3CL | BATCH 7 | 3768435.02 |  |  | Completed | 1
23473 | NC 2017 | K10 | Region II | Cagayan | 102617 | Nagsabaran ES | CLAVERIA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2692891.65 |  |  | Completed | 1
23474 | NC 2017 | K10 | Region II | Cagayan | 102620 | San Vicente Primary School | CLAVERIA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
23475 | NC 2017 | K10 | Region II | Cagayan | 102623 | Sto. Tomas PS | CLAVERIA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
23476 | NC 2017 | K10 | Region II | Cagayan | 102619 | Pinas ES | Claveria East | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2812608.98 |  |  | Completed | 1
23477 | NC 2017 | K10 | Region II | Cagayan | 102630 | Enrile East CS | ENRILE | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3620843 |  |  | Completed | 1
23478 | NC 2017 | K10 | Region II | Cagayan | 102630 | Enrile East CS | ENRILE | 3 |  | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3620843 |  |  | Completed | 1
23479 | NC 2017 | K10 | Region II | Cagayan | 102630 | Enrile East CS | ENRILE | 3 |  | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2549902 |  |  | Completed | 1
23480 | NC 2017 | K10 | Region II | Cagayan | 102630 | Enrile East CS | ENRILE | 3 |  | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2549902 |  |  | Completed | 1
23481 | NC 2017 | SHS | Region II | Cagayan | 300458 | Enrile Vocational High School | ENRILE | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3566417 |  |  | Completed | 1
23482 | NC 2017 | K10 | Region II | Cagayan | 102635 | Liwan Norte ES | ENRILE | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3637197 |  |  | Completed | 1
23483 | NC 2017 | K10 | Region II | Cagayan | 102640 | Roma Sur ES | ENRILE | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3626557 |  |  | Completed | 1
23484 | NC 2017 | TVL | Region II | Cagayan | 300459 | Western Enrile Vocational High School | ENRILE | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3108183 |  |  | Completed | 1
23485 | NC 2017 | TVL | Region II | Cagayan | 306001 | Gammad National High School | IGUIG | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3058772 |  |  | Completed | 1
23486 | NC 2017 | K10 | Region II | Cagayan | 102756 | Alannay ES | LASAM | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3854778.37 |  |  | Completed | 1
23487 | NC 2017 | K10 | Region II | Cagayan | 155036 | Cabatacan West ES | LASAM | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2669233.29 |  |  | Completed | 1
23488 | NC 2017 | K10 | Region II | Cagayan | 102759 | Calapangan ES | LASAM | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2669607.92 |  |  | Completed | 1
23489 | NC 2017 | K10 | Region II | Cagayan | 102760 | Callao ES | LASAM | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2669607.92 |  |  | Completed | 1
23490 | NC 2017 | SHS | Region II | Cagayan | 300443 | Callao National High School | LASAM | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2669607.92 |  |  | Completed | 1
23491 | NC 2017 | K10 | Region II | Cagayan | 102762 | Gabun ES | LASAM | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2669607.92 |  |  | Completed | 1
23492 | NC 2017 | K10 | Region II | Cagayan | 102765 | Magsaysay ES | LASAM | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2669233.29 |  |  | Completed | 1
23493 | NC 2017 | K10 | Region II | Cagayan | 102765 | Magsaysay ES | LASAM | 2 |  | 2 | 1STY2CL | BATCH 7 | 2669233.29 |  |  | Completed | 1
23494 | NC 2017 | K10 | Region II | Cagayan | 102766 | Malinta ES | LASAM | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2669607.92 |  |  | Completed | 1
23495 | NC 2017 | K10 | Region II | Cagayan | 102767 | Minanga Norte ES | LASAM | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2669607.92 |  |  | Completed | 1
23496 | NC 2017 | K10 | Region II | Cagayan | 102768 | Minanga Sur ES | LASAM | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2669607.92 |  |  | Completed | 1
23497 | NC 2017 | K10 | Region II | Cagayan | 102769 | Nabannagan East ES | LASAM | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2669607.92 |  |  | Completed | 1
23498 | NC 2017 | K10 | Region II | Cagayan | 102770 | Nabannagan West ES | LASAM | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3852063.05 |  |  | Completed | 1
23499 | NC 2017 | K10 | Region II | Cagayan | 102771 | New Orlins ES | LASAM | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2669607.92 |  |  | Completed | 1
23500 | NC 2017 | K10 | Region II | Cagayan | 102774 | San Pedro ES | LASAM | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2669607.92 |  |  | Completed | 1
23501 | NC 2017 | K10 | Region II | Cagayan | 102776 | Tagao ES | LASAM | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2669607.92 |  |  | Completed | 1
23502 | NC 2017 | K10 | Region II | Cagayan | 102777 | Tucalan Passing ES | LASAM | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2669607.92 |  |  | Completed | 1
23503 | NC 2017 | K10 | Region II | Cagayan | 102778 | Viga ES | LASAM | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2669607.92 |  |  | Completed | 1
23504 | NC 2017 | K10 | Region II | Cagayan | 102791 | Pamplona CS | PAMPLONA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2679370.92 |  |  | Completed | 1
23505 | NC 2017 | K10 | Region II | Cagayan | 102791 | Pamplona CS | PAMPLONA | 2 |  | 2 | 1STY2CL | BATCH 7 | 2679370.92 |  |  | Completed | 1
23506 | NC 2017 | K10 | Region II | Cagayan | 102791 | Pamplona CS | PAMPLONA | 2 |  | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
23507 | NC 2017 | K10 | Region II | Cagayan | 102791 | Pamplona CS | PAMPLONA | 2 |  | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
23508 | NC 2017 | K10 | Region II | Cagayan | 102794 | Tabba ES | PAMPLONA | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3768435.02 |  |  | Completed | 1
23509 | NC 2017 | TVL | Region II | Cagayan | 300456 | Don Severino Pagalilauan National High School | PEÑABLANCA | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3058772 |  |  | Completed | 1
23510 | NC 2017 | SHS | Region II | Cagayan | 300457 | Penablanca East NHS | PEÑABLANCA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2596518 |  |  | Completed | 1
23511 | NC 2017 | TVL | Region II | Cagayan | 300457 | Penablanca East NHS | PEÑABLANCA | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3169336 |  |  | Completed | 1
23512 | NC 2017 | TVL | Region II | Cagayan | 300445 | Penablanca National High School | PEÑABLANCA | 3 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 5855267 |  |  | Completed | 1
23513 | NC 2017 | K10 | Region II | Cagayan | 102807 | Quibal ES | PEÑABLANCA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2558216 |  |  | Completed | 1
23514 | NC 2017 | K10 | Region II | Cagayan | 102808 | San Roque ES | PEÑABLANCA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2569246 |  |  | Completed | 1
23515 | NC 2017 | K10 | Region II | Cagayan | 102830 | Villa Rey ES | PIAT | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
23516 | NC 2017 | K10 | Region II | Cagayan | 102845 | San Juan ES | RIZAL | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2724017.4 |  |  | Completed | 1
23517 | NC 2017 | K10 | Region II | Cagayan | 102861 | Sanchez Mira CS | SANCHEZ-MIRA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
23518 | NC 2017 | K10 | Region II | Cagayan | 102920 | Mabnang PS | SANTA PRAXEDES | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
23519 | NC 2017 | K10 | Region II | Cagayan | 102938 | Balanni Elementary School | SANTO NIÑO (FAIRE) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2697684.02 |  |  | Completed | 1
23520 | NC 2017 | K10 | Region II | Cagayan | 155052 | LAGUM PRIMARY SCHOOL | SANTO NIÑO (FAIRE) | 2 | 1 | 2 | 1STY2CL ALL WOOD | BATCH 7 | 2205536.96 |  |  | Completed | 1
23521 | NC 2017 | K10 | Region II | Cagayan | 155052 | LAGUM PRIMARY SCHOOL | SANTO NIÑO (FAIRE) | 2 |  | 2 | 1STY2CL ALL WOOD | BATCH 7 | 2205536.96 |  |  | Completed | 1
23522 | NC 2017 | K10 | Region II | Cagayan | 102947 | Nag-Uma ES | SANTO NIÑO (FAIRE) | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3768435.02 |  |  | Completed | 1
23523 | NC 2017 | K10 | Region II | Cagayan | 102948 | Namuccayan ES | SANTO NIÑO (FAIRE) | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3768435.02 |  |  | Completed | 1
23524 | NC 2017 | K10 | Region II | Cagayan | 102951 | Sta. Felicitas PS | SANTO NIÑO (FAIRE) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2697684.02 |  |  | Completed | 1
23525 | NC 2017 | K10 | Region II | Cagayan | 102956 | Virginia ES | SANTO NIÑO (FAIRE) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
23526 | NC 2017 | K10 | Region II | Cagayan | 102866 | Andarayan ES | SOLANA | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3566417 |  |  | Completed | 1
23527 | NC 2017 | K10 | Region II | Cagayan | 102866 | Andarayan ES | SOLANA | 3 |  | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3566417 |  |  | Completed | 1
23528 | NC 2017 | K10 | Region II | Cagayan | 102866 | Andarayan ES | SOLANA | 3 |  | 4 | 1STY4CL W/ TOILET | BATCH 7 | 4755223 |  |  | Completed | 1
23529 | NC 2017 | SHS | Region II | Cagayan | 300427 | Dassun NHS | SOLANA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2520058 |  |  | Completed | 1
23530 | NC 2017 | TVL | Region II | Cagayan | 300461 | Gadu National High School | SOLANA | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3058772 |  |  | Completed | 1
23531 | NC 2017 | TVL | Region II | Cagayan | 306424 | Gadu NHS- Nangalisan Extension | SOLANA | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3058772 |  |  | Completed | 1
23532 | NC 2017 | K10 | Region II | Cagayan | 102886 | Lingu ES | SOLANA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2614300 |  |  | Completed | 1
23533 | NC 2017 | K10 | Region II | Cagayan | 102875 | Natappian ES | SOLANA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2520741 |  |  | Completed | 1
23534 | NC 2017 | K10 | Region II | Cagayan | 102875 | Natappian ES | SOLANA | 3 |  | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2511094 |  |  | Completed | 1
23535 | NC 2017 | TVL | Region II | Cagayan | 300484 | Sampaguita NHS | SOLANA | 3 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 5780267 |  |  | Completed | 1
23536 | NC 2017 | TVL | Region II | Cagayan | 300487 | Solana Fresh Water Fishery School | SOLANA | 3 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 5780267 |  |  | Completed | 1
23537 | NC 2017 | K10 | Region II | Cagayan | 102895 | Solana South CS | SOLANA | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3566417 |  |  | Completed | 1
23538 | NC 2017 | K10 | Region II | Cagayan | 102895 | Solana South CS | SOLANA | 3 |  | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2511094 |  |  | Completed | 1
23539 | NC 2017 | K10 | Region II | Cagayan | 102893 | Solana West CS | SOLANA | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3566417 |  |  | Completed | 1
23540 | NC 2017 | K10 | Region II | Cagayan | 102893 | Solana West CS | SOLANA | 3 |  | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3566417 |  |  | Completed | 1
23541 | NC 2017 | TVL | Region II | Cagayan | 300466 | Itawes Nat'l. Agr'l. & Tech'l. School | TUAO | 3 | 1 | 3 | Workshop Bldg. (7x18) | BATCH 7 | 9175950 |  |  | Completed | 1
23542 | NC 2017 | TVL | Region II | Cagayan | 300466 | Itawes Nat'l. Agr'l. & Tech'l. School | TUAO | 3 |  | 3 | Workshop Bldg. (7x18) | BATCH 7 | 9175950 |  |  | Completed | 1
23543 | NC 2017 | TVL | Region II | Cagayan | 300468 | Itawes Nat'l.l Agr'l. & Tech'l. School - Bagumbayan Annex | TUAO | 3 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3108183 |  |  | Completed | 1
23544 | NC 2017 | SHS | Region II | Cagayan | 300468 | Itawes Nat'l.l Agr'l. & Tech'l. School - Bagumbayan Annex | TUAO | 3 | 1 | 6 | 2STY6CL | BATCH 7 | 8254717.53 |  |  | Completed | 1
23545 | NC 2017 | K10 | Region II | Cagayan | 102985 | Lallayug ES | TUAO | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2574039 |  |  | Completed | 1
23546 | NC 2017 | TVL | Region II | Cagayan | 300492 | TUAO VOCATIONAL AND TECHNICAL SCHOOL | TUAO | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3108183 |  |  | Completed | 1
23547 | NC 2017 | TVL | Region II | Cagayan | 300494 | Tuao Voc'l. and Tech'l. School - Pata Annex | TUAO | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3108183 |  |  | Completed | 1
23548 | NC 2017 | K10 | Region II | City of Ilagan | 155505 | Bangag PS | ILAGAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2616650 |  |  | Completed | 1
23549 | NC 2017 | SHS | Region II | City of Ilagan | 500080 | Lupigue Integrated School (formerly Lupigue ES) | ILAGAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2714839.6 |  |  | Completed | 1
23550 | NC 2017 | K10 | Region II | City of Ilagan | 103427 | Mangcuram ES | ILAGAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
23551 | NC 2017 | K10 | Region II | Isabela | 103104 | Capuseran Elementary School | BENITO SOLIVEN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2915046.86 |  |  | Completed | 1
23552 | NC 2017 | K10 | Region II | Isabela | 103121 | Sinipit Elementary School | BENITO SOLIVEN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2656745.92 |  |  | Completed | 1
23553 | NC 2017 | SHS | Region II | Isabela | 300510 | Bacnor National High School | BURGOS | 5 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3783435.02 |  |  | Completed | 1
23554 | NC 2017 | TVL | Region II | Isabela | 300521 | Alfreda Albano National High School - Magassi, Cabagan | CABAGAN | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3199590.47 |  |  | Completed | 1
23555 | NC 2017 | K10 | Region II | Isabela | 155535 | Casibarag Norte Elementary School | CABAGAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2687960 |  |  | Completed | 1
23556 | NC 2017 | K10 | Region II | Isabela | 103149 | Catabayungan ES | CABAGAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2699411 |  |  | Completed | 1
23557 | NC 2017 | TVL | Region II | Isabela | 300520 | Delfin Albano High School-Main | CABAGAN | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3199590.41 |  |  | Completed | 1
23558 | NC 2017 | TVL | Region II | Isabela | 300585 | San Antonio National High School | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3199590.41 |  |  | Completed | 1
23559 | NC 2017 | K10 | Region II | Isabela |  | Dicatian PS | DIVILICAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3502264 |  |  | Completed | 1
23560 | NC 2017 | K10 | Region II | Isabela |  | Dilakip PS | DIVILICAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3502264 |  |  | Completed | 1
23561 | NC 2017 | K10 | Region II | Isabela | 103326 | Villa Fermin ES | ECHAGUE | 6 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3931402.87 |  |  | Completed | 1
23562 | NC 2017 | K10 | Region II | Isabela | 306113 | Gamu Rural School Annex - Junction Upi Annex | GAMU | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2656745.92 |  |  | Completed | 1
23563 | NC 2017 | K10 | Region II | Isabela | 103349 | Songsong ES | GAMU | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3875959.02 |  |  | Completed | 1
23564 | NC 2017 | K10 | Region II | Isabela | 103349 | Songsong ES | GAMU | 2 |  | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3875959.02 |  |  | Completed | 1
23565 | NC 2017 | K10 | Region II | Isabela |  | STA. MARIA ES | MACONACON | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3568160 |  |  | Completed | 1
23566 | NC 2017 | K10 | Region II | Isabela | 103495 | Maligaya ES | MALLIG | 5 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3771435.02 |  |  | Completed | 1
23567 | NC 2017 | K10 | Region II | Isabela | 103542 | Dibungko PS | PALANAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3260280 |  |  | Completed | 1
23568 | NC 2017 | SHS | Region II | Isabela | 300564 | Palanan National High School | PALANAN | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4220647.22 |  |  | Completed | 1
23569 | NC 2017 | K10 | Region II | Isabela | 103561 | Taknalan PS | PALANAN | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 5823746.48 |  |  | Completed | 1
23570 | NC 2017 | K10 | Region II | Isabela | 306159 | San Miguel Integrated School | RAMON | 4 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 7 | 5112814.7 |  |  | Completed | 1
23571 | NC 2017 | K10 | Region II | Isabela | 306159 | San Miguel Integrated School | RAMON | 4 |  | 4 | 1STY4CL W/ TOILET | BATCH 7 | 5112814.7 |  |  | Completed | 1
23572 | NC 2017 | K10 | Region II | Isabela | 306142 | San Sebastian Integrated School | RAMON | 4 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3931402.87 |  |  | Completed | 1
23573 | NC 2017 | K10 | Region II | Isabela | 103630 | Anao-Kiling ES | ROXAS | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2636745.92 |  |  | Completed | 1
23574 | NC 2017 | K10 | Region II | Isabela | 103630 | Anao-Kiling ES | ROXAS | 5 |  | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2636745.92 |  |  | Completed | 1
23575 | NC 2017 | K10 | Region II | Isabela | 103631 | Imbiao Elementary School | ROXAS | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2816745.92 |  |  | Completed | 1
23576 | NC 2017 | K10 | Region II | Isabela | 103634 | Luna-Rang-ayan ES | ROXAS | 5 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3816435.02 |  |  | Completed | 1
23577 | NC 2017 | K10 | Region II | Isabela | 103636 | Roxas CS | ROXAS | 5 | 1 | 5 | 1STY5CL W/ TOILET | BATCH 7 | 6072650.72 |  |  | Completed | 1
23578 | NC 2017 | K10 | Region II | Isabela | 103636 | Roxas CS | ROXAS | 5 |  | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3874435.02 |  |  | Completed | 1
23579 | NC 2017 | K10 | Region II | Isabela | 103637 | San Jose ES | ROXAS | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2656745.92 |  |  | Completed | 1
23580 | NC 2017 | K10 | Region II | Isabela | 103649 | Bautista ES - Main | SAN AGUSTIN | 4 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3931402.87 |  |  | Completed | 1
23581 | NC 2017 | K10 | Region II | Isabela | 103660 | Palacian ES | SAN AGUSTIN | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2738254.17 |  |  | Completed | 1
23582 | NC 2017 | K10 | Region II | Isabela | 103661 | Panang ES | SAN AGUSTIN | 4 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 7 | 5112814.7 |  |  | Completed | 1
23583 | NC 2017 | K10 | Region II | Isabela | 103662 | Quimalabasa Norte ES | SAN AGUSTIN | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2738254.17 |  |  | Completed | 1
23584 | NC 2017 | K10 | Region II | Isabela | 103664 | Salay ES | SAN AGUSTIN | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2738254.17 |  |  | Completed | 1
23585 | NC 2017 | K10 | Region II | Isabela | 103664 | Salay ES | SAN AGUSTIN | 4 |  | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2738254.17 |  |  | Completed | 1
23586 | NC 2017 | K10 | Region II | Isabela | 103665 | San Agustin CS | SAN AGUSTIN | 4 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 7 | 5112814.7 |  |  | Completed | 1
23587 | NC 2017 | K10 | Region II | Isabela | 103666 | San Antonio Elementary School | SAN AGUSTIN | 4 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3931402.87 |  |  | Completed | 1
23588 | NC 2017 | K10 | Region II | Isabela | 103670 | Sto. Nino ES | SAN AGUSTIN | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2738254.17 |  |  | Completed | 1
23589 | NC 2017 | K10 | Region II | Isabela | 103805 | Minanga ES | SAN PABLO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2646278 |  |  | Completed | 1
23590 | NC 2017 | K10 | Region II | Isabela | 103805 | Minanga ES | SAN PABLO | 1 |  | 3 | 1STY3CL | BATCH 7 | 3817307.57 |  |  | Completed | 1
23591 | NC 2017 | TVL | Region II | Isabela | 300606 | Santo Tomas National High School | SANTO TOMAS | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3200025.05 |  |  | Completed | 1
23592 | NC 2017 | TVL | Region II | Isabela | 300606 | Santo Tomas National High School | SANTO TOMAS | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3200025.05 |  |  | Completed | 1
23593 | NC 2017 | K10 | Region II | Isabela | 103896 | Lalauanan-Sto. Niño ES | TUMAUINI | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2612890.59 |  |  | Completed | 1
23594 | NC 2017 | TVL | Region II | Isabela | 500088 | Cumabao IS | Tumauni | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3289774.94 |  |  | Completed | 1
23595 | NC 2017 | K10 | Region II | Nueva Vizcaya | 103982 | Ammoweg ES | AMBAGUIO | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3158000 |  |  | Completed | 1
23596 | NC 2017 | K10 | Region II | Nueva Vizcaya | 103996 | Pacdal ES | AMBAGUIO | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 4161706.88 |  |  | Completed | 1
23597 | NC 2017 | K10 | Region II | Nueva Vizcaya | 103976 | San Antonio North ES | BAMBANG | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2950000 |  |  | Completed | 1
23598 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104117 | Bulo-Galsa PS | KAYAPA | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3042555.61 |  |  | Completed | 1
23599 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104120 | Cabayo ES | KAYAPA | 0 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 4507898.57 |  |  | Completed | 1
23600 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104126 | Kayapa Proper ES Annex | KAYAPA | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2890867.16 |  |  | Completed | 1
23601 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104132 | Mapayao ES | KAYAPA | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2831442.17 |  |  | Completed | 1
23602 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104135 | Napo-Tuyak IS | KAYAPA | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2731168.56 |  |  | Completed | 1
23603 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104145 | Tuppan PS | KAYAPA | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2917981.27 |  |  | Completed | 1
23604 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104146 | Atan ES | QUEZON | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3770000 |  |  | Completed | 1
23605 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104157 | Maasin ES | QUEZON | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3158000 |  |  | Completed | 1
23606 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104158 | Maddiangat ES | QUEZON | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2815000 |  |  | Completed | 1
23607 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104189 | ATBU ELEMENTARY SCHOOL | SANTA FE | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3032971.61 |  |  | Completed | 1
23608 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104197 | Cauco ES | SANTA FE | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2973058.94 |  |  | Completed | 1
23609 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104202 | Imugan ES | SANTA FE | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2663745.92 |  |  | Completed | 1
23610 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104182 | Solano North ES | SOLANO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3000000 |  |  | Completed | 1
23611 | NC 2017 | K10 | Region II | Quirino | 104224 | Aglipay West CS | AGLIPAY | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2658000 |  |  | Completed | 1
23612 | NC 2017 | K10 | Region II | Quirino | 104227 | Dagupan ES | AGLIPAY | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2647000 |  |  | Completed | 1
23613 | NC 2017 | K10 | Region II | Quirino | 104229 | Diodol ES | AGLIPAY | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2636000 |  |  | Completed | 1
23614 | NC 2017 | K10 | Region II | Quirino | 104231 | Ligaya ES | AGLIPAY | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2640000 |  |  | Completed | 1
23615 | NC 2017 | K10 | Region II | Quirino | 104232 | Nagabgaban IS | AGLIPAY | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2839000 |  |  | Completed | 1
23616 | NC 2017 | K10 | Region II | Quirino | 104233 | Osmena ES | AGLIPAY | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2625000 |  |  | Completed | 1
23617 | NC 2017 | K10 | Region II | Quirino | 156501 | Pinahiw ES | AGLIPAY | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2656000 |  |  | Completed | 1
23618 | NC 2017 | K10 | Region II | Quirino | 104239 | Ramos ES | AGLIPAY | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2636000 |  |  | Completed | 1
23619 | NC 2017 | K10 | Region II | Quirino | 104241 | San Antonio ES | AGLIPAY | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2636000 |  |  | Completed | 1
23620 | NC 2017 | K10 | Region II | Quirino | 104242 | San Benigno ES | AGLIPAY | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2658000 |  |  | Completed | 1
23621 | NC 2017 | K10 | Region II | Quirino | 104245 | San Manuel ES | AGLIPAY | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2628000 |  |  | Completed | 1
23622 | NC 2017 | K10 | Region II | Quirino | 104249 | Villa Pagaduan Elementary School | AGLIPAY | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2690000 |  |  | Completed | 1
23623 | NC 2017 | K10 | Region II | Quirino | 104251 | Villa Ventura ES | AGLIPAY | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2640000 |  |  | Completed | 1
23624 | NC 2017 | K10 | Region II | Quirino | 104253 | Banuar ES | CABARROGUIS (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2646000 |  |  | Completed | 1
23625 | NC 2017 | K10 | Region II | Quirino | 104255 | Cabarroguis CS | CABARROGUIS (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2646000 |  |  | Completed | 1
23626 | NC 2017 | K10 | Region II | Quirino | 104259 | Dingasan IS | CABARROGUIS (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2680000 |  |  | Completed | 1
23627 | NC 2017 | K10 | Region II | Quirino | 104261 | Gen. Luna ES | CABARROGUIS (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2707000 |  |  | Completed | 1
23628 | NC 2017 | K10 | Region II | Quirino | 104262 | Gomez ES | CABARROGUIS (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2657000 |  |  | Completed | 1
23629 | NC 2017 | K10 | Region II | Quirino | 104263 | Loacan ES | CABARROGUIS (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2760000 |  |  | Completed | 1
23630 | NC 2017 | K10 | Region II | Quirino | 104264 | Mangandingay ES | CABARROGUIS (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2646000 |  |  | Completed | 1
23631 | NC 2017 | K10 | Region II | Quirino | 104268 | Tucod ES | CABARROGUIS (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2657000 |  |  | Completed | 1
23632 | NC 2017 | K10 | Region II | Quirino | 104272 | Villamor ES | CABARROGUIS (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2737000 |  |  | Completed | 1
23633 | NC 2017 | K10 | Region II | Quirino | 104273 | Villarose IS | CABARROGUIS (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2657000 |  |  | Completed | 1
23634 | NC 2017 | K10 | Region II | Quirino | 104290 | Aklan Village ES | DIFFUN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2657000 |  |  | Completed | 1
23635 | NC 2017 | K10 | Region II | Quirino | 104293 | Balagbag Elementary School | DIFFUN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2736000 |  |  | Completed | 1
23636 | NC 2017 | K10 | Region II | Quirino | 104296 | Campamento ES | DIFFUN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2646000 |  |  | Completed | 1
23637 | NC 2017 | K10 | Region II | Quirino | 104280 | Diffun CS | DIFFUN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2657000 |  |  | Completed | 1
23638 | NC 2017 | K10 | Region II | Quirino | 104303 | Guinagat PS | DIFFUN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2722000 |  |  | Completed | 1
23639 | NC 2017 | K10 | Region II | Quirino | 104304 | Ifugao Village IS | DIFFUN | 0 | 1 | 3 | 1STY3CL | BATCH 7 | 3799500 |  |  | Completed | 1
23640 | NC 2017 | K10 | Region II | Quirino | 104307 | Luttuad ES | DIFFUN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2657000 |  |  | Completed | 1
23641 | NC 2017 | K10 | Region II | Quirino | 104312 | Pimentel ES | DIFFUN | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 2677000 |  |  | Completed | 1
23642 | NC 2017 | K10 | Region II | Santiago City | 103834 | Balintocatoc ES | CITY OF SANTIAGO | 4 | 1 | 3 | 1STY3CL | BATCH 7 | 3931402.87 |  |  | Completed | 1
23643 | NC 2017 | K10 | Region II | Santiago City | 103813 | Divisoria ES | CITY OF SANTIAGO | 4 | 1 | 2 | 1STY2CL | BATCH 7 | 2738254.17 |  |  | Completed | 1
23644 | NC 2017 | K10 | Region II | Santiago City | 103813 | Divisoria ES | CITY OF SANTIAGO | 4 |  | 3 | 1STY3CL | BATCH 7 | 3931402.87 |  |  | Completed | 1
23645 | NC 2017 | K10 | Region II | Santiago City | 103828 | Patul Elementary School | CITY OF SANTIAGO | 4 | 1 | 2 | 1STY2CL | BATCH 7 | 2738254.17 |  |  | Completed | 1
23646 | NC 2017 | K10 | Region II | Santiago City | 103819 | Sagana Elementary School | CITY OF SANTIAGO | 4 | 1 | 4 | 1STY4CL | BATCH 7 | 5112814 |  |  | Completed | 1
23647 | NC 2017 | TVL | Region II | Cagayan | 300418 | Abulug National Rural and Vocational High School | ABULUG | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2983950.8 |  |  | Completed | 1
23648 | NC 2017 | TVL | Region II | Cagayan | 300418 | Abulug National Rural and Vocational High School | ABULUG | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2358227.58 |  |  | Completed | 1
23649 | NC 2017 | TVL | Region II | Cagayan | 300418 | Abulug National Rural and Vocational High School | ABULUG | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2358227.58 |  |  | Completed | 1
23650 | NC 2017 | TVL | Region II | Cagayan | 300418 | Abulug National Rural and Vocational High School | ABULUG | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2358227.58 |  |  | Completed | 1
23651 | NC 2017 | SHS | Region II | Cagayan | 300418 | Abulug NRVHS | ABULUG | 2 |  | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1
23652 | NC 2017 | TVL | Region II | Cagayan | 300419 | Abulug SOF | ABULUG | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3087675.23 |  |  | Completed | 1
23653 | NC 2017 | SHS | Region II | Cagayan | 300419 | Abulug SOF | ABULUG | 2 |  | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
23654 | NC 2017 | K10 | Region II | Cagayan | 102345 | Pinili ES | ABULUG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
23655 | NC 2017 | K10 | Region II | Cagayan | 102353 | Sto. Tomas ES | ABULUG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
23656 | NC 2017 | K10 | Region II | Cagayan | 102381 | Bulo Elementary School | ALLACAPAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2640390.67 |  |  | Completed | 1
23657 | NC 2017 | K10 | Region II | Cagayan | 102387 | Iringan ES | ALLACAPAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2640443.53 |  |  | Completed | 1
23658 | NC 2017 | K10 | Region II | Cagayan | 102389 | Kapalutan ES | ALLACAPAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2674862.29 |  |  | Completed | 1
23659 | NC 2017 | K10 | Region II | Cagayan | 102395 | Matucay Elementary School | ALLACAPAN | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3810302.12 |  |  | Completed | 1
23660 | NC 2017 | SHS | Region II | Cagayan | 300477 | Matucay National High School | ALLACAPAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2643456.88 |  |  | Completed | 1
23661 | NC 2017 | K10 | Region II | Cagayan | 102400 | Tubel Elementary School | ALLACAPAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2640390.67 |  |  | Completed | 1
23662 | NC 2017 | K10 | Region II | Cagayan | 102535 | Ammubuan ES | BALLESTEROS | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
23663 | NC 2017 | K10 | Region II | Cagayan | 102536 | Ballesteros CS | BALLESTEROS | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
23664 | NC 2017 | K10 | Region II | Cagayan | 102537 | Ballesteros West CS | BALLESTEROS | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
23665 | NC 2017 | K10 | Region II | Cagayan | 102537 | Ballesteros West CS | BALLESTEROS | 2 |  | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
23666 | NC 2017 | K10 | Region II | Cagayan | 102538 | Cabanabaan ES | BALLESTEROS | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
23667 | NC 2017 | K10 | Region II | Cagayan | 155025 | Caranan-Babbay PS | BALLESTEROS | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
23668 | NC 2017 | K10 | Region II | Cagayan | 102581 | Babuyan Claro IS | CALAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3265798.98 |  |  | Completed | 1
23669 | NC 2017 | SHS | Region II | Cagayan | 500064 | Babuyan Claro IS | CALAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3264374.36 |  |  | Completed | 1
23670 | NC 2017 | TVL | Region II | Cagayan | 500064 | Babuyan Claro IS | CALAYAN | 2 |  | 2 | Workshop Bldg. (7x18) | BATCH 10 | 5880401.79 |  |  | Completed | 1
23671 | NC 2017 | TVL | Region II | Cagayan | 500064 | Babuyan Claro IS | CALAYAN | 2 |  | 2 | Workshop Bldg. (7x18) | BATCH 10 | 5826394.77 |  |  | Completed | 1
23672 | NC 2017 | K10 | Region II | Cagayan | 102583 | Cadadalman ES | CALAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3237992.45 |  |  | Completed | 1
23673 | NC 2017 | SHS | Region II | Cagayan | 300441 | Calayan HS | CALAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3237992.45 |  |  | Completed | 1
23674 | NC 2017 | K10 | Region II | Cagayan | 102585 | Camiguin ES | CALAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3237992.45 |  |  | Completed | 1
23675 | NC 2017 | K10 | Region II | Cagayan | 102586 | Caniwalan ES | CALAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3265798.98 |  |  | Completed | 1
23676 | NC 2017 | K10 | Region II | Cagayan | 102588 | Dalupiri ES | CALAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3237992.45 |  |  | Completed | 1
23677 | NC 2017 | K10 | Region II | Cagayan | 102593 | Morol ES | CALAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3265798.98 |  |  | Completed | 1
23678 | NC 2017 | K10 | Region II | Cagayan | 102594 | Pilid ES | CALAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3265798.98 |  |  | Completed | 1
23679 | NC 2017 | TVL | Region II | Cagayan | 300450 | Claveria RVS | CLAVERIA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2983950.8 |  |  | Completed | 1
23680 | NC 2017 | TVL | Region II | Cagayan | 300451 | Claveria SAT | CLAVERIA | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2594658.81 |  |  | Completed | 1
23681 | NC 2017 | TVL | Region II | Cagayan | 300451 | Claveria SAT | CLAVERIA | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2983950.8 |  |  | Completed | 1
23682 | NC 2017 | K10 | Region II | Cagayan | 102755 | Aggunetan ES | LASAM | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2674862.29 |  |  | Completed | 1
23683 | NC 2017 | K10 | Region II | Cagayan | 102763 | I.B. Jurado ES | LASAM | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2674862.29 |  |  | Completed | 1
23684 | NC 2017 | TVL | Region II | Cagayan | 300439 | Nabannagan National High School | LASAM | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3169329.065 |  |  | Completed | 1
23685 | NC 2017 | TVL | Region II | Cagayan | 300439 | Nabannagan National High School | LASAM | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3169329.065 |  |  | Completed | 1
23686 | NC 2017 | TVL | Region II | Cagayan | 300497 | Western Cagayan SAT | LASAM | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3089457.37 |  |  | Completed | 1
23687 | NC 2017 | TVL | Region II | Cagayan | 300479 | Pamplona National School of Fisheries | PAMPLONA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2983950.8 |  |  | Completed | 1
23688 | NC 2017 | K10 | Region II | Cagayan | 102820 | Apayao ES | PIAT | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
23689 | NC 2017 | K10 | Region II | Cagayan | 102827 | Piat CS | PIAT | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
23690 | NC 2017 | SHS | Region II | Cagayan | 300481 | Piat National HS | PIAT | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
23691 | NC 2017 | SHS | Region II | Cagayan | 300481 | Piat National HS | PIAT | 2 |  | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1
23692 | NC 2017 | SHS | Region II | Cagayan | 300481 | Piat National HS | PIAT | 2 |  | 4 | 1STY4CL | BATCH 10 | 4888351.15 |  |  | Completed | 1
23693 | NC 2017 | K10 | Region II | Cagayan | 102837 | Gaggabutan Elementary School | RIZAL | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1
23694 | NC 2017 | TVL | Region II | Cagayan | 300464 | Illuru NHS | RIZAL | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2594658.81 |  |  | Completed | 1
23695 | NC 2017 | K10 | Region II | Cagayan | 102839 | Lattut ES | RIZAL | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
23696 | NC 2017 | K10 | Region II | Cagayan | 102841 | Masi Elementary School | RIZAL | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2664791.16 |  |  | Completed | 1
23697 | NC 2017 | K10 | Region II | Cagayan | 102841 | Masi Elementary School | RIZAL | 2 |  | 2 | 1STY2CL | BATCH 10 | 2664791.16 |  |  | Completed | 1
23698 | NC 2017 | TVL | Region II | Cagayan | 300478 | Mauanan NHS | RIZAL | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3049905.57 |  |  | Completed | 1
23699 | NC 2017 | K10 | Region II | Cagayan | 102844 | Rizal CS | RIZAL | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1
23700 | NC 2017 | K10 | Region II | Cagayan | 102846 | Sinicking ES | RIZAL | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3837965.07 |  |  | Completed | 1
23701 | NC 2017 | K10 | Region II | Cagayan | 102847 | Villa Cruz ES | RIZAL | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
23702 | NC 2017 | K10 | Region II | Cagayan | 155046 | Pureg Elementary School | SANCHEZ-MIRA | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2718273.37 |  |  | Completed | 1
23703 | NC 2017 | TVL | Region II | Cagayan | 300485 | Sanchez Mira NHS | SANCHEZ-MIRA | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2579261.77 |  |  | Completed | 1
23704 | NC 2017 | TVL | Region II | Cagayan | 300489 | Sta. Praxedes High School | SANTA PRAXEDES | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2594658.81 |  |  | Completed | 1
23705 | NC 2017 | TVL | Region II | Cagayan | 306006 | Abariongan National High School | SANTO NIÑO (FAIRE) | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3057601.45 |  |  | Completed | 1
23706 | NC 2017 | TVL | Region II | Cagayan | 306006 | Abariongan National High School | SANTO NIÑO (FAIRE) | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2661386.75 |  |  | Completed | 1
23707 | NC 2017 | K10 | Region II | Cagayan | 102939 | Calapangan Elementary School | SANTO NIÑO (FAIRE) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2669607.92 |  |  | Completed | 1
23708 | NC 2017 | TVL | Region II | Cagayan | 306425 | Namuccayan Integrated School | SANTO NIÑO (FAIRE) | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2983950.8 |  |  | Completed | 1
23709 | NC 2017 | TVL | Region II | Cagayan | 300491 | Sto. Nino NHS | SANTO NIÑO (FAIRE) | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2983950.8 |  |  | Completed | 1
23710 | NC 2017 | K10 | Region II | Isabela | 103125 | Yeban Integrated School | BENITO SOLIVEN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2788254.17 |  |  | Completed | 1
23711 | NC 2017 | K10 | Region II | Isabela | 300553 | Yeban Integrated School | BENITO SOLIVEN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2788254.17 |  |  | Completed | 1
23712 | NC 2017 | K10 | Region II | Isabela | 103128 | Burgos CS | BURGOS | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2912079.59 |  |  | Completed | 1
23713 | NC 2017 | K10 | Region II | Isabela | 103258 | Cordon North CS (Turod Norte ES) | CORDON | 4 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 3931402.87 |  |  | Completed | 1
23714 | NC 2017 | K10 | Region II | Isabela | 103258 | Cordon North CS (Turod Norte ES) | CORDON | 4 |  | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2738254.17 |  |  | Completed | 1
23715 | NC 2017 | K10 | Region II | Isabela | 103311 | Echague South CS | ECHAGUE | 6 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 3931402.87 |  |  | Completed | 1
23716 | NC 2017 | K10 | Region II | Isabela | 103311 | Echague South CS | ECHAGUE | 6 |  | 3 | 1STY3CL W/ TOILET | BATCH 10 | 3931402.87 |  |  | Completed | 1
23717 | NC 2017 | K10 | Region II | Isabela | 103311 | Echague South CS | ECHAGUE | 6 |  | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2738254.17 |  |  | Completed | 1
23718 | NC 2017 | K10 | Region II | Isabela | 103311 | Echague South CS | ECHAGUE | 6 |  | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2738254.17 |  |  | Completed | 1
23719 | NC 2017 | K10 | Region II | Isabela | 103315 | Pangal Sur ES | ECHAGUE | 6 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 3931402.87 |  |  | Completed | 1
23720 | NC 2017 | K10 | Region II | Isabela | 103315 | Pangal Sur ES | ECHAGUE | 6 |  | 3 | 1STY3CL W/ TOILET | BATCH 10 | 3931402.87 |  |  | Completed | 1
23721 | NC 2017 | SHS | Region II | Isabela | 300559 | Mabini NHS | GAMU | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2788254.17 |  |  | Completed | 1
23722 | NC 2017 | K10 | Region II | Isabela | 103446 | Jones East Central School | JONES | 4 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 3931402.87 |  |  | Completed | 1
23723 | NC 2017 | K10 | Region II | Isabela | 103446 | Jones East Central School | JONES | 4 |  | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2738254.17 |  |  | Completed | 1
23724 | NC 2017 | K10 | Region II | Isabela | 103481 | San Vicente ES | JONES | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2738254.17 |  |  | Completed | 1
23725 | NC 2017 | K10 | Region II | Isabela | 103481 | San Vicente ES | JONES | 4 |  | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2738254.17 |  |  | Completed | 1
23726 | NC 2017 | K10 | Region II | Isabela | 306138 | Bimonton Integrated School | MALLIG | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2788254.17 |  |  | Completed | 1
23727 | NC 2017 | K10 | Region II | Isabela | 103493 | Bimonton Integrated School (formerly Bimonton ES) | MALLIG | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2938254.17 |  |  | Completed | 1
23728 | NC 2017 | K10 | Region II | Isabela | 155537 | Dipadsanjan Primary School | PALANAN | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 4923700 |  |  | Completed | 1
23729 | NC 2017 | K10 | Region II | Isabela | 103584 | San Juan ES | QUIRINO | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2788254.17 |  |  | Completed | 1
23730 | NC 2017 | K10 | Region II | Isabela | 103597 | Bugallon Norte ES | RAMON | 4 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 10 | 5112814.7 |  |  | Completed | 1
23731 | NC 2017 | K10 | Region II | Isabela | 103640 | Bantug/Lintao ES | ROXAS | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2788254.17 |  |  | Completed | 1
23732 | NC 2017 | K10 | Region II | Isabela | 103647 | Simimbaan Integrated School | ROXAS | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2758254.17 |  |  | Completed | 1
23733 | NC 2017 | K10 | Region II | Isabela | 103655 | Dorganda ES | SAN AGUSTIN | 4 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 3933402.87 |  |  | Completed | 1
23734 | NC 2017 | K10 | Region II | Isabela | 103668 | Sinaoangan Norte ES | SAN AGUSTIN | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2738254.17 |  |  | Completed | 1
23735 | NC 2017 | K10 | Region II | Isabela | 103714 | Eden Integrated School | SAN MANUEL | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2788254.17 |  |  | Completed | 1
23736 | NC 2017 | K10 | Region II | Isabela | 103729 | Balagan Elementary School | SAN MARIANO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2816745.92 |  |  | Completed | 1
23737 | NC 2017 | K10 | Region II | Isabela | 103730 | Bitabian Elementary School | SAN MARIANO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2816745.92 |  |  | Completed | 1
23738 | NC 2017 | K10 | Region II | Isabela | 103731 | Buyasan ES (Buyasan PS) | SAN MARIANO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2976271.35 |  |  | Completed | 1
23739 | NC 2017 | K10 | Region II | Isabela | 103753 | Dibuluan Elementary School | SAN MARIANO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2915046.86 |  |  | Completed | 1
23740 | NC 2017 | K10 | Region II | Isabela | 103756 | Disusuan Elementary School | SAN MARIANO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2730352.98 |  |  | Completed | 1
23741 | NC 2017 | K10 | Region II | Isabela | 103742 | San Mariano Central School SPED Center | SAN MARIANO | 2 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 10 | 5624096.17 |  |  | Completed | 1
23742 | NC 2017 | K10 | Region II | Isabela | 103743 | San Pablo Elementary School | SAN MARIANO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2856745.92 |  |  | Completed | 1
23743 | NC 2017 | K10 | Region II | Isabela | 155511 | Udiao Elementary School | SAN MARIANO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2816745.92 |  |  | Completed | 1
23744 | NC 2017 | K10 | Region II | Isabela | 330501 | Dalena High School | SAN PABLO | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3777756.96 |  |  | Completed | 1
23745 | NC 2017 | K10 | Region II | Isabela | 330501 | Dalena High School | SAN PABLO | 1 |  | 3 | 1STY3CL | BATCH 10 | 3777756.96 |  |  | Completed | 1
23746 | NC 2017 | K10 | Region II | Isabela | 103809 | Simanu Norte Elementary School | SAN PABLO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
23747 | NC 2017 | K10 | Region II | Isabela | 103846 | Divisoria Elementary School | SANTA MARIA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
23748 | NC 2017 | K10 | Region II | Isabela | 103855 | Villabuena Elementary School | SANTA MARIA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
23749 | NC 2017 | K10 | Region II | Isabela | 155513 | San Rafael Alto Elementary School | SANTO TOMAS | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
23750 | NC 2017 | K10 | Region II | Isabela | 103869 | San Roque Elementary School | SANTO TOMAS | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3813703.02 |  |  | Completed | 1
23751 | NC 2017 | K10 | Region II | Isabela | 155533 | Dalayya Elementary School | TUMAUINI | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
23752 | NC 2017 | K10 | Region II | Isabela | 103894 | Dy-Abra Elementary School | TUMAUINI | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3777756.96 |  |  | Completed | 1
23753 | NC 2017 | K10 | Region II | Isabela | 103880 | San Francisco Elementary School | TUMAUINI | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
23754 | NC 2017 | K10 | Region II | Quirino | 104248 | Victoria Elementary School Annex | AGLIPAY | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2630000 |  |  | Completed | 1
23755 | NC 2017 | SHS | Region II | Quirino | 300656 | Cabarroguis NSAT | CABARROGUIS (Capital) | 0 | 1 | 12 | 3STY12CL | BATCH 10 | 30732135 |  |  | Completed | 1
23756 | NC 2017 | SHS | Region II | Quirino | 300656 | Cabarroguis NSAT | CABARROGUIS (Capital) | 0 |  | 16 | 4STY16CL | BATCH 10 | 39164930 |  |  | Completed | 1
23757 | NC 2017 | SHS | Region II | Quirino | 300656 | Cabarroguis NSAT | CABARROGUIS (Capital) | 0 |  | 16 | 4STY16CL | BATCH 10 | 39164930 |  |  | Completed | 1
23758 | NC 2017 | SHS | Region II | Quirino | 300656 | Cabarroguis NSAT | CABARROGUIS (Capital) | 0 |  | 8 | 2STY8CL | BATCH 10 | 17503471 |  |  | Completed | 1
23759 | NC 2017 | SHS | Region II | Quirino | 300664 | Quirino General HS | CABARROGUIS (Capital) | 0 |  | 4 | 2STY4CL | BATCH 10 | 9450000 |  |  | Completed | 1
23760 | NC 2017 | K10 | Region II | Quirino | 104292 | Baguio Village Elementary School | DIFFUN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2680000 |  |  | Completed | 1
23761 | NC 2017 | K10 | Region II | Quirino | 104294 | Bikibik ES | DIFFUN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2730000 |  |  | Completed | 1
23762 | NC 2017 | K10 | Region II | Quirino | 104306 | Liwayway ES | DIFFUN | 0 | 1 | 3 | 1STY3CL | BATCH 10 | 3778200 |  |  | Completed | 1
23763 | NC 2017 | SHS | Region II | Quirino | 300661 | Magsaysay National High School | DIFFUN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2657000 |  |  | Completed | 1
23764 | NC 2017 | K10 | Region II | Quirino | 104310 | Pallutan PS | DIFFUN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2707000 |  |  | Completed | 1
23765 | NC 2017 | K10 | Region II | Quirino | 104311 | Pamungyen E/S | DIFFUN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2817000 |  |  | Completed | 1
23766 | NC 2017 | K10 | Region II | Quirino | 104314 | Ricarte Norte ES | DIFFUN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2657000 |  |  | Completed | 1
23767 | NC 2017 | K10 | Region II | Quirino | 156506 | Rizal ES | DIFFUN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2706000 |  |  | Completed | 1
23768 | NC 2017 | K10 | Region II | Quirino | 156507 | Turayok Elementary School | DIFFUN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2730000 |  |  | Completed | 1
23769 | NC 2017 | K10 | Region II | Quirino | 104288 | Upper Gabriela ES | DIFFUN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2658000 |  |  | Completed | 1
23770 | NC 2017 | K10 | Region II | Quirino | 104319 | Cabaruan IS | MADDELA | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2625000 |  |  | Completed | 1
23771 | NC 2017 | K10 | Region II | Quirino | 104320 | Cofcaville ES | MADDELA | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2709000 |  |  | Completed | 1
23772 | NC 2017 | K10 | Region II | Quirino | 300659 | Dipintin HS | MADDELA | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2625000 |  |  | Completed | 1
23773 | NC 2017 | K10 | Region II | Quirino | 104325 | Divisoria Norte ES | MADDELA | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2624000 |  |  | Completed | 1
23774 | NC 2017 | K10 | Region II | Quirino | 104324 | Divisoria Sur IS | MADDELA | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2622000 |  |  | Completed | 1
23775 | NC 2017 | K10 | Region II | Quirino | 104327 | Kaboa-an ES | MADDELA | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2633000 |  |  | Completed | 1
23776 | NC 2017 | K10 | Region II | Quirino | 104328 | Lusod Elementary School | MADDELA | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2620000 |  |  | Completed | 1
23777 | NC 2017 | K10 | Region II | Quirino | 104329 | Mariano Gadingan ES | MADDELA | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2622000 |  |  | Completed | 1
23778 | NC 2017 | K10 | Region II | Quirino | 104335 | San Dionisio I ES | MADDELA | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2647000 |  |  | Completed | 1
23779 | NC 2017 | K10 | Region II | Quirino | 104338 | San Salvador ES | MADDELA | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2630000 |  |  | Completed | 1
23780 | NC 2017 | K10 | Region II | Quirino | 104340 | Sto. Niño ES | MADDELA | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2706000 |  |  | Completed | 1
23781 | NC 2017 | K10 | Region II | Quirino | 104341 | Sto. Tomas ES | MADDELA | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2628000 |  |  | Completed | 1
23782 | NC 2017 | K10 | Region II | Quirino | 156502 | VILLA FLOR E/S | MADDELA | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2640000 |  |  | Completed | 1
23783 | NC 2017 | K10 | Region II | Quirino | 306315 | Villagracia IS | MADDELA | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2630000 |  |  | Completed | 1
23784 | NC 2017 | K10 | Region II | Quirino | 104346 | Ysmael ES | MADDELA | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2630000 |  |  | Completed | 1
23785 | NC 2017 | K10 | Region II | Quirino | 104349 | Dicuraban ES | NAGTIPUNAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2659000 |  |  | Completed | 1
23786 | NC 2017 | K10 | Region II | Quirino | 104350 | Dioryong IS | NAGTIPUNAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2727000 |  |  | Completed | 1
23787 | NC 2017 | K10 | Region II | Quirino | 104354 | Keat ES | NAGTIPUNAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2759000 |  |  | Completed | 1
23788 | NC 2017 | K10 | Region II | Quirino | 104355 | Kimmabayo ES | NAGTIPUNAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2641000 |  |  | Completed | 1
23789 | NC 2017 | K10 | Region II | Quirino | 104359 | Macabo ES | NAGTIPUNAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2637000 |  |  | Completed | 1
23790 | NC 2017 | K10 | Region II | Quirino | 104361 | Matmad IS | NAGTIPUNAN | 0 | 1 | 2 | 1STY2CL ALL WOOD | BATCH 10 | 2290000 |  |  | Completed | 1
23791 | NC 2017 | K10 | Region II | Quirino | 104364 | San Pugo Elementary School | NAGTIPUNAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2681000 |  |  | Completed | 1
23792 | NC 2017 | K10 | Region II | Quirino | 104365 | San Ramos ES | NAGTIPUNAN | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2648000 |  |  | Completed | 1
23793 | NC 2017 | K10 | Region II | Quirino | 104380 | Tres Reyes ES | SAGUDAY | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2646000 |  |  | Completed | 1
23794 | NC 2017 | TVL | Region II | Batanes | 300414 | Itbayat National Agricultural HS | ITBAYAT | 0 | 1 | 1 | Unique Workshop (7x22.5) | BATCH 12 | 7215000 |  |  | Completed | 1
23795 | NC 2017 | TVL | Region II | Batanes | 300414 | Itbayat National Agricultural HS | ITBAYAT | 0 |  | 1 | Unique Workshop (7x22.5) | BATCH 12 | 7215000 |  |  | Completed | 1
23796 | NC 2017 | TVL | Region II | Batanes | 300414 | Itbayat National Agricultural HS | ITBAYAT | 0 |  | 1 | Unique Workshop (7x22.5) | BATCH 12 | 7215000 |  |  | Completed | 1
23797 | NC 2017 | TVL | Region II | Batanes | 300414 | Itbayat National Agricultural HS | ITBAYAT | 0 |  | 1 | Unique Workshop (7x22.5) | BATCH 12 | 7215000 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Funds 2018
23798 | NC 2017 | TVL | Region II | Batanes | 300414 | Itbayat National Agricultural HS | ITBAYAT | 0 |  | 1 | Unique Workshop (7x22.5) | BATCH 12 | 7215000 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Funds 2018
23799 | NC 2017 | TVL | Region II | Batanes | 300414 | Itbayat National Agricultural HS | ITBAYAT | 0 |  | 1 | Unique Workshop (7x22.5) | BATCH 12 | 7215000 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Funds 2018
23800 | NC 2017 | K10 | Region II | Cagayan | 102482 | Barsat East ES | BAGGAO | 1 | 1 | 6 | 2 Units of 1STY3CL W/ TOILET | BATCH 12 | 9000000 |  |  | Completed | 1
23801 | NC 2017 | K10 | Region II | Cagayan | 102500 | Santor ES | BAGGAO | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 3000000 |  |  | Completed | 1
23802 | NC 2017 | SHS | Region II | Cagayan | 300474 | Licerio Antiporda Sr. NHS | BUGUEY | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4500000 |  |  | Completed | 1
23803 | NC 2017 | SHS | Region II | Cagayan | 300474 | Licerio Antiporda Sr. NHS | BUGUEY | 1 |  | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4500000 |  |  | Completed | 1
23804 | NC 2017 | SHS | Region II | Cagayan | 306005 | Licerio Antiporda Sr. NHS - Sta. Isabel Ext. | BUGUEY | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4500000 |  |  | Completed | 1
23805 | NC 2017 | SHS | Region II | Cagayan | 306005 | Licerio Antiporda Sr. NHS - Sta. Isabel Ext. | BUGUEY | 1 |  | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4500000 |  |  | Completed | 1
23806 | NC 2017 | SHS | Region II | Cagayan | 306005 | Licerio Antiporda Sr. NHS - Sta. Isabel Ext. | BUGUEY | 1 |  | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4500000 |  |  | Completed | 1
23807 | NC 2017 | K10 | Region II | Cagayan | 102567 | Minanga ES | BUGUEY | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4500000 |  |  | Completed | 1
23808 | NC 2017 | SHS | Region II | Cagayan | 306012 | Pattao NHS - Maddalero Ext. | BUGUEY | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4500000 |  |  | Completed | 1
23809 | NC 2017 | SHS | Region II | Cagayan | 306012 | Pattao NHS - Maddalero Ext. | BUGUEY | 1 |  | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4500000 |  |  | Completed | 1
23810 | NC 2017 | K10 | Region II | Cagayan | 102575 | San Lorenzo ES | BUGUEY | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4500000 |  |  | Completed | 1
23811 | NC 2017 | K10 | Region II | Cagayan | 306426 | Camalaniugan National High School- Catotoran Annex | CAMALANIUGAN | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4500000 |  |  | Completed | 1
23812 | NC 2017 | K10 | Region II | Cagayan | 306426 | Camalaniugan National High School- Catotoran Annex | CAMALANIUGAN | 1 |  | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4500000 |  |  | Completed | 1
23813 | NC 2017 | SHS | Region II | Cagayan | 306422 | Calaoagan Dackel National High School-Capissayan Annex | GATTARAN | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4500000 |  |  | Completed | 1
23814 | NC 2017 | SHS | Region II | Cagayan | 306422 | Calaoagan Dackel National High School-Capissayan Annex | GATTARAN | 1 |  | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4500000 |  |  | Completed | 1
23815 | NC 2017 | SHS | Region II | Cagayan | 306422 | Calaoagan Dackel National High School-Capissayan Annex | GATTARAN | 1 |  | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4500000 |  |  | Completed | 1
23816 | NC 2017 | K10 | Region II | Cagayan |  | Cabiraoan NHS | GONZAGA | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4500000 |  |  | Completed | 1
23817 | NC 2017 | K10 | Region II | Cagayan |  | Gonzaga NHS-Sta. Clara Annex | GONZAGA | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4500000 |  |  | Completed | 1
23818 | NC 2017 | K10 | Region II | Cagayan |  | Gonzaga NHS-Sta. Clara Annex | GONZAGA | 1 |  | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4500000 |  |  | Completed | 1
23819 | NC 2017 | SHS | Region II | Cagayan | 300482 | Rebecca NHS | GONZAGA | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4500000 |  |  | Completed | 1
23820 | NC 2017 | SHS | Region II | Cagayan | 300482 | Rebecca NHS | GONZAGA | 1 |  | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4500000 |  |  | Completed | 1
23821 | NC 2017 | SHS | Region II | Cagayan | 300482 | Rebecca NHS | GONZAGA | 1 |  | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4500000 |  |  | Completed | 1
23822 | NC 2017 | K10 | Region II | Cagayan |  | Cambong PS | Lal-lo | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 3000000 |  |  | Completed | 1
23823 | NC 2017 | K10 | Region II | Cagayan | 102742 | Catugan ES | LAL-LO | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 3000000 |  |  | Completed | 1
23824 | NC 2017 | TVL | Region II | Cagayan | 300457 | Penablanca East NHS | PEÑABLANCA | 3 | 1 | 1 | Unique Workshop (7x22.5) | BATCH 12 | 3169336 |  |  | Completed | 1
23825 | NC 2017 | K10 | Region II | Cauayan City | 103182 | Buyon ES | CITY OF CAUAYAN | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4283419.24 |  |  | Completed | 1
23826 | NC 2017 | SHS | Region II | Cauayan City | 300516 | Cauayan City NHS | CITY OF CAUAYAN | 3 | 1 | 20 | 4STY20CL | BATCH 12 | 41017066 |  |  | Completed | 1
23827 | NC 2017 | SHS | Region II | Cauayan City | 300516 | Cauayan City NHS | CITY OF CAUAYAN | 3 | 1 | 6 | 2STY6CL | BATCH 12 | 12670595.54 |  |  | Completed | 1
23828 | NC 2017 | K10 | Region II | Cauayan City | 103228 | Cauayan South CS | CITY OF CAUAYAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 2934717.05 |  |  | Completed | 1
23829 | NC 2017 | K10 | Region II | Cauayan City | 103229 | E.B.TOMANENG ELEMENTARY SCHOOL | CITY OF CAUAYAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 3068935.22 |  |  | Completed | 1
23830 | NC 2017 | TVL | Region II | Cauayan City | 300538 | Gappal NHS | CITY OF CAUAYAN | 3 | 1 | 1 | Unique Workshop (7x22.5) | BATCH 12 | 3799526.84 |  |  | Completed | 1
23831 | NC 2017 | TVL | Region II | Cauayan City | 300538 | Gappal NHS | CITY OF CAUAYAN | 3 |  | 1 | Unique Workshop (7x22.5) | BATCH 12 | 3799526.84 |  |  | Completed | 1
23832 | NC 2017 | TVL | Region II | Cauayan City | 300538 | Gappal NHS | CITY OF CAUAYAN | 3 |  | 1 | Unique Workshop (7x22.5) | BATCH 12 | 3799526.84 |  |  | Completed | 1
23833 | NC 2017 | SHS | Region II | Cauayan City | 300538 | Gappal NHS | CITY OF CAUAYAN | 3 |  | 4 | 2STY4CL | BATCH 12 | 9436164.76 |  |  | Completed | 1
23834 | NC 2017 | TVL | Region II | Cauayan City | 300567 | Pinoma NHS | CITY OF CAUAYAN | 3 | 1 | 2 | Unique Workshop (7x22.5) | BATCH 12 | 6384033.09 |  |  | Completed | 1
23835 | NC 2017 | SHS | Region II | Cauayan City | 300567 | Pinoma NHS | CITY OF CAUAYAN | 3 |  | 4 | 2STY4CL | BATCH 12 | 9489454.37 |  |  | Completed | 1
23836 | NC 2017 | TVL | Region II | Cauayan City | 300567 | Pinoma NHS | CITY OF CAUAYAN | 3 |  | 1 | Workshop Bldg. (7x18) | BATCH 12 | 3104056.25 |  |  | Completed | 1
23837 | NC 2017 | TVL | Region II | Cauayan City | 300567 | Pinoma NHS | CITY OF CAUAYAN | 3 |  | 1 | Workshop Bldg. (7x18) | BATCH 12 | 3327199.74 |  |  | Completed | 1
23838 | NC 2017 | SHS | Region II | City of Ilagan | 306149 | ISAT-Cabannungan Annex | ILAGAN (Capital) | 1 | 1 | 12 | 3STY12CL | BATCH 12 | 29674069.88 |  |  | Completed | 1
23839 | NC 2017 | SHS | Region II | City of Ilagan | 300543 | Rang-ayan NHS (Isabela NHS - Rang-ayan Annex) | ILAGAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745 |  |  | Completed | 1
23840 | NC 2017 | TVL | Region II | Isabela | 300500 | Alicia National High School | ALICIA | 3 | 1 | 1 | Unique Workshop (7x22.5) | BATCH 12 | 3777908.3 |  |  | Completed | 1
23841 | NC 2017 | K10 | Region II | Isabela | 103006 | Alicia West CS | ALICIA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 2934717.05 |  |  | Completed | 1
23842 | NC 2017 | K10 | Region II | Isabela | 103007 | Apanay ES | ALICIA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 2934717.09 |  |  | Completed | 1
23843 | NC 2017 | K10 | Region II | Isabela | 102996 | Rizal ES | ALICIA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 2934717.05 |  |  | Completed | 1
23844 | NC 2017 | K10 | Region II | Isabela | 103031 | Dalenat ES | ANGADANAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 2934717.05 |  |  | Completed | 1
23845 | NC 2017 | K10 | Region II | Isabela | 103034 | LA SUERTE ELEMENTARY SCHOOL | ANGADANAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 2962049.08 |  |  | Completed | 1
23846 | NC 2017 | K10 | Region II | Isabela | 103166 | Cabatuan West CS | CABATUAN | 3 | 1 | 5 | 1STY5CL W/ TOILET | BATCH 12 | 6562176.46 |  |  | Completed | 1
23847 | NC 2017 | K10 | Region II | Isabela | 103172 | Luzon ES | CABATUAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 2934717.05 |  |  | Completed | 1
23848 | NC 2017 | K10 | Region II | Isabela | 103179 | S.G. Diamantina ES | CABATUAN | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4024885.25 |  |  | Completed | 1
23849 | NC 2017 | K10 | Region II | Isabela | 103679 | Dingading Integrated School | SAN GUILLERMO | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 2975726.97 |  |  | Completed | 1
23850 | NC 2017 | SHS | Region II | Isabela | 300596 | San Mateo Vocational and Industrial High School | SAN MATEO | 3 | 1 | 12 | 3STY12CL | BATCH 12 | 25352507.21 |  |  | Completed | 1
23851 | NC 2017 | K10 | Region II | Isabela | 103793 | Villa Fuerte E/S | SAN MATEO | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 12 | 4222626.75 |  |  | Completed | 1
23852 | NC 2017 | K10 | Region II | Tuguegarao City | 306402 | Tuguegarao City West High School | TUGUEGARAO CITY(Capital) | 3 | 1 | 2 | 1STY2CL | BATCH 12 | 2500000 |  |  | Completed | 1
23853 | NC 2017 | K10 | Region II | Cagayan | 102361 | Arana-ar ES | ALCALA | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3000000 |  |  | Completed | 1
23854 | NC 2017 | K10 | Region II | Cagayan | 102461 | Caroronan PS | APARRI | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3000000 |  |  | Completed | 1
23855 | NC 2017 | K10 | Region II | Cagayan | 102484 | Birao Elementary School | BAGGAO | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3000000 |  |  | Completed | 1
23856 | NC 2017 | K10 | Region II | Cagayan | 102513 | Bitag Grande ES | BAGGAO | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 4500000 |  |  | Completed | 1
23857 | NC 2017 | K10 | Region II | Cagayan | 102494 | Marus ES | BAGGAO | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 4500000 |  |  | Completed | 1
23858 | NC 2017 | K10 | Region II | Cagayan | 102495 | Nangalinan ES | BAGGAO | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 4500000 |  |  | Completed | 1
23859 | NC 2017 | K10 | Region II | Cagayan | 102526 | San Francisco ES | BAGGAO | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3000000 |  |  | Completed | 1
23860 | NC 2017 | K10 | Region II | Cagayan | 155001 | San Vicente ES | BAGGAO | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3000000 |  |  | Completed | 1
23861 | NC 2017 | K10 | Region II | Cagayan | 102534 | Tungel ES | BAGGAO | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3000000 |  |  | Completed | 1
23862 | NC 2017 | K10 | Region II | Cagayan | 300496 | Valley Cove IS | BAGGAO | 1 | 1 | 5 | 1STY5CL W/ TOILET | BATCH 13 | 7500000 |  |  | Completed | 1
23863 | NC 2017 | K10 | Region II | Cagayan | 102570 | Buguey South CS (Pattao ES) | BUGUEY | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 4500000 |  |  | Completed | 1
23864 | NC 2017 | K10 | Region II | Cagayan | 102558 | Calamegatan ES | BUGUEY | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3000000 |  |  | Completed | 1
23865 | NC 2017 | K10 | Region II | Cagayan | 102646 | Barbarit ES | GATTARAN | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3000000 |  |  | Completed | 1
23866 | NC 2017 | K10 | Region II | Cagayan | 102666 | Basao ES | GATTARAN | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 4500000 |  |  | Completed | 1
23867 | NC 2017 | K10 | Region II | Cagayan | 102647 | Batug Sur ES | GATTARAN | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3000000 |  |  | Completed | 1
23868 | NC 2017 | K10 | Region II | Cagayan | 102649 | Bolos Pt. ES | GATTARAN | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3000000 |  |  | Completed | 1
23869 | NC 2017 | K10 | Region II | Cagayan | 102651 | Capiddigan Elementary School | GATTARAN | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3000000 |  |  | Completed | 1
23870 | NC 2017 | K10 | Region II | Cagayan | 102669 | Cullit ES | GATTARAN | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3000000 |  |  | Completed | 1
23871 | NC 2017 | K10 | Region II | Cagayan | 102672 | Ganzano ES | GATTARAN | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3000000 |  |  | Completed | 1
23872 | NC 2017 | K10 | Region II | Cagayan | 102674 | Guising ES | GATTARAN | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 4500000 |  |  | Completed | 1
23873 | NC 2017 | K10 | Region II | Cagayan | 102656 | Mabuno ES | GATTARAN | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3000000 |  |  | Completed | 1
23874 | NC 2017 | K10 | Region II | Cagayan | 102677 | Nagatutuan ES | GATTARAN | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3000000 |  |  | Completed | 1
23875 | NC 2017 | K10 | Region II | Cagayan | 102686 | Baua Central School | GONZAGA | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 4500000 |  |  | Completed | 1
23876 | NC 2017 | K10 | Region II | Cagayan | 102690 | Cabiraoan ES | GONZAGA | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 4500000 |  |  | Completed | 1
23877 | NC 2017 | K10 | Region II | Cagayan | 102743 | Dagupan ES | LAL-LO | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 4500000 |  |  | Completed | 1
23878 | NC 2017 | K10 | Region II | Cagayan | 102734 | San Antonio ES | LAL-LO | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 4500000 |  |  | Completed | 1
23879 | NC 2017 | K10 | Region II | Cagayan | 155030 | San Mariano ES | LAL-LO | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3000000 |  |  | Completed | 1
23880 | NC 2017 | K10 | Region II | Cagayan | 102902 | Kapanikian ES | SANTA ANA | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3000000 |  |  | Completed | 1
23881 | NC 2017 | K10 | Region II | Cagayan | 155023 | Bangalao ES | SANTA TERESITA | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 4500000 |  |  | Completed | 1
23882 | NC 2017 | K10 | Region II | Cagayan | 102927 | Caniugan ES | SANTA TERESITA | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 4500000 |  |  | Completed | 1
23883 | NC 2017 | K10 | Region II | Cagayan | 102928 | Dungeg ES | SANTA TERESITA | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 4500000 |  |  | Completed | 1
23884 | NC 2017 | K10 | Region II | Cauayan City | 103226 | Tagaran ES | Cauayan North District | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2934717.05 |  |  | Completed | 1
23885 | NC 2017 | K10 | Region II | Cauayan City | 103180 | Andarayan-Bugallon ES | Cauayan Northeast District | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2934717.05 |  |  | Completed | 1
23886 | NC 2017 | K10 | Region II | Cauayan City | 103181 | Buduan ES | Cauayan Northeast District | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2955144.48 |  |  | Completed | 1
23887 | NC 2017 | K10 | Region II | Cauayan City | 103187 | Diparicao ES, Cauayan City, Isabela | Cauayan South District | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2962049.08 |  |  | Completed | 1
23888 | NC 2017 | K10 | Region II | Cauayan City | 103222 | San Fermin ES | Cauayan South District | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 4042885.25 |  |  | Completed | 1
23889 | NC 2017 | K10 | Region II | Cauayan City | 103232 | Marabulig II ES | Cauayan West District | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3068935.22 |  |  | Completed | 1
23890 | NC 2017 | K10 | Region II | Cauayan City | 103208 | Alicaocao ES | CITY OF CAUAYAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3068935.22 |  |  | Completed | 1
23891 | NC 2017 | SHS | Region II | Cauayan City | 300516 | Cauayan City NHS | CITY OF CAUAYAN | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 4240626.75 |  |  | Completed | 1
23892 | NC 2017 | SHS | Region II | Cauayan City | 300516 | Cauayan City NHS | CITY OF CAUAYAN | 3 |  | 20 | 4STY20CL | BATCH 13 | 41017066 |  |  | Completed | 1
23893 | NC 2017 | K10 | Region II | Cauayan City | 323905 | Cauayan National High School- Marabulig Extension | CITY OF CAUAYAN | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 4240626.75 |  |  | Completed | 1
23894 | NC 2017 | K10 | Region II | Cauayan City | 103233 | Cauayan West CS (Minante I ES) | CITY OF CAUAYAN | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 4107915.12 |  |  | Completed | 1
23895 | NC 2017 | K10 | Region II | Cauayan City | 103196 | Maligaya Elementary School | CITY OF CAUAYAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2955144.48 |  |  | Completed | 1
23896 | NC 2017 | K10 | Region II | Cauayan City | 103234 | Minante II ES | CITY OF CAUAYAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3068935.22 |  |  | Completed | 1
23897 | NC 2017 | TVL | Region II | Cauayan City | 300589 | San Antonio National High School | CITY OF CAUAYAN | 3 | 1 | 1 | Unique Workshop (7x22.5) | BATCH 13 | 3777908.3 |  |  | Completed | 1
23898 | NC 2017 | TVL | Region II | Cauayan City | 300589 | San Antonio National High School | CITY OF CAUAYAN | 3 |  | 1 | Workshop Bldg. (7x18) | BATCH 13 | 3327199.74 |  |  | Completed | 1
23899 | NC 2017 | SHS | Region II | Cauayan City | 306118 | Sillawit National High School | CITY OF CAUAYAN | 3 | 1 | 4 | 2STY4CL | BATCH 13 | 9489454.37 |  |  | Completed | 1
23900 | NC 2017 | TVL | Region II | Cauayan City | 306118 | Sillawit National High School | CITY OF CAUAYAN | 3 | 1 | 1 | Workshop Bldg. (7x18) | BATCH 13 | 3231888.34 |  |  | Completed | 1
23901 | NC 2017 | TVL | Region II | Cauayan City | 306118 | Sillawit National High School | CITY OF CAUAYAN | 3 |  | 1 | Workshop Bldg. (7x18) | BATCH 13 | 3467174.72 |  |  | Completed | 1
23902 | NC 2017 | TVL | Region II | Cauayan City | 300613 | Villa Concepcion HS | CITY OF CAUAYAN | 3 | 1 | 1 | Unique Workshop (7x22.5) | BATCH 13 | 3799526.84 |  |  | Completed | 1
23903 | NC 2017 | TVL | Region II | Cauayan City | 300613 | Villa Concepcion HS | CITY OF CAUAYAN | 3 |  | 1 | Workshop Bldg. (7x18) | BATCH 13 | 3132994.35 |  |  | Completed | 1
23904 | NC 2017 | TVL | Region II | Cauayan City | 300613 | Villa Concepcion HS | CITY OF CAUAYAN | 3 |  | 1 | Workshop Bldg. (7x18) | BATCH 13 | 3348134.2 |  |  | Completed | 1
23905 | NC 2017 | SHS | Region II | Cauayan City | 300613 | Villa Concepcion HS | CITY OF CAUAYAN | 3 |  | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2962049.08 |  |  | Completed | 1
23906 | NC 2017 | SHS | Region II | Cauayan City | 323903 | Villa Concepcion HS - Rogus Ext. | CITY OF CAUAYAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2962049.08 |  |  | Completed | 1
23907 | NC 2017 | SHS | Region II | Cauayan City | 323903 | Villa Concepcion HS - Rogus Ext. | CITY OF CAUAYAN | 3 |  | 4 | 2STY4CL | BATCH 13 | 9996300.5 |  |  | Completed | 1
23908 | NC 2017 | TVL | Region II | Cauayan City | 300614 | Villaluna NHS | CITY OF CAUAYAN | 3 | 1 | 1 | Unique Workshop (7x22.5) | BATCH 13 | 3929024.63 |  |  | Completed | 1
23909 | NC 2017 | TVL | Region II | Cauayan City | 300614 | Villaluna NHS | CITY OF CAUAYAN | 3 |  | 1 | Workshop Bldg. (7x18) | BATCH 13 | 3112083.25 |  |  | Completed | 1
23910 | NC 2017 | TVL | Region II | Cauayan City | 306107 | WEST TABACAL REGION NATIONAL HIGH SCHOOL | CITY OF CAUAYAN | 3 | 1 | 1 | Unique Workshop (7x22.5) | BATCH 13 | 3929024.63 |  |  | Completed | 1
23911 | NC 2017 | TVL | Region II | Cauayan City | 306107 | WEST TABACAL REGION NATIONAL HIGH SCHOOL | CITY OF CAUAYAN | 3 |  | 1 | Workshop Bldg. (7x18) | BATCH 13 | 3112083.25 |  |  | Completed | 1
23912 | NC 2017 | TVL | Region II | Cauayan City | 306107 | WEST TABACAL REGION NATIONAL HIGH SCHOOL | CITY OF CAUAYAN | 3 |  | 1 | Workshop Bldg. (7x18) | BATCH 13 | 3231888.34 |  |  | Completed | 1
23913 | NC 2017 | TVL | Region II | Cauayan City | 306107 | WEST TABACAL REGION NATIONAL HIGH SCHOOL | CITY OF CAUAYAN | 3 |  | 1 | Workshop Bldg. (7x18) | BATCH 13 | 3467174.72 |  |  | Completed | 1
23914 | NC 2017 | SHS | Region II | City of Ilagan | 500087 | Gayong-Gayong Sur Integrated School | ILAGAN (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 13 | 17404556.7 |  |  | Completed | 1
23915 | NC 2017 | SHS | Region II | City of Ilagan | 306105 | ISAT-Main | ILAGAN (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 13 | 36712316.75 |  |  | Completed | 1
23916 | NC 2017 | SHS | Region II | City of Ilagan | 306105 | ISAT-Main | ILAGAN (Capital) | 1 |  | 16 | 4STY16CL | BATCH 13 | 36712316.75 |  |  | Completed | 1
23917 | NC 2017 | SHS | Region II | City of Ilagan | 306105 | ISAT-Main | ILAGAN (Capital) | 1 |  | 16 | 4STY16CL | BATCH 13 | 36712316.75 |  |  | Completed | 1
23918 | NC 2017 | SHS | Region II | City of Ilagan | 500080 | Lupigue Integrated School (formerly Lupigue ES) | ILAGAN (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9813649.51 |  |  | Completed | 1
23919 | NC 2017 | SHS | Region II | City of Ilagan | 500080 | Lupigue Integrated School (formerly Lupigue ES) | ILAGAN (Capital) | 1 |  | 8 | 2STY8CL | BATCH 13 | 17605782.53 |  |  | Completed | 1
23920 | NC 2017 | SHS | Region II | City of Ilagan | 500078 | Manaring Integrated School | ILAGAN (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 13 | 17907753.07 |  |  | Completed | 1
23921 | NC 2017 | SHS | Region II | City of Ilagan | 300584 | San Rafael Nat'l & Voc'l HS (San Antonio NAIVHS-San Rafael Annex) | ILAGAN (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 13 | 17404556.7 |  |  | Completed | 1
23922 | NC 2017 | K10 | Region II | Isabela | 103005 | Alicia CS | ALICIA | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 4042885.25 |  |  | Completed | 1
23923 | NC 2017 | SHS | Region II | Isabela | 300565 | Palayan Region High School | ALICIA | 3 | 1 | 4 | 2STY4CL | BATCH 13 | 9868037.3 |  |  | Completed | 1
23924 | NC 2017 | K10 | Region II | Isabela | 103017 | San Pedro ES | ALICIA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2934717.05 |  |  | Completed | 1
23925 | NC 2017 | K10 | Region II | Isabela | 103019 | Sta. Maria ES | ALICIA | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2934717.05 |  |  | Completed | 1
23926 | NC 2017 | K10 | Region II | Isabela | 103102 | Benito Soliven CS | BENITO SOLIVEN | 2 | 1 | 3 | 1STY3CL | BATCH 13 | 4324543.16 |  |  | Completed | 1
23927 | NC 2017 | K10 | Region II | Isabela | 103103 | Calaocan ES | BENITO SOLIVEN | 2 | 1 | 3 | 1STY3CL | BATCH 13 | 4324543.16 |  |  | Completed | 1
23928 | NC 2017 | K10 | Region II | Isabela | 103110 | Maluno Integrated School - Main (formerly Maluno ES-Main) | BENITO SOLIVEN | 2 | 1 | 2 | 1STY2CL | BATCH 13 | 3012079.59 |  |  | Completed | 1
23929 | NC 2017 | SHS | Region II | Isabela | 300521 | Alfreda Albano National High School - Magassi, Cabagan | CABAGAN | 1 | 1 | 8 | 2STY8CL | BATCH 13 | 17404556.7 |  |  | Completed | 1
23930 | NC 2017 | SHS | Region II | Isabela | 300521 | Alfreda Albano National High School - Magassi, Cabagan | CABAGAN | 1 |  | 12 | 3STY12CL | BATCH 13 | 29711072.96 |  |  | Completed | 1
23931 | NC 2017 | SHS | Region II | Isabela | 300520 | Delfin Albano High School-Main | CABAGAN | 1 | 1 | 8 | 2STY8CL | BATCH 13 | 17404556.7 |  |  | Completed | 1
23932 | NC 2017 | SHS | Region II | Isabela | 300520 | Delfin Albano High School-Main | CABAGAN | 1 |  | 12 | 3STY12CL | BATCH 13 | 29711072.96 |  |  | Completed | 1
23933 | NC 2017 | SHS | Region II | Isabela | 300520 | Delfin Albano High School-Main | CABAGAN | 1 |  | 8 | 2STY8CL | BATCH 13 | 17404556.7 |  |  | Completed | 1
23934 | NC 2017 | K10 | Region II | Isabela | 103170 | L.B.G. Tandul ES | CABATUAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2934717.05 |  |  | Completed | 1
23935 | NC 2017 | TVL | Region II | Isabela | 306114 | La Paz National High School | CABATUAN | 3 | 1 | 1 | Workshop Bldg. (7x18) | BATCH 13 | 2976268.89 |  |  | Completed | 1
23936 | NC 2017 | K10 | Region II | Isabela | 103174 | Namnama ES | CABATUAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2934717.05 |  |  | Completed | 1
23937 | NC 2017 | SHS | Region II | Isabela | 300585 | San Antonio National High School | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9664793.59 |  |  | Completed | 1
23938 | NC 2017 | K10 | Region II | Isabela | 103343 | Gamu CS | GAMU | 2 | 1 | 2 | 1STY2CL | BATCH 13 | 2661745.95 |  |  | Completed | 1
23939 | NC 2017 | K10 | Region II | Isabela | 103487 | Luna CS | LUNA | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2934717.05 |  |  | Completed | 1
23940 | NC 2017 | TVL | Region II | Isabela | 306150 | Luna General Comprehensive High School | LUNA | 5 | 1 | 1 | Unique Workshop (7x22.5) | BATCH 13 | 3929024.63 |  |  | Completed | 1
23941 | NC 2017 | TVL | Region II | Isabela | 306150 | Luna General Comprehensive High School | LUNA | 5 |  | 1 | Workshop Bldg. (7x18) | BATCH 13 | 3467174.72 |  |  | Completed | 1
23942 | NC 2017 | K10 | Region II | Isabela | 103490 | Pulay-Union Kalinga ES | LUNA | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2934717.05 |  |  | Completed | 1
23943 | NC 2017 | SHS | Region II | Isabela | 500068 | Villa Cacho Integrated School | QUIRINO | 5 | 1 | 2 | 1STY2CL | BATCH 13 | 2738254.17 |  |  | Completed | 1
23944 | NC 2017 | SHS | Region II | Isabela | 300575 | Reina Mercedes Vocational and Industrial School | REINA MERCEDES | 3 | 1 | 6 | 3STY6CL | BATCH 13 | 13553882.07 |  |  | Completed | 1
23945 | NC 2017 | SHS | Region II | Isabela | 300575 | Reina Mercedes Vocational and Industrial School | REINA MERCEDES | 3 |  | 3 | 1STY3CL W/ TOILET | BATCH 13 | 4042885.25 |  |  | Completed | 1
23946 | NC 2017 | K10 | Region II | Isabela | 103630 | Anao-Kiling ES | ROXAS | 5 |  | 3 | 1STY3CL | BATCH 13 | 3816435.02 |  |  | Completed | 1
23947 | NC 2017 | K10 | Region II | Isabela |  | Roxas NHS- San Antonio Ext | ROXAS | 5 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 3768435.02 |  |  | Completed | 1
23948 | NC 2017 | K10 | Region II | Isabela |  | Roxas NHS- San Antonio Ext | ROXAS | 5 |  | 3 | 1STY3CL W/ TOILET | BATCH 13 | 3768435.02 |  |  | Completed | 1
23949 | NC 2017 | K10 | Region II | Isabela |  | Roxas NHS- San Antonio Ext | ROXAS | 5 |  | 3 | 1STY3CL W/ TOILET | BATCH 13 | 3768435.02 |  |  | Completed | 1
23950 | NC 2017 | K10 | Region II | Isabela |  | Roxas NHS- San Antonio Ext | ROXAS | 5 |  | 3 | 1STY3CL W/ TOILET | BATCH 13 | 3768435.02 |  |  | Completed | 1
23951 | NC 2017 | K10 | Region II | Isabela |  | Roxas NHS- San Antonio Ext | ROXAS | 5 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 3768435.02 |  |  | Completed | 1
23952 | NC 2017 | K10 | Region II | Isabela |  | Roxas NHS- San Antonio Ext | ROXAS | 5 |  | 3 | 1STY3CL W/ TOILET | BATCH 13 | 3768435.02 |  |  | Completed | 1
23953 | NC 2017 | K10 | Region II | Isabela | 103674 | Burgos East Elementary School | SAN GUILLERMO | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2975726.97 |  |  | Completed | 1
23954 | NC 2017 | K10 | Region II | Isabela | 103690 | San Guillermo CS | SAN GUILLERMO | 6 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 4085677.74 |  |  | Completed | 1
23955 | NC 2017 | TVL | Region II | Isabela | 300590 | San Guillermo Vocational & Industrial High School | SAN GUILLERMO | 6 | 1 | 1 | Workshop Bldg. (7x18) | BATCH 13 | 3002319.97 |  |  | Completed | 1
23956 | NC 2017 | SHS | Region II | Isabela | 300592 | San Mariano National High School - Main | SAN MARIANO | 2 |  | 2 | 1STY2CL | BATCH 13 | 3012079.59 |  |  | Completed | 1
23957 | NC 2017 | K10 | Region II | Isabela | 103775 | Marasat Pequeno ES | SAN MATEO | 3 | 1 | 5 | 1STY5CL W/ TOILET | BATCH 13 | 6525728.86 |  |  | Completed | 1
23958 | NC 2017 | SHS | Region II | Isabela | 300581 | Salinungan National High School | SAN MATEO | 3 | 1 | 8 | 2STY8CL | BATCH 13 | 18775819.98 |  |  | Completed | 1
23959 | NC 2017 | K10 | Region II | Isabela | 103788 | San Mateo East CS | SAN MATEO | 3 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 13 | 5300135.36 |  |  | Completed | 1
23960 | NC 2017 | SHS | Region II | Isabela | 300596 | San Mateo Vocational and Industrial High School | SAN MATEO | 3 | 1 | 8 | 2STY8CL | BATCH 13 | 18775819.98 |  |  | Completed | 1
23961 | NC 2017 | SHS | Region II | Isabela | 300596 | San Mateo Vocational and Industrial High School | SAN MATEO | 3 |  | 8 | 2STY8CL | BATCH 13 | 19040281.41 |  |  | Completed | 1
23962 | NC 2017 | TVL | Region II | Isabela | 300596 | San Mateo Vocational and Industrial High School | SAN MATEO | 3 |  | 2 | Unique Workshop (7x22.5) | BATCH 13 | 6138493.36 |  |  | Completed | 1
23963 | NC 2017 | K10 | Region II | Isabela | 103789 | San Mateo West CS | SAN MATEO | 3 | 1 | 5 | 1STY5CL W/ TOILET | BATCH 13 | 6525728.97 |  |  | Completed | 1
23964 | NC 2017 | K10 | Region II | Isabela | 103789 | San Mateo West CS | SAN MATEO | 3 |  | 5 | 1STY5CL W/ TOILET | BATCH 13 | 6525728.97 |  |  | Completed | 1
23965 | NC 2017 | K10 | Region II | Isabela | 103789 | San Mateo West CS | SAN MATEO | 3 |  | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2934717.05 |  |  | Completed | 1
23966 | NC 2017 | K10 | Region II | Isabela | 103796 | Auitan Elementary School | SAN PABLO | 1 | 1 | 6 | 2STY6CL | BATCH 13 | 12232587.52 |  |  | Completed | 1
23967 | NC 2017 | SHS | Region II | Isabela | 300597 | San Pablo National High School | SAN PABLO | 1 | 1 | 8 | 2STY8CL | BATCH 13 | 17907753.07 |  |  | Completed | 1
23968 | NC 2017 | SHS | Region II | Isabela | 300605 | Buenaventura G. Masigan National High School | SANTA MARIA | 1 | 1 | 16 | 4STY16CL | BATCH 13 | 36817825.25 |  |  | Completed | 1
23969 | NC 2017 | SHS | Region II | Isabela | 306101 | Calanigan National High School | SANTO TOMAS | 1 | 1 | 12 | 3STY12CL | BATCH 13 | 29750524.86 |  |  | Completed | 1
23970 | NC 2017 | K10 | Region II | Isabela | 103865 | Calinaoan ES | SANTO TOMAS | 1 | 1 | 8 | 2STY8CL | BATCH 13 | 17097352.38 |  |  | Completed | 1
23971 | NC 2017 | SHS | Region II | Isabela | 300606 | Santo Tomas National High School | SANTO TOMAS | 1 | 1 | 16 | 4STY16CL | BATCH 13 | 36652419.23 |  |  | Completed | 1
23972 | NC 2017 | SHS | Region II | Isabela | 500088 | Cumabao Integrated School | TUMAUINI | 1 | 1 | 8 | 4STY8CL | BATCH 13 | 17192770.36 |  |  | Completed | 1
23973 | NC 2017 | SHS | Region II | Isabela | 500088 | Cumabao Integrated School | TUMAUINI | 1 |  | 12 | 3STY12CL | BATCH 13 | 30112021.41 |  |  | Completed | 1
23974 | NC 2017 | SHS | Region II | Isabela | 306109 | Fermeldy National High School | TUMAUINI | 1 | 1 | 16 | 4STY16CL | BATCH 13 | 36525057.12 |  |  | Completed | 1
23975 | NC 2017 | SHS | Region II | Isabela | 300556 | Lalauanan National High School | TUMAUINI | 1 | 1 | 8 | 2STY8CL | BATCH 13 | 17404556.7 |  |  | Completed | 1
23976 | NC 2017 | SHS | Region II | Isabela | 300551 | Lanna National High School | TUMAUINI | 1 | 1 | 8 | 4STY8CL | BATCH 13 | 17192270.36 |  |  | Completed | 1
23977 | NC 2017 | SHS | Region II | Isabela | 300610 | Regional Science High School for Region II | TUMAUINI | 1 | 1 | 8 | 4STY8CL | BATCH 13 | 17395055.79 |  |  | Completed | 1
23978 | NC 2017 | SHS | Region II | Isabela | 300609 | Tumauini National High School | TUMAUINI | 1 | 1 | 16 | 4STY16CL | BATCH 13 | 36540085.79 |  |  | Completed | 1
23979 | NC 2017 | SHS | Region II | Isabela | 300609 | Tumauini National High School | TUMAUINI | 1 |  | 12 | 3STY12CL | BATCH 13 | 30344837.82 |  |  | Completed | 1
23980 | NC 2017 | K10 | Region II | Cagayan | 102490 | Dalla ES | BAGGAO | 1 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 14 | 6000000 |  |  | Completed | 1
23981 | NC 2017 | K10 | Region II | Cagayan | 102671 | Dummun ES | GATTARAN | 1 |  | 4 | 2 UNITS OF 1STY2CL W/ TOILET | BATCH 14 | 6000000 |  |  | Completed | 1
23982 | NC 2017 | K10 | Region II | Cagayan | 102693 | Caroan ES | GONZAGA | 1 |  | 3 | 1STY3CL W/ TOILET | BATCH 14 | 4500000 |  |  | Completed | 1
23983 | NC 2017 | K10 | Region II | Cagayan | 102694 | CASITAN E/S | GONZAGA | 1 |  | 3 | 1STY3CL W/ TOILET | BATCH 14 | 4500000 |  |  | Completed | 1
23984 | NC 2017 | K10 | Region II | Cagayan | 102701 | Pateng PS | GONZAGA | 1 |  | 3 | 1STY3CL W/ TOILET | BATCH 14 | 4500000 |  |  | Completed | 1
23985 | NC 2017 | K10 | Region II | Cagayan | 102705 | Sta. Clara ES | GONZAGA | 1 |  | 3 | 1STY3CL W/ TOILET | BATCH 14 | 4500000 |  |  | Completed | 1
23986 | NC 2017 | K10 | Region II | Cagayan | 102726 | Binag ES | LAL-LO | 1 |  | 3 | 1STY3CL W/ TOILET | BATCH 14 | 4500000 |  |  | Completed | 1
23987 | NC 2017 | K10 | Region II | Cagayan | 102733 | Naguilian ES | LAL-LO | 1 |  | 3 | 1STY3CL W/ TOILET | BATCH 14 | 4500000 |  |  | Completed | 1
23988 | NC 2017 | K10 | Region II | Cagayan | 102739 | Bicud ES | LAL-LO | 1 |  | 3 | 1STY3CL W/ TOILET | BATCH 14 | 4500000 |  |  | Completed | 1
23989 | NC 2017 | K10 | Region II | Cagayan | 102742 | Catugan ES | LAL-LO | 1 | 1 | 3 | 1STY3CL | BATCH 14 | 4500000 |  |  | Completed | 1
23990 | NC 2017 | K10 | Region II | Cagayan | 102748 | Magapit ES | LAL-LO | 1 | 1 | 3 | 1STY3CL | BATCH 14 | 4500000 |  |  | Completed | 1
23991 | NC 2017 | SHS | Region II | CAGAYAN | 300482 | Rebecca NHS | GONZAGA | 1 |  | 6 | 2 UNITS OF 1STY3CL | BATCH 14 | 9000000 |  |  | Completed | 1
23992 | NC 2017 | SHS | Region II | CAGAYAN | 306002 | Baggao NAS - Sta. Margarita Annex | BAGGAO | 1 |  | 6 | 2 UNITS OF 1STY3CL | BATCH 14 | 9000000 |  |  | Completed | 1
23993 | NC 2017 | K10 | Region II | Cagayan | 306011 | Licerio Antiporda Sr. NHS - Dalaya Ext. | BUGUEY | 1 |  | 6 | 2 UNITS OF 1STY3CL | BATCH 14 | 9000000 |  |  | Completed | 1
23994 | NC 2017 | SHS | Region II | Cagayan | 306012 | Pattao NHS - Maddalero Ext. | BUGUEY | 1 |  | 6 | 2 UNITS OF 1STY3CL | BATCH 14 | 9000000 |  |  | Completed | 1
23995 | NC 2017 | SHS | Region II | Cagayan | 306020 | AGAMAN NATIONAL HIGH SCHOOL | BAGGAO | 1 |  | 6 | 2 UNITS OF 1STY3CL | BATCH 14 | 9000000 |  |  | Completed | 1
23996 | NC 2017 | SHS | Region II | Cagayan | 306422 | Calaoagan Dackel National High School-Capissayan Annex | GATTARAN | 1 |  | 6 | 2 UNITS OF 1STY3CL | BATCH 14 | 9000000 |  |  | Completed | 1
23997 | NC 2017 | SHS | Region II | Cauayan City | 300589 | San Antonio National High School | CITY OF CAUAYAN | 3 |  | 4 | 2STY4CL | BATCH 14 | 9306001.28 |  |  | Completed | 1
23998 | NC 2017 | SHS | Region II | Cauayan City | 300613 | Villa Concepcion HS | CITY OF CAUAYAN | 3 |  | 8 | 2STY8CL | BATCH 14 | 19015551.32 |  |  | Completed | 1
23999 | NC 2017 | SHS | Region II | Cauayan City | 300614 | Villaluna NHS | CITY OF CAUAYAN | 3 |  | 4 | 2STY4CL | BATCH 14 | 9485012.15 |  |  | Completed | 1
24000 | NC 2017 | K10 | Region II | City of Ilagan | 103362 | Capo PS | ILAGAN (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 9539835.011 |  |  | Completed | 1
24001 | NC 2017 | SHS | Region II | City of Ilagan | 300543 | Rang-ayan NHS (Isabela NHS - Rang-ayan Annex) | ILAGAN (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 9539835.011 |  |  | Completed | 1
24002 | NC 2017 | SHS | Region II | City of Ilagan | 306105 | ISAT-Main | ILAGAN (Capital) | 1 | 1 | 20 | 4STY20CL | BATCH 14 | 41491885.17 |  |  | Completed | 1
24003 | NC 2017 | SHS | Region II | Isabela | 300576 | Rizal Region National High School | ALICIA | 3 | 1 | 4 | 2STY4CL | BATCH 14 | 10033137.29 |  |  | Completed | 1
24004 | NC 2017 | SHS | Region II | Isabela | 300576 | Rizal Region National High School | ALICIA | 3 |  | 4 | 2STY4CL | BATCH 14 | 9489454.37 |  |  | Completed | 1
24005 | NC 2017 | SHS | Region II | Isabela | 300596 | San Mateo Vocational and Industrial High School | SAN MATEO | 3 | 1 | 12 | 3STY12CL | BATCH 14 | 6101391.32 |  |  | Completed | 1
24006 | NC 2017 | SHS | Region II | Isabela | 500023 | Sto. Nino Integrated School | ANGADANAN | 3 | 1 | 4 | 2STY4CL | BATCH 14 | 9998300.5 |  |  | Completed | 1
24007 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104007 | Casat ES | BAYOMBONG (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 14 | 9000000 |  |  | Completed | 1
24008 | NC 2017 | K10 | Region II | Nueva Vizcaya | 104019 | Butao Elementary School | DIADI | 0 | 1 | 4 | 2STY4CL | BATCH 14 | 9000000 |  |  | Completed | 1
34883 | NC 2018 | SHS | Region II | Batanes | 300414 | Itbayat National Agricultural HS | ITBAYAT | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 11988000 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
34884 | NC 2018 | TVL | Region II | Batanes | 300415 | Ivana NHS | IVANA | 0 | 1 | 1 | WORKSHOP | BATCH 1 | 4920000 |  |  | Completed | 1
34885 | NC 2018 | TVL | Region II | Batanes | 300417 | Sabtang National School of Fisheries | SABTANG | 0 | 1 | 1 | WORKSHOP | BATCH 1 | 5232000 |  |  | Completed | 1 | [10 empty] | Completed on June 6, 2021; with Turn-Over Paper; Buffer fund reverted due to no interested bidder
34886 | NC 2018 | SHS | Region II | Batanes | 500062 | Itbud Integrated School | UYUGAN | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 11124000 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
34887 | NC 2018 | TVL | Region II | Cagayan | 300420 | Afusing NHS | ALCALA | 1 | 1 | 8 | 4STY20CL (4CL, 2-SCI LAB, 2- ICT, 4-REG. WORKSHOP) | BATCH 1 | 50686344.32 |  |  | Completed | 1
34888 | NC 2018 | SHS | Region II | Cagayan | 300421 | ALCALA RURAL SCHOOL | ALCALA | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 21114500 |  |  | Completed | 1
34889 | NC 2018 | TVL | Region II | Cagayan | 300421 | ALCALA RURAL SCHOOL | ALCALA | 1 |  | 1 | UNIQUE WORKSHOP (7.0mX22.50m) | BATCH 1 | 4589808 |  |  | Completed | 1
34890 | NC 2018 | K10 | Region II | Cagayan | 102450 | San Antonio ES | APARRI | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 3420900 |  |  | Completed | 1
34891 | NC 2018 | K10 | Region II | Cagayan | 102450 | San Antonio ES | APARRI | 1 |  | 2 | 1STY3CL W/ TOILET | BATCH 1 | 4780000 |  |  | Completed | 1
34892 | NC 2018 | K10 | Region II | Cagayan | 102451 | Tallungan ES | APARRI | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 3435000 |  |  | Completed | 1
34893 | NC 2018 | K10 | Region II | Cagayan | 102475 | Zinarag ES | APARRI | 1 | 1 | 5 | 1STY5CL W/ TOILET | BATCH 1 | 8506438 |  |  | Completed | 1
34894 | NC 2018 | TVL | Region II | Cagayan | 300437 | Bukig National Agricultural and Technical School | APARRI | 1 | 1 | 4 | 2STY8CL (4-REG. WORKSHOP) | BATCH 1 | 21114500 |  |  | Completed | 1
34895 | NC 2018 | TVL | Region II | Cagayan | 300437 | Bukig National Agricultural and Technical School | APARRI | 1 |  | 4 | 2STY8CL (2-SCIENCE LAB, 2- ICT LAB) | BATCH 1 | 21114500 |  |  | Completed | 1
34896 | NC 2018 | K10 | Region II | Cagayan | 102477 | Agaman Sur ES | BAGGAO | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 1 | 4750000 |  |  | Completed | 1
34897 | NC 2018 | K10 | Region II | Cagayan | 102509 | Assassi ES | BAGGAO | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 13100360 |  |  | Completed | 1
34898 | NC 2018 | K10 | Region II | Cagayan | 102524 | Mocag ES | BAGGAO | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 13100360 |  |  | Completed | 1
34899 | NC 2018 | K10 | Region II | Cagayan | 155001 | San Vicente ES | BAGGAO | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 1 | 4750000 |  |  | Completed | 1
34900 | NC 2018 | TVL | Region II | CAGAYAN | 300429 | Baggao National Agricultural School | BAGGAO | 1 | 1 | 6 | 2STY12CL (6-REG. WORKSHOP) | BATCH 1 | 27338503.54 |  |  | Completed | 1
34901 | NC 2018 | TVL | Region II | CAGAYAN | 300429 | Baggao National Agricultural School | BAGGAO | 1 |  | 4 | 2STY8CL (2-SCIENCE LAB, 2- ICT LAB) | BATCH 1 | 21114500 |  |  | Completed | 1
34902 | NC 2018 | TVL | Region II | Cagayan | 300430 | Baggao National School of Arts & Trades | BAGGAO | 1 | 1 | 6 | 2STY12CL (6-REG. WORKSHOP) | BATCH 1 | 27338503.54 |  |  | Completed | 1
34903 | NC 2018 | TVL | Region II | Cagayan | 300431 | Baggao NHS | BAGGAO | 1 | 1 | 2 | 2STY4CL (2-REG. WORKSHOP) | BATCH 1 | 12246700 |  |  | Completed | 1
34904 | NC 2018 | TVL | Region II | Cagayan | 300431 | Baggao NHS | BAGGAO | 1 |  | 4 | 2STY8CL (2-SCIENCE LAB, 2- ICT LAB) | BATCH 1 | 21114500 |  |  | Completed | 1
34905 | NC 2018 | TVL | Region II | Cagayan | 306002 | Baggao NAS - Sta. Margarita Annex | BAGGAO | 1 | 1 | 4 | 2STY12CL (2-REG. WORKSHOP 2-SCIENCE LAB, 2- ICT LAB) | BATCH 1 | 28104843.19 |  |  | Completed | 1
34906 | NC 2018 | TVL | Region II | Cagayan | 306002 | Baggao NAS - Sta. Margarita Annex | BAGGAO | 1 |  | 2 | 2STY4CL (SCIENCE LAB, ICT LAB) | BATCH 1 | 12246700 |  |  | Completed | 1
34907 | NC 2018 | TVL | Region II | Cagayan | 306020 | AGAMAN NATIONAL HIGH SCHOOL | BAGGAO | 1 | 1 | 4 | 2STY12CL (2-REG. WORKSHOP 2-SCIENCE LAB, 2- ICT LAB) | BATCH 1 | 27943653.19 |  |  | Completed | 1
34908 | NC 2018 | TVL | Region II | Cagayan | 306020 | AGAMAN NATIONAL HIGH SCHOOL | BAGGAO | 1 |  | 2 | 2STY4CL (SCIENCE LAB, ICT LAB) | BATCH 1 | 12246700 |  |  | Completed | 1
34909 | NC 2018 | K10 | Region II | Cagayan | 102556 | Buguey North CS | BUGUEY | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 21114500 |  |  | Completed | 1
34910 | NC 2018 | TVL | Region II | Cagayan | 300474 | Licerio Antiporda Sr. NHS | BUGUEY | 1 | 1 | 10 | 2STY10CL (4-REG WORKSHOP 2-ACAD RM)std bldg type | BATCH 1 Realignment | 25852326.4 |  |  | Completed | 1
34911 | NC 2018 | TVL | Region II | Cagayan | 300474 | Licerio Antiporda Sr. NHS | BUGUEY | 1 |  | 4 | 2STY8CL (2-SCIENCE LAB, 2- ICT LAB) | BATCH 1 | 21114500 |  |  | Completed | 1
34912 | NC 2018 | TVL | Region II | Cagayan | 300480 | Pattao NHS | BUGUEY | 1 | 1 | 6 | 3STY12CL (2-REG. WORKSHOP 2-SCIENCE LAB, 2- ICT LAB) | BATCH 1 | 34376711.64 |  |  | Completed | 1
34913 | NC 2018 | TVL | Region II | Cagayan | 306011 | Licerio Antiporda Sr. NHS - Dalaya Ext. | BUGUEY | 1 | 1 | 2 | 2STY4CL (SCIENCE LAB, ICT LAB) | BATCH 1 | 12246700 |  |  | Completed | 1
34914 | NC 2018 | TVL | Region II | Cagayan | 306012 | Pattao NHS - Maddalero Ext. | BUGUEY | 1 | 1 | 2 | 2STY4CL (SCIENCE LAB, ICT LAB) | BATCH 1 | 12246700 |  |  | Completed | 1
34915 | NC 2018 | TVL | Region II | Cagayan | 300444 | Camalaniugan NHS | CAMALANIUGAN | 1 | 1 | 4 | 2STY8CL (4-REG. WORKSHOP) | BATCH 1 | 21114500 |  |  | Completed | 1
34916 | NC 2018 | TVL | Region II | Cagayan | 300444 | Camalaniugan NHS | CAMALANIUGAN | 1 |  | 4 | 2STY8CL (2-SCIENCE LAB, 2- ICT LAB) | BATCH 1 | 21114500 |  |  | Completed | 1
34917 | NC 2018 | TVL | Region II | Cagayan | 102568 | Paddaya Elementary School | CAMALANIUGAN | 1 | 1 | 3 | 1sty3cl | BATCH 1 Realignment | 4500000 |  |  | Completed | 1
34918 | NC 2018 | TVL | Region II | Cagayan | 102569 | Paddaya Este Elementary School | CAMALANIUGAN | 1 | 1 | 3 | 1sty3cl | BATCH 1 Realignment | 4500000 |  |  | Completed | 1
34919 | NC 2018 | K10 | Region II | Cagayan | 102702 | Rebecca Elementary School | GONZAGA | 1 | 1 | 9 | 3 units 1sty3cl | BATCH 1 Realignment | 13500000 |  |  | Completed | 1
34920 | NC 2018 | K10 | Region II | Cagayan | 102516 | Callao Elementary School | BAGGAO | 1 | 1 | 4 | 1sty4cl | BATCH 1 Realignment | 6300000 |  |  | Completed | 1
34921 | NC 2018 | SHS | Region II | Cagayan | 300483 | Gonzaga National High School | GONZAGA | 1 |  | 3 | 1sty3cl | BATCH 1 Realignment | 4500000 |  |  | Completed | 1
34922 | NC 2018 | K10 | Region II | Cagayan | 102673 | Gattaran West CS | GATTARAN | 1 | 1 | 12 | 2STY12CL | BATCH 1 | 27338503.54 |  |  | Completed | 1
34923 | NC 2018 | SHS | Region II | Cagayan | 300440 | Calaoagan Dackel National High School | GATTARAN | 1 | 1 | 9 | 3STY9CL | BATCH 1 | 25790486.44 |  |  | Completed | 1
34924 | NC 2018 | TVL | Region II | Cagayan | 300440 | Calaoagan Dackel National High School | GATTARAN | 1 |  | 4 | 2STY8CL (2-SCIENCE LAB, 2- ICT LAB) | BATCH 1 | 21114500 |  |  | Completed | 1
34925 | NC 2018 | TVL | Region II | Cagayan | 300455 | Don Mariano Marcos NHS | GATTARAN | 1 | 1 | 4 | 2STY8CL (4-REG. WORKSHOP) | BATCH 1 | 21114500 |  |  | Completed | 1
34926 | NC 2018 | TVL | Region II | Cagayan | 300455 | Don Mariano Marcos NHS | GATTARAN | 1 |  | 4 | 2STY8CL (2-SCIENCE LAB, 2- ICT LAB) | BATCH 1 | 21114500 |  |  | Completed | 1
34927 | NC 2018 | TVL | Region II | Cagayan | 300462 | Gattaran National Trade School | GATTARAN | 1 | 1 | 6 | 2STY12CL (6-REG. WORKSHOP) | BATCH 1 | 27338503.54 |  |  | Completed | 1
34928 | NC 2018 | TVL | Region II | Cagayan | 300462 | Gattaran National Trade School | GATTARAN | 1 |  | 4 | 2STY8CL (4-REG. WORKSHOP) | BATCH 1 | 21114500 |  |  | Completed | 1
34929 | NC 2018 | TVL | Region II | Cagayan | 300462 | Gattaran National Trade School | GATTARAN | 1 |  | 4 | 2STY8CL (2-SCIENCE LAB, 2- ICT LAB) | BATCH 1 | 21114500 |  |  | Completed | 1
34930 | NC 2018 | TVL | Region II | Cagayan | 306422 | Calaoagan Dackel National High School-Capissayan Annex | GATTARAN | 1 | 1 | 6 | 2STY12CL (2-REG. WORKSHOP 2-SCIENCE LAB, 2- ICT LAB) | BATCH 1 | 27338503.54 |  |  | Completed | 1
34931 | NC 2018 | TVL | Region II | Cagayan | 300435 | Baua HS | GONZAGA | 1 | 1 | 4 | 2STY8CL (2-SCIENCE LAB, 2- ICT LAB) | BATCH 1 | 21114500 |  |  | Completed | 1
34932 | NC 2018 | TVL | Region II | Cagayan | 300435 | Baua HS | GONZAGA | 1 |  | 4 | 2STY8CL (4-REG. WORKSHOP) | BATCH 1 | 21114500 |  |  | Completed | 1
34933 | NC 2018 | TVL | Region II | Cagayan | 300465 | Ipil National High School | GONZAGA | 1 | 1 | 4 | 2STY8CL (4-REG. WORKSHOP) | BATCH 1 | 21114500 |  |  | Completed | 1 | [10 empty] | Ongoing rectification of the corrective observations and lacking
34934 | NC 2018 | TVL | Region II | Cagayan | 300465 | Ipil National High School | GONZAGA | 1 |  | 4 | 2STY8CL (2-SCIENCE LAB, 2- ICT LAB) | BATCH 1 | 21114500 |  |  | Completed | 1 | [10 empty] | Ongoing rectification of the corrective observations and lacking
34935 | NC 2018 | TVL | Region II | Cagayan | 300482 | Rebecca NHS | GONZAGA | 1 | 1 | 2 | 2STY4CL (2-REG. WORKSHOP) | BATCH 1 | 12246700 |  |  | Completed | 1
34936 | NC 2018 | TVL | Region II | Cagayan | 300482 | Rebecca NHS | GONZAGA | 1 |  | 4 | 2STY8CL (2-SCIENCE LAB, 2- ICT LAB) | BATCH 1 | 21114500 |  |  | Completed | 1
34937 | NC 2018 | TVL | Region II | Cagayan | 300483 | Gonzaga National High School | GONZAGA | 1 | 1 | 12 | 3STY12CL (2-SCIENCE LAB, 2- ICT LAB) | BATCH 1 Realignment | 34376711.64 |  |  | Completed | 1 | [10 empty] | Ongoing rectification of the corrective observations and lacking
34938 | NC 2018 | TVL | Region II | Cagayan | 306423 | Cabiraoan National High School | GONZAGA | 1 | 1 | 1 | UNIQUE WORKSHOP (7.0mX22.50m) | BATCH 1 | 4589808 |  |  | Completed | 1
34939 | NC 2018 | TVL | Region II | Cagayan | 306423 | Cabiraoan National High School | GONZAGA | 1 |  | 1 | REGULAR WORKSHOP (7.0mX18.0m) | BATCH 1 | 4583256 |  |  | Completed | 1
34940 | NC 2018 | TVL | Region II | Cagayan | 306423 | Cabiraoan National High School | GONZAGA | 1 |  | 2 | 2STY4CL (SCIENCE LAB, ICT LAB) | BATCH 1 | 12246700 |  |  | Completed | 1
34941 | NC 2018 | K10 | Region II | Cagayan | 102748 | Magapit ES | LAL-LO | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 13143802.23 |  |  | Completed | 1
34942 | NC 2018 | TVL | Region II | Cagayan | 300475 | Logac National High School | LAL-LO | 1 | 1 | 6 | 2STY12CL (6-REG. WORKSHOP) | BATCH 1 | 27338503.54 |  |  | Completed | 1
34943 | NC 2018 | TVL | Region II | Cagayan | 300475 | Logac National High School | LAL-LO | 1 |  | 4 | 2STY8CL (2-SCIENCE LAB, 2- ICT LAB) | BATCH 1 | 21114500 |  |  | Completed | 1
34944 | NC 2018 | TVL | Region II | Cagayan | 306003 | Lal-lo NHS - Cabayabasan Annex | LAL-LO | 1 | 1 | 4 | 2STY8CL (2-SCIENCE LAB, 2- ICT LAB) | BATCH 1 | 21114500 |  |  | Completed | 1
34945 | NC 2018 | TVL | Region II | Cagayan | 306004 | Magapit NHS | LAL-LO | 1 | 1 | 6 | 3STY9CL (3-Reg. Workshop, 3-Acad Room) | BATCH 1 | 25790486.44 |  |  | Completed | 1
34946 | NC 2018 | TVL | Region II | Cagayan | 306004 | Magapit NHS | LAL-LO | 1 |  | 8 | 3STY12CL (4-Acad Room, 2-SCIENCE LAB, 2- ICT LAB) | BATCH 1 | 34376711.64 |  |  | Completed | 1
34947 | NC 2018 | TVL | Region II | Cagayan | 300447 | Casambalangan NHS | SANTA ANA | 1 | 1 | 4 | 2STY8CL (2-SCIENCE LAB, 2- ICT LAB) | BATCH 1 | 21114500 |  |  | Completed | 1
34948 | NC 2018 | TVL | Region II | Cagayan | 300488 | Sta. Ana Fishery National High School | SANTA ANA | 1 | 1 | 4 | 2STY8CL (4-REG. WORKSHOP) | BATCH 1 | 21114500 |  |  | Completed | 1
34949 | NC 2018 | TVL | Region II | Cagayan | 300488 | Sta. Ana Fishery National High School | SANTA ANA | 1 |  | 4 | 2STY8CL (2-SCIENCE LAB,2- ICT LAB) | BATCH 1 | 21114500 |  |  | Completed | 1
34950 | NC 2018 | K10 | Region II | Cagayan | 102925 | Aridowen ES | SANTA TERESITA | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 13100360 |  |  | Completed | 1
34951 | NC 2018 | TVL | Region II | Cagayan | 306013 | Luga National High School | SANTA TERESITA | 1 | 1 | 4 | 2STY8CL (2-SCIENCE LAB, 2- ICT LAB) | BATCH 1 | 21114500 |  |  | Completed | 1
34952 | NC 2018 | K10 | Region II | Cagayan | 102337 | Canayun ES | ABULUG | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 2653900.28 |  |  | Completed | 1
34953 | NC 2018 | K10 | Region II | Cagayan | 102337 | Canayun ES | ABULUG | 2 |  | 2 | 1STY2CL | BATCH 1 | 2653900.28 |  |  | Completed | 1
34954 | NC 2018 | SHS | Region II | Cagayan | 300418 | Abulug National Rural and Vocational High School | ABULUG | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 2709289.3 |  |  | Completed | 1
34955 | NC 2018 | TVL | Region II | Cagayan | 300418 | Abulug National Rural and Vocational High School | ABULUG | 2 | 1 | 4 | 2STY4 LAB | BATCH 1 | 15914239.66 |  |  | Completed | 1
34956 | NC 2018 | TVL | Region II | Cagayan | 300419 | Abulug SOF | ABULUG | 2 | 1 | 6 | 2STY 6 LAB | BATCH 1 | 21565059.16 |  |  | Completed | 1
34957 | NC 2018 | TVL | Region II | Cagayan | 300473 | Libertad National High School | ABULUG | 2 | 1 | 7 | 3STY 2 LAB, 5CL | BATCH 1 | 19704373.57 |  |  | Completed | 1
34958 | NC 2018 | TVL | Region II | Cagayan | 300473 | Libertad National High School | ABULUG | 2 |  | 9 | 3STY 6 LAB, 3CL | BATCH 1 | 29416924 |  |  | Completed | 1
34959 | NC 2018 | TVL | Region II | Cagayan | 300423 | Alig Valley National High School | ALLACAPAN | 2 | 1 | 4 | 2STY4 LAB | BATCH 1 | 14110293.18 |  |  | Completed | 1
34960 | NC 2018 | TVL | Region II | Cagayan | 300477 | Matucay National High School | ALLACAPAN | 2 | 1 | 4 | 4STY4LAB (SL, ICT) | BATCH 1 | 16394338.45 |  |  | Completed | 1
34961 | NC 2018 | TVL | Region II | Cagayan | 500009 | Utan Integrated School | ALLACAPAN | 2 | 1 | 4 | 2STY 4 LAB (S, ICT) | BATCH 1 | 14110293.18 |  |  | Completed | 1
34962 | NC 2018 | TVL | Region II | Cagayan | 300434 | Ballesteros NHS | BALLESTEROS | 2 | 1 | 6 | 3STY 6 LAB | BATCH 1 | 26131751.72 |  |  | Completed | 1
34963 | NC 2018 | TVL | Region II | Cagayan | 300434 | Ballesteros NHS | BALLESTEROS | 2 |  | 2 | 2STY 2 LAB | BATCH 1 | 8923555.75 |  |  | Completed | 1
34964 | NC 2018 | K10 | Region II | Cagayan | 155040 | Bibigsan PS | CALAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 3465798.98 |  |  | Completed | 1
34965 | NC 2018 | K10 | Region II | Cagayan | 155040 | Bibigsan PS | CALAYAN | 2 |  | 2 | 1STY2CL | BATCH 1 | 3365798.98 |  |  | Completed | 1
34966 | NC 2018 | TVL | Region II | Cagayan | 300441 | Calayan HS | CALAYAN | 2 | 1 | 2 | 2STY 2 LAB | BATCH 1 | 10772844.75 |  |  | Completed | 1
34967 | NC 2018 | TVL | Region II | Cagayan | 300441 | Calayan HS | CALAYAN | 2 |  | 2 | 2STY 2 LAB | BATCH 1 | 10772844.75 |  |  | Completed | 1
34968 | NC 2018 | TVL | Region II | Cagayan | 300441 | Calayan HS | CALAYAN | 2 |  | 2 | 2STY 2 LAB | BATCH 1 | 10772844.75 |  |  | Completed | 1
34969 | NC 2018 | K10 | Region II | Cagayan | 102615 | Malilitao ES | CLAVERIA | 2 | 1 | 3 | 1STY3CL | BATCH 1 | 3851343.72 |  |  | Completed | 1
34970 | NC 2018 | TVL | Region II | Cagayan | 300449 | Claveria NHS | CLAVERIA | 2 | 1 | 6 | 2STY 4CL, 2 LAB | BATCH 1 | 12593885.23 |  |  | Completed | 1
34971 | NC 2018 | TVL | Region II | Cagayan | 300450 | Claveria RVS | CLAVERIA | 2 | 1 | 8 | 4STY 8 LAB (R,S,ICT) | BATCH 1 | 29422998 |  |  | Completed | 1
34972 | NC 2018 | TVL | Region II | Cagayan | 300451 | Claveria SAT | CLAVERIA | 2 | 1 | 6 | 2STY 6 LAB | BATCH 1 | 21110977.11 |  |  | Completed | 1
34973 | NC 2018 | TVL | Region II | Cagayan | 300451 | Claveria SAT | CLAVERIA | 2 | 1 | 4 | 2STY 4 LAB (S, ICT) | BATCH 1 | 13768447.38 |  |  | Completed | 1
34974 | NC 2018 | K10 | Region II | Cagayan | 102755 | Aggunetan ES | LASAM | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 2709289.3 |  |  | Completed | 1
34975 | NC 2018 | K10 | Region II | Cagayan | 102755 | Aggunetan ES | LASAM | 2 |  | 3 | 1STY3CL | BATCH 1 | 3902258.26 |  |  | Completed | 1
34976 | NC 2018 | K10 | Region II | Cagayan | 102758 | Lasam West Central School | LASAM | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 2709289.3 |  |  | Completed | 1
34977 | NC 2018 | K10 | Region II | Cagayan | 102758 | Lasam West Central School | LASAM | 2 |  | 2 | 1STY2CL | BATCH 1 | 2709289.3 |  |  | Completed | 1
34978 | NC 2018 | K10 | Region II | Cagayan | 102758 | Lasam West Central School | LASAM | 2 |  | 2 | 1STY2CL | BATCH 1 | 2709289.3 |  |  | Completed | 1
34979 | NC 2018 | K10 | Region II | Cagayan | 102763 | I.B. Jurado ES | LASAM | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 2709289.3 |  |  | Completed | 1
34980 | NC 2018 | K10 | Region II | Cagayan | 102763 | I.B. Jurado ES | LASAM | 2 |  | 2 | 1STY2CL | BATCH 1 | 2709289.3 |  |  | Completed | 1
34981 | NC 2018 | TVL | Region II | Cagayan | 300438 | Cabatacan National High School | LASAM | 2 | 1 | 1 | 1STY 1 LAB (7 x 22.5) | BATCH 1 | 3089457.37 |  |  | Completed | 1 | [9 empty] | 43520
34982 | NC 2018 | TVL | Region II | Cagayan | 300438 | Cabatacan National High School | LASAM | 2 |  | 4 | 2STY4 LAB | BATCH 1 | 14110293.18 |  |  | Completed | 1
34983 | NC 2018 | TVL | Region II | Cagayan | 300438 | Cabatacan National High School | LASAM | 2 |  | 4 | 2STY4 LAB | BATCH 1 | 14110293.18 |  |  | Completed | 1
34984 | NC 2018 | TVL | Region II | Cagayan | 300439 | Nabannagan National High School | LASAM | 2 | 1 | 5 | 2STY 3 LAB, 2CL | BATCH 1 | 17701505.01 |  |  | Completed | 1
34985 | NC 2018 | TVL | Region II | Cagayan | 300443 | Callao National High School | LASAM | 2 | 1 | 6 | 2STY4CL, 2 LAB | BATCH 1 | 13243083.68 |  |  | Completed | 1
34986 | NC 2018 | TVL | Region II | Cagayan | 300497 | Western Cagayan SAT | LASAM | 2 | 1 | 2 | 2STY 2 LAB | BATCH 1 | 7785123.51 |  |  | Completed | 1 | [9 empty] | 43561
34987 | NC 2018 | TVL | Region II | Cagayan | 300497 | Western Cagayan SAT | LASAM | 2 |  | 8 | 2STY 8 LAB | BATCH 1 | 21201091.85 |  |  | Completed | 1
34988 | NC 2018 | TVL | Region II | Cagayan | 300497 | Western Cagayan SAT | LASAM | 2 |  | 6 | 2STY6 LAB | BATCH 1 | 17832312.11 |  |  | Completed | 1
34989 | NC 2018 | K10 | Region II | Cagayan | 102787 | Casitan ES | PAMPLONA | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 2653900.28 |  |  | Completed | 1
34990 | NC 2018 | TVL | Region II | Cagayan | 300436 | Bidduang National High School | PAMPLONA | 2 | 1 | 4 | 2STY4 LAB (SCI LAB, ICT) | BATCH 1 | 13768447.38 |  |  | Completed | 1
34991 | NC 2018 | TVL | Region II | Cagayan | 300454 | David M. Puzon MNHS | PAMPLONA | 2 | 1 | 4 | 2STY 4 LAB (S, ICT) | BATCH 1 | 13768447.38 |  |  | Completed | 1
34992 | NC 2018 | TVL | Region II | Cagayan | 300454 | David M. Puzon MNHS | PAMPLONA | 2 |  | 6 | 2STY 6LAB | BATCH 1 | 17406691.22 |  |  | Completed | 1
34993 | NC 2018 | TVL | Region II | Cagayan | 300479 | Pamplona National School of Fisheries | PAMPLONA | 2 | 1 | 4 | 2STY 4 LAB | BATCH 1 | 13768447.38 |  |  | Completed | 1 | [9 empty] | 43615
34994 | NC 2018 | TVL | Region II | Cagayan | 300479 | Pamplona National School of Fisheries | PAMPLONA | 2 | 1 | 8 | 2STY 8 LAB | BATCH 1 | 21169425.32 |  |  | Completed | 1
34995 | NC 2018 | K10 | Region II | Cagayan | 102820 | Apayao ES | PIAT | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 2653900.28 |  |  | Completed | 1
34996 | NC 2018 | TVL | Region II | Cagayan | 300481 | Piat National HS | PIAT | 2 | 1 | 6 | 2STY4 LAB, 2CL | BATCH 1 | 17210559.23 |  |  | Completed | 1
34997 | NC 2018 | TVL | Region II | Cagayan | 300464 | Illuru NHS | RIZAL | 2 | 1 | 6 | 2STY 6 LAB (SCI LAB, ICT) | BATCH 1 | 21565059.16 |  |  | Completed | 1
34998 | NC 2018 | TVL | Region II | Cagayan | 300478 | Mauanan NHS | RIZAL | 2 | 1 | 2 | 2STY 2 LAB | BATCH 1 | 9126362.31 |  |  | Completed | 1
34999 | NC 2018 | TVL | Region II | Cagayan | 300478 | Mauanan NHS | RIZAL | 2 |  | 2 | 2STY 2 LAB | BATCH 1 | 9223662.31 |  |  | Completed | 1
35000 | NC 2018 | TVL | Region II | Cagayan | 300478 | Mauanan NHS | RIZAL | 2 |  | 2 | 2STY 2 LAB | BATCH 1 | 9223662.31 |  |  | Completed | 1
35001 | NC 2018 | K10 | Region II | Cagayan | 102861 | Sanchez Mira Central Elementary School | SANCHEZ-MIRA | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 2653900.28 |  |  | Completed | 1
35002 | NC 2018 | K10 | Region II | Cagayan | 102861 | Sanchez Mira Central Elementary School | SANCHEZ-MIRA | 2 |  | 3 | 1STY3CL | BATCH 1 | 3851343.72 |  |  | Completed | 1
35003 | NC 2018 | TVL | Region II | Cagayan | 300485 | Sanchez Mira NHS | SANCHEZ-MIRA | 2 | 1 | 4 | 2STY SCI LAB & ICT | BATCH 1 | 15914239.86 |  |  | Completed | 1
35004 | NC 2018 | TVL | Region II | Cagayan | 300486 | Sanchez Mira SAT | SANCHEZ-MIRA | 2 | 1 | 1 | 1STY 1 LAB (TECH VOC) | BATCH 1 | 3045441.75 |  |  | Completed | 1
35005 | NC 2018 | TVL | Region II | Cagayan | 300486 | Sanchez Mira SAT | SANCHEZ-MIRA | 2 |  | 1 | 1STY 1 LAB (TECH VOC) | BATCH 1 | 3045441.75 |  |  | Completed | 1
35006 | NC 2018 | TVL | Region II | Cagayan | 300486 | Sanchez Mira SAT | SANCHEZ-MIRA | 2 |  | 1 | 1STY 1 LAB | BATCH 1 | 3045441.75 |  |  | Completed | 1
35007 | NC 2018 | TVL | Region II | Cagayan | 300486 | Sanchez Mira SAT | SANCHEZ-MIRA | 2 |  | 1 | 1STY 1 LAB | BATCH 1 | 3045441.75 |  |  | Completed | 1
35008 | NC 2018 | TVL | Region II | Cagayan | 300489 | Sta. Praxedes High School | SANTA PRAXEDES | 2 | 1 | 4 | 2STY4 LAB (SCI LAB, ICT) | BATCH 1 | 13768447.38 |  |  | Completed | 1
35009 | NC 2018 | K10 | Region II | Cagayan | 102943 | Lattac ES | SANTO NIÑO (FAIRE) | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 3982288.26 |  |  | Completed | 1
35010 | NC 2018 | K10 | Region II | Cagayan | 155026 | Palusao PS | SANTO NIÑO (FAIRE) | 2 | 1 | 6 | 3STY6CL | BATCH 1 | 12539396.79 |  |  | Completed | 1 | [9 empty] | 43622
35011 | NC 2018 | TVL | Region II | Cagayan | 300491 | Sto. Nino NHS | SANTO NIÑO (FAIRE) | 2 | 1 | 9 | 3STY 9 LAB (R,S & ICT) | BATCH 1 | 33568614.16 |  |  | Completed | 1
35012 | NC 2018 | SHS | Region II | Cagayan | 300491 | Sto. Nino NHS | SANTO NIÑO (FAIRE) | 2 |  | 4 | 2STY4CL | BATCH 1 | 7184396.67 |  |  | Completed | 1
35013 | NC 2018 | TVL | Region II | Cagayan | 306006 | Abariongan National High School | SANTO NIÑO (FAIRE) | 2 | 1 | 4 | 2STY 4 LAB | BATCH 1 | 16278467.11 |  |  | Completed | 1
35014 | NC 2018 | TVL | Region II | Cagayan | 306425 | Namuccayan Integrated School | SANTO NIÑO (FAIRE) | 2 | 1 | 4 | 2STY4 LAB (SCI LAB, ICT) | BATCH 1 | 16248422.54 |  |  | Completed | 1
35015 | NC 2018 | TVL | Region II | Cagayan | 300425 | AMULUNG NATIONAL HIGH SCHOOL | AMULUNG | 3 | 1 | 8 | 2 STY 8 CL: (2CL Sci. Lab., 2CL ICT) | BATCH 1 | 15919594 |  |  | Completed | 1
35016 | NC 2018 | TVL | Region II | Cagayan | 300452 | Cordova National High Sschool | AMULUNG | 3 | 1 | 12 | 3STY12CL (2CL Reg. Workshop, 2CL Sci. Lab. & 2CL ICT) | BATCH 1 | 28489030 |  |  | Completed | 1
35017 | NC 2018 | SHS | Region II | Cagayan | 306008 | Amulung NHS - Baculud Ext. | AMULUNG | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2580796 |  |  | Completed | 1
35018 | NC 2018 | TVL | Region II | Cagayan | 306009 | Bayabat NHS - La Suerte Ext. | AMULUNG | 3 | 1 | 12 | 3STY12CL (2CL Sci. Lab., 2CL ICT & 4CL SHS Bldg.) | BATCH 1 | 28507138 |  |  | Completed | 1
35019 | NC 2018 | TVL | Region II | Cagayan | 306010 | PACAC GRANDE NAT'L. HIGH SCHOOL | AMULUNG | 3 | 1 | 8 | 2STY8CL (2CL Sci. Lab. & 2CL ICT) | BATCH 1 | 16275981 |  |  | Completed | 1
35020 | NC 2018 | TVL | Region II | Cagayan | 300458 | Enrile Vocational High School | ENRILE | 3 | 1 | 12 | 3STY12CL (2CL Sci. Lab., 2CL ICT & 2CL Reg. Workshop Bldg.) | BATCH 1 | 28286796 |  |  | Completed | 1
35021 | NC 2018 | TVL | Region II | Cagayan | 300472 | Lemu NHS | ENRILE | 3 | 1 | 12 | 3STY12CL (2CL Sci. Lab., 2CL ICT & 4CL SHS Bldg.) | BATCH 1 | 28141031 |  |  | Completed | 1
35022 | NC 2018 | TVL | Region II | Cagayan | 300463 | Vicente D. Trinidad High School | IGUIG | 3 | 1 | 8 | 2STY8 CL (2CL Sci. Lab., 2 CL ICT) | BATCH 1 | 16143887 |  |  | Completed | 1
35023 | NC 2018 | TVL | Region II | Cagayan | 306001 | Gammad National High School | IGUIG | 3 | 1 | 12 | 3STY12CL (2CL Sci. Lab., 2CL ICT , 2CL Reg. Workshop Bldg.) | BATCH 1 | 28015086 |  |  | Completed | 1
35024 | NC 2018 | SHS | Region II | Cagayan | 306421 | Caridad B. Trinidad National High School | IGUIG | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2511094 |  |  | Completed | 1
35025 | NC 2018 | SHS | Region II | Cagayan | 300445 | Penablanca National High School | PEÑABLANCA | 3 | 1 | 9 | 3STY9CL | BATCH 1 | 23206492.9 |  |  | Completed | 1
35026 | NC 2018 | TVL | Region II | Cagayan | 300445 | Penablanca National High School | PEÑABLANCA | 3 |  | 8 | 2STY8CL (2cl Sci. Lab. & 2cl ICT) | BATCH 1 | 15862844 |  |  | Completed | 1
35027 | NC 2018 | SHS | Region II | Cagayan | 300446 | Cabbo NHS | PEÑABLANCA | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 10227363 |  |  | Completed | 1
35028 | NC 2018 | TVL | Region II | Cagayan | 300446 | Cabbo NHS | PEÑABLANCA | 3 |  | 12 | 3STY12CL (2CL Sci. Lab., 2CL Reg. Workshop, & 2CL ICT) | BATCH 1 | 28286796 |  |  | Completed | 1
35029 | NC 2018 | SHS | Region II | Cagayan | 300456 | Don Severino Pagalilauan National High School | PEÑABLANCA | 3 | 1 | 8 | 2STY8CL | BATCH 1 | 15767075 |  |  | Completed | 1
35030 | NC 2018 | TVL | Region II | Cagayan | 300456 | Don Severino Pagalilauan National High School | PEÑABLANCA | 3 |  | 8 | 2STY8CL (2cl Sci. Lab. & 2cl ICT) | BATCH 1 | 16002844 |  |  | Completed | 1
35031 | NC 2018 | TVL | Region II | Cagayan | 300457 | Penablanca East NHS | PEÑABLANCA | 3 | 1 | 8 | 2STY8CL (2CL Sci. Lab. & 2CL ICT) | BATCH 1 | 16087213 |  |  | Completed | 1
35032 | NC 2018 | TVL | Region II | Cagayan | 300426 | Andarayan NHS | SOLANA | 3 | 1 | 18 | 3STY18CL (3CL Reg. Workshop, 3CL ICT & 3CL Sci. Lab.) | BATCH 1 | 35979650.8 |  |  | Completed | 1
35033 | NC 2018 | TVL | Region II | Cagayan | 300484 | Sampaguita NHS | SOLANA | 3 | 1 | 16 | 4STY16CL (2CL Sci. Lab., 2CL ICT & 4CL Reg. Workshop Bldg.) | BATCH 1 | 35272185.15 |  |  | Completed | 1
35034 | NC 2018 | TVL | Region II | Cagayan | 300487 | Solana Fresh Water Fishery School | SOLANA | 3 | 1 | 8 | 2STY8CL (2CL Sci. Lab. & 2CL ICT) | BATCH 1 | 16162837 |  |  | Completed | 1
35035 | NC 2018 | SHS | Region II | Cagayan | 306424 | Gadu NHS- Nangalisan Extension | SOLANA | 3 | 1 | 8 | 2STY8CL | BATCH 1 | 15590861 |  |  | Completed | 1
35036 | NC 2018 | TVL | Region II | Cagayan | 306424 | Gadu NHS- Nangalisan Extension | SOLANA | 3 |  | 12 | 3STY12CL (2CL Reg. Workshop, 2CL Sci. Lab. & 2CL ICT) | BATCH 1 | 28286796 |  |  | Completed | 1
35037 | NC 2018 | TVL | Region II | Cagayan | 300466 | Itawes Nat'l. Agr'l. & Tech'l. School | TUAO | 3 | 1 | 8 | 2STY8CL (2CL Sci. Lab. & 2CL ICT) | BATCH 1 | 15638551 |  |  | Completed | 1
35038 | NC 2018 | TVL | Region II | Cagayan | 300468 | Itawes Nat'l.l Agr'l. & Tech'l. School - Bagumbayan Annex | TUAO | 3 | 1 | 12 | 3STY12CL (2CL Sci. Lab., 2CL ICT, & 2CL Reg. Workshop Bldg.) | BATCH 1 | 28035086 |  |  | Completed | 1
35039 | NC 2018 | TVL | Region II | Cagayan | 300494 | Tuao Voc'l. and Tech'l. School - Pata Annex | TUAO | 3 | 1 | 12 | 3STY12CL (2CL Science Lab., 2CL ICT & 2CL Reg. Workshop Bldg.) | BATCH 1 | 28173705 |  |  | Completed | 1
35040 | NC 2018 | TVL | Region II | Cauayan City | 300516 | Cauayan City NHS | CITY OF CAUAYAN | 3 | 1 | 4 | 2STY 4 REG WORKSHOP | BATCH 1 | 19309481.08 |  |  | Completed | 1
35041 | NC 2018 | TVL | Region II | Cauayan City | 300516 | Cauayan City NHS | CITY OF CAUAYAN | 3 |  | 4 | 2STY 4 REG WORKSHOP | BATCH 1 | 19309481.08 |  |  | Completed | 1
35042 | NC 2018 | TVL | Region II | Cauayan City | 300516 | Cauayan City NHS | CITY OF CAUAYAN | 3 |  | 4 | 2STY 4LAB (2 ICT & 2 SCI LAB) | BATCH 1 | 19432804.91 |  |  | Completed | 1
35043 | NC 2018 | SHS | Region II | Cauayan City | 300538 | Gappal NHS | CITY OF CAUAYAN | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9934388.61 |  |  | Completed | 1
35044 | NC 2018 | SHS | Region II | Cauayan City | 300567 | Pinoma NHS | CITY OF CAUAYAN | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9733435.94 |  |  | Completed | 1
35045 | NC 2018 | SHS | Region II | Cauayan City | 300589 | San Antonio National High School | CITY OF CAUAYAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2968627.7 |  |  | Completed | 1
35046 | NC 2018 | TVL | Region II | Cauayan City | 300589 | San Antonio National High School | CITY OF CAUAYAN | 3 |  | 1 | 1STY 1 SCI LAB | BATCH 1 | 3134292.58 |  |  | Completed | 1
35047 | NC 2018 | SHS | Region II | Cauayan City | 300613 | Villa Concepcion HS | CITY OF CAUAYAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2997082.46 |  |  | Completed | 1
35048 | NC 2018 | SHS | Region II | Cauayan City | 306107 | WEST TABACAL REGION NATIONAL HIGH SCHOOL | CITY OF CAUAYAN | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 1 | 4381924.95 |  |  | Completed | 1
35049 | NC 2018 | SHS | Region II | Cauayan City | 306118 | Sillawit National High School | CITY OF CAUAYAN | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 1 | 4381924.95 |  |  | Completed | 1
35050 | NC 2018 | SHS | Region II | Cauayan City | 323903 | Villa Concepcion HS - Rogus Ext. | CITY OF CAUAYAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2997082.46 |  |  | Completed | 1
35051 | NC 2018 | K10 | Region II | Cauayan City | 103224 | San Francisco ES - Annex | CITY OF CAUAYAN | 3 | 1 | 2 | 1STY2CL | Batch 3 | 6033840.56 |  |  | Completed | 1
35052 | NC 2018 | K10 | Region II | Cauayan City | 103228 | Cauayan South CS | CITY OF CAUAYAN | 3 | 1 | 3 | 1STY3CL | Batch 3 | 8531819.63 |  |  | Completed | 1
35053 | NC 2018 | K10 | Region II | Cauayan City | 103232 | Marabulig II ES | CITY OF CAUAYAN | 3 | 1 | 2 | 1STY2CL | Batch 3 | 5950378.19 |  |  | Completed | 1
35054 | NC 2018 | K10 | Region II | City of Ilagan | 103364 | Ilagan East CS | ILAGAN (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 1 | 37494405.65 |  |  | Completed | 1
35055 | NC 2018 | K10 | Region II | City of Ilagan | 103376 | San Lorenzo Integrated School (San Lorenzo ES) | ILAGAN (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9640356.31 |  |  | Completed | 1
35056 | NC 2018 | SHS | Region II | City of Ilagan | 300542 | Isabela NHS - Main | ILAGAN (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 1 | 37523389.65 |  |  | Completed | 1
35057 | NC 2018 | SHS | Region II | City of Ilagan | 300584 | San Rafael Nat'l & Voc'l HS (San Antonio NAIVHS-San Rafael Annex) | ILAGAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 2793756.12 |  |  | Completed | 1
35058 | NC 2018 | SHS | Region II | City of Ilagan | 500078 | Manaring Integrated School | ILAGAN (Capital) | 1 | 1 | 9 | 3STY9CL | BATCH 1 | 25357623.18 |  |  | Completed | 1
35059 | NC 2018 | SHS | Region II | City of Ilagan | 300583 | San Antonio Nat'l. Agro-Ind'l. & Voc'l. HS | ILAGAN CITY (CAPITAL) | 1 | 1 | 8 | 2STY8CL | Batch 3 | 23493542.49 |  |  | Completed | 1
35060 | NC 2018 | K10 | Region II | Isabela | 103149 | Catabayungan ES | CABAGAN | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 2830001.79 |  |  | Completed | 1
35061 | NC 2018 | K10 | Region II | Isabela | 155535 | Casibarag Norte Elementary School | CABAGAN | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 2939401 |  |  | Completed | 1
35062 | NC 2018 | TVL | Region II | Isabela | 300587 | Ragan Sur National High School | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | 12 | 3STY12CL (ICT & SCI LAB) | BATCH 1 | 43835905.15 |  |  | Completed | 1
35063 | NC 2018 | TVL | Region II | Isabela | 300560 | Maconacon National High School | MACONACON | 1 | 1 | 8 | 2 UNITS OF 2STY4CL (WORKSHOP / LAB) | BATCH 1 | 24319807.88 |  |  | Completed | 1
35064 | NC 2018 | TVL | Region II | Isabela | 300554 | Isabela School of Fisheries | PALANAN | 1 | 1 | 16 | 2 UNITS OF 2STY8CL (WORKSHOP / LAB) | BATCH 1 | 48060695 |  |  | Completed | 1
35065 | NC 2018 | K10 | Region II | Isabela | 103854 | Sta. Maria Central School | SANTA MARIA | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 2907447.61 |  |  | Completed | 1
35066 | NC 2018 | K10 | Region II | Isabela | 103883 | Sta. Catalina Elementary School | TUMAUINI | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 2805114.71 |  |  | Completed | 1
35067 | NC 2018 | K10 | Region II | Isabela | 155536 | Pallacot Elementary School | TUMAUINI | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 2907447.61 |  |  | Completed | 1
35068 | NC 2018 | SHS | Region II | Isabela | 300547 | Antagan National High School | TUMAUINI | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 2805114.71 |  |  | Completed | 1
35069 | NC 2018 | TVL | Region II | Isabela | 342077 | Dona Aurora Senior High School | AURORA | 5 | 1 | 20 | 4STY20CL (4 REG WORKSHOP & 12 SHS) | BATCH 1 | 45549250.71 |  |  | Completed | 1
35070 | NC 2018 | TVL | Region II | Isabela | 342077 | Dona Aurora Senior High School | AURORA | 5 | 1 | 16 | 4STY20CL (2 REG WORKSHOP, SCI LAB, ICT & 12 SHS CL) | BATCH 1 | 45549250.71 |  |  | Completed | 1
35071 | NC 2018 | TVL | Region II | Isabela | 300503 | BENITO SOLIVEN NATIONAL HIGH SCHOOL | BENITO SOLIVEN | 2 | 1 | 2 | 2STY4CL (2 REG WORKSHOP) | BATCH 1 | 10149703.19 |  |  | Completed | 1
35072 | NC 2018 | TVL | Region II | Isabela | 300546 | Andabuen National High School | BENITO SOLIVEN | 2 | 1 | 2 | 2STY4CL (SCI LAB &REG) | BATCH 1 | 10149703.19 |  |  | Completed | 1
35073 | NC 2018 | TVL | Region II | Isabela | 300509 | Burgos National High School | BURGOS | 5 | 1 | 4 | 2STY8CL (2 REG, SCI & ICT) | BATCH 1 | 19840259.73 |  |  | Completed | 1
35074 | NC 2018 | TVL | Region II | Isabela | 300511 | San Antonino National High School | BURGOS | 5 | 1 | 2 | 2STY4CL (REG & SCI LAB) | BATCH 1 | 10149703.19 |  |  | Completed | 1
35075 | NC 2018 | TVL | Region II | Isabela | 300537 | Gamu Rural School-Main | GAMU | 2 | 1 | 8 | 2STY8CL (REG, SCI, ICT, REG) | BATCH 1 | 19840259.73 |  |  | Completed | 1
35076 | NC 2018 | TVL | Region II | Isabela | 300559 | Mabini National High School | GAMU | 2 | 1 | 4 | 2STY4CL (SCI & REG) | BATCH 1 | 10149703.19 |  |  | Completed | 1
35077 | NC 2018 | TVL | Region II | Isabela | 300561 | Mallig National High School-Main | MALLIG | 5 | 1 | 2 | 2STY4CL (2 REG) | BATCH 1 | 10149703.19 |  |  | Completed | 1
35078 | NC 2018 | TVL | Region II | Isabela | 306110 | San Jose National High School | MALLIG | 5 | 1 | 2 | 2STY4CL (SCI LAB & ICT) | BATCH 1 | 9277002.9 |  |  | Completed | 1
35079 | NC 2018 | TVL | Region II | Isabela | 500077 | Bimonton Integrated School | MALLIG | 5 | 1 | 2 | 2STY4CL (SCI LAB & ICT) | BATCH 1 | 10149703.19 |  |  | Completed | 1
35080 | NC 2018 | TVL | Region II | Isabela | 300563 | Naguillian National High School | NAGUILIAN | 2 | 1 | 8 | 4STY8CL (2 REG, SCI, ICT) | BATCH 1 | 19840259.73 |  |  | Completed | 1
35081 | NC 2018 | TVL | Region II | Isabela | 306157 | Cabaruan Integrated School | NAGUILIAN | 2 | 1 | 2 | 2STY4CL (SCI LAB & REG) | BATCH 1 | 10149703.19 |  |  | Completed | 1
35082 | NC 2018 | TVL | Region II | Isabela | 300568 | Quezon National High School | QUEZON | 5 | 1 | 2 | 2STY4CL (2 REG WORKSHOP) | BATCH 1 | 10149703.19 |  |  | Completed | 1
35083 | NC 2018 | TVL | Region II | Isabela | 300568 | Quezon National High School | QUEZON | 5 |  | 2 | 2STY4CL (ICT & SCI LAB) | BATCH 1 | 10149703.19 |  |  | Completed | 1
35084 | NC 2018 | TVL | Region II | Isabela | 306112 | Barucboc National High School | QUEZON | 5 | 1 | 2 | 2STY4CL (2 REG WORKSHOP) | BATCH 1 | 9277002.9 |  |  | Completed | 1
35085 | NC 2018 | TVL | Region II | Isabela | 306112 | Barucboc National High School | QUEZON | 5 |  | 2 | 2STY4CL (ICT & SCI LAB) | BATCH 1 | 9277002.9 |  |  | Completed | 1
35086 | NC 2018 | TVL | Region II | Isabela | 300569 | Quirino National High School | QUIRINO | 5 | 1 | 2 | 2STY4CL (2 REG WORKSHOP) | BATCH 1 | 10149703.19 |  |  | Completed | 1
35087 | NC 2018 | TVL | Region II | Isabela | 300569 | Quirino National High School | QUIRINO | 5 |  | 2 | 2STY4CL (ICT & SCI LAB) | BATCH 1 | 10149703.19 |  |  | Completed | 1
35088 | NC 2018 | TVL | Region II | Isabela | 500082 | Sto. Domingo Integrated School | QUIRINO | 5 | 1 | 2 | 2STY4CL (2 REG WORKSHOP) | BATCH 1 | 10149703.19 |  |  | Completed | 1
35089 | NC 2018 | TVL | Region II | Isabela | 300562 | Munoz High School | ROXAS | 5 | 1 | 2 | 2STY4CL (SCI LAB & REG) | BATCH 1 | 9277002.9 |  |  | Completed | 1
35090 | NC 2018 | SHS | Region II | Isabela | 300579 | Roxas National High School | ROXAS | 5 | 1 | 4 | 2STY4CL | BATCH 1 | 10149703.19 |  |  | Completed | 1
35091 | NC 2018 | TVL | Region II | Isabela | 300579 | Roxas National High School | ROXAS | 5 |  | 3 | 3STY6CL (3 REG WORKSHOP) | BATCH 1 | 13644987.47 |  |  | Completed | 1
35092 | NC 2018 | TVL | Region II | Isabela | 306111 | Monico Rarama National High School | ROXAS | 5 | 1 | 6 | 3STY6CL (SCI LAB & 2 REG WORKSHOP) | BATCH 1 | 13644987.47 |  |  | Completed | 1
35093 | NC 2018 | TVL | Region II | Isabela | 306135 | Matusalem National High School | ROXAS | 5 | 1 | 6 | 3STY6CL (SCI LAB & 2 REG WORKSHOP) | BATCH 1 | 13644987.47 |  |  | Completed | 1
35094 | NC 2018 | TVL | Region II | Isabela | 500094 | Simimbaan Integrated School | ROXAS | 5 | 1 | 2 | 2STY4CL (SCI LAB & REG) | BATCH 1 | 9277002.9 |  |  | Completed | 1
35095 | NC 2018 | TVL | Region II | Isabela | 300512 | Callang National High School - Main | SAN MANUEL | 5 | 1 | 6 | 3STY6CL (3 REG WORKSHOP) | BATCH 1 | 13644987.47 |  |  | Completed | 1
35096 | NC 2018 | TVL | Region II | Isabela | 300513 | Malalinta National High School | SAN MANUEL | 5 | 1 | 2 | 2STY4CL (2 REG) | BATCH 1 | 9277002.9 |  |  | Completed | 1
35097 | NC 2018 | TVL | Region II | Isabela | 300514 | Sandiat National High School | SAN MANUEL | 5 | 1 | 4 | 2STY4CL (ICT & SCI LAB) | BATCH 1 | 9277002.9 |  |  | Completed | 1
35098 | NC 2018 | TVL | Region II | Isabela | 300592 | San Mariano National High School - Main | SAN MARIANO | 2 | 1 | 2 | 2STY4CL (2 REG WORKSHOP) | BATCH 1 | 10149703.19 |  |  | Completed | 1
35099 | NC 2018 | TVL | Region II | Isabela | 300592 | San Mariano National High School - Main | SAN MARIANO | 2 |  | 2 | 2STY4CL (SCI LAB & ICT) | BATCH 1 | 10149703.19 |  |  | Completed | 1
35100 | NC 2018 | TVL | Region II | Isabela | 300593 | Alibadbad National High School | SAN MARIANO | 2 | 1 | 2 | 2STY4CL (SCI LAB & REG.) | BATCH 1 | 10149703.19 |  |  | Completed | 1
35101 | NC 2018 | TVL | Region II | Isabela | 306137 | Daragutan East National High School | SAN MARIANO | 2 | 1 | 2 | 2STY4CL ( SCI LAB & ICT) | BATCH 1 | 9277002.9 |  |  | Completed | 1
35102 | NC 2018 | TVL | Region II | Isabela | 300499 | Alicia Vocational School | ALICIA | 3 | 1 | 4 | 2STY 4 REG WORKSHOP | BATCH 1 | 19309481.08 |  |  | Completed | 1
35103 | NC 2018 | TVL | Region II | Isabela | 300499 | Alicia Vocational School | ALICIA | 3 |  | 2 | 2STY 2LAB (ICT & SCI LAB) | BATCH 1 | 9767224.01 |  |  | Completed | 1
35104 | NC 2018 | TVL | Region II | Isabela | 300500 | Alicia National High School | ALICIA | 3 | 1 | 2 | 2STY 2 REG WORKSHOP | BATCH 1 | 9379174.62 |  |  | Completed | 1
35105 | NC 2018 | TVL | Region II | Isabela | 300500 | Alicia National High School | ALICIA | 3 |  | 2 | 2STY 2LAB (ICT & SCI LAB) | BATCH 1 | 9767224.01 |  |  | Completed | 1
35106 | NC 2018 | TVL | Region II | Isabela | 300558 | Luna National High School | LUNA | 5 | 1 | 2 | 1STY 2 UNIQUE WORKSHOP | BATCH 1 | 7051441.5 |  |  | Completed | 1
35107 | NC 2018 | TVL | Region II | Isabela | 306116 | Reina Mercedes Vocational High School | REINA MERCEDES | 3 | 1 | 2 | 2STY 2LAB (ICT & SCI LAB) | BATCH 1 | 9936464.29 |  |  | Completed | 1
35108 | NC 2018 | TVL | Region II | Isabela | 306116 | Reina Mercedes Vocational High School | REINA MERCEDES | 3 |  | 2 | 2STY 2 REG WORKSHOP | BATCH 1 | 9562627.71 |  |  | Completed | 1
35109 | NC 2018 | K10 | Region II | Isabela | 103680 | Dipacamo ES | SAN GUILLERMO | 6 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 1 | 5598745.06 |  |  | Completed | 1
35110 | NC 2018 | K10 | Region II | Isabela | 103243 | Anonang Elementary School | CORDON | 4 | 1 | 2 | 1STY2CL W/ TOILET (KINDER) | BATCH 1 | 2738254.17 |  |  | Completed | 1
35111 | NC 2018 | K10 | Region II | Isabela | 103249 | Dallao Elementary School | CORDON | 4 | 1 | 2 | 1STY2CL W/ TOILET (KINDER) | BATCH 1 | 2811111.4 |  |  | Completed | 1
35112 | NC 2018 | TVL | Region II | Isabela | 300508 | Cagasat National High School | CORDON | 4 | 1 | 4 | 2STY4CL (SCI LAB, ICT) | BATCH 1 | 9586071.53 |  |  | Completed | 1
35113 | NC 2018 | TVL | Region II | Isabela | 300508 | Cagasat National High School | CORDON | 4 |  | 4 | 2STY4CL (2STY REG WORKSHOP) | BATCH 1 | 9227002.9 |  |  | Completed | 1
35114 | NC 2018 | TVL | Region II | Isabela | 300508 | Cagasat National High School | CORDON | 4 |  | 4 | 2STY4CL (2STY REG WORKSHOP) | BATCH 1 | 9227002.9 |  |  | Completed | 1
35115 | NC 2018 | TVL | Region II | Isabela | 300508 | Cagasat National High School | CORDON | 4 |  | 1 | UNIQUE WORKSHOP (7.0mX22.50m) | BATCH 1 | 3170000 |  |  | Completed | 1
35116 | NC 2018 | TVL | Region II | Isabela | 300523 | Diadi Region High School | CORDON | 4 | 1 | 4 | 4STY8CL (2 SCI LAB & 2 ICT LAB) | BATCH 1 | 18439908.21 |  |  | Completed | 1
35117 | NC 2018 | TVL | Region II | Isabela | 300532 | Dona Josefa E. Marcos High School | CORDON | 4 | 1 | 2 | 2STY4CL (2 ICT LAB) | BATCH 1 | 9520552 |  |  | Completed | 1
35118 | NC 2018 | TVL | Region II | Isabela | 300532 | Dona Josefa E. Marcos High School | CORDON | 4 |  | 1 | 1STY SCI LAB | BATCH 1 | 3091098.32 |  |  | Completed | 1
35119 | NC 2018 | TVL | Region II | Isabela | 300532 | Dona Josefa E. Marcos High School | CORDON | 4 |  | 1 | 1STY2CL (REG WORKSHOP) | BATCH 1 | 2878804.24 |  |  | Completed | 1
35120 | NC 2018 | TVL | Region II | Isabela | 306143 | Cagasat HS-Magsaysay Annex | CORDON | 4 | 1 | 4 | 2STY4CL (2 ICT LAB ) | BATCH 1 | 9520552 |  |  | Completed | 1
35121 | NC 2018 | TVL | Region II | Isabela | 306143 | Cagasat HS-Magsaysay Annex | CORDON | 4 |  | 1 | 1STY2CL ( SCI LAB) | BATCH 1 | 3091098.32 |  |  | Completed | 1
35122 | NC 2018 | TVL | Region II | Isabela | 306143 | Cagasat HS-Magsaysay Annex | CORDON | 4 |  | 1 | 1STY2CL ( SCI LAB) | BATCH 1 | 3091098.32 |  |  | Completed | 1
35123 | NC 2018 | TVL | Region II | Isabela | 500073 | Wigan Integrated School | CORDON | 4 | 1 | 2 | 2STY4CL (2 1CT LAB) | BATCH 1 | 9520552 |  |  | Completed | 1
35124 | NC 2018 | TVL | Region II | Isabela | 500073 | Wigan Integrated School | CORDON | 4 |  | 1 | 1STY2CL SCI LAB | BATCH 1 | 3091098.32 |  |  | Completed | 1
35125 | NC 2018 | TVL | Region II | Isabela | 500073 | Wigan Integrated School | CORDON | 4 |  | 1 | 1STY2CL SCI LAB | BATCH 1 | 3091098.32 |  |  | Completed | 1
35126 | NC 2018 | SHS | Region II | Isabela | 300526 | Dinapigue National High School | DINAPIGUE | 4 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 1 | 5258529.16 |  |  | Completed | 1
35127 | NC 2018 | TVL | Region II | Isabela | 300526 | Dinapigue National High School | DINAPIGUE | 4 |  | 2 | 2STY4CL (2 SCI LAB) | BATCH 1 | 9855591.32 |  |  | Completed | 1
35128 | NC 2018 | TVL | Region II | Isabela | 300526 | Dinapigue National High School | DINAPIGUE | 4 |  | 2 | 2STY4CL (2 ICT LAB) | BATCH 1 | 9724552.26 |  |  | Completed | 1
35129 | NC 2018 | K10 | Region II | Isabela | 103284 | Benguet Elementary School | ECHAGUE | 6 | 1 | 2 | 1STY2CL W/ TOILET (KINDER) | BATCH 1 | 2811111.4 |  |  | Completed | 1
35130 | NC 2018 | K10 | Region II | Isabela | 103307 | Babaran Elementary School | ECHAGUE | 6 | 1 | 2 | 1STY2CL W/ TOILET (KINDER) | BATCH 1 | 2738254.17 |  |  | Completed | 1
35131 | NC 2018 | TVL | Region II | Isabela | 300529 | Don Mariano Marcos National High School | ECHAGUE | 6 | 1 | 1 | 1STY2CL (REG WORKSHOP) | BATCH 1 | 2878804.24 |  |  | Completed | 1
35132 | NC 2018 | TVL | Region II | Isabela | 300529 | Don Mariano Marcos National High School | ECHAGUE | 6 |  | 2 | 2STY4CL (2 ICT LAB) | BATCH 1 | 10136029.55 |  |  | Completed | 1
35133 | NC 2018 | TVL | Region II | Isabela | 300529 | Don Mariano Marcos National High School | ECHAGUE | 6 |  | 2 | 2STY4CL (2 SCI LAB) | BATCH 1 | 10481934.83 |  |  | Completed | 1
35134 | NC 2018 | TVL | Region II | Isabela | 300533 | Dona Magdalena H. Gaffud HIgh School | ECHAGUE | 6 | 1 | 2 | 2STY4CL (ICT & SCI LAB) | BATCH 1 | 9586071.53 |  |  | Completed | 1
35135 | NC 2018 | TVL | Region II | Isabela | 300533 | Dona Magdalena H. Gaffud HIgh School | ECHAGUE | 6 |  | 2 | 2STY4CL (2STY REG WORKSHOP) | BATCH 1 | 9227002.9 |  |  | Completed | 1
35136 | NC 2018 | TVL | Region II | Isabela | 300539 | Highway Region National High School | ECHAGUE | 6 | 1 | 2 | 2SY4CL (2 ICT LAB) | BATCH 1 | 9520552 |  |  | Completed | 1
35137 | NC 2018 | TVL | Region II | Isabela | 300539 | Highway Region National High School | ECHAGUE | 6 |  | 2 | 2STY4CL (2 SCI LAB) | BATCH 1 | 10267068.61 |  |  | Completed | 1
35138 | NC 2018 | TVL | Region II | Isabela | 300541 | Imelda R. Marcos High School | ECHAGUE | 6 | 1 | 2 | 2STY4CL (2 ICT LAB) | BATCH 1 | 9520552 |  |  | Completed | 1
35139 | NC 2018 | TVL | Region II | Isabela | 300541 | Imelda R. Marcos High School | ECHAGUE | 6 |  | 2 | 2STY4CL (2 SCI LAB) | BATCH 1 | 9651591.06 |  |  | Completed | 1
35140 | NC 2018 | TVL | Region II | Isabela | 300566 | Pangal Sur High School | ECHAGUE | 6 | 1 | 2 | 2STY4CL (2 SCI LAB) | BATCH 1 | 9651591.06 |  |  | Completed | 1
35141 | NC 2018 | TVL | Region II | Isabela | 300566 | Pangal Sur High School | ECHAGUE | 6 |  | 1 | 1STY ICT LAB | BATCH 1 | 3025578.79 |  |  | Completed | 1
35142 | NC 2018 | TVL | Region II | Isabela | 300611 | Ugad High School | ECHAGUE | 6 | 1 | 2 | 2STY4CL (ICT & SCI LAB) | BATCH 1 | 11048551.23 |  |  | Completed | 1
35143 | NC 2018 | TVL | Region II | Isabela | 300612 | Echague National High School | ECHAGUE | 6 | 1 | 2 | 2STY4CL (2 ICT LAB) | BATCH 1 | 9520552 |  |  | Completed | 1
35144 | NC 2018 | TVL | Region II | Isabela | 300612 | Echague National High School | ECHAGUE | 6 |  | 2 | 2STY4CL (2 SCI LAB) | BATCH 1 | 9651591.06 |  |  | Completed | 1
35145 | NC 2018 | TVL | Region II | Isabela | 300524 | Dibuluan National High School | JONES | 4 | 1 | 3 | 3STY6CL ( 1 SCI LAB & 2 ICT LAB) | BATCH 1 | 15253823.09 |  |  | Completed | 1
35146 | NC 2018 | TVL | Region II | Isabela | 300555 | Jones Rural School - Main | JONES | 4 | 1 | 4 | 2STY8CL (4 REG WORKSHOP) | BATCH 1 | 17536990.54 |  |  | Completed | 1
35147 | NC 2018 | TVL | Region II | Isabela | 300555 | Jones Rural School - Main | JONES | 4 |  | 1 | UNIQUE WORKSHOP | BATCH 1 | 3170000 |  |  | Completed | 1
35148 | NC 2018 | TVL | Region II | Isabela | 300555 | Jones Rural School - Main | JONES | 4 |  | 2 | 2SY4CL (2 ICT LAB) | BATCH 1 | 9520552 |  |  | Completed | 1
35149 | NC 2018 | TVL | Region II | Isabela | 300555 | Jones Rural School - Main | JONES | 4 |  | 2 | 2STY4CL (2 SCI LAB) | BATCH 1 | 9651591.06 |  |  | Completed | 1
35150 | NC 2018 | TVL | Region II | Isabela | 300600 | Sgt. Prospero Bello HS - Main | JONES | 4 | 1 | 2 | 2STY4CL (2 ICT LAB) | BATCH 1 | 9520552 |  |  | Completed | 1
35151 | NC 2018 | TVL | Region II | Isabela | 300600 | Sgt. Prospero Bello HS - Main | JONES | 4 |  | 2 | 2STY4CL (2 REGULAR WORKSHOP) | BATCH 1 | 9227002.9 |  |  | Completed | 1
35152 | NC 2018 | TVL | Region II | Isabela | 300571 | Ramon National High School | RAMON | 4 | 1 | 2 | 2STY4CL (2 SCI LAB) | BATCH 1 | 9651591.06 |  |  | Completed | 1
35153 | NC 2018 | TVL | Region II | Isabela | 300571 | Ramon National High School | RAMON | 4 |  | 1 | 1STY ICT LAB | BATCH 1 | 3025578.79 |  |  | Completed | 1
35154 | NC 2018 | TVL | Region II | Isabela | 300571 | Ramon National High School | RAMON | 4 |  | 1 | UNIQUE WORKSHOP | BATCH 1 | 3170000 |  |  | Completed | 1
35155 | NC 2018 | TVL | Region II | Isabela | 300572 | General Emilio Aguinaldo National High School | RAMON | 4 | 1 | 4 | 4STY8CL (2 SCIENCE 2 ICT LAB) | BATCH 1 | 18439908.21 |  |  | Completed | 1
35156 | NC 2018 | TVL | Region II | Isabela | 300574 | Raniag HIgh School | RAMON | 4 | 1 | 4 | 4STY8CL (2 SCI LAB & 2 ICT LAB) | BATCH 1 | 18439908.21 |  |  | Completed | 1
35157 | NC 2018 | TVL | Region II | Isabela | 306142 | San Sebastian Integrated School | RAMON | 4 | 1 | 3 | 3STY6CL (1 SCI LAB & 2 ICT) | BATCH 1 | 14667008.49 |  |  | Completed | 1
35158 | NC 2018 | TVL | Region II | Isabela | 306142 | San Sebastian Integrated School | RAMON | 4 |  | 1 | UNIQUE WORKSHOP | BATCH 1 | 3170000 |  |  | Completed | 1
35159 | NC 2018 | TVL | Region II | Isabela | 306159 | San Miguel Integrated School | RAMON | 4 | 1 | 2 | 2STY4CL (2 ICT LAB) | BATCH 1 | 9520552 |  |  | Completed | 1
35160 | NC 2018 | TVL | Region II | Isabela | 306159 | San Miguel Integrated School | RAMON | 4 |  | 3 | 3STY6CL (3 SCI LAB) | BATCH 1 | 14798047.55 |  |  | Completed | 1
35161 | NC 2018 | TVL | Region II | Isabela | 300518 | Dabubu High School - Main | SAN AGUSTIN | 4 | 1 | 4 | 2STY4CL (2 REG WORKSHOP) | BATCH 1 | 9750816.06 |  |  | Completed | 1
35162 | NC 2018 | TVL | Region II | Isabela | 300518 | Dabubu High School - Main | SAN AGUSTIN | 4 |  | 4 | 2STY4CL (2 ICT LAB ) | BATCH 1 | 10044365.16 |  |  | Completed | 1
35163 | NC 2018 | TVL | Region II | Isabela | 300591 | San Isidro National High School | SAN ISIDRO | 6 | 1 | 3 | 3STY6CL (SCI LAB, ICT & REG WORKSHOP) | BATCH 1 | 14520233.94 |  |  | Completed | 1
35164 | NC 2018 | TVL | Region II | Isabela | 300591 | San Isidro National High School | SAN ISIDRO | 6 |  | 1 | UNIQUE WORKSHOP | BATCH 1 | 3170000 |  |  | Completed | 1
35165 | NC 2018 | K10 | Region II | Isabela | 103888 | Antagan 1st ES - Sitio Magoli Annex | TUMAUINI | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4861778.28 |  |  | Completed | 1
35166 | NC 2018 | SHS | Region II | Isabela | 300603 | Santa Maria High School | SANTA MARIA | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4861778.28 |  |  | Completed | 1
35167 | NC 2018 | SHS | Region II | Isabela | 306132 | Simanu National High School | SAN PABLO | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4861778.28 |  |  | Completed | 1
35168 | NC 2018 | K10 | Region II | Isabela | 102990 | Burgos Elementary School | ALICIA | 3 | 1 | 6 | 2STY6CL | Batch 3 | 18322665.18 |  |  | Completed | 1
35169 | NC 2018 | K10 | Region II | Isabela | 103034 | LA SUERTE ELEMENTARY SCHOOL | ANGADANAN | 3 | 1 | 3 | 1STY3CL | Batch 3 | 8101430.33 |  |  | Completed | 1
35170 | NC 2018 | K10 | Region II | Isabela | 103051 | Allangigan ES | ANGADANAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | Batch 3 | 5727519.67 |  |  | Completed | 1
35171 | NC 2018 | K10 | Region II | Isabela | 300550 | La Suerte HS | ANGADANAN | 3 | 1 | 4 | 1STY4CL | Batch 3 | 10883954.96 |  |  | Completed | 1
35172 | NC 2018 | SHS | Region II | Isabela | 306127 | San Mateo National High School | SAN MATEO | 3 | 1 | 6 | 2STY6CL | Batch 3 | 18945621.88 |  |  | Completed | 1
35173 | NC 2018 | K10 | Region II | Isabela | 500017 | Fugaru Integrated School | ANGADANAN | 3 | 1 | 3 | 1STY3CL | Batch 3 | 8389990.48 |  |  | Completed | 1
35174 | NC 2018 | K10 | Region II | Isabela | 500020 | Lomboy Integrated School | ANGADANAN | 3 | 1 | 3 | 1STY3CL | Batch 3 | 8648859.19 |  |  | Completed | 1
35175 | NC 2018 | K10 | Region II | Nueva Vizcaya | 103906 | Aritao Central School | ARITAO | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 8305095.43 |  |  | Completed | 1
35176 | NC 2018 | TVL | Region II | Nueva Vizcaya | 300618 | Aritao National High School | ARITAO | 0 | 1 | 6 | 3STY 2RW, 2ICT & 2SL | BATCH 1 | 13525400.22 |  |  | Completed | 1
35177 | NC 2018 | TVL | Region II | Nueva Vizcaya | 300647 | Sta. Clara HS | ARITAO | 0 | 1 | 6 | 3STY 2RW, 2ICT & 2SL | BATCH 1 | 25634097.14 |  |  | Completed | 1
35178 | NC 2018 | TVL | Region II | Nueva Vizcaya | 300622 | Belance HS | DUPAX DEL NORTE | 0 | 1 | 6 | 2STY 2ICT, 2SL & 2RW | BATCH 1 | 19544786.47 |  |  | Completed | 1
35179 | NC 2018 | TVL | Region II | Nueva Vizcaya | 300635 | LAMO NATIONAL HIGH SCHOOL | DUPAX DEL NORTE | 0 | 1 | 6 | 3STY 2RW, 2ICT & 2SL | BATCH 1 | 25401311.97 |  |  | Completed | 1
35180 | NC 2018 | TVL | Region II | Nueva Vizcaya | 300637 | Munguia NHS | DUPAX DEL NORTE | 0 | 1 | 7 | 3STY 2CL, 2ICT, 2SL & 1RW | BATCH 1 | 26338874.27 |  |  | Completed | 1
35181 | NC 2018 | TVL | Region II | Nueva Vizcaya | 306206 | DUPAX DEL NORTE NATIONAL HIGH SCHOOL | DUPAX DEL NORTE | 0 | 1 | 7 | 3STY 2CL, 2 ICT, 2SL & 1RW | BATCH 1 | 26935782.68 |  |  | Completed | 1
35182 | NC 2018 | TVL | Region II | Nueva Vizcaya | 300625 | Carolotan High School | DUPAX DEL SUR | 0 | 1 | 4 | 2STY 2ICT & 2SL | BATCH 1 | 14882784.95 |  |  | Completed | 1
35183 | NC 2018 | TVL | Region II | Nueva Vizcaya | 300628 | Dupax del Sur NHS | DUPAX DEL SUR | 0 | 1 | 6 | 2STY 4CL, 1ICT, 1SL | BATCH 1 | 14926617.3 |  |  | Completed | 1
35184 | NC 2018 | TVL | Region II | Nueva Vizcaya | 300628 | Dupax del Sur NHS | DUPAX DEL SUR | 0 |  | 3 | 2STY 1RW, 1ICT & 1SL | BATCH 1 | 14837821.07 |  |  | Completed | 1
35185 | NC 2018 | TVL | Region II | Nueva Vizcaya | 300629 | Ganao National HS | DUPAX DEL SUR | 0 | 1 | 4 | 2STY 2ICT & 2SL | BATCH 1 | 15186661.27 |  |  | Completed | 1
35186 | NC 2018 | K10 | Region II | Nueva Vizcaya | 104075 | Antutot E/S | KASIBU | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 8432192.37 |  |  | Completed | 1
35187 | NC 2018 | K10 | Region II | Nueva Vizcaya | 104098 | Papalungan ES | KASIBU | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 8529956.68 |  |  | Completed | 1
35188 | NC 2018 | TVL | Region II | Nueva Vizcaya | 300631 | Kasibu National Agricultural School | KASIBU | 0 | 1 | 7 | 2STY 2CL & 5RW | BATCH 1 | 19414430.05 |  |  | Completed | 1
35189 | NC 2018 | TVL | Region II | Nueva Vizcaya | 300631 | Kasibu National Agricultural School | KASIBU | 0 |  | 5 | 2STY 2ICT & 2SL | BATCH 1 | 14986222.92 |  |  | Completed | 1
35190 | NC 2018 | TVL | Region II | Nueva Vizcaya | 300634 | Kongkong Valley NHS | KASIBU | 0 | 1 | 4 | 2STY 2SL & 2ICT | BATCH 1 | 14968705.47 |  |  | Completed | 1
35191 | NC 2018 | TVL | Region II | Nueva Vizcaya | 300634 | Kongkong Valley NHS | KASIBU | 0 |  | 5 | 2STY 3RW & 2CL | BATCH 1 | 14813160.16 |  |  | Completed | 1
35192 | NC 2018 | TVL | Region II | Nueva Vizcaya | 300636 | Malabing Valley NHS-INTEGRATED SENIOR HIGH SCHOOL | KASIBU | 0 | 1 | 6 | 3STY 2RW, 2ICT & 2SL | BATCH 1 | 26362861.64 |  |  | Completed | 1
35193 | NC 2018 | K10 | Region II | Nueva Vizcaya | 104130 | Luclocos PS | KAYAPA | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 8520925.77 |  |  | Completed | 1
35194 | NC 2018 | K10 | Region II | Nueva Vizcaya | 104142 | San Fabian ES | KAYAPA | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 8547913.9 |  |  | Completed | 1
35195 | NC 2018 | TVL | Region II | Nueva Vizcaya | 300633 | Martinez Cuyangan National High School | KAYAPA | 0 | 1 | 4 | 2STY 2ICT & 2SL | BATCH 1 | 15304807.1 |  |  | Completed | 1
35196 | NC 2018 | TVL | Region II | Nueva Vizcaya | 300639 | Nansiakan NHS | KAYAPA | 0 | 1 | 7 | 2STY 2CL, 1RW, 2ICT & 2SL | BATCH 1 | 19797592.69 |  |  | Completed | 1
35197 | NC 2018 | TVL | Region II | Nueva Vizcaya | 300648 | Sta. Cruz Pingkian High School | KAYAPA | 0 | 1 | 5 | 3STY 2ICT, 2SL & 2RW | BATCH 1 | 25704611.57 |  |  | Completed | 1
35198 | NC 2018 | TVL | Region II | Nueva Vizcaya | 500024 | Napo-Tuyak National High School | KAYAPA | 0 | 1 | 2 | 2STY 1ICT & 1SL | BATCH 1 | 8602711.18 |  |  | Completed | 1
35199 | NC 2018 | TVL | Region II | Nueva Vizcaya | 500096 | Binalian Integrated National High School | KAYAPA | 0 | 1 | 4 | 2STY 2ICT & 2SL | BATCH 1 | 15624380.6 |  |  | Completed | 1
35200 | NC 2018 | SHS | Region II | Nueva Vizcaya | 300644 | Quezon NHS | QUEZON | 0 | 1 | 8 | 4STY8CL | BATCH 1 | 37100000 |  |  | Completed | 1
35201 | NC 2018 | TVL | Region II | Nueva Vizcaya | 300649 | Santa Fe National High School | SANTA FE | 0 | 1 | 6 | 3STY 6RW | BATCH 1 | 25385268.91 |  |  | Completed | 1
35202 | NC 2018 | TVL | Region II | Nueva Vizcaya | 300649 | Santa Fe National High School | SANTA FE | 0 |  | 7 | 3STY 2CL, 2ICT, 2SL & 1RW | BATCH 1 | 25719815.79 |  |  | Completed | 1
35203 | NC 2018 | TVL | Region II | Nueva Vizcaya | 306205 | Canabuan National High School | SANTA FE | 0 | 1 | 4 | 2STY 2ICT & 2SL | BATCH 1 | 14938476.85 |  |  | Completed | 1
35204 | NC 2018 | TVL | Region II | Quirino | 300652 | Aglipay NHS | AGLIPAY | 0 | 1 | 1 | Unique Workshop (7x22.5m) | BATCH 1 | 5028736.54 |  |  | Completed | 1
35205 | NC 2018 | TVL | Region II | Quirino | 300656 | Cabarroguis NSAT | CABARROGUIS (Capital) | 0 | 1 | 1 | Unique Workshop (7x22.5m) | BATCH 1 | 5048503.8 |  |  | Completed | 1
35206 | NC 2018 | TVL | Region II | Quirino | 300656 | Cabarroguis NSAT | CABARROGUIS (Capital) | 0 |  | 1 | Unique Workshop (7x22.5m) | BATCH 1 | 5048503.8 |  |  | Completed | 1
35207 | NC 2018 | K10 | Region II | Quirino | 104232 | Nagabgaban IS | AGLIPAY | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5661601.38 |  |  | Completed | 1
35208 | NC 2018 | K10 | Region II | Quirino | 104266 | San Marcos ES | CABARROGUIS (Capital) | 0 | 1 | 3 | 1STY3CL | Batch 3 | 7885648.44 |  |  | Completed | 1
35209 | NC 2018 | K10 | Region II | Quirino | 104273 | Villarose IS | CABARROGUIS (Capital) | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5635277.75 |  |  | Completed | 1
35210 | NC 2018 | K10 | Region II | Quirino | 104278 | Der-An ES | DIFFUN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5781556.28 |  |  | Completed | 1
35211 | NC 2018 | K10 | Region II | Quirino | 104280 | Diffun CS - Integrated SPED Center | DIFFUN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5687065.11 |  |  | Completed | 1
35212 | NC 2018 | K10 | Region II | Quirino | 104282 | Guribang PS | DIFFUN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5713563.17 |  |  | Completed | 1
35213 | NC 2018 | K10 | Region II | Quirino | 104283 | Isidro Paredes ES | DIFFUN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5734801.9 |  |  | Completed | 1
35214 | NC 2018 | K10 | Region II | Quirino | 104288 | Upper Gabriela ES | DIFFUN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5840570.61 |  |  | Completed | 1
35215 | NC 2018 | K10 | Region II | Quirino | 104302 | Dumanisi ES | DIFFUN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5823617.21 |  |  | Completed | 1
35216 | NC 2018 | K10 | Region II | Quirino | 104362 | Mataddi ES | NAGTIPUNAN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5683014.55 |  |  | Completed | 1
35217 | NC 2018 | K10 | Region II | Quirino | 104375 | La Paz ES | SAGUDAY | 0 | 1 | 4 | 1STY4CL | Batch 3 | 9924762.15 |  |  | Completed | 1
35218 | NC 2018 | K10 | Region II | Quirino | 156502 | VILLA FLOR E/S | MADDELA | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5648871.74 |  |  | Completed | 1
35219 | NC 2018 | K10 | Region II | Quirino | 300655 | Burgos NHS | CABARROGUIS (Capital) | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5637672.61 |  |  | Completed | 1
35220 | NC 2018 | SHS | Region II | Quirino | 500106 | Giayan IS | NAGTIPUNAN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5683014.55 |  |  | Completed | 1
35221 | NC 2018 | K10 | Region II | Quirino | 500109 | Ifugao Village IS | DIFFUN | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5889515.59 |  |  | Completed | 1
35222 | NC 2018 | K10 | Region II | Quirino | 500872 | Cabarroguis CS - Integrated SPED Center | CABARROGUIS (Capital) | 0 | 1 | 2 | 1STY2CL | Batch 3 | 5611405.79 |  |  | Completed | 1
35223 | NC 2018 | K10 | Region II | Santiago City | 103817 | Nabbuan ES | CITY OF SANTIAGO | 4 | 1 | 2 | 1STY2CL | BATCH 1 | 2738254.17 |  |  | Completed | 1
35224 | NC 2018 | K10 | Region II | Santiago City | 103827 | Dubinan ES | CITY OF SANTIAGO | 4 | 1 | 2 | 1STY2CL | BATCH 1 | 2738254.17 |  |  | Completed | 1
35225 | NC 2018 | K10 | Region II | Santiago City | 103833 | Villa Gonzaga ES | CITY OF SANTIAGO | 4 | 1 | 2 | 1STY2CL | BATCH 1 | 2738254.17 |  |  | Completed | 1
35226 | NC 2018 | TVL | Region II | Santiago City | 300505 | Cabulay High School | CITY OF SANTIAGO | 4 | 1 | 8 | 2STY 1 SCI LAB, 2 SHS CL, 1 ICT, 2 SHS CL | BATCH 1 | 16974790.26 |  |  | Completed | 1
35227 | NC 2018 | TVL | Region II | Santiago City | 300505 | Cabulay High School | CITY OF SANTIAGO | 4 |  | 4 | 2STY 1 SCI LAB, 1 ICT | BATCH 1 | 9227002.9 |  |  | Completed | 1
35228 | NC 2018 | SHS | Region II | Santiago City | 300528 | Divisoria High School | CITY OF SANTIAGO | 4 | 1 | 2 | 1STY2CL | BATCH 1 | 2738254.17 |  |  | Completed | 1
35229 | NC 2018 | TVL | Region II | Santiago City | 300528 | Divisoria High School | CITY OF SANTIAGO | 4 |  | 8 | 2STY 2 SCI LAB, 2 ICT | BATCH 1 | 17024790.26 |  |  | Completed | 1
35230 | NC 2018 | TVL | Region II | Santiago City | 300578 | Rizal National High School | CITY OF SANTIAGO | 4 | 1 | 12 | 3STY 2 SCI LAB, 2 WORKSHOP, 2 ICT LAB | BATCH 1 | 29359267.25 |  |  | Completed | 1
35231 | NC 2018 | TVL | Region II | Santiago City | 300578 | Rizal National High School | CITY OF SANTIAGO | 4 |  | 1 | UNIQUE WORKSHOP (7X22.5M) | BATCH 1 | 3170000 |  |  | Completed | 1
35232 | NC 2018 | TVL | Region II | Santiago City | 300599 | Santiago City National High School | CITY OF SANTIAGO | 4 | 1 | 8 | 4STY 4 REG. WORKSHOP | BATCH 1 | 17209570.67 |  |  | Completed | 1
35233 | NC 2018 | TVL | Region II | Santiago City | 300599 | Santiago City National High School | CITY OF SANTIAGO | 4 |  | 8 | 4STY 2 SCI LAB, 2ICT LAB | BATCH 1 | 17309570.67 |  |  | Completed | 1
35234 | NC 2018 | TVL | Region II | Santiago City | 325201 | Santiago City National High School - Sinsayon | CITY OF SANTIAGO | 4 | 1 | 8 | 2STY 2 SCI LAB, 2 ICT | BATCH 1 | 16974790.26 |  |  | Completed | 1
35235 | NC 2018 | SHS | Region II | Santiago City | 325202 | Santiago City National High School - Sagana | CITY OF SANTIAGO | 4 | 1 | 6 | 2STY6CL | BATCH 1 | 12623014.84 |  |  | Completed | 1
35236 | NC 2018 | SHS | Region II | Santiago City | 325202 | Santiago City National High School - Sagana | CITY OF SANTIAGO | 4 |  | 2 | 1STY2CL | BATCH 1 | 2738254.17 |  |  | Completed | 1
35237 | NC 2018 | TVL | Region II | Santiago City | 325202 | Santiago City National High School - Sagana | CITY OF SANTIAGO | 4 |  | 4 | 2STY 2 SCI LAB | BATCH 1 | 9227002.9 |  |  | Completed | 1
35238 | NC 2018 | TVL | Region II | Santiago City | 325202 | Santiago City National High School - Sagana | CITY OF SANTIAGO | 4 |  | 4 | 2STY 2 ICT LAB | BATCH 1 | 9227002.9 |  |  | Completed | 1
35239 | NC 2018 | SHS | Region II | Santiago City | 325203 | Santiago City National High School - Rosario Extension | CITY OF SANTIAGO | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8945902.76 |  |  | Completed | 1
35240 | NC 2018 | K10 | Region II | Tuguegarao City | 104382 | Tuguegarao Northeast CS | TUGUEGARAO CITY(Capital) | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 11376288.71 |  |  | Completed | 1
35241 | NC 2018 | K10 | Region II | Tuguegarao City | 104393 | Annafunan ES | TUGUEGARAO CITY(Capital) | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 11376288.71 |  |  | Completed | 1
35242 | NC 2018 | TVL | Region II | Tuguegarao City | 300668 | Cagayan National High Sschool | TUGUEGARAO CITY(Capital) | 3 | 1 | 8 | 4 STY 16 CL: (2 CL Science Lab., 2 CL ICT Lab., & 4 CL Regular bldg.) | BATCH 1 | 35334998.04 |  |  | Completed | 1
35243 | NC 2018 | TVL | Region II | Tuguegarao City | 300670 | Linao National High School | TUGUEGARAO CITY(Capital) | 3 | 1 | 4 | 4 STY 8 CL: (2 CL Science Lab. & 2 CL Regular Workshop Bldg.) | BATCH 1 | 20084082.28 |  |  | Completed | 1
35244 | NC 2018 | TVL | Region II | Tuguegarao City | 300671 | Gosi National High School | TUGUEGARAO CITY(Capital) | 3 | 1 | 4 | 2 STY 8 CL: (2 CL Science Lab. & 2 CL ICT Lab. bldg.) | BATCH 1 | 15942844 |  |  | Completed | 1
35245 | NC 2018 | TVL | Region II | Tuguegarao City | 306401 | Tuguegarao City Science High School | TUGUEGARAO CITY(Capital) | 3 | 1 | 4 | 2 STY 8 CL: (2 CL Science Lab. & 2 CL ICT Lab. Bldg.) | BATCH 1 | 15862844 |  |  | Completed | 1
39360 | NC 2019 | SHS | Region II | Batanes | 300415 | Ivana NHS | IVANA | 0 | 1 | 2 | 1STY2CL |  | 9563320.0284 |  | completed | 1 | [10 empty] | Completed on June 30, 2021; Turn-Over Paper duly concurred by DepEd not yet signed (Document received by the end-user on July 27, 2020) | 0
39361 | NC 2019 | K10 | Region II | Cagayan | 102766 | Malinta ES | LASAM | 2 | 1 | 2 | 1STY2CL |  | 5147025.5752 |  | completed | 1 | [11 empty] | 0
39362 | NC 2019 | K10 | Region II | Cagayan | 102352 | Sta. Rosa Elementary School | ABULUG | 2 | 1 | 2 | 1STY2CL |  | 4100860.3745 |  | completed | 1 | [11 empty] | 0
39363 | NC 2019 | K10 | Region II | Cauayan City | 103241 | Sillawit ES | CITY OF CAUAYAN | 3 | 1 | 2 | 1STY2CL W/ TOILET |  | 5471868.1866 |  | completed | 1 | [11 empty] | 0
39364 | NC 2019 | K10 | Region II | City of Ilagan | 103393 | Cabeceria 3 Elementary School | ILAGAN CITY (CAPITAL) | 1 | 1 | 2 | 1STY2CL W/ TOILET |  | 4692585.0872 |  | completed | 1 | [11 empty] | 0
39365 | NC 2019 | K10 | Region II | Isabela | 103888 | Antagan 1st ES - Sitio Magoli Annex | TUMAUINI | 1 | 1 | 3 | 1STY3CL W/ TOILET |  | 6345794.7847 |  | completed | 1 | [11 empty] | 0
39366 | NC 2019 | K10 | Region II | Isabela |  | SANTA ES - SITIO MINABANG ANNEX | TUMAUINI | 1 | 1 | 2 | 1STY2CL W/ TOILET |  | 4300378.7566 |  | completed | 1 | [11 empty] | 0
39367 | NC 2019 | K10 | Region II | Isabela | 103098 | Andabuen Elementary School - Main | BENITO SOLIVEN | 2 | 1 | 3 | 1STY3CL W/ TOILET |  | 6753370.6333 |  | completed | 1 | [11 empty] | 0
39368 | NC 2019 | SHS | Region II | Isabela | 300580 | Lanting Region National High School | ROXAS | 2 | 1 | 10 | 2STY10CL |  | 20085370.5158 |  | completed | 1 | [11 empty] | 0
39369 | NC 2019 | SHS | Region II | Isabela | 300562 | Munoz High School | ROXAS | 2 | 1 | 10 | 2STY10CL |  | 20085370.5158 |  | completed | 1 | [11 empty] | 0
39370 | NC 2019 | K10 | Region II | Isabela | 103636 | Roxas Central School | ROXAS | 2 | 1 | 10 | 2STY10CL |  | 20085370.5158 |  | completed | 1 | [11 empty] | 0
39371 | NC 2019 | SHS | Region II | Isabela | 300579 | Roxas National High School | ROXAS | 2 | 1 | 10 | 2STY10CL |  | 20085370.5158 |  | completed | 1 | [11 empty] | 0
39372 | NC 2019 | K10 | Region II | Isabela | 103643 | Roxas West Central School | ROXAS | 2 | 1 | 10 | 2STY10CL |  | 20085370.5158 |  | completed | 1 | [11 empty] | 0
39373 | NC 2019 | K10 | Region II | Isabela | 103648 | Sinamar Elementary School | ROXAS | 2 | 1 | 3 | 1STY3CL W/ TOILET |  | 6774472.2357 |  | completed | 1 | [11 empty] | 0
39374 | NC 2019 | K10 | Region II | Isabela | 102990 | Burgos Elementary School | ALICIA | 3 | 1 | 2 | 1STY2CL |  | 5932062.3529 |  | completed | 1 | [11 empty] | 0
39375 | NC 2019 | K10 | Region II | Isabela | 103174 | Namnama Elementary School | CABATUAN | 3 | 1 | 2 | 1STY2CL |  | 5932062.3529 |  | completed | 1 | [11 empty] | 0
39376 | NC 2019 | K10 | Region II | Nueva Vizcaya | 104166 | Bascaran ES | SOLANO | 0 | 1 | 2 | 1STY2CL |  | 5233050 |  | Completed | 1 | [10 empty] | Project did not statst due to the late release of Permit to Demolish | 0
39377 | NC 2019 | K10 | Region II | Nueva Vizcaya | 104021 | DIADI CENTRAL SCHOOL | DIADI | 0 | 1 | 2 | 1STY2CL |  | 5333300 |  | Completed | 1 | [11 empty] | 0
39378 | NC 2019 | K10 | Region II | Nueva Vizcaya | 300525 | Tiblac High School | AMBAGUIO | 0 | 1 | 2 | 1STY2CL |  | 5513750 |  | Completed | 1 | [10 empty] | Location of school building is re-positioned to adapt orientation in the Site Development Plan | 0
39379 | NC 2019 | K10 | Region II | Quirino | 156517 | Agta Community P/S | MADDELA | 0 | 1 | 2 | 1STY2CL W/ TOILET |  | 6873140 |  | completed | 1 |  |  |  | 19BK0101 |  |  | 2019-10-01 | 2019-10-11 | 2019-10-16 |  |  | 0
39380 | NC 2019 | K10 | Region II | Santiago City | 103839 | San Jose ES | CITY OF SANTIAGO | 4 | 1 | 2 | 1STY2CL W/ TOILET |  | 4417965.4101 |  | completed | 1 | [11 empty] | 0
39381 | NC 2019 | K10 | Region II | Tuguegarao City | 104397 | Carig Norte Elementary School | TUGUEGARAO CITY(Capital) | 3 | 1 | 2 | 1STY2CL W/ TOILET |  | 4035321.3756 |  | completed | 1 | [11 empty] | 0
40075 | NC 2020 | SHS | Region II | Batanes | 500063 | Raele Integrated School | ITBAYAT | 0 | 1 | 4 | 2STY4CL |  | 21476659.29 |  |  | Completed | 1
40076 | NC 2020 | K10 | Region II | Cagayan | 102443 | Dodan ES | APARRI | 1 | 1 | 3 | 1STY3CL |  | 7611539.27 |  |  | Completed | 1
40077 | NC 2020 | K10 | Region II | Cagayan | 102443 | Dodan ES | APARRI | 1 |  | 2 | 1STY2CL |  | 5737041.68 |  |  | Completed | 1
40078 | NC 2020 | K10 | Region II | Cagayan | 102507 | Adaoag ES | BAGGAO | 1 | 1 | 2 | 1STY2CL |  | 5938545.18 |  |  | Completed | 1
40079 | NC 2020 | TVL | Region II | Cagayan | 300471 | Aparri East National High School | APARRI | 1 | 1 | 2 | 1STY4CL (1 SCI LAB, 1 ICT LAB) |  | 10155402.19 |  |  | Completed | 1
40080 | NC 2020 | K10 | Region II | Cagayan | 102331 | Abulug CES (Bldg 1) | ABULUG | 2 | 1 | 3 | 1STY3CL |  | 6197709.38 |  |  | Completed | 1
40081 | NC 2020 | K10 | Region II | Cagayan | 102334 | Banguian ES | ABULUG | 2 | 1 | 2 | 1STY2CL |  | 4631841.03 |  |  | Completed | 1
40082 | NC 2020 | K10 | Region II | Cagayan | 102337 | Canayun ES (Bldg 1) | ABULUG | 2 | 1 | 3 | 1STY3CL |  | 6197709.38 |  |  | Completed | 1
40083 | NC 2020 | K10 | Region II | Cagayan | 102338 | Dana-ili ES | ABULUG | 2 | 1 | 2 | 1STY2CL |  | 4671941.03 |  |  | Completed | 1
40084 | NC 2020 | K10 | Region II | Cagayan | 102340 | Guiddam ES | ABULUG | 2 | 1 | 2 | 1STY2CL |  | 4500471.12 |  |  | Completed | 1
40085 | NC 2020 | K10 | Region II | Cagayan | 102343 | Macugay ES | ABULUG | 2 | 1 | 2 | 1STY2CL |  | 4460371.12 |  |  | Completed | 1
40086 | NC 2020 | K10 | Region II | Cagayan | 102351 | Sta. Filomena ES | ABULUG | 2 | 1 | 2 | 1STY2CL |  | 4702016.03 |  |  | Completed | 1
40087 | NC 2020 | K10 | Region II | Cagayan | 102390 | Kapanickian Norte ES | ALLACAPAN | 2 | 1 | 3 | 1STY3CL |  | 6428362.02 |  |  | Completed | 1
40088 | NC 2020 | K10 | Region II | Cagayan | 102543 | Fugu ES | BALLESTEROS | 2 | 1 | 6 | 2UNITS OF 1STY3CL |  | 13181548.39 |  |  | Completed | 1
40089 | NC 2020 | K10 | Region II | Cagayan | 102826 | Minanga ES | PIAT | 2 | 1 | 2 | 1STY2CL |  | 2620280.28 |  |  | Completed | 1
40090 | NC 2020 | K10 | Region II | Cagayan | 102827 | Piat CS | PIAT | 2 | 1 | 2 | 1STY2CL |  | 7525348.44 |  |  | Completed | 1
40091 | NC 2020 | K10 | Region II | Cagayan | 102829 | Sto. Domingo ES | PIAT | 2 | 1 | 4 | 1STY4CL |  | 4905068.16 |  |  | Completed | 1
40092 | NC 2020 | K10 | Region II | Cagayan | 102831 | Warat ES | PIAT | 2 | 1 | 2 | 1STY2CL |  | 2620280.28 |  |  | Completed | 1
40093 | NC 2020 | SHS | Region II | Cagayan | 300418 | Abulug National Rural and Vocational High School | ABULUG | 2 | 1 | 4 | 2 Sty, 2 CL, 2 Lab |  | 22055000 |  |  | Completed | 1
40094 | NC 2020 | SHS | Region II | Cagayan | 300481 | Piat National HS | PIAT | 2 | 1 | 4 | 2STY4CL |  | 16623456.77 |  |  | Completed | 1
40095 | NC 2020 | K10 | Region II | Cagayan | 102625 | Alibago ES | ENRILE | 3 | 1 | 6 | 2STY6CL |  | 14548948.87 |  |  | Completed | 1
40096 | NC 2020 | K10 | Region II | Cagayan | 102629 | Lemu Elementary School | ENRILE | 3 | 1 | 6 | 2STY6CL |  | 15021640.01 |  |  | Completed | 1
40097 | NC 2020 | K10 | Region II | Cagayan | 102718 | Manaoag ES | IGUIG | 3 | 1 | 6 | 2STY6CL |  | 14248198.87 |  |  | Completed | 1
40098 | NC 2020 | K10 | Region II | Cagayan | 102870 | Dassun ES | SOLANA | 3 | 1 | 6 | 2STY6CL |  | 14548948.87 |  |  | Completed | 1
40099 | NC 2020 | SHS | Region II | Cagayan | 300425 | AMULUNG NATIONAL HIGH SCHOOL | AMULUNG | 3 | 1 | 6 | 2STY6CL |  | 14448698.87 |  |  | Completed | 1
40100 | NC 2020 | K10 | Region II | Cauayan City | 103186 | Cauayan East CS - Main | CITY OF CAUAYAN | 6 | 1 | 3 | 1STY3CL & 1STY2CL |  | 14178500.67 |  |  | Completed | 1
40101 | NC 2020 | K10 | Region II | Cauayan City | 103211 | Cauayan North CS | CITY OF CAUAYAN | 6 | 1 | 4 | 1STY4CL |  | 8484119.83 |  |  | Completed | 1
40102 | NC 2020 | TVL | Region II | Cauayan City | 300516 | Cauayan City NHS | CITY OF CAUAYAN | 6 | 1 | 1 | TVL WORKSHOP |  | 6317969.82 |  |  | Completed | 1
40103 | NC 2020 | K10 | Region II | City of Ilagan | 103432 | San Felipe ES | ILAGAN (CAPITAL) | 1 | 1 | 6 | 2STY6CL |  | 14603091.19 |  |  | completed | 1
40104 | NC 2020 | K10 | Region II | Isabela | 103147 | Cansan ES | Cabagan | 1 | 1 | 4 | 2STY4CL |  | 12289813.12 |  |  | Completed | 1
40105 | NC 2020 | K10 | Region II | Isabela | 103161 | San Juan ES | Cabagan | 1 | 1 | 3 | 1STY3CL |  | 6089713.28 |  |  | Completed | 1
40106 | NC 2020 | K10 | Region II | Isabela | 103740 | Old San Mariano Elementary School | SAN MARIANO | 2 | 1 | 2 | 1STY2CL |  | 6003833.86 |  |  | Completed | 1
40107 | NC 2020 | SHS | Region II | Isabela | 300595 | Ueg National High School | SAN MARIANO | 2 | 1 | 4 | 1STY4CL |  | 10815631.68 |  |  | Completed | 1
40108 | NC 2020 | K10 | Region II | Isabela | 103166 | Cabatuan West CS | Cabatuan | 3 | 1 | 2 | 1STY2CL w/ Toilet |  | 6091713.77 |  |  | Completed | 1
40109 | NC 2020 | K10 | Region II | Isabela | 103770 | Daramuangan Norte Elem. School | San Mateo | 3 | 1 | 2 | 1 sty 2 - Academic CL |  | 5912663.49 |  |  | Completed | 1
40110 | NC 2020 | K10 | Region II | Isabela | 103770 | Daramuangan Norte Elem. School | San Mateo | 3 |  | 3 | 1 sty 3 - Academic CL |  | 8013324.3 |  |  | Completed | 1
40111 | NC 2020 | K10 | Region II | ISABELA | 103248 | Cordon South CS Annex | CORDON | 4 | 1 | 3 | 1STY3CL w/ Toilet |  | 6563591.38 |  |  | Completed | 1
40112 | NC 2020 | K10 | Region II | ISABELA | 103260 | Villa Miemban ES | CORDON | 4 | 1 | 2 | 1STY2CL w/ Toilet |  | 4442560.92 |  |  | Completed | 1
40113 | NC 2020 | K10 | Region II | Isabela | 103443 | Dicamay I Elementary School | JONES | 4 | 1 | 4 | 1STY4CL W/ TOILET |  | 8484121.83 |  |  | Completed | 1
40114 | NC 2020 | K10 | Region II | Isabela | 103456 | Sto. Domingo ES - Annex (LSB) | JONES | 4 | 1 | 3 | 1STY3CL W/ TOILET |  | 6363091.38 |  |  | Completed | 1
40115 | NC 2020 | K10 | Region II | Isabela | 103537 | Bucal Sur Elementary School | DINAPIGUE | 4 | 1 | 2 | 1STY2CL W/ TOILET |  | 4242060.92 |  |  | Completed | 1
40116 | NC 2020 | K10 | Region II | Isabela | 103671 | Virgonesa Elementary School | SAN AGUSTIN | 4 | 1 | 3 | 1STY3CL W/ TOILET |  | 6363091.38 |  |  | Completed | 1
40117 | NC 2020 | K10 | Region II | Isabela | 103073 | Bagnos Elementary School | AURORA | 5 | 1 | 3 | 1STY3CL w/ Toilet |  | 6793404.3 |  |  | Completed | 1
40118 | NC 2020 | K10 | Region II | Isabela | 103633 | Lucban Masigun Elementary School | ROXAS | 5 | 1 | 6 | 2STY6CL |  | 19662626.39 |  |  | Completed | 1
40119 | NC 2020 | K10 | Region II | Isabela | 103637 | San Jose Elementary School | ROXAS | 5 | 1 | 6 | 2STY6CL |  | 19662626.39 |  |  | Completed | 1
40120 | NC 2020 | K10 | Region II | Isabela | 103638 | San Pedro-Villa Concepcion Elementary School | ROXAS | 5 | 1 | 6 | 2STY6CL |  | 19662626.39 |  |  | Completed | 1
40121 | NC 2020 | K10 | Region II | Isabela | 103648 | Sinamar ES | ROXAS | 5 | 1 | 2 | 1STY2CL w/ Toilet |  | 4508337.47 |  |  | Completed | 1
40122 | NC 2020 | K10 | Region II | Isabela | 103692 | San Mariano Sur Prim. School | San Guillermo | 6 | 1 | 2 | 1STY2CL w/ Toilet |  | 4993935.92 |  |  | Completed | 1
40123 | NC 2020 | SHS | Region II | Nueva Vizcaya | 300627 | Diadi NHS | DIADI | 0 | 1 | 8 | 4STY8CL |  | 22556250 |  |  | Completed | 1
40124 | NC 2020 | K10 | Region II | Quirino | 104238 | Aglipay East CS | Aglipay | 0 | 1 | 6 | 2UNITS OF 1STY3CL |  | 15845823.65 |  |  | Completed | 1
40125 | NC 2020 | SHS | Region II | Santiago City | 306124 | Patul National High School | City of Santiago | 4 | 1 | 4 | 2STY4CL |  | 12211919.2 |  |  | Completed | 1
40126 | NC 2020 | K10 | Region II | Santiago City | 325204 | Divisoria High School - Naggasican Extension | CITY OF SANTIAGO | 4 | 1 | 4 | 2STY4CL |  | 13018903.99 |  |  | Completed | 1
40127 | NC 2020 | K10 | Region II | Santiago City | 500936 | Balintocatoc Integrated School | CITY OF SANTIAGO | 4 | 1 | 7 | 1STY7CL W/ TOILET |  | 15198088.21 |  |  | Completed | 1
40128 | NC 2020 | K10 | Region II | Tuguegarao City | 104383 | Capatan ES | TUGUEGARAO CITY(Capital) | 3 | 1 | 8 | 2STY8CL |  | 18399614.17 |  |  | Completed | 1
40129 | NC 2020 | K10 | Region II | Tuguegarao City | 104389 | Namabbalan Elementary School | TUGUEGARAO CITY(Capital) | 3 | 1 | 6 | 2STY6CL |  | 15309992.74 |  |  | Completed | 1
40130 | NC 2020 | TVL | Region II | Tuguegarao City | 300670 | Linao National High School | TUGUEGARAO CITY(Capital) | 3 | 1 | 8 | 4 STY, 8CL (2 Sci Lab, 2,ICT Lab and 4 Reg. CL) |  | 30225375 |  |  | Completed | 1
40131 | NC 2020 | TVL | Region II | Tuguegarao City | 104388 | Libag Elementary School | TUGUEGARAO CITY(Capital) | 3 |  | 4 | 4 STY,4 CL ( 2 Unique workshop and 2 Reg. workshop) |  | 15187875 |  |  | Completed | 1
40828 | NC 2021 | K10 | Region II | Cagayan | 102450 | San Antonio ES | APARRI | 1 | 1 | 2 | Construction/Completion (1STY3CL W/ TOILET) |  | 287634.7837 | 286917.49 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40829 | NC 2021 | K10 | Region II | Cagayan | 102475 | Zinarag ES | APARRI | 1 | 1 | 5 | Construction/Completion (1STY5CL W/ TOILET) |  | 1279155.6143 | 1275965.7 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40830 | NC 2021 | K10 | Region II | Cagayan | 102477 | Agaman Sur ES | BAGGAO | 1 | 1 | 3 | Construction/Completion (1STY3CL W/ TOILET) |  | 324785.4688 | 323975.53 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40831 | NC 2021 | K10 | Region II | Cagayan | 102509 | Assassi ES | BAGGAO | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 880403.4198 | 878207.9 |  | COMPLETED | 1 | [10 empty] | substantially completed ( rectification of corrective works observed)
40832 | NC 2021 | K10 | Region II | Cagayan | 102673 | Gattaran West CS | GATTARAN | 1 | 1 | 12 | Construction/Completion (2STY12CL) |  | 2073104.5267 | 2067934.69 |  | COMPLETED | 1 | [10 empty] | substantially completed ( rectification of corrective works observed)
40833 | NC 2021 | K10 | Region II | Cagayan | 102925 | Aridowen ES | SANTA TERESITA | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 1123240.4985 | 1120439.4 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40834 | NC 2021 | K10 | Region II | Cagayan | 155001 | San Vicente ES | BAGGAO | 1 | 1 | 3 | Construction/Completion (1STY3CL W/ TOILET) |  | 467543.1731 | 466377.23 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40835 | NC 2021 | SHS | Region II | Cagayan | 300420 | Afusing NHS | ALCALA | 1 | 1 | 8 | Construction/Completion (4STY20CL (4CL, 2-SCI LAB, 2- ICT, 4-REG. WORKSHOP)) |  | 304878.3652 | 304118.07 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40836 | NC 2021 | SHS | Region II | Cagayan | 300421 | ALCALA RURAL SCHOOL | ALCALA | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 523305 | 522000 |  | COMPLETED | 1 | [10 empty] | substantially completed ( rectification of corrective works observed)
40837 | NC 2021 | SHS | Region II | Cagayan | 300421 | ALCALA RURAL SCHOOL | ALCALA | 1 |  | 1 | Construction/Completion (UNIQUE WORKSHOP (7.0mX22.50m)) |  | 382444.8578 | 381491.13 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40838 | NC 2021 | SHS | Region II | Cagayan | 300429 | Baggao National Agricultural School | BAGGAO | 1 | 1 | 6 | Construction/Completion (2STY12CL (6-REG. WORKSHOP)) |  | 2845377.0935 | 2838281.39 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40839 | NC 2021 | SHS | Region II | Cagayan | 300429 | Baggao National Agricultural School | BAGGAO | 1 |  | 4 | Construction/Completion (2STY8CL (2-SCIENCE LAB, 2- ICT LAB)) |  | 944054.0996 | 941699.85 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40840 | NC 2021 | SHS | Region II | Cagayan | 300430 | Baggao National School of Arts & Trades | BAGGAO | 1 | 1 | 6 | Construction/Completion (2STY12CL (6-REG. WORKSHOP)) |  | 2845377.0935 | 2838281.39 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40841 | NC 2021 | SHS | Region II | Cagayan | 300437 | Bukig National Agricultural and Technical School | APARRI | 1 | 1 | 4 | Construction/Completion (2STY8CL (4-REG. WORKSHOP)) |  | 843373.977 | 841270.8 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40842 | NC 2021 | SHS | Region II | Cagayan | 300437 | Bukig National Agricultural and Technical School | APARRI | 1 |  | 4 | Construction/Completion (2STY8CL (2-SCIENCE LAB, 2- ICT LAB)) |  | 944054.0996 | 941699.85 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40843 | NC 2021 | SHS | Region II | Cagayan | 300440 | Calaoagan Dackel National High School | GATTARAN | 1 | 1 | 9 | Construction/Completion (3STY9CL) |  | 4129974.1374 | 4119674.95 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40844 | NC 2021 | SHS | Region II | Cagayan | 300440 | Calaoagan Dackel National High School | GATTARAN | 1 |  | 4 | Construction/Completion (2STY8CL (2-SCIENCE LAB, 2- ICT LAB)) |  | 944054.0996 | 941699.85 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40845 | NC 2021 | SHS | Region II | Cagayan | 300447 | Casambalangan NHS | SANTA ANA | 1 | 1 | 4 | Construction/Completion (2STY8CL (2-SCIENCE LAB, 2- ICT LAB)) |  | 944054.0996 | 941699.85 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40846 | NC 2021 | SHS | Region II | Cagayan | 300474 | Licerio Antiporda Sr. NHS | BUGUEY | 1 | 1 | 10 | Construction/Completion (2STY10CL (4-REG WORKSHOP 2-ACAD RM)std bldg type) |  | 1002500 | 1000000 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40847 | NC 2021 | SHS | Region II | Cagayan | 300474 | Licerio Antiporda Sr. NHS | BUGUEY | 1 |  | 4 | Construction/Completion (2STY8CL (2-SCIENCE LAB, 2- ICT LAB)) |  | 944054.0996 | 941699.85 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40848 | NC 2021 | SHS | Region II | Cagayan | 300475 | Logac National High School | LAL-LO | 1 | 1 | 6 | Construction/Completion (2STY12CL (6-REG. WORKSHOP)) |  | 2845377.0935 | 2838281.39 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40849 | NC 2021 | SHS | Region II | Cagayan | 300475 | Logac National High School | LAL-LO | 1 |  | 4 | Construction/Completion (2STY8CL (2-SCIENCE LAB, 2- ICT LAB)) |  | 1220784.35 | 1217740 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40850 | NC 2021 | SHS | Region II | Cagayan | 300480 | Pattao NHS | BUGUEY | 1 | 1 | 6 | Construction/Completion (3STY12CL (2-REG. WORKSHOP 2-SCIENCE LAB, 2- ICT LAB)) |  | 1503750 | 1500000 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40851 | NC 2021 | SHS | Region II | Cagayan | 300483 | Gonzaga National High School | GONZAGA | 1 | 1 | 12 | Construction/Completion (3STY12CL (2-SCIENCE LAB, 2- ICT LAB)) |  | 1503750 | 1500000 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40852 | NC 2021 | SHS | Region II | Cagayan | 300488 | Sta. Ana Fishery National High School | SANTA ANA | 1 | 1 | 4 | Construction/Completion (2STY8CL (4-REG. WORKSHOP)) |  | 832470.9574 | 830394.97 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40853 | NC 2021 | SHS | Region II | Cagayan | 300488 | Sta. Ana Fishery National High School | SANTA ANA | 1 |  | 4 | Construction/Completion (2STY8CL (2-SCIENCE LAB,2- ICT LAB)) |  | 944054.0996 | 941699.85 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40854 | NC 2021 | SHS | Region II | Cagayan | 306004 | Magapit NHS | LAL-LO | 1 | 1 | 6 | Construction/Completion (3STY9CL (3-Reg. Workshop, 3-Acad Room)) |  | 4129974.1374 | 4119674.95 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40855 | NC 2021 | SHS | Region II | Cagayan | 306004 | Magapit NHS | LAL-LO | 1 |  | 8 | Construction/Completion (3STY12CL (4-Acad Room, 2-SCIENCE LAB, 2- ICT LAB)) |  | 1503750 | 1500000 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40856 | NC 2021 | SHS | Region II | Cagayan | 306013 | Luga National High School | SANTA TERESITA | 1 | 1 | 4 | Construction/Completion (2STY8CL (2-SCIENCE LAB, 2- ICT LAB)) |  | 944054.0996 | 941699.85 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40857 | NC 2021 | SHS | Region II | Cagayan | 306422 | Calaoagan Dackel National High School-Capissayan Annex | GATTARAN | 1 | 1 | 6 | Construction/Completion (2STY12CL (2-REG. WORKSHOP 2-SCIENCE LAB, 2- ICT LAB)) |  | 2958726.5605 | 2951348.19 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40858 | NC 2021 | K10 | Region II | Cagayan | 155026 | Palusao PS | SANTO NIÑO (FAIRE) | 2 | 1 | 6 | Construction/Completion (3STY6CL) |  | 1429804.9684 | 1426239.37 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40859 | NC 2021 | SHS | Region II | Cagayan | 300418 | Abulug National Rural and Vocational High School | ABULUG | 2 | 1 | 4 | Construction/Completion (2STY4 LAB) |  | 3215918.4868 | 3207898.74 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40860 | NC 2021 | SHS | Region II | Cagayan | 300419 | Abulug SOF | ABULUG | 2 | 1 | 6 | Construction/Completion (2STY 6 LAB) |  | 3320556.3191 | 3312275.63 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40861 | NC 2021 | SHS | Region II | Cagayan | 300438 | Cabatacan National High School | LASAM | 2 | 1 | 4 | Construction/Completion (2STY4 LAB) |  | 3260238.5106 | 3252108.24 |  | COMPLETED | 1 | [10 empty] | substantially completed ( rectification of corrective works observed)
40862 | NC 2021 | SHS | Region II | Cagayan | 300438 | Cabatacan National High School | LASAM | 2 |  | 4 | Construction/Completion (2STY4 LAB) |  | 3182673.2109 | 3174736.37 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40863 | NC 2021 | SHS | Region II | Cagayan | 300443 | Callao National High School | LASAM | 2 | 1 | 6 | Construction/Completion (2STY4CL, 2 LAB) |  | 3619173.9314 | 3610148.56 |  | COMPLETED | 1 | [10 empty] | substantially completed ( rectification of corrective works observed)
40864 | NC 2021 | SHS | Region II | Cagayan | 300449 | Claveria NHS | CLAVERIA | 2 | 1 | 6 | Construction/Completion (2STY 4CL, 2 LAB) |  | 5248074.257 | 5234986.79 |  | COMPLETED | 1 | [10 empty] | substantially completed ( rectification of corrective works observed)
40865 | NC 2021 | SHS | Region II | Cagayan | 300477 | Matucay National High School | ALLACAPAN | 2 | 1 | 4 | Construction/Completion (4STY4LAB (SL, ICT)) |  | 1064598.2284 | 1061943.37 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40866 | NC 2021 | SHS | Region II | Cagayan | 300479 | Pamplona National School of Fisheries | PAMPLONA | 2 | 1 | 4 | Construction/Completion (2STY 4 LAB) |  | 4359289.0751 | 4348418.03 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40867 | NC 2021 | SHS | Region II | Cagayan | 300479 | Pamplona National School of Fisheries | PAMPLONA | 2 |  | 8 | Construction/Completion (2STY 8 LAB) |  | 6243710.7811 | 6228140.43 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40868 | NC 2021 | SHS | Region II | Cagayan | 300481 | Piat National HS | PIAT | 2 | 1 | 6 | Construction/Completion (2STY4 LAB, 2CL) |  | 2648829.8407 | 2642224.28 |  | COMPLETED | 1 | [10 empty] | substantially completed ( rectification of corrective works observed)
40869 | NC 2021 | SHS | Region II | Cagayan | 300485 | Sanchez Mira NHS | SANCHEZ-MIRA | 2 | 1 | 4 | Construction/Completion (2STY SCI LAB & ICT) |  | 2641249.838 | 2634663.18 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40870 | NC 2021 | SHS | Region II | Cagayan | 300489 | Sta. Praxedes High School | SANTA PRAXEDES | 2 | 1 | 4 | Construction/Completion (2STY4 LAB (SCI LAB, ICT)) |  | 5060055.6627 | 5047437.07 |  | COMPLETED | 1 | [10 empty] | substantially completed ( rectification of corrective works observed)
40871 | NC 2021 | SHS | Region II | Cagayan | 300491 | Sto. Nino NHS | SANTO NIÑO (FAIRE) | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1690479.9908 | 1686264.33 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40872 | NC 2021 | SHS | Region II | Cagayan | 306006 | Abariongan National High School | SANTO NIÑO (FAIRE) | 2 | 1 | 4 | Construction/Completion (2STY 4 LAB) |  | 4245769.153 | 4235181.2 |  | COMPLETED | 1 | [10 empty] | requested joint inspection for validations
40873 | NC 2021 | TVL | Region II | Cagayan | 306425 | Namuccayan Integrated School | SANTO NIÑO (FAIRE) | 2 | 1 | 4 | Construction/Completion (2STY4 LAB (SCI LAB, ICT)) |  | 3716621.5529 | 3707353.17 |  | COMPLETED | 1 | [10 empty] | substantially completed ( rectification of corrective works observed)
40874 | NC 2021 | TVL | Region II | Isabela | 500090 | Minagbag Integrated School (Secondary) | QUEZON | 5 | 1 | 4 | Construction/Completion (2STY4CL LAB) |  | 12215748.3128 | 12185285.1 |  | completed | 1
40875 | NC 2021 | K10 | Region II | Nueva Vizcaya | 104044 | Inaban Elementary School | DUPAX DEL NORTE | 0 | 1 | 8 | Construction/Completion (2STY8CL) |  | 22761710.8813 | 22704948.51 |  | Completed | 1
40876 | NC 2021 | SHS | Region II | Nueva Vizcaya | 300615 | Alfonso Castañeda NHS | ALFONSO CASTAÑEDA | 0 | 1 | 8 | Construction/Completion (2STY8CL) |  | 21553750 | 21500000 |  | Completed | 1
40877 | NC 2021 | SHS | Region II | Nueva Vizcaya | 300637 | Munguia NHS | DUPAX DEL NORTE | 0 | 1 | 7 | Construction/Completion (3STY 2CL, 2ICT, 2SL & 1RW) |  | 1795402.1621 | 1790924.85 |  | Completed | 1
41607 | NC 2022 | K10 | Region II | Cagayan | 501586 | San Juan Integrated School | RIZAL | 2 | 1 | 3 | 1STY3CL | 2 |  | 7588439.8502 |  | Completed | 1 | 2023-06-01 | [9 empty] | The project is on-going. The office requested for Time Extension to cope with the delay caused by intermittent rain in the locality.
41608 | NC 2022 | K10 | Region II | Cagayan | 102916 | Cadongdongan ES | SANTA PRAXEDES | 2 | 1 | 2 | 1STY2CL | 2 |  | 4973857.9959 |  | Completed | 1 | 2023-07-16 | [9 empty] | The project is on-going. The office requested for Time Extension to cope with the delay caused by intermittent rain in the locality.
41609 | NC 2022 | K10 | Region II | Isabela | 103484 | Bustamante Elementary School | LUNA | 5 | 1 | 3 | 1STY3CL w/ Toilet Attached | 2 |  | 6483391.2881 | 6462139.09 | Completed | 1 | 2023-05-05 |  | 23BF0028
41610 | NC 2022 | K10 | Region II | Isabela | 103486 | Lalog Elementary School | LUNA | 5 | 1 | 3 | 1STY3CL w/ Toilet Attached | 2 |  | 6483391.2881 | 6305575.01 | Completed | 1 | 2023-05-05 |  | 23BF0024
41611 | NC 2022 | K10 | Region II | Isabela | 103487 | Luna Central School | LUNA | 5 | 1 | 3 | 1STY3CL w/ Toilet Attached | 2 |  | 6456966.0598 | 6279854.09 | Completed | 1 | 2023-05-05 |  | 23BF0027
41612 | NC 2022 | K10 | Region II | Isabela | 103488 | Mambabanga Elementary School | LUNA | 5 | 1 | 3 | 1STY3CL w/ Toilet Attached | 2 |  | 6528049.5453 | 6511763.75 | Completed | 1 | 2023-05-05 |  | 23BF0023
41613 | NC 2022 | K10 | Region II | Isabela | 103490 | Pulay-Union Kalinga Elementary School | LUNA | 5 | 1 | 3 | 1STY3CL w/ Toilet Attached | 2 |  | 6383141.2881 | 6208455.42 | Completed | 1 | 2023-05-05 |  | 23BF0026
41614 | NC 2022 | K10 | Region II | Isabela | 103491 | Puroc-Concepcion ES | LUNA | 5 | 1 | 3 | 1STY3CL w/ Toilet Attached | 2 |  | 6506182.5742 | 6476776.36 | Completed | 1 | 2023-05-05 |  | 23BF0025
41615 | NC 2022 | K10 | Region II | Isabela | 500970 | Sto. Domingo-San Isidro Integrated School | LUNA | 5 | 1 | 6 | 2STY6CL | 2 |  | 16659878.4515 | 16608300 | Completed | 1 | 2023-07-09 |  | 22BF0089
41616 | NC 2022 | K10 | Region II | Isabela | 103701 | Gud Elementary School | SAN ISIDRO | 6 | 1 | 4 | 1STY4CL W/ TOILET | 2 |  | 8885121.831 | 8727809.57 | Completed | 1 |  |  | 22BH0160
41617 | NC 2022 | K10 | Region II | Isabela | 103702 | Nagbukel Elementary School | SAN ISIDRO | 6 | 1 | 2 | 1STY2CL W/ TOILET | 2 |  | 4442560.9155 | 4363957.13 | Completed | 1 |  |  | 22BH0164
41618 | NC 2022 | K10 | Region II | Isabela | 103703 | Patanad Elementary School | SAN ISIDRO | 6 | 1 | 2 | 1STY2CL W/ TOILET | 2 |  | 4442560.9155 | 4363957.13 | Completed | 1 |  |  | 22BH0163
41619 | NC 2022 | K10 | Region II | Isabela | 103705 | Ramos Elementary School | SAN ISIDRO | 6 | 1 | 3 | 1STY3CL W/ TOILET | 2 |  | 6663841.3783 | 6547000 | Completed | 1 |  |  | 22BH0166
41620 | NC 2022 | K10 | Region II | Isabela | 155510 | Ramos West Elementary School | SAN ISIDRO | 6 | 1 | 2 | 1STY2CL W/ TOILET | 2 |  | 4442560.9155 | 4364739.37 | Completed | 1 |  |  | 22BH0162
41621 | NC 2022 | K10 | Region II | Isabela | 103706 | San Isidro East Central School | SAN ISIDRO | 6 | 1 | 8 | 2STY8CL W/ TOILET | 2 |  | 24484897.996 | 24057476.46 | Completed | 1 |  |  | 22BH0161
41622 | NC 2022 | K10 | Region II | Isabela | 103709 | Villaflor Elementary School | SAN ISIDRO | 6 | 1 | 2 | 1STY2CL W/ TOILET | 2 |  | 5012500 | 4924737.6 | Completed | 1 |  |  | 22BH0165
41623 | NC 2022 | K10 | Region II | Nueva Vizcaya | 104188 | Alfonso Castañeda Central School | ALFONSO CASTAÑEDA | 0 | 1 | 4 | 2STY4CL | 2 |  | 15588875 |  | Completed | 1 | 2023-03-28
41624 | NC 2022 | K10 | Region II | Nueva Vizcaya | 137028 | Bagingey Elementary School | AMBAGUIO | 0 | 1 | 2 | 1STY2CL w/ CR | 2 |  | 6015000 | 5941481.68 | Completed | 1 | 2023-06-08 | 2023-06-08 | P00675092LZ | 22BI0095 | 2022-11-04 | 2022-11-24 | 2022-12-06 | 2022-12-12 | 2022-12-15 | N-J Construction
41625 | NC 2022 | K10 | Region II | Nueva Vizcaya | 104215 | Ernesto "Lapan" Pale ES | VILLAVERDE | 0 | 1 | 2 | 1STY2CL w/ CR | 2 |  | 5513750 | 5440385.46 | Completed | 1 | 2023-06-05 | 2023-06-05 | P00675094LZ | 22BI0096 | 2022-11-04 | 2022-11-24 | 2022-12-06 | 2022-12-12 | 2022-12-15 | Mighty Construction & Supply
41626 | NC 2022 | K10 | Region II | Quirino | 104364 | San Pugo Elementary School | NAGTIPUNAN | 0 | 1 | 6 | 2UNITS 1STY3CL | 2 |  | 20050000 |  | Completed | 1 | [8 empty] | 2023-01-13 | Juris Construction & Builders
41627 | NC 2022 | K10 | Region II | Quirino | 501562 | Salvacion Integrated School | SAGUDAY | 0 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1 | [8 empty] | 2023-01-09 | JMD-68 Builders
41805 | NC 2022 | SHS | Region II | Batanes | 300411 | Batanes Nat"l Science High School | BASCO (Capital) | 0 | 1 | 6 | 3STY6CL | 2 |  | 27869500 |  | Ongoing | 0.95 | 2024-03-19
41806 | NC 2022 | SHS | Region II | Isabela | 300558 | Luna National High School | LUNA | 5 | 1 | 4 | 2STY4CL | 2 |  | 10886035.641 | 10848500 | Completed | 1 | 2023-06-19 |  | 22BF0090
41807 | NC 2022 | SHS | Region II | Nueva Vizcaya | 300633 | Martinez Cuyangan National High School | KAYAPA | 0 | 1 | 4 | 2STY4CL | 2 |  | 15588875 |  | Completed | 1 | 2023-03-27
42070 | NC 2023 | SHS | Region II | Batanes | 300414 | Itbayat National Agricultural HS | ITBAYAT |  | 1 | 3 |  | Batch 1 | 15131250 | 15000000 |  | Not Yet Started | 0 | [10 empty] | Collecting data from DPWH. The project was put on hold pending issuance of ECC by the authorities concerned.
42071 | NC 2023 | K10 | Region II | Batanes | 102317 | Mayan Elementary School | ITBAYAT |  | 1 | 4 |  | Batch 1 | 20175000 | 5000000 | #REF! | Not Yet Started | 0 | [10 empty] | Collecting data from DPWH. The project was put on hold pending issuance of ECC by the authorities concerned.
42072 | NC 2023 | K10 | Region II | Cagayan | 102378 | Tupang ES | ALCALA |  | 1 | 2 |  | Batch 1 | 5581060.69 | 5532650 | 5581060.69 | Completed | 1 | 2024-03-19 | 2024-09-02 |  | 23BB0175 | 2023-06-16 | 2023-06-23 | 2023-07-06 | 2023-08-17 | 2023-08-24 | NCL BUILDERS & CONSTRUCTION SUPPLY
42073 | NC 2023 | K10 | Region II | Cagayan | 102485 | C. Verzosa ES | BAGGAO |  | 1 | 2 |  | Batch 1 | 5823715.5 | 5773200 | 5823715.5 | Completed | 1 | 2024-03-19 | 2024-09-02 |  | 23BB0175 | 2023-06-16 | 2023-06-23 | 2023-07-06 | 2023-08-17 | 2023-08-24 | NCL BUILDERS & CONSTRUCTION SUPPLY
42074 | NC 2023 | K10 | Region II | Cagayan | 102504 | Taguntungan ES | BAGGAO |  | 1 | 2 |  | Batch 1 | 5581060.69 | 5532650 | 5581060.69 | Completed | 1 | 2024-03-07 | 2024-05-02 |  | 23BB01074 | 2023-06-16 | 2023-06-23 | 2023-07-06 | 2023-08-17 | 2023-08-24 | DECA CONSTRUCTION
42075 | NC 2023 | K10 | Region II | Cagayan | 102533 | Tueg ES | BAGGAO |  | 1 | 3 |  | Batch 1 | 7452947.63 | 7388300 |  | Reverted | 0 | [10 empty] | REVERTED DUE TO VERY LIMITED FUND
42076 | NC 2023 | K10 | Region II | Cagayan | 102681 | Tasica ES | GATTARAN |  | 1 | 2 |  | Batch 1 | 5823715.5 | 5773200 | 5823715.5 | Completed | 1 | 2024-03-12 | 2024-02-07 |  | 23BB0172 | 2023-06-16 | 2023-06-23 | 2023-07-06 | 2023-08-17 | 2023-08-24 | TJMT CONSTRUCTION
42077 | NC 2023 | SHS | Region II | Cagayan | 300419 | Abulug SOF | ABULUG |  | 1 | 6 |  | Batch 1 | 18422474.39 | 18262675.97 | 18161337.08 | Completed | 1 | 2024-03-15 | 2024-06-05 | CONSTRUCTION OF 2 STORY 6 CL | 23BC0129 | 2023-03-23 | 2023-03-31 | 2023-04-18 | 2023-06-13 | 2023-06-14 | J.G. YACAS CONSTRUCTION SUPPLY & EQUIPMENT RENTAL
42078 | NC 2023 | K10 | Region II | Cagayan | 102340 | Guiddam ES | ABULUG |  | 1 | 3 |  | Batch 1 | 6661039.51 | 6603260.98 | 6603260.98 | Completed | 1 | 2024-05-14 | 2024-05-14 | CONSTRUCTION OF 1 STY 3CL | 23BC191 | 2023-06-08 | 2023-06-19 | 2023-07-03 | 2023-09-15 | 2023-09-28 | V.S. LAUNGAYAN HARDWARE & CONSTRUCTION SUPPLY
42079 | NC 2023 | K10 | Region II | Cagayan | 102352 | Sta. Rosa Elementary School | ABULUG |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4723299.77 | Completed | 1 | 410452 | 410452 | CONSTRUCTION OF 1STY 2CL | 23BC0128 | 2023-03-23 | 2023-03-31 | 2023-04-18 | 2023-06-13 | 2023-06-14 | OLIVA DESIGN CONSTRUCTION
42080 | NC 2023 | K10 | Region II | Cagayan | 102607 | Capannikian Elementary School | CLAVERIA |  | 1 | 5 |  | Batch 1 | 10732989.77 | 10639890.72 | 10453292.45 | Completed | 1 | 2024-04-29 | 2024-01-19 | CONSTRUCTION OF 1-STORY 5 CL | 23BC0126 | 2023-08-04 | 2023-08-11 | 2023-08-29 | 2023-09-04 | 2023-09-08 | A. NIDUAZA BUILDERS
42081 | NC 2023 | K10 | Region II | Cagayan | 102609 | Claveria East CS | CLAVERIA |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4664314 | Completed | 1 | 2023-11-20 | 2024-01-19 | 23BC0127 | 23BC0127 | 2023-02-15 | 2023-02-27 | 2023-03-17 | 2023-06-13 | 2023-06-14 | JPO BUILDERS & CONSTRUCTION SUPPLY
42082 | NC 2023 | K10 | Region II | Cagayan | 102835 | Duyun ES | RIZAL |  | 1 | 2 |  | Batch 1 | 5029918.3 | 4986288.28 | 4749246.54 | Completed | 1 | 2024-03-27 | 2024-06-05 | CONSTRUCTION OF 1STYV-2CL | 23BC0190 | 2023-06-08 | 2023-06-19 | 2023-07-03 | 2023-09-15 | 2023-09-28 | SOA CONSTRUCTION
42083 | NC 2023 | K10 | Region II | Cagayan | 102836 | Gaddangao ES | RIZAL |  | 1 | 3 |  | Batch 1 | 6807351.68 | 6748304.02 | 6559389.57 | Completed | 1 | 2024-02-14 | 2024-02-14 | CONSTRUCTION OF 1STY 3CL | 23BC0189 | 2023-06-08 | 2023-06-19 | 2023-07-03 | 2023-09-15 | 2023-09-28 | SOA CONSTRUCTION
42084 | NC 2023 | K10 | Region II | Cagayan | 102838 | Illuru ES | RIZAL |  | 1 | 2 |  | Batch 1 | 5029918.3 | 4986288.28 | 4750894.3 | Completed | 1 | 2024-03-27 | 2024-06-05 | CONSTRUCTION OF 1 STY-2CL | 23BC0192 | 2023-06-08 | 2023-06-19 | 2023-07-03 | 2023-09-15 | 2023-09-28 | SOA CONSTRUCTION
42085 | NC 2023 | K10 | Region II | Cagayan | 102842 | Mauanan Elementary School | RIZAL |  | 1 | 2 |  | Batch 1 | 5029918.3 | 4986288.28 | 4706098.78 | Completed | 1 | 2024-01-27 | 2024-01-21 | CONSTRUCTION OF 1 STY-2CL | 23BC0193 | 2023-06-08 | 2023-06-19 | 2023-07-03 | 2023-09-15 | 2023-09-28 | SOA CONSTRUCTION
42086 | NC 2023 | SHS | Region II | Cagayan | 300478 | Mauanan NHS | RIZAL |  | 1 | 6 |  | Batch 1 | 18365910.76 | 18206602.98 | 17769521.8 | Ongoing | 0.95 | 2024-06-18 |  | CONSTRUCTION OF 2 STY 6CL | 23BC0194 | 2023-06-08 | 2023-06-19 | 2023-07-03 | 2023-09-15 | 2023-09-28 | HEXADECA CONSTRUCTION
42087 | NC 2023 | K10 | Region II | Cagayan | 102716 | Iguig CS | IGUIG |  | 1 | 6 |  | Batch 1 | 10087500 | 10000000 | 9940031.21 | Completed | 1 | 2024-03-17 | 2023-12-15 | P00775173LZ | 23BD0130 | 2023-06-16 | 2023-06-22 | 2023-07-22 | 2023-07-24 | 2023-08-04 | J3M3 CONSTRUCTION
42088 | NC 2023 | K10 | Region II | Cagayan | 502307 | Bangag Integrated School (102867-Banagag ES) | SOLANA |  | 1 | 6 |  | Batch 1 | 10087500 | 10000000 | 9947378.15 | Completed | 1 | 2024-03-06 | 2024-02-26 | P00775172LZ | 23BD0129 | 2023-06-16 | 2023-06-22 | 2023-07-22 | 2023-07-21 | 2023-08-04 | MAIDA'S CONSTRUCTION
42089 | NC 2023 | K10 | Region II | Isabela | 501434 | Cubag Integrated School | CABANGAN |  | 1 | 2 |  | Batch 1 | 4835686.6 | 4793741.36 | 4789046.25 | Completed | 1 | 2024-01-23 | 2024-01-23 | P00775174LZ-CW1 | 23BE0146 | 2023-07-21 | 2023-07-28 | 2023-08-10 | 2023-08-31 | 2023-09-08 | Dragon Twelve Builders & Construction Supply
42090 | NC 2023 | K10 | Region II | Isabela | 103271 | Maui Elementary School | DELFIN ALBANO (MAGSAYSAY) |  | 1 | 3 |  | Batch 1 | 6738545.9 | 6680095.07 | 6667095.05 | Completed | 1 | 2024-02-13 | 2024-02-13 | P00775175LZ-CW1 | 23BE0149 | 2023-07-21 | 2023-07-28 | 2023-08-10 | 2023-08-31 | 2023-09-08 | RD Bedaña Construction & Supplies
42091 | NC 2023 | K10 | Region II | Isabela | 103797 | Ballacayu Elementary School | SAN PABLO |  | 1 | 4 |  | Batch 1 | 15360176.45 | 15226940.72 | 15222097.72 | Completed | 1 | 2024-03-19 | 2024-03-19 | P00775176LZ-CW1 | 23BE0151 | 2023-07-21 | 2023-07-28 | 2023-08-10 | 2023-08-31 | 2023-09-08 | SMT Construction
42092 | NC 2023 | K10 | Region II | Isabela | 103854 | Sta. Maria Central School | SANTA MARIA |  | 1 | 2 |  | Batch 1 | 4163331.08 | 4127217.92 | 4125158.88 | Completed | 1 | 2024-01-23 | 2024-01-23 | P00775177LZ-CW1 | 23BE0147 | 2023-07-21 | 2023-07-28 | 2023-08-10 | 2023-08-31 | 2023-09-08 | SMT Construction
42093 | NC 2023 | K10 | Region II | Isabela | 103862 | Barumbung Elementary School | SANTO TOMAS |  | 1 | 3 |  | Batch 1 | 5903305.88 | 5852100 | 5849101.62 | Completed | 1 | 2024-02-13 | 2024-02-13 | P00775178LZ-CW1 | 23BE0148 | 2023-07-21 | 2023-07-28 | 2023-08-10 | 2023-08-31 | 2023-09-08 | Dragon Twelve Builders & Construction Supply
42094 | NC 2023 | SHS | Region II | Isabela | 305942 | Tumauini Stand-Alone Senior High Schol | TUMAUINI |  | 1 | 4 |  | Batch 1 | 14852539.05 | 14723706.62 | 14718859.57 | Completed | 1 | 2024-03-19 | 2024-03-19 | P00775179LZ-CW1 | 23BE0150 | 2023-07-21 | 2023-07-28 | 2023-08-10 | 2023-08-31 | 2023-09-08 | Dragon Twelve Builders & Construction Supply
42095 | NC 2023 | K10 | Region II | Isabela | 500467 | Sto. Tomas Integrated School | NAGUILIAN |  | 1 | 3 |  | Batch 1 | 9078750 | 9000000 | 8910397.28 | Completed | 1 | 2024-01-19 | 2024-01-18 |  | 23BG0200 | 2023-08-09 | 2023-08-16 | 2023-08-30 | 2023-09-12 | 2023-09-13 | CAMBERWELL CONSTRUCTION AND SUPPLIES
42096 | NC 2023 | K10 | Region II | Isabela | 103620 | Dangan Elementary School | REINA MERCEDES |  | 1 | 2 |  | Batch 1 | 6556875 | 6500000 | 6492410.88 | Completed | 1 | 2024-01-06 | 2024-03-05 |  | 23BG0201 | 2023-08-09 | 2023-08-16 | 2023-08-30 | 2023-09-12 | 2023-09-13 | Danysons Construction and Development Corporation
42097 | NC 2023 | K10 | Region II | Isabela | 103627 | Santor Elementary School | REINA MERCEDES |  | 1 | 2 |  | Batch 1 | 6556875 | 6500000 | 6492238.32 | Completed | 1 | 2024-01-06 | 2024-02-16 |  | 23BG0202 | 2023-08-09 | 2023-08-16 | 2023-08-30 | 2023-09-12 | 2023-09-13 | Danysons Construction and Development Corporation
42098 | NC 2023 | K10 | Region II | Isabela | 500070 | San Jose Integrated School | SAN MARIANO |  | 1 | 3 |  | Batch 1 | 9078750 | 9000000 | 8988933.96 | Completed | 1 | 2024-01-19 | 2024-02-16 |  | 23BG0203 | 2023-08-09 | 2023-08-16 | 2023-08-30 | 2023-09-12 | 2023-09-13 | YZK Builders
42099 | NC 2023 | K10 | Region II | Isabela | 500095 | San Mariano II Central Integrated School | SAN MARIANO |  | 1 | 4 |  | Batch 1 | 12105000 | 12000000 | 11879772.4 | Completed | 1 | 2024-01-30 | 2024-03-04 |  | 23BG0204 | 2023-08-09 | 2023-08-16 | 2023-08-30 | 2023-09-12 | 2023-09-13 | CAMBERWELL CONSTRUCTION AND SUPPLIES
42100 | NC 2023 | SHS | Region II | Isabela | 300502 | Villa Domingo National High School | ANGADANAN |  | 1 | 4 |  | Batch 1 | 17148750 | 17000000 | 16989152.23 | Completed | 1 | 2024-02-19 | 2024-05-18 |  | 23BG0205 | 2023-08-09 | 2023-08-16 | 2023-08-30 | 2023-09-12 | 2023-09-13 | JWU CONSTRUCTION AND SUPPLY
42101 | NC 2023 | K10 | Region II | Isabela | 103608 | Raniag Elementary School | RAMON |  | 1 | 2 |  | Batch 1 | 6556875 | 6500000 | 6469978.64 | Completed | 1 | 2024-01-06 | 2024-01-05 |  | 23BG0206 | 2023-08-09 | 2023-08-16 | 2023-08-30 | 2023-09-12 | 2023-09-13 | CHU SAN CONSTRUCTION AND SUPPLY
42102 | NC 2023 | K10 | Region II | Isabela | 103793 | Villa Fuerte Elementary School | SAN MATEO |  | 1 | 2 |  | Batch 1 | 6556875 | 6500000 | 6488645.49 | Completed | 1 | 2024-01-06 | 2024-03-05 |  | 23BG0207 | 2023-08-09 | 2023-08-16 | 2023-08-30 | 2023-09-12 | 2023-09-13 | JWU CONSTRUCTION AND SUPPLY
42103 | NC 2023 | K10 | Region II | Isabela | 103245 | Camarao Elementary School | CORDON |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4912188 | Completed | 1 | 2024-02-12 | 2024-02-12 | P00775188LZ-CW1 | 23BH0205 | 2023-04-18 | 2023-04-17 | 2023-05-09 | 2023-07-19 | 2023-07-19 | VBM CONSTRUCTION CORP.
42104 | NC 2023 | K10 | Region II | Isabela | 103246 | Capirpiriwan Elementary School | CORDON |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4907756.94 | Completed | 1 | 2023-12-07 | 2023-11-18 | P00775189LZ-CW1 | 23BH0206 | 2023-04-18 | 2023-04-17 | 2023-05-09 | 2023-07-17 | 2023-07-17 | WBS CONSTRUCTION & CONST. SUPPLY
42105 | NC 2023 | K10 | Region II | Isabela | 103249 | Dallao Elementary School | CORDON |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4944768.49 | Completed | 1 | 2023-12-13 | 2023-12-13 | P00775190LZ-CW1 | 23BH0208 | 2023-04-18 | 2023-04-17 | 2023-05-09 | 2023-07-17 | 2023-07-17 | RBV CONSTRUCTION
42106 | NC 2023 | K10 | Region II | Isabela | 103470 | Jones West Central School-C2 | JONES |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4878632.78 | Completed | 1 | 2023-12-14 | 2023-11-17 | P00775191LZ-CW1 | 23BH0204 | 2023-04-18 | 2023-04-17 | 2023-05-09 | 2023-07-18 | 2023-07-18 | GB CARLOS CONSTRUCTION
42107 | NC 2023 | K10 | Region II | Isabela | 103653 | Dabubu Elementary School | SAN AGUSTIN |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4925664.4 | Completed | 1 | 2023-12-13 | 2023-10-15 | P00775192LZ-CW1 | 23BH0209 | 2023-04-18 | 2023-04-17 | 2023-05-09 | 2023-07-17 | 2023-07-17 | CASAN CONSTRUCTION AND TRADING
42108 | NC 2023 | K10 | Region II | Isabela | 103669 | Sinaoangan Sur Elementary School | SAN AGUSTIN |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4919916.53 | Completed | 1 | 2023-12-14 | 2023-10-18 | P00775193LZ-CW1 | 23BH0207 | 2023-04-18 | 2023-04-17 | 2023-05-09 | 2023-07-19 | 2023-07-19 | MONTE CARLO CONSTRUCTION CORP.
42109 | NC 2023 | K10 | Region II | Isabela | 103130 | Cullalabo Elementary School | BURGOS |  | 1 | 3 |  | Batch 1 | 6661039.51 | 6603260.98 | 6603260.98 | Completed | 1 |  | 2024-03-22 | 23BF0096 | 23BH0235 |  |  |  |  | 2023-08-29 | Danysons Construction & Development Corporation
42110 | NC 2023 | K10 | Region II | Isabela | 103502 | San Jose Norte Elementary School | MALLIG |  | 1 | 3 |  | Batch 1 | 6661039.51 | 6603260.98 | 6603260.98 | Completed | 1 |  |  | 23BF0098 | [5 empty] | 2023-08-29 | R.S.K.M. Construction services
42111 | NC 2023 | K10 | Region II | Isabela | 103573 | Turod Elementary School | QUEZON |  | 1 | 3 |  | Batch 1 | 6661039.51 | 6603260.98 | 6603260.98 | Completed | 1 |  | 2024-04-02 | 23BF00100 | 23BF0100 |  |  |  |  | 2023-08-29 | Danysons Construction & Development Corporation
42112 | NC 2023 | K10 | Region II | Isabela | 103587 | Santiago Elementary School | QUIRINO |  | 1 | 3 |  | Batch 1 | 6661039.51 | 6603260.98 | 6603260.98 | Completed | 1 |  | 2024-01-31 | 23BF0099 | 23BF0099 |  |  |  |  | 2023-08-29 | R.S.K.M. Construction services
42113 | NC 2023 | K10 | Region II | Isabela | 103635 | Matusalem Elementary School | ROXAS |  | 1 | 3 |  | Batch 1 | 6661039.51 | 6603260.98 | 6603260.98 | Completed | 1 |  | 2024-03-22 | 23BF0097 | 23BF0097 |  |  |  |  | 2023-08-29 | Danysons Construction & Development Corporation
42114 | NC 2023 | SHS | Region II | Isabela | 300612 | Echague National High School | ECHAGUE |  | 1 | 12 |  | Batch 1 | 30262500 | 30000000 | 29551083.65 | Completed | 1 | 2024-08-06 | 2024-08-06 | P00775199LZ-CW1 | 23BH0235 | 2023-07-11 | 2023-07-10 | 2023-07-31 | 2023-08-10 | 2023-08-10 | AYLAN CONSTRUCTION AND TRADING
42115 | NC 2023 | SHS | Region II | Nueva Vizcaya | 300617 | Ambaguio High School | AMBAGUIO |  | 1 | 8 |  | Batch 1 | 21889875 | 21700000 | 21700000 | Completed | 1 | 2024-06-02 |  | P00775203LZ |  | 2023-06-29 | 2023-07-11 | 2023-07-19 | 2023-08-03 | 2023-08-03 | Prime Built Construction & Supply | -
42116 | NC 2023 | K10 | Region II | Nueva Vizcaya | 502194 | Balong IS | AMBAGUIO |  | 1 | 6 |  | Batch 1 | 19388175 | 19220000 | 19220000 | Completed | 1 | 2024-09-05 | 2024-09-05 | P00775205LZ | - | 2023-06-29 | 2023-07-11 | 2023-07-19 | 2023-08-03 | 2023-08-03 | NJ Construction | -
42117 | NC 2023 | K10 | Region II | Nueva Vizcaya | 501901 | Dulli Integrated School | AMBAGUIO |  | 1 | 6 |  | Batch 1 | 19125900 | 18960000 | 18960000 | Completed | 1 | 2024-05-14 | 2024-05-14 | P00775204LZ | - | 2023-06-29 | 2023-07-11 | 2023-07-19 | 2023-08-03 | 2023-08-03 | CRES Construction and Supply | -
42118 | NC 2023 | K10 | Region II | Nueva Vizcaya | 137027 | Pihipi Elementary School | AMBAGUIO |  | 1 | 2 |  | Batch 1 | 10087500 | 10000000 | 10000000 | Completed | 1 | 2024-04-02 | 2024-04-02 | P00775201LZ | - | 2023-06-29 | 2023-07-11 | 2023-07-19 | 2023-08-03 | 2023-08-03 | Upland Construction | -
42119 | NC 2023 | K10 | Region II | Nueva Vizcaya | 103999 | Tiblac ES | AMBAGUIO |  | 1 | 2 |  | Batch 1 | 6052500 | 6000000 | 6000000 | Completed | 1 | 2024-02-16 | 2024-02-16 | P00775200LZ | - | 2023-06-29 | 2023-07-11 | 2023-07-25 | 2023-08-03 | 2023-08-03 | Mighty Construction & Supply | -
42120 | NC 2023 | SHS | Region II | Nueva Vizcaya | 300525 | Tiblac National High School | AMBAGUIO |  | 1 | 12 |  | Batch 1 | 40753500 | 40400000 | 40400000 | Completed | 1 | 2024-08-06 | 2024-08-06 | P00775202LZ | - | 2023-08-03 | 2023-08-15 | 2023-09-04 | 2023-09-19 | 2023-09-19 | C.D.J. BUILDERS & CONSTRUCTION SUPPLIES/E.M. BAYATAN CONSTRUCTION (J.V.) | -
42121 | NC 2023 | SHS | Region II | Nueva Vizcaya | 300620 | Bambang NHS | BAMBANG |  | 1 | 4 |  | Batch 1 | 30262500 | 30000000 | 30000000 | Completed | 1 | 2024-12-05 | 2024-10-21 | P00775206LZ | - | 2023-06-29 | 2023-07-11 | 2023-08-07 | 2023-08-22 | 2023-08-22 | CDJ Builders and Construction Supply | -
42122 | NC 2023 | K10 | Region II | Nueva Vizcaya | 501941 | Sto. Domingo IS | BAMBANG |  | 1 | 4 |  | Batch 1 | 15131250 | 15000000 | 15000000 | Completed | 1 | 2024-03-17 | 2024-03-17 | P00775207LZ | - | 2023-06-29 | 2023-07-11 | 2023-07-19 | 2023-08-03 | 2023-08-03 | M.R. Vargas Construction Corporation | -
42123 | NC 2023 | K10 | Region II | Quirino | 501566 | Eden Integrated School | CABARROGUIS (Capital) |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4745017.19 | Completed | 1 | 2023-12-20 | 2023-12-18 | P00775208LZ-CW1 | 23BK0119 | 2023-06-27 | 2023-07-11 | 2023-07-24 | 2023-08-01 | 2023-08-10 | JURIS CONST. & BUILDERS
42124 | NC 2023 | K10 | Region II | Quirino | 501560 | Gulac Integrated School | DIFFUN |  | 1 | 4 |  | Batch 1 | 4788571.5 | 4747034.94 | 4600681.82 | Completed | 1 | 2023-12-20 | 2023-12-20 | P00775211LZ-CW1 | 23BK0122 | 2023-06-27 | 2023-07-11 | 2023-07-24 | 2023-08-01 | 2023-08-10 | JURIS CONST. & BUILDERS
42125 | NC 2023 | K10 | Region II | Quirino | 500104 | San Antonio Integrated School | DIFFUN |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4604346.74 | Completed | 1 | 2023-12-20 | 2023-12-20 | P00775210LZ-CW1 | 23BK0121 | 2023-06-27 | 2023-07-11 | 2023-07-24 | 2023-08-01 | 2023-08-10 | JMD-68 BUILDERS
42126 | NC 2023 | K10 | Region II | Quirino | 156507 | Turayok Elementary School | DIFFUN |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4731915.58 | Completed | 1 | 2024-01-15 | 2024-01-14 | P00775209LZ-CW1 | 23BK0120 | 2023-06-27 | 2023-07-11 | 2023-07-24 | 2023-08-01 | 2023-08-10 | JURIS CONST. & BUILDERS
42127 | NC 2023 | SHS | Region II | Quirino | 300654 | Balligui HS | MADDELA |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4603776.14 | Completed | 1 | 2023-12-20 | 2023-12-15 | P00775212LZ-CW1 | 23BK0123 | 2023-06-27 | 2023-07-11 | 2023-07-24 | 2023-08-01 | 2023-08-10 | JURIS CONST. & BUILDERS
42128 | NC 2023 | K10 | Region II | Quirino | 500103 | Divisoria Sur IS | MADDELA |  | 1 | 4 |  | Batch 1 | 8687799.44 | 8612440.58 | 8351623.93 | Completed | 1 | 2024-03-07 | 2024-03-07 | P00775213LZ-CW1 | 23BK0124 | 2023-07-21 | 2023-07-21 | 2023-08-02 | 2023-08-15 | 2023-08-24 | JURIS CONST. & BUILDERS
42129 | NC 2023 | K10 | Region II | Tuguegarao City | 104395 | Bagay Elementary School | TUGUEGARAO CITY(Capital) |  | 1 | 6 |  | Batch 1 | 10087500 | 10000000 | 10000000 | Completed | 1 | 2024-03-15 | 2024-03-15 | P00775214LZ-CW1 | 23BD00128 | 2023-06-16 | 2023-06-22 | 2023-07-06 | 2023-07-24 | 2023-08-04 | 4MDJJL Construction Inc. | Completed
43400 | NC 2024 |  | Region II | Batanes | 300414 | Itbayat National Agricultural HS | ITBAYAT |  | 1 | 3 | 1STY3CL | GAA 17B | 15000000 |  |  | Not Yet Started | 0
43401 | NC 2024 |  | Region II | Batanes | 102317 | Mayan Elementary School | ITBAYAT |  | 1 | 3 | 1STY3CL | GAA 17B | 15000000 |  |  | Not Yet Started | 0
43402 | NC 2024 |  | Region II | Batanes | 300415 | Ivana NHS | IVANA |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  |  | Not Yet Started | 0
43403 | NC 2024 |  | Region II | Cagayan | 300421 | Alcala Rural School | ALCALA |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9975000 | Ongoing | 0.31 | 2025-07-15 |  | CONSTRUCTION 1STY 3CL | 24BB0209 | 2024-11-29 | 2024-06-12 | 2024-12-20 | 2025-06-03 | 2025-12-03 | TJMT CONSTRUCTION
43404 | NC 2024 |  | Region II | Cagayan | 300428 | Aparri School of Arts and Trades | APARRI |  | 1 | 11 | Construction of School Building | BATCH 1 | 26790795.47 |  | 26723818.48 | Ongoing | 0.55 | 2026-11-09 |  | Construction of School Building | 24BB0200 | 2024-07-10 | 2024-10-14 | 2024-10-28 | 2024-02-12 | 2024-05-12 | ZERO THREE CONSTRUCTION
43405 | NC 2024 |  | Region II | Cagayan | 102512 | Bagunot Elementary School | BAGGAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 | 2024-03-11 | 2024-07-10 | CONSTRUCTION 1STY 2CL | 24BD0151 | 2024-03-28 | 2024-04-04 | 2024-04-17 | 2024-06-24 | 2024-07-01 | TIKA CONST
43406 | NC 2024 |  | Region II | Cagayan | 102522 | Mabini ES | BAGGAO |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9975000 | Ongoing | 0.21 | 2025-04-08 |  | CONSTRUCTION 1STY 3CL | 24BB0210 | 2024-11-29 | 2024-06-12 | 2024-12-20 | 2025-06-03 | 2025-12-03 | TIKA CONST
43407 | NC 2024 |  | Region II | Cagayan | 102595 | Alilinu ES | CAMALANIUGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | [11 empty] | Not inluded in FY
43408 | NC 2024 |  | Region II | Cagayan | 102596 | Bulala-Fugu ES | CAMALANIUGAN |  | 1 | 10 | 2STY10CL | BATCH 1 | 45660000 |  | 45545850 | Ongoing | 0.3 | 2025-02-12 |  | CONSTRUCTION 2STY 10CL | 24BB0207 | 2024-11-29 | 2024-06-12 | 2024-12-20 | 2024-12-26 | 2024-12-27 | TJMT CONSTRUCTION
43409 | NC 2024 |  | Region II | Cagayan | 102597 | Camalaniugan Central School | CAMALANIUGAN |  | 1 | 4 | 2STY4CL | BATCH 1 | 18200000 |  | 18154500 | Ongoing | 0.96 | 2025-02-05 |  | CONSTRUCTION 2STY 4CL | 24BB0199 | 2024-02-08 | 2024-09-08 | 2024-08-22 | 2024-09-16 | 2024-09-19 | PNC CONSTRUCTION
43410 | NC 2024 |  | Region II | Cagayan | 306426 | Camalaniugan National High School- Catotoran Annex | CAMALANIUGAN |  | 1 | 8 | 2STY8CL | BATCH 1 | 36550000 |  | 36458625 | Ongoing | 0.5 | 2026-04-26 |  | CONSTRUCTION 2UNITS-1STY4CL | 24BB0203 | 2024-11-29 | 2024-06-12 | 2024-12-20 | 2024-12-26 | 2024-12-27 | TJMT CONSTRUCTION | CHANGE OF PROJECT DESCRIPTION FROM 2STY8CL TO 2 UNITS-1STY4CL
43411 | NC 2024 |  | Region II | Cagayan | 155043 | Joaquin Dela Cruz Elementary School | CAMALANIUGAN |  | 1 | 3 | 1STY3CL | BATCH 1 | 11600000 |  | 11571000 | Ongoing | 0.64 | 2025-10-07 |  | CONSTRUCTION 1STY 4CL | 24BB0204 | 2024-11-29 | 2024-06-12 | 2024-12-20 | 2024-12-26 | 2024-12-27 | TJMT CONSTRUCTION | CHANGE OF PROJECT DESCRIPTION FROM 1STY3CL TO 1STY4CL
43412 | NC 2024 |  | Region II | Cagayan | 102681 | Tasica ES | GATTARAN |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 5823715.5 | Not Yet Started | [11 empty] | REALIGNED TO NABACCAYAN ES FROM 2STY4CL TO 1STY3CL
43413 | NC 2024 |  | Region II | Cagayan | 300483 | Gonzaga National High School | GONZAGA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4964887.75 | Completed | 1 | 2025-11-02 | 2025-02-21 | CONSTRUCTION 1STY 2CL | 24BD0152 | 2024-03-28 | 2024-04-04 | 2024-04-17 | 2024-06-24 | 2024-07-01 | APS CONT
43414 | NC 2024 |  | Region II | Cagayan | 102331 | Abulug Central Elementary School | ABULUG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4912925.09 | Completed | 1 | 2024-07-13 | 2024-08-13 | CONSTRUCTION 1STY 2CL | 24bc0110 | 2024-02-07 | 2024-02-15 | 2024-02-27 | 2024-03-20 | 2024-03-21 | J.G. YACAS CONSTRUCTION SUPPLY & EQUIPMENT RENTAL
43415 | NC 2024 |  | Region II | Cagayan | 102333 | Bagu ES | ABULUG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 | 2024-07-13 | 2024-07-13 | CONSTRUCTION 1STY 2CL | 24bc0111 | 2024-02-07 | 2024-02-15 | 2024-02-27 | 2024-03-20 | 2024-03-21 | J.G. YACAS CONSTRUCTION SUPPLY & EQUIPMENT RENTAL
43416 | NC 2024 |  | Region II | Cagayan | 102335 | Calog Norte ES | ABULUG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 | 2024-07-12 | 2024-07-12 | CONSTRUCTION 1STY 2CL | 24bc0109 | 2024-02-07 | 2024-02-15 | 2024-02-27 | 2024-03-19 | 2024-03-20 | FLAVIE CIVIL ENGINEERING CONSTRUCTION
43417 | NC 2024 |  | Region II | Cagayan | 102336 | CALOG SUR ELEMENTARY SCHOOL | ABULUG |  | 1 |  | Construction of School Building | GAA 17B | 20000000 |  | 19950000 | Completed | 1 | 2025-01-26 | 2024-12-27 | CONSTRUCTION OF SCHOOL BUILDING | 24bc0105 | 2024-02-07 | 2024-02-15 | 2024-02-27 | 2024-03-20 | 2024-03-21 | JEICCA BUILDERS
43418 | NC 2024 |  | Region II | Cagayan | 102341 | Libertad Elementary School | ABULUG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 | 2024-07-12 | 2024-10-04 | CONSTRUCTION 1STY 2CL | 24BC0106 | 2024-02-07 | 2024-02-15 | 2024-02-27 | 2024-03-19 | 2024-03-20 | OLIVA DESIGN CONSTRUCTION
43419 | NC 2024 |  | Region II | Cagayan | 102342 | Lucban ES | ABULUG |  | 1 | 4 | 2UNITS 1STY2CL | GAA 17B | 10000000 |  | 9975000 | Completed | 1 | 2024-08-08 | 2024-09-07 | CONSTRUCTION OF 2 UNITS OF 1STY 2CL | 24BC0112 | 2024-02-07 | 2024-02-15 | 2024-02-27 | 2024-03-20 | 2024-03-21 | J.G. YACAS CONSTRUCTION SUPPLY & EQUIPMENT RENTAL
43420 | NC 2024 |  | Region II | Cagayan | 102349 | Simayung ES | ABULUG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 | 2024-07-12 | 2024-07-12 | CONSTRUCTION 1STY 2CL | 24BC0108 | 2024-02-07 | 2024-02-15 | 2024-02-27 | 2024-03-19 | 2024-03-20 | FLAVIE CIVIL ENGINEERING CONSTRUCTION
43421 | NC 2024 |  | Region II | Cagayan | 102405 | Baccuit Elementary School | AMULUNG |  | 1 | 6 | 2STY6CL (PHASE I) | GAA 17B | 10000000 |  | 9975000 | Ongoing | 1 | 2025-05-04 | 2025-05-28 | P00869177LZ-CW1 | 24BD0107 | 2024-06-25 | 2024-03-07 | 2024-06-25 | 2024-07-29 | 2024-12-07 | VHT Cagayan Builders Corp
43422 | NC 2024 |  | Region II | Cagayan | 102634 | Enrile West CS | ENRILE |  | 1 | 6 | 2STY6CL (PHASE I) | GAA 17B | 10000000 |  | 9975000 | Ongoing | 1 | 2025-10-02 | 2025-11-05 | P00875196LZ-CW1 | 24BD0197 | 2024-06-25 | 2024-03-07 | 2024-07-15 | 2024-02-08 | 2024-09-08 | Maida's Construction
43423 | NC 2024 |  | Region II | Cagayan | 502068 | Lagum Integrated School | PEÑABLANCA |  | 1 | 6 | 2STY6CL (PHASE I) | GAA 17B | 10000000 |  | 9975000 | Not Yet Started | 0.45 | 2025-05-02 |  | P00875194LZ-CW1 | 24BD0198 | 2024-06-25 | 2024-03-07 | 2024-07-15 | 2024-02-08 | 2024-09-08 | 4MD JSL Construction Inc.
43424 | NC 2024 |  | Region II | Cagayan |  | Sampaguita ES | SOLANA |  | 1 | 6 | 2STY6CL (PHASE I) | GAA 17B | 10000000 |  | 9975000 | Completed | 1 | 2025-07-03 | 2025-07-03 | P00875195LZ-CW1 | 24BD0199 | 2024-06-25 | 2024-03-07 | 2024-07-15 | 2024-09-07 | 2024-12-07 | 5MJ's Construction
43425 | NC 2024 |  | Region II | Cauayan City | 103210 | Buena Suerte F. Pante ES | CITY OF CAUAYAN |  | 1 | 3 | 1STY3CL | BATCH 2 | 6697698.87 |  | 6632942.12 | Ongoing | 0.65 | 2025-06-13 |  | P00876026LZ-CW1 | 24BH0339 | 2024-10-29 | 2024-10-28 | 2024-11-18 | 2024-11-25 | 2024-12-12 | JWU CONSTRUCTION | Still ongoing
43426 | NC 2024 |  | Region II | Cauayan City | 103228 | Cauayan South CS | CITY OF CAUAYAN |  | 1 | 6 | 1STY6CL | GAA 17B | 15000000 |  | 14912007.16 | Ongoing | 0.8 | 2025-03-21 |  | P00875227LZ-CW1 | 24BH0338 | 2024-07-08 | 2024-06-08 | 2024-08-27 | 2024-12-09 | 2024-09-30 | OROSET CONSTRUCTION | Modified to 4STY20CL PHASE 1 (Still ongoing)
43427 | NC 2024 |  | Region II | City of Ilagan | 103390 | Cabeceria 24 ES | ILAGAN CITY (CAPITAL) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969944.2 | Completed | 1 | 2024-05-11 | 2024-09-23 | P00875201LZ-CW1 | 24BE0070 | 2024-02-04 | 2024-11-04 | 2024-04-24 | 2024-09-05 | 2024-05-22 | Dragon Twelve Builders and Construction Supply
43428 | NC 2024 |  | Region II | Isabela | 103139 | Aggub Elementary School | CABAGAN |  | 1 | 8 | 2STY8CL | GAA 17B | 25000000 |  | 24869843.4 | Ongoing | 0.75 | 2025-06-25 |  | P00875198LZ-CW1 | 24BE0163 | 2024-08-08 | 2024-08-16 | 2024-08-29 | 2024-12-26 | 2024-12-26 | Dragon Twelve Builders and Construction Supply
43429 | NC 2024 |  | Region II | Isabela | 103145 | Cabagan Science Elementary School | CABAGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4971501.13 | Completed | 1 | 2025-01-18 | 2025-01-18 | P00875246LZ-CW1 | 24BE0086 | 2024-04-11 | 2024-04-18 | 2024-04-30 | 2024-05-27 | 2024-05-06 | EGB Construction Corporation
43430 | NC 2024 |  | Region II | Isabela | 103148 | Casibarag Elementary School | CABAGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969206.6 | Completed | 1 | 2024-11-19 | 2024-10-25 | P00875249LZ-CW1 | 24BE0083 | 2024-04-11 | 2024-04-18 | 2024-04-30 | 2024-05-27 | 2024-05-06 | Dragon Twelve Builders and Construction Supply
43431 | NC 2024 |  | Region II | Isabela | 103157 | Ngarag Primary School | CABAGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969826.5 | Completed | 1 | 2024-11-19 | 2024-10-25 | P00875247LZ-CW1 | 24BE0085 | 2024-04-11 | 2024-04-18 | 2024-04-30 | 2024-05-27 | 2024-05-06 | Dragon Twelve Builders and Construction Supply
43432 | NC 2024 |  | Region II | Isabela | 103160 | San Bernardo Elementary School | CABAGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969660.6 | Completed | 1 | 2024-11-19 | 2024-10-25 | P00875248LZ-CW1 | 24BE0084 | 2024-04-11 | 2024-04-18 | 2024-04-30 | 2024-05-27 | 2024-05-06 | Dragon Twelve Builders and Construction Supply
43433 | NC 2024 |  | Region II | Isabela | 103809 | Simanu Norte Elementary School | SAN PABLO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969642.1 | Completed | 1 | 2024-11-19 | 2024-10-21 | P00875199LZ-CW1 | 24BE0082 | 2024-04-11 | 2024-04-18 | 2024-04-30 | 2024-05-27 | 2024-05-06 | Dragon Twelve Builders and Construction Supply
43434 | NC 2024 |  | Region II | Isabela | 501307 | Biga Integrated School | SANTO TOMAS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4971500.14 | Completed | 1 | 2024-12-14 | 2024-12-14 | P00875200LZ-C W1 | 24BE0071 | 2024-02-04 | 2024-11-04 | 2024-04-24 | 2024-09-05 | 2024-05-22 | EGB Construction Corporation
43435 | NC 2024 |  | Region II | Isabela | 103103 | Calaocan Elementary School | BENITO SOLIVEN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 | 2024-03-10 | 2024-10-16 |  | 24BG0157 | 2024-04-30 | 2024-09-05 | 2024-05-30 | 2024-06-21 | 2024-04-07 | GR8- Builders Construction
43436 | NC 2024 |  | Region II | Isabela | 500732 | New Magsaysay Integrated School | BENITO SOLIVEN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 | 2024-03-10 | 2024-04-11 |  | 24BG0156 | 2024-04-30 | 2024-09-05 | 2024-05-30 | 2024-06-21 | 2024-04-07 | CAMBERWELL CONSTRUCTION AND SUPPLIES
43437 | NC 2024 |  | Region II | Isabela | 103117 | San Carlos Elementary School | BENITO SOLIVEN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 | 2024-08-21 | 2024-08-23 |  | 24BG0133 | 2024-03-26 | 2024-03-04 | 2024-02-05 | 2024-05-15 | 2024-05-24 | CAMBERWELL CONSTRUCTION AND SUPPLIES
43438 | NC 2024 |  | Region II | Isabela | 103559 | San Isidro Elementary School | PALANAN |  | 1 | 3 | 1STY3CL | BATCH 1 | 9814969.18 |  | 9790431.76 | Ongoing | 0.1 | 2025-05-26 |  |  | 24BG0211 | 2024-09-24 |  | 2024-01-10 | 2024-10-22 | 2024-06-11 | CAMBERWELL CONSTRUCTION AND SUPPLIES | DIFFICULTY IN HAULING OF MATERIALS
43439 | NC 2024 |  | Region II | Isabela | 103751 | Cataguing Elementary School | SAN MARIANO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 | 2024-08-10 | 2024-05-11 |  | 24BG0159 | 2024-04-30 | 2024-09-05 | 2024-06-06 | 2024-06-25 | 2024-09-07 | CAMBERWELL CONSTRUCTION AND SUPPLIES
43440 | NC 2024 |  | Region II | Isabela | 500086 | Dicamay Integrated School | SAN MARIANO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 | 2024-08-27 | 2024-01-09 |  | 24BG0135 | 2024-03-26 | 2024-03-04 | 2024-02-05 | 2024-05-15 | 2024-05-30 | AGE CONSTRUCTION
43441 | NC 2024 |  | Region II | Isabela | 136938 | Luzcon Elementary School | SAN MARIANO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 | 2024-03-10 | 2024-08-10 |  | 24BG0158 | 2024-04-30 | 2024-09-05 | 2024-05-30 | 2024-06-21 | 2024-04-07 | CAMBERWELL CONSTRUCTION AND SUPPLIES
43442 | NC 2024 |  | Region II | Isabela | 500501 | San Isidro Integrated School | SAN MARIANO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 | 2024-08-27 | 2024-01-09 |  | 24BG0134 | 2024-03-26 | 2024-03-04 | 2024-02-05 | 2024-05-15 | 2024-05-30 | AGE CONSTRUCTION
43443 | NC 2024 |  | Region II | Isabela | 103766 | San Pedro Elementary School | SAN MARIANO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 | 2024-08-21 | 2024-08-23 |  | 24BG0145 | 2024-09-04 | 2024-04-18 | 2024-02-05 | 2024-05-15 | 2024-05-24 | CAMBERWELL CONSTRUCTION AND SUPPLIES
43444 | NC 2024 |  | Region II | Isabela | 300500 | Alicia National High School | ALICIA |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  | 9975000 | Ongoing | 0.9 | 2024-10-30 |  |  | 24BG0164 | 2024-11-05 | 2024-05-17 | 2024-05-30 | 2024-06-21 | 2024-04-07 | JWU CONSTRUCTION AND SUPPLY
43445 | NC 2024 |  | Region II | Isabela | 102988 | Alicia North Central School | ALICIA |  | 1 | 3 | 1STY3CL | BATCH 1 | 8639187.23 |  | 8617589.26 | Completed | 1 | 2024-10-17 | 2024-11-21 |  | 24BG0166 | 2024-11-05 | 2024-05-17 | 2024-06-06 | 2024-06-25 | 2024-09-07 | THREE V CONSTRUCTION
43446 | NC 2024 |  | Region II | Isabela | 103054 | Bunnay Elementary School | ANGADANAN |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  | 9975000 | Completed | 1 | 2024-12-09 | 2024-11-17 |  | 24BG0144 | 2024-09-04 | 2024-04-18 | 2024-02-05 | 2024-05-15 | 2024-05-17 | BDA, JR. CONSTRUCTION
43447 | NC 2024 |  | Region II | Isabela | 300571 | Ramon National High School | RAMON |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  | 9975000 | Completed | 1 | 2024-09-25 | 2024-06-11 |  | 24BG0143 | 2024-09-04 | 2024-04-18 | 2024-02-05 | 2024-05-15 | 2024-05-30 | CHU SAN CONSTRUCTION AND SUPPLY
43448 | NC 2024 |  | Region II | Isabela | 300581 | Salinungan National High School | SAN MATEO |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  | 9975000 | Completed | 1 | 2024-10-12 | 2024-12-16 |  | 24BG0209 | 2024-06-25 | 2024-04-07 | 2024-07-18 | 2024-07-30 | 2024-08-14 | JWU CONSTRUCTION AND SUPPLY
43449 | NC 2024 |  | Region II | Isabela | 306143 | Cordon National High School | CORDON |  | 1 | 2 | 1STY2CL WITH TOILET ATTACHED | GAA 17B | 5000000 |  | 4987500 | Completed | 1 | 2024-10-18 | 2024-10-15 | P00875239LZ-CW1 | 24BH0244 | 2024-04-23 | 2024-04-22 | 2024-05-14 | 2024-05-24 | 2024-06-13 | R AN CONSTRUCTION AND CONSTRUCTION SUPPLY
43450 | NC 2024 |  | Region II | Isabela | 501316 | Taliktik Integrated School | CORDON |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9975000 | Ongoing | 0.95 |  |  | P00875242LZ-CW1 | 24BH0336 | 2024-08-07 | 2024-06-08 | 2024-08-27 | 2024-09-09 | 2024-09-25 | VBM CONSTRUCTION CORP.
43451 | NC 2024 |  | Region II | Isabela | 501309 | Ayod Integrated School | DINAPIGUE |  | 1 | 2 | 1STY2CL WITH TOILET ATTACHED | GAA 17B | 5000000 |  | 4987500 | Completed | 1 | 2024-10-18 | 2024-10-17 | P00875235LZ-CW1 | 24BH0246 | 2024-04-23 | 2024-04-22 | 2024-05-14 | 2024-05-24 | 2024-06-13 | MONTE CARLO CONSTRUCTION CORP.
43452 | NC 2024 |  | Region II | Isabela | 501310 | Dibulo Integrated School | DINAPIGUE |  | 1 | 2 | 1STY2CL WITH TOILET ATTACHED | GAA 17B | 5000000 |  | 4987500 | Completed | 1 | 2024-10-18 | 2024-10-17 | P00875234LZ-CW1 | 24BH0245 | 2024-04-23 | 2024-04-22 | 2024-05-14 | 2024-05-24 | 2024-06-13 | DIVINE ROSA MYSTICA CONSTRUCTION INC.
43453 | NC 2024 |  | Region II | Isabela | 103465 | Disimpit Elementary School | JONES |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 | 2024-10-18 | 2024-10-15 | P00875244LZ-CW1 | 24BH0248 | 2024-04-23 | 2024-04-22 | 2024-05-14 | 2024-05-24 | 2024-06-13 | EXTREME BUILDERS
43454 | NC 2024 |  | Region II | Isabela | 103469 | Jones West Central School Campus 1 | JONES |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9975000 | Completed | 1 | 2025-02-21 | 2025-02-21 | P00875245LZ-CW1 | 24BH0337 | 2024-06-27 | 2024-06-08 | 2024-08-27 | 2024-09-09 | 2024-09-27 | WBS CONSTRUCTION AND CONSTRUCTION SUPPLY
43455 | NC 2024 |  | Region II | Isabela | 103470 | Jones West Central School-C2 | JONES |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 | 2025-05-01 | 2024-11-13 | P00875243LZ-CW1 | 24BH0325 | 2024-06-27 | 2024-06-26 | 2024-07-16 | 2024-12-08 | 2024-08-30 | JMD-68 BUILDERS
43456 | NC 2024 |  | Region II | Isabela | 103447 | JT Sebastian Primary School | JONES |  | 1 | 2 | 1STY2CL WITH TOILET ATTACHED | GAA 17B | 5000000 |  | 4987500 | Ongoing | 0.97 |  |  | P00875233LZ-CW1 | 24BH0249 | 2024-04-23 | 2024-04-22 | 2024-05-14 | 2024-05-29 | 2024-06-17 | MONTE CARLO CONSTRUCTION CORP.
43457 | NC 2024 |  | Region II | Isabela | 501315 | San Sebastian Integrated School | JONES |  | 1 | 2 | 1STY2CL WITH TOILET ATTACHED | GAA 17B | 5000000 |  | 4987500 | Ongoing | 0.8 |  |  | P00875232LZ-CW1 | 24BH0250 | 2024-04-23 | 2024-04-22 | 2024-05-14 | 2024-05-24 | 2024-06-13 | MONTE CARLO CONSTRUCTION CORP.
43458 | NC 2024 |  | Region II | Isabela | 103669 | Sinaoangan Sur Elementary School | SAN AGUSTIN |  | 1 | 2 | 1STY2CL WITH TOILET ATTACHED | GAA 17B | 5000000 |  | 4987500 | Ongoing | 0.9 |  |  | P00875236LZ-CW1 | 24BH0247 | 2024-04-23 | 2024-04-22 | 2024-05-14 | 2024-05-24 | 2024-06-19 | VBM CONSTRUCTION CORP.
43459 | NC 2024 |  | Region II | Isabela | 103080 | Camarunggayan Elementary School | AURORA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 |  | 2024-06-10 |  | 24BF0084 | [5 empty] | RSKM Construction Services | COLLECTIONG DATA FROM DPWH
43460 | NC 2024 |  | Region II | Isabela | 103129 | Catabban Elementary School | BURGOS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 |  |  |  | 24BF0085 | [5 empty] | BDA Jr. Construction | COLLECTIONG DATA FROM DPWH
43461 | NC 2024 |  | Region II | Isabela | 103484 | Bustamante Elementary School | LUNA |  | 1 | 2 | 1STY2CL WITH TOILET ATTACHED | GAA 17B | 6150000 |  | 6134625 | Completed | 1 |  | 2025-10-03 |  | 24BF0109 | [5 empty] | Chu San Construction & Supply | COLLECTIONG DATA FROM DPWH
43462 | NC 2024 |  | Region II | Isabela | 103486 | Lalog Elementary School | LUNA |  | 1 | 2 | 1STY2CL WITH TOILET ATTACHED | GAA 17B | 6150000 |  | 6134625 | Completed | 1 |  | 2025-10-03 |  | 24BF0110 | [5 empty] | Chu San Construction & Supply | COLLECTIONG DATA FROM DPWH
43463 | NC 2024 |  | Region II | Isabela | 103487 | Luna Central School | LUNA |  | 1 | 4 | 1STY4CL WITH TOILET ATTACHED | GAA 17B | 12350000 |  | 12319125 | Completed | 1 |  | 2025-04-28 |  | 24BF0119 | [5 empty] | Chu San Construction & Supply | COLLECTIONG DATA FROM DPWH
43464 | NC 2024 |  | Region II | Isabela | 103490 | Pulay-Union Kalinga Elementary School | LUNA |  | 1 | 2 | 1STY2CL WITH TOILET ATTACHED | GAA 17B | 6150000 |  | 6134625 | Completed | 1 |  | 2025-11-02 |  | 24BF0108 | [5 empty] | Chu San Construction & Supply | COLLECTIONG DATA FROM DPWH
43465 | NC 2024 |  | Region II | Isabela | 103491 | Puroc-Concepcion ES | LUNA |  | 1 | 3 | 1STY3CL WITH TOILET ATTACHED | GAA 17B | 9200000 |  | 9177000 | Completed | 1 |  | 2025-04-28 |  | 24BF0120 | [5 empty] | Chu San Construction & Supply | COLLECTIONG DATA FROM DPWH
43466 | NC 2024 |  | Region II | Isabela | 103501 | Rang-ayan Elementary School | MALLIG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 |  |  |  | 24BF0089 | [5 empty] | RSKM Construction Services | COLLECTIONG DATA FROM DPWH
43467 | NC 2024 |  | Region II | Isabela | 306112 | Barucboc National High School | QUEZON |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 |  |  |  | 24BF0083 | [5 empty] | CSD Engineering & Construction | COLLECTIONG DATA FROM DPWH
43468 | NC 2024 |  | Region II | Isabela | 300570 | Rizal Comprehensive National High School | QUIRINO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 |  | 2024-11-10 |  | 24BF0090 | [5 empty] | BDA Jr. Construction | COLLECTIONG DATA FROM DPWH
43469 | NC 2024 |  | Region II | Isabela | 103632 | Lanting Elementary School | ROXAS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 |  | 2024-06-12 |  | 24BF0087 | [5 empty] | MNIS Construction | COLLECTIONG DATA FROM DPWH
43470 | NC 2024 |  | Region II | Isabela | 103635 | Matusalem Elementary School | ROXAS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 |  | 2024-11-19 |  | 24BF0088 | [5 empty] | VRDJ Construction | COLLECTIONG DATA FROM DPWH
43471 | NC 2024 |  | Region II | Isabela | 300512 | Callang National High School | SAN MANUEL |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 |  | 2024-12-26 |  | 24BF0086 | [5 empty] | R.S.K.M. Construction Services | COLLECTIONG DATA FROM DPWH
43472 | NC 2024 |  | Region II | Isabela | 103282 | Annafunan Elementary School | ECHAGUE |  | 1 | 4 | 1STY4CL WITH TOILET ATTACHED | GAA 17B | 5000000 |  | 4987500 | Ongoing | 0.85 |  |  | P00875223LZ-CW1 | 24BH0332 | 2024-07-31 | 2024-07-30 | 2024-08-20 | 2024-09-30 | 2024-10-18 | JWU CONSTRUCTION AND SUPPLY
43473 | NC 2024 |  | Region II | Isabela | 306120 | Imelda R. Marcos HS - Mabbayad Annex | ECHAGUE |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9975000 | Ongoing | 0.75 |  |  | P00875224LZ-CW1 | 24BH0335 | 2024-07-08 | 2024-06-08 | 2024-08-27 | 2024-09-30 | 2024-10-18 | AYLAN CONSTRUCTION AND TRADING
43474 | NC 2024 |  | Region II | Isabela | 103297 | Pag-asa Elementary School | ECHAGUE |  | 1 | 3 | 1STY3CL WITH TOILET ATTACHED | GAA 17B | 5000000 |  | 4987500 | Ongoing | 0.8 |  |  | P00875225LZ-CW1 | 24BH0333 | 2024-07-31 | 2024-07-30 | 2024-08-20 | 2024-09-30 | 2024-10-18 | AYLAN CONSTRUCTION AND TRADING
43475 | NC 2024 |  | Region II | Isabela | 103302 | Sta. Cruz Elementary School | Echague |  | 1 | 5 | 1STY5CL w/ Toilet Attached | BATCH 1 | 11595000 |  | 11566012.5 | Ongoing | 0.9 |  |  | P00875820LZ-CW1 | 24BH0316 | 2024-06-19 | 2024-06-18 | 2024-09-07 | 2024-07-08 | 2024-08-26 | AYLAN CONSTRUCTION AND TRADING
43476 | NC 2024 |  | Region II | Isabela | 500015 | Dietban Integrated School | SAN GUILLERMO |  | 1 | 3 | 1STY3CL WITH TOILET ATTACHED | GAA 17B | 5000000 |  | 4987500 | Ongoing | 0.8 |  |  | P00875226LZ-CW1 | 24BH0334 | 2024-07-31 | 2024-07-30 | 2024-08-20 | 2024-09-30 | 2024-10-18 | DIVINE ROSA MYSTICA CONSTRUCTION INC.
43477 | NC 2024 |  | Region II | Nueva Vizcaya | 103978 | San Fernando ES | BAMBANG |  | 1 |  | Construction of School Building | GAA 17B | 10000000 |  | 9845617.48 | Ongoing | 0.79 | 2025-08-11 |  | P00875251LZ | 24BI0119 | 2024-07-17 | 2024-07-25 | 2024-08-08 | 2024-12-11 | 2024-12-19 | TAMRHEY CONSTRUCTION | -
43478 | NC 2024 |  | Region II | Nueva Vizcaya |  | Pinayag ES | KAYAPA |  | 1 |  | Construction of School Building | GAA 17B | 10000000 |  | - | Reverted | 0 |  |  | - | - | [5 empty] | - | Reverted due to disapproved modification of school name of Macdu Elementary School, Kayapa, Nueva Vizcaya
43479 | NC 2024 |  | Region II | Nueva Vizcaya | 304675 | Pinayag National High School | KAYAPA |  | 1 |  | Construction of School Building | GAA 17B | 10000000 |  | 9830459.96 | Completed | 1 | 2024-08-05 | 2024-08-05 |  | 24BJ0075 | 2024-03-07 | 2024-03-14 | 2024-03-27 | 2024-04-03 | 2024-04-08 | PRIME BUILT CONSTRUCTION & SUPPLY | -
43480 | NC 2024 |  | Region II | Nueva Vizcaya | 300649 | Santa Fe National High School | SANTA FE |  | 1 | 8 | 2STY8CL | GAA 17B | 20000000 |  | 19661754.66 | Ongoing | 0.92 | 2024-02-07 |  | P00875250LZ | 24BJ0076 | 2024-03-07 | 2024-03-14 | 2024-03-27 | 2024-04-03 | 2024-04-08 | PRIME BUILT CONSTRUCTION & SUPPLY | -
43481 | NC 2024 |  | Region II | Nueva Vizcaya | 104209 | Sta. Fe CS | SANTA FE |  | 1 |  | Construction of School Building | GAA 17B | 10000000 |  | 9830630.44 | Ongoing | 0.98 | 2024-10-21 |  | P00875254LZ | 24BJ0074 | 2024-03-07 | 2024-03-14 | 2024-03-27 | 2024-04-03 | 2024-04-08 | PRIME BUILT CONSTRUCTION & SUPPLY | -
43482 | NC 2024 |  | Region II | Quirino | 501565 | Dagupan Integrated School | AGLIPAY |  | 1 | 3 | 1STY3CL | GAA 17B | 7650000 |  | 7383336.26 | Completed | 1 | 2024-11-22 | 2024-11-12 | P00875259LZ-CW1 | 24BK0106 | 2024-07-05 | 2024-05-17 | 2024-05-31 | 2024-11-06 | 2024-06-20 | JMD-68 Builders
43483 | NC 2024 |  | Region II | Quirino | 104250 | Villa Santiago ES | AGLIPAY |  | 1 | 3 | 1STY3CL | BATCH 1 | 6697698.87 |  | 6526027.86 | Completed | 1 | 2024-11-16 | 2025-04-14 | P00875821LZ-CW1 | 24BK0109 | 2024-07-05 | 2024-05-17 | 2024-05-31 | 2024-11-06 | 2024-06-20 | JURIS Const. & Builders
43484 | NC 2024 |  | Region II | Quirino | 104264 | Mangandingay ES | CABARROGUIS (Capital) |  | 1 | 3 | 1STY3CL | GAA 17B | 7610000 |  | 7340266.23 | Completed | 1 | 2024-11-22 | 2024-12-12 | P00875257LZ-CW1 | 24BK0107 | 2024-07-05 | 2024-05-17 | 2024-05-31 | 2024-11-06 | 2024-06-20 | JURIS Const. & Builders
43485 | NC 2024 |  | Region II | Quirino | 104275 | Zamora ES | CABARROGUIS (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5855000 |  | 5647684.78 | Completed | 1 | 2024-10-14 | 2025-02-01 | P00875258LZ-CW1 | 24BK0096 | 2024-04-23 | 2024-02-05 | 2024-05-16 | 2024-05-27 | 2024-04-06 | JURIS Const. & Builders
43486 | NC 2024 |  | Region II | Quirino | 501561 | Der-an Integrated School | DIFFUN |  | 1 | 2 | 1STY2CL | GAA 17B | 5335000 |  | 5143318.1 | Completed | 1 | 2024-09-30 | 2024-10-30 | P00875255LZ-CW1 | 24BK0076 | 2024-04-04 | 2024-04-15 | 2024-04-29 | 2024-09-05 | 2024-05-21 | A-CZAR18 Construction
43487 | NC 2024 |  | Region II | Quirino | 104306 | Liwayway ES | DIFFUN |  | 1 | 2 | 1STY2CL | GAA 17B | 5300000 |  | 5112006.91 | Completed | 1 | 2024-09-30 | 2024-10-30 | P00875256LZ-CW1 | 24BK0077 | 2024-04-04 | 2024-04-15 | 2024-04-29 | 2024-09-05 | 2024-05-21 | Jhuers Construction
43488 | NC 2024 |  | Region II | Quirino | 136924 | Pulang Lupa Elementary School | NAGTIPUNAN |  | 1 | 3 | 1STY3CL | GAA 17B | 8250000 |  | 7954637.77 | Not Yet Started | 0 | 2024-11-22 |  | P00875260LZ-CW1 | 24BK0108 | 2024-07-05 | 2024-05-17 | 2024-05-31 | 2024-11-06 | 2024-06-20 | NC Construction | Project is suspended. Awaiting for the PAMB Clearance from DENR
43489 | NC 2024 |  | Region II | Santiago City | 103836 | Bannawag ES | CITY OF SANTIAGO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
43490 | NC 2024 |  | Region II | Santiago City | 501147 | San Jose Integrated School | CITY OF SANTIAGO |  | 1 | 2 | 1STY2CL WITH TOILET ATTACHED | GAA 17B | 5000000 |  |  | Ongoing | 0.95
43491 | NC 2024 |  | Region II | Santiago City | 500938 | Sinili Integrated School | CITY OF SANTIAGO |  | 1 | 2 | 1STY2CL WITH TOILET ATTACHED | GAA 17B | 5000000 |  |  | Completed | 1
43492 | NC 2024 |  | Region II | Santiago City | 103832 | Sinsayon ES | CITY OF SANTIAGO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
43493 | NC 2024 |  | Region II | Tuguegarao City | 300669 | Cataggaman National High School | TUGUEGARAO CITY(Capital) |  | 1 | 5 | Construction of School Building | BATCH 1 | 13395397.73 |  | 13297283.38 | Ongoing | 0.96 | 2025-06-05 |  | P00855203LZ-CW1 | 24BD0193 | 2024-06-25 | 2024-07-03 | 2024-07-15 | 2024-08-30 | 2024-09-06 | Northwide Jaar Construction Corp. | on going

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.