## Sheet1
INDEX (DO NOT MODIFY) | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LEG DISTRICT | NO. OF SITES | SCOPE OF WORK | TOTAL ALLOCATION | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | TARGET COMPLETION DATE | ACTUAL DATE OF COMPLETION | PROJECT ID | CONTRACT ID | ISSUANCE OF INVITATION TO BID | PRE-SUBMISSION CONFERENCE | BID OPENING | ISSUANCE OF RESOLUTION TO AWARD | ISSUANCE OF NOTICE TO PROCEED | NAME OF CONTRACTOR | OTHER REMARKS | Status as of July 11, 2025
3 | Region III | Aurora | 300690 | Lual NHS | CASIGURAN | Lone | 1 | PROPOSED TWO (2) - STOREY ALTERNATIVE LEARNING SYSTEM (ALS) BUILDING (22.50m x 9.50m) - with Roof Deck( TO be elevated by 1.0m) | 12446387.1 | 10458975.45 | ongoing | 0.7 | June 21, 2025 |  | 2024-04-181 | SGOD-INFRA-32 | July 1, 2024 | July 8, 2024 | July 22, 2024 | August 1, 2024 | August 17, 2024 | MACCO CONSTRUCTION | Request to utilized savings is up to now no response from CO

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%